## Sheet 1
Name | Work Status | Work Type | Home Domain/Portfolio | Work ID # | Associated Initiative Seq ID | Associated Initiative | Execution Type | AP Top Lane | Agility # | Agility URL | T-Shirt Size | Agility Actual/Planned Start | Agility Actual/Planned Finish | Agility % Complete (Size) | Agility Child Card Total Size | Agility Child Complete Card Size | Agility Child In Progress Card Size | Agility Child Not Started Card Size | Blocked Flag | Schedule Start | Schedule Finish | Agility Actual Start | Agility Actual Finish
Biz w/ Tech Epic: CLH | Not Started | Biz w/ Tech Epic | Global Air Hubs & Ramps Domain | 0113389 | 8810 | OneView | Biz w/ Tech Epic
Biz w/ Tech Epic: Operation View | Not Started | Biz w/ Tech Epic | Global Air Hubs & Ramps Domain | 0113390 | 8810 | OneView | Biz w/ Tech Epic
Biz w/ Tech Epic: Merchant Reviews | Not Started | Biz w/ Tech Epic | Global Capabilities Strategy Domain | 0110811 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: ERMA Overlapping Sorts Logic Update | Approved | Biz w/ Tech Epic | Global Capabilities Strategy Domain | 0116674 | 9066 | PLANS - US Air Planning Labor & Rostering | Biz w/ Tech Epic |  |  |  | 2: S | [8 empty] | 2026-05-25 | 2027-05-24
Biz w/ Tech Epic: Fuel Price Accuracy Tool - DO NOT USE | Cancelled | Biz w/ Tech Epic | Air Ops Domain | 0103384 |  |  | Biz w/ Tech Epic |  |  |  | 1: XS
Biz w/ Tech Epic: E-402444 | Cancelled | Biz w/ Tech Epic | Air Ops Domain | 0104925 |  |  | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: Modernize Audit Logging Phase 1 | Not Started | Biz w/ Tech Epic | Air Ops Domain | 0108956 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Modernize Irregularity Reporting | Approved | Biz w/ Tech Epic | Air Ops Domain | 0108973 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  |  |  | 1: XS | [8 empty] | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Autoslip Enhancement – AMS ULD Movement Capability | Not Started | Biz w/ Tech Epic | Air Ops Domain | 0117657 | 109270 | Global-Autoslip Enhancements:AMS Movements | Biz w/ Tech Epic |  |  |  | 3: M
Biz w/ Tech Epic: AirPath+ Shipment Assignment Phase 2 enhancement | Cancelled | Biz w/ Tech Epic | APAC Domain | 0112503 | 7085 | AirPath+ | Biz w/ Tech Epic
Biz w/ Tech Epic: VN 2-4 tier city penetration (Da Nang) | Not Started | Biz w/ Tech Epic | APAC Domain | 0115990 |  |  | Biz w/ Tech Epic
Local Enhancement Epic: Sales Model to penetrate Tier 2-4 Cities | Not Started | Local Enhancement Epic | APAC Domain | 0116004 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: APAC Ancillary Service Fees | Not Started | Biz w/ Tech Epic | APAC Domain | 0117892 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Customer Agreement Experience | Approved | Biz w/ Tech Epic | Commercial Domain | 0108876 | 109817 | Customer Agreement Experience | Biz w/ Tech Epic |  |  |  | 4: L | [8 empty] | 2026-03-02 | 2028-02-29
Biz w/ Tech Epic: Customer Agreement Experience | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0108877 |  |  | Biz w/ Tech Epic |  |  |  | 3: M
Biz w/ Tech Epic: Semi-automated invoice accounts LAC/MEISA/APAC | Not Started | Biz w/ Tech Epic | Commercial Domain | 0116915 | 105766 | Semi-automated Account Creation on Invoice on .com | Biz w/ Tech Epic |  |  |  | 3: M
Local Enhancement Epic: Collection Letter Archive - eCIS update | Cancelled | Local Enhancement Epic | Commercial Domain | 0110884 |  |  | Local Enhancement Epic
Local Enhancement Epic: US Inbound Processing Fee - Rate Increase | Cancelled | Local Enhancement Epic | Commercial Domain | 0111355 |  |  | Local Enhancement Epic
Local Enhancement Epic: Update XAPI emails | Cancelled | Local Enhancement Epic | Commercial Domain | 0111421 |  |  | Local Enhancement Epic
Local Enhancement Epic: COM-SandCDE-CRM PI04 S3 Enhancement | Not Started | Local Enhancement Epic | Commercial Domain | 0116911 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: Enterprise SLAs (Availability 99.9% target) and pe | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0112303 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: COM- EPIC2 SpS US Billing,Pynts & Sales Comp Auton | On Hold | Biz w/ Tech Epic | Commercial Domain | 0112472 | 7160 | Special Services - US | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: Test CI | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0112843 |  |  | Biz w/ Tech Epic
Lifecycle Management Epic: COM-IA-DART-FY26_PI5_Marketing Tagging_LCM | Cancelled | Lifecycle Management Epic | Commercial Domain | 0116908 |  |  | Lifecycle Management Epic
Local Enhancement Epic: Global Payment Dashboard | Cancelled | Local Enhancement Epic | Commercial Domain | 0113991 |  |  | Local Enhancement Epic
Local Enhancement Epic: Global Payment Dashboard | Not Started | Local Enhancement Epic | Commercial Domain | 0113992 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: Epic 1a | Not Started | Biz w/ Tech Epic | Commercial Domain | 0114113 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: Epic 1b Dedicated Vehicle | Not Started | Biz w/ Tech Epic | Commercial Domain | 0114115 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: Epic 3 Special Express | Not Started | Biz w/ Tech Epic | Commercial Domain | 0114116 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Epic 4 NFO | Not Started | Biz w/ Tech Epic | Commercial Domain | 0114117 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Modernize FAPI | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0114140 |  |  | Biz w/ Tech Epic |  |  |  | 5: XL
Biz w/ Tech Epic: Epic 1 - SAF-T | Not Started | Biz w/ Tech Epic | Commercial Domain | 0114316 | 109509 | E-VAT & Standard Audit File for Tax (SAF-T) | Biz w/ Tech Epic |  |  |  | 3: M
Biz w/ Tech Epic: Epic 2 - E-VAT | Not Started | Biz w/ Tech Epic | Commercial Domain | 0114317 | 109509 | E-VAT & Standard Audit File for Tax (SAF-T) | Biz w/ Tech Epic |  |  |  | 3: M
Biz w/ Tech Epic: SAF-T | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0114420 |  |  | Biz w/ Tech Epic
Local Enhancement Epic: Paper Commercial Invoice Surcharge | Cancelled | Local Enhancement Epic | Commercial Domain | 0115092 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: EPIC 1a Dedicated Vehicle | Not Started | Biz w/ Tech Epic | Commercial Domain | 0115517 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: EPIC 1b Dedicated Vehicle with Clearance | Not Started | Biz w/ Tech Epic | Commercial Domain | 0115518 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Epic 2 Special Express | Not Started | Biz w/ Tech Epic | Commercial Domain | 0115519 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: EPIC 3 NFO | Not Started | Biz w/ Tech Epic | Commercial Domain | 0115520 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Commercial Impact | Not Started | Biz w/ Tech Epic | Commercial Domain | 0115591 | 103870 | Retire FGE Services to USPS Only Locations | Biz w/ Tech Epic |  |  |  | 3: M
Biz w/ Tech Epic: Commercial EPIC | Not Started | Biz w/ Tech Epic | Commercial Domain | 0115599 |  |  | Biz w/ Tech Epic |  |  |  | 3: M
Local Enhancement Epic: Qualtrics Agentic AI | Not Started | Local Enhancement Epic | Commercial Domain | 0116522 |  |  | Local Enhancement Epic
Local Enhancement Epic: Display Confirmation# on Express MPU | Cancelled | Local Enhancement Epic | Commercial Domain | 0116768 |  |  | Local Enhancement Epic
Local Enhancement Epic: COM-IA-DART-FY26_PI2_Marketing Tagging_LCM | Cancelled | Local Enhancement Epic | Commercial Domain | 0116882 |  |  | Local Enhancement Epic
Lifecycle Management Epic: Benelux Caller Improvement | Not Started | Lifecycle Management Epic | Commercial Domain | 0116929 |  |  | Lifecycle Management Epic
Biz w/ Tech Epic: PIV Differentiated Premium tier feature developme | Approved | Biz w/ Tech Epic | Commercial Domain | 0116925 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic |  | E-558915 | E-558915 | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Enterprise SLAs (Availability 99.9% target) and p | Approved | Biz w/ Tech Epic | Commercial Domain | 0116926 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic |  | E-558917 | E-558917 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: AIV – New APIs to enable advanced visibility | Approved | Biz w/ Tech Epic | Commercial Domain | 0116922 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic |  | E-558916 | E-558916 | 5: XL |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: BIV - New Webhook and changes to existing API | Approved | Biz w/ Tech Epic | Commercial Domain | 0116923 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic | Build | E-565399 | E-565399 | 4: L | 2026-01-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-05-01 | 2027-11-11 | 2026-01-23
Biz w/ Tech Epic: Integration experience enhancements | Approved | Biz w/ Tech Epic | Commercial Domain | 0116924 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic |  | E-558913 | E-558913 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: AIV Customer Onboarding, enablement | Approved | Biz w/ Tech Epic | Commercial Domain | 0116927 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic |  | E-558914 | E-558914 | 3: M |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: IVP Global Roll out, Billing linkage | Approved | Biz w/ Tech Epic | Commercial Domain | 0116921 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-565682 | E-565682 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: WAVE FDW initiative #50339 | Not Started | Biz w/ Tech Epic | Commercial Domain | 0116937 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: WAVE FDW initiative (#50339) | Not Started | Biz w/ Tech Epic | Commercial Domain | 0116938 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: WAVE FEW initiative #50339 | Not Started | Biz w/ Tech Epic | Commercial Domain | 0116939 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: APAC Doc Upload PI02 Enhancements | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0117114 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Order Create | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0117123 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Ops under Payables | Cancelled | Biz w/ Tech Epic | Commercial Domain | 0117132 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Local Enhancement Epic: Rebrand FGE Invoice to Replace SmartPost Name | Cancelled | Local Enhancement Epic | Commercial Domain | 0117165 |  |  | Local Enhancement Epic
Local Enhancement Epic: Global SpotPricing-Surcharge Enhan./Error on Inv. | Cancelled | Local Enhancement Epic | Commercial Domain | 0117166 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - International Shipper | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117544 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - Digital Products Upsell | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117545 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - RTCDP to Target: High-Value | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117546 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - Foundational Work (Adobe) | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117547 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - Email Warming | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117548 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - Operating Model & Governance | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117549 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - Migration of Existing Journey | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117550 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Biz w/ Tech Epic: COM - S&CDE - CDE - Retirement of SFMC and MCP | Not Started | Biz w/ Tech Epic | Commercial Domain | 0117551 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic
Lifecycle Management Epic: Onboarding IMADE from PCF to Fedex cloud platform | Not Started | Lifecycle Management Epic | Data and Tech Domain | 0109157 |  |  | Lifecycle Management Epic
Lifecycle Management Epic: Managed Services - Define Scope, Responsibilities, | Not Started | Lifecycle Management Epic | Data and Tech Domain | 0112082 |  |  | Lifecycle Management Epic
Biz w/ Tech Epic: Infosec: Deploy Zscaler Workflow Manager for DLP | Approved | Biz w/ Tech Epic | Data and Tech Domain | 0112087 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic |  |  |  | 3: M
Biz w/ Tech Epic: Pesonalized Discovery and Activation | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0112466 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Global Software Request/Tile Catalog | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113023 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: Bringg SaaS License Integration | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0110987 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SAM Software as a Subscription Integrations FY2026 | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113102 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: Address Validation Override in Customer Onboarding | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113179 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Address Validation Override in Customer Onboarding | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113180 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Address Validation Override in Customer Onboarding | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113186 | 93588 | Address validation override in customer onboarding | Biz w/ Tech Epic
Biz w/ Tech Epic: Address Validation Override in Customer Onboarding | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113187 | 93588 | Address validation override in customer onboarding | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: Address Validation Override in Customer Onboarding | Not Started | Biz w/ Tech Epic | Data and Tech Domain | 0113189 | 93588 | Address validation override in customer onboarding | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: Archer Migration to OnSpring | Cancelled | Biz w/ Tech Epic | Data and Tech Domain | 0116395 |  |  | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: Claro. Um bom título de Epic deve ser conciso e di | Cancelled | Biz w/ Tech Epic | SG&A Domain | 0113434 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: BridgeOps - Transition EBS TMS for Continuity | Cancelled | Biz w/ Tech Epic | SG&A Domain | 0113435 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: EU Real Estate directly updating EnCoRE | Not Started | Biz w/ Tech Epic | Europe Domain | 0103185 |  |  | Biz w/ Tech Epic |  |  |  | 4: L
Biz w/ Tech Epic: Digital Support Ticket - MVP | Approved | Biz w/ Tech Epic | Europe Domain | 0103259 | 9279 | WS8 - T4 – Online case creation (link with GS) | Biz w/ Tech Epic |  |  |  | 4: L | [8 empty] | 2025-06-20 | 2025-10-10
Biz w/ Tech Epic: EDM-FIT | Cancelled | Biz w/ Tech Epic | Europe Domain | 0103857 |  |  | Biz w/ Tech Epic
Local Enhancement Epic: SMLs bagging (origin station) Campaign | Cancelled | Local Enhancement Epic | Europe Domain | 0104823 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: Global P&D Ecosystem France Rollout | Not Started | Biz w/ Tech Epic | Europe Domain | 0105691 |  |  | Biz w/ Tech Epic
Local Enhancement Epic: Stratus Development to Remove T-status Lanes | Cancelled | Local Enhancement Epic | Europe Domain | 0106131 |  |  | Local Enhancement Epic
Lifecycle Management Epic: CE VVA Benelux Caller Improvements | Cancelled | Lifecycle Management Epic | Europe Domain | 0109038 |  |  | Lifecycle Management Epic
Biz w/ Tech Epic: Canceled:TNT Legacy Cluster Decommission and Mig | Cancelled | Biz w/ Tech Epic | Europe Domain | 0112111 |  |  | Biz w/ Tech Epic |  |  |  | 1: XS
Biz w/ Tech Epic: 1. Epic SCO_0 | Cancelled | Biz w/ Tech Epic | Europe Domain | 0114892 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: EUM: Commercial - Reporting (Turkey) | Cancelled | Biz w/ Tech Epic | Europe Domain | 0115721 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: EUM: Other (To Be Retained) | Cancelled | Biz w/ Tech Epic | Europe Domain | 0115722 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: EUM: EDW BAU | Cancelled | Biz w/ Tech Epic | Europe Domain | 0115723 |  |  | Biz w/ Tech Epic
Lifecycle Management Epic: EUM: UK Sameday | Not Started | Lifecycle Management Epic | Europe Domain | 0115755 |  |  | Lifecycle Management Epic | [12 empty] | 2025-10-01 | 2026-12-01
Local Enhancement Epic: PEDA Station Relocation | Not Started | Local Enhancement Epic | Europe Domain | 0116507 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: Global Invoice Presentment & Delivery -GIPD: Epic1 | Approved | Biz w/ Tech Epic | Europe Domain | 0116315 | 155418 | Global Invoice Presentment Delivery (GIPD) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2028-12-29 | 2028-12-29
Local Enhancement Epic: DG Nav - Courier ADR Points | Cancelled | Local Enhancement Epic | Europe Domain | 0116828 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: RO eTransport | Not Started | Biz w/ Tech Epic | Europe Domain | 0117209 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: RO eTransport data provision | Not Started | Biz w/ Tech Epic | Europe Domain | 0117294 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: RO eTransport data provisioning | Not Started | Biz w/ Tech Epic | Europe Domain | 0117295 | 90829 | RO eTransport compliance - Data requirement | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: Close the Loop - reinstatement | Cancelled | Biz w/ Tech Epic | Europe Domain | 0117446 |  |  | Biz w/ Tech Epic
Local Enhancement Epic: 6. Performance and Compliance Measurement | Not Started | Local Enhancement Epic | Freight Domain | 0106054 |  |  | Local Enhancement Epic
Local Enhancement Epic: OCR for export broker | Cancelled | Local Enhancement Epic | Global Clearance Domain | 0108062 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: GEMINI – METL Data/EDI Translation & Transportatio | Cancelled | Biz w/ Tech Epic | Global Clearance Domain | 0109071 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic |  |  |  | 5: XL
Biz w/ Tech Epic: EPIC FiT Phase 2.5 DocUpload | In Progress | Biz w/ Tech Epic | Global Clearance Domain | 0111717 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: ExpressClear - Touchless Clearance Global | Cancelled | Biz w/ Tech Epic | Global Clearance Domain | 0114235 | 90021 | US Broker Automation, FXL Brokerage | Biz w/ Tech Epic
Biz w/ Tech Epic: ExpressClear - Touchless Clearance Global | Cancelled | Biz w/ Tech Epic | Global Clearance Domain | 0114237 | 90021 | US Broker Automation, FXL Brokerage | Biz w/ Tech Epic
Biz w/ Tech Epic: Phase 1/iPFS | In Progress | Biz w/ Tech Epic | Global Clearance Domain | 0116963 | 98476 | ELVIS - e-commerce Low Value Inspection System | Biz w/ Tech Epic |  |  |  | 3: M | [8 empty] | 2026-02-02 | 2026-06-15
Biz w/ Tech Epic: Trade and Tariff Analysis Tool VB2 | Not Started | Biz w/ Tech Epic | Global Clearance Domain | 0117173 | 107528 | Trade and Tariff Impact Analysis Tool | Biz w/ Tech Epic |  |  |  | 3: M | [8 empty] | 2026-03-27 | 2026-09-30
Biz w/ Tech Epic: Expand Broker Support through AI | Approved | Biz w/ Tech Epic | Global Clearance Domain | 0117345 | 177373 | FedEx Butler | Biz w/ Tech Epic |  |  |  | 3: M | [8 empty] | 2026-07-13 | 2026-09-21
Local Enhancement Epic: Unified Butler UI for AI Components | Not Started | Local Enhancement Epic | Global Clearance Domain | 0117357 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: Unified Butler for AI components | Approved | Biz w/ Tech Epic | Global Clearance Domain | 0117358 | 177373 | FedEx Butler | Biz w/ Tech Epic |  |  |  | 3: M | [8 empty] | 2026-07-13 | 2026-09-21
Biz w/ Tech Epic: Alignment session with Clearance | Not Started | Biz w/ Tech Epic | MEISA Domain | 0106709 | 113169 | ZA Clearance process RPA automation | Biz w/ Tech Epic |  |  |  | 2: S | [8 empty] | 2026-01-05 | 2026-06-01
Local Enhancement Epic: CHIPATA STATION CLOSURE | Not Started | Local Enhancement Epic | MEISA Domain | 0111479 |  |  | Local Enhancement Epic
Local Enhancement Epic: FIC AI incubation - PPI | Not Started | Local Enhancement Epic | MEISA Domain | 0117805 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Couriers leveraging FXG fuel islands | Cancelled | Biz w/ Tech Epic | P&D Domain | 0103648 |  |  | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: NOP Delivery Forecast Epic 2 | Not Started | Biz w/ Tech Epic | P&D Domain | 0104057 | 6727 | NOP Delivery Forecast | Biz w/ Tech Epic |  |  |  | 2: S | [8 empty] | 2024-12-30 | 2025-02-28
Local Enhancement Epic: Support Daily Dock Chute/ENWPR Changes for HTM 1.0 | Not Started | Local Enhancement Epic | P&D Domain | 0116525 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: ALT VAN Scan in FORGE | Cancelled | Biz w/ Tech Epic | P&D Domain | 0116650 | 170574 | ALT VAN Scan in FORGE | Biz w/ Tech Epic
Biz w/ Tech Epic: FY26 H1 Network 2.0 | Not Started | Biz w/ Tech Epic | Surface Operations Domain | 0108221 | 9246 | [Enabler] USGO Station Projects & Build to Suits | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: FY26 H2 Network 2.0 | Not Started | Biz w/ Tech Epic | Surface Operations Domain | 0108222 | 9246 | [Enabler] USGO Station Projects & Build to Suits | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: FY27 H1 Network 2.0 | Not Started | Biz w/ Tech Epic | Surface Operations Domain | 0108223 | 9246 | [Enabler] USGO Station Projects & Build to Suits | Biz w/ Tech Epic |  |  |  | 2: S
Biz w/ Tech Epic: FY27 H2 Network 2.0 | Not Started | Biz w/ Tech Epic | Surface Operations Domain | 0108224 | 9246 | [Enabler] USGO Station Projects & Build to Suits | Biz w/ Tech Epic |  |  |  | 2: S
Local Enhancement Epic: Consume Ground Economy - GDPP EDD Predictions | Cancelled | Local Enhancement Epic | Surface Operations Domain | 0112235 |  |  | Local Enhancement Epic
Local Enhancement Epic: Consume Ground Economy - GDPP EDD predictions | Cancelled | Local Enhancement Epic | Surface Operations Domain | 0112236 |  |  | Local Enhancement Epic
Biz w/ Tech Epic: Consume FXG Economy GDPP predictions - BwT | Cancelled | Biz w/ Tech Epic | Surface Operations Domain | 0112851 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: Executive View | Not Started | Biz w/ Tech Epic | Tricolor Domain | 0113388 | 8810 | OneView | Biz w/ Tech Epic
Biz w/ Tech Epic: Integrated D&C Dashboard Expansion | Cancelled | Biz w/ Tech Epic | Tricolor Domain | 0113640 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: DCM Flow Planning Engine | Cancelled | Biz w/ Tech Epic | Tricolor Domain | 0116080 |  |  | Biz w/ Tech Epic |  |  |  | 5: XL
Biz w/ Tech Epic: Expansion of DS to Domestic Exp. and Grd Resi | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103273 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: GCP Data Lake Migration into Azure | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103308 | 7750 | TS-VL3-HybridCloud-GCPMigrateFraudDataLakeMigratio | Biz w/ Tech Epic | Build | E-530245 | E-530245 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-03-26 | 2025-12-31 | 2025-12-06
Biz w/ Tech Epic: E-453082 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103392 | 9314 | Smart Logistics ATRK/Large Shipper Enhancements | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-427599 - COM - RS Environment Database Setup, Da | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103532 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-532756 | E-532756 | 3: M | 2025-08-25 | 2025-08-25 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-25 | 2025-08-25
Biz w/ Tech Epic: E-364779 - COM - RS Rewrite - Create RMA Lite and | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103537 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-534552 | E-534552 | 3: M | 2025-08-25 | 2025-08-25 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-25 | 2025-08-25
Biz w/ Tech Epic: E-405177 - COM - RS Rewrite - Continuing developme | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103539 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-534563 | E-534563 | 3: M | 2025-08-25 | 2025-08-25 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-25 | 2025-08-25
Biz w/ Tech Epic: E-413314 - COM - RS RMA Processing - All Labels - | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103540 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-521080 | E-521080 | 3: M | 2025-08-25 | 2025-08-25 |  | 1 | 0 |  | 1 | No |  |  | 2025-08-25 | 2025-08-25
Biz w/ Tech Epic: E-427621 - COM - RS Long Term Inmar Program - FY24 | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103541 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-427621 | E-427621 | 2: S | 2025-07-01 | 2025-08-27 | 20% | 5 | 1 | 1 | 3 | No |  |  | 2025-07-01 | 2025-08-27
Biz w/ Tech Epic: COM - RS - RET - History and Archive Purging | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103542 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-450257 | E-450257 | 2: S | 2025-07-01 |  | 50% | 2 | 1 | 1 | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: E-456366 - COM - RS Build Remaining APIs to Suppor | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103545 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-532755 | E-532755 | 3: M | 2025-08-27 | 2025-08-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-27 | 2025-08-27
Biz w/ Tech Epic: COM - RS - RET - Finalization of Integration | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103547 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-456464 | E-456464 | 2: S | 2025-07-01 |  | 50% | 8 | 4 | 2 | 2 | No | 2024-11-05 | 2027-03-22 | 2025-07-01
Biz w/ Tech Epic: E-456486 - COM - RS FRT 2.0 - 24.05 - Rewrite Repo | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103548 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Done | E-456486 | E-456486 | 2: S | 2025-07-01 | 2025-08-22 |  | 3 | 0 | 2 | 1 | No |  |  | 2025-07-01 | 2025-08-22
Biz w/ Tech Epic: Testing SO Saturday delivery - FORGE & LEO | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103598 |  |  | Biz w/ Tech Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: PRJ 576143 Adding DG and Address Correction to Fue | Completed | Biz w/ Tech Epic | Commercial Portfolio | 0103667 | 8712 | Adding Dangerous Goods and Address Correction to F | Biz w/ Tech Epic | Done |  |  | 1: XS | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: Enabler - iView Improvement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103727 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Driver Name and Photo - Phase 2 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103763 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DP - Min/Max Threshold Pricing - EPIC 1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103764 | 6759 | Dynamic Pricing Min/Max Threshold Pricing | Biz w/ Tech Epic | Build | E-525822 | E-525822 | 3: M | 2025-08-26 |  |  | 3 | 0 | 2 | 1 | No | 2025-07-30 | 2025-10-21 | 2025-08-26
Biz w/ Tech Epic: PPM706410:Regulatory Fee to Compensate for CBP fee | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103773 | 84563 | Regulatory Fee to Compensate for CBP Fee | Biz w/ Tech Epic | Done | E-464247 | E-464247 | 3: M | 2025-09-10 | 2025-09-10 | 100% | 3 | 3 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: Visibility Quality Tracking Enhancements | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103788 | 7108 | [VIS]Tracking Quality | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: PRJ 474126 COM - RMIC - GROUND RATING MODERNIZATI | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103790 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Build | E-521079 | E-521079 | 5: XL | 2025-09-26 |  | 97.56% | 41 | 40 | 1 | 0 | No | 2025-07-30 | 2025-10-21 | 2025-09-26
Biz w/ Tech Epic: EDM - FIT | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103854 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Visibility EDD Suppression | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103875 | 8606 | E2E – High-Tech – Finished Goods - Apple (Phase 1) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2025-01-28
Biz w/ Tech Epic: Dynamic Pricing-UC#1 Enhancements for FGE - EPIC 1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103889 | 6762 | Dynamic Pricing Use Case #1 Enhancements (Enabler | Biz w/ Tech Epic | Build | E-525820 | E-525820 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-12-08 | 2026-04-30 | 2025-12-06
Biz w/ Tech Epic: WS11: Grow I-EU ERN-New rate card initiative Epic1 | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0103919 | 7717 | WS11: Grow I-EU ERN - New rate card initiative | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Optimize on-road activity Epic - 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103977 | 7161 | Optimize on-road activity to improve productivity. | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2025-12-31
Biz w/ Tech Epic: Implement 2-Step Authentication for 3rd Party usag | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104077 | 6842 | eLock: 2-factor authentication for 3rd party payme | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DataWorks Pickup PFS VB1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104186 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Last Mile Optimization (LMO) - Delivery for EU | Assumed Completed | Biz w/ Tech Epic | Commercial Portfolio | 0104265 | 6722 | AT - B2C operational setup (ENABLER) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Last Mile Optimization (LMO) - Delivery for DK | Assumed Completed | Biz w/ Tech Epic | Commercial Portfolio | 0104270 | 7684 | DK - B2C Operational Set-up (ENABLER) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FDMi Development - Include Specific Shipper EANs | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104271 | 7685 | Capability to switch on and off FDMI - EU LMO | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-03-13
Biz w/ Tech Epic: Last Mile Optimization (LMO) - Delivery for IE | Assumed Completed | Biz w/ Tech Epic | Commercial Portfolio | 0104357 | 9515 | IE - B2C operational setup (ENABLER) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dim Selection Logic Modernization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104363 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - Postal enablement EPIC 1: EE, LV, LT, SI | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0104419 | 9491 | Postal enablement EE, LV, LT, IE, BG, CY, SI, UA | Biz w/ Tech Epic | Build | E-483797 | E-483797 | 4: L | 2025-10-28 |  | 50% | 2 | 1 | 1 | 0 | No |  |  | 2025-10-28
Biz w/ Tech Epic: COM - Postal Enablement Epic 2: BG UA CY IE | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0104422 | 9491 | Postal enablement EE, LV, LT, IE, BG, CY, SI, UA | Biz w/ Tech Epic | Build | E-483801 | E-483801 | 4: L | 2026-01-14 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2026-01-14
Biz w/ Tech Epic: COM - EPIC 1 TR, PT, SK | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0104423 | 7710 | EUM - Express Domestics final countries | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-08-26
Biz w/ Tech Epic: COM - EPIC 2 EE, LV, LT, IE, SI | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104424 | 7710 | EUM - Express Domestics final countries | Biz w/ Tech Epic | Assessment & Analysis | E-550183 | E-550183 | 5: XL |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - RS - Online Chat/Virtual Assistant (E-475873 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104442 | 9381 | FXO Online Chatbot Pilot | Biz w/ Tech Epic | Assessment & Analysis | E-475873 | E-475873 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Third Party Account Creation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104490 | 9222 | FedEx account creation via 3rd party digital chann | Biz w/ Tech Epic | Assessment & Analysis | E-557254 | E-557254 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM-RS28-Product Bundling (E-475862) | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0104492 | 92305 | Product Bundling - FedEx Office | Biz w/ Tech Epic | Build | E-475862 | E-475862 | 1: XS | 2025-11-24 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-11-24
Biz w/ Tech Epic: Capability and API Rationalization | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0104566 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DRIVE #90505 – EDM Google Storage and API to Azure | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104590 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Notification Intelligence | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104599 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Weight Based Fuel Surcharge (Intl. Services) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104619 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM-RS28-Parcel Management Enhancements in FUSE | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104717 | 9380 | Parcel Management Enhancements in FUSE | Biz w/ Tech Epic | Build | E-157060 | E-157060 | 3: M | 2025-07-01 |  | 50% | 16 | 8 | 5 | 3 | No | 2025-04-23 | 2026-03-23 | 2025-07-01
Local Enhancement Epic: COM - RMIC - ID VAT Rate Update - 4 Feb 2025 Reg | Closed | Local Enhancement Epic | Commercial Portfolio | 0104725 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: COM - RMIC - Updt Fastbill Codes for FedEx Pkg Lab | Not Started | Local Enhancement Epic | Commercial Portfolio | 0104817 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RS -Store Inventory Client Upgd (Jet Mobile) | Closed | Lifecycle Management Epic | Commercial Portfolio | 0104818 |  |  | Lifecycle Management Epic | Build | E-502135 | E-502135 | 2: S | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM - RS - Price/Promo audit between ORC and FUSE | Approved | Local Enhancement Epic | Commercial Portfolio | 0104819 |  |  | Local Enhancement Epic | Build | E-482190 | E-482190 | 2: S | 2025-07-01 |  | 50% | 2 | 1 | 1 | 0 | No | 2025-08-27 | 2025-11-04 | 2025-07-01
Local Enhancement Epic: COM - RS-ServiceNow Pipeline Channel for Quickbase | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0104820 |  |  | Local Enhancement Epic | Assessment & Analysis | E-514058 | E-514058 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Fiji Direct Serve Conversion - Epic 1 (Commercial) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104822 | 6945 | Fiji Direct Serve Conversion | Biz w/ Tech Epic | Build | E-518858 | E-518858 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-18 | 2026-04-07 | 2025-12-06
Local Enhancement Epic: COM - GDX - (Vis) Domestic tracking PL/ZA redirect | Closed | Local Enhancement Epic | Commercial Portfolio | 0104846 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: Com - MVP Print As You Go (PASGO) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104861 | 6813 | FedEx Print As You Go (PASGO) | Biz w/ Tech Epic | Build | E-484905 | E-484905 | 4: L | 2025-07-02 |  | 50% | 8 | 4 |  | 4 | No | 2025-05-21 | 2027-08-20 | 2025-07-02
Biz w/ Tech Epic: Introduce new Unauthorized surcharge - com scope | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0104889 | 7690 | WS7 - Introduce Unauthorized surcharge | Biz w/ Tech Epic | Assessment & Analysis | E-574563 | E-574563 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-Google Playstore img/vid usage permissions | Closed | Local Enhancement Epic | Commercial Portfolio | 0104892 |  |  | Local Enhancement Epic | Backlog | E-521095 | E-521095 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - RS - Third Party Marketplace Expansion | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0104918 | 7845 | Packaging - Offer for Purchase (US) | Biz w/ Tech Epic | Build | E-422176 | E-422176 | 2: S | 2025-07-01 |  | 88.89% | 9 | 8 |  | 1 | No |  |  | 2025-07-01
Biz w/ Tech Epic: 1 - US Domestic Outbound parcel shipping | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105001 | 94166 | Sirius-Shipping-Core | Biz w/ Tech Epic | Assessment & Analysis | E-513437 | E-513437 | 4: L |  |  |  | 2 | 0 | 1 | 1 | No | 2025-01-20 | 2025-11-18
Local Enhancement Epic: COM - GDX - WREG Enhancement due to FedEx Rewards | Approved | Local Enhancement Epic | Commercial Portfolio | 0105343 |  |  | Local Enhancement Epic | Backlog | E-521096 | E-521096 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Lifecycle Management Epic: COM-GDX-Decommission of Shipping Admin (IPAS) | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105344 |  |  | Lifecycle Management Epic | Build | E-485843 | E-485843 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-04-01 | 2025-06-13 | 2026-04-23
Local Enhancement Epic: COM-MS-Enhance Visual API to add loc ID from Fus | Approved | Local Enhancement Epic | Commercial Portfolio | 0105348 |  |  | Local Enhancement Epic | Launch & Evaluate | E-527687 | E-527687 | 1: XS | 2025-06-26 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-06-26
Lifecycle Management Epic: COM-MS-Google ESR Security Review Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105350 |  |  | Lifecycle Management Epic | Backlog | E-521100 | E-521100 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-HEAT weather messaging | Approved | Local Enhancement Epic | Commercial Portfolio | 0105351 |  |  | Local Enhancement Epic | Backlog | E-521099 | E-521099 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-RS-WMS Redwood Application | Closed | Lifecycle Management Epic | Commercial Portfolio | 0105354 |  |  | Lifecycle Management Epic | Backlog | E-482191 | E-482191 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - S&CDE - Sending CDP curated data to Atlas | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105373 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic Vis. Core List view, filtering capabilities | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104983 | 94149 | Visibility-Core | Biz w/ Tech Epic | Build | E-513421 | E-513421 | 4: L | 2025-07-18 |  |  | 3 | 0 | 1 | 2 | No | 2025-01-20 | 2025-09-01 | 2025-07-18
Biz w/ Tech Epic: Epic Sirius Visibility Core- Shipment Details View | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105374 | 94149 | Visibility-Core | Biz w/ Tech Epic | Build | E-513416 | E-513416 | 4: L | 2025-07-18 |  |  | 3 | 0 | 1 | 2 | No | 2025-01-20 | 2025-09-01 | 2025-07-18
Local Enhancement Epic: COM - S&CDE - Foundational Customer View | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105376 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - DDC Pre-Sales Leads | Approved | Local Enhancement Epic | Commercial Portfolio | 0105377 |  |  | Local Enhancement Epic | Backlog | E-484887 | E-484887 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - S&CDE - FS-Digital Sales Activate-UC1 Expand | Approved | Local Enhancement Epic | Commercial Portfolio | 0105380 |  |  | Local Enhancement Epic | Build | E-485250 | E-485250 | 1: XS | 2025-10-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-10-01
Local Enhancement Epic: COM - S&CDE - FedEx Rewards Expansion | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105381 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - Canada Journey Use Cases | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105382 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - Legacy Core Data Migration | Approved | Local Enhancement Epic | Commercial Portfolio | 0105383 |  |  | Local Enhancement Epic | Build | E-485266 | E-485266 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM -S&CDE -PR Re-image Journey w/ Adverse Factors | Approved | Local Enhancement Epic | Commercial Portfolio | 0105384 |  |  | Local Enhancement Epic | Backlog | E-501103 | E-501103 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: Epic Sirius Visibility Core-Actionable links | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105385 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513417 | E-513417 | 4: L |  |  |  | 2 | 0 |  | 2 | No | 2025-03-31 | 2025-09-15
Biz w/ Tech Epic: Epic Sirius Visibility Core Notifications | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105387 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513411 | E-513411 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-31 | 2025-09-15
Local Enhancement Epic: COM - RMIC - CA FDS ARC EDI 0 Dollar Activity Recs | Approved | Local Enhancement Epic | Commercial Portfolio | 0105389 |  |  | Local Enhancement Epic | Launch & Evaluate | E-497445 | E-497445 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Biz w/ Tech Epic: Epic Sirius Visibility Core-Multicarrier Tracking | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105393 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513418 | E-513418 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-01-20 | 2025-09-01
Biz w/ Tech Epic: 2 - International, Non-US dom, Intra EU, USMCA | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105396 | 94166 | Sirius-Shipping-Core | Biz w/ Tech Epic | Assessment & Analysis | E-513443 | E-513443 | 4: L |  |  |  | 1 | 0 | 1 | 0 | No | 2025-01-20 | 2026-01-29
Biz w/ Tech Epic: 3 - Special Services | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105397 | 94166 | Sirius-Shipping-Core | Biz w/ Tech Epic | Assessment & Analysis | E-513445 | E-513445 | 4: L |  |  |  | 1 | 0 | 1 | 0 | No | 2025-01-20 | 2026-02-20
Biz w/ Tech Epic: 4 - Managed Users | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105399 | 94166 | Sirius-Shipping-Core | Biz w/ Tech Epic | Assessment & Analysis | E-513447 | E-513447 | 4: L |  |  |  | 1 | 0 | 1 | 0 | No | 2025-01-20 | 2026-06-01
Biz w/ Tech Epic: 5 - Express Freight | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105400 | 94166 | Sirius-Shipping-Core | Biz w/ Tech Epic | Assessment & Analysis | E-513449 | E-513449 | 4: L |  |  |  | 1 | 0 | 1 | 0 | No | 2025-01-20 | 2026-06-25
Biz w/ Tech Epic: Warehouse Order Fulfillment Optimization | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0105402 | 88849 | Warehouse Order Fulfillment Optimization | Biz w/ Tech Epic | Done | E-479546 | E-479546 | 1: XS | 2025-07-01 | 2025-08-07 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-08-07
Local Enhancement Epic: COM - Sales/CDE TNT2FedEx Cust Migration Incent Db | Approved | Local Enhancement Epic | Commercial Portfolio | 0105405 |  |  | Local Enhancement Epic | Build | E-484316 | E-484316 | 1: XS | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2025-03-12 | 2025-10-07 | 2025-07-02
Local Enhancement Epic: COM - Sales/CDE CRM - BAC Top 100 Overview Dashb | On Hold | Local Enhancement Epic | Commercial Portfolio | 0105406 |  |  | Local Enhancement Epic | Build | E-482093 | E-482093 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | Yes | 2025-03-12 | 2025-10-07 | 2025-07-01
Lifecycle Management Epic: COM - S&CDE - Refactoring CHT GUI | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105407 |  |  | Lifecycle Management Epic | Build | E-478508 | E-478508 | 1: XS | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Biz w/ Tech Epic: EDM Google Storage/API to Azure Storage/API | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105446 | 6702 | TS-VL3-HybridCloud-GCPMigrateGoogleStorage | Biz w/ Tech Epic | Backlog | E-483248 | E-483248 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2025-10-29
Biz w/ Tech Epic: COM - DELIVERY PREDICTIONS VB5 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105465 | 7727 | [US] Implement visibility enhancements on FedEx.co | Biz w/ Tech Epic | Assessment & Analysis | E-472651 | E-472651 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-08 | 2025-08-12
Local Enhancement Epic: COM - RMIC - Nova Scotia HST reduce to 14% | Approved | Local Enhancement Epic | Commercial Portfolio | 0105487 |  |  | Local Enhancement Epic | Build | E-520911 | E-520911 | 4: L | 2025-07-21 |  | 50% | 2 | 1 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2025-07-21
Local Enhancement Epic: COM - DART - Marketing Tagging Request - DART PI02 | Closed | Local Enhancement Epic | Commercial Portfolio | 0105488 |  |  | Local Enhancement Epic | Backlog | E-520999 | E-520999 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - Penguin Pickup - P4e Integration | Completed | Local Enhancement Epic | Commercial Portfolio | 0105502 |  |  | Local Enhancement Epic | Done | E-504401 | E-504401 | 2: S | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Biz w/ Tech Epic: Epic Sirius Visibiity Core Export Shipment Data | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105503 | 94149 | Visibility-Core | Biz w/ Tech Epic | Build | E-513403 | E-513403 | 3: M | 2025-07-18 |  |  | 1 | 0 | 1 | 0 | No | 2025-01-01 | 2025-07-02 | 2025-07-18
Biz w/ Tech Epic: Epic Sirius Visibility Core Inbound Experience | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105505 | 94149 | Visibility-Core | Biz w/ Tech Epic | Build | E-513407 | E-513407 | 4: L | 2025-08-13 |  |  | 2 | 0 | 1 | 1 | No | 2025-03-31 | 2025-09-15 | 2025-08-13
Biz w/ Tech Epic: Epic Sirius Visibility Core Third Party Tracking | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105508 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513414 | E-513414 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-03-31 | 2025-09-15
Local Enhancement Epic: COM - RMIC-STC - BaC Enhncmnt Due to FedEx Rwds | Closed | Local Enhancement Epic | Commercial Portfolio | 0105511 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: COM - GDX - Invite User Template Email | Approved | Local Enhancement Epic | Commercial Portfolio | 0105531 |  |  | Local Enhancement Epic | Launch & Evaluate | E-482395 | E-482395 | 1: XS | 2025-06-26 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-06-26
Local Enhancement Epic: COM - GDX -ADMC 3.0 Retire APIG Gateway Switchover | Approved | Local Enhancement Epic | Commercial Portfolio | 0105532 |  |  | Local Enhancement Epic | Build | E-482399 | E-482399 | 1: XS | 2026-04-23 |  |  | 2 | 0 | 2 | 0 | No | 2025-07-30 | 2025-10-07 | 2026-04-23
Biz w/ Tech Epic: Epic- Sirius Visibility core Common Data Layer | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105542 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513420 | E-513420 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-08-27
Biz w/ Tech Epic: Epic Sirius Visibility Core Data Retention and Rep | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105543 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513406 | E-513406 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2025-10-02
Biz w/ Tech Epic: Epic Sirius Visibility Core Clear Shipment Status | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105544 | 94149 | Visibility-Core | Biz w/ Tech Epic | Build | E-513405 | E-513405 | 4: L | 2025-07-18 |  |  | 1 | 0 | 1 | 0 | No | 2025-03-31 | 2025-09-15 | 2025-07-18
Biz w/ Tech Epic: Epic Sirius Visibility Core User Experience Perf | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105546 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513415 | E-513415 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Epic Sirius Visibility Core Localization for Exp | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105547 | 94149 | Visibility-Core | Biz w/ Tech Epic | Backlog | E-513410 | E-513410 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: L1 Sirius-fdxPlatform-Re-platform journey | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105017 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513806 | E-513806 | 4: L |  |  |  | 2 | 0 |  | 2 | No
Local Enhancement Epic: COM - GDX - EU Retail store list API failure alert | Approved | Local Enhancement Epic | Commercial Portfolio | 0105583 |  |  | Local Enhancement Epic | Build | E-504000 | E-504000 | 1: XS | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-02
Local Enhancement Epic: COM - GDX -DDTC AES Data Element Filing Requiremts | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105585 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - Quickbase Location Data | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105586 |  |  | Local Enhancement Epic | Assessment & Analysis | E-514057 | E-514057 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-GDX-Apple Watch & Widget Sprt Forgerock Cookie | Approved | Local Enhancement Epic | Commercial Portfolio | 0105587 |  |  | Local Enhancement Epic | Build | E-482400 | E-482400 | 2: S | 2026-03-03 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-03-03
Lifecycle Management Epic: COM - GDX - GHAS Scan for iOS | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105588 |  |  | Lifecycle Management Epic | Build | E-483043 | E-483043 | 2: S | 2025-07-21 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-21
Local Enhancement Epic: COM - RMIC-STC - Fiji NON-STANDARD BILLING | Approved | Local Enhancement Epic | Commercial Portfolio | 0105590 |  |  | Local Enhancement Epic | Backlog | E-521088 | E-521088 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-RS28-Add SKUs to PFC Assortment (VALUE) | Closed | Local Enhancement Epic | Commercial Portfolio | 0105593 |  |  | Local Enhancement Epic | Build | E-473739 | E-473739 | 1: XS | 2025-08-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-06
Local Enhancement Epic: COM - RMIC - Intl Map “Activity Date” Inv in ERA | Approved | Local Enhancement Epic | Commercial Portfolio | 0105594 |  |  | Local Enhancement Epic | Build | E-512454 | E-512454 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - GDX - Add new accts to Apple DM Suppresion | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105595 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX -FDM Enhc - Delivery Instructions on Trk | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105596 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RMIC-ROPs - CAN Credit Card Declines Automate | Approved | Local Enhancement Epic | Commercial Portfolio | 0105597 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542279 | E-542279 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - CAPS Support - CY25 | Closed | Lifecycle Management Epic | Commercial Portfolio | 0105598 |  |  | Lifecycle Management Epic | Done |  |  | 3: M | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Local Enhancement Epic: COM - GDX - Remove FDX login cookie API call | Approved | Local Enhancement Epic | Commercial Portfolio | 0105599 |  |  | Local Enhancement Epic | Build | E-482397 | E-482397 | 3: M | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: COM - GIX-Grnd Econ FXSP & Inv Composite Map Chngs | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105600 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CT-Grnd Econ FXSP & Inv Composite Map Chngs | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105601 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - Canada SAM Growth Journey | Approved | Local Enhancement Epic | Commercial Portfolio | 0105602 |  |  | Local Enhancement Epic | Build | E-484854 | E-484854 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Biz w/ Tech Epic: Onboarding and Upsell-VB1-E2 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105606 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513808 | E-513808 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB1-E3 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105611 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513810 | E-513810 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB1-E4 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105621 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513812 | E-513812 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB2-E5 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105625 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513814 | E-513814 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - GIX - Norfolk Southern Placard Issues | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105633 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB2-E6 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105634 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513816 | E-513816 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB2-E7 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105639 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513818 | E-513818 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB2-E8 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105642 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513820 | E-513820 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB3-E9 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105643 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513831 | E-513831 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB3-E10 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105645 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513822 | E-513822 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB3-E11 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105646 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513824 | E-513824 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB3-E12 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105647 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513826 | E-513826 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Onboarding and Upsell-VB3-E13 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105649 | 96317 | Sirius-Onboard&Upsell-Re-platforming journey | Biz w/ Tech Epic | Assessment & Analysis | E-513828 | E-513828 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - GIX - Home Depot EDI 214 4060 Local | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105682 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TBD | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105740 | 7363 | VAN Migration and Provider Consolidation ¦ SURGE | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - MS - ENS - Lifecycle Management - CY25 PI2 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105743 |  |  | Lifecycle Management Epic | Build | E-485847 | E-485847 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - MS - NDS - Local Enhancements - CY25 PI2 | Approved | Local Enhancement Epic | Commercial Portfolio | 0105744 |  |  | Local Enhancement Epic | Build | E-485851 | E-485851 | 2: S | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM-RS28-Enable Marketplace in FUSE (VALUE) | Approved | Local Enhancement Epic | Commercial Portfolio | 0105747 |  |  | Local Enhancement Epic | Backlog | E-514066 | E-514066 | 2: S |  |  |  | 2 | 0 |  | 2 | No | 2026-03-25 | 2026-08-25
Local Enhancement Epic: COM - GDX - Direct to Retail for Lockers | Approved | Local Enhancement Epic | Commercial Portfolio | 0105749 |  |  | Local Enhancement Epic | Build | E-503998 | E-503998 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-01
Local Enhancement Epic: COM - RS - Direct to Retail for Lockers | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105750 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VAN Migration and Provider Consolidation ¦ SURGE | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0105758 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VAN Migration and Provider Consolidation ¦ SURGE | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0105759 | 7363 | VAN Migration and Provider Consolidation ¦ SURGE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Track 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105761 | 7682 | WS8 - T1 – Conclusive info about shipment status | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - GDX- MS-NDS - LCM - CY25 PI2 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105765 |  |  | Lifecycle Management Epic | Build | E-485853 | E-485853 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-01
Local Enhancement Epic: COM-RS28-AEC Printer Refresh | Closed | Local Enhancement Epic | Commercial Portfolio | 0105785 |  |  | Local Enhancement Epic | Build | E-514078 | E-514078 | 2: S | 2025-08-06 |  | 66.67% | 3 | 2 |  | 1 | No |  |  | 2025-08-06
Local Enhancement Epic: COM - RMIC-GDX - CA FBO EFT Text Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0105788 |  |  | Local Enhancement Epic | Backlog | E-527688 | E-527688 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - EDM - Lifecycle Management PI25.2 | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0105790 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - LCM - Enterprise Currency PI25.2 | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0105791 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - EDM Local Enhancements - PI25.2 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105792 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Add LAC Non-MX New Reason Cate in ERA | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105793 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - Enterprise Currency - LE - PI25.2 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105794 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - ENS - Local Enhancements - CY25 PI2 | Approved | Local Enhancement Epic | Commercial Portfolio | 0105823 |  |  | Local Enhancement Epic | Build | E-485850 | E-485850 | 2: S | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Biz w/ Tech Epic: COM - GSP TO DIRECT SERVE - BULGARIA (BG) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105836 | 7670 | Enable- G2D conversion Bulgaria and Cyprus (ACE en | Biz w/ Tech Epic | Assessment & Analysis | E-518867 | E-518867 | 3: M |  |  |  | 2 | 0 | 1 | 1 | No | 2025-10-22 | 2026-02-03
Biz w/ Tech Epic: Driver Name & Photo Phase 2 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105838 | 91393 | [VIS] Driver Name & Photo - Phase 2 | Biz w/ Tech Epic | Assessment & Analysis | E-497451 | E-497451 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-08-27
Biz w/ Tech Epic: 781967 - FXO Omni-Channel Profile - Phase 1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105839 | 86367 | FXO Omni-Channel Experience - Profile Unification | Biz w/ Tech Epic | Build | E-500558 | E-500558 | 2: S | 2025-12-31 |  | 83.33% | 18 | 15 |  | 3 | No | 2025-11-05 | 2026-06-02 | 2025-12-31
Biz w/ Tech Epic: COM - GSP TO DIRECT SERVE - CYPRUS (CY) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105840 | 7670 | Enable- G2D conversion Bulgaria and Cyprus (ACE en | Biz w/ Tech Epic | Build | E-518864 | E-518864 | 3: M | 2025-11-13 |  |  | 2 | 0 | 1 | 1 | No | 2025-03-03 | 2025-04-28 | 2025-11-13
Local Enhancement Epic: COM-RS28-Retail Political Advertising Compliance | Approved | Local Enhancement Epic | Commercial Portfolio | 0105841 |  |  | Local Enhancement Epic | Build | E-504267 | E-504267 | 2: S | 2026-03-18 |  | 20% | 5 | 1 |  | 4 | No | 2025-08-27 | 2026-05-29 | 2026-03-18
Local Enhancement Epic: COM - GDX -DAL API Enhancement for Express Freight | Closed | Local Enhancement Epic | Commercial Portfolio | 0105843 |  |  | Local Enhancement Epic | Build | E-536750 | E-536750 | 2: S | 2025-09-05 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-09-05
Local Enhancement Epic: COM - GDX - EU e-com retail expansion CZ & Baltics | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105845 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-FUSE Account & Customer Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0105846 |  |  | Local Enhancement Epic | Build | E-514086 | E-514086 | 2: S | 2026-03-19 |  |  | 2 | 0 | 1 | 1 | No | 2025-11-05 | 2026-03-25 | 2026-03-19
Lifecycle Management Epic: COM - GDX - PCC Infrastructure Support 25.02-05 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0105847 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-486707 | E-486707 | 2: S | 2025-06-27 |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07 | 2025-06-27
Local Enhancement Epic: COM - GDX - Cache for ADMC & FCLA Retire(USRC3.5) | Approved | Local Enhancement Epic | Commercial Portfolio | 0105848 |  |  | Local Enhancement Epic | Backlog | E-497608 | E-497608 | 1: XS |  |  | 100% | 3 | 3 |  | 0 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: Direct to Retail (DTR) Location Project | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105851 | 8174 | WS11 - I-EU B2C: Global Direct-to-Retail | Biz w/ Tech Epic | Build | E-518846 | E-518846 | 5: XL | 2025-09-26 |  | 90% | 10 | 9 |  | 1 | No | 2025-07-30 | 2025-10-21 | 2025-09-26
Biz w/ Tech Epic: Assessment of Weight Based Fuel using custom fuel | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105863 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-03-25
Biz w/ Tech Epic: Assessing Weight Based Fuel Surcharge | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105868 | 6755 | Weight Based Fuel Surcharge for Intl. Express | Biz w/ Tech Epic | Assessment & Analysis | E-518662 | E-518662 | 1: XS |  |  |  | 1 | 0 | 1 | 0 | No | 2025-01-01 | 2025-10-20
Biz w/ Tech Epic: Turkey Instant Invoicing - TO DELETE | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0105905 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Turkey Instant Invoice | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0105908 | 8431 | Turkey Instant Invoicing | Biz w/ Tech Epic | Backlog | E-484738 | E-484738 | 2: S |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: Project Clarity | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0105915 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Project Clarity | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105918 | 84393 | COM - S&CDE - CRM - Project Clarity | Biz w/ Tech Epic | Build | E-507762 | E-507762 | 3: M | 2025-09-10 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-09-10
Local Enhancement Epic: COM - S&CDE - Integrate Ambition Coach Tool iSell | Approved | Local Enhancement Epic | Commercial Portfolio | 0105920 |  |  | Local Enhancement Epic | Build | E-484885 | E-484885 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - GIX - J&J Update EDI Mapping Support | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105922 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - CT Highspot Pitch, Digital Room Design | Closed | Local Enhancement Epic | Commercial Portfolio | 0105923 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528373 | E-528373 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: COM - GIX - Lowes Custom EDI 211 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105935 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-03-24 | 2025-04-10
Local Enhancement Epic: COM - GIX - BD EDI 856 214/315 & 810 Mapping Spprt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105943 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Monthly FPOS Maintenance Loads FXO | Approved | Local Enhancement Epic | Commercial Portfolio | 0105944 |  |  | Local Enhancement Epic | Build | E-512821 | E-512821 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - GDX - Digital Res-High Risk/Value-Security | Approved | Local Enhancement Epic | Commercial Portfolio | 0105945 |  |  | Local Enhancement Epic | Backlog | E-486940 | E-486940 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - RMIC-STC - TH Electronic Invoice/Receipt | Approved | Local Enhancement Epic | Commercial Portfolio | 0105946 |  |  | Local Enhancement Epic | Backlog | E-534775 | E-534775 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - GDX - Password Reset For Admin Users | Approved | Local Enhancement Epic | Commercial Portfolio | 0105947 |  |  | Local Enhancement Epic | Build | E-520899 | E-520899 | 1: XS | 2025-07-10 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-12-30 | 2025-07-10
Local Enhancement Epic: COM - GDX - Swisspost POD automatization | Approved | Local Enhancement Epic | Commercial Portfolio | 0105948 |  |  | Local Enhancement Epic | Backlog | E-517557 | E-517557 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX - API Enablement - Login V2 in Prod | Approved | Local Enhancement Epic | Commercial Portfolio | 0105949 |  |  | Local Enhancement Epic | Launch & Evaluate | E-488545 | E-488545 | 1: XS | 2025-06-26 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-06-26
Local Enhancement Epic: COM - RMIC - Duty Tax Invoice Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0105950 |  |  | Local Enhancement Epic | Build | E-497433 | E-497433 | 2: S | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: COM - RMIC - Estonia VAT Rate Change July 2025 | Approved | Local Enhancement Epic | Commercial Portfolio | 0105951 |  |  | Local Enhancement Epic | Build | E-501166 | E-501166 | 2: S | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-13
Local Enhancement Epic: COM - RMIC - CA Disbursement Fee Change | Closed | Local Enhancement Epic | Commercial Portfolio | 0105952 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: COM - IA - GIX - B&H Photo Freight EDI Manifest | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105953 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - APAC LDP chng Taiwan GUI inv | Approved | Local Enhancement Epic | Commercial Portfolio | 0105954 |  |  | Local Enhancement Epic | Build | E-512818 | E-512818 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM - GDX - New OOH partner France (drop-off) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0105955 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Completing Ground Economy Rating Modernization | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105970 | 6754 | Completing Ground Economy Rating Modernization | Biz w/ Tech Epic | Backlog | E-512055 | E-512055 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - MMR WEBADI Make Acct Number Optional | Closed | Local Enhancement Epic | Commercial Portfolio | 0105974 |  |  | Local Enhancement Epic | Done | E-512456 | E-512456 | 1: XS | 2025-07-01 | 2025-07-22 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-07-22
Local Enhancement Epic: COM - GIX - Home Depot EDI 214 4060 Local | In Progress | Local Enhancement Epic | Commercial Portfolio | 0105987 |  |  | Local Enhancement Epic | Assessment & Analysis | E-486980 | E-486980 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-RD3 - TNT ID Incr Amount Field Limit | Approved | Local Enhancement Epic | Commercial Portfolio | 0106032 |  |  | Local Enhancement Epic | Build | E-521087 | E-521087 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM-RS28-Color Verification Automation | Closed | Local Enhancement Epic | Commercial Portfolio | 0105444 |  |  | Local Enhancement Epic | Build | E-515454 | E-515454 | 3: M | 2025-08-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-01
Local Enhancement Epic: COM-RS-Email Returns Print at Walgreens | Closed | Local Enhancement Epic | Commercial Portfolio | 0105372 |  |  | Local Enhancement Epic | Build | E-514063 | E-514063 | 2: S | 2025-08-04 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-04
Biz w/ Tech Epic: Digital Customer Support Application | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106056 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - GDX - CAPS Support - Upgrade APPD App Agent | Closed | Lifecycle Management Epic | Commercial Portfolio | 0106064 |  |  | Lifecycle Management Epic | Backlog | E-486953 | E-486953 | 1: XS |  |  |  | 1 | 0 | 1 | 0 | No
Local Enhancement Epic: COM - GDX - Visibility - Manage Delvry Errors Updt | Approved | Local Enhancement Epic | Commercial Portfolio | 0106066 |  |  | Local Enhancement Epic | Build | E-486949 | E-486949 | 1: XS | 2025-11-18 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-11-18
Local Enhancement Epic: COM - GDX - MS-Retail EU AT/DE locker PUPCd Provdr | On Hold | Local Enhancement Epic | Commercial Portfolio | 0106068 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | Yes
Lifecycle Management Epic: COM - GIX - FedEx Net WebTrade Guide Update | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106086 |  |  | Lifecycle Management Epic | Backlog | E-486986 | E-486986 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Lifecycle Management Epic: COM - CSX - Migrate Case EBS Colo to MS Azure | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106087 |  |  | Lifecycle Management Epic | Backlog | E-512059 | E-512059 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-04-07 | 2026-08-27
Local Enhancement Epic: COM - RMIC-RD3 - Blackline remit Intl Cash Apps | Approved | Local Enhancement Epic | Commercial Portfolio | 0106089 |  |  | Local Enhancement Epic | Build | E-461778 | E-461778 | 1: XS | 2025-08-13 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-13
Biz w/ Tech Epic: Digital Customer Support Application | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106094 | 7092 | WS8-GS1-Digital Reactive Cust Support Acceleration | Biz w/ Tech Epic | Backlog | E-511600 | E-511600 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-04-21 | 2027-07-14
Biz w/ Tech Epic: Admin Console Application | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106096 | 7092 | WS8-GS1-Digital Reactive Cust Support Acceleration | Biz w/ Tech Epic | Build | E-511603 | E-511603 | 3: M | 2025-09-15 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-15
Biz w/ Tech Epic: Decision Engine/Service Jour. Orchestration Engine | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106098 | 7092 | WS8-GS1-Digital Reactive Cust Support Acceleration | Biz w/ Tech Epic | Build | E-511608 | E-511608 | 4: L | 2025-09-15 |  |  | 1 | 0 | 1 | 0 | No | 2025-04-21 | 2027-07-14 | 2025-09-15
Biz w/ Tech Epic: Customer Support Channels Alignment - GS1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106106 | 7092 | WS8-GS1-Digital Reactive Cust Support Acceleration | Biz w/ Tech Epic | Backlog | E-511609 | E-511609 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-04-21 | 2027-07-14
Biz w/ Tech Epic: CE Agent Desktop Enhancements - GS1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106108 | 7092 | WS8-GS1-Digital Reactive Cust Support Acceleration | Biz w/ Tech Epic | Build | E-511892 | E-511892 | 3: M | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-04-21 | 2027-07-14 | 2025-07-01
Local Enhancement Epic: COM - IA - GIX - EDI 945 & 214 Matching-Apple Inc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106168 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - CRM - US DDC Dashb Reporting Updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0106169 |  |  | Local Enhancement Epic | Build | E-486945 | E-486945 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - S&CDE - CRM - TMD and MyTerr Simplification | Approved | Local Enhancement Epic | Commercial Portfolio | 0106170 |  |  | Local Enhancement Epic | Build | E-487044 | E-487044 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Lifecycle Management Epic: COM - S&CDE - CRM - PI-03 iSell LCM Requests | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0106171 |  |  | Lifecycle Management Epic | Build | E-485519 | E-485519 | 1: XS | 2025-07-01 |  | 25% | 4 | 1 | 1 | 2 | No |  |  | 2025-07-01
Lifecycle Management Epic: COM - GDX-AppDynamics Intgrt Mobile apps-IPHN/ANDR | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106175 |  |  | Lifecycle Management Epic | Build | E-498219 | E-498219 | 1: XS | 2026-03-03 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-03-03
Local Enhancement Epic: COM - GDX - FiT DocUpload Reminders sent weekdays | Closed | Local Enhancement Epic | Commercial Portfolio | 0106178 |  |  | Local Enhancement Epic | Done | E-517542 | E-517542 | 1: XS | 2025-07-21 | 2025-08-19 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-21 | 2025-08-19
Local Enhancement Epic: COM - GDX - FiT DocUpload - Docs tab enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0106179 |  |  | Local Enhancement Epic | Build | E-501878 | E-501878 | 2: S | 2025-10-23 |  | 50% | 2 | 1 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2025-10-23
Local Enhancement Epic: COM - GDX - FiT DocUpload Notfctns storg EISTC | Closed | Local Enhancement Epic | Commercial Portfolio | 0106180 |  |  | Local Enhancement Epic | Done | E-507616 | E-507616 | 1: XS | 2025-07-21 | 2025-07-21 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-21 | 2025-07-21
Biz w/ Tech Epic: Manually extract and store exchange rates | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0106080 | 7036 | Global Air Freight Contract Exchange Rates | Biz w/ Tech Epic | Done | E-518617 | E-518617 | 2: S | 2025-06-26 | 2025-07-21 |  | 1 | 0 | 1 | 0 | No |  |  | 2025-06-26 | 2025-07-21
Biz w/ Tech Epic: COM-RS28-FedEx Office Upload to Quote - Retail | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106214 | 93474 | FedEx Office Upload to Quote - Retail | Biz w/ Tech Epic | Build | E-475884 | E-475884 | 1: XS | 2025-07-15 |  | 33.33% | 3 | 1 | 1 | 1 | No | 2025-06-18 | 2026-03-24 | 2025-07-15
Biz w/ Tech Epic: First API Gateway Enabler | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106218 | 7137 | CASCADE 3.1-API Enabler | Biz w/ Tech Epic | Assessment & Analysis | E-497811 | E-497811 | 3: M |  |  | 50% | 2 | 1 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX - New OOH partner France (drop-off) | Approved | Local Enhancement Epic | Commercial Portfolio | 0106222 |  |  | Local Enhancement Epic | Backlog | E-501874 | E-501874 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Pkg Lvl Chrg Smry Pre-Rated Shpmnts | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106223 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA/GDX - Support on APIF Country API | Approved | Local Enhancement Epic | Commercial Portfolio | 0106224 |  |  | Local Enhancement Epic | Backlog | E-463094 | E-463094 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - IA - CIS -New SWID APIF APIs for EC-Shipping | Approved | Local Enhancement Epic | Commercial Portfolio | 0106225 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543428 | E-543428 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - Invited Users Cannot Access .com Apps | Approved | Local Enhancement Epic | Commercial Portfolio | 0106226 |  |  | Local Enhancement Epic | Backlog | E-501876 | E-501876 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - Collect Clearance Authrztn Resi Shpts | Approved | Local Enhancement Epic | Commercial Portfolio | 0106227 |  |  | Local Enhancement Epic | Build | E-513339 | E-513339 | 2: S | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-06-27
Lifecycle Management Epic: COM - GDX - update comm description in Rating API | On Hold | Lifecycle Management Epic | Commercial Portfolio | 0106257 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - CRM Sales Telephony | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106285 |  |  | Local Enhancement Epic | Build | E-498922 | E-498922 | 2: S | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | Yes |  |  | 2025-07-02
Local Enhancement Epic: COM-S&CDE - CRM Sales Action Hub | Approved | Local Enhancement Epic | Commercial Portfolio | 0106286 |  |  | Local Enhancement Epic | Build | E-497813 | E-497813 | 2: S | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: COM - S&CDE - CRM - Re-launching Salesforce Mobile | Approved | Local Enhancement Epic | Commercial Portfolio | 0106287 |  |  | Local Enhancement Epic | Build | E-497826 | E-497826 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-21 | 2025-10-07 | 2025-07-01
Local Enhancement Epic: COM - S&CDE - CRM - Project Shift Ocean/Brokerage | Approved | Local Enhancement Epic | Commercial Portfolio | 0106288 |  |  | Local Enhancement Epic | Backlog | E-497834 | E-497834 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-05-21 | 2025-10-07
Local Enhancement Epic: COM - S&CDE - CRM Poppulo Email Platform | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106289 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX -Mobile App Fraud Awareness & Protection | Closed | Local Enhancement Epic | Commercial Portfolio | 0106291 |  |  | Local Enhancement Epic | Done | E-517590 | E-517590 | 1: XS | 2025-09-10 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: COM - IA-GIX-Customer Experiment-J&J EDI Data Updt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106292 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - New User Defined Attributes (UDAs) ORC | Closed | Local Enhancement Epic | Commercial Portfolio | 0106293 |  |  | Local Enhancement Epic | Build | E-504036 | E-504036 | 2: S | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM - IA-GIX-Whaleco CA Shp Dt/Tender Dt Map Chngs | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106294 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - Modernize ACTC | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106295 |  |  | Lifecycle Management Epic | Build | E-507658 | E-507658 | 3: M | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-04 | 2026-05-19 | 2025-07-01
Biz w/ Tech Epic: KMS 2.0 Adoption and Knowledge Reporting | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106300 | 7681 | WS8 - GS6 – Knowledge Management 2.0 – System Enh | Biz w/ Tech Epic | Backlog | E-527431 | E-527431 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: COM - RMIC - eDD - NMFC Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0106303 |  |  | Local Enhancement Epic | Build | E-512450 | E-512450 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - IA - CIS - Support on APIF Shipping APIs | Approved | Local Enhancement Epic | Commercial Portfolio | 0106319 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553076 | E-553076 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Modernize Express US Domestic Rating | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106331 | 92081 | Modernize Express US Domestic Rating | Biz w/ Tech Epic | Build | E-518624 | E-518624 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-21 | 2025-12-06
Biz w/ Tech Epic: Epic 1 A (US) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106337 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | E-500559 | E-500559 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-11-14
Biz w/ Tech Epic: Implement GDL for FDX/Shoprunner | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106358 | 98435 | Digital-Enablers-Data collection & Analytics tool | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2026-09-30
Biz w/ Tech Epic: ITN Flexibility for Label Creation and Filing | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106380 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Automated Invoice Account Creation EU/CA/US | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106412 | 8241 | Automated Account Creation on Invoice via .com | Biz w/ Tech Epic | Build | E-499006 | E-499006 | 3: M | 2026-03-09 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2026-03-09
Local Enhancement Epic: COM - RMIC - Optimize MBG Policy Grid | Approved | Local Enhancement Epic | Commercial Portfolio | 0106414 |  |  | Local Enhancement Epic | Build | E-521001 | E-521001 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Ground Global Payor Account | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106420 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Macedonia Country Name Change | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106422 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - APAC FiT Pre-clearance Notify Importer | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106423 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX-MS-Mobile App Access Violation Resol | Approved | Local Enhancement Epic | Commercial Portfolio | 0106424 |  |  | Local Enhancement Epic | Backlog | E-501441 | E-501441 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX - MS-APAC FiT: Pre-clear Notify Importer | Approved | Local Enhancement Epic | Commercial Portfolio | 0106425 |  |  | Local Enhancement Epic | Backlog | E-512157 | E-512157 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX - MS - Move Push Notify Templates to ENS | Approved | Local Enhancement Epic | Commercial Portfolio | 0106427 |  |  | Local Enhancement Epic | Backlog | E-501443 | E-501443 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM- PI-03 iSell Case Channel/Enhancemnt | Closed | Local Enhancement Epic | Commercial Portfolio | 0106431 |  |  | Local Enhancement Epic | Done | E-498841 | E-498841 | 2: S | 2025-07-01 | 2025-09-10 |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01 | 2025-09-10
Local Enhancement Epic: COM - S&CDE - CRM - PI-03 CRMA Dashbd Enhancements | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106432 |  |  | Local Enhancement Epic | Build | E-498560 | E-498560 | 1: XS | 2025-07-01 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM-S&CDE-CRM CY25 iSell Local Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0106433 |  |  | Local Enhancement Epic | Build | E-485499 | E-485499 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-21 | 2025-07-16 | 2025-07-01
Local Enhancement Epic: COM - RMIC - Oracle Inv Reprint for CA EDI Accts | Approved | Local Enhancement Epic | Commercial Portfolio | 0106438 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556007 | E-556007 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dynamic Pickup to schedule on-demand pickups | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106463 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: {Enabler] MEISA - Simplifying WREG Account Opening | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106488 | 7643 | [Enabler] MEISA - Simplifying WREG Account Opening | Biz w/ Tech Epic | Assessment & Analysis | E-500336 | E-500336 | 4: L |  |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: Dynamic Pickup with visibility | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106497 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - SOAP API Upgrade Authentication P12 | Closed | Local Enhancement Epic | Commercial Portfolio | 0106513 |  |  | Local Enhancement Epic | Done | E-413746 | E-413746 | 1: XS | 2025-06-26 | 2025-07-14 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-07-14
Local Enhancement Epic: COM - GDX - Humanized Tone:Progress Bar Updates | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106516 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - SK ECIS "Bus Reg Id" Values UME | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106517 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-RD3 - TNT France Legal Text update | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106518 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Automate MI Customer Onboarding | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106524 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Build | E-498960 | E-498960 | 3: M | 2025-07-31 |  |  | 13 | 0 | 8 | 5 | No | 2025-10-08 | 2026-01-15 | 2025-07-31
Biz w/ Tech Epic: REX83 Intervention Surcharges | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106526 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Backlog | E-521082 | E-521082 | 3: M |  |  |  | 3 | 0 |  | 3 | No
Local Enhancement Epic: COM -GDX-Mobile - Humanized Tone - Enhance Err Msg | Approved | Local Enhancement Epic | Commercial Portfolio | 0106632 |  |  | Local Enhancement Epic | Backlog | E-502216 | E-502216 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX- WREG - HOPE 2.0 integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0106633 |  |  | Local Enhancement Epic | Backlog | E-517878 | E-517878 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Lifecycle Management Epic: COM - GDX - MS - Mobile - Remove Branch SDK | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106634 |  |  | Lifecycle Management Epic | Build | E-501872 | E-501872 | 1: XS | 2026-02-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-02-01
Local Enhancement Epic: COM - GDX - TRKC Internal API include addl. fields | Closed | Local Enhancement Epic | Commercial Portfolio | 0106635 |  |  | Local Enhancement Epic | Build | E-512163 | E-512163 | 1: XS | 2025-07-01 |  | 50% | 2 | 1 | 1 | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: COM - GDX - Update CPOF URL in FDSD | Closed | Lifecycle Management Epic | Commercial Portfolio | 0106636 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-501868 | E-501868 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM - GDX - V Bridge Integration ENS- email notif | Approved | Local Enhancement Epic | Commercial Portfolio | 0106637 |  |  | Local Enhancement Epic | Backlog | E-517872 | E-517872 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX - Go-to-Market Promotional Blocks | Approved | Local Enhancement Epic | Commercial Portfolio | 0106638 |  |  | Local Enhancement Epic | Launch & Evaluate | E-517228 | E-517228 | 1: XS | 2025-06-26 |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07 | 2025-06-26
Local Enhancement Epic: COM - GDX - E-468557 - Migrate Login V2 GET Call | Approved | Local Enhancement Epic | Commercial Portfolio | 0106639 |  |  | Local Enhancement Epic | Launch & Evaluate | E-501877 | E-501877 | 2: S | 2025-06-26 |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2025-06-26
Local Enhancement Epic: COM - GDX - PCC API Migration for Mobile | Approved | Local Enhancement Epic | Commercial Portfolio | 0106640 |  |  | Local Enhancement Epic | Backlog | E-501870 | E-501870 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Lifecycle Management Epic: COM - GDX - Gradle update for FedEx Android app | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106641 |  |  | Lifecycle Management Epic | Build | E-501871 | E-501871 | 1: XS | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-13
Local Enhancement Epic: COM - IA - GIX - Richemont/Centiro Fuse update | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106643 |  |  | Local Enhancement Epic | Assessment & Analysis | E-511932 | E-511932 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: CDA Commercial Offering | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106658 | 89068 | Customs Data Automation (CDA) - Europe POC Exp. | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - VN VAT rate change from 8% to 10% | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106665 |  |  | Local Enhancement Epic | Backlog | E-520986 | E-520986 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CSX - Social Media Parity Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0106666 |  |  | Local Enhancement Epic | Backlog | E-524200 | E-524200 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-03-16
Local Enhancement Epic: COM - RMIC - BG 10 Numeric Digits Inv # | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106668 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CIS - Updt Tranltn St.Maarten or St.Martin | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106669 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-517873 | E-517873 | 1: XS | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-06-26
Local Enhancement Epic: COM - RMIC - OPA ODA July 2025 CSR File update | Closed | Local Enhancement Epic | Commercial Portfolio | 0106670 |  |  | Local Enhancement Epic | Done | E-512460 | E-512460 | 1: XS | 2025-06-27 | 2025-09-10 |  | 1 | 0 | 1 | 0 | No |  |  | 2025-06-27 | 2025-09-10
Local Enhancement Epic: COM - RMIC - VAT Rate Chng South Africa 15%-15.5% | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106672 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - Integrate DW sellers into GSO Apps | Approved | Local Enhancement Epic | Commercial Portfolio | 0106712 |  |  | Local Enhancement Epic | Build | E-498778 | E-498778 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-21 | 2025-11-18 | 2025-07-01
Local Enhancement Epic: COM - S&CDE - CRM Sales Modernization | Approved | Local Enhancement Epic | Commercial Portfolio | 0106724 |  |  | Local Enhancement Epic | Build | E-499001 | E-499001 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-21 | 2025-11-18 | 2025-07-01
Local Enhancement Epic: COM-S&CDE-CRM CT Org of the Future Implementation | Closed | Local Enhancement Epic | Commercial Portfolio | 0106725 |  |  | Local Enhancement Epic | Build | E-498753 | E-498753 | 1: XS | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: COM-S&CDE-CRM PI03 CT Apps (non-iSell) Enhancement | Closed | Local Enhancement Epic | Commercial Portfolio | 0106726 |  |  | Local Enhancement Epic | Build | E-498712 | E-498712 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM-S&CDE-CRM PI03 CART Search Enhancements | Closed | Local Enhancement Epic | Commercial Portfolio | 0106727 |  |  | Local Enhancement Epic | Build | E-498767 | E-498767 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM - S&CDE - CORE - CHT Change pricing Option | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106729 |  |  | Local Enhancement Epic | Assessment & Analysis | E-498964 | E-498964 | 1: XS |  |  |  | 1 | 0 | 1 | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM PI03 CT Apps (iSell) Enhancements | Closed | Local Enhancement Epic | Commercial Portfolio | 0106731 |  |  | Local Enhancement Epic | Build | E-498707 | E-498707 | 1: XS | 2025-07-01 |  | 100% | 50 | 50 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM - RMIC - Inc Late Fee % Charge 8% to 9.9% | Approved | Local Enhancement Epic | Commercial Portfolio | 0106733 |  |  | Local Enhancement Epic | Backlog | E-501160 | E-501160 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-GIX-Increase Array Size for ED991DP Programs | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0106734 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Plant Node Removal | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106779 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 2 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106785 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - CRM - FTIP Modernization and Enhance | Approved | Local Enhancement Epic | Commercial Portfolio | 0106801 |  |  | Local Enhancement Epic | Build | E-498916 | E-498916 | 3: M | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - RMIC - Del Area Surch Zip Chgs Jun25 | Completed | Local Enhancement Epic | Commercial Portfolio | 0106802 |  |  | Local Enhancement Epic | Done | E-508841 | E-508841 | 2: S | 2025-06-27 | 2025-07-23 | 100% | 4 | 4 |  | 0 | No |  |  | 2025-06-27 | 2025-07-23
Biz w/ Tech Epic: SSS | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106817 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM-GIX- LCM-Quarterly Critical Patches WLS/Java | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0106846 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - Duplication of shipping account on FDP | Approved | Local Enhancement Epic | Commercial Portfolio | 0106847 |  |  | Local Enhancement Epic | Build | E-504397 | E-504397 | 2: S | 2025-07-01 |  | 50% | 2 | 1 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - S&CDE - CRM SPR Redesign (MyComp) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106848 |  |  | Local Enhancement Epic | Backlog | E-528225 | E-528225 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Paypal Refund Aggregation | Approved | Local Enhancement Epic | Commercial Portfolio | 0106849 |  |  | Local Enhancement Epic | Backlog | E-521003 | E-521003 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-21
Local Enhancement Epic: COM - RMIC - Separ Discount for Disburse Fee Tiers | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106850 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - CAN FBO EFT Email Bank Name | Approved | Local Enhancement Epic | Commercial Portfolio | 0106851 |  |  | Local Enhancement Epic | Build | E-536454 | E-536454 | 2: S | 2025-10-28 |  | 50% | 2 | 1 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-10-28
Local Enhancement Epic: COM - RMIC - Remove Stale Credit Cards | Approved | Local Enhancement Epic | Commercial Portfolio | 0106852 |  |  | Local Enhancement Epic | Backlog | E-521048 | E-521048 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FAST Bill TH Customs Fee | Not Started | Local Enhancement Epic | Commercial Portfolio | 0106853 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - ENS Template text change - FBO EFT | Approved | Local Enhancement Epic | Commercial Portfolio | 0106854 |  |  | Local Enhancement Epic | Build | E-521043 | E-521043 | 1: XS | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-10-23
Local Enhancement Epic: COM - RMIC-RD3 - CREDO HU NAV Reporting Fix - REG | Approved | Local Enhancement Epic | Commercial Portfolio | 0106867 |  |  | Local Enhancement Epic | Build | E-527274 | E-527274 | 1: XS | 2025-06-26 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-06-26
Local Enhancement Epic: COM - GDX - APAC FIT-GEMINI 2.0/(ACCS) - PES | Approved | Local Enhancement Epic | Commercial Portfolio | 0106887 |  |  | Local Enhancement Epic | Build | E-504395 | E-504395 | 4: L | 2026-03-19 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-03-19
Local Enhancement Epic: COM - GDX - FIT Add ENT for import in clearnce act | Approved | Local Enhancement Epic | Commercial Portfolio | 0106889 |  |  | Local Enhancement Epic | Build | E-504393 | E-504393 | 3: M | 2025-08-08 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-08
Local Enhancement Epic: COM - GDX - FIT-Singap-D&T require confirm email | Approved | Local Enhancement Epic | Commercial Portfolio | 0106890 |  |  | Local Enhancement Epic | Build | E-504389 | E-504389 | 3: M | 2025-11-03 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-11-03
Local Enhancement Epic: COM - GDX - FIT Support dynamic text for pre-not | Approved | Local Enhancement Epic | Commercial Portfolio | 0106891 |  |  | Local Enhancement Epic | Build | E-517870 | E-517870 | 2: S | 2025-08-08 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-08
Local Enhancement Epic: COM - GDX - APAC FiT New Reason Code Phs 3 | Approved | Local Enhancement Epic | Commercial Portfolio | 0106892 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528372 | E-528372 | 2: S | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: COM - GDX - FIT D&T - Clearance system feed (AT) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106893 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - APAC FIT Japan DT Pment adjust config | Approved | Local Enhancement Epic | Commercial Portfolio | 0106894 |  |  | Local Enhancement Epic | Backlog | E-504385 | E-504385 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-07-08 | 2025-10-07
Local Enhancement Epic: COM - GDX - Mobile Shipping -Rev PU Drop Off Scrn | Approved | Local Enhancement Epic | Commercial Portfolio | 0106895 |  |  | Local Enhancement Epic | Build | E-503032 | E-503032 | 1: XS | 2025-11-18 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-11-18
Biz w/ Tech Epic: Epic 1 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106918 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Preference Management Solution | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106924 | 7387 | Project Firefly - Enhancing Data Privacy and Reduc | Biz w/ Tech Epic | Backlog | E-532503 | E-532503 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - [AE] Launch HAL & Dropoff Svcs at FASC | Approved | Local Enhancement Epic | Commercial Portfolio | 0106927 |  |  | Local Enhancement Epic | Build | E-530663 | E-530663 | 2: S | 2025-08-07 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-07
Lifecycle Management Epic: COM - GDX - Visibility ART - GitHub Actions & RDSO | Approved | Lifecycle Management Epic | Commercial Portfolio | 0106928 |  |  | Lifecycle Management Epic | Backlog | E-504381 | E-504381 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Lifecycle Management Epic: COM - RS - Dell 7020/7420 model replacements | Closed | Lifecycle Management Epic | Commercial Portfolio | 0106929 |  |  | Lifecycle Management Epic | Done | E-513398 | E-513398 | 2: S | 2025-06-26 | 2025-08-12 | 33.33% | 3 | 1 |  | 2 | No |  |  | 2025-06-26 | 2025-08-12
Biz w/ Tech Epic: Clearance Fees Prepayment & Release to Invoicing | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106930 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Backlog | E-518845 | E-518845 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - GDX - Humanized Tone:Progress Bar updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0106937 |  |  | Local Enhancement Epic | Backlog | E-502741 | E-502741 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: Provides proper flow of invoice data to government | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106947 | 108080 | COM-RMIC-Invoice Delivery Flow | Biz w/ Tech Epic | Build | E-521107 | E-521107 | 3: M | 2025-08-15 |  | 83.33% | 6 | 5 |  | 1 | No | 2025-11-18 | 2026-03-20 | 2025-08-15
Biz w/ Tech Epic: VAT Validation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106989 |  |  | Biz w/ Tech Epic | Backlog | E-517317 | E-517317 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106996 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic1 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106997 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106999 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0107000 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Argentina e-Invoicing Tax Transparency Requirement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107006 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - Notification suppression for case upds | Approved | Local Enhancement Epic | Commercial Portfolio | 0107017 |  |  | Local Enhancement Epic | Build | E-517322 | E-517322 | 1: XS | 2025-11-18 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-11-18
Biz w/ Tech Epic: Epic 1 B (APAC) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107018 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | E-504411 | E-504411 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2026-01-16
Biz w/ Tech Epic: China UEL/ MFA Shipping Control | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107019 | 97381 | China UEL/ MFA Shipping Control | Biz w/ Tech Epic | Build | E-511533 | E-511533 | 2: S | 2025-11-21 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-11-21
Biz w/ Tech Epic: China UEL/ MFA Shipping Control (Duplicated) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107021 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: LAC-Shipfast-Renewal - Mexico Dom T&C | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107038 | 103910 | LAC-Shipfast-Renewal - Mexico Dom T&C | Biz w/ Tech Epic | Backlog | E-508489 | E-508489 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: MPU IVR Automation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107040 | 6840 | Pickup QAT (Enabler for Pickup PFS) | Biz w/ Tech Epic | Assessment & Analysis | E-539539 | E-539539 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CE - Morocco CE Call Center | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0107041 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - TR "TaxExemptFlag" “N” LDP File | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107043 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RMIC-ROPs - CAN D&T CCTR Rebill Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0107051 |  |  | Local Enhancement Epic | Backlog | E-520975 | E-520975 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-10-31
Local Enhancement Epic: COM - GDX - Edt the lngth for name&phne in ShipAPI | Approved | Local Enhancement Epic | Commercial Portfolio | 0107052 |  |  | Local Enhancement Epic | Build | E-525663 | E-525663 | 1: XS | 2025-07-22 |  | 50% | 2 | 1 |  | 1 | No | 2025-07-30 | 2025-10-07 | 2025-07-22
Local Enhancement Epic: COM - IA - DART - MKT Tagging Request -PI03 Demand | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107054 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-05-21 | 2025-07-16
Local Enhancement Epic: COM - RMIC-STC - KR Dunning Print Job Vndr DestChg | Approved | Local Enhancement Epic | Commercial Portfolio | 0107070 |  |  | Local Enhancement Epic | Build | E-512836 | E-512836 | 1: XS | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-13
Local Enhancement Epic: COM - S&CDE - CORE ART - USI Level Up Movements | Approved | Local Enhancement Epic | Commercial Portfolio | 0107088 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528371 | E-528371 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: [MEISA] FDMI SMS to WhatsApp in ME | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107100 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enhancements in MIA for Cust Migration Intl & Dom | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107120 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enhancements in MIA for Cust Migration Intl & Dom | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107122 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enhancements in MIA for Cust Migration Intl & Dom | Assumed Completed | Biz w/ Tech Epic | Commercial Portfolio | 0107123 | 97139 | Enhance MIA for Customer Migration (Intl & Dom) | Biz w/ Tech Epic | Build | E-501901 | E-501901 | 2: S | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: Enhancements for PRIDE to enable Dom Migration | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107125 | 97147 | Enhancements for PRIDE to enable DomesticMigration | Biz w/ Tech Epic | Backlog | E-521083 | E-521083 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-05-28 | 2026-03-19
Biz w/ Tech Epic: Enhancements for DORA for Dom Cust Migration | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107127 | 97134 | Enhancements DORA for Domestic Customer Migration | Biz w/ Tech Epic | Build | E-501890 | E-501890 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-28 | 2026-03-19 | 2025-12-06
Local Enhancement Epic: iView Improvement | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0106378 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SAM Growth Journey | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104689 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EPIC 2 – Proactive Retention Migration | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104690 | 7071 | Proactive Retention (PR) Journey Migration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Case EBS Value Bundle 5 | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0103179 | 8430 | [US] Case EBS Value Bundle 5 | Biz w/ Tech Epic | Backlog | E-512016 | E-512016 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - Updt KR Customer Supt Hotline # | Approved | Local Enhancement Epic | Commercial Portfolio | 0107225 |  |  | Local Enhancement Epic | Backlog | E-521086 | E-521086 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - MS - FIT D&T SMS foreign ph# | Closed | Local Enhancement Epic | Commercial Portfolio | 0107226 |  |  | Local Enhancement Epic | Done | E-517871 | E-517871 | 1: XS | 2025-06-26 | 2025-07-21 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-07-21
Local Enhancement Epic: COM - RMIC-RD3 - Jordan Tax eInving FedEx & TNT | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107227 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CDE-CRMA Data Connector to Data Cloud | Approved | Local Enhancement Epic | Commercial Portfolio | 0107228 |  |  | Local Enhancement Epic | Backlog | E-501081 | E-501081 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Add taxes to Offline Rate Quote | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0104038 | 7034 | Add Taxes to Offline Rate Quotes from Rating EBS R | Biz w/ Tech Epic | Assessment & Analysis | E-516823 | E-516823 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-04-30 | 2026-07-06
Local Enhancement Epic: COM-S&CDE-CDE-Model Attribute Ingestion into DC | Approved | Local Enhancement Epic | Commercial Portfolio | 0107252 |  |  | Local Enhancement Epic | Build | E-501131 | E-501131 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - S&CDE - CDE - Update GPC to all Countries | Approved | Local Enhancement Epic | Commercial Portfolio | 0107254 |  |  | Local Enhancement Epic | Build | E-501105 | E-501105 | 1: XS | 2026-01-14 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-01-14
Local Enhancement Epic: COM - S&CDE - CRM & CORE ARTs - Project LaCrosse | Approved | Local Enhancement Epic | Commercial Portfolio | 0107255 |  |  | Local Enhancement Epic | Build | E-501310 | E-501310 | 2: S | 2025-07-31 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-31
Local Enhancement Epic: COM - S&CDE - CDE - Service Alerts Query Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0107256 |  |  | Local Enhancement Epic | Build | E-501110 | E-501110 | 1: XS | 2025-09-30 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-09-30
Lifecycle Management Epic: COM - IA - CT Compatible Info Website Migration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107257 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-528370 | E-528370 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-11-28 | 2025-06-26
Local Enhancement Epic: COM - RMIC-STC - APAC BFC Changes/Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0107258 |  |  | Local Enhancement Epic | Build | E-533814 | E-533814 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM - RMIC - Retail F1R Standard Overnight Pricing | Approved | Local Enhancement Epic | Commercial Portfolio | 0107259 |  |  | Local Enhancement Epic | Build | E-508836 | E-508836 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - RMIC - Full Stes IXF New Oracle Ent & CN ABS | Approved | Local Enhancement Epic | Commercial Portfolio | 0107268 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542671 | E-542671 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: COM-RS28-Dye Sub in Ecommerce | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103502 | 8335 | Dye Sub Omni-Channel (FXO) | Biz w/ Tech Epic | Build | E-311595 | E-311595 | 2: S | 2025-07-02 |  | 60% | 5 | 3 | 1 | 1 | No | 2025-04-10 | 2026-07-13 | 2025-07-02
Biz w/ Tech Epic: Dye Sub Visualization (E-332637) | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0103686 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dye Sub in Ecommerce MMP - ECVS (E-311605) | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0103570 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-FREV - FXF Account Selection Accuracy | On Hold | Local Enhancement Epic | Commercial Portfolio | 0107281 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: COM - GDX - Shipment Label change/update for FR | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107284 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic A: Discount & Rating Data | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105512 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Build | E-383457 | E-383457 | 4: L | 2025-07-01 |  | 90.91% | 22 | 20 | 1 | 1 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Epic B: Pickup Data Access | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105517 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Build | E-397076 | E-397076 | 5: XL | 2025-09-27 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-27
Biz w/ Tech Epic: Epic C: Rating Calculation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105519 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Build | E-397084 | E-397084 | 5: XL | 2025-09-27 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-09-27
Biz w/ Tech Epic: Epic D: Invoicing, Accnting, Settlement, Reporting | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105522 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Build | E-407290 | E-407290 | 4: L | 2025-07-01 |  | 84% | 25 | 21 | 1 | 3 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Epic E: Saturday Expedited Processing Fee | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105523 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Backlog | E-407295 | E-407295 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Epic F: Pickup Notifications MVP | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105789 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Assessment & Analysis | E-497749 | E-497749 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-09-22 | 2025-12-30
Local Enhancement Epic: COM - S&CDE - CRM - Customer Referral Program | Closed | Local Enhancement Epic | Commercial Portfolio | 0107305 |  |  | Local Enhancement Epic | Build | E-499837 | E-499837 | 2: S | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: COM-GIX-Transcom Custom Mapping Change | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0107306 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-511944 | E-511944 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-GIX-Retire IBM I-Legacy | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0107307 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - GRIT Production Support (GRI Tool) | Approved | Local Enhancement Epic | Commercial Portfolio | 0107308 |  |  | Local Enhancement Epic | Backlog | E-521092 | E-521092 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Global GRI Tool for Enhancements only | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107309 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Update Bundling Logic Cut Off Time | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107310 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - FDP - Show Custom Order Form | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107311 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - Ground Scan 95 Display On FedEx.com | Approved | Local Enhancement Epic | Commercial Portfolio | 0107312 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546452 | E-546452 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - Vis ART - CY25PI03 System Optimization | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107313 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-517568 | E-517568 | 2: S | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: COM-RS28-POD Commercial Stabilization (KPIs) | Approved | Local Enhancement Epic | Commercial Portfolio | 0107314 |  |  | Local Enhancement Epic | Build | E-507143 | E-507143 | 2: S | 2025-07-01 |  |  | 2 | 0 | 1 | 1 | No | 2025-12-01 | 2026-04-15 | 2025-07-01
Local Enhancement Epic: COM-RS28-Shipping accounts for logged in users | Closed | Local Enhancement Epic | Commercial Portfolio | 0107315 |  |  | Local Enhancement Epic | Build | E-514075 | E-514075 | 1: XS | 2025-08-06 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-08-06
Local Enhancement Epic: COM - GDX - Updt CSHP Hard Coded Vague Descrp List | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107316 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - AHS Wght Threshold Chge-FXE Intl | Closed | Local Enhancement Epic | Commercial Portfolio | 0107317 |  |  | Local Enhancement Epic | Done | E-512798 | E-512798 | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: COM - CSX - Enable ECSH Retire-Enterprise Claims | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107319 |  |  | Local Enhancement Epic | Backlog | E-521052 | E-521052 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - RetalShip Extra Shpmt Creation Fields | Closed | Local Enhancement Epic | Commercial Portfolio | 0107320 |  |  | Local Enhancement Epic | Build | E-514072 | E-514072 | 1: XS | 2025-08-04 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-04
Local Enhancement Epic: COM - RMIC - US FAST Bill Product Code Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0107321 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578399 | E-578399 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - US Tariff Disbursement Fee Changes | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107322 |  |  | Local Enhancement Epic | Build | E-486174 | E-486174 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM - IA - GIX - Lexmark 940 Msg - Ship To Telphn# | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107323 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM-S&CDE -CDE -Testing and Configuration CY25 PI3 | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0107366 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CE PI-03 LCM Meet ProbRes ProtectPurp Rqmts | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107378 |  |  | Lifecycle Management Epic | Backlog | E-515113 | E-515113 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Implement GDL for fedex.com | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107385 | 98435 | Digital-Enablers-Data collection & Analytics tool | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2026-09-30
Biz w/ Tech Epic: WA Capabilities for CE | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107386 | 106755 | Whatsapp and Direct messaging channels for CE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 OTB : Parcel Non-conveyable & Limited Quantity | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105118 | 94177 | OTB : Parcel Non-conveyable & Limited Quantity | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM-RS28-Customer Delivery Share to NFC | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107434 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Backlog | E-386605 | E-386605 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-08-12 | 2026-10-20
Biz w/ Tech Epic: COM-RS28-FUSE Order Mod-Non-Price Impacting | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107438 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-455101 | E-455101 | 3: M | 2025-08-28 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-08-28
Biz w/ Tech Epic: FUSE Order Modification - Price Impacting | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107439 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-337122 | E-337122 | 5: XL | 2025-08-28 |  | 50% | 6 | 3 | 2 | 1 | No | 2025-11-05 | 2026-10-20 | 2025-08-28
Biz w/ Tech Epic: COM-RS28-FUSE Prepay/Cust Deposit | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107440 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Backlog | E-446023 | E-446023 | 4: L |  |  |  | 2 | 0 |  | 2 | No | 2026-03-25 | 2026-10-20
Biz w/ Tech Epic: CMAR/Till Audit - FUSE Reporting | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107441 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-432662 | E-432662 | 4: L | 2025-08-28 |  | 100% | 4 | 4 |  | 0 | No | 2025-04-09 | 2025-09-30 | 2025-08-28
Biz w/ Tech Epic: COM-RS28-Audit Journal | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107442 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-432664 | E-432664 | 4: L | 2025-08-28 |  |  | 3 | 0 | 2 | 1 | No | 2025-06-02 | 2026-10-20 | 2025-08-28
Biz w/ Tech Epic: Bidding | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107443 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-371988 | E-371988 | 5: XL | 2025-08-28 |  | 60% | 5 | 3 |  | 2 | No | 2025-06-16 | 2026-03-24 | 2025-08-28
Biz w/ Tech Epic: COM-RS28-Product Expansion-resolve existing Gaps | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107444 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-245174 | E-245174 | 3: M | 2025-08-28 |  | 44.44% | 9 | 4 | 4 | 1 | No | 2025-07-16 | 2026-10-20 | 2025-08-28
Biz w/ Tech Epic: FUSE Mobile Phase 1 | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107445 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Backlog | E-535791 | E-535791 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FUSE Mobile ph 2: | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107446 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-432919 | E-432919 | 4: L | 2025-08-28 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-08-28
Biz w/ Tech Epic: COM-RS28-FUSE Mobile ph 3: | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107447 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-512853 | E-512853 | 4: L | 2025-08-27 |  | 66.67% | 6 | 4 | 2 | 0 | No | 2025-08-27 | 2026-10-20 | 2025-08-27
Biz w/ Tech Epic: Sell MDSE using Ship Account: | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107448 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-439898 | E-439898 | 4: L | 2025-08-28 |  | 100% | 2 | 2 |  | 0 | No | 2025-10-10 | 2026-03-24 | 2025-08-28
Biz w/ Tech Epic: COM-RS28-PR Origin | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107449 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-417953 | E-417953 | 4: L | 2025-08-28 |  | 33.33% | 3 | 1 | 2 | 0 | No | 2026-03-25 | 2026-10-20 | 2025-08-28
Biz w/ Tech Epic: Ship with non US Account- currency symbol: | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107450 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-450394 | E-450394 | 2: S | 2025-08-28 |  | 100% | 7 | 7 |  | 0 | No |  |  | 2025-08-28
Biz w/ Tech Epic: Express Locations in ORC | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107451 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-502136 | E-502136 | 3: M | 2025-08-12 |  | 100% | 1 | 1 |  | 0 | No | 2025-08-27 | 2026-03-24 | 2025-08-12
Biz w/ Tech Epic: End-to-end Enterprise Automation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107508 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM-S&CDE-CDE -Testing and Configuration CY25 PI3 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107530 |  |  | Lifecycle Management Epic | Build | E-501721 | E-501721 | 1: XS | 2025-07-01 |  | 50% | 2 | 1 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - RMIC - Enable EPA for Cambodia (KH) | Approved | Local Enhancement Epic | Commercial Portfolio | 0107559 |  |  | Local Enhancement Epic | Build | E-536381 | E-536381 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Change VAT Trtmnt for RO & Ch Islands | Approved | Local Enhancement Epic | Commercial Portfolio | 0107563 |  |  | Local Enhancement Epic | Build | E-547729 | E-547729 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Build Dom FXE and FXG Cubic Pricing | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107564 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Supplies Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0107568 |  |  | Local Enhancement Epic | Backlog | E-514979 | E-514979 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FUSE Identifiable Customer Data Encryption | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107569 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CSX - US/CA IVR NLU Changes PIO3 | Approved | Local Enhancement Epic | Commercial Portfolio | 0107570 |  |  | Local Enhancement Epic | Backlog | E-537194 | E-537194 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX - US/CA IVR Infrastructure Changes | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107571 |  |  | Lifecycle Management Epic | Backlog | E-521050 | E-521050 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-GIX-Product Support for ART | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107572 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-512934 | E-512934 | 1: XS | 2025-06-26 |  |  | 1 | 0 |  | 1 | No |  |  | 2025-06-26
Local Enhancement Epic: FUSE Identifiable Customer Data Encryption | Approved | Local Enhancement Epic | Commercial Portfolio | 0107573 |  |  | Local Enhancement Epic | Build | E-521000 | E-521000 | 2: S | 2025-07-08 |  |  | 2 | 0 | 2 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-08
Local Enhancement Epic: Quote Platform External API integration | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107602 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Quote Platform API expansion to 3rd Party Platform | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107603 | 9176 | Global Spot Modernization | Local Enhancement Epic | Assessment & Analysis | E-512468 | E-512468 |  |  |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: GC3 Customer Experience Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107614 | 96542 | GC3 Customer Experience Enhancements | Biz w/ Tech Epic | Assessment & Analysis | E-515449 | E-515449 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2028-06-09
Lifecycle Management Epic: COM - GDX - MS - CY25 PI3 FiT App perf enh | Closed | Lifecycle Management Epic | Commercial Portfolio | 0107655 |  |  | Lifecycle Management Epic | Done | E-528369 | E-528369 | 1: XS | 2025-06-26 | 2025-08-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-08-26
Local Enhancement Epic: COM - RMIC-FREV - CBSA Total Weight Requirement | Approved | Local Enhancement Epic | Commercial Portfolio | 0107665 |  |  | Local Enhancement Epic | Backlog | E-521089 | E-521089 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-09
Lifecycle Management Epic: COM-GIX-ECPMO evidence | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107676 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-512796 | E-512796 | 1: XS | 2025-06-26 |  |  | 1 | 0 |  | 1 | No |  |  | 2025-06-26
Local Enhancement Epic: COM - GDX - MS-EU Retl - SE RTH enh: Add Instabox | Closed | Local Enhancement Epic | Commercial Portfolio | 0107696 |  |  | Local Enhancement Epic | Backlog | E-521101 | E-521101 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-EU Retl - SE RTH enh:fbck loop tool | Approved | Local Enhancement Epic | Commercial Portfolio | 0107697 |  |  | Local Enhancement Epic | Backlog | E-521102 | E-521102 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: Disbursement Fee increase from PHP105 to PHP300 | Completed | Biz w/ Tech Epic | Commercial Portfolio | 0107724 | 91210 | EMR OTC-[APAC] SG/PH Ancillary Charges Review | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - IBM Entry Summ (7501) EDI Flr COM-GIX | Approved | Local Enhancement Epic | Commercial Portfolio | 0107732 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546663 | E-546663 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Lifecycle Management Epic: COM - IA - GIX - CSV Select Solution Retirement | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107736 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-513674 | E-513674 | 3: M | 2025-06-26 |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2025-06-26
Local Enhancement Epic: COM - RMIC-RD3 - ANZ Bank File PUP Template | Approved | Local Enhancement Epic | Commercial Portfolio | 0107737 |  |  | Local Enhancement Epic | Backlog | E-521097 | E-521097 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-STC - PHVAT Xl file format & OR chg/upd | Approved | Local Enhancement Epic | Commercial Portfolio | 0107738 |  |  | Local Enhancement Epic | Build | E-532359 | E-532359 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM-S&CDE-CRM PI03 CART Oracle/Ab Initio Upgrades | Closed | Local Enhancement Epic | Commercial Portfolio | 0107739 |  |  | Local Enhancement Epic | Build | E-498769 | E-498769 | 1: XS | 2025-07-01 |  | 100% | 50 | 50 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM-S&CDE-CRM PI03 Knowledge Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0107740 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528368 | E-528368 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: COM - RMIC - GRIT Surcharge Update Int'l Zones | Approved | Local Enhancement Epic | Commercial Portfolio | 0107741 |  |  | Local Enhancement Epic | Backlog | E-521091 | E-521091 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - GRIT Add Zone All Surcharge Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0107742 |  |  | Local Enhancement Epic | Build | E-521090 | E-521090 | 1: XS | 2025-10-07 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-10-07
Biz w/ Tech Epic: Gov't Smart Pay (Card Swipe) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107805 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Backlog | E-446016 | E-446016 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-06-18 | 2026-08-11
Biz w/ Tech Epic: FUSE Account Acceptance, Order Entry-Adding an LTE | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0107810 | 90113 | Single Point of Sale Completion | Biz w/ Tech Epic | Build | E-287712 | E-287712 | 3: M | 2025-08-28 |  | 100% | 6 | 6 |  | 0 | No |  |  | 2025-08-28
Local Enhancement Epic: COM - RMIC - New FASTBill Products for APAC | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107812 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - Upd SRID (OD) notif trigge rules | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107816 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - GRM to Supply Non-Bill Chgs & Net Amt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107817 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Reg FDS Changes for FASTBill Inv | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107819 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - METL Webhooks Decom | Approved | Local Enhancement Epic | Commercial Portfolio | 0107821 |  |  | Local Enhancement Epic | Backlog | E-520991 | E-520991 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CRM PI03 S3 Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0107823 |  |  | Local Enhancement Epic | Launch & Evaluate | E-498975 | E-498975 | 1: XS | 2025-07-16 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-16
Local Enhancement Epic: COM - CSX - Bus Rule Engine Enhancements for ECD | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107830 |  |  | Local Enhancement Epic | Backlog | E-521103 | E-521103 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - Home Depot EDI 820 4060 | Approved | Local Enhancement Epic | Commercial Portfolio | 0107832 |  |  | Local Enhancement Epic | Backlog | E-521046 | E-521046 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Biz w/ Tech Epic: Shipment /Order Creation - Magic/FDX | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0105876 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-485663 | E-485663 | 5: XL |  |  |  | 2 | 0 | 1 | 1 | No | 2026-07-30 | 2026-07-31
Local Enhancement Epic: COM-RS28-FXO Customer 360 (Accounts & Users) | Approved | Local Enhancement Epic | Commercial Portfolio | 0107844 |  |  | Local Enhancement Epic | Build | E-407943 | E-407943 | 2: S | 2025-07-16 |  | 57.14% | 7 | 4 | 3 | 0 | No | 2025-06-18 | 2026-08-28 | 2025-07-16
Local Enhancement Epic: COM RS Int 3P Direct Mail Prtn Taradel MP (VALUE) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107847 |  |  | Local Enhancement Epic | Backlog | E-514069 | E-514069 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RMIC - Germ Change Vatabaility of Prepmt Fee | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107848 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Generation of 13 Software IDs | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107850 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - REV - LAC-ARG e-Inv Reg Chngs 4/2025 | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107852 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - VN VAT Imposition VN Inbound Freight | Approved | Local Enhancement Epic | Commercial Portfolio | 0107853 |  |  | Local Enhancement Epic | Build | E-521093 | E-521093 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2025-06-25 | 2025-12-06
Local Enhancement Epic: COM - RMIC - ePRS Rate Vis Enhancements | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107854 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Cust Impact Analyzer (CIA) Redesign | Rejected | Local Enhancement Epic | Commercial Portfolio | 0107855 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - UME File Modification fo GRCC Control | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107856 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - UME File Provide Mailing Addr Sol | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107857 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - NSMC_IRC_InterfaceEnhance | Approved | Local Enhancement Epic | Commercial Portfolio | 0107858 |  |  | Local Enhancement Epic | Build | E-522919 | E-522919 | 1: XS | 2025-07-22 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-22
Local Enhancement Epic: COM - VIS - EDD Notifications Suppression | Approved | Local Enhancement Epic | Commercial Portfolio | 0105338 |  |  | Local Enhancement Epic | Build | E-520990 | E-520990 | 1: XS | 2025-10-30 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-10-30
Local Enhancement Epic: COM - MS - LAC WREG MX Credit Card | Approved | Local Enhancement Epic | Commercial Portfolio | 0105339 |  |  | Local Enhancement Epic | Build | E-483392 | E-483392 | 2: S | 2026-03-03 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-12-30 | 2026-03-03
Local Enhancement Epic: COM - CS - FedEx Integration Client | Approved | Local Enhancement Epic | Commercial Portfolio | 0105342 |  |  | Local Enhancement Epic | Build | E-521045 | E-521045 | 2: S | 2025-07-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2027-10-28 | 2025-07-08
Local Enhancement Epic: CE IVR Enhancement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0105899 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Clearance | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106024 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: MPU IVR Automation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106154 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 3-PAC-JOIN API | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106282 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: API Retirements - FCLA/WFCL/SSO/ADMC3.0 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106370 | 92238 | Global Digital Plat - Simplify & Amplify Login | Biz w/ Tech Epic | Build | E-521084 | E-521084 | 3: M | 2025-09-10 |  | 50% | 12 | 6 | 4 | 2 | No | 2025-09-12 | 2026-06-01 | 2025-09-10
Biz w/ Tech Epic: Data Upload | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106509 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Make changes in ePRS (strategic/embp) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0106512 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Country Rollout EU | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106564 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: MAGIC Collaborative Shipping Development | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106805 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: MAGIC Collaborative Shipping Development | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0106807 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: MAGIC Collaborative Shipping Development | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0106808 | 8303 | RPI Digital Experience Improvement - MAGIC / Notif | Biz w/ Tech Epic | Done | E-529786 | E-529786 | 3: M | 2025-08-26 | 2025-08-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-26 | 2025-08-26
Biz w/ Tech Epic: Bulk Upload of Delivery Preferences | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0107104 | 7836 | Delivery PFS - Commercial Delivery Management Phas | Biz w/ Tech Epic | Build | E-540128 | E-540128 | 5: XL | 2025-10-20 |  |  | 3 | 0 | 2 | 1 | No | 2024-07-22 | 2028-09-04 | 2025-10-20
Biz w/ Tech Epic: MAGIC Collaborative Shipping Development | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0107296 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM- CX - CE Desktop FY25 Value Bundle - Phase B | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103249 | 8129 | [US] CE Desktop FY25 Value Bundle - Phase B | Biz w/ Tech Epic | Assessment & Analysis | E-436484 | E-436484 | 5: XL |  |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-04-23
Biz w/ Tech Epic: BigID Implementation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103396 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AHS Dim MBW - Pricing, Invoicing and Settlement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103980 | 79817 | Minimum Billable Weight for AHS Dim | Biz w/ Tech Epic | Assessment & Analysis | E-462865 | E-462865 | 3: M |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: AHS Dim Minimum Billable Weight package rating | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0103985 | 79817 | Minimum Billable Weight for AHS Dim | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Localize FDP | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0103997 | 7874 | [VIS] Global Integrated Track Data MVP | Biz w/ Tech Epic | Backlog | E-535660 | E-535660 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-12-15 | 2026-02-13
Biz w/ Tech Epic: Localization of FedEx Developer Portal/ Dev | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0104113 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Cookie Consent | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0104542 | 7387 | Project Firefly - Enhancing Data Privacy and Reduc | Biz w/ Tech Epic | Backlog | E-532504 | E-532504 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-02-17 | 2025-04-16
Biz w/ Tech Epic: New | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0104576 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CPT-All Clients of CALC or FCI.jar Import | Approved | Local Enhancement Epic | Commercial Portfolio | 0105323 |  |  | Local Enhancement Epic | Build | E-520989 | E-520989 | 2: S | 2026-02-18 |  |  | 0 | 0 |  | 0 | No |  |  | 2026-02-18
Biz w/ Tech Epic: Epic 2 QP - US Domestic Freight | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105741 | 85719 | QP Spot - Ground and US Domestic Freight | Biz w/ Tech Epic | Assessment & Analysis | E-545766 | E-545766 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-07-01 | 2026-09-30
Biz w/ Tech Epic: MPU Automation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0106783 | 6840 | Pickup QAT (Enabler for Pickup PFS) | Biz w/ Tech Epic | Assessment & Analysis | E-539538 | E-539538 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FedEx Unified Label Experience @ Walgreens | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0103301 | 6765 | [Retail PFS] FedEx Unified Experience Label | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 - FXR FXF Integration | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0103357 | 8704 | My FedEx Rewards 2.0: FedEx Freight Integration (P | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Support EBI App Lev3_JUL25CSR | Approved | Local Enhancement Epic | Commercial Portfolio | 0107865 |  |  | Local Enhancement Epic | Backlog | E-521094 | E-521094 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Publish Copy EC Table EIW/ATLAS | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107866 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - CAPC Rule Creation Fix | Approved | Local Enhancement Epic | Commercial Portfolio | 0107867 |  |  | Local Enhancement Epic | Build | E-521108 | E-521108 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - RMIC-LCM - Offline Rating Java Update | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107869 |  |  | Lifecycle Management Epic | Build | E-459282 | E-459282 | 3: M | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2024-09-02 | 2025-07-31 | 2025-07-01
Local Enhancement Epic: COM - RMIC - Svc & Mkg Msgs US & CA Inv Pdfs | Approved | Local Enhancement Epic | Commercial Portfolio | 0107870 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573107 | E-573107 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RMIC - GRI EU 2026 | Closed | Local Enhancement Epic | Commercial Portfolio | 0107871 |  |  | Local Enhancement Epic | Backlog | E-520940 | E-520940 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RMIC - Pricing Data Updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0107873 |  |  | Local Enhancement Epic | Build | E-513618 | E-513618 | 1: XS | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - RMIC - US-CA Ground Intl Demand Surcharge | Approved | Local Enhancement Epic | Commercial Portfolio | 0107874 |  |  | Local Enhancement Epic | Build | E-513620 | E-513620 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Lifecycle Management Epic: COM - GDX - NOTF - LCM-CY25 PI3-Spprt & Serv Now | Closed | Lifecycle Management Epic | Commercial Portfolio | 0107885 |  |  | Lifecycle Management Epic | Done | E-517536 | E-517536 | 1: XS | 2025-06-26 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-09-10
Lifecycle Management Epic: COM - GDX - NOTF - LCM-CY25PI3-NDS Support Modrn | Approved | Lifecycle Management Epic | Commercial Portfolio | 0107887 |  |  | Lifecycle Management Epic | Build | E-517610 | E-517610 | 1: XS | 2025-08-08 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-08
Local Enhancement Epic: COM - IA - GIX - Medtronic Multi-Phase | Approved | Local Enhancement Epic | Commercial Portfolio | 0107906 |  |  | Local Enhancement Epic | Backlog | E-520996 | E-520996 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - IA - GIX - Genesco | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107907 |  |  | Local Enhancement Epic | Backlog | E-520995 | E-520995 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - Bass Pro | Approved | Local Enhancement Epic | Commercial Portfolio | 0107908 |  |  | Local Enhancement Epic | Backlog | E-520994 | E-520994 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - IA - GIX - NFI Industries | Approved | Local Enhancement Epic | Commercial Portfolio | 0107909 |  |  | Local Enhancement Epic | Backlog | E-520997 | E-520997 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - IA - GIX - AMAZON.COM FC / DF | Approved | Local Enhancement Epic | Commercial Portfolio | 0107910 |  |  | Local Enhancement Epic | Backlog | E-520993 | E-520993 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - IA - GIX - Victor Multi-Service | Approved | Local Enhancement Epic | Commercial Portfolio | 0107911 |  |  | Local Enhancement Epic | Backlog | E-520998 | E-520998 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - IA - GIX - DART 2.0 User Interface Dev | Approved | Local Enhancement Epic | Commercial Portfolio | 0107912 |  |  | Local Enhancement Epic | Backlog | E-513713 | E-513713 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM - RMIC - GSP Value Proposition Expansion | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107936 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - ODS Labor Management Module | Approved | Local Enhancement Epic | Commercial Portfolio | 0107945 |  |  | Local Enhancement Epic | Build | E-514081 | E-514081 | 1: XS | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-11-05 | 2026-01-13 | 2025-12-08
Local Enhancement Epic: COM - CSX - ECRD Assignment by Spec Acct for Clms | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107963 |  |  | Local Enhancement Epic | Backlog | E-521104 | E-521104 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-Log-ForgeRock-Session-Cookie | Not Started | Local Enhancement Epic | Commercial Portfolio | 0107966 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - FiT DocUpload templates changes | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107965 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - FedEx Rpting: GSP Report Enhancement | Closed | Local Enhancement Epic | Commercial Portfolio | 0107968 |  |  | Local Enhancement Epic | Backlog | E-530664 | E-530664 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM - GDX - CS - FSMS - Validate on Rate & Rte Req | Completed | Local Enhancement Epic | Commercial Portfolio | 0107967 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - FedEx Rpting: Shipper Smmry Enhncmnt | Closed | Local Enhancement Epic | Commercial Portfolio | 0107970 |  |  | Local Enhancement Epic | Backlog | E-530662 | E-530662 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - FIT DT Bnk xfer dets & recpt upl | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107969 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - E-inv Vol Rpt FIT DT Rpting | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107971 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - Drop off customer receipt | Closed | Local Enhancement Epic | Commercial Portfolio | 0107972 |  |  | Local Enhancement Epic | Build | E-517880 | E-517880 | 1: XS | 2025-10-30 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-30
Local Enhancement Epic: COM - GDX - MS - FedEx Rpting: Prefm Implmntn | Completed | Local Enhancement Epic | Commercial Portfolio | 0107973 |  |  | Local Enhancement Epic | Build | E-530667 | E-530667 | 2: S | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-23
Biz w/ Tech Epic: DG Road Solution allow full TNT volume migration | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0107990 | 9372 | Enable a scalable FedEx DG road offering allowing | Biz w/ Tech Epic | Assessment & Analysis | E-212823 | E-212823 | 5: XL | 2025-07-02 |  | 75% | 20 | 15 | 3 | 2 | No | 2025-06-18 | 2025-11-04 | 2025-07-02
Local Enhancement Epic: COM - GDX - CS - DSS - LE - Customer Email Prompt | Approved | Local Enhancement Epic | Commercial Portfolio | 0108026 |  |  | Local Enhancement Epic | Build | E-521214 | E-521214 | 2: S | 2025-07-08 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2027-12-06 | 2025-07-08
Local Enhancement Epic: COM - RMIC - GRI APAC 2026 | Approved | Local Enhancement Epic | Commercial Portfolio | 0108027 |  |  | Local Enhancement Epic | Backlog | E-521109 | E-521109 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: EU After First Shipment (Relay 42) - DC Implement | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108072 | 106340 | COM - S&CDE - CDE ART - Relay42 Migration to Azure | Biz w/ Tech Epic | Backlog | E-520972 | E-520972 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Quote Retargeting (Relay 42) - DC Implementation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108073 | 106340 | COM - S&CDE - CDE ART - Relay42 Migration to Azure | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EU Onboarding Activation (Relay 42) - DC Implemen | Assumed Completed | Biz w/ Tech Epic | Commercial Portfolio | 0108074 | 106340 | COM - S&CDE - CDE ART - Relay42 Migration to Azure | Biz w/ Tech Epic | Launch & Evaluate | E-501137 | E-501137 | 1: XS | 2025-06-27 |  |  | 3 | 0 | 3 | 0 | No |  |  | 2025-06-27
Biz w/ Tech Epic: Build Data Product for Relay42 Use Cases Migration | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108076 | 106340 | COM - S&CDE - CDE ART - Relay42 Migration to Azure | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: eClaims Canada rollout | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108080 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims - tech Debt | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108086 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims - GDL tagging | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108087 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims App config | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108089 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims - FAQ/Help Feature Rollover | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108090 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims -API error handling | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108091 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims Address Validation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108092 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims - UI error messaging | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108093 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims Mobile view Responsive | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108094 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims Application Config & Dynatrace Implement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108095 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims GDL tagging - PI02 Rollover | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108096 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims Canada release roll over | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108097 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-515040 | E-515040 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims - Tech Debt - PI02 Rollover | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108098 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims FAQ/Help Feature - PI02 Rollover | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108099 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CE IT PI-03 LCM Manage ProbRes Cert Updates | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108136 |  |  | Lifecycle Management Epic | Backlog | E-515178 | E-515178 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - PI03 CAMP Software Upgrade | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0108138 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - EU E-com Retail Expnsn CZ&Baltics | Approved | Local Enhancement Epic | Commercial Portfolio | 0108139 |  |  | Local Enhancement Epic | Backlog | E-521042 | E-521042 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - EU Countries Duty Tax Invoice Break | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108140 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Actvt Ancillary Chrg Code Israel | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108141 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Dim Rounding Logic Changes (Ground) | Closed | Local Enhancement Epic | Commercial Portfolio | 0108142 |  |  | Local Enhancement Epic | Build | E-521114 | E-521114 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Lifecycle Management Epic: COM - CSX - CE IT PI03 LCM Estb ProbRes RaSS Team | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108143 |  |  | Lifecycle Management Epic | Backlog | E-515182 | E-515182 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX - CEIT PI03 LCM Estb Azure Migra Rdmp | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108144 |  |  | Lifecycle Management Epic | Backlog | E-515142 | E-515142 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX - CEIT PI03 LCM Adrs ProbRes Vulner | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108145 |  |  | Lifecycle Management Epic | Backlog | E-515151 | E-515151 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-05-30 | 2026-01-13
Lifecycle Management Epic: COM - CSX-CEIT PI03LCM Prvd ProdMaint & Firewl Sup | Completed | Lifecycle Management Epic | Commercial Portfolio | 0108147 |  |  | Lifecycle Management Epic | Backlog | E-515174 | E-515174 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - CEIT PI03 LCM Create ProbRes Test Arch | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108148 |  |  | Lifecycle Management Epic | Backlog | E-515126 | E-515126 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX-CEIT PI03 LCM Implmnt ProbRes DevSecOps | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108149 |  |  | Lifecycle Management Epic | Backlog | E-515159 | E-515159 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX-CEIT PI03LCM Implmnt ProbRes Infra Upgds | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108150 |  |  | Lifecycle Management Epic | Backlog | E-515163 | E-515163 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX-CEIT PI03 LCM Bld Knwldg Across RaSS Tms | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108151 |  |  | Lifecycle Management Epic | Backlog | E-515170 | E-515170 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-05-30 | 2025-10-21
Lifecycle Management Epic: COM - CSX-CEITPI03LCM MatureProbRes Pega Sys Infra | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108152 |  |  | Lifecycle Management Epic | Backlog | E-515133 | E-515133 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX - CEIT PI03 LCM Cmplt ProbRes RegresTst | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108155 |  |  | Lifecycle Management Epic | Backlog | E-515121 | E-515121 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX-CEIT PI03LCM Cmplt ProbRes New Feat Test | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108156 |  |  | Lifecycle Management Epic | Backlog | E-515117 | E-515117 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RS - DME PI03 LCM Security & RELY NFR's | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108157 |  |  | Lifecycle Management Epic | Done | E-515798 | E-515798 | 3: M | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Lifecycle Management Epic: COM - RS - DME FY26 LCM Production Support | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0108158 |  |  | Lifecycle Management Epic | Done | E-514194 | E-514194 | 2: S | 2025-06-26 | 2025-06-26 |  | 2 | 0 | 2 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-06-26 | 2025-06-26
Local Enhancement Epic: RDAT/ Retailship Mass Upload | Approved | Local Enhancement Epic | Commercial Portfolio | 0108165 |  |  | Local Enhancement Epic | Build | E-514094 | E-514094 | 2: S | 2025-08-04 |  |  | 2 | 0 | 1 | 1 | No | 2023-12-06 | 2026-05-29 | 2025-08-04
Lifecycle Management Epic: COM - IA - CIS - Stratus FedEx APIs Migration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108169 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-553077 | E-553077 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-09-30
Local Enhancement Epic: COM - GDX - CP - FY26 PCC Shipping & Utilities: LE | Approved | Local Enhancement Epic | Commercial Portfolio | 0108181 |  |  | Local Enhancement Epic | Build | E-526459 | E-526459 | 2: S | 2025-07-24 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-24
Local Enhancement Epic: COM - GDX - CP - FY26 PCC FOS Team: LE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108182 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - FY26 PCC FOS TRAM: LE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108183 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Modify eMBP | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108185 | 96463 | FXF Earned Discount Decouple from Parcel | Biz w/ Tech Epic | Assessment & Analysis | E-554858 | E-554858 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - DART - CY25PI03 System Optimization | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0108188 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RS - Print FY26 LCM Production Support | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0108190 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-514191 | E-514191 | 3: M | 2025-06-26 |  |  | 7 | 0 | 7 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-06-26
Lifecycle Management Epic: COM - RS - Print PI03 LCM Security & RELY NFR's | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108191 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-515800 | E-515800 | 3: M | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26
Lifecycle Management Epic: COM - RS - Ship FY26 LCM Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108192 |  |  | Lifecycle Management Epic | Build | E-514192 | E-514192 | 3: M | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-07-01
Local Enhancement Epic: COM - RMIC - South Africa VAT 15.5 reversal to 15p | Closed | Local Enhancement Epic | Commercial Portfolio | 0108196 |  |  | Local Enhancement Epic | Backlog | E-521002 | E-521002 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS- Move EULA to AEM | Approved | Local Enhancement Epic | Commercial Portfolio | 0108198 |  |  | Local Enhancement Epic | Backlog | E-520965 | E-520965 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - New RCCE Crtl Supplement Existg Ctrl | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108199 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - New ROD Invoice (Canada) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108200 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - FBO IN Payment - BillDesk Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0108201 |  |  | Local Enhancement Epic | Build | E-520941 | E-520941 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Lmt Rblls Self-Srv Apps&Ovrrds ERA | Approved | Local Enhancement Epic | Commercial Portfolio | 0108202 |  |  | Local Enhancement Epic | Backlog | E-529785 | E-529785 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RS - RET - FY26 LCM Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108208 |  |  | Lifecycle Management Epic | Build | E-514195 | E-514195 | 3: M | 2025-08-20 |  | 33.33% | 3 | 1 | 2 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-08-20
Lifecycle Management Epic: COM - RS - Rtrns PI03 LCM Patching Maint&Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108209 |  |  | Lifecycle Management Epic | Done | E-515814 | E-515814 | 2: S | 2025-08-26 | 2025-08-29 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-26 | 2025-08-29
Biz w/ Tech Epic: EDM Storage Build | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0108220 | 8161 | Modernized FMCSA Imaging / Database | Biz w/ Tech Epic | Assessment & Analysis | E-518876 | E-518876 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RS - Returns PI03 LCM Security & RELY NFR's | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108234 |  |  | Lifecycle Management Epic | Done | E-515805 | E-515805 | 2: S | 2025-08-12 | 2025-08-28 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-12 | 2025-08-28
Lifecycle Management Epic: COM - RS - SASS FY26 LCM Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108235 |  |  | Lifecycle Management Epic | Build | E-514193 | E-514193 | 3: M | 2025-09-25 |  |  | 3 | 0 | 3 | 0 | No | 2025-06-18 | 2025-12-30 | 2025-09-25
Lifecycle Management Epic: COM - RS - SASS PI03 LCM Patching Maint & Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108236 |  |  | Lifecycle Management Epic | Build | E-515817 | E-515817 | 2: S | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-25
Lifecycle Management Epic: COM - RS - SASS PI03 LCM Security & RELY NFR | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108238 |  |  | Lifecycle Management Epic | Build | E-515802 | E-515802 | 2: S | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-25
Lifecycle Management Epic: COM - GDX - CY25PI.03 Offline Perf Tstng/TstngSup | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108244 |  |  | Lifecycle Management Epic | Done | E-517864 | E-517864 | 5: XL | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Lifecycle Management Epic: COM - GDX - CS - CY25PI.03 FACTOR Sppt DSS ART | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108245 |  |  | Lifecycle Management Epic | Done | E-517868 | E-517868 | 2: S | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Local Enhancement Epic: COM - GDX - MS - Joint Rgstrtn Design Carryover | Approved | Local Enhancement Epic | Commercial Portfolio | 0108246 |  |  | Local Enhancement Epic | Build | E-517602 | E-517602 | 1: XS | 2025-07-21 |  | 100% | 1 | 1 |  | 0 | No | 2024-03-20 | 2024-07-22 | 2025-07-21
Local Enhancement Epic: COM - GDX - MS - Auth Guest Mltpl Contact Carryov | Closed | Local Enhancement Epic | Commercial Portfolio | 0108247 |  |  | Local Enhancement Epic | Build | E-517583 | E-517583 | 1: XS | 2025-09-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-02
Local Enhancement Epic: COM - GDX - MS - Add to Calendar | Closed | Local Enhancement Epic | Commercial Portfolio | 0108248 |  |  | Local Enhancement Epic | Backlog | E-520971 | E-520971 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - Home Scrn Trcking Tile Enhncment | Closed | Local Enhancement Epic | Commercial Portfolio | 0108249 |  |  | Local Enhancement Epic | Done | E-517631 | E-517631 | 1: XS | 2025-08-27 | 2025-08-27 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27 | 2025-08-27
Local Enhancement Epic: COM - GDX - MS - Home Screen Pick Up Tile | Approved | Local Enhancement Epic | Commercial Portfolio | 0108250 |  |  | Local Enhancement Epic | Backlog | E-520967 | E-520967 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - MS - Guest Auth Alt Verifications | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108251 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - Del Instr Tile Carryover | Closed | Local Enhancement Epic | Commercial Portfolio | 0108252 |  |  | Local Enhancement Epic | Build | E-520969 | E-520969 | 2: S | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-23
Local Enhancement Epic: COM - GDX - MS - Home Screen Tile Accessibility | Closed | Local Enhancement Epic | Commercial Portfolio | 0108253 |  |  | Local Enhancement Epic | Done | E-517617 | E-517617 | 1: XS | 2025-08-08 | 2025-08-29 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-08 | 2025-08-29
Local Enhancement Epic: COM - GDX - MS - In App Surveys | Approved | Local Enhancement Epic | Commercial Portfolio | 0108254 |  |  | Local Enhancement Epic | Backlog | E-520970 | E-520970 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RET - Retailship- Webservices to API Mig | Approved | Local Enhancement Epic | Commercial Portfolio | 0108261 |  |  | Local Enhancement Epic | Build | E-515460 | E-515460 | 2: S | 2025-07-09 |  |  | 2 | 0 | 2 | 0 | No | 2025-06-18 | 2026-05-29 | 2025-07-09
Local Enhancement Epic: COM - CSX - Fraud Clms Cases Auto Remediation | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108267 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - US/CA IVR Lifecycle Management PIO3 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108268 |  |  | Lifecycle Management Epic | Backlog | E-537342 | E-537342 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RS - Ship PI03 LCM Security & RELY NFR's | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108270 |  |  | Lifecycle Management Epic | Build | E-515852 | E-515852 | 5: XL | 2025-08-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-26
Local Enhancement Epic: COM - CSX - GoogleAPI 2 AzureAPI-CED Translation | Approved | Local Enhancement Epic | Commercial Portfolio | 0108273 |  |  | Local Enhancement Epic | Backlog | E-517861 | E-517861 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RS - [IN] [OB] Target Amazon’s B2B with API | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108275 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - RPA - Okta Verification Flow Change | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108277 |  |  | Lifecycle Management Epic | Backlog | E-521005 | E-521005 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: COM - CSX - Paper Airway bill Reduction (IT add) | Approved | Local Enhancement Epic | Commercial Portfolio | 0108278 |  |  | Local Enhancement Epic | Backlog | E-524194 | E-524194 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX - NICE RPA Platform 7.9 Migration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108279 |  |  | Lifecycle Management Epic | Backlog | E-521004 | E-521004 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-13 | 2026-01-13
Local Enhancement Epic: COM - CSX - Migrate Cust Technology Dept-CED | Approved | Local Enhancement Epic | Commercial Portfolio | 0108282 |  |  | Local Enhancement Epic | Backlog | E-524198 | E-524198 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Work queue Simplification CEBES | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108315 | 93866 | CEBS Work Queue simplification | Biz w/ Tech Epic | Assessment & Analysis | E-538722 | E-538722 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INTL Ground Collect - Inbound Fee Responsibility | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108318 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RS - Ship PI03 LCM Patching Maint&Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108319 |  |  | Lifecycle Management Epic | Build | E-516224 | E-516224 | 3: M | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: COM - RS - HS Code Lookup Implm Retailship | Closed | Local Enhancement Epic | Commercial Portfolio | 0108320 |  |  | Local Enhancement Epic | Build | E-515466 | E-515466 | 2: S | 2025-08-04 |  | 50% | 2 | 1 | 1 | 0 | No |  |  | 2025-08-04
Lifecycle Management Epic: COM - RS - DME PI03 LCM Patching Maint&Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108321 |  |  | Lifecycle Management Epic | Build | E-516229 | E-516229 | 3: M | 2025-08-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-26
Lifecycle Management Epic: COM - RS - Print PI03 LCM Patching Maint&Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108338 |  |  | Lifecycle Management Epic | Done | E-516228 | E-516228 | 3: M | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Lifecycle Management Epic: COM - S&CDE - CRM - FY26 CRM ART Production&Mx | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108412 |  |  | Lifecycle Management Epic | Build | E-517935 | E-517935 | 1: XS | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - RMIC - Update FBO Alert Message (LAC) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108421 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - IMADE RHEL 8 Migration UAT PI3 CED | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108426 |  |  | Lifecycle Management Epic | Backlog | E-528224 | E-528224 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - MS - New ENS Email: APAC FiT Pre-clrnc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108427 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-Fiery XF Enhmts CAMO Large Format | Approved | Local Enhancement Epic | Commercial Portfolio | 0108429 |  |  | Local Enhancement Epic | Build | E-515480 | E-515480 | 2: S | 2025-07-01 |  | 50% | 2 | 1 |  | 1 | No | 2025-08-28 | 2025-11-04 | 2025-07-01
Local Enhancement Epic: COM - GDX - MS - Fix 'Return to Shipper' Notf Exp | Approved | Local Enhancement Epic | Commercial Portfolio | 0108431 |  |  | Local Enhancement Epic | Backlog | E-527689 | E-527689 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - CP - MvEEI Filing Endpnts 2 Dedctd API | Approved | Local Enhancement Epic | Commercial Portfolio | 0108462 |  |  | Local Enhancement Epic | Build | E-521458 | E-521458 | 2: S | 2025-07-08 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-08
Local Enhancement Epic: COM - GDX - CP - Paid Integrtn prdcts rebranding | Approved | Local Enhancement Epic | Commercial Portfolio | 0108464 |  |  | Local Enhancement Epic | Build | E-519041 | E-519041 | 2: S | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: COM - GDX - MS - Shopify 2 .com affiliate link fix | Approved | Local Enhancement Epic | Commercial Portfolio | 0108466 |  |  | Local Enhancement Epic | Build | E-521075 | E-521075 | 1: XS | 2025-08-08 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-08
Lifecycle Management Epic: COM - IA - GIX - PCF platform update | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108468 |  |  | Lifecycle Management Epic | Done | E-521078 | E-521078 | 1: XS | 2025-07-09 | 2025-07-09 |  | 0 | 0 |  | 0 | No |  |  | 2025-07-09 | 2025-07-09
Lifecycle Management Epic: COM - IA - GIX - PCF platform update | Closed | Lifecycle Management Epic | Commercial Portfolio | 0108469 |  |  | Lifecycle Management Epic | Done | E-518313 | E-518313 | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: COM - RMIC-STC - Update Virtual Bank Acct #-SG/PH | Approved | Local Enhancement Epic | Commercial Portfolio | 0108473 |  |  | Local Enhancement Epic | Build | E-522948 | E-522948 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-08-12 | 2024-10-07 | 2025-12-06
Local Enhancement Epic: COM - S&CDE - Salesforce API Retirement | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108478 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - Chewy Custom EDI 204 | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108479 |  |  | Local Enhancement Epic | Backlog | E-521105 | E-521105 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM FedEx Integrator Meter ID in iSell | Approved | Local Enhancement Epic | Commercial Portfolio | 0108480 |  |  | Local Enhancement Epic | Build | E-500143 | E-500143 | 1: XS | 2025-07-17 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-17
Biz w/ Tech Epic: Ground Rating Modernization: Fraud Intercept | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108502 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Backlog | E-517893 | E-517893 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Bill Type Management | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108517 | 7896 | (Enabler)iSPI upgrade and enhancements | Biz w/ Tech Epic | Backlog | E-518272 | E-518272 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Bill Completion | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108518 | 7896 | (Enabler)iSPI upgrade and enhancements | Biz w/ Tech Epic | Build | E-518269 | E-518269 | 4: L | 2025-07-31 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-31
Biz w/ Tech Epic: Bill Management | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108519 | 7896 | (Enabler)iSPI upgrade and enhancements | Biz w/ Tech Epic | Backlog | E-518278 | E-518278 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: System Management | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108520 | 7896 | (Enabler)iSPI upgrade and enhancements | Biz w/ Tech Epic | Backlog | E-518281 | E-518281 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Zone Jump | Approved | Local Enhancement Epic | Commercial Portfolio | 0108531 |  |  | Local Enhancement Epic | Build | E-540127 | E-540127 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - GDX - CP-Add orgType-Splunk all 3rd pty APIs | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108532 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - Lowes 214 Update | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108546 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - Vldt CntryofManfctr Agnst Cntry | Approved | Local Enhancement Epic | Commercial Portfolio | 0108547 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583026 | E-583026 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - IA - GIX - FORTIFY RETIREMENT | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0108549 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - GDX - MS - FY26_PI4_Mobile_LCM_Platfm_Spprt | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108551 |  |  | Lifecycle Management Epic | Backlog | E-521215 | E-521215 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - GDX - FBO Credit Note (ENS Work) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108552 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Add prcng_geo_dyn_grp Table to EDW | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108553 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - Pty api-Grd Econ[smartpost] | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108554 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - CUPID (Cust Unfd Prsntmnt Invce Data) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108556 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX CSV Map Reengineer | Approved | Local Enhancement Epic | Commercial Portfolio | 0108557 |  |  | Local Enhancement Epic | Backlog | E-521074 | E-521074 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2026-03-10
Lifecycle Management Epic: COM - GDX - MS - FY26_JOIN_WREG_Prod Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108558 |  |  | Lifecycle Management Epic | Backlog | E-521420 | E-521420 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - RMIC - FDF Full ePRS Implementation | Approved | Local Enhancement Epic | Commercial Portfolio | 0108559 |  |  | Local Enhancement Epic | Build | E-524725 | E-524725 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Vldt Chg Cdes for Int'l Expt Prerate | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108560 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - LAC Charge Code Activation | Approved | Local Enhancement Epic | Commercial Portfolio | 0108561 |  |  | Local Enhancement Epic | Build | E-521053 | E-521053 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Split Oracle AR Extracts EU&MEISA | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108562 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - INTL Grnd Collect-Inbnd Procsing Fee | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108563 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - CEIT FY26 Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108566 |  |  | Lifecycle Management Epic | Backlog | E-521040 | E-521040 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-STC - Impl Trm&Cond-PEACE Pymnt Portal | Approved | Local Enhancement Epic | Commercial Portfolio | 0108570 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558945 | E-558945 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-28 | 2026-05-19
Local Enhancement Epic: COM - CSX - Restrict Clms Waiver/Buyout Shipments | Approved | Local Enhancement Epic | Commercial Portfolio | 0108580 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553215 | E-553215 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - CSX - CE - FY26 CED ART_Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108584 |  |  | Lifecycle Management Epic | Backlog | E-521041 | E-521041 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Change Physical Add of the Can Off | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108587 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - FBO Credit Note | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108598 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX -Lowes EDI preplan moves focus | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108615 |  |  | Local Enhancement Epic | Assessment & Analysis | E-521044 | E-521044 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - IA - GIX - FY26_PI04_GIX ART_I&A | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108617 |  |  | Lifecycle Management Epic | Backlog | E-521077 | E-521077 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Lifecycle Management Epic: COM - S&CDE - CRM - iSell Adpt of Cosmos Dsgn Lang | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108618 |  |  | Lifecycle Management Epic | Build | E-517948 | E-517948 | 2: S | 2025-07-16 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-16
Biz w/ Tech Epic: Guided Problem Resolution | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108627 | 113306 | CED B2 - Improving CE Desktop | Biz w/ Tech Epic | Backlog | E-525256 | E-525256 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Biz w/ Tech Epic: Core Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108628 | 113306 | CED B2 - Improving CE Desktop | Biz w/ Tech Epic | Backlog | E-525262 | E-525262 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Biz w/ Tech Epic: Email Migration and Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108629 | 113306 | CED B2 - Improving CE Desktop | Biz w/ Tech Epic | Backlog | E-525254 | E-525254 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Biz w/ Tech Epic: Chat Migration and Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108630 | 113306 | CED B2 - Improving CE Desktop | Biz w/ Tech Epic | Backlog | E-525255 | E-525255 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Local Enhancement Epic: COM - CSX - CE FY26 PCC Rating: Local Enhcmnts | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108634 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Commercial Epic POD 3.1 Claims automation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108654 | 6750 | [EU] Pod 3.1 Simplify and automate the claims proc | Biz w/ Tech Epic | Assessment & Analysis | E-548506 | E-548506 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CMOD - Technical Support - Case closure Survey | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0108657 | 6742 | SU - Issue resolution -Technical support (CMOD) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM-RS28-Shipping Account Management | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0108656 | 92862 | Retail Account Creation and Warnings in FUSE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - GDX - DSS -FY26_COM_DSS ART_Prod Supp (Supp) | Completed | Lifecycle Management Epic | Commercial Portfolio | 0108659 |  |  | Lifecycle Management Epic | Done | E-569019 | E-569019 | 3: M | 2025-06-26 | 2025-06-26 |  | 1 | 0 | 1 | 0 | No |  |  | 2025-06-26 | 2025-06-26
Lifecycle Management Epic: COM - GDX - DSS FY26_COM_DSS Prod Supp(Offline) | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0108660 |  |  | Lifecycle Management Epic | Build | E-575146 | E-575146 | 3: M | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Lifecycle Management Epic: COM - IA - CIS - FY26_PI3_CIS_Upgrd, Maint./Prod | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108669 |  |  | Lifecycle Management Epic | Build | E-519067 | E-519067 | 4: L | 2025-07-18 |  |  | 2 | 0 | 1 | 1 | No | 2025-10-23 | 2025-12-31 | 2025-07-18
Local Enhancement Epic: COM - S&CDE - CDE - iSell Connection to CDP | Approved | Local Enhancement Epic | Commercial Portfolio | 0108670 |  |  | Local Enhancement Epic | Backlog | E-524379 | E-524379 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RS - SHIP AnomalyDimDetection(HCH Buss. Rule | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108675 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - SHIP - FUSE - Upld. to Quote Map Update | Closed | Local Enhancement Epic | Commercial Portfolio | 0108678 |  |  | Local Enhancement Epic | Build | E-519237 | E-519237 | 1: XS | 2025-08-06 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-08-06
Local Enhancement Epic: COM-RS28-PRINT -Anomaly Detect Analy Model Ideas | Approved | Local Enhancement Epic | Commercial Portfolio | 0108680 |  |  | Local Enhancement Epic | Assessment & Analysis | E-518028 | E-518028 | 2: S |  |  |  | 2 | 0 |  | 2 | No
Local Enhancement Epic: COM-RS28-FUSE - Imprv Team Member Notif. | Approved | Local Enhancement Epic | Commercial Portfolio | 0108683 |  |  | Local Enhancement Epic | Build | E-519235 | E-519235 | 1: XS | 2025-08-06 |  | 50% | 2 | 1 |  | 1 | No | 2025-07-10 | 2026-03-25 | 2025-08-06
Local Enhancement Epic: COM-RS28-FUSE - Finishing Only Product | Approved | Local Enhancement Epic | Commercial Portfolio | 0108685 |  |  | Local Enhancement Epic | Build | E-521049 | E-521049 | 2: S | 2025-08-06 |  |  | 2 | 0 | 1 | 1 | No | 2025-08-27 | 2026-03-25 | 2025-08-06
Local Enhancement Epic: COM - GDX - MS - GEU Retl/E-comm - ADM/P4E Enhan | Approved | Local Enhancement Epic | Commercial Portfolio | 0108711 |  |  | Local Enhancement Epic | Build | E-525828 | E-525828 | 2: S | 2025-07-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-12-30 | 2025-07-23
Local Enhancement Epic: COM - CE - Cust Care Desktop (CCD) mig dates upd | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108712 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-IA-GIX-Sherwin Williams reporting to new 211 | Approved | Local Enhancement Epic | Commercial Portfolio | 0108714 |  |  | Local Enhancement Epic | Backlog | E-521047 | E-521047 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-08
Local Enhancement Epic: COM - RS - FUSE & PPA Print Sppt-KM 751i & KM 451i | Approved | Local Enhancement Epic | Commercial Portfolio | 0108726 |  |  | Local Enhancement Epic | Launch & Evaluate | E-515481 | E-515481 | 1: XS | 2025-06-26 |  | 66.67% | 3 | 2 | 1 | 0 | No | 2025-08-27 | 2026-01-13 | 2025-06-26
Local Enhancement Epic: COM-RS28-Salesforce & FUSE Bidding Intergration | Approved | Local Enhancement Epic | Commercial Portfolio | 0108728 |  |  | Local Enhancement Epic | Build | E-554944 | E-554944 | 2: S | 2026-03-17 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2026-03-17
Local Enhancement Epic: COM-RS28-Office.FedEx.Com Bounce Rate Reduction | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108729 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Zambia Tax Logic Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0108731 |  |  | Local Enhancement Epic | Build | E-536382 | E-536382 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RS - FUSE PRINT - Data reporting in Power BI | Approved | Local Enhancement Epic | Commercial Portfolio | 0108732 |  |  | Local Enhancement Epic | Build | E-516273 | E-516273 | 1: XS | 2025-08-26 |  |  | 2 | 0 | 1 | 1 | No | 2026-01-15 | 2026-03-25 | 2025-08-26
Local Enhancement Epic: COM - RMIC - GRI MEISA 2026 | Approved | Local Enhancement Epic | Commercial Portfolio | 0108734 |  |  | Local Enhancement Epic | Backlog | E-521556 | E-521556 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Disburse Fee Calc & VAT Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0108735 |  |  | Local Enhancement Epic | Backlog | E-536380 | E-536380 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - GRI Tool Load Old/New Rates | Approved | Local Enhancement Epic | Commercial Portfolio | 0108737 |  |  | Local Enhancement Epic | Backlog | E-525670 | E-525670 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - Global Metrics | Approved | Local Enhancement Epic | Commercial Portfolio | 0108740 |  |  | Local Enhancement Epic | Backlog | E-521051 | E-521051 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-02-27
Local Enhancement Epic: COM - RMIC - GRI Tool Add Sys Option Upd Old/New | Approved | Local Enhancement Epic | Commercial Portfolio | 0108739 |  |  | Local Enhancement Epic | Backlog | E-525664 | E-525664 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FastBill Rollout for IN, JO, NG | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108741 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - H-E-B EDI 212 | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108745 |  |  | Local Enhancement Epic | Backlog | E-521110 | E-521110 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - IA - GIX - ED864DP Production Enhancement | Approved | Lifecycle Management Epic | Commercial Portfolio | 0108746 |  |  | Lifecycle Management Epic | Backlog | E-521098 | E-521098 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - IA - GIX - ZORO AG Delay Code for RESD | Approved | Local Enhancement Epic | Commercial Portfolio | 0108750 |  |  | Local Enhancement Epic | Backlog | E-521113 | E-521113 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - RMIC-RD3 - Botswana Inv & Crd Note Integrate | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108770 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - MegaTaxillaDigitalSignQR,duplPDF | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108772 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Mismatch Orig & PUP State of Expt | Approved | Local Enhancement Epic | Commercial Portfolio | 0108775 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543884 | E-543884 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3 - SendInvPDFviaCREDOforNon-FBO acc | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108777 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - Bill Shipper/3P Per Manifest | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108778 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1C (LAC)(CO) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108789 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | E-556927 | E-556927 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-02-25 | 2027-01-15
Biz w/ Tech Epic: Epic 2 (Global ROD) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0108791 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - FUSE/POD Incrs file upld limit to 300mb | Approved | Local Enhancement Epic | Commercial Portfolio | 0108805 |  |  | Local Enhancement Epic | Build | E-521054 | E-521054 | 2: S | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-02 | 2026-07-15 | 2025-12-08
Local Enhancement Epic: COM - CSX - GC3 Five9 Software Updates & Upgrades | Approved | Local Enhancement Epic | Commercial Portfolio | 0108813 |  |  | Local Enhancement Epic | Backlog | E-530209 | E-530209 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-12 | 2025-10-22
Local Enhancement Epic: COM - RMIC - AnomalyDimDetection(HCH Buss. Rule | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108817 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Add Chrg Code to GB VAT List | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108819 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - SHIPAnomalyDimDetection HCH Bus Rule | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108820 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CSX - GC3 - Incidents, Fiv9 Adminis Reports | Approved | Local Enhancement Epic | Commercial Portfolio | 0108821 |  |  | Local Enhancement Epic | Backlog | E-530212 | E-530212 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-12 | 2025-10-22
Local Enhancement Epic: COM - CSX - GC3 SharePoint and Dashboards | Approved | Local Enhancement Epic | Commercial Portfolio | 0108822 |  |  | Local Enhancement Epic | Backlog | E-530211 | E-530211 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-12 | 2025-10-22
Local Enhancement Epic: COM – IA -GIX - GAP/Good American | Approved | Local Enhancement Epic | Commercial Portfolio | 0108823 |  |  | Local Enhancement Epic | Backlog | E-521112 | E-521112 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - RMIC - TaxLogicChgNon-INT FRTAWBs Billed INT | Approved | Local Enhancement Epic | Commercial Portfolio | 0108829 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543873 | E-543873 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FB Incr # Rows for Bulk Upload | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108830 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - RDA to Add Unique ID & Ship Dt Rng | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108831 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Sep Inv Prsntmnt Backend LDP Flw Reg | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108832 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Set Err on Shp Dt > thn Finl Dispo Dt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108833 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Deactivate Shpmnts Getting STAT 14 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108834 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - GRI US 2026 | Approved | Local Enhancement Epic | Commercial Portfolio | 0108835 |  |  | Local Enhancement Epic | Build | E-521111 | E-521111 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Upd Polcy Grid fr Non-Stckble Surcha | Approved | Local Enhancement Epic | Commercial Portfolio | 0108836 |  |  | Local Enhancement Epic | Build | E-536412 | E-536412 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM-RS28-PFC Standard API Adoption | Closed | Local Enhancement Epic | Commercial Portfolio | 0108873 |  |  | Local Enhancement Epic | Build | E-519928 | E-519928 | 3: M | 2025-08-07 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-08-07
Biz w/ Tech Epic: Commercial: Skeleton Shipment Void | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108296 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Build | E-518878 | E-518878 | 2: S | 2025-09-27 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-27
Biz w/ Tech Epic: Commercial: Duplicate Tracking Number | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108297 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Backlog | E-521085 | E-521085 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - CORE - Modified CIA Data Load | Approved | Local Enhancement Epic | Commercial Portfolio | 0108881 |  |  | Local Enhancement Epic | Backlog | E-521106 | E-521106 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - CP - FDP - FY25_PI03_GDL Enhancement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0108886 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - FDX - FDP - FY25_PI03_Com_FDP_ProdSupp | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0108888 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - FY25_PI03_FDP_API_Versioning | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0108906 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - F1R 2025 Eff July 14 Rate Incr | Approved | Local Enhancement Epic | Commercial Portfolio | 0108907 |  |  | Local Enhancement Epic | Build | E-521118 | E-521118 | 1: XS | 2025-07-21 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-21
Local Enhancement Epic: COM - RMIC - SAM List Rate Jul'25 Rate Increases | Approved | Local Enhancement Epic | Commercial Portfolio | 0108909 |  |  | Local Enhancement Epic | Build | E-521117 | E-521117 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - GCCS Rollout for KSA | Approved | Local Enhancement Epic | Commercial Portfolio | 0108989 |  |  | Local Enhancement Epic | Build | E-522949 | E-522949 | 2: S | 2025-08-07 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-07
Local Enhancement Epic: COM-RS28-FUSE - Head to Toe Printing | Approved | Local Enhancement Epic | Commercial Portfolio | 0109020 |  |  | Local Enhancement Epic | Backlog | E-523138 | E-523138 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: COM - RMIC - FY26_Prod_Maintenance_&_Support | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0109022 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RMIC - FY26 General Release Activities | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109023 |  |  | Lifecycle Management Epic | Build | E-522340 | E-522340 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - RMIC - FY26 Planning & Analysis | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109024 |  |  | Lifecycle Management Epic | Build | E-522339 | E-522339 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - RMIC - FY26_Prod_Maint_&_Support | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0109025 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RMIC - FY26 Production Maint & Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109026 |  |  | Lifecycle Management Epic | Build | E-522338 | E-522338 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - RMIC - FY26_Prod_Maint_&_Support | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0109027 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-RD3 - UAE Tax eInvoicing Fdx, PS&TNT | Approved | Local Enhancement Epic | Commercial Portfolio | 0109039 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543883 | E-543883 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3 - Oman Tax eInvoicing FDX&Fastbill | Not Started | Local Enhancement Epic | Commercial Portfolio | 0109040 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - FBO Collection Email Updates | Not Started | Local Enhancement Epic | Commercial Portfolio | 0109053 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-RD3 - Migrate Italy GovtInvSovos-Pagero | Approved | Local Enhancement Epic | Commercial Portfolio | 0109054 |  |  | Local Enhancement Epic | Build | E-530098 | E-530098 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-29 | 2025-12-31 | 2025-12-06
Local Enhancement Epic: COM - RMIC - VAT Table SEZ Taxable @ 0% | Not Started | Local Enhancement Epic | Commercial Portfolio | 0109057 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX-FAPI-Meter Genrte-Err CodeMessage Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0109059 |  |  | Local Enhancement Epic | Build | E-526650 | E-526650 | 2: S | 2025-07-24 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-24
Lifecycle Management Epic: COM - RMIC-RD3 - FY26PI03 Peoplesoft CRAFT | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0109061 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP-FY26 PCC Rating-CurrencyUtil Object | Approved | Local Enhancement Epic | Commercial Portfolio | 0109063 |  |  | Local Enhancement Epic | Build | E-533303 | E-533303 | 2: S | 2025-08-18 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-18
Local Enhancement Epic: COM - RMIC-RD3 - PS Inv&Cr Masking of AC # | Approved | Local Enhancement Epic | Commercial Portfolio | 0109080 |  |  | Local Enhancement Epic | Build | E-522386 | E-522386 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - CSX - DICE -Qualtrics Data Feed Enhancements | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0109081 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - CSX - GC3 Invoicing and Contracts | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0109082 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - GDX - CP - FY26 PCC LCM Non-KTLO | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109084 |  |  | Lifecycle Management Epic | Build | E-521423 | E-521423 | 2: S | 2025-07-09 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-09
Local Enhancement Epic: COM - RMIC - Incr FBO CharLimit for CI Name Fields | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109085 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552254 | E-552254 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - GDX - MS - Retl. EUR-PostNL RTH, DTR & ARTH | Approved | Local Enhancement Epic | Commercial Portfolio | 0109086 |  |  | Local Enhancement Epic | Build | E-525825 | E-525825 | 2: S | 2025-07-23 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-23
Local Enhancement Epic: COM - RMIC - FB Need Non Vat Chrg Cd (AE,BH,KW,KE) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0109087 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-FREV - MX FBE Broker Validation | On Hold | Local Enhancement Epic | Commercial Portfolio | 0109088 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | Yes
Lifecycle Management Epic: COM - IA - CIS - FY25_PI4_CIS_Upgrd, Maint./Prod. | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0109089 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - MS - Mobile - Home Screen Tracking Exp | Closed | Local Enhancement Epic | Commercial Portfolio | 0109090 |  |  | Local Enhancement Epic | Build | E-528367 | E-528367 | 2: S | 2025-09-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-02
Local Enhancement Epic: COM - GDX - MS -DEX08 Txt chng Trking scrn/notif. | Approved | Local Enhancement Epic | Commercial Portfolio | 0109091 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546453 | E-546453 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Build Designated Shipping Service Options | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109095 | 7621 | [AE, SA] MERN LTL Revenue Growth incl. DG launch | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dangerous Goods option/handling codes | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109096 | 7621 | [AE, SA] MERN LTL Revenue Growth incl. DG launch | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Set Up Account Enablement for Designated Shipping | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109097 | 7621 | [AE, SA] MERN LTL Revenue Growth incl. DG launch | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Designated Shipping Service Options Available Duri | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109098 | 7621 | [AE, SA] MERN LTL Revenue Growth incl. DG launch | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Deploy Service Options in channels for shipping se | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109099 | 7621 | [AE, SA] MERN LTL Revenue Growth incl. DG launch | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - [APAC] TW NEW CLEARANCE ANCILLARIES | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109181 | 9428 | EMR OTC-[APAC] TW New Clearance Ancillaries | Biz w/ Tech Epic | Assessment & Analysis | E-518616 | E-518616 |  |  |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22
Biz w/ Tech Epic: COM - [ENABLER] RATING MODERNIZATION | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109182 | 8291 | Rating Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-518618 | E-518618 |  |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: COM - CAPACITY MANAGEMENT QUOTING TOOL 2.0 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109183 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-518652 | E-518652 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - CONTRACTS & SAVINGS FOR ALL BI CONSOLIDATION | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109184 | 8215 | Contracts and savings for all BI Consolidation Ini | Biz w/ Tech Epic | Assessment & Analysis | E-518608 | E-518608 |  |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: COM - DP/BRE - APPLY GLOBAL PEAK SURCHARGE BY ORIG | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109185 | 9098 | DP/BRE - Apply Global Peak Surcharge by Origin/Des | Biz w/ Tech Epic | Assessment & Analysis | E-518822 | E-518822 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - EMBP TRANSFORMATION | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109186 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-518749 | E-518749 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - ENHANCEMENTS FOR PRIDE TO ENABLE DOMESTIC MI | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109187 | 97147 | Enhancements for PRIDE to enable DomesticMigration | Biz w/ Tech Epic | Assessment & Analysis | E-518632 | E-518632 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - FCF TRANSFORMATION PHASE 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109188 | 9235 | FCF transformation: Epic 1 | Biz w/ Tech Epic | Assessment & Analysis | E-518863 | E-518863 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - FEDEX ROUTING OPTIMIZATION VALUE BUNDLE 1 (N | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109189 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Assessment & Analysis | E-518849 | E-518849 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - GDX - CUSTOMER LABEL CREATION THRESHOLD | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109190 | 8139 | Customer Label Creation Threshold | Biz w/ Tech Epic | Assessment & Analysis | E-318479 | E-318479 | 2: S |  |  | 100% | 4 | 4 |  | 0 | No
Biz w/ Tech Epic: COM - GDX - EDM GOOGLE STORAGE AND API TO AZURE ST | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109191 | 6702 | TS-VL3-HybridCloud-GCPMigrateGoogleStorage | Biz w/ Tech Epic | Assessment & Analysis | E-481067 | E-481067 | 4: L |  |  | 33.33% | 3 | 1 | 1 | 1 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: COM - GDX - EPIC 1 | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109192 | 7036 | Global Air Freight Contract Exchange Rates | Biz w/ Tech Epic | Build | E-497810 | E-497810 | 2: S | 2026-01-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-06
Biz w/ Tech Epic: COM - GDX - FXFD PERSONALIZED NOTIFICATIONS - SCO | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109193 | 6809 | FXFD Personalized Notifications - per customer req | Biz w/ Tech Epic | Assessment & Analysis | E-511632 | E-511632 | 2: S |  |  |  | 3 | 0 |  | 3 | No
Biz w/ Tech Epic: COM - GEMINI - GLOBAL PLATFORM | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109194 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Assessment & Analysis | E-518630 | E-518630 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - GSP TO DIRECT SERVE - SLOVAKIA (SK) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109195 | 7528 | Enable- G2D conversion Slovakia ( ACE enablement) | Biz w/ Tech Epic | Assessment & Analysis | E-518860 | E-518860 | 3: M |  |  | 50% | 2 | 1 |  | 1 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: COM - METRICS TO VIEW THE FAILURE OCCURRENCES | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109196 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-517318 | E-517318 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - MULTI DIM - HANDLING UNIT MOVEMENT (HUM) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109197 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Assessment & Analysis | E-518639 | E-518639 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - OPTIMIZE INBOUND ANCILLARIES OFFER | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109198 | 7794 | EMR OTC - Optimize Inbound Ancillaries Offer | Biz w/ Tech Epic | Assessment & Analysis | E-518817 | E-518817 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - OWN THE BORDER PHASE 2 - US-CA-US PARCEL POR | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109199 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-518847 | E-518847 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Biz w/ Tech Epic: COM - RMIC - BILL MANAGEMENT | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109200 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-518279 | E-518279 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - RMIC - OWN THE BORDER-SURFACE & CLEARANCE-EP | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109201 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-431711 | E-431711 |  |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: COM - RS - RET - Create RMA all types in Consumer | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109202 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-512155 | E-512155 | 2: S | 2025-09-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-05
Biz w/ Tech Epic: COM - RS - RET - Research and Develop Bulk Upload | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109203 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-512158 | E-512158 | 2: S | 2025-09-05 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-25 | 2026-05-29 | 2025-09-05
Biz w/ Tech Epic: COM - SCO - SORT UNITIZE C STATUS INDICATION ON BA | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109204 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-514841 | E-514841 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - VALIDATING THE VAT WHEN CHANGED | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109205 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-517315 | E-517315 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - ZUORA SUBSCRIPTION MANAGEMENT FOR DIGITAL PR | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109206 | 7407 | Zuora Subscription Management for Digital Products | Biz w/ Tech Epic | Assessment & Analysis | E-450724 | E-450724 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CIS - ECSuite - PPM558905 - VF InforNexus Integrat | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109255 | 115639 | EGER F&R-VF Corporation | Biz w/ Tech Epic | Assessment & Analysis | E-460860 | E-460860 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-30
Biz w/ Tech Epic: COM - Enable Oracle ATA (LXF) Consignee 3rd Party | On Hold | Biz w/ Tech Epic | Commercial Portfolio | 0109256 | 105953 | Enable Oracle ATA (LXF) 3rd party billing Solution | Biz w/ Tech Epic | Assessment & Analysis | E-518667 | E-518667 | 2: S |  |  |  | 3 | 0 | 3 | 0 | No
Biz w/ Tech Epic: COM - FEDEX FREUGHT (FXF) ARCH, ENG& GOVE OF INFO | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109257 | 91377 | Fedex Freight (FXF) Arch,Eng&Gov of Info Sys AEGIS | Biz w/ Tech Epic | Assessment & Analysis | E-518657 | E-518657 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - FEDEX INTERNATIONAL DEFERRED FREIGHT (FDF) M | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109258 | 9240 | Launch International Deferred Freight 1A & 1B | Biz w/ Tech Epic | Assessment & Analysis | E-518856 | E-518856 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - FEDEX ONE RATE - INTRODUCING EXTRA SMALL BOX | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109259 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-518857 | E-518857 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-08-27 | 2026-05-29
Biz w/ Tech Epic: COM - GDX - MODERNIZE EXPRESS US DOMESTIC RATING | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109260 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-500442 | E-500442 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - GDX -FEDEX INTERNATIONAL DEFERRED FREIGHT PR | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109261 | 9240 | Launch International Deferred Freight 1A & 1B | Biz w/ Tech Epic | Assessment & Analysis | E-419447 | E-419447 | 4: L |  |  | 100% | 4 | 4 |  | 0 | No | 2024-07-22 | 2025-01-14
Biz w/ Tech Epic: COM - LOCAL ZONE AND SAME DAY OFFERING | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0109262 | 97873 | Local Zone - Contract only | Biz w/ Tech Epic | Assessment & Analysis | E-518824 | E-518824 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2028-06-15 | 2028-10-17
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109263 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-518851 | E-518851 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109264 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-518861 | E-518861 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109265 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-518862 | E-518862 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109266 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415517 | E-415517 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109267 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415518 | E-415518 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109268 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415521 | E-415521 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109269 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415522 | E-415522 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109270 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415523 | E-415523 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109271 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415524 | E-415524 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - REGISTRATION & PAYMENT OPTIONS (JOIN/HOPE) - | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109272 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-415520 | E-415520 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - RMIC - PROJECT CLARITY | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109273 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-485357 | E-485357 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - RMIC PRJ 850876 - Easy Ways to Pay Epic 1A ( | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109274 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | E-504155 | E-504155 |  |  |  |  | 1 | 0 | 1 | 0 | No | 2025-07-23 | 2025-10-21
Biz w/ Tech Epic: COM - RS - Data Governance Strategy & Transformati | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109275 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-436112 | E-436112 | 1: XS |  |  | 100% | 10 | 10 |  | 0 | No | 2025-06-02 | 2026-05-29
Biz w/ Tech Epic: COM - RS - INIT - DME EIW-to-Atlas: MARS App | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109276 | 130291 | TS-VL3-DB-EIWMigration-Retail ecommerce Apps | Biz w/ Tech Epic | Assessment & Analysis | E-517809 | E-517809 | 2: S |  |  |  | 2 | 0 |  | 2 | No
Biz w/ Tech Epic: COM-RS28-Retail Account Creation & Warnings FUSE | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109277 | 92862 | Retail Account Creation and Warnings in FUSE | Biz w/ Tech Epic | Build | E-518002 | E-518002 | 1: XS | 2025-08-14 |  |  | 2 | 0 | 1 | 1 | No | 2025-08-27 | 2026-03-24 | 2025-08-14
Biz w/ Tech Epic: COM - RS - SHIP - RCPA - Global Retail Tech Enable | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109278 | 6866 | Globalizing Retail Automation Tools (RCPA) | Biz w/ Tech Epic | Assessment & Analysis | E-447075 | E-447075 | 3: M |  |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29
Biz w/ Tech Epic: COM - S&CDE - CA Proactive Retention Migration (Le | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109279 | 7071 | Proactive Retention (PR) Journey Migration | Biz w/ Tech Epic | Assessment & Analysis | E-484880 | E-484880 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: COM - S&CDE - Commercial Data Migration (Integrate | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109280 | 130280 | TS-VL3-DB-EIWMigration-COM S&CDE CDP Migration | Biz w/ Tech Epic | Assessment & Analysis | E-501148 | E-501148 |  |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: COM - S&CDE - Ingestions from Original Sources and | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109281 | 98380 | TS-VL3-DB-EIWMigration-EIW Retirement | Biz w/ Tech Epic | Assessment & Analysis | E-501125 | E-501125 | 5: XL |  |  | 95.45% | 22 | 21 | 1 | 0 | No | 2024-08-05 | 2025-05-30
Biz w/ Tech Epic: COM - S&CDE - SDW to Atlas | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109282 | 97428 | TS-VL3-EIW Migration - Sales Data Warehouse to Atl | Biz w/ Tech Epic | Assessment & Analysis | E-507779 | E-507779 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: COM - S&CDE - Send CDP curated data to Atlas | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109283 | 98380 | TS-VL3-DB-EIWMigration-EIW Retirement | Biz w/ Tech Epic | Assessment & Analysis | E-501141 | E-501141 |  |  |  | 100% | 1 | 1 |  | 0 | No | 2025-03-12 | 2025-05-20
Biz w/ Tech Epic: COM - Build local CN CC3 DB Auto Refresh | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109284 | 8166 | APAC Enhanced CC3 & IVA CHINA | Biz w/ Tech Epic | Assessment & Analysis | E-513966 | E-513966 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-07-06 | 2026-12-31
Biz w/ Tech Epic: PRJ 275125 - FXF - 593 Rating Modernization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109285 | 8291 | Rating Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-456203 | E-456203 | 5: XL |  |  |  | 4 | 0 | 3 | 1 | No
Biz w/ Tech Epic: PRJ 532008 - ServiceNow Implementation Phase 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0109286 | 8992 | ServiceNow Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-424018 | E-424018 |  |  |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-04-30
Biz w/ Tech Epic: Replace Trellix SolidCore with Airlock Cloud Solut | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0109287 | 108485 | SolidCore Replacement | Biz w/ Tech Epic | Assessment & Analysis | E-513657 | E-513657 |  |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: CIS - EC Suite-PPM533065 - Samsung KR new process | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109433 | 8587 | E2E-High Tech- Samsung Semiconductor (Phase 1) | Biz w/ Tech Epic | Backlog | E-399025 | E-399025 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-06-09
Biz w/ Tech Epic: CIS - Windows/Mcafee patches - Legacy ECShip serve | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109434 | 8606 | E2E – High-Tech – Finished Goods - Apple (Phase 1) | Biz w/ Tech Epic | Backlog | E-514707 | E-514707 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-07 | 2025-08-19
Biz w/ Tech Epic: CIS-ECSuite-PPMXXXXX - Apple Distribution Centre ( | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109435 | 8606 | E2E – High-Tech – Finished Goods - Apple (Phase 1) | Biz w/ Tech Epic | Backlog | E-471665 | E-471665 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-02-04 | 2026-06-02
Biz w/ Tech Epic: CIS-ECSuite-PPMXXXXX - EDI180 and EDI 858 for App | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109436 | 8606 | E2E – High-Tech – Finished Goods - Apple (Phase 1) | Biz w/ Tech Epic | Backlog | E-486573 | E-486573 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-01 | 2025-12-01
Biz w/ Tech Epic: COM - CSX - DELIVERY PREDICTION VB6: GLOBAL GUEST | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109437 | 7189 | [VIS] GBL Guest Authentication | Biz w/ Tech Epic | Build | E-439395 | E-439395 | 3: M | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: COM - GDX - ANCHOR PLC – INTL AHS/OS PACKAGE LEVEL | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109438 | 7875 | ANCHOR PLC - Change International AHS/OS Surcharge | Biz w/ Tech Epic | Build | E-363578 | E-363578 | 3: M | 2025-07-02 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: COM - GDX - DANGEROUS GOODS: ROAD - PRODUCT & ORDE | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109439 | 9372 | Enable a scalable FedEx DG road offering allowing | Biz w/ Tech Epic | Build | E-315143 | E-315143 | 4: L | 2025-07-01 |  | 100% | 3 | 3 |  | 0 | No | 2023-08-16 | 2026-06-02 | 2025-07-01
Biz w/ Tech Epic: COM - GDX - EXPRESS DOMESTICS - PHASE 2 WAVE 5 SSD | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109440 | 9394 | Enable Express Domestic standard product & pricing | Biz w/ Tech Epic | Build | E-393304 | E-393304 | 3: M | 2025-07-01 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: COM - GDX - EXPRESS DOMESTICS - SINGLE STANDARD DO | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109441 | 9394 | Enable Express Domestic standard product & pricing | Biz w/ Tech Epic | Build | E-275272 | E-275272 | 3: M | 2025-07-02 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-07-02
Biz w/ Tech Epic: COM - GDX - OWN THE BORDER - COMMERCIAL, SURFACE & | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109442 |  |  | Biz w/ Tech Epic | Build | E-421133 | E-421133 | 3: M | 2025-07-01 |  | 87.5% | 8 | 7 | 1 | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: COM - GDX - WS#11 ENABLEMENT OF IED ON INTRA-EUROP | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109443 | 7380 | WS #11 Enablement of IED on Intra-European single | Biz w/ Tech Epic | Build | E-477221 | E-477221 |  | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No | 2025-08-13 | 2025-10-22 | 2025-07-01
Biz w/ Tech Epic: COM - IVR/VA - NUANCE APPLICATION USAGE & PROFEE S | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109444 | 9056 | IVR/VA - Nuance Application Usage and ProFee Spend | Biz w/ Tech Epic | Build | E-429748 | E-429748 |  | 2026-01-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-23
Biz w/ Tech Epic: COM - RMIC - PRJ 489561 - HEALTHCARE IDENTIFIER - | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0109445 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Build | E-385636 | E-385636 | 3: M | 2026-01-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-23
Biz w/ Tech Epic: COM - RMIC - PRJ 708530 - PEACE IN - TDS Column E | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109446 | 8197 | [IN] [Enabler] Improve billing, Cash Application a | Biz w/ Tech Epic | Build | E-517348 | E-517348 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: COM - RMIC - PRJ 758540 - Weight Based Fuel Surcha | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109447 | 6755 | Weight Based Fuel Surcharge for Intl. Express | Biz w/ Tech Epic | Build | E-475524 | E-475524 |  | 2025-11-13 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-04-30 | 2025-11-13
Biz w/ Tech Epic: COM - RMIC - PRJ 847062 - eMBP Transformation Jul | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109448 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Build | E-500350 | E-500350 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-04-01 | 2025-07-31 | 2025-12-06
Biz w/ Tech Epic: COM - RS - DRIVE Enterprise IT Infrastructure Prox | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109449 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Build | E-484820 | E-484820 |  | 2025-07-01 |  | 75% | 4 | 3 | 1 | 0 | No | 2025-10-01 | 2026-01-16 | 2025-07-01
Biz w/ Tech Epic: COM - RS - RET - Retailer Management - Rewrite | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109450 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-473978 | E-473978 | 5: XL | 2025-06-30 |  | 28.57% | 7 | 2 | 3 | 2 | No | 2025-06-16 | 2026-05-29 | 2025-06-30
Local Enhancement Epic: China Medtronic Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0109630 |  |  | Local Enhancement Epic | Backlog | E-517264 | E-517264 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-08-19
Local Enhancement Epic: CIS - 1. WFM CE Predictive Insights (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109631 |  |  | Local Enhancement Epic | Backlog | E-432746 | E-432746 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - 2. CE Issue Resolution Insights (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109632 |  |  | Local Enhancement Epic | Backlog | E-432747 | E-432747 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - 3. PCC Operations Analytics (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109633 |  |  | Local Enhancement Epic | Backlog | E-432748 | E-432748 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - 4. DRIVE Dashboard (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109634 |  |  | Local Enhancement Epic | Backlog | E-432749 | E-432749 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - 5. Data Ingestion & Transformation (ETL) (PG | Closed | Local Enhancement Epic | Commercial Portfolio | 0109635 |  |  | Local Enhancement Epic | Backlog | E-434038 | E-434038 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - 6. PI DEPENDENCIES (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109636 |  |  | Local Enhancement Epic | Backlog | E-434033 | E-434033 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - EC Governance and Audit for EC-Suite - CY25 | Approved | Local Enhancement Epic | Commercial Portfolio | 0109637 |  |  | Local Enhancement Epic | Backlog | E-514132 | E-514132 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-07 | 2025-08-19
Local Enhancement Epic: CIS - EC Suite-PPM513968-SMC JP - CY25 | Closed | Local Enhancement Epic | Commercial Portfolio | 0109638 |  |  | Local Enhancement Epic | Backlog | E-399022 | E-399022 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: [WIN] Iris Galerie Poland EC-Ship Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0109639 |  |  | Local Enhancement Epic | Backlog | E-514752 | E-514752 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-03-24
Local Enhancement Epic: [WIN] NienMade AU Domestic API Integration and IPD | Approved | Local Enhancement Epic | Commercial Portfolio | 0109640 |  |  | Local Enhancement Epic | Backlog | E-515930 | E-515930 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-08-20 | 2026-06-09
Local Enhancement Epic: CIS - EC-EDI - PPM558905 - VF InforNexus CY25 PI01 | Closed | Local Enhancement Epic | Commercial Portfolio | 0109641 |  |  | Local Enhancement Epic | Backlog | E-460859 | E-460859 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - EC-Shipping-PPM#647027-HP_Mentor-TH | Closed | Local Enhancement Epic | Commercial Portfolio | 0109642 |  |  | Local Enhancement Epic | Backlog | E-458326 | E-458326 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - EC-Shipping-PVSeqID114276-HP_HuaQin_VN | Approved | Local Enhancement Epic | Commercial Portfolio | 0109643 |  |  | Local Enhancement Epic | Backlog | E-513948 | E-513948 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-17 | 2025-08-19
Local Enhancement Epic: CIS - ECSuite - PPM595711 - Coherent Project (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109644 |  |  | Local Enhancement Epic | Backlog | E-432428 | E-432428 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS - EC-Suite-PPM547936-Framework Computer (PGM) | Approved | Local Enhancement Epic | Commercial Portfolio | 0109645 |  |  | Local Enhancement Epic | Backlog | E-469504 | E-469504 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2025-02-11
Local Enhancement Epic: CIS - FY24/25-PPM# 476589-Post Implementation Mai | Approved | Local Enhancement Epic | Commercial Portfolio | 0109646 |  |  | Local Enhancement Epic | Backlog | E-360300 | E-360300 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2026-12-31
Local Enhancement Epic: CIS -FY25/26- EC-Reporting-PPM107324-Continuous Im | Approved | Local Enhancement Epic | Commercial Portfolio | 0109647 |  |  | Local Enhancement Epic | Backlog | E-513909 | E-513909 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-05 | 2026-12-29
Local Enhancement Epic: CIS-EC Reporting-PPMxxx-Mid-Oceans | Approved | Local Enhancement Epic | Commercial Portfolio | 0109648 |  |  | Local Enhancement Epic | Backlog | E-472374 | E-472374 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2025-04-01
Local Enhancement Epic: CIS-ECSuite-PPM1403583 - Coupang Korea | Approved | Local Enhancement Epic | Commercial Portfolio | 0109649 |  |  | Local Enhancement Epic | Backlog | E-447178 | E-447178 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-08-20 | 2026-11-25
Local Enhancement Epic: CIS-SCS-AU-Arthrex-RFID (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109650 |  |  | Local Enhancement Epic | Backlog | E-377941 | E-377941 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS-SCS-AU-Cutera-Onboarding (PGM) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109651 |  |  | Local Enhancement Epic | Backlog | E-446840 | E-446840 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS-SCS-BD-BARD | Approved | Local Enhancement Epic | Commercial Portfolio | 0109652 |  |  | Local Enhancement Epic | Backlog | E-516654 | E-516654 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-08-19
Local Enhancement Epic: CIS-SCS-Hachiko-Maintenance-CRs-CY25 PI01 (PGM) | Approved | Local Enhancement Epic | Commercial Portfolio | 0109653 |  |  | Local Enhancement Epic | Backlog | E-467880 | E-467880 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2024-12-31
Local Enhancement Epic: CIS-SCS-Hachiko-Maintenance-CRs-CY25 PI02 (PGM) | Approved | Local Enhancement Epic | Commercial Portfolio | 0109654 |  |  | Local Enhancement Epic | Backlog | E-482459 | E-482459 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2025-06-10
Local Enhancement Epic: CIS-SCS-IN-ATOMY-CR-Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0109655 |  |  | Local Enhancement Epic | Backlog | E-517269 | E-517269 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: CIS-SCS-IN-Canon E-Commerce (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109656 |  |  | Local Enhancement Epic | Backlog | E-416106 | E-416106 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS-SCS-IN-Canon Medical-Onboarding (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109657 |  |  | Local Enhancement Epic | Backlog | E-446836 | E-446836 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS-SCS-JP-Hilti-COE (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109658 |  |  | Local Enhancement Epic | Backlog | E-461322 | E-461322 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS-SCS-KR-BDBard-Onboarding (PGM) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109659 |  |  | Local Enhancement Epic | Backlog | E-419005 | E-419005 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CIS-SCS-Medtronic-TRACK | Approved | Local Enhancement Epic | Commercial Portfolio | 0109660 |  |  | Local Enhancement Epic | Backlog | E-519059 | E-519059 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: CIS-SCS-SG-Canon-Medical-Hachiko (PGM) | Closed | Local Enhancement Epic | Commercial Portfolio | 0109661 |  |  | Local Enhancement Epic | Backlog | E-456406 | E-456406 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - APAC FIT Japan DT Pment adjust config | Approved | Local Enhancement Epic | Commercial Portfolio | 0109662 |  |  | Local Enhancement Epic | Backlog | E-512164 | E-512164 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - APAC FIT-GEMINI 2.0/(ACCS) - PES | Approved | Local Enhancement Epic | Commercial Portfolio | 0109663 |  |  | Local Enhancement Epic | Backlog | E-512197 | E-512197 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - CAPS Support - Upgrade APPD App Agent | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109664 |  |  | Lifecycle Management Epic | Backlog | E-497625 | E-497625 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - FIT-Singap-D&T require confirm email | Approved | Local Enhancement Epic | Commercial Portfolio | 0109665 |  |  | Local Enhancement Epic | Backlog | E-512165 | E-512165 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - Invite User Template Email | Approved | Local Enhancement Epic | Commercial Portfolio | 0109666 |  |  | Local Enhancement Epic | Backlog | E-485845 | E-485845 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - NOTF - LCM-CY25 PI3-Spprt & Serv Now | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109667 |  |  | Lifecycle Management Epic | Backlog | E-519013 | E-519013 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - IA - GIX - WTG Upgrade (UI Access Post-Intun | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109668 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-504445 | E-504445 | 1: XS | 2025-07-30 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-30
Local Enhancement Epic: COM - IA - METL Packing List Returns (PLR) Init | Approved | Local Enhancement Epic | Commercial Portfolio | 0109669 |  |  | Local Enhancement Epic | Backlog | E-513002 | E-513002 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-08
Local Enhancement Epic: COM - IA/GDX - Support on APIF Country API | Approved | Local Enhancement Epic | Commercial Portfolio | 0109670 |  |  | Local Enhancement Epic | Backlog | E-517885 | E-517885 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - PRJ 532299 Commercial Data Enablement | Approved | Local Enhancement Epic | Commercial Portfolio | 0109671 |  |  | Local Enhancement Epic | Build | E-423617 | E-423617 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-08-29 | 2025-07-02
Local Enhancement Epic: COM - RMIC - PRJ 855993 - Regulatory - Reversal of | Approved | Local Enhancement Epic | Commercial Portfolio | 0109672 |  |  | Local Enhancement Epic | Backlog | E-514877 | E-514877 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-05-01 | 2025-06-30
Local Enhancement Epic: COM - RMIC - PRJ 858861 2025 July FPOS Maintenanc | Approved | Local Enhancement Epic | Commercial Portfolio | 0109673 |  |  | Local Enhancement Epic | Build | E-517511 | E-517511 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-03 | 2025-07-31 | 2025-12-06
Local Enhancement Epic: COM - RS - INIT - UberEats | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109675 |  |  | Local Enhancement Epic | Backlog | E-518238 | E-518238 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - Order Delivery | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109676 |  |  | Local Enhancement Epic | Build | E-519937 | E-519937 |  | 2025-07-01 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: COM - RS - PRINT - FUSE Print Stabilization | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109677 |  |  | Local Enhancement Epic | Backlog | [6 empty] | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RS - PRINT Salesforce Integration & FUSE Bid | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109678 |  |  | Local Enhancement Epic | Backlog | E-515469 | E-515469 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - (CDE) | Approved | Local Enhancement Epic | Commercial Portfolio | 0109679 |  |  | Local Enhancement Epic | Backlog | E-500190 | E-500190 |  |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - S&CDE - CONDOR Ephemeral Testing | Approved | Local Enhancement Epic | Commercial Portfolio | 0109681 |  |  | Local Enhancement Epic | Build | E-501695 | E-501695 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: COM - S&CDE - CVM EIW Tables - Column Change | Approved | Local Enhancement Epic | Commercial Portfolio | 0109682 |  |  | Local Enhancement Epic | Build | E-501314 | E-501314 |  | 2025-08-11 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-11
Lifecycle Management Epic: COM - S&CDE - IT Initiatives | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109683 |  |  | Lifecycle Management Epic | Build | E-498801 | E-498801 |  | 2025-07-02 |  |  | 7 | 0 | 6 | 1 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: COM - S&CDE - License Intergration Service Now | Approved | Local Enhancement Epic | Commercial Portfolio | 0109684 |  |  | Local Enhancement Epic | Backlog | E-504361 | E-504361 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-07-01 | 2025-10-07
Local Enhancement Epic: COM - S&CDE - Salesforce Marketing Cloud and Stens | Approved | Local Enhancement Epic | Commercial Portfolio | 0109685 |  |  | Local Enhancement Epic | Build | E-501073 | E-501073 |  | 2025-09-30 |  | 100% | 1 | 1 |  | 0 | No | 2025-05-21 | 2025-07-29 | 2025-09-30
Local Enhancement Epic: COM - S&CDE - Storylane | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109686 |  |  | Local Enhancement Epic | Backlog | E-503778 | E-503778 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - S&CDE - Synthesia | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109687 |  |  | Local Enhancement Epic | Backlog | E-503780 | E-503780 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - S&CDE - Unified Customer Profile (UCP) Desig | Approved | Local Enhancement Epic | Commercial Portfolio | 0109688 |  |  | Local Enhancement Epic | Build | E-504340 | E-504340 | 5: XL | 2025-07-01 |  |  | 3 | 0 | 2 | 1 | No | 2024-07-22 | 2025-05-30 | 2025-07-01
Lifecycle Management Epic: COM-IA-GIX-FedEx Net Post-Migration Demand (CONDOR | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109689 |  |  | Lifecycle Management Epic | Backlog | E-508202 | E-508202 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: PRJ 857271 US-CAN Ground Int'l Demand Surcharge | Approved | Local Enhancement Epic | Commercial Portfolio | 0109690 |  |  | Local Enhancement Epic | Build | E-515418 | E-515418 |  | 2025-10-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-05-01 | 2025-06-30 | 2025-10-01
Local Enhancement Epic: COM-RS-SASS-CISPS: FY26 Local Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0109691 |  |  | Local Enhancement Epic | Build | E-516384 | E-516384 |  | 2025-07-31 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-07-31
Local Enhancement Epic: COM-RS-SASS-Titans:Enhance Test Peripheral Utility | Closed | Local Enhancement Epic | Commercial Portfolio | 0109692 |  |  | Local Enhancement Epic | Build | E-513609 | E-513609 |  | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: Copy Of COM - Sales & CDE - CDE- iSell Connection | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0109693 |  |  | Local Enhancement Epic | Backlog | E-518688 | E-518688 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: EC-Shipping-PPM476589-Acushnet-CY25 CY26 | Approved | Local Enhancement Epic | Commercial Portfolio | 0109694 |  |  | Local Enhancement Epic | Backlog | E-472324 | E-472324 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-12-03 | 2025-04-01
Local Enhancement Epic: HPU Loading for TNT Customer Migration Exercise - | Approved | Local Enhancement Epic | Commercial Portfolio | 0109695 |  |  | Local Enhancement Epic | Build | E-513025 | E-513025 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-01-01 | 2026-01-30 | 2025-12-06
Local Enhancement Epic: IA - CSR ENABLEMENT APPS - MASTER ART BUNDLE REPOS | Approved | Local Enhancement Epic | Commercial Portfolio | 0109696 |  |  | Local Enhancement Epic | Backlog | E-438692 | E-438692 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2037-01-01
Local Enhancement Epic: LABEL-LESS - PPM165706 - R7: Contingency Plan | Closed | Local Enhancement Epic | Commercial Portfolio | 0109697 |  |  | Local Enhancement Epic | Backlog | E-433112 | E-433112 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Operations WFM Reports | Approved | Local Enhancement Epic | Commercial Portfolio | 0109698 |  |  | Local Enhancement Epic | Backlog | E-513970 | E-513970 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-08-19
Local Enhancement Epic: PRJ 160027 - MIA Migration Impact Analyzer | Closed | Local Enhancement Epic | Commercial Portfolio | 0109699 |  |  | Local Enhancement Epic | Backlog | E-459405 | E-459405 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: PRJ 171514 - Retire WebLogic and move to Springboo | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109700 |  |  | Lifecycle Management Epic | Build | E-135513 | E-135513 |  | 2025-07-01 |  | 100% | 3 | 3 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-01
Local Enhancement Epic: PRJ 214669 - ACCS Modernization BFC (Billing for C | Approved | Local Enhancement Epic | Commercial Portfolio | 0109701 |  |  | Local Enhancement Epic | Build | E-397835 | E-397835 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: PRJ 254455 - Business Updates Data in Invoicing | Approved | Local Enhancement Epic | Commercial Portfolio | 0109702 |  |  | Local Enhancement Epic | Build | E-213617 | E-213617 | 2: S | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: PRJ 344703 - RCCE BAM GUI - Clean-up Outdated Term | Approved | Local Enhancement Epic | Commercial Portfolio | 0109703 |  |  | Local Enhancement Epic | Backlog | E-208939 | E-208939 |  |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: PRJ 359192 - CONDOR: Error Correction Webservices | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109704 |  |  | Lifecycle Management Epic | Build | E-308403 | E-308403 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-02
Local Enhancement Epic: PRJ 451742 - Rerate Tool For Non-Integrated Domest | Closed | Local Enhancement Epic | Commercial Portfolio | 0109705 |  |  | Local Enhancement Epic | Build | E-459410 | E-459410 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Lifecycle Management Epic: PRJ 461471 - Zscaler Private Access (ZPA) Purple C | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109706 |  |  | Lifecycle Management Epic | Build | E-477411 | E-477411 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2025-01-20 | 2025-09-30 | 2025-07-02
Local Enhancement Epic: PRJ 469146 - Update and Create FedEx Credit/Denial | Closed | Local Enhancement Epic | Commercial Portfolio | 0109707 |  |  | Local Enhancement Epic | Build | E-361260 | E-361260 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: PRJ 536479 - FY25 Store Retail25 Initiative (Aug 2 | Approved | Local Enhancement Epic | Commercial Portfolio | 0109708 |  |  | Local Enhancement Epic | Build | E-477420 | E-477420 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2025-01-27 | 2025-07-31 | 2025-07-02
Lifecycle Management Epic: PRJ 539122 - DBR Application Enhancements | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109709 |  |  | Lifecycle Management Epic | Build | E-423970 | E-423970 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Lifecycle Management Epic: PRJ 539810 - PP: Infrastructure: Quarterly patchin | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109710 |  |  | Lifecycle Management Epic | Build | E-424602 | E-424602 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-02
Lifecycle Management Epic: PRJ 541329 RatingEBS Upgrade to Spring Boot 3.0 & | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109711 |  |  | Lifecycle Management Epic | Build | E-435550 | E-435550 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: PRJ 541837 DBR Enhancements to Handle Additional B | Closed | Local Enhancement Epic | Commercial Portfolio | 0109712 |  |  | Local Enhancement Epic | Build | E-428838 | E-428838 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 543085 Technical Resiliency & Reliability NFR | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109713 |  |  | Lifecycle Management Epic | Build | E-427862 | E-427862 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 543245 - Technical Resiliency & Reliability NF | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109714 |  |  | Lifecycle Management Epic | Build | E-428177 | E-428177 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 543307 ePRS OAuth2 Adoption | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109715 |  |  | Lifecycle Management Epic | Build | E-428097 | E-428097 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Lifecycle Management Epic: PRJ 543327 - Angular and Spring boot Migration (AD | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109716 |  |  | Lifecycle Management Epic | Build | E-436958 | E-436958 |  | 2025-10-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-01
Lifecycle Management Epic: PRJ 544657 - Feature Testing using SI Pipeline for | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109717 |  |  | Lifecycle Management Epic | Build | E-442956 | E-442956 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Lifecycle Management Epic: PRJ 547391 - Resiliency/Global Rely-NFRs for Settl | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0109718 |  |  | Lifecycle Management Epic | Build | E-432224 | E-432224 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: PRJ 548173 - ePAT Enhancement and Maintenance FY25 | Closed | Local Enhancement Epic | Commercial Portfolio | 0109719 |  |  | Local Enhancement Epic | Backlog | E-445134 | E-445134 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PRJ 549631 - Regulatory - Update VAT Logic Calcula | Closed | Local Enhancement Epic | Commercial Portfolio | 0109720 |  |  | Local Enhancement Epic | Backlog | E-434351 | E-434351 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: PRJ 558371 - Canadian Clearance & Accounting Docum | Closed | Local Enhancement Epic | Commercial Portfolio | 0109721 |  |  | Local Enhancement Epic | Build | E-438492 | E-438492 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Lifecycle Management Epic: PRJ 561969 DRDS S3 Cloud Storage to Replace Curre | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109722 |  |  | Lifecycle Management Epic | Build | E-445941 | E-445941 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: PRJ 562904 - CA Production - Enable Invoice Reprin | Closed | Local Enhancement Epic | Commercial Portfolio | 0109723 |  |  | Local Enhancement Epic | Build | E-450675 | E-450675 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 563272 Enterprise Rating Rely Best Practices | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109724 |  |  | Lifecycle Management Epic | Build | E-443506 | E-443506 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: PRJ 563837 - Purchase Return Authorization (PRA) M | Closed | Local Enhancement Epic | Commercial Portfolio | 0109725 |  |  | Local Enhancement Epic | Build | E-457963 | E-457963 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 563870 - FCORS Enhancements | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109726 |  |  | Lifecycle Management Epic | Build | E-474681 | E-474681 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-06-30 | 2025-07-01
Lifecycle Management Epic: PRJ 564749 - Email Invoice Research Screen and Web | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109727 |  |  | Lifecycle Management Epic | Build | E-451042 | E-451042 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: PRJ 569364 - Short Paid Issue When One of the Paym | Closed | Local Enhancement Epic | Commercial Portfolio | 0109728 |  |  | Local Enhancement Epic | Build | E-456888 | E-456888 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 569366 - InfoSec PAG Remediation | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109729 |  |  | Lifecycle Management Epic | Build | E-448321 | E-448321 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Lifecycle Management Epic: PRJ 569680 - Migration to Java 21 and Springboot 3 | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109730 |  |  | Lifecycle Management Epic | Build | E-454778 | E-454778 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: PRJ 579424 - GLIDE Phase 3 - Local Invoice Number | Closed | Local Enhancement Epic | Commercial Portfolio | 0109731 |  |  | Local Enhancement Epic | Build | E-455826 | E-455826 |  | 2025-08-12 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-12
Local Enhancement Epic: PRJ 582856 - FXF Legacy Pricing Expiration | Closed | Local Enhancement Epic | Commercial Portfolio | 0109732 |  |  | Local Enhancement Epic | Backlog | E-460061 | E-460061 |  |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: PRJ 586907 - Technical Resilency & Reliability NFR | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109733 |  |  | Lifecycle Management Epic | Build | E-454579 | E-454579 |  | 2025-09-30 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-30
Lifecycle Management Epic: PRJ 587267 - Upgrade to Sprint Boot 3 and Java 17 | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109734 |  |  | Lifecycle Management Epic | Build | E-454597 | E-454597 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PRJ 703039 - Technical Resilency & Reliability NFR | Closed | Lifecycle Management Epic | Commercial Portfolio | 0109735 |  |  | Lifecycle Management Epic | Build | E-461005 | E-461005 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: PRJ 705565 - Assistance with UAT Support for Enter | Approved | Local Enhancement Epic | Commercial Portfolio | 0109736 |  |  | Local Enhancement Epic | Backlog | E-464086 | E-464086 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-09-02 | 2025-05-30
Lifecycle Management Epic: PRJ 706838 - Protect Purple – Vulnerability Manage | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109737 |  |  | Lifecycle Management Epic | Build | E-463785 | E-463785 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2024-10-01 | 2025-05-30 | 2025-07-02
Local Enhancement Epic: PRJ 706864 - Regulatory - Tcheck/Wex File Change | Approved | Local Enhancement Epic | Commercial Portfolio | 0109738 |  |  | Local Enhancement Epic | Backlog | E-463806 | E-463806 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-09-02 | 2024-12-31
Lifecycle Management Epic: PRJ 721626 - CONDOR - Code Translation Retirement | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109739 |  |  | Lifecycle Management Epic | Build | E-467282 | E-467282 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-10-01 | 2025-04-30 | 2025-12-06
Local Enhancement Epic: PRJ 723012 New Software IDs (SWID) for 9 Applicat | Approved | Local Enhancement Epic | Commercial Portfolio | 0109740 |  |  | Local Enhancement Epic | Build | E-468724 | E-468724 |  | 2025-08-12 |  | 100% | 1 | 1 |  | 0 | No | 2024-08-01 | 2025-04-30 | 2025-08-12
Lifecycle Management Epic: PRJ 751638 - CONDOR - Migration to METL | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109741 |  |  | Lifecycle Management Epic | Build | E-476620 | E-476620 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2024-10-01 | 2025-07-31 | 2025-07-01
Lifecycle Management Epic: PRJ 758322 Y2029 Problem: Expiration dates will | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109742 |  |  | Lifecycle Management Epic | Build | E-475335 | E-475335 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-04-30 | 2025-07-02
Local Enhancement Epic: PRJ 759647 Change Country Table Pay Values for Ca | Approved | Local Enhancement Epic | Commercial Portfolio | 0109743 |  |  | Local Enhancement Epic | Build | E-477132 | E-477132 |  | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-07-31 | 2025-07-02
Local Enhancement Epic: PRJ 759684 - Error Code 4720 - Verify ROD Payment | Approved | Local Enhancement Epic | Commercial Portfolio | 0109744 |  |  | Local Enhancement Epic | Build | E-476600 | E-476600 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-04-30 | 2025-07-01
Local Enhancement Epic: PRJ 760918 - Update Invoice Due Date Value for APA | Approved | Local Enhancement Epic | Commercial Portfolio | 0109745 |  |  | Local Enhancement Epic | Build | E-477285 | E-477285 |  | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-09-01 | 2025-08-13
Local Enhancement Epic: PRJ 760920 - Update Government Contact Info on Inv | Approved | Local Enhancement Epic | Commercial Portfolio | 0109746 |  |  | Local Enhancement Epic | Build | E-477286 | E-477286 |  | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-09-01 | 2025-08-13
Local Enhancement Epic: PRJ 760926 - Parcel Collection Letter Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0109747 |  |  | Local Enhancement Epic | Backlog | E-477288 | E-477288 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-08-29
Local Enhancement Epic: PRJ 760989 - Regulatory - Invoicing Delivery Flow | Approved | Local Enhancement Epic | Commercial Portfolio | 0109748 |  |  | Local Enhancement Epic | Backlog | E-477373 | E-477373 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-31
Local Enhancement Epic: PRJ 761942 - FAST Bill - New FASTBill Product Code | Approved | Local Enhancement Epic | Commercial Portfolio | 0109749 |  |  | Local Enhancement Epic | Backlog | E-478342 | E-478342 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: PRJ 770252 - Retire Legacy FCLA Registrations | Approved | Lifecycle Management Epic | Commercial Portfolio | 0109750 |  |  | Lifecycle Management Epic | Build | E-513029 | E-513029 |  | 2025-12-06 |  | 100% | 1 | 1 |  | 0 | No | 2025-01-01 | 2025-05-30 | 2025-12-06
Local Enhancement Epic: PRJ 770636 - CBS/HOPE - Enhancements Based on DOTS | Approved | Local Enhancement Epic | Commercial Portfolio | 0109751 |  |  | Local Enhancement Epic | Build | E-514938 | E-514938 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-11-01 | 2025-07-31 | 2025-12-06
Local Enhancement Epic: PRJ 837244 - Restrict DT Rebills to City Center Ac | Approved | Local Enhancement Epic | Commercial Portfolio | 0109752 |  |  | Local Enhancement Epic | Build | E-512951 | E-512951 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-01 | 2025-07-31 | 2025-12-06
Local Enhancement Epic: PRJ 843563 - Limit Rebills from Self Serve Applica | Approved | Local Enhancement Epic | Commercial Portfolio | 0109753 |  |  | Local Enhancement Epic | Build | E-501423 | E-501423 |  | 2025-11-11 |  | 100% | 1 | 1 |  | 0 | No | 2025-04-04 | 2025-10-31 | 2025-11-11
Local Enhancement Epic: PRJ 857384 - SOAP API Upgrade Authentication P12 | Approved | Local Enhancement Epic | Commercial Portfolio | 0109754 |  |  | Local Enhancement Epic | Build | E-515770 | E-515770 |  | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-04-30 | 2025-07-29 | 2025-12-06
Local Enhancement Epic: Risk Management for CIS - CY24 to CY26 | Approved | Local Enhancement Epic | Commercial Portfolio | 0109755 |  |  | Local Enhancement Epic | Backlog | E-462453 | E-462453 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-10
Local Enhancement Epic: SCS-Sterling to Hachiko Migration | Approved | Local Enhancement Epic | Commercial Portfolio | 0109756 |  |  | Local Enhancement Epic | Backlog | E-478011 | E-478011 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Strategic Executive Reporting | Approved | Local Enhancement Epic | Commercial Portfolio | 0109757 |  |  | Local Enhancement Epic | Backlog | E-514733 | E-514733 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-08-19
Local Enhancement Epic: COM - GDX - CP - FDP - FY25_PI03_GDL Enhance | Approved | Local Enhancement Epic | Commercial Portfolio | 0110381 |  |  | Local Enhancement Epic | Build | E-521422 | E-521422 | 2: S | 2025-07-09 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-09
Local Enhancement Epic: COM - GDX - CP - FY25_PI03_FDP_API_Versioning | Approved | Local Enhancement Epic | Commercial Portfolio | 0110532 |  |  | Local Enhancement Epic | Build | E-530674 | E-530674 | 2: S | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-07
Lifecycle Management Epic: COM - GDX - CP - FY25_PI03_Com_FDP_ProdSupp | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110633 |  |  | Lifecycle Management Epic | Build | E-521421 | E-521421 | 2: S | 2025-07-09 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-07-09
Local Enhancement Epic: COM - RMIC - FBO AMEA Enablmnt Due to FCL Retirmnt | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0110677 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA – GIX Add GST Flag Logic | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110678 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Use Rated Service/Packaging for D/Txs | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110679 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - AMB Retirement (FIMS) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110680 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Traceability of Shpt-Build EDI GUI | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110682 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Rmvl of Rounding in Rate Escal Proc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110683 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - COP Pymnt Portal Batch & QR Cd Pymnts | Approved | Local Enhancement Epic | Commercial Portfolio | 0110684 |  |  | Local Enhancement Epic | Build | E-543869 | E-543869 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - IA - GIX CIM-GB/CNS MQ Put | Approved | Local Enhancement Epic | Commercial Portfolio | 0110685 |  |  | Local Enhancement Epic | Backlog | E-522879 | E-522879 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Lifecycle Management Epic: COM - IA - GIX - FY26_Production Support | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0110686 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Virtual Assistant Self Service Capabilities | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110712 | 6906 | [US] Build additional self-service capabilities in | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP FY26 PCC Rating: Local Enhcmnts | Approved | Local Enhancement Epic | Commercial Portfolio | 0110715 |  |  | Local Enhancement Epic | Build | E-533337 | E-533337 | 2: S | 2025-08-18 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-18
Biz w/ Tech Epic: Case EBS Value Bundle 6 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0110729 | 106820 | Case EBS Value Bundle 6 | Biz w/ Tech Epic | Backlog | E-536298 | E-536298 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2027-03-23
Local Enhancement Epic: COM - RMIC - GRI CAN 2026 | Approved | Local Enhancement Epic | Commercial Portfolio | 0110746 |  |  | Local Enhancement Epic | Backlog | E-522047 | E-522047 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - GDX - CP - E-469375-Migrate Shipping APIs | Approved | Local Enhancement Epic | Commercial Portfolio | 0110822 |  |  | Local Enhancement Epic | Build | E-536752 | E-536752 | 3: M | 2025-09-05 |  |  | 2 | 0 | 2 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-09-05
Local Enhancement Epic: COM - RS - Plant Node Removal | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110823 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDP - CP - FY26 PCC Data Services | Approved | Local Enhancement Epic | Commercial Portfolio | 0110824 |  |  | Local Enhancement Epic | Build | E-533336 | E-533336 | 1: XS | 2025-08-18 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-18
Local Enhancement Epic: COM - GDX - CP - PCC Rating: Split code base repo | Approved | Local Enhancement Epic | Commercial Portfolio | 0110825 |  |  | Local Enhancement Epic | Build | E-533335 | E-533335 | 2: S | 2025-08-18 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-18
Local Enhancement Epic: COM-RS28-FUSE-Order Delivery | Closed | Local Enhancement Epic | Commercial Portfolio | 0110827 |  |  | Local Enhancement Epic | Build | E-523131 | E-523131 | 3: M | 2025-07-16 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-16
Lifecycle Management Epic: COM - RMIC-LCM - Qtr Patching Java, WL, Linux FY26 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110839 |  |  | Lifecycle Management Epic | Build | E-522568 | E-522568 | 2: S | 2025-10-09 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-10-09
Lifecycle Management Epic: COM - RMIC-LCM - Audit Support for Freight Rev | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110840 |  |  | Lifecycle Management Epic | Build | E-522570 | E-522570 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - GDX-PCC Data Services:Updt field char length | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110846 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - High Value Edits | Approved | Local Enhancement Epic | Commercial Portfolio | 0110847 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570300 | E-570300 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RS - Remove Customer Print Instructions | Approved | Local Enhancement Epic | Commercial Portfolio | 0110848 |  |  | Local Enhancement Epic | Backlog | E-523874 | E-523874 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Removal of ADT Error Code in ADT | Approved | Local Enhancement Epic | Commercial Portfolio | 0110849 |  |  | Local Enhancement Epic | Build | E-547728 | E-547728 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RS - FUSE Receipt Messaging | In Progress | Local Enhancement Epic | Commercial Portfolio | 0110852 |  |  | Local Enhancement Epic | Backlog | E-523873 | E-523873 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - CSX - Claims Adoption of DPR Feed Change | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110878 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - FAME API - Retire & Sunset DG API | Approved | Local Enhancement Epic | Commercial Portfolio | 0110880 |  |  | Local Enhancement Epic | Build | E-525824 | E-525824 | 1: XS | 2025-07-23 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-23
Local Enhancement Epic: COM - GDX - CP -FAME API_JSON Schm Descripency fix | Approved | Local Enhancement Epic | Commercial Portfolio | 0110881 |  |  | Local Enhancement Epic | Build | E-525821 | E-525821 | 1: XS | 2025-07-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-23
Local Enhancement Epic: COM - GDX - CP -FAME Ph 2:Relax fld len restrictio | Approved | Local Enhancement Epic | Commercial Portfolio | 0110883 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546451 | E-546451 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-12-30
Biz w/ Tech Epic: E-517654 - [MEISA] FiT launch in Saudi Arabia | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0110889 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Define Data Mapping and Migration Strategy | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0110745 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-10-04 | 2024-10-04
Lifecycle Management Epic: COM - RS - GAT - Canon Pro 4600 Follow-on Device | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110901 |  |  | Lifecycle Management Epic | Build | E-523872 | E-523872 | 1: XS | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-01-13 | 2025-12-08
Lifecycle Management Epic: COM - RMIC-LCM - Abinitio Co-op Upgrade for GRCC | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110908 |  |  | Lifecycle Management Epic | Build | E-529787 | E-529787 | 2: S | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-07
Lifecycle Management Epic: COM - RMIC - Invoicing-FDS: Updt EDM Interface | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110909 |  |  | Lifecycle Management Epic | Build | E-522569 | E-522569 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Invoicing-FDS: Load balance | Approved | Local Enhancement Epic | Commercial Portfolio | 0110910 |  |  | Local Enhancement Epic | Launch & Evaluate | E-524067 | E-524067 | 3: M | 2025-07-16 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-16
Local Enhancement Epic: COM - RMIC - Invoicing-FDS:Decouple Archiving | Approved | Local Enhancement Epic | Commercial Portfolio | 0110911 |  |  | Local Enhancement Epic | Build | E-526649 | E-526649 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - US Payor Billings & Inv Adj to GRCC | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110913 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FedEx Implementation & Discovery | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110914 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS -DME MARS Infrastructure and Optimization | Approved | Local Enhancement Epic | Commercial Portfolio | 0110915 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528420 | E-528420 | 1: XS | 2025-07-16 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-18 | 2026-03-24 | 2025-07-16
Local Enhancement Epic: COM - RS - DME Modify HR Datahub API Pull | Approved | Local Enhancement Epic | Commercial Portfolio | 0110916 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528418 | E-528418 | 1: XS | 2025-07-16 |  |  | 2 | 0 | 1 | 1 | No | 2025-06-18 | 2026-01-13 | 2025-07-16
Lifecycle Management Epic: COM-GDX-CS - DSS_FSMNetworkClientDefaultEncryption | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110920 |  |  | Lifecycle Management Epic | Build | E-525823 | E-525823 | 1: XS | 2025-07-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-13 | 2025-10-21 | 2025-07-23
Local Enhancement Epic: COM - GDX - MS - FedEx Integrator Global Launch | Approved | Local Enhancement Epic | Commercial Portfolio | 0110921 |  |  | Local Enhancement Epic | Build | E-536747 | E-536747 | 3: M | 2025-09-05 |  |  | 2 | 0 | 1 | 1 | No | 2026-01-19 | 2026-01-19 | 2025-09-05
Local Enhancement Epic: COM - GDX - MS [MOB] Shipping List Banner Creation | Approved | Local Enhancement Epic | Commercial Portfolio | 0110923 |  |  | Local Enhancement Epic | Backlog | E-530671 | E-530671 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - TED Global | Approved | Local Enhancement Epic | Commercial Portfolio | 0110924 |  |  | Local Enhancement Epic | Backlog | E-521804 | E-521804 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-02-27
Biz w/ Tech Epic: Establish Systems Connectivity and Readiness | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110927 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Execute Final Production Data Migration | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110928 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - CP - FAME: API Minor Version Capture | Approved | Local Enhancement Epic | Commercial Portfolio | 0110929 |  |  | Local Enhancement Epic | Build | E-530672 | E-530672 | 2: S | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-07
Biz w/ Tech Epic: Perform Mock Runs and Execute Dress Rehearsal | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110930 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - fdx intl shipping | Approved | Local Enhancement Epic | Commercial Portfolio | 0110933 |  |  | Local Enhancement Epic | Backlog | E-533884 | E-533884 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - S&CDE - CDE - Data Cloud One (Research) | Approved | Local Enhancement Epic | Commercial Portfolio | 0110934 |  |  | Local Enhancement Epic | Backlog | E-524378 | E-524378 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - Dispute Flow for US | Approved | Local Enhancement Epic | Commercial Portfolio | 0110935 |  |  | Local Enhancement Epic | Backlog | E-524496 | E-524496 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - MS-FY26_MGSV_ Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110936 |  |  | Lifecycle Management Epic | Build | E-525827 | E-525827 | 3: M | 2025-07-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-23
Lifecycle Management Epic: COM - GDX - MS - FY26_PI04_MGSV_Security Updates | Approved | Lifecycle Management Epic | Commercial Portfolio | 0110937 |  |  | Lifecycle Management Epic | Build | E-525826 | E-525826 | 3: M | 2025-07-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-07-23
Local Enhancement Epic: COM-RS-SASS LE FJMP Price and Promotion Changes | Rejected | Local Enhancement Epic | Commercial Portfolio | 0110938 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-SASS - SSAC Transaction Report | Closed | Local Enhancement Epic | Commercial Portfolio | 0110940 |  |  | Local Enhancement Epic | Backlog | E-523136 | E-523136 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - CN BaC Enhncmnt New Links & Addr | Approved | Local Enhancement Epic | Commercial Portfolio | 0110946 |  |  | Local Enhancement Epic | Build | E-535873 | E-535873 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: MEISA - Saudi Arabia (Phone # val) | Approved | Local Enhancement Epic | Commercial Portfolio | 0107831 |  |  | Local Enhancement Epic | Backlog | E-521007 | E-521007 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CSX - DICE-APAC CLR GC3: migrate MY,TH,KULGC | Closed | Local Enhancement Epic | Commercial Portfolio | 0110955 |  |  | Local Enhancement Epic | Backlog | E-524193 | E-524193 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Loyalty Program Strategy & Performance Evolution | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110960 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Member Engagement & Redemption Experience | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110961 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Omnichannel Integration & Activation | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110963 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Operational Support & Customer Experience | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0110964 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CSX - ECAM Mapping for Customer ID for VN | Approved | Local Enhancement Epic | Commercial Portfolio | 0110979 |  |  | Local Enhancement Epic | Backlog | E-525324 | E-525324 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - CSX - Software Modernization for CE Org | Not Started | Local Enhancement Epic | Commercial Portfolio | 0110980 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Supply order go automatic by RPA | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111009 | 8445 | [AMEA] APAC - Supplies Orders process automation b | Biz w/ Tech Epic | Backlog | E-535875 | E-535875 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-01 | 2026-02-27
Local Enhancement Epic: COM - IA – GIX – FUSE Wuerth | Approved | Local Enhancement Epic | Commercial Portfolio | 0110742 |  |  | Local Enhancement Epic | Backlog | E-533170 | E-533170 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Biz w/ Tech Epic: Project Sprint Plan | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111077 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-EGER-Healthcare Bio-Rad POD Rprt Dev | Approved | Local Enhancement Epic | Commercial Portfolio | 0111079 |  |  | Local Enhancement Epic | Build | E-535741 | E-535741 | 2: S | 2025-08-29 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-29
Local Enhancement Epic: COM - CSX - Continuous Improvement Analysis | Approved | Local Enhancement Epic | Commercial Portfolio | 0111091 |  |  | Local Enhancement Epic | Backlog | E-524804 | E-524804 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-18 | 2026-06-12
Local Enhancement Epic: COM - RMIC - Custom Template Pricing Restriction | Approved | Local Enhancement Epic | Commercial Portfolio | 0111092 |  |  | Local Enhancement Epic | Build | E-534003 | E-534003 | 4: L | 2025-10-08 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-10-08
Local Enhancement Epic: COM - RMIC - FASTBill Invoicing in MEISA & EU | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111093 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RMIC-ROPs - Duty Tax Exec Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0111094 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544220 | E-544220 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2025-10-31
Local Enhancement Epic: COM - RMIC - CAN Demand Surcharges Enablement | Approved | Local Enhancement Epic | Commercial Portfolio | 0111095 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558291 | E-558291 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-GDX - Email QR Code Batch Pymt Enhcmnt | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111096 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - New FASTBill Prodts Billing Chg Fee | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111097 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Inv Message Updt D/T Payor Non Acct | Approved | Local Enhancement Epic | Commercial Portfolio | 0111099 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573106 | E-573106 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-RS28-Retail Products on UberEats (VALUE) | Closed | Local Enhancement Epic | Commercial Portfolio | 0111101 |  |  | Local Enhancement Epic | Build | E-524066 | E-524066 | 1: XS | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Local Enhancement Epic: COM-CSX-Claims-NYCE Variable Pass | Approved | Local Enhancement Epic | Commercial Portfolio | 0111102 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538986 | E-538986 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3-STC - FDX & TNT Credit Note change | Closed | Local Enhancement Epic | Commercial Portfolio | 0111103 |  |  | Local Enhancement Epic | Done | E-526443 | E-526443 | 2: S | 2025-08-06 | 2025-08-27 |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-06 | 2025-08-27
Local Enhancement Epic: COM-RS-Retailship / RDAT LOC ID Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111104 |  |  | Local Enhancement Epic | Build | E-527277 | E-527277 | 2: S | 2025-11-24 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-24
Local Enhancement Epic: COM-RS-Retailship Scan Compliance for 3rd party | Closed | Local Enhancement Epic | Commercial Portfolio | 0111105 |  |  | Local Enhancement Epic | Build | E-527275 | E-527275 | 2: S | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Local Enhancement Epic: RDAP / Accounts and locations Import | Closed | Local Enhancement Epic | Commercial Portfolio | 0111106 |  |  | Local Enhancement Epic | Backlog | E-527278 | E-527278 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM - IA - GIX - Grainger RESD, CNSOL, LFTG keywor | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111121 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM-Add Lifecycle Insights in iSell | Approved | Local Enhancement Epic | Commercial Portfolio | 0111155 |  |  | Local Enhancement Epic | Backlog | E-524197 | E-524197 | 1: XS |  |  |  | 2 | 0 |  | 2 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM- Domestic &Intl Trace Changes - RS | Closed | Local Enhancement Epic | Commercial Portfolio | 0111156 |  |  | Local Enhancement Epic | Build | E-524192 | E-524192 | 1: XS | 2025-10-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CRM-APOLLO Billing Flag Detection Case | Closed | Local Enhancement Epic | Commercial Portfolio | 0111157 |  |  | Local Enhancement Epic | Build | E-524196 | E-524196 | 1: XS | 2025-11-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-05
Local Enhancement Epic: COM-S&CDE-CRM-Include Daily Wgt in iSell Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0111158 |  |  | Local Enhancement Epic | Build | E-524195 | E-524195 | 1: XS | 2025-11-18 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-29 | 2025-10-07 | 2025-11-18
Local Enhancement Epic: COM-S&CDE-CRM MyTerritory/TMD - Gold/Silver/Bronze | Approved | Local Enhancement Epic | Commercial Portfolio | 0111159 |  |  | Local Enhancement Epic | Backlog | E-524304 | E-524304 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CRM-KPI Dashboard BDS Regional (WWS) | Approved | Local Enhancement Epic | Commercial Portfolio | 0111160 |  |  | Local Enhancement Epic | Backlog | E-524303 | E-524303 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-10-07 | 2026-03-03
Local Enhancement Epic: COM-S&CDE-CRM- Inside Sales Monthly Payouts in SPR | Approved | Local Enhancement Epic | Commercial Portfolio | 0111161 |  |  | Local Enhancement Epic | Backlog | E-524302 | E-524302 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CRM- BDS Role Implementation | Closed | Local Enhancement Epic | Commercial Portfolio | 0111162 |  |  | Local Enhancement Epic | Build | E-524301 | E-524301 | 3: M | 2025-11-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-05
Local Enhancement Epic: COM-S&CDE-CRM- Display Verticals Revenue | Approved | Local Enhancement Epic | Commercial Portfolio | 0111163 |  |  | Local Enhancement Epic | Backlog | E-524300 | E-524300 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CRM- Strategic Init filter on Global TMD | Approved | Local Enhancement Epic | Commercial Portfolio | 0111164 |  |  | Local Enhancement Epic | Backlog | E-524298 | E-524298 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CRM- CY25 My Pricing App Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0111165 |  |  | Local Enhancement Epic | Backlog | E-524299 | E-524299 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CRM- Suggested Calls 2.0 - Digital Sales | Approved | Local Enhancement Epic | Commercial Portfolio | 0111166 |  |  | Local Enhancement Epic | Backlog | E-524310 | E-524310 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CRM- Overlays MyPipe and MyPerf Visiblty | Approved | Local Enhancement Epic | Commercial Portfolio | 0111167 |  |  | Local Enhancement Epic | Backlog | E-524309 | E-524309 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CRM-TNT Email Visibility in iSell | Approved | Local Enhancement Epic | Commercial Portfolio | 0111168 |  |  | Local Enhancement Epic | Backlog | E-524373 | E-524373 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Customer Supplies Enhancements - RS | Closed | Local Enhancement Epic | Commercial Portfolio | 0111169 |  |  | Local Enhancement Epic | Build | E-524374 | E-524374 | 1: XS | 2025-11-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-05
Local Enhancement Epic: COM-S&CDE-CRM-Opus API integration | Closed | Local Enhancement Epic | Commercial Portfolio | 0111170 |  |  | Local Enhancement Epic | Build | E-524308 | E-524308 | 1: XS | 2025-11-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-05
Local Enhancement Epic: COM-S&CDE-CDE - FTE% Visible in SPR | Approved | Local Enhancement Epic | Commercial Portfolio | 0111171 |  |  | Local Enhancement Epic | Backlog | E-524377 | E-524377 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CDE - Pause SLA clock for TPO Cases | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111172 |  |  | Local Enhancement Epic | Backlog | E-524376 | E-524376 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-S&CDE-CDE - Digital Scheduler Platform Improve | Approved | Local Enhancement Epic | Commercial Portfolio | 0111173 |  |  | Local Enhancement Epic | Backlog | E-524375 | E-524375 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Biz w/ Tech Epic: COM - CC3 New APIs Capability to Build into CN IVA | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111195 | 8166 | APAC Enhanced CC3 & IVA CHINA | Biz w/ Tech Epic | Assessment & Analysis | E-538909 | E-538909 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2025-10-31
Biz w/ Tech Epic: GC3 - New APIs Capability to Build into APAC DTMF | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111196 | 6895 | AMEA Enhanced GC3 & IVA (Non-CN) | Biz w/ Tech Epic | Backlog | E-531758 | E-531758 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2025-10-31
Local Enhancement Epic: COM-S&CDE-CORE-Modify CESE Reject NOI Events Logic | Approved | Local Enhancement Epic | Commercial Portfolio | 0111219 |  |  | Local Enhancement Epic | Backlog | E-528226 | E-528226 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - IA - GIX Update Specs for PPFS Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0111220 |  |  | Local Enhancement Epic | Backlog | E-526722 | E-526722 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Lifecycle Management Epic: COM - IA - GIX - TUNL New Sectigo Root | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111222 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-528419 | E-528419 | 1: XS | 2025-07-16 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-16
Biz w/ Tech Epic: FSMS Modernization CY25 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111226 | 93961 | E-Commerce Rating Response Improvement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - SFTP server New print vndr for JP | Approved | Local Enhancement Epic | Commercial Portfolio | 0111232 |  |  | Local Enhancement Epic | Build | E-525669 | E-525669 | 2: S | 2025-09-25 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-25
Local Enhancement Epic: COM-IA-GIX-DRAEGER SAFETY AG & CO. KGAA | Approved | Local Enhancement Epic | Commercial Portfolio | 0111234 |  |  | Local Enhancement Epic | Backlog | E-523833 | E-523833 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM - RMIC-RD3 - Add various cust types ZATCA reg | Approved | Local Enhancement Epic | Commercial Portfolio | 0111235 |  |  | Local Enhancement Epic | Build | E-543886 | E-543886 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Add Employee ID to Source Tab in RDA | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111238 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-SupplyWeb Upload Canada | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111239 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GIX-GXO FUSE | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111249 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-Customer Loaded Trailer VerbiageChanges | Approved | Local Enhancement Epic | Commercial Portfolio | 0111250 |  |  | Local Enhancement Epic | Backlog | E-533777 | E-533777 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-GDX-MS-Hide GDPP status on dotcom/mobile | Approved | Local Enhancement Epic | Commercial Portfolio | 0111252 |  |  | Local Enhancement Epic | Backlog | E-533780 | E-533780 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-GDX-FDP - Accepted License Agreement(s) Email | Approved | Local Enhancement Epic | Commercial Portfolio | 0111254 |  |  | Local Enhancement Epic | Build | E-533775 | E-533775 | 1: XS | 2025-08-22 |  |  | 2 | 0 | 1 | 1 | No | 2026-01-19 | 2026-01-19 | 2025-08-22
Local Enhancement Epic: COM-GDX-MS-Accepted License Agreement(s) Auth user | Approved | Local Enhancement Epic | Commercial Portfolio | 0111255 |  |  | Local Enhancement Epic | Build | E-533779 | E-533779 | 2: S | 2025-08-22 |  | 50% | 2 | 1 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2025-08-22
Local Enhancement Epic: COM-GDX-MS-Updt Org Details Email Notification | Approved | Local Enhancement Epic | Commercial Portfolio | 0111257 |  |  | Local Enhancement Epic | Build | E-533778 | E-533778 | 2: S | 2025-08-22 |  |  | 2 | 0 | 1 | 1 | No | 2026-01-19 | 2026-01-19 | 2025-08-22
Lifecycle Management Epic: COM - CSX - Telco Routing Regulatory Changes | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111258 |  |  | Lifecycle Management Epic | Backlog | E-530944 | E-530944 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-06 | 2026-06-12
Local Enhancement Epic: COM - CSX - MEISA Inbound/Outbound Number Change | Approved | Local Enhancement Epic | Commercial Portfolio | 0111260 |  |  | Local Enhancement Epic | Backlog | E-530943 | E-530943 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-06 | 2026-01-13
Lifecycle Management Epic: COM - CSX - GC3 Invoicing and Contracts | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111262 |  |  | Lifecycle Management Epic | Backlog | E-525323 | E-525323 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-18 | 2026-06-11
Lifecycle Management Epic: COM-CSX-CE VVA Benelux Caller Imprrmnt | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0111267 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-VA - Tracking looping UAT testing | Closed | Local Enhancement Epic | Commercial Portfolio | 0111272 |  |  | Local Enhancement Epic | Backlog | E-530200 | E-530200 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-TODS Modernization 4 Reports Updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0111273 |  |  | Local Enhancement Epic | Build | E-530690 | E-530690 | 1: XS | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-18 | 2026-06-18 | 2025-12-08
Local Enhancement Epic: COM-RS-FUSE - Order Creation optimizing | Approved | Local Enhancement Epic | Commercial Portfolio | 0111277 |  |  | Local Enhancement Epic | Build | E-526921 | E-526921 | 2: S | 2025-08-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-01 | 2026-08-25 | 2025-08-06
Lifecycle Management Epic: COM-RS-CY25PI04 LCM Patching Maint Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111278 |  |  | Lifecycle Management Epic | Build | E-524370 | E-524370 | 1: XS | 2025-08-26 |  | 20% | 5 | 1 |  | 4 | No |  |  | 2025-08-26
Lifecycle Management Epic: COM-RS-CY25PI05 LCM Patching Maint Upgrades | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111279 |  |  | Lifecycle Management Epic | Build | E-524371 | E-524371 | 1: XS | 2025-07-31 |  | 100% | 6 | 6 |  | 0 | No |  |  | 2025-07-31
Lifecycle Management Epic: COM-RS-CY25PI04 LCM Security & RELY NFRs | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111280 |  |  | Lifecycle Management Epic | Build | E-524369 | E-524369 | 1: XS | 2025-10-28 |  | 60% | 5 | 3 |  | 2 | No |  |  | 2025-10-28
Lifecycle Management Epic: COM-RS-CY25PI05 LCM Security & RELY NFRs | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111282 |  |  | Lifecycle Management Epic | Build | E-524372 | E-524372 | 1: XS | 2025-07-31 |  | 87.5% | 8 | 7 |  | 1 | No |  |  | 2025-07-31
Lifecycle Management Epic: COM-CSX-CE_DICE ART_Prod Defects & Support | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111287 |  |  | Lifecycle Management Epic | Backlog | E-530203 | E-530203 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_COM-CSX_DICE_LCM_Content Updates | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111290 |  |  | Lifecycle Management Epic | Backlog | E-530202 | E-530202 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI5_COM-CSX_DICE_LCM_Content Updates | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111291 |  |  | Lifecycle Management Epic | Backlog | E-533042 | E-533042 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-GC3 India Clearance Ops to a Non-CE Domain | Approved | Local Enhancement Epic | Commercial Portfolio | 0111293 |  |  | Local Enhancement Epic | Backlog | E-530942 | E-530942 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-06 | 2026-06-15
Lifecycle Management Epic: COM - CSX - Claims EDM 2.0 Final State | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111294 |  |  | Lifecycle Management Epic | Backlog | E-530199 | E-530199 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - CSX - Claims Prod Support-Production Defects | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111295 |  |  | Lifecycle Management Epic | Backlog | E-530198 | E-530198 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - CSX - eContact Migration to ECDC | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111297 |  |  | Lifecycle Management Epic | Backlog | E-530205 | E-530205 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - CSX - Claims - Login Re-engineering | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111298 |  |  | Lifecycle Management Epic | Backlog | E-530208 | E-530208 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - CSX - Claims Prot Purple Sec Vulnerabilities | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111299 |  |  | Lifecycle Management Epic | Backlog | E-530215 | E-530215 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - CSX - Claims System Stabilization | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111300 |  |  | Lifecycle Management Epic | Backlog | E-530213 | E-530213 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - CSX - Claims Protect Purple | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111302 |  |  | Lifecycle Management Epic | Backlog | E-530214 | E-530214 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: FY26_COM - CSX - CE - Polaris ART CCD Prd support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111303 |  |  | Lifecycle Management Epic | Backlog | E-524199 | E-524199 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-CSX-VA - Compliment/Complaint country check | Closed | Local Enhancement Epic | Commercial Portfolio | 0111308 |  |  | Local Enhancement Epic | Backlog | E-530201 | E-530201 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-VA - FedEx One Rate content update | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111309 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-VA - Incomprehension Form Implementation | Closed | Local Enhancement Epic | Commercial Portfolio | 0111310 |  |  | Local Enhancement Epic | Backlog | E-530204 | E-530204 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-VA - Schedule a Pickup - CA FR | Closed | Local Enhancement Epic | Commercial Portfolio | 0111312 |  |  | Local Enhancement Epic | Backlog | E-530206 | E-530206 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Commercial Portfolio creating visibility | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111336 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Visibility of weight range on ship label | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111338 | 9231 | DE_§73 Specifications for packages with increased | Biz w/ Tech Epic | Build | E-542860 | E-542860 | 3: M | 2026-02-28 |  | 66.67% | 3 | 2 |  | 1 | No | 2024-07-22 | 2026-04-01 | 2026-02-28
Biz w/ Tech Epic: Collection Letter Archive - eCIS update BwT | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111339 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - CSX - Global Telco Resiliency | Approved | Local Enhancement Epic | Commercial Portfolio | 0111359 |  |  | Local Enhancement Epic | Backlog | E-530945 | E-530945 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-07 | 2026-06-15
Local Enhancement Epic: COM-IA-GIX-APPLE-GENIUS_858 mapping change | Closed | Local Enhancement Epic | Commercial Portfolio | 0111360 |  |  | Local Enhancement Epic | Done | E-526723 | E-526723 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Lifecycle Management Epic: COM-CSX-Maintain and Evolve Global VA APIs | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0111361 |  |  | Lifecycle Management Epic | Backlog | E-530207 | E-530207 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM-CSX-ECAM Hope Adoption | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111362 |  |  | Lifecycle Management Epic | Backlog | E-525322 | E-525322 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-21
Local Enhancement Epic: COM - RMIC - Romania VAT Rate Change Aug'25 | Approved | Local Enhancement Epic | Commercial Portfolio | 0111363 |  |  | Local Enhancement Epic | Build | E-525667 | E-525667 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - US Inbound Processing Fee Rate Incr | Closed | Local Enhancement Epic | Commercial Portfolio | 0111391 |  |  | Local Enhancement Epic | Build | E-525259 | E-525259 | 1: XS | 2025-11-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-26
Local Enhancement Epic: COM - RMIC-GDX - F2F Pilot 3P Access Fee to APIs | Approved | Local Enhancement Epic | Commercial Portfolio | 0111392 |  |  | Local Enhancement Epic | Build | E-532071 | E-532071 | 2: S | 2025-12-06 |  |  | 2 | 0 | 1 | 1 | No | 2025-07-30 | 2025-10-07 | 2025-12-06
Local Enhancement Epic: COM-GDX-CP- ID (IAPI) for Internal CXS caller | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111393 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enable CIAM Support for Loyalty Portal Integration | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111414 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Integrate FedEx.com with Kobie-hosted Loyalty Port | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111413 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Validate Loyalty Fulfillment Partner Integrations | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111417 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Integrate Kobie Loyalty Data into FedEx Data Wareh | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111419 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update XAPI emails | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111422 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic Dashboard | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111423 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - EC Edit to Prevent Sending Dims | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111435 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Celonis: Database Connections for AR | On Hold | Local Enhancement Epic | Commercial Portfolio | 0111436 |  |  | Local Enhancement Epic | Build | E-543871 | E-543871 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM-GDX-FY26_FiT ART_ LCM_Prod Def Management | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111437 |  |  | Lifecycle Management Epic | Build | E-530666 | E-530666 | 2: S | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-07
Local Enhancement Epic: COM-GDX-[VIS]-Simplified tracking Signature enhan | Approved | Local Enhancement Epic | Commercial Portfolio | 0111438 |  |  | Local Enhancement Epic | Build | E-533776 | E-533776 | 2: S | 2026-02-03 |  | 100% | 1 | 1 |  | 0 | No | 2025-10-08 | 2025-12-30 | 2026-02-03
Local Enhancement Epic: COM - RMIC-GDX - Hybrid Integratn Updte Payer Auth | Approved | Local Enhancement Epic | Commercial Portfolio | 0111440 |  |  | Local Enhancement Epic | Build | E-549291 | E-549291 | 3: M | 2025-12-06 |  |  | 3 | 0 | 1 | 2 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - RMIC-LCM - P&RS Ephemeral Adoption FY26 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111441 |  |  | Lifecycle Management Epic | Build | E-526655 | E-526655 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - RMIC - FY26_FeatureTesting_using_SI_Pipeline | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111442 |  |  | Lifecycle Management Epic | Build | E-526656 | E-526656 | 3: M | 2025-08-21 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-21
Local Enhancement Epic: COM-RMIC-ROPs - EU D&T Proactive Rebill Dash | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111443 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Remove Invoice Messages | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111444 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Delay in File Processing (UME) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111445 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - RMIC-LCM - Rating Hardening Improvements | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111446 |  |  | Lifecycle Management Epic | Build | E-526651 | E-526651 | 2: S | 2025-09-04 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22 | 2025-09-04
Local Enhancement Epic: COM - RMIC - Enable D/T Import Bill GSP Countries | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111447 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - CAN EDI Resend EDI Files Incl Images | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111448 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM – IA -GIX - Eaton FUSE | Approved | Local Enhancement Epic | Commercial Portfolio | 0111449 |  |  | Local Enhancement Epic | Backlog | E-533166 | E-533166 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CDE-Unified Customer Profile Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0111450 |  |  | Local Enhancement Epic | Backlog | E-530317 | E-530317 | 5: XL |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - JOIN_FY26_MAGR_Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111451 |  |  | Lifecycle Management Epic | Build | E-530665 | E-530665 | 3: M | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-07
Lifecycle Management Epic: COM - GDX - CS - CY25_PI.04_FACTOR Sppt DSS ART | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111452 |  |  | Lifecycle Management Epic | Build | E-530668 | E-530668 | 1: XS | 2025-08-06 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-12-30 | 2025-08-06
Lifecycle Management Epic: COM-GDX-CS-FY25_PI.04_Offline Perf Tstng/TstngSup | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111453 |  |  | Lifecycle Management Epic | Build | E-530670 | E-530670 | 1: XS | 2025-08-07 |  | 100% | 1 | 1 |  | 0 | No | 2025-08-13 | 2025-10-22 | 2025-08-07
Local Enhancement Epic: COM-S&CDE-CRM Viva Engage Community for Rogers org | Closed | Local Enhancement Epic | Commercial Portfolio | 0111454 |  |  | Local Enhancement Epic | Build | E-528362 | E-528362 | 1: XS | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Lifecycle Management Epic: COM-S&CDE-CRM - LifeCycle Management CY25 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111455 |  |  | Lifecycle Management Epic | Backlog | E-525666 | E-525666 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM CT METL Migration | Approved | Local Enhancement Epic | Commercial Portfolio | 0111456 |  |  | Local Enhancement Epic | Backlog | E-528407 | E-528407 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM CT Assignments/Alignments/Atlantis | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111457 |  |  | Local Enhancement Epic | Build | E-528376 | E-528376 | 1: XS | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Local Enhancement Epic: COM-S&CDE-CRM CT FTIP Experience Support | Approved | Local Enhancement Epic | Commercial Portfolio | 0111458 |  |  | Local Enhancement Epic | Backlog | E-528410 | E-528410 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM - Deduplication of Leads in iSell | Closed | Local Enhancement Epic | Commercial Portfolio | 0111459 |  |  | Local Enhancement Epic | Build | E-525817 | E-525817 | 2: S | 2025-11-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-05
Local Enhancement Epic: COM-S&CDE-CRM - CE Agents Visblty to Status of CRs | Approved | Local Enhancement Epic | Commercial Portfolio | 0111460 |  |  | Local Enhancement Epic | Backlog | E-525816 | E-525816 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CRM - Missed P/Us to CEBS | On Hold | Local Enhancement Epic | Commercial Portfolio | 0111461 |  |  | Local Enhancement Epic | Backlog | E-525819 | E-525819 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-10-07
Biz w/ Tech Epic: ADS SFTP and Security Configuration (All Environme | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111462 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-CP-FDP Responsive Experience | Approved | Local Enhancement Epic | Commercial Portfolio | 0111463 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537899 | E-537899 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CP-FDP API Recipes | Approved | Local Enhancement Epic | Commercial Portfolio | 0111464 |  |  | Local Enhancement Epic | Build | E-530669 | E-530669 | 2: S | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-07
Local Enhancement Epic: COM-GDX-CP-FDP API Quota Management | Approved | Local Enhancement Epic | Commercial Portfolio | 0111465 |  |  | Local Enhancement Epic | Build | E-530673 | E-530673 | 3: M | 2025-08-07 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-07
Local Enhancement Epic: COM - RMIC - FO Rating Issue in PX Service Area | Approved | Local Enhancement Epic | Commercial Portfolio | 0111466 |  |  | Local Enhancement Epic | Backlog | E-536453 | E-536453 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Configure and Validate Loyalty Data Flow in Produc | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111468 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-CP-FDP Session Management | Approved | Local Enhancement Epic | Commercial Portfolio | 0111469 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537894 | E-537894 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - IA - GIX - ED350DP Production Enhancement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111472 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM - GSP CRM leads upload to iSell | Approved | Local Enhancement Epic | Commercial Portfolio | 0111474 |  |  | Local Enhancement Epic | Backlog | E-525818 | E-525818 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-10-07
Biz w/ Tech Epic: Design and Implement Loyalty Reporting Infrastruct | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0111483 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM - My Quote iSell Report Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0111486 |  |  | Local Enhancement Epic | Backlog | E-525815 | E-525815 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-11-14
Local Enhancement Epic: COM-S&CDE-CRM - Digital Svs Rev estimates in Oppty | Approved | Local Enhancement Epic | Commercial Portfolio | 0111487 |  |  | Local Enhancement Epic | Backlog | E-525814 | E-525814 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-29 | 2025-12-30
Local Enhancement Epic: COM-CSX-CashApps and CopyDocs GenAI Automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0111489 |  |  | Local Enhancement Epic | Backlog | E-526989 | E-526989 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: New Extra Small Box Package Type: Express Services | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0109359 | 7251 | New Extra Small Box Package Type: Express Services | Biz w/ Tech Epic | Build | E-449375 | E-449375 | 3: M | 2025-11-11 |  | 50% | 4 | 2 |  | 2 | No | 2024-07-22 | 2030-12-06 | 2025-11-11
Local Enhancement Epic: N701 header on EDI’s error | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111409 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: METL FedEx Net Modernization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111545 | 107715 | METL FedEx Net Modernization | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-12-31
Lifecycle Management Epic: COM-S&CDE-CDE_CY25_PI04_Testing & Configuration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111604 |  |  | Lifecycle Management Epic | Build | E-528617 | E-528617 | 1: XS | 2025-10-07 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-10-07
Local Enhancement Epic: COM-S&CDE-CRM - PCAC Redesign & Qtrly Refresh | Approved | Local Enhancement Epic | Commercial Portfolio | 0111605 |  |  | Local Enhancement Epic | Backlog | E-528081 | E-528081 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM - Live Chat Expansion APAC Mrkts | Closed | Local Enhancement Epic | Commercial Portfolio | 0111606 |  |  | Local Enhancement Epic | Build | E-528083 | E-528083 | 2: S | 2025-11-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-05
Local Enhancement Epic: COM-S&CDE-CRM - Update Special Service Options | Approved | Local Enhancement Epic | Commercial Portfolio | 0111607 |  |  | Local Enhancement Epic | Backlog | E-528080 | E-528080 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Enable Acct Contact Relationship | Approved | Local Enhancement Epic | Commercial Portfolio | 0111608 |  |  | Local Enhancement Epic | Backlog | E-528084 | E-528084 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Exception hierarchy Acct2 Territory | Approved | Local Enhancement Epic | Commercial Portfolio | 0111609 |  |  | Local Enhancement Epic | Backlog | E-528082 | E-528082 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: FAPI - Account Reg - PIN Validation window extend | Approved | Local Enhancement Epic | Commercial Portfolio | 0111611 |  |  | Local Enhancement Epic | Build | E-539447 | E-539447 | 1: XS | 2025-09-24 |  |  | 2 | 0 | 2 | 0 | No |  |  | 2025-09-24
Local Enhancement Epic: COM - RMIC-RD3 - TNT NZ/FJ Invoice Generation | Approved | Local Enhancement Epic | Commercial Portfolio | 0111618 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546164 | E-546164 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Change of VAT Rules on TR Ancillaries | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111622 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Ground Rating Modernization: Retail | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111624 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Backlog | E-526918 | E-526918 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-GDX-Shipping Account Cleanup - CAMP/MAGIC | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111625 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - NSB Implemtn for MEISA Billing | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111626 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-GAT-FXO API email enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0111627 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538757 | E-538757 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-11-05 | 2026-06-18
Lifecycle Management Epic: COM-IA-DART-FY26_PI4_Marketing Tagging_LCM | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0111629 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-RS-FXO API order response timing for Canva | Approved | Local Enhancement Epic | Commercial Portfolio | 0111631 |  |  | Local Enhancement Epic | Build | E-543247 | E-543247 | 2: S | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-08
Local Enhancement Epic: COM-RS28-FXO API Intl Credit Card used for Payment | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111632 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-FedEx Shipping Account addition | Approved | Local Enhancement Epic | Commercial Portfolio | 0111633 |  |  | Local Enhancement Epic | Build | E-527276 | E-527276 | 1: XS | 2026-04-13 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-14 | 2026-05-29 | 2026-04-13
Local Enhancement Epic: COM-RS-Disable discontinued media in FUSE, POD&PPA | Closed | Local Enhancement Epic | Commercial Portfolio | 0111634 |  |  | Local Enhancement Epic | Build | E-529870 | E-529870 | 1: XS | 2026-01-29 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-29
Local Enhancement Epic: COM-RS-Remove Monotype fonts from PPA | Closed | Local Enhancement Epic | Commercial Portfolio | 0111635 |  |  | Local Enhancement Epic | Build | E-529871 | E-529871 | 2: S | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Lifecycle Management Epic: COM - RMIC-LCM - GitHub Actions & RDSO | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111637 |  |  | Lifecycle Management Epic | Build | E-528227 | E-528227 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM - DART - CY25PI04 System Optimization | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0111639 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: COM-S&CDE-CRM Canada iSell Activity Updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0111645 |  |  | Local Enhancement Epic | Backlog | E-528374 | E-528374 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM Support Team iSell Activity Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111646 |  |  | Local Enhancement Epic | Build | E-528364 | E-528364 | 1: XS | 2026-01-14 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-14
Local Enhancement Epic: COM-S&CDE-CRM CT Leadership Case PowerBI Report | Approved | Local Enhancement Epic | Commercial Portfolio | 0111647 |  |  | Local Enhancement Epic | Backlog | E-536668 | E-536668 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Ground Rating Modernization: Duplicates | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111651 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Backlog | E-526919 | E-526919 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: WREG Error reduction | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111654 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Bulk Pickup Streamlining - Commercial | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0111665 | 8819 | Bulk Pickup Streamlining | Biz w/ Tech Epic | Backlog | E-532820 | E-532820 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: COM - GDX - JOIN_FY26_JOIN_Tech debt improvements | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0111673 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-CS-SS FSM v4000 COD removal | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111763 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-Addr Validation for Guest Authenticatio | Approved | Local Enhancement Epic | Commercial Portfolio | 0111764 |  |  | Local Enhancement Epic | Backlog | E-536748 | E-536748 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CS-DSS - FSM v4000 Hardware Ver. Clean Up | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111765 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-Eligibility for Guest Authentication | Approved | Local Enhancement Epic | Commercial Portfolio | 0111766 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539258 | E-539258 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Build Inv Traceability Screen in EDI | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111767 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-Sales Rep/CTC BCC on U2Q Quote | Approved | Local Enhancement Epic | Commercial Portfolio | 0111768 |  |  | Local Enhancement Epic | Backlog | E-530698 | E-530698 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-08-27 | 2025-11-04
Local Enhancement Epic: COM-GDX-Comprehensive Rate API Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0111769 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537551 | E-537551 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: Make commodity info optional for Rate & CRAT | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111770 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-RD3 - NG Tax eInvoicing FedEx & TNT | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111771 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-CP-FAPI - LISTRates for IntraCA Exp Shipmt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111772 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - US Holiday Demand Surcharges CY25 | Approved | Local Enhancement Epic | Commercial Portfolio | 0111773 |  |  | Local Enhancement Epic | Build | E-530275 | E-530275 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Lifecycle Management Epic: COM-S&CDE-CRM CY25 Compatible List Maintenance | Closed | Lifecycle Management Epic | Commercial Portfolio | 0111774 |  |  | Lifecycle Management Epic | Build | E-528363 | E-528363 | 1: XS | 2026-02-11 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-02-11
Local Enhancement Epic: COM-S&CDE-CRM Canada iSell Case Flow Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111775 |  |  | Local Enhancement Epic | Build | E-528357 | E-528357 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM-S&CDE-CRM LAC iSell Case Flow Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111776 |  |  | Local Enhancement Epic | Build | E-528361 | E-528361 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM-S&CDE-CRM APAC/Europe/MEISA Case Flow Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111777 |  |  | Local Enhancement Epic | Backlog | E-528360 | E-528360 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM EU Customer Survey Email Templates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111778 |  |  | Local Enhancement Epic | Build | E-528359 | E-528359 | 1: XS | 2025-11-11 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-11
Local Enhancement Epic: COM - RS - PRINT - Late Order Notifications (LE) | Approved | Local Enhancement Epic | Commercial Portfolio | 0111785 |  |  | Local Enhancement Epic | Build | E-530696 | E-530696 | 3: M | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-01-13 | 2025-12-08
Local Enhancement Epic: COM-S&CDE-CRM G2 Close Case Flow Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111790 |  |  | Local Enhancement Epic | Build | E-528375 | E-528375 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM-S&CDE-CRM Remove Training Support | Approved | Local Enhancement Epic | Commercial Portfolio | 0111791 |  |  | Local Enhancement Epic | Backlog | E-528358 | E-528358 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM Knowledge Article Recommendation | Closed | Local Enhancement Epic | Commercial Portfolio | 0111792 |  |  | Local Enhancement Epic | Build | E-528356 | E-528356 | 1: XS | 2025-11-11 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-11
Local Enhancement Epic: COM-S&CDE-CRM ShipView User Metrics Report | Approved | Local Enhancement Epic | Commercial Portfolio | 0111794 |  |  | Local Enhancement Epic | Build | E-528365 | E-528365 | 1: XS | 2025-08-08 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-08-08
Local Enhancement Epic: COM-S&CDE-CRM ShipView EPDI Viewer Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0111795 |  |  | Local Enhancement Epic | Build | E-528366 | E-528366 | 1: XS | 2025-08-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-08
Local Enhancement Epic: COM-S&CDE-CRM Migrate RealTime Meter to Ab Initio | Approved | Local Enhancement Epic | Commercial Portfolio | 0111796 |  |  | Local Enhancement Epic | Backlog | E-528408 | E-528408 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM Migrate Nightly Meter to Ab Initio | Closed | Local Enhancement Epic | Commercial Portfolio | 0111798 |  |  | Local Enhancement Epic | Build | E-528409 | E-528409 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM-RS-Enhcmnt for Specialty Products block displa | Closed | Local Enhancement Epic | Commercial Portfolio | 0111801 |  |  | Local Enhancement Epic | Build | E-530697 | E-530697 | 1: XS | 2025-10-17 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-17
Local Enhancement Epic: COM-RS28-Access to Workspace | Closed | Local Enhancement Epic | Commercial Portfolio | 0111802 |  |  | Local Enhancement Epic | Build | E-530693 | E-530693 | 1: XS | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-23
Local Enhancement Epic: COM-RS28-Magento Admin - Reset Shopping Cart | Closed | Local Enhancement Epic | Commercial Portfolio | 0111804 |  |  | Local Enhancement Epic | Build | E-530692 | E-530692 | 1: XS | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Local Enhancement Epic: COM-RS28-User Import Data Elements | Approved | Local Enhancement Epic | Commercial Portfolio | 0111805 |  |  | Local Enhancement Epic | Backlog | E-530695 | E-530695 | 1: XS |  |  |  | 2 | 0 |  | 2 | No | 2026-04-01 | 2026-05-29
Local Enhancement Epic: COM – IA -GIX - Richemont EU FUSE | Approved | Local Enhancement Epic | Commercial Portfolio | 0111833 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554831 | E-554831 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: CY25_PI05_COM - IA - GIX - GIX ART_I&A | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111834 |  |  | Lifecycle Management Epic | Backlog | E-533165 | E-533165 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Lifecycle Management Epic: COM-IA-GIX ART_FY26_Patching | Approved | Lifecycle Management Epic | Commercial Portfolio | 0111835 |  |  | Lifecycle Management Epic | Backlog | E-533171 | E-533171 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - S&CDE - CDE - CED Money Back Guarantee | Approved | Local Enhancement Epic | Commercial Portfolio | 0111838 |  |  | Local Enhancement Epic | Backlog | E-528645 | E-528645 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Shipper capabilities for CDOs offered to recipient | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111839 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Claims - FXE Canada Claims worked in ECD (TBD) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111842 | 130411 | FXE Canada Claims worked in ECD | Biz w/ Tech Epic | Assessment & Analysis | E-546758 | E-546758 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - M&I HC - Automate Cust Onboarding - INTL | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111857 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - M&I HC - Automate M&I - LEGAL | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0111858 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-PPA Retire-FUSE: File Manipulations | Approved | Local Enhancement Epic | Commercial Portfolio | 0111879 |  |  | Local Enhancement Epic | Build | E-536476 | E-536476 | 3: M | 2025-10-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-01-13 | 2025-10-23
Local Enhancement Epic: COM-RS28-PPA Retire-FUSE: Auto imposition | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111880 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-PPA Retire-FUSE:Adobe Creative Suite Conv | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111881 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-PPA Retire-FUSE: Long term storage | Approved | Local Enhancement Epic | Commercial Portfolio | 0111882 |  |  | Local Enhancement Epic | Backlog | E-530691 | E-530691 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: L1 EDI Checker Replacement | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0105139 | 9233 | EDI Checker Replacement | Biz w/ Tech Epic | Assessment & Analysis | E-492873 | E-492873 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS28-PPA Retire-FUSE: Auto Preflight | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111900 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-FASC Disputes - Scan - Order Of Operations | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111903 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-PPA Retire-FUSE Color Verification | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111907 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-Financial Controls for Claims Pymnts | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111911 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-WREG CN roll-out | Approved | Local Enhancement Epic | Commercial Portfolio | 0111913 |  |  | Local Enhancement Epic | Backlog | E-532325 | E-532325 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-GDX-MS-WREG - analytics tracking for country | Closed | Local Enhancement Epic | Commercial Portfolio | 0111914 |  |  | Local Enhancement Epic | Backlog | E-532321 | E-532321 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-GDX-RS-WREG experiment on intent | Approved | Local Enhancement Epic | Commercial Portfolio | 0111915 |  |  | Local Enhancement Epic | Backlog | E-532322 | E-532322 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-WREG Error reduction | Approved | Local Enhancement Epic | Commercial Portfolio | 0111916 |  |  | Local Enhancement Epic | Build | E-532326 | E-532326 | 2: S | 2026-03-19 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-03-19
Local Enhancement Epic: COM-S&CDE-CORE-IP/IE HeavyWeight Split in CRP | Approved | Local Enhancement Epic | Commercial Portfolio | 0111918 |  |  | Local Enhancement Epic | Backlog | E-532505 | E-532505 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-PRINT Platform Simplification App Builder | Approved | Local Enhancement Epic | Commercial Portfolio | 0111922 |  |  | Local Enhancement Epic | Backlog | E-532075 | E-532075 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-RS-PRINT Shift Left Test Automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0111923 |  |  | Local Enhancement Epic | Backlog | E-530694 | E-530694 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-S&CDE-CRM-SYNTHESIA | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111925 |  |  | Local Enhancement Epic | Build | E-530274 | E-530274 | 2: S | 2025-11-12 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-12
Local Enhancement Epic: COM-S&CDE-CRM-STORYLANE | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0111926 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-ACME-Secure OTC Release | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111929 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-IA-GIX-N701 header on EDI’s error | Approved | Local Enhancement Epic | Commercial Portfolio | 0111934 |  |  | Local Enhancement Epic | Backlog | E-533167 | E-533167 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-IA-GIX-Prod Tare weight EDI issue | Approved | Local Enhancement Epic | Commercial Portfolio | 0111935 |  |  | Local Enhancement Epic | Backlog | E-533164 | E-533164 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-12-31 | 2026-03-10
Local Enhancement Epic: COM-IA-GIX/GAF - Alcon - EDI 204/990 Data Mapping | Approved | Local Enhancement Epic | Commercial Portfolio | 0111980 |  |  | Local Enhancement Epic | Backlog | E-533172 | E-533172 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-IA-GIX/GAF - J&J EDI Conversion to JSON | Approved | Local Enhancement Epic | Commercial Portfolio | 0111981 |  |  | Local Enhancement Epic | Backlog | E-533168 | E-533168 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-IA-GIX-DOT FOODS | Approved | Local Enhancement Epic | Commercial Portfolio | 0111982 |  |  | Local Enhancement Epic | Backlog | E-533885 | E-533885 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-IA-GIX/GAF - J&J K&N IFCSUM to JSON Solution | Approved | Local Enhancement Epic | Commercial Portfolio | 0111983 |  |  | Local Enhancement Epic | Backlog | E-533169 | E-533169 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - RMIC-RD3 - CREDO Add Addtl Print Vendor | Approved | Local Enhancement Epic | Commercial Portfolio | 0111984 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543885 | E-543885 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS28-Store Number in Customer Generated POD | Closed | Local Enhancement Epic | Commercial Portfolio | 0111985 |  |  | Local Enhancement Epic | Build | E-539909 | E-539909 | 1: XS | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-23
Local Enhancement Epic: COM - RMIC - OPA/ODA Jan 2026 CSR File Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0111986 |  |  | Local Enhancement Epic | Build | E-538390 | E-538390 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Weight Based Fuel - BackDating (GAF) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0111988 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - RMIC - PRJ 853017 - eMBP Transformation Oct | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0111987 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Build | E-530210 | E-530210 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM-S&CDE-CRM Expand iSell Travel Form to Europe | Closed | Local Enhancement Epic | Commercial Portfolio | 0111989 |  |  | Local Enhancement Epic | Build | E-534535 | E-534535 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM-S&CDE-CRM CTC Case PowerBI Report | Approved | Local Enhancement Epic | Commercial Portfolio | 0111990 |  |  | Local Enhancement Epic | Backlog | E-534530 | E-534530 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM CT Data Conflict PowerBI Report | Closed | Local Enhancement Epic | Commercial Portfolio | 0111991 |  |  | Local Enhancement Epic | Build | E-534536 | E-534536 | 1: XS | 2025-11-11 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-11
Local Enhancement Epic: COM-S&CDE-CRM Decommission CT SQL Server | Closed | Local Enhancement Epic | Commercial Portfolio | 0111992 |  |  | Local Enhancement Epic | Build | E-534533 | E-534533 | 1: XS | 2026-03-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-03-10
Lifecycle Management Epic: COM-RS-Zund Cut Center (ZCC) Migration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112006 |  |  | Lifecycle Management Epic | Build | E-532078 | E-532078 | 1: XS | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2025-11-04 | 2025-12-08
Lifecycle Management Epic: COM-RS-Canon Pro 2600 and 6600 LF Printing | On Hold | Lifecycle Management Epic | Commercial Portfolio | 0112007 |  |  | Lifecycle Management Epic | Build | E-532076 | E-532076 | 1: XS | 2026-01-21 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2025-11-04 | 2026-01-21
Lifecycle Management Epic: COM-RS-Caldera 18.X and Primecenter 4.X Update | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112008 |  |  | Lifecycle Management Epic | Build | E-532073 | E-532073 | 2: S | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-06-02 | 2025-12-08
Local Enhancement Epic: COM-RS-SSAC UI Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0112009 |  |  | Local Enhancement Epic | Build | E-532074 | E-532074 | 1: XS | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2025-11-04 | 2025-12-08
Local Enhancement Epic: COM-GDX-Upgrade/Downgrade Service Options for FSMS | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112010 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RS - PRINT - Code Reusability & Maint (LE) | Approved | Local Enhancement Epic | Commercial Portfolio | 0112011 |  |  | Local Enhancement Epic | Build | E-533740 | E-533740 | 2: S | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-06-03 | 2025-12-08
Local Enhancement Epic: COM-RS-Epson DS-1730 Flatbed Document Scanner | Closed | Local Enhancement Epic | Commercial Portfolio | 0112012 |  |  | Local Enhancement Epic | Backlog | E-532079 | E-532079 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-GDX - Do Not Link Account Attribute Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0112036 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545722 | E-545722 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CP-Enable Single Packages FGE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112037 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-CP-FDP 3P Project Nomenclature | Approved | Local Enhancement Epic | Commercial Portfolio | 0112038 |  |  | Local Enhancement Epic | Build | E-532323 | E-532323 | 1: XS | 2025-08-13 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-13
Lifecycle Management Epic: COM - GDX - VIS-FY26 - SysOpt/Patching/ProdSupp | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112039 |  |  | Lifecycle Management Epic | Build | E-535264 | E-535264 | 3: M | 2025-08-27 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-08-27
Lifecycle Management Epic: COM - GDX - NOTF - LCM-FY26 -Spprt & Serv Now | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112040 |  |  | Lifecycle Management Epic | Backlog | E-532324 | E-532324 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM - RMIC - TH VAT Rate Change from 7% to 10% | Approved | Local Enhancement Epic | Commercial Portfolio | 0112042 |  |  | Local Enhancement Epic | Backlog | E-534808 | E-534808 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - eMBP Short Term Contracts | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112044 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM – IA -GIX - Electronic Document Upload (EDU) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112045 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: JP Clearance Ancillary Charge in CY26 | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0107595 |  |  | Local Enhancement Epic | Backlog | E-534723 | E-534723 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - GDX - PLC-FHD Conv Dlvry Optn (CDO) Chg | Approved | Local Enhancement Epic | Commercial Portfolio | 0112085 |  |  | Local Enhancement Epic | Build | E-536749 | E-536749 | 3: M | 2025-09-05 |  | 33.33% | 3 | 1 | 1 | 1 | No | 2026-01-19 | 2026-01-19 | 2025-09-05
Biz w/ Tech Epic: Epic 1D - MEISA | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112115 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | E-556928 | E-556928 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2026-03-11 | 2027-01-15
Local Enhancement Epic: COM-S&CDE-CRM-SpS Service Simplification | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112181 |  |  | Local Enhancement Epic | Backlog | E-531614 | E-531614 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-S&CDE-CRM-iSell RFP Data | Approved | Local Enhancement Epic | Commercial Portfolio | 0112182 |  |  | Local Enhancement Epic | Backlog | E-531613 | E-531613 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Canada BDA Case Changes - RS | Approved | Local Enhancement Epic | Commercial Portfolio | 0112184 |  |  | Local Enhancement Epic | Backlog | E-534537 | E-534537 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Customer Transition Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0112185 |  |  | Local Enhancement Epic | Backlog | E-534534 | E-534534 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - S&CDE- CDE -UC2 Int'l Journey Segmentation | Approved | Local Enhancement Epic | Commercial Portfolio | 0112186 |  |  | Local Enhancement Epic | Build | E-531590 | E-531590 | 1: XS | 2025-10-01 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-10-01
Local Enhancement Epic: COM - S&CDE - CDE -UC1 - Marketing Touch Addition | Approved | Local Enhancement Epic | Commercial Portfolio | 0112187 |  |  | Local Enhancement Epic | Backlog | E-531589 | E-531589 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - S&CDE - CDE - CJO Metrics Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0112188 |  |  | Local Enhancement Epic | Backlog | E-532141 | E-532141 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-FXO SSAC Credit Card Estimated Authorizat | Closed | Local Enhancement Epic | Commercial Portfolio | 0112244 |  |  | Local Enhancement Epic | Build | E-532524 | E-532524 | 1: XS | 2025-12-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-08
Local Enhancement Epic: COM-RS28-FUSE- Session Management Research | Approved | Local Enhancement Epic | Commercial Portfolio | 0112245 |  |  | Local Enhancement Epic | Backlog | E-532072 | E-532072 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-11-04 | 2026-03-25
Local Enhancement Epic: COM-RS28-FXO FUSE Customer Profile - Capture | Approved | Local Enhancement Epic | Commercial Portfolio | 0112246 |  |  | Local Enhancement Epic | Assessment & Analysis | E-547877 | E-547877 | 2: S |  |  |  | 3 | 0 |  | 3 | No | 2026-01-28 | 2026-06-16
Local Enhancement Epic: COM-RS-FASC Disputes Validation | Closed | Local Enhancement Epic | Commercial Portfolio | 0112247 |  |  | Local Enhancement Epic | Build | E-534938 | E-534938 | 1: XS | 2025-08-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-26
Local Enhancement Epic: COM-RS28-FUSE Voice of Team Member | Approved | Local Enhancement Epic | Commercial Portfolio | 0112248 |  |  | Local Enhancement Epic | Backlog | E-532077 | E-532077 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-GDX-MS-Mob-Home Scrn Trackng Exp (carryover) | Approved | Local Enhancement Epic | Commercial Portfolio | 0112249 |  |  | Local Enhancement Epic | Backlog | E-535267 | E-535267 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob-Tracking-Incld sort & enhnc filter | Approved | Local Enhancement Epic | Commercial Portfolio | 0112250 |  |  | Local Enhancement Epic | Backlog | E-535265 | E-535265 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob - Tracking - Enhance shipment list | Approved | Local Enhancement Epic | Commercial Portfolio | 0112251 |  |  | Local Enhancement Epic | Backlog | E-535263 | E-535263 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-FUSE Scan 2 way gun display | Closed | Local Enhancement Epic | Commercial Portfolio | 0112268 |  |  | Local Enhancement Epic | Backlog | E-533739 | E-533739 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Relax the phone length field in 3rd party APIs | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112276 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: IVA Epic 1 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0112324 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Five9 IVA Capability Enablement Epic 1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112326 | 113316 | Five9 IVA Capability Enablement | Biz w/ Tech Epic | Build | E-538772 | E-538772 | 3: M | 2026-01-28 |  | 100% | 1 | 1 |  | 0 | No | 2025-09-01 | 2025-10-15 | 2026-01-28
Local Enhancement Epic: COM - RMIC - GRCC/RPI FUSE/Oracle AR Discrepancy | Approved | Local Enhancement Epic | Commercial Portfolio | 0112331 |  |  | Local Enhancement Epic | Build | E-549295 | E-549295 | 2: S | 2025-11-11 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-11-11
Local Enhancement Epic: COM - RMIC-RD3 - TNT TH VAT Rate Change 7% to 10% | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112333 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Impl Zone Lvl Discounts Exp D/T Surch | Closed | Local Enhancement Epic | Commercial Portfolio | 0112340 |  |  | Local Enhancement Epic | Build | E-535972 | E-535972 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM - RMIC - AHS DIM MBW on eMBP | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112342 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-FUSE Customer Search Improvements | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112343 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS- Adobe Analytics | Approved | Local Enhancement Epic | Commercial Portfolio | 0112345 |  |  | Local Enhancement Epic | Backlog | E-533816 | E-533816 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-08-27 | 2025-11-04
Local Enhancement Epic: COM-RS-RetailShip - U.S. Version | Approved | Local Enhancement Epic | Commercial Portfolio | 0112347 |  |  | Local Enhancement Epic | Backlog | E-533815 | E-533815 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-08-27 | 2026-01-27
Local Enhancement Epic: COM - RMIC-RD3 - Credo Setup Rptg NCP Credit IRP | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112350 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SCO - Enhanced Global Returns - ETD Testing | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112367 | 9219 | Enhance Global Returns | Biz w/ Tech Epic | Backlog | E-536934 | E-536934 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-01-27
Local Enhancement Epic: COM - RMIC-RAA - ePAT Enhancement & Maintenance | Approved | Local Enhancement Epic | Commercial Portfolio | 0112399 |  |  | Local Enhancement Epic | Backlog | E-534431 | E-534431 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - CN VAT Rate Change (9% to 6%) | Approved | Local Enhancement Epic | Commercial Portfolio | 0112402 |  |  | Local Enhancement Epic | Build | E-535973 | E-535973 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Biz w/ Tech Epic: COM - RS - RET - Improve RMA Proc CEX and Efficien | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112437 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-534641 | E-534641 | 2: S | 2025-11-11 |  | 16.67% | 6 | 1 | 3 | 2 | No | 2025-08-27 | 2026-05-29 | 2025-11-11
Local Enhancement Epic: COM - RMIC - CSR Modernization | Approved | Local Enhancement Epic | Commercial Portfolio | 0112506 |  |  | Local Enhancement Epic | Build | E-535974 | E-535974 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Biz w/ Tech Epic: Contract to Collect: Epic 1 - Order Capture | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112509 | 97870 | Contract to Collect | Biz w/ Tech Epic | Assessment & Analysis | E-558768 | E-558768 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RMIC-STC - MY eInvng Crdt Note (Co Name) | Approved | Local Enhancement Epic | Commercial Portfolio | 0112544 |  |  | Local Enhancement Epic | Build | E-535266 | E-535266 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM - RMIC-STC - APAC LDP ID CoreTax Change | Approved | Local Enhancement Epic | Commercial Portfolio | 0112545 |  |  | Local Enhancement Epic | Build | E-545062 | E-545062 | 3: M | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM-RS28-NTEP Certification | Approved | Local Enhancement Epic | Commercial Portfolio | 0112546 |  |  | Local Enhancement Epic | Backlog | E-537189 | E-537189 | 1: XS |  |  |  | 1 | 0 | 1 | 0 | No | 2025-11-05 | 2026-01-13
Local Enhancement Epic: COM-RS28-FedEX Office Dry Ice Enablement | Closed | Local Enhancement Epic | Commercial Portfolio | 0112547 |  |  | Local Enhancement Epic | Backlog | E-537191 | E-537191 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-RS-Senseaware Phase III | Approved | Local Enhancement Epic | Commercial Portfolio | 0112548 |  |  | Local Enhancement Epic | Backlog | E-537188 | E-537188 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-08-27 | 2025-11-04
Local Enhancement Epic: COM-RS28-Items of Extraordinary Value- FUSE | Approved | Local Enhancement Epic | Commercial Portfolio | 0112549 |  |  | Local Enhancement Epic | Backlog | E-537198 | E-537198 | 2: S |  |  | 50% | 2 | 1 |  | 1 | No | 2025-08-04 | 2026-03-24
Local Enhancement Epic: COM-RS28-STAT44-Modify Shipmnt(Pending Litigation) | Closed | Local Enhancement Epic | Commercial Portfolio | 0112550 |  |  | Local Enhancement Epic | Backlog | E-537193 | E-537193 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Lifecycle Management Epic: COM-RS-MN High Volume Black and White Printer | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112551 |  |  | Lifecycle Management Epic | Build | E-536475 | E-536475 | 2: S | 2025-12-08 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2025-11-04 | 2025-12-08
Local Enhancement Epic: COM-RS28-CAS Payment Option | Approved | Local Enhancement Epic | Commercial Portfolio | 0112552 |  |  | Local Enhancement Epic | Backlog | E-537190 | E-537190 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-10-23 | 2026-03-25
Local Enhancement Epic: COM-RS28-After Pick Up Toggle | Approved | Local Enhancement Epic | Commercial Portfolio | 0112553 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566057 | E-566057 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-12-15 | 2026-04-15
Local Enhancement Epic: COM - RMIC - Correct Non-Revenue Mismatch | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112554 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-IA-GIX-FXF PT Issues | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112555 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - GDX-MS-FY26_JOIN_EandA ART_Prod Support | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0112556 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-Remove Automated Pickup Res (APU) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112558 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - IA – GIX Update inv110v41- L4_04 Logic | Approved | Local Enhancement Epic | Commercial Portfolio | 0112559 |  |  | Local Enhancement Epic | Backlog | E-534762 | E-534762 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-GIX-LEVI-EU-GERMANY-CENTIRO | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112560 |  |  | Local Enhancement Epic | Backlog | E-534763 | E-534763 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RMIC-ROPs - Inv/AWB Bulk lookup tool | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112561 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RMIC-ROPs - DT Dispute automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0112562 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539512 | E-539512 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Major Segment Attribute Derived | Approved | Local Enhancement Epic | Commercial Portfolio | 0112563 |  |  | Local Enhancement Epic | Backlog | E-534531 | E-534531 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Global Source of Truth for Verticals | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112564 |  |  | Local Enhancement Epic | Backlog | E-534538 | E-534538 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM-S&CDE-CRM-CRMA DDC Close Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0112565 |  |  | Local Enhancement Epic | Backlog | E-534532 | E-534532 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Expand Request Support for CE in EU | Approved | Local Enhancement Epic | Commercial Portfolio | 0112566 |  |  | Local Enhancement Epic | Backlog | E-534539 | E-534539 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-Revenue HZ_CUST_PROFILE_AMTS Copy | Approved | Local Enhancement Epic | Commercial Portfolio | 0112567 |  |  | Local Enhancement Epic | Backlog | E-535240 | E-535240 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-Revenue HZ_ORGANIZATION_PROFILES Copy | Approved | Local Enhancement Epic | Commercial Portfolio | 0112568 |  |  | Local Enhancement Epic | Backlog | E-535239 | E-535239 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: COM - RS - RET - Migration of FRT 2.0 to COLO DB | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112585 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-534640 | E-534640 | 2: S | 2025-11-11 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-05-29 | 2025-11-11
Local Enhancement Epic: COM-GDX-TD Packages ¦ Production Issue Fix | Approved | Local Enhancement Epic | Commercial Portfolio | 0112601 |  |  | Local Enhancement Epic | Build | E-538547 | E-538547 | 3: M | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-10-23
Biz w/ Tech Epic: System optimization of GDL | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112606 | 98435 | Digital-Enablers-Data collection & Analytics tool | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Implement standardized data collection for mobile | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112607 | 98435 | Digital-Enablers-Data collection & Analytics tool | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EMR OTC – Storage Fee (Canada) Enhancement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112617 | 104469 | EMR OTC – Storage Fee (Canada) Enhancement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-BOA North Platform Settlement Migration | Closed | Local Enhancement Epic | Commercial Portfolio | 0112622 |  |  | Local Enhancement Epic | Build | E-536474 | E-536474 | 3: M | 2025-10-23 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-10-23
Local Enhancement Epic: COM-S&CDE-CORE-GB ICR rev integration into CRP | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112624 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - FPOS New Chargs&FXO Price Chgs(Sep25) | Approved | Local Enhancement Epic | Commercial Portfolio | 0112631 |  |  | Local Enhancement Epic | Build | E-535159 | E-535159 | 1: XS | 2025-11-18 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2025-11-18
Local Enhancement Epic: RS:WS2API Migr-Registermeter-Secured Tool Request | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112634 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: RS:WS2API Migr-“Registermeter-Secured” Tool Access | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112635 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM-IA-CIS-STRATUS - DG restriction con FedEX API | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0112642 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-Wght Based Fuel-Online/Offline Rate Quotes | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112643 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - TOAD EMEA REPORT | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112644 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-MS-Get Support CTA Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0112648 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549392 | E-549392 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-CSX-FY26_PI4_ECCP_LCM_ EDGE Prod Supp | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112654 |  |  | Lifecycle Management Epic | Backlog | E-535571 | E-535571 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - ERA MBG Enhancement | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112659 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - ePRS LT Solution for GRM; PPM# 474126 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112660 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-TODS Modernization - Transaction Search | Closed | Local Enhancement Epic | Commercial Portfolio | 0112661 |  |  | Local Enhancement Epic | Backlog | E-537199 | E-537199 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-RS-TODS Modernization - Eliminate FCF Suspense | Closed | Local Enhancement Epic | Commercial Portfolio | 0112662 |  |  | Local Enhancement Epic | Backlog | E-537201 | E-537201 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-RS-TODS Modernization-New Accounting Module | Closed | Local Enhancement Epic | Commercial Portfolio | 0112663 |  |  | Local Enhancement Epic | Backlog | E-537202 | E-537202 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: COM-GDX-Inclusion of Disclaimer on FIDF Rate Quote | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112664 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS28-FXO-Commercial Click to Cash | Approved | Local Enhancement Epic | Commercial Portfolio | 0112665 |  |  | Local Enhancement Epic | Build | E-537192 | E-537192 | 3: M | 2025-10-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-27 | 2026-05-29 | 2025-10-23
Local Enhancement Epic: COM-GDX-MS-Mob RYDE Updates: ApplyTime Limit | Approved | Local Enhancement Epic | Commercial Portfolio | 0112666 |  |  | Local Enhancement Epic | Backlog | E-536751 | E-536751 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Invoice Restore Automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0112669 |  |  | Local Enhancement Epic | Build | E-543983 | E-543983 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM-S&CDE- CDE -Adding Channel Guidance Email APAC | Approved | Local Enhancement Epic | Commercial Portfolio | 0112670 |  |  | Local Enhancement Epic | Build | E-535659 | E-535659 | 1: XS | 2026-01-14 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-19 | 2026-01-19 | 2026-01-14
Local Enhancement Epic: COM - CSX - API Updates for CED Rating | Approved | Local Enhancement Epic | Commercial Portfolio | 0112683 |  |  | Local Enhancement Epic | Backlog | E-535640 | E-535640 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-CSX-API access for Shipment Comments(OG) | Approved | Local Enhancement Epic | Commercial Portfolio | 0112685 |  |  | Local Enhancement Epic | Backlog | E-535639 | E-535639 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2026-01-13
Local Enhancement Epic: COM-RS-Online Passport Photos | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112704 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-CP-FAPI - 3rd party Multi Factor Auth | Approved | Local Enhancement Epic | Commercial Portfolio | 0112705 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545720 | E-545720 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-STC - Update Virtual Bank Act No for JP | Approved | Local Enhancement Epic | Commercial Portfolio | 0112707 |  |  | Local Enhancement Epic | Build | E-540899 | E-540899 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM - RMIC - Add Pkg Bumping Message to LDP File | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112708 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-CSX-International STC Supp Optimization - LE | Approved | Local Enhancement Epic | Commercial Portfolio | 0112709 |  |  | Local Enhancement Epic | Backlog | E-535638 | E-535638 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-03-24
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_CART_Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112711 |  |  | Lifecycle Management Epic | Backlog | E-536667 | E-536667 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-CSX-Claims Documents and Pictures Metadata | Approved | Local Enhancement Epic | Commercial Portfolio | 0112712 |  |  | Local Enhancement Epic | Build | E-544526 | E-544526 | 1: XS | 2026-04-09 |  | 100% | 1 | 1 |  | 0 | No | 2025-12-24 | 2026-04-07 | 2026-04-09
Local Enhancement Epic: COM-IA-GIX-ATP 214 Custom Map Formating changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0112717 |  |  | Local Enhancement Epic | Backlog | E-537312 | E-537312 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-IA-GIX-Governement NGDS EDI 214 2025 updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0112719 |  |  | Local Enhancement Epic | Backlog | E-537314 | E-537314 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2026-03-10
Biz w/ Tech Epic: MVP | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0112735 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Personalisation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112736 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Progressive onboarding | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112738 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Improvements to registration | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112739 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Payment and subscription setup | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112741 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Organisation switcher | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0112743 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-RS:WS2API Migr-“Registermeter-Secured” | Approved | Local Enhancement Epic | Commercial Portfolio | 0112764 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538756 | E-538756 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM RS Azure XMPie (attempt 2) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112765 |  |  | Local Enhancement Epic | Backlog | E-536533 | E-536533 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: COM - RMIC - Jamaica C87 Export Entry Fee Dispute | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112806 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-S&CDE-CRM New Case Flow for EU Speed Team | Closed | Local Enhancement Epic | Commercial Portfolio | 0112807 |  |  | Local Enhancement Epic | Build | E-537281 | E-537281 | 1: XS | 2026-01-14 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-14
Local Enhancement Epic: COM-GDX-MS-Mob Accessibility: Form Control label | Approved | Local Enhancement Epic | Commercial Portfolio | 0112808 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539259 | E-539259 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Clrnc Entry Fee Tiers Low Cstms Value | Closed | Local Enhancement Epic | Commercial Portfolio | 0112809 |  |  | Local Enhancement Epic | Build | E-538243 | E-538243 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-12-06
Local Enhancement Epic: COM - RMIC - FAST Bill Product Code | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112811 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - Remove Disb Fee Waiver Crdt Card Acct | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112812 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - New Revenue Charge Codes | Approved | Local Enhancement Epic | Commercial Portfolio | 0112813 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559741 | E-559741 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM Update Global CTC Case Assignment | Closed | Local Enhancement Epic | Commercial Portfolio | 0112814 |  |  | Local Enhancement Epic | Build | E-537280 | E-537280 | 1: XS | 2025-11-07 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-07
Local Enhancement Epic: COM - RMIC - Regulatory e-Inv Changes Argentina | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112815 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM – IA -GIX - Walmart FUSE FGE | Approved | Local Enhancement Epic | Commercial Portfolio | 0112816 |  |  | Local Enhancement Epic | Backlog | E-537313 | E-537313 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - RMIC-STC - TH eTax Inv Submission to Revenue | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112817 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - TH VAT Rate Change (9/30/25) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0112818 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-First API Gateway Enabler Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0112819 |  |  | Local Enhancement Epic | Build | E-545721 | E-545721 | 3: M | 2026-03-11 |  | 50% | 2 | 1 |  | 1 | No | 2026-01-19 | 2026-01-19 | 2026-03-11
Biz w/ Tech Epic: PROJECT CENTAUR | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112824 | 104641 | ECD Preferred Future State | Biz w/ Tech Epic | Assessment & Analysis | E-546002 | E-546002 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2026-01-22 | 2028-01-31
Local Enhancement Epic: COM-GDX-DSS - GSM 2601 Sig. Options for Distri | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112828 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-Consume FXG Economy GDPP predictions | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112829 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM – IA -GIX - Footlocker FGE | Approved | Local Enhancement Epic | Commercial Portfolio | 0112853 |  |  | Local Enhancement Epic | Backlog | E-537315 | E-537315 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-GDX-Timed Notifications Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0112854 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537898 | E-537898 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: AHS OS Cubic Volume Threshold | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112888 | 148173 | AHS OS Cubic Volume Thresholds | Biz w/ Tech Epic | Build | E-554345 | E-554345 | 3: M | 2026-02-27 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2026-02-27
Local Enhancement Epic: COM-CSX-APAC-ID GC3 Call system-clrnc-CPE | Approved | Local Enhancement Epic | Commercial Portfolio | 0112911 |  |  | Local Enhancement Epic | Backlog | E-537110 | E-537110 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Expand additional enterprise source requirements | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112952 | 8420 | Digital-Enablers-Analytics | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Integrated Environment for our Analytic and ML | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112954 | 8420 | Digital-Enablers-Analytics | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Integrate with Activation Systems | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112956 | 8420 | Digital-Enablers-Analytics | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - JP Clearance Ancillary Charge CY26 | Approved | Local Enhancement Epic | Commercial Portfolio | 0112973 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552253 | E-552253 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - GDX - MS - FY26 Mobile LCM Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0112974 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-537897 | E-537897 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - GAF Rate/Zone Visibility | Approved | Local Enhancement Epic | Commercial Portfolio | 0112975 |  |  | Local Enhancement Epic | Build | E-553429 | E-553429 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - MBG Accuracy for MPS Shipments | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112976 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-RS-Separate XAPI Transaction Wrapper | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112978 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - [TH} VAT Adjustment | Not Started | Local Enhancement Epic | Commercial Portfolio | 0112979 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: COM - IA - DART - TNT.com - Italy Migration | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0112980 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 2- Metered Data Service | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112988 | 97870 | Contract to Collect | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 3- Invoice Solutioning | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0112989 | 97870 | Contract to Collect | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 4 - Payment Solutions | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112990 | 97870 | Contract to Collect | Biz w/ Tech Epic | Assessment & Analysis | E-580388 | E-580388 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 5 - Product ADS | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0112991 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Customer Pricing Contracting Experience | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0112993 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: COM - RMIC- PRJ 1673138 eMBP Transformation Jan'26 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112995 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Backlog | E-537169 | E-537169 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: GIX - EDI Platform Design, Backend Readiness | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112865 | 143551 | Project Fairway - Commercial Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-547133 | E-547133 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-GDX-Improve Customer Experience on CDOs | Approved | Local Enhancement Epic | Commercial Portfolio | 0113006 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539261 | E-539261 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-GDX-Improve Post PPODA Experience-tracking pg | Approved | Local Enhancement Epic | Commercial Portfolio | 0113007 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539260 | E-539260 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-10-08 | 2025-12-30
Lifecycle Management Epic: COM-GDX-FY26_COM_CAMP_ProductionSupport | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113008 |  |  | Lifecycle Management Epic | Build | E-551135 | E-551135 | 1: XS | 2025-11-03 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-11-03
Local Enhancement Epic: COM-RS-Update browser local storage attribute | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113009 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM-GDX-Pickup API v2: Product Requirements Doc. | Approved | Local Enhancement Epic | Commercial Portfolio | 0113010 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537895 | E-537895 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CORE-Atlantis UI Modernization | Approved | Local Enhancement Epic | Commercial Portfolio | 0113013 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537653 | E-537653 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob Trckng tile enhc- Add PPOD and ETDW | Approved | Local Enhancement Epic | Commercial Portfolio | 0113014 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537893 | E-537893 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM – IA -GIX - Adidas FUSE Implementation | Approved | Local Enhancement Epic | Commercial Portfolio | 0113016 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538567 | E-538567 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM-GDX-CP-EEI & ITN Endpoints Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0113017 |  |  | Local Enhancement Epic | Build | E-537896 | E-537896 | 1: XS | 2026-04-13 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2026-04-13
Local Enhancement Epic: COM-S&CDE-CRM-Adding CLOC number in CRMA Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0113020 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538546 | E-538546 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Product DIM: Svc/Product Standardize | Approved | Local Enhancement Epic | Commercial Portfolio | 0113021 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538545 | E-538545 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-MyPipeline Health Metrics | Approved | Local Enhancement Epic | Commercial Portfolio | 0113022 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538544 | E-538544 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: COM - FiT-ACCS Phase 2.5 New Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113031 | 154881 | APAC FiT: Phase 2.5 enhance for customer adoption | Biz w/ Tech Epic | Assessment & Analysis | E-557432 | E-557432 | 3: M |  |  |  | 201 | 0 |  | 201 | No | 2025-12-12 | 2026-11-30
Local Enhancement Epic: COM-GDX-API access for Shipment API | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113042 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC - CPG Enablement in Saudi Arabia | Approved | Local Enhancement Epic | Commercial Portfolio | 0113048 |  |  | Local Enhancement Epic | Build | E-543870 | E-543870 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 | No | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM-CSX-Addnl World Tariff Account Data Format | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113055 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GDX-MS-Notification Redesign - Phase 2 | Approved | Local Enhancement Epic | Commercial Portfolio | 0113056 |  |  | Local Enhancement Epic | Assessment & Analysis | E-547207 | E-547207 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: Merchant Delivery Management | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113074 | 130405 | Merchant Delivery Management | Biz w/ Tech Epic | Assessment & Analysis | E-556287 | E-556287 | 4: L |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Enable Trial and Demo Capabilities for Digital Pro | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113077 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Establish End-to-End Marketing Analytics and Attri | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113079 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Imade-booking excpt flow for CCD Iceland | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113096 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - CANCEL(BwT) - WhatsApp Oracle Integration | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113103 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-US/ CA IVR Tracking Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0113104 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543504 | E-543504 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-CSX-FY 26 US/ CA Configuration - DICE ART | Cancelled | Lifecycle Management Epic | Commercial Portfolio | 0113106 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-544911 | E-544911 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: EPIC B: Recient Email Address for Notification | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0113114 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM- Epic 1-AE MKTPL Sys Integ- EAN Billing | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112467 | 7160 | Special Services - US | Biz w/ Tech Epic | Build | E-537719 | E-537719 | 4: L | 2025-09-18 |  |  | 5 | 0 | 3 | 2 |  | 2025-07-30 | 2026-10-30 | 2025-09-18
Local Enhancement Epic: COM-GDX-Limited Anon View and Blocked Anon View En | Approved | Local Enhancement Epic | Commercial Portfolio | 0113118 |  |  | Local Enhancement Epic | Build | E-537720 | E-537720 | 2: S | 2025-09-12 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-30 | 2025-09-12
Biz w/ Tech Epic: test epic | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113125 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FR Day Definite product vis fedex.com | Approved | Local Enhancement Epic | Commercial Portfolio | 0113130 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551136 | E-551136 | 1: XS |  |  |  | 2 | 0 |  | 2 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-FDX-Office POD Review & Submit UI Imprvmnt | Approved | Local Enhancement Epic | Commercial Portfolio | 0113132 |  |  | Local Enhancement Epic | Build | E-538242 | E-538242 | 1: XS | 2026-01-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-14 | 2026-05-29 | 2026-01-22
Local Enhancement Epic: COM-RS-FXO Retail 26 - AI Product Recommendations | Approved | Local Enhancement Epic | Commercial Portfolio | 0113134 |  |  | Local Enhancement Epic | Build | E-538773 | E-538773 | 1: XS | 2026-01-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-06-03 | 2026-01-22
Local Enhancement Epic: COM – IA -GIX - Dick's Sporting Goods - FUSE | Approved | Local Enhancement Epic | Commercial Portfolio | 0113135 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539150 | E-539150 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-07-30 | 2025-10-07
Local Enhancement Epic: COM – IA -GIX - Victoria's Secret - FUSE - IPD | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113136 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Clearance Entry Fee CA/US Discnt Fix | Approved | Local Enhancement Epic | Commercial Portfolio | 0113137 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554031 | E-554031 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-Automated Retry mechanism for confirmed 3p | Approved | Local Enhancement Epic | Commercial Portfolio | 0113152 |  |  | Local Enhancement Epic | Build | E-543246 | E-543246 | 2: S | 2026-03-17 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-14 | 2026-05-29 | 2026-03-17
Biz w/ Tech Epic: Epic 1 - FedEx Authenticated Delivery | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113153 | 7777 | FedEx Authenticated Delivery | Biz w/ Tech Epic | Build | E-543770 | E-543770 | 5: XL | 2026-01-22 |  |  | 3 | 0 | 1 | 2 |  | 2025-09-24 | 2027-05-18 | 2026-01-22
Lifecycle Management Epic: COM - CSX - US/CA IVR Lifecycle Management PIO3 | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0113154 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Closing the Fraud Feedback Loop | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113155 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-10-30
Local Enhancement Epic: COM - RMIC - GRI Global Disbursement Fee 2026 | Approved | Local Enhancement Epic | Commercial Portfolio | 0113156 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554030 | E-554030 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RMIC - INVG FDS: Reduce Artifact Footprint | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113157 |  |  | Lifecycle Management Epic | Build | E-540801 | E-540801 | 2: S | 2025-10-07 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-10-07
Local Enhancement Epic: COM-IA -GIX - PPFS CSV Address Logic Change | Approved | Local Enhancement Epic | Commercial Portfolio | 0113160 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538566 | E-538566 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-07-30 | 2025-10-07
Local Enhancement Epic: Trimposer Graphic Whizard SCC Template Software | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113183 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Currency Code Request XCG for Curacao/St Maarten | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113198 | 106783 | Currency Code Request XCG for Curacao/St Maarten | Biz w/ Tech Epic | Assessment & Analysis | E-563782 | E-563782 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-04-13 | 2026-07-28
Biz w/ Tech Epic: GPS Proof of Delivery for EU Inbound Shipments | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113230 | 143243 | GPS Proof of Delivery for EU Inbound Shipments | Biz w/ Tech Epic | Build | E-543812 | E-543812 | 3: M | 2025-10-28 |  | 25% | 4 | 1 | 1 | 2 |  | 2024-07-22 | 2034-06-30 | 2025-10-28
Biz w/ Tech Epic: Phase 1 - CIA Tool, Enhancement to Legacy Platform | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113273 | 154446 | CIA Tool Transformaton | Biz w/ Tech Epic | Assessment & Analysis | E-565823 | E-565823 | 2: S |  |  |  | 2 | 0 |  | 2 |  | 2026-01-05 | 2026-05-01
Local Enhancement Epic: COM-GDX-MAGR 300 MPS Quote Capability | Closed | Local Enhancement Epic | Commercial Portfolio | 0113310 |  |  | Local Enhancement Epic | Assessment & Analysis | E-547208 | E-547208 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Signature Services for IPD/IED | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113316 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-OnSite Progressive Web Application (PWA) | Approved | Local Enhancement Epic | Commercial Portfolio | 0113318 |  |  | Local Enhancement Epic | Build | E-543613 | E-543613 | 2: S | 2025-10-09 |  |  | 1 | 0 | 1 | 0 |  | 2025-11-05 | 2026-01-13 | 2025-10-09
Local Enhancement Epic: COM-GDX-PL - Config New Retail Network in P4e | Approved | Local Enhancement Epic | Commercial Portfolio | 0113320 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545276 | E-545276 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Tracking FAQs | Approved | Local Enhancement Epic | Commercial Portfolio | 0113321 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544391 | E-544391 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-S&CDE-CRM - ServiceMaxUpgrade | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113322 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-539571 | E-539571 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3 - Kenya Buyer info to be passed | Approved | Local Enhancement Epic | Commercial Portfolio | 0113323 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558828 | E-558828 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob Humanized Tone Progress Bar updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0113324 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540637 | E-540637 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob- Add out for delivery filter | Approved | Local Enhancement Epic | Commercial Portfolio | 0113325 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540636 | E-540636 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RMIC-RD3 - Orange Invoicing Dashboard | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0113326 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-FUSE Order Entry of (130lb Paper ) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113327 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-NSR messaging for FDMi 6005 email | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113328 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-RD3 - Global Account Exception CQL | Approved | Local Enhancement Epic | Commercial Portfolio | 0113329 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558969 | E-558969 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-FY25_PI05_Unified (API + Webhooks) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113330 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Empathetic,Action riented Prompts for DE | Approved | Local Enhancement Epic | Commercial Portfolio | 0113331 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544392 | E-544392 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Invalid trk number experience imprvmnt | Approved | Local Enhancement Epic | Commercial Portfolio | 0113332 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544390 | E-544390 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Migrate Plain Text Emails to HTML Email | Approved | Local Enhancement Epic | Commercial Portfolio | 0113333 |  |  | Local Enhancement Epic | Assessment & Analysis | E-547209 | E-547209 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob RYDE survey - Expansion to Canada | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113334 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - GDX- WREG - HOPE 2.0 integration (part 2) | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113335 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Trimposer Graphic Whizard SCC Template Soft | Approved | Local Enhancement Epic | Commercial Portfolio | 0113336 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559442 | E-559442 | 1: XS |  |  |  | 2 | 0 |  | 2 |  | 2026-03-25 | 2026-05-29
Local Enhancement Epic: COM-IA-Business Partner Mapping- Local | Approved | Local Enhancement Epic | Commercial Portfolio | 0113337 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543113 | E-543113 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-RS-Essendant: Simple products display Enc. | Approved | Local Enhancement Epic | Commercial Portfolio | 0113338 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539908 | E-539908 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-06-16
Local Enhancement Epic: COM-RS-CAS/NDC as Tender/Discount type with SSAC | Approved | Local Enhancement Epic | Commercial Portfolio | 0113339 |  |  | Local Enhancement Epic | Build | E-554467 | E-554467 | 3: M | 2026-01-22 |  |  | 2 | 0 | 1 | 1 |  | 2026-01-14 | 2026-05-29 | 2026-01-22
Local Enhancement Epic: COM - RMIC-GDX - Curr Convrsn Bulgarian Lev-Euro | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113394 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Digital Media Commercialization | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113398 | 133494 | Digital Media Commercialization | Biz w/ Tech Epic | Assessment & Analysis | E-580948 | E-580948 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-10-23
Lifecycle Management Epic: COM-IA-DART-FY26_PI5_Marketing Tagging_LCM | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0113408 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Incl 5.26 VN IB FRT VAT Othr Cntries | Approved | Local Enhancement Epic | Commercial Portfolio | 0113411 |  |  | Local Enhancement Epic | Build | E-543867 | E-543867 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Payor Code Logic US Dom Shpmnts | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113412 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FIT US Doc Upload Standard | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113426 | 8848 | Doc Upload | Biz w/ Tech Epic | Assessment & Analysis | E-540166 | E-540166 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2027-01-08
Biz w/ Tech Epic: EMR OTC - Paper Invoicing Fee EU, CA, and LAC | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113436 | 126301 | EMR OTC - Paper Invoicing Fee EU, CA, and LAC | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - RS - RET - Create Partial Status for RMAs | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113453 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-540429 | E-540429 | 2: S | 2025-09-26 |  | 100% | 1 | 1 |  | 0 |  | 2025-08-27 | 2026-05-29 | 2025-09-26
Local Enhancement Epic: COM-S&CDE-CDE-Sales Cloud to MC Lead Sync | Approved | Local Enhancement Epic | Commercial Portfolio | 0113463 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539958 | E-539958 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-Customer Onboarding Journey segment | Approved | Local Enhancement Epic | Commercial Portfolio | 0113464 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539990 | E-539990 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-DSFS Activation Journey - Updates | Approved | Local Enhancement Epic | Commercial Portfolio | 0113465 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539989 | E-539989 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-APAC Supplies Automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0113466 |  |  | Local Enhancement Epic | Build | E-539907 | E-539907 | 1: XS | 2026-01-14 |  | 100% | 1 | 1 |  | 0 |  | 2026-01-19 | 2026-01-19 | 2026-01-14
Local Enhancement Epic: COM-S&CDE-CDE-DSM Customer auto response | Approved | Local Enhancement Epic | Commercial Portfolio | 0113467 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539906 | E-539906 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-Add Data Cloud Segmentation for EU | Approved | Local Enhancement Epic | Commercial Portfolio | 0113468 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539905 | E-539905 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-MyComp Phase 2 Features | Approved | Local Enhancement Epic | Commercial Portfolio | 0113469 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540098 | E-540098 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Exception Global IDs | Approved | Local Enhancement Epic | Commercial Portfolio | 0113470 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540102 | E-540102 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-GSA Case Revisions | Approved | Local Enhancement Epic | Commercial Portfolio | 0113471 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540099 | E-540099 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-CARE Case Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0113472 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540101 | E-540101 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Digital Commerce Solution Case Chgs | Approved | Local Enhancement Epic | Commercial Portfolio | 0113473 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540103 | E-540103 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Pilot BDS Role in LAC | Approved | Local Enhancement Epic | Commercial Portfolio | 0113474 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540105 | E-540105 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-EU MyTerritory - Add FXL Revenue | Approved | Local Enhancement Epic | Commercial Portfolio | 0113475 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540100 | E-540100 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-EU/Glbl My Terr - Express HW visible | Approved | Local Enhancement Epic | Commercial Portfolio | 0113476 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540104 | E-540104 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - GRI Tool Enhancement Undo Feature | Approved | Local Enhancement Epic | Commercial Portfolio | 0113477 |  |  | Local Enhancement Epic | Build | E-547730 | E-547730 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Post Cash CAS View at Bill-to Level | Approved | Local Enhancement Epic | Commercial Portfolio | 0113478 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549293 | E-549293 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RMIC - FDS: Qrtly Upgrade 3rd Party S/W | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113479 |  |  | Lifecycle Management Epic | Build | E-540898 | E-540898 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - ERA Chrge Code 924 Mappg & Automation | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113480 |  |  | Local Enhancement Epic | Build | E-549296 | E-549296 | 1: XS | 2025-11-06 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2025-11-06
Local Enhancement Epic: COM - RMIC - Turkey/Poland Use Next Day as Inv Dat | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113481 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-MS-Mob-HomeScreen-Welcome tile enhnc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113482 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-03-02
Local Enhancement Epic: COM-GDX-CP-FDP Alignment with WCAG/ADA Guidelines | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113483 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP Alignment of UI Patterns | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113484 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP SEO Optimization | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113485 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP CTAs on Docs Headers | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113486 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP Global Search | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113487 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Updt pages to have titles instead of URLs | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113488 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-{VIS}-Promote mobile app on mobile web | Approved | Local Enhancement Epic | Commercial Portfolio | 0113489 |  |  | Local Enhancement Epic | Build | E-540635 | E-540635 | 5: XL | 2026-02-03 |  | 100% | 1 | 1 |  | 0 |  | 2025-10-08 | 2025-12-30 | 2026-02-03
Local Enhancement Epic: COM-GDX-FDP Getting Started Guide Phase 2 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113490 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FSMS Grnd Eco Rate Zones CRSV Correction | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113491 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM -IA- DART_CY25_PI05_System Optimization | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113492 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-550104 | E-550104 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: FIT Doc Upload US | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113499 | 108661 | Clearance Doc/info uploadTAXID | Biz w/ Tech Epic | Assessment & Analysis | E-582024 | E-582024 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-04-08 | 2026-11-04
Biz w/ Tech Epic: FIT Doc Upload LAC | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113500 | 108661 | Clearance Doc/info uploadTAXID | Biz w/ Tech Epic | Assessment & Analysis | E-582023 | E-582023 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2026-11-03
Biz w/ Tech Epic: Recipient Management of Delivery Preferences | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108054 | 7836 | Delivery PFS - Commercial Delivery Management Phas | Biz w/ Tech Epic |  | E-540289 | E-540289 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2025-12-02 | 2026-04-17
Biz w/ Tech Epic: Vintage Address Retirement | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0108166 | 7836 | Delivery PFS - Commercial Delivery Management Phas | Biz w/ Tech Epic |  | E-540288 | E-540288 | 5: XL |  |  |  | 2 | 0 |  | 2 |  | 2025-11-12 | 2027-01-19
Local Enhancement Epic: Infosec - Memcyco POC in WREG | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113554 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: 781967 - FXO Omni-Channel Profile - Phase 2 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113568 | 86367 | FXO Omni-Channel Experience - Profile Unification | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-06-03 | 2027-01-12
Biz w/ Tech Epic: 781967 - FXO Omni-Channel Profile - Phase 3 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113569 | 86367 | FXO Omni-Channel Experience - Profile Unification | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2027-01-13 | 2028-01-11
Biz w/ Tech Epic: 781967 - FXO Omni-Channel Profile - Phase 4 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113570 | 86367 | FXO Omni-Channel Experience - Profile Unification | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2028-01-12 | 2028-10-19
Biz w/ Tech Epic: COM - RS - RET - Develop Amazon Return Solution | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113572 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-540633 | E-540633 | 1: XS | 2025-09-29 |  | 33.33% | 3 | 1 | 1 | 1 |  | 2025-08-27 | 2026-05-29 | 2025-09-29
Local Enhancement Epic: COM-GDX-FY25_PI05_1P - Ability to host integrator | Approved | Local Enhancement Epic | Commercial Portfolio | 0113579 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545277 | E-545277 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-FY25_PI05_1P-Ability to create a Unified | Approved | Local Enhancement Epic | Commercial Portfolio | 0113580 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545271 | E-545271 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-FY25_PI05_1P-Ability to search EANs | Approved | Local Enhancement Epic | Commercial Portfolio | 0113581 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545270 | E-545270 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Error Correction Dim Rounding Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0113583 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551137 | E-551137 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-STC - ABS Enhncmnt Inbound &3P Billing | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113596 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-RD3 - TR G2D_Minor Enhcmnts for CREDO | Closed | Local Enhancement Epic | Commercial Portfolio | 0113597 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554302 | E-554302 | 1: XS |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM-CSX-CEIT FY26 Vulnerability Remediation | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0113598 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-CSX-CEIT FY26 Infrastructure Upgrades | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113600 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-573717 | E-573717 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Loading spinner for shopify shop app users | Approved | Local Enhancement Epic | Commercial Portfolio | 0113601 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545268 | E-545268 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3 - REMOVING QR CODE FROM CHY EURO | Approved | Local Enhancement Epic | Commercial Portfolio | 0113602 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557872 | E-557872 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-CSX-US/CA-IVR Enhancements PI05 | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113603 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-CSX DICE Configuration Changes FY26 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113604 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-544586 | E-544586 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-08-13 | 2026-05-29
Lifecycle Management Epic: COM - RMIC - Invg FDS: Validate Inv Images Size | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113606 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-543868 | E-543868 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM - RMIC - Invg FDS: Internationaliztn OpenText | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113607 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-543872 | E-543872 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CP-FDP Add to projects from catalog | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113608 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP Paid Products Dashboards & Reports | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113609 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP Improved Released Notes | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113610 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-GIX/GAF - BMS via CH Robinson EDI messages | Approved | Local Enhancement Epic | Commercial Portfolio | 0113611 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541687 | E-541687 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-S&CDE-CRM-Executive Insights | Approved | Local Enhancement Epic | Commercial Portfolio | 0113612 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541391 | E-541391 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CP-FDP 1DX Design Alignment | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113613 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-FDP Page Loading Performance | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113614 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-CP-FDP 1DX CSS Library Alignment | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0113615 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - Fiji VAT Monitoring System (VMS) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113617 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - FPOS New Chargs&FXO Price Chgs(Oct25) | Approved | Local Enhancement Epic | Commercial Portfolio | 0113618 |  |  | Local Enhancement Epic | Build | E-541808 | E-541808 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: LSSI Integration for FXO Location data | Closed | Local Enhancement Epic | Commercial Portfolio | 0106971 |  |  | Local Enhancement Epic | Build | E-516564 | E-516564 | 1: XS | 2025-07-31 |  | 66.67% | 3 | 2 |  | 1 | No |  |  | 2025-07-31
Lifecycle Management Epic: COM-CSX GC3 BCDR Maintenance | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113667 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-543503 | E-543503 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-01 | 2026-05-29
Biz w/ Tech Epic: Account Setup & Maintenance Portals | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113669 | 113849 | COM-CSX-ARMOR | Biz w/ Tech Epic | Backlog | E-571254 | E-571254 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2028-03-24
Biz w/ Tech Epic: Account Maintenance Portals | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0113670 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Analytics & Reporting | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0113671 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: User Authentication & Access Control | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0113672 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: WAAA Modernization | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0113673 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-[WIN] Samsung Suwon Integration | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113693 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-CED Dim Rounding Changes | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113694 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_CTiSell_Prod Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113695 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542040 | E-542040 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_CTAssignments_Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113696 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542260 | E-542260 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_BLS_Production Suppor | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113697 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542572 | E-542572 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_ShipView_Prod_Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113698 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542569 | E-542569 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_iTrade_Prod Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113699 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542571 | E-542571 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-FY25_PI04_Sandbox Findability Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0113700 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545278 | E-545278 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM New Close Flow for Support Teams | Closed | Local Enhancement Epic | Commercial Portfolio | 0113701 |  |  | Local Enhancement Epic | Build | E-542038 | E-542038 | 1: XS | 2026-01-14 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-14
Local Enhancement Epic: COM-S&CDE-CRM Expand iSell Travel Form to AMEA | Approved | Local Enhancement Epic | Commercial Portfolio | 0113702 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542039 | E-542039 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-EDTW Enhncmnt-Rmve commit time in tracking | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113703 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-S&CDE-FY26_COM_CRM ART_Sharepoint_Prod_Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113704 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542570 | E-542570 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: EMR OTC-[APAC] Regulatory Fee in AU NZ | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0113707 | 91207 | EMR OTC-[APAC] Regulatory Fee in AU NZ | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-05-29
Biz w/ Tech Epic: Epic 2 - Digital Signature Release for DSR | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113713 | 7777 | FedEx Authenticated Delivery | Biz w/ Tech Epic | Assessment & Analysis | E-571553 | E-571553 | 3: M |  |  |  | 2 | 0 |  | 2
Biz w/ Tech Epic: Epic 3 - Discontinue ISR | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113714 | 7777 | FedEx Authenticated Delivery | Biz w/ Tech Epic | Assessment & Analysis | E-571552 | E-571552 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: E2: DTH for Canada Domestic Ground Shipment | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113779 | 87034 | Canada - Domestic Ground Weekend Delivery | Biz w/ Tech Epic | Assessment & Analysis | E-554186 | E-554186 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-02-09 | 2026-06-09
Local Enhancement Epic: COM - RMIC - FBO Batch Secondary Account Linking | Approved | Local Enhancement Epic | Commercial Portfolio | 0113802 |  |  | Local Enhancement Epic | Build | E-552255 | E-552255 | 4: L | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - FBO Remove Non-Admin Users From Acct | Approved | Local Enhancement Epic | Commercial Portfolio | 0113803 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554032 | E-554032 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FBO Add Dispute Summary Report File | Approved | Local Enhancement Epic | Commercial Portfolio | 0113805 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553428 | E-553428 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FBO Credit Note Rprt Avail All Frmts | Approved | Local Enhancement Epic | Commercial Portfolio | 0113806 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554552 | E-554552 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FBO New Invoice Table Dispute Icons | Approved | Local Enhancement Epic | Commercial Portfolio | 0113807 |  |  | Local Enhancement Epic | Build | E-554551 | E-554551 | 2: S | 2026-03-16 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2026-03-16
Local Enhancement Epic: COM - RMIC - FBO Allow Mass Document Download | Approved | Local Enhancement Epic | Commercial Portfolio | 0113808 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554553 | E-554553 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - GRI Tool DCO Feature New G3P Zones | Approved | Local Enhancement Epic | Commercial Portfolio | 0113809 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552256 | E-552256 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-CSX DICE-IVR/VA Enhancements FY26 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113885 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-544204 | E-544204 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-05-29
Local Enhancement Epic: COM-GDX-Prompt CDO Options through Notifications | Approved | Local Enhancement Epic | Commercial Portfolio | 0113898 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549393 | E-549393 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Delivery Instructions Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0113899 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552504 | E-552504 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-CSX Five9 Software Updates, Upgrades & Reports | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113903 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-544885 | E-544885 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-05-29
Lifecycle Management Epic: COM-GDX-CS-CY25_PI.05_Offline Perf Tstng/TstngSup | Completed | Lifecycle Management Epic | Commercial Portfolio | 0113904 |  |  | Lifecycle Management Epic | Build | E-545273 | E-545273 | 1: XS | 2026-03-11 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-03-11
Lifecycle Management Epic: COM - GDX - CS - CY25_PI.05_FACTOR Sppt DSS ART | Approved | Lifecycle Management Epic | Commercial Portfolio | 0113905 |  |  | Lifecycle Management Epic | Build | E-545275 | E-545275 | 1: XS | 2026-03-11 |  | 100% | 1 | 1 |  | 0 |  | 2025-10-22 | 2026-01-13 | 2026-03-11
Local Enhancement Epic: COM-GDX-MS-Mob Show RTH/HAL addrs on progress bar | Approved | Local Enhancement Epic | Commercial Portfolio | 0113906 |  |  | Local Enhancement Epic | Assessment & Analysis | E-547204 | E-547204 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM-RS-FXO Self-Serve Print from QR Code | Approved | Local Enhancement Epic | Commercial Portfolio | 0113907 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552656 | E-552656 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-14 | 2026-05-29
Local Enhancement Epic: COM-RMIC-ROPs - Email for Duty & Tax Invoices | Approved | Local Enhancement Epic | Commercial Portfolio | 0113908 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550558 | E-550558 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Add shipper /Recipient email in track | Approved | Local Enhancement Epic | Commercial Portfolio | 0113909 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552503 | E-552503 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - IA - CIS - FY26_CIS_Simple Enhancements | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113910 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Report Missing Package Confirmation Page | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113911 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Suppliers site ID field into RDAT | Closed | Local Enhancement Epic | Commercial Portfolio | 0113912 |  |  | Local Enhancement Epic | Build | E-560637 | E-560637 | 2: S | 2026-01-23 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-23
Local Enhancement Epic: HAL Inventory Visibility & RS Return Alerts | Approved | Local Enhancement Epic | Commercial Portfolio | 0113913 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554527 | E-554527 | 2: S |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: FXO POD October 2025 A11Y_ADA Findings | Not Started | Local Enhancement Epic | Commercial Portfolio | 0113915 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: EClaims Mod Phase 2 | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0113944 | 9238 | Modernize Online Claims Experience | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-LAC-3-Retail POS Expansion to ASC and CCA | Approved | Local Enhancement Epic | Commercial Portfolio | 0113948 |  |  | Local Enhancement Epic | Build | E-547977 | E-547977 | 1: XS | 2025-10-20 |  |  | 1 | 0 | 1 | 0 |  | 2025-09-01 | 2028-05-05 | 2025-10-20
Local Enhancement Epic: COM-GIX-SIEMENS-IFCSUM IP TO IPF CHANGE | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0113950 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548889 | E-548889 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Centaur | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0114001 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-CED (Impact Only) - ART | Approved | Local Enhancement Epic | Commercial Portfolio | 0114006 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553608 | E-553608 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-12-04 | 2026-02-27
Biz w/ Tech Epic: Pick up functionality at Stratus | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0114010 | 7527 | COD at Express Domestic PL | Biz w/ Tech Epic | Assessment & Analysis | E-558551 | E-558551 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-ENS-Tokenized FDM Notifications | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114052 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-ROPs - BOA Prop to North Migration | Approved | Local Enhancement Epic | Commercial Portfolio | 0114053 |  |  | Local Enhancement Epic | Build | E-552257 | E-552257 | 2: S | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM-GDX-FSMS Modernization: Shipping Container Dev | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114055 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-ORC Integration with PACE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114056 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Supplier Payment Optimization | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114057 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Change paper type on 5 PFC SKUs | Closed | Local Enhancement Epic | Commercial Portfolio | 0114058 |  |  | Local Enhancement Epic | Build | E-552076 | E-552076 | 2: S | 2026-01-26 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-26
Lifecycle Management Epic: COM-RS-FY26 LCM Patching Maint Upgrades | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114059 |  |  | Lifecycle Management Epic | Build | E-548021 | E-548021 | 3: M | 2026-01-14 |  |  | 11 | 0 | 11 | 0 |  | 2026-01-13 | 2026-05-29 | 2026-01-14
Lifecycle Management Epic: COM-RS-FY26 LCM Security and RELY NFRs | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114060 |  |  | Lifecycle Management Epic | Build | E-548020 | E-548020 | 3: M | 2026-01-21 |  |  | 5 | 0 | 5 | 0 |  | 2026-01-14 | 2026-05-29 | 2026-01-21
Local Enhancement Epic: COM-RS-FUSE Quote Enhancement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114061 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - HOPE Allow Custmrs Chg Billing Cntry | Approved | Local Enhancement Epic | Commercial Portfolio | 0114062 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559739 | E-559739 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - FDS Fix Invoice Due Date in FBO | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114064 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - eRD Zone Template Ratescale Copy Chng | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114065 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - US Shipmt Curr Code Restrict Reqt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114066 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - TR Creation of Two New ADT Fields | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114067 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Express Clearance Entry Fee | Approved | Local Enhancement Epic | Commercial Portfolio | 0114068 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549292 | E-549292 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3 - Turkey G2D "KAMU" Customers | Approved | Local Enhancement Epic | Commercial Portfolio | 0114069 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558535 | E-558535 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-MS-Mob Update sort order for shipment list | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114071 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - GDX - EDM - LCM-FY26 -Spprt & Serv Now | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114072 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-549394 | E-549394 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2026-05-19
Biz w/ Tech Epic: Global Trade Navigator | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114120 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: GIX | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0114135 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FBO - Enable Auto-downloads for Billing Medium Q | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114136 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Remove all LTL Freight capabilities from WADM | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0114156 | 143551 | Project Fairway - Commercial Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Pre-Print App Modernization - Paper Air Waybills | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114164 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Fairway: COMM Redirect to New FXF Gateway | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0113717 | 143551 | Project Fairway - Commercial Separation Enablement | Biz w/ Tech Epic | Build | E-547113 | E-547113 | 3: M | 2025-10-17 |  | 25% | 4 | 1 | 2 | 1 |  | 2025-10-20 | 2026-03-10 | 2025-10-17
Biz w/ Tech Epic: Project Fairway: COMM:Final Separation Completion | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114082 | 143551 | Project Fairway - Commercial Separation Enablement | Biz w/ Tech Epic |  | E-547114 | E-547114 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-12-09 | 2028-01-03
Biz w/ Tech Epic: Epic Rebill Enhacenment | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114262 | 109829 | EMR OTC - Rebill Enhancements | Biz w/ Tech Epic | Assessment & Analysis | E-555485 | E-555485 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-01 | 2026-03-31
Biz w/ Tech Epic: GLIDE Phase 1 Epic | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114294 | 114428 | GLIDE - Phase 1 | Biz w/ Tech Epic | Assessment & Analysis | E-549989 | E-549989 | 4: L |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CDE-Extend EU Onboarding segment in DC | Approved | Local Enhancement Epic | Commercial Portfolio | 0114311 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549294 | E-549294 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-IA-SIEMENS EU Germany VDA-4983 PAPERLESS | Approved | Local Enhancement Epic | Commercial Portfolio | 0114351 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554830 | E-554830 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Offline Web Service WSDL to API Upgrade | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114352 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-LAC-BR-iSell: integration Neoway | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114353 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic for MEISA Tax eInvoicing initiative (154440) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114367 | 154440 | MEISA Tax eInvoicing initiatives | Biz w/ Tech Epic | Assessment & Analysis | E-552534 | E-552534 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-06-02 | 2027-06-30
Local Enhancement Epic: COM - RMIC-STC - APAC BFC Enhncmnt View Cstoms Pwk | Approved | Local Enhancement Epic | Commercial Portfolio | 0114414 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553408 | E-553408 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC-STC - SG BFC Enhncmnt Perform Acct Srch | Approved | Local Enhancement Epic | Commercial Portfolio | 0114424 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553409 | E-553409 | 3: M |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: COM - RMIC - PRJ 1372304 - ePRS Mobile Phase 1 Oct | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0114437 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-551663 | E-551663 | 4: L |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-USMCA Details Update-Automation Tools Fix | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114442 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FXIC-1st Party API-Address Resolution | Approved | Local Enhancement Epic | Commercial Portfolio | 0114443 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561844 | E-561844 | 2: S |  |  |  | 2 | 0 |  | 2 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-Two-step authentication Logic Retailship | Closed | Local Enhancement Epic | Commercial Portfolio | 0114444 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559468 | E-559468 | 2: S |  |  | 100% | 1 | 1 |  | 0
Lifecycle Management Epic: COM-S&CDE-CDE_CY25_PI05_Testing & Configuration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114445 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-551219 | E-551219 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-IA-CIS-STRATUS - VACS Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0114446 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556314 | E-556314 | 1: XS |  |  |  | 1 | 0 | 1 | 0 |  | 2025-12-01 | 2026-03-02
Local Enhancement Epic: COM-CSX-Americas CE MEXUS Firewall | Approved | Local Enhancement Epic | Commercial Portfolio | 0114448 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567825 | E-567825 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-30 | 2026-05-29
Local Enhancement Epic: COM-GDX-Access request for LGNC v5 login validate | Approved | Local Enhancement Epic | Commercial Portfolio | 0114503 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563828 | E-563828 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-IA-GIX - New SCAC FEDI | Approved | Local Enhancement Epic | Commercial Portfolio | 0114506 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550813 | E-550813 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-08 | 2025-12-30
Local Enhancement Epic: COM - RMIC - Pre-Rate Hold Time Extension | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114507 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Document Retention for ePRS | Approved | Local Enhancement Epic | Commercial Portfolio | 0114509 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570299 | E-570299 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Review and Submit UI Enhancement | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114510 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-RD3 - TR CREDO "Alias Address" PS Dbase | Approved | Local Enhancement Epic | Commercial Portfolio | 0114511 |  |  | Local Enhancement Epic |  | E-559153 | E-559153 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: FY26_COM-CSX_ACME_Call Center Production Support | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0114512 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [WIN] [COMM] F&R-VF Corporation | Approved | Local Enhancement Epic | Commercial Portfolio | 0114516 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556691 | E-556691 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: [WIN] [COMM] Flashbay Phase 2 EC Ship IT | Approved | Local Enhancement Epic | Commercial Portfolio | 0114517 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556695 | E-556695 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-IA-[WIN] [COMM] Caterpillar-EC Suite | Approved | Local Enhancement Epic | Commercial Portfolio | 0114518 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554443 | E-554443 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-08-10 | 2026-12-31
Local Enhancement Epic: COM-RS-Non-Published Location Shipping Enablement | Closed | Local Enhancement Epic | Commercial Portfolio | 0114519 |  |  | Local Enhancement Epic | Build | E-563810 | E-563810 | 3: M | 2026-01-16 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-16
Local Enhancement Epic: COM-S&CDE-CORE-ICR Enhancement Bad Airway Bills | Approved | Local Enhancement Epic | Commercial Portfolio | 0114521 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558492 | E-558492 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Piece Surcharges | Approved | Local Enhancement Epic | Commercial Portfolio | 0114522 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556285 | E-556285 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM New Flow to Create Cases for MMI | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114523 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM New Compatible Survey in iSell | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114524 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-First Shipment – Digital & Field | Approved | Local Enhancement Epic | Commercial Portfolio | 0114525 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551222 | E-551222 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-Account Onboarding: Digital/Field | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114526 |  |  | Local Enhancement Epic | Build | E-551217 | E-551217 | 1: XS | 2026-02-24 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-02-24
Local Enhancement Epic: COM-S&CDE-CDE-Intl Journey Current Shipper Expand | Approved | Local Enhancement Epic | Commercial Portfolio | 0114527 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551221 | E-551221 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-MFXR Eligibility Flag | Approved | Local Enhancement Epic | Commercial Portfolio | 0114528 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551218 | E-551218 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CDE-Update MC Channel Guidance Journey | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114529 |  |  | Local Enhancement Epic | Build | E-551220 | E-551220 | 1: XS | 2026-02-24 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-02-24
Local Enhancement Epic: COM - RMIC - FBO Enable Auto-Downlds for Billing | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114530 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Ship & Go Data Recording | Approved | Local Enhancement Epic | Commercial Portfolio | 0114532 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583085 | E-583085 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - GDX - Direct to Retail for Lockers (Part 2) | Approved | Local Enhancement Epic | Commercial Portfolio | 0114534 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569167 | E-569167 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - Dyn Pricg AI/ML ST Pricing Recomm Eng | Approved | Local Enhancement Epic | Commercial Portfolio | 0114535 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554344 | E-554344 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Weekly Option for Summary Reports | Approved | Local Enhancement Epic | Commercial Portfolio | 0114536 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556313 | E-556313 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-Add Intl Shipment Creation to FUSE Mobile | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114537 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - FBO BG 10 Yr Document Repository | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114538 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-FXO Bulk Customer Profile Tool | Approved | Local Enhancement Epic | Commercial Portfolio | 0114539 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559469 | E-559469 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-10-20
Local Enhancement Epic: COM-RS-FXO FUSE 10 Digit Account Flag | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114540 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Prontopacco API Change | Closed | Local Enhancement Epic | Commercial Portfolio | 0114541 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559132 | E-559132 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-GAM EVP Adhoc Requests CRMA Dshbds | Approved | Local Enhancement Epic | Commercial Portfolio | 0114542 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552028 | E-552028 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-RD3-STC - WHT Automatch for CashApps | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114543 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_COM_GDX_FCR_Production Support/Defect Resolve | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114544 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556283 | E-556283 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM_GDX_FCR_QA Testing Automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0114545 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556284 | E-556284 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: GSP Value Proposition Expansion Europe | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114574 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - New Paper Invoice and Payment Fees | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114581 | 114432 | New Invoice & Payment Fees (US & CA) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-05-01 | 2027-02-26
Biz w/ Tech Epic: DDS/Exemption advance capture for EUDR shipments | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114703 | 96352 | EU Deforestation Regulation (EUDR) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2025-11-06 | 2025-12-30
Biz w/ Tech Epic: Package Research Case Reimagined | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0114714 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Disable FBO Credit Note Notification | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114724 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Add TrackByTracking endpoint to FXO | Approved | Local Enhancement Epic | Commercial Portfolio | 0114725 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561842 | E-561842 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Register Meter Number access | Approved | Local Enhancement Epic | Commercial Portfolio | 0114726 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561843 | E-561843 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GIX-DELL-X12.211-DG-SUPPORT | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114727 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Canva Connect | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114728 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM_GDX_FCR_ Additional Handling Surcharge – SPIKE | Approved | Local Enhancement Epic | Commercial Portfolio | 0114729 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556282 | E-556282 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-POD Production Look-a-like NFR | Approved | Local Enhancement Epic | Commercial Portfolio | 0114730 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559467 | E-559467 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RS - FUSE Receipt Messaging v2.0 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114731 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-03-02
Local Enhancement Epic: COM - RS - PCI Compliance POD2 and XAPI | Approved | Local Enhancement Epic | Commercial Portfolio | 0114732 |  |  | Local Enhancement Epic | Build | E-569417 | E-569417 | 2: S | 2026-04-14 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-14 | 2026-05-29 | 2026-04-14
Local Enhancement Epic: COM-GDX-Stop account usage on non restorable | Approved | Local Enhancement Epic | Commercial Portfolio | 0114733 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559152 | E-559152 | 2: S |  |  |  | 2 | 0 |  | 2 |  | 2026-01-14 | 2026-02-10
Local Enhancement Epic: COM-S&CDE-CRM-Varicent/iSell Connectivity via API | Approved | Local Enhancement Epic | Commercial Portfolio | 0114734 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552556 | E-552556 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-ICR Report Data Source Conversion | Approved | Local Enhancement Epic | Commercial Portfolio | 0114735 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552557 | E-552557 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Salesforce Mobile Transformation | Approved | Local Enhancement Epic | Commercial Portfolio | 0114736 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552558 | E-552558 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - Disputed Invoice Data for CE | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114737 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - AMEX EPPRC to GRRCN | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114738 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - GSP Value Proposition Expansion EU | Approved | Local Enhancement Epic | Commercial Portfolio | 0114739 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556006 | E-556006 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: RPA Centralization to Automation Anywhere | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114748 | 155362 | TS-VL3-Infra-Automation_Anywhere | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-10 | 2027-06-01
Biz w/ Tech Epic: Package Research Case Reimagined | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114750 | 92086 | Package Research Case Reimagined | Biz w/ Tech Epic | Assessment & Analysis | E-561006 | E-561006 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-01-12
Local Enhancement Epic: FXO Omni-Channel Profile Unification - Opt-in | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114770 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - Digital Support Manager | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114777 | 142092 | Global CE Reinvention - Digital Resolution Journey | Biz w/ Tech Epic | Assessment & Analysis | E-560693 | E-560693 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2027-11-04
Biz w/ Tech Epic: 110719 Loyalty Rewards Vendor Onboarding RFP | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114785 | 110719 | Loyalty Rewards RFP - New Vendor Onboarding | Biz w/ Tech Epic | Build | E-555860 | E-555860 | 3: M | 2025-12-08 |  |  | 44 | 0 | 42 | 2 |  | 2026-01-14 | 2026-06-30 | 2025-12-08
Local Enhancement Epic: Test - Can delete | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114812 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - RS - RET - Database and Reporting Updates | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0114820 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Build | E-552786 | E-552786 | 2: S | 2026-01-08 |  |  | 2 | 0 | 1 | 1 |  | 2025-08-27 | 2026-05-29 | 2026-01-08
Local Enhancement Epic: COM - RMIC - FPOS New Charges (Nov25) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114825 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: AIV & PIV Core Webhook Fixes, Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0112232 | 103334 | [VIS] Integrated Visibility 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-554484 | E-554484 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2026-04-07
Local Enhancement Epic: FXO POD October 2025 A11Y_ADA Findings (2) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114841 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - FedEx Support Hub (FSH) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114852 | 152982 | FedEx Support Hub (FSH) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-PRINT Enterprise reCAPTCHA Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0114856 |  |  | Local Enhancement Epic | Build | E-553598 | E-553598 | 1: XS | 2026-03-17 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-08 | 2026-03-24 | 2026-03-17
Local Enhancement Epic: COM-GDX-AWB - Make Packaging Materials | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114857 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Charge Codes Creation for Fiji | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114858 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - GRI Tool Edit Validate Base/Freeze Dt | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114859 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Enable FIF US EXP Rates for Zone K | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0114861 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - Elim of Cheque Pymts in Singapore | Approved | Local Enhancement Epic | Commercial Portfolio | 0114862 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578738 | E-578738 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-WREG personalization & automation | Approved | Local Enhancement Epic | Commercial Portfolio | 0114863 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558614 | E-558614 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Fixed Amount Discount Option for PUP | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114864 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - FPOS New Charges (Nov25) | Approved | Local Enhancement Epic | Commercial Portfolio | 0114866 |  |  | Local Enhancement Epic | Build | E-553202 | E-553202 | 1: XS | 2025-12-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2025-12-06
Local Enhancement Epic: COM - RMIC - Rename SmartPost to Grd Econ in ePRS | Approved | Local Enhancement Epic | Commercial Portfolio | 0114867 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566765 | E-566765 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Surround Access to Pickup API | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114953 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: MI elite pricing launch | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0114967 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Add Opt-in to EU Onboarding Dataset | Approved | Local Enhancement Epic | Commercial Portfolio | 0114968 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553504 | E-553504 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-Tender Shipping Transactions to CAS | Not Started | Local Enhancement Epic | Commercial Portfolio | 0114970 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_COM-S&CDE_CRM ART_Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114971 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-553917 | E-553917 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: CY26_PI-01_COM-S&CDE-CRM_Business KTLO | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114972 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-553916 | E-553916 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: CY26_PI-01_COM-S&CDE-CRM - Sales IT_ KTLO | Approved | Lifecycle Management Epic | Commercial Portfolio | 0114973 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-553642 | E-553642 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM- Logging an Attempt w/out a Contact | Approved | Local Enhancement Epic | Commercial Portfolio | 0114974 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553641 | E-553641 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM- Oppty Active Participation Flag | Approved | Local Enhancement Epic | Commercial Portfolio | 0114975 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553639 | E-553639 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM - Mass Upload Tool 2.0 | Approved | Local Enhancement Epic | Commercial Portfolio | 0114976 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553640 | E-553640 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM RS FXO POD OCT 25 A11Y-ADA Findings (3) | Approved | Local Enhancement Epic | Commercial Portfolio | 0114977 |  |  | Local Enhancement Epic | Build | E-554167 | E-554167 | 1: XS | 2025-11-26 |  |  | 1 | 0 |  | 1 |  | 2025-10-01 | 2026-05-29 | 2025-11-26
Biz w/ Tech Epic: | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0114989 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - MPS Parcel Freight Corporate | Closed | Biz w/ Tech Epic | Commercial Portfolio | 0114991 | 7418 | EUM - MPS Parcel/Freight Corporate | Biz w/ Tech Epic | Assessment & Analysis | E-564580 | E-564580 | 2: S |  |  | 100% | 1 | 1 |  | 0
Biz w/ Tech Epic: Epic 1E- Canada | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115023 | 9159 | Easy ways to pay duty & tax | Biz w/ Tech Epic | Assessment & Analysis | E-556929 | E-556929 | 3: M |  |  |  | 2 | 0 |  | 2 |  | 2026-03-11 | 2027-01-15
Biz w/ Tech Epic: COM - RMIC - PRJ 1372304 - ePRS Mobile App P1 Oct | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115024 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-553862 | E-553862 | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Peak Surch(F1R/diff values Non-Frt) | Approved | Local Enhancement Epic | Commercial Portfolio | 0115036 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559740 | E-559740 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - Add Port Code 5578 to ADT & DBR | Approved | Local Enhancement Epic | Commercial Portfolio | 0115038 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556008 | E-556008 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-PRINT-Adobe Express Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0115056 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569418 | E-569418 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-FXO Omni Channel Profile - Opt-in | Approved | Local Enhancement Epic | Commercial Portfolio | 0115057 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558473 | E-558473 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2027-01-13 | 2027-03-23
Local Enhancement Epic: COM-RMIC-ROPs - EU CCA/EZD Outbound Queue in TED | Approved | Local Enhancement Epic | Commercial Portfolio | 0115058 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554176 | E-554176 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - US&CA-Paperless CCard exp letter | Approved | Local Enhancement Epic | Commercial Portfolio | 0115059 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580387 | E-580387 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-CIS-STRATUS-MPS Mixed P\F C- Status Rest | In Progress | Local Enhancement Epic | Commercial Portfolio | 0115061 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567525 | E-567525 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-02-16 | 2026-05-29
Lifecycle Management Epic: COM-S&CDE-CORE Sales IT Production Suppo_CY26_PI01 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115062 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-558493 | E-558493 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: COM-S&CDE-CORE Business Production Suppo_CY26_PI01 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115063 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-558491 | E-558491 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - US Disbursement Fee Low Tier Increase | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0115074 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Finalize Contract and Secure Resources | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0115086 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 |  | 2025-12-01 | 2026-05-29
Biz w/ Tech Epic: Implementation (Contract, Resources, Tech Review) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0115088 | 103897 | Rohan RFP - Generative AI Platform Proposal LLM | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-12-01 | 2026-05-29
Local Enhancement Epic: COM-GDX-[SA] Masking Addr line 3 to National addr | Closed | Local Enhancement Epic | Commercial Portfolio | 0115091 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559766 | E-559766 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - Disbursmnt Fee Calc Logic Chng for TH | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0115100 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Addtl Filer Code 1FX for FXL | Approved | Local Enhancement Epic | Commercial Portfolio | 0115115 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561875 | E-561875 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-Enable the RSLS API for 3rd party | Approved | Local Enhancement Epic | Commercial Portfolio | 0115124 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558505 | E-558505 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Rating traffic migration to CloudOps | Approved | Local Enhancement Epic | Commercial Portfolio | 0115125 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556288 | E-556288 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-FXO Omni Channel Profile - FCL/WREG | Approved | Local Enhancement Epic | Commercial Portfolio | 0115126 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561841 | E-561841 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RS-Stations Reporting into RDAT | Closed | Local Enhancement Epic | Commercial Portfolio | 0115127 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559877 | E-559877 | 2: S |  |  | 100% | 1 | 1 |  | 0
Local Enhancement Epic: COM-IA-ROCHE_DG_NL_EDI_TRANSLATION_CHANGE_BIS | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0115128 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Enhance Address Validation API | Approved | Local Enhancement Epic | Commercial Portfolio | 0115129 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556335 | E-556335 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: COM - FiT D&T Expansion - Israel Implementation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115139 | 154878 | FiT D&T Expansion - Israel Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-556838 | E-556838 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-06-16
Local Enhancement Epic: COM-GDX-MAGR 4FF Quote Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0115150 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577270 | E-577270 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-SASS-Vendor Fujitsu journey to the cloud | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115151 |  |  | Lifecycle Management Epic | Build | E-555566 | E-555566 | 2: S | 2026-01-21 |  |  | 1 | 0 | 1 | 0 |  | 2025-11-04 | 2026-05-29 | 2026-01-21
Local Enhancement Epic: COM - RMIC-RD3 - Reduce EU Invg Copy Doc Request | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115152 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Updt BDT Fee Logic Rmove Existg Limit | Approved | Local Enhancement Epic | Commercial Portfolio | 0115153 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564272 | E-564272 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC - eRD Workbook Prod Enhancements | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115154 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - FPOS New Charges and Updates (Jan 26) | Approved | Local Enhancement Epic | Commercial Portfolio | 0115155 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557402 | E-557402 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: E-commerce value prop and digital capabilities | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0115168 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - Outbound Contact Center | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115176 | 142092 | Global CE Reinvention - Digital Resolution Journey | Biz w/ Tech Epic | Assessment & Analysis | E-560689 | E-560689 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-09-30
Biz w/ Tech Epic: COM - Live Chat and CED Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115177 | 142092 | Global CE Reinvention - Digital Resolution Journey | Biz w/ Tech Epic | Assessment & Analysis | E-560696 | E-560696 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-09-30
Biz w/ Tech Epic: COM - Social Messaging and DSM integration | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115179 | 142092 | Global CE Reinvention - Digital Resolution Journey | Biz w/ Tech Epic | Assessment & Analysis | E-560695 | E-560695 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-07-30
Biz w/ Tech Epic: COM - Digital Support Content | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115194 | 142092 | Global CE Reinvention - Digital Resolution Journey | Biz w/ Tech Epic | Assessment & Analysis | E-560692 | E-560692 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-06-03 | 2027-10-29
Local Enhancement Epic: COM-GDX-RMIC - Quote Platform RATC Internal API | Approved | Local Enhancement Epic | Commercial Portfolio | 0115285 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566799 | E-566799 | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-GDX - Make Brazil CTE File Avail Dwnld | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115286 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Robotic Automation of e-Invoicing | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115287 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC-STC - LCM: BfC Azure Migration | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115288 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-565244 | E-565244 | 5: XL |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM-GDX-CS-CY26_PI.01_Offline Perf Tstng/TstngSup | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115289 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-559131 | E-559131 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Add Retention Date field in EDM | Approved | Local Enhancement Epic | Commercial Portfolio | 0115290 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567594 | E-567594 | 3: M |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: COM - Global Airfreight Parity | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115312 | 114082 | Global Airfreight - parity | Biz w/ Tech Epic | Assessment & Analysis | E-583745 | E-583745 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM - Feedback in Salesforce | Approved | Local Enhancement Epic | Commercial Portfolio | 0115341 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556593 | E-556593 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Officer Selling Program-Traditional | Approved | Local Enhancement Epic | Commercial Portfolio | 0115342 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558477 | E-558477 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-Customer Engineering Group Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0115344 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558469 | E-558469 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM-FTIP Modernization | Approved | Local Enhancement Epic | Commercial Portfolio | 0115345 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558471 | E-558471 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: COM - RMIC - PRJ18355 - eMBP Transformation Apr'26 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115351 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-556172 | E-556172 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-FAPI Modernization | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115388 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-559765 | E-559765 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: COM - RMIC - ePRS Mobile App - GPAS - P2 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115401 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-557972 | E-557972 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - SpS Enablement in Enterprise System -MVP1 | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0115408 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-12-01 | 2025-12-01
Biz w/ Tech Epic: Enhancements to Legacy Platform | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0115411 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-DTR MPS pre-advice to partner | Approved | Local Enhancement Epic | Commercial Portfolio | 0115412 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559768 | E-559768 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-Consolidation Results Retrieval | Approved | Local Enhancement Epic | Commercial Portfolio | 0115422 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559767 | E-559767 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-GC3 Call Flow Change | Approved | Local Enhancement Epic | Commercial Portfolio | 0115428 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570967 | E-570967 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM New Email Automation for EU | Approved | Local Enhancement Epic | Commercial Portfolio | 0115429 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558476 | E-558476 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - BO retirement slated impact EU | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115430 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-ROPs - Critical Major Customer Reptg | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115431 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM New ETL Job for Batch Open Case | Closed | Local Enhancement Epic | Commercial Portfolio | 0115432 |  |  | Local Enhancement Epic | Build | E-558475 | E-558475 | 1: XS | 2026-03-10 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-03-10
Lifecycle Management Epic: COM-CSX-Five9 IVA Capability Enablement | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115433 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-566455 | E-566455 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-CSX-Five9 IVA Capability Enablement | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115434 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-566457 | E-566457 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Hermes LMO Scan Mapping | Approved | Local Enhancement Epic | Commercial Portfolio | 0115435 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569166 | E-569166 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-CSX-MEISA Exec Desk Email Discovery routing | Approved | Local Enhancement Epic | Commercial Portfolio | 0115436 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558037 | E-558037 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Biz w/ Tech Epic: MAGIC China Data Localization Removal | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0115437 | 157485 | Local Apps Modification for MAGIC CDL Removal | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-10-08 | 2025-10-08
Local Enhancement Epic: COM - RMIC - Storage Fee Chrg Shpmnt Held > 10days | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115440 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Storage Fee Cage Reason Expansion | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115441 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - D&T Invoice Trigger Update | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115442 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Storage Fee Update Fee Days Logic | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115443 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM Batch Case PoweBI Dashboard | Approved | Local Enhancement Epic | Commercial Portfolio | 0115444 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558470 | E-558470 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-S&CDE-CRM Allow CAN CT to engage US Sr Support | Closed | Local Enhancement Epic | Commercial Portfolio | 0115445 |  |  | Local Enhancement Epic | Build | E-558474 | E-558474 | 1: XS | 2026-03-10 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-03-10
Local Enhancement Epic: COM-S&CDE-CRM New Flow to Create Cases for ECM | Approved | Local Enhancement Epic | Commercial Portfolio | 0115446 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558472 | E-558472 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM - RMIC-STC - PEACE VN Updt 2C2P M-Pay EndPoint | Approved | Local Enhancement Epic | Commercial Portfolio | 0115447 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565243 | E-565243 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-28 | 2026-03-24
Local Enhancement Epic: COM - RMIC-STC - PEACE APAC Wthhldg Tax ID, PH, TH | Approved | Local Enhancement Epic | Commercial Portfolio | 0115448 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565245 | E-565245 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-02-25 | 2026-05-19
Local Enhancement Epic: COM - RMIC - FASTBill for 2 Digital Products in CA | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115449 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: 1- Classification DB & Resi Surcharge Capabilities | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0105079 | 6868 | Global Residential Database & Surcharge | Biz w/ Tech Epic | Assessment & Analysis | E-492838 | E-492838 | 3: M |  |  |  | 2 | 0 |  | 2 | No | 2026-04-06 | 2027-01-22
Local Enhancement Epic: COM-CSX-AUDIT: FARM Hierarchy Report embedded | Approved | Local Enhancement Epic | Commercial Portfolio | 0115563 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578878 | E-578878 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FAPI - PCC - Web Services/API Gap Fixture | Approved | Local Enhancement Epic | Commercial Portfolio | 0115564 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565302 | E-565302 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-FAPI: Adrs Vldtn Non ASCII Characters | Approved | Local Enhancement Epic | Commercial Portfolio | 0115565 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573409 | E-573409 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FAPI: TradeDocUpld API new feature | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115566 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CY26-PI.01 - Enable Family | Approved | Local Enhancement Epic | Commercial Portfolio | 0115567 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564924 | E-564924 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CY26-PI.01 - Visibility Family | Approved | Local Enhancement Epic | Commercial Portfolio | 0115568 |  |  | Local Enhancement Epic | Build | E-563833 | E-563833 | 2: S | 2026-01-19 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-GDX-CY26-PI.02-Data & Digital Commerce: MOBILE | Approved | Local Enhancement Epic | Commercial Portfolio | 0115569 |  |  | Local Enhancement Epic | Build | E-579854 | E-579854 | 3: M | 2026-03-27 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-27
Local Enhancement Epic: COM-GDX-CY26-PI.01 - Ship Family | Approved | Local Enhancement Epic | Commercial Portfolio | 0115570 |  |  | Local Enhancement Epic | Build | E-565062 | E-565062 | 2: S | 2026-01-22 |  |  | 2 | 0 | 2 | 0 |  | 2026-01-19 | 2026-01-19 | 2026-01-22
Biz w/ Tech Epic: Extend Rated Charge Amount Field Limits | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0115593 | 109411 | COM-RMIC Extend Rated Charge Amount Field Limits | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Hermes LMO - Address Quality Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0115633 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562980 | E-562980 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-RMIC-ROPs - Credit Check US API | Approved | Local Enhancement Epic | Commercial Portfolio | 0115635 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569017 | E-569017 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-P4e daily report for OPS onPostNL drop-off | Approved | Local Enhancement Epic | Commercial Portfolio | 0115636 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569204 | E-569204 | 1: XS |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Epic 1 - Dynamic territory integration | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0115639 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-MAG Scorecard Development | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0115641 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-fedex-com-customeraccountcxs-ShipFast API | Approved | Local Enhancement Epic | Commercial Portfolio | 0115642 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566781 | E-566781 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC-STC - Updt QR Pay Msg APAC Cust Facing | Approved | Local Enhancement Epic | Commercial Portfolio | 0115643 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571189 | E-571189 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - Lower US Disbursement Fee Threshold | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115644 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FIC Webservices Migration to 1P Gateway | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115645 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - LDP Customs Pprwk Mtchg Lgic Chng | Approved | Local Enhancement Epic | Commercial Portfolio | 0115647 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580329 | E-580329 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC-RD3 - Upgrade & Rebuild IRIS | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0115648 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FSM Additional Language Options | Closed | Local Enhancement Epic | Commercial Portfolio | 0115649 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566800 | E-566800 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - Dim Volume Tolerance for XL Boxes | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115650 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - GDX - CS - CY26_PI.01_FACTOR Sppt DSS ART | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115651 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-561840 | E-561840 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: COM-CSX-FedEx Support Hub (FSH) (SSO) | Approved | Local Enhancement Epic | Commercial Portfolio | 0115652 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581503 | E-581503 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - Update new QR Code URLs for China | Approved | Local Enhancement Epic | Commercial Portfolio | 0115653 |  |  | Local Enhancement Epic | Build | E-563212 | E-563212 | 2: S | 2026-01-14 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-01-14
Biz w/ Tech Epic: AI Deal Management - EPRS and EPAT Integration | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115675 | 113092 | AI Deal Management | Biz w/ Tech Epic | Build | E-576905 | E-576905 | 2: S | 2026-03-30 |  |  | 2 | 0 | 1 | 1 |  | 2026-01-01 | 2026-06-30 | 2026-03-30
Biz w/ Tech Epic: Visibility | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115778 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-562749 | E-562749 | 4: L |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: GCS OTC Error Correction Automation: Epic 1 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115776 | 164243 | GCS OTC Error Corrections EMR | Biz w/ Tech Epic | Assessment & Analysis | E-568315 | E-568315 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2025-10-10 | 2026-02-27
Biz w/ Tech Epic: FedEx Rewards for Canada | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0115788 | 153923 | FedEx Rewards for Canada | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-S&CDE - IMAGE Sale Roles Territry Basd | Approved | Local Enhancement Epic | Commercial Portfolio | 0115819 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574586 | E-574586 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Salesforce Einstein Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0115836 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567445 | E-567445 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Weight Icon Printed on NL inbound FDX AWB | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115837 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-FEC SFMC Package Mgr. to FXF | Approved | Local Enhancement Epic | Commercial Portfolio | 0115838 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565651 | E-565651 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Shipping and Quote | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115849 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-562750 | E-562750 | 5: XL |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: RMIC / Invoicing and Settlement | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115850 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Build | E-562718 | E-562718 | 5: XL | 2026-03-17 |  |  | 2 | 0 | 1 | 1 |  |  |  | 2026-03-17
Biz w/ Tech Epic: MAGIC Page Load Times | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115851 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-562752 | E-562752 | 3: M |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: FedEx Dotcom apps | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115852 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-569139 | E-569139 | 4: L |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Nordics invoicing requirement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0115859 | 170274 | EUM - Nordics Invoicing Requirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CORE-Workday Data into Varicent | Approved | Local Enhancement Epic | Commercial Portfolio | 0115877 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568367 | E-568367 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC-STC - PEACE KR Disable Email Notif KPN | Approved | Local Enhancement Epic | Commercial Portfolio | 0115878 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579355 | E-579355 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Express Retail Pricing using City Center Accounts | Approved | Local Enhancement Epic | Commercial Portfolio | 0115879 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581296 | E-581296 | 1: XS |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: COM - RMIC - CAN ADT Weekly Report | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115880 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_COM_MS_eIANs_Prod Support_Patching | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115881 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-563074 | E-563074 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-05-29
Local Enhancement Epic: COM - RMIC - CBS Add Credit Note Field to FBO | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115883 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - CBS Customs Document Download | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115884 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - CBS View Only Role for FBST | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115885 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM CACEM iSell Case Flow Updates | Closed | Local Enhancement Epic | Commercial Portfolio | 0115886 |  |  | Local Enhancement Epic | Build | E-570796 | E-570796 | 1: XS | 2026-03-10 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-03-10
Local Enhancement Epic: COM-S&CDE-CRM New Case Process for CT DPX Team | Approved | Local Enhancement Epic | Commercial Portfolio | 0115887 |  |  | Local Enhancement Epic | Build | E-577220 | E-577220 | 1: XS | 2026-03-17 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-17
Local Enhancement Epic: COM-RS-Block Scan of Retailer Store’s POD’d Packag | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115936 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-Colorado M Series Printer | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115937 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-566059 | E-566059 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-06-16
Local Enhancement Epic: EUM - COM-GDX-DG in PASGO | Approved | Local Enhancement Epic | Commercial Portfolio | 0115938 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567595 | E-567595 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-RS-User Guidance Text Changes FASCs(FR/EN) | Closed | Local Enhancement Epic | Commercial Portfolio | 0115939 |  |  | Local Enhancement Epic | Build | E-564921 | E-564921 | 2: S | 2026-01-23 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-23
Local Enhancement Epic: COM-RS-Extra Fields to RDAT (locations &Report) | Closed | Local Enhancement Epic | Commercial Portfolio | 0115940 |  |  | Local Enhancement Epic | Build | E-564922 | E-564922 | 2: S | 2026-01-23 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-23
Local Enhancement Epic: COM-GDX-fdxSAMS-RTS Replacement | Approved | Local Enhancement Epic | Commercial Portfolio | 0115941 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577269 | E-577269 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-18 | 2026-06-19
Local Enhancement Epic: COM-GDX-Fedex.com.au err message Improving the acc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115945 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: EIN/VAT # Field Change - AWB | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115946 | 136570 | EIN/VAT # Field Change - AWB | Biz w/ Tech Epic | Assessment & Analysis | E-577960 | E-577960 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Streamlined Attributes Edit Check | Approved | Local Enhancement Epic | Commercial Portfolio | 0115949 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581629 | E-581629 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Product Bundling - Part 2 | Approved | Local Enhancement Epic | Commercial Portfolio | 0115951 |  |  | Local Enhancement Epic | Build | E-564920 | E-564920 | 1: XS | 2026-04-14 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-14 | 2026-05-29 | 2026-04-14
Local Enhancement Epic: KSeF number in Poland - CANCEL | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115952 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - EDD Testing Support for MDM Mod | Approved | Local Enhancement Epic | Commercial Portfolio | 0115953 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568316 | E-568316 | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Dispach user in RDAT | Approved | Local Enhancement Epic | Commercial Portfolio | 0115954 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564925 | E-564925 | 2: S |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Epic 1 QP - Modernized Ground services | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0115971 | 85719 | QP Spot - Ground and US Domestic Freight | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-06-30
Local Enhancement Epic: COM-RS-GDX--RET-Onboard Enterprise APIs for FRT | Approved | Local Enhancement Epic | Commercial Portfolio | 0115978 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564923 | E-564923 | 1: XS |  |  |  | 2 | 0 |  | 2 |  | 2026-01-19 | 2026-02-27
Local Enhancement Epic: COM - RMIC-STC - FX TH as Authorized WHT Agent | Not Started | Local Enhancement Epic | Commercial Portfolio | 0115979 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC - PAG to Okta EPA GUI | Approved | Lifecycle Management Epic | Commercial Portfolio | 0115984 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-565736 | E-565736 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - FPOS New Charges and Updates (Feb 26) | Approved | Local Enhancement Epic | Commercial Portfolio | 0116014 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565735 | E-565735 | 1: XS |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: RPA develop for auto data flow from PowerBI to PH | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116029 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CORE- Jan Data Load for Pricing Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0116048 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568368 | E-568368 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - RMIC - ePRS Mobile App - GPAS - P2 - I2 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116061 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-571570 | E-571570 | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Enable Shipping Account for 3P Products | Approved | Local Enhancement Epic | Commercial Portfolio | 0116098 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566056 | E-566056 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-08-11
Local Enhancement Epic: COM-RS-Decompose Large Services into Microservices | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116100 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Retailer Countertop Scan Integrate for RCPA | Approved | Local Enhancement Epic | Commercial Portfolio | 0116101 |  |  | Local Enhancement Epic | Build | E-569416 | E-569416 | 2: S | 2026-02-18 |  |  | 2 | 0 | 2 | 0 |  | 2026-03-25 | 2026-06-16 | 2026-02-18
Local Enhancement Epic: COM-RS-Thermal Label Printing | Approved | Local Enhancement Epic | Commercial Portfolio | 0116103 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566058 | E-566058 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-06-16
Local Enhancement Epic: Test | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116108 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-myFXO | Approved | Local Enhancement Epic | Commercial Portfolio | 0116110 |  |  | Local Enhancement Epic | Build | E-570831 | E-570831 | 1: XS | 2026-02-25 |  |  | 1 | 0 | 1 | 0 |  | 2026-02-02 | 2026-05-29 | 2026-02-25
Lifecycle Management Epic: COM-GDX-CP-Print Suite Num on Label for HAL spmnts | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116121 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-565645 | E-565645 | 2: S |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM - IA - CIS - CY26 - Gov & Feasibility Studies | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116122 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-567524 | E-567524 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-14 | 2026-12-31
Lifecycle Management Epic: COM - IA - CIS - CY26_CIS_Sys/App Maint. | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116123 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-567523 | E-567523 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-14 | 2026-12-31
Lifecycle Management Epic: COM - IA - CIS - CY26_CIS_Sys Modernization | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116124 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-567522 | E-567522 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-14 | 2026-12-31
Local Enhancement Epic: COM - GDX - JOIN - WREG migration to Azure | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116137 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic-Global Billing&Collections BPO Consolidation | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116144 | 168196 | Global Billing & Collections BPO Consolidation | Biz w/ Tech Epic | Assessment & Analysis | E-581134 | E-581134 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GIX-APPLE-POLARIS-EDI/API-SEEBURGER-TACTICAL | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116150 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Enable Programmatic Acc-to-Project Assoc | Approved | Local Enhancement Epic | Commercial Portfolio | 0116153 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566102 | E-566102 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-VIS - Adjust Matching Profile & Contact | Approved | Local Enhancement Epic | Commercial Portfolio | 0116154 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583244 | E-583244 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - RAA & Refund History Enhancements | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116156 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Cybersource API | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116157 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-API Validation Enhancement Feature | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116160 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GDX-CP-FedEx Smart Shipper (FSS) - FCL SSO | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116161 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FDP - The Next Chapter - Epic 1 | Approved | Local Enhancement Epic | Commercial Portfolio | 0116165 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579418 | E-579418 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Excl ADT Chrg NZ GST-Map Chg Code FJ | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116166 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Re-Calc of Tax on APAC Pre-Rated | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116171 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-PDF label change to comply with ADA | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116172 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CORE-GAF CRP Data at Airway Bill Level | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116173 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Digital Platform Modernization - Shell | Approved | Local Enhancement Epic | Commercial Portfolio | 0116177 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568177 | E-568177 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: US High Impact Growth | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116181 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: US High Impact Share | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116183 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: US Low Impact Maintenance | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116184 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: US High Impact Retain | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116185 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC: Retarget Saved Shipment in MAGIC | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116186 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: EU Growth - Lapsed Customer Journey | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116188 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: MEISA: Cross sell EU and APAC and other Lanes | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116187 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: EU Growth - FXR Activation Journey | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116189 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-12-31
Biz w/ Tech Epic: AI Deal Management - iSell | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116202 | 113092 | AI Deal Management | Biz w/ Tech Epic | Assessment & Analysis | E-576906 | E-576906 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Biz w/ Tech Epic: APAC e-Invoice (TH & FJ) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116205 | 171131 | APAC e-Invoice (TH & FJ) | Biz w/ Tech Epic | Assessment & Analysis | E-570514 | E-570514 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-02-23 | 2026-11-02
Biz w/ Tech Epic: Pricing Analysis and Intelligence Suite Epic | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116214 | 126689 | Pricing Analysis and Intelligence Suite | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-13 | 2027-10-29
Local Enhancement Epic: COM - RMIC - EDI Surcharge VAT Exemption | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116233 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Optimus Integration with CE Desktop | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116235 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-FARM expansion EU | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116237 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Database Replacement-FSMS, FSM, and GSM | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116238 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-locker Drop-off service Spain&Portugal | Approved | Local Enhancement Epic | Commercial Portfolio | 0116239 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570328 | E-570328 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Expansion retaildeliveries MR to Portugal | Approved | Local Enhancement Epic | Commercial Portfolio | 0116240 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570329 | E-570329 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - F1R Cubic Inch Threshold Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0116242 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574587 | E-574587 | 1: XS |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: CY26_COM-CSX_DICE_LCM_Global Content Updates | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116250 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-569607 | E-569607 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-11 | 2026-12-31
Biz w/ Tech Epic: Americas Acquire – Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116255 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Biz w/ Tech Epic: Americas Onboard – Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116256 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Americas Grow - Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116257 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Americas Retain / Recover – Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116258 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ACQ26: EU - Acquisition - Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116259 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ACT26: EU - Activation - Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116260 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: GRW26: EU - Growth - Monitor / Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116261 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: EU Growth - Onboarding 3.0 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116262 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: MEISA & APAC Growth | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116263 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: MEISA Growth | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116264 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: TLA: EU Telesales Lead automation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116265 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ICJP: EU Inhousing CES journey programs | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116266 | 161043 | FY26 Commercial Journey Orchestration | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FiF Epic | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116267 | 96406 | FIF (FedEx International First) enablement in ePRS | Biz w/ Tech Epic | Assessment & Analysis | E-582747 | E-582747 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PEACE TH - API Integration with Ksher | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116288 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Deploy RS Services To Both Datacenters | Approved | Local Enhancement Epic | Commercial Portfolio | 0116316 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570832 | E-570832 | 2: S |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: COM - RMIC - Add IPD to AGT and IRE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116317 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - UME File Enhancement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116318 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Enable FUSE to automatic log user in FRT | Closed | Local Enhancement Epic | Commercial Portfolio | 0116319 |  |  | Local Enhancement Epic | Build | E-575087 | E-575087 | 2: S | 2026-03-11 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-03-11
Local Enhancement Epic: COM - RMIC - CBS/CPG-Updt Inv Due Date CBS Mapping | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116320 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM–RMIC–PDF Inv & LDP Update:Add O/D Postal Codes | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116321 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-GIX-Dell EDI 214 Time Zone Modification | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116322 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM – IA -GIX - Macy's FUSE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116323 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GIX-IA-AMZN - Bulk Delivery Manifest | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116324 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-ROPs-Email for DT Invoices (expand to EU) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116328 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Telephony Sol. for KSA Clearance Activity | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116350 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-FTIP-remove mention of FXF from agree | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116351 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-FTIP Algorithm - Request Finance Assist | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116352 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-US CALL ROUTING CHANGES | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116354 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_COM-CSX-CE_Global Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116355 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-568287 | E-568287 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-11 | 2026-12-31
Local Enhancement Epic: COM-GDX-FDP TNC - Epic 2-LoggedIn Experience Dev | Approved | Local Enhancement Epic | Commercial Portfolio | 0116356 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579417 | E-579417 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-CP-API–WS Parity - Field-Length Handling | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116357 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-568366 | E-568366 | 1: XS |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM - RMIC - FDS POC to Create PDF & Print Ready | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116359 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-569191 | E-569191 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-CP-CY26-PI.01 – GTN Milestone 1 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116383 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM- My Executive App | Approved | Local Enhancement Epic | Commercial Portfolio | 0116384 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568364 | E-568364 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Defend the Core: US Digital Sales | Approved | Local Enhancement Epic | Commercial Portfolio | 0116385 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568365 | E-568365 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Access to VACS getCommitment | Approved | Local Enhancement Epic | Commercial Portfolio | 0116386 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582311 | E-582311 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC - Inv FDS - Cleanup Feature Flags | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116396 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-569174 | E-569174 | 2: S |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM - RMIC - Inv FDS Web Report Oracle Letters | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116397 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-569192 | E-569192 | 2: S |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: CE Support for MDM Modernization | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116400 | 9067 | Account MDM Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-570321 | E-570321 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM Update ETL Jobs to EIW Connection | Approved | Local Enhancement Epic | Commercial Portfolio | 0116414 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568370 | E-568370 | 1: XS |  |  |  | 1 | 0 |  | 1
Work: COM-S&CDE-CRM-EIW-iSell InfoSec Database Changes | Approved |  | Commercial Portfolio
Local Enhancement Epic: COM-S&CDE-CRM-EIW-iSell InfoSec Database Changes | Approved | Local Enhancement Epic | Commercial Portfolio | 0116415 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570763 | E-570763 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Automate Opportunity Special Flag | Approved | Local Enhancement Epic | Commercial Portfolio | 0116416 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570794 | E-570794 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Slack Pilot | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116417 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Automotive End-to-End Support | Approved | Local Enhancement Epic | Commercial Portfolio | 0116418 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570797 | E-570797 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Dropship Pipeline Visibility | Approved | Local Enhancement Epic | Commercial Portfolio | 0116419 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570793 | E-570793 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Enhanced Attainment and Forecast | Approved | Local Enhancement Epic | Commercial Portfolio | 0116420 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570795 | E-570795 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM FUSE Dashboard in CART | Approved | Local Enhancement Epic | Commercial Portfolio | 0116421 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568369 | E-568369 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-RMIC-ROPs - Email for DT Invoice Ph 2 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116424 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-STRATUS ONLINE-ENABLEMENT FIXED LENGTH | Approved | Local Enhancement Epic | Commercial Portfolio | 0116425 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569937 | E-569937 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2027-05-14
Lifecycle Management Epic: COM-IA-DART-FY26_PI01_Marketing Tagging_LCM | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0116426 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - IA - DART - CY26 PI01 - System Optimization | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0116427 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Data Discovery | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116170 | 88108 | Commercial Data Migration - Journey Enablement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-05-01
Local Enhancement Epic: COM-GDX-KSA Smart Locker | Approved | Local Enhancement Epic | Commercial Portfolio | 0116441 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580574 | E-580574 | 1: XS |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM-CSX enable DPA triggers for EPA | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0116442 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: VIS - TS-VL3-Integration-GAS Utilization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116475 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: VIS - TS-VL3-Integration-GAS Utilization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116476 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CSX-Salesforce Security Tools | Approved | Local Enhancement Epic | Commercial Portfolio | 0116494 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570764 | E-570764 | 4: L |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-RS-Document Scanner for HR Records | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116495 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Matic Helios Laser Cutter | Approved | Local Enhancement Epic | Commercial Portfolio | 0116496 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579641 | E-579641 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - FastBill Product Setup SameDay Local | Approved | Local Enhancement Epic | Commercial Portfolio | 0116497 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578397 | E-578397 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Onboarding ONEPICKUP from PCF to Azure(FCP) | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0109159 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-GIX-Trailer close time field exposure to Ve | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116604 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-ODS as a Marketplace Seller | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116605 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Retail Products on DoorDash | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116606 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - FDA Fee Waiver for Customer JF | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116607 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - GDX - JOIN - WREG migration to Azure (FCP) | Approved | Local Enhancement Epic | Commercial Portfolio | 0116608 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570346 | E-570346 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FICP Tracking Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0116611 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583208 | E-583208 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - FPOS New Charges and Updates (Mar'26) | Approved | Local Enhancement Epic | Commercial Portfolio | 0116612 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573108 | E-573108 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - CAPC Change to Exclude OCA | Approved | Local Enhancement Epic | Commercial Portfolio | 0116613 |  |  | Local Enhancement Epic | Build | E-582489 | E-582489 | 1: XS | 2026-04-14 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-14
Lifecycle Management Epic: FY26_Commercial_CAPS_Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116614 |  |  | Lifecycle Management Epic | Build | E-570345 | E-570345 | 4: L | 2026-03-16 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-16
Local Enhancement Epic: COM-GDX-WREG - Document validation and pre-filling | Approved | Local Enhancement Epic | Commercial Portfolio | 0116615 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579420 | E-579420 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-MS-LAC: Update Tracking Verbiage R0056 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116617 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - GRI Tool/HPU Dynamc Geographies | Approved | Local Enhancement Epic | Commercial Portfolio | 0116678 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581384 | E-581384 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC - Certificate Maint Rating ARTs | Approved | Lifecycle Management Epic | Commercial Portfolio | 0116679 |  |  | Lifecycle Management Epic | Build | E-578398 | E-578398 | 1: XS | 2026-03-24 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-24
Local Enhancement Epic: COM - RMIC - Automated Surcharge Extension Process | Approved | Local Enhancement Epic | Commercial Portfolio | 0116680 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581819 | E-581819 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Days to Wait for Inv (Transportation) | Approved | Local Enhancement Epic | Commercial Portfolio | 0116681 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580793 | E-580793 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Remove Commercial Invoice Restriction | Approved | Local Enhancement Epic | Commercial Portfolio | 0116682 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582991 | E-582991 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-GDX-Digital Services BILL TO Options Configura | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116713 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Express Brokerage Clearance - SBP Group Em | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116715 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Documentation PoC w/ MAGIC (EPIC 2) | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116728 | 92782 | CUBE | Biz w/ Tech Epic | Assessment & Analysis | E-578309 | E-578309 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-06 | 2026-10-02
Biz w/ Tech Epic: GAF Pricing Transformation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116738 | 165808 | GAF Pricing Transformation | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-GDX-ISS Enablement for ROSA/RESA | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116748 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-[SA] String validation of National Address | Approved | Local Enhancement Epic | Commercial Portfolio | 0116751 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579399 | E-579399 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY27_COM_Matrix ART_LCM_ ECCP_EDGE Production Supp | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0116752 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Ship & Pickup traffic migration to CloudOp | Approved | Local Enhancement Epic | Commercial Portfolio | 0116753 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577904 | E-577904 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Resize EU RYDE Container | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116754 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-VACS to return derived O/D data | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116755 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Automate inbound customer queries | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116756 | 131245 | GEN AI Automation webform to case | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-07-01 | 2026-12-31
Biz w/ Tech Epic: Common Support Platform | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116766 | 167915 | COM - OTC - Common Support Platform | Biz w/ Tech Epic | Assessment & Analysis | E-581691 | E-581691 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2027-02-01
Local Enhancement Epic: COM - CSX - Display Confirmation# on Express MPUs | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116767 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: MARS - Cost Optimization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0116771 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: E-521320 - COM - RS - DME MARS Infrastructure and | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0116772 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Webform automation | Cancelled | Biz w/ Tech Epic | Commercial Portfolio | 0116799 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: GRM VB2: Data from eRD to EIW | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116849 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Assessment & Analysis | E-573589 | E-573589 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-RS-Veritiv MP Onboarding | Approved | Local Enhancement Epic | Commercial Portfolio | 0116903 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579640 | E-579640 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-02 | 2026-04-30
Local Enhancement Epic: COM-GDX-CP - Enable Guest Pickup Scheduling in US | Approved | Local Enhancement Epic | Commercial Portfolio | 0116905 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582312 | E-582312 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Ground Economy to REBS | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116909 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic |  | E-574055 | E-574055 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-05 | 2026-07-31
Local Enhancement Epic: COM-GDX-Ground Economy Fixed Demand Surcharge | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116950 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Premium Surcharge Contingency Plan | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0116910 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic |  | E-574289 | E-574289 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-11-03 | 2026-01-12
Local Enhancement Epic: COM - RMIC - LAC-CCA-Chile VAT Calculation Change | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116982 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Canada FRT API Integration – Penguin Pickup | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0116983 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579639 | E-579639 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC - CBS Replace Expanded Inv Table View | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116984 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Dyn Pric UC #1 Update Baseline Calc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0116985 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Greenhouse Medtronic MVP | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117004 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CIS-[WIN] Samsung ZA EC-Ship Onboarding | Approved | Local Enhancement Epic | Commercial Portfolio | 0117014 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576975 | E-576975 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-12-10 | 2026-04-30
Local Enhancement Epic: COM-GDX-CY26-PI.02-Visibility Family | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117022 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - Reg PH Reprint FedEx Credit Note | Approved | Local Enhancement Epic | Commercial Portfolio | 0117025 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579508 | E-579508 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC-STC - Switch to New Print Vendor | Approved | Local Enhancement Epic | Commercial Portfolio | 0117026 |  |  | Local Enhancement Epic | Build | E-578832 | E-578832 | 2: S | 2026-03-24 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-24
Local Enhancement Epic: COM - RMIC-GDX - FIT India D&T HOPE Enablemnt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117029 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Update GCCS to Support Grd 12 Digit | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117030 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - GDX - IP Address Capturing for FDM Enrollmen | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117033 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-GC3 telephony system for Local NZ Clearanc | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117034 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Retail Qualtrics Migration - Survey Invite | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117035 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-Move to Github Actions | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117039 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575634 | E-575634 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-08-31
Local Enhancement Epic: COM - RMIC - Modify Invoice Adjustment and Rebill | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117041 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - POC AI Implement & Continuous Learng | Approved | Local Enhancement Epic | Commercial Portfolio | 0117042 |  |  | Local Enhancement Epic | Build | E-582487 | E-582487 | 3: M | 2026-04-20 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-20
Local Enhancement Epic: COM - RMIC - FPOS New Charges and Updates (Apr 26) | Approved | Local Enhancement Epic | Commercial Portfolio | 0117043 |  |  | Local Enhancement Epic | Build | E-581295 | E-581295 | 1: XS | 2026-04-08 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-08
Local Enhancement Epic: COM-GDX-CY26-PI.02-Visibility Family | Approved | Local Enhancement Epic | Commercial Portfolio | 0117045 |  |  | Local Enhancement Epic | Build | E-577662 | E-577662 | 2: S | 2026-03-19 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-19
Biz w/ Tech Epic: METL FedEx Net Modernization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117047 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: METL FedEx Net Modernization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117049 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Pre-Shipment Creation- CPSC Readiness | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117061 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: CPSC MVP 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117062 | 163090 | CPSC PGA Message set | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-07-08
Biz w/ Tech Epic: Post Shipment Creation | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117089 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Insight Utilization of SHARE WS | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0117097 | 168056 | TS-VL3-Integration-SHARE WS Utilization | Biz w/ Tech Epic | Assessment & Analysis | E-583408 | E-583408 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Storage and Access to COD RO Payment Recipt | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117102 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Doc Upload PI Enhancements (PI02) | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0117113 | 154881 | APAC FiT: Phase 2.5 enhance for customer adoption | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-05-29
Biz w/ Tech Epic: Per Order Delivery Instructions - MVP | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0117135 | 108601 | Per Order Delivery Instructions | Biz w/ Tech Epic | Assessment & Analysis | E-581163 | E-581163 | 2: S |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: SAP Business network for logistics integrations | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117136 | 177461 | SAP Business network for logistics integrations | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - PEACE TH API Integration Ksher | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117148 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-STC - BFC Enhncmnt to Migrate New Msg | Approved | Local Enhancement Epic | Commercial Portfolio | 0117149 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580331 | E-580331 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM - RMIC-STC - BFC Enhncmt Migrate to new data | Approved | Local Enhancement Epic | Commercial Portfolio | 0117150 |  |  | Local Enhancement Epic | Build | E-580328 | E-580328 | 2: S | 2026-03-31 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-31
Local Enhancement Epic: COM - RMIC-STC - SG BFC Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0117151 |  |  | Local Enhancement Epic | Build | E-580330 | E-580330 | 3: M | 2026-03-31 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-03-31
Local Enhancement Epic: COM – GDX – RET - Make FRT APIs available on FDP | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117152 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Digital Platform Modernization - FE and BE | Approved | Local Enhancement Epic | Commercial Portfolio | 0117153 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579419 | E-579419 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Blocking the creation of pick-ups when the | Approved | Local Enhancement Epic | Commercial Portfolio | 0117154 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582899 | E-582899 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Rebrand FGE on Inv to Replace FEC SmartPost Name | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0117163 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Rebrand FGE Invoice to Replace SmartPost Name | Cancelled | Local Enhancement Epic | Commercial Portfolio | 0117164 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Packaging & Supplies Modernization | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117167 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: MAGIC - Clearance ¦ Customs AI part 1 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117178 | 112934 | MAGIC - Clearance ¦ Customs AI | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - CBS Update Name Field Char Limits | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117180 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Visa Com Enhncd Data Prgm Error Codes | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117181 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Glbl Spot Pric Srchrg Enhan/Error Msg | Approved | Local Enhancement Epic | Commercial Portfolio | 0117182 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582490 | E-582490 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Rebrand FGE Inv to Replace SmartPost | Approved | Local Enhancement Epic | Commercial Portfolio | 0117184 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582486 | E-582486 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-CHT and TP&O Combined Case Flow | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117185 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - BUDI Tax Rate GUI Enhancement | Approved | Local Enhancement Epic | Commercial Portfolio | 0117186 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582488 | E-582488 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: External APIs (EPIC 3) | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117187 | 92782 | CUBE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC-GDX - FiT PEACE D/T Paymnt Application | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117195 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-RMIC - Quote Platform rerate AKS migration | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117233 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Interim Billing Solution for RO | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117271 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Turn Off Paper Customs Documentation | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117272 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - OPA ODA Jul'26 File Update | Approved | Local Enhancement Epic | Commercial Portfolio | 0117273 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582993 | E-582993 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Automated Executive Compensation Vis | Approved | Local Enhancement Epic | Commercial Portfolio | 0117274 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580859 | E-580859 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: COM-S&CDE-CRM-Update iSell Opportunity Reasons/Not | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117275 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-IMAGE Cloud Migration | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117276 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM- iSell Product Definition, Name, Ali | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117277 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Account Strategy Compliance Report | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117278 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - GDX - eIANS FedEx PLR Enhancements | Approved | Local Enhancement Epic | Commercial Portfolio | 0117280 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583243 | E-583243 | 2: S |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: COM_GDX_DRPT_UX Enhancement-CY26-LCM | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117281 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-581371 | E-581371 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-HappyRobot/Google Experiment | Approved | Local Enhancement Epic | Commercial Portfolio | 0117287 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579301 | E-579301 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: New Visibility PFS | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0117299 | 7665 | [VIS] Secure Tracking Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-579278 | E-579278 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic G: Ground Sata System Enablement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117307 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-CI&O (CAMP) - CY26_Environment Support/Sys | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117323 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-579793 | E-579793 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-CY26-PI.02 - Enable Family | Approved | Local Enhancement Epic | Commercial Portfolio | 0117326 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579853 | E-579853 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Enable Admin Tool for FXE Location | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117329 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-Konica Minolta Computer Rental Printer | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117330 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-Narrow Format Lamination | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117331 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-Narrow Format Folder | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117332 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM RS_TY26_PI03_LCM_Production Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117333 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-579638 | E-579638 | 3: M |  |  |  | 5 | 0 |  | 5
Local Enhancement Epic: COM - CSX - GDX- CP - Onboard ECAM & CEBS for 2FA | Approved | Local Enhancement Epic | Commercial Portfolio | 0117335 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582496 | E-582496 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-FAME FILE EEI API - Rename API Fields to m | Approved | Local Enhancement Epic | Commercial Portfolio | 0117336 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583245 | E-583245 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-ENABLE FIVE9 POST-CALL SURVEY FOR VIETNAM | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117337 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CIS-[WIN][COMM]Caterpillar Receive Certificate | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117338 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CIS-[WIN] ByteDance EC-Ship Integration | Approved | Local Enhancement Epic | Commercial Portfolio | 0117339 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580075 | E-580075 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-09-17 | 2026-08-18
Biz w/ Tech Epic: Payment Processing Fee | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117386 | 189518 | Payment Processing Fee | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Guest Pickup | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117391 | 152953 | Transform CX Program | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - F1R 2026 Eff April 20 Rate Incr | Approved | Local Enhancement Epic | Commercial Portfolio | 0117405 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582491 | E-582491 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - CRATE Regional Data Deployment APAC | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117406 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-Ingenico Lane 8000 V2 | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117420 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582157 | E-582157 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-06-16
Local Enhancement Epic: COM-GDX-AI Label Certification and URSA Validation | Approved | Local Enhancement Epic | Commercial Portfolio | 0117422 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583689 | E-583689 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-RS-KVM Switch Qualification | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117423 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582156 | E-582156 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-25 | 2026-06-16
Lifecycle Management Epic: COM-RS-HDD Qualification | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117425 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Pickup Historical Summary and Detail | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117427 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-ROPs Non-Acct Holder City Center Rebill Q | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117428 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-ROPs - Access MUT Int'l Temp Builder | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117429 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-Apple Developer Account - EAI 3536169 (MAG | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117430 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC - PRS Secrets Remedtn (Vulnerability C | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117432 |  |  | Lifecycle Management Epic | Build | E-582677 | E-582677 | 3: M | 2026-04-20 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-20
Lifecycle Management Epic: COM - RMIC - FDS CY26: Qrtly Upgrade 3rd Party S/W | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117433 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582676 | E-582676 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC - FY26 RMIC ShipToCash CVD Test Support | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117434 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582990 | E-582990 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CORE-Archive Visibility in CHT Tree View | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117435 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CORE-CHT Change Comments for System-Gene | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117436 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CP-3P Production Data Cleanup & API Ecosys | Approved | Local Enhancement Epic | Commercial Portfolio | 0117437 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583242 | E-583242 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Commercial EPIC | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0115598 | 103870 | Retire FGE Services to USPS Only Locations | Biz w/ Tech Epic |  | E-581404 | E-581404 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2027-08-31
Biz w/ Tech Epic: CPSC MVP 2 | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117493 | 163090 | CPSC PGA Message set | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-08-28
Local Enhancement Epic: COM-CSX-CE_DICE_VA & IVR Global Tracking Enhancem | Approved | Local Enhancement Epic | Commercial Portfolio | 0117496 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582077 | E-582077 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-06 | 2026-12-31
Local Enhancement Epic: COM - RMIC - New Control for PPFS for SOX Complian | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117505 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Case and Customer Support Enhancements | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0117510 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-581936 | E-581936 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - Architecture Setup | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117525 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - GSP Countries | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117526 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - DS Single Language | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117527 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - DS Multi-Language | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117528 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - Scale up | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117529 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - Headless Content | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117530 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Experimentation Framework | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117531 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - Enable Connected Eco | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117532 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - Enable Shared Nav | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117533 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - Enable New Alerts | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117534 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - On-Prem Retirement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117535 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - Inform Stakeholders | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117536 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - Support Sites | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117537 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - GDL Next Migration | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117538 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - GDL Next for Polaris | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117539 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - Migrate Mobile to CJA | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117540 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - CJA - Support Personalizatio | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117541 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: PRIDE Long Term Capabilities Features | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117565 | 180482 | PRIDE Dev Features for Cust. Migration & Cust. Exp | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2027-01-01 | 2027-12-31
Biz w/ Tech Epic: EBS GBS Automation Opportunities – AMEA/ EU | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117599 | 177893 | EBS GBS Automation Opportunities – AMEA/ EU | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Digital Platform Modernization - FE and BE | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117626 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-CY26-PI.03-Visibility Family | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117627 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Ship API — Contact Object Validation Corre | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117628 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - HPU Loading TNT Cust Migration CY26 | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117630 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Incorrect GST/Tax for Multi-Country | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117631 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM - RMIC - EY Audit Support Tracking in Canvas | Approved | Lifecycle Management Epic | Commercial Portfolio | 0117632 |  |  | Lifecycle Management Epic | Build | E-582992 | E-582992 | 2: S | 2026-04-20 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-20
Local Enhancement Epic: COM - RMIC - Modify DCIS to Accept < 999 Lines | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117633 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - Add Port Codes to DBR and ADT | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117634 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - RMIC - PRJ 1372304 - ePRS Mobile App-eMBP-P3 | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0117635 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-582594 | E-582594 | 5: XL |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Domestic multi-country / multi-level ID agreements | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117642 | 180482 | PRIDE Dev Features for Cust. Migration & Cust. Exp | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-05-01 | 2026-12-31
Lifecycle Management Epic: COM-IA-DART-FY26_PI2_Marketing Tagging_LCM | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117692 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-04-08 | 2026-06-16
Local Enhancement Epic: COM-RS-Consolidated Returns at Ship & Go | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117693 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RS-Advanced Ship Notice (ASN) Implementation | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117694 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-EN-Guest Pickup | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117696 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM - RMIC - FPOS New Charges and Updates (May 26) | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117697 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC - RDA to log User Activities | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117698 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FIT Doc Upload CA expansion | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0117086 | 108661 | Clearance Doc/info uploadTAXID | Biz w/ Tech Epic |  | E-583086 | E-583086 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-08 | 2026-11-03
Biz w/ Tech Epic: Quote, Rate, Price | Approved | Biz w/ Tech Epic | Commercial Portfolio | 0117126 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis | E-583380 | E-583380 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Sales Compensation, Reporting, iSell | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117127 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-New Charge Code Required for Saudi Arabia | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117730 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Connected Ecosystem - Sites - DS Single Language | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117745 | 157742 | COM - Connected Ecosystem Strategy | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Order Create | In Progress | Biz w/ Tech Epic | Commercial Portfolio | 0117122 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Customer Service | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117124 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Visibility | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117125 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: MSS enhancement | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117757 | 113616 | Global Spot Modernisation - Part 2 | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: COM-IA-CIS-[WIN][COMM] Onsemi Data Integration | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117785 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Upsellit Abandoned Cart Email Projec | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117786 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Lapsed Customer Re-Engagement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117788 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Add Segment number to EU First Year | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117789 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-MEISA Supplies Automation | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117790 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-CSX-Migration of CE outbound notifications to | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117821 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-PEXP-CY26-LCM-PRODUCTION-SUPPORT | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117822 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-CSX-Customer Experience Bots Migration to Auto | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117823 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-06-02 | 2026-09-15
Local Enhancement Epic: COM-RMIC-View Pricing Modernization | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117825 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-Negative bill amount after currency conve | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117826 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Guest-Specific Design for /globaltrade/v2/ | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117827 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: COM-GDX-FY27_COM_MS_eIANs_Prod Support_Patching | Not Started | Lifecycle Management Epic | Commercial Portfolio | 0117828 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-RMIC-KR ABS Enablement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117829 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Einstein Activity Capture Tuning | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117833 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Email Storage in iSell | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117834 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Storing iSell Files in EDM System | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117835 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Title of Request | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117836 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Linking FedEx Services Hub to iSell | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117837 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CRM-Container Intake Form FCF | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117838 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Salesforce Export to Adobe Analytics | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117849 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Migration of CED to DC Home Org | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117863 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-MyFedExRewards Canada Sales | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117864 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-ON24 Connector for MC | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117866 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Unified Email Suppression Logging | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117868 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Global Journey Log Data Availability | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117869 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-SFMC add Do Not Sell Flag | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117872 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Journey Log Requirement | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117873 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-Stensul CDN Image Migration | Not Started | Local Enhancement Epic | Commercial Portfolio | 0117874 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC - Ancillary Services Fees | Not Started | Biz w/ Tech Epic | Commercial Portfolio | 0117893 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: MOBIUS: ODIN data migration to AZURE | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0103288 | 7563 | TS-VL3-HybridCloud-GCPMigrateMOBIUSSurfCoDataMigra | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-03-03 | 2026-01-30
Biz w/ Tech Epic: Centralize Data Inputs | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0103589 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Alteryx Server Installation on MS Azure VM | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0103590 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Centralize Model Outputs | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0103594 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dataworks initiatives for Phoenix STC '24 | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0103632 | 7389 | Phoenix - STC - DW | Biz w/ Tech Epic | Done |  |  | 4: L | 2025-06-26 | 2025-06-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Biz w/ Tech Epic: Datawork for Phoenix STC | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0103635 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-447369 DAWG - BI Consolidation Phase2 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0103734 | 8145 | TS-VL3-DATAVISUAL-SASFedExGround | Biz w/ Tech Epic | Assessment & Analysis | E-447369 | E-447369 | 5: XL |  |  |  | 80 | 0 | 80 | 0 | No | 2024-10-16 | 2025-08-04
Biz w/ Tech Epic: EPIC AirPath+ | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0103805 | 7085 | AirPath+ | Biz w/ Tech Epic | Assessment & Analysis | E-583798 | E-583798 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0103820 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: NOP Delivery Forecast Epic 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104005 | 6727 | NOP Delivery Forecast | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-12-09 | 2025-03-25
Biz w/ Tech Epic: FXF Enablement to Apollo | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104093 | 7324 | Enhancing existing Apollo Dashboards and Expanding | Biz w/ Tech Epic | Done |  |  | 3: M | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: D&C Support | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104162 |  |  | Biz w/ Tech Epic | Backlog | E-520913 | E-520913 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2026-12-31
Biz w/ Tech Epic: Ease of Use Enhancement | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104163 | 8809 | ARROW - Air Routing Regional Operation Workstation | Biz w/ Tech Epic | Backlog | E-528123 | E-528123 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2026-12-31
Biz w/ Tech Epic: Demand & Capacity Support | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104164 | 8809 | ARROW - Air Routing Regional Operation Workstation | Biz w/ Tech Epic | Backlog | E-528124 | E-528124 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-05-01 | 2026-12-31
Biz w/ Tech Epic: Data & Report Enhancements | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104165 | 8809 | ARROW - Air Routing Regional Operation Workstation | Biz w/ Tech Epic | Backlog | E-528125 | E-528125 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2026-12-31
Biz w/ Tech Epic: DEX MVP1 | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0104207 | 8454 | Centralize admin activities | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Capability 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104497 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Capability 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104499 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Capability 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104500 | 6970 | Establish Single Source of Truth for Ops Driven CE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-02-24 | 2025-06-10
Biz w/ Tech Epic: Volupia station model | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104524 | 90346 | Volupia-move solution to OIP & station deployment | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-07 | 2025-05-19
Biz w/ Tech Epic: Volupia - country model deployment for EU | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104528 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Volupia country model | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104529 | 90346 | Volupia-move solution to OIP & station deployment | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-07 | 2025-05-21
Biz w/ Tech Epic: Dashboard – move into OIP | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104574 | 90346 | Volupia-move solution to OIP & station deployment | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-07 | 2025-04-29
Biz w/ Tech Epic: Dataworks #88715- Phase 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104655 | 6991 | EU Datamart Migration and associated Data products | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dataworks #88715- Phase 2 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104756 | 6991 | EU Datamart Migration and associated Data products | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L3 Demand and Capacity Planning -Management tool | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104932 | 6907 | (Both) Demand and Capacity Planning and Management | Biz w/ Tech Epic | Assessment & Analysis | E-492702 | E-492702 |  |  |  |  | 2 | 0 |  | 2 | No | 2024-07-22 | 2025-02-28
Biz w/ Tech Epic: *L3-Cabnit Retirement - Freight | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104933 | 9317 | Cabnit Retirement | Biz w/ Tech Epic | Build | E-492725 | E-492725 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Libra Tactical Planning Simulation tool | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104934 | 7077 | (Both) Dynamic, in-day D&C management (LIBRA) | Biz w/ Tech Epic | Done | E-492924 | E-492924 |  | 2025-06-30 | 2025-06-30 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-30 | 2025-06-30
Biz w/ Tech Epic: L2 Secure by Design - FedExSecure | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104935 | 91820 | InfoSec - Secure by Design - Phase 1 | Biz w/ Tech Epic | Launch & Evaluate | E-492917 | E-492917 | 5: XL | 2025-07-21 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-03-31 | 2025-07-21
Biz w/ Tech Epic: Short-Term Intervention Plan | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104936 | 8267 | [CLONED FROM #38250/New 80703] Short-Term Interven | Biz w/ Tech Epic | Assessment & Analysis | E-492992 | E-492992 | 3: M |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: Network Definition Source | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104937 | 6775 | WS1 - [1C - Project Zenith ] Network Definition | Biz w/ Tech Epic | Launch & Evaluate | E-492944 | E-492944 | 2: S | 2025-07-29 |  |  | 1 | 0 |  | 1 | No | 2025-03-31 | 2025-03-31 | 2025-07-29
Biz w/ Tech Epic: Air Path (Automate Load Planning Process) DW | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104938 | 7085 | AirPath+ | Biz w/ Tech Epic | Backlog | E-492733 | E-492733 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Odyssey (Recharge Phase 3) | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0104939 |  |  | Biz w/ Tech Epic | Build | E-492914 | E-492914 |  | 2025-07-15 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: Proactive CMOD Case Creation - Drive # 17515 | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104940 | 9358 | [EU] Pod 3.5 Proactive Notifications | Biz w/ Tech Epic | Done | E-492964 | E-492964 |  | 2025-07-30 | 2025-09-10 |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-30 | 2025-09-10
Biz w/ Tech Epic: EU CRA - Customer Reporting Automation Long Term S | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104941 | 7066 | ACE - Enable Proactive Monitoring & Intervention - | Biz w/ Tech Epic | Backlog | E-492807 | E-492807 |  |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: [US] CE Desktop FY25 Value Bundle - Phase B | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104942 | 8129 | [US] CE Desktop FY25 Value Bundle - Phase B | Biz w/ Tech Epic | Backlog | E-492727 | E-492727 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CDE: CDP to support Customer Data Enablement | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104943 | 9212 | Customer Data Enablement – Omnichannel Customer Jo | Biz w/ Tech Epic | Build | E-492751 | E-492751 | 3: M | 2025-07-30 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-11-28 | 2025-07-30
Biz w/ Tech Epic: DW Network Capacity Bundle 1: Unload Distribution | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104944 | 8801 | [Enabler] DW Network Capacity Bundle 1: Unload Di | Biz w/ Tech Epic | Done | E-492780 | E-492780 | 2: S | 2025-09-10 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: UKG Enterprise Implementation | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104945 | 6933 | UKG Enterprise Implementation | Biz w/ Tech Epic | Backlog | E-493016 | E-493016 |  |  |  |  | 41 | 0 |  | 41 | No | 2024-07-22 | 2025-12-31
Biz w/ Tech Epic: *L3 DW: Market Tune-Ups | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104946 | 7613 | Market Tune-Ups | Biz w/ Tech Epic | Build | E-492704 | E-492704 | 4: L | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-07 | 2025-07-07 | 2025-07-01
Biz w/ Tech Epic: Airline Performance KPI Dashboard Crew - Datawork | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104948 | 8028 | Airline Performance KPIs - Crew (POC) | Biz w/ Tech Epic | Backlog | E-492734 | E-492734 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: *L3 Critical Close Model Improvement | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104949 | 6932 | Critical Close Model Improvement | Biz w/ Tech Epic | Build | E-492701 | E-492701 |  | 2025-12-06 |  |  | 3 | 0 | 1 | 2 | No | 2025-02-04 | 2025-11-28 | 2025-12-06
Biz w/ Tech Epic: Network 2.0 Financial Tooling | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104950 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492943 | E-492943 |  |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Global Delivery Prediction Platform (GDPP) | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104951 | 9220 | [VIS] Integrated Track Data MVP | Biz w/ Tech Epic | Done | E-492837 | E-492837 | 5: XL | 2025-06-27 | 2025-06-27 |  | 1 | 0 |  | 1 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: N2.0 Premium Volume | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104952 | 9326 | [Enabler] Designated Courier Workforce Phases 1 & | Biz w/ Tech Epic | Backlog | E-492940 | E-492940 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-09-30 | 2025-11-28
Biz w/ Tech Epic: Premium Visibility Insights (PVI) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104953 | 9220 | [VIS] Integrated Track Data MVP | Biz w/ Tech Epic | Build | E-492962 | E-492962 | 5: XL | 2025-07-17 |  | 45.45% | 11 | 5 | 2 | 4 | No | 2024-07-22 | 2025-11-28 | 2025-07-17
Biz w/ Tech Epic: N2.0 Reporting Gap Closure for Express - Interim S | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104954 | 7200 | N2.0 One FedEx Reporting and Visibility - MVP1 (Pr | Biz w/ Tech Epic | Done |  |  |  | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: L2 Globalization of Track Data Monetization | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0104955 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492910 | E-492910 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L2 N2.0 Reporting - Facility Performance Reportin | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104956 | 7200 | N2.0 One FedEx Reporting and Visibility - MVP1 (Pr | Biz w/ Tech Epic | Assessment & Analysis | E-492694 | E-492694 | 2: S |  |  |  | 1 | 0 |  | 1 | Yes
Biz w/ Tech Epic: Multimodal Quoting - Capacity Management Quoting T | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104957 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Backlog | E-492939 | E-492939 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: NW 2.0 Hyperdrive 1 #1671 - Alcohol reporting | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104958 | 7816 | N2.0 Tech Phase 1 (18 month roadmap) | Biz w/ Tech Epic | Build | E-492952 | E-492952 | 4: L | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No | 2024-10-01 | 2024-10-01 | 2025-07-01
Biz w/ Tech Epic: GEMINI - Shipment Data View | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104959 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Build | E-492835 | E-492835 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-08-08 | 2026-01-30 | 2025-07-01
Biz w/ Tech Epic: NW 2.0 Hyperdrive 1 #1671 - EESSP-32 (P&D on-road | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104960 | 7816 | N2.0 Tech Phase 1 (18 month roadmap) | Biz w/ Tech Epic | Build | E-492953 | E-492953 | 4: L | 2025-07-22 |  | 100% | 5 | 5 |  | 0 | No | 2025-10-01 | 2025-11-28 | 2025-07-22
Biz w/ Tech Epic: GEMINI - Harmonized Code Identification Service (A | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104961 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Build | E-492833 | E-492833 |  | 2025-10-16 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-16
Biz w/ Tech Epic: International APAC (Load Quality Advisor) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104962 | 6799 | Load Quality Advisor (LQA) tool to support ULD den | Biz w/ Tech Epic | Build | E-492857 | E-492857 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-01
Biz w/ Tech Epic: GEMINI - Customer Facing Reports | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104963 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Done |  |  |  | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: DW: Accident and Injury Dashboard | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104964 | 6700 | Accident and Injury Dashboard | Biz w/ Tech Epic | Build | E-492703 | E-492703 | 2: S | 2025-07-01 |  |  | 8 | 0 | 6 | 2 | No | 2024-10-11 | 2026-04-30 | 2025-07-01
Biz w/ Tech Epic: GEMINI - KPI & Feedback Loops | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104965 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Build | E-492834 | E-492834 |  | 2025-09-29 |  |  | 1 | 0 |  | 1 | No | 2025-06-30 | 2025-11-28 | 2025-09-29
Biz w/ Tech Epic: Airline Performance KPI Fleet Dashboard - Datawork | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104966 | 8022 | Airline Performance KPIs - Fleet (POC) | Biz w/ Tech Epic | Backlog | E-492736 | E-492736 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: *L3 DW: WS1 1C UK Domestics into MAGNUS - 1 | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104967 | 8985 | WS1 1C UK Domestics into MAGNUS - 1 | Biz w/ Tech Epic | Backlog | E-492706 | E-492706 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L3 FDW : Service Recovery Spares Quantification ( | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104968 | 8021 | Service Recovery Spares Quantification (SRSQ) - An | Biz w/ Tech Epic | Assessment & Analysis | E-492708 | E-492708 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: ROAD 4 - Advanced Load Planning Hub Application (A | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104969 | 8941 | ALPHA - Advanced Load Planning and Hub Application | Biz w/ Tech Epic | Backlog | E-492980 | E-492980 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: FDW : Service Recovery Spares Quantification (SRSQ | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0104970 | 8021 | Service Recovery Spares Quantification (SRSQ) - An | Biz w/ Tech Epic | Assessment & Analysis | E-492810 | E-492810 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Last Mile Performance | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104971 | 91513 | Last Mile Performance | Biz w/ Tech Epic | Assessment & Analysis | E-492923 | E-492923 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: SPOTLight Evolution - Customer Experience MVP | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104972 | 6827 | [ENABLER] SPOTlight Evolution - Customer Experienc | Biz w/ Tech Epic | Build | E-493000 | E-493000 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: Enterprise Service Performance Metrics (Ties to #3 | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104973 | 6970 | Establish Single Source of Truth for Ops Driven CE | Biz w/ Tech Epic | Launch & Evaluate | E-492800 | E-492800 | 4: L | 2025-07-08 |  |  | 1 | 0 |  | 1 | No | 2025-06-02 | 2025-11-28 | 2025-07-08
Biz w/ Tech Epic: SPOTLight Evolution - Service Excellence | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104974 | 7876 | [ENABLER] SPOTlight Evolution - NW 2.0 Service Exc | Biz w/ Tech Epic | Build | E-493001 | E-493001 | 1: XS | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: Enterprise Service Disruptions | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104975 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492799 | E-492799 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2025-10-01 | 2025-12-19
Biz w/ Tech Epic: (DRO-A analytics application) Align settlement mod | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0104976 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492677 | E-492677 | 5: XL |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Enterprise Failure Analysis (RACER) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104977 | 92364 | Enterprise Failure Analysis | Biz w/ Tech Epic | Assessment & Analysis | E-492796 | E-492796 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-12-15 | 2026-08-03
Biz w/ Tech Epic: NOP Delivery Forecast | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104978 | 6727 | NOP Delivery Forecast | Biz w/ Tech Epic | Assessment & Analysis | E-492951 | E-492951 | 2: S |  |  | 50% | 2 | 1 |  | 1 | No | 2026-01-12 | 2026-12-24
Biz w/ Tech Epic: Enterprise Network Monitor (inclusive of Service a | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104979 | 9378 | Enterprise Network Monitor | Biz w/ Tech Epic | Launch & Evaluate | E-492797 | E-492797 | 4: L | 2025-07-21 |  |  | 1 | 0 |  | 1 | No | 2025-02-14 | 2026-08-31 | 2025-07-21
Biz w/ Tech Epic: SPOTLight | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104980 | 8896 | SPOTlight- | Biz w/ Tech Epic | Build | E-492999 | E-492999 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: CEM + Initial Commit | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104981 | 7784 | Customer Experience Metric MVP | Biz w/ Tech Epic | Assessment & Analysis | E-492752 | E-492752 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-08-01 | 2026-05-01
Biz w/ Tech Epic: Airline Performance KPI Fuel Dashboard - Dataworks | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104982 | 6987 | Airline Performance KPIs - Fuel (POC) | Biz w/ Tech Epic | Backlog | E-492737 | E-492737 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: Enhanced Engineered Demand Planning - N2.0 | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104984 | 6911 | [ENABLER] Enhanced Engineered Demand Planning - N2 | Biz w/ Tech Epic | Done | E-492793 | E-492793 | 2: S | 2025-07-01 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Biz w/ Tech Epic: Enhanced Engineering Demand Planning - VB1 | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104985 | 8100 | Enhanced Engineering Demand Planning - VB1 | Biz w/ Tech Epic | Done | E-492794 | E-492794 | 3: M | 2025-07-01 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Biz w/ Tech Epic: WS1 - [1C - Project Zenith ] Comprehensive E2E Net | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104986 | 6786 | WS1 - [1C - Project Zenith ] Comprehensive E2E Net | Biz w/ Tech Epic | Assessment & Analysis | E-493027 | E-493027 | 5: XL |  |  | 12.5% | 8 | 1 | 1 | 6 | No | 2025-05-30 | 2025-11-28
Biz w/ Tech Epic: Enhanced Engineering Demand Planning - VB2 | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104987 | 8101 | Enhanced Engineering Demand Planning - VB2 | Biz w/ Tech Epic | Backlog | E-492795 | E-492795 | 1: XS |  |  |  | 1 | 0 |  | 1 | Yes | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: WS1 - [1C - Project Zenith ] Interim EU Flow Plan | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0104988 | 6788 | WS1 - [1C - Project Zenith ] Interim SFP | Biz w/ Tech Epic | Assessment & Analysis | E-493029 | E-493029 | 2: S |  |  | 25% | 4 | 1 | 2 | 1 | No
Biz w/ Tech Epic: Network Operating Plan - Value Bundle 1.1 -1.3 | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104989 | 9429 | Network Operating Plan (NOP) Sort Plan - 2 week | Biz w/ Tech Epic | Done | E-492945 | E-492945 | 3: M | 2025-07-01 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Biz w/ Tech Epic: Network Operating Plan (NOP) VB1.4 Sort Plan (3 mo | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0104990 | 9440 | Network Operating Plan (NOP) Sort Plan - Peak&3mo | Biz w/ Tech Epic | Done | E-492946 | E-492946 | 3: M | 2025-07-01 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Biz w/ Tech Epic: TRACK Re-engineer | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104991 | 9045 | Enterprise Drayage | Biz w/ Tech Epic | Backlog | E-493011 | E-493011 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Biz w/ Tech Epic: Airline Performance KPI Dashboard GPN - Dataworks | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0104992 | 8019 | Airline Performance KPIs - GPN (POC) | Biz w/ Tech Epic | Backlog | E-492735 | E-492735 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: CLH KPI Dashboard – DW Execution Initiative | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104994 | 7602 | CLH KPI Dashboard – DW Execution Initiative | Biz w/ Tech Epic | Build | E-492756 | E-492756 | 2: S | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: L1 PathTracker lift and shift of model to Datawork | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0104995 | 91995 | PathTracker lift and shift of model to Dataworks | Biz w/ Tech Epic | Assessment & Analysis | E-492891 | E-492891 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L3 GOC Ad hoc cost calculator with volume revenue | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104996 | 7434 | GOC Ad hoc cost calculator with volume revenue | Biz w/ Tech Epic | Build | E-492710 | E-492710 | 3: M | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2024-10-31 | 2024-10-31 | 2025-07-01
Biz w/ Tech Epic: Medical Service Tower- Station/Ramp | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104997 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Backlog | E-492932 | E-492932 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-31 | 2025-11-28
Biz w/ Tech Epic: GOC Commercial Linehaul Visibility | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0104998 | 7435 | GOC Commercial Linehaul Visibility | Biz w/ Tech Epic | Done | E-492840 | E-492840 | 1: XS | 2025-07-01 | 2025-07-01 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-07-01
Biz w/ Tech Epic: MST / CST Global Adoption | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0104999 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Backlog | E-492937 | E-492937 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-11-29 | 2025-11-28
Biz w/ Tech Epic: *L3 GOC Jet Fuel - Payload Visibility Improvements | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105000 | 6967 | GOC Jet Fuel - Payload Visibility Improvements | Biz w/ Tech Epic | Assessment & Analysis | E-492711 | E-492711 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: *L3 GOC Proactively identify potential volume spik | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105002 | 7381 | GOC Proactively identify potential volume spikes t | Biz w/ Tech Epic | Assessment & Analysis | E-492712 | E-492712 | 5: XL |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: L2 Global P&D Ecosystem Enabler | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105003 | 7406 | Global P&D Ecosystem Enabler | Biz w/ Tech Epic | Build | E-492909 | E-492909 |  | 2025-07-18 |  | 100% | 1 | 1 |  | 0 | No | 2025-01-31 | 2025-01-31 | 2025-07-18
Biz w/ Tech Epic: *L3 GOC Slot Swap Tool Replacement | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105004 | 6969 | GOC Slot Swap Tool | Biz w/ Tech Epic | Assessment & Analysis | E-492713 | E-492713 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No | 2024-10-14 | 2024-10-14
Biz w/ Tech Epic: L2 PLANS - Planning Labor and Network Scheduling | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105005 | 9066 | PLANS - US Air Planning Labor & Rostering | Biz w/ Tech Epic | Build | E-492913 | E-492913 | 2: S | 2025-07-15 |  | 50% | 2 | 1 |  | 1 | No | 2026-01-30 | 2026-01-30 | 2025-07-15
Biz w/ Tech Epic: Damaged Package Tool (DPT) New Opportunities & New | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105006 | 7659 | Damaged Package Tool (DPT) New Opportunities & New | Biz w/ Tech Epic | Backlog | E-492765 | E-492765 | 3: M |  |  |  | 5 | 0 |  | 5 | No | 2024-10-23 | 2026-05-29
Biz w/ Tech Epic: WS8 - GS4 – CED Data Visibility, Intent Classific | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105007 | 7655 | WS8 - GS4 – CED Data Visibility, Intent Classific | Biz w/ Tech Epic | Backlog | E-493032 | E-493032 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: *L3 Ramps - Freight P&D stops / hr improvement | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105008 | 7786 | Ramps - Freight P&D stops / hr improvement | Biz w/ Tech Epic | Build | E-492718 | E-492718 | 1: XS | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: *L3 VIRGO - Global (Under)Valuation Infringement R | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105009 | 9047 | VIRGO - Global (Under)Valuation Infringement Reduc | Biz w/ Tech Epic | Build | E-492722 | E-492722 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-02
Biz w/ Tech Epic: Dock Data Modernization | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105010 | 7145 | [Enabler] Dock Data Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-492773 | E-492773 | 1: XS |  |  |  | 2 | 0 |  | 2 | No | 2025-08-08 | 2027-01-27
Biz w/ Tech Epic: L1 Hope Enablement- Part 2 (Additional Payment Met | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105011 | 89754 | Hope Enablement- Part 2 (Additional Payment Method | Biz w/ Tech Epic | Assessment & Analysis | E-492880 | E-492880 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L2 [Enabler] Compass - Surface Priority Metrics | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105012 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492691 | E-492691 | 4: L |  |  |  | 1 | 0 |  | 1 | Yes | 2025-05-09 | 2025-11-28
Biz w/ Tech Epic: LTP (Local Transport Provider) PFS | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105013 | 8085 | EMR – WS6 – Develop & implement CSP PFS | Biz w/ Tech Epic | Build | E-492929 | E-492929 | 1: XS | 2026-01-28 |  |  | 1 | 0 | 1 | 0 | No | 2025-11-24 | 2026-04-30 | 2026-01-28
Biz w/ Tech Epic: Compass VB2 & VB3 (Ground) | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105014 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Done | E-492760 | E-492760 | 3: M | 2025-07-07 | 2025-07-07 |  | 1 | 0 |  | 1 | No |  |  | 2025-07-07 | 2025-07-07
Biz w/ Tech Epic: WS11 - I-EU B2C: Become a market relevant B2C play | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105015 | 8174 | WS11 - I-EU B2C: Global Direct-to-Retail | Biz w/ Tech Epic | Backlog | E-449037 | E-449037 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-11-28
Biz w/ Tech Epic: Foundational Data for Dock Mod | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105016 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Build | E-492824 | E-492824 | 5: XL | 2025-07-25 |  |  | 2 | 0 | 1 | 1 | No | 2024-10-25 | 2026-09-04 | 2025-07-25
Biz w/ Tech Epic: Real-Time Ops Manager (ROM) | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105018 | 9518 | Real-Time Ops Manager (ROM) | Biz w/ Tech Epic | Backlog | E-492969 | E-492969 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: L2 WS1 - [1B - Project Zenith ] Common Data Model | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105019 | 7693 | WS1 - [1B] Shipment CDM - First iteration for Sort | Biz w/ Tech Epic | Backlog | E-492921 | E-492921 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-12-16 | 2025-08-01
Biz w/ Tech Epic: L2 [IN][OB] 5% Yield improvement on spot shipments | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105020 | 7183 | [IN][OB] 5% Yield improvement on spot shipments | Biz w/ Tech Epic | Assessment & Analysis | E-492900 | E-492900 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: *L1 Transit Time Data Enablement | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105021 | 85939 | Transit Time Data Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-492689 | E-492689 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L3 iClear collaboration with Dataworks - AMEA | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105022 | 6897 | [APAC] iClear collaboration with Dataworks | Biz w/ Tech Epic | Build | E-492714 | E-492714 | 3: M | 2025-11-19 |  |  | 1 | 0 | 1 | 0 | No | 2024-11-26 | 2025-11-28 | 2025-11-19
Biz w/ Tech Epic: DW: ROCS2.0 Reporting Data to dAtlas | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105023 | 7393 | ROCS2.0 Reporting Data to dAtlas | Biz w/ Tech Epic | Backlog | E-492785 | E-492785 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-31 | 2027-04-01
Biz w/ Tech Epic: PUD 1 - VRP Route Optimization Tool | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105024 | 7649 | 03 - Increase Route Productivity - PUD Planning To | Biz w/ Tech Epic | Build | E-492965 | E-492965 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: ROCS 2.0 - Data Ingestion | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105025 | 7393 | ROCS2.0 Reporting Data to dAtlas | Biz w/ Tech Epic | Backlog | E-492981 | E-492981 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-11-25 | 2025-11-28
Biz w/ Tech Epic: VOLUPIA | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105026 | 7649 | 03 - Increase Route Productivity - PUD Planning To | Biz w/ Tech Epic | Build | E-493021 | E-493021 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: PUD 3 – In-Station Optimization | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105028 | 7638 | 04 - Optimize in-station processes | Biz w/ Tech Epic | Build | E-492966 | E-492966 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: PUD 4 - Inbound Linehaul Visibility | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105029 | 7638 | 04 - Optimize in-station processes | Biz w/ Tech Epic | Build | E-492967 | E-492967 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: IVVI / SIV | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105030 | 7627 | 06 - EU PUD Route Optimization - Integrated countr | Biz w/ Tech Epic | Done |  |  | 4: L | 2025-06-26 | 2025-06-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Biz w/ Tech Epic: L2 AU PCC customer Self-Serve Portal | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105031 | 89676 | AU PCC Customer Self-Serve Portal | Biz w/ Tech Epic | Assessment & Analysis | E-492903 | E-492903 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Centralize Admin Activities - Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105032 | 8454 | Centralize admin activities | Biz w/ Tech Epic | Assessment & Analysis | E-492753 | E-492753 | 2: S |  |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-11-28
Biz w/ Tech Epic: L2 Packaging - Launch Reusable Packaging (US) | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105033 | 7647 | Packaging - Launch Reusable Packaging (US) | Biz w/ Tech Epic | Assessment & Analysis | E-492912 | E-492912 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-11-12 | 2024-11-27
Biz w/ Tech Epic: First Time Delivery Success Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105034 | 9471 | Improve first time delivery success | Biz w/ Tech Epic | Assessment & Analysis | E-492822 | E-492822 | 1: XS |  |  |  | 1 | 0 | 1 | 0 | No | 2025-02-19 | 2025-11-28
Biz w/ Tech Epic: *L1 Enhanced Workforce Visibility & Decision Suppo | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105035 | 88756 | Workforce Decisioning | Biz w/ Tech Epic | Assessment & Analysis | E-492683 | E-492683 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DW: WS1 - [1A] Improve address correction by autom | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105036 | 7866 | WS1 - 1A Improve address correction by automation | Biz w/ Tech Epic | Build | E-492787 | E-492787 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No | 2024-11-25 | 2025-02-07 | 2025-07-15
Biz w/ Tech Epic: VRP Route Optimization Tool PUD 1 | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105037 | 7787 | Product Commit Modeling | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EU - Automate the Application of Pickup Scans for | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105038 | 8861 | WS2 - Automate the application of pickup scans and | Biz w/ Tech Epic | Assessment & Analysis | E-492804 | E-492804 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2024-12-31 | 2025-11-28
Biz w/ Tech Epic: *L3 WS6 - Acquire LTP cost data for EU non-integra | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105039 | 8441 | WS6 - Acquire LTP cost data for EU non-integrated | Biz w/ Tech Epic | Build | E-492724 | E-492724 | 4: L | 2025-09-04 |  |  | 1 | 0 | 1 | 0 | No | 2025-01-09 | 2025-11-28 | 2025-09-04
Biz w/ Tech Epic: Cross-Network Flow Planning (OTB) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105040 |  |  | Biz w/ Tech Epic | Build | E-492763 | E-492763 | 4: L | 2025-07-22 |  | 66.67% | 3 | 2 | 1 | 0 | No | 2025-01-31 | 2025-01-31 | 2025-07-22
Biz w/ Tech Epic: OTB - Shipment Eligibility Orchestrator | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105041 |  |  | Biz w/ Tech Epic | Build | E-492955 | E-492955 | 3: M | 2025-07-15 |  |  | 1 | 0 | 1 | 0 | No | 2024-10-15 | 2025-11-28 | 2025-07-15
Biz w/ Tech Epic: DEX03 Bad Address Process Improvement | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105042 | 8352 | Improve DEX03 (Bad Address) Handling | Biz w/ Tech Epic | Build | E-492771 | E-492771 | 2: S | 2026-04-16 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-04-16
Biz w/ Tech Epic: L1 Legacy Retirement of Air Expedite Applications | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105043 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492883 | E-492883 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Improve DEX08 Customer Not In Package Handling | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105044 | 8353 | Improve DEX08 (Business Closed/Recipient Not In) h | Biz w/ Tech Epic | Build | E-492852 | E-492852 | 2: S | 2025-07-19 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-19
Biz w/ Tech Epic: L1 Legacy Retirement of Air Expedite Applications | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105045 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492884 | E-492884 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L2 Small Parcel Reusable Bag Deployment | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105046 | 89380 | Global-Small Parcel Reusable Bag-Parent-US | Biz w/ Tech Epic | Assessment & Analysis | E-492919 | E-492919 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: WS9 - EU Customer Migration Technical Architecture | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105047 |  |  | Biz w/ Tech Epic | Build | E-493034 | E-493034 |  | 2025-09-04 |  | 100% | 1 | 1 |  | 0 | No | 2024-09-30 | 2024-09-30 | 2025-09-04
Biz w/ Tech Epic: L2 Package Service Delays - Phase 4 - Weather Dela | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105048 | 7744 | Package Service Delays - Phase 4 - Weather Delays, | Biz w/ Tech Epic | Assessment & Analysis | E-492911 | E-492911 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: WS9 - EU Customer Migration Strategy | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105049 |  |  | Biz w/ Tech Epic | Build | E-493033 | E-493033 |  | 2025-09-04 |  | 100% | 1 | 1 |  | 0 | No | 2024-12-31 | 2024-12-31 | 2025-09-04
Biz w/ Tech Epic: WS9 - fdx Migration Large Solutioning Customer - P | In Progress | Biz w/ Tech Epic | Data & AI Portfolio | 0105051 |  |  | Biz w/ Tech Epic | Build | E-493039 | E-493039 |  | 2025-09-09 |  | 100% | 1 | 1 |  | 0 | No | 2024-12-31 | 2024-12-31 | 2025-09-09
Biz w/ Tech Epic: Golden eye reporting: Build Daily Monitoring Repor | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105052 | 9155 | Increased Capture of Express Operational Data | Biz w/ Tech Epic | Done | E-492842 | E-492842 |  | 2025-07-01 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Biz w/ Tech Epic: WS9 - fdx Migration Large Solutioning Customer - P | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105053 |  |  | Biz w/ Tech Epic | Build | E-493035 | E-493035 |  | 2025-09-04 |  | 100% | 1 | 1 |  | 0 | No | 2024-12-31 | 2024-12-31 | 2025-09-04
Biz w/ Tech Epic: Revenue Recovery | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105054 | 7148 | Revenue Recovery of Weight (RRW) | Biz w/ Tech Epic | Done | E-492975 | E-492975 | 5: XL | 2025-07-23 | 2025-07-23 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-23 | 2025-07-23
Biz w/ Tech Epic: *L3 External Customer Reporting Project PFS | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105055 | 7358 | External Customer Reporting Project PFS | Biz w/ Tech Epic | Done |  |  |  | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: L1 CA - Introduce FedEx Home Delivery (FHD) in Can | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105056 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492865 | E-492865 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Address Intelligence Suite - Model development | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105057 | 7640 | Address Intelligence Suite | Biz w/ Tech Epic | Assessment & Analysis | E-492731 | E-492731 |  |  |  |  | 2 | 0 | 1 | 1 | No | 2024-07-22 | 2025-11-28
Biz w/ Tech Epic: Returns (ABR, Exchanges, etc) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105058 | 6885 | Sirius - Segment/CX - Branded Returns | Biz w/ Tech Epic | Build | E-492973 | E-492973 | 4: L | 2025-07-18 |  | 7.692% | 39 | 3 | 11 | 25 | No | 2024-10-01 | 2028-05-30 | 2025-07-18
Biz w/ Tech Epic: SAS Migration Air Ops GRID | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105059 | 9390 | TS-VL3-DATAVISUAL-SASFedExAirOpsTechGRID | Biz w/ Tech Epic | Assessment & Analysis | E-492985 | E-492985 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DW - 82747 Optimum Flight Dispatch- Machine Learn | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105060 | 7338 | Optimum Flight Dispatch- Machine Learning | Biz w/ Tech Epic | Build | E-492777 | E-492777 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: L2 Tug Optimization | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105061 | 8515 | Tug Dispatch Management | Biz w/ Tech Epic | Assessment & Analysis | E-492920 | E-492920 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L2 WS2 - Build ULD Move Model to enable CDG effic | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105062 | 7454 | WS2 - Build ULD Move Model to enable CDG efficienc | Biz w/ Tech Epic | Assessment & Analysis | E-492698 | E-492698 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: DWs support EU Datamart and associated Data produc | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105063 | 6991 | EU Datamart Migration and associated Data products | Biz w/ Tech Epic | Build | E-492788 | E-492788 | 4: L | 2025-07-01 |  | 61.54% | 26 | 16 | 10 | 0 | No | 2024-09-27 | 2028-07-10 | 2025-07-01
Biz w/ Tech Epic: Digital Hub Planner Model + App | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105064 | 8382 | Digital Hub Planner Model + App | Biz w/ Tech Epic | Build | E-492772 | E-492772 |  | 2025-07-25 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-11-28 | 2025-07-25
Biz w/ Tech Epic: Dock Layout Optimization | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105065 | 9543 | Dock Layout Tool Mod. | Biz w/ Tech Epic | Build | E-492774 | E-492774 |  | 2025-07-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-25
Biz w/ Tech Epic: WS7 - Optimize AHS surcharges: New Data Quality Da | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105066 | 7689 | WS7 - Optimize AHS surcharges through GRI / CPR cl | Biz w/ Tech Epic | Backlog | E-493031 | E-493031 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-11-07 | 2025-03-19
Biz w/ Tech Epic: L1 AHS-P (Straps) - Introduction of charge in Euro | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105067 | 93239 | AHS-P (Straps) - Introduction of charge in Europe | Biz w/ Tech Epic | Assessment & Analysis | E-492864 | E-492864 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ROAD 1 - Trailer Balancing & Inventory Visibility | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105069 | 8963 | Decrease empty trailers from volume imbalanced cou | Biz w/ Tech Epic | Backlog | E-492977 | E-492977 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Apollo: Support Expiring Pricing Dashboard Use cas | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105070 | 9338 | EPD ( Expiring Pricing Dashboard) Lift & Shift to | Biz w/ Tech Epic | Build | E-492741 | E-492741 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: ROAD 3 - Sort Time Windows Planning | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105071 | 8908 | Introduce Sort Time Windows | Biz w/ Tech Epic | Build | E-492979 | E-492979 |  | 2025-07-17 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-17
Biz w/ Tech Epic: Apollo new FXF enablement use case for FY 25 | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105072 | 7324 | Enhancing existing Apollo Dashboards and Expanding | Biz w/ Tech Epic | Done | E-492740 | E-492740 |  | 2025-06-26 | 2025-06-26 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Biz w/ Tech Epic: ROAD 2 - Daily Load Factor (MAGNUS) | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105073 | 8919 | Magnus 2.0 | Biz w/ Tech Epic | Backlog | E-492978 | E-492978 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: L2 FY 25 Enhance Existing Apollo Dashboard | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105074 | 7324 | Enhancing existing Apollo Dashboards and Expanding | Biz w/ Tech Epic | Assessment & Analysis | E-492907 | E-492907 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DW: WS 2 - Increasing Service performance by visua | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105075 | 7635 | WS 2 - Load content sequence and priority summary | Biz w/ Tech Epic | Assessment & Analysis | E-492786 | E-492786 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: L1 Continue - CEDL to Atlas Migration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105076 | 93162 | Continue - CEDL to Atlas Migration | Biz w/ Tech Epic | Assessment & Analysis | E-492867 | E-492867 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: LSSI Banded Commit Analysis Tools | Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105077 | 9243 | Banded Commit for Competitive Profitable Network | Biz w/ Tech Epic | Done | E-492927 | E-492927 | 4: L | 2025-06-30 | 2025-06-30 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-30 | 2025-06-30
Biz w/ Tech Epic: LSSI Banded Commit Analysis Tools MVP2 | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105078 |  |  | Biz w/ Tech Epic | Build | E-492928 | E-492928 | 4: L | 2025-07-17 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-17
Biz w/ Tech Epic: Harmonized System (HS) Code Classification | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105080 | 8038 | HS Auto-Classification-Pre-Shipping with WorldTari | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | Yes | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: *L3 WS5 – Operational Analytics (KPIs) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105081 | 6696 | WS5 - Operational Analytics (KPIs) | Biz w/ Tech Epic | Build | E-492723 | E-492723 | 5: XL | 2025-07-25 |  | 30% | 20 | 6 | 11 | 3 | No | 2025-02-28 | 2025-11-28 | 2025-07-25
Biz w/ Tech Epic: L1 Streamline Clearance EU Process Utilising RPA | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105082 | 88479 | Streamline Clearance EU Process using RPA [ECTS] | Biz w/ Tech Epic | Assessment & Analysis | E-492899 | E-492899 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L2 WS-8 GS3 Minimum Quality Mgmt Framework for Cu | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105083 | 9133 | WS8 - GS3 - Minimum Quality Mgmt Framework | Biz w/ Tech Epic | Assessment & Analysis | E-492699 | E-492699 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-05-30 | 2025-05-30
Biz w/ Tech Epic: *L1 Optimum Flight Dispatch: Data transfer to air | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105084 | 7449 | Optimum Flight Dispatch: Data transfer to air oper | Biz w/ Tech Epic | Assessment & Analysis | E-492688 | E-492688 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: SAS Migration EU - Europe - Marketing ID Cust Anal | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105085 | 6900 | BI Consol - SAS - EU - Europe - Marketing ID Cust | Biz w/ Tech Epic | Assessment & Analysis | E-492986 | E-492986 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: GDX Data Transfer to Atlas | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105086 | 8420 | Digital-Enablers-Analytics | Biz w/ Tech Epic | Assessment & Analysis | E-492863 | E-492863 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SAS Migration FedEx Marketing | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105087 | 7121 | TS-VL3-DATAVISUAL-SASFedExMarketing | Biz w/ Tech Epic | Assessment & Analysis | E-492988 | E-492988 |  |  |  | 100% | 100 | 100 |  | 0 | No
Biz w/ Tech Epic: 2.0: Enterprise Badging & Physical Access Data&AI | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105088 | 92356 | 92356- ENT Badging and Physical Access Release 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-492875 | E-492875 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SAS Migration FedEx Marketing POC | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105089 | 7121 | TS-VL3-DATAVISUAL-SASFedExMarketing | Biz w/ Tech Epic | Assessment & Analysis | E-492989 | E-492989 |  |  |  |  | 1 | 0 |  | 1 | No | 2026-07-31 | 2026-07-31
Biz w/ Tech Epic: SAS migration FedEx Freight | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105090 | 7127 | BI Consol - SAS - FedEx Freight | Biz w/ Tech Epic | Assessment & Analysis | E-492987 | E-492987 |  |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: FDW Clearance: Estimated Landed Cost Bundle | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105091 | 6807 | Estimated Landed Cost (ELC) Commercialization | Biz w/ Tech Epic | Assessment & Analysis | E-492811 | E-492811 |  |  |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-08-16
Biz w/ Tech Epic: SAS Migration: FedEx Freight Pilot | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105092 | 7127 | BI Consol - SAS - FedEx Freight | Biz w/ Tech Epic | Backlog | E-492990 | E-492990 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-08-15 | 2025-08-15
Biz w/ Tech Epic: GCP Odin Retirement | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105093 | 7614 | Decision Science Pilot Apps Migration to Azure - E | Biz w/ Tech Epic | Assessment & Analysis | E-492831 | E-492831 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-08-05 | 2025-11-28
Biz w/ Tech Epic: L2 SAS Migration: FedEx Ground - Resource Alloc | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105094 | 8145 | TS-VL3-DATAVISUAL-SASFedExGround | Biz w/ Tech Epic | Assessment & Analysis | E-492916 | E-492916 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 ODIN Retirement: Surface Apps Migration to Azur | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105095 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492889 | E-492889 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L2 [VIS] Residential Delivery Instructions Enhance | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105096 | 7167 | [VIS] Residential Delivery Instructions Enhancemen | Biz w/ Tech Epic | Assessment & Analysis | E-492901 | E-492901 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L1 Export Shipment Analytics | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105097 | 7013 | Export Shipment Analytics | Biz w/ Tech Epic | Assessment & Analysis | E-492684 | E-492684 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: WS1 - [1C - Project Zenith ] Forecasting | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105098 | 8442 | WS1 - [1C - Project Zenith ] Forecast Solution | Biz w/ Tech Epic | Assessment & Analysis | E-493028 | E-493028 | 2: S |  |  |  | 6 | 0 | 3 | 3 | Yes
Biz w/ Tech Epic: GOC Jet Fuel - Payload Visibility Improvements - D | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105099 | 6967 | GOC Jet Fuel - Payload Visibility Improvements | Biz w/ Tech Epic | Assessment & Analysis | E-492841 | E-492841 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: L1 DPFS - NEW Secured Delivery Service (QR Code) | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105100 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492869 | E-492869 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L3 Reduce manual handling efforts in stations (WS | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105101 | 7705 | WS7 - Reduce Manual Handling Efforts in Stations | Biz w/ Tech Epic | Backlog | E-492719 | E-492719 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-07-22 | 2024-07-22
Biz w/ Tech Epic: Unified Equipment Pool (rail + dray) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105102 | 7318 | Unified Equipment Pool (rail + dray) | Biz w/ Tech Epic | Build | E-493017 | E-493017 |  | 2025-07-14 |  | 100% | 1 | 1 |  | 0 | No | 2025-03-31 | 2025-12-05 | 2025-07-14
Biz w/ Tech Epic: Common Sort Value Bundle 1 - DW | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105103 | 7216 | Common Sort - Value Bundle 1 | Biz w/ Tech Epic | Backlog | E-492759 | E-492759 | 3: M |  |  |  | 2 | 0 |  | 2 | No | 2025-10-01 | 2026-05-29
Biz w/ Tech Epic: Automated Billing And Clearance Using Synapse (ABA | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105104 | 7229 | Improve Broker Reconciliation by reducing Gross Wr | Biz w/ Tech Epic | Build | E-492744 | E-492744 | 3: M | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Establish Single Source of Truth for Service Visib | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105105 | 7779 | Enterprise Service Data | Biz w/ Tech Epic | Backlog | E-492803 | E-492803 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: *L3 Launch Automated Billing And Clearance Using S | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105106 | 9062 | Launch - Automated Billing And Clearance (ABACUS) | Biz w/ Tech Epic | Build | E-492716 | E-492716 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: L1 - Dataworks Azure Usage Optimization | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105107 | 87973 | Dataworks Azure Usage Optimization | Biz w/ Tech Epic | Assessment & Analysis | E-492862 | E-492862 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CA - Correct Address Prior to Destination Arrival | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105108 | 9266 | CA - Correct Address Prior to Destination Arrival | Biz w/ Tech Epic | Backlog | E-492749 | E-492749 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: L1 GCP Migration and Exit | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105109 | 88640 | TS-VL3-HybridCloud-GCPMigration | Biz w/ Tech Epic | Assessment & Analysis | E-492879 | E-492879 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CLH Tool kit Rationalization | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105110 | 9527 | International Commercial Linehaul - VSOP | Biz w/ Tech Epic | Build | E-492757 | E-492757 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: Commercial Data Migration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105111 | 88108 | Commercial Data Migration - Journey Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-492904 | E-492904 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-03-02 | 2026-11-27
Biz w/ Tech Epic: *L3 LAC: Enabler: Improve LAC scan compliance and | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105112 | 8289 | LAC: Enabler: Improve LAC scan compliance and adop | Biz w/ Tech Epic | Done | E-492715 | E-492715 | 2: S | 2025-07-08 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-08 | 2025-09-10
Biz w/ Tech Epic: L2 Delivery PFS - Commercial Delivery Management P | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105113 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492905 | E-492905 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: *L3 USI: US OB: Export screening compliance - gran | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105114 | 8356 | USI: US OB: Export screening compliance | Biz w/ Tech Epic | Done | E-492721 | E-492721 | 2: S | 2025-07-01 | 2025-07-01 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-07-01
Biz w/ Tech Epic: L1 Legal-Remove Minimums and Stop Rounding (in HCH | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105116 | 89357 | Legal - Remove Minimums and Stop Rounding (in HCH) | Biz w/ Tech Epic | Assessment & Analysis | E-492885 | E-492885 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DW: Multi Dim | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105117 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Launch & Evaluate | E-492783 | E-492783 | 3: M | 2025-06-30 |  |  | 1 | 0 |  | 1 | No |  |  | 2025-06-30
Biz w/ Tech Epic: L1 EEI Filing Enhancements | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105119 | 84577 | EEI Filing Enhancements | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EADD - FRO C1.2 | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105121 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Build | E-492789 | E-492789 | 3: M | 2025-07-25 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-25
Biz w/ Tech Epic: NoN - Replace Surface-Freight Planning Tool (LNAT) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105122 | 7228 | Origin Market Surface First - N2.0 Tech Phase II / | Biz w/ Tech Epic | Build | E-492949 | E-492949 |  | 2025-07-22 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-22
Biz w/ Tech Epic: NoN - SSP OB Flow Planning | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105123 | 7228 | Origin Market Surface First - N2.0 Tech Phase II / | Biz w/ Tech Epic | Build | E-492950 | E-492950 |  | 2025-07-22 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-22
Biz w/ Tech Epic: NoN - Combined Shipment Flow Plan | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105124 | 7228 | Origin Market Surface First - N2.0 Tech Phase II / | Biz w/ Tech Epic | Done | E-492948 | E-492948 | 3: M | 2025-07-29 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-29 | 2025-09-10
Biz w/ Tech Epic: Contingency Overhaul | Assumed Completed | Biz w/ Tech Epic | Data & AI Portfolio | 0105125 | 7560 | Contingency Process Overhaul - Front End | Biz w/ Tech Epic | Build | E-492762 | E-492762 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: SP Liquidated Damages (SP Contractual Obligation) | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105126 | 8914 | Pursuit of Liquidated Damages for Service Failures | Biz w/ Tech Epic | Build | E-492998 | E-492998 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: HTM Model Phase 2 Release 0 Streaming Refactor | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105127 | 7151 | Operational Hold to Match (HTM) | Biz w/ Tech Epic | Backlog | E-492850 | E-492850 | 1: XS |  |  |  | 2 | 0 |  | 2 | No
Biz w/ Tech Epic: Generic Broker Interface (GBI) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105128 | 7906 | Generic Broker Interface (GBI) | Biz w/ Tech Epic | Build | E-492836 | E-492836 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-01
Biz w/ Tech Epic: Hold to Match | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105129 | 7894 | Hold to Match (HTM) - Actuals Tracking Only | Biz w/ Tech Epic | Build | E-492848 | E-492848 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: L1 Dynamic Pick up for a Healthcare Diagnostic Sol | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105130 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | E-492871 | E-492871 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: First Overnight product service improvement - gran | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105131 | 7844 | First Overnight product service improvement | Biz w/ Tech Epic | Build | E-492821 | E-492821 |  | 2025-07-31 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-31
Biz w/ Tech Epic: US CBP ACAS Vague Description Enforcement | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105132 | 7310 | US CBP ACAS Vague Description Enforcement | Biz w/ Tech Epic | Assessment & Analysis | E-493018 | E-493018 |  |  |  | 100% | 1 | 1 |  | 0 | No | 2025-09-01 | 2025-09-01
Biz w/ Tech Epic: Reduction of Origin Wrong Day Lates (WDLs) - Focus | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105133 | 8888 | Reduction of Origin Wrong Day Lates (WDLs) - Focus | Biz w/ Tech Epic | Done | E-492970 | E-492970 | 1: XS | 2025-08-04 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-04 | 2025-09-10
Biz w/ Tech Epic: L2 SAP BO Replacement | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105134 | 8424 | SAP BO Replacement | Biz w/ Tech Epic | Assessment & Analysis | E-492915 | E-492915 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L3 Scan Integrity - Improving Scan Compliance Thr | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105135 | 9073 | Scan Integrity - Improving Scan Compliance Through | Biz w/ Tech Epic | Assessment & Analysis | E-492720 | E-492720 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-10-24 | 2024-10-24
Biz w/ Tech Epic: L3 Drayage Optimization (Now) | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105136 | 6715 | Drayage Optimization (Now) | Biz w/ Tech Epic | Build | E-492922 | E-492922 | 3: M | 2025-07-14 |  | 100% | 1 | 1 |  | 0 | No | 2025-03-06 | 2025-07-31 | 2025-07-14
Biz w/ Tech Epic: *L3 Predictive Tech. (#27253) | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105137 | 8780 | Using Predictive Technology to Enhance the Custome | Biz w/ Tech Epic | Assessment & Analysis | E-492717 | E-492717 | 3: M |  |  |  | 2 | 0 |  | 2 | No | 2025-11-03 | 2026-06-05
Biz w/ Tech Epic: DW: MOBIUS | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105138 | 7563 | TS-VL3-HybridCloud-GCPMigrateMOBIUSSurfCoDataMigra | Biz w/ Tech Epic | Build | E-492705 | E-492705 | 3: M | 2025-07-15 |  |  | 7 | 0 | 2 | 5 | No | 2025-06-30 | 2026-03-16 | 2025-07-15
Biz w/ Tech Epic: Build GRIP Platform to Support Spot Pricing | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105140 | 8195 | Dynamic Pricing - Spot Pricing Reco. Engine | Biz w/ Tech Epic | Build | E-492747 | E-492747 |  | 2025-07-01 |  |  | 3 | 0 | 3 | 0 | No | 2025-03-05 | 2028-07-12 | 2025-07-01
Biz w/ Tech Epic: Overflow / Reload Rules | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105141 | 8104 | Overflow / Reload Rules | Biz w/ Tech Epic | Build | E-492956 | E-492956 |  | 2025-07-14 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-11-28 | 2025-07-14
Biz w/ Tech Epic: Increase First Mile Package Pickup Visibility | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105142 | 7778 | Customer Data Exchange - Ground Enablement | Biz w/ Tech Epic | Backlog | E-492854 | E-492854 | 5: XL |  |  |  | 1 | 0 |  | 1 | Yes
Biz w/ Tech Epic: Spots - Low Trailer Fullness | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105143 | 8027 | Spots - Low Trailer Fullness | Biz w/ Tech Epic | Done | E-493002 | E-493002 |  | 2025-07-25 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-25 | 2025-09-10
Biz w/ Tech Epic: Early Package Visibility (EPV) 8278- MVP | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105144 | 7778 | Customer Data Exchange - Ground Enablement | Biz w/ Tech Epic | Build | E-492790 | E-492790 | 4: L | 2025-08-13 |  |  | 10 | 0 | 8 | 2 | No | 2025-05-15 | 2025-12-31 | 2025-08-13
Biz w/ Tech Epic: Inefficient P&D Spots - Bobtail to Bobtail | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105145 | 8833 | Inefficient P&D Spots - Bobtail to Bobtail | Biz w/ Tech Epic | Done | E-492855 | E-492855 |  | 2025-09-10 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: Inefficient P&D Spots - Empty to Empty | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105146 | 8883 | Inefficient P&D Spots - Empty to Empty | Biz w/ Tech Epic | Done | E-492856 | E-492856 |  | 2025-07-25 | 2025-07-28 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-25 | 2025-07-28
Biz w/ Tech Epic: Early warning adoption: Yield Anomaly Classificati | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105147 | 8236 | Dynamic Pricing - Early Warning System for Shippi | Biz w/ Tech Epic | Done | E-492791 | E-492791 |  | 2025-06-27 | 2025-06-27 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: *L1 Mode of Transport - Federal Excise Tax | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105148 | 7315 | Mode Shift Analysis Tool | Biz w/ Tech Epic | Assessment & Analysis | E-492686 | E-492686 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-31 | 2026-03-31
Biz w/ Tech Epic: FXF Grocery - Consignee Inbound Visibility Dashboa | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105149 |  |  | Biz w/ Tech Epic | Backlog | E-492826 | E-492826 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-08-30
Biz w/ Tech Epic: GPN Scan Data Capture for Fusion Consumption | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105150 | 9527 | International Commercial Linehaul - VSOP | Biz w/ Tech Epic | Backlog | E-492844 | E-492844 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: Data Privacy Platform Build - Project Firefly | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105151 | 7387 | Project Firefly - Enhancing Data Privacy and Reduc | Biz w/ Tech Epic | Build | E-492767 | E-492767 | 3: M | 2025-07-18 |  | 80% | 25 | 20 | 2 | 3 | No | 2024-06-03 | 2028-07-04 | 2025-07-18
Biz w/ Tech Epic: Support Pickup PFS VB2 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105152 | 9200 | Rationalize On-Call Pickup Product and Scheduling | Biz w/ Tech Epic | Assessment & Analysis | E-493004 | E-493004 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enterprise Costing | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105153 | 9457 | Enterprise Costing Model Development | Biz w/ Tech Epic | Assessment & Analysis | E-492906 | E-492906 |  |  |  | 5.882% | 17 | 1 | 2 | 14 | No | 2025-01-06 | 2025-12-04
Biz w/ Tech Epic: Equipment Balance Data Analytics, Visibility, and | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105154 | 7494 | Equipment Balance Data Analytics, Visibility, and | Biz w/ Tech Epic | Build | E-492801 | E-492801 |  | 2025-07-25 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-25
Biz w/ Tech Epic: DW Alternate Solution: Finance - Expand US parcel | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105155 | 7316 | Finance - Expand US parcel late fees to Canada | Biz w/ Tech Epic | Assessment & Analysis | E-492778 | E-492778 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF SR&A Reduction - Invoicing Perfection | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105156 | 9189 | Invoicing Profile Accuracy | Biz w/ Tech Epic | Build | E-492827 | E-492827 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2025-01-09 | 2025-02-26 | 2025-07-02
Biz w/ Tech Epic: Hire Ahead (Algorithmic Sourcing) | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105157 | 9451 | Hire Ahead (Algorithmic Sourcing Tool) | Biz w/ Tech Epic | Build | E-492847 | E-492847 | 3: M | 2025-06-30 |  | 71.43% | 7 | 5 |  | 2 | No |  |  | 2025-06-30
Biz w/ Tech Epic: L1 Revenue Planning - Domestic | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105158 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492894 | E-492894 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 DWC for non COY shipments when sorted using tot | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105159 | 89532 | DWC for non COY shipments when sorted using totes | Biz w/ Tech Epic | Assessment & Analysis | E-492870 | E-492870 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DW: Project SENTRY - P&D Safety Analytics - Interv | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105160 | 6704 | P&D Safety Analytics | Biz w/ Tech Epic | Done | E-492784 | E-492784 | 2: S | 2025-07-01 | 2025-07-01 | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-01 | 2025-07-01
Biz w/ Tech Epic: FXF Financial Reporting -MRA SAS Migration | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105161 | 7127 | BI Consol - SAS - FedEx Freight | Biz w/ Tech Epic | Backlog | E-492825 | E-492825 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: *L4 SPECS Drive initiative - 27914 Dataworks supp | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105162 | 89838 | Project Mercury – Next Generation BD and SPECS | Biz w/ Tech Epic | Assessment & Analysis | E-492726 | E-492726 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No | 2024-10-01 | 2025-11-28
Biz w/ Tech Epic: L1 Project Mercury - Next Generation BD and SPECS | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105163 | 89838 | Project Mercury – Next Generation BD and SPECS | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Destination Scan Compliance | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105164 | 9073 | Scan Integrity - Improving Scan Compliance Through | Biz w/ Tech Epic | Assessment & Analysis | E-492770 | E-492770 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: GOC Ad hoc cost calculator with volume revenue ( | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105165 | 7434 | GOC Ad hoc cost calculator with volume revenue | Biz w/ Tech Epic | Build | E-492839 | E-492839 | 3: M | 2025-07-16 |  | 100% | 1 | 1 |  | 0 | No | 2024-12-02 | 2025-05-30 | 2025-07-16
Biz w/ Tech Epic: Network Report Card KPI Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105166 | 88067 | Network Report Card KPI Dashboard | Biz w/ Tech Epic | Assessment & Analysis | E-492886 | E-492886 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L1 - Messaging Service for Data Warehouse | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105167 | 8247 | Messaging Service for Data Warehouse | Biz w/ Tech Epic | Assessment & Analysis | E-492679 | E-492679 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L2 APAC Data Hub Migration | On Hold | Biz w/ Tech Epic | Data & AI Portfolio | 0105168 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492902 | E-492902 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: *L2 [ENABLER] Purchased Motor Carrier Dashboard/KP | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105169 | 7030 | [ENABLER] Purchased Motor Carrier Dashboard/KPIs | Biz w/ Tech Epic | Assessment & Analysis | E-492692 | E-492692 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 Integration of SIV prior to FRO international | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105170 | 87142 | Integration of SIV prior to FRO international | Biz w/ Tech Epic | Assessment & Analysis | E-492881 | E-492881 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L1 Alternate Route Visibility and Compliance | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105172 | 89832 | Trip Mileage Compliance | Biz w/ Tech Epic | Assessment & Analysis | E-492680 | E-492680 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L2 Chairman's Challenge 2.0: Dataworks Air Freigh | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105173 | 7453 | Chairman's Challenge 2.0: Dataworks Air Freight RF | Biz w/ Tech Epic | Assessment & Analysis | E-492693 | E-492693 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L2 Volupia - move solution to OIP & station deplo | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0105174 | 90346 | Volupia-move solution to OIP & station deployment | Biz w/ Tech Epic | Build | E-492697 | E-492697 | 3: M | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Biz w/ Tech Epic: *L1 AVME CO2 Emission reporting at AWB Level | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105175 | 90196 | AVME CO2 Emission reporting at AWB level | Biz w/ Tech Epic | Assessment & Analysis | E-492681 | E-492681 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 DE Export & Exit Clearance System | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105176 | 92121 | DE Exit Clearance System | Biz w/ Tech Epic | Assessment & Analysis | E-492868 | E-492868 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-01-20 | 2026-11-10
Biz w/ Tech Epic: L1 NonCon Auto Secondary Sort | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105177 | 88407 | NonCon Auto Secondary Sort [MEMH only] | Biz w/ Tech Epic | Assessment & Analysis | E-492888 | E-492888 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-07-15
Biz w/ Tech Epic: *L2 Network 2.0/Multi Network Service Reporting To | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105178 | 7780 | Network 2.0/Multi Network Service Reporting Tools | Biz w/ Tech Epic | Assessment & Analysis | E-492695 | E-492695 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L1 US Broker Automation, FXL Brokerage | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105179 | 90021 | US Broker Automation, FXL Brokerage | Biz w/ Tech Epic | Assessment & Analysis | E-492690 | E-492690 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: *L1 Optimize payment methods (e.g., implement e-in | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105180 | 8343 | Optimize payment methods (e.g., implement e-invoic | Biz w/ Tech Epic | Assessment & Analysis | E-492687 | E-492687 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 China UEL/MFA Routing | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105181 | 89968 | China UEL/MFA Routing | Biz w/ Tech Epic | Assessment & Analysis | E-492866 | E-492866 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: *L1 Enhanced Flight Profitability Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105182 | 89455 | Enhanced Flight Profitability Dashboard | Biz w/ Tech Epic | Assessment & Analysis | E-492682 | E-492682 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 FXL Transformation | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0105183 | 89066 | FXL Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-492878 | E-492878 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 Revenue Planning - International | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105184 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492895 | E-492895 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: L2 Shopify Extension (Shoprunner / Fedex Shopify A | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105188 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492918 | E-492918 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Sustainability Insights Platform (SIP) | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105189 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493005 | E-493005 | 5: XL |  |  |  | 6 | 0 | 1 | 5 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: LIP One FedEx People Analytics | Assumed Completed | Local Enhancement Epic | Data & AI Portfolio | 0105190 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492925 | E-492925 | 5: XL |  |  | 7.143% | 14 | 1 | 3 | 10 | No
Local Enhancement Epic: WS9 - fdx Migration Large Solutioning Customer - P | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105191 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493036 | E-493036 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-12-31 | 2024-12-31
Local Enhancement Epic: Multicarrier Transportation in FDX | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105192 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492938 | E-492938 |  |  |  | 12.5% | 24 | 3 | 11 | 10 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: WS9 - fdx Migration Large Solutioning Customer - P | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105193 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493040 | E-493040 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-12-31 | 2024-12-31
Local Enhancement Epic: Idexx | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105194 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: L1 Dynamic Pick up for a Healthcare Diagnostic Sol | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105195 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492872 | E-492872 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Volvo Truck | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105196 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493022 | E-493022 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Salesforce Commerce Cloud (B2C) and Salesforce Ord | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105197 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492983 | E-492983 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: (GEN AI) Virtual Assistant Improvements | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105198 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493020 | E-493020 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: Commerce Tags | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105199 |  |  | Local Enhancement Epic | Build | E-493006 | E-493006 | 4: L | 2025-08-13 |  |  | 10 | 0 | 1 | 9 | No | 2024-10-01 | 2025-11-28 | 2025-08-13
Local Enhancement Epic: UCC Submission | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105200 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493015 | E-493015 |  |  |  | 100% | 1 | 1 |  | 0 | Yes | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Regulatory Framework - Canada Boarder Services Age | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105201 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492971 | E-492971 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-10-01 | 2025-11-28
Local Enhancement Epic: FedEx SameDay Local | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105202 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492984 | E-492984 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Walmart - PVI | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105203 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493024 | E-493024 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-07-22 | 2025-11-28
Local Enhancement Epic: 1-800-Flowers - ITDE/PDE | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105204 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: WS9 - fdx Migration Large Solutioning Customer - P | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105205 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493037 | E-493037 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-12-31 | 2024-12-31
Local Enhancement Epic: Sirius - fdx Platform -Developer Exp. (DevX) | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105206 |  |  | Local Enhancement Epic | Build | E-492814 | E-492814 | 3: M | 2025-07-23 |  |  | 12 | 0 | 4 | 8 | No | 2024-07-22 | 2025-11-28 | 2025-07-23
Local Enhancement Epic: Micron | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105207 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-01
Local Enhancement Epic: Medtronic | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105208 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Network Weather Contingency Tool | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105209 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492947 | E-492947 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-25
Local Enhancement Epic: Tags Bundle - Onsite Integration | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105210 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492991 | E-492991 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-08-02 | 2025-01-31
Local Enhancement Epic: Fingerprint 2.0 | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105211 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492820 | E-492820 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-07-22 | 2025-11-28
Local Enhancement Epic: AbbVie | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105212 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492730 | E-492730 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: EU-CDP Customer rates and incentives – Pricing imp | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105213 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492809 | E-492809 |  |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: EU CDP POD – Customer Interactions History | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105214 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492806 | E-492806 |  |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: EU CDP : Customer Network Impact | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105215 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492805 | E-492805 |  |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: HR Labor Insights | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105216 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492849 | E-492849 |  |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: Privacy and Compliance: Data | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105217 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492963 | E-492963 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-09-16
Local Enhancement Epic: Flight On Time Performance Dashboard | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105218 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492823 | E-492823 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: FDX Console | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105219 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492813 | E-492813 |  |  |  |  | 40 | 0 | 11 | 29 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Richemont Alerting Solution | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105220 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Advanced Visibility | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105221 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492732 | E-492732 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: GameStop POC | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105222 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: ML based Claims Decision Engine | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105223 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492936 | E-492936 |  |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: RaaS (RouteSmart) for AMEA POC | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105224 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: fdx Analytics & Insights | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105225 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492816 | E-492816 |  |  |  |  | 15 | 0 | 5 | 10 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Network 2.0 - Pickup window Performance | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105226 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492942 | E-492942 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Package Loss | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105227 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492957 | E-492957 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DW: Dynamic Bypass Opportunities | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105228 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Branded Track & Notify | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105229 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492746 | E-492746 |  |  |  |  | 2 | 0 |  | 2 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: *L2 Oneview | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105230 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492696 | E-492696 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Healthcare Pickup | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105231 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492846 | E-492846 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-08-13
Local Enhancement Epic: DW: Freight Palletization | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105232 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Tier 1 and 2 Management Board KPIs (EU) | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105233 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493010 | E-493010 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Arthrex | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105234 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492742 | E-492742 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-05-28
Local Enhancement Epic: Phillips | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105235 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492960 | E-492960 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: Increase conversions with ShopRunner Checkout | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105236 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492853 | E-492853 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: J&J Global Air Freight KNIL Integration | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105237 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492860 | E-492860 | 3: M |  |  |  | 0 | 0 |  | 0 | Yes | 2025-10-01 | 2025-11-28
Local Enhancement Epic: USVP - US Variable Pay | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105238 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: DW- Global Address Accuracy POC with Tamr | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105239 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-08-09
Local Enhancement Epic: Cabinet Executive KPI Dashboard | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105240 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492750 | E-492750 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Siemens - POC 3 HAL EDTW | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105241 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492995 | E-492995 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-09-24
Local Enhancement Epic: Build Membership Strategy to Drive Demand | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105242 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492748 | E-492748 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: Atlas Data Optimization | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105243 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492743 | E-492743 | 2: S |  |  |  | 1 | 0 |  | 1 | Yes | 2024-10-01 | 2025-01-01
Local Enhancement Epic: FDX India/Floship | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105244 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492815 | E-492815 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: OIP Platform Optimization | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105245 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492954 | E-492954 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-08-01 | 2025-11-28
Local Enhancement Epic: Chewy - Visibility Experiment | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105246 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: eAtlas Decommissioning | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105247 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492792 | E-492792 | 3: M |  |  |  | 41 | 0 | 40 | 1 | No | 2025-05-19 | 2026-03-13
Local Enhancement Epic: Essilor Luxottica | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105248 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492802 | E-492802 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: StockX | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105249 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493003 | E-493003 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Tri-Color Costing / Pricing | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105251 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493013 | E-493013 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Migrating Sales Operations from SF Dataworks to En | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105252 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492935 | E-492935 | 5: XL |  |  |  | 1 | 0 |  | 1 | No | 2025-01-07 | 2025-05-30
Local Enhancement Epic: FedEx Rather Educated Describer (FRED) - A GPT Int | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105253 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492818 | E-492818 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Siemens - POC 1 Probability of Recovery | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105254 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492993 | E-492993 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Siemens - POC 2 Priority within Priority | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105255 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492994 | E-492994 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 1-800-Flowers (Pmall) - PVI | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105256 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-05
Local Enhancement Epic: Siemens - POC 5 HAL High Performing Locations | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105257 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492996 | E-492996 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-09-24
Local Enhancement Epic: Webstaurants | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105258 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493026 | E-493026 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: FDX Labs | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105259 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492817 | E-492817 |  |  |  |  | 3 | 0 | 1 | 2 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: FDW FSM Magic HS Code Generative AI Assistant | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105260 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492812 | E-492812 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Wayfair - PVI | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105261 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Google - Clearance | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105262 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492843 | E-492843 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-02-18
Local Enhancement Epic: Lyft | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105263 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Local Enhancement Epic: Data Ingestion for Dataworks Finance | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105264 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492766 | E-492766 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2024-08-01 | 2024-08-01
Local Enhancement Epic: LIP Workday Integration (PRISM Retirement) | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105265 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492926 | E-492926 |  |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: Signify | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105266 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492997 | E-492997 |  |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: Thuma (Fraud POCs) | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105267 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493009 | E-493009 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-08-06 | 2025-11-28
Biz w/ Tech Epic: Dataworks Salesforce Operations (RTB) | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105268 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492768 | E-492768 | 5: XL |  |  | 35.48% | 31 | 11 | 12 | 8 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Tesla - HS Code Classification Tool | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105269 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Tesla - Single Point of Contact (SPOC) | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105270 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Kodak | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105271 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492861 | E-492861 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: (GEN AI) Consumer Insights | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105272 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: (GEN AI) FXO Bot | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105273 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: J&J Global Air Freight 810 | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105274 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492859 | E-492859 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: WS9 - fdx Migration Large Solutioning Customer - P | On Hold | Local Enhancement Epic | Data & AI Portfolio | 0105275 |  |  | Local Enhancement Epic | Assessment & Analysis | E-493038 | E-493038 |  |  |  |  | 1 | 0 |  | 1 | Yes | 2024-12-31 | 2024-12-31
Local Enhancement Epic: Becton Dickinson EDI | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105276 |  |  | Local Enhancement Epic | Assessment & Analysis | E-492745 | E-492745 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: TWINS 2.0 -Enhanced Development | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105278 |  |  | Local Enhancement Epic | Done | E-493014 | E-493014 |  | 2025-07-01 | 2025-07-01 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-07-01
Local Enhancement Epic: Delete Duplicate System Form Analysis Toolset - (T | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105279 |  |  | Local Enhancement Epic | Backlog | E-492769 | E-492769 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Drive demand by increasing member usage across Sho | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105280 |  |  | Local Enhancement Epic | Build | E-492775 | E-492775 |  | 2025-07-30 |  | 13.33% | 15 | 2 | 4 | 9 | No |  |  | 2025-07-30
Local Enhancement Epic: PDE: Predictive Delivery Estimates (fka Delivery A | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105281 |  |  | Local Enhancement Epic | Backlog | E-492959 | E-492959 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: Anticipate and manage shipment exceptions [a.k.a S | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105282 |  |  | Local Enhancement Epic | Backlog | E-492738 | E-492738 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-28
Local Enhancement Epic: EU Route Optimization Dashboard - 387 | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105283 |  |  | Local Enhancement Epic | Build | E-492808 | E-492808 | 2: S | 2026-04-23 |  | 100% | 1 | 1 |  | 0 | No | 2024-09-16 | 2025-11-28 | 2026-04-23
Local Enhancement Epic: CIP: Consumer Insights (Data) Platform | Closed | Local Enhancement Epic | Data & AI Portfolio | 0105284 |  |  | Local Enhancement Epic | Done | E-492755 | E-492755 |  | 2025-07-31 | 2025-09-10 | 50% | 2 | 1 |  | 1 | No |  |  | 2025-07-31 | 2025-09-10
Local Enhancement Epic: FedEx Sustainability Insights (FSI) | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105285 |  |  | Local Enhancement Epic | Backlog | E-492819 | E-492819 |  |  |  |  | 2 | 0 |  | 2 | No
Local Enhancement Epic: Enterprise Planning- Financial Revenue Forecasting | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105286 |  |  | Local Enhancement Epic | Build | E-492798 | E-492798 |  | 2025-07-18 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-11-28 | 2025-07-18
Local Enhancement Epic: Pathfinder Air Network Planner | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105287 |  |  | Local Enhancement Epic | Build | E-492958 | E-492958 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-11-01 | 2025-07-02
Local Enhancement Epic: Customer Experience to CDP Migration - Phase 1 (At | Closed | Local Enhancement Epic | Data & AI Portfolio | 0105288 |  |  | Local Enhancement Epic | Done | E-492764 | E-492764 |  | 2025-07-01 | 2025-07-09 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-07-09
Local Enhancement Epic: PIVIT | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105289 |  |  | Local Enhancement Epic | Done | E-492961 | E-492961 |  | 2025-07-07 | 2025-08-12 | 66.67% | 3 | 2 |  | 1 | No |  |  | 2025-07-07 | 2025-08-12
Local Enhancement Epic: Finance Insights Platform | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105290 |  |  | Local Enhancement Epic | Build | E-492709 | E-492709 |  | 2025-07-18 |  | 11.48% | 61 | 7 | 24 | 30 | No | 2024-07-22 | 2025-11-28 | 2025-07-18
Local Enhancement Epic: Drive demand through capitalizing on anonymous sho | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105291 |  |  | Local Enhancement Epic | Build | E-492776 | E-492776 |  | 2025-09-04 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-09-04
Local Enhancement Epic: Regulatory Framework - Import Control System 2 - R | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105292 |  |  | Local Enhancement Epic | Build | E-492972 | E-492972 |  | 2025-11-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-11-28 | 2025-11-06
Local Enhancement Epic: *L3 CLH Management Tool | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105294 |  |  | Local Enhancement Epic | Done | E-492700 | E-492700 | 2: S | 2025-07-01 | 2025-07-01 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-07-01
Local Enhancement Epic: Commercial Linehaul Scan Visibility | In Progress | Local Enhancement Epic | Data & AI Portfolio | 0105295 |  |  | Local Enhancement Epic | Backlog | E-465945 | E-465945 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-09-30 | 2024-09-30
Local Enhancement Epic: Transition from Omnitracs to Nauto | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105296 |  |  | Local Enhancement Epic | Build | E-493012 | E-493012 |  | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-10-14 | 2025-07-15
Local Enhancement Epic: Medical Service Tower- Hub | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105297 |  |  | Local Enhancement Epic | Backlog | E-492931 | E-492931 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-11-29
Local Enhancement Epic: Zuora: Build Billing Integration Service to Suppor | Closed | Local Enhancement Epic | Data & AI Portfolio | 0105298 |  |  | Local Enhancement Epic | Done | E-493041 | E-493041 |  | 2025-06-30 | 2025-06-30 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-30 | 2025-06-30
Local Enhancement Epic: Apollo | Closed | Local Enhancement Epic | Data & AI Portfolio | 0105299 |  |  | Local Enhancement Epic | Done | E-492739 | E-492739 |  | 2025-07-01 | 2025-09-10 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Local Enhancement Epic: S3LICK 1.0 | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105300 |  |  | Local Enhancement Epic | Build | E-492982 | E-492982 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-01
Local Enhancement Epic: FXG Financial Forecasting | Completed | Local Enhancement Epic | Data & AI Portfolio | 0105301 |  |  | Local Enhancement Epic | Build | E-492828 | E-492828 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: EPM Portfolio Insight Platform | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105345 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VIRGO - Cage code Filter for US tariff analysis | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0105467 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enhancement :: Contingency Request Tool | Closed | Local Enhancement Epic | Data & AI Portfolio | 0105630 |  |  | Local Enhancement Epic | Build | E-534825 | E-534825 | 1: XS | 2025-09-08 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-08
Local Enhancement Epic: sirius - fdx platform - design system & UI library | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105658 |  |  | Local Enhancement Epic | Build | E-520964 | E-520964 | 2: S | 2025-08-05 |  |  | 3 | 0 |  | 3 | No |  |  | 2025-08-05
Lifecycle Management Epic: Sirius – fdx platform – SRE & CloudOps Support | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0105692 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-528422 | E-528422 | 3: M | 2025-06-26 |  | 52.63% | 19 | 10 |  | 9 | No |  |  | 2025-06-26
Local Enhancement Epic: (GEN AI) SG&A Dashboard | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105694 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Sirius - fdx Platform – Notifications | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105696 |  |  | Local Enhancement Epic | Build | E-521011 | E-521011 | 3: M | 2025-07-09 |  | 66.67% | 12 | 8 | 3 | 1 | No |  |  | 2025-07-09
Local Enhancement Epic: Sirius – fdx platform – Global Infrastructure | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105742 |  |  | Local Enhancement Epic | Backlog | E-528589 | E-528589 | 3: M |  |  |  | 5 | 0 |  | 5 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Sirius – fdx platform – Data Foundation layer | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105756 |  |  | Local Enhancement Epic | Build | E-521008 | E-521008 | 5: XL | 2025-07-18 |  | 47.37% | 19 | 9 | 2 | 8 | No | 2025-10-01 | 2025-11-28 | 2025-07-18
Biz w/ Tech Epic: Generic Rate Card Exposure to Shopify | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0105778 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Backlog | E-534997 | E-534997 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Bring Your Own Account Registration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105779 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Purchasing Shipping Labels | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105780 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Fetching Rates | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105781 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Compliance | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105782 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Integration Testing | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0105783 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Change Update Time on Data Warehouse Table | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0105797 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Sirius - fdx Platform – Orchestrator | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105803 |  |  | Local Enhancement Epic | Build | E-520966 | E-520966 | 3: M | 2025-07-31 |  | 66.67% | 12 | 8 | 2 | 2 | No |  |  | 2025-07-31
Local Enhancement Epic: Sirius - fdx Platform – Experience Manager (XM) | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105804 |  |  | Local Enhancement Epic | Build | E-520968 | E-520968 | 3: M | 2025-08-13 |  | 14.29% | 7 | 1 | 1 | 5 | No |  |  | 2025-08-13
Local Enhancement Epic: Sirius – fdx platform – Widget Framework | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105805 |  |  | Local Enhancement Epic | Build | E-528581 | E-528581 | 2: S | 2025-08-12 |  | 100% | 5 | 5 |  | 0 | No | 2025-01-02 | 2025-04-09 | 2025-08-12
Local Enhancement Epic: Sirius – fdx platform – Product deployments | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105816 |  |  | Local Enhancement Epic | Backlog | E-528573 | E-528573 | 2: S |  |  |  | 4 | 0 |  | 4 | No
Local Enhancement Epic: Sirius – fdx platform – Boilerplates for fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105817 |  |  | Local Enhancement Epic | Build | E-524800 | E-524800 | 3: M | 2025-08-05 |  |  | 5 | 0 | 1 | 4 | No | 2024-12-02 | 2025-06-04 | 2025-08-05
Local Enhancement Epic: Sirius – fdx platform – Dashboard | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105818 |  |  | Local Enhancement Epic | Backlog | E-521009 | E-521009 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Lifecycle Management Epic: Performance optimizations | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0105881 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Sirius -fdx platform-Tags as a Platform Capability | Approved | Local Enhancement Epic | Data & AI Portfolio | 0105937 |  |  | Local Enhancement Epic | Backlog | E-521010 | E-521010 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enhance RYDE Data in SPOTlight | Closed | Local Enhancement Epic | Data & AI Portfolio | 0105938 |  |  | Local Enhancement Epic | Done |  |  | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Customer Experimentation: J&J EDI GAF Support | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106055 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Gen AI Enabling Doorstep/CX Enhancements | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106057 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Live Reweigh/DIMS Report Refresh Time | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106320 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CPQ Datacubes Extract - IDC refactoring | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106375 |  |  | Local Enhancement Epic | Assessment & Analysis | E-507883 | E-507883 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: APAC DH Administration and Support | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106451 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: First Time Delivery Dashboard | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106467 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: One FedEx Reusable Bag Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0106567 | 89380 | Global-Small Parcel Reusable Bag-Parent-US | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-08-13
Biz w/ Tech Epic: One FedEx Reusable Bag Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0106570 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - S&CDE - Foundational Customer View | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0106755 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: All Mandatory metrics and controls | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106756 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-03-19
Local Enhancement Epic: N2.0 Service Dashboards | Approved | Local Enhancement Epic | Data & AI Portfolio | 0106758 |  |  | Local Enhancement Epic | Launch & Evaluate | E-521803 | E-521803 | 2: S | 2025-07-08 |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28 | 2025-07-08
Local Enhancement Epic: Azure VM for OR Geocoding Service/FMCSA | Approved | Local Enhancement Epic | Data & AI Portfolio | 0106759 |  |  | Local Enhancement Epic | Build | E-514269 | E-514269 | 2: S | 2025-08-15 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-07-10 | 2025-08-15
Local Enhancement Epic: Integrated D&C Dashboard | Approved | Local Enhancement Epic | Data & AI Portfolio | 0106761 |  |  | Local Enhancement Epic | Backlog | E-536933 | E-536933 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Live Reweigh/DIMS Report Refresh Time | Approved | Local Enhancement Epic | Data & AI Portfolio | 0106763 |  |  | Local Enhancement Epic | Backlog | E-533080 | E-533080 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SBDD calculated package volume per next waypoint | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0106764 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Webalytics Generative AI Integration | Approved | Local Enhancement Epic | Data & AI Portfolio | 0106765 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552509 | E-552509 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXFDW CallPass API | Approved | Local Enhancement Epic | Data & AI Portfolio | 0106786 |  |  | Local Enhancement Epic | Build | E-514266 | E-514266 | 3: M | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-11 | 2025-08-19 | 2025-07-01
Local Enhancement Epic: Upload GDP zip data | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0106799 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Fedex Rewards - Audit Implementation | Closed | Local Enhancement Epic | Data & AI Portfolio | 0106800 |  |  | Local Enhancement Epic | Launch & Evaluate | E-503690 | E-503690 | 1: XS | 2025-06-27 |  | 100% | 13 | 13 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: SPOTlight - Update CDAS API | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0106932 |  |  | Lifecycle Management Epic | Build | E-520976 | E-520976 | 1: XS | 2025-11-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-10
Lifecycle Management Epic: External Customer Reporting Project PFS/ TNT | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0106933 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-03-09 | 2026-03-09
Local Enhancement Epic: Customer Experimentation: Becton Dickinson GAF | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0106934 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: STOPS application Admin | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0106951 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Odin Migration App Analysis & Pilot App Migration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0106967 | 106928 | TS-VL3-Infrastructure Consolidation and Retirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Odin Pilot App Migration and Analysis | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107131 | 7062 | TS-VL3-HybridCloud-GCPMigrateODINDecomm | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: O-WDL Tool Update (Ground and Optimized Origins) | Approved | Local Enhancement Epic | Data & AI Portfolio | 0107304 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528421 | E-528421 | 1: XS | 2025-06-30 |  |  | 1 | 0 |  | 1 | No | 2025-10-01 | 2025-11-28 | 2025-06-30
Lifecycle Management Epic: EDD - Ground\Express - Model/Feature Enhancements | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0107359 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: GDPP Model Refresh | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0107360 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: RBAC module migration | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0107362 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: PNA Disable - Storage Accounts | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0107363 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Pydantic DQ Module Integration | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0107364 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Service by Flight Dashboard Development | Approved | Local Enhancement Epic | Data & AI Portfolio | 0107365 |  |  | Local Enhancement Epic | Launch & Evaluate | E-521802 | E-521802 | 2: S | 2025-07-08 |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28 | 2025-07-08
Local Enhancement Epic: SPOTlight - Access Expansion | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0107425 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EU RO Dashboard | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0107453 | 7627 | 06 - EU PUD Route Optimization - Integrated countr | Biz w/ Tech Epic | Backlog | E-521006 | E-521006 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: Informatica - Reinstall and reconfigure in new VMs | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0107553 |  |  | Lifecycle Management Epic | Build | E-540259 | E-540259 | 2: S | 2026-04-07 |  | 100% | 20 | 20 |  | 0 | No | 2025-06-02 | 2026-04-13 | 2026-04-07
Biz w/ Tech Epic: Spotlight - ENM | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0107707 | 110818 | Spotlight ENM | Biz w/ Tech Epic | Backlog | E-530917 | E-530917 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-28 | 2025-07-11
Biz w/ Tech Epic: Customer Support Operations | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107710 | 93592 | Unified Platform - Customer Onboarding & Growth | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: eGPS API access to Dataworks Webhooks application | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0107849 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Compass - Compliance Report Enhancenments | Approved | Local Enhancement Epic | Data & AI Portfolio | 0107851 |  |  | Local Enhancement Epic | Backlog | E-526917 | E-526917 | 1: XS |  |  |  | 2 | 0 |  | 2 | No | 2024-07-22 | 2026-10-26
Local Enhancement Epic: Publish EDD Confidence Scores | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0107876 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Total Turnover Analytics Suite | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0107892 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Internal Audit Innovation and Efficiency | Approved | Local Enhancement Epic | Data & AI Portfolio | 0108002 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559002 | E-559002 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MSAT Azure Web Services | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108003 |  |  | Local Enhancement Epic | Assessment & Analysis | E-514264 | E-514264 | 2: S |  |  |  | 1 | 0 | 1 | 0 | No
Local Enhancement Epic: iOCR data consumption from SEP to SDV | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108004 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Package Security Insights Dashboard | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108005 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Workload Identity Implementation - FunctionApp | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108006 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Logic Creation/Review Relay42 Rate Quote Retarget | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0108075 | 106340 | COM - S&CDE - CDE ART - Relay42 Migration to Azure | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Combined Baseline EU E2E Shipment Flow Plan | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0108225 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Combined Baseline EU E2E Shipment Flow Plan | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0108226 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Branded Order Tracking EPIC | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0108304 | 98708 | Sirius- Segment/CX - Branded Order Tracking | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Coordinate the processing of Shipment Demand Order | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107949 | 109393 | TS-VL1-CM-Ship Visibility-Build | Biz w/ Tech Epic | Assessment & Analysis | E-516026 | E-516026 | 3: M |  |  | 20% | 5 | 1 | 4 | 0 | No | 2025-06-09 | 2025-09-29
Biz w/ Tech Epic: Coordinate the processing of Sort Event to be made | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107951 | 109393 | TS-VL1-CM-Ship Visibility-Build | Biz w/ Tech Epic | Assessment & Analysis | E-518732 | E-518732 | 3: M |  |  |  | 4 | 0 | 4 | 0 | No | 2025-06-30 | 2025-09-29
Biz w/ Tech Epic: Coordinate the processing of Pickup and Delv Event | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107950 | 109393 | TS-VL1-CM-Ship Visibility-Build | Biz w/ Tech Epic | Assessment & Analysis | E-518729 | E-518729 | 3: M |  |  |  | 6 | 0 | 6 | 0 | No | 2025-06-30 | 2025-09-29
Biz w/ Tech Epic: Implement the LH events to be made available for F | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107953 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Processing of Consolidations and propagate Air Eve | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0107952 | 109393 | TS-VL1-CM-Ship Visibility-Build | Biz w/ Tech Epic | Assessment & Analysis | E-518735 | E-518735 | 3: M |  |  |  | 7 | 0 | 7 | 0 | No | 2025-06-30 | 2025-09-29
Biz w/ Tech Epic: EPD Enhancements | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0108564 | 109407 | Apollo EPD Improvements | Biz w/ Tech Epic | Build | E-529849 | E-529849 | 3: M | 2025-08-16 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-16
Biz w/ Tech Epic: APOLLO USE Cases | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0108565 | 109407 | Apollo EPD Improvements | Biz w/ Tech Epic | Build | E-529848 | E-529848 | 3: M | 2025-08-13 |  |  | 2 | 0 | 2 | 0 | No |  |  | 2025-08-13
Local Enhancement Epic: GEMINI - CE Event | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108574 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: North American Shipment Flow Plan | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0108662 | 92265 | North American Shipment Flow Plan for Common Sort | Biz w/ Tech Epic | Assessment & Analysis | E-562769 | E-562769 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-08-19
Biz w/ Tech Epic: CVM Value Bundle 1 | In Progress | Biz w/ Tech Epic | Data & AI Portfolio | 0108724 | 9243 | Banded Commit for Competitive Profitable Network | Biz w/ Tech Epic | Build | E-530573 | E-530573 | 3: M | 2025-08-06 |  | 100% | 4 | 4 |  | 0 | No | 2024-08-01 | 2026-04-01 | 2025-08-06
Biz w/ Tech Epic: CVM Value Bundle 2 - Lean Product Delivery | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0108730 | 9243 | Banded Commit for Competitive Profitable Network | Biz w/ Tech Epic | Build | E-530774 | E-530774 | 4: L | 2025-09-24 |  | 100% | 1 | 1 |  | 0 | No | 2025-09-15 | 2026-03-06 | 2025-09-24
Local Enhancement Epic: OIP-CFR Data Ingestion and Curation | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108798 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: Data Transfer for Optimum Flight Dispatch | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0108867 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-29 | 2026-02-13
Biz w/ Tech Epic: CIP: Consumer Insights (Data) Platform | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0108963 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Ad Tech Data Feed | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0109083 | 111235 | Data Monetization – AdTech | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-15 | 2028-07-04
Local Enhancement Epic: Canadian Issue with Station OB Load Planning Dash. | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0109122 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: N2.0 District Rollout Support | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0109123 | 107401 | N2.0 - District Rollout Support (Zenith) | Biz w/ Tech Epic | Backlog | E-530179 | E-530179 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: fdx AI | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109140 |  |  | Local Enhancement Epic | Build | E-528588 | E-528588 | 2: S | 2025-08-15 |  |  | 12 | 0 | 4 | 8 | No | 2025-07-07 | 2025-11-28 | 2025-08-15
Local Enhancement Epic: CLASS data ingestion in Atlas | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0109166 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L2 Global Digital Plat - Simplify & Amplify Login | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0109207 | 92238 | Global Digital Plat - Simplify & Amplify Login | Biz w/ Tech Epic | Assessment & Analysis | E-492908 | E-492908 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 EEI Filing Enhancements | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0109288 | 84577 | EEI Filing Enhancements | Biz w/ Tech Epic | Assessment & Analysis | E-492874 | E-492874 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: L1 Project Mercury - Next Generation BD and SPECS | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0109289 | 89838 | Project Mercury – Next Generation BD and SPECS | Biz w/ Tech Epic | Assessment & Analysis | E-492893 | E-492893 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DAI - EIW - CRP DB Changes to support IP/IE HW | Closed | Local Enhancement Epic | Data & AI Portfolio | 0109430 |  |  | Local Enhancement Epic | Build | E-530296 | E-530296 | 1: XS | 2025-10-02 |  | 100% | 5 | 5 |  | 0 | No |  |  | 2025-10-02
Biz w/ Tech Epic: Dynamic Profile eMBP DRIVE Transformation | Closed | Biz w/ Tech Epic | Data & AI Portfolio | 0109451 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Done | E-511635 | E-511635 | 1: XS | 2025-07-01 | 2025-09-10 | 100% | 8 | 8 |  | 0 | No |  |  | 2025-07-01 | 2025-09-10
Biz w/ Tech Epic: Returns Technology (FRT) 2.0 FY25 Launch | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0109452 | 9360 | Returns Technology (FRT) 2.0 Rewrite | Biz w/ Tech Epic | Backlog | E-492974 | E-492974 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VRP Route Optimization Tool PUD 1 | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0109453 | 7787 | Product Commit Modeling | Biz w/ Tech Epic | Build | E-493023 | E-493023 |  | 2025-07-18 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-18
Biz w/ Tech Epic: WS11 - I-EU B2C: Become a market relevant B2C play | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0109454 | 8174 | WS11 - I-EU B2C: Global Direct-to-Retail | Biz w/ Tech Epic | Backlog | E-493030 | E-493030 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-05-30 | 2025-05-30
Local Enhancement Epic: #15601 - Check if new FedEx customer already has a | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109758 |  |  | Local Enhancement Epic | Backlog | E-405627 | E-405627 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: #20708 - Phoenix StC | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109759 |  |  | Local Enhancement Epic | Backlog | E-405640 | E-405640 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: #28545 S2C and Sales Data Integration | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109760 |  |  | Local Enhancement Epic | Backlog | E-376505 | E-376505 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: #388 DRIVE - PUD3/PUD4 Analysis & Support | Closed | Local Enhancement Epic | Data & AI Portfolio | 0109761 |  |  | Local Enhancement Epic | Backlog | E-332815 | E-332815 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: #68946 - DRIVE International Infrastructure | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109762 |  |  | Local Enhancement Epic | Backlog | E-405645 | E-405645 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: #DRIVE 66535 - Customer Migration - Customer Hiera | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109763 |  |  | Local Enhancement Epic | Backlog | E-407663 | E-407663 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-18
Local Enhancement Epic: (GEN AI) GenAI Sidekick | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109764 |  |  | Local Enhancement Epic | Build | E-492678 | E-492678 |  | 2025-08-05 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22 | 2025-08-05
Local Enhancement Epic: [TSV 1.5] Create Email Notification Request (ENR) | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109765 |  |  | Local Enhancement Epic | Build | E-492898 | E-492898 | 4: L | 2026-01-03 |  | 50% | 2 | 1 | 1 | 0 | No | 2025-01-20 | 2025-10-24 | 2026-01-03
Local Enhancement Epic: [VEDA] IDC Architecture Runway | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109766 |  |  | Local Enhancement Epic | Backlog | E-359449 | E-359449 |  |  |  |  | 2 | 0 |  | 2 | No | 2024-07-22 | 2025-07-18
Local Enhancement Epic: Add Origin and Destination Country Zone Fields to | Closed | Local Enhancement Epic | Data & AI Portfolio | 0109767 |  |  | Local Enhancement Epic | Build | E-511886 | E-511886 |  | 2025-07-01 |  | 100% | 8 | 8 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: Backoffice - ITAPP Payroll | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109768 |  |  | Local Enhancement Epic | Backlog | E-407684 | E-407684 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Business Data Visualization | Closed | Local Enhancement Epic | Data & AI Portfolio | 0109769 |  |  | Local Enhancement Epic | Backlog | E-379593 | E-379593 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Commercial Linehaul Scan Visibility - E-492758 | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109770 |  |  | Local Enhancement Epic | Build | E-492758 | E-492758 | 3: M | 2025-07-17 |  | 100% | 1 | 1 |  | 0 | No | 2024-09-30 | 2024-09-30 | 2025-07-17
Local Enhancement Epic: DAI - FDNA - Lifecycle Management (LCM) / Purple P | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109771 |  |  | Local Enhancement Epic | Build | E-450783 | E-450783 | 2: S | 2025-07-02 |  | 20% | 5 | 1 | 4 | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: DAI - FDNA - Production (PROD) Support - KTLO/Inci | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109772 |  |  | Local Enhancement Epic | Build | E-501287 | E-501287 | 2: S | 2025-07-01 |  |  | 4 | 0 | 4 | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: DAI - IA - FDNA - Freight Forecasting from OIP to | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109773 |  |  | Local Enhancement Epic | Backlog | E-514268 | E-514268 | 4: L |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Architecture Support - PHOENIX | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109774 |  |  | Local Enhancement Epic | Backlog | E-376504 | E-376504 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Data Privacy - Chinese Data Privacy Impact Analysi | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109775 |  |  | Local Enhancement Epic | Backlog | E-407676 | E-407676 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Data&AI - FDNA - 643 CONDOR - Mainframe SAS | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109776 |  |  | Local Enhancement Epic | Build | E-450858 | E-450858 | 4: L | 2025-07-01 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: Data&AI - FDNA - Data Center Exit | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109777 |  |  | Local Enhancement Epic | Build | E-450855 | E-450855 | 4: L | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: DRIVE - #7063 CLEARANCE / Abacus | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109778 |  |  | Local Enhancement Epic | Backlog | E-343753 | E-343753 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Local Enhancement Epic: DRIVE - Non-Integrated Domestics Ingestion into d- | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109779 |  |  | Local Enhancement Epic | Backlog | E-332811 | E-332811 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DRIVE - Non-Integrated Domestics Ingestion into d- | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109780 |  |  | Local Enhancement Epic | Build | E-288292 | E-288292 |  | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-06
Local Enhancement Epic: DRIVE - Non-Integrated Domestics Ingestion into d- | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109781 |  |  | Local Enhancement Epic | Build | E-359363 | E-359363 | 4: L | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-06
Local Enhancement Epic: DRIVE - VEDA support | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109782 |  |  | Local Enhancement Epic | Backlog | E-317924 | E-317924 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-06-02 | 2026-12-31
Local Enhancement Epic: DRIVE #394 - PUD4 Analysis & Support | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109783 |  |  | Local Enhancement Epic | Build | E-332816 | E-332816 |  | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-06
Local Enhancement Epic: DRIVE 21010 -CRA Enable Proactive Monitoring & Int | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109784 |  |  | Local Enhancement Epic | Backlog | E-399960 | E-399960 | 5: XL |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Migrate LVT and ROLLS to Dataworks Platform | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109785 |  |  | Local Enhancement Epic | Build | E-399950 | E-399950 | 5: XL | 2026-03-04 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2026-05-29 | 2026-03-04
Local Enhancement Epic: DRIVE 58188 - Migrate Nucleus Back-End Application | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109786 |  |  | Local Enhancement Epic | Build | E-399954 | E-399954 | 5: XL | 2026-04-07 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2026-03-31 | 2026-04-07
Local Enhancement Epic: Migrate YOS repository and reports to Dataworks | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109787 |  |  | Local Enhancement Epic | Backlog | E-399956 | E-399956 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-10-01 | 2026-05-29
Local Enhancement Epic: Eddex Enhancements | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109788 |  |  | Local Enhancement Epic | Backlog | E-451346 | E-451346 |  |  |  |  | 1 | 0 |  | 1 | No | 2026-01-01 | 2026-06-30
Local Enhancement Epic: ePDSM / BO Deliverables | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109789 |  |  | Local Enhancement Epic | Backlog | E-379596 | E-379596 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU Bunker - WS#- FIP - Nucleus Eplp ingestions | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109790 |  |  | Local Enhancement Epic | Backlog | E-434068 | E-434068 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: EU Bunker-Workstream5-Online Analytics-Support | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109791 |  |  | Local Enhancement Epic | Backlog | E-434067 | E-434067 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU Marketing Datamart Migration to Atlas | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109792 |  |  | Local Enhancement Epic | Backlog | E-434065 | E-434065 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXE-EU-VEDA-Data Architecture | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109793 |  |  | Local Enhancement Epic | Backlog | E-397394 | E-397394 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXO Bot | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109794 |  |  | Local Enhancement Epic | Build | E-492829 | E-492829 | 2: S | 2026-03-17 |  | 50% | 2 | 1 |  | 1 | No | 2025-11-05 | 2026-03-24 | 2026-03-17
Lifecycle Management Epic: FY26 DAI EDA Production Support | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0109795 |  |  | Lifecycle Management Epic | Build | E-516746 | E-516746 | 5: XL | 2025-07-01 |  |  | 3 | 0 | 3 | 0 | No | 2025-06-02 | 2026-12-31 | 2025-07-01
Local Enhancement Epic: IDC Performance Improvement and Support | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109796 |  |  | Local Enhancement Epic | Build | E-293658 | E-293658 |  | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-07-22 | 2025-11-06
Local Enhancement Epic: Informatica ETL Pipeline | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109797 |  |  | Local Enhancement Epic | Build | E-317668 | E-317668 |  | 2025-11-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-11-06
Local Enhancement Epic: ISK-RDI-Automated Data Ingestion for StC-Collectio | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109798 |  |  | Local Enhancement Epic | Build | E-318426 | E-318426 |  | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-06
Local Enhancement Epic: Modernize FedEx Ground Speeds data into Atlas | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109799 |  |  | Local Enhancement Epic | Build | E-451895 | E-451895 |  | 2025-07-01 |  | 50% | 80 | 40 | 40 | 0 | No | 2024-01-01 | 2026-01-30 | 2025-07-01
Local Enhancement Epic: Nucleus - Europe Rollout/POV Enhancement | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109800 |  |  | Local Enhancement Epic | Backlog | E-179778 | E-179778 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Nucleus - Italy Domestic | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109801 |  |  | Local Enhancement Epic | Backlog | E-179777 | E-179777 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Nucleus - MD Dashboard | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109802 |  |  | Local Enhancement Epic | Backlog | E-179776 | E-179776 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Nucleus - Snr Manager Dashboard | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109803 |  |  | Local Enhancement Epic | Backlog | E-179780 | E-179780 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Nucleus 1.0 Migration to ATLAS | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109804 |  |  | Local Enhancement Epic | Backlog | E-444896 | E-444896 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-09-30 | 2025-01-15
Local Enhancement Epic: Nucleus 2.0 - France Domestic | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109805 |  |  | Local Enhancement Epic | Backlog | E-332813 | E-332813 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Nucleus 2.0 - Italy Domestics | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109806 |  |  | Local Enhancement Epic | Backlog | E-434139 | E-434139 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Nucleus 2.0 - One Stop View | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109807 |  |  | Local Enhancement Epic | Backlog | E-288247 | E-288247 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Nucleus 2.0 - Poland Domestic | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109808 |  |  | Local Enhancement Epic | Backlog | E-400783 | E-400783 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Nucleus 2.0 - Self Service | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109809 |  |  | Local Enhancement Epic | Backlog | E-374431 | E-374431 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Nucleus 2.0 - Source switch from ODS tables to d-A | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109810 |  |  | Local Enhancement Epic | Build | E-342007 | E-342007 |  | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-06
Local Enhancement Epic: Nucleus 2.0 Closure | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109811 |  |  | Local Enhancement Epic | Backlog | E-433546 | E-433546 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-11-29
Local Enhancement Epic: Nucleus 2.0 Improvements | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109812 |  |  | Local Enhancement Epic | Build | E-342019 | E-342019 |  | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2026-03-31 | 2025-11-06
Local Enhancement Epic: Nucleus migration to Atlas | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109813 |  |  | Local Enhancement Epic | Backlog | E-433713 | E-433713 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Project Firefly- Cookie Consent | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109814 |  |  | Local Enhancement Epic | Backlog | E-517553 | E-517553 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Project Firefly- Data Privacy Management | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109815 |  |  | Local Enhancement Epic | Build | E-517554 | E-517554 |  | 2025-07-02 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: Project Firefly- Preference Management | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0109816 |  |  | Local Enhancement Epic | Backlog | E-517556 | E-517556 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ROLLS - Road Operations Load Factor & Linehaul Ser | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109817 |  |  | Local Enhancement Epic | Backlog | E-377641 | E-377641 | 5: XL |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Ship2Collect - FCM dispute module | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109818 |  |  | Local Enhancement Epic | Backlog | E-407681 | E-407681 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Transit Time Enablement | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109819 |  |  | Local Enhancement Epic | Backlog | E-434066 | E-434066 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VEDA - Base Team Infosys | Completed | Local Enhancement Epic | Data & AI Portfolio | 0109820 |  |  | Local Enhancement Epic | Backlog | E-286392 | E-286392 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: VEDA - BAU Support and Maintenance | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109821 |  |  | Local Enhancement Epic | Build | E-288477 | E-288477 | 4: L | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-04-29 | 2025-11-06
Local Enhancement Epic: VEDA Production Support Activities | Approved | Local Enhancement Epic | Data & AI Portfolio | 0109822 |  |  | Local Enhancement Epic | Backlog | E-446325 | E-446325 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: YOS Migration to Dataworks Platform | Closed | Local Enhancement Epic | Data & AI Portfolio | 0109823 |  |  | Local Enhancement Epic | Backlog | E-463339 | E-463339 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FSI Development | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0110805 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Visibility Event Integration Evaluation | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0110806 | 97178 | FedEx SameDay Local | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Same Day Billing Data | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0110807 | 97178 | FedEx SameDay Local | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: White-Label Integration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0110808 | 97178 | FedEx SameDay Local | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FedEx-Branded Experience | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0110809 | 97178 | FedEx SameDay Local | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-30 | 2026-01-30
Biz w/ Tech Epic: Customer Access and Authentication | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0110810 | 97178 | FedEx SameDay Local | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Locate Data Initiative | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0110816 | 8515 | Tug Dispatch Management | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-15 | 2026-01-15
Local Enhancement Epic: FXE Access to ROM - DW | Approved | Local Enhancement Epic | Data & AI Portfolio | 0110896 |  |  | Local Enhancement Epic | Backlog | E-528014 | E-528014 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-10-01 | 2025-11-28
Lifecycle Management Epic: FY26_Production Support _GDPP | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0110970 |  |  | Lifecycle Management Epic | Backlog | E-523769 | E-523769 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-08-01 | 2026-07-31
Local Enhancement Epic: Data Monetization - Finance | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0111044 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Surface DS ODIN Retirement | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0111053 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: CDG Volume Forecasting Tool | Approved | Local Enhancement Epic | Data & AI Portfolio | 0111490 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552510 | E-552510 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Trade and Tariff Impact Analysis Tool VB1 | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0111513 | 107528 | Trade and Tariff Impact Analysis Tool | Biz w/ Tech Epic | Assessment & Analysis | E-563041 | E-563041 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-05-26 | 2026-03-27
Local Enhancement Epic: FIT logic in MDIM | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0111704 |  |  | Local Enhancement Epic | Build | E-530737 | E-530737 | 1: XS | 2026-01-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-05
Lifecycle Management Epic: FY26_Data&AI_IA_FDNA_LCM Patching | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0111711 |  |  | Lifecycle Management Epic | Backlog | E-533079 | E-533079 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: FY26_Data&AI_IA_FDNA_Production Support | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0111712 |  |  | Lifecycle Management Epic | Backlog | E-533081 | E-533081 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Compass Surface Expansion | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0111736 | 7429 | Compass - Surface Expansion | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: EU-KTLO - SAS Admin Support | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0111840 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-551253 | E-551253 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_DAI_SalesforceB2CIntegration_ProductionSupprt | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0111969 |  |  | Lifecycle Management Epic | Build | E-533273 | E-533273 | 4: L | 2025-08-27 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-01 | 2025-11-28 | 2025-08-27
Lifecycle Management Epic: FY26_DAI_ShopifySRIntegration_Production Support | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0111970 |  |  | Lifecycle Management Epic | Build | E-533338 | E-533338 | 4: L | 2025-08-18 |  |  | 2 | 0 | 1 | 1 | No | 2025-09-01 | 2025-11-28 | 2025-08-18
Lifecycle Management Epic: FY26_Data&AI_DAI_P1_Comm_Pricing&Rev_ProdSupport | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0112002 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: LIP Core HR | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0112025 | 131685 | Labor Insights Platform (LIP) | Biz w/ Tech Epic | Build | E-549657 | E-549657 | 5: XL | 2025-11-03 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-03 | 2028-02-08 | 2025-11-03
Biz w/ Tech Epic: Custom/Export Documents | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112127 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enhance Generic Rate Card for International | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112128 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: BYOA International | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112129 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enhance GRC w/ F1R | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112130 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Purchase Labels w/ F1R | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112131 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Return Labels on Shopify MSA | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112132 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Return Labels on BYOA | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112133 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Return Labels on Intl Shopify MSA | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112134 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Return Labels on BYOA Intl | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112135 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Data Integration with SFCC to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112209 |  |  | Local Enhancement Epic | Backlog | E-533510 | E-533510 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with WIX to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112210 |  |  | Local Enhancement Epic | Backlog | E-533147 | E-533147 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with NetSuite to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112211 |  |  | Local Enhancement Epic | Backlog | E-533501 | E-533501 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Data Integration with AliExpress to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112212 |  |  | Local Enhancement Epic | Backlog | E-533512 | E-533512 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with TikTok Shop to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112213 |  |  | Local Enhancement Epic | Backlog | E-533508 | E-533508 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with BigCommerce to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112214 |  |  | Local Enhancement Epic | Backlog | E-533502 | E-533502 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with Ebay to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112215 |  |  | Local Enhancement Epic | Backlog | E-533504 | E-533504 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with Shopify to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112216 |  |  | Local Enhancement Epic | Backlog | E-533503 | E-533503 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with WooCommerce to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112217 |  |  | Local Enhancement Epic | Backlog | E-533505 | E-533505 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with Amazon to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112218 |  |  | Local Enhancement Epic | Backlog | E-533506 | E-533506 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Data Integration with Walmart to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112219 |  |  | Local Enhancement Epic | Backlog | E-533507 | E-533507 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Sirius - fdx Platform - Data Integration Services | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112220 |  |  | Local Enhancement Epic | Build | E-534407 | E-534407 | 2: S | 2025-08-27 |  |  | 3 | 0 | 1 | 2 | No |  |  | 2025-08-27
Local Enhancement Epic: Migration of PowerBI Premium Capacities to Fabric | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0112320 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Data Integration with Salesforce OMS to fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0112363 |  |  | Local Enhancement Epic | Backlog | E-533509 | E-533509 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Carbon Offset Product Capability | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112386 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Predictive Analytics Product Capability | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112387 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Goals and Recommendations Product Capability | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112388 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Historical Emissions Reporting Product Capability | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112389 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Configure Technical Dependencies | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112390 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FSI Development | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112391 | 93964 | FedEx Sustainability Insights (FSI) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Data Improvements | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112392 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Enhanced Consumer Experience Capability | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112393 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: UI Enhancements | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112394 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Calculation & Methodology Improvements | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112395 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Multi-Carrier | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112396 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Insetting Capability | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112397 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Pickup Page Visibility Enablement in fdx | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112414 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Integration Enablement | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112415 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Create & Update a new pickup location | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112416 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Notification | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112417 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Real time scheduling with RFID | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112418 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AI Enablement: The ability to use AI for enhanced | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112419 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dedicated dashboard- Pickup Location | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112420 | 92856 | Shipping-Dynamic Pickup | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: ECR reporting enhancement | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0112441 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Financial Sys modernization and simplification | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0112451 | 7600 | Financial Insights Platform (FIP) | Biz w/ Tech Epic | Assessment & Analysis | E-549819 | E-549819 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Financial sys tech modernization & simplification | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0112453 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 90439-TS-VL3-HybridCloud-GCPMigrateSurfaceAppsEpic | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0112490 | 90439 | TS-VL3-HybridCloud-GCPMigrateSurfaceApps | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Copy a Table from EDW to VDAP and refresh data | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0112569 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Security Enhancement for VIRGO | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0112570 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Atlas Pipeline Metadata Automation | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0112577 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: Custom Upload | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112749 | 113891 | (GEN AI) GenAI Hub | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2025-03-03 | 2025-10-31
Biz w/ Tech Epic: MCP/Sharepoint Integration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112750 | 113891 | (GEN AI) GenAI Hub | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Scaling Shopify Solutions | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0112782 | 90231 | Shopify Engagement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Adhoc RNCO ROCS 2.0 reporting | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0112910 | 7393 | ROCS2.0 Reporting Data to dAtlas | Biz w/ Tech Epic | Assessment & Analysis | E-577549 | E-577549 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-09-01 | 2027-03-01
Local Enhancement Epic: EDW Column size expansion | Closed | Local Enhancement Epic | Data & AI Portfolio | 0113004 |  |  | Local Enhancement Epic | Build | E-545323 | E-545323 | 1: XS | 2025-11-11 |  | 100% | 8 | 8 |  | 0 | No |  |  | 2025-11-11
Lifecycle Management Epic: FY26 DAI Core Frameworks Atlas Production Support | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0113005 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Move Dashboard from DEV to PROD - MDVS | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0113098 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Move Dashboard from DEV to PROD - Status Code | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0113100 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Global Trade MVP1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0113175 | 131235 | Project Michelangelo | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - Sales & CDE - CRM - CY25 - ATLAS | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0113231 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Customer Account Cleanup Web Application | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0113249 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: fdx Mobile App | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0113250 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Data Hub Migration | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113274 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Data Hub Migration on-prem to cloud | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113275 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC DataHub Migration | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113276 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Data Hub Migration | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113285 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Data Hub Migration - migrate on-prem to cloud | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113286 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Data Hub Migration - Migrate On-prem to Cloud | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0113347 | 85741 | APAC Data Hub Migration | Biz w/ Tech Epic | Assessment & Analysis | E-545097 | E-545097 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2026-01-30
Biz w/ Tech Epic: APAC Data Hub Migration - Migrate to atlas cloud | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113349 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: On-prem data analytics migration to cloud | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113350 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: On-prem Data analytics migration to cloud | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113351 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC Data Hub migration to cloud | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0113352 | 85741 | APAC Data Hub Migration | Biz w/ Tech Epic | Assessment & Analysis | E-545098 | E-545098 | 4: L |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data&AI Portfolio_Azure Production Support | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0113528 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Column Add from Purescale to Oracle/Synapse | Approved | Local Enhancement Epic | Data & AI Portfolio | 0113539 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541652 | E-541652 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: COM - Sales & CDE - CRM - CY25 - Data Science Rese | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0113567 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Revenue Planning - International | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0113663 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Revenue Planning - International | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0113665 | 87392 | Revenue Planning - International | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Revenue Planning - Domestic | In Progress | Biz w/ Tech Epic | Data & AI Portfolio | 0113668 | 87396 | Revenue Planning - Domestic | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ODIN Retirment Surface Ops Linehaul and Self Servi | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0113718 | 90974 | TS-VL3-HybridCloud-GCPMigrateODINRetirements | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Fraud Control GCP ATLAS Ingestions | In Progress | Biz w/ Tech Epic | Data & AI Portfolio | 0113833 | 88006 | TS-VL3-HybridCloud-MigrateDataIngestionsFromGCPToA | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-S&CDE-CDE-SFMC Journey Log Fields into ATLAS | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0113854 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Integration from eComm Platform to fdx via Copilot | Approved | Local Enhancement Epic | Data & AI Portfolio | 0114016 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549405 | E-549405 | 2: S |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Globalization of 360 Nav Dashboard | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0114086 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: MPS Cons-Specific Tagging Phase I | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114213 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Fairway - Data and AI all Dispositions | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0114236 | 143544 | Project Fairway - Data & AI Separation Enablement | Biz w/ Tech Epic | Build | E-548281 | E-548281 | 3: M | 2025-11-11 |  |  | 21 | 0 | 20 | 1 |  | 2025-10-15 | 2026-06-01 | 2025-11-11
Biz w/ Tech Epic: Compass AI - Epic 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0114019 | 141638 | Compass - AI Navigator | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-11-20
Biz w/ Tech Epic: Compass AI - Epic 2 (Data Analysis) | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0114241 | 141638 | Compass - AI Navigator | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Compass AI - Epic 3 (Tool Refinement) | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0114243 | 141638 | Compass - AI Navigator | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: SASBOFXS - Migration Epic | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0114346 | 7113 | TS-VL3-DATAVISUAL-SASBOFXS | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-10-23 | 2026-08-19
Local Enhancement Epic: CAB dashboard - enhancement and enrichment | Approved | Local Enhancement Epic | Data & AI Portfolio | 0114394 |  |  | Local Enhancement Epic | Build | E-577749 | E-577749 | 2: S | 2026-04-15 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-01 | 2026-06-30 | 2026-04-15
Local Enhancement Epic: FY26_PI05_GenAI Documentation Assitant | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114409 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SPOTlight - PPODA + DT Comp | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114479 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ROCS 2.0 - ROCS REPORTING 2.0 - Integration with D | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0109250 | 7393 | ROCS2.0 Reporting Data to dAtlas | Biz w/ Tech Epic | Assessment & Analysis | E-409053 | E-409053 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2027-03-31
Local Enhancement Epic: GSP CEBS Data Sharing | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0114571 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Data Validations in fdx | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114772 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: SIV/IVVI LAC Deployment | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114836 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Replacement Intrastate/Intracity Tax Report | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114842 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Data Validations in fdx | Approved | Local Enhancement Epic | Data & AI Portfolio | 0114855 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553201 | E-553201 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Volupia - domestics data | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0114919 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: HTM Model Phase 2 Release 1 Capability 1.1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0115053 | 7151 | Operational Hold to Match (HTM) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: HTM Model Phase 2 Release 2 | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0115054 | 7151 | Operational Hold to Match (HTM) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: SAS Ground Migration - Resource Alloc | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0115216 | 8145 | TS-VL3-DATAVISUAL-SASFedExGround | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ALPHA Performance Updates | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0115224 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: MST : ADX to Azure Databricks | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0115397 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: APOLLO Impact to Project Fairway - FXFSeparation | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0115469 | 143544 | Project Fairway - Data & AI Separation Enablement | Biz w/ Tech Epic | Build | E-568690 | E-568690 | 2: S | 2026-02-11 |  |  | 80 | 0 | 80 | 0 |  | 2026-03-23 | 2026-07-20 | 2026-02-11
Biz w/ Tech Epic: Standard Operating Procedure - Agility | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0115715 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Standard Operating Procedures - Agility Epic | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0115716 | 109485 | Standard Operating Procedure - Automated Planning | Biz w/ Tech Epic | Build | E-560252 | E-560252 | 1: XS | 2026-01-23 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-01-23
Biz w/ Tech Epic: Epic 2 Surgical Demand Shaping | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0115782 | 127948 | Surgical Demand Shaping | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-09-08 | 2026-03-31
Biz w/ Tech Epic: New features development in PUD3 and PUD4 | Approved | Biz w/ Tech Epic | Data & AI Portfolio | 0111781 | 103193 | PUD3&4 Improvement | Biz w/ Tech Epic | Assessment & Analysis | E-572750 | E-572750 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-12-12 | 2025-12-12
Biz w/ Tech Epic: Epic 1 Surgical Demand Shaping | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0115987 | 127948 | Surgical Demand Shaping | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-09-08 | 2026-03-31
Biz w/ Tech Epic: Global Capacity Forecast Engine | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0116002 |  |  | Biz w/ Tech Epic
Biz w/ Tech Epic: US High Impact Growth | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0116167 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: US High Impact Share | Cancelled | Biz w/ Tech Epic | Data & AI Portfolio | 0116168 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Data Ingestion and Curation | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116169 | 88108 | Commercial Data Migration - Journey Enablement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DW - NAK Notification | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0116194 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Improve pre-shipment prediction accuracy to >85% ? | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116244 | 97174 | CX- Predictive Delivery Estimates PDE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Reflect service disruption info near real time | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116245 | 97174 | CX- Predictive Delivery Estimates PDE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Increase GE accuracy to >80% for a 3-day window | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116247 | 97174 | CX- Predictive Delivery Estimates PDE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Infuse intelligence & awareness in PDE predictions | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116249 | 97174 | CX- Predictive Delivery Estimates PDE | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Blackline LEES - CMD EU South update | Closed | Local Enhancement Epic | Data & AI Portfolio | 0116340 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579739 | E-579739 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Automated placing of clearance reports | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0116341 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-05-29
Lifecycle Management Epic: 2026 IATA Table for Offline | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0116346 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: ETL Product adjustment - FDF | Approved | Local Enhancement Epic | Data & AI Portfolio | 0116408 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581363 | E-581363 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-06-30
Local Enhancement Epic: AUTOPILOT | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0116509 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Webform automation with Gen AI | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116757 | 131245 | GEN AI Automation webform to case | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-07-01 | 2026-12-31
Biz w/ Tech Epic: FedEx Butler (aka Broker Butler) | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0116808 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: SI Backlog | Approved | Local Enhancement Epic | Data & AI Portfolio | 0116819 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573318 | E-573318 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enterprise Info Warehouse Ingestion of eYMS Data | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117002 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Optimization — Planning & Operational mode | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117057 | 126781 | AU LH Optimization | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Corporate Compliance Data Ingestion | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117098 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Scaling AI - Development of AI Foundations [Model] | Approved | Local Enhancement Epic | Data & AI Portfolio | 0117219 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579896 | E-579896 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: 2026 Contingency Enhancements _ Dataworks | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117223 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Linehaul Planning – Increment 1 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117254 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Linehaul Planning – Increment 2 | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117255 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Sort & Clearance Integration | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117256 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Commit & Transit Time Calculation | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117257 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Scaling AI - Development of AI Foundations [Data] | Approved | Local Enhancement Epic | Data & AI Portfolio | 0117282 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579873 | E-579873 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EIW Teradata L1 Support AI Agent | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117316 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AUTOPILOT - Automation initiative for roll out in | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117318 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PF - Data&AI: Unity Catalog Enablement on GRIP and | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117320 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ELVIS - Extend D&AI Work | Approved | Local Enhancement Epic | Data & AI Portfolio | 0117352 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579874 | E-579874 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-04-01 | 2025-10-01
Biz w/ Tech Epic: 15 Power BI pages (Demand, Capacity & backlog) | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117369 | 169303 | Integrated D&C Dashboard Phase 2 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-20 | 2026-07-31
Biz w/ Tech Epic: Development of 15 pages in the D&C Integrated Dash | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117371 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Data exploration and Business logic | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117372 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Data and Business logic | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117374 | 169303 | Integrated D&C Dashboard Phase 2 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-20 | 2026-07-31
Local Enhancement Epic: EU FOPD Route Optimization dashboard V2 | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117379 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Mode of Transportation/Data &AI Porfolio | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117388 | 180702 | Test BizOnly_IO Splash_cpropst | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_PickupandDelivery_Production Supp | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0117462 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-581518 | E-581518 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_&_TY26_Data and AI_PickupandDelivery_Security | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0117465 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-581517 | E-581517 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_Sort_Production Support | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117508 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_Sort_Production Support | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117512 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_VEDA_EMEA-BI-Report_Production_Support | Approved | Lifecycle Management Epic | Data & AI Portfolio | 0117575 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582649 | E-582649 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-20 | 2026-12-31
Lifecycle Management Epic: FY26_Data and AI_Sort_Security_Infrastructure_Upda | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117576 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Linehaul Volume Tree Enhancements | Approved | Local Enhancement Epic | Data & AI Portfolio | 0117580 |  |  | Local Enhancement Epic | Assessment & Analysis | E-584143 | E-584143 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_ClearanceCommercialAPI_Security_I | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117581 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_ClearanceCommercialAPI_Production | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117582 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_ClearanceAnalytics_Security_Infra | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117583 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_Data and AI_ClearanceAnalytics_Production Sup | Not Started | Lifecycle Management Epic | Data & AI Portfolio | 0117585 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HS Classification: Deep Thought | Approved | Local Enhancement Epic | Data & AI Portfolio | 0117589 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582418 | E-582418 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: IN ACCS Clearance system automation | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117777 | 161663 | IN ACCS Clearance system Automation | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-05-21 | 2027-11-30
Local Enhancement Epic: FXO FUSE Customer Profile Capture - EIW Data | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117779 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-06-03 | 2026-08-11
Local Enhancement Epic: DEX08 Dashboard Enhancement | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117781 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Pre-sort Overflow Recommendation | Not Started | Biz w/ Tech Epic | Data & AI Portfolio | 0117795 | 105977 | Autodock | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FIC - AI Incubation Center | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0117802 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FIC - AI Incubation | Cancelled | Local Enhancement Epic | Data & AI Portfolio | 0117806 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Scaling AI - Development of AI Foundations [Data] | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117907 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Scaling AI - Development of AI Foundations [Model] | Not Started | Local Enhancement Epic | Data & AI Portfolio | 0117908 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: One FedEx Injury System E-341211 | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103395 | 8859 | FedEx Injury Reporting System Alignment | Biz w/ Tech Epic | Assessment & Analysis | E-508829 | E-508829 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2026-08-19
Biz w/ Tech Epic: Phase I: HQ facilities onboarded | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103467 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 2.0: Managing Workers in ePIAM (E-548895) | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103504 | 92356 | 92356- ENT Badging and Physical Access Release 2.0 | Biz w/ Tech Epic | Build | E-548895 | E-548895 | 4: L | 2026-01-09 |  |  | 13 | 0 | 1 | 12 | No | 2025-10-01 | 2026-03-31 | 2026-01-09
Biz w/ Tech Epic: Phase III: Operational SIDA facilities | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103505 | 92350 | 92350-ENT Badging and Physical Access Release 3.0 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Visitor Management | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103506 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Retiree Badge | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103507 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-421649 | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103622 | 168954 | New Document Management System for Legal | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Implement PHIRE for Peoplesoft Change management | Closed | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103683 | 7646 | Phire software for PeopleTools application change | Biz w/ Tech Epic | Backlog | E-520900 | E-520900 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C 3.1 - Curate and Distribute Shipment Flow Plan | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103704 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C3.1 XX | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103706 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C3.1 Curate and Distribute Shipment Flow Plan | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103717 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C2.3 Sort Plan Helper | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103719 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Retired Application Savings | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0103987 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Retired Apps | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104045 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Retired Apps | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104046 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Workday Security Configuration | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104479 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Backlog | E-512183 | E-512183 | 4: L |  |  |  | 4 | 0 |  | 4 | No | 2025-08-13 | 2026-01-13
Biz w/ Tech Epic: Workday Tenant Configuration and Deployment | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104491 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512189 | E-512189 | 5: XL | 2026-03-16 |  |  | 4 | 0 | 3 | 1 | No | 2025-08-13 | 2025-10-22 | 2026-03-16
Biz w/ Tech Epic: EBS demand request, REQ – 1296 Legacy FXE and FXG | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104508 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 18 Downstream Adoption of FDM | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104825 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-521801 | E-521801 | 5: XL | 2025-12-31 |  |  | 38 | 0 | 7 | 31 | No | 2024-08-08 | 2034-12-15 | 2025-12-31
Biz w/ Tech Epic: Enterprise Services Recharge FDM Adoption | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104869 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Data & AI adoption | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104896 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-435408 | E-435408 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Commercial Portfolio FDM Adoption - Cancelled | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104899 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Compensation Market Levels by Location | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104902 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512178 | E-512178 | 3: M | 2026-02-13 |  | 100% | 2 | 2 |  | 0 | No | 2025-08-13 | 2025-10-21 | 2026-02-13
Biz w/ Tech Epic: Cost Center Structure in Workday | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104903 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512287 | E-512287 | 3: M | 2026-02-20 |  |  | 6 | 0 | 4 | 2 | No | 2025-08-13 | 2026-01-13 | 2026-02-20
Biz w/ Tech Epic: Enterprise Job Catalog | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104909 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512179 | E-512179 | 5: XL | 2026-02-13 |  | 100% | 5 | 5 |  | 0 | No | 2025-08-13 | 2026-01-26 | 2026-02-13
Biz w/ Tech Epic: Harmonize Compensation and Allowance Plans | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104910 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512180 | E-512180 | 5: XL | 2026-02-05 |  |  | 5 | 0 | 3 | 2 | No | 2025-08-13 | 2026-01-20 | 2026-02-05
Biz w/ Tech Epic: AZURE API Creation | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104919 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-520931 | E-520931 | 5: XL | 2026-02-05 |  | 33.33% | 3 | 1 | 2 | 0 | No | 2025-04-10 | 2026-01-21 | 2026-02-05
Biz w/ Tech Epic: Business Process Harmonization | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105185 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512185 | E-512185 | 5: XL | 2026-02-13 |  | 33.33% | 3 | 1 |  | 2 | No | 2025-03-03 | 2025-08-20 | 2026-02-13
Biz w/ Tech Epic: Supervisory Organization Structures | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105186 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512181 | E-512181 | 5: XL | 2026-02-13 |  | 50% | 4 | 2 |  | 2 | No | 2025-08-13 | 2026-02-25 | 2026-02-13
Biz w/ Tech Epic: Workforce Planning and Staffing Model | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105327 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Backlog | E-512187 | E-512187 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-08-13 | 2026-01-13
Biz w/ Tech Epic: Integrate Everbridge with Workday | Closed | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105347 | 7368 | Transition LiveSafe to Everbridge | Biz w/ Tech Epic | Done | E-520909 | E-520909 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: FedEx Supply Chain Workday Implementation | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105352 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Workday Reporting Migration | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105356 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-520936 | E-520936 | 4: L | 2026-03-16 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-13 | 2026-08-31 | 2026-03-16
Biz w/ Tech Epic: Workday FedEx Vendor Integrations | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105357 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512377 | E-512377 | 5: XL | 2026-03-16 |  |  | 3 | 0 | 1 | 2 | No | 2025-08-13 | 2026-08-31 | 2026-03-16
Local Enhancement Epic: Update employee id for MGRS WKLY MIN REPORT | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105448 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: AIC International Region - Aligned Elements ES 261 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105472 |  |  | Local Enhancement Epic | Backlog | E-520985 | E-520985 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ground PLP SP CP 42 split and move in cube | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105476 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-06-26 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-09-10
Local Enhancement Epic: Remove SPOT Default from Pickup in Ground PLP | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105477 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-06-26 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-09-10
Biz w/ Tech Epic: International UKG Timekeeping Implementation | On Hold | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104947 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-492882 | E-492882 | 5: XL |  |  |  | 1 | 0 |  | 1 | Yes
Local Enhancement Epic: HRPAY: Create New Interface for YouDecide Pet Ins | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105677 |  |  | Local Enhancement Epic | Backlog | E-483791 | E-483791 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PCRS - FGE Surcharge Cost adjustments | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105680 |  |  | Local Enhancement Epic | Launch & Evaluate | E-483614 | E-483614 | 2: S | 2025-06-27 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: EPLP-Invalid Loc Codes when converting Ground loc | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105681 |  |  | Local Enhancement Epic | Backlog | E-520925 | E-520925 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PlanviewPortfolios Integration w/ Workday ES 264 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105683 |  |  | Local Enhancement Epic | Backlog | E-512529 | E-512529 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Requirements for EU Pay Transparency ES 260 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105684 |  |  | Local Enhancement Epic | Backlog | E-501445 | E-501445 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Workday Integration With ADP/eTime ES 278 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105685 |  |  | Local Enhancement Epic | Backlog | E-504446 | E-504446 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Global Telecom Onboarding & Multicurrency Integrat | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105719 | 9316 | TS-VL4-Network-StrategicTelecomFramework | Biz w/ Tech Epic | Assessment & Analysis | E-553503 | E-553503 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ESSP- Identifying Packages PU/Del between FXE/FXG | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105844 |  |  | Local Enhancement Epic | Backlog | E-486151 | E-486151 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRPAY: Job Family is Not Loading with Job Codes | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105885 |  |  | Local Enhancement Epic | Done | E-484082 | E-484082 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Lifecycle Management Epic: Implement MicroSegmentation for Lenel | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0105897 |  |  | Lifecycle Management Epic | Done | E-488496 | E-488496 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: PCRS: FXE INTL FRT LAC Orig/Dest cost reallocation | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105909 |  |  | Local Enhancement Epic | Assessment & Analysis | E-486144 | E-486144 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: ArcherGRC (6366) annual system upgrade to producti | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0105990 |  |  | Lifecycle Management Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: FedEx - Talent Succession Report - ES 276 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105992 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Succession Planning Summary with FedEx ID ES 277 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0105994 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Biz w/ Tech Epic: Riskonnect/FedEx API Connection | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0106004 | 8165 | Riskonnect | Biz w/ Tech Epic | Backlog | E-473119 | E-473119 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2026-01-13
Local Enhancement Epic: PCRS: FXE International - FedEx Packaging Costs | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106229 |  |  | Local Enhancement Epic | Assessment & Analysis | E-497156 | E-497156 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New VMS App account needed for Vehicle Oversight | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0106364 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VMS EWM Implementation for the U.S. | Closed | Biz w/ Tech Epic | Enterprise Services Portfolio | 0106365 | 9442 | Global Temp Labor VMS | Biz w/ Tech Epic | Assessment & Analysis | E-504247 | E-504247 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Issue Loading Disciplinary Data ES 293 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106441 |  |  | Local Enhancement Epic | Backlog | E-520901 | E-520901 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Pull files from BO to FADV for Driver files | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106508 |  |  | Local Enhancement Epic | Backlog | E-504263 | E-504263 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DataHub Access Request ES 312 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106546 |  |  | Local Enhancement Epic | Backlog | E-520937 | E-520937 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Key Contributor Stock Option (KCSO) Program ES294 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106577 |  |  | Local Enhancement Epic | Backlog | E-520983 | E-520983 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ACCOPS Safety Awards Change | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0106606 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-503802 | E-503802 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New data field added to existing HR Feed ES 317 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106738 |  |  | Local Enhancement Epic | Backlog | E-520910 | E-520910 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Qualtrics 4.0 WorkDay Enhancement ES 339 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106740 |  |  | Local Enhancement Epic | Backlog | E-504449 | E-504449 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Gov and Vulnerability Mgmt of OT/IoT CY25 PI 3-4 | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0106762 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FDX 2nd Tier II Tracking Sys (2TTS) Portal Update | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106949 |  |  | Local Enhancement Epic | Backlog | E-504070 | E-504070 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Preproc WD files compare to id dups | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106950 |  |  | Local Enhancement Epic | Backlog | E-502156 | E-502156 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ireland pension automation ES 347 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106955 |  |  | Local Enhancement Epic | Backlog | E-520905 | E-520905 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Missouri Paid Sick Leave ES 321 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106962 |  |  | Local Enhancement Epic | Done | E-501440 | E-501440 | 2: S | 2025-06-27 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-09-10
Local Enhancement Epic: New company code for ACC ES 307 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0106964 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539537 | E-539537 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXE EU Employee Service Award - ES 357 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107087 |  |  | Local Enhancement Epic | Assessment & Analysis | E-508030 | E-508030 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: eContact Retirement and Mastering of Contacts | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107113 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SunLife / Manulife - Move from DH to LIP ES 361 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0107137 |  |  | Local Enhancement Epic | Backlog | E-520919 | E-520919 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Blackbird EIB from Workday | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107147 |  |  | Local Enhancement Epic | Backlog | E-520922 | E-520922 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXEEU One Time Payment plans ES 353 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107153 |  |  | Local Enhancement Epic | Backlog | E-508032 | E-508032 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Transition Insight Vendors to Accenture | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0107207 |  |  | Local Enhancement Epic | Launch & Evaluate | E-485795 | E-485795 | 2: S | 2025-06-27 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: Korea GSP Pickup Delivery Agent Costs | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0107206 |  |  | Local Enhancement Epic | Assessment & Analysis | E-506352 | E-506352 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Onit LSR/Litigation eDiscovery Support Request | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0107401 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538205 | E-538205 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Local Enhancement Epic: FEC Incentive Code | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0107407 |  |  | Local Enhancement Epic | Assessment & Analysis | E-516674 | E-516674 | 2: S |  |  |  | 1 | 0 | 1 | 0 | No | 2025-08-11 | 2025-10-10
Local Enhancement Epic: RightAngle to FCF Feed Time Change | Rejected | Local Enhancement Epic | Enterprise Services Portfolio | 0107418 |  |  | Local Enhancement Epic | Assessment & Analysis | E-501921 | E-501921 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: International Timekeeping Business Structure | On Hold | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107465 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: International Processes & Personas | On Hold | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107467 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: AZURE Ingestion of Workday FDM | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107607 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-521424 | E-521424 | 5: XL | 2025-11-07 |  | 9.091% | 11 | 1 | 4 | 6 | No | 2025-07-01 | 2026-08-31 | 2025-11-07
Biz w/ Tech Epic: Workday FedEx Internal Integrations | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107608 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512378 | E-512378 | 2: S | 2026-01-23 |  |  | 3 | 0 | 3 | 0 | No | 2025-08-13 | 2026-08-31 | 2026-01-23
Local Enhancement Epic: HRPAY: Project Jade Phase 2 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0107634 |  |  | Local Enhancement Epic | Launch & Evaluate | E-483543 | E-483543 | 2: S | 2025-06-27 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27
Biz w/ Tech Epic: Workday FDM Integrations | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107636 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512535 | E-512535 | 5: XL | 2026-02-05 |  | 25% | 4 | 1 |  | 3 | No | 2025-08-13 | 2026-01-13 | 2026-02-05
Biz w/ Tech Epic: Data & AI Portfolio Adoption | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107637 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DOT Regulatory Reporting enhancement | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0107714 |  |  | Local Enhancement Epic | Backlog | E-501922 | E-501922 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Migrate development resources to Enterprise Servic | Cancelled | Lifecycle Management Epic | Enterprise Services Portfolio | 0107715 |  |  | Lifecycle Management Epic | Backlog | E-520920 | E-520920 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Upgrade JAVA/Angular for Fumes application | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0107717 |  |  | Lifecycle Management Epic | Backlog | E-517190 | E-517190 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FCOE Bulk Invoice Enhancement Request | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0107718 |  |  | Local Enhancement Epic | Backlog | E-518396 | E-518396 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ground PLP New PU and DEL Flags | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107719 |  |  | Local Enhancement Epic | Assessment & Analysis | E-512347 | E-512347 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ground PLP Region update for Fiscal FY26 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0107720 |  |  | Local Enhancement Epic | Launch & Evaluate | E-512365 | E-512365 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Lifecycle Management Epic: Upgrade Digital Signage at FXG field sites | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0107727 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: AU-Motor Claims Laberg Replacement | Completed | Local Enhancement Epic | Enterprise Services Portfolio | 0107728 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-06-26 | 2025-06-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Local Enhancement Epic: New time off set up for Romania ES 370 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0107729 |  |  | Local Enhancement Epic | Done | E-520917 | E-520917 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: MyTime Personal Day Configuration - Canada ONLY | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107731 |  |  | Local Enhancement Epic | Assessment & Analysis | E-514800 | E-514800 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRPAY: Network 2.0 Immediate Pay States | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0107733 |  |  | Local Enhancement Epic | Backlog | E-520908 | E-520908 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL UAE - Compensation Component Structure ES 375 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0107745 |  |  | Local Enhancement Epic | Backlog | E-526046 | E-526046 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-421649 EDMS - Enterprise Document Management Sys | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0105489 | 168954 | New Document Management System for Legal | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: RightCrowd & Lenel INT Upgrade (E-464918) ES-53 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107421 |  |  | Local Enhancement Epic | Assessment & Analysis | E-464918 | E-464918 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Second Quarter 2025 ADP Interface Spec Release | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0107977 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Merit Cycle Planning ES 385 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108045 |  |  | Local Enhancement Epic | Backlog | E-508533 | E-508533 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add column to DATAHUB table view ES 316 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108046 |  |  | Local Enhancement Epic | Backlog | E-514368 | E-514368 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Create Additional Roles in Workday Learning ES 349 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108050 |  |  | Local Enhancement Epic | Backlog | E-514394 | E-514394 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Commercial Press SPD file Datahub to WD ES 365 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108052 |  |  | Local Enhancement Epic | Backlog | E-521810 | E-521810 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Global Benefit Broker Integration ES 372 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108053 |  |  | Local Enhancement Epic | Backlog | E-521809 | E-521809 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Paradox Re-architecture | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0108068 | 9434 | Implement Paradox across enterprise to streamline | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRPAY: Salary Termination Report (ZXROKTPM) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108122 |  |  | Local Enhancement Epic | Backlog | E-520943 | E-520943 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Consolidated Sort | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108123 |  |  | Local Enhancement Epic | Assessment & Analysis | E-515631 | E-515631 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Cost Pool 59 Classification | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108124 |  |  | Local Enhancement Epic | Assessment & Analysis | E-515633 | E-515633 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRPAY: Supply Chain Canada Sun Life Retirements | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108125 |  |  | Local Enhancement Epic | Done | E-520942 | E-520942 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: International Vehicle Fuel - Tailored Report | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108126 |  |  | Local Enhancement Epic | Backlog | E-525811 | E-525811 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update FSC SunLife Benefits Data Feed ES 384 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108146 |  |  | Local Enhancement Epic | Backlog | E-526045 | E-526045 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Hourly Incentive Comp Bonus Plan ES 358 FCC | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108572 |  |  | Local Enhancement Epic | Backlog | E-528590 | E-528590 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL QAT - Comp Component Structure Changes ES 386 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108575 |  |  | Local Enhancement Epic | Backlog | E-528585 | E-528585 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Officer Adjustment Pool (OAP) Redesign ES 388 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0108578 |  |  | Local Enhancement Epic | Backlog | E-528587 | E-528587 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: New Timeoff Plan & LOA Plan for FXL INDWH ES 393 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108583 |  |  | Local Enhancement Epic | Backlog | E-528586 | E-528586 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DIM Visibility ES 401 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108591 |  |  | Local Enhancement Epic | Backlog | E-520977 | E-520977 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-3-PROJURIS_on-prem to Cloud Migration | Cancelled | Lifecycle Management Epic | Enterprise Services Portfolio | 0108609 |  |  | Lifecycle Management Epic | Backlog | E-528646 | E-528646 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Biz w/ Tech Epic: FRAME | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0108704 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Creation of Report Templates for FXL MEISA -ES 394 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108852 |  |  | Local Enhancement Epic | Backlog | E-536441 | E-536441 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXE EU - Workday changes Contingent workers ES 395 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0108853 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Poppulo - Workday Integration (ES 403) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108856 |  |  | Local Enhancement Epic | Backlog | E-521012 | E-521012 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRPAY: Ground Equifax Interface Changes | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0108952 |  |  | Local Enhancement Epic | Done | E-520982 | E-520982 | 1: XS | 2025-08-26 | 2025-08-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-26 | 2025-08-26
Local Enhancement Epic: CE Operations Hourly Overtime ES 399 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0108964 |  |  | Local Enhancement Epic | Backlog | E-534376 | E-534376 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Lifecycle Management Epic: FY26_ES_BO_HRT_ProdSup | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0108991 |  |  | Lifecycle Management Epic | Backlog | E-533350 | E-533350 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Biz w/ Tech Epic: Prepare Commercial Apps for 8-digit FedEx ID | In Progress | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109013 | 89644 | FedEx ID to 8-Digit | Biz w/ Tech Epic | Build | E-535636 | E-535636 | 3: M | 2026-01-14 |  | 100% | 5 | 5 |  | 0 | No | 2025-08-21 | 2026-02-20 | 2026-01-14
Local Enhancement Epic: Manulife Demographic file update | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0109033 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Remote Worker | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109136 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-521329 | E-521329 | 3: M | 2026-02-05 |  |  | 3 | 0 | 1 | 2 | No | 2025-08-13 | 2025-10-22 | 2026-02-05
Lifecycle Management Epic: Workday Release 2025R2 ES 402 | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0109170 |  |  | Lifecycle Management Epic | Backlog | E-521531 | E-521531 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Rearchitect the Talent Acquisition Process | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109208 | 9434 | Implement Paradox across enterprise to streamline | Biz w/ Tech Epic | Assessment & Analysis | E-507985 | E-507985 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ELS - eDiscovery - Remote Local Collections SaaS S | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109290 | 9257 | Legal technologies for Legal | Biz w/ Tech Epic | Assessment & Analysis | E-400992 | E-400992 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2026-01-06
Biz w/ Tech Epic: ELS - EMMS - ONIT - Intake System - Onit/ServiceNo | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109291 | 9257 | Legal technologies for Legal | Biz w/ Tech Epic | Assessment & Analysis | E-351156 | E-351156 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2026-01-06
Biz w/ Tech Epic: ELS - Prevail - Stand up without integrations - DR | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109292 | 9257 | Legal technologies for Legal | Biz w/ Tech Epic | Assessment & Analysis | E-429252 | E-429252 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2025-08-05
Biz w/ Tech Epic: METL Migration in HRT | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109293 | 107715 | METL FedEx Net Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-507549 | E-507549 |  |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Paradox ATS Hardening | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0109455 | 9434 | Implement Paradox across enterprise to streamline | Biz w/ Tech Epic | Backlog | E-465828 | E-465828 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2025-10-14 | 2026-03-24
Local Enhancement Epic: 361314 HRPAY _ Permanent fix for the deduction sub | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109824 |  |  | Local Enhancement Epic | Build | E-396414 | E-396414 | 4: L | 2026-04-07 |  |  | 21 | 0 | 21 | 0 | No | 2025-10-13 | 2026-01-05 | 2026-04-07
Local Enhancement Epic: 433045 Modification to ZX_TER_PYSHT Program to Pro | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109825 |  |  | Local Enhancement Epic | Backlog | E-402890 | E-402890 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-01
Local Enhancement Epic: 439450 Replace Purple Promise Message with Employe | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109826 |  |  | Local Enhancement Epic | Backlog | E-398904 | E-398904 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-28
Local Enhancement Epic: 475676 P&C Wage Statements for Crewmembers Based i | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109827 |  |  | Local Enhancement Epic | Backlog | E-447929 | E-447929 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-01
Local Enhancement Epic: 475910 Modifications to Pushup Audit Report BNS | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109828 |  |  | Local Enhancement Epic | Build | E-404141 | E-404141 | 2: S | 2026-04-07 |  |  | 25 | 0 | 25 | 0 | No | 2024-07-22 | 2025-08-01 | 2026-04-07
Local Enhancement Epic: 525995 AWU - HCM Labor Insights Platform (#524172) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109829 |  |  | Local Enhancement Epic | Backlog | E-411782 | E-411782 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-30
Lifecycle Management Epic: 542052 Planview #2998 METL Project: Retire FedEx N | Cancelled | Lifecycle Management Epic | Enterprise Services Portfolio | 0109830 |  |  | Lifecycle Management Epic | Backlog | E-428195 | E-428195 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 563254 Update MetLife (Farmers) Auto-Home Insuranc | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109831 |  |  | Local Enhancement Epic | Backlog | E-443102 | E-443102 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2025-09-01
Local Enhancement Epic: 563911 Kronos to UKG for FXF | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109832 |  |  | Local Enhancement Epic | Backlog | E-443765 | E-443765 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 574168 FEC Dimensions Timekeeping Implementation - | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109833 |  |  | Local Enhancement Epic | Backlog | E-450750 | E-450750 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-09-02 | 2025-09-30
Local Enhancement Epic: 594457 HRC0193413 - FXG Department copy setid 2000 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109834 |  |  | Local Enhancement Epic | Backlog | E-456548 | E-456548 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 596222 TH54L7FZ¦ Mail Wrap Enhancement for Dedicat | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109835 |  |  | Local Enhancement Epic | Backlog | E-457637 | E-457637 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-01 | 2025-06-30
Local Enhancement Epic: 596325 Frontstream/HRPay Evergreen Charitable Dedu | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109836 |  |  | Local Enhancement Epic | Backlog | E-461874 | E-461874 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-01 | 2025-08-01
Local Enhancement Epic: 709082 HRC0245277¦ Equifax Interface and 1A Change | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109837 |  |  | Local Enhancement Epic | Backlog | E-465096 | E-465096 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: 761426 Installation of PeopleSoft Tax Update 25-A | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0109838 |  |  | Lifecycle Management Epic | Backlog | E-478167 | E-478167 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-02-03 | 2025-05-30
Local Enhancement Epic: 761727 HRC0231942 - Provide FEC employee hours and | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109839 |  |  | Local Enhancement Epic | Launch & Evaluate | E-478561 | E-478561 |  | 2025-09-10 |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-08-04 | 2025-09-10
Local Enhancement Epic: 784483 New Canadian Benefit Vendor (Manulife) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109840 |  |  | Local Enhancement Epic | Backlog | E-483411 | E-483411 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-03 | 2025-12-31
Local Enhancement Epic: ADP 2nd Quarter Updates for 2025 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109841 |  |  | Local Enhancement Epic | Launch & Evaluate | E-518060 | E-518060 |  | 2025-08-27 |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2025-06-30 | 2025-08-27
Local Enhancement Epic: Annual Incentive Compensation (AIC) FY25 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109842 |  |  | Local Enhancement Epic | Backlog | E-501464 | E-501464 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Badge Production & Shipping | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109843 |  |  | Local Enhancement Epic | Backlog | E-502097 | E-502097 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Badging Lifecycle Management | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109844 |  |  | Local Enhancement Epic | Backlog | E-470453 | E-470453 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-29 | 2025-04-08
Local Enhancement Epic: BOI: Document Viewing | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109845 |  |  | Local Enhancement Epic | Backlog | E-504114 | E-504114 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Bravo Zulu Redesign and OTP setups | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109846 |  |  | Local Enhancement Epic | Backlog | E-459783 | E-459783 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Compliance Report Enhancements - Workday | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109847 |  |  | Local Enhancement Epic | Backlog | E-470319 | E-470319 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CRC PH Rate & Location Calculator | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109848 |  |  | Local Enhancement Epic | Backlog | E-459101 | E-459101 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: DataHub to Workday | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109849 |  |  | Local Enhancement Epic | Backlog | E-518493 | E-518493 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Deloitte Invoice Review | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109850 |  |  | Local Enhancement Epic | Backlog | E-518492 | E-518492 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-05-28 | 2026-08-05
Local Enhancement Epic: DRIVE 7272 - Vector to Lenel Integration | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109851 |  |  | Local Enhancement Epic | Backlog | E-473529 | E-473529 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ECRM Transition to Insight | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109852 |  |  | Local Enhancement Epic | Backlog | E-518491 | E-518491 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-05-28 | 2026-08-05
Local Enhancement Epic: ELS - Apptitude Ticketing and Integration | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109853 |  |  | Local Enhancement Epic | Backlog | E-485792 | E-485792 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2025-08-05
Local Enhancement Epic: ELS - Demand Planning & Architectural Support | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109854 |  |  | Local Enhancement Epic | Backlog | E-485790 | E-485790 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2026-01-06
Local Enhancement Epic: ELS - ECRM - RK - FY25 enhancements | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109855 |  |  | Local Enhancement Epic | Backlog | E-430841 | E-430841 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-27
Local Enhancement Epic: ELS - EMMS - ONIT - Oracle Financial rollout to FS | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109856 |  |  | Local Enhancement Epic | Backlog | E-438923 | E-438923 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ELS - FedEx Freight Research | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109857 |  |  | Local Enhancement Epic | Backlog | E-485793 | E-485793 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ELS - LiveSafe decommission | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109858 |  |  | Local Enhancement Epic | Backlog | E-429249 | E-429249 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ELS - Recharge - ONIT 2.0 - Build and Testing | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109859 |  |  | Local Enhancement Epic | Backlog | E-409877 | E-409877 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: ELS - Recharge - ONIT 2.0 - Migration | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109860 |  |  | Local Enhancement Epic | Backlog | E-409879 | E-409879 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ELS - Recharge - ONIT 2.0 - Planning | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109861 |  |  | Local Enhancement Epic | Backlog | E-409875 | E-409875 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ELS Production Support FY25 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109862 |  |  | Local Enhancement Epic | Backlog | E-399161 | E-399161 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-08
Local Enhancement Epic: ELS Production Support FY26 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109863 |  |  | Local Enhancement Epic | Backlog | E-462433 | E-462433 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-06-01
Local Enhancement Epic: ELS Training FY25 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109864 |  |  | Local Enhancement Epic | Backlog | E-399170 | E-399170 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-27
Local Enhancement Epic: ERMA Scheduling Enhancements | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109865 |  |  | Local Enhancement Epic | Backlog | E-459097 | E-459097 |  |  |  |  | 299 | 0 |  | 299 | No | 2025-01-27 | 2026-01-02
Local Enhancement Epic: Fairway - Workday | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109866 |  |  | Local Enhancement Epic | Backlog | E-513008 | E-513008 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FIIS Rewrite - AKS | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109867 |  |  | Local Enhancement Epic | Backlog | E-461527 | E-461527 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-01 | 2026-05-29
Local Enhancement Epic: FXEPLP - PPM 368136 - FXE - FAAR Famis Data Source | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109868 |  |  | Local Enhancement Epic | Backlog | E-377457 | E-377457 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-12 | 2026-05-29
Local Enhancement Epic: Give Feedback Reporting (ES 52) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109869 |  |  | Local Enhancement Epic | Backlog | E-517707 | E-517707 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-08-12
Local Enhancement Epic: HRC0408564¦ Supply Chain Canada Sun Life Retiremen | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109870 |  |  | Local Enhancement Epic | Backlog | E-518518 | E-518518 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRC0682052¦ Ground Equifax Interface Changes | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109871 |  |  | Local Enhancement Epic | Backlog | E-518514 | E-518514 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: International Tuition Reimbursement Harmonization | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109872 |  |  | Local Enhancement Epic | Backlog | E-459784 | E-459784 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HRPAY: IRS Secured Act Regulation for Retirement | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109873 |  |  | Local Enhancement Epic | Backlog | E-518517 | E-518517 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LDAP Data feed for FSC US - ES 234 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109874 |  |  | Local Enhancement Epic | Launch & Evaluate | E-504355 | E-504355 |  | 2025-08-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-08-26
Local Enhancement Epic: Managing Worker Additions, Changes, and Removals f | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109876 |  |  | Local Enhancement Epic | Backlog | E-502091 | E-502091 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: My Schedule Ecosystem Adoption in FXE - Epic 1 - C | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109877 |  |  | Local Enhancement Epic | Build | E-462119 | E-462119 |  | 2025-07-01 |  | 12.5% | 8 | 1 | 4 | 3 | No | 2024-10-07 | 2025-10-03 | 2025-07-01
Local Enhancement Epic: Navex / Workday API ES 256 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109878 |  |  | Local Enhancement Epic | Backlog | E-513311 | E-513311 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Network 2.0 Immediate Pay States | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109879 |  |  | Local Enhancement Epic | Launch & Evaluate | E-518571 | E-518571 |  | 2025-08-27 |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2025-07-31 | 2025-08-27
Local Enhancement Epic: New York Prenatal Leave | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109880 |  |  | Local Enhancement Epic | Build | E-519510 | E-519510 |  | 2026-04-07 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-01 | 2025-06-30 | 2026-04-07
Local Enhancement Epic: OAP International Improvements ES 388 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109881 |  |  | Local Enhancement Epic | Backlog | E-459788 | E-459788 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: OMEGA - Expand Project # field from 7 to 8 charact | On Hold | Local Enhancement Epic | Enterprise Services Portfolio | 0109882 |  |  | Local Enhancement Epic | Backlog | E-414418 | E-414418 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-12 | 2026-02-27
Local Enhancement Epic: Passport Date & Place Issued (City, State) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109883 |  |  | Local Enhancement Epic | Backlog | E-483226 | E-483226 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PCRS - PPM 294391 - FXF Intra CA & Cross-Border Co | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109884 |  |  | Local Enhancement Epic | Backlog | E-273524 | E-273524 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PCRS - PPM 704095 - FXE DOM - support to cost pool | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109885 |  |  | Local Enhancement Epic | Backlog | E-461467 | E-461467 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PCRS - PPM 708080 - OneFedEx/ Network2.0 costs for | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109886 |  |  | Local Enhancement Epic | Backlog | E-464727 | E-464727 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PCRS PPM 759600 - Pickup Preferred Future State (P | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109887 |  |  | Local Enhancement Epic | Backlog | E-476595 | E-476595 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-30 | 2026-05-29
Local Enhancement Epic: Photo Capture & Validation? | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109888 |  |  | Local Enhancement Epic | Backlog | E-502092 | E-502092 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Position Management Enhancements for Paradox | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109889 |  |  | Local Enhancement Epic | Backlog | E-504426 | E-504426 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PPR-PPM-758566-Recon Report | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0109890 |  |  | Local Enhancement Epic | Backlog | E-475735 | E-475735 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-11-07 | 2025-12-25
Local Enhancement Epic: Retiree Badge | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109891 |  |  | Local Enhancement Epic | Backlog | E-466547 | E-466547 |  |  |  |  | 4 | 0 |  | 4 | No
Local Enhancement Epic: Retiree Badge Modernization? | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109892 |  |  | Local Enhancement Epic | Backlog | E-502099 | E-502099 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Salary Termination Report (ZXROKTPM) Producing Too | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109893 |  |  | Local Enhancement Epic | Backlog | E-518509 | E-518509 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Scheduling FOSS Compliance (Springboot, Angular, J | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0109894 |  |  | Lifecycle Management Epic | Backlog | E-478460 | E-478460 |  |  |  |  | 13 | 0 |  | 13 | No
Local Enhancement Epic: TechOps Roster - ES 232 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109895 |  |  | Local Enhancement Epic | Done | E-513063 | E-513063 |  | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Tonmiles Upgrade | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109896 |  |  | Local Enhancement Epic | Backlog | E-508041 | E-508041 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Visitor Management | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0109897 |  |  | Local Enhancement Epic | Backlog | E-502101 | E-502101 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: WOS - Talent Review Statement update - DIR 1232 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0109898 |  |  | Local Enhancement Epic | Backlog | E-513179 | E-513179 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: BOI Access for Training Instructors - (LTT) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0110681 |  |  | Local Enhancement Epic | Backlog | E-535274 | E-535274 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: International Implementation | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0110707 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: International timekeeping implementation | On Hold | Biz w/ Tech Epic | Enterprise Services Portfolio | 0110710 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: ArcherGRC (6366) Prod migration from Azure to COLO | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0110717 |  |  | Local Enhancement Epic | Backlog | E-526732 | E-526732 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SAM Software as a Subscription Integrations | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0110788 | 8204 | FedEx ITAM practice for the Enterprise | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: PLP Data ingestion into FIP to Atlas | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0110850 |  |  | Local Enhancement Epic | Backlog | E-522996 | E-522996 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Allowance Plan 003 for HR Technology ES 405 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0110851 |  |  | Local Enhancement Epic | Backlog | E-533351 | E-533351 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Immigration Team ES 409 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0110854 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541982 | E-541982 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: FXL Qatar & Saudi Absence Module Creation ES415 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0110856 |  |  | Local Enhancement Epic | Backlog | E-527332 | E-527332 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Data Input into FedEx Timekeeping System Intl | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0110859 | 88482 | International UKG Timekeeping Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-569312 | E-569312 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-04-01 | 2026-09-30
Biz w/ Tech Epic: Data Output from FedEx Timekeeping System Intl | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0110860 | 88482 | International UKG Timekeeping Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-569310 | E-569310 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-04-01 | 2026-09-30
Local Enhancement Epic: Ground PLP Total Facility Touches | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0110941 |  |  | Local Enhancement Epic | Launch & Evaluate | E-523612 | E-523612 | 1: XS | 2025-07-28 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-28
Local Enhancement Epic: HRPAY: Rescind Actions Affects WTW Benefits | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0110945 |  |  | Local Enhancement Epic | Backlog | E-524114 | E-524114 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Support API access to DOTS database | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0111074 |  |  | Local Enhancement Epic | Backlog | E-535379 | E-535379 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AIC - Proration Report Change Prompt ES 424 | On Hold | Local Enhancement Epic | Enterprise Services Portfolio | 0111100 |  |  | Local Enhancement Epic | Backlog | E-531419 | E-531419 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: New Package Handler 401k Plan ES 422 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0111132 |  |  | Local Enhancement Epic | Backlog | E-527333 | E-527333 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Package Handler 401k Plan - SPD file ES 421 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0111134 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: report 251 - express Ita eur ES 423 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0111352 |  |  | Local Enhancement Epic | Backlog | E-527279 | E-527279 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-12 | 2026-03-06
Local Enhancement Epic: FY 26 SSP Enhancements 843925 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0111416 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Decommission & Data Archive Intl | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111425 | 88482 | International UKG Timekeeping Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-569311 | E-569311 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-04-01 | 2026-09-30
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111542 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111657 | 92116 | FRAME (Financial Reconciliation and Management Eff | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: ES - TEN-153953 Self-Serve Remediation (ES 432) | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0111659 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-530970 | E-530970 | 2: S | 2025-08-18 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-08-18
Local Enhancement Epic: HRPAY - Interface File Format Change ES 425 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0111701 |  |  | Local Enhancement Epic | Backlog | E-535136 | E-535136 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-09-22 | 2025-11-28
Lifecycle Management Epic: Install PeopleSoft Tax Update 25-B to HRPAY | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0111726 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Install PeopleSoft Tax Update 25-B to HRPAY | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0111727 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VMS EWM Implementation For CDG (France) | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0106572 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VMS EWM Implementation For Additional Countries | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111815 | 9442 | Global Temp Labor VMS | Biz w/ Tech Epic | Assessment & Analysis | E-575269 | E-575269 | 4: L |  |  |  | 4 | 0 |  | 4 | No | 2026-03-09 | 2026-10-20
Biz w/ Tech Epic: VMS WPM Implementation For Additional Countries | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111818 | 9442 | Global Temp Labor VMS | Biz w/ Tech Epic | Assessment & Analysis | E-575260 | E-575260 | 4: L |  |  |  | 5 | 0 |  | 5 | No | 2026-03-06 | 2026-10-20
Biz w/ Tech Epic: Load VNDLY Data to Labor Insights Platform (LIP) | Completed | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111819 | 9442 | Global Temp Labor VMS | Biz w/ Tech Epic | Assessment & Analysis | E-575259 | E-575259 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ERMA Availability Cleared when Marked Not Avail. | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0111859 |  |  | Local Enhancement Epic | Backlog | E-529683 | E-529683 | 2: S | 2025-08-18 |  |  | 10 | 0 |  | 10 | No |  |  | 2025-08-18
Local Enhancement Epic: Move ancillary billing accounts IP/IPF Other | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0111860 |  |  | Local Enhancement Epic | Launch & Evaluate | E-529788 | E-529788 | 1: XS | 2025-09-04 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-09-04
Local Enhancement Epic: ERMA New Hires, Rehires, & Transfers (ES 439) | Completed | Local Enhancement Epic | Enterprise Services Portfolio | 0111861 |  |  | Local Enhancement Epic | Done | E-529684 | E-529684 | 2: S | 2025-08-18 | 2025-08-18 |  | 46 | 0 |  | 46 | No |  |  | 2025-08-18 | 2025-08-18
Local Enhancement Epic: ERMA Search Bar for Dropdowns (ES 442) | Completed | Local Enhancement Epic | Enterprise Services Portfolio | 0111863 |  |  | Local Enhancement Epic | Done | E-529678 | E-529678 | 1: XS | 2025-08-18 | 2025-08-18 |  | 10 | 0 |  | 10 | No |  |  | 2025-08-18 | 2025-08-18
Local Enhancement Epic: ERMA Limit Jobs (ES 443) | Completed | Local Enhancement Epic | Enterprise Services Portfolio | 0111865 |  |  | Local Enhancement Epic | Done | E-529679 | E-529679 | 2: S | 2025-08-13 | 2025-08-13 |  | 225 | 0 |  | 225 | No |  |  | 2025-08-13 | 2025-08-13
Local Enhancement Epic: ERMA Fixed Shifts (ES 446) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0111866 |  |  | Local Enhancement Epic | Backlog | E-529682 | E-529682 | 2: S |  |  |  | 113 | 0 |  | 113 | No | 2025-10-14 | 2026-03-13
Lifecycle Management Epic: FY26_ES_BO_FIN_All Patching | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0111868 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-531277 | E-531277 | 2: S | 2025-08-22 |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29 | 2025-08-22
Lifecycle Management Epic: FY26_ES_BO_FIN_ProdSup | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0111869 |  |  | Lifecycle Management Epic | Backlog | E-532898 | E-532898 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2026-05-29
Local Enhancement Epic: MyTime Vacation Payout - FXG Canada (ES 430) | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0111873 |  |  | Local Enhancement Epic | Build | E-529677 | E-529677 | 1: XS | 2026-04-07 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2026-04-07
Local Enhancement Epic: MyTime Sick Day Configuration - Canada ONLY ES 431 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0111877 |  |  | Local Enhancement Epic | Build | E-536017 | E-536017 | 1: XS | 2026-04-07 |  | 100% | 9 | 9 |  | 0 | No | 2025-10-06 | 2026-01-02 | 2026-04-07
Biz w/ Tech Epic: VMS EWM Implementation For CDG France | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111885 | 9442 | Global Temp Labor VMS | Biz w/ Tech Epic | Assessment & Analysis | E-573976 | E-573976 | 4: L |  |  |  | 6 | 0 |  | 6 | No | 2026-03-09 | 2026-06-02
Lifecycle Management Epic: FY26_HRT_Distributed_LCM_Linux, Weblogic, Java | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0111930 |  |  | Lifecycle Management Epic | Backlog | E-533349 | E-533349 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-05-29
Local Enhancement Epic: ONA DataHub Filter Update for FedEx One 435 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0111938 |  |  | Local Enhancement Epic | Backlog | E-536211 | E-536211 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Canceled: TNT Legacy Decommission - Migration | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0112110 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: ERMA Job Qualifications (ES 449) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0112167 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541981 | E-541981 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-03-30
Biz w/ Tech Epic: 1.0 Retiree Badge Modernization | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111754 | 7641 | 7641- ENT Badging and Physical Access Security 1.0 | Biz w/ Tech Epic | Backlog | E-531114 | E-531114 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-11-14
Biz w/ Tech Epic: 1.0 Badge Production | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111749 | 7641 | 7641- ENT Badging and Physical Access Security 1.0 | Biz w/ Tech Epic | Backlog | E-531113 | E-531113 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-12-05
Biz w/ Tech Epic: 1.0 Managing Worker Additions and Changes | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0104037 | 7641 | 7641- ENT Badging and Physical Access Security 1.0 | Biz w/ Tech Epic | Build | E-531112 | E-531112 | 4: L | 2025-09-15 |  |  | 2 | 0 | 2 | 0 | No | 2025-08-13 | 2025-12-04 | 2025-09-15
Biz w/ Tech Epic: 1.0 Photo Capture & Validation | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111745 | 7641 | 7641- ENT Badging and Physical Access Security 1.0 | Biz w/ Tech Epic | Backlog | E-531110 | E-531110 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Biz w/ Tech Epic: 1.0 Visitor Managment | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0111751 | 7641 | 7641- ENT Badging and Physical Access Security 1.0 | Biz w/ Tech Epic | Backlog | E-531111 | E-531111 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Biz w/ Tech Epic: 2.0: CSP/Remote Worker Adds, Changes, Removal | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107956 | 92356 | 92356- ENT Badging and Physical Access Release 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-548896 | E-548896 | 4: L |  |  |  | 9 | 0 |  | 9 | No | 2025-10-22 | 2026-03-31
Local Enhancement Epic: PLP Ground and Express Pickup PFS (ES 451) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112197 |  |  | Local Enhancement Epic | Backlog | E-532429 | E-532429 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EnCoRE Production LDAP Inbound Integration Code Ch | On Hold | Local Enhancement Epic | Enterprise Services Portfolio | 0112207 |  |  | Local Enhancement Epic | Launch & Evaluate | E-536987 | E-536987 | 1: XS | 2025-09-09 |  |  | 0 | 0 |  | 0 | No | 2025-09-15 | 2025-11-28 | 2025-09-09
Lifecycle Management Epic: Installation of PeopleSoft Tax Update 25-B (ES462) | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0112260 |  |  | Lifecycle Management Epic | Backlog | E-532502 | E-532502 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-31
Lifecycle Management Epic: FY25_PI4_ES_Finance_Avengers_LCM_JAVA_WL_Angular_S | Cancelled | Lifecycle Management Epic | Enterprise Services Portfolio | 0112307 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_ES_BO_SPaT_ProdSup (ES 466) | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0112317 |  |  | Lifecycle Management Epic | Build | E-532609 | E-532609 | 2: S | 2026-04-07 |  | 27.03% | 37 | 10 | 7 | 20 | No | 2025-06-02 | 2026-05-29 | 2026-04-07
Biz w/ Tech Epic: Workday Learning Implementation | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112321 | 9288 | Contract management and negotiation - Workday | Biz w/ Tech Epic | Backlog | E-532754 | E-532754 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-08-13 | 2026-02-27
Local Enhancement Epic: Minnesota Paid Sick Leave (ES 455) | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0112341 |  |  | Local Enhancement Epic | Backlog | E-536018 | E-536018 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Missouri Paid Sick Leave (ES 458) | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0112346 |  |  | Local Enhancement Epic | Backlog | E-536016 | E-536016 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: OMEGA - Reformat Item Desc for Grainger PO | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112370 |  |  | Local Enhancement Epic | Backlog | E-535111 | E-535111 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Travel Group Admin Page for Eligibility Check | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112377 |  |  | Local Enhancement Epic | Backlog | E-534515 | E-534515 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: API access to Right Angle for ESG reporting | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112535 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541465 | E-541465 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Officer & Director Workflow in Paradox ES 450 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0112536 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Modify Programming on Nightly WTW File ES 472 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112537 |  |  | Local Enhancement Epic | Backlog | E-536988 | E-536988 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Merit Grid layout for Intl Regions ES 475 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112539 |  |  | Local Enhancement Epic | Backlog | E-536986 | E-536986 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Prepare SCO Applications for 8-digit FedEx ID | In Progress | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112620 | 89644 | FedEx ID to 8-Digit | Biz w/ Tech Epic | Build | E-535501 | E-535501 | 4: L | 2025-11-07 |  | 85.71% | 14 | 12 |  | 2 | No | 2025-08-11 | 2026-10-12 | 2025-11-07
Biz w/ Tech Epic: Prepare Platforms Apps for 8-digit FedEx ID | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112621 | 89644 | FedEx ID to 8-Digit | Biz w/ Tech Epic | Build | E-535500 | E-535500 | 3: M | 2025-11-17 |  | 50% | 2 | 1 |  | 1 | No | 2025-09-01 | 2026-02-20 | 2025-11-17
Biz w/ Tech Epic: Prepare DAI Applications for FedEx 8-Digit ID | In Progress | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112625 | 89644 | FedEx ID to 8-Digit | Biz w/ Tech Epic | Build | E-535499 | E-535499 | 3: M | 2025-10-02 |  | 100% | 13 | 13 |  | 0 | No | 2026-01-01 | 2026-03-31 | 2025-10-02
Biz w/ Tech Epic: Prepare Enterprise Svcs Apps for 8-digit FedEx ID | In Progress | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112626 | 89644 | FedEx ID to 8-Digit | Biz w/ Tech Epic | Backlog | E-535637 | E-535637 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2026-01-05 | 2026-02-20
Biz w/ Tech Epic: Project Genesis FCF CY Change | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112650 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Project Genesis FCF CY Change | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112653 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Workday/Workiva Data Integration ES 460 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0112751 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542000 | E-542000 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2027-03-31
Local Enhancement Epic: New Workday report on Spend Authorization ES 474 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112752 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541997 | E-541997 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Nebraska Paid Sick Leave (ES 473) | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0112774 |  |  | Local Enhancement Epic | Backlog | E-536092 | E-536092 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: FCOE: Retire NVision reports and decom servers 478 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112883 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538796 | E-538796 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Workday Historical Form I-9 Data Load ES 480 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0112889 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Allowance Plan for FXEEU - DEU - ES 481 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112890 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541999 | E-541999 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Project Genesis - Oracle FCF and Boundaries | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0112912 | 127973 | Project Genesis - Oracle FCF - FY to CY | Biz w/ Tech Epic | Build | E-542750 | E-542750 | 4: L | 2025-11-06 |  |  | 47 | 0 | 2 | 45 | No | 2025-09-01 | 2026-09-15 | 2025-11-06
Local Enhancement Epic: New Allowance FXEEU DEU Salary Diff Ded ES 482 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0112925 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541998 | E-541998 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FEC-US MX Planner Allowance plan (ES 444) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0113088 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552027 | E-552027 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Global Security RAPBACK Program Automation ES 459 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0113089 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552478 | E-552478 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Implement Secure 2.0 regulations (ES 483) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0113097 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537618 | E-537618 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: eDiscovery Automation (ES 491) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0113099 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538391 | E-538391 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-15 | 2026-03-17
Local Enhancement Epic: BI Publisher report for FCF Workbench Orders ES492 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0113101 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Vector - LS QR Service Revision/Implementation 488 | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0113110 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-551134 | E-551134 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-12 | 2026-02-16
Local Enhancement Epic: FXO Badge Renewal Reminder (ES 407) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0113151 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569327 | E-569327 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: PCRS - Enterprise Costing Integration | On Hold | Biz w/ Tech Epic | Enterprise Services Portfolio | 0113227 | 127979 | PCRS - Enterprise Costing Integration | Biz w/ Tech Epic | Assessment & Analysis | E-563729 | E-563729 | 3: M |  |  |  | 6 | 0 |  | 6 |  | 2026-01-01 | 2026-12-30
Biz w/ Tech Epic: Project Sundance - Fiscal Year to Calendar Year | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0113241 | 127976 | Project Sundance - Calendar Year Change | Biz w/ Tech Epic | Build | E-544197 | E-544197 | 4: L | 2026-01-23 |  |  | 20 | 0 | 12 | 8 |  | 2025-11-12 | 2026-08-28 | 2026-01-23
Local Enhancement Epic: OMEGA - Inventory Quantity Balance Correction | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0113290 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545719 | E-545719 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-05 | 2026-04-24
Lifecycle Management Epic: PeopleSoft Application Updates 50-52 (ES 471) | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0113296 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-538795 | E-538795 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-03 | 2026-01-09
Lifecycle Management Epic: 2025 ADP Interface Spec Release for 3rd Quarter | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0113299 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-538794 | E-538794 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Vector - Lenel Assessment of Non- LFXG Expansion | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0113304 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-01-07
Local Enhancement Epic: Manulife Demographic file update (ES 464) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0113540 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548893 | E-548893 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-24 | 2025-12-19
Local Enhancement Epic: Comp Security for FEC (ES 490) | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0113541 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552322 | E-552322 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Tax: Legacy FXE FUMES Vusion Project | On Hold | Local Enhancement Epic | Enterprise Services Portfolio | 0113538 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541464 | E-541464 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-12-26 | 2026-03-31
Biz w/ Tech Epic: Data input into FedEx Timekeeping system | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0113731 | 6933 | UKG Enterprise Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-543981 | E-543981 | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-10-01 | 2026-09-30
Biz w/ Tech Epic: Data output from FedEx Timekeeping system | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0113773 | 6933 | UKG Enterprise Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-543982 | E-543982 | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-09-30
Biz w/ Tech Epic: Decommission & Data Archive | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0113775 | 6933 | UKG Enterprise Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-543980 | E-543980 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2027-12-31
Biz w/ Tech Epic: Project Fairway/Back Office Separation Enablement | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0113792 | 143548 | Project Fairway - Back Office Separation Enablemen | Biz w/ Tech Epic | Assessment & Analysis | E-546439 | E-546439 | 4: L |  |  |  | 5 | 0 |  | 5 |  | 2025-09-01 | 2026-06-01
Local Enhancement Epic: HRPAY: Pilot Pay - Incorporate Processing Controls | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0113880 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548891 | E-548891 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Installation of PeopleSoft Tax Update 25-C (ES501) | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0113881 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-548890 | E-548890 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY25_PI5_HRT_LCM_FY26_SOX_Compliance1 (ES 512) | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0114014 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-552480 | E-552480 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-28 | 2026-02-27
Local Enhancement Epic: Workday Learning Retraining Clean-up Need | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0114081 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: 2026 Vertical (SIDA) Rebadge | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0114167 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: New Payroll Earnings Code -Civic Service/Jury Duty | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0114199 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548279 | E-548279 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-10-27 | 2026-01-30
Lifecycle Management Epic: 2025 ADP Interface Spec Release for 4th Quarter | Closed | Lifecycle Management Epic | Enterprise Services Portfolio | 0114203 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-553447 | E-553447 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Install PeopleSoft Tax Update 25-D and PRPs ES 505 | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0114206 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-553448 | E-553448 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-11-21 | 2026-01-02
Local Enhancement Epic: INT0170 in Hire BP (ES 500) | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0114207 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552479 | E-552479 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: New Flex Pay Codes Needed for Ticket HRC0528077 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0114211 |  |  | Local Enhancement Epic | Build | E-548280 | E-548280 | 2: S | 2026-04-07 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-27 | 2026-01-30 | 2026-04-07
Local Enhancement Epic: Change existing View in datahub (ES 496) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0114215 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552481 | E-552481 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Ground PLP LMO New Cost Pool (ES 504) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0114217 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549522 | E-549522 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: EIB Option for Talent Data (ES 507) | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0114254 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: 2.0: Badge Production and Shipping (E-549126) | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107997 | 92356 | 92356- ENT Badging and Physical Access Release 2.0 | Biz w/ Tech Epic | Build | E-549126 | E-549126 | 4: L | 2026-01-09 |  | 25% | 4 | 1 | 1 | 2 |  | 2025-10-01 | 2026-03-31 | 2026-01-09
Biz w/ Tech Epic: 2.0: Photo Capture & Validation (E-549128) | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0107995 | 92356 | 92356- ENT Badging and Physical Access Release 2.0 | Biz w/ Tech Epic |  | E-549128 | E-549128 | 4: L |  |  |  | 1 | 0 |  | 1 |  | 2025-10-01 | 2026-03-31
Biz w/ Tech Epic: Pathlock for HRPAY access | Closed | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114323 | 130471 | Pathlock for HRPAY access | Biz w/ Tech Epic | Assessment & Analysis | E-549057 | E-549057 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: GTreasury RemainCo -EPIC | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114325 | 166110 | GTreasury RemainCo | Biz w/ Tech Epic | Assessment & Analysis | E-581094 | E-581094 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2026-08-31
Local Enhancement Epic: WorkPerks Eligibility File (ES 499) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0114327 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552482 | E-552482 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: RightCrowd & Lenel INT Upgrade (E-464918) ES-53 | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0114329 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Test | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114331 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Test | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114333 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Oracle FCF integration with the Purchasing Gate | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114365 | 153735 | EMR IFT Purchasing Gateway | Biz w/ Tech Epic | Assessment & Analysis | E-569881 | E-569881 | 2: S |  |  |  | 6 | 0 |  | 6
Local Enhancement Epic: Civic Service/Jury Duty Unpaid Abs/Reason ES 511 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0114497 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-03-27
Local Enhancement Epic: Workday Discovery Boards (ES 513) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0114498 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555322 | E-555322 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-12-16 | 2026-03-24
Local Enhancement Epic: OMEGA S&F Inventory to MAXIMO (ES 514) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0114502 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553376 | E-553376 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-20 | 2026-05-22
Local Enhancement Epic: Fixed Assets Construction In Progress (CIP)_SOX | Assumed Completed | Local Enhancement Epic | Enterprise Services Portfolio | 0114505 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569034 | E-569034 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-03-09
Biz w/ Tech Epic: PCRS: eMBP Transformation | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114552 | 8407 | eMBP Transformation | Biz w/ Tech Epic | Assessment & Analysis | E-552252 | E-552252 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-11-07 | 2027-08-31
Local Enhancement Epic: Wage payment files to ADPimprovement (ES 502) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0114710 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561683 | E-561683 | 1: XS |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: TS-VL3-Azure-Tanium Migration to Cloud | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0114767 | 166054 | TS-VL3-Azure-Tanium Migration to Cloud | Biz w/ Tech Epic | Build | E-564326 | E-564326 | 2: S | 2026-03-06 |  |  | 3 | 0 | 1 | 2 |  |  |  | 2026-03-06
Local Enhancement Epic: Workday Integration- AIQ Learning Contract -ES 517 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0114926 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570290 | E-570290 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY25_ES_BO_FIN_LCM_FY26_SOX_Compliance | Cancelled | Lifecycle Management Epic | Enterprise Services Portfolio | 0114995 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Security Time - Timekeeping System Changes | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0115013 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553993 | E-553993 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Integration of machine software with Oracle FCF | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0115035 | 166021 | PPE Consumption Reduction - Vending Machines | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-13 | 2026-01-23
Local Enhancement Epic: Network 2.0 HRT Support CY25 PI5 (ES 526) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0115051 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554185 | E-554185 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXF, FFC & FCC- Semi-Annual CI Cycle (ES 527) | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0115052 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570294 | E-570294 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ES - BO - SPaT Support of METL HIPPA Compliance | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115070 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560558 | E-560558 | 4: L |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: FEC/003 CRC Report Update: CA TOR Report (ES 524) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115076 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554548 | E-554548 | 2: S |  |  |  | 5 | 0 |  | 5 |  | 2026-01-05 | 2026-03-13
Local Enhancement Epic: CA Vacation/PTO Final Payout Rate Update (ES 521) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115098 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554746 | E-554746 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-05 | 2026-03-13
Lifecycle Management Epic: IMAGE -OCI EFBV Integration(EBS Team testing only) | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0115205 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CW Universal ID feed to VNDLY - onboarding ES 528 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115254 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563187 | E-563187 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-30 | 2026-06-02
Local Enhancement Epic: New Allowance Plans for ZAF & NAM ES 532 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0115255 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570293 | E-570293 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FEC FY26 AIC Exception Workday Admin ES 534 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115258 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570292 | E-570292 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: Germany - Local Enhancement Workday (ES 535) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115260 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575784 | E-575784 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-30 | 2026-06-02
Local Enhancement Epic: LIP PI-6 Workday Performance Reports (ES 538) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0115267 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: New absence plan for Thailand (ES 542) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115270 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570295 | E-570295 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-18
Local Enhancement Epic: Add task to manager when creating a SIDA CW ES 539 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115272 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566780 | E-566780 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-02-11 | 2026-03-24
Biz w/ Tech Epic: Adjust FedEx ID Incrementor | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0115303 | 89644 | FedEx ID to 8-Digit | Biz w/ Tech Epic | Assessment & Analysis | E-555861 | E-555861 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-05 | 2026-05-29
Biz w/ Tech Epic: Brazil Tax Reform - Alphanumeric CNPJ | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0115314 | 166045 | LAC-BR- Brazil Tax Reform - Alphanumeric CNPJ | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: New Onit LSR/National Labor Relations Board Filing | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0115530 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Contingent Worker Type Attribute to InfoSec ES 548 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0115531 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LIP data feed for FSC emps - WD + Populo ES 550 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115863 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570291 | E-570291 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Minnesota Rest and Meal Regulatory Changes -ES 552 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0115868 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564741 | E-564741 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AIC Administration - Plan Assignments Missing -555 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0115869 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581135 | E-581135 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-09
Lifecycle Management Epic: Workday Release 2026R1 (ES 557) | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0115893 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-570298 | E-570298 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-03-25
Local Enhancement Epic: Training Equivalency Records from WDL to Datahub | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0115928 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: The Pilot code SDA needs to be mapped to POV ES537 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0115975 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PTO Harmonization and Fiscal Year Changes ES 562 | Cancelled | Local Enhancement Epic | Enterprise Services Portfolio | 0116043 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564762 | E-564762 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Add GL Account Descriptions for Supplemental GL Ac | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0116079 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565835 | E-565835 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: APAC WFM | In Progress | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116086 | 113481 | Weekly Forecast Management (WFM) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GIBS Badge Expiration Update (ES 570) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0116376 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Handler Saturday Bonus (ES 564) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0116377 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576146 | E-576146 | 1: XS |  |  |  | 45 | 0 |  | 45 |  | 2026-05-25 | 2026-08-03
Local Enhancement Epic: Network 2.0 HRT Support CY26 PI1 (ES 569) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0116379 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570296 | E-570296 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-25
Local Enhancement Epic: Network 2.0 HRT Support CY26 PI2 (ES 568) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0116380 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570297 | E-570297 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-26 | 2026-06-02
Biz w/ Tech Epic: Test Epic | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116398 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ES Proxy to Purple Connect Migration | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116436 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FedEx - Audit - Job Profiles Report (ES 549) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0116493 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581428 | E-581428 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Global Deployment of Onit (Onit International) | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116640 | 168950 | Onit Expansion for Legal | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: HRPAY: Equifax Interface Changes ES 566 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0116641 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: California Emergency Contact Note ES 577 | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0116643 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570833 | E-570833 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-25 | 2026-04-01
Biz w/ Tech Epic: Archer to OnSpring Migration | Cancelled | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116729 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Transition Layer Deprecation | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116807 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2027-04-01 | 2029-03-30
Biz w/ Tech Epic: Setup Case IQ Case Management System | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116835 | 170387 | Implement New Alert Line Software | Biz w/ Tech Epic | Assessment & Analysis | E-580601 | E-580601 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-05-26
Biz w/ Tech Epic: Integrations with Case IQ Case Management System | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116836 | 170387 | Implement New Alert Line Software | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-08-03 | 2026-10-01
Lifecycle Management Epic: Purple Access Gateway (PAG) Decommission - Impleme | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0116900 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582337 | E-582337 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-05-29
Biz w/ Tech Epic: NetDocuments | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0116940 | 168954 | New Document Management System for Legal | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: 2026 ADP Interface Spec Release for 1st Q, ES 580 | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0116949 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-574538 | E-574538 | 2: S |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: Install PeopleSoft Tax Update 26-A, ES 579 | Approved | Lifecycle Management Epic | Enterprise Services Portfolio | 0116951 |  |  | Lifecycle Management Epic | Build | E-574539 | E-574539 | 3: M | 2026-03-12 |  |  | 100 | 0 | 100 | 0 |  |  |  | 2026-03-12
Local Enhancement Epic: Launch Hourly merit cycle for FXECAN, ES 583 | Closed | Local Enhancement Epic | Enterprise Services Portfolio | 0116956 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578831 | E-578831 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: SIP Integrations | Approved | Biz w/ Tech Epic | Enterprise Services Portfolio | 0117016 | 153778 | EMR IFT Supplier Portal | Biz w/ Tech Epic | Assessment & Analysis | E-577720 | E-577720 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-16 | 2027-03-12
Local Enhancement Epic: 28 Crime return process (ES 585) | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0117093 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581798 | E-581798 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-20 | 2026-05-29
Local Enhancement Epic: Perceptyx Outbound Labor Insights Platform file | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117121 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: New SAF-T reporting - mismatch between TB and 052 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117231 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Archer Migration OnSpring | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0117245 | 177745 | TS-VL2-ES-CON-Migrate Archer Solutions to Onspring | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-09-01 | 2026-09-18
Biz w/ Tech Epic: Archer to OnSpring Migration | Not Started | Biz w/ Tech Epic | Enterprise Services Portfolio | 0117246 | 177745 | TS-VL2-ES-CON-Migrate Archer Solutions to Onspring | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-09-01 | 2026-09-18
Local Enhancement Epic: PCRS - Performance fine-tuning PoC (ES 586) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117366 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: New Pay Hours report from the Preprocessor Data | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0117482 |  |  | Local Enhancement Epic | Build | E-582146 | E-582146 | 1: XS | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-22
Local Enhancement Epic: Accounting Reporting - Paid Time Off Accruals (US | Approved | Local Enhancement Epic | Enterprise Services Portfolio | 0117486 |  |  | Local Enhancement Epic | Build | E-581525 | E-581525 | 2: S | 2026-04-21 |  |  | 45 | 0 | 45 | 0 |  | 2026-04-06 | 2026-06-01 | 2026-04-21
Local Enhancement Epic: FIND Application (ES 597) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117501 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Perceptyx Automated Data File (ES 591) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117637 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Contingent Worker - Process Change for TSA ES 594 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117638 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Eliminate step 2 for C grade structures ES 595 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117639 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PCRS: Piece-Level Dimensions Visibility for Intern | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117750 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PCRS: US customs cost recalibration for historical | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117751 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable Pay Range visibility Europe (ES 588) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117877 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HRPAY-Restrict ZXAGEADJ to U.S. only es592 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117888 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HRPAY: Terminate 401(k) Election for Rehires es593 | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117889 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXEPLP-Research BSO/Express Clear/Customs (ES 602) | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117890 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Notification to New Account Holder on Social Msg | Not Started | Local Enhancement Epic | Enterprise Services Portfolio | 0117894 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: PeopleSoft Update Manager images 53-58 (ES 599) | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0117911 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: 2026 Tax Update ... - 26 B,C,D, etc. (ES 600) | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0117912 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: HRPAY People Tools Upgrade 8.60 to 8.62 (ES 601) | Not Started | Lifecycle Management Epic | Enterprise Services Portfolio | 0117913 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Pilot Sites and Evaluation | Completed | Biz w/ Tech Epic | Platforms Portfolio | 0103337 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Full AT&T Rollout - FY26 | In Progress | Biz w/ Tech Epic | Platforms Portfolio | 0103340 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-08-09 | 2026-05-29
Biz w/ Tech Epic: Implement HW Asset Management Global Practice | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0103447 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Retirement of TNT Mainframe | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0104570 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: VERVE Asset Manager | Closed | Local Enhancement Epic | Platforms Portfolio | 0104870 |  |  | Local Enhancement Epic | Done |  |  | 2: S | 2025-06-26 | 2025-06-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Local Enhancement Epic: MEM Ramp Wireless Connectivity | Approved | Local Enhancement Epic | Platforms Portfolio | 0104872 |  |  | Local Enhancement Epic | Build | E-482380 | E-482380 | 2: S | 2025-09-19 |  |  | 1 | 0 | 1 | 0 | No | 2025-03-06 | 2026-03-30 | 2025-09-19
Local Enhancement Epic: Apple Watch and Widget to support Forgerock Cookie | Rejected | Local Enhancement Epic | Platforms Portfolio | 0104873 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Remove FDX login cookie API call | Rejected | Local Enhancement Epic | Platforms Portfolio | 0104874 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Platform Portfolio FDM Adoption | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0104893 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Establish the foundational support for the SbD | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0105315 | 91820 | InfoSec - Secure by Design - Phase 1 | Biz w/ Tech Epic | Build | E-468968 | E-468968 | 5: XL | 2025-07-21 |  | 21.62% | 37 | 8 | 12 | 17 | No | 2024-07-22 | 2029-09-13 | 2025-07-21
Biz w/ Tech Epic: Project and Portfolio Management (PPM) Retirement | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0105068 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Build | E-514373 | E-514373 | 3: M | 2025-09-12 |  | 12.99% | 231 | 30 | 201 | 0 | No | 2024-07-22 | 2029-05-02 | 2025-09-12
Lifecycle Management Epic: FY25 IBM LCM CLEAR | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0105479 |  |  | Lifecycle Management Epic | Backlog | E-483146 | E-483146 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: IMS servers upgrade and migration | Completed | Lifecycle Management Epic | Platforms Portfolio | 0105480 |  |  | Lifecycle Management Epic | Build | E-517902 | E-517902 | 2: S | 2025-11-17 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-11-17
Local Enhancement Epic: LEFS Composite Object Service access to AddressEFS | Approved | Local Enhancement Epic | Platforms Portfolio | 0105591 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528424 | E-528424 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: PAW Rollout | Approved | Local Enhancement Epic | Platforms Portfolio | 0105665 |  |  | Local Enhancement Epic | Build | E-482986 | E-482986 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No | 2025-03-13 | 2026-04-03 | 2025-07-15
Local Enhancement Epic: SOX Control Rationalization - EIAM | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0105852 |  |  | Local Enhancement Epic | Backlog | E-498984 | E-498984 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: IND Ramp Wireless Connectivity | Approved | Local Enhancement Epic | Platforms Portfolio | 0105853 |  |  | Local Enhancement Epic | Build | E-487048 | E-487048 | 2: S | 2025-10-10 |  |  | 1 | 0 | 1 | 0 | No | 2025-03-27 | 2026-03-30 | 2025-10-10
Local Enhancement Epic: IP Address Management Project | Approved | Local Enhancement Epic | Platforms Portfolio | 0105864 |  |  | Local Enhancement Epic | Build | E-486479 | E-486479 | 2: S | 2025-10-20 |  | 50% | 2 | 1 | 1 | 0 | No | 2025-04-14 | 2025-12-31 | 2025-10-20
Local Enhancement Epic: Spotlight Documentation Migration | Approved | Local Enhancement Epic | Platforms Portfolio | 0105869 |  |  | Local Enhancement Epic | Launch & Evaluate | E-487047 | E-487047 | 1: XS | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: EDI Customer Logic Enhancements | Approved | Local Enhancement Epic | Platforms Portfolio | 0105889 |  |  | Local Enhancement Epic | Build | E-500249 | E-500249 | 2: S | 2025-06-26 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-12-31 | 2025-06-26
Local Enhancement Epic: End User Application Vulnerability Management | Not Started | Local Enhancement Epic | Platforms Portfolio | 0105942 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Github SaaS Integration | Approved | Local Enhancement Epic | Platforms Portfolio | 0105959 |  |  | Local Enhancement Epic | Launch & Evaluate | E-504405 | E-504405 | 1: XS | 2025-06-27 |  |  | 0 | 0 |  | 0 | No | 2025-05-06 | 2026-05-29 | 2025-06-27
Local Enhancement Epic: Allowing Light Catalog Builder to Map SW Models | Approved | Local Enhancement Epic | Platforms Portfolio | 0105960 |  |  | Local Enhancement Epic | Launch & Evaluate | E-504400 | E-504400 | 2: S | 2025-06-27 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: IBM Onboarding Through Anglepoint | Closed | Local Enhancement Epic | Platforms Portfolio | 0105962 |  |  | Local Enhancement Epic | Done | E-504383 | E-504383 | 1: XS | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Local Enhancement Epic: Client Software Dist (CSD) Go-Live and Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0105964 |  |  | Local Enhancement Epic | Launch & Evaluate | E-501762 | E-501762 | 1: XS | 2025-06-27 |  |  | 0 | 0 |  | 0 | No | 2025-04-08 | 2026-05-20 | 2025-06-27
Local Enhancement Epic: Implement QoL Improvements for Software Requests | Closed | Local Enhancement Epic | Platforms Portfolio | 0105965 |  |  | Local Enhancement Epic | Done | E-501765 | E-501765 | 2: S | 2025-06-27 | 2025-09-02 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-09-02
Lifecycle Management Epic: FXL Cisco LCM | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0105984 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FXL Cisco LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0106015 |  |  | Lifecycle Management Epic | Build | E-487066 | E-487066 | 2: S | 2025-09-20 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-14 | 2025-11-04 | 2025-09-20
Biz w/ Tech Epic: IT and Bus. Ownership availability in CMDB | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106017 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: RAPID Compliance Controls in PDSM | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106019 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ITAM- IT Model Management | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0106026 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Impacts to CI/CD from RAPID Controls in PDSM | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106033 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: PPM Financial Rptng Rehoming Solution Impl. | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106052 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Data retention, rptg continuity, discontinue adhoc | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106079 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Observability Platform Modernization | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106091 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26Q1Q2 IF Network - LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0106101 |  |  | Lifecycle Management Epic | Build | E-487734 | E-487734 | 4: L | 2025-06-27 |  | 100% | 2 | 2 |  | 0 | No | 2025-06-02 | 2026-03-16 | 2025-06-27
Biz w/ Tech Epic: Citrix Epic 1 | In Progress | Biz w/ Tech Epic | Platforms Portfolio | 0106215 | 92747 | TS-VL4-ENDUSER-Cirtix Optimization (International) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-07-31 | 2025-09-30
Local Enhancement Epic: Yubikey Rollout - Deployment | Approved | Local Enhancement Epic | Platforms Portfolio | 0106243 |  |  | Local Enhancement Epic | Build | E-500353 | E-500353 | 3: M | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-03-17 | 2025-10-10 | 2025-07-01
Local Enhancement Epic: 2 catalog items inserting duplicate core companies | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106354 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PDSM Integration for Certificate Management | Approved | Local Enhancement Epic | Platforms Portfolio | 0106355 |  |  | Local Enhancement Epic | Launch & Evaluate | E-500254 | E-500254 | 2: S | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-06-27
Lifecycle Management Epic: LAN Replacement 2025 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0106445 |  |  | Lifecycle Management Epic | Build | E-523268 | E-523268 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-01-30 | 2026-04-23
Local Enhancement Epic: HAM Data Cleanup Support | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106457 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26-PF-SEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0106461 |  |  | Lifecycle Management Epic | Build | E-500362 | E-500362 | 4: L | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2026-05-29 | 2025-07-01
Local Enhancement Epic: EU Pathways Expansion to international regions | Completed | Local Enhancement Epic | Platforms Portfolio | 0106468 |  |  | Local Enhancement Epic | Backlog | E-511823 | E-511823 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Feature for PI2 - HAM: Mandatory Attributes | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106470 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HAM Adoption Support | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106471 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Re-architecture RL integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106472 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Citizen Development for ServiceNow | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106474 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Oracle Publisher Onboarding | Approved | Local Enhancement Epic | Platforms Portfolio | 0106475 |  |  | Local Enhancement Epic | Backlog | E-508090 | E-508090 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-04-30 | 2026-05-29
Lifecycle Management Epic: Decom Delegation Web Services App (3536181) | Closed | Lifecycle Management Epic | Platforms Portfolio | 0106519 |  |  | Lifecycle Management Epic | Build | E-500321 | E-500321 | 1: XS | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: Development Demand Request: Prevent Retired Busine | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106534 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXF - Portland, ME BTS - CLEAR FXFI00000005437 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106548 |  |  | Local Enhancement Epic | Assessment & Analysis | E-508018 | E-508018 | 1: XS |  |  |  | 1 | 0 | 1 | 0 | No
Local Enhancement Epic: FXF-Bolingbrook, IL Make-Ready-CLEAR 100012221 | Approved | Local Enhancement Epic | Platforms Portfolio | 0106549 |  |  | Local Enhancement Epic | Launch & Evaluate | E-508013 | E-508013 | 1: XS | 2025-06-27 |  |  | 2 | 0 | 2 | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: FXF - Beaumont,TX BTS Facility - CLEAR 100012269 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106550 |  |  | Local Enhancement Epic | Launch & Evaluate | E-508045 | E-508045 | 1: XS | 2025-06-27 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-06-27
Biz w/ Tech Epic: InfoSec-XSIAM Deployment & Full Operationalization | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0106607 | 7662 | Next-Gen GCCR Threat Detection Engineering & Respo | Biz w/ Tech Epic | Assessment & Analysis | E-502129 | E-502129 | 3: M |  |  |  | 2 | 0 | 1 | 1 | No | 2024-07-22 | 2026-01-30
Biz w/ Tech Epic: Observability Implementation | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0106644 | 9302 | TS-VL3-Observability-Tools Modernization | Biz w/ Tech Epic | Build | E-535572 | E-535572 | 2: S | 2025-10-09 |  |  | 6 | 0 | 3 | 3 | No | 2025-09-29 | 2028-08-21 | 2025-10-09
Local Enhancement Epic: Refactor core location table data in ServiceNow | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106679 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Limitation on Slovakia "VAT Number" field in ECIS | Closed | Local Enhancement Epic | Platforms Portfolio | 0106680 |  |  | Local Enhancement Epic | Build | E-517936 | E-517936 | 1: XS | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-13
Local Enhancement Epic: CNAPP Cloud Security | Approved | Local Enhancement Epic | Platforms Portfolio | 0106689 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528423 | E-528423 | 1: XS | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: New Hardware Implementation | Approved | Local Enhancement Epic | Platforms Portfolio | 0106692 |  |  | Local Enhancement Epic | Build | E-501096 | E-501096 | 1: XS | 2025-06-27 |  |  | 1 | 0 | 1 | 0 | No | 2025-04-25 | 2026-03-30 | 2025-06-27
Local Enhancement Epic: FXF - Valdosta, GA Expansion - CLEAR # 100012206 | Approved | Local Enhancement Epic | Platforms Portfolio | 0106694 |  |  | Local Enhancement Epic | Build | E-508044 | E-508044 | 1: XS | 2025-06-27 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: Separation of Duties - IMAGE Roles - app3531338 | Closed | Local Enhancement Epic | Platforms Portfolio | 0106696 |  |  | Local Enhancement Epic | Done |  |  | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Enable PG In Platform Notifications for HR Agents | Approved | Local Enhancement Epic | Platforms Portfolio | 0106698 |  |  | Local Enhancement Epic | Backlog | E-513915 | E-513915 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: FORGE testing of FedEx Street Vector Tiles - eGIS | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106713 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Feature for PI2 Hardware Asset Need Help Requests | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0106741 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Fully automate the Virtual Agent iReset bot | Approved | Local Enhancement Epic | Platforms Portfolio | 0106742 |  |  | Local Enhancement Epic | Launch & Evaluate | E-520960 | E-520960 | 2: S | 2025-07-07 |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-08-31 | 2025-07-07
Local Enhancement Epic: FXL Portal - FedEx Enterprise maps support | Approved | Local Enhancement Epic | Platforms Portfolio | 0106787 |  |  | Local Enhancement Epic | Build | E-508264 | E-508264 | 3: M | 2025-07-18 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-10-08 | 2025-07-18
Local Enhancement Epic: CPC Phone Logic Realignment | Not Started | Local Enhancement Epic | Platforms Portfolio | 0106836 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Password Reset Strategy - Implementation Support | Closed | Local Enhancement Epic | Platforms Portfolio | 0106838 |  |  | Local Enhancement Epic | Done |  |  | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: CXPC Phone System Migration for Legacy Dispatch | Approved | Local Enhancement Epic | Platforms Portfolio | 0106855 |  |  | Local Enhancement Epic | Build | E-525261 | E-525261 | 2: S | 2025-10-28 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-02-27 | 2025-10-28
Lifecycle Management Epic: IT Room Compliance EU - Wiesbaden Local Initiative | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0106857 |  |  | Lifecycle Management Epic | Backlog | E-520902 | E-520902 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Infrastructure Platform | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0106899 | 107208 | TS-VL3-Platform-POC-Infra DevX Data | Biz w/ Tech Epic | Launch & Evaluate | E-504084 | E-504084 | 3: M | 2025-06-26 |  | 67.25% | 397 | 267 | 129 | 1 | No |  |  | 2025-06-26
Lifecycle Management Epic: Wissous - Refresh FY25 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0106903 |  |  | Lifecycle Management Epic | Build | E-517913 | E-517913 | 3: M | 2026-04-24 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2026-04-24
Lifecycle Management Epic: FY26 Replacement of EOSL VCs | Approved | Lifecycle Management Epic | Platforms Portfolio | 0106913 |  |  | Lifecycle Management Epic | Backlog | E-517921 | E-517921 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-02-24
Biz w/ Tech Epic: DevEx Product Platform | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106961 | 107208 | TS-VL3-Platform-POC-Infra DevX Data | Biz w/ Tech Epic | Build | E-504088 | E-504088 | 3: M | 2025-07-01 |  | 100% | 41 | 41 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Data Platform | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106963 | 107208 | TS-VL3-Platform-POC-Infra DevX Data | Biz w/ Tech Epic | Build | E-504110 | E-504110 | 3: M | 2025-07-01 |  | 100% | 40 | 40 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Engineering Security Solutions FY26 PI 3-5 | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0106980 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Onboard Database Administrator credentials into PA | Approved | Local Enhancement Epic | Platforms Portfolio | 0107028 |  |  | Local Enhancement Epic | Build | E-502206 | E-502206 | 2: S | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No | 2025-04-30 | 2026-03-30 | 2025-09-19
Local Enhancement Epic: Activate and setup ServiceNow Issue Autoresolution | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107033 |  |  | Local Enhancement Epic | Backlog | E-513916 | E-513916 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Life Cycle Events for L&D tasks | Closed | Local Enhancement Epic | Platforms Portfolio | 0107044 |  |  | Local Enhancement Epic | Backlog | E-513917 | E-513917 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Activate auto-Translate Case Descriptions in HR Ag | Closed | Local Enhancement Epic | Platforms Portfolio | 0107049 |  |  | Local Enhancement Epic | Backlog | E-513918 | E-513918 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enable IT Admin for Controlled Feature Releases | Closed | Local Enhancement Epic | Platforms Portfolio | 0107055 |  |  | Local Enhancement Epic | Backlog | E-513919 | E-513919 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Integrate FedEx DocuSign Solution for Digital Sign | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107057 |  |  | Local Enhancement Epic | Backlog | E-513920 | E-513920 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enable Quick Emoji Survey for Case Satisfaction | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107058 |  |  | Local Enhancement Epic | Backlog | E-513921 | E-513921 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Task creation in Purple Gateway upon Workday Hire | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107059 |  |  | Local Enhancement Epic | Backlog | E-513922 | E-513922 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Welcome email to new hire on day 1 | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107061 |  |  | Local Enhancement Epic | Backlog | E-513923 | E-513923 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Onboarding tasks to be accessible by HR&PSSC | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107062 |  |  | Local Enhancement Epic | Backlog | E-513924 | E-513924 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Archive and Purge HR Cases | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107063 |  |  | Local Enhancement Epic | Backlog | E-513925 | E-513925 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: NHDM - Toggle on/off onboarding task | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107064 |  |  | Local Enhancement Epic | Backlog | E-513926 | E-513926 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Additional attributes in EDM | Closed | Local Enhancement Epic | Platforms Portfolio | 0107065 |  |  | Local Enhancement Epic | Backlog | E-520963 | E-520963 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: Add [Effective date] field to ‘Create New Employee | Closed | Local Enhancement Epic | Platforms Portfolio | 0107066 |  |  | Local Enhancement Epic | Backlog | E-517942 | E-517942 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: CMS Report Enhancement | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107068 |  |  | Local Enhancement Epic | Backlog | E-517943 | E-517943 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EIAM Attack Surface Reporting | Closed | Local Enhancement Epic | Platforms Portfolio | 0107114 |  |  | Local Enhancement Epic | Build | E-507703 | E-507703 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Lifecycle Management Epic: CY25 PI-3_Address EFS Defect Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107151 |  |  | Lifecycle Management Epic | Build | E-511674 | E-511674 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: CY25 PI-3_Customer EFS Defect Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107152 |  |  | Lifecycle Management Epic | Build | E-511644 | E-511644 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: METL and Direct Connect Consultation/Execution | Approved | Local Enhancement Epic | Platforms Portfolio | 0107196 |  |  | Local Enhancement Epic | Backlog | E-518434 | E-518434 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-10-08
Local Enhancement Epic: EDM - Display Requestor in the Created By Column | Closed | Local Enhancement Epic | Platforms Portfolio | 0107199 |  |  | Local Enhancement Epic | Backlog | E-513927 | E-513927 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI-3_Geography EFS Defect Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107200 |  |  | Lifecycle Management Epic | Build | E-511633 | E-511633 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: CY25 PI-3_Product EFS Defect Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107201 |  |  | Lifecycle Management Epic | Build | E-511667 | E-511667 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: OSAT Edge - FY26 Edge LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107202 |  |  | Lifecycle Management Epic | Build | E-517946 | E-517946 | 1: XS | 2025-08-21 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-21
Lifecycle Management Epic: CY25 PI-3_GeoPolitical EFS Defect Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107203 |  |  | Lifecycle Management Epic | Build | E-511649 | E-511649 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: CY25 PI-3_Location EFS Defect Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107204 |  |  | Lifecycle Management Epic | Build | E-511656 | E-511656 | 1: XS | 2025-07-01 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: Accenture AZURE remediation AZURE Pod | Approved | Local Enhancement Epic | Platforms Portfolio | 0107208 |  |  | Local Enhancement Epic | Build | E-517991 | E-517991 | 2: S | 2026-03-23 |  | 100% | 1 | 1 |  | 0 | No | 2025-06-27 | 2026-03-30 | 2026-03-23
Local Enhancement Epic: Improve ServiceNow DB performance and scalability | Not Started | Local Enhancement Epic | Platforms Portfolio | 0107209 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Assignment group auto-routing for Pay Issue - Miss | Closed | Local Enhancement Epic | Platforms Portfolio | 0107210 |  |  | Local Enhancement Epic | Backlog | E-517960 | E-517960 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add Create Incident option for Timekeeping - Time | Closed | Local Enhancement Epic | Platforms Portfolio | 0107211 |  |  | Local Enhancement Epic | Backlog | E-517956 | E-517956 | 2: S |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: Move EBS Payroll Systems Support (HRPay) service c | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107212 |  |  | Local Enhancement Epic | Backlog | E-517951 | E-517951 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: EIAM Cyber Resiliency - Failover Execution FY26H1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107213 |  |  | Lifecycle Management Epic | Build | E-507777 | E-507777 | 2: S | 2025-07-09 |  |  | 2 | 0 | 2 | 0 | No | 2025-06-02 | 2026-03-30 | 2025-07-09
Local Enhancement Epic: Update Virtual Agent search algorithm and improve | Approved | Local Enhancement Epic | Platforms Portfolio | 0107214 |  |  | Local Enhancement Epic | Backlog | E-513928 | E-513928 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Track Virtual Agent usage analytics to drive impro | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107215 |  |  | Local Enhancement Epic | Backlog | E-513929 | E-513929 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Roles & Entitlements Strategy CY25H2 | Approved | Local Enhancement Epic | Platforms Portfolio | 0107222 |  |  | Local Enhancement Epic | Build | E-507701 | E-507701 | 2: S | 2025-09-19 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-03-30 | 2025-09-19
Local Enhancement Epic: Accenture AZURE remediation PMO Pod | Approved | Local Enhancement Epic | Platforms Portfolio | 0107274 |  |  | Local Enhancement Epic | Backlog | E-517966 | E-517966 | 2: S |  |  |  | 2 | 0 |  | 2 | No | 2025-06-12 | 2026-03-30
Local Enhancement Epic: Properties FXE - 5025 Tuggle Road MEM TN | Not Started | Local Enhancement Epic | Platforms Portfolio | 0107286 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EDM Enhancement - EDM App Manager UX update | Closed | Local Enhancement Epic | Platforms Portfolio | 0107287 |  |  | Local Enhancement Epic | Launch & Evaluate | E-518070 | E-518070 | 2: S | 2025-06-26 |  |  | 1 | 0 |  | 1 | No |  |  | 2025-06-26
Lifecycle Management Epic: Active Directory Domain Controller Rebuild PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107295 |  |  | Lifecycle Management Epic | Done | E-507465 | E-507465 | 1: XS | 2025-06-27 | 2025-09-03 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27 | 2025-09-03
Lifecycle Management Epic: FY26 Cargo Screening Equipment Lifecycle Program | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107324 |  |  | Lifecycle Management Epic | Build | E-517923 | E-517923 | 2: S | 2025-09-26 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-12 | 2026-05-29 | 2025-09-26
Local Enhancement Epic: Secrets Modernization (AKV) - Oversight & Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0107330 |  |  | Local Enhancement Epic | Build | E-518466 | E-518466 | 2: S | 2025-09-19 |  | 50% | 2 | 1 |  | 1 | No | 2025-06-02 | 2026-03-30 | 2025-09-19
Lifecycle Management Epic: CY25 H2_IMAGE (IIQ) Lifecycle Updates | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107331 |  |  | Lifecycle Management Epic | Build | E-511822 | E-511822 | 2: S | 2025-07-15 |  |  | 1 | 0 | 1 | 0 | No | 2025-05-14 | 2026-03-30 | 2025-07-15
Lifecycle Management Epic: FY26H1_EIAM Trellix PCI Audit | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107332 |  |  | Lifecycle Management Epic | Build | E-511800 | E-511800 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: Passwordless Pre-Release CY25H2 | Approved | Local Enhancement Epic | Platforms Portfolio | 0107336 |  |  | Local Enhancement Epic | Build | E-511856 | E-511856 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No | 2025-05-26 | 2025-10-10 | 2025-07-15
Lifecycle Management Epic: EIAM Audit Support CY25PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107338 |  |  | Lifecycle Management Epic | Build | E-511784 | E-511784 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Lifecycle Management Epic: Defect-InfoSec-XM ART- CY25 PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107339 |  |  | Lifecycle Management Epic | Build | E-511794 | E-511794 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Lifecycle Management Epic: InfoSec - EIAM FIRST Support - CY25PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107340 |  |  | Lifecycle Management Epic | Build | E-511801 | E-511801 | 2: S | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: InfoSec - Public Cloud Transformation – Directory | Approved | Local Enhancement Epic | Platforms Portfolio | 0107344 |  |  | Local Enhancement Epic | Build | E-511799 | E-511799 | 2: S | 2025-07-15 |  | 100% | 2 | 2 |  | 0 | No | 2025-05-15 | 2025-12-31 | 2025-07-15
Local Enhancement Epic: ITAM- IT Model Management | Approved | Local Enhancement Epic | Platforms Portfolio | 0107345 |  |  | Local Enhancement Epic | Backlog | E-513376 | E-513376 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-08-31
Lifecycle Management Epic: Patching-PF-EFS-Geopolitical-GpEFS-PLG ART-CY25 PI | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107349 |  |  | Lifecycle Management Epic | Build | E-512608 | E-512608 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: InfoSec - Crowdstrike Falcon Exposure Mgmt | Approved | Local Enhancement Epic | Platforms Portfolio | 0107367 |  |  | Local Enhancement Epic | Build | E-521532 | E-521532 | 1: XS | 2025-08-27 |  | 16.67% | 6 | 1 | 4 | 1 | No | 2024-07-22 | 2027-01-13 | 2025-08-27
Local Enhancement Epic: InfoSec BC & DR Resiliency Compliance | Closed | Local Enhancement Epic | Platforms Portfolio | 0107410 |  |  | Local Enhancement Epic | Build | E-508674 | E-508674 | 2: S | 2025-06-27 |  | 50% | 2 | 1 | 1 | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: Rename two US HR Onboarding services | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107433 |  |  | Local Enhancement Epic | Backlog | E-520958 | E-520958 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Defect-Network Management Team - FY25 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107435 |  |  | Lifecycle Management Epic | Build | E-516420 | E-516420 | 1: XS | 2025-08-14 |  | 66.67% | 3 | 2 | 1 | 0 | No | 2024-07-22 | 2028-02-18 | 2025-08-14
Local Enhancement Epic: CAnceled:AKS | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107456 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Tooling-PF-EFS-Unified Systems-UST ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107470 |  |  | Lifecycle Management Epic | Build | E-512637 | E-512637 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Shipment-SEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107473 |  |  | Lifecycle Management Epic | Build | E-512636 | E-512636 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Geopolitical-GpEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107474 |  |  | Lifecycle Management Epic | Build | E-512635 | E-512635 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107476 |  |  | Lifecycle Management Epic | Build | E-512633 | E-512633 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Product-PEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107478 |  |  | Lifecycle Management Epic | Build | E-512639 | E-512639 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Geography-GEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107479 |  |  | Lifecycle Management Epic | Build | E-512638 | E-512638 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Customer-CEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107480 |  |  | Lifecycle Management Epic | Build | E-512634 | E-512634 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Tooling-PF-EFS-Address-AEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107488 |  |  | Lifecycle Management Epic | Build | E-512632 | E-512632 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Unified Systems-UST ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107489 |  |  | Lifecycle Management Epic | Build | E-512631 | E-512631 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Shipment-SEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107492 |  |  | Lifecycle Management Epic | Build | E-512629 | E-512629 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Geopolitical-GpEFS-PLG ART-CY25 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107496 |  |  | Lifecycle Management Epic | Build | E-512625 | E-512625 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Location-LEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107499 |  |  | Lifecycle Management Epic | Build | E-512630 | E-512630 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Product-PEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107505 |  |  | Lifecycle Management Epic | Build | E-512628 | E-512628 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Geography-GEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107512 |  |  | Lifecycle Management Epic | Build | E-512627 | E-512627 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Customer-CEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107513 |  |  | Lifecycle Management Epic | Build | E-512626 | E-512626 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Compliance-PF-EFS-Address-AEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107514 |  |  | Lifecycle Management Epic | Build | E-512624 | E-512624 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: InfoSec-Next-Gen FTI - Strategy | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107515 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: InfoSec-Red Team Enhancements | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0107516 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: InfoSec-Cloud Incident Response | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0107517 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: InfoSec-Next-Gen FTI Strategy | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0107518 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI 03 OT/IoT Governance | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107519 |  |  | Lifecycle Management Epic | Done | E-511516 | E-511516 | 2: S | 2025-07-15 | 2025-09-05 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15 | 2025-09-05
Biz w/ Tech Epic: InfoSec-Threat Detection Engineering OT/IOT | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0107520 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: OT/IoT Engineering_FY26 PI 3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107521 |  |  | Lifecycle Management Epic | Done | E-511514 | E-511514 | 3: M | 2025-07-15 | 2025-09-05 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15 | 2025-09-05
Lifecycle Management Epic: Upgrade-PF-EFS-Unified Systems-UST ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107522 |  |  | Lifecycle Management Epic | Build | E-512622 | E-512622 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Shipment-SEFS ART-CY25 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107523 |  |  | Lifecycle Management Epic | Build | E-512621 | E-512621 | 1: XS | 2025-06-27 |  |  | 1 | 0 |  | 1 | No | 2026-04-20 | 2026-04-20 | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Geopolitical-GpEFS-PLGART-CY25 PI-3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107524 |  |  | Lifecycle Management Epic | Backlog | E-512620 | E-512620 | 1: XS | 2025-06-27 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Location-LEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107525 |  |  | Lifecycle Management Epic | Build | E-512619 | E-512619 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Product-PEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107526 |  |  | Lifecycle Management Epic | Build | E-512618 | E-512618 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Geography-GEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107527 |  |  | Lifecycle Management Epic | Build | E-512617 | E-512617 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Customer-CEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107528 |  |  | Lifecycle Management Epic | Build | E-512616 | E-512616 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Upgrade-PF-EFS-Address-AEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107529 |  |  | Lifecycle Management Epic | Build | E-512615 | E-512615 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Patching-PF-EFS-Unified Systems-UST ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107533 |  |  | Lifecycle Management Epic | Build | E-512614 | E-512614 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Patching-PF-EFS-Shipment-SEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107534 |  |  | Lifecycle Management Epic | Build | E-512613 | E-512613 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Patching-PF-EFS-Location-LEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107535 |  |  | Lifecycle Management Epic | Build | E-512612 | E-512612 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Patching-PF-EFS-Product-PEFS-PLG ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107536 |  |  | Lifecycle Management Epic | Build | E-512611 | E-512611 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Patching-PF-EFS-Geography-GEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107537 |  |  | Lifecycle Management Epic | Build | E-512610 | E-512610 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Lifecycle Management Epic: Patching-PF-EFS-Customer-CEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107538 |  |  | Lifecycle Management Epic | Build | E-512609 | E-512609 | 1: XS | 2025-06-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: Office Reduction Program - HQ AMS closure | Not Started | Local Enhancement Epic | Platforms Portfolio | 0107544 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Deactivate HR Case Template: Erasure of Personal D | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107546 |  |  | Local Enhancement Epic | Backlog | E-520956 | E-520956 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Compliance/L&R/Audits – GNE team - CY25 PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107556 |  |  | Lifecycle Management Epic | Build | E-520916 | E-520916 | 1: XS | 2025-09-04 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-04
Lifecycle Management Epic: InfoSec - LCM - Windows LAPS Update - CY25 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107557 |  |  | Lifecycle Management Epic | Build | E-512174 | E-512174 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No | 2025-05-26 | 2025-10-24 | 2025-07-15
Lifecycle Management Epic: InfoSec-LCM-EIAM-Vulnerability-Management-CY25PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107558 |  |  | Lifecycle Management Epic | Build | E-512173 | E-512173 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: DSAR Data Deletion Process Automation | Completed | Local Enhancement Epic | Platforms Portfolio | 0107560 |  |  | Local Enhancement Epic | Done | E-514952 | E-514952 | 4: L | 2025-06-27 | 2025-06-27 |  | 2 | 0 | 1 | 1 | No |  |  | 2025-06-27 | 2025-06-27
Lifecycle Management Epic: New Vendor Location TP Alexandria CE Call Center | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0107589 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: New Vendor Location Telus Morocco CE Call Center | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0107592 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 PI 03 Endpoint Trellix | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107593 |  |  | Lifecycle Management Epic | Build | E-512190 | E-512190 | 2: S | 2025-07-15 |  | 50% | 2 | 1 | 1 | 0 | No |  |  | 2025-07-15
Lifecycle Management Epic: Standard Accounting Bridge Tool Mod_CY25 PI3 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107594 |  |  | Lifecycle Management Epic | Backlog | E-520984 | E-520984 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Credit Card Obfuscation Mod_CY25 PI3 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107596 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Enterprise Fraud Web Services Mod_CY25 PI3 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107597 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Customer Identity Management Ops Tool Mod_CY25 PI3 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107598 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Patching-PF-EFS-Address-AEFS ART-CY25 PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107599 |  |  | Lifecycle Management Epic | Build | E-518065 | E-518065 | 1: XS | 2025-09-09 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-09
Lifecycle Management Epic: Patching – Global Network Engineering – CY25 PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107621 |  |  | Lifecycle Management Epic | Build | E-518474 | E-518474 | 1: XS | 2025-08-12 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-12
Lifecycle Management Epic: Tooling – Network Management Team – CY25 PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107624 |  |  | Lifecycle Management Epic | Build | E-518468 | E-518468 | 1: XS | 2025-08-12 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-12
Local Enhancement Epic: Facility - 200 N. Sepulveda, El Segundo, CA (LE) | Not Started | Local Enhancement Epic | Platforms Portfolio | 0107641 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Facility - 900 7th St NW, Washington, DC (LE) | Approved | Local Enhancement Epic | Platforms Portfolio | 0107642 |  |  | Local Enhancement Epic | Build | E-536553 | E-536553 | 2: S | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-11-10 | 2025-11-06
Local Enhancement Epic: Facility-9311 San Pedro, San Antonio, TX (LE) | Approved | Local Enhancement Epic | Platforms Portfolio | 0107643 |  |  | Local Enhancement Epic | Build | E-536551 | E-536551 | 3: M | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2026-04-10 | 2025-11-06
Local Enhancement Epic: POC to integrate DW OIP with Neubird Hawkeye GenAI | Approved | Local Enhancement Epic | Platforms Portfolio | 0107644 |  |  | Local Enhancement Epic | Backlog | E-520979 | E-520979 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec-Global Segmentation Program | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107651 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec - LCM - CY25PI03 - PAM | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107654 |  |  | Lifecycle Management Epic | Build | E-512528 | E-512528 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Lifecycle Management Epic: InfoSec-LCM-AoA-CY25PI03-SSO Maint/Optimization | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107657 |  |  | Lifecycle Management Epic | Build | E-516440 | E-516440 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: FY26 PI 03 AD Domain Feasibility Study | Closed | Local Enhancement Epic | Platforms Portfolio | 0107658 |  |  | Local Enhancement Epic | Build | E-512727 | E-512727 | 2: S | 2025-07-15 |  |  | 2 | 0 | 1 | 1 | No |  |  | 2025-07-15
Local Enhancement Epic: App Onboarding Role Cleanup | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107667 |  |  | Local Enhancement Epic | Build | E-523631 | E-523631 | 1: XS | 2025-10-09 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-09
Local Enhancement Epic: [UDS-NRT] - Platforms | Approved | Local Enhancement Epic | Platforms Portfolio | 0107244 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549448 | E-549448 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Canceled: Azure Cognitive Services | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0107688 | 88003 | Azure Usage Optimization | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Canceled:Azure Cognitive Services | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107689 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: FCP Blueprint/Operator | Not Started | Local Enhancement Epic | Platforms Portfolio | 0107690 | 114672 | TS-VL3-HybridCloud-OptimizeDelphixUnlimitedAgreeme | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FCP Landing Zone | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0107698 | 96196 | TS-VL3-APILM-Apigee To Azure APIM | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FCP AKS Process Updates ( Cluster Upgrade + Backup | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0107699 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FCP AKS DMZ | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0107700 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Global ACR Strategy:Cache enabling + Keyvault RBAC | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0107701 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Canceled: Traefik Upgrade v2 (v3 Stretch) KTLO | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107702 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CANCELED:FY25_P3_LCM_PCF Upgrades + Cert Rotations | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107703 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CANCELED: Decommission Thunder Application | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107705 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CANCELED: GIT Repo Bootstrapping by language | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107706 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: ServiceMax Integration to Jitterbit cloud | Approved | Local Enhancement Epic | Platforms Portfolio | 0107711 |  |  | Local Enhancement Epic | Build | E-520924 | E-520924 | 2: S | 2025-10-27 |  | 100% | 1 | 1 |  | 0 | No | 2025-06-27 | 2026-03-30 | 2025-10-27
Lifecycle Management Epic: FY26 PI 03 Endpoint Crowdstrike | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107712 |  |  | Lifecycle Management Epic | Done | E-512723 | E-512723 | 2: S | 2025-07-15 | 2025-09-05 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15 | 2025-09-05
Local Enhancement Epic: Facility-Marsh-1000 Ridgeway 4, 5, 6 Floor closure | Approved | Local Enhancement Epic | Platforms Portfolio | 0107713 |  |  | Local Enhancement Epic | Build | E-537200 | E-537200 | 5: XL | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-06
Lifecycle Management Epic: Infosec-LCM-PI-03-Firewalls | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107730 |  |  | Lifecycle Management Epic | Build | E-513343 | E-513343 | 2: S | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-19
Local Enhancement Epic: InfoSec BCDR Resiliency Protection MVC | Closed | Local Enhancement Epic | Platforms Portfolio | 0107756 |  |  | Local Enhancement Epic | Build | E-516168 | E-516168 | 3: M | 2025-07-15 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: Guided Self Service Total Rewards | Closed | Local Enhancement Epic | Platforms Portfolio | 0107761 |  |  | Local Enhancement Epic | Backlog | E-520959 | E-520959 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Upgrades - Global Network Engineering – CY25 PI03 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107762 |  |  | Lifecycle Management Epic | Build | E-518481 | E-518481 | 1: XS | 2025-08-12 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-12
Local Enhancement Epic: Customize Organization Widget to enable HR View As | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107763 |  |  | Local Enhancement Epic | Backlog | E-520961 | E-520961 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Total Rewards Taxonomy | Approved | Local Enhancement Epic | Platforms Portfolio | 0107764 |  |  | Local Enhancement Epic | Backlog | E-520957 | E-520957 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Enable Page Template Setup for Content Authoring | Approved | Local Enhancement Epic | Platforms Portfolio | 0107765 |  |  | Local Enhancement Epic | Backlog | E-520962 | E-520962 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Purple Gateway HRSD Guided Self Service | Approved | Local Enhancement Epic | Platforms Portfolio | 0107767 |  |  | Local Enhancement Epic | Backlog | E-520955 | E-520955 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Record producer for requesting boost and synonym d | Rejected | Local Enhancement Epic | Platforms Portfolio | 0107768 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Restrict Case Visibility for Tier 2 and Tier 3 HR | Closed | Local Enhancement Epic | Platforms Portfolio | 0107769 |  |  | Local Enhancement Epic | Backlog | E-520954 | E-520954 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Local Enhancement Epic: Customize Organization Widget to enable HR View As | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107770 |  |  | Local Enhancement Epic | Backlog | E-520953 | E-520953 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Rollout of Dynatrace tool across Enterprise | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0107776 | 9302 | TS-VL3-Observability-Tools Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-477052 | E-477052 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-01-14 | 2027-02-25
Biz w/ Tech Epic: FCP Workshops | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0107778 | 114672 | TS-VL3-HybridCloud-OptimizeDelphixUnlimitedAgreeme | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Canceled:Storage Accounts and Key Vaults pendp | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0107780 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec-Monitor Systems/Networks for Threats | Completed | Lifecycle Management Epic | Platforms Portfolio | 0107781 |  |  | Lifecycle Management Epic | Done | E-514854 | E-514854 | 3: M | 2025-06-27 | 2025-06-27 | 25% | 44 | 11 | 19 | 14 | No |  |  | 2025-06-27 | 2025-06-27
Lifecycle Management Epic: InfoSec - Operations Analytic Sys Support FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107783 |  |  | Lifecycle Management Epic | Build | E-513381 | E-513381 | 3: M | 2025-06-27 |  | 33.33% | 3 | 1 | 1 | 1 | No | 2025-06-05 | 2026-06-01 | 2025-06-27
Biz w/ Tech Epic: eContact Retirement and Mastering of Contacts | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0107785 | 97425 | eContact Retirement and Mastering of Contacts | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-05-12 | 2027-03-12
Lifecycle Management Epic: Infosec - LCM - Attack Surface Analytics CY24PI3 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107788 |  |  | Lifecycle Management Epic | Build | E-513374 | E-513374 | 3: M | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: SEFS View Enhancements | Closed | Local Enhancement Epic | Platforms Portfolio | 0107789 |  |  | Local Enhancement Epic | Build | E-520988 | E-520988 | 1: XS | 2025-07-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-25
Lifecycle Management Epic: InfoSec-Operation Support-Kafka Cluster FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107790 |  |  | Lifecycle Management Epic | Build | E-513392 | E-513392 | 3: M | 2025-06-27 |  | 33.33% | 3 | 1 |  | 2 | No | 2025-06-05 | 2026-06-01 | 2025-06-27
Lifecycle Management Epic: InfoSec-Operation Support Existing Script FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107795 |  |  | Lifecycle Management Epic | Build | E-513402 | E-513402 | 3: M | 2025-06-27 |  | 33.33% | 3 | 1 |  | 2 | No | 2025-06-05 | 2026-06-01 | 2025-06-27
Lifecycle Management Epic: InfoSec - Operational Support for Anomali FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107796 |  |  | Lifecycle Management Epic | Build | E-513559 | E-513559 | 3: M | 2025-06-27 |  | 33.33% | 3 | 1 |  | 2 | No | 2025-06-05 | 2026-06-01 | 2025-06-27
Lifecycle Management Epic: InfoSec-Operation Support-Data Source Log FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107797 |  |  | Lifecycle Management Epic | Build | E-513390 | E-513390 | 3: M | 2025-06-27 |  | 33.33% | 3 | 1 |  | 2 | No | 2025-06-05 | 2026-06-01 | 2025-06-27
Lifecycle Management Epic: InfoSec - Operation Support-Relay Servers FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107798 |  |  | Lifecycle Management Epic | Build | E-513385 | E-513385 | 3: M | 2025-06-26 |  | 33.33% | 3 | 1 | 1 | 1 | No | 2025-06-05 | 2026-06-01 | 2025-06-26
Lifecycle Management Epic: Infosec Data & Technology Risk Management_CY25 PI3 | Rejected | Lifecycle Management Epic | Platforms Portfolio | 0107799 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_Infosec_C3InvestCaseMgmt_Production Support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0107800 |  |  | Lifecycle Management Epic | Backlog | E-522584 | E-522584 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Record Producers for Guided Self Service, Boost, S | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107802 |  |  | Local Enhancement Epic | Backlog | E-520951 | E-520951 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Employee Verification Letter - Phase 2 | Closed | Local Enhancement Epic | Platforms Portfolio | 0107803 |  |  | Local Enhancement Epic | Backlog | E-520949 | E-520949 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Disable users from selecting invalid employees in | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107804 |  |  | Local Enhancement Epic | Backlog | E-520950 | E-520950 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Purple Gateway HRSD Operational Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107806 |  |  | Local Enhancement Epic | Backlog | E-520933 | E-520933 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Expanding HR Data Sync from Workday to ServiceNow | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107807 |  |  | Local Enhancement Epic | Backlog | E-520948 | E-520948 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ebonding and API Integration for Incident Creation | Approved | Local Enhancement Epic | Platforms Portfolio | 0107809 |  |  | Local Enhancement Epic | Backlog | E-519537 | E-519537 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: Open EDM for emp - Able to upload/view/download | Approved | Local Enhancement Epic | Platforms Portfolio | 0107828 |  |  | Local Enhancement Epic | Backlog | E-520946 | E-520946 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Contract Testing environment setup and config | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0107859 | 107791 | Adoption of PactFlow as Contract Testing standard | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: InfoSec - Cyberdata Strategy Epic | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0107484 | 104315 | InfoSec - Cyberdata Strategy | Biz w/ Tech Epic | Build | E-469010 | E-469010 | 4: L | 2025-08-12 |  | 33.33% | 9 | 3 | 4 | 2 | No | 2025-08-01 | 2029-06-01 | 2025-08-12
Local Enhancement Epic: InfoSec - Public Cloud Transformation - PIM | Closed | Local Enhancement Epic | Platforms Portfolio | 0107902 |  |  | Local Enhancement Epic | Build | E-518487 | E-518487 | 2: S | 2025-07-15 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-07-15
Local Enhancement Epic: Singapore Internet Optimization | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0107913 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec Cyber Vault Improvements/Implementations | Closed | Local Enhancement Epic | Platforms Portfolio | 0107920 |  |  | Local Enhancement Epic | Build | E-514467 | E-514467 | 2: S | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Lifecycle Management Epic: InfoSec Cyber Recovery Vault Lifecycle Mgt CY25PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107921 |  |  | Lifecycle Management Epic | Build | E-514491 | E-514491 | 4: L | 2025-08-14 |  | 33.33% | 3 | 1 |  | 2 | No | 2025-06-02 | 2026-05-29 | 2025-08-14
Lifecycle Management Epic: Infosec Data & Technology Risk Management_FY25 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0107938 |  |  | Lifecycle Management Epic | Build | E-513798 | E-513798 | 1: XS | 2025-09-19 |  |  | 3 | 0 | 2 | 1 | No | 2025-05-23 | 2026-05-29 | 2025-09-19
Local Enhancement Epic: Lcl Dem-Mktg-PF-EFS-Product-PEFS-PLG-CY25 PI3&PI4 | Closed | Local Enhancement Epic | Platforms Portfolio | 0108047 |  |  | Local Enhancement Epic | Build | E-522722 | E-522722 | 1: XS | 2025-08-08 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-08
Local Enhancement Epic: InfoSec – Proofpoint EFD renewal | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108051 |  |  | Local Enhancement Epic | Backlog | E-527331 | E-527331 | 3: M | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: Cyber Resiliency Analytics & Automation PI03 | Closed | Local Enhancement Epic | Platforms Portfolio | 0108056 |  |  | Local Enhancement Epic | Build | E-515861 | E-515861 | 1: XS | 2025-07-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-15
Local Enhancement Epic: Update HR Criteria on Foreign National VOE Service | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108058 |  |  | Local Enhancement Epic | Backlog | E-520945 | E-520945 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automate Accessibility Feedback Collection and Rou | Approved | Local Enhancement Epic | Platforms Portfolio | 0108059 |  |  | Local Enhancement Epic | Backlog | E-520944 | E-520944 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: ADP/Ipay Access Issue HR Service Updates | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108060 |  |  | Local Enhancement Epic | Backlog | E-520935 | E-520935 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CANCELED: IaaS Infrastructure TF plan (Blueprint) | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0108064 | 88003 | Azure Usage Optimization | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec-Forensics Investigation case management ri | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108078 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec-Red Team Enhancements | Not Started | Local Enhancement Epic | Platforms Portfolio | 0108079 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_InfoSec_Threat Detect Eng_Production Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0108082 |  |  | Lifecycle Management Epic | Build | E-522586 | E-522586 | 2: S | 2025-08-21 |  | 33.33% | 3 | 1 | 1 | 1 | No | 2024-07-22 | 2026-03-13 | 2025-08-21
Local Enhancement Epic: InfoSec-Next-Gen FTI strategy | Approved | Local Enhancement Epic | Platforms Portfolio | 0108088 |  |  | Local Enhancement Epic | Build | E-523771 | E-523771 | 3: M | 2025-09-10 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-12-31 | 2025-09-10
Biz w/ Tech Epic: Data Management Strategy, Metrics, and Reporting | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0108104 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Architecture Modernization Platforms (AMP) KTLO | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0108105 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DELETE - FCP GitHub; duplicate | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0108106 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Global IaaS Strategy | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0108173 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Canceled: Global IaaS Security and Compliance | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108174 |  |  | Local Enhancement Epic | Assessment & Analysis | E-477044 | E-477044 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: F5 Load Balancing | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108207 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec - Access Review Enhancements | Approved | Local Enhancement Epic | Platforms Portfolio | 0108256 |  |  | Local Enhancement Epic | Backlog | E-520929 | E-520929 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-21 | 2026-02-09
Biz w/ Tech Epic: WS10 - One Italy Hub footprint - platform | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0108288 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26Q3Q4 IF Network - LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0108312 |  |  | Lifecycle Management Epic | Build | E-497883 | E-497883 | 4: L | 2025-06-26 |  | 50% | 2 | 1 | 1 | 0 | No | 2025-12-01 | 2026-03-30 | 2025-06-26
Local Enhancement Epic: CE facility in Gurgaon | Approved | Local Enhancement Epic | Platforms Portfolio | 0108325 |  |  | Local Enhancement Epic | Backlog | E-518411 | E-518411 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-12 | 2026-03-30
Local Enhancement Epic: Case automated reminder email & due date | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108361 |  |  | Local Enhancement Epic | Backlog | E-520932 | E-520932 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Cisco ISE Design Re-architecture | Approved | Local Enhancement Epic | Platforms Portfolio | 0108368 |  |  | Local Enhancement Epic | Build | E-522866 | E-522866 | 3: M | 2025-09-19 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-10-31 | 2025-09-19
Local Enhancement Epic: Develop Network Management Standards | Not Started | Local Enhancement Epic | Platforms Portfolio | 0108369 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Fault Monitoring Tool Replacement (NetCure) | Approved | Lifecycle Management Epic | Platforms Portfolio | 0108370 |  |  | Lifecycle Management Epic | Backlog | E-519641 | E-519641 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-06-20 | 2026-03-30
Local Enhancement Epic: Upgrade Digital Signage at FXG field sites | Approved | Local Enhancement Epic | Platforms Portfolio | 0108371 |  |  | Local Enhancement Epic | Build | E-555419 | E-555419 | 1: XS | 2026-04-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-09 | 2026-04-15 | 2026-04-23
Local Enhancement Epic: [UDS-TPEIP] - Platforms Portfolio | Approved | Local Enhancement Epic | Platforms Portfolio | 0108373 |  |  | Local Enhancement Epic | Launch & Evaluate | E-519645 | E-519645 | 4: L | 2025-06-26 |  |  | 1 | 0 |  | 1 | No |  |  | 2025-06-26
Local Enhancement Epic: Migration of South Africa NAP | Approved | Local Enhancement Epic | Platforms Portfolio | 0108374 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554640 | E-554640 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Facility Set-Up at Ahmedabad | Approved | Local Enhancement Epic | Platforms Portfolio | 0108381 |  |  | Local Enhancement Epic | Backlog | E-520987 | E-520987 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2026-03-30
Local Enhancement Epic: Integrate Dataworks Application with eGPS API | Not Started | Local Enhancement Epic | Platforms Portfolio | 0108401 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Integrate Dataworks application with eGPS API | Not Started | Local Enhancement Epic | Platforms Portfolio | 0108403 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Global Address Service AstraDB | Approved | Local Enhancement Epic | Platforms Portfolio | 0108439 |  |  | Local Enhancement Epic | Build | E-519224 | E-519224 | 2: S | 2025-10-29 |  |  | 2 | 0 | 2 | 0 | No | 2025-06-17 | 2026-03-16 | 2025-10-29
Local Enhancement Epic: Integrate DW Webhooks Application with eGPS API | Approved | Local Enhancement Epic | Platforms Portfolio | 0108444 |  |  | Local Enhancement Epic | Launch & Evaluate | E-519506 | E-519506 | 3: M | 2025-06-26 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-12-31 | 2025-06-26
Local Enhancement Epic: Optiv Penetration Testing 2.0 | Approved | Local Enhancement Epic | Platforms Portfolio | 0108475 |  |  | Local Enhancement Epic | Build | E-521719 | E-521719 | 3: M | 2025-07-21 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-04 | 2026-03-30 | 2025-07-21
Lifecycle Management Epic: FY26 IBMi LifeCycle Clear | Approved | Lifecycle Management Epic | Platforms Portfolio | 0108476 |  |  | Lifecycle Management Epic | Build | E-520978 | E-520978 | 2: S | 2026-01-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-03-31 | 2026-01-06
Local Enhancement Epic: Enterprise User Security Remediation | Approved | Local Enhancement Epic | Platforms Portfolio | 0108482 |  |  | Local Enhancement Epic | Build | E-520914 | E-520914 | 1: XS | 2025-09-19 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22 | 2025-09-19
Local Enhancement Epic: Managers and HR Field Agents to Create Cases | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108483 |  |  | Local Enhancement Epic | Backlog | E-520930 | E-520930 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Software Decommission Process | Approved | Local Enhancement Epic | Platforms Portfolio | 0108484 |  |  | Local Enhancement Epic | Build | E-567484 | E-567484 | 4: L | 2026-03-20 |  |  | 1 | 0 | 1 | 0 | No | 2026-02-09 | 2026-06-30 | 2026-03-20
Local Enhancement Epic: Workday Learning HR Service Updates | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108485 |  |  | Local Enhancement Epic | Backlog | E-520928 | E-520928 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TechArch WTC Pre-UTE Consolidation 20-111 FY26-PI1 | In Progress | Local Enhancement Epic | Platforms Portfolio | 0108573 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-14 | 2026-01-30
Biz w/ Tech Epic: NextGen PAM Planning, Implementation, & Migration | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0108649 | 88193 | TS-VL3-Security-PAM | Biz w/ Tech Epic | Assessment & Analysis | E-518675 | E-518675 | 4: L |  |  |  | 2 | 0 | 1 | 1 | No | 2025-09-30 | 2027-05-21
Local Enhancement Epic: BLR AISATS logistic park facility | Approved | Local Enhancement Epic | Platforms Portfolio | 0108653 |  |  | Local Enhancement Epic | Build | E-520981 | E-520981 | 3: M | 2025-12-15 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-12-02 | 2025-12-15
Biz w/ Tech Epic: FCP: Regional Observability Strategy | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0108694 | 9302 | TS-VL3-Observability-Tools Modernization | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: PCI Scoping Process | Not Started | Local Enhancement Epic | Platforms Portfolio | 0108707 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY_26_PI3_InfoSec_LCM_TenableUpgrades | Approved | Lifecycle Management Epic | Platforms Portfolio | 0108749 |  |  | Lifecycle Management Epic | Backlog | E-520915 | E-520915 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-06-02 | 2026-03-30
Local Enhancement Epic: Platforms - Reducing Customer hierarchy volatility | Approved | Local Enhancement Epic | Platforms Portfolio | 0108751 |  |  | Local Enhancement Epic | Build | E-523134 | E-523134 | 2: S | 2025-09-25 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-01-08 | 2025-09-25
Local Enhancement Epic: INFRA-PDSM API Access for integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0108824 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: "Close Complete HR Compliance Notices - US Case im | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108825 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Prevent Unauthorized/Accidental Triggering of HR C | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108826 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: RPA Implementation for Attack Surface Management | Closed | Local Enhancement Epic | Platforms Portfolio | 0108827 |  |  | Local Enhancement Epic | Backlog | E-520974 | E-520974 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Record producer for requesting boost and synonym d | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108849 |  |  | Local Enhancement Epic | Backlog | E-525257 | E-525257 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Purple Gateway Employee Experience Feedback Module | Approved | Local Enhancement Epic | Platforms Portfolio | 0108858 |  |  | Local Enhancement Epic | Backlog | E-525251 | E-525251 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Credit Card Obfuscation Mod_CY25 PI4&5 | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108865 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: AI Search Reporting | Approved | Local Enhancement Epic | Platforms Portfolio | 0108860 |  |  | Local Enhancement Epic | Backlog | E-527785 | E-527785 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Direct served coverage in 14 Markets[AMERICANO] | Approved | Local Enhancement Epic | Platforms Portfolio | 0108901 |  |  | Local Enhancement Epic | Build | E-521280 | E-521280 | 2: S | 2026-01-19 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-07 | 2025-10-31 | 2026-01-19
Local Enhancement Epic: Remove EDM Document Manager Restriction | Closed | Local Enhancement Epic | Platforms Portfolio | 0108902 |  |  | Local Enhancement Epic | Backlog | E-527686 | E-527686 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ETG Datastore Refinement | Approved | Local Enhancement Epic | Platforms Portfolio | 0108903 |  |  | Local Enhancement Epic | Build | E-521393 | E-521393 | 2: S | 2025-08-25 |  |  | 2 | 0 | 1 | 1 | No | 2026-02-23 | 2026-07-07 | 2025-08-25
Lifecycle Management Epic: InfoSec - FY26_PI03_Vulnerability_ Mgmt_ Support | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0108904 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec - FY26_PI03_Vulnerability_ Mgmt_ Support | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0108905 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Redesign EDM Manager Document Overview Page with D | Closed | Local Enhancement Epic | Platforms Portfolio | 0108908 |  |  | Local Enhancement Epic | Backlog | E-527685 | E-527685 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Implement Guided Tour for the “Submit a Document” | Closed | Local Enhancement Epic | Platforms Portfolio | 0108910 |  |  | Local Enhancement Epic | Backlog | E-527786 | E-527786 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Purple Gateway for Compliance Attestations - The L | Closed | Local Enhancement Epic | Platforms Portfolio | 0108911 |  |  | Local Enhancement Epic | Backlog | E-527783 | E-527783 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add Duty/Tax as a new account type | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0108997 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26 Shipment EFS Enabler for Adoptions_PF | Completed | Local Enhancement Epic | Platforms Portfolio | 0109016 |  |  | Local Enhancement Epic | Build | E-524135 | E-524135 | 3: M | 2025-09-25 |  |  | 2 | 0 | 2 | 0 | No |  |  | 2025-09-25
Local Enhancement Epic: Modification-of-FDW-Poland-Infrastructure | Approved | Local Enhancement Epic | Platforms Portfolio | 0109037 |  |  | Local Enhancement Epic | Build | E-524171 | E-524171 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-01 | 2026-05-29 | 2026-02-06
Local Enhancement Epic: Network infrastructure for FedEx Facilities in KSA | Closed | Local Enhancement Epic | Platforms Portfolio | 0109052 |  |  | Local Enhancement Epic | Backlog | E-520980 | E-520980 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PRA Chat Bot | Closed | Local Enhancement Epic | Platforms Portfolio | 0109073 |  |  | Local Enhancement Epic | Build | E-521432 | E-521432 | 3: M | 2025-12-08 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-12-08
Local Enhancement Epic: FXL Norther Border WxCCE Setup | Approved | Local Enhancement Epic | Platforms Portfolio | 0109076 |  |  | Local Enhancement Epic | Build | E-521442 | E-521442 | 1: XS | 2025-07-10 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-20 | 2025-10-03 | 2025-07-10
Local Enhancement Epic: Customer Attribute Validation Services/Functions | Approved | Local Enhancement Epic | Platforms Portfolio | 0109142 |  |  | Local Enhancement Epic | Build | E-534828 | E-534828 | 3: M | 2025-10-20 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-12-31 | 2025-10-20
Local Enhancement Epic: OT SAG Infrastructure | Approved | Local Enhancement Epic | Platforms Portfolio | 0109145 |  |  | Local Enhancement Epic | Build | E-536914 | E-536914 | 2: S | 2025-10-21 |  |  | 3 | 0 | 2 | 1 | No | 2025-09-10 | 2026-05-25 | 2025-10-21
Local Enhancement Epic: Enable Bulk Document Migration and Upload for EDM | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109146 |  |  | Local Enhancement Epic | Backlog | E-527684 | E-527684 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: InfoSec - CY25 PI3_Remove_Low_Vulnerabilities | Completed | Lifecycle Management Epic | Platforms Portfolio | 0109147 |  |  | Lifecycle Management Epic | Done |  |  | 2: S | 2025-06-26 | 2025-06-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26 | 2025-06-26
Biz w/ Tech Epic: 7584-AS/RS in MEMH East Cage | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109209 | 7584 | AS/RS in MEMH East Cage #7584 | Biz w/ Tech Epic | Assessment & Analysis | E-502019 | E-502019 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-02
Biz w/ Tech Epic: 8291-[Enabler] Rating Modernization - SDOM changes | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109210 | 8291 | Rating Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-502021 | E-502021 |  |  |  | 100% | 1 | 1 |  | 0 | No | 2025-06-02 | 2025-09-01
Biz w/ Tech Epic: 86611-Recharge Phase 3 | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109211 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-502128 | E-502128 |  |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Accessing e-GPS data for the SRO (Static Route Opt | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109212 | 9525 | Optimize On-Road Route Plan to improve OnRoad Effi | Biz w/ Tech Epic | Assessment & Analysis | E-476083 | E-476083 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: AS/RS in MEMH East Cage | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109213 | 7584 | AS/RS in MEMH East Cage #7584 | Biz w/ Tech Epic | Assessment & Analysis | E-514254 | E-514254 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2025-08-01
Biz w/ Tech Epic: Evaluate Solution | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109214 | 6685 | Telematics Vendor Selection and Integration - Peop | Biz w/ Tech Epic | Assessment & Analysis | E-378360 | E-378360 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FCF Transformation - Epic 2 - Operational Changes | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109215 | 9235 | FCF transformation: Epic 1 | Biz w/ Tech Epic | Assessment & Analysis | E-410826 | E-410826 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Biz w/ Tech Epic: FCF Transformation - Epic 3 - Customized Notificat | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109216 | 9235 | FCF transformation: Epic 1 | Biz w/ Tech Epic | Assessment & Analysis | E-410833 | E-410833 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Biz w/ Tech Epic: Field Network Optimization - Full AT&T Rollout | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109217 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Assessment & Analysis | E-463616 | E-463616 | 5: XL |  |  | 66.67% | 3 | 2 | 1 | 0 | No | 2024-07-22 | 2026-05-21
Biz w/ Tech Epic: Global PPOD Phase 2 - Option to Out & Image Qualit | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109218 | 7727 | [US] Implement visibility enhancements on FedEx.co | Biz w/ Tech Epic | Assessment & Analysis | E-314489 | E-314489 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.7) | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109219 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Assessment & Analysis | E-421210 | E-421210 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-03-31
Biz w/ Tech Epic: I/EU Increase Revenue by Improving Onboarding Flow | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109220 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-449157 | E-449157 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-27
Biz w/ Tech Epic: US Edge Network Optimization - Deployment of Pilot | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109221 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Assessment & Analysis | E-463629 | E-463629 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: (JOIN/HOPE) Registration & Payment options - Phase | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109294 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-383941 | E-383941 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-01
Biz w/ Tech Epic: 89968-China UEL/MFA Routing | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109295 | 89968 | China UEL/MFA Routing | Biz w/ Tech Epic | Assessment & Analysis | E-502017 | E-502017 | 1: XS |  |  | 100% | 1 | 1 |  | 0 | No | 2025-06-18 | 2025-07-01
Biz w/ Tech Epic: Brazil TAX ID change starting 1/1/25 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109296 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-455134 | E-455134 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2026-04-01
Biz w/ Tech Epic: CDS Migration To DSE | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109297 | 92253 | CustomerAcct.Mgmt.CAM/UnifiedSvc.LayerUSL Ret. | Biz w/ Tech Epic | Assessment & Analysis | E-149084 | E-149084 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2026-01-30
Biz w/ Tech Epic: Data Management Strategy, Metrics and Reporting (F | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109298 | 7910 | J2C Initiative: PCF to FedEx Cloud Platform (AKS) | Biz w/ Tech Epic | Assessment & Analysis | E-423986 | E-423986 | 4: L |  |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-05-30
Biz w/ Tech Epic: Delivery PFS | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109299 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-409383 | E-409383 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Dock Data Modernization [ Platforms ] | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109300 | 7145 | [Enabler] Dock Data Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-455081 | E-455081 | 4: L |  |  | 60% | 5 | 3 | 1 | 1 | No | 2025-07-30 | 2026-06-02
Biz w/ Tech Epic: Enhanced Commodity Visibility | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109301 | 8548 | Enhanced Commodity Visibility | Biz w/ Tech Epic | Assessment & Analysis | E-392750 | E-392750 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-01
Biz w/ Tech Epic: Enterprise Service Modernization_1.0 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109302 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-447134 | E-447134 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-08-19 | 2025-09-30
Biz w/ Tech Epic: FCP BCDR | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109303 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-477322 | E-477322 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-02-03 | 2025-12-31
Biz w/ Tech Epic: FCP Data Engineering | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109304 | 7910 | J2C Initiative: PCF to FedEx Cloud Platform (AKS) | Biz w/ Tech Epic | Assessment & Analysis | E-477046 | E-477046 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FCP Developer Experience | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109305 | 7910 | J2C Initiative: PCF to FedEx Cloud Platform (AKS) | Biz w/ Tech Epic | Assessment & Analysis | E-468341 | E-468341 | 5: XL |  |  | 100% | 1 | 1 |  | 0 | No | 2025-01-08 | 2025-08-12
Biz w/ Tech Epic: FCP Engagement & Enablement | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109306 | 7910 | J2C Initiative: PCF to FedEx Cloud Platform (AKS) | Biz w/ Tech Epic | Assessment & Analysis | E-472286 | E-472286 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No | 2025-01-08 | 2026-01-08
Biz w/ Tech Epic: Orchestrator/Platform Integration | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109307 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-477320 | E-477320 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-02-03 | 2026-05-01
Biz w/ Tech Epic: FCP CICD GitHub | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109308 | 7910 | J2C Initiative: PCF to FedEx Cloud Platform (AKS) | Biz w/ Tech Epic | Assessment & Analysis | E-472299 | E-472299 | 5: XL |  |  | 100% | 1 | 1 |  | 0 | No | 2025-05-23 | 2025-12-26
Biz w/ Tech Epic: FCP Regions Implementation | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109309 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-468314 | E-468314 | 4: L |  |  | 100% | 1 | 1 |  | 0 | No | 2025-06-04 | 2026-01-30
Biz w/ Tech Epic: FCP Security | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109310 | 7910 | J2C Initiative: PCF to FedEx Cloud Platform (AKS) | Biz w/ Tech Epic | Assessment & Analysis | E-477323 | E-477323 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-02-03 | 2025-12-31
Biz w/ Tech Epic: FedEx account creation via 3rd party digital chann | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109311 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-415018 | E-415018 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-04-30
Biz w/ Tech Epic: Fiji Direct Serve Conversion | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109312 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-515012 | E-515012 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Global ARTH (Auto Redirect To Hold) | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109313 | 9215 | Global ARTH | Biz w/ Tech Epic | Assessment & Analysis | E-397266 | E-397266 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-04-01
Biz w/ Tech Epic: GSP-to-Direct Serve (FJ) (Platforms Portfolio) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109315 | 6945 | Fiji Direct Serve Conversion | Biz w/ Tech Epic | Assessment & Analysis | E-366755 | E-366755 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-10
Biz w/ Tech Epic: HR Process Optimisation | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109316 | 8992 | ServiceNow Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-412822 | E-412822 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: HR ServiceNow Payroll Adoption | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109317 | 8992 | ServiceNow Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-412821 | E-412821 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: InfoSec - Global Segmentation Program - Placeholde | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109318 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-514253 | E-514253 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: JOIN / HoPE - Phase 1 VB2A - Guest Shipping Paymen | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109319 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-406658 | E-406658 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-17
Biz w/ Tech Epic: JOIN/HoPE Phase 1 VB1A - Beyond Credit Card | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109320 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-383438 | E-383438 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-29
Biz w/ Tech Epic: JOIN/HoPE Phase 2 VB 1B - Enable Guest Shipping fo | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109321 | 9190 | HoPE Enablement- Part 1 | Biz w/ Tech Epic | Assessment & Analysis | E-411108 | E-411108 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-15
Biz w/ Tech Epic: JOIN/HOPE Phase 2 VB 2B - Enable Guest Shipping fo | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109322 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-383452 | E-383452 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-15
Biz w/ Tech Epic: JOIN/HoPE Registration & Payment options - Phase 3 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109323 | 9245 | Introducing the Pay as you Ship (PAYS) cust. type | Biz w/ Tech Epic | Assessment & Analysis | E-383471 | E-383471 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-15
Biz w/ Tech Epic: LOCATE Asset Data Storage | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109324 | 8515 | Tug Dispatch Management | Biz w/ Tech Epic | Assessment & Analysis | E-423327 | E-423327 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-12-30
Biz w/ Tech Epic: POC - Data Authors & Prod Delivery | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109325 | 106932 | TS-VL3-Data-FD-Enabler-Release2 | Biz w/ Tech Epic | Assessment & Analysis | E-516414 | E-516414 | 3: M |  |  |  | 12 | 0 | 12 | 0 | No | 2025-05-05 | 2025-06-30
Biz w/ Tech Epic: UCC ICS2 Release 3 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0109326 | 106149 | UCC ICS2 Release 3 | Biz w/ Tech Epic | Assessment & Analysis | E-511963 | E-511963 | 3: M |  |  |  | 1 | 0 | 1 | 0 | No | 2025-05-20 | 2025-09-30
Biz w/ Tech Epic: 31471 - Develop cellphone policy | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109456 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369754 | E-369754 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 31472 - Get HR approval for the new wireless / cel | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109457 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369755 | E-369755 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 31473 - Draft communication for employees | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109458 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369756 | E-369756 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 31778 - Verify Billing | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109459 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369757 | E-369757 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 31962 - Communicate to employees | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109460 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369758 | E-369758 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 31963 - Contact the impacted employees | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109461 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369759 | E-369759 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 31964 - Submit disconnects | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109462 | 6948 | Cell Phone Usage Reduction | Biz w/ Tech Epic | Backlog | E-369760 | E-369760 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 7214-FXF Paperless Delivery Receipt and Photo Capt | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109463 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Build | E-502020 | E-502020 |  | 2025-07-01 |  |  | 2 | 0 | 1 | 1 | No | 2025-11-20 | 2026-01-20 | 2025-07-01
Biz w/ Tech Epic: 9204 Pickup PFS Value Bundle 1: One FedEx Rating - | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109464 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Build | E-485787 | E-485787 |  | 2025-07-01 |  |  | 1 | 0 |  | 1 | No | 2025-05-29 | 2025-09-08 | 2025-07-01
Biz w/ Tech Epic: 92747-DC Optimization - Citrix | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109465 | 92747 | TS-VL4-ENDUSER-Cirtix Optimization (International) | Biz w/ Tech Epic | Build | E-500498 | E-500498 |  | 2025-10-28 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-07-15 | 2025-10-28
Biz w/ Tech Epic: Accept RAW Address for contacts in ECDC | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109466 | 8129 | [US] CE Desktop FY25 Value Bundle - Phase B | Biz w/ Tech Epic | Backlog | E-454184 | E-454184 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Automate MI (Monitoring & Intervention) Customer O | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109467 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Build | E-406167 | E-406167 |  | 2025-09-25 |  |  | 13 | 0 | 11 | 2 | No | 2025-07-30 | 2026-01-08 | 2025-09-25
Biz w/ Tech Epic: Change in LEAN trigger rule in CAM | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109468 | 9198 | FedEx Freight : Modernize fedex.com LTL shipping | Biz w/ Tech Epic | Backlog | E-455153 | E-455153 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CMQT 2.0 Multimodal | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109469 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Backlog | E-442420 | E-442420 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-31 | 2026-12-22
Biz w/ Tech Epic: Common Sort Value Bundle 1 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109470 | 7216 | Common Sort - Value Bundle 1 | Biz w/ Tech Epic | Build | E-456582 | E-456582 | 3: M | 2025-07-01 |  |  | 3 | 0 | 1 | 2 | No | 2024-10-07 | 2027-03-23 | 2025-07-01
Biz w/ Tech Epic: Customer Label Creation Threshold | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109471 | 8139 | Customer Label Creation Threshold | Biz w/ Tech Epic | Backlog | E-292130 | E-292130 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Delivery Predictions Mapview - Rental Vehicle Chan | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109472 | 7727 | [US] Implement visibility enhancements on FedEx.co | Biz w/ Tech Epic | Backlog | E-458491 | E-458491 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-14 | 2026-06-23
Biz w/ Tech Epic: Deploy Solution to FedEx Freight Canada Ops | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109473 | 6685 | Telematics Vendor Selection and Integration - Peop | Biz w/ Tech Epic | Backlog | E-394693 | E-394693 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Designated Workforce Phase 2 (3.1) | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109474 | 9326 | [Enabler] Designated Courier Workforce Phases 1 & | Biz w/ Tech Epic | Backlog | E-438969 | E-438969 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FCF (FedEx Customized Freight) Transformation - Ep | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109475 | 9235 | FCF transformation: Epic 1 | Biz w/ Tech Epic | Backlog | E-391971 | E-391971 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FRO Epic 2 Pickup and Enabler Work (2.1) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109476 | 7816 | N2.0 Tech Phase 1 (18 month roadmap) | Biz w/ Tech Epic | Backlog | E-386826 | E-386826 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2026-07-08
Biz w/ Tech Epic: FRO Epic 2 Pickup and Enabler Work (2.4) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109477 | 7816 | N2.0 Tech Phase 1 (18 month roadmap) | Biz w/ Tech Epic | Backlog | E-390633 | E-390633 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-11
Biz w/ Tech Epic: FRO Epics 3 -4 (2.1, 2.2, 2.3) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109478 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-405363 | E-405363 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Biz w/ Tech Epic: FRO Epics 3-4 (1.1) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109479 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-398725 | E-398725 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Biz w/ Tech Epic: FRO Epics 3-4 (2.4) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109480 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-405367 | E-405367 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Biz w/ Tech Epic: FRO Epics 3-4 (3.2, 3.3, 3.4) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109481 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-405356 | E-405356 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Biz w/ Tech Epic: FRO Epics 3-4 (6.1) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109482 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-405373 | E-405373 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Biz w/ Tech Epic: FRO VB 2 Epic 2 Pickup and Enabler Work (2.5) | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109483 | 7816 | N2.0 Tech Phase 1 (18 month roadmap) | Biz w/ Tech Epic | Backlog | E-390642 | E-390642 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Geospatial Access for Tricolor Banded Commit | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109484 | 9243 | Banded Commit for Competitive Profitable Network | Biz w/ Tech Epic | Backlog | E-437964 | E-437964 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-31
Biz w/ Tech Epic: Global P&D Ecosystem - Epic 1 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109485 | 7406 | Global P&D Ecosystem Enabler | Biz w/ Tech Epic | Build | E-434726 | E-434726 | 2: S | 2025-07-01 |  | 28.57% | 7 | 2 | 3 | 2 | No | 2025-07-30 | 2027-05-13 | 2025-07-01
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.12) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109486 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Backlog | E-422864 | E-422864 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-30
Biz w/ Tech Epic: GSP to Direct Serve- Bulgaria | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109487 |  |  | Biz w/ Tech Epic | Backlog | E-437170 | E-437170 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: GSP to Direct Serve- Vietnam | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109488 |  |  | Biz w/ Tech Epic | Backlog | E-430445 | E-430445 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: GSP-to-Direct Serve Sizing - Cyprus | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109489 |  |  | Biz w/ Tech Epic | Backlog | E-400596 | E-400596 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Implement a solution to move SAM into the common a | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109490 | 8204 | FedEx ITAM practice for the Enterprise | Biz w/ Tech Epic | Backlog | E-358220 | E-358220 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-27
Biz w/ Tech Epic: Implement HAMPro and HAM-Harware Asset Management | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109491 | 8204 | FedEx ITAM practice for the Enterprise | Biz w/ Tech Epic | Backlog | E-381376 | E-381376 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: InfoSec - 7641- ENT Badging and Physical Access Se | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109492 | 7641 | 7641- ENT Badging and Physical Access Security 1.0 | Biz w/ Tech Epic | Build | E-485781 | E-485781 |  | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No | 2025-05-09 | 2025-08-29 | 2025-09-19
Biz w/ Tech Epic: InfoSec - Global - ZTNA - Zscaler | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109493 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Build | E-471588 | E-471588 | 3: M | 2025-07-01 |  | 5.97% | 67 | 4 | 63 | 0 | No | 2025-07-07 | 2026-04-10 | 2025-07-01
Biz w/ Tech Epic: InfoSec - Zero Trust Adaptive / Contextual MFA - C | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109494 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Build | E-434601 | E-434601 | 2: S | 2025-07-01 |  | 100% | 6 | 6 |  | 0 | No | 2025-01-06 | 2025-05-23 | 2025-07-01
Biz w/ Tech Epic: InfoSec - Zero Trust Identity Provider - CY25 PI 1 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109495 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Build | E-434609 | E-434609 | 4: L | 2025-07-01 |  | 100% | 80 | 80 |  | 0 | No | 2025-01-06 | 2025-05-23 | 2025-07-01
Biz w/ Tech Epic: InfoSec - Zero Trust Privileged Access Management | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109496 | 7249 | HOS (Hours of Service) Vendor | Biz w/ Tech Epic | Build | E-434612 | E-434612 | 4: L | 2025-07-01 |  | 100% | 25 | 25 |  | 0 | No | 2025-01-06 | 2025-05-23 | 2025-07-01
Biz w/ Tech Epic: Multi-GpEFS Postal Code validation for WREG | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109497 |  |  | Biz w/ Tech Epic | Launch & Evaluate | E-203534 | E-203534 | 4: L | 2025-08-27 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-07 | 2025-08-27
Biz w/ Tech Epic: NDS (Network Definition Source) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109498 | 6775 | WS1 - [1C - Project Zenith ] Network Definition | Biz w/ Tech Epic | Build | E-476137 | E-476137 |  | 2025-06-30 |  | 57.14% | 7 | 4 | 1 | 2 | No | 2025-01-20 | 2026-02-09 | 2025-06-30
Biz w/ Tech Epic: Network 2.0 Properties Projects | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109499 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Backlog | E-424369 | E-424369 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Network Scheduling | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109500 | 6756 | TS-VL4-NETWORK-Office MPLS Carrier Change | Biz w/ Tech Epic | Backlog | E-424368 | E-424368 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-31
Biz w/ Tech Epic: HTM Phase 2 Release 0 Resource Allocation Platform | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109501 | 7151 | Operational Hold to Match (HTM) | Biz w/ Tech Epic | Build | E-452204 | E-452204 | 2: S | 2025-07-01 |  | 33.33% | 3 | 1 |  | 2 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Pickup PFS VB 1 Epic D | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109502 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Backlog | E-459779 | E-459779 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Pickup PFS VB1 Epic B - Pickup Data Access | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109503 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Backlog | E-333548 | E-333548 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-01 | 2026-03-31
Biz w/ Tech Epic: Platinum - Enterprise Platform and Architecture RA | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0109504 | 90032 | TS-VL3-SDLC-PPMRetirement | Biz w/ Tech Epic | Backlog | E-385158 | E-385158 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Postal enablement EE, LV, LT, BG, CY, SI, UA and I | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109505 | 9491 | Postal enablement EE, LV, LT, IE, BG, CY, SI, UA | Biz w/ Tech Epic | Build | E-451144 | E-451144 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: PPFS VB 1- Epic C - Enable Services and Service Op | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109506 | 9204 | Pickup PFS Value Bundle 1: One FedEx Rating | Biz w/ Tech Epic | Backlog | E-444255 | E-444255 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Project Firefly | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109507 | 7387 | Project Firefly - Enhancing Data Privacy and Reduc | Biz w/ Tech Epic | Build | E-453277 | E-453277 | 4: L | 2025-07-01 |  | 16.67% | 6 | 1 | 2 | 3 | No | 2024-09-19 | 2026-09-30 | 2025-07-01
Biz w/ Tech Epic: ROM 1.5 Compliance Metrics & Actual Staffing | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109508 | 9518 | Real-Time Ops Manager (ROM) | Biz w/ Tech Epic | Build | E-476146 | E-476146 |  | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No | 2025-02-28 | 2025-06-06 | 2025-07-01
Biz w/ Tech Epic: Seeking CPP - Customer Profile Product Data for Dr | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109509 |  |  | Biz w/ Tech Epic | Backlog | E-435027 | E-435027 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SEPA enablement for Portugal | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109510 | 9541 | Enable- G2D migration Portugal ( ACE enablement) | Biz w/ Tech Epic | Backlog | E-455108 | E-455108 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SSCSO retirement - Shipment order delta in CSO | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109511 | 7778 | Customer Data Exchange - Ground Enablement | Biz w/ Tech Epic | Backlog | E-411024 | E-411024 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SSP Enablement for Surface Linehaul Execution (for | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109512 | 9058 | SSP Enablement for Surface LH Execution | Biz w/ Tech Epic | Backlog | E-350344 | E-350344 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-25 | 2026-03-27
Biz w/ Tech Epic: Turkey G2D New Tax Exemption on Account Level for | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109513 | 9373 | Enable - G2D conversion for Turkey ( ACE enableme | Biz w/ Tech Epic | Build | E-476088 | E-476088 | 1: XS | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: Update Interactions Search API | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0109514 | 6728 | [US] Enhance IVR capabilities and performance | Biz w/ Tech Epic | Backlog | E-461719 | E-461719 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-25 | 2025-10-31
Biz w/ Tech Epic: Vietnam GSP-to-Direct Serve Sizing Request | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109515 | 7300 | Vietnam Direct Serve Conversion - Corporate Load | Biz w/ Tech Epic | Backlog | E-417621 | E-417621 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Access to the Geography EFS API for the FedEx Offi | Closed | Local Enhancement Epic | Platforms Portfolio | 0109899 |  |  | Local Enhancement Epic | Build | E-474060 | E-474060 | 1: XS | 2025-07-02 |  |  | 1 | 0 |  | 1 | No |  |  | 2025-07-02
Local Enhancement Epic: Adding New Enterprise Account Source Group Name Op | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109900 |  |  | Local Enhancement Epic | Backlog | E-465912 | E-465912 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Address FY25 Production Readiness and Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0109901 |  |  | Local Enhancement Epic | Backlog | E-423824 | E-423824 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-02
Local Enhancement Epic: Alternate Messaging Platform, Apache Pulsar | On Hold | Local Enhancement Epic | Platforms Portfolio | 0109902 |  |  | Local Enhancement Epic | Backlog | E-433561 | E-433561 | 5: XL |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2026-03-24
Local Enhancement Epic: API Gateway Automation and Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109903 |  |  | Local Enhancement Epic | Backlog | E-433567 | E-433567 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Architecture Delivery | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109904 |  |  | Local Enhancement Epic | Backlog | E-433517 | E-433517 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Architecture Modernization Platforms (AMP) KTLO/Op | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0109905 |  |  | Lifecycle Management Epic | Backlog | E-468988 | E-468988 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AuditVault & Data Services security work | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109906 |  |  | Local Enhancement Epic | Backlog | E-433928 | E-433928 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automation of PDSM Requests | Approved | Local Enhancement Epic | Platforms Portfolio | 0109907 |  |  | Local Enhancement Epic | Backlog | E-379162 | E-379162 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-03-30
Local Enhancement Epic: Beyond Big6 Tech Mins Operational Standards | Approved | Local Enhancement Epic | Platforms Portfolio | 0109908 |  |  | Local Enhancement Epic | Backlog | E-412992 | E-412992 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-11-17
Local Enhancement Epic: Campus Infrastructure Refresh | Closed | Local Enhancement Epic | Platforms Portfolio | 0109909 |  |  | Local Enhancement Epic | Backlog | E-447470 | E-447470 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CCOB Modernization | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109910 |  |  | Local Enhancement Epic | Backlog | E-467792 | E-467792 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Changing Default Billing Cycles for Canada Bill-To | Approved | Local Enhancement Epic | Platforms Portfolio | 0109911 |  |  | Local Enhancement Epic | Build | E-477544 | E-477544 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2025-03-03 | 2025-05-30 | 2025-07-02
Local Enhancement Epic: CI/CD and SCM standards (Big 6 Tech Mins) | Approved | Local Enhancement Epic | Platforms Portfolio | 0109912 |  |  | Local Enhancement Epic | Backlog | E-319857 | E-319857 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-21
Local Enhancement Epic: Citizen Development for ServiceNow | Completed | Local Enhancement Epic | Platforms Portfolio | 0109913 |  |  | Local Enhancement Epic | Backlog | E-512990 | E-512990 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Collaboration Tools Break/Fix | Closed | Local Enhancement Epic | Platforms Portfolio | 0109914 |  |  | Local Enhancement Epic | Backlog | E-379166 | E-379166 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Create Tibco EMS Environment for Apps in COLO | On Hold | Local Enhancement Epic | Platforms Portfolio | 0109915 |  |  | Local Enhancement Epic | Build | E-433568 | E-433568 | 3: M | 2026-03-26 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-03-24 | 2026-03-26
Local Enhancement Epic: CSR Environment Management Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109916 |  |  | Local Enhancement Epic | Backlog | E-433597 | E-433597 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CyberVault Tool Implementation | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109917 |  |  | Local Enhancement Epic | Backlog | E-433866 | E-433866 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Data Center Facilities Maintenance | Approved | Local Enhancement Epic | Platforms Portfolio | 0109918 |  |  | Local Enhancement Epic | Backlog | E-433553 | E-433553 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-31
Local Enhancement Epic: Data Center Management | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109919 |  |  | Local Enhancement Epic | Backlog | E-433891 | E-433891 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Database Changes as Code/Versioning (SQL Server) | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109920 |  |  | Local Enhancement Epic | Backlog | E-433859 | E-433859 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Database Operations - patching/day-to-day support | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109921 |  |  | Lifecycle Management Epic | Done | E-433874 | E-433874 | 5: XL | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Database Provisioning as Code (SQL Server) | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109922 |  |  | Local Enhancement Epic | Backlog | E-433865 | E-433865 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dataworks (Regulatory) platform | Approved | Local Enhancement Epic | Platforms Portfolio | 0109923 |  |  | Local Enhancement Epic | Build | E-474058 | E-474058 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2025-05-19 | 2025-05-20 | 2025-09-25
Local Enhancement Epic: DevTest Ephemeral Environments - CONDOR | Approved | Local Enhancement Epic | Platforms Portfolio | 0109924 |  |  | Local Enhancement Epic | Backlog | E-340865 | E-340865 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-12-30
Local Enhancement Epic: Drive Initiatives & Specialized Projects - CY25 | Completed | Local Enhancement Epic | Platforms Portfolio | 0109925 |  |  | Local Enhancement Epic | Backlog | E-470763 | E-470763 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DSE RA New Release Planning and Arch | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109926 |  |  | Local Enhancement Epic | Backlog | E-433576 | E-433576 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EAN Express Enablement | Approved | Local Enhancement Epic | Platforms Portfolio | 0109927 |  |  | Local Enhancement Epic | Backlog | E-470037 | E-470037 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-12-17 | 2025-05-30
Local Enhancement Epic: ECAM/ECIS International LAC request | Approved | Local Enhancement Epic | Platforms Portfolio | 0109928 |  |  | Local Enhancement Epic | Backlog | E-409412 | E-409412 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: EDCW/WTC Data Center Asset Clean-up | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109929 |  |  | Local Enhancement Epic | Backlog | E-379232 | E-379232 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Email Services KTLO | Completed | Local Enhancement Epic | Platforms Portfolio | 0109930 |  |  | Local Enhancement Epic | Backlog | E-379172 | E-379172 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enhancements to SEFS Acquired & Relinquished Task | Approved | Local Enhancement Epic | Platforms Portfolio | 0109931 |  |  | Local Enhancement Epic | Build | E-463613 | E-463613 | 2: S | 2025-11-10 |  |  | 5 | 0 |  | 5 | No | 2024-11-05 | 2026-03-24 | 2025-11-10
Local Enhancement Epic: Enterprise Automation Schedule Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109932 |  |  | Local Enhancement Epic | Backlog | E-433547 | E-433547 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enterprise Customer - Organization Entity Manageme | Approved | Local Enhancement Epic | Platforms Portfolio | 0109933 |  |  | Local Enhancement Epic | Backlog | E-160714 | E-160714 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2026-05-29
Local Enhancement Epic: Enterprise Customer FY25 Production Readiness and | Approved | Local Enhancement Epic | Platforms Portfolio | 0109934 |  |  | Local Enhancement Epic | Build | E-419465 | E-419465 |  | 2025-07-02 |  | 60% | 10 | 6 |  | 4 | No | 2024-07-22 | 2025-05-30 | 2025-07-02
Local Enhancement Epic: Enterprise DBA Support KTLO | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109935 |  |  | Local Enhancement Epic | Backlog | E-433887 | E-433887 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enterprise Linux Automation Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109936 |  |  | Local Enhancement Epic | Backlog | E-433532 | E-433532 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enterprise Linux Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109937 |  |  | Local Enhancement Epic | Backlog | E-433925 | E-433925 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enterprise Shipment FY25 Production Readiness and | Approved | Local Enhancement Epic | Platforms Portfolio | 0109938 |  |  | Local Enhancement Epic | Backlog | E-423259 | E-423259 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: F5 Application Load balancer Upgrades and LCM | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109939 |  |  | Local Enhancement Epic | Backlog | E-379234 | E-379234 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: F5 Application Study Tool | Closed | Local Enhancement Epic | Platforms Portfolio | 0109940 |  |  | Local Enhancement Epic | Done | E-482702 | E-482702 |  | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Fault Monitoring Replacement Tool | Closed | Local Enhancement Epic | Platforms Portfolio | 0109941 |  |  | Local Enhancement Epic | Backlog | E-417411 | E-417411 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Fieldglass CY25 | Completed | Local Enhancement Epic | Platforms Portfolio | 0109942 |  |  | Local Enhancement Epic | Backlog | E-477342 | E-477342 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GEFS service adoption to draw country boundaries o | Approved | Local Enhancement Epic | Platforms Portfolio | 0109943 |  |  | Local Enhancement Epic | Backlog | E-474055 | E-474055 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-10-30 | 2025-10-31
Local Enhancement Epic: Geopolitical FY25 Production Readiness and Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0109944 |  |  | Local Enhancement Epic | Backlog | E-423291 | E-423291 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Lifecycle Management Epic: GitHub Actions | Approved | Lifecycle Management Epic | Platforms Portfolio | 0109945 |  |  | Lifecycle Management Epic | Backlog | E-448615 | E-448615 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2024-08-21 | 2028-10-19
Local Enhancement Epic: GPS Interface Integration (AXON) | Approved | Local Enhancement Epic | Platforms Portfolio | 0109946 |  |  | Local Enhancement Epic | Backlog | E-457458 | E-457458 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-16 | 2026-08-06
Local Enhancement Epic: HAM KTLO Management/Maintenance | Approved | Local Enhancement Epic | Platforms Portfolio | 0109947 |  |  | Local Enhancement Epic | Backlog | E-477731 | E-477731 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-03-17 | 2026-05-29
Local Enhancement Epic: Hardware Asset Management (HAM) Local Work | Approved | Local Enhancement Epic | Platforms Portfolio | 0109948 |  |  | Local Enhancement Epic | Build | E-411322 | E-411322 | 5: XL | 2026-04-02 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-02-28 | 2026-04-02
Local Enhancement Epic: HR ServiceNow Operational Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0109949 |  |  | Local Enhancement Epic | Backlog | E-400478 | E-400478 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: IBMi HA Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109950 |  |  | Local Enhancement Epic | Backlog | E-434544 | E-434544 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Improve ServiceNow DB Performance and scailability | Approved | Lifecycle Management Epic | Platforms Portfolio | 0109951 |  |  | Lifecycle Management Epic | Backlog | E-512989 | E-512989 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: INF21 022: CCTV Renewal Project | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109952 |  |  | Local Enhancement Epic | Backlog | E-391669 | E-391669 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF23 014: Israel Migration (Domestics) | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109953 |  |  | Local Enhancement Epic | Backlog | E-391685 | E-391685 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF23 028s: DUB14 IZ DMZ | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109954 |  |  | Local Enhancement Epic | Backlog | E-391687 | E-391687 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 004: Italy AS400 Phase 2 User Failover Test | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109955 |  |  | Local Enhancement Epic | Backlog | E-391689 | E-391689 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 015: International Infrastructure - Legacy D | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109956 |  |  | Local Enhancement Epic | Backlog | E-391675 | E-391675 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 028: Change Enablement Programme | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109957 |  |  | Local Enhancement Epic | Backlog | E-406739 | E-406739 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 031: LAC Azure Migration | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109958 |  |  | Local Enhancement Epic | Backlog | E-396192 | E-396192 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 032: JMS Redhat Upgrade | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109959 |  |  | Local Enhancement Epic | Backlog | E-406759 | E-406759 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 039: Gemini2 / Customs Clearance Application | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109960 |  |  | Local Enhancement Epic | Backlog | E-420752 | E-420752 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 045: BMC Upgrade and Modernisation | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109961 |  |  | Local Enhancement Epic | Backlog | E-420742 | E-420742 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: INF24 046: The Baldrick Programme | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109962 |  |  | Local Enhancement Epic | Backlog | E-420741 | E-420741 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec - Archer/OnSpring Maintenance and Manageme | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109963 |  |  | Lifecycle Management Epic | Build | E-472040 | E-472040 | 2: S | 2025-07-02 |  | 100% | 100 | 100 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: InfoSec - BCDR /Resiliency CORP Active Directory | Closed | Local Enhancement Epic | Platforms Portfolio | 0109964 |  |  | Local Enhancement Epic | Build | E-478432 | E-478432 | 1: XS | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: InfoSec - Centralized Security Logging - PI3 - PI5 | Closed | Local Enhancement Epic | Platforms Portfolio | 0109965 |  |  | Local Enhancement Epic | Build | E-482391 | E-482391 |  | 2025-08-14 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-08-14
Local Enhancement Epic: InfoSec - Endpoint Security Trellix - PI 02-04 | Approved | Local Enhancement Epic | Platforms Portfolio | 0109966 |  |  | Local Enhancement Epic | Backlog | E-481034 | E-481034 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-03-17 | 2025-10-13
Local Enhancement Epic: InfoSec - Evaluate Alternative Application Securit | Closed | Local Enhancement Epic | Platforms Portfolio | 0109967 |  |  | Local Enhancement Epic | Build | E-433353 | E-433353 | 4: L | 2025-07-01 |  | 69.23% | 39 | 27 | 12 | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: InfoSec - FY 24/25 C3 Technology SE-367268trategy | Closed | Local Enhancement Epic | Platforms Portfolio | 0109968 |  |  | Local Enhancement Epic | Backlog | E-367268 | E-367268 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec - FY 25 Demand - One Infosec | Closed | Local Enhancement Epic | Platforms Portfolio | 0109969 |  |  | Local Enhancement Epic | Done | E-432504 | E-432504 | 5: XL | 2025-07-01 | 2025-07-21 | 85.03% | 441 | 375 | 66 | 0 | No |  |  | 2025-07-01 | 2025-07-21
Lifecycle Management Epic: InfoSec - FY 25 Demand - Risk Management | Approved | Lifecycle Management Epic | Platforms Portfolio | 0109970 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-466105 | E-466105 | 5: XL | 2025-07-23 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30 | 2025-07-23
Local Enhancement Epic: InfoSec - Harden Resiliency Plans to Reduce Risk a | Approved | Local Enhancement Epic | Platforms Portfolio | 0109971 |  |  | Local Enhancement Epic | Build | E-434580 | E-434580 | 5: XL | 2025-07-01 |  | 100% | 50 | 50 |  | 0 | No | 2025-01-06 | 2025-05-26 | 2025-07-01
Lifecycle Management Epic: InfoSec - Identify Enterprise Security Gaps and Re | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109972 |  |  | Lifecycle Management Epic | Build | E-433357 | E-433357 | 4: L | 2025-07-01 |  | 53.57% | 28 | 15 | 10 | 3 | No |  |  | 2025-07-01
Local Enhancement Epic: InfoSec - Micro-segmentation for applications in E | Closed | Local Enhancement Epic | Platforms Portfolio | 0109973 |  |  | Local Enhancement Epic | Build | E-478425 | E-478425 | 2: S | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: InfoSec - Monitor Systems and Networks for Detecti | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109974 |  |  | Lifecycle Management Epic | Build | E-433359 | E-433359 | 4: L | 2025-07-01 |  | 100% | 34 | 34 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: InfoSec - OT/IoT AD Domain Feasibility Study | Closed | Local Enhancement Epic | Platforms Portfolio | 0109975 |  |  | Local Enhancement Epic | Launch & Evaluate | E-478436 | E-478436 | 2: S | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: InfoSec - Prevention of Security Misconfigurations | Closed | Local Enhancement Epic | Platforms Portfolio | 0109976 |  |  | Local Enhancement Epic | Build | E-433362 | E-433362 | 5: XL | 2025-07-01 |  | 100% | 23 | 23 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: InfoSec - Prevention of Security Misconfigurations | Closed | Local Enhancement Epic | Platforms Portfolio | 0109977 |  |  | Local Enhancement Epic | Build | E-481843 | E-481843 | 5: XL | 2025-07-01 |  | 88.89% | 9 | 8 |  | 1 | No |  |  | 2025-07-01
Lifecycle Management Epic: InfoSec - Product Security Governance & Technology | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109978 |  |  | Lifecycle Management Epic | Backlog | E-440646 | E-440646 | 5: XL |  |  | 100% | 3 | 3 |  | 0 | No
Lifecycle Management Epic: InfoSec - Research, Identification and Remediation | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109979 |  |  | Lifecycle Management Epic | Build | E-433365 | E-433365 | 4: L | 2025-07-01 |  | 96.15% | 26 | 25 |  | 1 | No |  |  | 2025-07-01
Lifecycle Management Epic: InfoSec - Risk Assessment of Security Misconfigura | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109980 |  |  | Lifecycle Management Epic | Build | E-481845 | E-481845 |  | 2025-11-03 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-03
Local Enhancement Epic: InfoSec - Technology Adoptions for Cybersecurity - | Approved | Local Enhancement Epic | Platforms Portfolio | 0109981 |  |  | Local Enhancement Epic | Build | E-434596 | E-434596 | 4: L | 2025-07-01 |  | 100% | 2 | 2 |  | 0 | No | 2025-01-06 | 2025-05-26 | 2025-07-01
Local Enhancement Epic: Infrastructure Capacity Planning | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109982 |  |  | Local Enhancement Epic | Backlog | E-434219 | E-434219 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Internal Optimization, Communication, Growth & Lea | Approved | Local Enhancement Epic | Platforms Portfolio | 0109983 |  |  | Local Enhancement Epic | Backlog | E-424349 | E-424349 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-02-03
Local Enhancement Epic: ITSM (Change, Problem, Incident, Request) Local De | Approved | Local Enhancement Epic | Platforms Portfolio | 0109984 |  |  | Local Enhancement Epic | Backlog | E-401000 | E-401000 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-08-31
Local Enhancement Epic: KTLO - Puppet product and infrastructure support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109985 |  |  | Local Enhancement Epic | Backlog | E-433384 | E-433384 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: KTLO - Reference Architecture packaging, testing, | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109986 |  |  | Local Enhancement Epic | Backlog | E-433514 | E-433514 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - Communications - Quarterly Weblogic & Java P | Closed | Local Enhancement Epic | Platforms Portfolio | 0109987 |  |  | Local Enhancement Epic | Backlog | E-379244 | E-379244 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - Coordination - Retire EOL Legacy Storage Arr | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109988 |  |  | Local Enhancement Epic | Backlog | E-379245 | E-379245 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - Replace EOL G7 Hardware in DC | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109989 |  |  | Local Enhancement Epic | Backlog | E-379246 | E-379246 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - Replace EOL G8Hardware in DC | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109990 |  |  | Local Enhancement Epic | Backlog | E-379247 | E-379247 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - RHEL 6 Retirement | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109991 |  |  | Local Enhancement Epic | Backlog | E-379249 | E-379249 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - RHEL 7 Retirement | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109992 |  |  | Local Enhancement Epic | Backlog | E-379250 | E-379250 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LCM - Windows 2012 Retirement | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109993 |  |  | Local Enhancement Epic | Backlog | E-379251 | E-379251 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LEFS FY25 Production Readiness and Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0109994 |  |  | Local Enhancement Epic | Backlog | E-423290 | E-423290 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-06-09
Local Enhancement Epic: Logging and Alerting (Big 6 Tech Mins) | Approved | Local Enhancement Epic | Platforms Portfolio | 0109995 |  |  | Local Enhancement Epic | Backlog | E-319855 | E-319855 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-07-31 | 2025-12-31
Local Enhancement Epic: MaaS/AMQ in LAS, MaaS enhancements | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109996 |  |  | Local Enhancement Epic | Backlog | E-433566 | E-433566 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Messaging Arch. | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109997 |  |  | Local Enhancement Epic | Backlog | E-433564 | E-433564 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Messaging Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0109998 |  |  | Local Enhancement Epic | Backlog | E-434231 | E-434231 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Migrate ALM to new ValueEdge Platform in the SaaS | Closed | Lifecycle Management Epic | Platforms Portfolio | 0109999 |  |  | Lifecycle Management Epic | Backlog | E-423987 | E-423987 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Migration of Toll Free Lines to IP Toll Free | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110000 |  |  | Local Enhancement Epic | Backlog | E-476216 | E-476216 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Multi-data center Active Everywhere with failover | Approved | Local Enhancement Epic | Platforms Portfolio | 0110001 |  |  | Local Enhancement Epic | Backlog | E-319150 | E-319150 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-07
Local Enhancement Epic: Network Automation And Tooling KTLO | Closed | Local Enhancement Epic | Platforms Portfolio | 0110002 |  |  | Local Enhancement Epic | Backlog | E-390661 | E-390661 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Network Automation Demand | Closed | Local Enhancement Epic | Platforms Portfolio | 0110003 |  |  | Local Enhancement Epic | Backlog | E-390657 | E-390657 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Network Tooling Demand | Closed | Local Enhancement Epic | Platforms Portfolio | 0110004 |  |  | Local Enhancement Epic | Backlog | E-390659 | E-390659 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Airway bill Default Setting in FARM | Approved | Local Enhancement Epic | Platforms Portfolio | 0110005 |  |  | Local Enhancement Epic | Build | E-474291 | E-474291 | 1: XS | 2025-08-13 |  |  | 1 | 0 | 1 | 0 | No | 2025-10-08 | 2026-03-10 | 2025-08-13
Local Enhancement Epic: Next Gen Server Evaluations | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110006 |  |  | Local Enhancement Epic | Backlog | E-434458 | E-434458 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: NOI for datachanges in ePP | Approved | Local Enhancement Epic | Platforms Portfolio | 0110007 |  |  | Local Enhancement Epic | Backlog | E-433092 | E-433092 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-31
Lifecycle Management Epic: On Prem Engagements | Closed | Lifecycle Management Epic | Platforms Portfolio | 0110008 |  |  | Lifecycle Management Epic | Backlog | E-433294 | E-433294 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Onboard RegCXS on CVM | Closed | Local Enhancement Epic | Platforms Portfolio | 0110009 |  |  | Local Enhancement Epic | Backlog | E-463634 | E-463634 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Oracle New Release Planning & Arch | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110010 |  |  | Local Enhancement Epic | Backlog | E-433924 | E-433924 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Pass Operational UUID into Existing Tasks Coming f | Closed | Local Enhancement Epic | Platforms Portfolio | 0110011 |  |  | Local Enhancement Epic | Backlog | E-470845 | E-470845 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: PF Infra PDSM Epic | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0110012 |  |  | Lifecycle Management Epic | Build | E-500985 | E-500985 | 4: L | 2025-07-01 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: PF Network - PDSM Epic | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110013 |  |  | Lifecycle Management Epic | Backlog | E-516854 | E-516854 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-06-23 | 2026-06-01
Local Enhancement Epic: Pickup PFS VB1 Epic C - Pickup Rating | Approved | Local Enhancement Epic | Platforms Portfolio | 0110014 |  |  | Local Enhancement Epic | Backlog | E-407465 | E-407465 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-21
Local Enhancement Epic: Product FY25 Production Readiness and Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0110015 |  |  | Local Enhancement Epic | Backlog | E-423292 | E-423292 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: Properties Projects - Business Initiative Support | Completed | Local Enhancement Epic | Platforms Portfolio | 0110016 |  |  | Local Enhancement Epic | Backlog | E-379197 | E-379197 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Software Development Lifecycle (SDLC) - 250711 | Approved | Local Enhancement Epic | Platforms Portfolio | 0110017 |  |  | Local Enhancement Epic | Build | E-116300 | E-116300 | 4: L | 2025-07-02 |  | 100% | 3 | 3 |  | 0 | No | 2024-07-22 | 2026-07-31 | 2025-07-02
Local Enhancement Epic: Ephemeral Environment Capabilities Adoption | Closed | Local Enhancement Epic | Platforms Portfolio | 0110018 |  |  | Local Enhancement Epic | Build | E-348689 | E-348689 | 5: XL | 2025-07-02 |  | 100% | 21 | 21 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: IRIS Enterprise Architecture - 250763 | Closed | Local Enhancement Epic | Platforms Portfolio | 0110019 |  |  | Local Enhancement Epic | Build | E-356059 | E-356059 | 4: L | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Local Enhancement Epic: Sparx Enterprise Architecture - 137822 | Closed | Local Enhancement Epic | Platforms Portfolio | 0110020 |  |  | Local Enhancement Epic | Build | E-356057 | E-356057 | 4: L | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Local Enhancement Epic: Refactor Core location table data in Servicenow | Approved | Local Enhancement Epic | Platforms Portfolio | 0110021 |  |  | Local Enhancement Epic | Backlog | E-512950 | E-512950 |  |  |  |  | 1 | 0 |  | 1 | No | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Rely Design Diagrams (Big 6 Tech Mins) | Approved | Local Enhancement Epic | Platforms Portfolio | 0110022 |  |  | Local Enhancement Epic | Backlog | E-319856 | E-319856 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-31
Local Enhancement Epic: Retention Strategy and Implementation for PPM Data | Closed | Local Enhancement Epic | Platforms Portfolio | 0110023 |  |  | Local Enhancement Epic | Backlog | E-403837 | E-403837 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Salesforce SaaS Integrations | Approved | Local Enhancement Epic | Platforms Portfolio | 0110024 |  |  | Local Enhancement Epic | Backlog | E-501714 | E-501714 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-28 | 2026-05-29
Local Enhancement Epic: ServiceNow - PI maintenance updates | Approved | Local Enhancement Epic | Platforms Portfolio | 0110025 |  |  | Local Enhancement Epic | Backlog | E-504522 | E-504522 | 3: M |  |  |  | 2 | 0 |  | 2 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: ServiceNow Operational Excellence and User Experie | Approved | Local Enhancement Epic | Platforms Portfolio | 0110026 |  |  | Local Enhancement Epic | Backlog | E-402048 | E-402048 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: ServiceNow Platform - Yokohama major release | Approved | Local Enhancement Epic | Platforms Portfolio | 0110027 |  |  | Local Enhancement Epic | Launch & Evaluate | E-504521 | E-504521 | 4: L | 2025-08-05 |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2025-08-15 | 2025-08-05
Local Enhancement Epic: ServiceNow Platform Foundation and Modernization F | Approved | Local Enhancement Epic | Platforms Portfolio | 0110028 |  |  | Local Enhancement Epic | Backlog | E-402026 | E-402026 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: Smartsheet Automation for TEMS Scheduling Enhancem | Closed | Local Enhancement Epic | Platforms Portfolio | 0110029 |  |  | Local Enhancement Epic | Build | E-478398 | E-478398 |  | 2025-12-09 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-09
Local Enhancement Epic: Software Distribution Support | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110030 |  |  | Local Enhancement Epic | Backlog | E-433578 | E-433578 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SQL 2012 | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110031 |  |  | Local Enhancement Epic | Backlog | E-379264 | E-379264 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SQL Server New Release Planning & Arch | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110032 |  |  | Local Enhancement Epic | Backlog | E-433869 | E-433869 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Storage Operations - day-to-day support of AppDev | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110033 |  |  | Local Enhancement Epic | Backlog | E-434475 | E-434475 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Technology Services Planning | Approved | Local Enhancement Epic | Platforms Portfolio | 0110034 |  |  | Local Enhancement Epic | Backlog | E-435152 | E-435152 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: Telecom Management | Closed | Local Enhancement Epic | Platforms Portfolio | 0110035 |  |  | Local Enhancement Epic | Done | E-435153 | E-435153 | 5: XL | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: UST FY25 Production Readiness and Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0110036 |  |  | Local Enhancement Epic | Backlog | E-446623 | E-446623 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: UST-GitHub Advanced Security | Approved | Local Enhancement Epic | Platforms Portfolio | 0110037 |  |  | Local Enhancement Epic | Backlog | E-438765 | E-438765 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2025-12-31
Local Enhancement Epic: Video and Workspace Services Break/Fix | Completed | Local Enhancement Epic | Platforms Portfolio | 0110038 |  |  | Local Enhancement Epic | Backlog | E-379210 | E-379210 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Video and Workspace Services Monitoring and Suppor | Completed | Local Enhancement Epic | Platforms Portfolio | 0110039 |  |  | Local Enhancement Epic | Backlog | E-379211 | E-379211 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Virtual Environment Support/Patching | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110040 |  |  | Local Enhancement Epic | Backlog | E-433862 | E-433862 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VMWare Monitoring | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110041 |  |  | Local Enhancement Epic | Backlog | E-434359 | E-434359 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VMWare Patching | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110042 |  |  | Local Enhancement Epic | Backlog | E-434530 | E-434530 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Windows Server Support and Monitoring | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110043 |  |  | Local Enhancement Epic | Backlog | E-434851 | E-434851 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Workshift | Approved | Local Enhancement Epic | Platforms Portfolio | 0110044 |  |  | Local Enhancement Epic | Backlog | E-424344 | E-424344 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-02-03
Local Enhancement Epic: CONDOR - Data Center Decommission | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110645 |  |  | Local Enhancement Epic | Backlog | E-433879 | E-433879 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 30669 - FY24 and FY25 Pre & Post Peak Phased rollo | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110649 | 6756 | TS-VL4-NETWORK-Office MPLS Carrier Change | Biz w/ Tech Epic | Launch & Evaluate | E-369750 | E-369750 | 5: XL | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-04-30 | 2025-06-26
Biz w/ Tech Epic: 30671 - All FXO Circuits Moved to Masergy | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110650 | 6756 | TS-VL4-NETWORK-Office MPLS Carrier Change | Biz w/ Tech Epic | Launch & Evaluate | E-369752 | E-369752 | 5: XL | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30 | 2025-06-26
Biz w/ Tech Epic: Designated Workforce Phase 2 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110651 | 9326 | [Enabler] Designated Courier Workforce Phases 1 & | Biz w/ Tech Epic | Launch & Evaluate | E-428958 | E-428958 | 3: M | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-02-09 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.1) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110652 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-421194 | E-421194 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.10) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110653 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-421214 | E-421214 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.13) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110654 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-422869 | E-422869 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.14) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110655 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-439799 | E-439799 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2026-01-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.15) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110656 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-455182 | E-455182 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-09-27 | 2026-01-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.4) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110657 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-421205 | E-421205 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.5) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110658 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-421209 | E-421209 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-30 | 2025-06-26
Biz w/ Tech Epic: Ground Rating Modernization (GRM) VB2 (2.9) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110659 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Launch & Evaluate | E-421213 | E-421213 | 4: L | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-30 | 2025-06-26
Biz w/ Tech Epic: GSP to Direct Serve- Slovakia | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110660 | 7528 | Enable- G2D conversion Slovakia ( ACE enablement) | Biz w/ Tech Epic | Launch & Evaluate | E-436221 | E-436221 | 3: M | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-04-14 | 2025-06-26
Biz w/ Tech Epic: Support for EU Dangerous Goods by Road part 3A | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0110661 | 9372 | Enable a scalable FedEx DG road offering allowing | Biz w/ Tech Epic | Launch & Evaluate | E-435729 | E-435729 | 3: M | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2026-10-08 | 2025-06-26
Lifecycle Management Epic: FY26_PI3_Platforms_LCM_ValueEdgeOctane_Upgrade | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110754 |  |  | Lifecycle Management Epic | Build | E-522341 | E-522341 | 1: XS | 2025-08-25 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-04-09 | 2025-08-25
Local Enhancement Epic: Empowering Chatbot and Designing Mindmaps | Approved | Local Enhancement Epic | Platforms Portfolio | 0110774 |  |  | Local Enhancement Epic | Build | E-538245 | E-538245 | 2: S | 2025-11-14 |  |  | 1 | 0 | 1 | 0 | No | 2025-10-08 | 2027-06-17 | 2025-11-14
Lifecycle Management Epic: FY26Q2-Q4_Platforms_X-MEN_Production_Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110777 |  |  | Lifecycle Management Epic | Backlog | E-521565 | E-521565 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-17 | 2026-05-29
Lifecycle Management Epic: InfoSec - EIAM FIRST Support - CY25PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110778 |  |  | Lifecycle Management Epic | Build | E-521566 | E-521566 | 2: S | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No | 2025-08-04 | 2025-10-10 | 2025-09-19
Local Enhancement Epic: TEN-51192 (3389) Vulnerability Remediation CY25PI4 | Closed | Local Enhancement Epic | Platforms Portfolio | 0110779 |  |  | Local Enhancement Epic | Done | E-521533 | E-521533 | 1: XS | 2025-09-03 | 2025-09-05 | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-03 | 2025-09-05
Local Enhancement Epic: INFOSEC - Setting up a password reset workflow | Not Started | Local Enhancement Epic | Platforms Portfolio | 0110780 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI 04 OT/IoT Engineering | Closed | Lifecycle Management Epic | Platforms Portfolio | 0110793 |  |  | Lifecycle Management Epic | Build | E-521722 | E-521722 | 3: M | 2025-08-21 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-21
Lifecycle Management Epic: CY25 PI 04 OT/IoT Governance | Closed | Lifecycle Management Epic | Platforms Portfolio | 0110794 |  |  | Lifecycle Management Epic | Build | E-521718 | E-521718 | 2: S | 2025-08-21 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-21
Local Enhancement Epic: PL_Siedlce Station extension | Closed | Local Enhancement Epic | Platforms Portfolio | 0110795 |  |  | Local Enhancement Epic | Backlog | E-526458 | E-526458 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dial Plan Standardization in Cloud | Closed | Local Enhancement Epic | Platforms Portfolio | 0110796 |  |  | Local Enhancement Epic | Build | E-536552 | E-536552 | 2: S | 2025-10-28 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-28
Local Enhancement Epic: Dial Plan Standardization in Cloud | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110797 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CMDB Data Export/API Int for Ent Risk Assessment | Not Started | Local Enhancement Epic | Platforms Portfolio | 0110798 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec - CY25 SNVR VIT Pending Decom Automation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0110799 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26 IBM Lab Services | Approved | Local Enhancement Epic | Platforms Portfolio | 0110812 |  |  | Local Enhancement Epic | Build | E-548894 | E-548894 | 2: S | 2026-01-14 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-08-04 | 2026-01-14
Lifecycle Management Epic: InfoSec - FY26_TG_Production_Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110814 |  |  | Lifecycle Management Epic | Build | E-522720 | E-522720 | 4: L | 2025-07-17 |  | 66.67% | 9 | 6 | 3 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-07-17
Lifecycle Management Epic: CY25/26 Endpoint Crowdstrike Enhancement | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110821 |  |  | Lifecycle Management Epic | Build | E-521457 | E-521457 | 2: S | 2025-08-21 |  |  | 2 | 0 | 2 | 0 | No | 2025-08-04 | 2026-05-29 | 2025-08-21
Local Enhancement Epic: PL_Siedlce Station extension | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0110882 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26-PF-LEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110885 |  |  | Lifecycle Management Epic | Build | E-523770 | E-523770 | 3: M | 2025-08-26 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-08-07 | 2025-08-26
Local Enhancement Epic: InfoSec - IDPT - BRT Archer/Onspring Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0110905 |  |  | Local Enhancement Epic | Build | E-531580 | E-531580 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-22 | 2026-03-30 | 2026-02-06
Local Enhancement Epic: [UDS – CANIP] – Platforms Portfolio | Closed | Local Enhancement Epic | Platforms Portfolio | 0110943 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537986 | E-537986 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: FY26_PI4_Platforms_LCM_CEFS_CCOB-Modernization | Closed | Lifecycle Management Epic | Platforms Portfolio | 0110984 |  |  | Lifecycle Management Epic | Build | E-523705 | E-523705 | 3: M | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Biz w/ Tech Epic: OKTA SaaS License Integration | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0110983 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Workday SaaS License Integration | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0110985 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Citrix SaaS License Integration | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0110986 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DigiAI SaaS License Integration | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0110989 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26-PF-AEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110988 |  |  | Lifecycle Management Epic | Build | E-522721 | E-522721 | 3: M | 2025-09-25 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2026-05-29 | 2025-09-25
Lifecycle Management Epic: InfoSec - IDPT - BRT Archer/Onspring ProdSupport | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110995 |  |  | Lifecycle Management Epic | Backlog | E-531535 | E-531535 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-08-21 | 2026-05-29
Lifecycle Management Epic: Tooling - Global Network Engineering - CY25 PI04 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0110998 |  |  | Lifecycle Management Epic | Build | E-522717 | E-522717 | 1: XS | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-19
Lifecycle Management Epic: Patching - Global Network Engineering - FY25 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0110999 |  |  | Lifecycle Management Epic | Build | E-522865 | E-522865 | 1: XS | 2025-09-19 |  | 50% | 2 | 1 | 1 | 0 | No | 2025-07-18 | 2026-05-29 | 2025-09-19
Lifecycle Management Epic: Tooling-PF-EFS-Address-AEFS ART-CY25 PI4 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111001 |  |  | Lifecycle Management Epic | Build | E-523697 | E-523697 | 1: XS | 2026-01-09 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-01-09
Local Enhancement Epic: CA - Enable access to eCIS BRE field | Approved | Local Enhancement Epic | Platforms Portfolio | 0111002 |  |  | Local Enhancement Epic | Build | E-540016 | E-540016 | 1: XS | 2025-10-20 |  | 50% | 2 | 1 |  | 1 | No | 2024-07-22 | 2026-03-31 | 2025-10-20
Local Enhancement Epic: Global Address Service US/CA Foundations | Approved | Local Enhancement Epic | Platforms Portfolio | 0111003 |  |  | Local Enhancement Epic | Build | E-522723 | E-522723 | 3: M | 2025-07-25 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-04-15 | 2025-07-25
Local Enhancement Epic: API Account - Access to vulnerability table | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111004 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Compliance-PF-AEFS- ART-CY25 PI5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111005 |  |  | Lifecycle Management Epic | Build | E-524726 | E-524726 | 1: XS | 2025-11-14 |  | 100% | 1 | 1 |  | 0 | No | 2025-10-08 | 2026-02-24 | 2025-11-14
Lifecycle Management Epic: Tooling-PF-EFS-AEFS -ART-CY25 PI5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111006 |  |  | Lifecycle Management Epic | Build | E-523700 | E-523700 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2025-10-08 | 2025-12-31 | 2025-09-25
Lifecycle Management Epic: InfoSec - FY26_TG_Information Sec Prod Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111007 |  |  | Lifecycle Management Epic | Build | E-522718 | E-522718 | 4: L | 2025-07-17 |  | 64.44% | 45 | 29 | 12 | 4 | No | 2025-06-02 | 2026-05-29 | 2025-07-17
Lifecycle Management Epic: Compliance-PF-AEFS- ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111008 |  |  | Lifecycle Management Epic | Build | E-523698 | E-523698 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: FY26_Platform_CRISPS_Production Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111020 |  |  | Lifecycle Management Epic | Build | E-524941 | E-524941 | 3: M | 2025-09-26 |  |  | 2 | 0 | 2 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-09-26
Local Enhancement Epic: InfoSec: stale data removal automation for Illumio | Closed | Local Enhancement Epic | Platforms Portfolio | 0111024 |  |  | Local Enhancement Epic | Build | E-524942 | E-524942 | 1: XS | 2025-09-19 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-19
Lifecycle Management Epic: FY26 Canada Network LCM. | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111027 |  |  | Lifecycle Management Epic | Build | E-529928 | E-529928 | 4: L | 2025-07-11 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-22 | 2026-05-29 | 2025-07-11
Lifecycle Management Epic: FY26 Canada Network LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111028 |  |  | Lifecycle Management Epic | Build | E-522380 | E-522380 | 4: L | 2025-07-10 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-12-31 | 2025-07-10
Lifecycle Management Epic: Upgrades - Global Network Engineering - CY25 PI04 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111029 |  |  | Lifecycle Management Epic | Build | E-522867 | E-522867 | 1: XS | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-19
Lifecycle Management Epic: InfoSec-LCM-EIAM-Vulnerability-Management-CY25PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111045 |  |  | Lifecycle Management Epic | Build | E-522719 | E-522719 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2025-08-04 | 2025-10-10 | 2025-09-25
Local Enhancement Epic: PL Zielona Góra new facility | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0111046 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26-FIT-EU-Enterprise Fax-EMEA 5589 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111048 |  |  | Lifecycle Management Epic | Backlog | E-526652 | E-526652 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-03-30
Local Enhancement Epic: AppViewX EST Agent Evaluation | Approved | Local Enhancement Epic | Platforms Portfolio | 0111049 |  |  | Local Enhancement Epic | Launch & Evaluate | E-522585 | E-522585 | 2: S | 2025-07-11 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-11
Local Enhancement Epic: Rewrite Active Directory Toolkit C# | Approved | Local Enhancement Epic | Platforms Portfolio | 0111050 |  |  | Local Enhancement Epic | Launch & Evaluate | E-522587 | E-522587 | 1: XS | 2025-07-11 |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-11
Local Enhancement Epic: PL Nowy Sacz New station | On Hold | Local Enhancement Epic | Platforms Portfolio | 0111055 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: AppViewX Certificate Lifecycle Contract Renewal | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111056 |  |  | Lifecycle Management Epic | Build | E-522379 | E-522379 | 2: S | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-10-10 | 2025-09-19
Local Enhancement Epic: Delphix International Expansion | Approved | Local Enhancement Epic | Platforms Portfolio | 0111057 |  |  | Local Enhancement Epic | Build | E-538925 | E-538925 | 2: S | 2025-10-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-03 | 2026-04-30 | 2025-10-23
Local Enhancement Epic: FY26_Pl4_Platforms_Enterprise_QA_POC | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0111058 |  |  | Local Enhancement Epic | Build | E-524803 | E-524803 | 2: S | 2025-09-17 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-17
Biz w/ Tech Epic: Transitioning International SAM Tiles into Global | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0111072 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_Platforms_PF ITOM Asset-Avengers_Prod Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111115 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-524157 | E-524157 | 3: M | 2025-07-17 |  | 6.667% | 15 | 1 | 12 | 2 | No | 2025-07-22 | 2026-05-29 | 2025-07-17
Lifecycle Management Epic: FY26_Platforms_Infra_AMP_LCM_PDSM | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111120 |  |  | Lifecycle Management Epic | Build | E-527683 | E-527683 | 2: S | 2025-08-13 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-13
Lifecycle Management Epic: FY26_Platforms_InfrastructurePlatform_LCM_PDSM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111122 |  |  | Lifecycle Management Epic | Build | E-524636 | E-524636 | 4: L | 2025-09-10 |  |  | 2 | 0 | 1 | 1 | No | 2025-11-05 | 2026-05-29 | 2025-09-10
Lifecycle Management Epic: FY26_PI4_Platforms_LCM_CEFS_EFWS-Modernization | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111127 |  |  | Lifecycle Management Epic | Build | E-523701 | E-523701 | 3: M | 2025-09-11 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-11
Lifecycle Management Epic: FY26_PI4_Platforms_LCM_CEFS_SABT-Modernization | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111135 |  |  | Lifecycle Management Epic | Build | E-523702 | E-523702 | 3: M | 2025-10-20 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-20
Lifecycle Management Epic: FY26_PI4_Platforms_LCM_CEFS_CIMOPS-Modernization | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111137 |  |  | Lifecycle Management Epic | Build | E-523699 | E-523699 | 3: M | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-25
Lifecycle Management Epic: FY26_PI4_Platforms_LCM_CEFS_CPP-UI-Modernization | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111138 |  |  | Lifecycle Management Epic | Backlog | E-524136 | E-524136 | 3: M |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: FY26-PF-PEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111139 |  |  | Lifecycle Management Epic | Build | E-523704 | E-523704 | 3: M | 2025-08-18 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-10-15 | 2025-08-18
Local Enhancement Epic: LE - eCIS & eCUSTBATCH Product Enhancements FY25 | Closed | Local Enhancement Epic | Platforms Portfolio | 0111140 |  |  | Local Enhancement Epic | Build | E-524070 | E-524070 | 2: S | 2025-08-27 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: FY26-PF-CEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111141 |  |  | Lifecycle Management Epic | Build | E-523707 | E-523707 | 3: M | 2025-08-20 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2026-05-29 | 2025-08-20
Lifecycle Management Epic: FY26-PF-GEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111142 |  |  | Lifecycle Management Epic | Build | E-523703 | E-523703 | 3: M | 2025-08-08 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-08-08
Lifecycle Management Epic: FY26-PF-GpEFS-Production-Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111143 |  |  | Lifecycle Management Epic | Build | E-523706 | E-523706 | 3: M | 2025-09-25 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-09-25
Local Enhancement Epic: Next Generation messaging POC | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111180 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Next Gen Messaging | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0111182 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TS-VL3-Next Generation Messaging Platform | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0111183 | 92246 | TS-VL3-Messaging-NextGen Messaging Platform | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: OneItaly - Vendor Connectivity | Approved | Local Enhancement Epic | Platforms Portfolio | 0111185 |  |  | Local Enhancement Epic | Backlog | E-530092 | E-530092 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: FY26_Platforms_Non-PDSM_Production_Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0111206 |  |  | Local Enhancement Epic | Build | E-524802 | E-524802 | 2: S | 2025-09-17 |  |  | 2 | 0 | 2 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-09-17
Local Enhancement Epic: Platforms_PrometheusExporter_Enhancement | Approved | Local Enhancement Epic | Platforms Portfolio | 0111227 |  |  | Local Enhancement Epic | Build | E-532142 | E-532142 | 3: M | 2025-09-10 |  | 66.67% | 3 | 2 | 1 | 0 | No | 2024-07-22 | 2025-12-30 | 2025-09-10
Lifecycle Management Epic: Infosec - Firewall LCM CY25 PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111240 |  |  | Lifecycle Management Epic | Build | E-525260 | E-525260 | 1: XS | 2025-09-19 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-29 | 2026-01-02 | 2025-09-19
Local Enhancement Epic: InfoSec CloudOps VRA Load Balancer data to Illumio | Approved | Local Enhancement Epic | Platforms Portfolio | 0111242 |  |  | Local Enhancement Epic | Backlog | E-524206 | E-524206 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2025-11-04
Local Enhancement Epic: IPAM Global Meta Data Governance | Approved | Local Enhancement Epic | Platforms Portfolio | 0111256 |  |  | Local Enhancement Epic | Backlog | E-530815 | E-530815 | 1: XS |  |  |  | 3 | 0 |  | 3 | No
Local Enhancement Epic: InfoSec - Akamai API Call Integration With XSIAM | Completed | Local Enhancement Epic | Platforms Portfolio | 0111271 |  |  | Local Enhancement Epic | Backlog | E-524944 | E-524944 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: Compliance Work - PF - EFS - Customer - CY25-PI-4 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111275 |  |  | Lifecycle Management Epic | Build | E-534154 | E-534154 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-09-25
Local Enhancement Epic: Faciltiy AV installations | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111281 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Compliance Work - PF - EFS - Customer - CY25-PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111285 |  |  | Lifecycle Management Epic | Build | E-534157 | E-534157 | 1: XS | 2025-09-26 |  | 100% | 1 | 1 |  | 0 | No | 2025-10-08 | 2025-12-31 | 2025-09-26
Lifecycle Management Epic: Tooling Work - PF - EFS - Customer - CY25-PI-4 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111286 |  |  | Lifecycle Management Epic | Build | E-534155 | E-534155 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-09-25
Lifecycle Management Epic: Tooling Work - PF - EFS - Customer - CY25-PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111289 |  |  | Lifecycle Management Epic | Build | E-534156 | E-534156 | 1: XS | 2025-10-20 |  |  | 2 | 0 | 2 | 0 | No | 2025-10-08 | 2025-12-31 | 2025-10-20
Lifecycle Management Epic: Upgrades-PF-AEFS- ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111292 |  |  | Lifecycle Management Epic | Build | E-524940 | E-524940 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: FY26_Platforms_Network Domestic_LCM_PDSM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111296 |  |  | Lifecycle Management Epic | Build | E-525252 | E-525252 | 1: XS | 2025-09-19 |  | 75% | 4 | 3 | 1 | 0 | No | 2024-07-22 | 2028-06-23 | 2025-09-19
Lifecycle Management Epic: Upgrades-PF-AEFS- ART-CY25 PI5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111301 |  |  | Lifecycle Management Epic | Build | E-524939 | E-524939 | 1: XS | 2025-09-26 |  | 100% | 1 | 1 |  | 0 | No | 2025-10-08 | 2025-12-31 | 2025-09-26
Lifecycle Management Epic: Patching-PF-AEFS- ART-CY25 PI5 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111304 |  |  | Lifecycle Management Epic | Backlog | E-524936 | E-524936 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26-Patching-PF-AEFS- ART | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111305 |  |  | Lifecycle Management Epic | Build | E-524938 | E-524938 | 1: XS | 2025-08-27 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2028-06-15 | 2025-08-27
Lifecycle Management Epic: Infosec LCM Cyber Knights CY25PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111306 |  |  | Lifecycle Management Epic | Build | E-525253 | E-525253 | 2: S | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-10-10 | 2025-09-19
Lifecycle Management Epic: EIAM Audit Support CY25PI04 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111307 |  |  | Lifecycle Management Epic | Build | E-525258 | E-525258 | 2: S | 2025-09-20 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-20
Local Enhancement Epic: PF - CEFS - CPP - Big 6 - LE | Approved | Local Enhancement Epic | Platforms Portfolio | 0111311 |  |  | Local Enhancement Epic | Build | E-534829 | E-534829 | 4: L | 2026-02-04 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-12-30 | 2026-02-04
Local Enhancement Epic: PF-SEFS-Big6-Support-LE | Completed | Local Enhancement Epic | Platforms Portfolio | 0111313 |  |  | Local Enhancement Epic | Build | E-525452 | E-525452 | 2: S | 2025-08-13 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-13
Lifecycle Management Epic: FY26_InfoSec_Red Team Enh_Production Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111315 |  |  | Lifecycle Management Epic | Build | E-524727 | E-524727 | 2: S | 2025-09-19 |  | 33.33% | 3 | 1 |  | 2 | No | 2024-07-22 | 2025-10-10 | 2025-09-19
Lifecycle Management Epic: FY26_Infosec_Forensics CM RI_Production Support | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111316 |  |  | Lifecycle Management Epic | Backlog | E-524724 | E-524724 | 2: S |  |  |  | 2 | 0 |  | 2 | No
Lifecycle Management Epic: Quarterly Critical Patch Updates for Enterprise | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111317 |  |  | Lifecycle Management Epic | Build | E-544033 | E-544033 | 4: L | 2025-10-28 |  | 12.5% | 8 | 1 | 4 | 3 | No | 2024-07-22 | 2029-10-01 | 2025-10-28
Lifecycle Management Epic: Compliance/L&R/Audits - GNE team - CY25 PI04 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111318 |  |  | Lifecycle Management Epic | Build | E-525250 | E-525250 | 1: XS | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-19
Lifecycle Management Epic: Infosec LCM Always on Avengers CY25PI04 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111319 |  |  | Lifecycle Management Epic | Build | E-524943 | E-524943 | 2: S | 2025-09-19 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-19
Local Enhancement Epic: PF-AEFS-ART-Big6 Support | Approved | Local Enhancement Epic | Platforms Portfolio | 0111320 |  |  | Local Enhancement Epic | Build | E-524937 | E-524937 | 2: S | 2025-08-13 |  |  | 1 | 0 |  | 1 | No | 2025-07-30 | 2025-12-30 | 2025-08-13
Lifecycle Management Epic: Video Conferencing Life Cycle Management | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0111321 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EPIC 1: Manage & Use Established Business Relation | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0107991 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Discovery Transformation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111382 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2025-08-05 | 2025-09-15
Local Enhancement Epic: Discoverey Transformation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111383 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Infosec - Illumio migration from CoLo to SaaS | Approved | Local Enhancement Epic | Platforms Portfolio | 0111410 |  |  | Local Enhancement Epic | Build | E-526895 | E-526895 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2026-02-06
Local Enhancement Epic: InfoSec - Illumio migration from CoLo to SaaS | Approved | Local Enhancement Epic | Platforms Portfolio | 0111412 |  |  | Local Enhancement Epic | Build | E-526894 | E-526894 | 2: S | 2025-09-18 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-12-31 | 2025-09-18
Local Enhancement Epic: InfoSec - Crowdstrike Falcon Exposure Mgmt | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111420 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: B454 to C201 Relocation RTO | Approved | Local Enhancement Epic | Platforms Portfolio | 0111505 |  |  | Local Enhancement Epic | Build | E-533027 | E-533027 | 2: S | 2025-10-28 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2026-10-14 | 2025-10-28
Lifecycle Management Epic: Compliance-PF-EFS-Location-LEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111549 |  |  | Lifecycle Management Epic | Build | E-526378 | E-526378 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-25
Lifecycle Management Epic: Compliance-PF-EFS-Geopolitical-GpEFSPLG ARTCY25PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111550 |  |  | Lifecycle Management Epic | Build | E-526373 | E-526373 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: Patching-PF-EFS-Geopolitical-GpEFS-PLG ART-FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111551 |  |  | Lifecycle Management Epic | Build | E-526380 | E-526380 | 1: XS | 2025-09-25 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2026-05-29 | 2025-09-25
Lifecycle Management Epic: Patching-PF-EFS-Geography-GEFS-PLG ART-FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111552 |  |  | Lifecycle Management Epic | Build | E-526381 | E-526381 | 1: XS | 2025-08-08 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-08-08
Lifecycle Management Epic: Compliance-PF-EFS-Product-PEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111553 |  |  | Lifecycle Management Epic | Build | E-526382 | E-526382 | 1: XS | 2025-08-18 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-18
Local Enhancement Epic: PF-LEFS-Big 6/Beyond Big 6 -Support-LE | Closed | Local Enhancement Epic | Platforms Portfolio | 0111554 |  |  | Local Enhancement Epic | Build | E-531834 | E-531834 | 2: S | 2025-10-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-10
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111555 |  |  | Lifecycle Management Epic | Build | E-526383 | E-526383 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: Upgrade-PF-EFS-Location-LEFS-PLG ART-CY25 PI4 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111556 |  |  | Lifecycle Management Epic | Build | E-532873 | E-532873 | 1: XS | 2025-10-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-10
Lifecycle Management Epic: Patching-PF-EFS-Product-PEFS-PLG ART-FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111557 |  |  | Lifecycle Management Epic | Build | E-526374 | E-526374 | 1: XS | 2025-08-18 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-06-08 | 2025-08-18
Local Enhancement Epic: PF-GEFS-Big 6/Beyond Big 6 -Support-LE | Approved | Local Enhancement Epic | Platforms Portfolio | 0111558 |  |  | Local Enhancement Epic | Build | E-535502 | E-535502 | 2: S | 2025-10-15 |  |  | 1 | 0 | 1 | 0 | No | 2024-12-19 | 2026-05-29 | 2025-10-15
Local Enhancement Epic: PF-GpEFS-Big 6/Beyond Big 6 -Support-LE | Closed | Local Enhancement Epic | Platforms Portfolio | 0111559 |  |  | Local Enhancement Epic | Build | E-535001 | E-535001 | 2: S | 2025-11-13 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-13
Local Enhancement Epic: PF-PEFS-Big 6/Beyond Big 6 -Support-LE | Approved | Local Enhancement Epic | Platforms Portfolio | 0111560 |  |  | Local Enhancement Epic | Build | E-535002 | E-535002 | 2: S | 2025-10-09 |  |  | 1 | 0 | 1 | 0 | No | 2024-12-19 | 2026-05-29 | 2025-10-09
Lifecycle Management Epic: Tooling-PF-EFS-Geopolitical-GpEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111561 |  |  | Lifecycle Management Epic | Build | E-526376 | E-526376 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: Tooling-PF-EFS-Geography-GEFS ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111564 |  |  | Lifecycle Management Epic | Build | E-526372 | E-526372 | 1: XS | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-25
Lifecycle Management Epic: Tooling-PF-EFS-Product-PEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111565 |  |  | Lifecycle Management Epic | Build | E-526384 | E-526384 | 1: XS | 2025-08-18 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-18
Lifecycle Management Epic: Upgrade-PF-EFS-Product-PEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111568 |  |  | Lifecycle Management Epic | Build | E-526385 | E-526385 | 1: XS | 2025-08-18 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-18
Lifecycle Management Epic: Upgrade-PF-EFS-Geopolitical-GpEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111569 |  |  | Lifecycle Management Epic | Build | E-526377 | E-526377 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: Upgrade-PF-EFS-Geography-GEFS-PLG ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111570 |  |  | Lifecycle Management Epic | Build | E-526375 | E-526375 | 1: XS | 2025-08-27 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-27
Lifecycle Management Epic: Compliance-PF-EFS-Geography-GEFS ART-CY25 PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111571 |  |  | Lifecycle Management Epic | Build | E-526379 | E-526379 | 1: XS | 2025-09-26 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-26
Lifecycle Management Epic: Patching-PF-EFS-Location-LEFS-PLG ART-FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111572 |  |  | Lifecycle Management Epic | Build | E-532872 | E-532872 | 1: XS | 2025-08-27 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-08-27
Lifecycle Management Epic: FY26_Platforms_LCM_ETGOpenTextUpgrades | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111575 |  |  | Lifecycle Management Epic | Build | E-527120 | E-527120 | 2: S | 2025-08-22 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-08-22
Lifecycle Management Epic: FY26_Platforms_LCM_ETGIntegrationUpgrades | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111576 |  |  | Lifecycle Management Epic | Build | E-527119 | E-527119 | 2: S | 2025-08-22 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-04-09 | 2025-08-22
Lifecycle Management Epic: FY26_Platforms_LCM_DRIVEGovernanceandArch | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111577 |  |  | Lifecycle Management Epic | Build | E-527280 | E-527280 | 2: S | 2026-03-16 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-04-12 | 2026-03-16
Lifecycle Management Epic: InfoSec LCM Secret Hustlers (PAM) CY25PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111578 |  |  | Lifecycle Management Epic | Build | E-529869 | E-529869 | 2: S | 2025-09-18 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-10-10 | 2025-09-18
Local Enhancement Epic: Helpdesk IVR - Password Reset Restrictions Exempt | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0111579 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Infosec - LCM - Attack Surface Analytics CY25PI4 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111580 |  |  | Lifecycle Management Epic | Backlog | E-526893 | E-526893 | 5: XL |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: InfoSec LCM 5th Dimension CY25PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111582 |  |  | Lifecycle Management Epic | Build | E-530031 | E-530031 | 2: S | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-10-03 | 2025-09-25
Lifecycle Management Epic: MDS Modules Replacement - Atherstone | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0111586 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec-Cloud Incident Response | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111703 |  |  | Lifecycle Management Epic | Build | E-527682 | E-527682 | 2: S | 2025-09-10 |  |  | 3 | 0 | 2 | 1 | No | 2024-07-22 | 2026-05-29 | 2025-09-10
Lifecycle Management Epic: FY26 LCM Oracle DB Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111706 |  |  | Lifecycle Management Epic | Build | E-528077 | E-528077 | 1: XS | 2025-09-11 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-07-31 | 2025-09-11
Local Enhancement Epic: Data & Technology Data Collection Automation | Closed | Local Enhancement Epic | Platforms Portfolio | 0111730 |  |  | Local Enhancement Epic | Build | E-527784 | E-527784 | 3: M | 2025-09-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-23
Lifecycle Management Epic: Servicenow Work Request and Incident Bucket | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111731 |  |  | Lifecycle Management Epic | Build | E-535902 | E-535902 | 2: S | 2026-04-08 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2026-04-08
Local Enhancement Epic: InfoSec - SaaS Security Posture Management (SSPM) | Approved | Local Enhancement Epic | Platforms Portfolio | 0111732 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541173 | E-541173 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ANC Close Off-Airport Warehouse Facility | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111733 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec Compliance and Regulatory Support_FY26 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111734 |  |  | Lifecycle Management Epic | Backlog | E-528013 | E-528013 | 2: S |  |  | 100% | 1 | 1 |  | 0 | No
Lifecycle Management Epic: Support for adding an additional LOB (IPW) to TP M | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0111735 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 LCM SQL DB Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111747 |  |  | Lifecycle Management Epic | Build | E-528347 | E-528347 | 1: XS | 2025-09-11 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-07-31 | 2025-09-11
Lifecycle Management Epic: FY26 LCM Redis DB Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111748 |  |  | Lifecycle Management Epic | Build | E-528346 | E-528346 | 1: XS | 2025-09-11 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-06-11 | 2025-09-11
Lifecycle Management Epic: FY26 LCM DataStax DB Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111752 |  |  | Lifecycle Management Epic | Build | E-528350 | E-528350 | 1: XS | 2025-09-11 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-07-31 | 2025-09-11
Lifecycle Management Epic: FY26 LCM RHEL OS Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111753 |  |  | Lifecycle Management Epic | Build | E-528348 | E-528348 | 1: XS | 2025-09-11 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-07-31 | 2025-09-11
Lifecycle Management Epic: FY26 LCM Windows OS Patching | Closed | Lifecycle Management Epic | Platforms Portfolio | 0111755 |  |  | Lifecycle Management Epic | Build | E-528353 | E-528353 | 1: XS | 2025-09-11 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-11
Local Enhancement Epic: DSE Cohesity | Approved | Local Enhancement Epic | Platforms Portfolio | 0111756 |  |  | Local Enhancement Epic | Build | E-528352 | E-528352 | 1: XS | 2025-09-10 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-06-28 | 2025-09-10
Local Enhancement Epic: Puppet Deployment Valkey | Approved | Local Enhancement Epic | Platforms Portfolio | 0111757 |  |  | Local Enhancement Epic | Build | E-528349 | E-528349 | 1: XS | 2025-09-03 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-04-09 | 2025-09-03
Local Enhancement Epic: FedEx VMware VROPS to ServiceNOW Integration | Rejected | Local Enhancement Epic | Platforms Portfolio | 0111760 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Oracle Cohesity | Approved | Local Enhancement Epic | Platforms Portfolio | 0111761 |  |  | Local Enhancement Epic | Build | E-528351 | E-528351 | 2: S | 2025-09-03 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-03-31 | 2025-09-03
Local Enhancement Epic: SQL Server Audit/Security Enhancement | Closed | Local Enhancement Epic | Platforms Portfolio | 0111762 |  |  | Local Enhancement Epic | Build | E-528354 | E-528354 | 1: XS | 2025-09-03 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-03
Local Enhancement Epic: CSDM EMMa3D Install and Licensing | Approved | Local Enhancement Epic | Platforms Portfolio | 0111817 |  |  | Local Enhancement Epic | Backlog | E-535222 | E-535222 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-07 | 2027-06-02
Local Enhancement Epic: Work force intelligence | In Progress | Local Enhancement Epic | Platforms Portfolio | 0111151 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MNL Gateway Relocation Plan | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0111864 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FCP - Delphix Ephemeral VDBs | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111872 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FCP - Delphix Multi Region DR in EMEA | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111876 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FCP - Delphix Hyperscale POC & MVP | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111901 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: F5 - Load Balancing | Approved | Local Enhancement Epic | Platforms Portfolio | 0111931 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543502 | E-543502 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-08 | 2026-03-30
Local Enhancement Epic: DC Circuit Redundancy Investigation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0111932 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Support for Adding Shipper LOB to Telus Morocco | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0111937 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_Platform_CRISPS_ Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0111939 |  |  | Lifecycle Management Epic | Build | E-531461 | E-531461 | 3: M | 2025-09-25 |  |  | 2 | 0 | 1 | 1 | No | 2024-07-22 | 2026-05-29 | 2025-09-25
Local Enhancement Epic: Info Sec CY25 OT/IOT Specific Risk Scores | Closed | Local Enhancement Epic | Platforms Portfolio | 0111940 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539140 | E-539140 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: Tools onboarding to FCP | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0111957 | 109485 | Standard Operating Procedure - Automated Planning | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Platforms_Jarvis_New_Features | Approved | Local Enhancement Epic | Platforms Portfolio | 0111964 |  |  | Local Enhancement Epic | Build | E-530295 | E-530295 | 3: M | 2025-09-16 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-05-29 | 2025-09-16
Biz w/ Tech Epic: Test | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0111974 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Infosec - Illumio cloud secure svc for SAAS | On Hold | Local Enhancement Epic | Platforms Portfolio | 0112014 |  |  | Local Enhancement Epic | Build | E-530802 | E-530802 | 1: XS | 2025-09-26 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-09-26
Lifecycle Management Epic: CAL7 Upgrade - PI5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112016 |  |  | Lifecycle Management Epic | Build | E-538926 | E-538926 | 3: M | 2026-02-25 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-23 | 2026-05-29 | 2026-02-25
Local Enhancement Epic: Shannon Property Project - Local Enhancement | Approved | Local Enhancement Epic | Platforms Portfolio | 0112018 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543911 | E-543911 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-09 | 2026-03-30
Local Enhancement Epic: FY26_PI4_Platforms_Enterprise_OEM_Metrics | Closed | Local Enhancement Epic | Platforms Portfolio | 0112020 |  |  | Local Enhancement Epic | Build | E-533713 | E-533713 | 2: S | 2025-09-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-02
Local Enhancement Epic: Platforms_Enterprise_Grafana_Enhancement | Closed | Local Enhancement Epic | Platforms Portfolio | 0112026 |  |  | Local Enhancement Epic | Build | E-533716 | E-533716 | 2: S | 2025-09-16 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-16
Lifecycle Management Epic: Infosec - Vulnerability Disclosure Program Launch | Closed | Lifecycle Management Epic | Platforms Portfolio | 0112028 |  |  | Lifecycle Management Epic | Build | E-530901 | E-530901 | 2: S | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-23
Local Enhancement Epic: FY26_Platforms_Enterprise_Archival Eval POC | Approved | Local Enhancement Epic | Platforms Portfolio | 0112030 |  |  | Local Enhancement Epic | Build | E-537109 | E-537109 | 1: XS | 2025-10-28 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-03-13 | 2025-10-28
Local Enhancement Epic: Move WTC JMS queues to Colo | Completed | Local Enhancement Epic | Platforms Portfolio | 0112031 |  |  | Local Enhancement Epic | Build | E-536012 | E-536012 | 3: M | 2025-10-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-15
Local Enhancement Epic: PDSM API User Access | Rejected | Local Enhancement Epic | Platforms Portfolio | 0112032 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update Netbox and Circuitcon with ISP Maintenance | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112033 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Change Passwords on JMS queues for security | Completed | Local Enhancement Epic | Platforms Portfolio | 0112034 |  |  | Local Enhancement Epic | Build | E-536013 | E-536013 | 3: M | 2025-10-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-15
Local Enhancement Epic: Discovery Transformation | On Hold | Local Enhancement Epic | Platforms Portfolio | 0112035 |  |  | Local Enhancement Epic | Backlog | E-532992 | E-532992 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-08-18 | 2026-04-30
Local Enhancement Epic: Workforce Intelligence | Approved | Local Enhancement Epic | Platforms Portfolio | 0112046 |  |  | Local Enhancement Epic | Backlog | E-533223 | E-533223 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-06 | 2026-03-30
Lifecycle Management Epic: Tooling-PF-EFS-Shipment-SEFS ART-CY25 PI_ 04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112059 |  |  | Lifecycle Management Epic | Build | E-530998 | E-530998 | 2: S | 2025-09-25 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2025-10-07 | 2025-09-25
Local Enhancement Epic: Provide GPS coordinates of the POD Scan to CED | Approved | Local Enhancement Epic | Platforms Portfolio | 0112071 |  |  | Local Enhancement Epic | Build | E-534826 | E-534826 | 1: XS | 2025-10-20 |  |  | 1 | 0 | 1 | 0 | No | 2024-11-04 | 2026-03-30 | 2025-10-20
Lifecycle Management Epic: FY26-Patching-PF-EFS-Shipment-SEFS ART | Assumed Completed | Lifecycle Management Epic | Platforms Portfolio | 0112093 |  |  | Lifecycle Management Epic | Build | E-530996 | E-530996 | 3: M | 2025-08-27 |  |  | 1 | 0 | 1 | 0 | No | 2025-12-31 | 2026-05-19 | 2025-08-27
Lifecycle Management Epic: Compliance-PF-EFS-Shipment-SEFS ART-CY25 PI_04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112095 |  |  | Lifecycle Management Epic | Build | E-530997 | E-530997 | 4: L | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No | 2025-07-30 | 2025-10-07 | 2025-09-25
Local Enhancement Epic: Update ServiceNow Discovery ACLs on All Network De | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112234 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec - Cloud Inf. Entitlement Management (CIEM) | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112239 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Infosec - Tenable security center upgrade to v6.5 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0112254 |  |  | Lifecycle Management Epic | Build | E-534514 | E-534514 | 2: S | 2025-10-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-10
Biz w/ Tech Epic: TS-VL3-Messaging POC Enabler | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0112257 | 152855 | TS-VL3-Messaging-POC Enabler | Biz w/ Tech Epic | Build | E-545984 | E-545984 | 1: XS | 2025-10-28 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2027-04-19 | 2025-10-28
Lifecycle Management Epic: FY26_PF_TG ART2_SNVR VM Patch Orchestration Modul | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0112279 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: [UDS – CANH] – Platforms Portfolio | Closed | Local Enhancement Epic | Platforms Portfolio | 0112294 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537985 | E-537985 | 2: S |  |  |  | 2 | 0 |  | 2 | No
Lifecycle Management Epic: FY26_PI-4_PF_New Client Onboarding to Geopolitical | Closed | Lifecycle Management Epic | Platforms Portfolio | 0112296 |  |  | Lifecycle Management Epic | Build | E-534827 | E-534827 | 1: XS | 2025-11-13 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-13
Local Enhancement Epic: Automatically Remove IMAGE Role from Inactive Visa | Approved | Local Enhancement Epic | Platforms Portfolio | 0112304 |  |  | Local Enhancement Epic | Build | E-533614 | E-533614 | 2: S | 2026-04-24 |  | 100% | 1 | 1 |  | 0 | No | 2025-08-22 | 2026-04-01 | 2026-04-24
Lifecycle Management Epic: IT - MXP Core Network Equipment replacement | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0112305 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: International Freight Canopy Expansion | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112329 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Migrate Ephemeral JMS to a Different Data Model | Closed | Local Enhancement Epic | Platforms Portfolio | 0112380 |  |  | Local Enhancement Epic | Build | E-533813 | E-533813 | 2: S | 2025-09-25 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-25
Local Enhancement Epic: InfoSec FXF Identity & Access Infrastructure | In Progress | Local Enhancement Epic | Platforms Portfolio | 0112398 |  |  | Local Enhancement Epic | Backlog | E-536964 | E-536964 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-06-02
Local Enhancement Epic: PurpleID App Onboarding Automation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112412 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Demand Flow test | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0112422 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Aviation Cybersecurity | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112479 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: IT - Fastweb DC Core Network Equipment Replacement | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0112488 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: eCommerce Security | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112492 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: WTC SBE Migration "Work status cancelled " | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0112498 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DUPLICATE_ please delDell Platform Assessment SOW | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112511 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: NOS1 Upgrade Epic 1 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0112533 | 109261 | NOS1 Migration to NOS2 - Europe | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2026-03-02 | 2027-03-31
Local Enhancement Epic: Contract Lifecycle Management App and Reporting | Approved | Local Enhancement Epic | Platforms Portfolio | 0112587 |  |  | Local Enhancement Epic | Build | E-537156 | E-537156 | 2: S | 2026-01-09 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2026-01-09
Lifecycle Management Epic: TEM Operations | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112588 |  |  | Lifecycle Management Epic | Build | E-544238 | E-544238 | 3: M | 2026-01-09 |  |  | 1 | 0 | 1 | 0 | No | 2026-03-30 | 2026-06-30 | 2026-01-09
Local Enhancement Epic: TBM: Application TCO | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112589 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TBM: One FedEx Allocations | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112590 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TBM: Enterprise Contracts Mapping | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112591 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TBM: Service Now Integration | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112592 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IT WAR Reporting – Migration to Power BI | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112594 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ESDA - Service desk Chat Bot Automation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112595 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU and APAC Reliability Report | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112597 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26_Platforms_Enterprise Service desk_Production | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112598 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26_Platforms_IT Command Center_Production suppo | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112599 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TBM: Consolidated GL File | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112600 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Patching-PF-EFS-CEFS-ART-FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112641 |  |  | Lifecycle Management Epic | Build | E-540287 | E-540287 | 2: S | 2025-10-20 |  |  | 1 | 0 | 1 | 0 | No | 2025-07-30 | 2026-05-29 | 2025-10-20
Local Enhancement Epic: ACLC3 Office Facility Setup | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112647 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MEMH Diverse Circuit Path | Approved | Local Enhancement Epic | Platforms Portfolio | 0112690 |  |  | Local Enhancement Epic | Build | E-542064 | E-542064 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-12-05 | 2026-05-29 | 2026-04-23
Local Enhancement Epic: Granite EPIK Solution Approval & POTS Migration | Approved | Local Enhancement Epic | Platforms Portfolio | 0112727 |  |  | Local Enhancement Epic | Build | E-541572 | E-541572 | 3: M | 2026-04-24 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2026-04-24
Lifecycle Management Epic: Edge Compute Modernization | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0112728 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec PS Governance | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0112730 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Infosec - Compliance Data moving from Splunk | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0112742 | 104315 | InfoSec - Cyberdata Strategy | Biz w/ Tech Epic | Build | E-540077 | E-540077 | 3: M | 2025-12-18 |  |  | 9 | 0 | 4 | 5 | No | 2025-10-13 | 2026-10-27 | 2025-12-18
Local Enhancement Epic: Enable Partial Search for Phone Numbers on Contact | Approved | Local Enhancement Epic | Platforms Portfolio | 0112804 |  |  | Local Enhancement Epic | Build | E-548888 | E-548888 | 2: S | 2025-11-06 |  | 100% | 1 | 1 |  | 0 | No | 2026-04-20 | 2026-04-20 | 2025-11-06
Biz w/ Tech Epic: Migrate to Modern Authn & Authz & Build ISC Env | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0112826 | 98665 | TS-VL3-IMAGECloudMigrate | Biz w/ Tech Epic | Build | E-555061 | E-555061 | 2: S | 2026-02-06 |  |  | 8 | 0 | 1 | 7 | No | 2024-07-22 | 2027-12-09 | 2026-02-06
Local Enhancement Epic: FortKnox Implementation | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0112855 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Canada Legacy PSTN to centralized SIP migration | In Progress | Local Enhancement Epic | Platforms Portfolio | 0112860 |  |  | Local Enhancement Epic | Build | E-555208 | E-555208 | 3: M | 2026-04-23 |  |  | 1 | 0 | 1 | 0 | No | 2025-09-02 | 2026-05-01 | 2026-04-23
Lifecycle Management Epic: Contract Renewals FY 26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112896 |  |  | Lifecycle Management Epic | Build | E-536965 | E-536965 | 3: M | 2026-01-09 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-06-01 | 2026-01-09
Local Enhancement Epic: Single Invoice Option for APAC Customer | Approved | Local Enhancement Epic | Platforms Portfolio | 0112899 |  |  | Local Enhancement Epic | Build | E-540014 | E-540014 | 5: XL | 2025-12-04 |  | 100% | 1 | 1 |  | 0 | No | 2026-01-20 | 2026-12-21 | 2025-12-04
Local Enhancement Epic: Cisco Identify Services Engine Logs to Splunk | Not Started | Local Enhancement Epic | Platforms Portfolio | 0112986 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Database Infrastructure Modernization_LCM_CY25 PI5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0112998 |  |  | Lifecycle Management Epic | Build | E-539192 | E-539192 | 2: S | 2025-12-03 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-12-03
Local Enhancement Epic: DataStax Evaluation and PoC | Completed | Local Enhancement Epic | Platforms Portfolio | 0112999 |  |  | Local Enhancement Epic | Build | E-539191 | E-539191 | 1: XS | 2025-12-03 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-12-03
Local Enhancement Epic: InfoSec ServiceNow Licenses | Closed | Local Enhancement Epic | Platforms Portfolio | 0113000 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537936 | E-537936 | 2: S |  |  |  | 2 | 0 |  | 2 | No
Local Enhancement Epic: Replacement of Pittsburgh Employee Vehicle ID App | Not Started | Local Enhancement Epic | Platforms Portfolio | 0113001 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FortKnox Implementation POC | Closed | Local Enhancement Epic | Platforms Portfolio | 0113002 |  |  | Local Enhancement Epic | Build | E-541212 | E-541212 | 2: S | 2025-10-15 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-15
Biz w/ Tech Epic: Full AT&T Rollout - June - Dec 2026 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113044 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Assessment & Analysis | E-550433 | E-550433 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Full AT&T Rollout - FY27 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113046 | 8903 | TS-VL4-NETWORK-EdgeOptimization | Biz w/ Tech Epic | Assessment & Analysis | E-551949 | E-551949 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Security Scorecard | Not Started | Local Enhancement Epic | Platforms Portfolio | 0113054 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: RedHat Linux 7 Upgrade | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113059 | 107093 | RedHat Linux 7 LCM Upgrade | Biz w/ Tech Epic | Build | E-569157 | E-569157 | 1: XS | 2026-02-25 |  |  | 3 | 0 | 1 | 2 | No | 2025-06-02 | 2027-01-29 | 2026-02-25
Biz w/ Tech Epic: RedHat Linux 7 Upgrade - Epic1 | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0113061 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EPIC 1: Manage & Use EBR v2 | Closed | Biz w/ Tech Epic | Platforms Portfolio | 0109401 | 89399 | AVsec regulatory requirements | Biz w/ Tech Epic | Build | E-459156 | E-459156 | 2: S | 2025-10-09 |  | 66.67% | 3 | 2 | 1 | 0 | No |  |  | 2025-10-09
Local Enhancement Epic: InfoSec - API Dev Work - Salesforce & Workday | Not Started | Local Enhancement Epic | Platforms Portfolio | 0113105 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dell Platform Assessment SOW | Completed | Local Enhancement Epic | Platforms Portfolio | 0113109 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538985 | E-538985 | 1: XS |  |  | 100% | 1 | 1 |  | 0
Biz w/ Tech Epic: One Italy - Station Footprint | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113115 | 9269 | WS10 - One Italy - Station footprint | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-09-02 | 2026-06-30
Biz w/ Tech Epic: Evaluation of Tanium for Tech Simplification | On Hold | Biz w/ Tech Epic | Platforms Portfolio | 0113140 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Windows Server 2008 Decommission and Upgrade | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113174 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: 13725-EU Migration of Infoblox to Micetro Platform | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113195 |  |  | Lifecycle Management Epic | Build | E-558550 | E-558550 | 3: M | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-02 | 2027-04-30 | 2026-04-23
Local Enhancement Epic: Vendor Risk- Vendor Monitoring (SecurityScorecard) | Approved | Local Enhancement Epic | Platforms Portfolio | 0113196 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541213 | E-541213 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2024-07-22 | 2026-02-02
Lifecycle Management Epic: Infosec PI05 OT/IoT Engineering | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113197 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-541210 | E-541210 | 2: S |  |  | 100% | 1 | 1 |  | 0
Lifecycle Management Epic: Infosec PI05 OT/IoT Governance | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113199 |  |  | Lifecycle Management Epic | Build | E-541209 | E-541209 | 1: XS | 2025-10-28 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2025-10-28
Biz w/ Tech Epic: 1. Secure System Access & User Management | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113223 | 103989 | TS-VL3-DocMgt-Corporate Web Scanning | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-06-15
Biz w/ Tech Epic: AirOps Strategic Projects .gov environment | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113244 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: AirOps Strategic Projects ;gov access | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113245 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: InfoSec AO Strat Projects DoD Security Compliance | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113247 | 154593 | InfoSec AO Strat Projects DoD Security Compliance | Biz w/ Tech Epic | Build | E-564926 | E-564926 | 1: XS | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2025-11-03 | 2027-12-31 | 2026-04-23
Biz w/ Tech Epic: InfoSec AO Strat Projects DoD Security Compliance | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113248 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrades -PF-EFS-Shipment - SEFS ART- CY25-PI_05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113251 |  |  | Lifecycle Management Epic | Build | E-540022 | E-540022 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Compliance-PF-EFS-Shipment-SEFS ART-CY25 PI_05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113252 |  |  | Lifecycle Management Epic | Build | E-540017 | E-540017 | 2: S | 2025-11-11 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2025-12-31 | 2025-11-11
Lifecycle Management Epic: Tooling-PF-EFS-Shipment-SEFS ART-CY25 PI_ 05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113253 |  |  | Lifecycle Management Epic | Build | E-540020 | E-540020 | 2: S | 2025-11-14 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-09 | 2025-12-31 | 2025-11-14
Lifecycle Management Epic: Compliance-PF-EFS-Location-LEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113254 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-539241 | E-539241 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2025-12-31
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113255 |  |  | Lifecycle Management Epic | Build | E-540013 | E-540013 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Upgrade-PF-EFS-Location-LEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113256 |  |  | Lifecycle Management Epic | Build | E-539247 | E-539247 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Upgrade-PF-EFS-GeoPolitical-GpEFS-PLG ART-CY25 PI- | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113257 |  |  | Lifecycle Management Epic | Build | E-540021 | E-540021 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Upgrade-PF-EFS-Geography-GEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113258 |  |  | Lifecycle Management Epic | Build | E-539245 | E-539245 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-30 | 2025-11-13
Lifecycle Management Epic: Tooling-PF-EFS-Product-PEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113259 |  |  | Lifecycle Management Epic | Build | E-540019 | E-540019 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Tooling-PF-EFS-GeoPolitical-GpEFS-PLG ART-CY25 PI- | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113260 |  |  | Lifecycle Management Epic | Build | E-540018 | E-540018 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Tooling-PF-EFS-Geography-GEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113261 |  |  | Lifecycle Management Epic | Build | E-539240 | E-539240 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-30 | 2025-11-13
Lifecycle Management Epic: Compliance-PF-EFS-Product-PEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113262 |  |  | Lifecycle Management Epic | Build | E-539242 | E-539242 | 3: M | 2025-10-09 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-10-09
Lifecycle Management Epic: Compliance-PF-EFS-GeoPolitical-GpEFS-PLG ART-CY25 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113263 |  |  | Lifecycle Management Epic | Build | E-540023 | E-540023 | 3: M | 2025-11-13 |  | 100% | 1 | 1 |  | 0 |  | 2024-07-22 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Upgrade-PF-EFS-Product-PEFS-PLG ART-CY25 PI-5 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113264 |  |  | Lifecycle Management Epic | Build | E-540025 | E-540025 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2025-12-31 | 2025-11-13
Lifecycle Management Epic: Compliance-PF-EFS-Geography-GEFS-PLG ART-CY25 PI-5 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0113265 |  |  | Lifecycle Management Epic | Build | E-539244 | E-539244 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2025-11-13
Local Enhancement Epic: PF-CEFS-Enhancements Foundational Services Quality | Approved | Local Enhancement Epic | Platforms Portfolio | 0113370 |  |  | Local Enhancement Epic | Build | E-540015 | E-540015 | 2: S |  |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2026-05-29
Local Enhancement Epic: PF-PLG-GpEFS-Enhancements to Foundational Services | Approved | Local Enhancement Epic | Platforms Portfolio | 0113371 |  |  | Local Enhancement Epic | Build | E-539246 | E-539246 | 3: M | 2025-10-10 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2027-08-17 | 2025-10-10
Local Enhancement Epic: PF-PLG-LEFS-Enhancements to Foundational Services | Approved | Local Enhancement Epic | Platforms Portfolio | 0113372 |  |  | Local Enhancement Epic | Build | E-540024 | E-540024 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2026-05-29 | 2025-11-13
Local Enhancement Epic: PF-PLG-PEFS-Enhancements to Foundational Services | Approved | Local Enhancement Epic | Platforms Portfolio | 0113373 |  |  | Local Enhancement Epic | Build | E-540642 | E-540642 | 3: M | 2025-11-13 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2026-05-29 | 2025-11-13
Local Enhancement Epic: PF-GEFS-Enhancements to Foundational Services | Approved | Local Enhancement Epic | Platforms Portfolio | 0113375 |  |  | Local Enhancement Epic | Build | E-540643 | E-540643 | 3: M | 2025-10-20 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-08 | 2026-05-29 | 2025-10-20
Local Enhancement Epic: Implementation - Service Mapping/TopDown Discovery | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0113428 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564959 | E-564959 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Service Mapping/Top Down Discovery Implementation | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0113429 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Accenture Automation Efforts Cancelled 10/30/25 | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0113437 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543811 | E-543811 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Puppet Enterprise Infrastructure Retirement | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0113438 |  |  | Local Enhancement Epic | Build | E-543810 | E-543810 | 4: L | 2025-11-05 |  |  | 1 | 0 |  | 1 |  |  |  | 2025-11-05
Lifecycle Management Epic: Infosec LCM Cyber Knights CY25PI05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113439 |  |  | Lifecycle Management Epic | Build | E-541211 | E-541211 | 2: S | 2025-12-18 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-01 | 2026-03-30 | 2025-12-18
Lifecycle Management Epic: InfoSec-LCM-EIAM-Vulnerability-Management-CY25PI05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113440 |  |  | Lifecycle Management Epic | Build | E-541208 | E-541208 | 1: XS | 2025-12-17 |  | 100% | 1 | 1 |  | 0 |  | 2025-10-13 | 2026-01-02 | 2025-12-17
Local Enhancement Epic: AFWH and OAKH Infrastructure Upgrades | Approved | Local Enhancement Epic | Platforms Portfolio | 0113441 |  |  | Local Enhancement Epic | Build | E-542482 | E-542482 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-04 | 2026-05-29 | 2026-02-06
Local Enhancement Epic: Purple Gateway Landing Page Enhancement 20250911 | Approved | Local Enhancement Epic | Platforms Portfolio | 0113442 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552548 | E-552548 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Wiz Sensor/Connector Deployment | Approved | Local Enhancement Epic | Platforms Portfolio | 0113449 |  |  | Local Enhancement Epic | Build | E-550480 | E-550480 | 2: S | 2026-03-30 |  | 50% | 2 | 1 | 1 | 0 |  | 2025-10-01 | 2026-10-01 | 2026-03-30
Lifecycle Management Epic: TCN Atlanta Facility Closure | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0113501 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Facility New Loc - CY27 Relocation Bundle | Approved | Local Enhancement Epic | Platforms Portfolio | 0113564 |  |  | Local Enhancement Epic | Build | E-553245 | E-553245 | 3: M | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-13 | 2026-03-30 | 2026-04-23
Biz w/ Tech Epic: FXF - PF – Network | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113629 | 143541 | Project Fairway - Infrastructure Separation Enable | Biz w/ Tech Epic | Build | E-542749 | E-542749 | 5: XL | 2025-10-28 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2027-06-25 | 2025-10-28
Lifecycle Management Epic: FY26_PI5_Platforms_LCM_CEFS_CPP-UI-Modernization | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113641 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-541336 | E-541336 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2025-12-31
Lifecycle Management Epic: FY26_PI5_Platforms_LCM_CEFS_EFWS-Modernization | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113642 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-541335 | E-541335 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2025-12-31
Lifecycle Management Epic: FY26_PI5_Platforms_LCM_CEFS_SABT-Modernization | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0113643 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554836 | E-554836 | 3: M |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: FY26_PI5_Platforms_LCM_CEFS_CIMOPS-Modernization | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113644 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-541338 | E-541338 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2025-12-31
Lifecycle Management Epic: FY26_PI5_Platforms_LCM_CEFS_CCOB-Modernization | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113645 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-541337 | E-541337 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-10-08 | 2025-12-31
Lifecycle Management Epic: Infosec LCM Always on Avengers CY25PI05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113646 |  |  | Lifecycle Management Epic | Build | E-542881 | E-542881 | 2: S | 2025-10-24 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-13 | 2026-03-30 | 2025-10-24
Lifecycle Management Epic: Infosec - LCM - Attack Surface Analytics CY25PI5 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113647 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-541616 | E-541616 | 3: M |  |  | 100% | 1 | 1 |  | 0
Lifecycle Management Epic: InfoSec LCM 5th Dimension CY25PI05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113648 |  |  | Lifecycle Management Epic | Build | E-549238 | E-549238 | 2: S | 2026-04-24 |  | 100% | 1 | 1 |  | 0 |  | 2025-10-24 | 2026-03-30 | 2026-04-24
Local Enhancement Epic: Express-Ops-Airwatch Metrics in Grafana | Closed | Local Enhancement Epic | Platforms Portfolio | 0113649 |  |  | Local Enhancement Epic | Build | E-541721 | E-541721 | 1: XS | 2025-10-28 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-28
Local Enhancement Epic: Oracle Audit Vault | Closed | Local Enhancement Epic | Platforms Portfolio | 0113651 |  |  | Local Enhancement Epic | Build | E-541926 | E-541926 | 1: XS | 2025-10-28 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-28
Local Enhancement Epic: Oracle Audit Vault | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0113652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EUS Weak Cipher | Closed | Local Enhancement Epic | Platforms Portfolio | 0113653 |  |  | Local Enhancement Epic | Build | E-541929 | E-541929 | 1: XS | 2025-10-28 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-28
Local Enhancement Epic: IMAGE Birthright Impact Automation | Approved | Local Enhancement Epic | Platforms Portfolio | 0113654 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542880 | E-542880 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-10-13 | 2026-03-30
Lifecycle Management Epic: EIAM Audit Support CY25PI05 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113655 |  |  | Lifecycle Management Epic | Build | E-542882 | E-542882 | 2: S | 2025-10-24 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-13 | 2026-03-30 | 2025-10-24
Local Enhancement Epic: InfoSec - Passwordless Prod Enablement | Approved | Local Enhancement Epic | Platforms Portfolio | 0113660 |  |  | Local Enhancement Epic | Build | E-541927 | E-541927 | 2: S | 2026-04-24 |  | 100% | 1 | 1 |  | 0 |  | 2025-10-09 | 2026-03-30 | 2026-04-24
Biz w/ Tech Epic: Infosec: FXF - PF - InfoSec | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113666 | 143541 | Project Fairway - Infrastructure Separation Enable | Biz w/ Tech Epic | Build | E-541653 | E-541653 | 5: XL | 2025-10-16 |  |  | 7 | 0 | 5 | 2 |  | 2025-09-30 | 2026-06-01 | 2025-10-16
Biz w/ Tech Epic: FXF - PF - Infrastructure | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113678 | 143541 | Project Fairway - Infrastructure Separation Enable | Biz w/ Tech Epic | Build | E-546440 | E-546440 | 5: XL | 2025-10-29 |  |  | 3 | 0 | 3 | 0 |  | 2025-06-02 | 2029-05-11 | 2025-10-29
Local Enhancement Epic: DataStax - HCD | Approved | Local Enhancement Epic | Platforms Portfolio | 0113679 |  |  | Local Enhancement Epic | Build | E-541928 | E-541928 | 1: XS | 2025-10-28 |  | 100% | 1 | 1 |  | 0 |  | 2024-07-22 | 2027-06-28 | 2025-10-28
Local Enhancement Epic: DataStax - Grafana | Completed | Local Enhancement Epic | Platforms Portfolio | 0113680 |  |  | Local Enhancement Epic | Build | E-541930 | E-541930 | 1: XS | 2025-10-28 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-28
Local Enhancement Epic: PostgreSQL Design Services | Closed | Local Enhancement Epic | Platforms Portfolio | 0113681 |  |  | Local Enhancement Epic | Build | E-541654 | E-541654 | 5: XL | 2025-10-29 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-29
Local Enhancement Epic: Enhance Customs clearance capabilities | Approved | Local Enhancement Epic | Platforms Portfolio | 0113715 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567934 | E-567934 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Hub and Spoke Infrastructure for Metadata Catalog | Approved | Local Enhancement Epic | Platforms Portfolio | 0113733 |  |  | Local Enhancement Epic | Build | E-548375 | E-548375 | 3: M | 2025-12-30 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-30 | 2026-05-29 | 2025-12-30
Local Enhancement Epic: FXF- Spokane, WA BTS Facility - CLEAR 100013529 | Approved | Local Enhancement Epic | Platforms Portfolio | 0113742 |  |  | Local Enhancement Epic | Build | E-549217 | E-549217 | 1: XS | 2026-02-06 |  |  | 2 | 0 | 2 | 0 |  | 2025-10-27 | 2026-06-30 | 2026-02-06
Local Enhancement Epic: FXF - Fort Myers, FL BTS Facility-CLEAR 100013312 | Approved | Local Enhancement Epic | Platforms Portfolio | 0113743 |  |  | Local Enhancement Epic | Build | E-549216 | E-549216 | 1: XS | 2026-02-06 |  |  | 2 | 0 | 2 | 0 |  | 2025-10-27 | 2026-06-30 | 2026-02-06
Biz w/ Tech Epic: CEFS - FedEx Freight Separation | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0113755 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-542576 | E-542576 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: NSX Advanced Load Balancer AVI Migration | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0113756 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Cohesity & Isilon Performance Metrics | Closed | Local Enhancement Epic | Platforms Portfolio | 0113810 |  |  | Local Enhancement Epic | Build | E-543211 | E-543211 | 1: XS | 2025-10-28 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-28
Local Enhancement Epic: Infrastructure Logging and Monitoring | Approved | Local Enhancement Epic | Platforms Portfolio | 0113811 |  |  | Local Enhancement Epic | Build | E-543292 | E-543292 | 3: M | 2025-10-28 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-13 | 2026-01-06 | 2025-10-28
Lifecycle Management Epic: Production Support – Platform Architecture Publish | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113812 |  |  | Lifecycle Management Epic | Build | E-543245 | E-543245 | 4: L | 2025-10-28 |  |  | 2 | 0 | 1 | 1 |  | 2025-08-04 | 2026-05-29 | 2025-10-28
Local Enhancement Epic: SORT OPF Messaging Infrastructure Redesign | Completed | Local Enhancement Epic | Platforms Portfolio | 0113814 |  |  | Local Enhancement Epic | Build | E-547203 | E-547203 | 2: S | 2025-10-29 |  |  | 0 | 0 |  | 0 |  |  |  | 2025-10-29
Local Enhancement Epic: Service-Now (PDSM) API Establish | Rejected | Local Enhancement Epic | Platforms Portfolio | 0113825 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Integrate Parent-Child Relationship | Not Started | Local Enhancement Epic | Platforms Portfolio | 0113834 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AMEA increase credit limit fields in eCIS to 12 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0113835 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ECIS Character Limit for Name and Address | Not Started | Local Enhancement Epic | Platforms Portfolio | 0113836 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: EFS FXF Separation Architecture | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0113853 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: PF - EFS - Project Fairway | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0113942 | 143541 | Project Fairway - Infrastructure Separation Enable | Biz w/ Tech Epic | Build | E-545983 | E-545983 | 5: XL | 2025-10-31 |  |  | 2 | 0 | 1 | 1 |  | 2025-10-08 | 2026-07-14 | 2025-10-31
Lifecycle Management Epic: Broadcom Layer7 11.1.2 Upgrade | Approved | Lifecycle Management Epic | Platforms Portfolio | 0113962 |  |  | Lifecycle Management Epic | Build | E-554250 | E-554250 | 3: M | 2025-12-02 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2026-01-05 | 2025-12-02
Local Enhancement Epic: Cyber Resiliency Analytics&Automation PI05 & PIU01 | Approved | Local Enhancement Epic | Platforms Portfolio | 0113973 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549239 | E-549239 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-10-13 | 2026-03-13
Local Enhancement Epic: Cyber Vaults Improvements PI05 & PI01 | Approved | Local Enhancement Epic | Platforms Portfolio | 0113974 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549240 | E-549240 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-10-13 | 2026-03-13
Lifecycle Management Epic: Tooling – Network Management Team – CY25 PI05 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113976 |  |  | Lifecycle Management Epic | Build | E-549213 | E-549213 | 1: XS | 2025-12-09 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-12-09
Lifecycle Management Epic: Applications Adoption to WLS 14.1.2 (LTS) | In Progress | Lifecycle Management Epic | Platforms Portfolio | 0113977 |  |  | Lifecycle Management Epic | Build | E-545855 | E-545855 | 2: S | 2025-10-29 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2025-10-29
Lifecycle Management Epic: Compliance/ Legal & Regulatory/ Audits - CY25 PI05 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113979 |  |  | Lifecycle Management Epic | Build | E-549214 | E-549214 | 1: XS | 2025-12-09 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-12-09
Lifecycle Management Epic: InfoSec - EIAM FIRST Support - CY25PI05 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0113980 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrades – Global Network Engineering – CY25 PI05 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113981 |  |  | Lifecycle Management Epic | Build | E-549215 | E-549215 | 1: XS | 2025-12-09 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-12-09
Local Enhancement Epic: Digital Certificates CY25PI05 - CY26PI01 | Approved | Local Enhancement Epic | Platforms Portfolio | 0113982 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556698 | E-556698 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-11 | 2026-03-30
Lifecycle Management Epic: InfoSec - LCM - Secret Hustlers - CY25PI05 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0113983 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-563567 | E-563567 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LUZA Station - Modernization | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114009 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-07-01 | 2026-09-30
Local Enhancement Epic: EU Voice Infrastructure to Cloud. | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114024 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Urgent Network Deployment for Kuwait SWC Warehouse | Approved | Local Enhancement Epic | Platforms Portfolio | 0114063 |  |  | Local Enhancement Epic | Build | E-556717 | E-556717 | 1: XS | 2026-04-03 |  | 100% | 1 | 1 |  | 0 |  | 2025-12-11 | 2026-05-29 | 2026-04-03
Local Enhancement Epic: Malmo Station Relocation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114070 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Mapping of Unification of Trip/Itinerary/Waypoint | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114091 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: PF-ITOM - Fairway | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0114110 | 143541 | Project Fairway - Infrastructure Separation Enable | Biz w/ Tech Epic | Build | E-546368 | E-546368 | 5: XL | 2025-10-28 |  |  | 1 | 0 | 1 | 0 |  | 2025-10-28 | 2027-02-03 | 2025-10-28
Local Enhancement Epic: CloudSec Ongoing/Operational Projects (Container) | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114123 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY26 PI-1 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0114132 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: InfoSec - Firewall LCM FY26 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114188 | 154810 | Infosec - Firewall LCM | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-06-05
Biz w/ Tech Epic: InfoSec - Firewall LCM FY27 | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114189 | 154810 | Infosec - Firewall LCM | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2027-05-31
Local Enhancement Epic: Major Incident Communication | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114193 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Puppet to Ansible Migration | Approved | Local Enhancement Epic | Platforms Portfolio | 0114195 |  |  | Local Enhancement Epic | Build | E-548080 | E-548080 | 3: M | 2025-10-29 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2026-01-05 | 2025-10-29
Local Enhancement Epic: Proactive Monitoring for Oracle Databases | Closed | Local Enhancement Epic | Platforms Portfolio | 0114197 |  |  | Local Enhancement Epic | Build | E-547976 | E-547976 | 1: XS | 2025-10-29 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-29
Biz w/ Tech Epic: Knowledge Center | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114239 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-05-29
Local Enhancement Epic: OEM Monitoring and Alerting Enhancements | Closed | Local Enhancement Epic | Platforms Portfolio | 0114278 |  |  | Local Enhancement Epic | Build | E-548892 | E-548892 | 1: XS | 2025-10-29 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2025-10-29
Local Enhancement Epic: GitHub SNVR Integration | Approved | Local Enhancement Epic | Platforms Portfolio | 0114279 |  |  | Local Enhancement Epic | Build | E-552547 | E-552547 | 3: M | 2026-02-25 |  | 33.33% | 3 | 1 |  | 2 |  | 2025-10-13 | 2026-05-29 | 2026-02-25
Local Enhancement Epic: Ephemeral JMS API Redesign | Approved | Local Enhancement Epic | Platforms Portfolio | 0114281 |  |  | Local Enhancement Epic | Build | E-553773 | E-553773 | 2: S | 2026-01-14 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2026-01-06 | 2026-01-14
Local Enhancement Epic: Kolding Station Relocation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114284 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Purchasing Assistant | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114289 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: 2. End-to-End Scanning | In Progress | Biz w/ Tech Epic | Platforms Portfolio | 0114291 | 103989 | TS-VL3-DocMgt-Corporate Web Scanning | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-12-15 | 2026-06-15
Biz w/ Tech Epic: 3. Data Transfer/Export & Operational Visibility | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114292 | 103989 | TS-VL3-DocMgt-Corporate Web Scanning | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-06-15
Lifecycle Management Epic: InfoSec - Global Segmentation Program_LCM_FY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114314 |  |  | Lifecycle Management Epic | Build | E-552026 | E-552026 | 3: M | 2025-11-11 |  | 41.67% | 12 | 5 | 4 | 3 |  | 2025-11-07 | 2026-05-29 | 2025-11-11
Local Enhancement Epic: DBC & AO Telephony *Platforms Portfolio* | Approved | Local Enhancement Epic | Platforms Portfolio | 0114347 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566101 | E-566101 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SOX Remediations - Oracle-Database(6074) - CY26 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114348 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PagerDuty - Retain or Replace | Approved | Local Enhancement Epic | Platforms Portfolio | 0114349 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564502 | E-564502 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-09 | 2027-08-31
Biz w/ Tech Epic: Develop Purchasing Gateway on the ServiceNow pl | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0114364 | 153735 | EMR IFT Purchasing Gateway | Biz w/ Tech Epic | Assessment & Analysis | E-570614 | E-570614 | 3: M |  |  |  | 4 | 0 |  | 4 |  | 2025-11-28 | 2026-08-31
Biz w/ Tech Epic: MOBIUS Waves 7-8 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0112571 | 104743 | MOBIUS - SURFCO - Waves 1 - 8 Implementation | Biz w/ Tech Epic | Build | E-554294 | E-554294 | 3: M | 2026-03-05 |  |  | 1 | 0 | 1 | 0 | No | 2026-03-02 | 2027-05-31 | 2026-03-05
Local Enhancement Epic: Test- ESPM would like to see the IO view for L1/2 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114378 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TBM: Production Support | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0114380 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: WS10 - New Bologna Hub - SCO and Platform Epic | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0112608 | 9037 | WS10 - One Italy - New Bologna Hub | Biz w/ Tech Epic | Build | E-553566 | E-553566 | 2: S | 2026-03-23 |  |  | 3 | 0 | 2 | 1 | No | 2026-04-01 | 2027-01-15 | 2026-03-23
Lifecycle Management Epic: Cloud Security Engineering KTLO Initiatives | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114449 |  |  | Lifecycle Management Epic | Build | E-551746 | E-551746 | 2: S | 2026-01-16 |  |  | 1 | 0 | 1 | 0 |  | 2025-11-03 | 2026-10-30 | 2026-01-16
Local Enhancement Epic: JMS Monitoring Enhancements | Approved | Local Enhancement Epic | Platforms Portfolio | 0114450 |  |  | Local Enhancement Epic | Build | E-550812 | E-550812 | 1: XS | 2025-10-31 |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2027-04-22 | 2025-10-31
Local Enhancement Epic: CloudSec Ongoing/Operational Projects (Cloud) | Approved | Local Enhancement Epic | Platforms Portfolio | 0114451 |  |  | Local Enhancement Epic | Build | E-551750 | E-551750 | 3: M | 2026-01-16 |  |  | 1 | 0 | 1 | 0 |  | 2025-11-13 | 2026-08-03 | 2026-01-16
Local Enhancement Epic: CloudSec Ongoing/Operational Projects (CI/CD Sec) | Approved | Local Enhancement Epic | Platforms Portfolio | 0114452 |  |  | Local Enhancement Epic | Build | E-551747 | E-551747 | 3: M | 2026-01-16 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-05 | 2026-08-03 | 2026-01-16
Local Enhancement Epic: CloudSec Ongoing/Operational Projects (Container) | Approved | Local Enhancement Epic | Platforms Portfolio | 0114453 |  |  | Local Enhancement Epic | Build | E-551748 | E-551748 | 3: M | 2026-01-16 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-05 | 2026-08-04 | 2026-01-16
Local Enhancement Epic: EWR Ramp Wireless Connectivity | Approved | Local Enhancement Epic | Platforms Portfolio | 0114454 |  |  | Local Enhancement Epic | Build | E-569015 | E-569015 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-23
Lifecycle Management Epic: Compliance-PF-EFS-Geography-GEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114467 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554839 | E-554839 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-23 | 2026-05-19
Local Enhancement Epic: MICentral Admin Simplification | Approved | Local Enhancement Epic | Platforms Portfolio | 0114490 |  |  | Local Enhancement Epic | Build | E-550989 | E-550989 | 1: XS | 2025-11-21 |  |  | 1 | 0 | 1 | 0 |  | 2025-11-05 | 2026-01-06 | 2025-11-21
Local Enhancement Epic: Implement Axon BWC at AFWH and INDH Locations | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114563 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FY26 Airco PV Bundle for Closure Projects | Approved | Local Enhancement Epic | Platforms Portfolio | 0114565 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553246 | E-553246 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FY26 Airco PV Bundle for Expansion Projects | Approved | Local Enhancement Epic | Platforms Portfolio | 0114566 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553244 | E-553244 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FY26 Airco PV Retrofit Project Bundle | Approved | Local Enhancement Epic | Platforms Portfolio | 0114567 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553243 | E-553243 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Test | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114573 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Gothenburg Station Relocation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114586 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-GeoPolitical-GpEFS-PLGART-CY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114588 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554846 | E-554846 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-05-19
Lifecycle Management Epic: Compliance-PF-EFS-Location-LEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114589 |  |  | Lifecycle Management Epic | Build | E-554844 | E-554844 | 2: S | 2026-04-01 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-31 | 2026-03-31 | 2026-04-01
Lifecycle Management Epic: Compliance-PF-EFS-Product-PEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114590 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554854 | E-554854 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2026-03-30
Lifecycle Management Epic: Tooling-PF-EFS-Geography-GEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114591 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554835 | E-554835 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-03-31
Lifecycle Management Epic: Tooling-PF-EFS-GeoPolitical-GpEFS-PLGART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114592 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554848 | E-554848 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2026-03-30
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114594 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554845 | E-554845 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-03-31
Lifecycle Management Epic: Tooling-PF-EFS-Product-PEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114595 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554850 | E-554850 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2026-03-30
Lifecycle Management Epic: Upgrade-PF-EFS-Geography-GEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114596 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554856 | E-554856 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-03-23
Lifecycle Management Epic: Upgrade-PF-EFS-Product-PEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114597 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554847 | E-554847 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-03-31
Lifecycle Management Epic: Upgrade-PF-EFS-Location-LEFS-PLG ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114598 |  |  | Lifecycle Management Epic | Build | E-554843 | E-554843 | 2: S | 2026-02-16 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-31 | 2026-03-10 | 2026-02-16
Lifecycle Management Epic: Upgrade-PF-EFS-GeoPolitical-GpEFS-PLGART-CY26 PI-1 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0114599 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572656 | E-572656 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrades-PF-AEFS- ART-CY26-PI1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114605 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554840 | E-554840 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2025-12-31 | 2026-03-10
Local Enhancement Epic: Facility - 3860 FHI Suites 102-105, 107, 110) -LE | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114606 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PL/Lomza SMALL BTS Station | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114607 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrades PF-AEFS- ART-CY26 PI3 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0114608 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrades PF-AEFS- ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114609 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554849 | E-554849 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2026-05-29
Local Enhancement Epic: Ljungby Station Relocation | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114613 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Network Upgrade for FedEx CAC Facility in MEM | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114614 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: CloudBees Flow Retirement | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0114649 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: InfoSec - Acceptable Use Display for Devices | Approved | Local Enhancement Epic | Platforms Portfolio | 0114653 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556040 | E-556040 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2025-12-11 | 2026-05-29
Biz w/ Tech Epic: Migrate CloudBees Flow users to GitHub Action | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0114662 | 160266 | TS-VL3-SDLC-CBFlowRetirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Windows Server Replacement, Adelia Studio Upgrade | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114789 |  |  | Lifecycle Management Epic | Build | E-556786 | E-556786 | 3: M | 2026-04-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-02-23 | 2026-07-15 | 2026-04-06
Lifecycle Management Epic: MIS Archive Storage Capacity Increase | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0114817 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: BTSA New Facility (SK) | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0114821 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: APAC Network Refresh – APAC WAN Routers | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114824 |  |  | Lifecycle Management Epic | Build | E-563245 | E-563245 | 2: S | 2026-04-24 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-01 | 2026-05-29 | 2026-04-24
Local Enhancement Epic: Addition to World Tariff Associated account format | Closed | Local Enhancement Epic | Platforms Portfolio | 0114829 |  |  | Local Enhancement Epic | Build | E-554841 | E-554841 | 2: S | 2026-02-04 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-02-04
Lifecycle Management Epic: Upgrades-PF-EFS-Shipment-SEFS ART-CY26 PI_ 01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114830 |  |  | Lifecycle Management Epic | Build | E-554851 | E-554851 | 3: M | 2026-04-21 |  | 100% | 1 | 1 |  | 0 |  | 2025-12-31 | 2026-04-20 | 2026-04-21
Lifecycle Management Epic: Tooling-PF-EFS-Shipment-SEFS ART-CY26 PI_ 01 | Closed | Lifecycle Management Epic | Platforms Portfolio | 0114831 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554855 | E-554855 | 3: M |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: Compliance-PF-EFS-Shipment-SEFS ART-CY26 PI_01 | Completed | Lifecycle Management Epic | Platforms Portfolio | 0114832 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554853 | E-554853 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: FY26 ITSM Change Management | Approved | Local Enhancement Epic | Platforms Portfolio | 0114922 |  |  | Local Enhancement Epic | Build | E-555071 | E-555071 | 3: M | 2025-12-31 |  |  | 1 | 0 | 1 | 0 |  | 2026-04-20 | 2026-05-29 | 2025-12-31
Lifecycle Management Epic: Compliance-PF-EFS-CEFS ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114933 |  |  | Lifecycle Management Epic | Build | E-554842 | E-554842 | 1: XS | 2026-04-03 |  | 100% | 1 | 1 |  | 0 |  | 2026-01-01 | 2026-03-30 | 2026-04-03
Lifecycle Management Epic: Tooling-PF-EFS-CEFS ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114934 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554838 | E-554838 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2026-03-30
Lifecycle Management Epic: Upgrade-PF-EFS-CEFS ART-CY26 PI-1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0114935 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554837 | E-554837 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-05 | 2026-03-13
Lifecycle Management Epic: Tooling-PF-EFS-Address-AEFS ART-CY26 PI-1 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0114948 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554852 | E-554852 | 2: S |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: EPIC Project FORCE (FY26 Openings) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0114949 | 141899 | Project FORCE (FY26 Openings) | Biz w/ Tech Epic | Assessment & Analysis | E-581338 | E-581338 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2025-06-02 | 2026-06-01
Local Enhancement Epic: FY26 ITSM Change Management--Org Adoption | Approved | Local Enhancement Epic | Platforms Portfolio | 0114954 |  |  | Local Enhancement Epic | Build | E-555073 | E-555073 | 3: M | 2025-12-31 |  |  | 1 | 0 | 1 | 0 |  | 2026-04-20 | 2026-05-29 | 2025-12-31
Local Enhancement Epic: FY26 ITSM Change Management-Knowledge CoE | Approved | Local Enhancement Epic | Platforms Portfolio | 0114956 |  |  | Local Enhancement Epic | Build | E-555072 | E-555072 | 3: M | 2025-12-31 |  |  | 1 | 0 | 1 | 0 |  | 2026-04-20 | 2026-05-29 | 2025-12-31
Local Enhancement Epic: MAGIC China Data Localization Removal | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114982 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: MAGIC China Data Localization removal Epic | Not Started | Local Enhancement Epic | Platforms Portfolio | 0114988 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: APAC Network Refresh – APAC CUCM and APs | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115005 |  |  | Lifecycle Management Epic | Build | E-569713 | E-569713 | 1: XS | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-01 | 2026-05-29 | 2026-04-23
Local Enhancement Epic: FY26 Airco PV Bundle New Openings / Relocations | Approved | Local Enhancement Epic | Platforms Portfolio | 0115014 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554184 | E-554184 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Vita Application Upgrade | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115015 |  |  | Lifecycle Management Epic | Build | E-556785 | E-556785 | 3: M | 2026-04-06 |  |  | 1 | 0 | 1 | 0 |  | 2026-02-23 | 2026-07-15 | 2026-04-06
Local Enhancement Epic: IMS_AUTOMATION_2.0 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115019 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: IMS_AUTOMATION_QUASAR_PDSM_INTEGRATION | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115020 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: InfoSec Implementation of Armis Network MapperSNMP | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115021 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ATT Wireless Migration and Savings Initiative | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0115025 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: InfoSec Annual Cyber Response Exercise (PF) | Closed | Lifecycle Management Epic | Platforms Portfolio | 0115082 |  |  | Lifecycle Management Epic | Build | E-556039 | E-556039 | 2: S | 2026-01-12 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-12
Local Enhancement Epic: Infosec OT/IoT Rockwell Assessment | Approved | Local Enhancement Epic | Platforms Portfolio | 0115089 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559242 | E-559242 | 3: M |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: IMAGE to Oracle Cloud EFBV Integration | Approved | Local Enhancement Epic | Platforms Portfolio | 0115105 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562693 | E-562693 | 1: XS |  |  |  | 2 | 0 |  | 2 |  | 2026-03-30 | 2026-06-30
Biz w/ Tech Epic: RedHat Linux 4,5 and 6 Upgrade to 9 Complete | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115106 | 107382 | RedHat Linux 4, 5, 6 LCM Upgrade | Biz w/ Tech Epic | Build | E-569156 | E-569156 | 1: XS | 2026-02-25 |  |  | 2 | 0 | 1 | 1 |  | 2025-04-01 | 2027-04-01 | 2026-02-25
Lifecycle Management Epic: SEW - Field IT EU - WLAN AP8533 LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115110 |  |  | Lifecycle Management Epic | Build | E-554647 | E-554647 | 2: S | 2026-04-23 |  |  | 2 | 0 | 1 | 1 |  | 2026-01-05 | 2026-12-31 | 2026-04-23
Local Enhancement Epic: SEFS View Enhancements_FY26_PI0102 | Approved | Local Enhancement Epic | Platforms Portfolio | 0115117 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556611 | E-556611 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-15 | 2026-05-15
Biz w/ Tech Epic: Platform for Speedcargo | In Progress | Biz w/ Tech Epic | Platforms Portfolio | 0115157 | 109589 | APAC Speedcargo Density Solution | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-06-01
Biz w/ Tech Epic: DC Build | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115161 | 91925 | TS-VL4-NETWORK-EU SD WAN | Biz w/ Tech Epic | Assessment & Analysis | E-583978 | E-583978 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2026-09-30
Local Enhancement Epic: DE-Koblenz New Building (#0016419) | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115162 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: HRSD New Service - Global eAcknowledgement | Approved | Local Enhancement Epic | Platforms Portfolio | 0115187 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564503 | E-564503 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-09 | 2026-05-29
Lifecycle Management Epic: InfoSec CY26 PI01 OT/IoT Governance | Closed | Lifecycle Management Epic | Platforms Portfolio | 0115209 |  |  | Lifecycle Management Epic | Build | E-556072 | E-556072 | 2: S | 2026-01-16 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-16
Lifecycle Management Epic: InfoSec FY26 PI01 OT/IoT Engineering | Closed | Lifecycle Management Epic | Platforms Portfolio | 0115210 |  |  | Lifecycle Management Epic | Build | E-556209 | E-556209 | 3: M | 2026-01-16 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-16
Lifecycle Management Epic: Infosec LCM Cyber Knights CY26PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115211 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556041 | E-556041 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2025-12-11 | 2026-03-30
Local Enhancement Epic: InfoSec Sonatype Workflow Integration with SNVR | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115212 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PL_Koszalin NEW Station (BTS) | On Hold | Local Enhancement Epic | Platforms Portfolio | 0108212 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: InfoSec CY26 PI 01 AD Domain Feasibility Study | Approved | Local Enhancement Epic | Platforms Portfolio | 0115231 |  |  | Local Enhancement Epic | Build | E-556286 | E-556286 | 3: M | 2026-01-16 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-01 | 2026-06-01 | 2026-01-16
Lifecycle Management Epic: InfoSec - EIAM FIRST Support - CY26PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115299 |  |  | Lifecycle Management Epic | Build | E-556709 | E-556709 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-11 | 2026-03-30 | 2026-02-06
Lifecycle Management Epic: InfoSec-LCM-EIAM-Vulnerability-Management-CY26PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115300 |  |  | Lifecycle Management Epic | Build | E-556696 | E-556696 | 2: S | 2026-01-16 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-11 | 2026-03-30 | 2026-01-16
Lifecycle Management Epic: EIAM Audit Support CY26PI01 | Rejected | Lifecycle Management Epic | Platforms Portfolio | 0115301 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Infosec LCM Always on Avengers CY26PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115322 |  |  | Lifecycle Management Epic | Build | E-556697 | E-556697 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-11 | 2026-04-06 | 2026-02-06
Biz w/ Tech Epic: SNOW Field Service Management (FSM) Implementation | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115332 | 107744 | TS-VL2-Con-ServiceNowAppPorfolioMgmnt | Biz w/ Tech Epic | Build | E-564705 | E-564705 | 2: S | 2026-04-14 |  |  | 2 | 0 | 1 | 1 |  |  |  | 2026-04-14
Local Enhancement Epic: BTSA New Facility (SK) - Platforms | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115347 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DSE OpenShift Environment | Completed | Local Enhancement Epic | Platforms Portfolio | 0115357 |  |  | Local Enhancement Epic | Build | E-556461 | E-556461 | 2: S | 2026-01-05 |  | 100% | 1 | 1 |  | 0 |  |  |  | 2026-01-05
Local Enhancement Epic: SQL 2025 Development | Approved | Local Enhancement Epic | Platforms Portfolio | 0115358 |  |  | Local Enhancement Epic | Build | E-556464 | E-556464 | 2: S | 2026-01-05 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-05 | 2026-05-22 | 2026-01-05
Local Enhancement Epic: Oracle Goldengate MicroServices Standards | Approved | Local Enhancement Epic | Platforms Portfolio | 0115359 |  |  | Local Enhancement Epic | Build | E-556463 | E-556463 | 2: S | 2026-01-05 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-05 | 2026-05-22 | 2026-01-05
Local Enhancement Epic: Certify Oracle CAD Build On IPV6 | Approved | Local Enhancement Epic | Platforms Portfolio | 0115360 |  |  | Local Enhancement Epic | Build | E-556462 | E-556462 | 2: S | 2026-01-05 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-05 | 2026-05-22 | 2026-01-05
Local Enhancement Epic: EU Regulatory Requirement Updates | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115361 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: APAC Network Refresh - CANHub Extreme Access Point | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0115363 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: APAC Network Refresh – APAC CANHub Switches | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115364 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-569700 | E-569700 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-01-19
Local Enhancement Epic: InfoSec-Next-Gen FTI Strategy | Approved | Local Enhancement Epic | Platforms Portfolio | 0115387 |  |  | Local Enhancement Epic | Build | E-556592 | E-556592 | 3: M | 2026-02-06 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-12 | 2026-05-22 | 2026-02-06
Biz w/ Tech Epic: Citrix Retirement Epic 1 | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115389 | 84419 | TS-VL4-ENDUSER-Windows RDS (Citrix Replacement) | Biz w/ Tech Epic | Assessment & Analysis | E-566914 | E-566914 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-06-30
Lifecycle Management Epic: Migration Out of the Legacy Data Centers for Chile | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0115390 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: EIAM Audit Support CY26PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115406 |  |  | Lifecycle Management Epic | Build | E-556710 | E-556710 | 2: S | 2026-02-06 |  |  | 1 | 0 | 1 | 0 |  | 2025-12-01 | 2026-03-30 | 2026-02-06
Lifecycle Management Epic: MEISA Network Refresh - Extreme Access Point | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115416 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582277 | E-582277 | 3: M |  |  |  | 1 | 0 |  | 1
Lifecycle Management Epic: MEISA Network Refresh - Routers and Switches | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115417 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582276 | E-582276 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: TSRA New Facility - Platforms | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115461 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Develop CLM on Icertis Platform | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115463 | 153742 | EMR IFT CLM | Biz w/ Tech Epic | Assessment & Analysis | E-568277 | E-568277 | 4: L |  |  |  | 19 | 0 |  | 19 |  | 2027-05-31 | 2027-05-31
Local Enhancement Epic: Implement Fuel Card Record Producer in Purple Gate | In Progress | Local Enhancement Epic | Platforms Portfolio | 0115472 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564501 | E-564501 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-09 | 2026-05-29
Local Enhancement Epic: Enable Employee Relations Module in Purple Gateway | Closed | Local Enhancement Epic | Platforms Portfolio | 0115473 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564497 | E-564497 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Non-Human Account Management | Approved | Local Enhancement Epic | Platforms Portfolio | 0115474 |  |  | Local Enhancement Epic | Build | E-560429 | E-560429 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-08 | 2026-05-22 | 2026-04-23
Lifecycle Management Epic: Upgrades – Global Network Engineering – CY26 PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115485 |  |  | Lifecycle Management Epic | Build | E-558542 | E-558542 | 1: XS | 2026-01-27 |  | 100% | 1 | 1 |  | 0 |  | 2025-12-18 | 2026-04-20 | 2026-01-27
Lifecycle Management Epic: Tooling – Network Management Team – CY26 PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115486 |  |  | Lifecycle Management Epic | Build | E-558540 | E-558540 | 1: XS | 2026-01-27 |  | 100% | 1 | 1 |  | 0 |  | 2025-12-03 | 2026-04-20 | 2026-01-27
Lifecycle Management Epic: Compliance/ Legal & Regulatory/ Audits - CY26 PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115487 |  |  | Lifecycle Management Epic | Build | E-558541 | E-558541 | 1: XS | 2026-01-27 |  | 100% | 1 | 1 |  | 0 |  | 2025-12-18 | 2026-04-20 | 2026-01-27
Lifecycle Management Epic: InfoSec LCM 5th Dimension CY26PI01 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115488 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-580353 | E-580353 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: InfoSec - International Governance | Approved | Local Enhancement Epic | Platforms Portfolio | 0115489 |  |  | Local Enhancement Epic | Build | E-563566 | E-563566 | 3: M | 2026-03-26 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-23 | 2026-05-25 | 2026-03-26
Lifecycle Management Epic: FY26_PI1_Platforms_Embarcadero_License_Server | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115490 |  |  | Lifecycle Management Epic | Build | E-563523 | E-563523 | 1: XS | 2026-01-21 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-05 | 2026-03-02 | 2026-01-21
Lifecycle Management Epic: FY26 Reliability and Supportability Enhancements | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115523 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-565363 | E-565363 | 3: M |  |  |  | 1 | 0 | 1 | 0 |  | 2024-07-22 | 2027-04-26
Local Enhancement Epic: ETAC R&D - Enterprise Modernization | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0115557 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563913 | E-563913 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: External Storage - NetApp ASA A70A | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115578 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: InfoSec Testing Viakoo Asset Integration to CMDB | Approved | Local Enhancement Epic | Platforms Portfolio | 0115580 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568682 | E-568682 | 2: S |  |  |  | 2 | 0 |  | 2 |  | 2026-03-16 | 2026-05-29
Local Enhancement Epic: Update company car HR Services and enable intake o | In Progress | Local Enhancement Epic | Platforms Portfolio | 0115588 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564498 | E-564498 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-09 | 2026-05-29
Local Enhancement Epic: FXU Network 2.0 Intake Process | In Progress | Local Enhancement Epic | Platforms Portfolio | 0115589 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564500 | E-564500 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-09 | 2026-05-29
Local Enhancement Epic: InfoSec GCCR Insider Threat Program POV | On Hold | Local Enhancement Epic | Platforms Portfolio | 0115592 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Oracle Enterprise Manager - OEM | Approved | Local Enhancement Epic | Platforms Portfolio | 0115606 |  |  | Local Enhancement Epic | Build | E-559395 | E-559395 | 1: XS | 2025-12-30 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-03-13 | 2025-12-30
Local Enhancement Epic: Grafana - Grafana IFRely Enhancements | Approved | Local Enhancement Epic | Platforms Portfolio | 0115607 |  |  | Local Enhancement Epic | Build | E-559394 | E-559394 | 3: M | 2025-12-30 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-19 | 2026-03-13 | 2025-12-30
Local Enhancement Epic: New Sort Line for RZEA Station | Approved | Local Enhancement Epic | Platforms Portfolio | 0115608 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582117 | E-582117 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Network Infrastructure for FDX New Gateway in KSA | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115609 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SAM Integration Cleanup | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115628 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Global Software Asset Catalog | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115629 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Bringg SaaS License Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115630 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DigiAI SaaS License Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115631 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Workday SaaS License Integration | Approved | Local Enhancement Epic | Platforms Portfolio | 0115638 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564499 | E-564499 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-22 | 2026-05-29
Local Enhancement Epic: Red Hat Satellite | Approved | Local Enhancement Epic | Platforms Portfolio | 0115661 |  |  | Local Enhancement Epic | Build | E-565361 | E-565361 | 2: S | 2026-03-16 |  |  | 1 | 0 | 1 | 0 |  | 2025-07-01 | 2026-08-28 | 2026-03-16
Local Enhancement Epic: Red Hat Enterprise Linux 10 | Approved | Local Enhancement Epic | Platforms Portfolio | 0115662 |  |  | Local Enhancement Epic | Build | E-565360 | E-565360 | 2: S | 2026-04-20 |  |  | 1 | 0 | 1 | 0 |  | 2025-07-01 | 2026-03-23 | 2026-04-20
Local Enhancement Epic: Computer Room Compliance Europe - UDS on-prem | Approved | Local Enhancement Epic | Platforms Portfolio | 0115683 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565952 | E-565952 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Broadcom-ITPAM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115685 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-565749 | E-565749 | 2: S |  |  |  | 1 | 0 | 1 | 0 |  | 2026-01-26 | 2027-06-30
Biz w/ Tech Epic: Standard Operating Procedure Automation | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0115686 | 109485 | Standard Operating Procedure - Automated Planning | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: InfoSec new WAF capability/solution | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0115705 | 143732 | InfoSec new WAF capability/solution | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU Privacy Mailbox Categorization Automation | Approved | Local Enhancement Epic | Platforms Portfolio | 0115848 |  |  | Local Enhancement Epic | Build | E-568970 | E-568970 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-02-17 | 2026-05-29 | 2026-04-23
Local Enhancement Epic: Automation - MWA | Approved | Local Enhancement Epic | Platforms Portfolio | 0115895 |  |  | Local Enhancement Epic | Build | E-567978 | E-567978 | 2: S | 2026-02-26 |  | 100% | 1 | 1 |  | 0 |  | 2026-01-06 | 2026-03-20 | 2026-02-26
Local Enhancement Epic: Display Mgr. User ID & Email Notification | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115896 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26 RHEL OS Patching | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0115907 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Azure Cloud Witness | Approved | Local Enhancement Epic | Platforms Portfolio | 0115911 |  |  | Local Enhancement Epic | Build | E-565783 | E-565783 | 1: XS | 2026-03-30 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-02 | 2026-05-25 | 2026-03-30
Local Enhancement Epic: Wiz PDSM Ticketing & Messaging Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115913 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-05 | 2026-05-04
Local Enhancement Epic: miCA Enhancements | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115915 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Develop Supplier Portal on Oracle Platform | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0115914 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: ANZ - LCM - Extreme Networks EOL Wi-Fi AP | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115916 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575660 | E-575660 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-05-01 | 2026-11-30
Lifecycle Management Epic: Migration to Dynatrace Monitoring Tool | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0115923 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: FY27_InfoSec_Threat Detect Eng_Production Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115956 |  |  | Lifecycle Management Epic | Build | E-566456 | E-566456 | 3: M | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-02-04 | 2026-10-30 | 2026-04-23
Lifecycle Management Epic: CY26 Planned vCF Patching | Approved | Lifecycle Management Epic | Platforms Portfolio | 0115977 |  |  | Lifecycle Management Epic | Build | E-565362 | E-565362 | 5: XL | 2026-03-25 |  |  | 1 | 0 | 1 | 0 |  | 2026-02-09 | 2027-12-31 | 2026-03-25
Biz w/ Tech Epic: InfoSec-XSIAM: Phase 2 Deployment | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115993 | 7662 | Next-Gen GCCR Threat Detection Engineering & Respo | Biz w/ Tech Epic | Build | E-566873 | E-566873 | 2: S | 2026-03-16 |  |  | 4 | 0 | 2 | 2 |  | 2026-01-26 | 2026-08-03 | 2026-03-16
Biz w/ Tech Epic: Migration to Dynatrace Monitoring Tool | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115996 | 9302 | TS-VL3-Observability-Tools Modernization | Biz w/ Tech Epic | Build | E-565620 | E-565620 | 2: S | 2026-03-20 |  | 100% | 1 | 1 |  | 0 |  | 2026-01-26 | 2026-05-29 | 2026-03-20
Biz w/ Tech Epic: Develop SIP on Oracle Platform | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0115999 | 153778 | EMR IFT Supplier Portal | Biz w/ Tech Epic | Assessment & Analysis | E-577721 | E-577721 | 3: M |  |  |  | 20 | 0 |  | 20 |  | 2026-03-16 | 2027-03-12
Local Enhancement Epic: Dynatrace Observability for CLIP Platform | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116013 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ASR Upgrades for Miami / Dallas Equinix | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116035 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-580412 | E-580412 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: MTTC Ship Center Downsize | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116036 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Radio Managed Services | Approved | Local Enhancement Epic | Platforms Portfolio | 0116053 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569016 | E-569016 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable Agent Client Connector | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0116067 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Enable Data Certification Within SN and Ownership | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0116070 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: ServiceNow Zurich Upgrade | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0116091 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ServiceNow Australia Release | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0116092 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-Shipment-SEFS ART-CY26 PI_02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116130 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572658 | E-572658 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Tooling-PF-EFS-Shipment-SEFS ART-CY26 PI_ 02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116131 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572663 | E-572663 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Upgrades-PF-EFS-Shipment-SEFS ART-CY26 PI_ 02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116132 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572655 | E-572655 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: TS-VL3-Platform-POC-Infra DevX Data | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0116136 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ServiceNow Security Posture Control (SPC) Imp. | In Progress | Biz w/ Tech Epic | Platforms Portfolio | 0116142 | 166051 | InfoSec - Risk to Remediate Initiative | Biz w/ Tech Epic | Assessment & Analysis | E-579302 | E-579302 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2026-08-31
Biz w/ Tech Epic: Workstation Vulnerabilities | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116145 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Security Incident Response (SIR) Implementation | In Progress | Biz w/ Tech Epic | Platforms Portfolio | 0116146 | 166051 | InfoSec - Risk to Remediate Initiative | Biz w/ Tech Epic | Assessment & Analysis | E-579279 | E-579279 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2026-08-31
Local Enhancement Epic: Okhla Facility Relocation Due to Landlord Notice | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116196 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: INFOSEC-SBOM Process | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116268 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: OCI Remediation & PAM Implementation | On Hold | Local Enhancement Epic | Platforms Portfolio | 0116269 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568971 | E-568971 | 3: M |  |  |  | 2 | 0 |  | 2 |  | 2026-01-05 | 2026-07-31
Local Enhancement Epic: Enhance SCCM patch status integration with PDSM | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116282 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: InfoSec: Micro Segmentation Orange Prod | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116291 | 170917 | Infosec - Micro Segmentation Enforcement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-06 | 2026-10-30
Biz w/ Tech Epic: EPIC Project FORCE (FY27 Openings) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0116382 | 141902 | Project FORCE (FY27 Openings) | Biz w/ Tech Epic | Assessment & Analysis | E-581339 | E-581339 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2027-05-31
Lifecycle Management Epic: Compliance-PF-EFS-Geopolitical-GpEFS-PLG ART-CY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116409 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572662 | E-572662 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Compliance-PF-EFS-Location-LEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116410 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572659 | E-572659 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Compliance-PF-EFS-Geography-GEFS ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116411 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571050 | E-571050 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-01 | 2026-06-05
Lifecycle Management Epic: Compliance-PF-EFS-Product-PEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116413 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571048 | E-571048 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2026-05-19
Lifecycle Management Epic: CCTV LCM project in Multiple Locations | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116457 |  |  | Lifecycle Management Epic | Build | E-569669 | E-569669 | 3: M | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-09 | 2026-05-07 | 2026-04-23
Local Enhancement Epic: Scaling AI - Development of AI Foundations [Model] | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0116459 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrade-PF-EFS-CEFS ART-CY26 PI-2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116460 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571017 | E-571017 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Tooling-PF-EFS-CEFS ART-CY26 PI-2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116461 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571019 | E-571019 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Compliance-PF-EFS-CEFS ART-CY26 PI-2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116462 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571020 | E-571020 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Upgrade-PF-EFS-Geography-GEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116463 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571018 | E-571018 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Upgrade-PF-EFS-Location-LEFS-PLG ART-CY26 PI1 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116464 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572661 | E-572661 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-23 | 2026-03-23
Lifecycle Management Epic: Upgrade-PF-EFS-Geopolitical-GpEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116465 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571051 | E-571051 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Upgrade-PF-EFS-Product-PEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116466 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571052 | E-571052 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Tooling-PF-EFS-Geopolitical-GpEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116467 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-572657 | E-572657 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-11 | 2026-05-19
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116468 |  |  | Lifecycle Management Epic | Build | E-572660 | E-572660 | 1: XS | 2026-04-08 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-11 | 2026-05-19 | 2026-04-08
Lifecycle Management Epic: Tooling-PF-EFS-Product-PEFS-PLG ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116469 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-571053 | E-571053 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-30 | 2026-05-19
Lifecycle Management Epic: Tooling-PF-EFS-Geography-GEFS ART-CY26 PI2 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116470 |  |  | Lifecycle Management Epic | Build | E-571049 | E-571049 | 1: XS | 2026-03-27 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-11 | 2026-05-19 | 2026-03-27
Local Enhancement Epic: Scaling AI - Development of AI Foundations [Model] | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116477 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LCM-EIAM-Vulnerability-Management-CY26PI02-PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116549 |  |  | Lifecycle Management Epic | Build | E-570612 | E-570612 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-08-03 | 2026-04-22
Local Enhancement Epic: Digital Certificates CY26PI02 - CY26PI03 | Approved | Local Enhancement Epic | Platforms Portfolio | 0116550 |  |  | Local Enhancement Epic | Build | E-570319 | E-570319 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-05-29 | 2026-04-23
Lifecycle Management Epic: InfoSec - EIAM FIRST Support - CY26PI02-PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116551 |  |  | Lifecycle Management Epic | Build | E-570615 | E-570615 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-10-09 | 2026-04-22
Lifecycle Management Epic: InfoSec FY26 PI02 Ot/IoT Engineering | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116552 |  |  | Lifecycle Management Epic | Build | E-570611 | E-570611 | 3: M | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-05-22 | 2026-04-22
Lifecycle Management Epic: InfoSec CY26 PI02 OT/IoT Governance | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116553 |  |  | Lifecycle Management Epic | Build | E-570320 | E-570320 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-05-22 | 2026-04-22
Local Enhancement Epic: InfoSec - ServiceNow SIR Module | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116595 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXF - Ocala, FL Make-Ready - CLEAR 100014632 | Approved | Local Enhancement Epic | Platforms Portfolio | 0116596 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574371 | E-574371 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Direct FX service in 24 Markets [ICED AMERICANO] | Approved | Local Enhancement Epic | Platforms Portfolio | 0116597 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583629 | E-583629 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: EIAM Audit Support CY26PI02-CY26PI04 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116619 |  |  | Lifecycle Management Epic | Build | E-570613 | E-570613 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-10-09 | 2026-04-22
Lifecycle Management Epic: Infosec LCM Always on Avengers CY26PI02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116620 |  |  | Lifecycle Management Epic | Build | E-572738 | E-572738 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-05-22 | 2026-04-22
Lifecycle Management Epic: FY26 LAC Router and Switch LCM | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116628 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-577956 | E-577956 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Core Switch Upgrades - MX - CUAH | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116629 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-577958 | E-577958 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LAC-BR Systems Retirement – Platforms | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116630 |  |  | Lifecycle Management Epic | Build | E-569939 | E-569939 | 3: M | 2026-04-24 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-24
Local Enhancement Epic: LAC-BR-Infrastructure New Locations BR | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116631 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Infosec: FedEx Zscaler Cloud Tenant for BCDR | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0116636 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Build | E-569856 | E-569856 | 4: L | 2026-03-25 |  |  | 3 | 0 | 3 | 0 |  | 2026-03-16 | 2026-11-30 | 2026-03-25
Biz w/ Tech Epic: Migrate AMQ flows to EMS | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116642 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: ServiceNow/Workiva Data Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116654 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ISBPA Production Support Lifecycle Management | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116700 |  |  | Lifecycle Management Epic | Build | E-573587 | E-573587 | 2: S | 2026-04-23 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-23
Local Enhancement Epic: PDSM Enhancements for Managed Services Reporting | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116702 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Infosec IT Resiliency Protection | Approved | Local Enhancement Epic | Platforms Portfolio | 0116708 |  |  | Local Enhancement Epic | Build | E-576726 | E-576726 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2027-03-12 | 2026-04-22
Lifecycle Management Epic: InfoSec IT Resiliency Compliance | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116709 |  |  | Lifecycle Management Epic | Build | E-576723 | E-576723 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2027-03-12 | 2026-04-22
Local Enhancement Epic: GUAG New Ship Center | Approved | Local Enhancement Epic | Platforms Portfolio | 0116740 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577918 | E-577918 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Fraud Oversight and Remediation | Approved | Local Enhancement Epic | Platforms Portfolio | 0116759 |  |  | Local Enhancement Epic | Build | E-572739 | E-572739 | 2: S | 2026-04-24 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-02 | 2027-03-02 | 2026-04-24
Local Enhancement Epic: GUAK New Ship Center | Approved | Local Enhancement Epic | Platforms Portfolio | 0116761 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577957 | E-577957 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: GUAL New Ship Center | Approved | Local Enhancement Epic | Platforms Portfolio | 0116765 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577959 | E-577959 | 3: M |  |  |  | 1 | 0 |  | 1
Biz w/ Tech Epic: Service Mapping & Agent Client Connector Implement | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0116770 | 108247 | TS-VL2-Commercial App Retirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable and Implement CSDM within ServiceNow | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0116774 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FY26_PI2_& PI3_Platforms_Delphix_Enterprise_Expans | Approved | Local Enhancement Epic | Platforms Portfolio | 0116785 |  |  | Local Enhancement Epic | Build | E-572766 | E-572766 | 3: M | 2026-03-16 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-02 | 2026-05-29 | 2026-03-16
Local Enhancement Epic: HAM Prro Implementation at LGG HUB | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116813 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Akamai Edge IP Binding | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116817 | 143732 | InfoSec new WAF capability/solution | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Automation of DSAR Data Deletion Process - Phase 2 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116865 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: NMIAL Hub UDS integration – Platform Scope | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116870 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DIAL Hub UDS integration – Platform Scope | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116871 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CrowdStrike Falcon Sensor AI Support Assistant | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116872 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: InfoSec CY26 OT/IoT Emerging Technology | Approved | Local Enhancement Epic | Platforms Portfolio | 0116878 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576725 | E-576725 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: IPCC to APAC Network Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116880 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable and Implement CSDM within ServiceNow | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0116072 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Implement AutomatePro AutoDeploy | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116885 | 171172 | AutomatePro | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-05-04 | 2026-05-05
Biz w/ Tech Epic: Implement AutomatePro AutoTest | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116887 | 171172 | AutomatePro | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-05-04 | 2026-05-27
Biz w/ Tech Epic: FUSUS Core NVR Initiative | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0116892 | 8729 | FUSUS Core NVR Initiative | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Infosec LCM Cyber Knights CY26PI02 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0116955 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Infosec LCM 5th Dimension CY26PI02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0116957 |  |  | Lifecycle Management Epic | Build | E-576724 | E-576724 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-22
Lifecycle Management Epic: Audio Visual Life Cycle Management Upgrades | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0116972 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Infosec_FY27_PI2_Create Azure Bot for XSIAM "Micro | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117018 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enhancement of EBR Logic in CAM | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117050 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Proactive SO – Procurement of Dell PowerStore 1200 | On Hold | Lifecycle Management Epic | Platforms Portfolio | 0117071 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FXO Network Upgrades | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117091 | 8729 | FUSUS Core NVR Initiative | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FXO Network Readiness | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0117092 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Wiz CMDB Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0116800 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-13 | 2026-07-31
Biz w/ Tech Epic: EPIC Project FORCE (FY28 Openings) | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0117108 | 139945 | Project FORCE (FY28 Openings) | Biz w/ Tech Epic | Assessment & Analysis | E-581239 | E-581239 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2027-04-01 | 2028-05-31
Local Enhancement Epic: FY26_PI2_Infosec-CMDB_Integration_XSIAM | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117110 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: InfoSec - CY26 KTLO SSE Operational Support | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117111 |  |  | Lifecycle Management Epic | Build | E-579354 | E-579354 | 2: S | 2026-04-17 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-12-31 | 2026-04-17
Local Enhancement Epic: BTSA New Facility | Cancelled | Local Enhancement Epic | Platforms Portfolio | 0115533 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Transition of Managed Service Provider | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117117 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FR new station in Arras (XEBA) | Not Started | Local Enhancement Epic | Platforms Portfolio | 0115692 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: InfoSec OT/IoT AI | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117139 |  |  | Lifecycle Management Epic | Build | E-579353 | E-579353 | 3: M | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-22
Lifecycle Management Epic: REACT Application Retirement | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117156 |  |  | Lifecycle Management Epic | Build | E-577574 | E-577574 | 3: M | 2026-03-25 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2027-03-31 | 2026-03-25
Lifecycle Management Epic: Edge Compute 14G LCM | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117220 |  |  | Lifecycle Management Epic | Build | E-580085 | E-580085 | 3: M | 2026-04-13 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-30 | 2027-08-31 | 2026-04-13
Lifecycle Management Epic: Infosec - LCM - Attack Surface Analytics CY26 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117221 |  |  | Lifecycle Management Epic | Build | E-580389 | E-580389 | 3: M | 2026-04-16 |  |  | 2 | 0 | 1 | 1 |  |  |  | 2026-04-16
Local Enhancement Epic: Network Infrastructure Setup at RUHB (North Statio | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117222 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: InfoSec OT/IoT Phosphorus POV | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117239 |  |  | Lifecycle Management Epic | Build | E-579356 | E-579356 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  | 2026-03-16 | 2026-09-11 | 2026-04-22
Local Enhancement Epic: Office space for Data & AI Chennai | Approved | Local Enhancement Epic | Platforms Portfolio | 0117240 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583630 | E-583630 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: VALET New API Integration | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0117242 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Archer MIgration to OnSpring | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0117244 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance/ Legal & Regulatory/ Audits - CY26 PI02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117290 |  |  | Lifecycle Management Epic | Build | E-579713 | E-579713 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-22
Lifecycle Management Epic: Tooling – Network Management Team – CY26 PI02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117291 |  |  | Lifecycle Management Epic | Build | E-579715 | E-579715 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-22
Lifecycle Management Epic: Upgrades – Global Network Engineering – CY26 PI02 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117292 |  |  | Lifecycle Management Epic | Build | E-579714 | E-579714 | 2: S | 2026-04-22 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-04-22
Local Enhancement Epic: CCTV LCM project in Krakow and VKRA. | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117296 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Build J2C Network Infrastructure | Approved | Biz w/ Tech Epic | Platforms Portfolio | 0117341 | 189022 | Journey to Cloud GCP Network infrastructure | Biz w/ Tech Epic | Assessment & Analysis | E-583333 | E-583333 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-02 | 2026-09-30
Local Enhancement Epic: Ireland Postal Address Adoption - Implementing EI | Approved | Local Enhancement Epic | Platforms Portfolio | 0117348 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583496 | E-583496 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Support Server Enablement for Existing Geodata Pro | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117350 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: InfoSec - IDPT - BRT Archer/Onspring Support | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117351 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: LCM Brazil Legacy Transformation & Modernization | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117407 | 143378 | LCM Brazil Legacy Transformation & Modernization | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SD -WAN Assessment for MEISA, ANZ and APAC | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117413 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Koblenz New Building | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117415 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Airbill Max Quantity default change | Approved | Local Enhancement Epic | Platforms Portfolio | 0117416 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583495 | E-583495 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PL Suwalki Station (ZWK) New Location#2 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117448 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PL_Pila New Station#2 | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117450 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Odin Keep the Lights On (Maintenance) | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117453 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Linehaul Converting to call centre | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117458 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LCM Field Infrastructure Canada | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117459 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: International Hardware EOL - ESXi | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117461 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable Data Certification Within SN and Ownership | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117472 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ServiceNow Foundational Data Transformation & Data | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117473 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Fault Monitoring Tool Replacement (NetCure Replace | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117476 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582982 | E-582982 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Enable and Implement CSDM within ServiceNow | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117487 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ServiceNow Foundational Data Transformation & Data | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117488 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CPHA CCTV lifecycle replacement project | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117489 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LCM Field Infrastructure US | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117497 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: RFID Analytics - Platforms | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0117502 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrades-PF-EFS-Shipment-SEFS ART-CY26 PI_ 03 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117556 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-Shipment-SEFS ART-CY26 PI_ 03 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117557 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-Shipment-SEFS ART-CY26 PI_ 03 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117558 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Setup Network Infrastructure for GCP | Cancelled | Biz w/ Tech Epic | Platforms Portfolio | 0117562 | 189022 | Journey to Cloud GCP Network infrastructure | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Microsoft EAS License Remediation (FY26) | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117577 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: WTC Specialized Business Environment (SBE)/Node | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117594 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: MERN Video Conference System + Projector | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117595 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: InfoSec Cyber Resiliency LCM CY26 | Cancelled | Lifecycle Management Epic | Platforms Portfolio | 0117601 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: PEx Research - Understand dependent systems | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117605 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-Geography-GEFS ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117609 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583500 | E-583500 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-Product-PEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117610 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583499 | E-583499 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-Location-LEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117612 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583497 | E-583497 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-GpEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117613 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583498 | E-583498 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-Geography-GEFS ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117614 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583505 | E-583505 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-Product-PEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117615 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583503 | E-583503 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-Location-LEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117616 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583502 | E-583502 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-GpEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117617 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583501 | E-583501 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrade-PF-EFS-Product-PEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117618 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583507 | E-583507 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrade-PF-EFS-GpEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117619 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583506 | E-583506 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrade-PF-EFS-Location-LEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117620 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583508 | E-583508 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrade-PF-EFS-Geography-GEFS-PLG ART-CY26 PI3 | Approved | Lifecycle Management Epic | Platforms Portfolio | 0117621 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583504 | E-583504 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Compliance-PF-EFS-Customer-CEFS ART-CY26 PI3 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117622 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Tooling-PF-EFS-Customer-CEFS ART-CY26 PI3 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117623 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Upgrade-PF-EFS-Customer- CEFS ART-CY26 PI3 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117624 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FR: close stations incl. consolidation (111070) | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117640 | 111070 | FR ALPINE: close stations incl. consolidation | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-09-01 | 2026-10-14
Biz w/ Tech Epic: Agent Client Collector | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117645 | 188639 | TS-VL2-Con-ServiceNow – Svc Map+Agent Client Conn | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Scaling AI - Governance [ServiceNow AI Control To | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117687 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Transition of Managed Service Provider | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117702 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TY26-PF-PEFS-Production-Support | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117707 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TY26-PF-LEFS-Production-Support | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117709 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TY26-PF-GEFS-Production-Support | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117710 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TY26-PF-GpEFS-Production-Support | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117711 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Patching-PF-EFS-GpEFS-PLG ART-TY26 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117712 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Patching-PF-EFS-Product-PEFS-PLG ART-TY26 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117713 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Patching-PF-EFS-Geography-GEFS-PLG ART-TY26 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117714 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Patching-PF-EFS-Location-LEFS-PLG ART-TY26 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117715 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PF-PLG-LEFS-Enhancements Foundational Services Qua | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117717 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_InfoSec-Cloud Incident Response | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117719 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PF-PLG-PEFS-Enhancements Foundational Services Qua | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117735 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PF-PLG-GpEFS-Enhancements Foundational Services Qu | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117736 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PF- GEFS - Enhancements Foundational Services Qual | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117738 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Cyber Resiliency Lifecycle Management CY26 | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117739 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TY26-PF-SEFS-Production-Support | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117749 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SAMPro Autodesk API | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117754 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: OKTA SaaS License Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117755 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ANZ - LCM - Extreme Networks EOL Controllers | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117756 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: InfoSec - Micro Segmentation Outbound Apps | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117784 | 170917 | Infosec - Micro Segmentation Enforcement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-05-25 | 2026-10-30
Local Enhancement Epic: PEFS - Migration of Language Translation Service f | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117793 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: InfoSec: Micro Segmentation Inbound Applications | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117798 | 170917 | Infosec - Micro Segmentation Enforcement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2027-01-01 | 2027-12-31
Lifecycle Management Epic: SQL Server 2014 & Below LCM Upgrade | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117809 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: SQL Server 2014 & Below LCM Upgrade | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117810 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: SQL Server 2014 & Below LCM Upgrade | Not Started | Biz w/ Tech Epic | Platforms Portfolio | 0117811 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: ECDC Support for Digital Resolution capabilities | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117818 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Network Eng AI Data Sync and ServiceNow API for St | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117855 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Infosec - Service Graph Connector for use in Servi | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117861 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GpEFS - Support OSC Retirement (Research and Analy | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117871 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Traffic Analyst Upgrade to Optics | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117875 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Webex Contact Center Enterprise Upgrade to Version | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117876 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PF-Shipment SEFS-Enhancements Foundational Service | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117878 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: iSell - Enterprise Contact Re Integration | Not Started | Local Enhancement Epic | Platforms Portfolio | 0117910 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_InfoSec-Next-Gen FTI strategy | Not Started | Lifecycle Management Epic | Platforms Portfolio | 0117916 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic 1 - Employee Roster & Demand Planning | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103227 | 9066 | PLANS - US Air Planning Labor & Rostering | Biz w/ Tech Epic | Assessment & Analysis | E-470668 | E-470668 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-08-01 | 2026-10-15
Biz w/ Tech Epic: WS2 - Automate the application of pickup scans | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103714 | 8861 | WS2 - Automate the application of pickup scans and | Biz w/ Tech Epic | Assessment & Analysis | E-436641 | E-436641 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 4.0 Manage ACAS Rejected Shipments | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103726 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 5.0 Manage Intercepts and CASE(s) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103730 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 1.0 Stop The Creation of Non-Compliant Shipments | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103731 | 7310 | US CBP ACAS Vague Description Enforcement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: PIE Review | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103834 | 6851 | PIE Review | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Shipment CDM: 1.0 Pilot basic sortation enablement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104245 | 7693 | WS1 - [1B] Shipment CDM - First iteration for Sort | Biz w/ Tech Epic | Assessment & Analysis | E-427390 | E-427390 | 3: M |  |  | 50% | 6 | 3 | 3 | 0 | No | 2025-01-13 | 2025-09-19
Biz w/ Tech Epic: Inbound | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104249 | 7584 | AS/RS in MEMH East Cage #7584 | Biz w/ Tech Epic | Assessment & Analysis | E-513590 | E-513590 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-04-21 | 2025-04-21
Biz w/ Tech Epic: RFID - Core IT Development Work | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104404 | 7287 | [Enabler] RFID - Core IT Development Work | Biz w/ Tech Epic | Assessment & Analysis | E-552742 | E-552742 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2027-06-16
Biz w/ Tech Epic: Tricolor Facilities Enablement ORD- ORDRZ Bldg 612 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104510 | 7961 | Tricolor Facilities Enablement ORD- ORDRZ Bldg 612 | Biz w/ Tech Epic | Assessment & Analysis | E-476513 | E-476513 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic=E-134952. PPM=228235 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104543 | 88381 | Container Load Decision Support (Ring Scanner) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C1 - Ability to create a Service Disruption Reques | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104620 | 9083 | Enterprise Disruption Reporting | Biz w/ Tech Epic | Assessment & Analysis | E-570673 | E-570673 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C2 - Service Disruption Workflow Management | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104623 | 9083 | Enterprise Disruption Reporting | Biz w/ Tech Epic | Assessment & Analysis | E-570672 | E-570672 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: C3 - Service Disruption Handling Unit Impacts | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104624 | 9083 | Enterprise Disruption Reporting | Biz w/ Tech Epic | Assessment & Analysis | E-570670 | E-570670 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-451996 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104676 |  |  | Biz w/ Tech Epic | Backlog | E-521070 | E-521070 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-451996 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104677 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Global P&D Ecosystem Enabler E-449348 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104682 | 7406 | Global P&D Ecosystem Enabler | Biz w/ Tech Epic | Backlog | E-449348 | E-449348 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-29 | 2035-10-26
Local Enhancement Epic: SEDError Queue GUI pagination enhancement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104701 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Linehaul Next Trip Visibility | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104712 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Replace existing TRI scan with HIPS at DWCH | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104718 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539740 | E-539740 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Aircraft Tooling Project - Local Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104733 |  |  | Local Enhancement Epic | Assessment & Analysis | E-373833 | E-373833 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Optical Scan Tunnel | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104735 |  |  | Local Enhancement Epic | Assessment & Analysis | E-398817 | E-398817 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-22
Local Enhancement Epic: Linehaul Two-Way Communication | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104762 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Linehaul Route Turn-by-Turn Directions | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104764 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update UVSDK to include new FDG services | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104769 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC - BR: Connect to FedEx Net WMS - LMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104775 |  |  | Local Enhancement Epic | Backlog | E-521033 | E-521033 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FPOE IPFS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104784 |  |  | Local Enhancement Epic | Build | E-485725 | E-485725 | 2: S | 2026-03-17 |  |  | 5 | 0 | 5 | 0 | No | 2023-11-15 | 2026-02-27 | 2026-03-17
Local Enhancement Epic: LAC-FGC Mexico-XML Change Regulatory Due 01MAR25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104799 |  |  | Local Enhancement Epic | Backlog | E-470373 | E-470373 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UDS RTH Intercept | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104800 |  |  | Local Enhancement Epic | Backlog | E-485087 | E-485087 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Delivery side of DG by Road ADR points MVP+ | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104802 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ACAS Vague Commodity Description Enforcement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104829 | 7310 | US CBP ACAS Vague Description Enforcement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-10 | 2025-05-09
Biz w/ Tech Epic: Location Inputs to Workday (FMT) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104890 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build | E-512277 | E-512277 | 4: L | 2026-01-23 |  | 28.57% | 7 | 2 | 1 | 4 | No | 2025-11-03 | 2027-01-07 | 2026-01-23
Local Enhancement Epic: Apple Multiple HTS - 858 Data | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0104894 |  |  | Local Enhancement Epic | Done | E-501563 | E-501563 | 2: S | 2025-06-27 | 2025-08-11 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-08-11
Biz w/ Tech Epic: Common CONS VB1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104927 | 89829 | Common CONs - Value Bundle 1 | Biz w/ Tech Epic | Assessment & Analysis | E-400769 | E-400769 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-22
Biz w/ Tech Epic: Common CONS VB1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104928 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CDAS - CSA Dashboard Sunset | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105311 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-549836 | E-549836 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT- LMS_Ancillary Services Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105322 |  |  | Local Enhancement Epic | Backlog | E-520934 | E-520934 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Romania eTransport | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105328 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Process for adding accounts in SEP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105331 |  |  | Local Enhancement Epic | Launch & Evaluate | E-501801 | E-501801 | 2: S | 2025-06-27 |  |  | 0 | 0 |  | 0 | No | 2024-07-24 | 2024-12-10 | 2025-06-27
Local Enhancement Epic: FXCC/TCN Fuel Card Change | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105334 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CDAS Message Inquiry modifications | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105358 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571634 | E-571634 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-23 | 2026-08-19
Local Enhancement Epic: CDAS EU to Receive 1 year of Historical FAMIS data | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105360 |  |  | Local Enhancement Epic | Assessment & Analysis | E-341202 | E-341202 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update for EDT 1.0, 2.0, and 3.0 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105361 |  |  | Local Enhancement Epic | Backlog | E-482643 | E-482643 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-07
Local Enhancement Epic: LocationsDst.GVMax file amendment | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105362 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: YWGR IPD wrong URSA label post clearance | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105363 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL EDI Tracking Capability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105364 |  |  | Local Enhancement Epic | Backlog | E-482593 | E-482593 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2025-10-31
Lifecycle Management Epic: IT request to Refactoring Microservices to ENS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105366 |  |  | Lifecycle Management Epic | Backlog | E-521034 | E-521034 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CBAM | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105367 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SPS Alignment Table | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105368 |  |  | Local Enhancement Epic | Assessment & Analysis | E-309845 | E-309845 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-05
Biz w/ Tech Epic: *L1 MEMH Dynamic Flow Management | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105115 | 89396 | Phase 2 - MEMH Dynamic Flow Management | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG Integration to Customer Mooz | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105420 |  |  | Local Enhancement Epic | Backlog | E-521035 | E-521035 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: VB3: New U.S. Tariff Regulations for 2025 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105422 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Corrective Action Summary and Repeat Indicator | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105424 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DEX10 / DDEX09 / COMM scan enablement | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105458 | 7659 | Damaged Package Tool (DPT) New Opportunities & New | Biz w/ Tech Epic | Backlog | E-522714 | E-522714 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-01 | 2026-04-30
Biz w/ Tech Epic: 2. Export Shipment Info to Sequencer Solver | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105483 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-07-31
Local Enhancement Epic: Test Check - UVSDK Data | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105536 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LHIF - Crew Pay Ingestion | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105560 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update to the Webservice Call from Adapt to PCS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105561 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Panasonic Automotive EDI Setup | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105565 |  |  | Local Enhancement Epic | Backlog | E-501584 | E-501584 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LSSI -New API endpoint for Preference Center | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105566 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU Union Customs Code - Automated Export System | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105568 |  |  | Local Enhancement Epic | Assessment & Analysis | E-296322 | E-296322 | 3: M |  |  |  | 0 | 0 |  | 0 | Yes | 2024-07-22 | 2028-06-13
Local Enhancement Epic: EU Union Customs Code - PNTS | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105569 |  |  | Local Enhancement Epic | Assessment & Analysis | E-337127 | E-337127 | 3: M |  |  |  | 0 | 0 |  | 0 | Yes | 2024-07-22 | 2026-09-09
Local Enhancement Epic: EU Union Customs Code - Automated Import System | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105570 |  |  | Local Enhancement Epic | Assessment & Analysis | E-336452 | E-336452 | 2: S |  |  |  | 0 | 0 |  | 0 | Yes | 2024-07-22 | 2030-05-16
Lifecycle Management Epic: LAC-BR-3-TNT-SISTRIN - Red Hat 8 update | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105573 |  |  | Lifecycle Management Epic | Backlog | E-520906 | E-520906 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-04-06 | 2026-04-06
Local Enhancement Epic: FedEx Kenya PIN No. Indication under FWB | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105574 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SafetyNet Programs Improvements & New Features | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105575 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Address Service Now Vulnerability issues | Completed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105578 |  |  | Lifecycle Management Epic | Done | E-500338 | E-500338 | 3: M | 2025-06-27 | 2025-06-27 |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27 | 2025-06-27
Biz w/ Tech Epic: FXFD Personalized Notification - SCO Epic | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105604 | 6809 | FXFD Personalized Notifications - per customer req | Biz w/ Tech Epic | Build | E-482258 | E-482258 | 2: S | 2025-08-05 |  | 100% | 1 | 1 |  | 0 | No | 2025-06-02 | 2025-11-19 | 2025-08-05
Biz w/ Tech Epic: E-402444 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105619 | 7431 | Dangerous Goods Surcharge | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New data needed on existing HR Feed | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105651 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Part Plan Notification | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Settlement Payment Termination Processing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105653 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571021 | E-571021 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-23 | 2026-06-10
Local Enhancement Epic: Surface Clearance CBP Tariff Enforcement | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105654 |  |  | Local Enhancement Epic | Done | E-469323 | E-469323 | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: LAC MX Illicit Package Detection | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105655 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-402444 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105657 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-402444 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105661 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: OTB : Surface Sortation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105675 | 94177 | OTB : Parcel Non-conveyable & Limited Quantity | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO App Opt - VP Snyder - FXF RFID Notification | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105699 |  |  | Local Enhancement Epic | Backlog | E-504324 | E-504324 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: APAC_CN-US-CN Addit. Info/Reciprocal tariffs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105706 |  |  | Local Enhancement Epic | Backlog | E-499654 | E-499654 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2025-08-29
Local Enhancement Epic: Overages Inbound Spain | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105708 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Resolve issue with reading wrong barcode on DH2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105709 |  |  | Local Enhancement Epic | Backlog | E-499959 | E-499959 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: ADAPT Enhanced & Defect Improvements 24-00028 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105711 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ADAPT Enhanced & Defect Improvements 23-00025 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105712 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ADAPT Enhanced & Defect Improvements 24-00034 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105713 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ADAPT Enhanced & Defect Improvements 24-00064 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105714 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 767 Resubstantiation Report | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105715 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PVG OB declaration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105718 |  |  | Local Enhancement Epic | Assessment & Analysis | E-481849 | E-481849 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Mismatch in FHL upload to BD through RMS & SFTP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105720 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551638 | E-551638 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-10-28
Lifecycle Management Epic: LHRA Securing backend service E-478332 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105721 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-539739 | E-539739 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2026-01-14 | 2026-03-24
Local Enhancement Epic: Mandatory BITE for MELs - Investigate to automate | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105722 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automatic Sync Weight & Balance to WBOffline | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105723 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ADAPT Enhanced & Defect Improvements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105724 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ROCS 2.0 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105725 |  |  | Local Enhancement Epic | Build | E-503700 | E-503700 | 2: S | 2025-07-01 |  |  | 66 | 0 | 4 | 62 | No | 2023-04-17 | 2037-01-01 | 2025-07-01
Lifecycle Management Epic: Proxy to PurpleConnect (NGPS) | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105726 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Proxy to PurpleConnect (Adapt, PCS, Optix, APS) | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105727 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CGN HUBSTACK "DG-ON-LOOP"-instruction | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105728 |  |  | Local Enhancement Epic | Backlog | E-531033 | E-531033 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: [UDS - NRT] - SCO | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105730 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552031 | E-552031 | 3: M |  |  |  | 145 | 0 |  | 145 | No
Local Enhancement Epic: Enable TransferUnit for CONS from other Scan sol. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105732 |  |  | Local Enhancement Epic | Backlog | E-536354 | E-536354 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SchooX - 3PS LMS Application (Local Request) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105733 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540273 | E-540273 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-16 | 2026-03-16
Local Enhancement Epic: World Tariff & Trade Tools Support for GEMINI FY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105819 |  |  | Local Enhancement Epic | Backlog | E-520903 | E-520903 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Deploy FXG QA applications to LEO devices | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105820 |  |  | Local Enhancement Epic | Assessment & Analysis | E-507979 | E-507979 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-21
Local Enhancement Epic: Apple 945 Map Enhancement - Service Level | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105824 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Population enhancement to route leg for CONS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105825 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Accugenix - US Bank - Duplex Billing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105826 |  |  | Local Enhancement Epic | Backlog | E-503999 | E-503999 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Quarterly Patching for FTN Database and CIL | In Progress | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105856 |  |  | Lifecycle Management Epic | Done | E-503695 | E-503695 | 3: M | 2025-06-27 | 2025-06-27 | 50% | 2 | 1 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-06-27 | 2025-06-27
Local Enhancement Epic: BCS Automotive Interface Solutions US, LLC | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105857 |  |  | Local Enhancement Epic | Backlog | E-504020 | E-504020 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add Regulatory Controls Field to Number of Copies | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105858 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577600 | E-577600 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ISCQA VB1 - LSSI API | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105859 |  |  | Local Enhancement Epic | Backlog | E-520927 | E-520927 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: RS Americas Foreign Trade Zone (FTZ) EDI Trans | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105861 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: ROCARS UI adding columns as visual aid for CEFA | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105862 |  |  | Local Enhancement Epic | Assessment & Analysis | E-483317 | E-483317 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Settlement E&Y Request | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105916 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555675 | E-555675 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EUFOPD - transfert vendor to accenture | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105917 |  |  | Local Enhancement Epic | Backlog | E-521069 | E-521069 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IATA AWB - Limitations of Liability | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105919 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Customer Direct Weight Accuracy in TMS | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105921 |  |  | Local Enhancement Epic | Backlog | E-513699 | E-513699 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Panasonic Projector EDI Setup | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105927 |  |  | Local Enhancement Epic | Backlog | E-501585 | E-501585 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: L1 Fedex Freight (FXF) Arch,Eng&Gov of Info Sys AE | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104993 | 91377 | Fedex Freight (FXF) Arch,Eng&Gov of Info Sys AEGIS | Biz w/ Tech Epic | Assessment & Analysis | E-492877 | E-492877 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 3. ADJUST & APPLY STOP SEQ FROM SOLVER TO ACCOPS | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106030 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2026-07-31
Local Enhancement Epic: OSC Code Split in MAD | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106042 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enable Long Range scanner with phasar application | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106043 |  |  | Local Enhancement Epic | Assessment & Analysis | E-517244 | E-517244 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-22
Biz w/ Tech Epic: 4. Apply stop seq from solver to driver HH/Manife | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106049 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-07-31
Biz w/ Tech Epic: 5. Sequenced Shipment Map View | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106051 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-07-31
Biz w/ Tech Epic: 7. Address Manual Geocoding Corrections | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106053 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-07-31
Local Enhancement Epic: Communication GTS to OPS of all Intercepts in UDS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106058 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Display scale weight in SWAK V scanner application | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106060 |  |  | Local Enhancement Epic | Backlog | E-528480 | E-528480 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-31 | 2026-03-10
Local Enhancement Epic: EAI 3535089 - map coverage support for additional | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106067 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU Realignment | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106069 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-3-VIDEOWALL - Brazil Cajamar WHS-implement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106084 |  |  | Local Enhancement Epic | Backlog | E-520923 | E-520923 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Tesla - EDI Database | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106085 |  |  | Local Enhancement Epic | Backlog | E-504034 | E-504034 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-14 | 2026-03-24
Local Enhancement Epic: Descriptions & Tracking of Allocation errors eOPS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106088 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580825 | E-580825 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-02-16 | 2026-02-16
Local Enhancement Epic: Canada Realignment | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106090 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New GRSIS Instances | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106092 |  |  | Local Enhancement Epic | Backlog | E-521073 | E-521073 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL-Google-EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106102 |  |  | Local Enhancement Epic | Backlog | E-501573 | E-501573 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-08-12
Local Enhancement Epic: Avery EDI Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106104 |  |  | Local Enhancement Epic | Backlog | E-501564 | E-501564 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-15 | 2026-03-25
Local Enhancement Epic: Business Metrics For QA/Dock Apps | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106105 |  |  | Local Enhancement Epic | Assessment & Analysis | E-507982 | E-507982 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-29
Lifecycle Management Epic: LAC-BR-3-PHPONTO - Migration on-premise to Cloud. | Rejected | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106113 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-3-PHPONTO - Migration on-premise to Cloud. | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106114 |  |  | Lifecycle Management Epic | Backlog | E-520912 | E-520912 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: RPA solution - Pedro POA for HU | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106115 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add Shipment Weight to GRSIS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106116 |  |  | Local Enhancement Epic | Backlog | E-521906 | E-521906 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Workbench E8130/eARC Service Order | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106117 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577139 | E-577139 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Allocate function in DH2 without tapping screen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106118 |  |  | Local Enhancement Epic | Assessment & Analysis | E-499960 | E-499960 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2025-10-14
Local Enhancement Epic: Displaying Customer Location Alpha Origin Details | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106119 |  |  | Local Enhancement Epic | Backlog | E-479861 | E-479861 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: American Eagle Outfitter EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106120 |  |  | Local Enhancement Epic | Backlog | E-500951 | E-500951 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2026-03-24
Local Enhancement Epic: Stop showing invalid uDS Areas on DH2 App | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106121 |  |  | Local Enhancement Epic | Backlog | E-518447 | E-518447 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: Solve CustomsCage CONS type in DH2 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106122 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: XMN IB ACCS functionalities open | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106123 |  |  | Local Enhancement Epic | Backlog | E-508814 | E-508814 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GPS Proof of Delivery (POD) Enhancement | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106124 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DH2 Batch printing CONS for a Shift or Sort Cycle | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106125 |  |  | Local Enhancement Epic | Backlog | E-518476 | E-518476 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: PUX40 Mass Update | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106126 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Commercial BAU Continuity Challenges | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106127 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: SCO - SORT UNITIZE C STATUS INDICATION ON BARCODE | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106150 | 8095 | WS1 - [1A] 82582 Sort-Unitize C status on barcode | Biz w/ Tech Epic | Backlog | E-427385 | E-427385 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-02
Biz w/ Tech Epic: URSA/LSSI Rethink Track 1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106172 | 7247 | URSA/LSSI Rethink- Track 1 - LSSI and URSA Build | Biz w/ Tech Epic | Backlog | E-460560 | E-460560 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-04-02 | 2026-08-19
Lifecycle Management Epic: LAC-BR-TNT-LMS Data Retention (CleanUp LMS + SQ) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106181 |  |  | Lifecycle Management Epic | Backlog | E-520918 | E-520918 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS -freight table Adjustments (phase2) | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106182 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS - Improvements in the registration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106183 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-3-RetailPOS – Dynamics 365 Microsoft Upgrades | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106184 |  |  | Lifecycle Management Epic | Backlog | E-501960 | E-501960 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS- Unlocking of the Difal Quotation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106185 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Upgrade LAC-3-Informatica to 10.5.8 version | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106186 |  |  | Lifecycle Management Epic | Done |  |  | 2: S | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Customer Lexmark: Add Functionality to SPOTS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106187 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528417 | E-528417 | 2: S | 2025-06-27 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-27
Local Enhancement Epic: DH2 App to inquire nr. of pcs. & CONS into a CONS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106188 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575175 | E-575175 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL Transformation:Database Integration with IMAGE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106190 |  |  | Local Enhancement Epic | Backlog | E-503699 | E-503699 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-03 | 2025-10-31
Local Enhancement Epic: TradeSingleWindow(HK Customs new clearance system) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106191 |  |  | Local Enhancement Epic | Backlog | E-520904 | E-520904 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-07-16 | 2026-04-30
Local Enhancement Epic: BD CargoRes Booking WSDL Support | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106192 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Clearance submission trigger Events in Spain | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106193 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Intercept data sending from Hubstack to UDs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106219 |  |  | Local Enhancement Epic | Backlog | E-437040 | E-437040 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-06-09
Local Enhancement Epic: View of PSET CDAS page in Azure/Dataworks TVS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106228 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MW Enhancement for TB Doc Integration to Image | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106230 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CMS AU IMAGE User Provisioning | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106231 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: HP_RLOG Upgrade | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106232 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Publish Damage Data (DPR) to the DPT system | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106233 |  |  | Local Enhancement Epic | Backlog | E-501966 | E-501966 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-29
Local Enhancement Epic: Pop up for Mobile Trip App | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106234 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FSCFY Customer and Facility Support - T-Mobile | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106235 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add New Line For XMN-ICN IXF in China ABS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106242 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC Dominica OB XML | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106248 |  |  | Local Enhancement Epic | Backlog | E-500330 | E-500330 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Thin Client Replacement | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106249 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 232 Steel & Aluminum changes | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106250 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Surface Linehaul GitHub Actions Migration | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106251 |  |  | Lifecycle Management Epic | Backlog | E-517645 | E-517645 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2026-01-20
Local Enhancement Epic: Displaying Position Standards on Summary Screen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106252 |  |  | Local Enhancement Epic | Backlog | E-520938 | E-520938 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2026-01-27 | 2025-06-26
Local Enhancement Epic: Standards variability by Sort and Day of Week | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106253 |  |  | Local Enhancement Epic | Backlog | E-508428 | E-508428 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-27 | 2026-06-16
Local Enhancement Epic: Admin Metrics Screen to sort by Alphabetical Order | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106254 |  |  | Local Enhancement Epic | Backlog | E-520947 | E-520947 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-30 | 2025-09-12
Local Enhancement Epic: Breaks in EDP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106256 |  |  | Local Enhancement Epic | Backlog | E-508429 | E-508429 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2026-01-27 | 2025-06-26
Local Enhancement Epic: I.T. code refactoring to address existing issues | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106258 |  |  | Local Enhancement Epic | Backlog | E-511505 | E-511505 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2027-12-22
Local Enhancement Epic: Luxtrada API Integration | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106260 |  |  | Local Enhancement Epic | Backlog | E-503951 | E-503951 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Trailer Seal Verification and Compliance in eYMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106262 |  |  | Local Enhancement Epic | Backlog | E-522715 | E-522715 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-16 | 2025-11-07
Local Enhancement Epic: GURU Renewal | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106264 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-06-16 | 2026-06-16
Local Enhancement Epic: EU Union Customs Code - NCTS P6 | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106265 |  |  | Local Enhancement Epic | Assessment & Analysis | E-445815 | E-445815 | 3: M |  |  |  | 0 | 0 |  | 0 | Yes | 2024-07-22 | 2026-06-30
Local Enhancement Epic: LAC Argentina Clearance Enhancements - MVP 1 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106267 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Position Screen edits to group/view Facility Type | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106271 |  |  | Local Enhancement Epic | Backlog | E-520926 | E-520926 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Removal of positions and edits to Area Balancing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106273 |  |  | Local Enhancement Epic | Backlog | E-520921 | E-520921 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-11-04 | 2026-01-27
Biz w/ Tech Epic: URSA Rethink (to be deleted) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106274 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Fiscal Year Analysis and Changes | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106279 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Driver Admin and P&D Text Messaging (Citrix Dep) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106314 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CISCO - SPOTS Revised ETA Timezone | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106325 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528416 | E-528416 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: CISCO - amend NBD ETA Calculation for Outer Areas | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106326 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528414 | E-528414 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Local Enhancement Epic: IMAGE Role addition for SSAMI | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106333 |  |  | Local Enhancement Epic | Launch & Evaluate | E-520973 | E-520973 | 1: XS | 2025-07-14 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-14
Local Enhancement Epic: UCC PNTS - Hubstack CDG - Customs status rules | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106334 |  |  | Local Enhancement Epic | Backlog | E-518445 | E-518445 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: Scan Software For Ecommerce Solutions | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106335 |  |  | Local Enhancement Epic | Backlog | E-498480 | E-498480 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-03 | 2026-03-17
Biz w/ Tech Epic: WatchIt | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106356 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: U.S. Manifest Quality Requirements | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106366 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-LOAD-EDI-LG | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106379 |  |  | Local Enhancement Epic | Backlog | E-522382 | E-522382 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UDS Implementation for AU Melbourne Station | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106381 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: [UDS-TPEIP] - SCO Portfolio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106387 |  |  | Local Enhancement Epic | Backlog | E-471805 | E-471805 | 4: L |  |  |  | 7 | 0 |  | 7 | No
Local Enhancement Epic: XF indicator correction | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106388 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Garmin Foreign Trade Zone FTZ EDI Data Consumption | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106389 |  |  | Local Enhancement Epic | Backlog | E-504026 | E-504026 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: AU PCC Sony Exception Enhancement | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106391 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-EDI-Enable EDI process for new partners | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106394 |  |  | Local Enhancement Epic | Backlog | E-520939 | E-520939 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ciena Communications - EDI for Billing and Documen | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106395 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Entegris EDI for Brokerage | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106396 |  |  | Local Enhancement Epic | Backlog | E-513994 | E-513994 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-07-09 | 2025-11-04
Local Enhancement Epic: Idexx Laboratories Inc - US Bank - Billing for EDI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106397 |  |  | Local Enhancement Epic | Backlog | E-513992 | E-513992 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Local Enhancement Epic: Mapping enhancement for Etrans to CW Inner Packs | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106398 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MW Enhancement for TB Doc Integration to Image | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106439 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Microsoft - CUSDEC and CUSDOC | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106442 |  |  | Local Enhancement Epic | Backlog | E-503996 | E-503996 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC - BR: RF Implementations Phase 2 and 3 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106459 |  |  | Local Enhancement Epic | Backlog | E-521905 | E-521905 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Genesis Manifest Functionality | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106460 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FSC - DSCSA Enhancement for Healthcare | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106462 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: Ring Scanner Enablement for PHASAR | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106473 |  |  | Lifecycle Management Epic | Backlog | E-134952 | E-134952 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Swaziland Country Name Change | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106476 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-imp23-REC-migr-plan | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106477 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-Exporta-REC-migr-plan | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106478 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-3-Iglobal-REC-migr-plan | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106479 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PUX47 and Cons Combo Scan | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106490 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-ConsultaCS-CEP-REC-migr-plan | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106491 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - Waters Corporation EDI/API Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106493 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PH ACCS IMPORT – STORAGE FEE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106501 |  |  | Local Enhancement Epic | Backlog | E-480816 | E-480816 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-02-26 | 2025-10-21
Local Enhancement Epic: Formal Auto Assist/Submit Capability | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106504 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LSSI Test App server config into AppDynamics Tool | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106530 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Reflect DG by Road coverage in eSRG | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106535 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: UAE- Clearance server replacement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106536 |  |  | Lifecycle Management Epic | Backlog | E-501190 | E-501190 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Azazie EDI CI | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106538 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Cupshe EDI CI | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106540 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC BR New API Customs Regulation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106541 |  |  | Local Enhancement Epic | Backlog | E-521018 | E-521018 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-3-iGlobal Application Replacement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106542 |  |  | Local Enhancement Epic | Backlog | E-521019 | E-521019 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC BR Pending Clearance Release Module | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106543 |  |  | Local Enhancement Epic | Backlog | E-521020 | E-521020 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC BR New Outbound Systems Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106544 |  |  | Local Enhancement Epic | Backlog | E-521021 | E-521021 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: BAGB link on MBA | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106545 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Zip Assignment Effective Dating | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106565 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CISCO - amend NBD ETA Calculation for Outer Areas | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106608 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC Aruba & Curacao Clearance Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106645 |  |  | Local Enhancement Epic | Backlog | E-522383 | E-522383 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Apply Status Code scans for a unit/CON at creation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106646 |  |  | Local Enhancement Epic | Backlog | E-520992 | E-520992 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: KSA Grace - Report out for various measurements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106647 |  |  | Local Enhancement Epic | Backlog | E-507846 | E-507846 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-01-06
Local Enhancement Epic: Enablement for PV0106189 Customer Tracking API | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106648 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Germany: GDX Enablement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106649 |  |  | Local Enhancement Epic | Backlog | E-521038 | E-521038 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Multi-Object Detection Reporting Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106650 |  |  | Local Enhancement Epic | Backlog | E-520952 | E-520952 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-30 | 2026-01-21
Local Enhancement Epic: Request for Cons Maintenance | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106651 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Removal of COD from FXF BOL for US-CA | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Local Enhancement (ACCS) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106659 | 90765 | VN Direct Serve (Bloom) | Biz w/ Tech Epic | Assessment & Analysis | E-550850 | E-550850 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-15
Biz w/ Tech Epic: Epic 1 - Analysis in preparation for CH Regulatory | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106664 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: ZA ACCS Enhancements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106683 |  |  | Local Enhancement Epic | Backlog | E-501195 | E-501195 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Italy: Product enablement in Mainframe BDC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106700 |  |  | Local Enhancement Epic | Backlog | E-521039 | E-521039 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: AU Dom - Linux upgrade for Websphere and Trans-IT | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106701 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-563840 | E-563840 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Execute Sort Epic | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106739 | 6782 | WS1 - [1C - Project Zenith ] Execute Sort with Cur | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Remove uDS Orange status posting | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106747 |  |  | Local Enhancement Epic | Backlog | E-526456 | E-526456 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: Improve DH2 to avoid re-use (unclosed trailer)CONS | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106748 |  |  | Local Enhancement Epic | Backlog | E-518448 | E-518448 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-Argentina D&T eInvoicing Regulatory Chngs Ph1 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106749 |  |  | Local Enhancement Epic | Assessment & Analysis | E-499743 | E-499743 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Suppression of Delivery Locations in LEO for Chile | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106750 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC BR 3 SISTRIN_Business Rule Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106751 |  |  | Local Enhancement Epic | Backlog | E-523132 | E-523132 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Additional Duty and Tax Module for WTEditor | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106752 |  |  | Local Enhancement Epic | Backlog | E-522384 | E-522384 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-07
Local Enhancement Epic: AutoSlip App on WT6300 (semi integrated w) DH2 App | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106753 |  |  | Local Enhancement Epic | Backlog | E-518462 | E-518462 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: TNT Billing in ACCS (EAI 3535285) - CD Retirment | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106754 |  |  | Lifecycle Management Epic | Backlog | E-522387 | E-522387 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 SCO TN EPART IRG Operation Efficiency | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106766 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-516829 | E-516829 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LSRE2 to consume all physical scans (rawscan, cwc) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106767 |  |  | Local Enhancement Epic | Assessment & Analysis | E-518465 | E-518465 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Extend (Trailer) CONS in Maintce UI from 72 to 96h | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106768 |  |  | Local Enhancement Epic | Assessment & Analysis | E-518470 | E-518470 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GFA - SPVP integration to GVMax "sandbox" POC | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106770 |  |  | Local Enhancement Epic | Backlog | E-508064 | E-508064 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Data Enhancement Request for VISA Contract Events | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106771 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Incorrect ROD Flag on BON RLS Shipments – AS400 TN | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106782 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548509 | E-548509 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SSP Enablement for Surface Linehaul Execution | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106823 | 9058 | SSP Enablement for Surface LH Execution | Biz w/ Tech Epic | Build | E-366042 | E-366042 | 5: XL | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No | 2024-02-19 | 2026-03-27 | 2025-07-02
Biz w/ Tech Epic: FXG-LHE-Trip Dispatch & Arrival Business Rules | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106826 | 7205 | Enabler - Foundation for LH Systems Modernization | Biz w/ Tech Epic | Build | E-277024 | E-277024 | 5: XL | 2025-07-02 |  | 100% | 4 | 4 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: ID ACCS Import - Activity Log in ACCS System | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106840 |  |  | Local Enhancement Epic | Backlog | E-521022 | E-521022 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ID ACCS Import : ACCS Integration with RDA system | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106841 |  |  | Local Enhancement Epic | Done | E-483311 | E-483311 | 2: S | 2025-07-01 | 2025-07-01 |  | 0 | 0 |  | 0 | No |  |  | 2025-07-01 | 2025-07-01
Lifecycle Management Epic: CIL Transition to New WMS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106843 |  |  | Lifecycle Management Epic | Backlog | E-521013 | E-521013 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-10-31 | 2028-05-30
Local Enhancement Epic: CONS TAG Sort Rule Visibility | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106844 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: EPIC 1 - Export & Transit no-regrets | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106861 | 85946 | CH Regulatory Changes & Vendor Replacement | Biz w/ Tech Epic | Assessment & Analysis | E-430916 | E-430916 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-10-03 | 2028-05-11
Biz w/ Tech Epic: EPIC 2 - Export & Transit | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106862 | 85946 | CH Regulatory Changes & Vendor Replacement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-09 | 2025-11-20
Local Enhancement Epic: **** Will be cancelled once validated *** | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106878 |  |  | Local Enhancement Epic | Backlog | E-530689 | E-530689 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: DevSecOps initiatives for Ops excellence & support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106883 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-375061 | E-375061 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-05-28 | 2026-03-18 | 2025-06-26
Lifecycle Management Epic: AV Server Enhancement for Common Devices CT47/RP4 | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106885 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: AV Server Enhancement for Common Devices CT47/RP4 | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106886 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Build Data product 1 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106901 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Test | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106902 | 109637 | TS-VL1-CM-Ship Visibility-Consume | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: test | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106907 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG - Enable Services for Customer C6 Bank | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106912 |  |  | Local Enhancement Epic | Backlog | E-521904 | E-521904 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - Philips Healthcare Bus Opp IT portal | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106914 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR- Brazil Tax Reform - NT | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106936 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CCP Bulk User Access Capability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106941 |  |  | Local Enhancement Epic | Backlog | E-507568 | E-507568 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: New PL Prefix codes | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106954 |  |  | Local Enhancement Epic | Backlog | E-537157 | E-537157 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Team Driver Validation for Mobile Trip Application | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106970 |  |  | Local Enhancement Epic | Backlog | E-285101 | E-285101 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2026-01-20
Local Enhancement Epic: Aviation Security Compliance in uDS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106972 |  |  | Local Enhancement Epic | Backlog | E-531090 | E-531090 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GOL FEEDS UNSTACKING GTD/TNT DATABASE | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106973 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Trailer Pull Off Reduction for Mobile Trip Applica | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106974 |  |  | Local Enhancement Epic | Backlog | E-521016 | E-521016 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-2B: Support CSR L3CL Test Bed | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106975 |  |  | Lifecycle Management Epic | Backlog | E-461753 | E-461753 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Trusted Shipper Application Transition | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106976 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-3B: Support CSR L3CL Test Bed | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106977 |  |  | Lifecycle Management Epic | Backlog | E-508012 | E-508012 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-4B: Support CSR L3CL Test Bed | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106978 |  |  | Lifecycle Management Epic | Backlog | E-525812 | E-525812 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-5B: Support CSR L3CL Test Bed | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106982 |  |  | Lifecycle Management Epic | Backlog | E-531536 | E-531536 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2026-01-27
Lifecycle Management Epic: SCO.TN.ELRS CY26 PI-1B: Support CSR L3CL Test Bed | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106983 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-543614 | E-543614 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-28 | 2026-04-07
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-2B: Protect Purple-Secure Bus | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106984 |  |  | Lifecycle Management Epic | Backlog | E-458586 | E-458586 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-3B: Protect Purple-Secure Bus | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106985 |  |  | Lifecycle Management Epic | Backlog | E-508006 | E-508006 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-4B: Protect Purple-Secure Bus | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106986 |  |  | Lifecycle Management Epic | Backlog | E-528355 | E-528355 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS Nov'25 to Dec'26: Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106987 |  |  | Lifecycle Management Epic | Build | E-531911 | E-531911 | 2: S | 2025-11-11 |  | 49.48% | 388 | 192 |  | 196 | No | 2025-11-05 | 2026-01-27 | 2025-11-11
Lifecycle Management Epic: SCO.TN.ELRS CY26 PI-1B: Protect Purple-Secure Bus | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0106988 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UAE ACCS Changes & Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107001 |  |  | Local Enhancement Epic | Backlog | E-436148 | E-436148 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-05-26
Local Enhancement Epic: CN gateway IB/OB manifest declaration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107035 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USD Reporting Upgrade to Include Feeder & Outbound | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107036 |  |  | Local Enhancement Epic | Backlog | E-531065 | E-531065 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-08 | 2026-03-19
Local Enhancement Epic: USI INDH Clearance Package Processing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107037 |  |  | Local Enhancement Epic | Backlog | E-531066 | E-531066 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-08 | 2025-10-31
Local Enhancement Epic: ILS Base/Delta File Timeout Resolution on USDB | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107039 |  |  | Local Enhancement Epic | Backlog | E-531068 | E-531068 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2026-01-06
Local Enhancement Epic: FACS INDH Report Modifications & Bug Resolutions | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107042 |  |  | Local Enhancement Epic | Backlog | E-531072 | E-531072 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-08 | 2026-02-27
Local Enhancement Epic: USD - IND First Class Mail Table Editor | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107045 |  |  | Local Enhancement Epic | Backlog | E-531067 | E-531067 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-26 | 2026-03-19
Local Enhancement Epic: USD - Manual File Transfer Failures Resolution | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107046 |  |  | Local Enhancement Epic | Backlog | E-531071 | E-531071 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-26 | 2026-03-19
Local Enhancement Epic: USD - YTZ Save and Sync Process Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107047 |  |  | Local Enhancement Epic | Backlog | E-531070 | E-531070 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-31 | 2026-01-22
Local Enhancement Epic: USD - ILS Automated Count Start/Stop Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107048 |  |  | Local Enhancement Epic | Backlog | E-531069 | E-531069 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-26 | 2026-03-19
Local Enhancement Epic: USD - INDH Truck Table Editor Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107050 |  |  | Local Enhancement Epic | Backlog | E-531092 | E-531092 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-01 | 2026-03-19
Local Enhancement Epic: SSAMI Image roles revamp | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107053 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: E- Invoicing - Poland | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107056 |  |  | Local Enhancement Epic | Assessment & Analysis | E-504073 | E-504073 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-03-19 | 2026-03-31
Local Enhancement Epic: Elimination of Large Package Flow Plan | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107067 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-3-JDA-MXSC-YOUNG LIVING CUSTOMER ONBOARDING | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107069 |  |  | Local Enhancement Epic | Backlog | E-522390 | E-522390 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW Reg Export EDI new flag made in TW by 07May2025 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107076 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW Export Regulation changed for US Tariff | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107084 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ICS2 EU Admissibility (Pre Arrival) - Release 3 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107089 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ICS2 EU Admissibility (Pre Arrival) - Release 3 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107090 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ICS2 EU Admissibility (Pre Arrival) - Release 3 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107091 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FR Domestic Rollout of CT47 & WT63 scanners | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107130 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2026-10-01
Local Enhancement Epic: US-MCIS Maximo -MIX ELOG | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107132 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Remediate Microsoft ACS Vulnerability | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107133 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: 1. Formulate Solver Input | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105460 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-02-04 | 2026-01-20
Local Enhancement Epic: Indirect Signature Release in CA with Guest Auth | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107157 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538325 | E-538325 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ad Hoc Re-Rate Request from APAC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107160 |  |  | Local Enhancement Epic | Backlog | E-521015 | E-521015 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Archiving TradeTools RPS Batch Screening Tables | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107161 |  |  | Lifecycle Management Epic | Backlog | E-522389 | E-522389 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Modernize ProMiles Pricing Schedules | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107170 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MAS for FXF FM integration w/ user admin sys/ tool | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107175 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IT/MXP Air -Gtw HS enhancement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107180 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Domicile from Maximo needs to be sent to Motive. | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107181 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Preventive maintenance update in FXF Maximo | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107182 |  |  | Local Enhancement Epic | Backlog | E-511621 | E-511621 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: FXF Maximo inventory update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107183 |  |  | Local Enhancement Epic | Backlog | E-526314 | E-526314 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: Enable feed from Maximo to Oracle | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107184 |  |  | Local Enhancement Epic | Launch & Evaluate | E-511602 | E-511602 | 2: S | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2025-08-12 | 2025-06-26
Local Enhancement Epic: Invoice and purchase contract update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107185 |  |  | Local Enhancement Epic | Launch & Evaluate | E-511616 | E-511616 | 1: XS | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2025-10-21 | 2025-06-26
Local Enhancement Epic: Enhance asset info in FXF Maximo | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107186 |  |  | Local Enhancement Epic | Backlog | E-534984 | E-534984 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: US-MCIS Maximo MIX Shift Bid to Maximo | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107187 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: US-MCIS Maximo - MIX Incident Log | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107188 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LFXE Safety Apps Transition | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107189 |  |  | Lifecycle Management Epic | Backlog | E-501698 | E-501698 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2026-03-24
Local Enhancement Epic: GV Surface GV Max Application Fields Automation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107190 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GV MAX Mobile App Launch | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107191 |  |  | Local Enhancement Epic | Backlog | E-523554 | E-523554 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-06-11 | 2026-08-19
Local Enhancement Epic: Migrate LFXE PowerBI Fuel Dashboard | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107224 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: School Specialty EDI Billing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107241 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Japan 7th NACCS - Customs EDI renewal project | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107243 |  |  | Local Enhancement Epic | Assessment & Analysis | E-458313 | E-458313 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: CRS (Compliance Reporting System) Intl update rqd | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107245 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-3S-eInvoicingPortal New System (DANFE 55) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107246 |  |  | Local Enhancement Epic | Backlog | E-521023 | E-521023 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ISDC MDE Replacement for VISA MDE in EU Countries | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107247 |  |  | Local Enhancement Epic | Backlog | E-518731 | E-518731 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC App Compliance InfoSec Programs Mgmt | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107248 |  |  | Lifecycle Management Epic | Backlog | E-507666 | E-507666 | 2: S |  |  |  | 2 | 0 |  | 2 | No
Lifecycle Management Epic: App Retirment - ScanPad in ZA | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107249 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Customer Tracking API | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107250 |  |  | Local Enhancement Epic | Backlog | E-504322 | E-504322 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_CX ART_KTLO_MyGTD, DocuSign, Salesforce | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107275 |  |  | Lifecycle Management Epic | Build | E-503685 | E-503685 | 1: XS | 2025-07-22 |  | 62.5% | 8 | 5 | 1 | 2 | No | 2025-06-03 | 2026-06-02 | 2025-07-22
Lifecycle Management Epic: FY26_PI3_TBS ART_KTLO_eTrans,CW,BT,Unit4,Galaxy | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107276 |  |  | Lifecycle Management Epic | Backlog | E-503683 | E-503683 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Lifecycle Management Epic: SCO.TN.ELRS Aug'25-Dec'26 Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107277 |  |  | Lifecycle Management Epic | Build | E-527203 | E-527203 | 3: M | 2025-09-23 |  | 73.83% | 1918 | 1416 |  | 502 | No | 2025-11-19 | 2026-01-27 | 2025-09-23
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-3B: Prod Integration & Support | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107278 |  |  | Lifecycle Management Epic | Backlog | E-479841 | E-479841 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-2B: Prod Integration & Support | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107279 |  |  | Lifecycle Management Epic | Backlog | E-458555 | E-458555 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USD - Daytest Value (DTV) Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107280 |  |  | Local Enhancement Epic | Backlog | E-531061 | E-531061 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-06 | 2026-06-01
Local Enhancement Epic: [UDS – CANH] – SCO Portfolio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107283 |  |  | Local Enhancement Epic | Build | E-521036 | E-521036 | 2: S | 2026-01-07 |  |  | 33 | 0 | 21 | 12 | No | 2025-09-01 | 2026-10-12 | 2026-01-07
Biz w/ Tech Epic: API's for CVM | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107342 | 9243 | Banded Commit for Competitive Profitable Network | Biz w/ Tech Epic | Backlog | E-512823 | E-512823 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-27
Local Enhancement Epic: [UDS – CANIP] – SCO Portfolio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107348 |  |  | Local Enhancement Epic | Build | E-481853 | E-481853 | 2: S | 2025-10-30 |  |  | 14 | 0 | 4 | 10 | No | 2025-03-26 | 2026-01-13 | 2025-10-30
Biz w/ Tech Epic: Dock Data Modernization Epic 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105576 | 7145 | [Enabler] Dock Data Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-457408 | E-457408 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-11-01 | 2028-09-12
Local Enhancement Epic: US-MCIS Maximo Operational System Updates | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107353 |  |  | Local Enhancement Epic | Backlog | E-521723 | E-521723 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2027-01-20
Local Enhancement Epic: P&D Portal Integration with ESS | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107354 |  |  | Local Enhancement Epic | Backlog | E-521557 | E-521557 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Negotiations Dashboard | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107355 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: School Specialty EDI Billing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107356 |  |  | Local Enhancement Epic | Backlog | E-503866 | E-503866 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: RO eTransport - Data to FTP | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107390 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: RO eTransport - Data to FTP | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107392 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: China Ecommerce clearance system | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107394 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Shipment Visibility Increment 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107399 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Camera Tunnel & RFID Integration (Air & Surface) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107417 | 7285 | RFID - Package Loss and Recovery | Local Enhancement Epic | Backlog | E-532991 | E-532991 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-08 | 2026-08-19
Local Enhancement Epic: TNT Shipment Service Development | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107419 |  |  | Local Enhancement Epic | Backlog | E-525813 | E-525813 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2026-05-26
Local Enhancement Epic: spDM: Decouple Front End & Back End | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107422 |  |  | Local Enhancement Epic | Backlog | E-531063 | E-531063 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: iRoad backend access for SSO | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107423 |  |  | Local Enhancement Epic | Launch & Evaluate | E-523789 | E-523789 | 2: S | 2025-07-17 |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2025-11-11 | 2025-07-17
Local Enhancement Epic: Economy Label First API | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107424 |  |  | Local Enhancement Epic | Assessment & Analysis | E-512542 | E-512542 | 2: S |  |  |  | 0 | 0 |  | 0 | Yes
Lifecycle Management Epic: WESS Modernization and Architecture Refactoring | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107426 |  |  | Lifecycle Management Epic | Backlog | E-531054 | E-531054 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2026-05-29 | 2027-12-31
Local Enhancement Epic: ADLS Gen2 Storage Account for US Cage Inventory | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107428 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ADLS Gen2 Storage Account for US Cage Inventory | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107429 |  |  | Local Enhancement Epic | Backlog | E-521805 | E-521805 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IN ACCS Enhancements- Regulatory Requirements & Op | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107430 |  |  | Local Enhancement Epic | Backlog | E-504193 | E-504193 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-29 | 2026-05-26
Biz w/ Tech Epic: DataFlow to Sort Epic | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107477 | 97130 | Dataflow to Sort | Biz w/ Tech Epic | Build | E-545172 | E-545172 | 4: L | 2025-11-20 |  |  | 4 | 0 | 1 | 3 | No | 2025-05-30 | 2026-09-28 | 2025-11-20
Biz w/ Tech Epic: AU - SPS Hubs API Local Courier | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107532 | 89969 | AU - SpS Hubs API Local Courier | Biz w/ Tech Epic | Assessment & Analysis | E-567727 | E-567727 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107542 | 106669 | Project SEAL | Biz w/ Tech Epic | Backlog | E-513028 | E-513028 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2025-10-22
Local Enhancement Epic: FLM AMS Phase 2 - Neighbour testing with ITIH | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107548 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC_BR_DOM_CE_Automation tools improvements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107549 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: 2025 OpsSol - FedEx ID Expansion | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107577 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: 2025 OpsSol - Production Support (Work Request) | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107578 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: 2025 Ops Sol Lifecycle Management - Compliance | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107579 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: 2025 Ops Solutions LifeCycle Management - Hardware | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107580 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Re-rating Actuals - APAC Emergency Request 2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107581 |  |  | Local Enhancement Epic | Backlog | E-521014 | E-521014 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: eYMS Yard Central - Sort by Multiple Columns | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107582 |  |  | Local Enhancement Epic | Backlog | E-518601 | E-518601 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LFXG Business Operations Dashboard | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107583 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Migration Planning for LFXE Fuel Islands | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107584 |  |  | Lifecycle Management Epic | Backlog | E-508834 | E-508834 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2026-06-10
Local Enhancement Epic: Implement Automated Fuel Pricing Schedule | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107586 |  |  | Local Enhancement Epic | Backlog | E-508830 | E-508830 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2026-06-10
Local Enhancement Epic: Include LMS system Create and update date in IBIS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107587 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PH-483781-Manifest transmission thru INS & KONEK | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107588 |  |  | Local Enhancement Epic | Backlog | E-370230 | E-370230 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: US-MCIS Maximo Master Overtime Application | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107590 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-IBIS - BR Rlog & BR-Rlog-Cielo Create Views | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107591 |  |  | Local Enhancement Epic | Backlog | E-446252 | E-446252 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-09 | 2025-09-02
Biz w/ Tech Epic: GPDE-FIE | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107617 | 7406 | Global P&D Ecosystem Enabler | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-11-03 | 2026-02-27
Biz w/ Tech Epic: GPDE-FIE | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107618 | 108807 | One FedEx Global Facility Identification Expansion | Biz w/ Tech Epic | Build | E-550459 | E-550459 | 4: L | 2026-01-06 |  |  | 1 | 0 | 1 | 0 | No | 2025-11-03 | 2026-07-03 | 2026-01-06
Local Enhancement Epic: Change I-clear manifest file | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107627 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Deployment of HS 11.3.2 to CDG,CGN,MXP,CUA,CPH,CUA | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107628 |  |  | Lifecycle Management Epic | Backlog | E-518449 | E-518449 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-02-21
Local Enhancement Epic: Settlement SP Escalation Dashboard | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107629 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550228 | E-550228 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-02-23 | 2026-04-01
Local Enhancement Epic: FXL Applications to move to PAAS Model from IAAS | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107631 |  |  | Local Enhancement Epic | Launch & Evaluate | E-517562 | E-517562 | 2: S | 2025-07-21 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-21
Local Enhancement Epic: Update Verbiage on POF Cause Codes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107632 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580819 | E-580819 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG Integration to Customer Stone | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107633 |  |  | Local Enhancement Epic | Backlog | E-521902 | E-521902 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ALL-SORT- Production and Maintenance Support CY25 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107647 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG- New Integration with Adyen | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107650 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: US-MCIS MAX Refactoring Overtime Process Scripts | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 023 Cargo UCC compliance ICS/PNTS/ETD | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107659 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Re-activate GITR in Countries that moved to Vendor | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107660 |  |  | Local Enhancement Epic | Assessment & Analysis | E-499448 | E-499448 | 3: M |  |  |  | 0 | 0 |  | 0 | Yes | 2024-07-22 | 2027-08-11
Local Enhancement Epic: PH ACCS Imp - STAT14 Scan Client New Dropdown | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107661 |  |  | Local Enhancement Epic | Assessment & Analysis | E-404858 | E-404858 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PH ACCS Exp - Mass Notes | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107662 |  |  | Local Enhancement Epic | Assessment & Analysis | E-404847 | E-404847 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CONFIG CHANGE - set up new sorter configuration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107663 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_SS ART_KTLO_CW,BT,Unit4,DB, FXL Portal | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107666 |  |  | Lifecycle Management Epic | Backlog | E-521017 | E-521017 | 5: XL | 2025-07-08 |  |  | 0 | 0 |  | 0 | No | 2025-08-06 | 2026-05-29 | 2025-07-08
Local Enhancement Epic: Add PRA Fitments for the 777 Fleet | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107668 |  |  | Local Enhancement Epic | Backlog | E-524220 | E-524220 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 737-800 New Config Envelope Update | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107669 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DCM - Micro-Forecasting by Pegasus | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107670 |  |  | Local Enhancement Epic | Assessment & Analysis | E-537935 | E-537935 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL – ‘GE Healthcare’ EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107671 |  |  | Local Enhancement Epic | Assessment & Analysis | E-516217 | E-516217 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2026-01-13
Local Enhancement Epic: Shipment Replay Part 1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107673 |  |  | Local Enhancement Epic | Build | E-521558 | E-521558 | 3: M | 2025-11-17 |  | 50% | 4 | 2 | 2 | 0 | No | 2024-07-22 | 2026-03-31 | 2025-11-17
Local Enhancement Epic: Shipment Systems - Business Continuity & Infrastr. | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107674 |  |  | Local Enhancement Epic | Assessment & Analysis | E-512143 | E-512143 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Performance test for GSS Application | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107678 |  |  | Lifecycle Management Epic | Backlog | E-518469 | E-518469 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USD - Replay Sorts for Revenue | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107679 |  |  | Local Enhancement Epic | Backlog | E-531053 | E-531053 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-26 | 2026-03-19
Local Enhancement Epic: LAC Charge Code Activation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107680 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CGN HUBSTACK - adjust "B2C_DE"-instruction | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107681 |  |  | Local Enhancement Epic | Backlog | E-531031 | E-531031 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CGN HUBSTACK - modify GSS "Sort Assist"-label | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107682 |  |  | Local Enhancement Epic | Backlog | E-531032 | E-531032 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EIW to Atlas: Project Shift: EIW Data Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107683 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CGN HUBSTACK - SABRE to consume RR-event data | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107684 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552905 | E-552905 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-SC-WMS Implementation phase 3 Omron | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107685 |  |  | Local Enhancement Epic | Backlog | E-521907 | E-521907 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG- New Integration with Adyen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107686 |  |  | Local Enhancement Epic | Backlog | E-521903 | E-521903 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Transport Cost Inaccuracies | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107691 | 97525 | Transport Cost Inaccuracies [ECTS] | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Limit labor and parts for a specific group | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107704 |  |  | Local Enhancement Epic | Backlog | E-535045 | E-535045 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: US-MCIS-MAX CY25 PI05 Interface w/ FCF Inventory | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107716 |  |  | Local Enhancement Epic | Backlog | E-521024 | E-521024 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-10
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-2B: KT New Accenture Resources | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107735 |  |  | Lifecycle Management Epic | Backlog | E-460386 | E-460386 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO.TN.ELRS CY25 PI-3B: KT New Accenture Resources | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107746 |  |  | Lifecycle Management Epic | Backlog | E-512828 | E-512828 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ireland - Genius - Import - Invoice number | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107747 |  |  | Local Enhancement Epic | Build | E-533583 | E-533583 | 1: XS | 2026-04-13 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-11-11 | 2026-04-13
Local Enhancement Epic: ACCS-SZX IB and OB declare to non-trade system | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107749 |  |  | Local Enhancement Epic | Backlog | E-534721 | E-534721 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: eYMS System Performance Improvement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107753 |  |  | Local Enhancement Epic | Backlog | E-518969 | E-518969 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-16 | 2025-10-29
Local Enhancement Epic: eYMS Yard Central UI & Usability Enhancements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107754 |  |  | Local Enhancement Epic | Backlog | E-521037 | E-521037 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC BR Customs New Program [Remessa Conforme] | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107759 |  |  | Local Enhancement Epic | Backlog | E-533562 | E-533562 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Add scans to a LOC In Grisis | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107760 |  |  | Local Enhancement Epic | Backlog | E-521032 | E-521032 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Chute Scanning in the ERN - LE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107786 |  |  | Local Enhancement Epic | Backlog | E-517060 | E-517060 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-06-11 | 2025-10-14
Local Enhancement Epic: FXL - Waters Corporation EDI/API Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107793 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - Waters Corporation EDI Integration | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107794 |  |  | Local Enhancement Epic | Backlog | E-513990 | E-513990 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-IBIS - Add BR-TNT-LMS Create and Update Date | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107811 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL – Microsoft/TMC EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107815 |  |  | Local Enhancement Epic | Backlog | E-527430 | E-527430 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-03-24
Local Enhancement Epic: Ireland - Genius - Export - Postcode mandatory | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107820 |  |  | Local Enhancement Epic | Build | E-533569 | E-533569 | 1: XS | 2025-11-12 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-11-12
Local Enhancement Epic: FedEx Location Shipment Automation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107826 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_LHE_TRIP Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107829 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-473623 | E-473623 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL Account Integration Data Quality Improvements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107834 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Linehaul Execution (LHE) Lifecycle Management FY25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107835 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-474302 | E-474302 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-12 | 2026-04-28
Lifecycle Management Epic: Linehaul Execution (LHE) - TRIP Vcom System Modern | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107836 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-150149 | E-150149 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LACBR LMS Customer Dell Financial EDI Correction | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107837 |  |  | Local Enhancement Epic | Backlog | E-523130 | E-523130 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ABACUS Dashboard changes | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105451 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-449334 In-Station Consolidated Quality Assurance | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106129 | 9494 | In-Station Consolidated Quality Assurance VB1 | Biz w/ Tech Epic | Build | E-449334 | E-449334 | 3: M | 2025-07-09 |  | 100% | 1 | 1 |  | 0 | No | 2024-07-22 | 2025-10-29 | 2025-07-09
Biz w/ Tech Epic: Manifest Recharge Information Epic 1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106845 | 7847 | Manifest Recharged Information (MRI) | Biz w/ Tech Epic | Backlog | E-528415 | E-528415 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-30 | 2026-02-26
Biz w/ Tech Epic: Manifest Recharge Information Epic 2 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106896 | 7847 | Manifest Recharged Information (MRI) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-05 | 2026-05-29
Local Enhancement Epic: ETD-TIGERS Adoption Report Enhancements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107141 |  |  | Local Enhancement Epic | Assessment & Analysis | E-174553 | E-174553 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: Shinobi - GEMINI Analytics | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107142 |  |  | Local Enhancement Epic | Assessment & Analysis | E-308849 | E-308849 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Shinobi - Clearance Reporting: Web Reports CY 2025 | In Progress | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107150 |  |  | Local Enhancement Epic | Assessment & Analysis | E-454520 | E-454520 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Shinobi - Report migration to PowerBI | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107177 |  |  | Local Enhancement Epic | Assessment & Analysis | E-388556 | E-388556 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Shinobi - Clearance Reporting: Dashboards CY 2025 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107178 |  |  | Local Enhancement Epic | Assessment & Analysis | E-454521 | E-454521 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107300 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dock Device Refresh | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107620 | 9540 | [Enabler] Dock/QA/Garage Replacement Device | Biz w/ Tech Epic | Assessment & Analysis | E-444718 | E-444718 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-06-02
Local Enhancement Epic: CARM Fee - CBS & Classify | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107635 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: ELMO - NFR DevSecOps Activities | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107639 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Network Definition (NDS), Agility # E-416690 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103372 | 6775 | WS1 - [1C - Project Zenith ] Network Definition | Biz w/ Tech Epic | Build | E-416690 | E-416690 | 4: L | 2025-07-02 |  |  | 8 | 0 | 5 | 3 | No | 2025-03-20 | 2026-04-01 | 2025-07-02
Biz w/ Tech Epic: Wearable 3.5 Modernization | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103498 | 8118 | Wearable 3.5 Sortation Applications Modernization | Biz w/ Tech Epic | Assessment & Analysis | E-447297 | E-447297 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Outbound | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103737 | 7584 | AS/RS in MEMH East Cage #7584 | Biz w/ Tech Epic | Backlog | E-513591 | E-513591 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2025-08-06
Biz w/ Tech Epic: Inbound | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103739 | 7584 | AS/RS in MEMH East Cage #7584 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: GCSS POD | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104136 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Regulatory Proactive Notification | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104223 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Global Clearance Intercept to Downstream Scanning | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104880 | 7822 | BSO Intercept | Biz w/ Tech Epic | Build | E-62116 | E-62116 | 2: S | 2025-07-01 |  | 71.43% | 7 | 5 | 2 | 0 | No | 2025-02-28 | 2026-10-28 | 2025-07-01
Biz w/ Tech Epic: EEI Automation | Completed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106981 | 93676 | Automate EEI Filing | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Manage Shipment Handling Unit Flow Plan | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103606 | 9325 | Manage Shipment Handling Unit Flow Plan | Biz w/ Tech Epic | Assessment & Analysis | E-335468 | E-335468 | 2: S |  |  | 60% | 10 | 6 |  | 4 | No
Lifecycle Management Epic: Improve Automation, code coverage and CICD | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107880 |  |  | Lifecycle Management Epic | Backlog | E-518472 | E-518472 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: Grace - Alignment of ID types with Fasah | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107881 |  |  | Local Enhancement Epic | Backlog | E-521025 | E-521025 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Labor planning tool - APAC | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107882 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LHE ART; LHRA URR Updates | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107883 |  |  | Local Enhancement Epic | Backlog | E-521071 | E-521071 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Lonza - New Customer SG for SPOTS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107886 |  |  | Local Enhancement Epic | Backlog | E-521057 | E-521057 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_TBS ART_App Server upgrade, patching | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107888 |  |  | Lifecycle Management Epic | Backlog | E-516404 | E-516404 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-05-28 | 2025-08-05
Local Enhancement Epic: GV Surface GVMAX - Asset Transfer | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107893 |  |  | Local Enhancement Epic | Backlog | E-521058 | E-521058 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-06-10
Local Enhancement Epic: GV Surface GVMAX - Asset Transfer | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107894 |  |  | Local Enhancement Epic | Backlog | E-521059 | E-521059 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GVMAX - Required Fields | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107895 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GVMAX - Rental Locations | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107896 |  |  | Local Enhancement Epic | Backlog | E-521060 | E-521060 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GVMAX - User access review | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107897 |  |  | Local Enhancement Epic | Backlog | E-521061 | E-521061 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GVMAX - Review GL codes | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107899 |  |  | Local Enhancement Epic | Backlog | E-521062 | E-521062 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: GV Surface GVMAX - Version Upgrade | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0107900 |  |  | Lifecycle Management Epic | Backlog | E-521063 | E-521063 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2027-01-20
Local Enhancement Epic: GV Surface GVMAX - Asset Health | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107901 |  |  | Local Enhancement Epic | Backlog | E-521055 | E-521055 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2027-01-20
Local Enhancement Epic: GV Surface GVMAX - Estimate data entry | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107903 |  |  | Local Enhancement Epic | Backlog | E-521064 | E-521064 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GVMAX - Asset Template values | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107904 |  |  | Local Enhancement Epic | Backlog | E-521065 | E-521065 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GVMAX - Accident charges | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0107905 |  |  | Local Enhancement Epic | Backlog | E-521066 | E-521066 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Biz w/ Tech Epic: E-512376 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107947 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic #1 (LH Savings) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0106255 | 9343 | PL domestic LH PFS set up review | Biz w/ Tech Epic | Assessment & Analysis | E-425952 | E-425952 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-04-01 | 2025-11-07
Local Enhancement Epic: SHEIN API Setup | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108015 |  |  | Local Enhancement Epic | Assessment & Analysis | E-513983 | E-513983 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-01-13
Local Enhancement Epic: Monitoring & Intervention with HC ID and CT-US | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108042 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: More Granular intercept sort | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108067 | 8096 | WS1 - [1A] 82583 More granularity for intercepts | Biz w/ Tech Epic | Assessment & Analysis | E-422685 | E-422685 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SCO - SORT UNITIZE C STATUS ON BARCODE - SCO work | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108070 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Multi-Wave Dispatch | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108112 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Smalls consolidation on customer dock | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108113 | 112944 | Roadmap Market Expansion Plan | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Full “Driver” capabilities for employee drivers | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108115 | 112948 | Enable "bring your own vehicles" for employees | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Smalls consolidation on preload sort | On Hold | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108116 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 SCO-CLR LETS-LAC ART Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108194 |  |  | Lifecycle Management Epic | Backlog | E-515406 | E-515406 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: FY26_PI3_LCM_CIL_Support activities of Activities | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108197 |  |  | Lifecycle Management Epic | Backlog | E-522716 | E-522716 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: FY26_ ANZ IT - AU Domestic Business Continuity | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108204 |  |  | Lifecycle Management Epic | Backlog | E-527111 | E-527111 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Failsafe label enhancement for Safe Hand Freight | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108205 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25_PI03_AFCS.ART_Lifecycle.Management | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108210 |  |  | Lifecycle Management Epic | Backlog | E-518170 | E-518170 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS-Issue Cte using Content Declaration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108213 |  |  | Local Enhancement Epic | Backlog | E-533572 | E-533572 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Routing code Faroe Islands in DK Genius | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108214 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Channel Islands ETD requirement (UVSDK) | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108215 | 7097 | Channel Islands Integration | Biz w/ Tech Epic | Assessment & Analysis | E-564928 | E-564928 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Channel Islands ETD requirement (TradeTools) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108216 | 7097 | Channel Islands Integration | Biz w/ Tech Epic | Build | E-564927 | E-564927 | 1: XS | 2026-02-18 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-02-18
Local Enhancement Epic: South Africa: Invoice details on Mufasa label | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108232 |  |  | Local Enhancement Epic | Backlog | E-525315 | E-525315 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC Panama CARGO-XML-IATA Implementation | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108237 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO_TN_EPART PROTECT PURPLE_CY25 | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108255 |  |  | Lifecycle Management Epic | Build | E-516574 | E-516574 | 2: S | 2025-09-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-09-10
Lifecycle Management Epic: FY26SCOTNEPARTIRGProdSupport (Duplicate-Delete) | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108257 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_SCO_TN_EPART_LCM_IRG_InfoSec Updates | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108258 |  |  | Lifecycle Management Epic | Backlog | E-516805 | E-516805 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USD Timeout Configuration for EWR and YYZ Location | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108274 |  |  | Local Enhancement Epic | Backlog | E-531064 | E-531064 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-08 | 2025-10-31
Local Enhancement Epic: USD & USI: Alternate Runout Contingency Modes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108276 |  |  | Local Enhancement Epic | Backlog | E-531073 | E-531073 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-08 | 2026-06-11
Local Enhancement Epic: New Zealand Import Entry Fee Change | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108280 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FedEx Supply Chain Health Care Portal Support FCL | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108283 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dynamo - OKTA Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108284 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Zealand Import Entry Fee Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108295 |  |  | Local Enhancement Epic | Backlog | E-519060 | E-519060 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: PurpleID Setup | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108293 | 84493 | WheelRight | Biz w/ Tech Epic | Assessment & Analysis | E-516409 | E-516409 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: Additional SSDC/Sabre KT PI-3 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108300 |  |  | Local Enhancement Epic | Backlog | E-528413 | E-528413 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: vMeasure - Dimensioning Solution | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108301 |  |  | Local Enhancement Epic | Backlog | E-521160 | E-521160 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-08-13
Lifecycle Management Epic: Production Support for Trade Tools for CY25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108303 |  |  | Lifecycle Management Epic | Backlog | E-521026 | E-521026 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Zealand High Value Write off Removal in ICR | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108305 |  |  | Local Enhancement Epic | Backlog | E-521056 | E-521056 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_LCM_CIL_Support activities of CIL systems | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108307 |  |  | Lifecycle Management Epic | Backlog | E-522612 | E-522612 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SSRT-Modernizing SSPConfigurationDownloads | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108308 |  |  | Lifecycle Management Epic | Backlog | E-521072 | E-521072 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-21
Lifecycle Management Epic: EAI 4990 -Routing rewrite in SortMaintenance app | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108309 |  |  | Lifecycle Management Epic | Backlog | E-518200 | E-518200 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-13 | 2025-08-21
Lifecycle Management Epic: Economy Sortation Platform (ESP) KT | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108310 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Decommission Oracle WebLogic instances used in NGS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108311 |  |  | Lifecycle Management Epic | Backlog | E-518210 | E-518210 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-21
Local Enhancement Epic: LAC-BR-TNT- LMS - Proactive Profitability Manageme | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108329 |  |  | Local Enhancement Epic | Backlog | E-522447 | E-522447 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Validate GD Handling with PUP/PUX Relabel | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108335 |  |  | Local Enhancement Epic | Backlog | E-516834 | E-516834 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: GV Surface FXG Maximo - Version Upgrade 9.x | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108336 |  |  | Lifecycle Management Epic | Backlog | E-521720 | E-521720 | 2: S | 2025-07-08 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-08
Lifecycle Management Epic: GV Surface FXF Maximo - Version Upgrade 9.x | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108337 |  |  | Lifecycle Management Epic | Backlog | E-521721 | E-521721 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-03-24
Lifecycle Management Epic: FY26_P&D_Run&Close_Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108339 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_P&D_Plan&Prepare_Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108340 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_P&D_Conveyance_Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108341 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PEKIP ACCS report template change | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108345 |  |  | Local Enhancement Epic | Done |  |  | 1: XS | 2025-07-14 | 2025-07-14 |  | 0 | 0 |  | 0 | No |  |  | 2025-07-14 | 2025-07-14
Lifecycle Management Epic: FY26_SCO_ClosingSort_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108348 |  |  | Lifecycle Management Epic | Backlog | E-526920 | E-526920 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: US FXL Accuracy Reporting | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108349 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: API Integration for iClear OB Cat-D | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108350 |  |  | Local Enhancement Epic | Build | E-521068 | E-521068 | 1: XS | 2025-12-03 |  | 100% | 1 | 1 |  | 0 | No | 2025-06-18 | 2025-08-18 | 2025-12-03
Local Enhancement Epic: BR-TNT-LMS-Issue pickup in batches LMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108354 |  |  | Local Enhancement Epic | Backlog | E-522448 | E-522448 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-11-03 | 2025-11-03
Local Enhancement Epic: ACARS Lives message Unassign | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108356 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TSA Security Seal Rollout | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108360 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Develop New 767 Configuration I | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108362 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USI: MEMH Replace Secondary 20/21 - P#100007018 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108363 |  |  | Local Enhancement Epic | Backlog | E-531062 | E-531062 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-30 | 2027-06-01
Local Enhancement Epic: FXL - Salesforce Enhancements - iSell and iServe | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108364 |  |  | Local Enhancement Epic | Backlog | E-528494 | E-528494 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-03-24
Local Enhancement Epic: LAC-BR-RLOG TRACKING OS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108365 |  |  | Local Enhancement Epic | Backlog | E-533575 | E-533575 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG MVP CLOVER | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108366 |  |  | Local Enhancement Epic | Backlog | E-524069 | E-524069 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automate Testing For EDP application | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108367 |  |  | Local Enhancement Epic | Backlog | E-522256 | E-522256 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2027-05-12
Biz w/ Tech Epic: UCC ETD - EDI + DE SUMA | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108387 | 163628 | UCC ETD - EDI + DE SUMA | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FAXS - Secured arrival process - Redesign | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108394 |  |  | Local Enhancement Epic | Backlog | E-535158 | E-535158 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY_26_PI3 Self-Serve Remediation of TEN-153953 | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108406 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_Sort Monitor Production Defect | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108409 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_eATLAS | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108410 |  |  | Lifecycle Management Epic | Backlog | E-526896 | E-526896 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_eATLAS | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108411 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 SCO Surface International Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108416 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 SCO Surface International Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108417 |  |  | Lifecycle Management Epic | Build | E-533576 | E-533576 | 2: S | 2025-09-22 |  | 60% | 5 | 3 |  | 2 | No | 2025-06-02 | 2026-05-29 | 2025-09-22
Lifecycle Management Epic: FY26 PI3 LCM Database & PCF Upgrades | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108418 |  |  | Lifecycle Management Epic | Backlog | E-513330 | E-513330 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_IA_People&PlanningART_Production Support | In Progress | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108424 |  |  | Lifecycle Management Epic | Backlog | E-515302 | E-515302 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2025-06-02 | 2027-05-28
Local Enhancement Epic: Lonza - New Customer SG for SPOTS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108428 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dynamo - HIS - Sort Down and LMC based on Dpt gate | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108432 |  |  | Local Enhancement Epic | Backlog | E-531094 | E-531094 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Lifecycle Management Epic: FY26_SCO_G1andPH_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108440 |  |  | Lifecycle Management Epic | Build | E-521027 | E-521027 | 3: M | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2025-06-02 | 2026-05-29 | 2025-07-02
Lifecycle Management Epic: [Cancelled] FY26_SCO_G1andPH_Production Supportxxx | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108441 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IN KYC Local Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108442 |  |  | Local Enhancement Epic | Backlog | E-519094 | E-519094 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-03-17
Local Enhancement Epic: FXL – Ollie's Bargain/ORCA EDI/API Integration | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108454 |  |  | Local Enhancement Epic | Backlog | E-532320 | E-532320 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_AU Domestic - DevSec Ops Reliability | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108472 |  |  | Lifecycle Management Epic | Backlog | E-537217 | E-537217 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-25 | 2026-12-31
Lifecycle Management Epic: FY26_AU Domestic - TM1 Upgrade and Maintenance | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108477 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-564552 | E-564552 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: FXL – URBN/APLL EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108481 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539446 | E-539446 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Local Enhancement Epic: Integration CargoWise One to Fedex Ship API | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108486 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563969 | E-563969 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: SCO_TN_EPART PRODUCTION SUPPORT_CY25 | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108487 |  |  | Lifecycle Management Epic | Backlog | E-517371 | E-517371 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_EPART_LCM_InfoSec updates | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108488 |  |  | Lifecycle Management Epic | Backlog | E-517250 | E-517250 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: NetGen_FY26_Platform_LCM_LEFS Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108489 |  |  | Lifecycle Management Epic | Backlog | E-519390 | E-519390 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-03-27 | 2025-10-30
Lifecycle Management Epic: NetGen_FY26_PI4_Platform_LCM_LEFS Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108491 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: NetGen_FY26_PI5_Platform_LCM_LEFS Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108492 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_Supply Chain Operations_NetGen_Prod Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108494 |  |  | Lifecycle Management Epic | Backlog | E-473531 | E-473531 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-08-15 | 2027-06-09
Local Enhancement Epic: Improvement opportunities for Sort Stack | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108528 |  |  | Local Enhancement Epic | Backlog | E-528616 | E-528616 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2024-10-30
Local Enhancement Epic: eOps Historical Performance Report HPR RML Updates | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108529 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_EU Sort_Production Support | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108539 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-518228 | E-518228 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Milkyway EDI CI Setup | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108592 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Beckman Coulter EDI CI and EDI 7501 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108593 |  |  | Local Enhancement Epic | Backlog | E-521031 | E-521031 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS: Mercado Libre API | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108604 |  |  | Local Enhancement Epic | Backlog | E-521028 | E-521028 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS: Customer Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108607 |  |  | Local Enhancement Epic | Backlog | E-521029 | E-521029 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL-Cummins ’ EDI/API Integration | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108610 |  |  | Local Enhancement Epic | Backlog | E-521067 | E-521067 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS: DELL INTEGRATION | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108611 |  |  | Local Enhancement Epic | Backlog | E-521030 | E-521030 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - Sony API integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108613 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557772 | E-557772 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 - EU Sort ART Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108614 |  |  | Lifecycle Management Epic | Build | E-526457 | E-526457 | 2: S | 2025-07-30 |  | 80% | 5 | 4 | 1 | 0 | No |  |  | 2025-07-30
Local Enhancement Epic: CDAS Termination Codes Update | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108623 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571633 | E-571633 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Protect Purple for Trade Tools for CY25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108624 |  |  | Lifecycle Management Epic | Backlog | E-522254 | E-522254 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-360808 - DRIVE # 7278 - Ergonomic Assessment Aut | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105549 | 7278 | Ergonomics Program/482072 | Biz w/ Tech Epic | Backlog | E-360808 | E-360808 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-13 | 2026-06-10
Biz w/ Tech Epic: PLR ISE | Assumed Completed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103855 | 6903 | Packing List Return Service PFS | Biz w/ Tech Epic | Assessment & Analysis | E-508457 | E-508457 | 3: M |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Fuel Price Accuracy Tool | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103444 | 6687 | Fuel Price Accuracy Tool | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: HOS (Hours of Service) Vendor - 58563 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103265 | 7249 | HOS (Hours of Service) Vendor | Biz w/ Tech Epic | Assessment & Analysis | E-471014 | E-471014 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-03-26 | 2026-08-19
Local Enhancement Epic: PFS - GFA GV Maximo Test Env and Data Merge 1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105676 |  |  | Local Enhancement Epic | Backlog | E-486255 | E-486255 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-05-21
Lifecycle Management Epic: FXF Telematics Tech Simplification & Vulnerability | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105886 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-512257 | E-512257 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-28 | 2025-10-21
Lifecycle Management Epic: Remediate Untrusted SSL Certificate for DFI | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0105933 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VAR System Improvements & Performance Reliability | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0105939 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2026-06-10
Local Enhancement Epic: Maximo Conversions - Incorrect Mapping to TMS | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106363 |  |  | Local Enhancement Epic | Done | E-503871 | E-503871 | 3: M | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: Capture Lytx HOS Data for Regulatory/Legal Hold | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0106531 |  |  | Local Enhancement Epic | Backlog | E-501993 | E-501993 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL – The Apparel Group (TAG) EDI/API Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108631 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 2 - AIOps Improve Incident Response | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108637 | 91543 | AIOps Intelligent Apps for Operational Excellence | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-08 | 2026-03-10
Lifecycle Management Epic: LAC Brazil Apps move to LAC Azure environment | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108639 |  |  | Lifecycle Management Epic | Backlog | E-522446 | E-522446 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DropNet Fee Payment Cost Center Change | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108658 |  |  | Local Enhancement Epic | Backlog | E-533714 | E-533714 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FSC Revenue Exclusions from EIW | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108664 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DropNet's Vendor Number Length Field | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108666 |  |  | Local Enhancement Epic | Backlog | E-530816 | E-530816 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-24 | 2025-10-07
Local Enhancement Epic: Return to Station driver capture on FORGE | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108679 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AirMax system local enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108681 |  |  | Local Enhancement Epic | Backlog | E-521076 | E-521076 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-05-05 | 2025-08-26
Lifecycle Management Epic: FY26_SCO_MEISA Clearance_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108687 |  |  | Lifecycle Management Epic | Backlog | E-523133 | E-523133 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Lifecycle Management Epic: GoalDiggers LCM Upgrade to CT47 Android Device | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108688 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_EPART Java & Weblogic Updates | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108689 |  |  | Lifecycle Management Epic | Backlog | E-528614 | E-528614 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: One Click Safety Net | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108690 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580824 | E-580824 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: NNP dataexchange deployment | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108693 | 9036 | WS10 – One Italy – NNP Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-553992 | E-553992 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-11-17 | 2026-05-29
Lifecycle Management Epic: FY 26 SCO Clr Reg and Reim Op Excellence | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108700 |  |  | Lifecycle Management Epic | Backlog | E-533567 | E-533567 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS-Integration w/Customer InterfaceAPI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108705 |  |  | Local Enhancement Epic | Backlog | E-522444 | E-522444 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UK Sameday - Migration from Universe | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108709 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: OCR for export broker | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108713 |  |  | Local Enhancement Epic | Build | E-519593 | E-519593 | 2: S | 2025-12-03 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-12-03
Local Enhancement Epic: LAC-BR-RLOG POS TRIAGE AUTOMATION | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108753 |  |  | Local Enhancement Epic | Backlog | E-523135 | E-523135 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: MQ API Configuration on 2 Universe Servers | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108754 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY 26 SCO Clr Reg and Reim Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108755 |  |  | Lifecycle Management Epic | Backlog | E-533573 | E-533573 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-CLEARANCE-APPS FEDEX-ID-8 DIGIT EXPANSION | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108756 |  |  | Local Enhancement Epic | Backlog | E-522445 | E-522445 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Export SG SUBCERT Improvements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108757 |  |  | Local Enhancement Epic | Backlog | E-520907 | E-520907 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FiT APAC - ID | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108758 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_Clearance Regulatory Production Sup. | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108759 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL – Philips EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108760 |  |  | Local Enhancement Epic | Backlog | E-531521 | E-531521 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-04 | 2025-11-05
Local Enhancement Epic: GV Surface - Asset Core Data Attributes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108761 |  |  | Local Enhancement Epic | Backlog | E-523266 | E-523266 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-08-11
Local Enhancement Epic: GV Surface - Data Audit | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108762 |  |  | Local Enhancement Epic | Backlog | E-523269 | E-523269 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-11-23
Lifecycle Management Epic: FY 26 SCO Clr Reg and Reim Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108763 |  |  | Lifecycle Management Epic | Backlog | E-533566 | E-533566 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-06-10 | 2027-05-11
Lifecycle Management Epic: FY26_SCO_RCC_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108764 |  |  | Lifecycle Management Epic | Backlog | E-521459 | E-521459 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-01-13
Lifecycle Management Epic: FY26_PI3_SCO Clearance Reimagine Protect Purple | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108765 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR: Print Management tool (new ) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108766 |  |  | Local Enhancement Epic | Backlog | E-525316 | E-525316 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_SCO Clearance Reimagine Op Excellence | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108767 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-3-EFISC: Migration from Efisc to Alcis | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108773 |  |  | Local Enhancement Epic | Backlog | E-523139 | E-523139 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT- LMS_Automation of Payment associate | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108783 |  |  | Local Enhancement Epic | Backlog | E-527729 | E-527729 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: US-MCIS Maximo Inventory Control (Move from OMEGA) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108787 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554524 | E-554524 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-10-29 | 2027-01-28
Local Enhancement Epic: StatPost w. correct SourceSyst. DeviceId and EmpId | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108790 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580821 | E-580821 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IB iClear Mobile Platform request for Cat B | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108793 |  |  | Local Enhancement Epic | Backlog | E-526745 | E-526745 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-03-03 | 2026-01-13
Local Enhancement Epic: *Cancelled* - DH2 Keyword Change | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108794 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: NSR messaging on 6005 FDMi Notification | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108802 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ELRS | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108843 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: IRoads Art SCO - P&D - Plan & Prepare | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108847 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Physical Handling Epic | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108720 | 6938 | GEMINI - Global Platform | Biz w/ Tech Epic | Build | E-485362 | E-485362 | 4: L | 2025-09-05 |  |  | 4 | 0 | 4 | 0 | No | 2025-01-01 | 2027-11-30 | 2025-09-05
Lifecycle Management Epic: Refactoring for 3537805 FXF Asset Inner Edge | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108879 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PEKIP ACCS report template change | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108880 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Refactoring for 3536762 FXF-EquipmentService | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108882 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PH-CR_IMP_ACCS - De Minimis Fees Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108883 |  |  | Local Enhancement Epic | Backlog | E-534717 | E-534717 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI-3 Infrastructure Patching Maintenance | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108885 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI-3 Infrastructure Patching Maintenance | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108889 |  |  | Lifecycle Management Epic | Done | E-522257 | E-522257 | 2: S | 2025-08-26 | 2025-08-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-26 | 2025-08-26
Biz w/ Tech Epic: Common Sort VB1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0103433 | 7216 | Common Sort - Value Bundle 1 | Biz w/ Tech Epic | Build | E-416375 | E-416375 | 5: XL | 2026-03-05 |  | 20% | 25 | 5 | 14 | 6 | No | 2025-08-20 | 2026-09-02 | 2026-03-05
Biz w/ Tech Epic: WAVE FDW initiative (#50339) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0104240 | 8780 | Using Predictive Technology to Enhance the Custome | Biz w/ Tech Epic | Assessment & Analysis | E-431916 | E-431916 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dynamo- HIS - Correct CDG HIS Outbound Reliability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108915 |  |  | Local Enhancement Epic | Backlog | E-531093 | E-531093 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-12-30
Local Enhancement Epic: Dynamo - HIS OFD - Prioritize "Real Sort Down" | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108916 |  |  | Local Enhancement Epic | Backlog | E-531095 | E-531095 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dynamo - HORUS - Feasibility Study - Priority Pack | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108917 |  |  | Local Enhancement Epic | Backlog | E-531320 | E-531320 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: Dynamo - MSP - Enhance Monitoring for Sensitive Pr | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108918 |  |  | Local Enhancement Epic | Backlog | E-531091 | E-531091 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ensure Ingrasis continue using our services | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108919 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: NetGen_FY26_Platform_LCM_Co-Location HD Logic | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108920 |  |  | Lifecycle Management Epic | Backlog | E-522385 | E-522385 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2025-10-29
Lifecycle Management Epic: NetGen_FY26_Platform_LCM_GitHubActions | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0108921 |  |  | Lifecycle Management Epic | Backlog | E-522381 | E-522381 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-01-16 | 2026-04-02
Local Enhancement Epic: Printing of support Labels on DH2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108922 |  |  | Local Enhancement Epic | Backlog | E-536208 | E-536208 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-02
Local Enhancement Epic: Allow DH2 to re-create & print FDX/TNT Barcodes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108923 |  |  | Local Enhancement Epic | Backlog | E-536210 | E-536210 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: Change sort area by scanning a barcode on DH2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108924 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545272 | E-545272 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface - Asset Core Data Attributes(DUPLICATE) | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108926 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Maximo User Adaptor (User/Supervisor) | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108949 |  |  | Local Enhancement Epic | Backlog | E-528411 | E-528411 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DH2 to transfer scan status to Italy dom system | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0108992 |  |  | Local Enhancement Epic | Backlog | E-528481 | E-528481 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-28
Lifecycle Management Epic: Testing Automation Existing Applications | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109004 |  |  | Lifecycle Management Epic | Backlog | E-527681 | E-527681 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2025-10-28
Lifecycle Management Epic: All-SORT-Production and Maintenance Support CY25 | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109008 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25_PI03_AFCS.ART_Systems.Sustainability | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109014 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CY25_AFCS.ART_FY25_Production.Support | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109015 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI-3 Ground Fuel Defect Remediation | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109017 |  |  | Lifecycle Management Epic | Done | E-522253 | E-522253 | 2: S | 2025-08-26 | 2025-08-26 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-26 | 2025-08-26
Lifecycle Management Epic: Apache JMeter Conversion | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109018 |  |  | Lifecycle Management Epic | Backlog | E-522255 | E-522255 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-06-02 | 2026-08-19
Lifecycle Management Epic: CY25_PI03_AFCS.ART_Product.Improvements | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109019 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Zealand flight update in Import Declaration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109030 |  |  | Local Enhancement Epic | Backlog | E-522901 | E-522901 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2027-01-12
Local Enhancement Epic: Yesilsoft (vend) needs to upload elect | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109034 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enable autoposting STAT65/55/71/72/70/SIPS +AvSec | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109035 |  |  | Local Enhancement Epic | Backlog | E-536209 | E-536209 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: CR FOR ACCS SCAN CLIENT GK CONS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109043 |  |  | Local Enhancement Epic | Backlog | E-534722 | E-534722 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MY Air Manifest v2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109046 |  |  | Local Enhancement Epic | Backlog | E-528103 | E-528103 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-24 | 2025-12-31
Lifecycle Management Epic: Protect Purple for Trade Tools for PI03 | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109049 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Austria (Vend) clearance needs upload | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109066 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_CX ART_App Server upgrade, patching | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109068 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_SS ART_App Server upgrade, patching | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109070 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_LCM_IRG_ATLAS Publication Improvements | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109075 |  |  | Lifecycle Management Epic | Backlog | E-527731 | E-527731 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AFDC / Forms Scanner Application Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109077 |  |  | Local Enhancement Epic | Backlog | E-527134 | E-527134 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-30
Local Enhancement Epic: AS400 modification to filter locids | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109103 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_LCM_IRG_Quality & Supportability | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109104 |  |  | Lifecycle Management Epic | Backlog | E-522613 | E-522613 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HORUS - Transload Splits Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109108 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542543 | E-542543 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ID ACCS - APAC ID - AYO and Clearance Project | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109114 |  |  | Local Enhancement Epic | Backlog | E-534719 | E-534719 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_TN_EPART PHOENIX Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109115 |  |  | Lifecycle Management Epic | Backlog | E-528644 | E-528644 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_TN_EPART PEGASUS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109117 |  |  | Lifecycle Management Epic | Backlog | E-528615 | E-528615 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_TN_EPART_AFS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109119 |  |  | Lifecycle Management Epic | Backlog | E-527728 | E-527728 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Spirit Invoice Testing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109121 |  |  | Local Enhancement Epic | Backlog | E-528079 | E-528079 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2026-03-24
Local Enhancement Epic: LAC-BR-SC-WMS Enable indoor operation for the TIM | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109125 |  |  | Local Enhancement Epic | Backlog | E-523137 | E-523137 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG Field Service Redesign | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109127 |  |  | Local Enhancement Epic | Backlog | E-523141 | E-523141 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU Clearance ART - Local Enhancements CY25-4 | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109128 |  |  | Local Enhancement Epic | Build | E-536447 | E-536447 | 1: XS | 2025-09-04 |  |  | 2 | 0 | 2 | 0 | No |  |  | 2025-09-04
Lifecycle Management Epic: FY26_SCO_TN_EPART GRIPS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109129 |  |  | Lifecycle Management Epic | Backlog | E-527734 | E-527734 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_TN_EPART CARS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109130 |  |  | Lifecycle Management Epic | Backlog | E-527730 | E-527730 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_TN_EPART SLOT Mgt Sys Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109132 |  |  | Lifecycle Management Epic | Backlog | E-527733 | E-527733 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25_AFCS.ART_FY25_Production.Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109131 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-538244 | E-538244 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Lifecycle Management Epic: SCO_TN_EPART_OPERATIONAL_EXCELLENCE_CY25 | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109133 |  |  | Lifecycle Management Epic | Backlog | E-527732 | E-527732 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface - Asset Viewer | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109134 |  |  | Local Enhancement Epic | Backlog | E-523267 | E-523267 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2026-08-19
Local Enhancement Epic: Splits 3 Comment Scan Enhancement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109141 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DREUI Scheduled report creation and communication | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109143 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580822 | E-580822 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: RLS/DASH: 8680i Ring Scanner Deployment | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109144 |  |  | Local Enhancement Epic | Backlog | E-531089 | E-531089 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-02-02 | 2026-02-19
Biz w/ Tech Epic: SA Clearance and Sort Transition, On Demand Print | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109153 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: E&E Co Ltd - EDI for brokerage billing and docs | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109179 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #82682 - WS7 - Reduce Manual Handling Efforts in S | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109223 | 7705 | WS7 - Reduce Manual Handling Efforts in Stations | Biz w/ Tech Epic | Assessment & Analysis | E-448192 | E-448192 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: [VIS] Ground Fusion Retirement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109224 | 7668 | [VIS] Ground Fusion Retirement | Biz w/ Tech Epic | Assessment & Analysis | E-465946 | E-465946 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Air Path (Automate Load Planning Process) (Planvie | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109225 | 7085 | AirPath+ | Biz w/ Tech Epic | Assessment & Analysis | E-465944 | E-465944 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Biofuels | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109226 | 7158 | Road Network-Alternative fuels - strategy - contra | Biz w/ Tech Epic | Assessment & Analysis | E-503707 | E-503707 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Capture Delivery Information | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109227 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Assessment & Analysis | E-450773 | E-450773 | 4: L |  |  | 100% | 1 | 1 |  | 0 | No
Biz w/ Tech Epic: Customer Label Creation Threshold - NID | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109228 | 8139 | Customer Label Creation Threshold | Biz w/ Tech Epic | Assessment & Analysis | E-449374 | E-449374 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DMT/USSC Enablement for Legacy Express Sortation | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109229 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Assessment & Analysis | E-445136 | E-445136 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: DRIVE #4762 - Scale Clearance document upload solu | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109230 | 7805 | Scale Clearance document upload solution to reduce | Biz w/ Tech Epic | Assessment & Analysis | E-334109 | E-334109 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-12
Biz w/ Tech Epic: DRIVE #9104 - Expand & Optimize Inbound Clearance | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109231 | 7794 | EMR OTC - Optimize Inbound Ancillaries Offer | Biz w/ Tech Epic | Assessment & Analysis | E-334106 | E-334106 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-04-10
Biz w/ Tech Epic: Duplicate Tracking (Pilot) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109232 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Assessment & Analysis | E-431523 | E-431523 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-08-15
Biz w/ Tech Epic: EDP VB2 2.1.5 EDP-NOP Accuracy | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109233 | 8101 | Enhanced Engineering Demand Planning - VB2 | Biz w/ Tech Epic | Assessment & Analysis | E-508089 | E-508089 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2025-11-04
Biz w/ Tech Epic: Enable FR domestic in CDAS International | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109234 | 8085 | EMR – WS6 – Develop & implement CSP PFS | Biz w/ Tech Epic | Assessment & Analysis | E-450902 | E-450902 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2026-01-01
Biz w/ Tech Epic: Enhance integration of CDAS with Debrief | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109235 | 7865 | Reduce LTP duplicate stops through launch of Debri | Biz w/ Tech Epic | Assessment & Analysis | E-317040 | E-317040 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2026-02-27
Biz w/ Tech Epic: Future R+ Automate Delivery Exceptions - NID | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109236 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-274924 | E-274924 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - CMQT – Multimodal Enhancements | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109237 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-374563 | E-374563 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - CMQT 2.0 - Priority Plus - Guaranteed Servic | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109238 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Assessment & Analysis | E-415792 | E-415792 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - DRIVE 26276 Handling Unit Movement (HUM) - E | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109239 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Assessment & Analysis | E-479052 | E-479052 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-01 | 2025-12-31
Biz w/ Tech Epic: FXF - DRIVE 26276 Handling Unit Movement (HUM) Pil | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109240 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Assessment & Analysis | E-446459 | E-446459 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - HU Damages (Rollout #5) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109241 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Assessment & Analysis | E-408994 | E-408994 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - True Commit Date | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109242 | 9508 | FXF - True Commit Date | Biz w/ Tech Epic | Assessment & Analysis | E-465949 | E-465949 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF eDR and Photo Capture VB2 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109243 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Assessment & Analysis | E-450976 | E-450976 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ID0327 - Global P&D Ecosystem (International FRO & | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109244 | 7406 | Global P&D Ecosystem Enabler | Biz w/ Tech Epic | Assessment & Analysis | E-426708 | E-426708 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: iD3958 - MEMH AS/RS Pilot East Cage | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109245 | 7584 | AS/RS in MEMH East Cage #7584 | Biz w/ Tech Epic | Assessment & Analysis | E-391331 | E-391331 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Manage Document Prints | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109246 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Assessment & Analysis | E-450978 | E-450978 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Manage User Access | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109247 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Assessment & Analysis | E-450979 | E-450979 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: NOP: Delivery Forecast | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109248 | 7228 | Origin Market Surface First - N2.0 Tech Phase II / | Biz w/ Tech Epic | Assessment & Analysis | E-446279 | E-446279 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-31
Biz w/ Tech Epic: PLANS – Planning Labor and Network Scheduling – Ep | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109249 | 9066 | PLANS - US Air Planning Labor & Rostering | Biz w/ Tech Epic | Assessment & Analysis | E-436993 | E-436993 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Route Optimisation Phase 2 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109251 | 7627 | 06 - EU PUD Route Optimization - Integrated countr | Biz w/ Tech Epic | Assessment & Analysis | E-292560 | E-292560 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-01-01 | 2026-04-30
Biz w/ Tech Epic: Support DH2 - ROCS 2.0 Integration | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109252 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-474350 | E-474350 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TW-502948-IMP TAMR HSCode match (DRIVE:35867) | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109253 | 7008 | [APAC] Clearance Intelligent Automation (AIML) | Biz w/ Tech Epic | Assessment & Analysis | E-410240 | E-410240 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Win Back B2B and B2C >30kg shipments - NID | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109254 | 7313 | Win Back B2B and B2C >30kg shipments | Biz w/ Tech Epic | Assessment & Analysis | E-452151 | E-452151 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: # 82597- WS2 - Eliminate requirement for couriers | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109327 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-436667 | E-436667 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #33043 - Global Export Clearance Fees (Non EU But | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109328 | 6946 | EMR OTC - Global Export Clearance Fees | Biz w/ Tech Epic | Assessment & Analysis | E-436023 | E-436023 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #41696 - BI Consol - SAP BO - FXS (Non EU But EU I | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109330 | 7113 | TS-VL3-DATAVISUAL-SASBOFXS | Biz w/ Tech Epic | Assessment & Analysis | E-416158 | E-416158 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #57680 - FDX UK Oversize/Exceed Dims - Manual Scan | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109332 | 8107 | FDX UK Oversize/Exceed Dims - Manual Scan | Biz w/ Tech Epic | Assessment & Analysis | E-403822 | E-403822 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #82231 - WS2 - SR – Pickup Capabilities Informatio | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109334 | 7450 | WS2 - SR – Pickup Capabilities Information Accurac | Biz w/ Tech Epic | Assessment & Analysis | E-448187 | E-448187 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #82587 WS1 - [1C - Project Zenith ] Measure Plan v | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109335 | 6788 | WS1 - [1C - Project Zenith ] Interim SFP | Biz w/ Tech Epic | Assessment & Analysis | E-429927 | E-429927 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-08-30
Biz w/ Tech Epic: #82588 EU BUNKER - WS1 - [1C - Project Zenith ] Ex | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109336 | 6782 | WS1 - [1C - Project Zenith ] Execute Sort with Cur | Biz w/ Tech Epic | Assessment & Analysis | E-427392 | E-427392 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #82590 EU BUNKER - [1C - Project Zenith ] Comprehe | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109337 | 6786 | WS1 - [1C - Project Zenith ] Comprehensive E2E Net | Biz w/ Tech Epic | Assessment & Analysis | E-429929 | E-429929 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-23 | 2026-05-29
Biz w/ Tech Epic: [AMEA] Single Desktop with Automation using AI (Ch | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109338 | 7626 | [AMEA] Single Desktop with Automation (CN) | Biz w/ Tech Epic | Assessment & Analysis | E-449370 | E-449370 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: [MEISA] FiT launch in Saudi Arabia | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109339 | 110060 | [MEISA] FiT launch in Saudi Arabia | Biz w/ Tech Epic | Assessment & Analysis | E-517654 | E-517654 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2025-08-27 | 2026-04-30
Biz w/ Tech Epic: [SA] OCR-Driven Data Update in GRACE from Invoice | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109340 | 103633 | [MEISA] [SA} OCR-Driven Data Update in GRACE | Biz w/ Tech Epic | Assessment & Analysis | E-501664 | E-501664 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-04-16 | 2025-06-10
Biz w/ Tech Epic: 23553 Enhanced Commodity Visibility | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109341 | 8548 | Enhanced Commodity Visibility | Biz w/ Tech Epic | Assessment & Analysis | E-420192 | E-420192 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2026-02-02 | 2026-02-27
Biz w/ Tech Epic: 57268 [Enabler] Modernized Appointment Dashboard | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109342 | 7231 | Freight LTL/Direct Appt Application | Biz w/ Tech Epic | Assessment & Analysis | E-431764 | E-431764 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CARM - (Legal/Regulatory) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109343 | 104475 | EMR OTC– CARM Fee | Biz w/ Tech Epic | Assessment & Analysis | E-78936 | E-78936 |  |  |  | 52.38% | 21 | 11 | 10 | 0 | No
Biz w/ Tech Epic: Central clearance for SRDS/H7 PL in CDG based on a | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109344 | 90006 | IOSS Centralisation | Biz w/ Tech Epic | Assessment & Analysis | E-451150 | E-451150 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-02-27
Biz w/ Tech Epic: CH Regulatory Changes and Vendor Replacement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109345 | 85946 | CH Regulatory Changes & Vendor Replacement | Biz w/ Tech Epic | Assessment & Analysis | E-473204 | E-473204 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: China UEL/MFA Routing | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109346 | 89968 | China UEL/MFA Routing | Biz w/ Tech Epic | Assessment & Analysis | E-501241 | E-501241 | 4: L |  |  |  | 2 | 0 |  | 2 | No | 2025-06-18 | 2025-07-01
Biz w/ Tech Epic: CLR-REG:GB Channel Islands Domestic Clearance Data | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109347 | 7097 | Channel Islands Integration | Biz w/ Tech Epic | Assessment & Analysis | E-497507 | E-497507 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CLR-REIM:GB Channel Islands Domestic Clearance Dat | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109348 | 7097 | Channel Islands Integration | Biz w/ Tech Epic | Assessment & Analysis | E-497506 | E-497506 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CLR-TT: TT Orchestrator/DW HS Model Integration | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109349 | 107512 | HS classificaion and validation | Biz w/ Tech Epic | Assessment & Analysis | E-450797 | E-450797 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-07-09
Biz w/ Tech Epic: CN-784222-[CatB]-Display Cat B declaration data fr | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109350 | 91190 | [WIN] CN Ecommerce digital solution by iClear | Biz w/ Tech Epic | Backlog | E-481559 | E-481559 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-25 | 2025-10-31
Biz w/ Tech Epic: Crew Management Systems Modernization | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109351 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-113301 | E-113301 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Dangerous Goods/HazMat PFS Phase 1 - Surcharges | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109352 | 8920 | Dangerous Goods/HazMat PFS Phase I - Surcharges | Biz w/ Tech Epic | Assessment & Analysis | E-465948 | E-465948 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Define Enterprise Service Metrics - Service Disrup | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109353 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-363379 | E-363379 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Biz w/ Tech Epic: E2E Network Observability | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109354 | 91537 | OpEx E2E Assessment & Observability | Biz w/ Tech Epic | Assessment & Analysis | E-479198 | E-479198 | 5: XL |  |  |  | 5 | 0 | 2 | 3 | No | 2025-02-03 | 2025-05-30
Biz w/ Tech Epic: E-Commerce Low Value Inspection System (ELVIS) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109355 | 98476 | ELVIS - e-commerce Low Value Inspection System | Biz w/ Tech Epic | Assessment & Analysis | E-258442 | E-258442 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-19
Biz w/ Tech Epic: ENT Badging and Physical Access Release 3.0 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109356 | 92350 | 92350-ENT Badging and Physical Access Release 3.0 | Biz w/ Tech Epic | Assessment & Analysis | E-454758 | E-454758 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Fedex Freight (FXF) Arch,Eng&Gov of Info Sys AEGIS | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109357 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-486906 | E-486906 |  |  |  | 100% | 2 | 2 |  | 0 | No
Biz w/ Tech Epic: FedEx International Deferred Freight (FDF) MMP1B | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109358 | 9240 | Launch International Deferred Freight 1A & 1B | Biz w/ Tech Epic | Assessment & Analysis | E-435579 | E-435579 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Fiji Direct Serve Conversion (SCO portfolio) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109360 | 6945 | Fiji Direct Serve Conversion | Biz w/ Tech Epic | Assessment & Analysis | E-449368 | E-449368 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2025-10-31
Biz w/ Tech Epic: FOCUServices Retirement - NID | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109361 | 9229 | Flight Operations Crew Services Integration (FOCSI | Biz w/ Tech Epic | Assessment & Analysis | E-453306 | E-453306 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Fuel Modernization - Monthly Fuel Close | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109363 | 103642 | Monthly Fuel Close Automation | Biz w/ Tech Epic | Assessment & Analysis | E-294202 | E-294202 |  |  |  |  | 0 | 0 |  | 0 | No | 2023-08-16 | 2027-01-20
Biz w/ Tech Epic: FXG - GSI PL: Intercept Portal | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109364 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-422291 | E-422291 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2026-04-07
Biz w/ Tech Epic: FXL digital product and services development | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109365 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-501983 | E-501983 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Biz w/ Tech Epic: FXL Finance Transformation | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109366 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-501982 | E-501982 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXL Transformation Brokerage | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109367 | 114172 | FXL Transformation Brokerage | Biz w/ Tech Epic | Backlog | E-501979 | E-501979 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-08-28
Biz w/ Tech Epic: FXL Transformation Transportation | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109368 | 114420 | FXL Transformation Transportation | Biz w/ Tech Epic | Backlog | E-501975 | E-501975 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-08-28
Biz w/ Tech Epic: Germany Export Clearance System | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109369 | 92121 | DE Exit Clearance System | Biz w/ Tech Epic | Assessment & Analysis | E-195169 | E-195169 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-06-01
Biz w/ Tech Epic: Global Electronic Transport Document (GETD) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109370 | 96452 | UCC ETD | Biz w/ Tech Epic | Build | E-130831 | E-130831 | 3: M | 2026-01-14 |  |  | 11 | 0 | 2 | 9 | No | 2024-07-22 | 2024-07-22 | 2026-01-14
Biz w/ Tech Epic: GTS Canada Clearance System Fixes & Enhancements | On Hold | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109371 | 8159 | GTS Canada Clearance System Fixes & Enhancements | Biz w/ Tech Epic | Assessment & Analysis | E-465947 | E-465947 |  |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: iD3715 - ICS2 EU Admissibility (Pre Arrival) - Rel | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109372 | 106149 | UCC ICS2 Release 3 | Biz w/ Tech Epic | Assessment & Analysis | E-364830 | E-364830 | 3: M |  |  | 5.769% | 52 | 3 | 40 | 9 | No | 2024-08-20 | 2024-10-28
Biz w/ Tech Epic: iD4084 - FedEx Domestic Channel Island Integration | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109373 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-402084 | E-402084 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: LAC CALI Costa Rica (CRI) Stop Processing Invoices | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109374 | 91469 | LAC Costa Rica e-Invoicing Regul Changes 6/25 | Biz w/ Tech Epic | Assessment & Analysis | E-498693 | E-498693 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: LAC IBIS - EIW Deprecation/migration to Atlas - Im | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109375 | 130802 | TS-VL3-EIW - LAC-IBIS App/Data Migration to Atlas | Biz w/ Tech Epic | Assessment & Analysis | E-488582 | E-488582 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: LAC42 Costa Rica Enable eInvoicing Credit Note MVP | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109376 | 91469 | LAC Costa Rica e-Invoicing Regul Changes 6/25 | Biz w/ Tech Epic | Assessment & Analysis | E-484372 | E-484372 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Biz w/ Tech Epic: LAC42 Costa Rica Enable eInvoicing Invoice MVP | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109377 | 91469 | LAC Costa Rica e-Invoicing Regul Changes 6/25 | Biz w/ Tech Epic | Assessment & Analysis | E-350952 | E-350952 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Biz w/ Tech Epic: LAC-INCAS-PLUS LAC-42 LAC-LDP New Currency Code Re | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109378 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-518597 | E-518597 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-25 | 2025-09-02
Biz w/ Tech Epic: Manual Sort Augmentation/Enhancement Seq ID 89458 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109379 | 89458 | Manual Sort Augmentation/Enhancement | Biz w/ Tech Epic | Assessment & Analysis | E-488497 | E-488497 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: MEMH Non-Con Auto Secondary Sort (Bldg. 25) Seq ID | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109380 | 88407 | NonCon Auto Secondary Sort [MEMH only] | Biz w/ Tech Epic | Assessment & Analysis | E-488511 | E-488511 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-02-02 | 2026-03-03
Biz w/ Tech Epic: MPS Parcel/Freight Corporate | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109382 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-427847 | E-427847 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AU Domestic API Services Modernization | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109383 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-501238 | E-501238 | 4: L |  |  |  | 1 | 0 |  | 1 | No | 2025-06-02 | 2026-12-31
Biz w/ Tech Epic: N2.0 One FedEx Reporting - (Priority Metrics, TLH, | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109384 | 7200 | N2.0 One FedEx Reporting and Visibility - MVP1 (Pr | Biz w/ Tech Epic | Assessment & Analysis | E-438758 | E-438758 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: N2.0 Settlement & Liquidated Damages Automation | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109385 | 9035 | N2.0 Settlement Automation | Biz w/ Tech Epic | Assessment & Analysis | E-417040 | E-417040 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-29 | 2024-08-30
Biz w/ Tech Epic: New surcharge- late domestic invoice fee - Initiat | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109386 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-409542 | E-409542 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Non-Con Scanning Seq ID 90009 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109387 | 90009 | NonCon Scanning | Biz w/ Tech Epic | Assessment & Analysis | E-488507 | E-488507 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Payload Visibility Improvements - NID | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109388 | 6967 | GOC Jet Fuel - Payload Visibility Improvements | Biz w/ Tech Epic | Assessment & Analysis | E-453327 | E-453327 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: PV 6714 FRO-A-Preferred Future State Data Sources | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109389 | 6714 | Align settlement model with daily op performance | Biz w/ Tech Epic | Assessment & Analysis | E-434651 | E-434651 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: PV Request 1336 - Support Deforestation | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109390 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-485125 | E-485125 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2026-01-30
Biz w/ Tech Epic: Recovery Operations Control System | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109391 | 7886 | Recovery Operations Control System | Biz w/ Tech Epic | Assessment & Analysis | E-321908 | E-321908 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Remove Commercial Signature - Express | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109392 | 7390 | Remove Commercial Signature - Express | Biz w/ Tech Epic | Assessment & Analysis | E-449350 | E-449350 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Remove Commercial Signature - Ground - NID | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109393 | 8309 | Remove Commercial Signature - Ground | Biz w/ Tech Epic | Assessment & Analysis | E-449347 | E-449347 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2025-11-28
Biz w/ Tech Epic: Roadmap Techniques for Last Mile Delivery | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109394 | 8011 | [Pilot] Roadmap Techniques for Last Mile Delivery | Biz w/ Tech Epic | Assessment & Analysis | E-449349 | E-449349 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0303 - FDX UK Oversize/Exceed Dims - Manual Scan | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109395 | 8107 | FDX UK Oversize/Exceed Dims - Manual Scan | Biz w/ Tech Epic | Assessment & Analysis | E-436945 | E-436945 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0338 - Pickup Preferred Future State (PFS) Value | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109396 | 9200 | Rationalize On-Call Pickup Product and Scheduling | Biz w/ Tech Epic | Assessment & Analysis | E-432347 | E-432347 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0407 - N2.0 Financial Digital Tooling - Centraliz | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109397 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-431752 | E-431752 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0438 - Collect Error Automation | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109398 | 7880 | Collect Error Automation | Biz w/ Tech Epic | Assessment & Analysis | E-436092 | E-436092 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0467 - FXF PD Stop Sequencing | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109399 | 7520 | FXF PD Stop Sequencing | Biz w/ Tech Epic | Assessment & Analysis | E-446668 | E-446668 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SCO - WH - CIL - Legacy ACSS - New TMS for Air Exp | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109400 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-470023 | E-470023 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SCO070 ACAS Vague Commodity Description | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109402 | 7310 | US CBP ACAS Vague Description Enforcement | Biz w/ Tech Epic | Assessment & Analysis | E-455004 | E-455004 | 4: L |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: Service Change (Intercept) Automation /Change Orde | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109403 | 6832 | Service Change (Intercept) Automation /Change Orde | Biz w/ Tech Epic | Assessment & Analysis | E-470460 | E-470460 | 4: L |  |  |  | 6 | 0 | 5 | 1 | No | 2025-05-01 | 2027-01-08
Biz w/ Tech Epic: Small Parcel Reusable Bag Deployment Seq ID 89380 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109404 | 89380 | Global-Small Parcel Reusable Bag-Parent-US | Biz w/ Tech Epic | Assessment & Analysis | E-487755 | E-487755 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Surface bulk fueling – Cross OpCo fueling with FXG | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109405 | 7179 | Surface bulk fueling – Cross OpCo fueling with FXG | Biz w/ Tech Epic | Assessment & Analysis | E-449369 | E-449369 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Suspend PPOD on Ground Economy Stops | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109406 | 8123 | Suspend PPOD on Ground Economy Stops | Biz w/ Tech Epic | Assessment & Analysis | E-449352 | E-449352 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Tricolor – Facilities Enablement – DFW / Cowboy | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109408 | 7954 | Tricolor – Facilities Enablement – DFW / Cowboy | Biz w/ Tech Epic | Assessment & Analysis | E-512376 | E-512376 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Tricolor Freight Heavy Weight (FAST) VB2 (not VB1) | On Hold | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109409 | 9320 | Tricolor Feight Heavy Weight | Biz w/ Tech Epic | Assessment & Analysis | E-426826 | E-426826 | 4: L |  |  |  | 0 | 0 |  | 0 | Yes
Biz w/ Tech Epic: UCC EFBT - EU System ART | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109410 | 96300 | UCC-Export Followed By Transit Data availability | Biz w/ Tech Epic | Assessment & Analysis | E-500301 | E-500301 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-11-13 | 2026-10-19
Biz w/ Tech Epic: UCC Exit Handling | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109411 | 110211 | EU Exit Process | Biz w/ Tech Epic | Assessment & Analysis | E-446552 | E-446552 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: UCC ICS2 Phase P3 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109412 | 106149 | UCC ICS2 Release 3 | Biz w/ Tech Epic | Assessment & Analysis | E-148836 | E-148836 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-11-10
Biz w/ Tech Epic: UCC NCTS P5 upgrade (Roll out) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109413 | 96303 | NCTS p5 HS Code - iSearch functionality | Biz w/ Tech Epic | Assessment & Analysis | E-325039 | E-325039 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-12
Biz w/ Tech Epic: UCC NCTS P5 upgrade (CORE - GENERIC) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109414 | 96303 | NCTS p5 HS Code - iSearch functionality | Biz w/ Tech Epic | Assessment & Analysis | E-325052 | E-325052 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-02-25
Biz w/ Tech Epic: US CBP ACAS Vague Description Enforcement - MVP2 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109415 | 7310 | US CBP ACAS Vague Description Enforcement | Biz w/ Tech Epic | Assessment & Analysis | E-479149 | E-479149 |  |  |  |  | 3 | 0 |  | 3 | No
Biz w/ Tech Epic: US De Minimis Changes Section 321 Aggregate Value | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109416 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-448106 | E-448106 | 2: S |  |  |  | 1 | 0 | 1 | 0 | No
Biz w/ Tech Epic: VIPS Retirement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109417 |  |  | Biz w/ Tech Epic | Assessment & Analysis | E-516232 | E-516232 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2026-02-16 | 2026-06-16
Biz w/ Tech Epic: Windsor Agreement | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109418 | 98472 | Windsor Framework | Biz w/ Tech Epic | Assessment & Analysis | E-398450 | E-398450 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: WS1 - [1C - Project Zenith ] Execute Sort with Cur | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109419 | 6782 | WS1 - [1C - Project Zenith ] Execute Sort with Cur | Biz w/ Tech Epic | Assessment & Analysis | E-503899 | E-503899 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: WS1 - [1C - Project Zenith] Forecast Solution for | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109420 | 8442 | WS1 - [1C - Project Zenith ] Forecast Solution | Biz w/ Tech Epic | Assessment & Analysis | E-429930 | E-429930 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Biz w/ Tech Epic: [SA] HS Code Auto-Fill in GRACE from Invoice Data | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109421 | 103629 | [MEISA] [SA] HS Code Auto-Fill in GRACE | Biz w/ Tech Epic | Assessment & Analysis | E-507847 | E-507847 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-16 | 2025-06-10
Local Enhancement Epic: FXL - GLOBAL O RING - EDI/API INTEGRATION | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109423 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 - RunOpsSort- Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109427 |  |  | Lifecycle Management Epic | Build | E-531075 | E-531075 | 4: L | 2025-08-28 |  | 33.33% | 3 | 1 | 2 | 0 | No |  |  | 2025-08-28
Lifecycle Management Epic: LAC-BR-EXPORTA-DECOMISSION | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109432 |  |  | Lifecycle Management Epic | Backlog | E-525313 | E-525313 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: # 67236 - SU - Single Point Of Access Enhancement | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109516 | 6740 | SU - Single Point Of Access Enhancement | Biz w/ Tech Epic | Backlog | E-412365 | E-412365 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #27245 - Postal enablement EE, LV, LT, IE, BG, CY | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109519 | 9491 | Postal enablement EE, LV, LT, IE, BG, CY, SI, UA | Biz w/ Tech Epic | Build | E-423449 | E-423449 | 3: M | 2025-07-01 |  |  | 11 | 0 | 6 | 5 | No |  |  | 2025-07-01
Biz w/ Tech Epic: #407 - Domestic PUD Route Optimization - PL IT FR | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109520 |  |  | Biz w/ Tech Epic | Backlog | E-326010 | E-326010 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #4762 - Scale Clearance document upload solution t | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109521 | 7805 | Scale Clearance document upload solution to reduce | Biz w/ Tech Epic | Backlog | E-275809 | E-275809 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-01
Biz w/ Tech Epic: #67260 - WS #11 Create SPOC location in NL for Int | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109523 | 7411 | WS #11 Create SPOC location in NL for Intra-EU Eco | Biz w/ Tech Epic | Build | E-448177 | E-448177 | 2: S | 2025-12-23 |  |  | 2 | 0 | 1 | 1 | No | 2025-10-08 | 2026-03-31 | 2025-12-23
Biz w/ Tech Epic: #7062 - Scale Duty&Tax Online Payment Solutions (D | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109525 | 7783 | Scale Duty&Tax Online Payment Solutions (DOPS) to | Biz w/ Tech Epic | Backlog | E-268621 | E-268621 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-02
Biz w/ Tech Epic: #81043 - WS6 -Acquire LTP cost data for EU non-int | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109528 | 8441 | WS6 - Acquire LTP cost data for EU non-integrated | Biz w/ Tech Epic | Backlog | E-432052 | E-432052 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #82402 - WS7 - AHS - Packaging. Increase capture | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109529 | 7687 | CWC - WS7 - AHS - Packaging. Increase capture | Biz w/ Tech Epic | Backlog | E-449351 | E-449351 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-05-31 | 2026-05-29
Biz w/ Tech Epic: #82579 - WS1 - [1A] Exploit Shipment data opportun | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109530 | 7395 | WS1 - [1A] Exploit Shipment data opportunities wit | Biz w/ Tech Epic | Backlog | E-427380 | E-427380 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-13
Biz w/ Tech Epic: #82584 EU BUNKER (1A) - Clearance & Sort instruc | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109531 | 6780 | WS1 - [1A] Keep clearance and sort instructions Sy | Biz w/ Tech Epic | Backlog | E-427388 | E-427388 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #82598 - WS2 - Consolidate sortation, routing, lab | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109532 | 7437 | WS2 - Consolidate sortation, routing, label printi | Biz w/ Tech Epic | Backlog | E-439342 | E-439342 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-11
Biz w/ Tech Epic: #83027 - WS2 - Ops Tech Mobile - Lifecycle Replace | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109533 | 7700 | Ops Tech Mobile - Lifecycle Replacement Europe | Biz w/ Tech Epic | Backlog | E-436636 | E-436636 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #83047 -Ops Tech Mobile - Lifecycle Replacement It | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109534 | 7414 | Ops Tech Mobile - Lifecycle Replacement Italy | Biz w/ Tech Epic | Backlog | E-448828 | E-448828 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: #84180 - Align UDS CWC transmission to HCH with F | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109535 | 7718 | CWC - 84180 - Align UDS DWC devices to HCH naming | Biz w/ Tech Epic | Backlog | E-437903 | E-437903 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Biz w/ Tech Epic: #86416 - WS10 – ITALY ONE – Cross Sort Enablement | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109536 | 7391 | WS10 – ITALY ONE – Cross Sort Enablement | Biz w/ Tech Epic | Build | E-448826 | E-448826 |  | 2025-07-02 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: #9104 - Optimize inbound Ancillaries Offer | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109537 | 7794 | EMR OTC - Optimize Inbound Ancillaries Offer | Biz w/ Tech Epic | Backlog | E-275810 | E-275810 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-01
Biz w/ Tech Epic: (SCAN) Build an AutoSlip client application for F | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109538 | 89829 | Common CONs - Value Bundle 1 | Biz w/ Tech Epic | Backlog | E-259651 | E-259651 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-31
Biz w/ Tech Epic: [DIY] Predictive Maintenance (MOBIUS) | On Hold | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109539 | 7563 | TS-VL3-HybridCloud-GCPMigrateMOBIUSSurfCoDataMigra | Biz w/ Tech Epic | Done | E-449153 | E-449153 | 2: S | 2025-07-15 | 2025-07-15 |  | 0 | 0 |  | 0 | No | 2024-08-23 | 2027-03-31 | 2025-07-15 | 2025-07-15
Biz w/ Tech Epic: APAC-523591-FiT/CDEP–AMEA clearance online portal | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109540 | 7837 | APAC: FiT - Deploy clearance self-service platform | Biz w/ Tech Epic | Backlog | E-408537 | E-408537 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AU Domestic - DRP Final Plan Re-Architecture? | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109541 | 9361 | Courier productivity savings - Dynamic Route Plann | Biz w/ Tech Epic | Backlog | E-410444 | E-410444 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AU IDP data for ACCS to consume including HScode a | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109542 | 7008 | [APAC] Clearance Intelligent Automation (AIML) | Biz w/ Tech Epic | Backlog | E-409795 | E-409795 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AU: TAMR CP Auto Match (DRIVE:35867) | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109543 | 7008 | [APAC] Clearance Intelligent Automation (AIML) | Biz w/ Tech Epic | Backlog | E-385015 | E-385015 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Capture Delivery Photo | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109544 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Backlog | E-450969 | E-450969 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CLASS Tri-Color Enablement FY25 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109545 | 7524 | CLHQPI: CLASS Phase 3 - Tri-Color Enablement | Biz w/ Tech Epic | Build | E-451968 | E-451968 |  | 2025-07-02 |  | 100% | 7 | 7 |  | 0 | No | 2024-08-14 | 2025-06-10 | 2025-07-02
Biz w/ Tech Epic: CN-848437-[SRO]-Enable CN IB user to update dispat | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109546 | 9525 | Optimize On-Road Route Plan to improve OnRoad Effi | Biz w/ Tech Epic | Done | E-500904 | E-500904 | 2: S | 2025-08-15 | 2025-08-15 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-15 | 2025-08-15
Biz w/ Tech Epic: Common CONs - Value Bundle 1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109547 | 89829 | Common CONs - Value Bundle 1 | Biz w/ Tech Epic | Backlog | E-498893 | E-498893 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Compensation Model | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109548 | 8085 | EMR – WS6 – Develop & implement CSP PFS | Biz w/ Tech Epic | Backlog | E-409242 | E-409242 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-31
Biz w/ Tech Epic: Contingency Overhaul - Response Collection and Sel | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109549 | 7560 | Contingency Process Overhaul - Front End | Biz w/ Tech Epic | Backlog | E-390725 | E-390725 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-20
Biz w/ Tech Epic: Country Configuration - Americas - Costa Rica | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109550 | 6878 | Country Configuration - Americas - Costa Rica | Biz w/ Tech Epic | Backlog | E-465942 | E-465942 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Damaged Package Tool (DPT) New Opportunities | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109551 | 7659 | Damaged Package Tool (DPT) New Opportunities & New | Biz w/ Tech Epic | Backlog | E-473255 | E-473255 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-28 | 2026-01-06
Biz w/ Tech Epic: EDP - Bulk Area Functionality | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109552 | 8101 | Enhanced Engineering Demand Planning - VB2 | Biz w/ Tech Epic | Backlog | E-483177 | E-483177 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-09 | 2025-06-17
Biz w/ Tech Epic: EDP 1.1 Data Facilitation for Planned Operations O | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109553 | 8100 | Enhanced Engineering Demand Planning - VB1 | Biz w/ Tech Epic | Build | E-301322 | E-301322 |  | 2025-07-01 |  | 100% | 8 | 8 |  | 0 | No | 2023-09-13 | 2027-08-20 | 2025-07-01
Biz w/ Tech Epic: EDP CAB1.1 - Sort Operation Occurrence Creation | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109554 | 8100 | Enhanced Engineering Demand Planning - VB1 | Biz w/ Tech Epic | Backlog | E-333644 | E-333644 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-30 | 2026-01-21
Biz w/ Tech Epic: EDP VB2 2.1.4 Incorporate Goal TLH and historical | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109555 | 8101 | Enhanced Engineering Demand Planning - VB2 | Biz w/ Tech Epic | Backlog | E-485532 | E-485532 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2025-11-04
Biz w/ Tech Epic: EESSP - Route Planning and Execution | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109556 | 7816 | N2.0 Tech Phase 1 (18 month roadmap) | Biz w/ Tech Epic | Build | E-342759 | E-342759 | 3: M | 2025-07-02 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2026-02-16 | 2025-07-02
Biz w/ Tech Epic: Enhanced EDP PE #2 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109557 | 8100 | Enhanced Engineering Demand Planning - VB1 | Biz w/ Tech Epic | Build | E-380729 | E-380729 |  | 2026-02-10 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2026-02-10
Biz w/ Tech Epic: Express Domestics final countries | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109558 | 7710 | EUM - Express Domestics final countries | Biz w/ Tech Epic | Build | E-501253 | E-501253 | 4: L | 2026-03-05 |  | 62.5% | 8 | 5 | 2 | 1 | No | 2024-08-20 | 2026-12-17 | 2026-03-05
Biz w/ Tech Epic: Express Freight Multiple Shipment Detection | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109559 | 7088 | Express Freight Multiple Shipment Detection | Biz w/ Tech Epic | Backlog | E-449373 | E-449373 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-01-26 | 2026-06-10
Biz w/ Tech Epic: FD 1.12: Ability to capture and store attributes o | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109560 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Backlog | E-326122 | E-326122 |  |  |  |  | 2 | 0 |  | 2 | No
Biz w/ Tech Epic: FD 1.3: Ability to define, store, and support the | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109561 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Build | E-326074 | E-326074 | 3: M | 2025-07-01 |  |  | 3 | 0 | 3 | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: FD 1.7: Ability to calculate hours worked per sort | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109562 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Build | E-326114 | E-326114 | 3: M | 2025-07-02 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: FD 1.8: Ability to associate volume scanned by sor | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109563 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Build | E-326116 | E-326116 | 4: L | 2025-07-01 |  |  | 7 | 0 | 3 | 4 | No | 2024-07-22 | 2025-02-06 | 2025-07-01
Biz w/ Tech Epic: FD PE2 2.2 Leverage a SSoT for Critical Cut Times | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109564 | 9529 | Metrics - Compass | Biz w/ Tech Epic | Backlog | E-302924 | E-302924 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-23
Biz w/ Tech Epic: FDNA - HU Container Management (Rollout #4) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109565 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Backlog | E-408992 | E-408992 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FOPD FRO: Catch All | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109566 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-403120 | E-403120 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FRO - 3-4 Sep/Oct: Enhance Operational Capabiliti | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109567 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Build | E-417317 | E-417317 |  | 2025-07-01 |  | 77.42% | 31 | 24 | 7 | 0 | No | 2025-08-11 | 2027-10-07 | 2025-07-01
Biz w/ Tech Epic: FRO- 2- Pickup Enabler Work | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109568 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Build | E-375634 | E-375634 | 4: L | 2025-07-01 |  | 73.33% | 15 | 11 | 3 | 1 | No | 2024-06-24 | 2026-08-25 | 2025-07-01
Biz w/ Tech Epic: FRO- 3-4 June: Enhance Operational Capabilities a | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109569 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Build | E-375635 | E-375635 | 4: L | 2025-07-01 |  | 85.71% | 14 | 12 | 2 | 0 | No | 2024-07-22 | 2029-02-23 | 2025-07-01
Biz w/ Tech Epic: FXF - CMQT - Multimodal Operations & Settlements | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109570 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Backlog | E-374562 | E-374562 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - CMQT – Multimodal Service Quote | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109571 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Backlog | E-374561 | E-374561 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - CMQT 2.0 - LH | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109572 | 6680 | Capacity Management Quoting Tool 2.0 | Biz w/ Tech Epic | Backlog | E-314182 | E-314182 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - DRIVE #26276 Multiple Dimensions | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109573 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Backlog | E-315791 | E-315791 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: FXF - HU Discrepancies (Rollout #2) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109574 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Build | E-408989 | E-408989 |  | 2025-10-23 |  | 100% | 1 | 1 |  | 0 | No | 2025-02-03 | 2025-11-14 | 2025-10-23
Biz w/ Tech Epic: FXF - HU Load Exceptions (Rollout #6) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109575 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Build | E-408995 | E-408995 |  | 2025-07-01 |  |  | 2 | 0 | 2 | 0 | No | 2025-06-30 | 2025-11-14 | 2025-07-01
Biz w/ Tech Epic: FXF - HU Routing (Rollout #3) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109576 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Backlog | E-408990 | E-408990 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-12 | 2025-10-29
Biz w/ Tech Epic: FXF - HU Shipment Skeleton Bill Void (Rollout #7) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109577 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Build | E-408997 | E-408997 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: FXF - Multi Dim | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109578 | 8349 | Multi DIM - Handling Unit Movement (HUM) | Biz w/ Tech Epic | Backlog | E-467990 | E-467990 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-27 | 2025-10-22
Biz w/ Tech Epic: FXF Dimensional Capture Processes to Send FXE Dime | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109579 | 9481 | FXF Dimensional Capture Processes to Send FXE Dime | Biz w/ Tech Epic | Build | E-449232 | E-449232 | 2: S | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: FXG - DRIVE # 16591 - Trimble Vusion - Fuel & Mile | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109580 | 9290 | Tax: FXG Trimble Vusion Project | Biz w/ Tech Epic | Backlog | E-420292 | E-420292 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-06-05 | 2026-08-19
Biz w/ Tech Epic: FXG - DRIVE#3556 - Electronic Supplemental ISP Dat | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109581 | 9017 | Electronic Supplemental ISP Data Collection Report | Biz w/ Tech Epic | Backlog | E-406232 | E-406232 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2026-08-19
Biz w/ Tech Epic: iClear collaboration with DataWorks | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109582 | 6897 | [APAC] iClear collaboration with Dataworks | Biz w/ Tech Epic | Backlog | E-465943 | E-465943 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ID 86392 MRI Epic 1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109583 | 7847 | Manifest Recharged Information (MRI) | Biz w/ Tech Epic | Backlog | E-449243 | E-449243 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: iD3496 - DG Systems Publishing REX Events | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109584 | 7431 | Dangerous Goods Surcharge | Biz w/ Tech Epic | Build | E-333827 | E-333827 | 3: M | 2025-07-01 |  | 50% | 6 | 3 | 3 | 0 | No | 2024-07-22 | 2024-07-22 | 2025-07-01
Biz w/ Tech Epic: iD3585 - DRIVE MI CT Intervention (*Drive #15272 a | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109585 | 7111 | Monitoring & Intervention with HC ID and CT- US | Biz w/ Tech Epic | Backlog | E-352521 | E-352521 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: iD3890 - Bulk Pickup Streamlining (*DRIVE#1106) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109586 | 8819 | Bulk Pickup Streamlining | Biz w/ Tech Epic | Backlog | E-380223 | E-380223 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-09 | 2025-06-10
Biz w/ Tech Epic: iD3942 - Increase First Mile Package Pickup Visibi | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109587 | 7778 | Customer Data Exchange - Ground Enablement | Biz w/ Tech Epic | Backlog | E-383800 | E-383800 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Improve Station Labour Productivity Valet - Initia | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109588 | 8297 | Improve Station Labour Productivity | Biz w/ Tech Epic | Backlog | E-447647 | E-447647 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Interim Solution for Automated Sites (ISAS) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109589 | 8041 | N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | Biz w/ Tech Epic | Backlog | E-371837 | E-371837 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-03
Biz w/ Tech Epic: JP-503667-JP OCR/IDP data for ACCS to consume incl | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109590 | 7008 | [APAC] Clearance Intelligent Automation (AIML) | Biz w/ Tech Epic | Backlog | E-400787 | E-400787 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: KR-502951-KR OCR/IDP data for ACCS to consume for | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109591 | 7008 | [APAC] Clearance Intelligent Automation (AIML) | Biz w/ Tech Epic | Backlog | E-399917 | E-399917 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: KYC - Enhance KYC Processes with Automation, API I | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109592 | 7172 | [IN][Enablers]Reimagine the import clearance proce | Biz w/ Tech Epic | Backlog | E-456615 | E-456615 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: KYC - FiT Integration for Centralized Visibility, | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109593 | 7172 | [IN][Enablers]Reimagine the import clearance proce | Biz w/ Tech Epic | Backlog | E-456616 | E-456616 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: KYC - Migrate on-premises infrastructure to Azure, | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109594 | 7172 | [IN][Enablers]Reimagine the import clearance proce | Biz w/ Tech Epic | Backlog | E-456583 | E-456583 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Mange FXFD Return Pickup | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109595 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Backlog | E-450981 | E-450981 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Manifest Recharged Information (MRI) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109596 | 7847 | Manifest Recharged Information (MRI) | Biz w/ Tech Epic | Backlog | E-503901 | E-503901 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Market Tune Up NG | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109597 | 7613 | Market Tune-Ups | Biz w/ Tech Epic | Backlog | E-503657 | E-503657 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-04-28 | 2025-08-20
Biz w/ Tech Epic: NOP Projections- PE1.4-Create projections with a 6 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109598 | 9429 | Network Operating Plan (NOP) Sort Plan - 2 week | Biz w/ Tech Epic | Backlog | E-315792 | E-315792 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: HTM Phase 2 Release 0 Resource Allocation SCO | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109599 | 7151 | Operational Hold to Match (HTM) | Biz w/ Tech Epic | Build | E-449335 | E-449335 | 2: S | 2025-07-01 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-07-01
Biz w/ Tech Epic: Pallet Hire Reduction - Initiative #78459 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109600 | 9146 | Pallet Hire Reduction | Biz w/ Tech Epic | Backlog | E-446033 | E-446033 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-07-31 | 2026-03-24
Biz w/ Tech Epic: PE4 - Send Hire Ahead heatmaps and shift recommend | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109601 | 9451 | Hire Ahead (Algorithmic Sourcing Tool) | Biz w/ Tech Epic | Backlog | E-328168 | E-328168 |  |  |  |  | 5 | 0 |  | 5 | No
Biz w/ Tech Epic: PIP, APAC, Golden Eye, and LAC Enrollments | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109602 | 9155 | Increased Capture of Express Operational Data | Biz w/ Tech Epic | Backlog | E-447641 | E-447641 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Biz w/ Tech Epic: Provide Shipment Information | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109603 | 7214 | FXF Paperless Delivery Receipt and Photo Capture | Biz w/ Tech Epic | Build | E-450772 | E-450772 | 3: M | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: Proxy to PurpleConnect Migration - Supply Chain Op | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109604 | 6951 | TS-VL4-SECURITY-ZSCALER | Biz w/ Tech Epic | Build | E-477844 | E-477844 |  | 2025-07-01 |  | 80% | 5 | 4 |  | 1 | No | 2025-01-02 | 2026-01-14 | 2025-07-01
Biz w/ Tech Epic: Recharge Phase 3 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109605 |  |  | Biz w/ Tech Epic | Backlog | E-486901 | E-486901 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Remote Area Surcharge- Distance based pricing - In | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109606 | 7220 | Remote surcharge- distance based pricing | Biz w/ Tech Epic | Build | E-409544 | E-409544 | 2: S | 2025-10-16 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-16
Biz w/ Tech Epic: RFID Enabled automated DIM WT - RDIM Drive #87822 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109607 | 8079 | Freight Dim WT/NSS Revenue Capture-Parent US | Biz w/ Tech Epic | Launch & Evaluate | E-463573 | E-463573 |  | 2025-07-28 |  |  | 0 | 0 |  | 0 | No | 2025-07-10 | 2026-08-28 | 2025-07-28
Biz w/ Tech Epic: RO Phase 1.3 - MyFedExRoute (MFR) - Increment 2 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109608 | 7627 | 06 - EU PUD Route Optimization - Integrated countr | Biz w/ Tech Epic | Backlog | E-410753 | E-410753 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-11-03 | 2026-08-18
Biz w/ Tech Epic: ROM 1.5 Compliance Metrics & Actual Staffing | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109609 | 9518 | Real-Time Ops Manager (ROM) | Biz w/ Tech Epic | Build | E-328280 | E-328280 |  | 2025-07-25 |  |  | 1 | 0 | 1 | 0 | No | 2025-08-12 | 2026-01-13 | 2025-07-25
Biz w/ Tech Epic: S0254 - Picture Proof of Delivery Attempt (PPODA) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109610 | 7169 | [VIS] Picture Proof of Delivery Attempt (PPODA) | Biz w/ Tech Epic | Build | E-414879 | E-414879 | 3: M | 2025-07-01 |  |  | 3 | 0 | 3 | 0 | No | 2024-08-30 | 2024-09-02 | 2025-07-01
Biz w/ Tech Epic: S0300 - FCF Transformation Epic 1 (Identification: | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109611 | 9235 | FCF transformation: Epic 1 | Biz w/ Tech Epic | Backlog | E-436786 | E-436786 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0476 - FXFD Mainstreaming Phase 3A | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109612 | 8001 | FedEx Freight Direct Mainstream | Biz w/ Tech Epic | Backlog | E-444324 | E-444324 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: S0499 - Unified Equipment Pool | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109613 | 7318 | Unified Equipment Pool (rail + dray) | Biz w/ Tech Epic | Backlog | E-447391 | E-447391 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-21
Biz w/ Tech Epic: SCO: Ground Rating Modernization | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109614 | 9097 | Modernize Ground Rating Engine For Ground Commerci | Biz w/ Tech Epic | Build | E-452641 | E-452641 |  | 2025-07-01 |  |  | 18 | 0 | 12 | 6 | No | 2024-07-22 | 2026-03-31 | 2025-07-01
Biz w/ Tech Epic: Shipment CDM First Iteration for Sort (uDS) (WS1B) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109615 | 7693 | WS1 - [1B] Shipment CDM - First iteration for Sort | Biz w/ Tech Epic | Backlog | E-470466 | E-470466 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SSP OB Shipment Flow Planning? | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109616 | 7228 | Origin Market Surface First - N2.0 Tech Phase II / | Biz w/ Tech Epic | Backlog | E-290744 | E-290744 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-05
Biz w/ Tech Epic: Surface Clearance OTB | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109617 |  |  | Biz w/ Tech Epic | Build | E-472150 | E-472150 |  | 2025-07-01 |  | 33.33% | 3 | 1 | 2 | 0 | No | 2025-01-22 | 2026-01-20 | 2025-07-01
Biz w/ Tech Epic: Surface Clearance OTB ¦ Capability 1.0 & 2.0; Phas | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109618 |  |  | Biz w/ Tech Epic | Build | E-434592 | E-434592 |  | 2025-07-02 |  | 100% | 2 | 2 |  | 0 | No |  |  | 2025-07-02
Biz w/ Tech Epic: Surface Clearance OTB; NB Phase 1 Fortification | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109619 |  |  | Biz w/ Tech Epic | Backlog | E-452746 | E-452746 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TNT shipment de-duplication and pre-possession tra | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109620 | 7395 | WS1 - [1A] Exploit Shipment data opportunities wit | Biz w/ Tech Epic | Backlog | E-425315 | E-425315 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TW New Clearance Ancillaries | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109621 | 9428 | EMR OTC-[APAC] TW New Clearance Ancillaries | Biz w/ Tech Epic | Backlog | E-452177 | E-452177 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TW-502950-IMP TAMR CP match (DRIVE:35867) | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109622 | 7008 | [APAC] Clearance Intelligent Automation (AIML) | Biz w/ Tech Epic | Backlog | E-410238 | E-410238 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: URSA/LSSI Rethink- Track 1 -Duplicate Epic/delete | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109623 |  |  | Biz w/ Tech Epic | Backlog | E-486908 | E-486908 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: WS1 - [1B] Shipment CDM - First iteration for Sort | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109624 | 7693 | WS1 - [1B] Shipment CDM - First iteration for Sort | Biz w/ Tech Epic | Backlog | E-486903 | E-486903 |  |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: WS8 - T1 – Conclusive info about shipment status | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109625 | 7682 | WS8 - T1 – Conclusive info about shipment status | Biz w/ Tech Epic | Backlog | E-476007 | E-476007 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-FCBAS-DECOMMISSION | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109626 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-3-IGLOBAL-DECOMMISSION | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109627 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Brazil Clearance Applications Decommissioning-Cy25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0109628 |  |  | Lifecycle Management Epic | Backlog | E-528431 | E-528431 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-3-JDA SC Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109629 |  |  | Local Enhancement Epic | Backlog | E-533565 | E-533565 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: "Bucket" Conveyance ART - CY 25 Keep the Lights On | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110045 |  |  | Local Enhancement Epic | Backlog | E-467217 | E-467217 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-01-22 | 2026-01-14
Local Enhancement Epic: [Debrief] Payment Management Screen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110046 |  |  | Local Enhancement Epic | Backlog | E-465631 | E-465631 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: [DIY] UGS Rollout - SGS (Sortation Graphics System | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110047 |  |  | Local Enhancement Epic | Backlog | E-449202 | E-449202 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-23 | 2025-12-31
Local Enhancement Epic: [MFR] Facilitate communication between couriers & | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110048 |  |  | Local Enhancement Epic | Backlog | E-504531 | E-504531 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2025-08-05
Local Enhancement Epic: [MFR] Improve Data quality through collection of f | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110049 |  |  | Local Enhancement Epic | Backlog | E-512884 | E-512884 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-07-08 | 2025-12-31
Local Enhancement Epic: [RDNA] Built-in training tools | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110050 |  |  | Local Enhancement Epic | Backlog | E-515072 | E-515072 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 3rd parties integration modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110051 |  |  | Local Enhancement Epic | Build | E-270276 | E-270276 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: 625 CONDOR Application Migration Factory | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110052 |  |  | Local Enhancement Epic | Backlog | E-431527 | E-431527 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-02
Lifecycle Management Epic: 7-Day PE#3 -System Availability & Peak System Reli | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110053 |  |  | Lifecycle Management Epic | Backlog | E-68650 | E-68650 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ability to run the custom critical business effect | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110054 |  |  | Local Enhancement Epic | Backlog | E-449139 | E-449139 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-08-23 | 2026-08-24
Local Enhancement Epic: Access Management | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110055 |  |  | Local Enhancement Epic | Backlog | E-108208 | E-108208 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Accmulating Hazard | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110056 |  |  | Local Enhancement Epic | Backlog | E-519203 | E-519203 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-12-31
Local Enhancement Epic: Add Capacity Background Checks | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110057 |  |  | Local Enhancement Epic | Backlog | E-337330 | E-337330 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-11
Local Enhancement Epic: Added Capacity Agreement Administration | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110058 |  |  | Local Enhancement Epic | Backlog | E-295143 | E-295143 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Admissibility Security and Maintenance Table Imple | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110059 |  |  | Local Enhancement Epic | Backlog | E-40523 | E-40523 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Adopt CSA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110060 |  |  | Local Enhancement Epic | Backlog | E-512424 | E-512424 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-07-31 | 2027-03-31
Local Enhancement Epic: Advanced Analytics | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110061 |  |  | Local Enhancement Epic | Backlog | E-184822 | E-184822 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: AE - Dubai (DWC/GPN)- Block Chain Integration with | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110062 |  |  | Local Enhancement Epic | Backlog | E-436150 | E-436150 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-05-26
Local Enhancement Epic: AFWH Customs Clearance Cage | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110063 |  |  | Local Enhancement Epic | Backlog | E-463567 | E-463567 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-04-01
Local Enhancement Epic: AGC Globalization effort | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110064 |  |  | Local Enhancement Epic | Backlog | E-332880 | E-332880 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2026-05-29
Local Enhancement Epic: AGC Governance and control of manual address corre | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110065 |  |  | Local Enhancement Epic | Backlog | E-310487 | E-310487 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-04 | 2025-06-30
Local Enhancement Epic: AIM/WISE Enhancements & Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110066 |  |  | Local Enhancement Epic | Backlog | E-158313 | E-158313 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-31
Local Enhancement Epic: Align with Customer EFS for shipper information an | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110067 |  |  | Local Enhancement Epic | Backlog | E-371669 | E-371669 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-12-31 | 2026-12-31
Lifecycle Management Epic: ALL - ACCS Review of Messaging Queue CUPs usage fo | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110068 |  |  | Lifecycle Management Epic | Backlog | E-159124 | E-159124 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-18
Local Enhancement Epic: All For One ART Improvement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110069 |  |  | Local Enhancement Epic | Backlog | E-284022 | E-284022 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: ALL-401107-FedEx ID Expansion | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110070 |  |  | Lifecycle Management Epic | Backlog | E-293678 | E-293678 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-07-18
Lifecycle Management Epic: All-540152 - Lifecycle management of ACCS scanner | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110071 |  |  | Lifecycle Management Epic | Backlog | E-459016 | E-459016 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-10-01 | 2026-01-30
Local Enhancement Epic: Allow CDAS to run based on SEFS Interface | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110072 |  |  | Local Enhancement Epic | Backlog | E-193426 | E-193426 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ALL-SORT - Architecture Process Workflow Refinemen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110073 |  |  | Local Enhancement Epic | Backlog | E-471807 | E-471807 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ALL-SORT- Production and Maintenance Support CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110074 |  |  | Local Enhancement Epic | Backlog | E-473057 | E-473057 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AM System Enhancements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110075 |  |  | Local Enhancement Epic | Backlog | E-175743 | E-175743 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AM System Fixes | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110076 |  |  | Local Enhancement Epic | Backlog | E-175746 | E-175746 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: APAC ACCS Import: SOLAR (Strategic Orange Legacy A | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110077 |  |  | Local Enhancement Epic | Backlog | E-327215 | E-327215 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: APAC-855598-APAC-FIT Duty and Tax DOPS (DRIVE:1213 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110078 |  |  | Local Enhancement Epic | Backlog | E-513507 | E-513507 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Lifecycle Management Epic: Apache JMeter Conversion | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110079 |  |  | Lifecycle Management Epic | Backlog | E-510212 | E-510212 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-08-12
Local Enhancement Epic: APAC-ULD - Speed Cargo - CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110080 |  |  | Local Enhancement Epic | Backlog | E-514119 | E-514119 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-12-31 | 2028-12-29
Local Enhancement Epic: Architectural Runway and Prep for FAAR PFS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110081 |  |  | Local Enhancement Epic | Backlog | E-324946 | E-324946 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-21
Local Enhancement Epic: ASSET Core EAI separation (GFA) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110082 |  |  | Local Enhancement Epic | Backlog | E-476741 | E-476741 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-27 | 2025-03-27
Local Enhancement Epic: AU Business Continuity- FMS/CMS Re-platform | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110083 |  |  | Local Enhancement Epic | Backlog | E-339285 | E-339285 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AU Combine LV Shipments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110084 |  |  | Local Enhancement Epic | Backlog | E-483097 | E-483097 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2027-01-12
Local Enhancement Epic: AU Domestic - PEXa IT Audit and Data Estate | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110085 |  |  | Local Enhancement Epic | Backlog | E-410441 | E-410441 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2025-03-25
Local Enhancement Epic: AU Domestic PAF - Core Enablement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110086 |  |  | Local Enhancement Epic | Backlog | E-408332 | E-408332 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-14
Local Enhancement Epic: AU Domestic PAF - Ops Enablement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110087 |  |  | Local Enhancement Epic | Backlog | E-408333 | E-408333 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-31
Local Enhancement Epic: AU GRISIS Export Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110088 |  |  | Local Enhancement Epic | Backlog | E-412261 | E-412261 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Local Enhancement Epic: AU-440711-ACCS Import-Astra Label Layout Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110089 |  |  | Local Enhancement Epic | Backlog | E-321956 | E-321956 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-08-13
Local Enhancement Epic: AU-SORT - Implementation in AU - CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110090 |  |  | Local Enhancement Epic | Backlog | E-471802 | E-471802 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automated E2E across EU FOPD products | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110091 |  |  | Local Enhancement Epic | Backlog | E-464088 | E-464088 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-27 | 2026-05-29
Local Enhancement Epic: AutoVerify to coexist on same handheld device with | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110092 |  |  | Local Enhancement Epic | Backlog | E-332439 | E-332439 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Aviation Security Update - pre-Drive | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110093 |  |  | Local Enhancement Epic | Backlog | E-293673 | E-293673 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AYO and Clearance Project | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110094 |  |  | Local Enhancement Epic | Backlog | E-513518 | E-513518 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: Azure to AKS/CAL7 Migration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110095 |  |  | Local Enhancement Epic | Backlog | E-187258 | E-187258 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: BAU & Support-CY25 - ANZART | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110096 |  |  | Local Enhancement Epic | Backlog | E-477011 | E-477011 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2025-12-31
Local Enhancement Epic: Blue Bits - Backlog | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110097 |  |  | Local Enhancement Epic | Backlog | E-271125 | E-271125 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Bookies - Protect Purple | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110098 |  |  | Local Enhancement Epic | Backlog | E-201275 | E-201275 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Bookies Server Maintenance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110099 |  |  | Local Enhancement Epic | Backlog | E-270415 | E-270415 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: Build RampScape LaunchPad | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110100 |  |  | Local Enhancement Epic | Backlog | E-351312 | E-351312 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-09-06 | 2025-07-31
Local Enhancement Epic: Building a scalable CI/CD pipeline for Continuous | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110101 |  |  | Local Enhancement Epic | Backlog | E-419601 | E-419601 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Bunker#1A: Improve address quality through AI (i.e | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110102 |  |  | Local Enhancement Epic | Backlog | E-360376 | E-360376 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-06-30
Local Enhancement Epic: Business Management KT, Training, Onboarding | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110103 |  |  | Local Enhancement Epic | Backlog | E-432115 | E-432115 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Business rule engine for EU FOPD Products | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110104 |  |  | Local Enhancement Epic | Backlog | E-437860 | E-437860 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CA FXE Flying Truck Conveyance eManifest requireme | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110105 |  |  | Local Enhancement Epic | Backlog | E-40524 | E-40524 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CAGE MVP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110106 |  |  | Local Enhancement Epic | Backlog | E-80674 | E-80674 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CALI enhancements to retire Argentina | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110107 |  |  | Local Enhancement Epic | Backlog | E-513136 | E-513136 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Canada Checklist Edit | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110108 |  |  | Local Enhancement Epic | Backlog | E-465983 | E-465983 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-06-10
Local Enhancement Epic: Carrier Tiering | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110109 |  |  | Local Enhancement Epic | Backlog | E-433793 | E-433793 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-04-01
Lifecycle Management Epic: CCP Suite Technical Debt Reduction and Architectur | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110110 |  |  | Lifecycle Management Epic | Backlog | E-504109 | E-504109 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-27
Local Enhancement Epic: CDAS - Added Capacity (Calculation and Payment) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110111 |  |  | Local Enhancement Epic | Backlog | E-371484 | E-371484 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: CDAS CNDA/RFI Modifications | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110112 |  |  | Local Enhancement Epic | Backlog | E-211167 | E-211167 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: CDAS Contract Admin - Amendment Process Design | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110113 |  |  | Local Enhancement Epic | Backlog | E-439971 | E-439971 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CDAS to receive FAMIS data for task codes 10 and 1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110114 |  |  | Local Enhancement Epic | Backlog | E-417116 | E-417116 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-05
Local Enhancement Epic: Clearance Regulatory ART Bucket Features | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110115 |  |  | Local Enhancement Epic | Backlog | E-182290 | E-182290 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Clearance Reimagine ART Bucket Features | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110116 |  |  | Local Enhancement Epic | Backlog | E-182291 | E-182291 |  |  |  |  | 2 | 0 |  | 2 | No
Local Enhancement Epic: Closing Sort - Research and Development/R&D team E | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110117 |  |  | Local Enhancement Epic | Backlog | E-437501 | E-437501 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-01-01 | 2026-12-31
Local Enhancement Epic: CLR - TT Team Daredevil Enhance Tradetools HS sear | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110118 |  |  | Local Enhancement Epic | Backlog | E-448925 | E-448925 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-01 | 2027-01-19
Local Enhancement Epic: CLR-TT: Screen EEI Data in iReg | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110119 |  |  | Local Enhancement Epic | Backlog | E-512777 | E-512777 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CLR-TT: IT Support: InfoSec Compliant Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110120 |  |  | Local Enhancement Epic | Backlog | E-447910 | E-447910 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-21 | 2026-11-09
Local Enhancement Epic: CLR-TT: IT Support: Production Hardening for Trad | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110121 |  |  | Local Enhancement Epic | Backlog | E-447905 | E-447905 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-28 | 2026-06-02
Local Enhancement Epic: CLR-TT: IT Support: Production Hardening for Trad | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110122 |  |  | Local Enhancement Epic | Backlog | E-512193 | E-512193 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-08-19
Local Enhancement Epic: CLR-TT: IT Support: Production Support and defect | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110123 |  |  | Local Enhancement Epic | Backlog | E-447908 | E-447908 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-21 | 2026-06-09
Local Enhancement Epic: CLR-TT: Policy Grid Exceptions Management Work | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110124 |  |  | Local Enhancement Epic | Backlog | E-436628 | E-436628 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-12
Local Enhancement Epic: CLR-TT: Policy Grid Regression Testing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110125 |  |  | Local Enhancement Epic | Backlog | E-512963 | E-512963 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-17 | 2025-11-07
Local Enhancement Epic: CMS IMAGE Users Provisioning | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110126 |  |  | Local Enhancement Epic | Backlog | E-477010 | E-477010 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CN-562906-[NonTrade]-ACCS-SZX IB and OB declare to | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110127 |  |  | Local Enhancement Epic | Backlog | E-442225 | E-442225 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2024-10-22
Local Enhancement Epic: CN-849846-[expressMFT]-Declare Express MFT (?????? | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110128 |  |  | Local Enhancement Epic | Done | E-502031 | E-502031 | 4: L | 2025-08-15 | 2025-08-15 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-15 | 2025-08-15
Local Enhancement Epic: CN-SORT - 851775-Implementation in CANIP - CY25 | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110129 |  |  | Local Enhancement Epic | Backlog | E-471804 | E-471804 |  |  |  |  | 0 | 0 |  | 0 | Yes | 2024-12-31 | 2025-12-31
Local Enhancement Epic: Common KLO CY24 - NPOE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110130 |  |  | Local Enhancement Epic | Backlog | E-399735 | E-399735 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-22
Local Enhancement Epic: Common Portal - ASN Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110131 |  |  | Local Enhancement Epic | Backlog | E-243632 | E-243632 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Common Portal - Facility Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110132 |  |  | Local Enhancement Epic | Backlog | E-137739 | E-137739 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Common Portal - Item Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110133 |  |  | Local Enhancement Epic | Backlog | E-139240 | E-139240 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Compliance Work Speed Racer CY 24 PI5- CY25 PI2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110134 |  |  | Local Enhancement Epic | Backlog | E-456469 | E-456469 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-10
Local Enhancement Epic: CONDOR Data Center Application Retirement - local | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110135 |  |  | Local Enhancement Epic | Build | E-209127 | E-209127 |  | 2025-07-01 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2025-03-31 | 2025-07-01
Local Enhancement Epic: Condor PE#2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110136 |  |  | Local Enhancement Epic | Build | E-270222 | E-270222 | 4: L | 2025-07-01 |  | 84% | 25 | 21 | 4 | 0 | No | 2025-08-20 | 2026-01-20 | 2025-07-01
Local Enhancement Epic: Contract Admin - Expiration Date Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110137 |  |  | Local Enhancement Epic | Backlog | E-371306 | E-371306 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Contract Administration Module (Drive 409) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110138 |  |  | Local Enhancement Epic | Backlog | E-204550 | E-204550 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-05 | 2028-09-08
Local Enhancement Epic: Conveyance ART - CY 25 Architectural & NFRs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110139 |  |  | Local Enhancement Epic | Backlog | E-463002 | E-463002 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-13
Local Enhancement Epic: Conveyance ART - CY 25 Protect Purple | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110140 |  |  | Local Enhancement Epic | Backlog | E-467218 | E-467218 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-14
Local Enhancement Epic: Country Go Live Support | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110141 |  |  | Local Enhancement Epic | Backlog | E-203353 | E-203353 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Create a framework to facillitate integration of 3 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110142 |  |  | Local Enhancement Epic | Backlog | E-156364 | E-156364 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Crew Pay Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110143 |  |  | Local Enhancement Epic | Backlog | E-98359 | E-98359 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-05-29 | 2026-05-29
Local Enhancement Epic: Crew Stairs Enhancements/Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110144 |  |  | Local Enhancement Epic | Backlog | E-499020 | E-499020 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2027-04-07
Local Enhancement Epic: CSPA: Customer Stop Profile Attribute | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110145 |  |  | Local Enhancement Epic | Backlog | E-435366 | E-435366 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2025-07-31
Local Enhancement Epic: Customer Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110146 |  |  | Local Enhancement Epic | Backlog | E-83511 | E-83511 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CY 25 FORGE, FLM, PTD & XTRA Mile Small High Value | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110147 |  |  | Local Enhancement Epic | Backlog | E-467219 | E-467219 |  |  |  |  | 2 | 0 |  | 2 | No | 2025-01-22 | 2026-01-21
Lifecycle Management Epic: CY2025 Operation Solutions - Production Support | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110148 |  |  | Lifecycle Management Epic | Backlog | E-471530 | E-471530 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY2025 Operations Solutions LCM - Compliance | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110149 |  |  | Lifecycle Management Epic | Backlog | E-471531 | E-471531 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY2025 Operations Solutions LCM - Hardware | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110150 |  |  | Lifecycle Management Epic | Backlog | E-471538 | E-471538 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CY25 FORGE QA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110151 |  |  | Local Enhancement Epic | Backlog | E-476220 | E-476220 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-01 | 2026-10-28
Lifecycle Management Epic: CY25 TSPA Annual Enhancements | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110152 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-481599 | E-481599 |  | 2025-07-23 |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2025-11-05 | 2025-07-23
Local Enhancement Epic: Debrief MMP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110153 |  |  | Local Enhancement Epic | Backlog | E-349104 | E-349104 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2028-04-21
Local Enhancement Epic: Decommissioning of the NTAUS2HUB1/HUB2 SMTP Servic | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110154 |  |  | Local Enhancement Epic | Backlog | E-345430 | E-345430 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Defect Management | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110155 |  |  | Local Enhancement Epic | Backlog | E-126712 | E-126712 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Detect/handle multiple ShareIDs for the same compa | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110156 |  |  | Local Enhancement Epic | Backlog | E-432045 | E-432045 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-27 | 2026-05-29
Local Enhancement Epic: DevSecOps_Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110157 |  |  | Local Enhancement Epic | Backlog | E-40574 | E-40574 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: DG by Road Europe | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110158 |  |  | Local Enhancement Epic | Backlog | E-373502 | E-373502 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-20 | 2025-10-20
Local Enhancement Epic: DG Nav Development | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110159 |  |  | Local Enhancement Epic | Backlog | E-342397 | E-342397 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-15 | 2026-01-15
Local Enhancement Epic: DG News alert eAcknowledge | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110160 |  |  | Local Enhancement Epic | Backlog | E-361367 | E-361367 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-12-31 | 2026-12-31
Local Enhancement Epic: DG Production Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110161 |  |  | Local Enhancement Epic | Backlog | E-143206 | E-143206 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-07-23
Local Enhancement Epic: DG Spill Incident System | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110162 |  |  | Local Enhancement Epic | Backlog | E-197830 | E-197830 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Digital apps enhancements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110163 |  |  | Local Enhancement Epic | Backlog | E-284733 | E-284733 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DIRE Replatform to Ab-Initio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110164 |  |  | Local Enhancement Epic | Backlog | E-440074 | E-440074 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2029-01-09
Local Enhancement Epic: DRIVE # 88701 - One FedEx Accident Reporting Syste | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110165 |  |  | Local Enhancement Epic | Backlog | E-465826 | E-465826 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-08-12
Lifecycle Management Epic: DSO-128571-CLEARANCE MAINTENANCE | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110166 |  |  | Lifecycle Management Epic | Backlog | E-293371 | E-293371 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-01-15
Lifecycle Management Epic: EAI 4990 Sort Maintenance Modernization | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110167 |  |  | Lifecycle Management Epic | Backlog | E-482775 | E-482775 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-08-29
Local Enhancement Epic: EBC Refactor needed for Argentina online invoicing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110168 |  |  | Local Enhancement Epic | Backlog | E-513134 | E-513134 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EDP N2.0 2.1 - Updates to Ancillary Demand Plan Fu | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110169 |  |  | Local Enhancement Epic | Build | E-366046 | E-366046 |  | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: EDTW Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110170 |  |  | Local Enhancement Epic | Backlog | E-461628 | E-461628 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EFORMz Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110171 |  |  | Local Enhancement Epic | Backlog | E-428736 | E-428736 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-03-26
Local Enhancement Epic: ELSP - Detroit Sort Expansion | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110172 |  |  | Local Enhancement Epic | Done | E-418518 | E-418518 | 5: XL | 2025-09-10 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-09-10 | 2025-09-10
Local Enhancement Epic: ELSP - MEM Secondary 25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110173 |  |  | Local Enhancement Epic | Backlog | E-418511 | E-418511 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-10-31
Local Enhancement Epic: Enable Datawork teams to create Spotlight and Meda | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110174 |  |  | Local Enhancement Epic | Backlog | E-481585 | E-481585 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-09-11 | 2026-12-31
Local Enhancement Epic: Enable Economy Barcode support within POF | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110175 |  |  | Local Enhancement Epic | Backlog | E-507984 | E-507984 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enable SenseAware in AU with AU LEO and FMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110176 |  |  | Local Enhancement Epic | Backlog | E-453394 | E-453394 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-01 | 2026-02-26
Local Enhancement Epic: Enhancements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110177 |  |  | Local Enhancement Epic | Backlog | E-171514 | E-171514 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ePLP | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110178 |  |  | Local Enhancement Epic | Backlog | E-176581 | E-176581 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Ericsson UAT | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110179 |  |  | Local Enhancement Epic | Backlog | E-298921 | E-298921 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EU00017 - Improve inbound Volume Visibility | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110180 |  |  | Local Enhancement Epic | Build | E-134472 | E-134472 | 5: XL | 2025-07-02 |  |  | 42 | 0 | 42 | 0 | No | 2024-07-22 | 2025-12-31 | 2025-07-02
Local Enhancement Epic: EU-Clearance DRIVE ABACUS enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110181 |  |  | Local Enhancement Epic | Backlog | E-373149 | E-373149 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-04-13
Local Enhancement Epic: EU-Sort ART: Hub Stack BAU and Local Demand. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110182 |  |  | Local Enhancement Epic | Backlog | E-217030 | E-217030 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-21
Local Enhancement Epic: EU-Sort ART: Others BAU and Local Demand. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110183 |  |  | Local Enhancement Epic | Backlog | E-217362 | E-217362 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-22
Local Enhancement Epic: EU-Sort ART: Sort Stack BAU and Local Demand. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110184 |  |  | Local Enhancement Epic | Backlog | E-217239 | E-217239 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-22
Local Enhancement Epic: EU-Sort ART: Transition Knowledge Transfer KT 2024 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110185 |  |  | Local Enhancement Epic | Backlog | E-463108 | E-463108 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-13 | 2025-02-28
Local Enhancement Epic: EU-Sort: Hub Solutions BAU and Local Demand. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110186 |  |  | Local Enhancement Epic | Backlog | E-217324 | E-217324 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-22
Lifecycle Management Epic: eYMS GitHub Actions Migration | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110187 |  |  | Lifecycle Management Epic | Backlog | E-502105 | E-502105 |  |  |  |  | 0 | 0 |  | 0 | No | 2023-08-31 | 2025-10-29
Lifecycle Management Epic: eYMS Test Automation | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110188 |  |  | Lifecycle Management Epic | Backlog | E-502115 | E-502115 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-07-13
Local Enhancement Epic: F&LM Address and Geocoding Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110189 |  |  | Local Enhancement Epic | Backlog | E-156959 | E-156959 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-23
Local Enhancement Epic: FAA Login Compliance: PurpleID Authentication | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110190 |  |  | Local Enhancement Epic | Backlog | E-502149 | E-502149 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-20
Local Enhancement Epic: FAAR ART API/Ab Initio Defects | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110191 |  |  | Local Enhancement Epic | Backlog | E-463774 | E-463774 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2027-12-31
Local Enhancement Epic: FAAR Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110192 |  |  | Local Enhancement Epic | Backlog | E-313928 | E-313928 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-08-24
Local Enhancement Epic: FAAR Transition to Accenture | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110193 |  |  | Local Enhancement Epic | Backlog | E-472294 | E-472294 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-01 | 2025-04-01
Local Enhancement Epic: Falcons Business Requested Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110194 |  |  | Local Enhancement Epic | Backlog | E-384077 | E-384077 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Falcons Ensure Regulatory Compliance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110195 |  |  | Local Enhancement Epic | Backlog | E-384082 | E-384082 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Falcons Team Backlog | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110196 |  |  | Local Enhancement Epic | Backlog | E-316773 | E-316773 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-11-11
Local Enhancement Epic: FAMIS Mainframe Migration Move - Legacy | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110197 |  |  | Local Enhancement Epic | Build | E-106098 | E-106098 | 5: XL | 2025-08-28 |  |  | 1 | 0 | 1 | 0 | No |  |  | 2025-08-28
Local Enhancement Epic: FAMIS-R Defects - CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110198 |  |  | Local Enhancement Epic | Backlog | E-471892 | E-471892 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-20
Local Enhancement Epic: FAMISR Hardening | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110199 |  |  | Local Enhancement Epic | Backlog | E-475323 | E-475323 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2026-01-20
Local Enhancement Epic: FAMIS-R Innovation Activities | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110200 |  |  | Local Enhancement Epic | Backlog | E-497530 | E-497530 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FAMIS-R Production Support CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110201 |  |  | Local Enhancement Epic | Backlog | E-463221 | E-463221 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-20
Local Enhancement Epic: FAMIS-R Realignments and Location Maintenance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110202 |  |  | Local Enhancement Epic | Backlog | E-446220 | E-446220 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-20
Local Enhancement Epic: FAMIS-R Test Environment Support CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110203 |  |  | Local Enhancement Epic | Backlog | E-475330 | E-475330 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-20
Local Enhancement Epic: FBC Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110204 |  |  | Local Enhancement Epic | Backlog | E-208857 | E-208857 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-27
Local Enhancement Epic: FedEx Cross Border | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110205 |  |  | Local Enhancement Epic | Backlog | E-175748 | E-175748 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FedEx Fueling - Operations Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110206 |  |  | Lifecycle Management Epic | Backlog | E-501963 | E-501963 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-12-31
Local Enhancement Epic: FedEx Ground P&D Portal | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110207 |  |  | Local Enhancement Epic | Backlog | E-412549 | E-412549 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: Pilot Mobility (Vector-Wrench-Compass) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110208 |  |  | Local Enhancement Epic | Build | E-504043 | E-504043 |  | 2025-09-10 |  | 40% | 10 | 4 | 6 | 0 | No | 2026-03-30 | 2026-03-31 | 2025-09-10
Local Enhancement Epic: Fiscal Year Analysis and Modifications | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110209 |  |  | Local Enhancement Epic | Backlog | E-485722 | E-485722 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: Fleet Resubstantiation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110210 |  |  | Local Enhancement Epic | Backlog | E-477632 | E-477632 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2025-10-30 | 2025-10-30
Local Enhancement Epic: FLM AMS Phase II | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110211 |  |  | Local Enhancement Epic | Backlog | E-458898 | E-458898 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-11 | 2026-12-02
Local Enhancement Epic: FLM AMS Phase III | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110212 |  |  | Local Enhancement Epic | Backlog | E-458899 | E-458899 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-11-12 | 2026-08-18
Lifecycle Management Epic: FMA - Adopt GitHub Actions | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110213 |  |  | Lifecycle Management Epic | Backlog | E-507677 | E-507677 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-24 | 2025-10-17
Local Enhancement Epic: FMA - Defect Resolution | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110214 |  |  | Local Enhancement Epic | Backlog | E-508155 | E-508155 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FMA - UI/UX Design Standardization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110215 |  |  | Local Enhancement Epic | Backlog | E-507672 | E-507672 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-04 | 2025-08-21
Local Enhancement Epic: FOCUS Retirement | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110216 |  |  | Local Enhancement Epic | Backlog | E-516238 | E-516238 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FOPD FRO | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110217 |  |  | Local Enhancement Epic | Backlog | E-418947 | E-418947 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-10-31
Local Enhancement Epic: FORGE - GPDE on hold items | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110218 |  |  | Local Enhancement Epic | Backlog | E-497510 | E-497510 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-29 | 2026-01-20
Local Enhancement Epic: FORGE Implementation in EU | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110219 |  |  | Local Enhancement Epic | Backlog | E-409848 | E-409848 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2026-04-30
Local Enhancement Epic: FOTC App Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110220 |  |  | Local Enhancement Epic | Backlog | E-332131 | E-332131 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FPS / ACARS / FOIS / FRTB - Planned Work Items | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110221 |  |  | Local Enhancement Epic | Backlog | E-469222 | E-469222 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-07-01 | 2026-06-16
Local Enhancement Epic: FR-GEF-Gap analysis | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110222 |  |  | Local Enhancement Epic | Backlog | E-326990 | E-326990 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FSC - Portfolio Templates | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110223 |  |  | Local Enhancement Epic | Backlog | E-211978 | E-211978 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXE-AirOps-AIR-CDM-CHARTER-FOIS-GURU-SWIM - planne | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110224 |  |  | Local Enhancement Epic | Backlog | E-105602 | E-105602 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-03-30
Local Enhancement Epic: FXE-AirOps-AIR-CDM-CHARTER-FOIS-GURU-SWIM - Unplan | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110225 |  |  | Local Enhancement Epic | Backlog | E-119353 | E-119353 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-08-28 | 2026-08-28
Local Enhancement Epic: FXE-EU-Linehaul YOS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110226 |  |  | Local Enhancement Epic | Backlog | E-246149 | E-246149 |  |  |  |  | 2 | 0 |  | 2 | No | 2023-04-17 | 2037-01-01
Local Enhancement Epic: FXF - 602 DB2 Rehost Repoint Applications and Test | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110227 |  |  | Local Enhancement Epic | Build | E-178833 | E-178833 | 3: M | 2025-08-05 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-08-05
Local Enhancement Epic: FXF - 625 CONDOR Application Migration Factory Wav | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110228 |  |  | Local Enhancement Epic | Build | E-206184 | E-206184 | 3: M | 2025-07-02 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-07-02
Local Enhancement Epic: FXG-GSI Planning Zip Code Maintenance Modernizatio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110229 |  |  | Local Enhancement Epic | Backlog | E-414872 | E-414872 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-24 | 2025-10-28
Local Enhancement Epic: FXL – CX – TradeNet to METL Migration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110230 |  |  | Local Enhancement Epic | Backlog | E-501989 | E-501989 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-20 | 2026-12-31
Local Enhancement Epic: FXL - FTN-SS - IT OPS Excellence_FY25 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110231 |  |  | Local Enhancement Epic | Backlog | E-426008 | E-426008 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - FTN-SS - Keep the Lights On _FY25 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110232 |  |  | Local Enhancement Epic | Backlog | E-426005 | E-426005 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - SC - FLARE - Forward Logistics | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110233 |  |  | Local Enhancement Epic | Launch & Evaluate | E-142735 | E-142735 |  | 2025-07-08 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-08
Local Enhancement Epic: FXL - SC - FLARE - Reverse Logics | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110234 |  |  | Local Enhancement Epic | Launch & Evaluate | E-112756 | E-112756 |  | 2025-07-08 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-08
Local Enhancement Epic: FXL - TBS - Bill Trust | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110235 |  |  | Local Enhancement Epic | Backlog | E-516067 | E-516067 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-16 | 2025-10-14
Local Enhancement Epic: FXL - TBS - CW Downstream Feeds - Continued Integr | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110236 |  |  | Local Enhancement Epic | Backlog | E-516135 | E-516135 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2026-03-31
Local Enhancement Epic: FXL - TBS - Project Fusion | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110237 |  |  | Local Enhancement Epic | Backlog | E-504071 | E-504071 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Lifecycle Management Epic: FXL-FTN-SS-DBA-Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110238 |  |  | Lifecycle Management Epic | Backlog | E-499607 | E-499607 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-27 | 2026-05-29
Lifecycle Management Epic: FY26 AFS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110239 |  |  | Lifecycle Management Epic | Backlog | E-517367 | E-517367 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 CARS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110240 |  |  | Lifecycle Management Epic | Backlog | E-517365 | E-517365 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 GRIPS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110241 |  |  | Lifecycle Management Epic | Backlog | E-517368 | E-517368 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 LOAD PLAN Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110242 |  |  | Lifecycle Management Epic | Backlog | E-517370 | E-517370 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 PEGASUS Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110243 |  |  | Lifecycle Management Epic | Backlog | E-517366 | E-517366 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 Phoenix Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110244 |  |  | Lifecycle Management Epic | Backlog | E-516989 | E-516989 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 PI3 EPART Java & Weblogic Upgrades | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110245 |  |  | Lifecycle Management Epic | Backlog | E-517391 | E-517391 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26 SCO Surface International ¦ Production Suppor | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110246 |  |  | Lifecycle Management Epic | Done | E-514847 | E-514847 | 3: M | 2025-07-09 | 2025-09-10 |  | 0 | 0 |  | 0 | No |  |  | 2025-07-09 | 2025-09-10
Lifecycle Management Epic: FY26 SLOT Mgt Sys Production Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110247 |  |  | Lifecycle Management Epic | Backlog | E-517369 | E-517369 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_LCM_IRG ATLAS Publication Improvements | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110248 |  |  | Lifecycle Management Epic | Backlog | E-516937 | E-516937 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_LCM_IRG Quality and Supportability | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110249 |  |  | Lifecycle Management Epic | Backlog | E-516938 | E-516938 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI3_Platforms_LCM_SSRT EAI 5158- Modernizing | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110250 |  |  | Lifecycle Management Epic | Done | E-518204 | E-518204 | 1: XS | 2025-07-09 | 2025-09-08 |  | 0 | 0 |  | 0 | No |  |  | 2025-07-09 | 2025-09-08
Lifecycle Management Epic: FY26_SCO_EU Sort_Knowledge Transfers | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110251 |  |  | Lifecycle Management Epic | Build | E-519618 | E-519618 |  | 2025-07-01 |  | 80% | 5 | 4 | 1 | 0 | No | 2025-06-11 | 2026-06-09 | 2025-07-01
Lifecycle Management Epic: FY26_SCO_MEISA Clearance Production Support India | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110252 |  |  | Lifecycle Management Epic | Backlog | E-519603 | E-519603 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2026-05-29
Local Enhancement Epic: Gemini East US 2 PROD Database | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110253 |  |  | Local Enhancement Epic | Backlog | E-458556 | E-458556 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-02-05 | 2025-04-15
Local Enhancement Epic: Geocoding EPIC 2 - Improve Address Data Quality at | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110254 |  |  | Local Enhancement Epic | Backlog | E-196890 | E-196890 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Geocoding EPIC 5 - Enhance PUD operations through | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110255 |  |  | Local Enhancement Epic | Backlog | E-293135 | E-293135 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-07-24
Local Enhancement Epic: GFA Application Enhancements (SHV) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110256 |  |  | Local Enhancement Epic | Backlog | E-465145 | E-465145 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-09-11 | 2026-10-28
Local Enhancement Epic: Goal Diggers - Defect Resolution | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110257 |  |  | Local Enhancement Epic | Backlog | E-508156 | E-508156 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GTA Fully Qualified HS Codes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110258 |  |  | Local Enhancement Epic | Backlog | E-446766 | E-446766 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-13 | 2025-12-10
Local Enhancement Epic: Healthcare | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110259 |  |  | Local Enhancement Epic | Backlog | E-171507 | E-171507 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HK-566324-Use acknowledgment ID to get constraint | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110260 |  |  | Local Enhancement Epic | Backlog | E-458683 | E-458683 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: HK-854718-TSW | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110261 |  |  | Local Enhancement Epic | Backlog | E-482446 | E-482446 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: HK-SORT - Implementation in HKG - CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110262 |  |  | Local Enhancement Epic | Backlog | E-471803 | E-471803 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-12-31 | 2025-03-31
Lifecycle Management Epic: Honeywell CT47 (Common Config) Migration | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110263 |  |  | Lifecycle Management Epic | Backlog | E-502120 | E-502120 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-29
Local Enhancement Epic: I.T. Enabler | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110264 |  |  | Local Enhancement Epic | Backlog | E-203968 | E-203968 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ID0216 - GPN Origin-Destination Split Capability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110265 |  |  | Local Enhancement Epic | Backlog | E-171480 | E-171480 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-29
Local Enhancement Epic: iD2667 - Descartes Visual Compliance Implementatio | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110266 |  |  | Local Enhancement Epic | Backlog | E-297913 | E-297913 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ID-695021-EXPORT CEISA CGK and DPS OB | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110267 |  |  | Local Enhancement Epic | Backlog | E-458996 | E-458996 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ID-726465-EXP BTH FTZ of CEISA40 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110268 |  |  | Local Enhancement Epic | Backlog | E-469492 | E-469492 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ID-726467-IMP C5 MES & BPN host to host of CEISA 4 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110269 |  |  | Local Enhancement Epic | Backlog | E-470893 | E-470893 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Implement all business transactions in Rampscape | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110270 |  |  | Local Enhancement Epic | Backlog | E-479757 | E-479757 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-02 | 2026-01-30
Local Enhancement Epic: Implementation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110271 |  |  | Local Enhancement Epic | Backlog | E-120264 | E-120264 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Improve stop consolidation and address quality thr | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110272 |  |  | Local Enhancement Epic | Backlog | E-452777 | E-452777 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2025-06-20
Local Enhancement Epic: Inbound Stock | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110273 |  |  | Local Enhancement Epic | Backlog | E-83507 | E-83507 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Information Factory & SAS Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110274 |  |  | Local Enhancement Epic | Backlog | E-201126 | E-201126 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: Infrastructure Lifecycle Management (ILCM) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110275 |  |  | Lifecycle Management Epic | Backlog | E-464812 | E-464812 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2026-11-10
Lifecycle Management Epic: Infrastructure Maintenance and Requests | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110276 |  |  | Lifecycle Management Epic | Backlog | E-501945 | E-501945 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-12-31
Local Enhancement Epic: Innovation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110277 |  |  | Local Enhancement Epic | Backlog | E-107571 | E-107571 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Innovation and Planning | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110278 |  |  | Local Enhancement Epic | Backlog | E-478399 | E-478399 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2027-12-31
Local Enhancement Epic: Integration with eCIS system (Credit facility) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110279 |  |  | Local Enhancement Epic | Backlog | E-513516 | E-513516 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Invoicing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110280 |  |  | Local Enhancement Epic | Backlog | E-112359 | E-112359 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Invoicing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110281 |  |  | Local Enhancement Epic | Backlog | E-83512 | E-83512 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ISPA Enhancements – ISPA Redesign leftover work | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110282 |  |  | Local Enhancement Epic | Backlog | E-216553 | E-216553 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2025-11-05
Local Enhancement Epic: ITAR Closeout GAP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110283 |  |  | Local Enhancement Epic | Backlog | E-448629 | E-448629 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-08-23 | 2025-03-31
Local Enhancement Epic: Jeppesen Rostering App Onboarding | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110284 |  |  | Local Enhancement Epic | Backlog | E-426776 | E-426776 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-03-23 | 2026-06-30
Local Enhancement Epic: JP-SORT-??????- Implementation in NRT - CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110285 |  |  | Local Enhancement Epic | Backlog | E-514117 | E-514117 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-12-31 | 2026-12-31
Local Enhancement Epic: JP-ULD - LQA Utilization Improvement - CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110286 |  |  | Local Enhancement Epic | Backlog | E-471796 | E-471796 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-01 | 2026-10-09
Local Enhancement Epic: Kitting & De-kitting | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110287 |  |  | Local Enhancement Epic | Backlog | E-83509 | E-83509 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: KLO CY25 - Dock and Yard | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110288 |  |  | Local Enhancement Epic | Backlog | E-457697 | E-457697 |  |  |  |  | 1 | 0 |  | 1 | No | 2024-08-21 | 2027-03-12
Local Enhancement Epic: KLO CY25 - P&D Plan & Prepare | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110289 |  |  | Local Enhancement Epic | Backlog | E-472975 | E-472975 |  |  |  |  | 0 | 0 |  | 0 | No | 2012-08-13 | 2026-04-23
Lifecycle Management Epic: KLO CY25 - TVS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110290 |  |  | Lifecycle Management Epic | Backlog | E-472357 | E-472357 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-28
Local Enhancement Epic: KLO CY25 (PIs 2-5) - Feature Backlog | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110291 |  |  | Local Enhancement Epic | Launch & Evaluate | E-485811 | E-485811 |  | 2025-07-01 |  | 52.94% | 17 | 9 | 8 | 0 | No |  |  | 2025-07-01
Lifecycle Management Epic: KLO CY25 Unplanned - TVS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110292 |  |  | Lifecycle Management Epic | Backlog | E-475714 | E-475714 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-28
Local Enhancement Epic: KLO Sort Closing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110293 |  |  | Local Enhancement Epic | Backlog | E-447372 | E-447372 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: KR -209894-ACCS Export: new customs requirements f | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110294 |  |  | Local Enhancement Epic | Backlog | E-115097 | E-115097 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-01
Local Enhancement Epic: KR-120144-ACCS Export: changes for GOVCBRRR5 (Pend | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110295 |  |  | Local Enhancement Epic | Backlog | E-77687 | E-77687 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-01
Local Enhancement Epic: KR-167299-KR Import: changes for RegistrationNatio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110296 |  |  | Local Enhancement Epic | Backlog | E-78129 | E-78129 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-01 | 2026-06-01
Local Enhancement Epic: KR-191473-ACCS Import: new EDI specification for F | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110297 |  |  | Local Enhancement Epic | Backlog | E-292704 | E-292704 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-22 | 2024-12-30
Local Enhancement Epic: KR-51182-KR ACCS Import: changes for GOVCBR934 (Pe | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110298 |  |  | Local Enhancement Epic | Backlog | E-74855 | E-74855 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-01
Local Enhancement Epic: KR-566212-KR Export AirPath+ Connection | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110299 |  |  | Local Enhancement Epic | Backlog | E-449075 | E-449075 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: KR-570677-KR Import Mass upload of Inf-B/F declara | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110300 |  |  | Local Enhancement Epic | Backlog | E-445635 | E-445635 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2025-10-17
Local Enhancement Epic: KR-761818-KR Import_Suspicious Goods Inspection an | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110301 |  |  | Local Enhancement Epic | Backlog | E-471153 | E-471153 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-03-31
Local Enhancement Epic: KR-89088-KR ACCS Import: new EDI for CN-KR FTA (Re | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110302 |  |  | Local Enhancement Epic | Backlog | E-74972 | E-74972 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-01
Local Enhancement Epic: KSA clearance and sort transition with automation | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110303 |  |  | Local Enhancement Epic | Backlog | E-507842 | E-507842 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC - INCAS Plus - GEMINI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110304 |  |  | Local Enhancement Epic | Backlog | E-475182 | E-475182 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-09 | 2025-06-17
Local Enhancement Epic: LAC - LDP3/CALI - FedEx Logo Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110305 |  |  | Local Enhancement Epic | Backlog | E-433531 | E-433531 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-12
Local Enhancement Epic: LAC eBillingController (EBC) Costa Rica eInvoicing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110306 |  |  | Local Enhancement Epic | Backlog | E-472580 | E-472580 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-29 | 2025-06-02
Local Enhancement Epic: LAC eBillingController (EBC) Costa Rica eInvoicing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110307 |  |  | Local Enhancement Epic | Backlog | E-484299 | E-484299 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: LAC eBillingController (EBC) Costa Rica LIN Refact | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110308 |  |  | Local Enhancement Epic | Backlog | E-474344 | E-474344 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-29 | 2025-04-08
Lifecycle Management Epic: LAC- FGC Enhancements to support Post COLO Migrati | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110309 |  |  | Lifecycle Management Epic | Backlog | E-213963 | E-213963 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: LAC -INCAS PLUS - Enterprise Exchange Rate Servic | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110310 |  |  | Local Enhancement Epic | Backlog | E-269924 | E-269924 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-02-21
Local Enhancement Epic: LAC INCAS Plus Costa Rica eInvoicing 4.4 Release 2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110311 |  |  | Local Enhancement Epic | Launch & Evaluate | E-474644 | E-474644 | 3: M | 2025-07-23 |  |  | 0 | 0 |  | 0 | No | 2025-01-29 | 2025-04-08 | 2025-07-23
Local Enhancement Epic: LAC INCAS Plus Costa Rica eInvoicing updates Relea | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110312 |  |  | Local Enhancement Epic | Backlog | E-484804 | E-484804 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC- INCAS-PLUS - FGC - INCAS REST Service | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110313 |  |  | Local Enhancement Epic | Backlog | E-463511 | E-463511 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-13 | 2025-06-17
Lifecycle Management Epic: LAC-3-AW-VisualDeclarant /LAC-3-CU-VisualDeclarant | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110314 |  |  | Lifecycle Management Epic | Backlog | E-463052 | E-463052 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-11-13 | 2025-06-24
Local Enhancement Epic: LAC-3-FDXTM - Breco Enable CIOT Process - Linehaul | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110315 |  |  | Local Enhancement Epic | Backlog | E-358448 | E-358448 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-11-28
Lifecycle Management Epic: LAC-3-FDXTM-INFOSEC Mandatory Controls-Contract Tr | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110316 |  |  | Lifecycle Management Epic | Backlog | E-197487 | E-197487 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: LAC-3-Retail POS Implement Bank Reconciliation fun | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110317 |  |  | Local Enhancement Epic | Backlog | E-508220 | E-508220 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2026-01-30
Local Enhancement Epic: LAC-3-RetailPOS - Implement Prepaid Air Way Bill | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110318 |  |  | Local Enhancement Epic | Backlog | E-508083 | E-508083 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-23 | 2025-08-29
Local Enhancement Epic: LAC-3-RetailPOS - Expansion: Dominican Republic Im | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110319 |  |  | Local Enhancement Epic | Backlog | E-327296 | E-327296 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-3-RetailPOS -Chile Expansion: FTC as interim s | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110320 |  |  | Local Enhancement Epic | Launch & Evaluate | E-478520 | E-478520 | 3: M | 2025-07-22 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-22
Lifecycle Management Epic: LAC-3-Retail-POS Defect / Production Break-Fixes | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110321 |  |  | Lifecycle Management Epic | Backlog | E-508284 | E-508284 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-09-01 | 2027-09-01
Local Enhancement Epic: LAC42 Argentina MVP Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110322 |  |  | Local Enhancement Epic | Backlog | E-513131 | E-513131 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC42 Chile Domestic Enablement Credit Note MVP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110323 |  |  | Local Enhancement Epic | Launch & Evaluate | E-414423 | E-414423 | 3: M | 2025-07-07 |  |  | 0 | 0 |  | 0 | No | 2024-10-21 | 2025-01-31 | 2025-07-07
Local Enhancement Epic: LAC42 Enable Argentina | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110324 |  |  | Local Enhancement Epic | Backlog | E-350951 | E-350951 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC42 Enable PPFS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110325 |  |  | Local Enhancement Epic | Backlog | E-512852 | E-512852 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC42 MEXICO MVP Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110326 |  |  | Local Enhancement Epic | Backlog | E-467276 | E-467276 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-13 | 2025-12-31
Local Enhancement Epic: LAC42 System Enhancements for Expansion | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110327 |  |  | Local Enhancement Epic | Backlog | E-513097 | E-513097 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: LAC-ALPS3 Application Decommission | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110328 |  |  | Lifecycle Management Epic | Backlog | E-508312 | E-508312 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-CALI - Add Regulatory Message on PDF Documents | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110329 |  |  | Local Enhancement Epic | Backlog | E-508286 | E-508286 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-CALI-PLUS Architectural Runway | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110330 |  |  | Local Enhancement Epic | Backlog | E-516507 | E-516507 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2025-06-20
Local Enhancement Epic: LAC-eBillingController (EBC) - Honduras Ability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110331 |  |  | Local Enhancement Epic | Backlog | E-483899 | E-483899 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-eBillingController (EBC) - Architectural Runwa | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110332 |  |  | Local Enhancement Epic | Backlog | E-485538 | E-485538 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-21
Local Enhancement Epic: LAC-eBillingController (EBC) - Defects / Productio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110333 |  |  | Local Enhancement Epic | Backlog | E-293314 | E-293314 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-12
Local Enhancement Epic: LAC-FGC - AR IB Clearance Experience Improvement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110334 |  |  | Local Enhancement Epic | Backlog | E-400284 | E-400284 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Lifecycle Management Epic: LAC-FGC - Technical Debt reduction for application | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110335 |  |  | Lifecycle Management Epic | Build | E-474968 | E-474968 | 5: XL | 2026-02-05 |  |  | 3 | 0 | 1 | 2 | No | 2025-01-29 | 2025-04-08 | 2026-02-05
Lifecycle Management Epic: LAC-FGC App Security - SNVR – Vulnerability Remedi | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110336 |  |  | Lifecycle Management Epic | Backlog | E-508040 | E-508040 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-04-09 | 2025-06-24
Local Enhancement Epic: LAC-FGC to Cloud PCF environment Code Only | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110337 |  |  | Local Enhancement Epic | Backlog | E-106166 | E-106166 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: LAC-French Islands - MQ-GP- Brokerage - New EAI Cr | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110338 |  |  | Lifecycle Management Epic | Backlog | E-475440 | E-475440 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-21 | 2025-02-28
Local Enhancement Epic: LAC-INCAS-PLUS - Add new FY25 Ancillaries Charges | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110339 |  |  | Local Enhancement Epic | Backlog | E-450089 | E-450089 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-09 | 2025-06-17
Lifecycle Management Epic: LAC-FTS -Architectural Runway | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110340 |  |  | Lifecycle Management Epic | Backlog | E-389875 | E-389875 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: LAC-INCAS-PLUS Enable Mexico New Gateway CUU | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110341 |  |  | Local Enhancement Epic | Backlog | E-387273 | E-387273 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-02
Local Enhancement Epic: LAC-INCAS-PLUS Enhancements CY24-CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110342 |  |  | Local Enhancement Epic | Backlog | E-429881 | E-429881 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-12
Local Enhancement Epic: LAC-INCAS-PLUS GCM Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110343 |  |  | Local Enhancement Epic | Backlog | E-330204 | E-330204 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Lifecycle Management Epic: LAC-LDP3 - MX - Application Decomm | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110344 |  |  | Lifecycle Management Epic | Backlog | E-242531 | E-242531 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-LDP3 / CALI - Charge/Service Code Additions, D | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110345 |  |  | Local Enhancement Epic | Backlog | E-315760 | E-315760 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-31
Local Enhancement Epic: LAC-LDP3 Technical Debt and Local Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110346 |  |  | Local Enhancement Epic | Backlog | E-194387 | E-194387 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: LAC-Mbilling Phase 4 Part 2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110347 |  |  | Local Enhancement Epic | Build | E-475333 | E-475333 |  | 2025-07-01 |  | 66.67% | 3 | 2 |  | 1 | No | 2025-01-29 | 2025-04-08 | 2025-07-01
Local Enhancement Epic: Late Invoice Payment -Base Product | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110348 |  |  | Local Enhancement Epic | Backlog | E-515510 | E-515510 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-06 | 2025-10-31
Local Enhancement Epic: LCCSOI Calculation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110349 |  |  | Local Enhancement Epic | Backlog | E-417423 | E-417423 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-02-21 | 2025-11-05
Local Enhancement Epic: LEO - CY 25 Architectural & NFRs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110350 |  |  | Local Enhancement Epic | Backlog | E-474444 | E-474444 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2026-01-19
Local Enhancement Epic: LEO - CY 25 eSRG, URSA & UVSDK adoption | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110351 |  |  | Local Enhancement Epic | Backlog | E-474367 | E-474367 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2025-12-30
Local Enhancement Epic: LEO - CY 25 Mobile System Team Features | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110352 |  |  | Local Enhancement Epic | Backlog | E-472849 | E-472849 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-02-11 | 2026-01-20
Local Enhancement Epic: LEO - CY 25 Product Assurance support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110353 |  |  | Local Enhancement Epic | Backlog | E-474479 | E-474479 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-21 | 2026-01-20
Local Enhancement Epic: LEO - CY 25 Production support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110354 |  |  | Local Enhancement Epic | Backlog | E-473264 | E-473264 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2025-12-31
Local Enhancement Epic: LEO - CY25 Local Business Demand | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110355 |  |  | Local Enhancement Epic | Backlog | E-463003 | E-463003 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-13
Local Enhancement Epic: LEO Decoupling - EPIC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110356 |  |  | Local Enhancement Epic | Backlog | E-507787 | E-507787 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-26 | 2026-01-19
Local Enhancement Epic: LEO Innovation Features (SCO - P&D - Conveyance) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110357 |  |  | Local Enhancement Epic | Backlog | E-454130 | E-454130 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-09-04 | 2025-12-31
Local Enhancement Epic: LEO Now deployment in EU | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110358 |  |  | Local Enhancement Epic | Backlog | E-399113 | E-399113 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LEO Roslyn Warnings - EPIC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110359 |  |  | Local Enhancement Epic | Backlog | E-507782 | E-507782 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-07 | 2025-12-31
Local Enhancement Epic: LEO Scoped storage work for OS 11 and above - EPIC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110360 |  |  | Local Enhancement Epic | Backlog | E-507786 | E-507786 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-27 | 2026-01-20
Lifecycle Management Epic: Life Cycle Management / Purple Protect | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110361 |  |  | Lifecycle Management Epic | Backlog | E-444676 | E-444676 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-15
Local Enhancement Epic: Lifecycle Application Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110362 |  |  | Local Enhancement Epic | Backlog | E-465146 | E-465146 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2026-03-24
Lifecycle Management Epic: Lifecycle Application Management - Security Vulner | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110363 |  |  | Lifecycle Management Epic | Backlog | E-465142 | E-465142 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-29 | 2026-10-28
Local Enhancement Epic: Lifecycle Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110364 |  |  | Local Enhancement Epic | Backlog | E-431539 | E-431539 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Loadboard Tech Stack CY 24 PI5 - CY PI2 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110365 |  |  | Lifecycle Management Epic | Backlog | E-459827 | E-459827 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-10
Local Enhancement Epic: Locksmith - Record Missing and Broken Locks | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110366 |  |  | Local Enhancement Epic | Backlog | E-215195 | E-215195 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Make changes in RMAS and Rampscape to run RMAS off | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110367 |  |  | Local Enhancement Epic | Backlog | E-475986 | E-475986 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-23 | 2025-12-31
Local Enhancement Epic: Manage Stock | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110368 |  |  | Local Enhancement Epic | Backlog | E-83506 | E-83506 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Management of DEX & REX scans | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110369 |  |  | Local Enhancement Epic | Backlog | E-382997 | E-382997 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Management of Exceptions | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110370 |  |  | Local Enhancement Epic | Backlog | E-461652 | E-461652 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-04 | 2025-12-31
Local Enhancement Epic: MEM Secondary 25 Automated Non-Conveyable Phase 1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110371 |  |  | Local Enhancement Epic | Backlog | E-446173 | E-446173 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-01 | 2025-10-20
Local Enhancement Epic: Merge In transit | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110372 |  |  | Local Enhancement Epic | Backlog | E-83515 | E-83515 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: METEOR feeds transition to Kronos | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110373 |  |  | Local Enhancement Epic | Backlog | E-463610 | E-463610 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-12-26
Local Enhancement Epic: Mexico – GDL, MID , CUN ROD Invoice, Credit Note, | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110374 |  |  | Local Enhancement Epic | Backlog | E-330912 | E-330912 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-10-04
Local Enhancement Epic: MH - NS Customers - Stryker | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110375 |  |  | Local Enhancement Epic | Backlog | E-346585 | E-346585 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Microservice to consume message from FOIS / GDI/FA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110376 |  |  | Local Enhancement Epic | Backlog | E-420519 | E-420519 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: Migrate existing BW projects to java to retire TIB | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110377 |  |  | Local Enhancement Epic | Backlog | E-459773 | E-459773 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2026-10-30
Local Enhancement Epic: Mobile Device Facility Discovery (PE1) | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110378 |  |  | Local Enhancement Epic | Build | E-325587 | E-325587 |  | 2025-07-02 |  | 50% | 2 | 1 |  | 1 | No |  |  | 2025-07-02
Local Enhancement Epic: Multi wave support in SIV (i.e. Predict Date AND T | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110379 |  |  | Local Enhancement Epic | Backlog | E-432823 | E-432823 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-01 | 2026-08-31
Local Enhancement Epic: MY ACCS - changes to enable Physical Handling | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110382 |  |  | Local Enhancement Epic | Backlog | E-472353 | E-472353 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MY eInvoicing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110383 |  |  | Local Enhancement Epic | Backlog | E-427322 | E-427322 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MY IMPORT ACCS Change Route for JHB Shipment (Inte | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110384 |  |  | Local Enhancement Epic | Backlog | E-434752 | E-434752 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2025-01-14
Local Enhancement Epic: MY Import ACCS-740677-SIRIM CPE Template Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110385 |  |  | Local Enhancement Epic | Backlog | E-384463 | E-384463 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2024-10-22
Local Enhancement Epic: MY Split Declaration for Imports | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110386 |  |  | Local Enhancement Epic | Backlog | E-381915 | E-381915 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2025-08-12
Local Enhancement Epic: NDS work CY 24 PI5 - CY25 PI2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110387 |  |  | Local Enhancement Epic | Backlog | E-459828 | E-459828 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-10
Local Enhancement Epic: Network 2.0 changes for DG Systems | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110388 |  |  | Local Enhancement Epic | Backlog | E-463195 | E-463195 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-07-22 | 2026-07-22
Local Enhancement Epic: NextGen APS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110389 |  |  | Local Enhancement Epic | Backlog | E-463606 | E-463606 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-12-26
Local Enhancement Epic: NG Prod Support FY26 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110390 |  |  | Local Enhancement Epic | Backlog | E-519389 | E-519389 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: NGPS - A300 AMM updates | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110391 |  |  | Local Enhancement Epic | Backlog | E-153834 | E-153834 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS - Add-Modify Additional Publications content | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110392 |  |  | Local Enhancement Epic | Backlog | E-248830 | E-248830 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-13
Local Enhancement Epic: NGPS - Enhancement and Changes for the Manual Back | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110393 |  |  | Local Enhancement Epic | Backlog | E-474928 | E-474928 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-12-31
Local Enhancement Epic: NGPS - Migrate FrameMaker 11 manuals to XML and Ox | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110394 |  |  | Local Enhancement Epic | Backlog | E-507980 | E-507980 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2027-05-31
Local Enhancement Epic: NGPS - Move Engine Manuals to NGPS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110395 |  |  | Local Enhancement Epic | Backlog | E-300647 | E-300647 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-04-22
Local Enhancement Epic: NGPS - Move manuals to XML utilizing Documentum | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110396 |  |  | Local Enhancement Epic | Backlog | E-248801 | E-248801 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-12-31
Local Enhancement Epic: NGPS - New Multifleet Tech Manuals | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110397 |  |  | Local Enhancement Epic | Backlog | E-215990 | E-215990 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS - Outage redirect improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110398 |  |  | Local Enhancement Epic | Backlog | E-475318 | E-475318 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-12-31
Local Enhancement Epic: NGPS - Perform Maintenance on Existing Manual | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110399 |  |  | Local Enhancement Epic | Backlog | E-329593 | E-329593 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: NGPS - Policy Manual Schema changes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110400 |  |  | Local Enhancement Epic | Backlog | E-215985 | E-215985 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS - Publish manuals available via AOOL to NGPS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110401 |  |  | Local Enhancement Epic | Backlog | E-329587 | E-329587 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-05-30
Local Enhancement Epic: NGPS - Remediate AVISO vulnerabilities for Publica | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110402 |  |  | Local Enhancement Epic | Backlog | E-248826 | E-248826 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-13
Local Enhancement Epic: NGPS - TIS to TPS name change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110403 |  |  | Local Enhancement Epic | Backlog | E-168512 | E-168512 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS - Update sites to Chrome/Edge Browsers | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110404 |  |  | Local Enhancement Epic | Backlog | E-215210 | E-215210 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS - XML Wiring Diagram and Wire List Manuals to | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110405 |  |  | Local Enhancement Epic | Backlog | E-168520 | E-168520 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS Application Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110406 |  |  | Local Enhancement Epic | Backlog | E-507964 | E-507964 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: NGPS MEL reference links to other manuals | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110407 |  |  | Local Enhancement Epic | Backlog | E-185563 | E-185563 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS Move SSM XML Manuals to Documentum | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110408 |  |  | Local Enhancement Epic | Backlog | E-185569 | E-185569 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: NGPS Oxygen Maintenance and Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110409 |  |  | Local Enhancement Epic | Backlog | E-507960 | E-507960 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2027-12-31
Local Enhancement Epic: NGPS Publishing Maintenance and Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110410 |  |  | Local Enhancement Epic | Backlog | E-507962 | E-507962 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: NGPS Stylesheet changes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110411 |  |  | Local Enhancement Epic | Backlog | E-507963 | E-507963 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: NGPS Tech Ops Training Video management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110412 |  |  | Local Enhancement Epic | Backlog | E-507966 | E-507966 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: Non-Functional Requirements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110413 |  |  | Local Enhancement Epic | Backlog | E-202679 | E-202679 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Notification Center for EU FOPD products | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110414 |  |  | Local Enhancement Epic | Backlog | E-421532 | E-421532 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2026-04-29
Local Enhancement Epic: NPGS Viewer Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110415 |  |  | Local Enhancement Epic | Backlog | E-507971 | E-507971 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: NZ 6-digit HS code in ICR submission | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110416 |  |  | Local Enhancement Epic | Backlog | E-414484 | E-414484 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-08-13
Local Enhancement Epic: NZ: IM1 flight update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110417 |  |  | Local Enhancement Epic | Backlog | E-384471 | E-384471 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2024-10-22
Local Enhancement Epic: NZ-755645-Held Shipment in Wrong Queue | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110418 |  |  | Local Enhancement Epic | Backlog | E-471978 | E-471978 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2027-01-12
Local Enhancement Epic: Obtain Vendor Quote | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110419 |  |  | Local Enhancement Epic | Backlog | E-83497 | E-83497 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ON HOLD - Cage scanning solution for stations (PFS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110420 |  |  | Local Enhancement Epic | Backlog | E-389175 | E-389175 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ON HOLD - Station Dashboard based on SEFS Data str | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110421 |  |  | Local Enhancement Epic | Backlog | E-80675 | E-80675 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: OOE Tech Stack Upgrade (Owner Operator Extranet) C | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110422 |  |  | Local Enhancement Epic | Backlog | E-459833 | E-459833 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-10
Local Enhancement Epic: Operational Excellence - Application Monitoring (C | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110423 |  |  | Local Enhancement Epic | Backlog | E-470650 | E-470650 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-01-14 | 2025-07-28
Local Enhancement Epic: Operational Execution | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110424 |  |  | Local Enhancement Epic | Backlog | E-83482 | E-83482 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Optix - Modernization to optimize for modern frame | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110425 |  |  | Local Enhancement Epic | Backlog | E-507972 | E-507972 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: Optix Protect Purple | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110426 |  |  | Local Enhancement Epic | Backlog | E-507961 | E-507961 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2027-12-31
Local Enhancement Epic: Oracle Configurations | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110427 |  |  | Local Enhancement Epic | Backlog | E-135841 | E-135841 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Oracle OTM Recommendations | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110428 |  |  | Local Enhancement Epic | Backlog | E-406956 | E-406956 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Order Management Dashboard | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110429 |  |  | Local Enhancement Epic | Backlog | E-83447 | E-83447 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Order Visibility | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110430 |  |  | Local Enhancement Epic | Backlog | E-83505 | E-83505 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Outbound Stock | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110431 |  |  | Local Enhancement Epic | Backlog | E-83508 | E-83508 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Output Shipment Commodity Event (SCE) to JMS for | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110432 |  |  | Local Enhancement Epic | Backlog | E-342631 | E-342631 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: P&D Plan & Prepare Adopt Ephemeral Environments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110433 |  |  | Local Enhancement Epic | Backlog | E-449736 | E-449736 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-08-11 | 2026-08-18
Lifecycle Management Epic: P&D PPO Testing Upgrades | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110434 |  |  | Lifecycle Management Epic | Backlog | E-507673 | E-507673 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-05-11
Local Enhancement Epic: P&P - IND 123K Sort Expansion at INDH OB4 Facility | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110435 |  |  | Local Enhancement Epic | Backlog | E-447386 | E-447386 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PFCR 3.0 Protect Purple | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110436 |  |  | Local Enhancement Epic | Backlog | E-507976 | E-507976 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2028-12-29
Local Enhancement Epic: PFCR evaluation, support, and redevelop | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110437 |  |  | Local Enhancement Epic | Backlog | E-215208 | E-215208 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: PHASAR - Pending Modifications and Local Demand | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110438 |  |  | Local Enhancement Epic | Backlog | E-443668 | E-443668 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Plan & Prepare - Non-Critical Modifications (PI CY | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110439 |  |  | Local Enhancement Epic | Backlog | E-468487 | E-468487 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Lifecycle Management Epic: Plan&Prep - DMT: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110440 |  |  | Lifecycle Management Epic | Backlog | E-504462 | E-504462 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2026-01-21
Lifecycle Management Epic: Plan&Prep - EOSRO: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110441 |  |  | Lifecycle Management Epic | Backlog | E-504466 | E-504466 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2026-08-19
Lifecycle Management Epic: Plan&Prep - ESOP: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110442 |  |  | Lifecycle Management Epic | Backlog | E-504469 | E-504469 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2026-01-21
Lifecycle Management Epic: Plan&Prep - FICE: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110443 |  |  | Lifecycle Management Epic | Backlog | E-504473 | E-504473 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2026-01-21
Lifecycle Management Epic: Plan&Prep - FRaNS: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110444 |  |  | Lifecycle Management Epic | Backlog | E-504465 | E-504465 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2026-01-21
Lifecycle Management Epic: Plan&Prep - ILS: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110445 |  |  | Lifecycle Management Epic | Backlog | E-504475 | E-504475 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-21
Lifecycle Management Epic: Plan&Prep - KS: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110446 |  |  | Lifecycle Management Epic | Backlog | E-504474 | E-504474 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2026-08-20
Lifecycle Management Epic: Plan&Prep - LocGen: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110447 |  |  | Lifecycle Management Epic | Backlog | E-504477 | E-504477 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-22 | 2025-10-29
Lifecycle Management Epic: Plan&Prep - MOP: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110448 |  |  | Lifecycle Management Epic | Backlog | E-504470 | E-504470 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2026-08-19
Lifecycle Management Epic: Plan&Prep - PHUWV: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110449 |  |  | Lifecycle Management Epic | Backlog | E-504476 | E-504476 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-03 | 2026-08-19
Lifecycle Management Epic: Plan&Prep - SMOP: KLO Sort Solution Train | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110450 |  |  | Lifecycle Management Epic | Backlog | E-504472 | E-504472 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2026-08-20
Local Enhancement Epic: Platform Invoicing Module | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110451 |  |  | Local Enhancement Epic | Backlog | E-388291 | E-388291 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Pre-Invoicing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110452 |  |  | Local Enhancement Epic | Backlog | E-112355 | E-112355 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Prevent Manual Tracking ID Entry within Status Sca | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110453 |  |  | Local Enhancement Epic | Backlog | E-507947 | E-507947 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Prod Supp Ongoing Maintenance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110454 |  |  | Local Enhancement Epic | Backlog | E-432117 | E-432117 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Production Installs CY25 - P&D Plan & Prepare | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110455 |  |  | Local Enhancement Epic | Backlog | E-474875 | E-474875 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-02-29
Local Enhancement Epic: Production Support - CY25 P&D PPO | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110456 |  |  | Local Enhancement Epic | Backlog | E-473459 | E-473459 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-11 | 2026-01-20
Lifecycle Management Epic: Production Support - GFA | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110457 |  |  | Lifecycle Management Epic | Build | E-503694 | E-503694 | 4: L | 2025-08-13 |  | 100% | 3 | 3 |  | 0 | No |  |  | 2025-08-13
Local Enhancement Epic: Production support for Rampview, DSS, SALSA, RMAS, | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110458 |  |  | Local Enhancement Epic | Backlog | E-351331 | E-351331 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-31
Lifecycle Management Epic: Production Support RCC - CY25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110459 |  |  | Lifecycle Management Epic | Backlog | E-518734 | E-518734 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-01 | 2025-12-31
Local Enhancement Epic: Protect Purple - PZDZ CY24 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110460 |  |  | Local Enhancement Epic | Backlog | E-398679 | E-398679 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-21
Local Enhancement Epic: Protect Purple - Run and Close CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110461 |  |  | Local Enhancement Epic | Backlog | E-469784 | E-469784 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-01-20
Lifecycle Management Epic: Protect Purple CY25 - TVS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110462 |  |  | Lifecycle Management Epic | Backlog | E-475695 | E-475695 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: Provide enhancements to station workload allocatio | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110463 |  |  | Local Enhancement Epic | Backlog | E-185954 | E-185954 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: PScan- Pending Modifications and Local Demand | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110464 |  |  | Local Enhancement Epic | Backlog | E-443669 | E-443669 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-30 | 2025-12-31
Lifecycle Management Epic: Purple Access Gateway (PAG) Exit | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110465 |  |  | Lifecycle Management Epic | Backlog | E-447020 | E-447020 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-23 | 2025-05-01
Local Enhancement Epic: Purple Protect CY 24 PI5- CY25 PI2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110466 |  |  | Local Enhancement Epic | Backlog | E-461380 | E-461380 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-12-31
Lifecycle Management Epic: QA/Dock Cloudbees and Jenkins Migration to Github | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110467 |  |  | Lifecycle Management Epic | Backlog | E-507951 | E-507951 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-09-30
Local Enhancement Epic: Qualified Outside Carrier (QOC) LB CY 24 PI5- CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110468 |  |  | Local Enhancement Epic | Backlog | E-461385 | E-461385 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-06-10
Local Enhancement Epic: Quality Module - Standard Product | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110469 |  |  | Local Enhancement Epic | Backlog | E-345606 | E-345606 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Quarterly WebLogic/Java/Linux Patching | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110470 |  |  | Lifecycle Management Epic | Backlog | E-82280 | E-82280 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-01-20
Local Enhancement Epic: Quick Pickup- Phase 2 Enhancements (PPM 443143) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110471 |  |  | Local Enhancement Epic | Backlog | E-284397 | E-284397 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-23
Local Enhancement Epic: Quote Customer | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110472 |  |  | Local Enhancement Epic | Backlog | E-83479 | E-83479 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Quote Platform Connectivity | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110473 |  |  | Local Enhancement Epic | Backlog | E-186563 | E-186563 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Rampview,DSS & FASTR Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110474 |  |  | Local Enhancement Epic | Backlog | E-463386 | E-463386 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-12-31
Local Enhancement Epic: Rationalize station inbound scanning | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110475 |  |  | Local Enhancement Epic | Backlog | E-146338 | E-146338 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Re-branding - PPM 472509 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110476 |  |  | Local Enhancement Epic | Backlog | E-355712 | E-355712 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Replacement of Panasonic FZN1 devices with Honeywe | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110477 |  |  | Lifecycle Management Epic | Backlog | E-394230 | E-394230 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-24
Local Enhancement Epic: Reporting | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110478 |  |  | Local Enhancement Epic | Backlog | E-83503 | E-83503 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: RFQ Process Support | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110479 |  |  | Local Enhancement Epic | Backlog | E-83516 | E-83516 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: RMS FHL solution BAU & life cycle management suppo | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110480 |  |  | Local Enhancement Epic | Backlog | E-518480 | E-518480 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-16 | 2026-05-26
Local Enhancement Epic: Role-based access at NGPS manual tile level | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110481 |  |  | Local Enhancement Epic | Backlog | E-497311 | E-497311 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2026-02-27
Local Enhancement Epic: Route optimization Control room | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110482 |  |  | Local Enhancement Epic | Backlog | E-472100 | E-472100 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-06 | 2026-06-30
Lifecycle Management Epic: RunOpsSort - FY26 Prod Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110483 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-516142 | E-516142 |  | 2025-07-01 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-07-01
Local Enhancement Epic: S0293 USPS Ship | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110484 |  |  | Local Enhancement Epic | Backlog | E-420425 | E-420425 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-10-28
Local Enhancement Epic: Safer Driving Compliance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110485 |  |  | Local Enhancement Epic | Backlog | E-379711 | E-379711 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-22 | 2025-11-05
Local Enhancement Epic: Safer Highways - Support Linehaul and P&D HOS Trim | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110486 |  |  | Local Enhancement Epic | Backlog | E-429162 | E-429162 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-21
Local Enhancement Epic: SafetyNet Production Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110487 |  |  | Local Enhancement Epic | Backlog | E-375309 | E-375309 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-31
Local Enhancement Epic: Sameday | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110488 |  |  | Local Enhancement Epic | Backlog | E-216469 | E-216469 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SAS DRIVE Initiative | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110489 |  |  | Local Enhancement Epic | Backlog | E-404539 | E-404539 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-23
Lifecycle Management Epic: SAS Report Migration to PowerBI | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110490 |  |  | Lifecycle Management Epic | Backlog | E-385530 | E-385530 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Schedule K Rewrite | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110491 |  |  | Local Enhancement Epic | Backlog | E-239576 | E-239576 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-05
Local Enhancement Epic: SCO - CLR - Entry Review System - Evergreen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110492 |  |  | Local Enhancement Epic | Build | E-395063 | E-395063 |  | 2025-07-02 |  |  | 2 | 0 | 1 | 1 | No |  |  | 2025-07-02
Local Enhancement Epic: SCO - LH - AFCS - CLASS - IT OPS Excellence_FY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110493 |  |  | Local Enhancement Epic | Backlog | E-470298 | E-470298 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-15 | 2025-03-25
Local Enhancement Epic: SCO - LH - AFCS - CLASS_RTB_FY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110494 |  |  | Local Enhancement Epic | Backlog | E-454459 | E-454459 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: SCO - LH - CX - API - GEHC - GTM Product DB | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110495 |  |  | Local Enhancement Epic | Backlog | E-501608 | E-501608 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - API - Lenovo - Phase 2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110496 |  |  | Local Enhancement Epic | Backlog | E-501609 | E-501609 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-21 | 2026-01-12
Local Enhancement Epic: SCO - LH - CX - API - Logitech | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110497 |  |  | Local Enhancement Epic | Backlog | E-501610 | E-501610 |  |  |  |  | 0 | 0 |  | 0 | No | 2023-06-07 | 2024-01-16
Local Enhancement Epic: SCO - LH - CX - API - Tesla CI Mapping and FXL Sta | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110498 |  |  | Local Enhancement Epic | Backlog | E-501611 | E-501611 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2025-10-21
Local Enhancement Epic: SCO - LH - CX - EDI - ABB - Copper Hill | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110499 |  |  | Local Enhancement Epic | Backlog | E-501559 | E-501559 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Apple 810cb Routing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110500 |  |  | Local Enhancement Epic | Backlog | E-501560 | E-501560 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-06-03
Local Enhancement Epic: SCO - LH - CX - EDI - Apple FTZ Map Updates | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110501 |  |  | Local Enhancement Epic | Backlog | E-501561 | E-501561 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Apple FTZ v2 Map Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110502 |  |  | Local Enhancement Epic | Backlog | E-501562 | E-501562 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - AstraZenica EDI For Billing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110503 |  |  | Local Enhancement Epic | Backlog | E-508181 | E-508181 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-12-08 | 2026-02-27
Local Enhancement Epic: SCO - LH - CX - EDI - BMW Move Existing Feed to XM | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110504 |  |  | Local Enhancement Epic | Backlog | E-501565 | E-501565 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-06-19 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - BOMAG Americas 310 to Argus | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110505 |  |  | Local Enhancement Epic | Backlog | E-501566 | E-501566 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - CNH P44 Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110506 |  |  | Local Enhancement Epic | Backlog | E-501567 | E-501567 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-04-30 | 2026-03-25
Local Enhancement Epic: SCO - LH - CX - EDI - Dexcom | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110507 |  |  | Local Enhancement Epic | Backlog | E-501568 | E-501568 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - Disney 204 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110508 |  |  | Local Enhancement Epic | Backlog | E-501569 | E-501569 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2026-01-13
Local Enhancement Epic: SCO - LH - CX - EDI - Envista QAD 214 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110509 |  |  | Local Enhancement Epic | Backlog | E-501570 | E-501570 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Excelitas - Intelligent Audi | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110510 |  |  | Local Enhancement Epic | Backlog | E-501571 | E-501571 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-06-03
Local Enhancement Epic: SCO - LH - CX - EDI - GAP Onboarding | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110511 |  |  | Local Enhancement Epic | Backlog | E-501572 | E-501572 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2026-03-31
Local Enhancement Epic: SCO - LH - CX - EDI - Haemonetics EDI Invoice Mapp | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110512 |  |  | Local Enhancement Epic | Backlog | E-501574 | E-501574 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Hardware Resources CASS Bill | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110513 |  |  | Local Enhancement Epic | Backlog | E-501575 | E-501575 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-06-04 | 2026-01-13
Local Enhancement Epic: SCO - LH - CX - EDI - Hologic billing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110514 |  |  | Local Enhancement Epic | Backlog | E-501577 | E-501577 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-05-28 | 2026-06-02
Local Enhancement Epic: SCO - LH - CX - EDI - HP Canada and US SAP GTS E4H | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110515 |  |  | Local Enhancement Epic | Backlog | E-501578 | E-501578 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-06-05 | 2025-06-03
Local Enhancement Epic: SCO - LH - CX - EDI - IFF DHL Transactions | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110516 |  |  | Local Enhancement Epic | Backlog | E-501579 | E-501579 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Infinite Electronics | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110517 |  |  | Local Enhancement Epic | Backlog | E-501580 | E-501580 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-23 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - Isuzu Canada I/B CCI | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110518 |  |  | Local Enhancement Epic | Backlog | E-501581 | E-501581 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Klein - US Bank Billing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110519 |  |  | Local Enhancement Epic | Backlog | E-516247 | E-516247 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2025-08-26
Local Enhancement Epic: SCO - LH - CX - EDI - Milwaukee Tool - CASS Billin | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110520 |  |  | Local Enhancement Epic | Backlog | E-501582 | E-501582 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-12-31 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - Molex CTSI 210 for Air and | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110521 |  |  | Local Enhancement Epic | Backlog | E-501583 | E-501583 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2026-01-20
Local Enhancement Epic: SCO - LH - CX - EDI - Panduit UAT / MTP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110522 |  |  | Local Enhancement Epic | Backlog | E-501586 | E-501586 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-03-21 | 2026-01-13
Local Enhancement Epic: SCO - LH - CX - EDI - Parker Hannifin Canada and | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110523 |  |  | Local Enhancement Epic | Backlog | E-501587 | E-501587 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - Plexus Update I/B PD | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110524 |  |  | Local Enhancement Epic | Backlog | E-501588 | E-501588 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-05 | 2026-02-27
Local Enhancement Epic: SCO - LH - CX - EDI - Qorvo CI | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110525 |  |  | Local Enhancement Epic | Backlog | E-501589 | E-501589 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Rosemount Emerson E2Open | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110526 |  |  | Local Enhancement Epic | Backlog | E-501591 | E-501591 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Samtec 7501 O/B | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110527 |  |  | Local Enhancement Epic | Backlog | E-501592 | E-501592 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Spector CI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110528 |  |  | Local Enhancement Epic | Backlog | E-501593 | E-501593 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-14 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - Spigen CI AB28 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110529 |  |  | Local Enhancement Epic | Backlog | E-501594 | E-501594 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: SCO - LH - CX - EDI - Stryker Interface | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110530 |  |  | Local Enhancement Epic | Backlog | E-501595 | E-501595 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Local Enhancement Epic: SCO - LH - CX - EDI - TCI America Billing | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110531 |  |  | Local Enhancement Epic | Backlog | E-501597 | E-501597 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Tesla 7501 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110533 |  |  | Local Enhancement Epic | Backlog | E-501598 | E-501598 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: SCO - LH - CX - EDI - Top Knobs CASS Billing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110534 |  |  | Local Enhancement Epic | Backlog | E-501599 | E-501599 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-01-14 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - Urbn I/B CI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110535 |  |  | Local Enhancement Epic | Backlog | E-501601 | E-501601 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2026-03-24
Local Enhancement Epic: SCO - LH - CX - EDI - ZF Chassis- Focus | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110536 |  |  | Local Enhancement Epic | Backlog | E-501605 | E-501605 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO - LH - CX - EDI - Zimmer CASS 110 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110537 |  |  | Local Enhancement Epic | Backlog | E-501606 | E-501606 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2025-12-31
Lifecycle Management Epic: SCO - SO - GitHub Actions for CloudBees retirement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110538 |  |  | Lifecycle Management Epic | Launch & Evaluate | E-484368 | E-484368 | 5: XL | 2025-07-01 |  |  | 11 | 0 | 11 | 0 | No | 2024-10-24 | 2025-10-28 | 2025-07-01
Local Enhancement Epic: SCO Sort Plan & Prepare KLO CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110539 |  |  | Local Enhancement Epic | Backlog | E-462312 | E-462312 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-14 | 2028-06-08
Local Enhancement Epic: SCO-App-optimization (ANZ) | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110540 |  |  | Local Enhancement Epic | Backlog | E-467225 | E-467225 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SCO-LH--AFCS - ABSP - Improvements CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110541 |  |  | Local Enhancement Epic | Backlog | E-469082 | E-469082 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - ABSP - Keep the Lights On - Producti | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110542 |  |  | Local Enhancement Epic | Backlog | E-469072 | E-469072 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - ABSP Protect Purple CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110543 |  |  | Local Enhancement Epic | Backlog | E-469078 | E-469078 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - AFI Improvements CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110544 |  |  | Local Enhancement Epic | Backlog | E-469083 | E-469083 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - AFI Keep the Lights On - Production | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110545 |  |  | Local Enhancement Epic | Backlog | E-469075 | E-469075 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - AFI Protect Purple CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110546 |  |  | Local Enhancement Epic | Backlog | E-469041 | E-469041 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - AFI Rating Automation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110547 |  |  | Local Enhancement Epic | Backlog | E-255339 | E-255339 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-03
Local Enhancement Epic: SCO-LH-AFCS - eSRG Data Changes CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110548 |  |  | Local Enhancement Epic | Backlog | E-469098 | E-469098 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - K2 Improvements CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110549 |  |  | Local Enhancement Epic | Backlog | E-469084 | E-469084 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - K2 Keep the Lights On - Production S | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110550 |  |  | Local Enhancement Epic | Backlog | E-469076 | E-469076 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCO-LH-AFCS - K2 Protect Purple CY25 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110551 |  |  | Local Enhancement Epic | Backlog | E-469080 | E-469080 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2025-12-31
Local Enhancement Epic: SCOOP (Supply Chains Operations Observability Plat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110552 |  |  | Local Enhancement Epic | Build | E-333377 | E-333377 | 3: M | 2025-07-01 |  |  | 8 | 0 | 8 | 0 | No | 2024-07-22 | 2025-06-10 | 2025-07-01
Local Enhancement Epic: SCS Optimization Work | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110553 |  |  | Local Enhancement Epic | Backlog | E-303361 | E-303361 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Security Screening Capture in AutoSlip | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110554 |  |  | Local Enhancement Epic | Done | E-425709 | E-425709 |  | 2025-08-28 | 2025-08-28 |  | 0 | 0 |  | 0 | No |  |  | 2025-08-28 | 2025-08-28
Local Enhancement Epic: SEMF Production Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110555 |  |  | Local Enhancement Epic | Backlog | E-463600 | E-463600 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-12-26
Lifecycle Management Epic: SEMF Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110556 |  |  | Lifecycle Management Epic | Backlog | E-463595 | E-463595 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-12-26
Local Enhancement Epic: SG-523591-[FiT]-ACCS-SG Import interface with FiT/ | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110557 |  |  | Local Enhancement Epic | Backlog | E-519082 | E-519082 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-10-28
Local Enhancement Epic: SG-523591-[FIT]-ACCS-SG interface with FiT/CDEP to | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110558 |  |  | Local Enhancement Epic | Done | E-518181 | E-518181 | 4: L | 2025-07-11 | 2025-07-11 |  | 0 | 0 |  | 0 | No |  |  | 2025-07-11 | 2025-07-11
Local Enhancement Epic: Shinobi - Clearance Performance: HS Code, IWM & BP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110559 |  |  | Local Enhancement Epic | Backlog | E-323546 | E-323546 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-23
Local Enhancement Epic: SHV - CY24 Run&Close | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110560 |  |  | Local Enhancement Epic | Backlog | E-404375 | E-404375 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-29
Local Enhancement Epic: SHV - CY25 Run&Close | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110561 |  |  | Local Enhancement Epic | Backlog | E-475724 | E-475724 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-29 | 2026-02-27
Local Enhancement Epic: SHV CY25 - P&D Plan & Prepare | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110562 |  |  | Local Enhancement Epic | Backlog | E-470473 | E-470473 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-11 | 2026-10-05
Local Enhancement Epic: SHV PI1 CY25 - TVS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110563 |  |  | Local Enhancement Epic | Backlog | E-479408 | E-479408 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-23 | 2025-06-11
Lifecycle Management Epic: SIC and SF: Business Continuity, Production Suppor | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110564 |  |  | Lifecycle Management Epic | Done | E-477081 | E-477081 | 4: L | 2025-07-01 | 2025-07-01 | 61.9% | 21 | 13 | 8 | 0 | No |  |  | 2025-07-01 | 2025-07-01
Local Enhancement Epic: SIV Globalization effort | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110565 |  |  | Local Enhancement Epic | Backlog | E-408431 | E-408431 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-29
Local Enhancement Epic: SmartDG Angular Migration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110566 |  |  | Local Enhancement Epic | Backlog | E-342399 | E-342399 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-12-31 | 2026-12-31
Local Enhancement Epic: SmartDG Updates FY23 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110567 |  |  | Local Enhancement Epic | Backlog | E-342403 | E-342403 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SOD | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110568 |  |  | Local Enhancement Epic | Backlog | E-176982 | E-176982 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Spartans Business Management - FY2025 (#566187) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110569 |  |  | Local Enhancement Epic | Backlog | E-478210 | E-478210 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-05-30
Lifecycle Management Epic: Spartans Production Support - FY2025 (#566190) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110570 |  |  | Lifecycle Management Epic | Backlog | E-478186 | E-478186 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-05-30
Lifecycle Management Epic: Spartans Protect Purple - FY2025 (#189472) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110571 |  |  | Lifecycle Management Epic | Backlog | E-478190 | E-478190 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-05-30
Local Enhancement Epic: Spike: Modern java development in FCC environment | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110572 |  |  | Local Enhancement Epic | Backlog | E-485296 | E-485296 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-03-26 | 2025-07-31
Lifecycle Management Epic: Springboot 3.2.6, Java 17, & Common Services 3.3.8 | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110573 |  |  | Lifecycle Management Epic | Backlog | E-502109 | E-502109 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SSAMI ES User Role Revamp | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110574 |  |  | Local Enhancement Epic | Backlog | E-504248 | E-504248 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-05-12 | 2025-08-13
Local Enhancement Epic: Start an RMAS Client (as Master or Non-Master) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110575 |  |  | Local Enhancement Epic | Backlog | E-351311 | E-351311 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-10-03 | 2025-05-30
Local Enhancement Epic: STAT70 post on Direct Loading | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110576 |  |  | Local Enhancement Epic | Backlog | E-461152 | E-461152 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Station Workload Output Optimization Project (SWOO | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110577 |  |  | Local Enhancement Epic | Backlog | E-286257 | E-286257 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Surface Sort KLO CY25 - RunOpsSort | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110578 |  |  | Local Enhancement Epic | Backlog | E-467299 | E-467299 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-01 | 2026-12-31
Local Enhancement Epic: SYDIP Held shipment escapee | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110579 |  |  | Local Enhancement Epic | Backlog | E-503783 | E-503783 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: System Bid Award | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110580 |  |  | Lifecycle Management Epic | Backlog | E-477643 | E-477643 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-09-07 | 2026-11-13
Local Enhancement Epic: Tariff CY 24 PI5- CY25 PI2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110581 |  |  | Local Enhancement Epic | Backlog | E-461389 | E-461389 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-10-30 | 2025-12-31
Local Enhancement Epic: Tariff UI CY25 PI 3 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110582 |  |  | Local Enhancement Epic | Backlog | E-516958 | E-516958 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-11 | 2025-08-19
Local Enhancement Epic: T-Check Fuel Card | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110583 |  |  | Local Enhancement Epic | Backlog | E-403649 | E-403649 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-20
Local Enhancement Epic: Test automation - Critical scenarios covered by EU | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110584 |  |  | Local Enhancement Epic | Backlog | E-270339 | E-270339 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-10-27 | 2026-05-29
Local Enhancement Epic: TGE Integration to enable Toll in WA Country - PPM | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110585 |  |  | Local Enhancement Epic | Backlog | E-420876 | E-420876 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-08-27 | 2024-08-28
Local Enhancement Epic: TH-NA-TH Notification support to reduce cage code | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110586 |  |  | Local Enhancement Epic | Backlog | E-430690 | E-430690 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-30
Local Enhancement Epic: TKO-CMP/MOD-Airworthiness Directive Response (2261 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110587 |  |  | Local Enhancement Epic | Backlog | E-362524 | E-362524 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-10-18
Local Enhancement Epic: TKO-CMP/MOD-ARL Enablement (328063) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110588 |  |  | Local Enhancement Epic | Backlog | E-362720 | E-362720 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-01
Local Enhancement Epic: TKO-CMP/MOD-Backlog | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110589 |  |  | Local Enhancement Epic | Backlog | E-255482 | E-255482 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-06-24
Local Enhancement Epic: TKO-CMP/MOD-LOI 1948 Enhancements (PPM??) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110590 |  |  | Local Enhancement Epic | Backlog | E-458810 | E-458810 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2025-01-21
Local Enhancement Epic: TKO-CMP/MOD-Production Support (PPM#497021) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110591 |  |  | Local Enhancement Epic | Backlog | E-373819 | E-373819 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-31
Local Enhancement Epic: TKO-MAT-AeroRepair Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110592 |  |  | Local Enhancement Epic | Launch & Evaluate | E-482594 | E-482594 |  | 2025-07-23 |  |  | 0 | 0 |  | 0 | No | 2025-04-02 | 2025-06-10 | 2025-07-23
Local Enhancement Epic: TKO-MAT-Backlog | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110593 |  |  | Local Enhancement Epic | Backlog | E-255495 | E-255495 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-06-12
Local Enhancement Epic: TKO-MAT-Expired Part Warning | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110594 |  |  | Local Enhancement Epic | Backlog | E-511396 | E-511396 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: TKO-MAT-FCF/NOVITA Continued (PPM #497020) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110595 |  |  | Local Enhancement Epic | Backlog | E-387813 | E-387813 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-09-27
Local Enhancement Epic: TKO-MAT-PO Automation (165932) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110596 |  |  | Local Enhancement Epic | Backlog | E-362888 | E-362888 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: TKO-MAT-Production Support (PPM#496861) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110597 |  |  | Local Enhancement Epic | Backlog | E-373821 | E-373821 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-01-31
Local Enhancement Epic: TKO-MAT-Reconfigure Material messages from FedEx N | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110598 |  |  | Local Enhancement Epic | Backlog | E-513016 | E-513016 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-06-18 | 2025-09-30
Local Enhancement Epic: TKO-MAT-ValStream (PPM #495062) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110599 |  |  | Local Enhancement Epic | Backlog | E-419315 | E-419315 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-06-30
Local Enhancement Epic: FY26_AU Domestic - Ops TM1 reporting updates-GM | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110600 |  |  | Local Enhancement Epic | Backlog | E-518176 | E-518176 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TPS Protect Purple | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110601 |  |  | Local Enhancement Epic | Backlog | E-474932 | E-474932 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-22 | 2026-12-31
Lifecycle Management Epic: TRAMS Android Tablet (GETAC ZX10) Replacement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110602 |  |  | Lifecycle Management Epic | Backlog | E-502164 | E-502164 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-05-04
Local Enhancement Epic: TW-259497-FUNCTIONAL-TW ACCS Import: shipment decl | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110603 |  |  | Local Enhancement Epic | Backlog | E-163774 | E-163774 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW-286093-FUNCTIONAL- Image Handling Efficiency fo | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110604 |  |  | Local Enhancement Epic | Backlog | E-293364 | E-293364 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-08-14 | 2024-10-22
Local Enhancement Epic: TW-354303-TWACCS Import EZWay | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110605 |  |  | Local Enhancement Epic | Backlog | E-246462 | E-246462 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW-475479-Imp : B2B Clearance Cashflow Platform fo | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110606 |  |  | Local Enhancement Epic | Backlog | E-355714 | E-355714 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-12-20
Local Enhancement Epic: TW-511351-new warehouse FTZ MTP/Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110607 |  |  | Local Enhancement Epic | Backlog | E-458997 | E-458997 |  |  |  |  | 1 | 0 |  | 1 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: TW-51191-FUNCTIONAL - CEFAM and K2 system integrat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110608 |  |  | Local Enhancement Epic | Backlog | E-293366 | E-293366 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-08-13
Local Enhancement Epic: TW-554729-EXP interface for data exchange enhancem | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110609 |  |  | Local Enhancement Epic | Backlog | E-513499 | E-513499 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW-563795-IMP TAX limit for passenger to TWD 35,00 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110610 |  |  | Local Enhancement Epic | Backlog | E-478988 | E-478988 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW-566211-EXP unit price field format change to (1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110611 |  |  | Local Enhancement Epic | Backlog | E-478990 | E-478990 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: TW-569211-IMP Ancillary Fee | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110612 |  |  | Local Enhancement Epic | Backlog | E-444804 | E-444804 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: TW-850967-IMP Integration with uDS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110613 |  |  | Local Enhancement Epic | Backlog | E-484485 | E-484485 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: TW--EXP OffCode YT/NT | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110614 |  |  | Local Enhancement Epic | Backlog | E-504523 | E-504523 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UCC AES | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110615 |  |  | Local Enhancement Epic | Backlog | E-337123 | E-337123 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2030-12-09
Local Enhancement Epic: UCC Controlled Movement of Goods (enabler) | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110616 |  |  | Local Enhancement Epic | Backlog | E-445822 | E-445822 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: ULD Balancer (TRAMS) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110617 |  |  | Local Enhancement Epic | Backlog | E-502146 | E-502146 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-08-20
Local Enhancement Epic: Update to existing PHASAR/PSCAN and AutoVerify tra | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110618 |  |  | Local Enhancement Epic | Backlog | E-471060 | E-471060 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: US CLR REG - ROCS Seaport location generation and | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110619 |  |  | Local Enhancement Epic | Backlog | E-268951 | E-268951 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: US CLR REG - Swap Location Code identification | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110620 |  |  | Local Enhancement Epic | Backlog | E-269067 | E-269067 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: US SCAN - Migrate to Linux RHEL 8 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110621 |  |  | Lifecycle Management Epic | Backlog | E-394109 | E-394109 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-24
Local Enhancement Epic: USD/FACS Express Legacy System Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110622 |  |  | Local Enhancement Epic | Backlog | E-458006 | E-458006 | 5: XL |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-09-04
Local Enhancement Epic: USSC - Class 9 Hazmat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110623 |  |  | Local Enhancement Epic | Backlog | E-507681 | E-507681 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-24 | 2025-10-30
Local Enhancement Epic: USSC/DMT - Utilize New URL | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110624 |  |  | Local Enhancement Epic | Backlog | E-507682 | E-507682 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-22 | 2025-10-30
Local Enhancement Epic: VALET - Conversion to Web-client | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110625 |  |  | Local Enhancement Epic | Build | E-447172 | E-447172 |  | 2026-03-27 |  |  | 2 | 0 | 1 | 1 | No | 2025-08-27 | 2026-12-25 | 2026-03-27
Local Enhancement Epic: VALET - Reporting Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110626 |  |  | Local Enhancement Epic | Backlog | E-368748 | E-368748 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VALET IT CY23-3 and CY23-4 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110627 |  |  | Local Enhancement Epic | Backlog | E-369004 | E-369004 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VALET Planner | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110628 |  |  | Local Enhancement Epic | Backlog | E-176555 | E-176555 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2026-04-07
Local Enhancement Epic: VALET Scheduler CY23-3 and CY23-4 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110629 |  |  | Local Enhancement Epic | Backlog | E-368956 | E-368956 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VALET Scheduler CY24 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110630 |  |  | Local Enhancement Epic | Backlog | E-294636 | E-294636 |  |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: VALET Shift Module Enhancments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110631 |  |  | Local Enhancement Epic | Backlog | E-446656 | E-446656 |  |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Vendor clearance application retirement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110632 |  |  | Lifecycle Management Epic | Backlog | E-309229 | E-309229 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2028-04-20
Local Enhancement Epic: Vendor Management | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110634 |  |  | Local Enhancement Epic | Backlog | E-83500 | E-83500 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Vendor Payments | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110635 |  |  | Local Enhancement Epic | Backlog | E-83513 | E-83513 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Vendor rating | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110636 |  |  | Local Enhancement Epic | Backlog | E-83493 | E-83493 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Vulnerabilities & InfoSec compliance (PPM#206105) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110637 |  |  | Local Enhancement Epic | Backlog | E-295636 | E-295636 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-06-03 | 2026-06-03
Local Enhancement Epic: WAMT Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110638 |  |  | Local Enhancement Epic | Backlog | E-458754 | E-458754 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-08-06 | 2026-09-15
Local Enhancement Epic: Warehouse Documents | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110639 |  |  | Local Enhancement Epic | Backlog | E-112348 | E-112348 |  |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: WBDG E4 Migration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110640 |  |  | Local Enhancement Epic | Backlog | E-342806 | E-342806 |  |  |  |  | 0 | 0 |  | 0 | No | 2026-06-30 | 2026-06-30
Local Enhancement Epic: WBDG to Angular (WebDG) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110641 |  |  | Local Enhancement Epic | Backlog | E-438404 | E-438404 |  |  |  |  | 0 | 0 |  | 0 | No | 2025-01-31 | 2026-12-31
Local Enhancement Epic: Web Booking Tool - Booking TIme Validation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110642 |  |  | Local Enhancement Epic | Backlog | E-454378 | E-454378 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-09-11 | 2025-06-03
Local Enhancement Epic: Workbench Re-write | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110643 |  |  | Local Enhancement Epic | Backlog | E-459467 | E-459467 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-11-06 | 2027-06-08
Local Enhancement Epic: Workbench-Enhancements and Redesign in DCC,eMR,RDT | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110644 |  |  | Local Enhancement Epic | Backlog | E-154923 | E-154923 |  |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Express Dim Rounding Logic Changes | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110647 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545274 | E-545274 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Debrief MVP | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110663 | 7865 | Reduce LTP duplicate stops through launch of Debri | Biz w/ Tech Epic | Launch & Evaluate | E-81895 | E-81895 |  | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Biz w/ Tech Epic: Designated Workforce Phase 2 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110664 | 9326 | [Enabler] Designated Courier Workforce Phases 1 & | Biz w/ Tech Epic | Launch & Evaluate | E-427477 | E-427477 | 4: L | 2025-06-26 |  | 75% | 4 | 3 | 1 | 0 | No | 2025-08-11 | 2028-02-04 | 2025-06-26
Biz w/ Tech Epic: Handle PLR (Packing List Return) Process | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110665 | 6902 | Packing List Return Service iPFS | Biz w/ Tech Epic | Launch & Evaluate | E-434417 | E-434417 |  | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2025-01-06 | 2025-07-31 | 2025-06-26
Biz w/ Tech Epic: IN - India Customs Regulatory | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110666 | 7172 | [IN][Enablers]Reimagine the import clearance proce | Biz w/ Tech Epic | Launch & Evaluate | E-456611 | E-456611 |  | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Biz w/ Tech Epic: IN- India ACCS Clearance Reimagine (36315) | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110667 | 7172 | [IN][Enablers]Reimagine the import clearance proce | Biz w/ Tech Epic | Launch & Evaluate | E-456614 | E-456614 |  | 2025-06-26 |  |  | 0 | 0 |  | 0 | No |  |  | 2025-06-26
Biz w/ Tech Epic: RO Phase 1.3 - MyFedExRoute (MFR) - Increment 1 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110668 | 7627 | 06 - EU PUD Route Optimization - Integrated countr | Biz w/ Tech Epic | Launch & Evaluate | E-410752 | E-410752 |  | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-11-04 | 2025-07-31 | 2025-06-26
Biz w/ Tech Epic: SG-574030-[SRO]-Use daily SRO plan for printing di | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110669 | 9525 | Optimize On-Road Route Plan to improve OnRoad Effi | Biz w/ Tech Epic | Launch & Evaluate | E-450185 | E-450185 | 3: M | 2025-06-26 |  |  | 0 | 0 |  | 0 | No | 2024-08-28 | 2024-10-22 | 2025-06-26
Local Enhancement Epic: LAC-BR-TNT-RADAR-WEB - System improvement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110670 |  |  | Local Enhancement Epic | Backlog | E-522443 | E-522443 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Anomaly Dim Detection (HCH Buss. Rule) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110671 |  |  | Local Enhancement Epic | Backlog | E-536353 | E-536353 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-11-11 | 2026-08-19
Lifecycle Management Epic: FY26_PI3_LCM_EPART_GitHub Actions Migration | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110672 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FCA Alum/Steel Sent EDI & Automation Correct 99# | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110674 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Microsoft - Repair and Return | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110676 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Tariff Effective Dates in WTE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110687 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544245 | E-544245 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2026-08-19
Local Enhancement Epic: FXL – Siemens Energy SAP SBN / EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110688 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545533 | E-545533 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2026-06-02
Local Enhancement Epic: FY26 Work Area Planning Enhancements - LE | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110689 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Onboard DIRE to become client of RSV | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110702 |  |  | Local Enhancement Epic | Backlog | E-535479 | E-535479 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: JLA Home for EDI | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110705 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - Logitech/QAD/Arvato EDI/API Intergration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110714 |  |  | Local Enhancement Epic | Backlog | E-532358 | E-532358 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: USSC - Trailer Weights | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110716 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_Remediation of SHA1 (TEN-153953) | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110718 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SpS Migration Project Continuation to SPOTS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110719 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Dangerous Goods Handling Code Assignment | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110720 |  |  | Local Enhancement Epic | Backlog | E-533715 | E-533715 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-12-02
Local Enhancement Epic: FXL – ‘Regal Beloit’ EDI/API Integration. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110722 |  |  | Local Enhancement Epic | Backlog | E-531705 | E-531705 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Address correction and routing solution for IN | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110724 |  |  | Local Enhancement Epic | Backlog | E-531612 | E-531612 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS Create connect Intelipost API | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110725 |  |  | Local Enhancement Epic | Backlog | E-533574 | E-533574 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Major/ Minor defect in MAS User Access | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110726 |  |  | Local Enhancement Epic | Backlog | E-526316 | E-526316 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-01-13
Lifecycle Management Epic: Omnissa Intelligence SDK | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110727 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IE-GENIUS-EXPORT EX513 message | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110734 |  |  | Local Enhancement Epic | Backlog | E-534671 | E-534671 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-01 | 2026-03-31
Local Enhancement Epic: ACCS CR-ARIMFT UnloadingLocation mapping logic CR | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110743 |  |  | Local Enhancement Epic | Backlog | E-534720 | E-534720 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: iClear Connect | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110750 |  |  | Local Enhancement Epic | Build | E-546538 | E-546538 | 1: XS | 2025-10-21 |  | 100% | 1 | 1 |  | 0 | No |  |  | 2025-10-21
Local Enhancement Epic: LCC-SOI Dashboard Dispute Labels | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110751 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567694 | E-567694 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: International Economy US to CA Label | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110782 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542544 | E-542544 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PIP GUI Changes for External Image Sharing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110784 |  |  | Local Enhancement Epic | Backlog | E-526315 | E-526315 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-07-21 | 2025-08-20
Lifecycle Management Epic: Automated Test Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110786 |  |  | Lifecycle Management Epic | Backlog | E-531074 | E-531074 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Camera Tunnel & RFID Integration (Air Network) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110789 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR - New eVIR System Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110790 |  |  | Local Enhancement Epic | Backlog | E-523140 | E-523140 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Identify Motor Vehicle Report Capabilities | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110791 |  |  | Local Enhancement Epic | Backlog | E-531464 | E-531464 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-08-19
Lifecycle Management Epic: FY26_SCO_CIL_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110792 |  |  | Lifecycle Management Epic | Backlog | E-526312 | E-526312 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: 1: API develop by vendor | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110818 |  |  | Local Enhancement Epic | Backlog | E-536864 | E-536864 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2025-12-30
Lifecycle Management Epic: FY26_PI3_EU Sort _LCM uDS E2E Testing Environment | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0110826 |  |  | Lifecycle Management Epic | Backlog | E-532357 | E-532357 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-14
Local Enhancement Epic: LAC-BR-3-INFOR Inventory Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110842 |  |  | Local Enhancement Epic | Backlog | E-527726 | E-527726 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS Event and Occurences | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110843 |  |  | Local Enhancement Epic | Backlog | E-522388 | E-522388 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AU New Import Entry Fee | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110857 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: E-517654 - [MEISA] FiT launch in Saudi Arabia | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110890 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: CNDM Development | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110893 |  |  | Local Enhancement Epic | Launch & Evaluate | E-528412 | E-528412 | 2: S | 2025-07-17 |  | 100% | 4 | 4 |  | 0 | No | 2025-03-03 | 2025-10-24 | 2025-07-17
Local Enhancement Epic: Lexmark - 888 Repairable field - FRU | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110903 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541452 | E-541452 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CISCO - TPL Name Change from TNT/TNTE to FEDEX_TPL | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110904 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New CDAS view for Ground PLP (MDW) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110906 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS - Pickup API Implementation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110912 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: SCO Consumption Proof of Value | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0110956 | 136623 | TS-VL1-SC-Ship Visibility- Enabler - POV | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-07-01 | 2026-01-02
Local Enhancement Epic: LAC-BR-TNT-LMS Proof of Delivery API | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110975 |  |  | Local Enhancement Epic | Backlog | E-522449 | E-522449 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ECI-CI Set up for MCule Inc | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110976 |  |  | Local Enhancement Epic | Backlog | E-528078 | E-528078 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-02
Local Enhancement Epic: FXL GE Healthcare Broker Packets Outbound Feed | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110978 |  |  | Local Enhancement Epic | Backlog | E-531704 | E-531704 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: LAC-CT-Bulk-Ship-Labeling Create integration proc | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0110994 |  |  | Local Enhancement Epic | Backlog | E-527725 | E-527725 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Very Important Local Enhancement Work - ISRAEL | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111014 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Fellowes Canada CHB Invoicing to US Bank 2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111022 |  |  | Local Enhancement Epic | Backlog | E-525277 | E-525277 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-03-25 | 2026-06-02
Local Enhancement Epic: LAC-IBIS-Analytics analysis for long term strategy | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111030 |  |  | Local Enhancement Epic | Backlog | E-525314 | E-525314 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Account & Billing Restrictions with GRACE Upload V | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111031 |  |  | Local Enhancement Epic | Backlog | E-528430 | E-528430 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS_EDI LAC-BR-TNT-LMS_EDI adjustments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111032 |  |  | Local Enhancement Epic | Backlog | E-527724 | E-527724 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS_EDI issuance by freight payer Madei | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111035 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ACCS CR - TPE EGAC Modification | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111038 |  |  | Local Enhancement Epic | Backlog | E-530069 | E-530069 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS - Sending OCORREN by NFE to API Bru | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111040 |  |  | Local Enhancement Epic | Backlog | E-536443 | E-536443 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-LMS-TIM _KPMG and NDD | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111041 |  |  | Local Enhancement Epic | Backlog | E-527727 | E-527727 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS_EDI- read the NFE XML Dimensional W | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111042 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Apple Navigator Flight Plans | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111043 |  |  | Local Enhancement Epic | Backlog | E-524368 | E-524368 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ERN Integration in DH2 CONS Maintenance | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111059 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL – ‘Chromalloy/Intelligent’ EDI/API Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111060 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: APPLE LMS Migration - MVP3 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111061 |  |  | Local Enhancement Epic | Backlog | E-533568 | E-533568 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CW Transportation | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111062 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: CW Transportation | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111064 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: GV Surface VMS & SPVP Disaster Recovery (DR) | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111083 |  |  | Lifecycle Management Epic | Backlog | E-532697 | E-532697 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL-‘Chromalloy/Intel. Audit’ EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111086 |  |  | Local Enhancement Epic | Backlog | E-536240 | E-536240 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Lifecycle Management Epic: FY26_PI4_Platforms_LCM_Sort Rules ¦Prod Deployment | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111087 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_RunOpsSort_LCM_EAI 5158- E2E + Prod Move | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111089 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_RunOpsSort_LCM_SSRT apps Modernization | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111090 |  |  | Lifecycle Management Epic | Backlog | E-534774 | E-534774 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-22 | 2025-10-30
Local Enhancement Epic: FXE Access to ROM | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111107 |  |  | Local Enhancement Epic | Backlog | E-531076 | E-531076 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2025-10-31
Local Enhancement Epic: Cage Reason Codes for Storage Fee Computation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111130 |  |  | Local Enhancement Epic | Backlog | E-537369 | E-537369 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CREDITS MIS Archive Connection | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111131 |  |  | Local Enhancement Epic | Backlog | E-533564 | E-533564 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EDP - Application Performance Enhancements - Grp 1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111147 |  |  | Local Enhancement Epic | Backlog | E-531868 | E-531868 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2027-07-13
Local Enhancement Epic: Create dynamic/static group vendor CSP prod LDAP | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111148 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ACCS&DMS Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111149 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568627 | E-568627 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Trailer Middle Load Removal Handling in eYMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111152 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549450 | E-549450 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-20 | 2026-05-29
Local Enhancement Epic: CANIP ACCS scan post | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111202 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541862 | E-541862 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Sort Raw Scan Publisher (SRSP) GUI/Dashboard | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111241 |  |  | Local Enhancement Epic | Backlog | E-534073 | E-534073 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-26 | 2026-04-01
Local Enhancement Epic: ISRAEL - Customs Decisions Transmission to Sorter | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111245 |  |  | Local Enhancement Epic | Backlog | E-528406 | E-528406 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: EFS Data File | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111248 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GV MAX PM Scheduling/WO Return Date | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111251 |  |  | Local Enhancement Epic | Backlog | E-524204 | E-524204 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface GV MAX RO lines sequence | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111253 |  |  | Local Enhancement Epic | Backlog | E-530126 | E-530126 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SSAMI Email Notification changes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111259 |  |  | Local Enhancement Epic | Backlog | E-531173 | E-531173 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2025-10-15
Lifecycle Management Epic: FXL_FY26_SCO-IA-Customer Experience_Prod Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111284 |  |  | Lifecycle Management Epic | Backlog | E-525453 | E-525453 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI5_LCM_CIL_Support Activities of CIL Systems | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111288 |  |  | Lifecycle Management Epic | Backlog | E-524635 | E-524635 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-11-05 | 2026-03-24
Lifecycle Management Epic: FY26_PI4_LCM_CIL_Support Activities of CIL Systems | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111322 |  |  | Lifecycle Management Epic | Backlog | E-526313 | E-526313 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI5_LCM_CIL_Support Customer Activites | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111323 |  |  | Lifecycle Management Epic | Build | E-525668 | E-525668 | 1: XS | 2026-02-06 |  | 100% | 500 | 500 |  | 0 | No | 2025-11-05 | 2026-03-24 | 2026-02-06
Lifecycle Management Epic: FY26_PI4_LCM_CIL_Support Customer Activites | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111325 |  |  | Lifecycle Management Epic | Backlog | E-525665 | E-525665 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Change in ACCS Deferred invoices for India | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111327 |  |  | Local Enhancement Epic | Backlog | E-527202 | E-527202 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ZA ACCS - Archival Database Set Up | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111328 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: On demand printing of clearance labels | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111348 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: KSA clearance and sort transition with automation | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111350 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GVMAX Update VEH Equipment Type Descriptions | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111351 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: On demand printing of clearance labels | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111354 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL CA/AS400 CAD adjustments in CCP update AS400 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111366 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542252 | E-542252 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_SCO_CX ART_LCM_Salesforce, MyGTD,DocuSign | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111367 |  |  | Lifecycle Management Epic | Backlog | E-525454 | E-525454 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-23
Biz w/ Tech Epic: Grace FY25: On demand Printing of Clearance label | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111385 | 107540 | [MEISA] SA clearance & sort transition with automa | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2025-12-26
Biz w/ Tech Epic: Full Implementation with Tech Integration | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111386 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583726 | E-583726 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 3 Way Duty Recon Automation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111390 |  |  | Local Enhancement Epic | Backlog | E-533580 | E-533580 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-14 | 2025-12-22
Lifecycle Management Epic: CT47_CommonDevice_PI4_LCM_Testing_(Alpha/Beta) | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111394 |  |  | Lifecycle Management Epic | Backlog | E-531030 | E-531030 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Detention Calculations in TMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111395 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539738 | E-539738 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-26 | 2026-03-31
Lifecycle Management Epic: CY25 PI-4 Infrastructure Server Maintenance | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111396 |  |  | Lifecycle Management Epic | Backlog | E-531462 | E-531462 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: SSAMI Backend Data Expansion | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111397 |  |  | Local Enhancement Epic | Backlog | E-530624 | E-530624 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2025-10-29
Lifecycle Management Epic: CY25 PI-5 Infrastructure Server Maintenance | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111398 |  |  | Lifecycle Management Epic | Backlog | E-531465 | E-531465 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Multi-Object Detection Process Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111400 |  |  | Local Enhancement Epic | Backlog | E-537136 | E-537136 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-12-24 | 2026-04-01
Local Enhancement Epic: Spotlight API's for CDAS International(EU) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111401 | 8085 | EMR – WS6 – Develop & implement CSP PFS | Local Enhancement Epic | Assessment & Analysis | E-571635 | E-571635 | 2: S |  |  |  | 1 | 0 |  | 1 | No | 2026-03-23 | 2026-06-11
Lifecycle Management Epic: FY26_SS ART_App Server upgrade, patching | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111402 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SED Error Queue- Automate CBP Response Messages | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111403 |  |  | Local Enhancement Epic | Backlog | E-528432 | E-528432 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_TBS ART_App Server upgrade, patching | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111404 |  |  | Lifecycle Management Epic | Backlog | E-534160 | E-534160 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: CBS and Classify Migration to Cloud Enviro | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111405 |  |  | Local Enhancement Epic | Backlog | E-537363 | E-537363 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS LG EDI Customer | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111406 |  |  | Local Enhancement Epic | Backlog | E-533571 | E-533571 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: {VIS] Driver Name & Photo CDAS Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111407 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571631 | E-571631 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-03-30 | 2026-08-20
Local Enhancement Epic: FY26_PI.4_AU Domestic polygon changes for FMS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111408 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2025-10-31
Local Enhancement Epic: Capacity increase with multiple type & multiple GW | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111418 |  |  | Local Enhancement Epic | Build | E-534712 | E-534712 | 1: XS | 2025-12-03 |  | 100% | 1 | 1 |  | 0 | No | 2024-06-21 | 2025-11-07 | 2025-12-03
Local Enhancement Epic: Prod Tare weight EDI issue | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111426 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Block >24h CON & Allow ActiveIC DirectedLoadingDH2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111431 |  |  | Local Enhancement Epic | Backlog | E-536212 | E-536212 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25 PI-4 Fuel Network Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111467 |  |  | Lifecycle Management Epic | Backlog | E-531463 | E-531463 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Lifecycle Management Epic: CY25 PI-5 Fuel Network Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111470 |  |  | Lifecycle Management Epic | Backlog | E-531466 | E-531466 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Pilot Travel Centers EDI Billing for Canadian CHB | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111475 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Saudi Arabia - Automated Bank File-sFTP connection | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111476 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: AU Late Payment Fee | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0105877 | 8428 | EMR OTC- New surcharge- late domestic invoice fee | Biz w/ Tech Epic | Assessment & Analysis | E-464566 | E-464566 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-05-27 | 2025-10-31
Local Enhancement Epic: LAC Chile New IVA Digital Regulation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111492 |  |  | Local Enhancement Epic | Backlog | E-528405 | E-528405 | 1: XS |  |  |  | 1 | 0 |  | 1 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Update EDT for Chapters 98 and 99 HTS#s | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111507 |  |  | Local Enhancement Epic | Backlog | E-533570 | E-533570 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC BR New FedEx Formal Bonded Warehouse | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111508 |  |  | Local Enhancement Epic | Backlog | E-533577 | E-533577 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Outsourcing ODE 2nd screen to WNS for FR Export | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111510 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575107 | E-575107 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: India RHEL 8 Upgrade for ACCS Servers | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111515 |  |  | Lifecycle Management Epic | Backlog | E-528403 | E-528403 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-05-26
Local Enhancement Epic: FXL – ‘Apple’ EDI/API Integration. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111514 |  |  | Local Enhancement Epic | Backlog | E-534159 | E-534159 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2026-02-18
Local Enhancement Epic: Aerros Workscope Build Phase 2 and WB Plan Dates | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111516 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_LCM_AFCS.ART_IT.OPS.Excellence | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111518 |  |  | Lifecycle Management Epic | Backlog | E-536708 | E-536708 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-06-02 | 2026-05-29
Local Enhancement Epic: CCP EDM Cold Storage Document Access | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111519 |  |  | Local Enhancement Epic | Backlog | E-528404 | E-528404 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: LAC-BR-3-TNT-SISTRIN - IMPLEM OKTA AUTHENTICATION | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111540 |  |  | Lifecycle Management Epic | Backlog | E-531387 | E-531387 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automating SOIL-Automating Interception of Int pkg | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111543 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_RunOpsSort_LCM_Patching | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111562 |  |  | Lifecycle Management Epic | Build | E-534773 | E-534773 | 3: M | 2025-09-02 |  | 50% | 2 | 1 |  | 1 | No | 2025-08-22 | 2025-10-30 | 2025-09-02
Lifecycle Management Epic: FY26_SCO_RunOpsSort_LCM_WebLogic & Java Patching | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111563 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USSC - FMA Feedback Form | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111566 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: USSC - Mobile Designs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111567 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550544 | E-550544 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - FXL Salesforce - Add CargoWise ID | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111573 |  |  | Local Enhancement Epic | Backlog | E-528495 | E-528495 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-03-24
Biz w/ Tech Epic: Performance dashboards and reporting | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111590 | 114182 | FXL reporting, analytics, performance management | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: 3 Way Duty Recon Automation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111596 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Tricolor Facilities-- ONT/Bravo | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111603 | 7958 | Tricolor - Facilities Enablement-ONT/Bravo | Biz w/ Tech Epic | Build | E-536743 | E-536743 | 3: M | 2026-02-06 |  |  | 1 | 0 | 1 | 0 | No | 2024-07-22 | 2024-07-22 | 2026-02-06
Local Enhancement Epic: PVGIP RFID Application Promotion | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111636 |  |  | Local Enhancement Epic | Backlog | E-528583 | E-528583 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25_PI4_SCO-Salesforce Application Configurations | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111638 |  |  | Lifecycle Management Epic | Backlog | E-528503 | E-528503 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CY25PI4_EASE/P&D Portal Send HD Activity to CDAS | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111640 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GV Surface Maximo hosted in Azure | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111641 |  |  | Local Enhancement Epic | Backlog | E-533563 | E-533563 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_TVS_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111643 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-576590 | E-576590 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-03-16 | 2027-01-22
Local Enhancement Epic: Allow active TrackingNmbr Intercepts to allocate | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111648 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579277 | E-579277 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL – ‘Apple’ EDI/API Integration - US Exports | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111649 |  |  | Local Enhancement Epic | Backlog | E-534158 | E-534158 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Relay DH2 CONS Hierarchy to ROCS & TRIP movements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111662 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545269 | E-545269 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-04-06 | 2026-04-06
Local Enhancement Epic: Enhancement to Logic in Current PV ID 0102732 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111663 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549449 | E-549449 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Eu Sort ATWOW Alignment to Support SCO App Dev | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111664 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Creation of 1 record of LSSI codes per uDS and DH2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111666 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573924 | E-573924 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Workload and Personnel Management | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111692 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583693 | E-583693 | 5: XL |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MPS (Multi-Piece Shipment) Regulation Policy Grid | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111707 |  |  | Local Enhancement Epic | Backlog | E-528433 | E-528433 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL CA/AS400 New Surtax on Steel goods | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111709 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GRACE-Enhancements on Operations Feedback | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111741 |  |  | Local Enhancement Epic | Backlog | E-531386 | E-531386 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT-LMS-Vehicle Tracker Checklist | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111742 |  |  | Local Enhancement Epic | Backlog | E-534675 | E-534675 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: APAC_SEA_ID_CGKIP_Host To Host Regulatory CEISA 4. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111744 |  |  | Local Enhancement Epic | Backlog | E-534716 | E-534716 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2025-10-21
Local Enhancement Epic: Liberty Hardware CA Customs Brokerage EDI Billing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111746 |  |  | Local Enhancement Epic | Backlog | E-536230 | E-536230 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-01-14 | 2026-03-24
Local Enhancement Epic: CN Ecommerce solution | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111758 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: CN Ecommerce solution | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111759 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: COLO Migration of World Tariff applications | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111782 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-TNT-LMS Data Retention Automation Process | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111788 |  |  | Lifecycle Management Epic | Backlog | E-533582 | E-533582 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: P&D View | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111789 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554510 | E-554510 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-21 | 2026-10-27
Local Enhancement Epic: Commscope EDI 7501 Outbound | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111793 |  |  | Local Enhancement Epic | Backlog | E-536229 | E-536229 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: CSC Automation for Invoice dispatch and SOA | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111797 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: AU Domestic Routing label - 2D Barcode | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111841 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: LAC-BR-RLOG - New Demands PagBank | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111843 |  |  | Local Enhancement Epic | Backlog | E-531385 | E-531385 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PVG OB CAT C Declaration with English Product Name | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111851 |  |  | Local Enhancement Epic | Backlog | E-532696 | E-532696 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IL-Forced Container Update Transmission | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111854 |  |  | Local Enhancement Epic | Backlog | E-534670 | E-534670 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2027-01-18
Local Enhancement Epic: LAC-3-JDA CCA Customer Migration Analysis | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111855 |  |  | Local Enhancement Epic | Backlog | E-533579 | E-533579 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: VALET - Testing & Deployment Process Automation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111874 |  |  | Local Enhancement Epic | Backlog | E-531869 | E-531869 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-27 | 2026-04-07
Lifecycle Management Epic: CY 25 Protect Purple SCO FCC ART | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111875 |  |  | Lifecycle Management Epic | Build | E-534107 | E-534107 | 2: S | 2025-10-23 |  |  | 4 | 0 | 4 | 0 | No | 2025-08-20 | 2026-01-01 | 2025-10-23
Local Enhancement Epic: LSSI Mass Upload Tool Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111884 |  |  | Local Enhancement Epic | Build | E-532467 | E-532467 | 2: S | 2025-09-23 |  | 29.3% | 256 | 75 |  | 181 | No | 2025-08-27 | 2026-04-21 | 2025-09-23
Local Enhancement Epic: FXL – ‘American Honda’ EDI/API Integration. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111886 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541617 | E-541617 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-01-13
Local Enhancement Epic: CN Ecommerce solution by iclear | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111887 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC Costa Rica eInvoicing Changes 6/25 | Rejected | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111890 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR - LMS -LMS Business Rules Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111919 |  |  | Local Enhancement Epic | Backlog | E-534674 | E-534674 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: iCAGE - Detainment Location Information | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111921 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | Yes
Local Enhancement Epic: iCAGE Detainment Location Information | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111924 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: ICAGE Detainment Location Information | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0111927 | 7581 | Intl Soln for Warehouse Automation & Mgmt (iSWAM) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Optimizing Storage Fees at BKKIP Gateway | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111962 |  |  | Local Enhancement Epic | Backlog | E-534718 | E-534718 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26 US CHB General Rate Increase | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111966 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542259 | E-542259 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: InfoSec - LCM - PAG to PurpleID - Supply Chain Ops | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0111967 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-582373 | E-582373 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Gold Tip EDI for Southern Border CHB Entry Process | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111978 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IFM Efector Canada EDI Billing Request for CHB | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111979 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Israel - Enhance Subcos Module in NEXT | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0111993 |  |  | Local Enhancement Epic | Backlog | E-536445 | E-536445 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Update to the CF7501 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112019 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542258 | E-542258 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Implement Commitment View in ACCS Workflow | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112021 |  |  | Local Enhancement Epic | Backlog | E-536452 | E-536452 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ACCS Export - Auto Clearance for LV Shipments | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112023 |  |  | Local Enhancement Epic | Backlog | E-536451 | E-536451 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-CR Add Customs Declared Value to Chronos | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112024 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538631 | E-538631 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: BEYOND Solution for China PUD | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112048 | 91190 | [WIN] CN Ecommerce digital solution by iClear | Biz w/ Tech Epic | Build | E-532917 | E-532917 | 2: S | 2026-01-14 |  | 50% | 2 | 1 |  | 1 | No | 2025-01-01 | 2025-12-31 | 2026-01-14
Biz w/ Tech Epic: iClear Ecom for Farfetch and more customers | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112049 | 91190 | [WIN] CN Ecommerce digital solution by iClear | Biz w/ Tech Epic | Build | E-532916 | E-532916 | 2: S | 2025-08-22 |  | 66.67% | 3 | 2 | 1 | 0 | No | 2024-10-08 | 2025-12-24 | 2025-08-22
Local Enhancement Epic: Cte - Nota Técnica 2024.001 - 12/05/2025 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112054 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Cte - Nota Técnica 2024.001 - 12/05/2025 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112055 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: CIL L6 Database Decommission | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112063 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Configure FXF Inventory Application | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112090 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-TNT-BI Application Decommission | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112091 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-TNT-Discovery Application Decommission | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112092 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-TNT-Inform-BI Discovery App Decommissions | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112094 |  |  | Lifecycle Management Epic | Backlog | E-534669 | E-534669 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Lowe's EDI Changes | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112096 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Linehaul Peak Prep FY26 | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112097 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112138 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112140 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and integration development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112139 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Support of ECC /AOG requests and transportation | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112144 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112148 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-Transp Dom-TMS Retirement | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112159 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ISS/USSC Zip Code Data Source Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112160 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541722 | E-541722 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2025-10-31 | 2026-01-22
Local Enhancement Epic: LAC BR Alphanumeric Tax ID Regulatory Adequacy | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112162 |  |  | Local Enhancement Epic | Backlog | E-537365 | E-537365 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: IL-Correction in the Interpretation of Message 840 | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112164 |  |  | Local Enhancement Epic | Backlog | E-533578 | E-533578 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: TNT Legacy Cluster Decommission: App migration | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112112 | 130263 | TS-VL3-Infra-TNT-LEGACY-DECOMM | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_Closing Sort_LCM_Server Upgrades | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112183 |  |  | Lifecycle Management Epic | Backlog | E-533275 | E-533275 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2025-10-29
Local Enhancement Epic: K2 to Transmit FFM and FWB Messages via SITA | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112189 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-MX-LCCS _CITI MEXICO BANK MX INTERFACE CHANGES | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112190 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Sending data from GRACE to GCCS | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112208 | 153969 | GCCS rollout for KSA | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-12 | 2026-03-05
Lifecycle Management Epic: NetGen_FY26_PI4_Platform_LCM_Co-Location HD Logic | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112227 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112229 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: National Item Compliance Report Output | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112233 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112252 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: Customer Access EDI Setup For HVLV Bookings | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112259 |  |  | Local Enhancement Epic | Backlog | E-534375 | E-534375 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-13 | 2026-01-13
Lifecycle Management Epic: FY26_PI4_Closing Sort_LCM_Dev Security Ops | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112262 |  |  | Lifecycle Management Epic | Backlog | E-533274 | E-533274 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2026-01-22
Lifecycle Management Epic: FY26_SCO_Closing Sort_Server Patching- 0112263 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112263 |  |  | Lifecycle Management Epic | Backlog | E-533276 | E-533276 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2026-05-29
Local Enhancement Epic: UDS Sortplan Overview | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112264 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539551 | E-539551 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112266 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112267 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - Rugs USA - EDI integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112272 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: DOT-SP 15228 Flights Training Check and Tracking | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112273 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Shipment Assignment Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112275 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538324 | E-538324 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2030-02-13
Local Enhancement Epic: Leveraging FXL Portal-Invoices/Billings/Payments | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112271 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-RLOG- Improvements of Picpay Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112277 |  |  | Local Enhancement Epic | Backlog | E-534673 | E-534673 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR- ANTT Legislation OCT25 Changes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112278 |  |  | Local Enhancement Epic | Backlog | E-534672 | E-534672 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112280 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Local Enhancement Epic: UI and Integration Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112286 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: UI and Integration Development | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112287 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Support of ECC /AOG requests and transportation | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112288 | 135304 | Aerospace ECC and AOG Desk | Biz w/ Tech Epic | Assessment & Analysis | E-549165 | E-549165 | 4: L |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: COM - RMIC-STC - Add"Deliver to"-Dfrrd ROD Inv | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109064 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: UI and Integration Development | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112291 | 135304 | Aerospace ECC and AOG Desk | Biz w/ Tech Epic | Assessment & Analysis | E-549853 | E-549853 | 4: L |  |  |  | 0 | 0 |  | 0 | No | 2025-09-15 | 2026-04-30
Lifecycle Management Epic: NetGen_FY26_PI4_Platform_LCM_GitHubActions | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112339 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL CIL L6 Production Database Decommissioning | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112344 |  |  | Local Enhancement Epic | Backlog | E-536753 | E-536753 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Enhance Existing functionality (CDAS) Cartage | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112351 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-WMS-LMS/Logistics Integration with Platform | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112352 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26PI5 Contractor Settlement 1099 Testing/Posting | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112353 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-551118 | E-551118 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: MTA- MT Trailer Type Verification/Notification | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112354 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540430 | E-540430 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: ZA ACCS - Archival Database Set Up | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112355 |  |  | Lifecycle Management Epic | Backlog | E-533581 | E-533581 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_Closing Sort_LCM_BCDR | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112357 |  |  | Lifecycle Management Epic | Backlog | E-534051 | E-534051 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-21 | 2026-04-01
Local Enhancement Epic: Multi-line VLU (Vehicle Line-Up) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112358 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC LEO Devices Cell Phone Capabilities | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112359 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LAC-BR-TNT- Enable EDI between FedEx and LBT/Rio N | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112360 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538632 | E-538632 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: US-MCIS-CY25-PI04 MAX Version 9 Upgrade | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112368 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554329 | E-554329 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-06-04 | 2026-06-10
Local Enhancement Epic: US-MCIS-CY25-PI05 MAX Efficiency Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112369 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554523 | E-554523 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-08-19
Biz w/ Tech Epic: FXL Digital Product and Service Development | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112375 | 114176 | FXL digital product and services development | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-08-01 | 2026-12-31
Local Enhancement Epic: LAC-BR-3-GIS - Improvements in Tax Bookkeeping Pro | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112376 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542253 | E-542253 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PF_Upgrade OTM app from v6.5.2 to 6.5.3_Prod | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112428 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-538635 | E-538635 | 2: S |  |  |  | 1 | 0 |  | 1 | No
Local Enhancement Epic: US-MCIS-FY25-PI04 MAX Efficiency Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112435 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554521 | E-554521 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-10
Local Enhancement Epic: TH E-Tax Invoice submission to TH Revenue Dept. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112438 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539323 | E-539323 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2026-03-25 | 2026-06-02
Local Enhancement Epic: LAC-BR-TNT-LMS HERBALIFE EDI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112439 |  |  | Local Enhancement Epic | Backlog | E-537364 | E-537364 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Springs Window Fashions EDI for US CHB | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112440 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Thailand VAT Rate Change – System Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112442 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539324 | E-539324 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-09-24 | 2025-10-21
Lifecycle Management Epic: US-MCIS-MAX CY25-PI05 Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112449 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554526 | E-554526 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-10-22 | 2026-06-10
Lifecycle Management Epic: US-MCIS-MAX CY25-PI04 Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112450 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554522 | E-554522 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Spare Parts Management (SPM) Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112452 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577223 | E-577223 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_SCO_Closing Sort_Software Patching - 0112454 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112454 |  |  | Lifecycle Management Epic | Backlog | E-534052 | E-534052 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2026-06-11 | 2026-08-19
Local Enhancement Epic: Automated Device Emulator | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112455 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SG - Import Sub Certs and GST Computation | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112456 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539326 |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Springs Window Fashions EDI for US CHB Billing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112480 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: JP ACCS CR for Tax Breakdown | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112483 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539325 | E-539325 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Customer Query Phase 2 Enhancements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112484 |  |  | Local Enhancement Epic | Backlog | E-536448 | E-536448 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Automation of KYC and Clearance Document Flow | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112485 |  |  | Local Enhancement Epic | Backlog | E-536449 | E-536449 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Log Surepass IEC Hits & Enhance DMS BPO Report | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112486 |  |  | Local Enhancement Epic | Backlog | E-536444 | E-536444 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Duty Checklist Consignee Authentication | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112487 |  |  | Local Enhancement Epic | Backlog | E-536450 | E-536450 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Reopen Completed AWBs & New Trace Report | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112493 |  |  | Local Enhancement Epic | Backlog | E-536446 | E-536446 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CP Validations and Enhancements Grace | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112494 |  |  | Local Enhancement Epic | Backlog | E-537366 | E-537366 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-01-06
Local Enhancement Epic: FXL - Update Invoice SIF from TMS to include UN | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112496 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Invoice Accrual Report Line Items | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112512 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Grace General Enhancement to Support Business | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112519 |  |  | Local Enhancement Epic | Backlog | E-537370 | E-537370 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2025-10-28
Local Enhancement Epic: Customs Automation and Compliance Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112520 |  |  | Local Enhancement Epic | Backlog | E-536473 | E-536473 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-08-20 | 2026-01-06
Local Enhancement Epic: Pickup Cancellation on WeChat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112521 |  |  | Local Enhancement Epic | Backlog | E-536320 | E-536320 | 1: XS |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2025-10-08
Biz w/ Tech Epic: MOBIUS Waves 5-6 | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112543 | 104743 | MOBIUS - SURFCO - Waves 1 - 8 Implementation | Biz w/ Tech Epic | Assessment & Analysis | E-554295 | E-554295 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2025-11-03 | 2026-05-29
Lifecycle Management Epic: NetGen_Platform_LCM_MaterViewExport | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112596 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26_PI5_SCO_TN_EPART_LE_PHX/Pegasus Security | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112633 |  |  | Local Enhancement Epic | Build | E-542635 | E-542635 | 2: S | 2026-01-13 |  | 100% | 3 | 3 |  | 0 | No | 2025-11-03 | 2026-03-31 | 2026-01-13
Local Enhancement Epic: No Signature Required as Default - Europe I/B | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112645 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: APAC-SCD-Hachiko CUTERA EDI Integration CR | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112649 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: New Zealand Commodity Line CSV Upload on ACCS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Contractor Safety Management System | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112674 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539067 | E-539067 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: CDAS Views Creation in AID | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112679 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569683 | E-569683 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_SCO_LCM_PeakReadiness | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112681 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-537685 | E-537685 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-09 | 2025-11-28
Local Enhancement Epic: LAC-BR-EDI -Positivo CONEMB NFS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112721 |  |  | Local Enhancement Epic | Backlog | E-537368 | E-537368 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FY26 FXL_SCO_CX_Platform Modernization and Enhance | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112722 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549000 | E-549000 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Grace - Billing and Account restrictions and Logic | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112723 |  |  | Local Enhancement Epic | Backlog | E-537367 | E-537367 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Employee Driver Administration to CDAS for Safety | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112771 | 104036 | Employee Driver Optimization | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No
Lifecycle Management Epic: FY26_PI4_EU Sort_uDS Tech Debt CY25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112778 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-546241 | E-546241 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ROCS2.0-CDAS - testing needs support from FCF side | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112779 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539737 | E-539737 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR-Transp Dom-TMS Retirement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112780 |  |  | Lifecycle Management Epic | Backlog | E-536442 | E-536442 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: FXL - Apple ACH Report (GTD) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112783 |  |  | Local Enhancement Epic | Backlog | E-536808 | E-536808 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2026-03-24
Local Enhancement Epic: US-MCIS Maximo Integration with Everbridge | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112784 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554525 | E-554525 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-10-29 | 2027-01-20
Biz w/ Tech Epic: WS10 - Hub footprint - SCO and Platform Epic | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112790 | 7383 | WS10 - One Italy - Hub footprint | Biz w/ Tech Epic | Build | E-558652 | E-558652 | 2: S | 2026-04-10 |  |  | 2 | 0 | 1 | 1 | No | 2025-09-01 | 2026-08-31 | 2026-04-10
Biz w/ Tech Epic: Microsoft - Repair and Return v2.0 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112830 | 144046 | Microsoft - Repair and Return v2.0 | Biz w/ Tech Epic | Build | E-541056 | E-541056 | 2: S | 2026-03-24 |  |  | 1 | 0 | 1 | 0 | No | 2025-10-01 | 2026-03-31 | 2026-03-24
Biz w/ Tech Epic: Lonza - New Customer SG For SPOTS | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112839 | 153824 | Lonza - New Customer SG for SPOTS - URGENT Req. | Biz w/ Tech Epic | Assessment & Analysis | E-541055 | E-541055 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-09-01 | 2026-02-27
Local Enhancement Epic: LAC FAMIS Code Expansion | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112844 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: ACCS Business Continuity Without IE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112846 |  |  | Local Enhancement Epic | Backlog | E-536865 | E-536865 | 3: M |  |  |  | 1 | 0 |  | 1 | No | 2025-10-22 | 2026-12-31
Local Enhancement Epic: FiT DocUpload Genius Integration Fix | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112847 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112849 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Lifecycle Management Epic: FY26 SCO CLR LETS-LAC ART InfoSec LCM Updates | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112867 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-538633 | E-538633 | 1: XS |  |  |  | 1 | 0 |  | 1 | No
Lifecycle Management Epic: Genius/Gemini EU - W365 Developer Configuration | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112868 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: Genius/Gemini EU - W365 Developer Configuration | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112869 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: SmartChatBox on WeChat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112872 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544263 | E-544263 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-12-16 | 2025-11-24
Local Enhancement Epic: Modernization of SEP Service Invoker Bridge | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112874 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558038 | E-558038 | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Reject Queue Modernization | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112876 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: FXL - Enter Cases into FXL Salesforce for DM Pro | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112877 |  |  | Local Enhancement Epic | Backlog | E-537182 | E-537182 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: FXL - WorldWide Technology EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112879 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555074 | E-555074 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2026-01-14 | 2026-03-24
Local Enhancement Epic: CCTV Tech Features | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112913 |  |  | Local Enhancement Epic | Assessment & Analysis | E-538365 | E-538365 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-07-22
Local Enhancement Epic: 404 Rail Billing Issues - Fax Number Check | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112915 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545723 | E-545723 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Lifecycle Management Epic: LAC-BR: E1 Trunk RFP Implementation | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112916 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-538634 | E-538634 | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Stop Billing for Phantom & RTS within Origin | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112921 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: PUX79/STAT79 Logic Causing Wrong Shipment Origin | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112922 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580820 | E-580820 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Consumer Extract Adoption | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112924 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: LOCATE Asset Data Storage | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0109875 |  |  | Local Enhancement Epic | Backlog | E-475836 | E-475836 | 3: M |  |  |  | 0 | 0 |  | 0 | No | 2024-07-22 | 2024-11-29
Lifecycle Management Epic: FY26 SCO Surface International Patching | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0112996 |  |  | Lifecycle Management Epic | Build | E-538630 | E-538630 | 3: M | 2025-09-22 |  | 42.86% | 7 | 3 | 1 | 3 | No | 2025-08-27 | 2025-11-10 | 2025-09-22
Local Enhancement Epic: FXL Thermo Fisher LSG/QAD API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113025 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539243 | E-539243 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-11-19 | 2026-02-10
Local Enhancement Epic: LAC-BR-EDI -XML customer MMA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113026 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542257 | E-542257 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: Logic Changes to FedEx 023 Data to Vendors | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113092 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554395 | E-554395 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI4_FXL_SCO_CX_App_Mod_and_Enhancements | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113093 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Legacy ePkgInquiry (PKI) Retirement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113094 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542152 | E-542152 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-03 | 2025-10-03
Local Enhancement Epic: CDAS Views Creation in AID | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113095 |  |  | Local Enhancement Epic | Assessment & Analysis | E-541689 | E-541689 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PIP AI Configuration Enhancements and UI Update | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113107 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Remove EDD Configuration Logic Update from SEP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113108 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580826 | E-580826 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PZD Batch Upload | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113145 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: PZD Batch Upload | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113146 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: ID-APAC-ACCS C5 and C6 Host to Host of CEISA 4.0 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113161 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Batch Entry of Delivery Instructions | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113164 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552078 | E-552078 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2026-01-20
Local Enhancement Epic: LAC-BR-TNT-LMS and RADAR- Quotation Changes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113165 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542249 | E-542249 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_SCO_RCC_Fuel Network Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113166 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-539846 | E-539846 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-01-20
Lifecycle Management Epic: CY26_SCO_RCC_Infrastructure Maintenance | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113167 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-539847 | E-539847 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-01-20
Local Enhancement Epic: WT/TT Seearch API Improvement - GEMINI 2 Req. | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113168 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Filer Code Update to 1FX | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113172 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Common PLA Database | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113182 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SECRETLAB SG PTE LTD | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113201 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dock Apps Facility Locator Accuracy & Filtering | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113202 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552032 | E-552032 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: NGS GUI - provide read only access capability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113208 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552077 | E-552077 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-31 | 2026-01-12
Lifecycle Management Epic: FY26_SCO_Clearance_Regulatory_Production_Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113209 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_Clearance_Regulatory_prod_support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113210 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_Clearance_Regulatory_Prod_Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113212 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Forward Packaging Oracle Item Tracking. | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113232 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-EDI-RETORNO CONEMB customer SELENE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113236 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542251 | E-542251 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC Folio Management | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112801 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Ability for uDS to intercept no MDE shipments | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113283 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Validating 8-digit HSN for India Origin Customs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113287 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544239 | E-544239 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-08-27 | 2025-10-28
Lifecycle Management Epic: Ring Scanner Enablement for GRSIS | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113289 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542255 | E-542255 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PZD Batch Upload | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113301 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569562 | E-569562 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-16 | 2026-02-16
Local Enhancement Epic: LAC - Argentina - eInvoicing Regulatory changes | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113302 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HCH-DA Reporting Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113309 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546239 | E-546239 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-12-03 | 2026-08-19
Biz w/ Tech Epic: TKO-MAT-AeroRepair Enhancement E-482594 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113311 | 109264 | Aeroxchange (AeroRepair) functionality improvement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-03 | 2026-05-29
Local Enhancement Epic: Europe EDP Dev: Utilization and Material Type | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113313 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG&RLOG CIELO-Include "Update date" in DB | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113317 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542250 | E-542250 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Lifecycle Management Epic: SCO-CLR-EU Clearance CY26 LCM and Prod Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113319 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542254 | E-542254 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-11-12 | 2027-02-19
Local Enhancement Epic: Automate Multiple Line Items - ACCS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113360 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548513 | E-548513 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL- PSOT Dataloader | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113361 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542634 | E-542634 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Discontinue ITIH Feed to Receiver ZZ GSPSA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113362 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580823 | E-580823 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Tag KYC/CLR docs to correct flow & feed to ACCS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113363 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544240 | E-544240 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-29 | 2026-03-17
Local Enhancement Epic: INDH North Auto Primary Clearance Capability | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113364 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26 SCO GFA Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113365 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542143 | E-542143 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-02-05
Local Enhancement Epic: Port Arrival Can Only Be Sent After Shuttle Arrive | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113366 |  |  | Local Enhancement Epic | Assessment & Analysis | E-543373 | E-543373 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Repush of Clearance Request from ACCS to Microsite | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113367 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544244 | E-544244 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Duty Checklist Link Active Until OOC Issued | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113368 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544243 | E-544243 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-29 | 2026-05-26
Local Enhancement Epic: DBC & AO Telephony | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113383 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: OCE Attendance Email Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113385 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554444 | E-554444 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Local Enhancement Epic: EU Clearance ART - Local Enhancements CY26-1 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113386 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Phase 2 -Additional datasets for Daily URSA | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113395 | 7247 | URSA/LSSI Rethink- Track 1 - LSSI and URSA Build | Biz w/ Tech Epic | Assessment & Analysis | E-545324 | E-545324 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-09-22 | 2026-03-12
Local Enhancement Epic: ISRAEL - Verified H.S Code | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113405 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550557 | E-550557 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2026-01-13
Lifecycle Management Epic: CY26_SCO_RCC_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113443 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-542037 | E-542037 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2027-01-27
Local Enhancement Epic: FAAR Hardening | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113455 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dimensions Implementation for FAMIS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113456 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Dispatch Volume Assignment | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113509 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Adient API Integration. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113512 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542195 | E-542195 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-01-13
Biz w/ Tech Epic: C 1.0 - Dispatch Volume Assignment | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113513 | 8330 | Designated Workforce Phase 3 | Biz w/ Tech Epic | Build | E-553599 | E-553599 | 3: M | 2026-01-20 |  |  | 2 | 0 | 1 | 1 |  | 2024-07-22 | 2026-06-09 | 2026-01-20
Local Enhancement Epic: SSDC 1.0 to Consume CMIT Scans | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113514 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Add DOCUPLOAD as a Valid Source in EISTC | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113516 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AU Domestic GPS Courier Location Tracking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113521 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545610 | E-545610 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-15 | 2026-05-29
Local Enhancement Epic: FXL – Agilent EDI Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113522 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CQA Status Code 106 Address Verified | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113524 |  |  | Local Enhancement Epic | Assessment & Analysis | E-547394 | E-547394 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GV Surface API Infrastructure(SPVP, FADS, GVMAX) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113525 |  |  | Local Enhancement Epic | Assessment & Analysis | E-542142 | E-542142 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-08-19
Local Enhancement Epic: Export DQF Driver Files for FADV | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113526 |  |  | Local Enhancement Epic | Assessment & Analysis | E-540768 | E-540768 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-03-24
Local Enhancement Epic: LAC-BR-LOG-Customization for ASICS Customer | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113527 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544470 | E-544470 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: iClear Import Vendor Management Feature | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113537 |  |  | Local Enhancement Epic | Build | E-552542 | E-552542 | 3: M | 2026-03-05 |  | 50% | 2 | 1 | 1 | 0 |  | 2024-07-22 | 2026-08-07 | 2026-03-05
Local Enhancement Epic: EDT - Countries Not Served | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113544 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544242 | E-544242 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-04-07
Local Enhancement Epic: LAC-BR- TNT-LMS -JMS -EAN Exclusion Process | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113557 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548512 | E-548512 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Split Compliance Report for Multiple Locations | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113559 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Rlog Cielo Compatibility | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113563 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TAOIP OB ACCS ARIMFT for Customs Clearance | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113586 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Department ID Description Fix | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113588 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Watch/Clock Classification Tool | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113589 |  |  | Local Enhancement Epic | Assessment & Analysis | E-544241 | E-544241 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FORGE Pickup Transfer Capability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113590 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549100 | E-549100 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-12 | 2026-02-24
Local Enhancement Epic: Atallah Group US Inc DBA Ssense - EDI CI Setup | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113591 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548971 | E-548971 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS 66319804 Filing guidance on replacement duty | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113592 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551635 | E-551635 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [TH} E-TAX | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113634 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551078 | E-551078 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Hazmat/Dangerous Goods Manifest for all LH Movemen | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113635 | 92466 | Hazmat/Dangerous Goods Manifest for all LH Movemen | Biz w/ Tech Epic | Build | E-560607 | E-560607 | 4: L | 2026-03-16 |  |  | 4 | 0 | 2 | 2 |  | 2025-07-30 | 2027-11-09 | 2026-03-16
Lifecycle Management Epic: FY26_PI5_RunOpsSort_LCM_GitHub Actions Migration | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113637 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI5_RunOpsSort_LCM_FedEx SSL Trust Store | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113638 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CA: Calculate Additional Transit Days | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113656 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: CA: Calculate Additional Transit Days in Commit | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113657 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: CA: Calculate Additional Transit Days in Commit | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113658 | 88267 | CA Domestic Commit: Additional Transit Days | Biz w/ Tech Epic | Assessment & Analysis | E-568932 | E-568932 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2026-08-31
Biz w/ Tech Epic: CA\ Calculate Additional Transit days in commit | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113659 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: #1. AvSec Inspection & Routing | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113674 | 132985 | AvSec Phase 2 - EBR at shipment level + sort dec | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2027-04-30
Biz w/ Tech Epic: #2. Pickup with AvSec Check ID Status | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113676 | 132985 | AvSec Phase 2 - EBR at shipment level + sort dec | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-05-01 | 2027-06-30
Local Enhancement Epic: LAC Ancillary Clearance Services GRI CY26 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113688 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550276 | E-550276 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CLASS FHL PFS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113690 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LAC-BR: WeON Chat | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113691 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GRSIS SYSTEM-STA70 Posting | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113720 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SCO IN ACCS Clearance Ancillary Surcharges FY26 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0112977 |  |  | Local Enhancement Epic | Assessment & Analysis | E-539607 | E-539607 | 2: S |  |  |  | 0 | 0 |  | 0 | No
Local Enhancement Epic: GRSIS SYSTEM REQUEST FOR ASTRA LABEL | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113730 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dynamo-HIS-Overall Split Estimation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113732 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556038 | E-556038 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Lexmark - Map SP Reference | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113734 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - GTD Report Enhancement - Associated Tariffs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113735 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545532 | E-545532 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-01-13
Local Enhancement Epic: FXL Salesforce Brokerage Consent Clean-up | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113736 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545985 | E-545985 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-12-31 | 2026-03-24
Local Enhancement Epic: Isuzu Motors - EDI Tariff Stacking Map Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113737 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548973 | E-548973 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-10-13 | 2026-03-24
Local Enhancement Epic: The Boeing Company EDI Tariff Stacking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113738 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548972 | E-548972 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL- Agilent Technology Inc EDI Tariff Stacking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113741 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548970 | E-548970 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GV Surface SPVP to GVMax | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113744 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550193 | E-550193 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-10-29
Local Enhancement Epic: SG - ACCS UTC Time to Local Time | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113745 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545155 |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS 66347264 U.S. FDA Updates | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113746 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553743 |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EasySend 2.0 - Secure Unbilled Revenue | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113747 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571509 | E-571509 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SpS Finland: Customer Engaged Solution at RISK! | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113750 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EDT Modernization/Client On-boarding | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113751 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-EDI-ENTRADA - Create New Tables to IDX2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113752 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550269 | E-550269 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-CNH Industrial America LLC EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113753 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548969 | E-548969 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-SC-WMS Nestle Nespresso Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113754 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548508 | E-548508 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL iServe Adding Field for Customer Setup | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113757 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: UDS Config - Zenith Bar Code Solution | Assumed Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113782 |  |  | Local Enhancement Epic | Assessment & Analysis | E-546240 | E-546240 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL- Bos Logistics EDI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113786 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580076 | E-580076 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: WB #23-00364 Make PDSC/Tire Daily Cards eSignable | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113787 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EEI- OPA License (Other Partnership Agency) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113788 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550270 | E-550270 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Cordis Corporation EDI for U.S. CHB Billing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113793 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC Mexico Aduanapp (New Vendor) Solution | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113794 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553340 | E-553340 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Modernize ODDI in Azure | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113795 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Product Index Capacity Reclamation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113796 |  |  | Local Enhancement Epic | Assessment & Analysis | E-549127 | E-549127 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_LCM_BCDR | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113826 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-546238 | E-546238 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-22 | 2026-04-01
Lifecycle Management Epic: FY26_PI1_SCO_LCM_PeakReadiness | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113827 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-546317 | E-546317 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: C 2.0-Multiple PSD Submits? | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113829 | 8330 | Designated Workforce Phase 3 | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: C 3.0 Multiple FRO Plan Submits? | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113830 | 8330 | Designated Workforce Phase 3 | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: C 2.0-Additional PSD Attributes | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113831 | 8330 | Designated Workforce Phase 3 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-11-17 | 2026-04-30
Local Enhancement Epic: Classify Type of Sound or Color for GRSIS System | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113832 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554871 | E-554871 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-FGC- SLU_Inbound New Regulation - XML | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113852 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550268 | E-550268 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: UDS Implementation for AU PERA and SRRA Station | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113855 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552030 | E-552030 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-02-02 | 2026-02-27
Local Enhancement Epic: FY26_AU Domestic LEO Courier Scanner | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113858 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563214 | E-563214 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: Integrate Startrack PostToURL for Scan Statuses | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113859 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565042 | E-565042 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-02-09 | 2026-10-09
Local Enhancement Epic: Coordinate Pickup Work System Simplification | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113860 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550147 | E-550147 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-12-24 | 2026-08-18
Lifecycle Management Epic: LAC-BR-TNT-Pathfind-Pathfind-Mobile Retirement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113864 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-548510 | E-548510 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: PDD(TEMU) 9610 adaptation on iClear | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113870 | 115635 | PDD(TEMU) 9610 adaptation on iClear | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ZA ACCS Exports Improvements/Enhancements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113882 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548511 | E-548511 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ZA ACCS Imports Flow Management & Improvements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113883 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548507 | E-548507 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SG - ACCS - Automate Sub cert | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113888 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554274 | E-554274 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace UI enhancements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113889 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548514 | E-548514 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace - Clearance Label Layout Changes | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113890 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548504 | E-548504 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace Enhancements for Improved Efficiency | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113891 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548503 | E-548503 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-29 | 2026-05-26
Local Enhancement Epic: FXL – Bissell – EDI Tariff Stacking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113892 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548968 | E-548968 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Panasonic Avionics Corp | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113893 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Top Knobs/Hardware Resources | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113894 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SG - Medtronic Automation ( SFTP) | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113895 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553738 | E-553738 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-INCAS-PLUS - CRC Invoice Address Change | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113896 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FXL_SCO_CX_FY26_Vulnerability Remediation | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113918 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-547205 | E-547205 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-01-13
Lifecycle Management Epic: FY26_PI5_SCO_CX ART_LCM_CX_Application_Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113919 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-547206 | E-547206 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY25_PI5_SCO-Salesforce Application Configurations | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113920 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-547210 | E-547210 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-01-13
Local Enhancement Epic: Resolution for Deleted AWBs in ACCS System | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113921 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551639 | E-551639 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO_CX_FY26_PI5_Certificates, Upgrades, OKTA Suppo | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113924 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-547202 | E-547202 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-22 | 2026-01-13
Lifecycle Management Epic: FY26_SCO_CIL_Patches,Certificates,Vulnerabilities | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113925 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-545857 | E-545857 | 1: XS |  |  |  | 500 | 0 |  | 500 |  | 2024-12-20 | 2025-05-30
Local Enhancement Epic: iConnect local enhancement (smarter solution) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113926 |  |  | Local Enhancement Epic | Build | E-552803 | E-552803 | 3: M | 2026-03-09 |  | 100% | 1 | 1 |  | 0 |  | 2025-11-19 | 2026-01-30 | 2026-03-09
Lifecycle Management Epic: FY26_PI5_SCO_Sort_LCM_SOXAudit | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113928 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554719 | E-554719 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI5_SCO_Sort_LCM_Dev SecurityOps | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113929 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554718 | E-554718 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Acer - SPOTS Development | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113930 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Delivery Receipt Printing in FORGE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113931 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550906 | E-550906 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-11-11 | 2026-01-20
Lifecycle Management Epic: FY26_PI5_RunOpsSort_LCM_SSRT_GitHubActionMigration | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113933 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI5_RunOpsSort_LCM_NGS_GitHubActionsMigration | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113934 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI5_RunOpsSort_LCM_NGS_FedEx Trust Store | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113935 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI5_RunOpsSort_LCM_SSRT_FedEx SSL Trust Store | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113936 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Australia ACCS Underbond Tranship Number Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113938 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553737 | E-553737 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: India Ancillary Clearance Surcharge in FY26 | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113945 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550273 | E-550273 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AU ERQA Robotic Depalletizer - LE | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113946 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-02-27
Local Enhancement Epic: HK ACCS Label Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113947 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554276 | E-554276 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-11-26 | 2025-12-17
Local Enhancement Epic: CDAS Ingestions for LIP Initiatives | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113949 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554590 | E-554590 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-06-10
Local Enhancement Epic: LAC-BR-RLOG-New FedEx Branch NF Issuance Process | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113951 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550274 | E-550274 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL CA/AS400 - XML file ID Config for EDI feed fro | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113953 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL CA/AS400 update the BN for CAD BN Flag Y | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113954 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550275 | E-550275 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [WIN] [COMM] PDD(TEMU) 9610 adaptation on iClear | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113955 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545154 | E-545154 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-07-25 | 2025-11-07
Local Enhancement Epic: Integrated Customs Cage Mngt. Solution | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113956 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579276 | E-579276 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Philips - GTD - 232 Reporting | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113957 |  |  | Local Enhancement Epic | Assessment & Analysis | E-545986 | E-545986 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PVG ACCS POA Logic Adjust | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113959 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551050 | E-551050 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TradeSingleWindow(HK Customs New Clearance System) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113960 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583383 | E-583383 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Auto Slip Enablement in Leo | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113961 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-BI - Mviews, Views, TP - CY2026 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113985 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550271 | E-550271 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.AIR.GFO.FY26-Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113986 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-580511 | E-580511 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Eaton Corp | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113987 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Angular Upgrade - Dock and Yard SCO | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113988 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-552029 | E-552029 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-04-10
Local Enhancement Epic: iClear Connect - Shein | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113989 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551972 | E-551972 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-12-09 | 2026-02-06
Local Enhancement Epic: LAC-BR-TNT-LMS: Claims Receipt Approval Flow | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113990 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551632 | E-551632 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT- Blocked PF Issue | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0113994 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_People&Planning_ProductionSupport_Upgrade | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0113997 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554325 | E-554325 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL- HPE EDI INBOUND INVOICE INTERGRATION | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114015 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Fairway - SCO-Linehaul | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114020 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-545940 | E-545940 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Fairway - SCO-Sort | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114022 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Build | E-546537 | E-546537 | 3: M | 2025-10-30 |  | 100% | 1 | 1 |  | 0 |  | 2025-10-30 | 2026-05-29 | 2025-10-30
Biz w/ Tech Epic: Project Fairway - SCO-Global-Clearance | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114033 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-546535 | E-546535 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-10-15 | 2026-05-26
Biz w/ Tech Epic: Project Fairway - SCO - Independent ARTs | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114035 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Fairway - SCO-Independent-ARTs | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114036 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-546536 | E-546536 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-10-15 | 2026-06-03
Biz w/ Tech Epic: Project Fairway - SCO - Pick-Up & Delivery | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114037 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-546539 | E-546539 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-10-29 | 2026-08-18
Local Enhancement Epic: Display a Privacy Notice for All LEO Users in EU | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114048 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ***TEST *** 'New Request' option not available | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114088 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Project Fairway - SCO-Shipment-Operations | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114137 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-546652 | E-546652 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Update Service Code 84 Mapping FedEx to TNT | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114151 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Unified Five-Digit Series Integration | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114160 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: VEDR Enhancement CSA and KI Enhancement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114179 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: IATA Updates 2026 - Dangerous Goods | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114181 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: LAC Chile Domestic Healthcare Dashboard | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114216 |  |  | Local Enhancement Epic |  | E-555654 | E-555654 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LAC Customer Tech Edge-Cust Solution Enhancement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114219 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-551633 | E-551633 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [WIN] [COMM] Acer - Customer Requirement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114220 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551749 | E-551749 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – BWI/Livingston EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114222 |  |  | Local Enhancement Epic | Assessment & Analysis | E-548967 | E-548967 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-06-02
Local Enhancement Epic: [WIN] [COMM] Lexmark - Customer Requirements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114223 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551751 | E-551751 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY25_PI_SCO_Salesforce Application Configurations | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114226 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - ABB/William & Associates - EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114227 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560497 | E-560497 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI5_SCO_CX ART_LCM and Enhance - MGTD, DocuSi | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114228 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2024-07-22
Local Enhancement Epic: Common Auditor User Interface for KYC & Clearance. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114230 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551634 | E-551634 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-10-29 | 2026-05-26
Local Enhancement Epic: AU Reliability - CMS Performance for MyTNT2 Rates | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114231 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Goal Diggers-spDM: CSC Test Mode & Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114266 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562837 | E-562837 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GoalDiggers-spDM Stability & Usability Improvement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114267 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562836 | E-562836 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PUDCM Retirement (EAI 3532153) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114268 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561806 | E-561806 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Region Cage Scorecard Sync | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114271 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553038 | E-553038 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.AIR.GFO.FY26-Protect Purple (Patching Support) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114272 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-581704 | E-581704 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.AIR.GFO.FY26-Regulatory Requirements | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114273 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.AIR.TKO.FY26- Protect Purple (patching Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114274 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-580510 | E-580510 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.AIR.TKO.FY26-Regulatory Requirements | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114275 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Workaround FalsePositive Vintage Addr Validations | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114277 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.AIR.TKO.FY26-Production Support | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114280 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Project BEYOND (China Phase I) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114285 | 131593 | Project Beyond (phase I) | Biz w/ Tech Epic | Assessment & Analysis | E-565478 | E-565478 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-11-17 | 2027-02-26
Local Enhancement Epic: Tanzania Manifest Integration (Regulatory) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114296 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TW TPE DIM Machine Installation (3rd belt) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114298 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: App Retirment - DimWeight | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114299 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Allow Duty Field Changes on Checklist Rejection | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114300 |  |  | Local Enhancement Epic | Assessment & Analysis | E-550556 | E-550556 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-08-04
Lifecycle Management Epic: App Retirment - YES, API and WS | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114308 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Auto Assignment of Clearance AWBs to Trace Team | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114309 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551640 | E-551640 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-08-04
Local Enhancement Epic: DMS Customer Match Automation for KYC AWBs | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114310 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551637 | E-551637 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: E1: System. Svc commit - CAN GRND Resi Weekend Del | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113444 | 87034 | Canada - Domestic Ground Weekend Delivery | Biz w/ Tech Epic | Build | E-554052 | E-554052 | 3: M | 2026-03-09 |  | 33.33% | 3 | 1 | 1 | 1 |  | 2025-11-05 | 2027-01-20 | 2026-03-09
Local Enhancement Epic: Global - Aircraft PST Automation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114338 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567637 | E-567637 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: MD11 Low Mode Fueling/ Center Fuel Tank Distributi | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114337 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: MD11 Low Mode Fueling Center Fuel Tank Distriution | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114339 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Highlight High Priority Customer Account Trailers | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114341 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583144 | E-583144 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-06-11 | 2026-10-28
Local Enhancement Epic: MD11 Low Mode Center Fuel Tank Distibution | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114340 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Dynamo - HIS - SPSS Ctrl Room Enhancements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114345 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: View Edit Maintenance Screen Migration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114368 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: DUPLICATE of 00116894 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114371 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Emerson EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114384 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553551 | E-553551 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-08-11
Local Enhancement Epic: Update the POF/SRND scan shown on ePkgInquiry | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114385 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Urban/Bamboo Rose EDI/API Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114386 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Rebid for CNS Local DIM/Vacuum Maintenance Service | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114387 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CCP Report Enhancement (Instructions) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114388 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555410 | E-555410 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Italy: Enable D1 (FedEx First) for HAL | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114389 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555361 | E-555361 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GOALDIGGERS-Incremental PLfD Enhancements for 25.5 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114390 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570701 | E-570701 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL AMS & BRU CFS Project | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114391 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555059 | E-555059 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [WIN] [COMM] CISCO - Customer Requirements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114404 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552178 | E-552178 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GEHC Broker Packet Customized Response | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114405 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555060 | E-555060 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-12-03 | 2026-06-02
Local Enhancement Epic: AHM New Vendor EDI Setup | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114406 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552767 | E-552767 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-06-02
Biz w/ Tech Epic: FRO SLR Epic 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114408 | 91814 | FRO system legacy reduction to support N2.0 SSP | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ESP compliance add Stat70 to ACCS Bond in Australi | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114407 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565696 | E-565696 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Export and Exit Rules IE (Genius) | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114415 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: LAC-CL-TNT-Application Decommissions CY25 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114419 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-551636 | E-551636 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Sort By Look up phase 2 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114422 | 114013 | Sort By Lookup Phase 2 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-09-23 | 2028-11-06
Local Enhancement Epic: ITIH: Suppress HIPS Scans at (Legacy Ground) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114426 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557779 | E-557779 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: UDS Changes for Scan Compliance | In Progress | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114429 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-EDI-RETORNO - CRAL NFS Client | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114430 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-LMS: NEW TAGS DELL | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114431 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL -"AMSAFE" - sFTP/API Exchange | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114432 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DoorStep.AI (Pilot Test) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114433 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dynamo - FR/CDG - SPSS Test Automation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114472 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583142 | E-583142 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DropNet Regions | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114473 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554857 | E-554857 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL 3rd party WHS - FXE Integration via Beacon | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114480 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Enforcement of GitHub Secret Scanning & Protection | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114481 |  |  | Lifecycle Management Epic | Build | E-557399 | E-557399 | 3: M | 2026-01-08 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-26 | 2026-05-01 | 2026-01-08
Local Enhancement Epic: Request for New APP ID or Renew Current APP ID | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114483 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: NL Export and Exit Configuration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114484 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555407 | E-555407 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-20 | 2026-03-31
Local Enhancement Epic: Consume Additional Data Elements in PHUWV Needed | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114486 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569589 | E-569589 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: VALET Data Ingestion | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114514 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Update Service Code 84 Mapping FedEx to TNT | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114548 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553815 | E-553815 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: IE Export Location and Exit Configuration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114551 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555406 | E-555406 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-20 | 2026-06-09
Local Enhancement Epic: LAC-BR-RLOG CIELO_Intelipost Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114550 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560663 | E-560663 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: API for World Tariff | Closed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0113450 | 109578 | API for World Tariff | Biz w/ Tech Epic |  | E-551526 | E-551526 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Apple Changes to 810cb and MAINx Files - FXL | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114556 |  |  | Local Enhancement Epic | Assessment & Analysis | E-551102 | E-551102 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-11-05 | 2026-04-30
Local Enhancement Epic: Bond Release List Report | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114561 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555003 | E-555003 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: Proof of Concept for Enterprise Internal Tracking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114568 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556347 | E-556347 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-03-31
Lifecycle Management Epic: FY26 DSO (SCO CLR) Reg-Reim Inst-Prod Support | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114569 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-AU Book in surcharge 2.0 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114531 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-07-31 | 2026-12-31
Local Enhancement Epic: RFID Comm 90 Scan Events | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114577 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GRACE SORT Enhancement: Real-Time Info display | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114578 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555112 | E-555112 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Yanfeng/Avanzar New Vendor Billing EDI Feed | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114579 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HTMS Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114661 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581719 | E-581719 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-05-01 | 2026-07-30
Local Enhancement Epic: 9903 HTS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114663 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556925 | E-556925 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ID-APAC-ID ACCS for Class C5 of the New Regulation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114664 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562933 | E-562933 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Altice/Intelligent Audit EDI/API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114666 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: In Station Consolidated Quality Assurance VB2 | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114712 | 94029 | ISCQA #2 - VB2+ | Biz w/ Tech Epic | Assessment & Analysis | E-564579 | E-564579 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: ITAR Handling Code Preservation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114715 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Make LSRE2 Independent of Location Codes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114717 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573925 | E-573925 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Allow to Configure Which Areas Show on DH2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114718 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562747 | E-562747 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LexisNexis - SP Financial Health Checks | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114719 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571632 | E-571632 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-08-20
Local Enhancement Epic: TH ACCS Change to Support TH VAT Retirement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114720 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: JP Clearance Ancillary Charge in CY26 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114721 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555005 | E-555005 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-05 | 2025-12-31
Local Enhancement Epic: UVSDK Nest Reporting CONS with Other Form IDs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114722 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558259 | E-558259 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-16 | 2026-03-16
Local Enhancement Epic: [WIN] [COMM] LVMH iClear & ACCS Enhancment | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114723 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554275 | E-554275 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Biz w/ Tech Epic: ExpressClear - 03_Product Database | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114251 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 04_Rules Engine | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114253 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 10_AI Model Enrichment | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114260 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-12-01 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 02_HS Classification | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114247 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 05_Validation Rules | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114255 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 06_Data Quality Review | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114256 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 07_Data Schema | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114257 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 08_Feedback Loop | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114258 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 09_Pattern Recognition | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114259 | 177354 | ExpressClear for All | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-12-01 | 2028-05-31
Biz w/ Tech Epic: ExpressClear - 01_Digitization | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114238 | 143818 | ExpressClear (formerly Touchless Clearance) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0 |  | 2025-02-03 | 2028-05-31
Local Enhancement Epic: ACCS - Bill Third Party Option-Imports into India | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114758 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: UVSDK Print Command Update Zebra Printers | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114760 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Adding of QR Code on Labels Generated by GRSIS | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114761 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555152 | E-555152 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CN PEKIP Master AWB+AWB Cat D | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114776 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562918 | E-562918 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: DH2 Force Mindful Override Use | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114781 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562751 | E-562751 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC BR Informal Export New Regulation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114782 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555114 | E-555114 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Volvo EDI Tariff Stacking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114784 |  |  | Local Enhancement Epic | Assessment & Analysis | E-552768 | E-552768 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-12 | 2026-06-02
Local Enhancement Epic: PGA Regulated Data | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114786 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555111 | E-555111 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Thermo Fisher/Trames EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114787 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564740 | E-564740 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ROM - New Feature Bundle | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114788 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568439 | E-568439 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Ensure SAL is Printed to fully fit label | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114803 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562748 | E-562748 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Compliance with the Technical Notes - Tax Reform | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114798 | 131607 | LAC-BR- Brazil Tax Reform - NT Fiscal Documents | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-06-09 | 2026-01-05
Local Enhancement Epic: ANZ ACCS Identify and Stop Duplicate AWBs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114804 |  |  | Local Enhancement Epic | Assessment & Analysis | E-554550 | E-554550 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-11-12 | 2026-01-13
Local Enhancement Epic: EU Productivity & Workforce Monitoring | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114805 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CN CAT-B declaration EDI Message Adjustment for IB | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114806 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555932 | E-555932 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [EU Clearance] Filter Scans from CLASS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114807 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555409 | E-555409 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-20 | 2026-03-31
Local Enhancement Epic: Grace - Billing and ROD Enhancements V2 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114808 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Provide PPOD on TNT Online Secure Tracking Portal | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114809 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568246 | E-568246 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Lifecycle Management Epic: LAC-FGC-ESM-CIS, ARCC, Portal App Decommissions | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114837 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-555090 | E-555090 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Motion Works Warehouse IMAGE and LDAP Integration | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114838 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Kenya GRACE System Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114843 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556922 | E-556922 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-12-17 | 2025-12-17
Local Enhancement Epic: Nigeria GRACE System Enhancements | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114844 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556924 | E-556924 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Serve Robotics API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114853 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [IN] KYC Customer Portal - Eliminate Captcha | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114854 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555113 | E-555113 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Sort By Lookup Phase 2 | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114920 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FedEx to OneSource-2025 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114923 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Installation of GRSIS in CANH with Vietnam Linkage | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114924 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556921 | E-556921 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-04-30
Local Enhancement Epic: ACCS Enhancement-India (DTRC, Cancellation Sheet) | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114937 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-EBC Folio Mgmt CY26 Changes | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114938 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559275 | E-559275 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Test Environment Set Up for VN GRSIS Users | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114939 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559271 | E-559271 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS 66684128 Offset | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114940 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Add FAST ID to e-Manifest | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114941 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563619 | E-563619 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FMA - UI/UX Enhancements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114942 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EUM - Comnex Retirement (SCO) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114943 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561805 | E-561805 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2027-09-30
Local Enhancement Epic: [SA] ROD Data Flow to GCCS Logic | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114946 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559507 | E-559507 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-03-17
Local Enhancement Epic: Lenovo API Brokerage | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114955 |  |  | Local Enhancement Epic | Assessment & Analysis | E-553552 | E-553552 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL CA/AS400 GRI effective Jan.5.2026 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114957 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Posting comment scan on eops | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0114958 | 160787 | Operations Visibility to Bayan & ROD details | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-03-31
Lifecycle Management Epic: FY26_PI1_LCM_CIL_Support Activities of CIL Systems | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114978 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554873 | E-554873 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Lifecycle Management Epic: FY26_PI1_LCM_CIL_Support Customer Activities | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0114979 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-554872 | E-554872 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-01-14 | 2026-03-24
Local Enhancement Epic: Canada Time Off Manager | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114980 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561684 | E-561684 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Local Enhancement Epic: Dynamo - HIS-SPSS CDG - Automated Testing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115006 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555122 | E-555122 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Canada Scorecard / On-Line Performance Review | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115007 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561685 | E-561685 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Local Enhancement Epic: LAC-BR-RLOG Create Uninstalled Series Quantity Con | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115009 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556923 | E-556923 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FY26_AU Domestic Redcross Lifeblood - Cario TMS | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115010 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: KR ACCS Import - Value Declaration EDI update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115026 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555004 | E-555004 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EUM - CIA-ICAN | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115027 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561826 | E-561826 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2027-12-01 | 2028-03-31
Lifecycle Management Epic: InfoSec Annual Cyber Response Exercise - SC | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115028 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-557716 | E-557716 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-05 | 2026-03-13
Local Enhancement Epic: CLH CLASS Canada File Upload | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115029 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CONFIDENTIAL LRT Automation | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115030 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2025-03-28
Local Enhancement Epic: Canada Staffing Control Plan | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115039 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561861 | E-561861 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Local Enhancement Epic: Grace - Direct Integration with ZATCA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115040 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559272 | E-559272 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: NZ ACCS Multiple Suppliers for Combine Entry | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115041 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559041 | E-559041 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2025-12-16 | 2026-02-27
Local Enhancement Epic: ITAR Handling Code Preservation | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115042 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC FGC CO DEMINIMIS ELIMINATION | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115045 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555408 | E-555408 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Clearance manifest & cp matching automation | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115079 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: EAI 257- LAC-BR-BROKERAGEBILLING DECOM PLAN | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115095 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559506 | E-559506 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EUM - CIA (SCO) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115097 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555481 | E-555481 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-07-01 | 2027-02-26
Local Enhancement Epic: LEO for Venezuela to local currency update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115114 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560690 | E-560690 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-16 | 2026-03-16
Lifecycle Management Epic: FXL - SCO-CX CY26 PI1 Certificates, Upgrades, OKTA | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115133 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556372 | E-556372 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-03-24
Lifecycle Management Epic: FXL-FY26PI1-LCM-SCO-CX_App_Support-and-Enhancement | Closed | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115134 |  |  | Lifecycle Management Epic | Build | E-556371 | E-556371 | 1: XS | 2026-02-25 |  |  | 1 | 0 | 1 | 0 |  |  |  | 2026-02-25
Local Enhancement Epic: Implement GRACE for Bahrain | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115135 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: BEACON Scan Upload/GetManifest IT Support | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115136 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-CY26_PI1_SCO-Salesforce App Configurations | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115138 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556686 | E-556686 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-01-14 | 2026-03-24
Lifecycle Management Epic: FY26_AU Domestic PAF Maintenance | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115140 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575069 | E-575069 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Business Discussion Script for Familiarization | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115141 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Removal of Omnitracs (OTNav) Application | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115142 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-FY26-PI1-SCO-CX-API Platform Mod and Enhance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115143 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556671 | E-556671 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: GVMax LSSI Interface - Ops Region/District | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115144 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558745 | E-558745 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-13 | 2026-06-10
Local Enhancement Epic: GVSurface GVMax - Location data Normalization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115145 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558725 | E-558725 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-06-10
Local Enhancement Epic: GVSurface GVMax - PM Form Parent Work Order | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115146 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558724 | E-558724 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-06-10
Local Enhancement Epic: FXL - ASML FTZ EDI Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115149 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557717 | E-557717 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Speedcargo SCO Epic | In Progress | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115156 | 109589 | APAC Speedcargo Density Solution | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-06-01
Local Enhancement Epic: TH-De-minimis removal implement on January 1, 2026 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115173 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555933 | E-555933 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EUM - Kofax (SCO) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115182 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561803 | E-561803 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-31 | 2026-06-30
Local Enhancement Epic: EUM - TNT EU GroundOps Ready for Retirement (SCO) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115183 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561804 | E-561804 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2027-10-29
Biz w/ Tech Epic: Dashboarding & MVP+ Functionalities | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115213 | 7278 | Ergonomics Program/482072 | Biz w/ Tech Epic | Assessment & Analysis | E-555360 | E-555360 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-08-19
Local Enhancement Epic: Settlement LCC SOI Dispute Validation - Dashboard | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115222 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571630 | E-571630 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-06-10
Local Enhancement Epic: Publish FXE QA applied STAT Codes to SEP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115223 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567693 | E-567693 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Intel EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115226 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561641 | E-561641 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL Shein API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115229 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Koblenz New Building | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115230 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI.5_AU Domestic Google Maps API Upgrade | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115232 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-563213 | E-563213 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Lifecycle Management Epic: CY2026 Operation Solutions - Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115233 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-560751 | E-560751 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Local Enhancement Epic: FXL DuplEx Mainframe Ops Excellence Efficiency | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115235 |  |  | Local Enhancement Epic | Assessment & Analysis | E-555880 | E-555880 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Lush EDI Integration | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115249 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557718 | E-557718 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PDM (Personalized Digital Marketing) on WeChat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115251 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559443 | E-559443 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2026-02-27
Local Enhancement Epic: FY26_AU Domestic_MSSQL Auth Modernisation | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115253 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enhancement for Customs Gate Management System | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115257 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561186 | E-561186 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-12 | 2026-03-31
Lifecycle Management Epic: CY2026 Operations Solutions LCM - Hardware | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115262 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-560750 | E-560750 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Local Enhancement Epic: GRSIS deployment for HK | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115264 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Prompt to Associate SA ID to Child MPS Shipments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115265 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558260 | E-558260 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PIP with LSSI ClientID Generation, Endpoint Access | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115268 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Aggregate and Send Descriptions to AI Model | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115266 | 105850 | NMFC Update | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: SCO-SO-SF-SIC: Production Support CY26 (PIs 1-5) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115275 |  |  | Lifecycle Management Epic | Build | E-557401 | E-557401 | 3: M | 2026-01-16 |  |  | 15 | 0 | 14 | 1 |  | 2026-01-26 | 2026-01-26 | 2026-01-16
Lifecycle Management Epic: SCO-SO-SS-ST: Production Support CY26 (PIs 1-5) | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115276 |  |  | Lifecycle Management Epic | Build | E-557400 | E-557400 | 3: M | 2025-12-15 |  | 10% | 10 | 1 | 6 | 3 |  | 2026-01-21 | 2026-03-26 | 2025-12-15
Lifecycle Management Epic: CY2026 Operations Solutions LCM - Compliance | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115278 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-560752 | E-560752 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Local Enhancement Epic: Inactive Accounts HUBS Clean Up (Proposal 855427 ) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115279 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565043 | E-565043 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: ITIH - ZA Feed Removal | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115281 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580828 | E-580828 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ShipNow - Default print flag - Fix | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115282 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Insulet Corp (API Integration) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115283 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561640 | E-561640 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LAC-3S-Neopost - Application Decommission | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115307 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556926 | E-556926 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: To Add New Cage Code for EUDR Goods | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115315 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FAAR ETL & API Production Support CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115316 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-583876 | E-583876 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2027-01-19
Local Enhancement Epic: Vietnam Storage Fee Ancillary Charge | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115321 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568628 | E-568628 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FAMIS-R Production Support CY26 | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115323 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: iClear Export Sys Peak Performance Optimization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115324 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561232 | E-561232 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-07-08
Lifecycle Management Epic: SCO.P&D.Conveyanc Jan'26 to Dec'26: Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115325 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556816 | E-556816 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Lifecycle Management Epic: SCO.P&D.R&C Jan26 to Dec'26: Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115326 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556833 | E-556833 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-16 | 2026-03-16
Local Enhancement Epic: TEMU - Clearance Return System API Requirements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115327 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557434 | E-557434 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SCO.P&D.Conv CY 26 Architectural & NFRs | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115328 |  |  | Local Enhancement Epic | Assessment & Analysis | E-556835 | E-556835 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Local Enhancement Epic: Shein - Reconsolidation Function and Sending EDI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115329 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559556 | E-559556 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-02-27
Local Enhancement Epic: GENIUS (9) - New country roll-outs [Baltics] | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115330 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.P&D.PPO Jan'26 to Dec'26: Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115331 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556815 | E-556815 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: VCC Enhancements - Add Re-consolidation Feature | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115333 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559557 | E-559557 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-03-31
Local Enhancement Epic: GENIUS (9) to be Updated for New EUDR Legislation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115334 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559273 | E-559273 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-12-31
Lifecycle Management Epic: SCO_P&D_Conv PRODUCTION AND TESTING SUPPORT_CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115336 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556834 | E-556834 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Local Enhancement Epic: USD/USI/FACS/MOP - CANH Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115337 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560905 | E-560905 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-04-03
Lifecycle Management Epic: SCO_P&D_R&C PRODUCTION AND TESTING SUPPORT_CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115339 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556836 | E-556836 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AU - FMS Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115343 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563215 | E-563215 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: CDAS - 2026 ISP Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115346 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566161 | E-566161 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-01-22 | 2025-05-27
Lifecycle Management Epic: FAMIS-R Defects CY26 | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115348 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2027-01-19
Local Enhancement Epic: GENIUS (9) to Identify Dual Use and Military Goods | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115349 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559274 | E-559274 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-20 | 2026-12-31
Local Enhancement Epic: FORGE Real Time Photo Capture Feedback | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115350 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FAAR ETL & API Defects (CY25/CY26) | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115355 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-01-22 | 2027-01-19
Local Enhancement Epic: Implement GRACE for Kuwait | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115366 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560135 | E-560135 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO_P&D_PPO PRODUCTION AND TESTING SUPPORT_CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115367 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-556837 | E-556837 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2027-02-15
Local Enhancement Epic: LAC_Argentina - Online eInvoicing Enablement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115368 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559505 | E-559505 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Lifecycle Management Epic: FY26_SCO_CLR_TradeTools - Protect Purple | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115369 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-560133 | E-560133 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Ongoing Effort to Ensure CDAS Stable Operation | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115370 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enhancement Common Codes Application | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115371 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Production Support for Trade Tools for CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115372 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-560132 | E-560132 | 3: M |  |  |  | 1 | 0 |  | 1 |  | 2026-01-26 | 2026-12-31
Local Enhancement Epic: GVSurface GVMax - Integrate/Test SPVP - TEST Env | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115373 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558726 | E-558726 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-08-19
Local Enhancement Epic: GVSurface GVMax - Configure Repair Vendor Contract | Rejected | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115374 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Stop Updating Visa Route for OAK - AKL Flight | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115375 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565479 | E-565479 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [WIN][COMM] Caterpillar ACCS Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115376 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559042 | E-559042 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GENIUS (9) - CH Export - Upgrade to Passar Message | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115377 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564336 | E-564336 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: URSA Download Handheld Client | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115380 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Modernization of WT Data Services | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115382 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560136 | E-560136 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: [APAC] AU Clearance Cost Recovery | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115398 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562934 | E-562934 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2027-02-02
Local Enhancement Epic: GENIUS (9) Local Enhancements for Nordic Countries | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115399 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563668 | E-563668 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-11-10
Local Enhancement Epic: AirMax Connecting CANH Sort System | Completed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115410 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561231 | E-561231 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable SCSM for Ireland Exports in GENIUS (9) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115420 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563621 | E-563621 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-09-01
Local Enhancement Epic: LAC-BR-RLOG- New Improvement with Pagbank | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115423 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566571 | E-566571 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS SG - Character Limitation on Company Name | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115424 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559043 | E-559043 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU FOPD: Keep the Light on CY26 (Backend) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115457 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559358 | E-559358 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Local Enhancement Epic: EU FOPD: Keep the Light on CY26 (Frontend) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115458 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559359 | E-559359 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Local Enhancement Epic: IN ACCS Customs Documentation Compliance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115459 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560131 | E-560131 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: Express Connect expansion phase 1.1&1.2 (HK&JP) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115476 |  |  | Local Enhancement Epic | Assessment & Analysis | E-557833 | E-557833 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-11-10 | 2026-02-27
Local Enhancement Epic: Revvity Contax EDI/API Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115478 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575332 | E-575332 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ISRAEL - BSO Update for Broker-Handled Shipments – | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115479 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563625 | E-563625 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-02-23
Local Enhancement Epic: Broker Duty and Tax Calculator - FY26 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115480 |  |  | Local Enhancement Epic | Assessment & Analysis | E-559504 | E-559504 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-01-26 | 2026-01-26
Local Enhancement Epic: Avery Prod Corporation US Brokerage EDI Invoices | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115481 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DG Enablement on Third Party Consignee | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115492 |  |  | Local Enhancement Epic | Assessment & Analysis | E-558510 | E-558510 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-16 | 2026-03-16
Biz w/ Tech Epic: Automate and upgrade some stations (111073) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115495 | 111073 | FR ALPINE: automate and upgrade some stations | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2027-05-14
Local Enhancement Epic: LAC BR CSath Customer Interface with FedEx | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115502 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562746 | E-562746 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HCH Minimum Dim and Weight Limit Removal | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115503 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-EDI-RETORNO_LAMODA | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115506 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HUBS Notifications | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115508 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563839 | E-563839 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-25
Local Enhancement Epic: Auto Tariff Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115509 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571311 | E-571311 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable KYC Collection for High Value Shipments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115510 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560116 | E-560116 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-08-04
Local Enhancement Epic: ADFWP - Courier Random Selection Automations | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115512 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: 2- Courier Data & Business Rules Enhancement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0109314 | 6868 | Global Residential Database & Surcharge | Biz w/ Tech Epic | Assessment & Analysis | E-408943 | E-408943 | 2: S |  |  |  | 0 | 0 |  | 0 | No | 2025-12-31 | 2027-06-15
Local Enhancement Epic: Support from Clearance to Enable New Lane MAD-CUN | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115522 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566568 | E-566568 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EEI Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115524 |  |  | Local Enhancement Epic | Assessment & Analysis | E-565678 | E-565678 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TradeOne & FTN Legacy Services Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115525 |  |  | Local Enhancement Epic | Assessment & Analysis | E-560134 | E-560134 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EUM - C&D Retirement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115527 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562694 | E-562694 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-12 | 2026-12-18
Local Enhancement Epic: CA Ground Ops Document Pickup Compliance Report | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115528 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ISRAEL- Auto-Matching Process Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115529 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562819 | E-562819 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-02-23
Local Enhancement Epic: TSRA New Facility | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115538 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PL_Pila New Station | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115540 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ZA ACCS HS codes/broadband automation for LV | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115556 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563627 | E-563627 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: ZA ACCS Features Enhancements | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115558 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563626 | E-563626 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO_P&D Conveyance KLO | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115581 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-560229 | E-560229 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-01-19
Lifecycle Management Epic: SCO_P&D PPO KLO CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115582 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-564644 | E-564644 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2027-01-19
Lifecycle Management Epic: SCO_P&D RC KLO CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115583 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-561007 | E-561007 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Retrieve and Display HU Events | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115574 | 7781 | Enterprise Internal Tracking | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: JP ACCS CR to reflect FICP as the service in eAWB | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115590 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561877 | E-561877 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-12-31
Local Enhancement Epic: TAOIP OB ACCS ARIMFT for Customs Clearance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115594 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562917 | E-562917 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: LAC-FGC GT Manifest Process Update for New Regulat | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115595 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: P&D Mobile App Ecosystem Preferred Future State | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115596 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567548 | E-567548 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Gateway Operations System Enhancements - IMPTX | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115610 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563622 | E-563622 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PGA Bond Policy Alignment, Mode Agnostic | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115611 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563620 | E-563620 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS - Send D&T Payment link for additional amount | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115612 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563624 | E-563624 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: Returns Routing and Printing - FORGE | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115625 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enhancement - ACCS Export Module Port Of discharge | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115626 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563628 | E-563628 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GV Surface API Infrastructure -FADs/VMS/AIE/Garage | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115627 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563042 | E-563042 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-08-19
Local Enhancement Epic: FXL- Peak Technologies EDI for Brokerage Invoices | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115664 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Directed Handling Menu Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115665 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573926 | E-573926 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SortStack Status Autoposting (Clearance System) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115666 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: User Interface LSRE (Status Rule Engine)Exceptions | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115667 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS SG - Additional Entry Multi Line Items | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115668 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563265 | E-563265 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: [WIN] [COMM] Siemens Energy iClear Development | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115669 |  |  | Local Enhancement Epic | Assessment & Analysis | E-561752 | E-561752 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-19 | 2026-05-29
Local Enhancement Epic: Enhance Physical Handling system for Group 1 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115687 |  |  | Local Enhancement Epic | Build | E-563257 | E-563257 | 2: S | 2026-01-16 |  |  | 168 | 0 | 168 | 0 |  | 2026-01-01 | 2026-07-31 | 2026-01-16
Local Enhancement Epic: UAE ACCS - Automate DTRC Upload | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115688 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563623 | E-563623 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: Enable uDS to Identify no-MDE shipment | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115707 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Product | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115774 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Build | E-560694 | E-560694 | 5: XL | 2026-03-09 |  |  | 2 | 0 | 1 | 1 |  |  |  | 2026-03-09
Biz w/ Tech Epic: Pickup | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115775 | 7748 | AU domestic transformation due to ProIV retirement | Biz w/ Tech Epic | Assessment & Analysis | E-560691 | E-560691 | 4: L |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: ACCS TW - BSO and DR | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115786 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579331 | E-579331 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Innio/CTSI EDI/API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115789 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Cisco EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115793 |  |  | Local Enhancement Epic | Assessment & Analysis | E-562881 | E-562881 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Abbott/Data2Logistics EDI/API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115798 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CCP New GUI Enhancements Bundle | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115799 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564961 | E-564961 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Eliminate requirement for couriers to capture | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115803 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Eliminate requirement for couriers to capture | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115804 | 7695 | WS2 - Eliminate requirement for couriers to captur | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2026-08-31
Biz w/ Tech Epic: Project Fairway: Shipment Tracking for FXF Handoff | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115813 | 143555 | Project Fairway - Operations Separation Enablement | Biz w/ Tech Epic | Assessment & Analysis | E-563832 | E-563832 | 2: S |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: Molex API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115815 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Ciena EDI Database | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115816 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580413 | E-580413 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Ciena EDI7501 Data Outbound | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115817 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Ciena EDICI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115818 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566755 | E-566755 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-30 | 2026-06-02
Local Enhancement Epic: LAC-BR-RLOG and CIELO documents via MELT | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115821 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564960 | E-564960 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TMS Autoprint Modification | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115822 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575967 | E-575967 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Sett LCC SOI Adj Calc w/o Prior Qtr Occurrences | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115823 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569393 | E-569393 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-06-10
Local Enhancement Epic: ISRAEL- Automatic Sharing Improvements (Softolog) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115824 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: MY EXPORT – CHANGE DATA FLOW LOGIC | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115828 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: APAC_SEA_ID_HTH Exp Regulatory CEISA 4 phase 2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115829 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577002 | E-577002 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SG ACCS Enhancement - Bad Debt Reduction | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115830 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS to Integrate with EDM to Download Images | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115831 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564962 | E-564962 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: Apple ILS Systemic Capability | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115835 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568440 | E-568440 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-22 | 2027-01-20
Local Enhancement Epic: IN ACCS Import & Export Manifestation Alert | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115855 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566569 | E-566569 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: M&I Splits | Closed | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115856 |  |  | Local Enhancement Epic | Assessment & Analysis | E-563027 | E-563027 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: UAE ACCS - Reports | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115861 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564963 | E-564963 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-07 | 2026-05-26
Local Enhancement Epic: VN Restructure Cities - LE | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115870 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CCII & ILS Configuration for INDH 24K IP Expansion | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115873 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: MEISA ACCS UI Modernization | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115874 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566570 | E-566570 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Service Measurement: SK Exclusions | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115875 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Cancel epic | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115890 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - GTD Reporting Enhancement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115894 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Acer America EDI ntegration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115897 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566872 | E-566872 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic 3 (TEST - DO NOT USE THIS ONE) | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115904 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic 3a - for IE | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115905 | 7710 | EUM - Express Domestics final countries | Biz w/ Tech Epic | Assessment & Analysis | E-569433 | E-569433 | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ISRAEL - Security Exporter Identification Process | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115917 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL- Axalta EDI Integrate | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115918 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TW ACCS Import Bond-in Message Logic Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115919 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580307 | E-580307 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Interim CONS solution for France (111076) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115926 | 111076 | FR ALPINE: launch a combined and optimized network | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-08-31
Biz w/ Tech Epic: Decommissioning | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115935 | 7781 | Enterprise Internal Tracking | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Mercedes Benz IPD EDI Clearance Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115943 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573497 | E-573497 | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Top 7 Feature Enhance for iClear Doc Entry/Audit | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115947 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567474 | E-567474 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HS Code - Pop Up Message Alert in ACCS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115950 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567002 | E-567002 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Mirion Technologies Capintec Inc - EDI7501 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115957 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO_TN_EPART PROTECT PURPLE_CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115963 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-564350 | E-564350 | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Skyworks (Intelligent Audit) - EDI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115964 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568452 | E-568452 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-10 | 2026-06-02
Lifecycle Management Epic: SCO_TN_EPART PRODUCTION SUPPORT_CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0115965 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-564351 | E-564351 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SG Advancement Fee / Handling Fee | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115882 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568417 | E-568417 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Employee Assignment (EAI 3538652) Modernization | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115982 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GVSurface GVMax - Restrict PR/PO Material Lines | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115983 |  |  | Local Enhancement Epic | Assessment & Analysis | E-564860 | E-564860 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-10
Biz w/ Tech Epic: Azure Cloud Migration (PV#107304) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115991 | 9066 | PLANS - US Air Planning Labor & Rostering | Biz w/ Tech Epic | Assessment & Analysis | E-563960 | E-563960 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-28 | 2026-06-16
Biz w/ Tech Epic: EDP Reliability Enhancements for Global Rollout | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0115995 | 9066 | PLANS - US Air Planning Labor & Rostering | Biz w/ Tech Epic | Assessment & Analysis | E-564390 | E-564390 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-04-08 | 2026-12-31
Local Enhancement Epic: FXL 'Vishay' EDI Billing Intergration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116015 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO_TN_EPART_OPERATIONAL_EXCELLENCE_CY26 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116018 |  |  | Lifecycle Management Epic | Build | E-564337 | E-564337 | 3: M | 2026-02-09 |  |  | 6 | 0 | 1 | 5 |  |  |  | 2026-02-09
Local Enhancement Epic: Red Flag Export Shipment Analytics | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116019 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570262 | E-570262 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Early Pickup Alert Improvement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116020 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578740 | E-578740 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Consolidation Results Retrieval | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116021 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: INNOV_Automated PUX86 Posting on Sortstack | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116022 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573927 | E-573927 | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: iConnect Data to CargoWise | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116023 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566988 | E-566988 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-04-30
Local Enhancement Epic: FedEx TN Range for CREDITS Program | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116025 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567521 | E-567521 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS TW to Generate D&T Payment Note | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116026 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568418 | E-568418 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic: NC Dim Capture and Improvement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116912 | 7311 | NC Scan and Label Barcode | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ZA GRSIS ROD Label Changes/Additions | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116045 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: APAC ACCS – AWB Reuse Escapee Fix | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116046 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567112 | E-567112 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-01-14 | 2026-03-24
Local Enhancement Epic: SETT: Option to Stop Past Due Inv Notifications | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116049 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571127 | E-571127 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-08-20
Local Enhancement Epic: SETT: Inactivate FTX200 Feed from VMS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116050 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578117 | E-578117 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-08-19
Local Enhancement Epic: 2026 TSPA Annual Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116051 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571128 | E-571128 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-11-11
Local Enhancement Epic: Update IL D&T Chargeable Weight Calculation Method | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116052 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566567 | E-566567 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-04-15
Local Enhancement Epic: CSMS 67396599 DEA PGA Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116065 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566572 | E-566572 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS 67400472 Section 232 Semiconductors | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116066 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569126 | E-569126 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RlogPOSBilling - Register Rede Customer | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116074 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570259 | E-570259 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_SORT_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116075 |  |  | Lifecycle Management Epic | Build | E-568438 | E-568438 | 2: S | 2026-02-12 |  |  | 1 | 0 | 1 | 0 |  | 2026-01-22 | 2026-05-29 | 2026-02-12
Lifecycle Management Epic: FY26_SCO_Sort_LCM_Dev Securityops | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116076 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-568288 | E-568288 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GEHC Delete Date Fix | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116081 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566573 | E-566573 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS MY - Medtronics CR | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116083 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enhancements in DTRC File for D-ROD LV Shipments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116084 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571312 | E-571312 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-05-27 | 2026-08-04
Local Enhancement Epic: Update to AV Training Checks for Int'l Regions | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116085 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577104 | E-577104 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Class ODC as BSO - 3rd Party Brokerage Bus. Rule | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116104 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: InfoSec - LCM - PAG to PurpleID - Supply Chain Ops | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116105 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575174 | E-575174 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Amphenol Andrew- USB EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116106 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581558 | E-581558 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Ciena EDI invoicing to D2L | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116109 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: BYOD LEO Lite - Google Playstore LAC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116118 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574588 | E-574588 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC UY Reg Postal Shipmnts D&T Invoicing INCAS-FGC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116126 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578838 | E-578838 | 3: M |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: CDAS Integration for P&D Settlement Activity | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116127 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569561 | E-569561 | 2: S |  |  |  | 2 | 0 |  | 2
Local Enhancement Epic: LAC-BR-RLOG-Cielo Compatibility Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116128 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570263 | E-570263 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: CISCO - Customer Requirements | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116133 | 161260 | CISCO - Customer Requirements | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: HCH ESS Balancing Report | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0115931 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Bulk Shipment Import via XML File - Kenya GCCS | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116138 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577596 | E-577596 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL/CA AS400 C&R Fee Increase | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116139 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569127 | E-569127 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU Volume Transit via Spain to LAC | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116149 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: 2026 Winter Schedule K | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116152 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571621 | E-571621 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-06-01 | 2026-07-01
Local Enhancement Epic: 2026 Summer Schedule K | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116158 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571620 | E-571620 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-04-01
Local Enhancement Epic: EU FOPD: Keep the Lights on CY26 (FR Domestic) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116159 |  |  | Local Enhancement Epic | Assessment & Analysis | E-567847 | E-567847 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-01 | 2026-10-01
Local Enhancement Epic: S3 Retirement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116178 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581131 | E-581131 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EDM (Enterprise Data Management) for P&D Portal | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116197 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571276 | E-571276 | 2: S |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: FICP HAL sent to designed del stations (not LMO) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116198 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583143 | E-583143 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL Business Ops Portal (Replacement for MARS) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116200 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enhancement of GRSIS-Generated ACCS Labels | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116206 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Weekly Forecast Management (WFM) | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116217 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: CLASS Operational Planning/Booking | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116218 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Forecast Solution (Firefly) | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116219 |  |  | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: DCM Flow Planning Engine | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116221 | 157709 | Integrated Network Planning Technology | Biz w/ Tech Epic | Assessment & Analysis | E-566806 | E-566806 | 4: L |  |  |  | 4 | 0 |  | 4 |  | 2025-08-01 | 2026-09-30
Lifecycle Management Epic: LAC-BR-Systems-Retirement - SCO | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116229 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-569128 | E-569128 | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: ANZ-ART: Upgrade the Hubs Servers to RHEL9+ | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116230 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Solidigm API Mapping Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116231 |  |  | Local Enhancement Epic | Assessment & Analysis | E-566871 | E-566871 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CNDM Development & Enhancement In FY2026 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116234 |  |  | Local Enhancement Epic | Build | E-570512 | E-570512 | 1: XS | 2026-03-05 |  |  | 2 | 0 | 2 | 0 |  | 2026-03-02 | 2026-05-29 | 2026-03-05
Local Enhancement Epic: Beckman Coulter GTD Reporting Enhancement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116241 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: 3PM API Migration_Redis->Oracle Plus Enhancements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116251 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU/US D&T visibility on WeChat | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116252 |  |  | Local Enhancement Epic | Assessment & Analysis | E-568810 | E-568810 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-02-09 | 2026-04-30
Local Enhancement Epic: Enhancement to VN GRSIS-Generated Labels | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116274 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570261 | E-570261 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-04-24
Local Enhancement Epic: ACCS TW - Multi Line, Storage, BSO ,Enhanced entry | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116275 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570630 | E-570630 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: PVGIP RFID Application Promotion2 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116276 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574985 | E-574985 | 1: XS |  |  |  | 1 | 0 |  | 1 |  | 2026-03-16 | 2026-06-30
Local Enhancement Epic: SHEIN IDD-MAX | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116280 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: AWBs Are Not Getting Created for Some Countries | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116281 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Change of Invoice Date | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116283 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Issue in Saving Preference in Automation Tool | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116284 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EPIC - HTM Capability 1.5 Reporting | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116913 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: EPIC - HTM Reporting | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116914 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Signature Images are Not Getting Captured | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116293 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-Shipfast-Renewal CSB Enhancements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116294 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Residential Address Check Box on Recipient | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116295 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CY26 CLR REG Dashboard support | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116296 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0 |  | 2026-03-30 | 2026-03-30
Local Enhancement Epic: Non-Blocking Port Mismatch Handling / NB Shipments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116309 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569501 | E-569501 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-04-06 | 2026-04-06
Local Enhancement Epic: American Eagle Outfitter EDI Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116310 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FORGE Pickup Exception Scans - Popup Box | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116311 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FORGE – Popup Box for Pickup Exception Scans | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116312 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.TN.ELRS PI26.2b: L3CL Test Bed Build | Rejected | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116333 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.TN.ELRS PI26.5b: L3CL Test Bed Build | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116342 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.TN.ELRS PI26.4b: L3CL Test Bed Build | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116343 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: SCO.TN.ELRS PI26.3b: L3CL Test Bed Build | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116344 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Phinia - Copper Hill to Livingston EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116345 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573496 | E-573496 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-04 | 2026-05-29
Local Enhancement Epic: FCA- History | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116348 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573588 | E-573588 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL/CA AS400 C&R Fee ASU Default Setting | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116370 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CY26 SCO CLR REG Dashboard and Report Support | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116371 |  |  | Local Enhancement Epic | Build | E-573063 | E-573063 | 3: M | 2026-04-01 |  |  | 25 | 0 | 24 | 1 |  | 2026-03-30 | 2026-03-30 | 2026-04-01
Local Enhancement Epic: LAC U.S. VI: ACE Electronic Manifest Filing | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116373 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Deploy GRSIS in New Zealand | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116381 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Developer W365 Cloud PC SKU | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116401 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-573843 | E-573843 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-3-IBIS-Spotfire Application Decommission | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116402 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582838 | E-582838 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Romo Inc. EDI/API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116403 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: IDD MAX - FXL | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116445 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570515 | E-570515 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2026-04-30
Local Enhancement Epic: FXL - Ingram Micro - EDI Billing integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116446 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG_PicPay Status Code Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116447 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570264 | E-570264 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG_Quantum PagBank Project | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116448 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576683 | E-576683 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG_C6 Improvements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116449 |  |  | Local Enhancement Epic | Assessment & Analysis | E-570260 | E-570260 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_Sort_LCM_SOX Audit | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116450 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_Sort_LCM_SOXAudit | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116451 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-570669 | E-570669 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Otterbox EDI 944 PO Receipt Message Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116452 |  |  | Local Enhancement Epic | Assessment & Analysis | E-569225 | E-569225 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-02-17 | 2026-06-02
Local Enhancement Epic: LAC-BR-SC-WMS Optimizing Picking and INV-CABW Bran | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116453 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576682 | E-576682 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Indicator for Seller and Supplier Relation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116454 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576214 | E-576214 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-08-31
Biz w/ Tech Epic: AI-Powered validation of data quality & classifica | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116473 | 184872 | GC-VB1-Data Quality Foundation | Biz w/ Tech Epic | Assessment & Analysis | E-576321 | E-576321 | 2: S |  |  |  | 4 | 0 |  | 4 |  | 2026-03-30 | 2026-05-15
Lifecycle Management Epic: FY26_SCO_Sort_LCM_Server Upgrades/patching | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116478 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-570671 | E-570671 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-29 | 2026-05-29
Local Enhancement Epic: TMS Failing to Process Voided Checks | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116479 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577829 | E-577829 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: EMEA-S3-GSS (EAI 909263) Server Migration to RHEL9 | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116481 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-570466 | E-570466 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-02 | 2026-03-02
Local Enhancement Epic: Turbo Clear | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116483 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574076 | E-574076 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-06 | 2026-06-30
Local Enhancement Epic: PCS Modernization (Janus) Infrastructure Support | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116484 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Thermo Fisher 7501 EDI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116485 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573447 | E-573447 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT- EDI ENTRADA/RETORNO UNOVA PROJECT | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116489 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Confidence-based intelligent routing & automated | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116490 | 184872 | GC-VB1-Data Quality Foundation | Biz w/ Tech Epic | Assessment & Analysis | E-576322 | E-576322 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-04-17 | 2026-07-31
Biz w/ Tech Epic: IPP EXG, Gov, & Scalable Facilitation Framework | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116491 | 184872 | GC-VB1-Data Quality Foundation | Biz w/ Tech Epic | Assessment & Analysis | E-576320 | E-576320 | 4: L |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: LAC-BR-RLOG_REDE Add Order Number to FedEx NFe | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116514 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: BridgeOps – EBS/TMS Transition & Data Continuity | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116545 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: LAC BR BridgeOps EBS/TMS Trans & Data Continuity | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116546 | 153785 | LAC BR BridgeOps - EBS/TMS Transition Program | Biz w/ Tech Epic | Assessment & Analysis | E-580253 | E-580253 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-02-02 | 2026-09-30
Lifecycle Management Epic: LAC-BR-3-eFisc_Application Decommission | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116547 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-570265 | E-570265 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Retirement of Linehaul Equipment Webservice | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116548 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577103 | E-577103 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace - Customer experience enhacements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116554 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Grace - Customer experience enhacements | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116555 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Israel – Ministry of Economy Approval Declarations | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116557 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Israel – Ministry of Economy Approval Declarations | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116559 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: Migrate EAI 339172 (Pilot.fedex.com) to PurpleID | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116574 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: COM-GDX-Drop off scan - PAA30 TT impact fix | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0114865 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Advanced Search and Usability Enhancements | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116575 | 7781 | Enterprise Internal Tracking | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Differentiator Features | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116576 | 7781 | Enterprise Internal Tracking | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI2_LCM_CIL Support Customer Activities | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116578 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FXL_SCO_CX_FY26_PI2_Vulnerability Remediation | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116580 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575595 | E-575595 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Lifecycle Management Epic: FXL-FY26PI2-LCM-SCO-CX_App_Support-and-Enhancement | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116585 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-574697 | E-574697 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: EU WBWB- MTOW HIGH/LOW Mode | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116587 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU WBWB- WAA EQ64 Config Positions Renamed | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116588 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU WBWB- Potable Water Config (Winter Ops) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116590 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DIAL Hub UDS Integration – SCO Scope | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116593 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: NMIAL Hub UDS Integration – SCO Scope | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116594 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FXL - SCO-CX CY26 PI2 Certificates, Upgrades, OKTA | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116602 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-574699 | E-574699 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Bank Account in CSB V Preference for Capturing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116621 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Repurpose the AutoVerify Reports Landing Page for | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116622 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace - Intercepts and Bulk upload customization | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116626 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: FXL-FY26-PI2-SCO-CX-API Platform Mod and Enhance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116633 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574700 | E-574700 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PL Suwalki Station (ZWK) New Location | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116634 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-CY26_PI2_SCO-Salesforce App Configurations | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116635 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575330 | E-575330 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: FXL - Apple Air Shipments to EMEIA Onboarding - ED | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116637 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571252 | E-571252 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Provide Access via AutoVerify Reports to View User | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116644 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG_ REDE Inclusion of the NFE Order Numbe | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116647 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576680 | E-576680 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: GVMax METL2.0 testing | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116648 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-574205 | E-574205 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-10
Local Enhancement Epic: GVMax OAuth Update | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116649 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575070 | E-575070 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-10
Local Enhancement Epic: SETT: Limit Invoice Disputes to 120 Days | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116651 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578116 | E-578116 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-08-20
Local Enhancement Epic: IN ACCS Export NEFI FLAG, Freight & Other Charges | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GVSurface GVMax - Configure Repair Vendor Contract | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116653 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575067 | E-575067 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-08-19
Local Enhancement Epic: Multi-read Missorts in UDS due to Parcels Overlapp | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116660 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583645 | E-583645 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TSA/DHS AEV 26-1C | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116676 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577329 | E-577329 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Modernize Vacation System | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108985 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570591 | E-570591 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: General Search Tools | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108927 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570590 | E-570590 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Research and Admin Functions | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108928 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570592 | E-570592 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize FOCUS Reports | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108930 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570585 | E-570585 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Flight Display and Modification Tools | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108931 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570586 | E-570586 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Trip Display and Modification Tools | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108932 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570588 | E-570588 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Planning Process and Communications | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108938 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570589 | E-570589 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Background Processes and Communications | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108937 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570582 | E-570582 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Dynamic Crew Monitors | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108936 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570587 | E-570587 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Pilot Operating Experience Tools | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108934 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570583 | E-570583 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Pilot Display and Modification Tools | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108933 | 103455 | FOCUS Retirement | Biz w/ Tech Epic |  | E-570579 | E-570579 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Reserve Lines / Reserve Blocks | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108943 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570584 | E-570584 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Bid Period Processing - Custom Lines | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108947 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570573 | E-570573 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Bid Period Processing - Secondary Lines | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108946 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570580 | E-570580 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize NOQ / Qualification Tracking | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108948 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570572 | E-570572 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Trip Check-In | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108950 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570581 | E-570581 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Substitution Processes | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108957 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570575 | E-570575 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Sick / Well Tracking | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108959 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570566 | E-570566 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Crew Management | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108966 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570571 | E-570571 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Trip Information / Assignments | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108969 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570568 | E-570568 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize VIPS Reports | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108970 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570567 | E-570567 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Flight Manager Schedules | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108972 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570578 | E-570578 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Training - FLX and PRO Instructors | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108975 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570562 | E-570562 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Training IOE Processing | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108976 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570574 | E-570574 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Training - Pay Only Selections | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108977 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570563 | E-570563 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Recurrent TNG - TADs | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108979 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570565 | E-570565 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Recurrent TNG - External Interfaces | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108980 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570570 | E-570570 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Initial, Transition, Upgrade Training | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108981 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570560 | E-570560 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Vacation Bidding / Awards | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108986 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570561 | E-570561 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Vacation Buyback | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108987 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570569 | E-570569 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Special Bid and Special Intl Bid Awards | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108988 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570576 | E-570576 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize User Authorization/Menu | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108940 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570559 | E-570559 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Open Time Reporting | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108960 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570577 | E-570577 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Cancel Hotel Rooms | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108965 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570564 | E-570564 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Modernize Recurrent TNG - Operational/Reporting | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108978 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570624 | E-570624 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Pilot Make-Up Preference Inputs | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108939 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570628 | E-570628 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Pilot Volunteer Preference Inputs | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108958 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570623 | E-570623 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize System Bid Awards - Phase II | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108982 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570631 | E-570631 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Base Transfer Movements | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108984 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570627 | E-570627 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Standing Bid Award | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108983 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570625 | E-570625 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Crew Records-Seg Currency-NOQ Processing | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108971 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570626 | E-570626 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Crew Information - Inquires and Servlets | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108968 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570629 | E-570629 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize VIPS Human Resources | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108974 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570620 | E-570620 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Pilot Draft Preferences Inputs | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108954 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570618 | E-570618 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Consolidation Tracking and Maintenance | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108953 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570622 | E-570622 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Pilot CAT Status Maintenance - HIMIN | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108951 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570619 | E-570619 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Crew Pay Administrative Functions | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108942 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570621 | E-570621 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Biz w/ Tech Epic: Modernize Bank Maintenance | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0108941 | 103451 | VIPS Retirement | Biz w/ Tech Epic |  | E-570617 | E-570617 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2024-07-22 | 2028-12-29
Local Enhancement Epic: GVSurface GVMax FXG Assets | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116704 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575071 | E-575071 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-10
Local Enhancement Epic: Panasonic - EDI/AS2 Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116705 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573446 | E-573446 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GEMINI 1.0 (3538064) - Capturing Unique Values for | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116706 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578837 | E-578837 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AVSEC Priority and New Security/Regulatory Demands | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116707 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACAS IFR (Interim Final Rule) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116710 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577328 | E-577328 | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Cons Smalls Multi-Container User Notification | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116712 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Data Ingestion & Report Availability (Epic 1) | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116717 | 92782 | CUBE | Biz w/ Tech Epic | Build | E-578308 | E-578308 | 2: S | 2026-03-24 |  |  | 9 | 0 | 8 | 1 |  |  |  | 2026-03-24
Local Enhancement Epic: FXL: Global-e IDD-Max Solution for US-NL (Alo Yoga | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116731 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571253 | E-571253 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_SCO_Sort_LCM_KLO | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116732 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575241 | E-575241 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-11 | 2026-05-29
Local Enhancement Epic: SETT Contract Term Final Check Excel to CI | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116733 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578118 | E-578118 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-23 | 2026-09-01
Local Enhancement Epic: Australia DSC Payment Process Locate2u | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116734 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575068 | E-575068 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: OSC Code Split in BCN | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116735 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578135 | E-578135 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-3-Retail POS CY26-27 LAC Enhancements | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116736 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580862 | E-580862 | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: DIM Machine EOL Replacement - APAC FY26 | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116741 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LifeBlood Empty Shipper Tracking | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116742 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573775 | E-573775 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Archival of Old RMS Shipment Records and RMS Enhan | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116743 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Johnson & Johnson EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116747 |  |  | Local Enhancement Epic | Assessment & Analysis | E-571551 | E-571551 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Evaluate usage of company owned and rented vehicle | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116248 | 104451 | Rebalance owned fleet underutilized assets | Biz w/ Tech Epic |  | E-571459 | E-571459 | 2: S |  |  |  | 1 | 0 |  | 1 |  | 2026-06-11 | 2026-08-19
Lifecycle Management Epic: FY26_PI2_LCM_SPS/SPOTS_Production Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116781 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575047 | E-575047 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: LAC-BR-POSBilling Improvement on Vendors payment | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116782 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573942 | E-573942 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-Advanced Energy Indust. EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116783 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581579 | E-581579 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Siemens Healthcare - HTS Stacking Map Change | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116784 |  |  | Local Enhancement Epic | Assessment & Analysis | E-573495 | E-573495 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Create Restricted Geography | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116786 | 8894 | Enterprise Linehaul Route Optimization with Techno | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: 14 new domestic FDX to TNT mappings (D1-D7/22-26) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116795 |  |  | Local Enhancement Epic | Assessment & Analysis | E-574062 | E-574062 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: American Eagle (AEO)/GT Nexus EDI/API Integr | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116796 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575329 | E-575329 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: 3538064 DeMinimis in Gemini - FRANCE | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116797 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577597 | E-577597 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Panasonic - E2Open EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116798 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575788 | E-575788 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SI Backlog | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116801 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Cymax Group Technologies Ltd DBA Cymax Solutions | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116820 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - INFOBLOX SSUI EDI BILLING Canada AS400 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116838 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FY26_PI2_LCM_SPS/SPOTS_Patches, Certificates, Vuln | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116840 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575048 | E-575048 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Lifecycle Management Epic: FY26_PI2_LCM_SPS/SPOTS_Support Customer Activities | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116842 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-575046 | E-575046 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Google GCL/Blue Yonder/EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116844 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575331 | E-575331 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL CA/AS400 Billing - Missing CI Report | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116845 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Add New Fields in ACCS002 File | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116847 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Linking Tariffs in Databases | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116848 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CDAS: ISPA Assignment - Eff. Date and Edits | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116850 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578115 | E-578115 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-16 | 2026-08-04
Local Enhancement Epic: Estimated sort date SABRE logic adjustment at CPH | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116852 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Create Linehaul Route | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116428 | 8894 | Enterprise Linehaul Route Optimization with Techno | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Create Static Paths | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116856 | 8894 | Enterprise Linehaul Route Optimization with Techno | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Veeco 7501 Data to EDI/API Integration. | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116879 |  |  | Local Enhancement Epic | Assessment & Analysis | E-575756 | E-575756 | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Retro MRN 152250 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116889 | 152250 | Retroactive transmission of export MRN | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-02-23 | 2027-03-31
Local Enhancement Epic: ACCS :TNT/FedEx Cross-billing Report Automation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116890 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577599 | E-577599 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-05-26
Local Enhancement Epic: ACCS DWP (Delivered Without Payment) Management | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116891 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577601 | E-577601 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-05-26
Local Enhancement Epic: ACCS Easy Customs Notification Automation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116893 |  |  | Local Enhancement Epic | Assessment & Analysis | E-577598 | E-577598 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-05-26
Local Enhancement Epic: FXL – Smith & Nephew EDI Integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116894 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582935 | E-582935 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HCH Dual Scan Cleanup | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116895 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: HCH ESS Balancing Report | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116896 |  |  | Local Enhancement Epic | Assessment & Analysis | E-579102 | E-579102 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace – Archival capability & systematic intercept | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116897 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582841 | E-582841 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace – Capability to extract customer IDs for B2C | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116898 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582837 | E-582837 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Express Connect Expansion-MEISA | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116899 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Create a Report for Non-Accounting Entry to CBSA | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116901 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581765 | E-581765 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Create, Monitor and Modify Flight Plans | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0112066 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583690 | E-583690 | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Business Rules Post-Flight Analytics | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116904 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583692 | E-583692 | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Calculate and View Aircraft Performance | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116906 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583696 | E-583696 | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Receive Alerts | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116907 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583691 | E-583691 | 5: XL |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TMS DataMart Retirement | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116936 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: NonCon Scanning-1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116930 | 90009 | NonCon Scanning | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2025-06-02 | 2025-08-13
Biz w/ Tech Epic: NonCon Scanning | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116931 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: ICS2 EU Admissibility (Pre Arrival) - Release 3 | Completed | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116932 | 106149 | UCC ICS2 Release 3 | Biz w/ Tech Epic |  |  |  | 3: M | 2026-03-05 | 2026-03-05 |  | 0 | 0 |  | 0 |  |  |  | 2026-03-05 | 2026-03-05
Biz w/ Tech Epic: Distribute Flight Plan and Updates | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116916 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583694 | E-583694 | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Perform “What-If” Analysis | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116917 | 6686 | Modernized Flight Planning System | Biz w/ Tech Epic | Assessment & Analysis | E-583695 | E-583695 | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ExpressClear - Touchless Clearance Global | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116935 | 130966 | Clearance Common Data Model | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: ExpressClearance - Touchless Clearance Global | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116934 | 130966 | Clearance Common Data Model | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: FedEx Butler | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116933 | 7661 | [MEA] [RT] Clearance Digital Transformation | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: RFID Enabled Dimensional WT | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116920 | 8079 | Freight Dim WT/NSS Revenue Capture-Parent US | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116918 | 8017 | Missed Approach Fuel (MAF) | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116919 | 8017 | Missed Approach Fuel (MAF) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 5: XL |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: ISCQA VB 1 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116928 | 9494 | In-Station Consolidated Quality Assurance VB1 | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-CA AS400 - Create a Report Function for Monito | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116941 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Need ACCS Label Print Maintain RFID Type1 but New | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116942 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576107 | E-576107 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: Fix the Clearance Location for IPD/IED Shipments | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116947 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580827 | E-580827 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: MRN transmission after AWB creation 152250 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116958 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: Retro MRN 152250 | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116959 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Lifecycle Management Epic: TY26_SCO_IA_People&PlanningART_Production_Support | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0116964 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-577274 | E-577274 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PH - Import Mass AWB Search, Unclear Report, TOD | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116965 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581188 | E-581188 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG MASTER BOX | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116966 |  |  | Local Enhancement Epic | Assessment & Analysis | E-576681 | E-576681 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: 122 Tarriffs | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116967 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SPI Automation | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116968 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CCII New Intercept Add | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116969 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Jupiter 30 day to 1 year retention | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116975 | 9219 | Enhance Global Returns | Biz w/ Tech Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: I to I TP Process Module Enablement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116976 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PH - Export Processing Fee (Regulatory) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116981 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581187 | E-581187 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FY26_FMS Datamapping for LV | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0116995 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Manual QA Closure Scan Elimination | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116996 | 96381 | Manual QA Closure Scan Elimination | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-08-03 | 2026-12-21
Local Enhancement Epic: LAC-IBIS-Analytics: Create Datamart for LAC-CT-C | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117005 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable CBAM Acc. No within Customer Profiles in Ge | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117006 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582886 | E-582886 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Induct One - Proof of Concept - OLIVE BRANCH (389 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117007 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: To Add New iCage Cage Code for EUDR Goods | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117008 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Duplex Calculation of SEC232 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117010 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Express Connect (Trigger Rules) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117011 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580280 | E-580280 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-30 | 2026-03-30
Local Enhancement Epic: Local Enhancement to Express Connect Expansion | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117012 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582404 | E-582404 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-04-13 | 2026-05-29
Local Enhancement Epic: CDAS TSP Supplemental Service Settlement Pull-Back | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117017 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CDAS - Mass Change Pullback Screen Enhancements (I | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117019 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-04-01 | 2026-04-30
Lifecycle Management Epic: CY26_SCO_MEISA Clearance_LCM_SecretsRemediation | Approved | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117020 |  |  | Lifecycle Management Epic | Assessment & Analysis | E-578834 | E-578834 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CDAS - TSPA Mass Change Pullback Screen Enhancemen | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117021 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578119 | E-578119 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CTUIP OB/IB ACCS and iClear ARIMFT for Customs Cle | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117024 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580308 | E-580308 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: WBWB: Load Verification Manifest Pathway to Crew v | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117028 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Digital Fallback - Surge Event PUX-STAT79 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117036 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Digital Fallback - Surge PUX-STAT79 | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117037 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: CDAS Supplemental Service Charge Pullback Enhancem | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117048 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Hub & Outbound SBDD Functionality | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117051 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582932 | E-582932 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Hub & Outbound Loader Assignment Enhancements? | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117052 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582931 | E-582931 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Addition of CPSC Data Elements to CCP | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117053 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580861 | E-580861 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: STAR and Dimensions Hardening | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117054 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2029-01-23
Lifecycle Management Epic: STAR & Dimensions Production Support | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117055 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2027-01-19
Lifecycle Management Epic: STAR & Dimensions Defects | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117056 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2029-01-23
Local Enhancement Epic: UAE - Express Clearance | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117064 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578836 | E-578836 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-08-04
Local Enhancement Epic: Black Marker Media Selectable on DH2 App for SAL | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117065 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Auto create new CONS when continuing loading post | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117066 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Allow Trailer to Trailer and ULD to ULD nesting wi | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117067 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AirMax_Credit_Control | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117095 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Biz w/ Tech Epic: AZURE Migration - Safety Applications | Cancelled | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0107612 | 86611 | Odyssey (formerly Recharge Phase 3) | Biz w/ Tech Epic | Build |  |  | 3: M | 2026-03-13 |  |  | 0 | 0 |  | 0 | No |  |  | 2026-03-13
Local Enhancement Epic: Auto Clear RSI Screening Level Mismatch | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117099 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-IBIS-Analytics - Add CT-CDRM Datamart | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117100 |  |  | Local Enhancement Epic | Assessment & Analysis | E-578835 | E-578835 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26_TVS_Keep The Lights On (KLO) | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117104 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Requesting Access to Cartage Agents Mailbox Addres | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117105 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TMS View/Edit Daily Schedule-Column Sort Function | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117106 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581340 | E-581340 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: Protect Purple CY26 - TVS | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117109 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Automatic Intercept Republishing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117118 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Drop Box Ground Tracking Number Data Reporting | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117119 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Digital Fallback - SURGE - PUX79/STAT79 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117120 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Shipment Management | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117128 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis | E-583457 | E-583457 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Clearance | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117129 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic | Assessment & Analysis | E-583458 | E-583458 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FOC to OMT for LHE | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0116601 | 142111 | TS-VL2-ES-NetGen FOCtoOMTforLHE | Biz w/ Tech Epic |  | E-577330 | E-577330 | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-06-15 | 2027-05-14
Local Enhancement Epic: UAE- Update ROD amount / Prepayment Fee for Cash S | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117177 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580860 | E-580860 | 1: XS |  |  |  | 0 | 0 |  | 0 |  | 2026-03-18 | 2026-05-26
Local Enhancement Epic: Grace – Intercept module for managing intercepts w | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117188 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582839 | E-582839 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace – Bulk customer profile management (upload/d | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117189 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace – Missing document attributes with label pri | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117190 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582836 | E-582836 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC - MX - GP&DE - Publish COD / FTC Collection Am | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117199 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581766 | E-581766 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG- New Customer - BTG | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117201 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580441 | E-580441 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-CNH Industrial America-Duplex Database Mapping | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117202 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583442 | E-583442 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SETT: Check Date Changes-Weekly Settlement Process | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117203 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SETT: Manual Invoice Payment Plan Entry (CDAS) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117204 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SETT: Invoicing-Check Issued for Credit Processing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117205 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Microsoft CusDOC/CusDEC - Implementation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117206 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582835 | E-582835 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CDAS - ISP Action on Terminated Agreement Document | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117224 |  |  | Local Enhancement Epic |  |  |  | 1: XS
Local Enhancement Epic: KR ACCS Import – NEW EDI Specification of eCommerc | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117226 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580281 | E-580281 | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: KR ACCS Import – Additional guidelines for Value B | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117227 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580298 | E-580298 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-03-25 | 2026-06-02
Local Enhancement Epic: ExpressConnect CPSC | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117228 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582405 | E-582405 | 2: S |  |  |  | 4 | 0 |  | 4 |  | 2026-04-13 | 2026-07-30
Local Enhancement Epic: Prevent Parent into Child Nesting Loop DH2 | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117229 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: EUM - Quantum Retirement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117264 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: DG Nav - Courier ADR Points | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117279 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXU Modernization of Workbench W&B | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117297 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Canada Tread Tool | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117308 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Canada Vehicle Management System | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117309 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR -SC -Customer Portal | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117310 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581764 | E-581764 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Cordis Corporation CHB EDI Billing | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117311 |  |  | Local Enhancement Epic | Assessment & Analysis | E-581049 | E-581049 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: RO - COD Cashless Payment | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117312 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Quantum Retirement Epic | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117343 | 169174 | EUM - Quantum Retirement | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Quantum Retirement | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117344 |  |  | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: TNT Shipper Reference Number | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117353 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583356 | E-583356 | 1: XS |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: GV Surface - Security Vulnerabilities | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117354 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Regulatory change to AIM for GB-FR Goods Movement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117356 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CN Warehouse Management System with RFID | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117365 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583919 | E-583919 | 1: XS |  |  |  | 1 | 0 |  | 1
Local Enhancement Epic: UVSDK PMCD Enhancement | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117381 |  |  | Local Enhancement Epic | Assessment & Analysis | E-580631 | E-580631 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CHUT Refactor- No Regret Work (Shipment Tech Simpl | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117382 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582495 | E-582495 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-SC-WMS - Riquena Process Optmization | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117383 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Mobile Manager Access to AutoVerify Security Chec | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117385 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: TMS DataMart Retirement | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117396 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CN Storage Fee ACCS Template | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117397 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: DAFF DLS API integration | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117398 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583799 | E-583799 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dual Use Item Control in iClear Export | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117400 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR– Bringg Replacement by Driv.in | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117417 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GV Surface - Service Provider Rentals -AVs and P&D | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117419 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – VF Corp/CASS-Singapore EDI Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117421 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: AU HUBS Service Time Limitation | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117426 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582533 | E-582533 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Enable GEMINI SCSM publication to EDI uDS servers | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117439 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG CREATE API FISERV X FEDEX | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117440 |  |  | Local Enhancement Epic | Assessment & Analysis | E-582840 | E-582840 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Agency Holds Tracking Report | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117449 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC BR JDE Decom and Historical Data Migration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117451 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Set Up Grainger As A Direct Ship Supplier | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117452 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Informatica to Ab Initio Migration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117460 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC Scan Compliance Report - LAC Enabler | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117464 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Retire SpecBased FXSP EPDI (EAI 3537917) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117469 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583355 | E-583355 | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Microsoft - EDI 214/856 Trigger & Timing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117471 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FAMIS-R Timecard Entry for FAMIS(EU) | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117474 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583187 | E-583187 | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2025-07-01 | 2027-04-27
Local Enhancement Epic: PVG ACCS CNEE Name & Address Adjust | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117475 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583384 | E-583384 | 1: XS |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: OFACT File Builder | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117478 | 7247 | URSA/LSSI Rethink- Track 1 - LSSI and URSA Build | Biz w/ Tech Epic | Assessment & Analysis | E-581461 | E-581461 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT- EDI ENTRADA & LAC-BR-TNT- EDI RETORNO | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117477 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: BCA – BridgeOps Inbound Data Enablement | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117479 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TW ACCS import: comply to US CIF Threshold for X3 | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117480 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583382 | E-583382 | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: FR ALPINE: CDAS solution for France | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117485 | 111064 | FR ALPINE: optimize station org (incl CDAS dev) | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0 |  | 2026-05-01 | 2026-10-30
Biz w/ Tech Epic: OFACT6 with effective dating and file enhancements | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117490 | 7247 | URSA/LSSI Rethink- Track 1 - LSSI and URSA Build | Biz w/ Tech Epic | Assessment & Analysis | E-581498 | E-581498 | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Event Automation CW1 / Branch FRA | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117513 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-INCAS-Plus Automate Ancillary Fees Update | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117514 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Lush Manufacturing Ltd | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117515 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL- Gates-EDI/ 3rd party A3Freight Payment | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117516 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS # 67960213 - ACE Truck Manifest Enhancement: | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117517 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS 68253075 Smelt/cast, Melt/Pour | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117518 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: BOW Optimization | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117519 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LAC CL TNT Domestic Applications Decommission | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117520 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Pickup Order Flow Consistency | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117521 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Duplex System A updates | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117522 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ShipFast - CSB Screen Enhancements for Inda | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117523 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Shipfast - Three Fields Required for Capturing Sen | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117524 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: To Adjust FXL-CA Brokerage System to New Version | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117554 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-TNT-EDI ENTRADA & LAC-BR-TNT-EDI RETORNO - | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117564 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Dim Wgt. Capture Machine for Egypt, Morocco and PK | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117569 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583997 | E-583997 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS CR PVG IB CatD Field Logic | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117571 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Project FOKSI - IT Request to Support DocuSign Int | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117586 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Express Connect (Cloud Native in GCP) | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117592 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FedEx Supply Chain Forge Application | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117603 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Entry Data API Recon Shein | Approved | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117604 |  |  | Local Enhancement Epic | Assessment & Analysis | E-583646 | E-583646 | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Positve Sort Enablement in Transit Operations | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117606 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EU Clearance Vendor Communication to Sort | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117608 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Triloflow HVLV Cargowise | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117611 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: CY26 FAAR ART Security Updates | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117629 |  |  | Lifecycle Management Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: BOSCH SFTP Migration to MFT | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117636 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Tecovas API - Shipment Tracking | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117646 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: PDSM Support - VALET | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117650 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: ACCS Changes required to bill TNT shipments | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117652 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: TW ACCS import: Change declaration importer from F | On Hold | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117653 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: CSMS # 68315804 - Introduction - Consolidated Admi | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117654 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - The Topps Company - Technical Traffic EDI In | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117655 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Motorola Battery Country of Origin | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117661 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: FAMIS-R Test Environment Support CY26 | In Progress | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117663 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-01-21 | 2027-01-19
Local Enhancement Epic: Flexible Organization of X-ray Lines | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117668 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: North American Shipment Flow Plan | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117670 | 92265 | North American Shipment Flow Plan for Common Sort | Biz w/ Tech Epic | Build | E-582734 | E-582734 | 3: M | 2026-04-15 |  |  | 8 | 0 | 7 | 1 |  |  |  | 2026-04-15
Local Enhancement Epic: Clearance System (Gemini 1.0 (3538064)) Change to | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117672 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Grace - Dynamic Interception Based on Grace Fields | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117673 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Rotork Controls Inc/OPUS 4PL EDI Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117674 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC - Brazil Air Branch - CTe Issuing | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117690 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-917720-FTN-Best Choice Products Inc/OOCL EDI I | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117718 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Oshkosh Defense EDI Change from US Bank to Cass fo | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117720 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - GARMIN SFTP Image Setup | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117721 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Korea Import / Export Quick Fixes Enhancements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117724 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Document Automation Through Kofax/Tungsten Team | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117727 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: LAC-BR-3-TNT-JDE Application Decommission | Cancelled | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117411 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Evenflo-GoodBaby / Nexus EDI Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117731 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EDP Prime/Wrap Overhaul | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117732 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: EDP Dynamic Inputs & Demand Alignment | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117733 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GV Surface - Annual Tractor baseplate renewals | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117734 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: UCC-Export Followed By Transit Data availability | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117742 | 96300 | UCC-Export Followed By Transit Data availability | Biz w/ Tech Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0 |  | 2026-05-01 | 2027-01-01
Local Enhancement Epic: ExpressConnect UAT Enhancements | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117748 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Revenue Recognition | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117131 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic |  | E-583298 | E-583298 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Costing | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117133 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic |  | E-583475 | E-583475 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Invoicing/Accounting | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117130 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic |  | E-583459 | E-583459 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Reporting | Approved | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117134 | 9195 | EUM - [EUM] Global SpS | Biz w/ Tech Epic |  | E-583474 | E-583474 | 4: L |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: EU Deminimis - Clearance Tech Changes | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117758 | 187281 | Duty Deminimis removal in the European Union | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Change of IM IR Origin Trigger Logic | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117761 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL-Tecovas-EDI/API Intergration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117767 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – ‘Customer Name’ EDI/API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117768 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Ironman Scan Report in GRSIS Web UI | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117769 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: ACCS CR PVG IB CatD Field Logic adjustment | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117770 |  |  | Local Enhancement Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Arris (RC) EDI Database Setup | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117799 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: NFBRK - Communicate Address Change to Sort | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117812 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Lifecycle Management Epic: DH2 - Technical Debt Remediation and Code Rafactor | Not Started | Lifecycle Management Epic | Supply Chain Operations Portfolio | 0117813 |  |  | Lifecycle Management Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Marel EDI billing request for U.S. and Canada Cust | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117814 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: SETT: Superuser Dispute Override after Dispute Ter | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117815 |  |  | Local Enhancement Epic |  |  |  | 2: S
Local Enhancement Epic: FXL - Dexcom - EDI Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117816 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-INCAS-Plus New Ancillary Fees Implementations | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117817 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: K2 Extend CBP CSN Message Remarks Field from 20 to | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117820 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: Epic 3b for BG | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117839 | 7710 | EUM - Express Domestics final countries | Biz w/ Tech Epic | Assessment & Analysis |  |  | 4: L |  |  |  | 0 | 0 |  | 0 |  | 2026-08-03 | 2027-01-29
Biz w/ Tech Epic: LL and Hub & Spoke (111079) | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117842 | 111079 | FR ALPINE: switch to a Loose Load and Hub & Spoke | Biz w/ Tech Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Transportation Network Architecture Runway | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117854 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-BR-RLOG- ADJUSTMENTS INTEGRATION WITH ADYEN | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117856 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: IBM MAS Hosting and Managed Services with TCS | Cancelled | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117857 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: GB/XI-GENIUS-IMPORTS- Country of Origin and Countr | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117884 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL - Emerson API Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117885 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Dexcom – EDI Billing Integration | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117904 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Biz w/ Tech Epic: CVM Additional Enhancements | Not Started | Biz w/ Tech Epic | Supply Chain Operations Portfolio | 0117909 | 9243 | Banded Commit for Competitive Profitable Network | Biz w/ Tech Epic | Assessment & Analysis | [6 empty] | 0 | 0 |  | 0
Local Enhancement Epic: Interim Demand Capacity Management | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117914 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 3: M |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC-CT-ISA AR Add Bidirectional Vendor Interface | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117915 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Canada Destination Missing ITIH/EPDI Data | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117917 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: Request for iClear Enhancement on Clearance Fee Su | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117918 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 1: XS |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: LAC - French Islands eInvoicing implementation | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117920 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0
Local Enhancement Epic: FXL – Urban Outfitters/Redwood EDI Integration/Upd | Not Started | Local Enhancement Epic | Supply Chain Operations Portfolio | 0117921 |  |  | Local Enhancement Epic | Assessment & Analysis |  |  | 2: S |  |  |  | 0 | 0 |  | 0