## Sheet 1
Name | Initiative ID - Legacy Wave | Strategy Seq. ID | Initiative Type | Pod | Domain | Initiative Owner | Health Status | Status Rationale | Stage | Lifecycle Status | Lifecycle Model | Work Actual/Schedule Start | Work Actual/Schedule Finish
Business w/ Tech Initiative: Container Load Decision Support (Ring Scanner) |  | 88381 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough, Majid Ali | On Track | Placing project on hold to ensure this is not a duplicate initiative. Lifecycle has already entered an initiative that appears to be a duplication. Additionally the financial aspect of the shift in equipment is not optional since legacy equipment is no longer available for purchase. | E: L2 | On Hold | L2 Feedback Requested
Business w/ Tech Initiative: Global-Small Parcel Reusable Bag-Parent-US |  | 89380 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough, Katelyn Black | On Track | reassigned Primary I/O | E: L2 | Active | L2 Feedback Requested | 2025-06-18 | 2025-08-13
Business w/ Tech Initiative: International Off Dock Solution |  | 104244 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Makynn Ellison | On Track | This initiative is no longer needed because the main objective was accomplished by another, similar initiative (1106) | C: L1 | Cancelled | L1
Business Only Initiative: Global-ULD-Haz ULD Reduction |  | 107025 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Saarth Bhanot | On Track | Updated Financials | E: L2 | Active
Business w/ Tech Initiative: MPS Cons-Specific Tagging |  | 126536 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Stefan Gant, Dan Gleason | On Track | 07/10 - completing the LBC in order to submit to next step -adding a backup IO | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Dangerous Goods Surcharge | 80726 | 7431 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Grant Marshall, Larry Crull | On Track | Waiting on Tech evaluation timeline (DG Portfolio team) | K: L5 | Active | TEMP L5 - Enter L5 | 2024-07-22 | 2025-11-10
Business Only Initiative: Tricolor - Point-to-Catchment Enablement | 75188 | 7630 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Amanda Hewgley, Jasmine Hudgins, Sandeep Dhaliwal | On Track | Adding Jasmine Hudgins as an IO. | E: L2 | Active | TEMP L2 - Enter Value Prop | 2024-07-15 | 2025-08-21
Business Only Initiative: Global Vehicles - Eliminate Late Payment Charges | 85732 | 7911 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | James Morris, Stephen Glasl | On Track | Initiative is on track and has been rebaselined to FY25. | K: L5 | Completed | L5 - Restarted Initiative | 2024-07-05 | 2024-07-05
Business Only Initiative: Tricolor - Facilities Enablement - ANC / Saban | 17121 | 7951 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Jasmine Hudgins | On Track | Previous IO retired | E: L2 | Active | L2 Feedback Requested | 2023-01-09 | 2024-10-25
Business Only Initiative: Tricolor - Facilities Enablement - MEM / Swinnea | 17122 | 7952 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Jasmine Hudgins | On Track | 10/24: since launch we have onboarded and begun serving many large healthcare customers such as J&J, Thermo Fisher, Medtronic, etc. We have also begun building and screening export volume that is trucked to commercial linehaul gateways like Chicago to hand to FXL for final hand off to commercial carrier. Swinnea/Grizz facility is complete and functional for import and export. | E: L2 | Active | L2 Feedback Requested | 2023-02-20 | 2024-12-31
Business w/ Tech Initiative: Tricolor - Facilities Enablement - IND / Golden Ea | 17123 | 7953 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Sidney B. Smith, Amanda Hewgley, Jasmine Hudgins, Richard Wooten | Some Issues | 12/26: Added temp IO 12/9/25: due to change of scope, additional capital is being requested and going through business justification; import/ECF capabilities most likely pushed to 2027 which has been refelected in Money Step date and change in Funding milestone status 08/05/25: PM is working on approval of 30% design drawings. Project to be submitted for approval during August CMC. 05/08/2025: Initiative Supporting Architectural Documentation link required before mo8g to next stage. 05/08/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection 05/08/2025: Investment dependency connection not allowed due to not being listed as an IO on the .Tricolor Point-to-Catchment Initiavie. This request to be included on the Tricolor Point-to-Catchment was submitted. Awaiting a response. Previous IO retired | E: L2 | Active | L2 Feedback Requested | 2023-01-24 | 2027-02-26
Business w/ Tech Initiative: Tricolor – Facilities Enablement – DFW / Cowboy | 17124 | 7954 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Amanda Hewgley, Jasmine Hudgins, Stephen Glasl | Some Issues | 12/26: Added temp IO 11/12/2025: work mentioned below will be input into PV by Arvis Nichols' team as local demand to move more quickly to resolve issue and allow us to capture revenue on hold 11/11/2025: found 2 revenue systems that have not been updated with the Port Code causing issues with D&T billing (ADT & DBR)-- meetings in the works to resolve and create plan for future locations 10/16/2025: DFW went live on 10/13-- fully operational 08/05/2025: Project next steps includes obtaining temporary Certificate of Occupancy, obtain FIRMS and Port codes from CBP, Metal detector installation on 8/30/25. 05/07/2025: Initiative Supporting Architectural Documentation link required before moving to next stage. 05/07/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection 05/06/2025: Created PPM Proposal # 851209 however PPM field is not editable. PPM Project: 853655 Construction currently underway-- anticpated to be complete June 23, 2025. Seeking support for Financials and IT impacts to move to L3 to hit facility ready date-- at risk. | E: L2 | Active | L2 Feedback Requested | 2023-12-04 | 2025-10-13
Business Only Initiative: Tricolor - Facilities Enablement - LAX/ Hollywood | 32014 | 7955 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Added temp IO 11/13/25: waiting on resizing effort of enabled initiative to be able to realize benefit 08/05/25: Construction permitting completed. Previous IO retired | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-08-03 | 2026-04-01
Business w/ Tech Initiative: Tricolor - Facilities Enablement - MIA/Dolphin | 32016 | 7956 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Added temp IO 10/23/2025: MIA Dolphin is live/operational; no volume flowing through and export has not been approved by Customs 08/05/2025: Permitting has pushed the date about a month; cert of occupancy needed 05/08/2025: Initiative Supporting Architectural Documentation link required before mo8g to next stage. 05/08/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection Previous IO backup moved on | E: L2 | Active | L2 & CCH | 2023-08-14 | 2025-08-19
Business w/ Tech Initiative: Tricolor - Facilities Enablement-SLC | 33731 | 7957 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Jasmine Hudgins | On Track | 08/04/25 Cancel Initiative. Tri-Color no longer pursued at SLCR. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2023-08-07 | 2025-06-19
Business w/ Tech Initiative: Tricolor - Facilities Enablement-ONT/Bravo | 33732 | 7958 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Sidney B. Smith, Amanda Hewgley, Jasmine Hudgins, Stephen Glasl | On Track | 12/26: Added temp IO 08/05/25: Building plans have been resubmitted. Change order proposal for exterior parking lot/trailer fence recieved. Current ristk: Permitting with the City of Ontario. 05/08/2025: Initiative Supporting Architectural Documentation link required before mo8g to next stage. 05/08/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection | G: L3 | Active | TEMP L3 - Enter L3 | 2023-08-25 | 2026-09-02
Business w/ Tech Initiative: Tricolor Facilities Enablement JFK/Apple or Kenned | 68337 | 7959 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Jasmine Hudgins | On Track | This effort was completed in Feb 2025-- a separate initiative has been created for the Hangar 6 project. 08/05/25: PM stated the biggest risk will be permitting with Port Authority; diagram submitted to CBP. 05/07/2025: Initiative Supporting Architectural Documentation link required before moving to next stage. Current link shown is incorrect. 05/07/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection Previous IO retired | E: L2 | Active | L2 Feedback Requested | 2024-07-22 | 2026-09-25
Business w/ Tech Initiative: Tricolor Facilities Enablement ORD- ORDRZ Bldg 612 | 68406 | 7961 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Amanda Hewgley, Jasmine Hudgins | Some Issues | 12/26: Added temp IO 11/10/25: still no progress on stafffing for ECF at 632; exploring what would be needed at 612 for export capability in iterim 10/16/25: 612 will remain CFS and is complete from a buildout perspective; once 632 has been enabled as ECF (pending CBP staffing issues), tech will be enabled to make operational 08/05/25: Currently, 632 is a CFS location but will become ECF once build out is complete allowing for parcel volume clearance. Next Step: CBP approval on space requirements. Develop design & constructuion documents. 05/07/2025: Initiative Supporting Architectural Documentation link required before moving to next stage. Link currently listed is incorrect. 05/07/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection Previous IO retired | G: L3 | On Hold | L3 Feedback Requested | 2023-08-29 | 2026-10-01
Business w/ Tech Initiative: TriColor Facilities Enablement- EWR | 85607 | 7962 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Added temp IO 08/05/2025: Pnase 1 & 3 Construction complete. Completed Phase 3 design contract. Next steps - complete design for Phase 3. For EWRR Term A Customs Expansion, PM is coordinating a shutdowm with operations. The window for utility relocate currently limited to Sunday's / Monday. Currently working with facilities/ops to conduct a series of test on backup generator and meter building loads to increase working window required for power relocation. 05/08/2025: Initiative Supporting Architectural Documentation link required before moving to next stage. 05/08/2025: Enterprise Strategic Initiative (ESI) not editable to allow Tricolor connection 05/08/2025: Investment dependency connection not allowed due to not being listed as an IO on the Tricolor Point-to-Catchment Initiavie. This request to be included on the Tricolor Point-to-Catchment was submitted. Awaiting a response. Previous IO retired | C: L1 | Active | L1 Feedback Requested | 2023-08-29 | 2026-04-24
Business Only Initiative: Local Overgoods Reductions | 80628 | 8158 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Buck Miller, Walter Kirkeminde |  | In testing mode with ONTR and HHRA. July is gather data month. On Track. cxl since field locations do not roll up under mem og. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2024-07-22 | 2024-09-04
Business Only Initiative: Toll Violation Fee Reductions | 12420 | 8253 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Kraig Robertson | On Track | Currently being re-baselined. | K: L5 | Completed | L5 | 2023-04-05 | 2023-11-30
Business w/ Tech Initiative: Enabler - Add polybag packaging type | 67808 | 8317 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Makynn Ellison | On Track | Putting this initiative on hold until the larger projects it can enable are approved and moving forward. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: CTV Trucking Planning and Execution | 1236 | 8828 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Shane Floyd, Steven Lowder, Javier Martinez | On Track | YTD: $13.618 Plan: $9.918 Currently ahead of plan because the ability to eliminate contract carrier cost has been higher than originally projected. Engineering and operators have been aggressive, and execution has been outstanding. | K: L5 | Completed | L5 | 2022-11-09 | 2023-01-31
Business w/ Tech Initiative: Tricolor- Facilities Enablement ATLR (FOPRT)/ Bull |  | 89406 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Added temp IO 08/20/2025: Architectural Documentation updated along with Impacted Portfolios. More information needed on not allowing this initiative as an Enable. 05/08/2025: Investment dependency connection not allowed 05/08/2025: Initiative Supporting Architectural Documentation link required before next stage. 05/08/2025: Investment dependency connection not allowed due to not being listed as an IO on the Tricolor Point-to-Catchment Initiavie. Request to be included on the Tricolor Point-to-Catchment was submitted. Awaiting a response. Added backup IO | C: L1 | Active | L1 Feedback Requested | 2024-09-04 | 2026-05-08
Business Only Initiative: ULD Purchase Price and Repair Services | 3089 | 8986 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Laurin Murk, Kyle Mitchell | On Track |  | K: L5 | Completed | L5 | 2023-01-09 | 2023-06-30
Business w/ Tech Initiative: Tricolor- Facilities Enablement OAK/Raider |  | 90967 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Added temp IO 08/05/2025: Project scope change. PM is updating the scope from a full tr-color facility to an off-site customs cage. 05/08/2025: Initiative Supporting Architectural Documentation link required before mo8g to next stage. 05/08/2025: Investment dependency connection not allowed due to not being listed as an IO on the Tricolor Point-to-Catchment Initiavie. This request to be included on the Tricolor Point-to-Catchment was submitted. Awaiting a response. Added PEO's | C: L1 | Active | L1 Feedback Requested | 2024-07-22 | 2026-06-05
Business w/ Tech Initiative: Tri-Color Facilities Enablement- SEART |  | 94479 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Jasmine Hudgins, Amanda Hewgley | On Track | 12/26: Added temp IO 08/05/2025: Everything approved and moving forward; GTS is planning to meet with CBP once DFWis complete 05/08/2025: Initiative Supporting Architectural Documentation link required before moving to next stage. | C: L1 | Active | L1 Feedback Requested | 2024-12-18 | 2026-08-14
Business Only Initiative: Feb 25 Network Efficiency |  | 97218 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Chuck Pounders | On Track | The decision was made to not enter business as usual activities into Planview. The JAN25 Network Efficiencies was the only one that was counted towards FY25. | C: L1 | Cancelled | L1
Business Only Initiative: Global Hub and Ramp SOP |  | 141875 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Mario Magparangalan | On Track | Primary Initiative Owner retired. A new IO will be assigned. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Mini-Sort Piece Counts |  | 142228 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Raymond Yip, Christopher C. Yarborough | On Track | Changed IO to Ray Yip | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: Ramps - Freight P&D stops / hr improvement | 74125 | 7786 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | David Herford, Tanisha Torres | On Track | Currently working on a proof of concept using 10 Pilot Locations: MSPA, DENRT, ORDRT, ICTR, ONTRT, BOSRT, IAHRT, PBIR, GRRR and BWIRT. We are conducting POC to validate the savings resulting in the use of the tools we made available: VCR (virtual checkride), VRP Model and Route Viewer (along with the already available Gap Reports in FWR). 3/27 - Proof of Concept Completed and results reviewed with Regional VPs and Finance. SPH year over year improvement goal set at 4% which resulted in final yearly savings of $2.5 M. | K: L5 | Active | L5 Feedback Requested | 2024-04-23 | 2025-03-31
Business Only Initiative: Move FedEx to end-to-end management of temp labor | 24438 | 9439 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Eduardo Sciortino, Laura Bullion | On Track | this initiative has been replaced with 9442-Global Temp Labor VMS | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-04-17 | 2025-07-01
Business Only Initiative: Implement enterprise-wide best practice temp labor | 24440 | 9523 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Anne Hemp, Patrick McEntire | On Track | This initiave savings are being captured under initiatlive 24446 | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2023-04-24 | 2024-06-07
Business Only Initiative: Load Planning Improvement and Documentation |  | 143617 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Veda J. Howse | On Track | Business as usual. Process improvement without quantifiable financial savings. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Load Planning Improvement and Documentation |  | 143619 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Veda J. Howse | On Track | This initiative is a duplication of 14617: Load PLan Improvement and Documetation | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Standardization of MEMH Operational KPIs |  | 153172 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Absorbing the initiative into 168131 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: 10-Minute Ticker Modernization |  | 153178 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Absorbing the initiative into 168131 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Real-Time Ops Visibility |  | 153181 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Absorbing the initiative into 168131 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Employee Visibility |  | 153184 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Absorbing the initiative into 168131 if the data is available | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: ULD/Container Visibility |  | 153188 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Ready to move forward | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: MOP Standardization |  | 153239 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Larry Phillips | On Track | This initiative does not have a financial benefit in and of itself and does not enable a specific existing initiative. The identified process improvements warrant pursuit and will proceed. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Tricolor Facilities Enablement- ORD Building 632 |  | 154538 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Adding temp IO 11/13/25: Putting on hold as we wait for CBP to give approval of ECF (staffing challenges) 09/02/2025: IO Revisions | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2026-10-01 | 2026-10-01
Business w/ Tech Initiative: Tricolor Facilities Enablement- GSO |  | 154541 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Amanda Hewgley, Jasmine Hudgins | On Track | 12/26: Added temp IO 08/05/25: New initiative which requries properties & faciliteis resources to enable Tricolor | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Tricolor Facilities Enablement- JFK Hangar 6 |  | 157097 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Richard Wooten, Jasmine Hudgins | On Track | 12/26: Added temp IO 08/14/2025: Initiative Owner additon | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: NonCon Scanning |  | 90009 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough, Majid Ali | On Track | On hold to review the use case and actual value improvement from the bottom read scanner. MEM has disabled some packages from the non-cons line due to document bags traveling on the inputs resulting in lower capture percentages. | E: L2 | On Hold | L2 | 2025-02-28 | 2025-08-13
Business Only Initiative: Global-ULD-Damage Reduction |  | 157796 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Saarth Bhanot | On Track | Developing an improved process to reduce ULD damages by inserting checks and balances for serviceability checks. | E: L2 | Active | L2 Feedback Requested | 2025-07-01 | 2026-05-22
Business w/ Tech Initiative: MEM Specialty Sort Pickup Process |  | 153209 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Larry Phillips | On Track | This initiative does not have a financial benefit in and of itself and does not enable a specific existing initiative. The identified process improvements warrant pursuit and will proceed. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Month-To-Date Productivity Reports |  | 163933 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Mario Magparangalan | On Track | Business as usual based on guidance from Triage. | C: L1 | Cancelled | L1
Business Only Initiative: Standardization of "Run Rate" Positions |  | 163936 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Mario Magparangalan | On Track | Requires more specific objective and scope. Verify this initiative does not overlap with other initiatives. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR OTC-US&CA Parcel DIM Wgt Scan Imprvmt(Wave3) |  | 164059 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Armando Ruiz, Dave Metelko, Christopher C. Yarborough, Anshuman Prabhakar | On Track | Submit to L2. | G: L3 | Active | L3 | 2026-03-20 | 2026-04-30
Business Only Initiative: Memphis Hub Night sort Wave Project MEM2 |  | 164066 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Aaron T. Lamb, Shane Floyd | On Track | Domestic Ramps are splitting out ~125K Wave 2 boxes. This provides MEMH Nightsort the opportunity to call a Wave 1 sort down earlier, whilte still processing Wave 2 boxes at the input. ~50K boxes of Wave 2 can be held at dedicated Wave 2 Input Staging area at the tail end of the sort to prioritze Wave 1 ULDs sort down that is ~15 minutes earlier than current parameters. OP&E is currently working on a control room dashboard to monitor Wave 1 ULDs and helping call Wave 1 sort down time. OP&E is working with operations on offload pulls that enable Wave 1 pull prioritization and allows Wave 2 ULD drop off at the separate Input Staging. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Labor Tracker - INDH |  | 164322 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Chuck Barr, Darrell Jessup, Ahmed S. Imtiaz, Karl Sanftleben | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Ramp Sort Table Standarization |  | 164326 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Aaron T. Lamb, Mario Magparangalan | On Track | .This project is already on the list for Global Sort Systems. This project is important because URSAs updates could be more frequent and we need quicker ways to develop/produce the plans. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Early Bird |  | 164346 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Jeffry S. Kolbrener, Mario Magparangalan | On Track | Assign Jeffry Kolbrener as Primary Initiative Owner. | D: SL2 | Rejected | Reject Initiative
Business w/ Tech Initiative: Reduce freight canopy handling and scanning |  | 163479 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Nickolas Gray | On Track | 9/29 - We are currently keeping track of Mixed Ulds using a powerBi report. This report does not keep an archive of data and must be pulled each day to create a baseline of data. Project is ready for SL2. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Offload Optimization |  | 164954 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Sidney B. Smith | On Track | 10/9/2025: waiting for team to be formed to begin project | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Matrix Optimization |  | 164964 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Sidney B. Smith | On Track | 10/8 Requesting IO for FWSH Nights 155149 to submit as an enabler. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Aligning employee schedules to engineering plan |  | 165709 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Thomas A. Mogish | On Track | The scheduling tool has been implmented at MEM hub on 9/2/25. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Convert CTV to Bulk Trucks |  | 167786 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Ahmed S. Imtiaz | On Track | On Track | K: L5 | Active | L5 | 2025-10-06 | 2025-10-06
Business Only Initiative: MEM Non-Conveyable Smalls Bag DIM Solution |  | 168391 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Christopher C. Yarborough, Katelyn Black | On Track | On Track | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: MPS Interim Solution |  | 168394 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Stefan Gant | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: FEC Export |  | 169740 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Stefan Gant | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Datalogic Dual Head Dim |  | 152900 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Salvatore Signorelli | On Track | Correct Initiative is under #153147 under correct name EMR OTC - Datalogic Dual Head Dim | C: L1 | Cancelled | L1
Business Only Initiative: EMR OTC - Datalogic Dual Head Dim |  | 153147 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Salvatore Signorelli | On Track | Reworked numbers, found an additional 115k in savings coming out of services. Full Enterprise rollout Number of sites50 Number of tunnels172 Number of spares63 HW costs $2,064,000 Installation costs $982,601.60 Engineering/PM $218,233.60 Spares $409,500.00 Site Servey $ 126,000 Tax @9% $342,030.17 Shipping @ 6% $148,410.00 Contingency @ 5% $190,016.75 Total CAPITAL $4,480,792.12 MetricValue Initial Investment $4,543,500.00 Annual Benefit $2,724,523.18 Timeframe (Years) $2.00 Total Net Benefit $5,449,046.36 Annual Benefit × Timeframe ROI (%) 21.61% ((Total Net Benefit - Initial Investment) / Initial Investment) × 100 Payback Period (Years) 1.64 Initial Investment / Annual Benefit Payback Period (Years and Months) 7 months Converted from decimal years 10/14/2025 - QA Expert review completed by Kassandra Harden 11/26/2025 - Submitted CLEAR 100011987 - G0000967 for approvals - Currently working it way through approvals. 4/5/2026 ICompleted installation at 2 sites - 12 tunnels total Assumptions 8‑week before installation data used $0.05 value per additional LFT package 12 tunnels included Average 86.4% performace before update, 96.3% after upgrade on 12 tunnels. Additional 1326862 packages would have beeen Dim'd when `using the same 8 week data before the upgrade. with an additional 1326862 @ .05 cents per dim would results to an additional $66,343 at the new performace levels for the same 8 week period. | G: L3 | Active | L3 Feedback Requested | 2026-01-09 | 2026-04-01
Business w/ Tech Initiative: Enterprise DG/Hazmat Inspection and Manifesting |  | 180001 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Stephen D. Gallagher, Andrea W. Cole, Grant Marshall, Scott Morrison | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Convert CTVs to Bulk Trucks: IND-YYZ |  | 186122 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Ahmed S. Imtiaz | On Track | On Track | E: L2 | Active | L2 - Enter Value Prop
Business w/ Tech Initiative: Dim/Weight Validation 1FDX |  | 187359 | Business w/ Tech Initiative | GAHR - Process | Global Air Hubs & Ramps | Kristi Vaughn | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Global-ULD- Nets RFP |  | 189033 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Saarth Bhanot | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Global-ULD- CANH Repair Station |  | 189036 | Business Only Initiative | GAHR - Process | Global Air Hubs & Ramps | Saarth Bhanot | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Camera Upgrades |  | 88740 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough, Sandeep Dhaliwal | On Track | Needs to move to the new facility pod in GAHR and needs and IO | E: L2 | Active | L2 | 2024-07-22 | 2024-07-22
Business w/ Tech Initiative: Modernized Autorollover Application |  | 88747 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | AJ Johnson, Christopher C. Yarborough, Tara Nabors | On Track | Finances review of this initiative could not identify any potential business savings with this initiative and did not approve in L1. Review of the current applications capabilities do not identify any shortfalls beyond manual data entry and technology risk of being housed on a single PC. Additionally, we are working towards the future technology roadmap for ramps and yards. The solutions highlighted throughout the roadmap do consider applications like AutoRollover and similar. AJ 9/5/25" | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Workforce Decisioning |  | 88756 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough, Sandeep Dhaliwal | On Track | Merge with digital twin | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Tug Dispatch Management | 94811 | 8515 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Andrew Werner, Christopher C. Yarborough, Sandeep Dhaliwal | On Track | Update to IO's on the project | E: L2 | Active | L2 Feedback Requested | 2024-07-22 | 2027-09-30
Business w/ Tech Initiative: Global-ULD-SenseAware Tracking |  | 105799 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Saarth Bhanot, Christopher C. Yarborough, Andrew Werner | On Track | QAT to identify ID3W hardware as proposed ULD tracking solution is on track to be complete by April 1, 2025. | E: L2 | Active | L2 Feedback Requested | 2025-07-16 | 2025-12-09
Business Only Initiative: POC NonCons Scanning |  | 109382 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough, Majid Ali | On Track | This initiative is being combined with 90009 for redundancy. The POC is underway yeilding a 5% gain in capture and low return. Will finalize financials in the Non-Con initiative | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Damaged Package Tool (DPT) New Opportunities & New | 81134 | 7659 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Sabrina Sicard, Tammye Byars | On Track | On track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-01 | 2026-10-28
Business w/ Tech Initiative: Hub Simulation/Digital Twin |  | 88662 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough, Shane Floyd, Sandeep Dhaliwal | On Track | Architecture review for T-Shirt Sizing | E: L2 | Active | L2
Business w/ Tech Initiative: MEM SEC26 Sort System |  | 113854 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Francesca I. Smith, Torrey Rives | On Track | To enable the sort capabilities required for this facility, IT development will be essential. However, because the initial capital request was not submitted through Planview and therefore not connected to IT epics or enabling workstream, we are unable to tie the needed IT development to the original financial justification. As a result, this lack of alignment is preventing movement to L2. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Global-Automated Depalletization-US | 23511 | 8180 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Fico Arredondo, Xia Zhao | On Track | 06.02.2025: Update KPI (Total Labor Hours) to reflect equipment final installed locations. 05.20.2025: Installation at Vancouver, Canada complete. Going forward, expense & Savings actuals will reflect 2 of 3 Depal units. 03.10.2025: Milestones updatedto reflect installations at Reno, NV and Vancouver, Canada. 01.21.2025: Expense and Saving actuals represent deployment of 1 of 3 Depal untis to date. Funding required for initiative increased since the project started. A change in scope is required by finance to account for the changes. Once the additional funding gets approved, we’ll be able to adjust the business impact, KPI and timeline. Finance has advised this step is required before we submit for L3 approval. Installation of unit complete at TORO. Site Acceptance Testing underway. Training of Operations underway. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-01-30 | 2028-02-29
Business w/ Tech Initiative: Manual Sort Augmentation/Enhancement |  | 89458 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough, Jeremy D. Fiveash | Some Issues | After completing testing in MEMH some opportunities have been identified and the team needs to work with the IT department to see if the identified opportunities can be addressed. | E: L2 | On Hold | L2
Business Only Initiative: Enterprise PT analysis | 84084 | 9180 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Jon Warner, Jaime Nuessner | On Track | On hold until further notice. Waiting to confirm if this initiative needs to be in a FXE pod or FXF pod. Or if it even needs to be an drive initiative at all. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2022-01-03 | 2024-08-12
Business Only Initiative: Run RFP for temporary labor spend - FEI | 24445 | 9446 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Paul Barker, Laura Bullion | On Track | Nothing to Update | K: L5 | Completed | L5 | 2023-06-01 | 2025-12-23
Business w/ Tech Initiative: Move FedEx to one temp agency worker VMS | 24439 | 9522 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Antonia Rivera, Patrick McEntire | On Track | This initiative (9522) has been replaced with 9442-Global Temp Labor VMS | G: L3 | Cancelled | L3 Data Migration - TEMP
Business w/ Tech Initiative: Automate DG Inspection Process |  | 113858 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Grant Marshall, Stephen D. Gallagher | On Track | Just starting out | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Freight Pickup Automation Tools |  | 143332 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Re-defining scope of the initiative and combining with other work. | C: L1 | Cancelled | L1
Business Only Initiative: Load Plans Reporting and Compliance Tool |  | 143335 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Veda J. Howse | On Track | Business as usual. Process improvement without quantifiable financial savings. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Global-Forklift Dashcam-Parent-US |  | 143338 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Global Name Convention | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Hub to Ramp AM Flight Sequencing |  | 143342 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Enrique M. Sanqui | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Ramp, Longhaul RTD, Shuttle RTD |  | 143347 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Enrique M. Sanqui | On Track | updating LBC | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Audio/Visual Signal For Optimal Pull |  | 154769 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Complete LBC | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Productivity Reporting for Dimensions |  | 161867 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Richard Wooten, Rob Wibright | On Track | Updated IO | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AIR Split Tool |  | 163272 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Christopher C. Yarborough, Joseph Johnson | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: New AGFS Ops Enterprise Reporting Platform |  | 168131 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | JT Pickard | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR- FEI Recruitment RFP - Temp Labour Phase 2 & 3 |  | 177664 | Business Only Initiative | GAHR - Tech | Global Air Hubs & Ramps | Paul Barker, Laura Bullion | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2026-04-30 | 2026-05-29
Business w/ Tech Initiative: Hub/Ramp transit scan menu enhancements |  | 187674 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Elizabeth-Lynn Doiron, Anjum Sultana, Tamaria Bridgeforth | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Integrate DPT with AI to predict damage and loss |  | 189979 | Business w/ Tech Initiative | GAHR - Tech | Global Air Hubs & Ramps | Sabrina Sicard | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: HUBS - Offload Management Span of Control MEMH | 74715 | 7002 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Brian Riley, Joseph Irving | On Track | Initiative is on track. Both Nights and Days has begun its reduction. | K: L5 | Completed | L5 | 2024-05-10 | 2025-05-30
Business Only Initiative: Hub Non Sort Overhead | 36080 | 7027 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Mike Stambaugh, Lil Burroughs, Stephen Glasl | On Track | Initiative is being rebaselined, | K: L5 | Completed | L5 | 2023-08-14 | 2024-03-27
Business Only Initiative: Ramps - Reduce Touches at Ramps (pure splits from | 72632 | 7104 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Zachary Rhodes, Darrell Jessup, Larry Phillips | On Track | Date of Oct 31st updated due to October Implementation all listed ramps. | K: L5 | Completed | L5 | 2024-04-01 | 2025-05-30
Business Only Initiative: Ramp Efficiency | 59452 | 7277 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Tom Maxwell, Rob Wibright | On Track | Annualized impacts determined | K: L5 | Completed | L5 | 2023-12-01 | 2024-04-30
Business Only Initiative: Fix Head Count Reduction | 59592 | 7290 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Tom Maxwell, Rob Wibright | On Track | Annualized Impacts developed. Impacts, KPI's, and milestones completed. | K: L5 | Completed | L5 | 2023-12-01 | 2024-03-06
Business Only Initiative: HUBS - Transload Team Reduction for MEMH-N | 74699 | 7588 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Joseph Irving, Joe Kelly | On Track |  | K: L5 | Completed | L5 | 2024-05-13 | 2024-07-19
Business Only Initiative: Hubs - Refresh engineering inputs and update staff | 74098 | 7610 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Leroy Payne Jr, Terry Mayberry | On Track | For planview helpdesk | K: L5 | Completed | L5 - Restarted Initiative | 2024-05-27 | 2025-03-03
Business Only Initiative: Hubs & ramps - 3rd party transportation reduction | 74104 | 7611 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Shane Floyd, Karl Sanftleben | On Track |  | K: L5 | Completed | L5 | 2024-04-01 | 2025-05-30
Business Only Initiative: Hub Scanning Device Repair And Replace Expense Red | 24460 | 7823 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jake Dorris, Shane Floyd, Chuck Barr | On Track | Multiple weekly meetings between IND and MEM equipment issue teams to continue progressing toward L2 status. | K: L5 | Completed | L5 | 2023-02-01 | 2023-11-01
Business Only Initiative: Hubs - Hub scheduled employee worked hours control | 72634 | 7824 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jake Dorris, Shane Floyd, Chuck Barr | On Track | On track | K: L5 | Completed | L5 | 2024-05-01 | 2025-05-30
Business Only Initiative: Hubs & ramps - Matching job classification to func | 72721 | 7825 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jake Dorris, Shane Floyd, Chuck Barr | On Track | On track | K: L5 | Completed | L5 | 2024-05-01 | 2026-05-29
Business Only Initiative: Hubs and Ramps - Optimize Employee Award Program | 85734 | 7912 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Sasha Young, Stephen Glasl | On Track |  | K: L5 | Active | TEMP L5 - Enter L5 | 2024-07-22 | 2024-11-15
Business Only Initiative: Hubs - Control Room Modeling at RSOs (EWR) | 74124 | 8037 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Mario Magparangalan, Tanisha Torres | On Track | Updated baseline to FY25 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-09-09 | 2024-09-30
Business w/ Tech Initiative: Freight Dim WT/NSS Revenue Capture-Parent US | 87822 | 8079 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Tom Barry | On Track | 9/16/24 - project has been initiated by properties finance. Brandon Tolbert is the project sponsor. We have requested funding for 20 devices with the first 10 planned for delivery and deployment by Jan 2025. Work is ongoing with the Goldeneye tool to refine data and IT is engaged to schedule location installs and other related work 9/1/25 - Phase locations have MTP. We have also successfully launched the NSS solution. 11/20/25 Phase 3 locations have been identified and a funding request is in progress 2/20/26 The inititaive was rolled back to L3 to allow for Phase location IT work to be done(MTP). Work has begun to prep for installation at all locations with full deployment expected by 4/30/26. | G: L3 | Active | L4 | 2024-07-25 | 2026-11-02
Business Only Initiative: EWR Employee Transportation Cost Optimization | 38500 | 8081 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Mark Mundy, Tom Maxwell | On Track | Routes has been successfully reduced from three (3) to two (2) with vendor BeSpoke. Letter attached for reference. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-11-01 | 2023-12-15
Business Only Initiative: Eliminate LCK sort | 341 | 8130 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Kraig Robertson | On Track | LCKH has not operated since December 30, 2022, the last operating day. The effective date of closure was December 31, 2022. | K: L5 | Completed | L5 | 2022-12-01 | 2023-02-01
Business Only Initiative: Hubs - Aircraft Offload Flight Folder Automation | 75611 | 8212 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Zachary Rhodes, Darrell Jessup | On Track |  | I: L4 | Active | L4 | 2024-03-19 | 2026-03-04
Business Only Initiative: AFW Monday Day sort | 350 | 8355 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Rob Wibright | On Track | The AFW Monday Daysort was taken down effective Monday, January 9th and is no longer operating. | K: L5 | Completed | L5 | 2022-12-01 | 2023-01-03
Business Only Initiative: Global-DIM Weight Scanners -Ramp & Stations-US |  | 85736 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Armando Ruiz, Dave Metelko, Dana R. Gaston, Suzanne Sabbatini | On Track | Revised Financials, move to L4 | K: L5 | Active | L5 Feedback Requested | 2024-12-06 | 2025-08-29
Business Only Initiative: Employee Shuttle Services RFP |  | 87037 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Amanda Sewell | On Track | Duplicative initiatives entered in Planview. Cancelling #87037. #109669 will remain active” | C: L1 | Cancelled | L1
Business Only Initiative: Temp Staffing US RFP | 2162 | 8901 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Nicholas Bidinger, Daniel Provence, Laura Bullion | On Track | Savings have been updated for Supply Chain given relaxation in revenue for FY24/increase in sourcing efforts | K: L5 | Completed | L5 | 2023-02-01 | 2024-05-23
Business Only Initiative: Hubs - HR Overtime Policy Change | 74687 | 8926 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Micah S. Peterson, John Lamia, Ana Whitten | On Track | **12/9/2025** - Nov actuals rpt (109k hours v. 160k hours baseline v 112k hours target,5.7% OT rate v 7.10% baseline); above forecasted savings for month **11/9/2025** - Oct actuals rpt (86k hours v. 79k hours baseline v 54k hours target, 3.9% OT rate v 3.60% baseline); OT as % of all hours still under YTD avg (4.2%) **9/9/2025** - Aug actuals rpt (81k v. 108k baseline v 81k target, 4.0% OT v. 3.1% forecast) **8/12/2025** - July actuals rpt (90k v. 136k baseline, 4.7% OT v. 4.1% forecast) **7/9/2025** - ready and submitted to L5 **6/10/2025**- May actuals reported (90k v 87k baseline, 4% higher in hours) **5/19/2025**- April actuals reported (70k v 86k baseline, -18% reduction in hours) **3/27/2025**- Communication plan complete, distro to employees at 3/27/2025. IT implementation going in by 4/2 effective 3/30/2025. Move to L4, first savings to be reported in May for April 2025 payroll spend. Update to financials submitted to Finance by 3/31. **3/14/2025**- INDH enabler complete. Money step greenilght for March 30th effective date. Communication plan complete, going out to employees at 3/27/2025. Move to L4, first savings to be reported in May for April 2025 payroll spend. **2/26/2025**- Enabler of Dimensions rollout (dependency) for INDH.completed with go live on 2/23. Policy changes for this initiative in flight and targeted for effective March 16th. First savings to be reported in April for Mar 2025 payroll spend, savings realized over the remainder of FY2025. ***1/29/2025*** - Micah Peterson added as IO. Money step on track for Mar 2025. First savings to reported in Apr. for Mar 2025 payroll spend. Savings realized over the remainder of FY2025. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-01 | 2025-04-02
Business Only Initiative: Ramps - HR Overtime Policy Change | 77239 | 8927 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Micah S. Peterson, John Lamia, Ana Whitten | On Track | **8/12/2025** - July actulas rpt (184k actual hours to 200k baseline from Fy25, 5.6% OT to 5.0 % forecast) **6/10/2025**- Total hours and OT % marginal increase to baseline (171k to 168k, 5.4% to 5.2% forecast) for May 2025 payroll. Financials and KPIs updated. Enter L5 **5/14/2025** Total hours and OT % flat to baseline (170l v. 168k, 5.9% to 4.8% forecast) for April 2025 payroll, no cost savings recorded. Financials and KPIs updated. **4/15/2025** Total hours and OT % flat to baseline (160.4k v. 160.4k, 5.9% to 4.6% forecast) for March 2025 payroll, minimal cost savings recorded. Financials and KPIs updated. **3/28/2025** Financials submitted through FY28 to Finance by 3/31. Move to L5 after April actuals (March payroll) reported. **2/13/2025**- January actuals reported in Feb. Process stable, savings realized over the remainder of FY2025. Move to L5 in April. ***1/29/2025*** - Micah Peterson added as IO. Money step completed in May 2024. Savings being reported and realized over FY2025. | K: L5 | Completed | L5 | 2024-04-01 | 2025-05-15
Business Only Initiative: Ramps - Remove Guaranteed Minimum Hours (FT) | 80024 | 8928 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Micah S. Peterson, Ana Whitten, John Lamia | On Track | **6/9/2025**- May spend (actuals) inputted, savings stable. **5/6/2025**- April spend (actuals) inputted, savings stable. **4/7/2025**- March spend (actuals) inputted, submitted to L5. **3/28/2025**- Ready for L5 in April. Savings realized over the remainder of FY25. Financials updated through FY28 by 3/31. **2/13/2025**- January actuals reported in Feb. Process stable, savings realized over the remainder of FY2025. Move to L5 in April. ***1/5/2025*** System updates turned on to remove MIN effective 1/5/2025 ***1/29/2025*** - Micah Peterson added as IO. System audit this week shows process stable. First savings to reported in Feb. for Jan 2025 spend. Savings realized over the remainder of FY2025. | K: L5 | Completed | L5 | 2024-04-01 | 2025-01-06
Business Only Initiative: Hubs - Remove Guaranteed Minimum Hours (FT) | 80025 | 8931 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Micah S. Peterson, Ana Whitten, John Lamia | On Track | **3/9/2026** - Feb actuals reported, 100% to target. **12/8/2025** - Nov actuals reported, 100% to target. **11/5/2025** - Oct actuals reported, 100% to target. **8/5/2025** - 4 months mature savings, submit to L5. **6/9/2025**- May spend (actuals) inputted, savings stable. **5/6/2025** April actuals reported, savings stable. **3/27/2025**- Communication plan complete, distro to employees at 3/27/2025. IT implementation going in by 4/2 effective 3/30/2025. Move to L4, first savings to be reported in May for April 2025 payroll spend. Updates to financials submitted to Finance by 3/31. **3/14/2025**- INDH enabler complete. Money step greenilght for March 30th effective date. Communication plan complete, going out to employees at 3/27/2025. Move to L4, first savings to be reported in May for April 2025 payroll spend. **2/26/2025**- Enabler of Dimensions rollout (dependency) for INDH.completed with go live on 2/23. Policy changes for this initiative in flight and targeted for effective March 16th. First savings to be reported in April for Mar 2025 payroll spend, savings realized over the remainder of FY2025. **2/13/2025**- Weekly status meeting with IT to discuss Dimensions rollout (dependency) for INDH. On target for 2/23 with policy change for this initiative targeted for early March. First savings to be reported in April for Mar 2025 payroll spend, savings realized over the remainder of FY2025. Forecast up to date. IO Swap; 12/18 to Ana Dunn & 1/29 to Micah Peterson ***1/29/2025*** - Micah Peterson added as IO. Money step on track for Mar 2025. First savings to reported in Apr. for Mar 2025 payroll spend. Savings realized over the remainder of FY2025. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-01 | 2025-04-02
Business Only Initiative: GSOH Premium Reduction | 81439 | 8933 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Micah S. Peterson, John Lamia, Ana Whitten | On Track | ***6/4/2025*** May spend inputted, matured savings for FY2025. L5, should close in FY26. ***5/6/2025*** April spend inputted, matured savings for FY2025. ***4/15/2025*** March spend inputted, savings on track for FY2025. ***3/28/2025*** Moved to L5 based on money step completed Mar 2024. Savings being reported and realized over FY2025. ***2/26/2025*** Eliminating remaining $3 premium at these locations updated target as of March 9, 2025. Ready for L5. ***2/14/2025*** Savings being reported and realized over FY2025. Eliminating remaining $3 premium at these locations as of March 2, 2025. Ready for L5. ***1/29/2025*** - Micah Peterson added as IO. Money completed Mar 2024. Savings being reported and realized over FY2025. | K: L5 | Completed | L5 | 2024-03-11 | 2024-03-11
Business w/ Tech Initiative: Phase 2 - MEMH Dynamic Flow Management |  | 89396 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Christopher C. Yarborough | On Track | Need camera upgrades completed to make this financially viable | E: L2 | On Hold | L2
Business Only Initiative: Hub Expense Reduction | 343 | 9019 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Lil Burroughs, Jake Dorris | On Track | Initiative is progressing as planned. Monthly review of KPI and Impacts are reviewing with IO, pod owner, and finance to ensure results are in line with the target. | K: L5 | Completed | L5 | 2022-08-01 | 2024-01-01
Business Only Initiative: Hours control - AGFS |  | 90206 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Dave Metelko, Shane Floyd, Hector Gonzalez | On Track | On hold per Rob Wibright due to overlap with other initiatives. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Feeder Reduction | 352 | 9030 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Tom Barry, Asad Ali | On Track | 7/24 - Weekly meeting held on 7/20 was very productive. Finance requested updates to impacts and our engineering and feeder finane team members are in the process of providing this info. 7/5 - New baseline data has been entered and initiative has been pushed for L3 approval. Awaiting CCH and TCH approval 6/23 - Push to L3 delayed due to the requirement to re-calculate baseline data. This is currently under way. We have also identifed 2 additional feeders to pull down by 10/1/23. IND-PKB and LCK-PKB. 6/8 - The group held 2 calls this week. We have finalized the feeders and the financial savings to be captured so that we can push to L3. All subsequent feeder savings will be added to our actuals and we therefore expect to exceed the forecasted impact. Awaiting the final confirmation from Feeder Finance to be able to submit the needed inputs into wave for L3 approval. L4 and L5 will follow immediately after L3 approval. We have already begun to see savings from feeder takedowns. 3/16 - Met with team members and decided to push to L3 with the current feeders in the takedown phase. There are several additional feeders in review which when at the takedown phase; will be included in the actual impacts. | K: L5 | Completed | L5 | 2022-10-07 | 2023-08-31
Business Only Initiative: MEM Hub Efficiency Beyond OTP | 344 | 9041 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | James Joy, Brian Riley | On Track | Request to close the initiative as it has been superseded by numerous other initiatives. | I: L4 | Cancelled | L4 | 2022-06-01 | 2024-06-10
Business Only Initiative: Hub Sort Efficiency Economy of Scale | 345 | 9052 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jake Dorris, James Joy, Chuck Barr | On Track | Initiative is progressing as planned. Monthly review of KPI and Impacts are being reviewed with IO, pod owner, and finance to ensure results are in line with the target. Initiative is over-delivering YTDS due to solid execution by both MEMH and INDH. Under-planned staffing at both hubs is driving higher savings in variable salaries & wages than planned | K: L5 | Completed | L5 | 2022-04-01 | 2023-02-01
Business Only Initiative: Hubs and Ramps - Uniforms Spend Reduction | 81599 | 9074 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Kraig Robertson, Brad Bush | On Track | Communication is currently working on the memo for distribution to Network Operation's Hub and Ramp Leadership. Completion date updated to August 24, 2024. | K: L5 | Completed | L5 | 2024-05-27 | 2024-11-01
Business Only Initiative: Ramps - Reduce MT&E Spend | 82183 | 9085 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Kraig Robertson, Brad Bush | On Track | Memo has been distributed to all Network Operation's Hub and Ramp Leadership | K: L5 | Completed | L5 | 2024-06-03 | 2024-10-15
Business Only Initiative: Hubs and Ramps - Reduce Miscellaneous Expense | 85736 | 9096 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Kraig Robertson, Brad Bush | On Track | Memo has been distributed to Network Operation's Hub and Ramp Leadership. Milestone 88123 is cancelled due to the description contents are not supported in FCF. | K: L5 | Completed | L5 | 2024-06-03 | 2024-10-31
Business Only Initiative: Hours control - MEMH |  | 91011 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Brian Riley | On Track | Enabler to support the other Mem Hub Inititatives. Process being implemented to track pt emloyees over 29 hours and ft employees over 40 hours per week. Enabler supported by Triage Team. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-02-20 | 2025-07-01
Business Only Initiative: Hubs and Ramps: Reduce MEMH spend with Cube Ice | 88162 | 9107 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Brian Riley, Brad Bush | On Track | New Ice Making Machines Installed 02/03/25. Old Cube Ice Freezers being removed. JBB 6/5/25 - This is init is mature and is ready for L5. | K: L5 | Completed | L5 - Restarted Initiative | 2024-08-12 | 2025-01-31
Business Only Initiative: Hubs and Ramps - Supplies Spend Reduction | 81604 | 9130 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Fred Jacob, Brad Bush | On Track | Vendor was not able to be used due to the contract to grainger. Working with present vendors to reduce present prices. Canteen has already reduced. JBB 7/25/24 - loaded new forecast based on revised Grainger price as outlined in Attachment 2 JBB 6/3/25 - this initiative is mature and is ready for L5 | K: L5 | Completed | L5 - Restarted Initiative | 2024-05-27 | 2024-10-31
Business Only Initiative: Global-ULD-Transportation and Relocation | 82724 | 9141 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Saarth Bhanot, Wayne Thornburg | On Track | Changing IO to move from GV team to GNP team | K: L5 | Completed | L5 | 2024-05-20 | 2024-09-30
Business Only Initiative: Hubs and Ramps - Shuttle spend reduction | 81605 | 9152 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Mike Stambaugh, Brad Bush | On Track |  | K: L5 | Completed | L5 | 2024-05-27 | 2025-01-01
Business Only Initiative: MEM External Bus Route Reduction | 4559 | 9163 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Lil Burroughs, Jake Dorris | On Track | Initiative is progressing as planned. Monthly review of KPI and Impacts are reviewing with IO, pod owner, and finance to ensure results are in line with the target. | K: L5 | Completed | L5 | 2022-12-01 | 2023-03-31
Business Only Initiative: Transition from Vendor Yard Mule Drivers at MEMH | 2517 | 9174 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | James Joy, Jake Dorris | On Track | Initiative performance YTD vs Bankable Plan: $m 0.00 | K: L5 | Completed | L5 | 2023-01-12 | 2024-09-30
Business Only Initiative: Indy Hub Efficiency to Reduce FTEs | 59789 | 9185 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Shane Floyd, Jake Dorris, Chuck Barr | On Track | on track | K: L5 | Completed | L5 | 2023-10-02 | 2024-03-08
Business Only Initiative: MEMH AGD Reduction Initiative | 89655 | 9196 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Buck Miller, Brian Riley | On Track | Original initiative being replaced with S3 initiative to address AGD. S3 - Silhouette Safety Syetem is launched, however if this becomes an initiative, our role would be Enabler for one single AGD cost related initiative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-08-08 | 2024-10-31
Business Only Initiative: Mem Hub Rental Van Reduction | 96636 | 9207 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Brian Riley, Anna Lewis | On Track | No issues, rentals have been returned. Have had 4 monthis of savings. Ready for L5 | K: L5 | Completed | L5 | 2024-10-15 | 2024-11-15
Business Only Initiative: Traffic Group Savings Initiative | 38080 | 9218 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Buck Miller, James Joy |  | Changing to CXL. Will reimplent since financials have changed. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2024-11-07
Business Only Initiative: Mem Hub Right-Sizing | 64366 | 9230 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Brian Riley, James Joy | On Track |  | K: L5 | Completed | L5 | 2024-01-09 | 2024-03-01
Business Only Initiative: Streamline PM Operation | 1113 | 9241 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jason Straub, Robert Nowlen | On Track | With the rollout of the wave 1 markets, KPIs for financial tracking and performance are being determined. | K: L5 | Completed | L5 | 2023-03-01 | 2024-03-01
Business Only Initiative: Hubs - Reduce running rate orgs (MEM/IND) | 74100 | 9252 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Brian Riley, James Joy | On Track | Since the time of this inititave the operations have been reoganized such that it can no longer accurately measure the actuals and is not providing any value. | I: L4 | Cancelled | L4 | 2024-03-11 | 2024-08-30
Business Only Initiative: IND Night Capacity Increase | 78754 | 9263 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jake Dorris, Chuck Barr |  | This initiative is requested to be cancelled until there as current network needs do not justify running 102k for INDH-N sort, | E: L2 | Cancelled | L2 | 2024-07-22 | 2024-10-07
Business Only Initiative: Global-DIM Scanners- Wave 2 (15) |  | 93292 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Armando Ruiz, Dave Metelko, Dana R. Gaston | On Track | Received financial data, progressing to L2. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-01-23 | 2025-08-29
Business Only Initiative: ?Spend Control Tower- Implement governance to enfo | 24446 | 9437 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Nicholas Bidinger, Daniel Provence, Laura Bullion | Attention Needed | on track 4/23/2025 - spend control tower activities will cease in FY25; future value removed | K: L5 | Completed | L5 | 2023-04-25 | 2024-10-01
Business Only Initiative: Formalize process and increase capture rate for te | 24443 | 9444 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Nicholas Bidinger, Daniel Provence, Laura Bullion | On Track | Moved pilot milestone dates forward to incorporate Indy Hub | K: L5 | Completed | L5 | 2023-05-15 | 2024-10-11
Business Only Initiative: Reduction of emergency maintenance requests | 31704 | 9503 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Patrick Snyder, Brad Courtney | On Track |  | K: L5 | Completed | L5 | 2023-08-07 | 2023-12-29
Business Only Initiative: Hubs - MEM DTC room running rate reduction | 72726 | 9537 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Buck Miller, Dave Metelko | On Track | Baseline running rates provided by engineering showing FY24 plan and actuals. When initiated, a 10% reduction in headcount was the goal. 40 employees were in the group. Over the past several months, headcount has reduced to 36 through attrition. There are no plans to backfill. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-22 | 2024-10-15
Business Only Initiative: Ramps - Reduce Tractor, Trailer, GSE rentals | 72650 | 9542 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | David Herford, Dave Metelko | On Track |  | K: L5 | Completed | L5 | 2024-03-08 | 2025-07-08
Business w/ Tech Initiative: Global Temp Labor VMS | 96555 | 9442 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Jerry P. Howard, Grace Chiocco, Nicholas Bidinger, Laura Bullion, Adam Schumacher | On Track | On track N.Bidinger - Rebaselined to FY25 as of 03/26/2025 Project is currently on track and remains in green status for Phase 1A VNDLY implementation U.S. 72% overall completed. 11/10 MSP SOW executed on the 10/23 VMS hypercare lasting through November CDG Discovery Sessions and meeting are now on weekly cadence with a go -live expectation of late Mar, 2026. 10/16 MSP SOW Oct.15 AGS sent back clean version of MSP SOW Oct.16 Sourcing reviewed latest version from AGS and sent back to HRTA for final pass/review Next Steps: Encore approval process (led by HRTA), Legal review stamp followed by routing for signature CDG/Pontoon Continued discovery sessions conducted this week - Oct. 16 Recap Items below Order Process, Order Response, Contracts (TLAs), OSC entry and timekeeping Future Topics to be discussed Timekeeping – Allowances/Premiums Offboarding Project Focus/Risks Invoice testing is continuing till Oct. 17 No errors must be reported past this date. Oct. 16 invoicing testing poses a concern as errors/fails are still being reported but are gradually reducing Contributing There are delays with error resolutions partially due to the fact that teams are working across different global time zones, causing the resolution time challenges Deloitte/AGS/VNDLY/FedEx have prioritized resolving invoicing issues and will have a pulse check meeting tomorrow, Oct. 17 (go/no go decision point) ahead of go- live date. 10/6 Summary •Project status: Green •17 days until the U.S. slated go-live Phase 1A. MSP SOW •Commercial revisions: accepted by AGS Legal to send cleaned MSP agreement to AGS with SLAs to be added as an exhibit. SLA sent back to AGS Oct. 8 for review •Encore MSP Fee Amendments: Amendments oOct. 8 Legal is completing a sample amendment to be used against the agreements CDG/Pontoon •Discovery Sessions: Kicked off Oct. 9 –10 (participants: FedEx, AGS, CDG, Pontoon) •Received Pontoon Process Document Project Focus •Invoicing Invoice testing is continuing till Oct. 17 based on current timeline No errors must be reported past this date. 10/2 Summary Project status: GreenOverall completion: 63% US MSP SOWCommercial revisions: Accepted by AGS; currently under internal reviewLegal to send cleaned MSP agreement to AGS next week, with SLAs to be added as an exhibit. Encore MSP Fee Amendments: Amendments 16 and 17 are pending legal review; aim to expedite the review process. CDG/PontoonDiscovery Sessions: October 9–10 (participants: FedEx, AGS, CDG, Pontoon) 9/25 Status: Green; US 63% complete; 32 days to US go-live. MSP SOW: Legal review meeting Sep 26; CPA discussions ongoing. CDG/Pontoon: No updates. Recent: Blackout Oct 19–26; manager/supplier training Oct 21–23 (communications pending approvals). Risks: FXL configuration needs FXO finance sign-off; Glide (standardized electronic invoicing) may impact international invoicing. 9/18 Status: Green; US 58% complete; 38 days to US go-live. MSP SOW: Legal review call Sep 26; CPA discussions ongoing. CDG/Pontoon: Governance/RACI meeting planned; discovery dates pending. CDG go-live moved to Mar 2026 due to delayed start. Follow-ups: Reporting APIs details needed from FedEx; Phase II language requirements pending; cutover planning started. Recent: weekly status/data conversion calls, daily UAT, end-to-end and Dataworks approval sessions. 9/11 MSP legal call moved to Sep 12. CDG kickoff/planning done; discovery sessions scheduled. US project green, 58% complete. MSP/SOW: Legal call Sep 12. CDG: Kickoff with Pontoon, FedEx, Allegis done. Discovery on Sep 15; Solaris/VNDLY gaps under review. Pontoon and Allegis agreed on phased reversibility. Accomplishments: Supplier manual approval due Sep 12. Pre-discovery complete. FCF partial integration and finance requirements approved. Risks/Next: FCF connector date needed. Invoicing and Workday testing pending. Pontoon/CDG to confirm RASCI/governance. 8/28 MSP SOW: legal call on Aug 27 canceled; rescheduling pending. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-08 | 2026-10-30
Business Only Initiative: GSOH Line Haul Optimization - Phase I | 38502 | 7090 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Tom Maxwell, Rob Wibright | On Track | KPI's added in support of initiative to accurately track the use of TRIPS to/fr CAE, RIC, and IAD | K: L5 | On Hold | TEMP L5 - Enter L5 | 2023-10-16 | 2024-02-14
Business Only Initiative: Memphis Hub Night Sort Staffing Surge Effort |  | 107127 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Christopher C. Yarborough, Shane Floyd | On Track | Initiative conflicts with labor tracker projects underway. | C: L1 | Cancelled | L1
Business Only Initiative: MSL Secondary Netting |  | 152801 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Paul F. Ferrey | On Track | There's a need to get two test sites up and measure the FTE savings as well as sort performance indicators after installation in order to validate the cost to continue with prject. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Large Truck Training Optimization |  | 153204 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Christopher Siragusa, Shannon Arnold | On Track | Per confirmation with new Initiative Owner Shannon Arnold, her leadership team and field Ops leadership agreement this initiative will be placed on hold. Other efforts have moved forward within the Large Truck Training space to optimize program performance and meet business needs for interim due to inability to get technology prioritized for this specific initiative. Working with Ops VP team for direction, finance has provided the support needed to understand savings opportunity related to purchase trans, and we have a firm understanding of the program costs as well. Ready to define milestones for training program automation and enhancements. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Automated Sort Recirc Contingency v2 |  | 155194 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Douglas D. Combs, Christophe G. King | On Track | 8/8: Information entered, on schedule. 9/25: Meetings held, engineering team working through options. Added estimated efficency increases. Waiting on Architecht to provide feedback for their step to advance. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Hubs - Replace IND Temps with Permanent Staffing | 74121 | 7198 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | William B. McAlister, Kelly Wade, Chuck Barr, Frank Olson | On Track | 1.20.25 * Updated the 2028 Exit Rate. * Reviewed KPIs and updated with Finance * Submitted to L2 following the changes requested by feedback. 12.8.25 * Added November actuals. 11.19.25 -Pushed to L4 to begin tracking. Pending approval. 11.6.25 * Updated actuals and removed forecast. 10.20.25 * I've updated the money step again. Plaview continues to change the dates. I had someone else check it as well. I've also attached a screen shot and left it as "In Progress" as it seems to trigger the change of dates when I mark it as completed. 10.17.25 * I've updated the milestone dates twice as requested with the same start/stop dates and I'm not sure if they aren't saving correctly. I"ve got it right now as May 30, 2025. 10.15.25 * Met with Finance on projections. * Updated financials based on new projection. * Goal is to submit to L3 this week. * Awaiting Finance sign off. 9.3.25 * Updated Milestones for accuracy * Updated KPIs with baseline and forecast * Updated temp contract cost. * Next we'll update cost savings and any additional added costs. (Goal to L3 is in Oct.) 8.1.25 * Pinged the team again on the domain change. 7.9.25 * Heard back from the team today. PMO is working to get the domain approvals and then will submit the ticket for the move. 6.25.25 * Followed up with Daniel for form request approval. 6.18.25 * Per the DRIVE email from 6.17, we reached out to Daniel Thompson for approval to submit a domain change form request. 6.6.25 * Initial assessment of inti. is that it is in the wrong domain as INDH is a part of International and Airline. We reached out to PMO to assist with getting that updated. Updated temp to permanent staffing ratio to 1.33:1. Revised NRB to $3.1 million. Uploaded business case, benefit timeline, and assumptions document into Wave., | I: L4 | Active | TEMP L4 - Enter L4 | 2025-10-01 | 2026-11-02
Business w/ Tech Initiative: Cold Chain Solutions IND-MEM |  | 161478 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Al Cienfuegos | On Track | The project is off the ground and currently enables Parent Initiative is SS 91351 / Grow Pharma Air Freight in L1. Our target goal for this part of the project is to have all Bonded requirements completed by Oct 31 to support onboarding of new customers. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: ANCH Offside Clearance Loc Closure |  | 166993 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Armando Ruiz, Dave Metelko, Dana R. Gaston | On Track | On Track | I: L4 | Active | L4 | 2026-01-16 | 2026-02-13
Business Only Initiative: RTDA Training Support Enhancement |  | 167435 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Ariel Mendez, Dana R. Gaston, Rob Wibright | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: AGFS Contract Transportation |  | 169892 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Carl E. Nichols, Dana R. Gaston, Rob Wibright | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: MEM Hub Premium Pay (Existing Employees) |  | 186297 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | William B. McAlister, Dana R. Gaston, Rob Wibright | On Track | On Track -- Just got to L3 this week, so not much of an update yet. Meeting planned for this week with contact for this project in Compensation to discuss the best way to get actual monthly costs and savings for February. | I: L4 | Active | L4 | 2026-01-02 | 2027-02-26
Business Only Initiative: FWSH - Day |  | 165819 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Zachary Rhodes, Darrell Jessup, Katelyn Black, Thomas A. Mogish | On Track | Updated IOs | I: L4 | Active | L4 Feedback Requested | 2025-09-23 | 2025-10-08
Business Only Initiative: FWSH - Night |  | 155149 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Zachary Rhodes, Darrell Jessup, Katelyn Black, Thomas A. Mogish, Sidney B. Smith | On Track | 8/6/25 - ZR Added additional IOs, Required Fields L1 Net Recurring Benefits temporarily set to 0, TBD. | I: L4 | Active | L4 Feedback Requested | 2025-09-23 | 2025-10-08
Business w/ Tech Initiative: Increase Clearnace Capacity - FWSH |  | 187286 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Zachary Rhodes, Dana R. Gaston, Rob Wibright | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Peak Sort Reductions |  | 187356 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | JT Pickard, Dana R. Gaston, Rob Wibright | On Track | On Track | H: SL4 | Active | SL4 Domain Lead Approval | 2025-12-30 | 2025-12-30
Business Only Initiative: Shuttle Services |  | 109669 | Business Only Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Karl Kehr, Daniel Vargo | On Track | 02/26/2026- Removed the forecast for January, data showing additioanl spend in January instead of savings. 03/19/2026- Removed forecast for Feburary. Unable to pull accurate data to confirm savings. | G: L3 | Active | L3 Feedback Requested | 2025-07-30 | 2027-11-05
Business w/ Tech Initiative: Transition AGFS Heavyweight Ops to GPDE |  | 185790 | Business w/ Tech Initiative | GAHR - U.S. | Global Air Hubs & Ramps | Ray Lowe | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: LAC RDIM Installation |  | 163675 | Business w/ Tech Initiative | GAHR - LAC | Global Air Hubs & Ramps | Oliver H. Martin, Christopher Bernat | On Track | US Contract is being reviewed to leverage in LAC | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: IT Support & Development for DIAL Hub Sorter |  | 107398 | Business w/ Tech Initiative | GAHR - MEISA | Global Air Hubs & Ramps | Samir Bhatnagar, Hemal Lad | On Track | CLEAR is under process of submission | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Global-Small Parcel Reusable Bag Deployment-MEISA |  | 162235 | Business w/ Tech Initiative | GAHR - MEISA | Global Air Hubs & Ramps | Gavin Fernandes, Jarnail Singh | On Track | Since this is run by a central team in the US with stakeholder inputs for the regions, we're still on the testing phase and have not yet finalised a minimum viable product as the go to solution. Once we have more clarity on the Preferrede solution and associated costs involved. We will reinitiaite this | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global Benchmarking |  | 166074 | Business w/ Tech Initiative | GAHR - MEISA | Global Air Hubs & Ramps | Ralph Chigoya, Mohammed Wazif Ziavudheen | On Track | Change of IO | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global-ForkLift DashCams-MEISA |  | 167473 | Business w/ Tech Initiative | GAHR - MEISA | Global Air Hubs & Ramps | Mohammed Faisaluddin Khan | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Dim Wgt. Capture Machine for Morocco and Pakistan |  | 170716 | Business w/ Tech Initiative | GAHR - MEISA | Global Air Hubs & Ramps | Jyoti K. Narayanan | On Track | Please cancel this request as this has been approved as a Local Enhancement demand as it needs a very small IT effort. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Dim Wgt. Capture Machine for Egypt |  | 131618 | Business w/ Tech Initiative | GAHR - MEISA | Global Air Hubs & Ramps | Jyoti K. Narayanan | On Track | Please cancel this request as this has been approved as a Local Enhancement demand as it needs a very small IT effort. | E: L2 | Cancelled | L2 Feedback Requested
Business Only Initiative: Implement 108'' PMCs for freight/AMS packages on A | 30342 | 9546 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | Bob Chen, Pinky Jiang | On Track | Clarified with US Finance to cancel the initiative due to overlap with another initiative. | I: L4 | Cancelled | L4 | 2023-08-28 | 2023-10-06
Business Only Initiative: Global-Forklift Dashcams-APAC |  | 105664 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | Yan Pan, Terry Fu | On Track | Installing a dashcam on a forklift to minimize damage, with one device already tested and performing well on the CANH. Plan to communicate with the Finance and proceed with the implementation in the CANH in Phase 1. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-20 | 2026-06-01
Business Only Initiative: Off-site Options for APAC Gateways |  | 155462 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | In-Woo Ha | On Track | Per guide from Domain ownder and Kathleen, cancallation is submitted. | C: L1 | Cancelled | L1
Business Only Initiative: ICNR_Outsource Labor Contract Flexibility |  | 155466 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | JY Kim, In-Woo Ha | On Track | After initial assessment, the team decides to cancel the initiative. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: CANH_Outsource Labor Contract Flexibility |  | 155469 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | Christina Gan | On Track | in progress...collected saving data on Aug19,25 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2026-05-29
Business w/ Tech Initiative: Labor Planning Tool for Hubs and Gateways - APAC |  | 160514 | Business w/ Tech Initiative | GAHR - APAC | Global Air Hubs & Ramps | Wen-Fei Winnie Xu | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: DIM REX82/83 improvement to meet APAC country goal |  | 104341 | Business w/ Tech Initiative | GAHR - APAC | Global Air Hubs & Ramps | Wendy Ngai | On Track | Since we've another PV project to cover part of this request (adding scale), the scope has to be adjusted after review. Will need more time for vendor onsite survey for feasibility study and quotation, putting on hold till more concrete info available | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Expand automatic DIM&Weight Capture and Scanning C | 39949 | 6889 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | Cecile Xi, Vivien Zhang | On Track | Aligning scope, assumptions and methodology with CM and FP&A | I: L4 | Active | L4 | 2024-01-01 | 2026-03-30
Business Only Initiative: Expand automatic DIM&Weight Capture and Scanning C | 35742 | 6887 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | Cecile Xi, Vivien Zhang | On Track | Aligning scope, assumptions and methodology with CM and FP&A | I: L4 | Active | L4 | 2023-09-18 | 2026-04-02
Business Only Initiative: CANH Loading team Manpower Efficiency |  | 189706 | Business Only Initiative | GAHR - APAC | Global Air Hubs & Ramps | Jin-Xi Rossi Liu | On Track | On Track | G: L3 | Active | L3 | 2026-01-01 | 2026-04-30
Business w/ Tech Initiative: VIPS Retirement |  | 103451 | Business w/ Tech Initiative | FXE AN - Crew | Airline | David Moore, Chuck Galba, Henry Davis | On Track | This project is on track. | G: L3 | Active | L3 | 2024-07-22 | 2028-12-29
Business w/ Tech Initiative: FOCUS Retirement |  | 103455 | Business w/ Tech Initiative | FXE AN - Crew | Airline | David Moore, Chuck Galba, Henry Davis | On Track | Please see the attached word document titled "FOCUS Migration Management Summary - March 2025" | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2028-12-29
Business w/ Tech Initiative: Pilot Mobility |  | 109599 | Business w/ Tech Initiative | FXE AN - Crew | Airline | Christopher J. Spinelli | On Track | The Demand Type of 'Business with Tech' is incorrect; it should be 'Local Enhancements'/'Local Demand'. I emailed Lori Bertella about this and she agreed. We are going resubmit Pilot Mobility as a 'Local Enhancement'. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR - Catering |  | 155483 | Business Only Initiative | FXE AN - Crew | Airline | Ray Jansco, Aman Razzaqi | On Track | shifting ownership to SrMgr Flt Svcs | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: CAN-SIN rolled volume: Work with upline ramps to i | 30337 | 9545 | Business Only Initiative | FXE AN - Density | Airline | Bob Chen, Pinky Jiang | On Track | Change owner to Bob Chen | K: L5 | Completed | L5 | 2023-08-24 | 2023-09-01
Business Only Initiative: 2nd MD11 for SJU | 29854 | 6760 | Business Only Initiative | FXE AN - Fleet | Airline | Kevin Burkhart, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2023-07-31
Business Only Initiative: FY24 757/A300 Aircraft Parking | 31482 | 6801 | Business Only Initiative | FXE AN - Fleet | Airline | Kevin Burkhart, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2023-06-15 | 2024-02-29
Business Only Initiative: Service Recovery Spares Quantification (SRSQ) - Ex | 75003 | 7007 | Business Only Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Taylor Akin | On Track | #7007 SRSQ Execution savings total $6.65M, $3.47M from tail #683 parked 11.10.24 and $3.18M from tail #685 scheduled to park 5.29.25. All the AC MX savings has been recognized in FY25. | K: L5 | Completed | L5 | 2023-12-01 | 2025-05-23
Business w/ Tech Initiative: Service Recovery Spares Quantification (SRSQ) - An | 29855 | 8021 | Business w/ Tech Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Suzanne Sabbatini, Taylor Akin | Attention Needed | 5/20 - VDC placed initiative on hold due to the $0 nRB and low prioritization of the initiative. Cancellation request due to VDC not approving resources for model development to continue. | E: L2 | Cancelled | L2 & CCH | 2023-11-01 | 2025-12-29
Business Only Initiative: Airline Performance KPIs - Fleet (POC) | 33997 | 8022 | Business Only Initiative | FXE AN - Fleet | Airline | Guy M. See, Suzanne Sabbatini, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2024-05-31
Business Only Initiative: MD11 Programmatic Disposition Benefits for FY25 | 77128 | 8042 | Business Only Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2024-04-01 | 2025-02-28
Business Only Initiative: FY24 757 Retirement Depreciation Reduction | 86047 | 8043 | Business Only Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2024-06-14 | 2024-08-15
Business Only Initiative: FY25 Parking of Excess A300/757 Aircraft | 88718 | 8284 | Business Only Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Taylor Akin | On Track | The 5 A300 tails have parked or are scheduled to park within 30 days. The A300 $15.8M savings for FY25 relates to the deferral of MX expense; all completed as of 5/13/25. While initially 5 757 tails were to be parked, changes in the network/system planning during the fiscal year resulted in those tails no longer scheduled to be parked. However, planning was able to still achieve the financial savings of $4.68M with deferral of MX expense on 4 of the 5 tails for FY25; all completed as of 5/13/25. Mx events have been avoided for FY25 and therefore no need to wait for the actual parkings to occur. | K: L5 | Completed | L5 | 2024-08-05 | 2025-05-23
Business Only Initiative: Feeder Optimization - WAVE1 | 73952 | 8789 | Business Only Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Alden Bordwell, Taylor Akin | On Track | Optimize the U.S. Domestic Feeder Network based on four key criteria 1. Assume Feeder network is entirely replaced by trucking alternatives: 2. Analyze what products could be supported if cutoff times change 3. Categorize lanes and analyze trade-offs 4. Build Bottom-up Network | K: L5 | Completed | TEMP L5 - Enter L5 | 2024-02-20 | 2024-11-15
Business Only Initiative: FY25 757 Aircraft Parking from Rightsized I-EU Air | 74588 | 9397 | Business Only Initiative | FXE AN - Fleet | Airline | Kristen Geiger, Guy M. See, Taylor Akin | On Track | Added $28.773M to FY25 as a placeholder for now. Once EU and TO approve the proposed changes, we will a) remove modeled MX savings from #353 and b) add MX event-based savings to 74588 | K: L5 | Completed | L5 | 2024-04-01 | 2025-02-28
Business Only Initiative: Categorization of fleet status | 18215 | 9399 | Business Only Initiative | FXE AN - Fleet | Airline | Kevin Burkhart, Taylor Akin | On Track | Fleet status definitions are critical to the proper understanding of fleet parking opportunities, crew staffing requirements and airline lift capabilities. All groups/departments that report on or use fleet counts must understand the definitions and use them properly to facilitate cost and efficiency analyses. | K: L5 | Completed | L5 | 2023-02-13 | 2023-03-01
Business Only Initiative: Park Excess 757/A300 Aircraft in FY23 | 18216 | 9401 | Business Only Initiative | FXE AN - Fleet | Airline | Kevin Burkhart, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2022-09-01 | 2023-05-31
Business Only Initiative: MD11 Programmatic Disposition Benefits for FY24 | 19156 | 9421 | Business Only Initiative | FXE AN - Fleet | Airline | Kevin Burkhart, Taylor Akin | On Track |  | K: L5 | Completed | L5 | 2022-11-01 | 2024-05-31
Business Only Initiative: EMR - FAO |  | 141987 | Business Only Initiative | FXE AN - Fleet | Airline | Jennifer W. Viard, Alden Bordwell, Aman Razzaqi, Kristen Geiger | On Track | Alden changed to primary IO | G: L3 | Active | L3 | 2026-05-27 | 2026-05-27
Business Only Initiative: EMR - International Jet Fuel Tender |  | 161565 | Business Only Initiative | FXE AN - Fuel | Airline | Ajay Mahankali, LeRoy Marshall | On Track | Tender begins 9/8/25, all setup prior has been completed. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-07-21 | 2026-03-02
Business Only Initiative: EMR - Domestic Jet Fuel Tender |  | 133674 | Business Only Initiative | FXE AN - Fuel | Airline | Michael Crawford, LeRoy Marshall | On Track | Finalizednegotiation & quote activity, starting legal review. | K: L5 | Active | L5 | 2025-09-01 | 2025-09-01
Business Only Initiative: Create Commercial Linehaul Cost Center | 499 | 8670 | Business Only Initiative | FXE AN - Global Partner Network (GPN) | Airline | William Hopp, Clayton Williams | On Track | Created the Cost Centers for each region under a central Memphis entity. Currently waiting for additional guidance on ownership of the cost center by Express. | K: L5 | Completed | L5 | 2023-02-10 | 2023-06-30
Business Only Initiative: CLH Procurement COE | 18904 | 8834 | Business Only Initiative | FXE AN - Global Partner Network (GPN) | Airline | Clayton Williams, Jeff Euler | On Track | Ongoing meetings occuring | K: L5 | Completed | L5 | 2024-04-24 | 2024-08-15
Business Only Initiative: Tricolor CLH Supporting WBRTW Takedown Initiative | 31488 | 8838 | Business Only Initiative | FXE AN - Global Partner Network (GPN) | Airline | Christian Tengs, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2023-06-05 | 2023-09-29
Business w/ Tech Initiative: Fuel Price Accuracy Tool | 88157 | 6687 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Brad Christian, Jacob Triplett | On Track | Initiative ready to move to L5. All vendor changes are in place and all FedEx IT changes are also activated. The new automated process is active now. | K: L5 | Completed | L5 | 2024-08-21 | 2026-05-29
Business w/ Tech Initiative: Economic Tankering Compliance | 47571 | 6965 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Brad Christian, Chris Simons | On Track |  | K: L5 | Completed | L5 | 2023-10-17 | 2024-07-29
Business w/ Tech Initiative: GOC Jet Fuel - Payload Visibility Improvements | 64882 | 6967 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Joey Ray, Brad Christian | On Track | Pulled back to L2 per Dataworks | E: L2 | Active | L2 | 2024-07-01 | 2026-03-27
Business w/ Tech Initiative: GOC Slot Swap Tool | 69671 | 6969 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Brad Christian, Justin Lonie | On Track | Terms with the current vendor ended up being better than expected, so the savings potential for this initiative is no longer going to be worth the internal development costs. Requesting cancellation. | E: L2 | Cancelled | L2 Feedback Requested | 2024-06-10 | 2024-12-31
Business Only Initiative: Alternate fuel policy compliance | 73974 | 7153 | Business Only Initiative | FXE AN - GOC | Airline | Jenn Chessor, Chris Simons, Brad Christian | On Track | Added IO for parental leave | K: L5 | Completed | L5 | 2024-04-09 | 2025-04-01
Business Only Initiative: International Reserve Fuel Policy Compliance | 73983 | 7154 | Business Only Initiative | FXE AN - GOC | Airline | Jenn Chessor, Chris Simons, Brad Christian | On Track | Transfer ownership | K: L5 | Completed | L5 | 2024-04-09 | 2025-04-01
Business Only Initiative: Contingency Fuel Policy Compliance | 74491 | 7155 | Business Only Initiative | FXE AN - GOC | Airline | Jenn Chessor, Chris Simons, Brad Christian | On Track | Transfer ownership | K: L5 | Completed | L5 | 2024-04-09 | 2025-04-01
Business w/ Tech Initiative: Departure fuel rounding changes | 82024 | 7157 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Jenn Chessor, Chris Simons, Brad Christian | On Track | Transfer ownership | K: L5 | Completed | L5 | 2024-08-07 | 2024-12-05
Business w/ Tech Initiative: GOC Proactively identify potential volume spikes t | 73970 | 7381 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Joey Ray | Attention Needed | Ernie Papa is no longer a backup owner Sending back to L2 per Dataworks | E: L2 | Active | L2 | 2024-06-03 | 2026-02-27
Business Only Initiative: Tactical Network Inefficiencies (e.g., Stage Leg R | 73976 | 7382 | Business Only Initiative | FXE AN - GOC | Airline | Joey Ray | On Track | Ernie Papa is no longer a backup owner | K: L5 | Completed | L5 | 2024-05-06 | 2024-05-31
Business Only Initiative: GOC Tactical Flight Cancellations | 81732 | 7384 | Business Only Initiative | FXE AN - GOC | Airline | Joey Ray | On Track | Ernie Papa is no longer a backup owner | K: L5 | Completed | L5 | 2024-05-27 | 2024-06-28
Business w/ Tech Initiative: GOC Ad hoc cost calculator with volume revenue | 73977 | 7434 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Joey Ray, Greg Sullivan | On Track | Adjusted Money Step to 11/15 due to delay caused by onboarding of UI developers from Deliote 12/05 Adjusting Money Step to 5/16/25 for MVP2 delivery to provide an additional 400k of savings. Savings are currently being banked at L3 01/07/25 Loss for Month of DEC24 due to flight schedule underlifted and schedule adds needed | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-10 | 2025-05-30
Business w/ Tech Initiative: GOC Commercial Linehaul Visibility | 73980 | 7435 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Joey Ray, Greg Sullivan | On Track |  | K: L5 | Completed | L5 | 2024-06-10 | 2024-09-13
Business Only Initiative: Revenue visibility to maximize efficiency in inter | 73971 | 7604 | Business Only Initiative | FXE AN - GOC | Airline | Joey Ray | On Track | Tracking L5 values | K: L5 | Completed | L5 | 2024-05-06 | 2024-06-28
Business w/ Tech Initiative: Modernized Flight Planning System | 73978 | 6686 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Brad Christian, Donnie Hopkins | On Track | RFP Complete and vendors downselected to FlightKeys. Benchmarking exercise shows that a potential savings of $19.8M per year is attainable with this transition. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2024-05-01 | 2028-12-28
Business w/ Tech Initiative: Network Report Card KPI Dashboard |  | 88067 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Joey Ray | On Track | * Joey and Nawal Q/A Review (10/9/25) SCO PEO has been informed that they were added as portfolio so they can add it into their L2 Backlog and resource it when they have a resource to assign based on the inits priority. Next Action would be on the SCO PEO to acknowledge and evaluate this initaitive * Updating to add SCO as impacted portfolio (10/9/25) * Working on LBC | E: L2 | Active | L2 Feedback Requested | 2025-11-03 | 2026-02-06
Business Only Initiative: New DEL Alternate | 73981 | 6968 | Business Only Initiative | FXE AN - GOC | Airline | Drew Bailey, Chris Simons | On Track | Requesting to cancel this initiative due to the fact that it's an enabler to a separate initiative that never got off the ground. As such, no financials exist and there's no need to track $0 for 9 months. Canceling per Tom Bassett's recommendation. | K: L5 | Cancelled | L5 | 2024-03-22 | 2024-08-06
Business Only Initiative: Closer alternate airport for Sydney, AU | 82541 | 8308 | Business Only Initiative | FXE AN - GOC | Airline | Drew Bailey | On Track | **Money Step Update** - Canberra Airport & FedEx Legal came to an agreement to use Canberra Airport in January of 2025. Financials started being reported in Feb 2025. . . . As of 7/1/25, we no longer operate HNL-SYD, which part of this initiative is based on. That route has been replaced by OAK-SYD, and will have financial data for OAK-SYD going forward. Financial data is based on: OAK-SYD 5 flights / week With MEL/BNE as alternate: operating cost $101,600 With CBR as alternate: operating cost $100,000 $1,600 saved / per flight 260 flights per year = $416k. Subtract 26%/$108k of that (for flights that wouldn’t need an alternate) and it’s $308k saved per year using CBR iso MEL/BNE | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-02-28
Business w/ Tech Initiative: AIR Modernization Project |  | 161629 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Richard T. Mapes, Patrick Dimento | On Track | Completed PI-31 and moving into PI-32. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Low CI Speed Planning |  | 165017 | Business w/ Tech Initiative | FXE AN - GOC | Airline | Jenn Chessor | On Track | Submit for L1 | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: BUR MARKET OPTIMIZATION | 34127 | 6989 | Business Only Initiative | FXE AN - Hubs and Ramps | Airline | Don Heinz, Rob Wibright | On Track | Flight ceased operations and is no longer operating as of 9/12/23. | K: L5 | Completed | L5 | 2023-08-01 | 2023-10-17
Business Only Initiative: Eliminate AGFS heavy-weight dispatch, absorb into | 1116 | 8376 | Business Only Initiative | FXE AN - Hubs and Ramps | Airline | Tom Barry | On Track | 9/11 - All impacted employees have been notified and timeline of events is in place. Last switchover date will be 10/9 8/21 - still waiting on HR and legal for memos 8/7 - Held a meeting with HR to discuss timing of mapping memos. A delay has occurred with the departure of our L&E team member to another company. A new team member has been assigned and we expect to have the memos completed by 8/18 7/20 - All open positions to be mapped to affected employees have been provided to HR and legal. The next step is to communicate with the managers of these employees and the employees themselves. The goal to have this done is by 8/4. 7/5 - Updated PPT added in attachments. Met with VP/MD audience to review proposed time lines. 6/23 - Schedules for absorption have been received by all regions except the West. This manager is on vacation. 6/8 - The team met on 6/5 to discuss the timeline to execute and move to L4 in the next 90 days. Regional Dispatch Senior Managers have been tasked with providing a rollout schedule for dispatch absorption by location. Legal has provided a sample communication plan and an overview of the Staffing Effectiveness policy. Calls will be set with IO and SVC/RVP audience to gain approvals with the go forward plan. HR is providing a list of available positions in market for the affected employees. Next meeting will be 6/19. | K: L5 | Completed | L5 | 2023-03-01 | 2023-09-01
Business Only Initiative: Janitorial contract for Memphis Hub - FXE | 3014 | 8961 | Business Only Initiative | FXE AN - Hubs and Ramps | Airline | Jared Herring, Brad Courtney, Jacob Shearer, Vivek Cheekoti | On Track | On Track | K: L5 | Completed | L5 | 2023-04-03 | 2024-05-10
Business Only Initiative: TRI-COLOR Aircraft Load Quality Improvements | 462 | 9274 | Business Only Initiative | FXE AN - Hubs and Ramps | Airline | Buck Miller, Rob Wibright | On Track | Global initiative that will need to be reviewed by all the regions where 767's are scheduled to meet MD10/MD11/777 a/c with incompatible containers. Transload time and personnel will need to be reviewed at each gateway or consolidation. Improve density by converting 10% of AAD containers to AMJs on MD10s, MD11s and 777. Currently approximately 670+ AAD ulds are being used in load positions for AMJ ULDS. As such we lose the ability to move an additional 47 pkgs per AAD exception, focusing on 10% capture or 67 ULDS gives us the opportunity from MSL locations to move an additional 3149 pkgs and using gqsa data that 9.3% of wdls request refunds we can avoid 292 MBG events at $29.52 each = an MBG reduction of $8619.84 per day or $2,154,960 per year at 250 days. | K: L5 | Completed | L5 | 2022-11-15 | 2023-03-31
Business Only Initiative: WHQ, WTC, CAC, Hub, and Shady Grove Window Cleanin | 84265 | 9313 | Business Only Initiative | FXE AN - Hubs and Ramps | Airline | Brad Courtney, Jacob Shearer, Vivek Cheekoti | On Track | on track | K: L5 | Completed | L5 | 2024-07-16 | 2024-08-30
Business Only Initiative: Eliminate Atlas contract and return to purple tail | 490 | 7918 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | FLying on the MEM-HNL-MEM and MEM-SJU-MEM to reduce contractual hours and minimize costs N.A.R - Business as usual until we get to the JUL23 schedule and change back to purple tail. | K: L5 | Completed | L5 | 2022-09-01 | 2023-07-03
Business Only Initiative: November 2022 Revision 1 Flight Changes | 1095 | 7919 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Entered Impacts and KPI's for actuals This is a part of the Initiative #1262 collecting all that have been Launched | K: L5 | Completed | L5 | 2022-09-01 | 2022-12-05
Business Only Initiative: Oct24 P3: USPS Flight reductions - FY'25+ | 65718 | 7924 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | n/a | K: L5 | Completed | L5 | 2024-01-10 | 2024-11-22
Business Only Initiative: RAPTOR 1 | 76794 | 7925 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine |  | Rejected by CCH, will revisit additional opportunities. | E: L2 | On Hold | L2 & CCH
Business Only Initiative: RAPTOR 2 | 76816 | 7926 | Business Only Initiative | FXE AN - Network Transformations | Airline | Hannah Herring, Chuck Pounders, Stephen Levine | On Track |  | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-15 | 2025-01-06
Business Only Initiative: RAPTOR 3 | 76838 | 7928 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track |  | E: L2 | Active | L2
Business Only Initiative: RAPTOR Multi Flight Markets | 76841 | 7929 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Pending decisions on RAPTORs 1-3. | E: L2 | Active | L2
Business Only Initiative: RAPTOR 4 | 98016 | 7930 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Reduce VCP (Brazil) service from 6x to 5x | 453 | 7944 | Business Only Initiative | FXE AN - Network Transformations | Airline | Stephen Levine | On Track | The Commercial team has approved the 1x removal. BR-US CLH will be required at start up. GPN team is reviewing Entered Impacts and KPI's for JAN23 actuals | K: L5 | Completed | L5 | 2022-10-12 | 2022-11-30
Business Only Initiative: Front Door Takedown and Network Optimization Marsh | 60533 | 7965 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bryan D'Souza, Stephen Levine, Bryant T. McBride, Megha Susan Alex | On Track | n/a | K: L5 | Completed | L5 | 2023-12-12 | 2024-03-04
Business Only Initiative: MID Linehaul | 37360 | 7972 | Business Only Initiative | FXE AN - Network Transformations | Airline | Stephen Levine, Juan Gomez | On Track | ******Update 3/25/2024:** Thanks Paul. We have scheduled an implementation kickoff call tomorrow to **launch the MID double turn 2X on April 21st and the 5X on July 8th.** We anticipate no showstoppers, but we’ll advise if we run into any. JuanFer From: Paul Tronsor <paul.tronsor@fedex.com> Sent: Thursday, March 21, 2024 1:04 PM To: Juan Fernando Gomez <jfgomez@fedex.com>; Starria Clemmons <starria.clemmons@fedex.com>; Mohamad Sayegh <mhsayegh@fedex.com> Cc: DeeAnn Fulcher <deeann.fulcher@fedex.com>; Geary Hamm <gmhamm@fedex.com>; Joey Narvaez <janarvaez@fedex.com>; dhruv_piyush_shah@mckinsey.com; Alden Bordwell <alden.bordwell@fedex.com>; Timothy Harris <tfharris@fedex.com>; Dan Gleason <dan.gleason@fedex.com>; Amar Sakaan <asakaan@fedex.com>; Patrick Green <pgreen@fedex.com>; Stephen Woodgate <stephen.woodgate@fedex.com>; Chuck Pounders <clpounders@fedex.com>; Stephen Levine <stephen.levine@fedex.com> Subject: RE: MIA-MID PCC Opportunity Approved. Let’s go make this work. Would like an update in three months to see if we are getting the revenue we thought and evaluate the reliability as Tim has pointed out. PT From: Juan Fernando Gomez <jfgomez@fedex.com> Sent: Wednesday, March 20, 2024 5:57 PM To: Starria Clemmons <starria.clemmons@fedex.com>; Paul Tronsor <paul.tronsor@fedex.com>; Mohamad Sayegh <mhsayegh@fedex.com> Cc: DeeAnn Fulcher <deeann.fulcher@fedex.com>; Geary Hamm <gmhamm@fedex.com>; Joey Narvaez <janarvaez@fedex.com>; dhruv_piyush_shah@mckinsey.com; Alden Bordwell <alden.bordwell@fedex.com>; Timothy Harris <tfharris@fedex.com>; Dan Gleason <dan.gleason@fedex.com>; Amar Sakaan <asakaan@fedex.com>; Patrick Green <pgreen@fedex.com>; Stephen Woodgate <stephen.woodgate@fedex.com>; Chuck Pounders <clpounders@fedex.com>; Stephen Levine <stephen.levine@fedex.com> Subject: RE: MIA-MID PCC Opportunity **Hi Starria, we have reviewed in LAC and the double turn is good from our end to start either on April 21st - 2X, or on July 8th- 5X.** GNP’s approval is next. + Chuck and Stephen 090123 Block space proposal sent to Amerijet this week and waiting on a counter offer from Amerijet . 082123 082523 - Update Update: The ASD completed a high level “target rate” proposal for an Amerijet Block Space Agreement MIA-MID-MIA in a B757 (@ 25K lbs. each direction). Below is a proposed range of per-flight prices based on three different data points, assuming we would be able to block 25k pounds per flight each direction MIA-MID-MIA: Same cost as what our current feeder costs us: ~$19k a. Yes, this is probably pretty unreasonable; yet, it’s just a data point and would be a huge win if somehow it made sense If we are securing a BSA, we should be able to negotiate something lower than the average market rate a. For this initial discussion, let’s aim for get a 10% discount on the average MID-MIA air cargo price (per IATA) of $0.55/lb and get that down to ~$0.50/lb: ~$25k b. This may not buy us the specific departure/arrival times we want necessarily…see #3 below Understanding that there may be an additional cost to securing the ideal departure/arrival times needed to retain our current service offering, we should still at least target a 5% efficiency on our current cost/lb: ~$30k Note that this is a starting point and is directional only—we would still need to develop a P&L with incremental revenue, etc. to facilitate approvals needed. ![](inline-attachments/37360/image/dee41fbf-0f60-4750-9516-168e444077a3-image.png) | K: L5 | Completed | L5 | 2024-07-12 | 2024-07-12
Business Only Initiative: Eliminate WBRTW (P- MEM-SEA-ANC-PVG F-CAN-CDG A | 464 | 9329 | Business Only Initiative | FXE AN - Network Transformations | Airline | Stephen Levine, Richard Ramirez | On Track | 080723 - Impacts for Fuel revised to FY23 baseline figures. 060123 Approved by Executive Mgmt team to begin with the SEP23 schedule vs. OCT23 042023 -Updates from Paul Sousa 5 key milestones (assuming Oct’23 execution): 1. Budget set up in associated cost centers (e.g. CLH buy, revenue loss) – Jun’23 2. Flight schedule change – 1.5 month before execution – Mid-Aug’23 3. Yield management – Aug’23 4. CLH readiness – Sep’23 5. Ops readiness – Sep’23 Workstreams for each milestones & dependencies Workstreams 1.Air Network Planning workstream – Paul Sousa, Celine Semiond 2.CLH workstream – Kheng-Yau Yeoh, Audrey Kilesse 3.Revenue workstream – Alex Siu, Pieter Coeman 4.Finance workstream – Pat Kwok, Anke Van Gulck Dependencies 1.CLH availability 2.Yield management execution 3.GPN enablers (for TA FICP to flow via CLH) 042023 - FINANCIAL REVIEW - IMPACTS ENTERED - WAVE ASSUMES $3.50 PER GALLON. Decision P&L assumes $3.00 per gallon 041923 - Update Routing has been vetted (MEM-SEA-ANC-CAN-CDG-MEM) 032323 - Revived the conversation with the WBRTW take down. The team continues to review revenue opportunities with regional leadership. Targeted to go to the Commercial Clearinghouse on 11/22/22. | K: L5 | Completed | L5 | 2023-04-03 | 2023-09-01
Business Only Initiative: CYCLOPS- TransAtlantic - Pricing Actions |  | 108291 | Business Only Initiative | FXE AN - Network Transformations | Airline | Hannah Herring | On Track | Already in money step execution-wise, just need to catchup in Planview structure | I: L4 | Cancelled | L4 | 2025-03-03 | 2025-03-03
Business Only Initiative: CYCLOPS- TransPacific - Pricing Actions |  | 108295 | Business Only Initiative | FXE AN - Network Transformations | Airline | Hannah Herring | On Track | Already in money step execution-wise, just need to catchup in Planview structure | I: L4 | Cancelled | L4 | 2025-03-03 | 2025-03-03
Business Only Initiative: CYCLOPS- FrontDoor - Pricing Actions |  | 108298 | Business Only Initiative | FXE AN - Network Transformations | Airline | Hannah Herring | On Track | Already in money step execution-wise, just need to catchup in Planview structure | I: L4 | Cancelled | L4 | 2025-03-03 | 2025-03-03
Business w/ Tech Initiative: FXL Transformation Transportation |  | 114420 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Pieter Kop | On Track | Status 13 April 2026 High lights: * Ireland, Mexico and Brazil transitioned to CargoWise on April 1, 2026 Overall deployment plan, go live: * Canada - July 1, 2026 * Australia & New Zealand - July 1, 2026 * Hungary, Czech and Romania - Sep 1, 2026 Canada Go Live with CW on July 1 is at risk due to IT development required by Wisetech, followed by FedEx. Australia & New Zealand Go Live with CW is at risk, due to resquired IT integrations and Configurations that are delayed due to resource challenges. Deployment completed: SG, MY, UK, UA, TW, CN, HK, BE, NL, US, QT, SA, VN, DE, IN, FR, KR, TH, ES, PL, TR, JP, IT, ZA, IE, MX, BR (27countries) | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-01-01
Business w/ Tech Initiative: FXL US WMS replacement |  | 114593 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Pieter Kop | Some Issues | 4/10 Meeting with Executives still planned for April 13, 2026. Will update with next steps after this meeting 3/25/2026 Waiting for approval business case and prioritization. Meeting with FXL Executives on April 13, 2026 January 29, 2026: pending revised business case. Expect to be finalyzed for presentation to FXL Leadership in Feb 2026. Expect to submit for PEL Greenlight approval Feb 2026. | E: L2 | Active | L2
Business w/ Tech Initiative: FXL Ocean rate management and quoting |  | 114600 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Pieter Kop | Attention Needed | The rate managment and quoting solution enabler has been included as milestone in Strategic Initiative FXL Transformation Transportation (114420). Decission made as same systems (CargoWise) will be applied to implement this enabler. Benefits and implementation costs are included in FXL Transformation Transportation. | C: L1 | Cancelled | L1
Business Only Initiative: JAN23 Flight Cancellations at FNL | 10478 | 7939 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | JAN23 only flight cancellations at FNL. Waiting on L5 approval. | K: L5 | Completed | L5 | 2022-11-08 | 2022-11-25
Business Only Initiative: A300 to 767s CLT Flights JAN23 Only | 10669 | 7940 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Change gauges from the A300 to the 767 for lower DOCs . Market CLT Waiting on L5 approval | K: L5 | Completed | L5 | 2022-11-14 | 2022-12-30
Business Only Initiative: A300 to 767s for the TPA flight JAN23 Only | 10678 | 7941 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Change the TPA flights from an A300 to a 767, JAN23 only Due to a/c availability and flight crew BLGs, we had to change this 767 backt o an A300 for JAN23. Waiting on L5 approval | K: L5 | Completed | L5 | 2022-11-07 | 2022-11-28
Business Only Initiative: JAN23 A300 to 767 / 757 for lower DOC's PHL,DEN,S | 10840 | 7923 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Change in guage to meet the lift load while lowering DOC's for the US Domestic Network for the JAN23 Schedule Waiting on L5 approval | K: L5 | Completed | L5 | 2022-10-17 | 2022-12-05
Business Only Initiative: MD11 to 767 Flight Leg Downgauge MCI-MEM-MCI (TWT | 11546 | 7942 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Lower DOC's to operate the 767 vs the MD11 for MCI Flights were downgauged in the FEB23 schedule and tracking for 3 months as the WAVE guidance to submit for L5 | K: L5 | Completed | L5 | 2022-11-14 | 2022-12-13
Business w/ Tech Initiative: LAC C.A Linehaul GUA-GT / SAP-HN (Honduras | 12584 | 7946 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Jorge Palacios, Sandra Parras, Juan Gomez, Stephen Levine | On Track | 7/16/2025: initiative in L5 as of April, it was marked as “Complete” in planview and no longer requires updates to the financials monthly in Planview or for DRIVE purposes LAC Officer Request to add "Parking expense" forecasted but not realized cannot be added to financials forecast/target tab in Planview but is available in https://myfedex.sharepoint.com/:b:/t/G2DHonduras/EeuAWvbHWV9OmVz6xOE5IkkBksxtimipv78vSLsD3Kg-_g?e=ROdldZ for future reference/ future cases 5/29/2025: Actuals not available for Apr 2025 or May 2025 before end of FY; extended Mar 2025 as actuals for these amounts per TO office guidance. 5/27/2015: Financials with actuals updated thru March 2025. 4/21/2025: FP&A actuals updates not received for Mar 2025; PENDING; next update will be in May 2025 4/7/2025: Financials with actuals updated thru December 2024. Tab 1 (original mapped to SBC) Tab 2 (consolidated version mapped to SBC approved by officers January 2025). LAC plans to update acutuals based on Tab 2 version, Excel link. Excel Link: https://myfedex.sharepoint.com/:f:/t/G2DHonduras/EohYnCG7roVOpvr-_y10ifIBPJiBC5WcFJFQ2mIXsbZMjg?e=a7GhV0 01/20/2025: Project is fully implemented as of Sep 16, 2024 but cannot be moved to L5 (money step) in the system until the VP alignment occurs. Date for alignment is in progress Background: Although financials performance through Nov 2024 are available, LAC Team reconciling the #s needs more time for VP alignment before I/O can input the information. For reporting purposes: Sandra Parras to be the key contact for data entry/I/O until Jorge Palacios receives access to PV 10212024 - Previous I/O left FedEx; New I/O: Juan Fer Gomez 072523 Added Initiative Diagrams ![](inline-attachments/12584/image/d086a275-b9e0-4eae-b85d-95bc569657bd-image.png) North Loop Optimization Review for additional savings, 2 scenarios being reviewed. 757 dependent for one option. MAYA LOOP= MIA-GUA-SAP-MIA 5x JUN24 START UP DATE - PENDING THE LARGE A/C REVIEW per Joey 050823 ![](inline-attachments/12584/image/653d7f06-a07b-429f-b510-75b1cc79857d-image.png) 050423 Update YR2 is expected to be $3.2M and then it grows from there. YR1 is break even. If we just need a single number I’d recommend $3.2M since that is more reflective. 050223 - Milestones in place and structurally complete and reviewed. HN G2D / MAYA LOOP - 757 to replace 2 ATR72-600Fs 042623 1.Central America Linehaul GUA-GT / SAP-HN (Honduras) NEW JET CITIES (formally NORTH LOOP) 1a. Ameri jet SAP (waiting on rates) DRIVE: Target for L2: May 8 – may be delayed as we are pending Financials to be finalized and then L2 approval – dates are not available Risk to Apr 2024 Corporate Load: CPEL team will not move the G2D HN project to Solutioning until Wave is L2 approved ; Mitigation Plan: Documents needed for Solutioning Step 1 have been submitted [i.e.PDD] 042623 TECH SUPPORT REQUIRED FOR THIS INITIATIVE: - Enable FedEx Systems for accounts payable , receivables, legal entity and ramp operations / clearance in Honduras (SAP). - Per the project leads: We must have all in place for the corporate load by April 2024. Value Prop - Additional Capacity into SAP Revenue Quality - Incremental Revenue in LAC per the Commercial team forecasted data HR Dependency - Hiring at the ramp and back office to support Risk - 757 availability and flight crew support Risk - Corporate load risk if not completed by April 2024 042623 1.Central America Linehaul GUA-GT / SAP-HN (Honduras) NEW JET CITIES (formally NORTH LOOP) 1a. Ameri jet SAP (waiting on rates) | K: L5 | Completed | L5 | 2023-05-01 | 2025-07-16
Business Only Initiative: AIRPOD (Intiatives 473, 476-489) = 1262 Structura | 1262 | 7921 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Entered Impacts and KPI's for actuals | K: L5 | Completed | L5 | 2022-10-31 | 2022-10-31
Business Only Initiative: YOW/YMX truck vs. flying | 1270 | 7976 | Business Only Initiative | FXE AN - Network Transformations | Airline | Roland Zupancic, Stephen Levine | On Track | Update 040523 - Review completed UPDATE: 032823 USI is questioning whether the A300 will hold IND-YMX . Discussions pending with review. UPDATE: 032723 Taken back to L1 to allow added change of flying an A300 IND-YMX, 767MEM-YMX and 757 MEM-YOW in the short term. IMPACTS have been updated for JUN23 and AIR Transformation Management is to supply the number of months the A300 IND-YMX will be in place. JB is still reviewing. The Initiative will remain at L1 until this is determined. jc 032723 031923 Update: GNP /USI reviewed the load data and the plan is to move forward with the 2 767 scenario for YMX and 1 757 YOW. Prioritization of Initiatives 102022 Presented in the 12-20-22 Surge Meeting PM -30 minute cutoff / First delivery would not be until around noon. We are at par with UPS for overnight, we are behind UPS who using world cargo serving Intl overnight and they have a much earlier availability than FXE. Risks, Truck delays, flights arrive in YMX 30% delayed all the time. Delays to wave 2 sort will impact the PM sort operations Canada has asked marketing for analysis to determine business / revenue impact Will have to add trucks and employees. 13 Drivers/ 13 vehicles for 5 pm commit, If we maintain the current commitments they would double their courier and van force. 4 trucks per day YMX-YOW-YMX $1000.00 per truck per day... Later IP delivery and earlier cut offs On road - AM sort end time projected at 10:24 or a loss of 45 minutes. PM - Couriers have to less time or about 4,5 hours on road for the day. 2 million dollar impact to YOW market. YMX has some impact. Crew savings is approximately 2 million. Revenue Breakage or loss of business to come from marketing YOW as a major market will become a noon commit or later. IF we go down this path we will run into building size , crew force management issues, etc. USI / GNP Patrick to socialize this with them. Move YOW direct. MEM YOW - 757 YMX - 767 IND-YMX-YOW - 767 If we an downgauge the MD11. Weekends: Do we need the BUF-YOW flight ? or can we move the YOW SDR on the M-YMX SDR and truck to YOW. Possibly save the YOW-BUF-YOW weekend trunk flights. | K: L5 | Completed | L5 | 2023-01-03 | 2023-05-29
Business w/ Tech Initiative: MD11 to 767 Flight Leg Downgauge LAX #1 MEM-LA | 1886 | 7934 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Entered Impacts and KPI's for actuals | K: L5 | Completed | L5 | 2022-10-03 | 2022-11-30
Business w/ Tech Initiative: MD11 to 767 Flight Leg Downgauge OAK #1 MEM-OAK | 1887 | 7935 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Entered Impacts and KPI's for actuals | K: L5 | Completed | L5 | 2022-10-03 | 2022-11-30
Business Only Initiative: GNP Stage Flights Review & Removal | 31633 | 7943 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | •Staged flights are required to maintain fleet balance throughout the network. •Planners manually comb through all stage flights and decide what changes are required to tighten the schedule and keep it in balance. •The current planning application does not identify opportunities to minimize costs related to staged flights. •It took the team (GNP planners + Pathfinder dev team 2 weeks to go from ideation, iteration to implementation. | K: L5 | Completed | L5 | 2023-05-01 | 2023-07-31
Business Only Initiative: Maritimes Optimization | 33064 | 7977 | Business Only Initiative | FXE AN - Network Transformations | Airline | Roland Zupancic, Stephen Levine | On Track | **3/25/2024:** **Timeline (Updated):** Based on the information from FAO Canada the planned implementation will be in October 2024. Meanwhile, we have introduced this project to all the stakeholders. And we are collaborating with the local teams to finalize the details and address any concerns they might have. We are planning to schedule follow-up calls beginning month of June- 2024 after the launch of Phase 2 of Canadian Transformation Plan (FXE and FXG) to prepare for October 2024 launch. 082423 From JP, this is work under progress . We will need about 1 years' time to crew it before we can launch this . We are seeking an approval through DRIVE so that we can go ahead and ask (Morning Star) to do the needful (crew). Once approval from DRIVE team the lead time to implement this initiative is 1 year. Please see below a quick summary of developments on this initiative and it's current state. 1.System Form team Canada identified the opportunity to increase the lift capacity out of YHZR and YQMR 2.We were working on a couple of challenges in terms of connecting the international freight out of these markets via YMX 3.The proposal mentioned above was in a way came out of the above exercise as the most preferred long-term solution among 4.Looking at the long-term potential of this idea and other operational benefits that come with it, we did our high-level analysis with support from Canadian Finance, A/C ops (FAO) and other teams 5.Through our analysis we all are aligned that we can increase capacity without substantial increase in cost, and also create room for higher yield revenue freight (IP/FO/SO/PO) 6.Hence, we brought this idea to the DRIVE team so that we can validate it thoroughly through the SMEs 7.This lane has been always sought after in the past for high-value perishable IP shipments (seafood / lobsters) and currently the marketing team is crunching some numbers to get an idea of potential additional revenue that they can bring onboard 1. Current state challenges: Outbound capacity of YHZ and YQM is currently constrained as they are sharing a B757 ( F7054 YHZ-YQM-YMX-YYZ ). Additionally, the returning contract linehauls from YHZ and YQM cannot be used to move freight. YMX has operational challenges due to ULD incompatibility between the domestic B757 and international flight which is a B767, delaying F0130 YMX-MEM departure. Moreover, historically YMX has seen a high turnover and staffing challenges among ramp handlers. | K: L5 | Completed | L5 | 2024-02-19 | 2024-11-29
Business Only Initiative: Add a D5 MEM-SJU-MEM flight to help solve backlog | 33576 | 7891 | Business Only Initiative | FXE AN - Network Transformations | Airline | Starria Clemmons, Geary Hamm | On Track | This flight is no longer active in the Phoenix system effective JAN24. Flight operated SEP23-DEC23. 011924 Service Level Update ![](inline-attachments/33576/image/9312d610-fdea-4b68-bec3-0e01f6ab8218-image.png) 121823 Greater details in attachment. ![](inline-attachments/33576/image/919f3c8d-2df2-4730-adad-21fe50b1f979-image.png) 110723 USI plan is to continue flying the D5 MEM-SJU-MEM flight in JAN24 and beyond. GOC & FMC will tactically cancel as needed. Feedback below from AOD Finance (Patrick Green) •This flight was added for seasonal Peak volumes. •We have very firm directive to reduce expense ASAP. If there is space available on the weekend to recover any rollover I cannot recommend extending the D5 rotation as a scheduled flight. •I can support operating ad-hocs as needed. 110623 FX9651 D5 MEM-SJU Update 101823 - Update available in the table above. FX9351 D5 MEM-SJU Update. ![](inline-attachments/33576/image/f9b7cb48-6265-4eea-8502-1d3d82c5a560-image.png) 100923 FX9351 D5 MEM-SJU Update. Also included, trend chart outlining a before/after MBG and NSL service for the 4 Fridays preceding the XS and 4 Fridays after. ![](inline-attachments/33576/image/8264516f-3bf1-4671-8164-1d3909d27d22-image.png) ![](inline-attachments/33576/image/4a1e0397-10b8-4b3d-8224-ac7884527037-image.png) 091223 Starria, John Cap, DeeAnn, & Johnny impact inputs 1262 Initiative is the base for the D5 removal from NOV22. Therefore, our business case will have a 0 baseline. Our impacts will show the cost of a D5 MEM-SJU-MEM. 083023 USI submitted the D5 MEM-SJU extra section request to GNP for Fri 9/1. Revision was approved. Per GNP (John Biggs), the MEM-SJU B767 will be added in the schedule. GOC/FMC can cancel if volume does not warrant. 082923 Friday Onhand SJU Volume ![](inline-attachments/33576/image/dd1a0ec0-5bc1-42b3-bfbe-f19351985669-image.png) 081623 FDR data for August MTD and GLM data for June-Aug MTD for FX55 and here is what was discovered: •47% of the ULDS on FX55 MEM-SJU-PTY-SJO are for either PTY or SJO •ULD weights for PTY and SJO (especially the AADs) could be improved •Substantial voids on the D2 MEM-SJU leg; D3 and D4 have very limited voids •The ABK is barely used at all Geary will work with Ray and Jerry to get FX55 added to the density pod as a focus flight so we can improve stack performance (and ULD weights) to create more capacity on D3-D4. Doing so will allow us to create space so that Jan and the Sales team can sell SJU into the flight on D3 and D4 (plenty of room on D2), and also on D5 when we get it added to the schedule. D5 should only be SJU, and we should have ample capacity to move the existing backlog plus have a runway for growth for SJU. Below are a couple of tables from Geary's analysis. FX55 MEM-SJU voids by DOW 6/1-8/15/23 ![](inline-attachments/33576/image/57cbd958-2eb6-4580-b2c5-e28ee909c3fa-image.png) 081523 USI has exhausted different initiatives and ways to reduce the MEM-SJU rollover creating service issues into the market. Currently utilizing FX55 MEM-SJU-PTY, CLH lanes EWR-SJU & MIA-SJU. There is also a density initiative working with the Hub load teams to increase the utilization of the MEM-SJU flights. The USI team has engaged all Network Transformation teams and has finance reviewing ALL the options. Adding the D5 Northloop rotation back is being reviewed to eliminate 10+ positions of rollover creating adhoc or extra sections operating MEM-SJU. July 19, 2023 Add back a D5 rotation on the MEM-SJU-PTY-SJO flight solve the backlog issue for SJU ![](inline-attachments/33576/image/e612bc0e-19e5-4f37-b826-01968713185d-image.png) | K: L5 | Completed | L5 | 2022-10-04 | 2023-09-26
Business w/ Tech Initiative: MD11 to 767 Flight Leg Downgauge MEM-PDX-OAK-PDX-M | 3511 | 7937 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Update 031923 Changed to MEM-PDX-MEM FRIDAY ONLY downgauge MD11 to 767 Only so financials will change. MAY23 and beyond Tracking FEB23 actual loads in a non response schedule. GNP reviewed : MD11 to 767 Flight Leg Downgauge MEM-PDX-OAK-PDX-MEM (TWTF) FX1807/FX1857 (TWTF) FX0382 FX0400 We will implement the Friday only opportunity. There is 767 ground time available in PDX and the loads work. This will be for the PDX-M-PDX opportunity only. The PDX-OAK-PDX will still move on the MD-11 due to parking constraints in PDX and no other 767 available ground time in PDX. The TWT portion on the MEM-PDX-OAK-PDX-MEM request would be planned at 95-plus 100% on a 767 and is not an option as rollover/missed pieces would be a result on a flight planned at that high of a cube out of MEMH and with expected increasing volume surges to the corners for UPS strike surge volume and possible PML increases in the near term. | K: L5 | Completed | L5 | 2023-03-03 | 2023-03-28
Business w/ Tech Initiative: LAC S.C. Loop Redesign [B767 MIA-EZE-SCL-UIO-MIA] | 40049 | 7101 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Jorge Palacios, Sandra Parras, Juan Gomez, Stephen Levine | On Track | 7/16/2025: initiative in L5 as of April, it was marked as “Complete” in planview and no longer requires updates to the financials monthly in Planview or for DRIVE purposes 5/29/2025: Actuals not available for Apr 2025 or May 2025 before end of FY; extended Mar 2025 as actuals for these amounts per TO office guidance. 5/27/2025: Financials with actuals updated thru March 2025. 4/21/2025: FP&A actuals updates not received for Mar 2025; PENDING; next update will be in May 2025 4/7/2025: Financials with actuals updated thru December 2024. Tab 1 (original mapped to SBC) Tab 2 (consolidated version mapped to SBC approved by officers January 2025). LAC plans to update acutuals based on Tab 2 version, Excel link. Excel Link: https://myfedex.sharepoint.com/:f:/t/SouthConeAirLoopRedesign/EoJnzFdb_4NNt6Rux4a0Sc0BfaqR-9aRLhueSQaDZyImaw?e=Ir8ymc 1/20/2025: Project is fully implemented as of Sep 16, 2024 but cannot be moved to L5 (money step) in the system until the VP alignment occurs. Date for alignment is in progress Background: Although financials performance through Nov 2024 are available, LAC Team reconciling the #s needs more time for VP alignment before I/O can input the information. For reporting purposes: Sandra Parras to be the key contact for data entry/I/O until Jorge Palacios receives access to PV Previous I/O left the company; New I/O= Juan Fer Gomez | K: L5 | Completed | L5 | 2023-11-01 | 2024-11-29
Business Only Initiative: Swap MEM-BTV nonstop for SYR flight | 431 | 7913 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Awaiting L5 approval | K: L5 | Completed | L5 | 2022-08-01 | 2022-11-01
Business Only Initiative: Eliminate Truck Linehaul routes associated with th | 447 | 7931 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Entered Impacts and KPI's for JAN23 actuals | K: L5 | Completed | L5 | 2022-10-03 | 2022-12-13
Business Only Initiative: Eliminate GSO day sort flying 3 -767s (T/W/TH) | 448 | 7932 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | Prioritization of Initiatives 102022 Entered Impacts and KPI's for JAN23 actuals | K: L5 | Completed | L5 | 2022-10-10 | 2022-11-28
Business Only Initiative: Eliminate IND Sunday day sort | 450 | 9318 | Business Only Initiative | FXE AN - Network Transformations | Airline | Stephen Levine, Paul Tronsor | On Track | Entered Impacts and KPI's for JAN23 actuals GNP is almost complete with the JAN23 review. Numbers to be provided by 111722 Approximately 10 dayturns being removed from the JAN23 schedule , Sunday only. Value is approximately $25M. Truck savings are 3,792,362 annualized ![](inline-attachments/450/image/476d6e04-e0db-45d0-a423-1c9ebdf06962-image.png) | K: L5 | Completed | L5 | 2022-11-07 | 2022-12-01
Business Only Initiative: Replace A300 with newer and more efficient B767 BF | 463 | 7933 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine | On Track | 041923 The BFM-MEM-BFM 767 has been downgraded to an A300 for MAY23 and beyond. In its place the A300 FLL-IND-MIA-FLL is a 767 for MAY23 and beyond to replace. No changes to the initiative just a different routing per GNP. SMF, ORF are as is, 767's. Entered Impacts and KPI's for JAN23 actuals Prioritization of Initiatives 102022 | K: L5 | Completed | L5 | 2022-08-16 | 2022-12-16
Business Only Initiative: December schedule peak flying shaping | 468 | 7917 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Awaiting L5 approval. | K: L5 | Completed | L5 | 2022-09-30 | 2022-11-15
Business Only Initiative: TIJ -SAN-TIJ Feeder | 474 | 7945 | Business Only Initiative | FXE AN - Network Transformations | Airline | Stephen Levine | On Track | 040423 NEW TARGET DATE SET FOR THE SEPTEMBER 2023 schedule based on Feeder Ops CREW MEMBER HIRING FOR EMPIRE FEEDER GROUP.. Weekly Updates have been provide by the LAC team in each Tuesday Surge meeting as required. ![](inline-attachments/474/image/ef6e56d5-234c-47ad-af4d-9adb0320ec83-image.png) ![](inline-attachments/474/image/182af1ca-84ea-4475-b8ab-85b4f67631b9-image.png) | K: L5 | Completed | L5 | 2022-10-17 | 2023-08-31
Business Only Initiative: US Domestic Load Plan Process (Create - Formalize | 48636 | 6936 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bob McFarren, Dennis Richardson | On Track | Load Plan Process - NEXT Steps: 10/17/23 – US Domestic Load Plan Process communicated to all US and Canada OPE Managers and MD’ 11/8/23 - All six Training Sessions completed for all US Domestic OPE Engineers 2/15/24 - Target Date to have all load plans reviewed, approved and summitted to Veda Howse. 2/15/24 - All load plans uploaded in the Load Plan storage system 2/15/24 – Target date to be fully implemented with our US Domestic Load Plan Process 2/15/24 - Milestone completion date pushed out to reflect original deadline. 2/15/24 - OPE (US Domestic) On-track to complete by 2-15-24 due date. 2/15/24 - Project fully implemented Assigned Actions to OPE IC Leads (Veda Howse & Ghattas El Murr) for week ending 10/27/23 : OPE IC Training to be scheduled / conducted (OPE Training Leads: Veda Howse and Ghattas El Murr) Develop tracking tool and provide monthly status updates (OPE Leads: Veda Howse and Ghattas El Murr) | K: L5 | Completed | L5 | 2023-10-02 | 2024-02-15
Business Only Initiative: MIA Feeders Network Optimization | 49399 | 7974 | Business Only Initiative | FXE AN - Network Transformations | Airline | Juan Gomez, Stephen Levine | On Track | n/a | K: L5 | Completed | L5 | 2024-05-01 | 2024-05-01
Business Only Initiative: GDL downgrade from MD11 to 767 | 68952 | 8178 | Business Only Initiative | FXE AN - Network Transformations | Airline | Stephen Levine, William Vitullo | On Track | n/a | K: L5 | Completed | L5 | 2024-04-19 | 2024-04-19
Business Only Initiative: US Domestic IB and OB Daysort load plans for all M | 73238 | 6937 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bob McFarren, Dennis Richardson | On Track | US Domestic IB and OB Daysort load plans for all MSL’s OPE task to have their IB/OB Domestic “Day Sort” load plans completed and submitted for review by 4/20/24 OPE lead (Veda Howse) to have all IB/OB Domestic “Day Sort” load plans reviewed and posted in the load plan system by 5/20/24 Completion status updates to be provide to all OPE weekly 3/20/24 Load plan lead Veda Howse communicated Load Plan due date of 4/20/24 to all OPE. | K: L5 | Completed | L5 | 2024-03-01 | 2024-05-20
Business Only Initiative: 7080 takedown and D1 GPN | 87333 | 7979 | Business Only Initiative | FXE AN - Network Transformations | Airline | Roland Zupancic, Stephen Levine | On Track | n/a | K: L5 | Completed | L5 | 2024-09-18 | 2024-09-18
Business Only Initiative: Marco Polo for Peak 2024 | 96764 | 7968 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bryan D'Souza, Stephen Levine, Suzanne Sabbatini, Sara Hariga, Bryant T. McBride | On Track | n/a | K: L5 | Completed | L5 | 2024-09-27 | 2024-11-29
Business w/ Tech Initiative: LAC Brazil Domestic Optimization |  | 103177 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Tatiana Farias, Rhina Marte, Sandra Parras, Gabriel Kayser, Elaine Moraes Queiroz | Attention Needed | Jan 20th 2026 - canceled as per Sandra Parras' Instructions From Sandra Parras OIC, VPS + ESPM cc FYI Dear BDE Core and Extended Team: With the recent announcement regarding Brazil Domestic Exit, it means the Brazil Domestic Enablement and Domestic Customer Integration (BDE) Project is canceled Some of you have asked me what should be done with the requests in Planview, Onspring and/or PPM as it relates to Brazil DOM or the other portfolios. Below please find a list of the Planview initiatives that should be canceled NLT Jan 31, 2026. A copy of this email should be attached to each initiative canceled. Job aid link: Setting Initiatives to On Hold-Cancel.pdf I want to thank you for all your efforts in the last few years with BDE and I hope we get to work together in the future Any questions please let me know Thanks Sandra Initiatives to be canceled in Planview by Initiative Owner Rationale: BDE project canceled as of Jan 5, 2026 Initiatives where a PDSM should be entered to cancel the request: Enter a PDSM under Enterprise Tools/Planview to cancel request, email to send to Lisa Rolfe with PDSM # entered Rationale: BDE project canceled as of Jan 5, 2026 Sandra Parras Manager, Program Management Office¦ LAC Marketing¦(786) 473-3605 -------------------------------------------------------- Sep 17th 2025 Pending info to Tech Simplification program movement: Finance approval @sara barnes Refactor initiative in Planview to capture scope for legacy retirement @tatiana farias (pending information from IT) Update financials to show Data & Tech IT hard savings (e.g., NDD contract, others) @tatiana farias (pending information from IT) Obtain approvals from current Domain and DRIVE Pod Leads @rachel segura Aug 15, 2025 : We are pending FP&A team to provide us some guidance and help our I/O MD finalize the business case for submission (due to some other priorities ahead of this one, the PMO has not received a date yet for when we can finalize this item). Apr 28, 2205: Uploaded Business scenarios and AbS for this project | E: L2 | Cancelled | L2 & CCH - Feedback Requested
Business Only Initiative: Remove MEM-ANC-MEM, add YEG-ANC-MEM, and Cancel/Re | 88722 | 6998 | Business Only Initiative | FXE AN - Network Transformations | Airline | Roland Zupancic, Chuck Pounders, Stephen Levine | On Track | All values now represent $18.81M NRB. Submitted for L3 Need to roll back to L2 to update final values. | K: L5 | Completed | L5 | 2024-08-28 | 2024-10-29
Business Only Initiative: LAC-US Load Plan Process (Create - Formalize - Com | 74282 | 7585 | Business Only Initiative | FXE AN - Network Transformations | Airline | Jason Trimble, Mario Corredor | On Track | Load Plan Process - 6/3 - Veda Howse from OP&E confirmed that all LAC-US (MSLs) load plans were uploaded. 4/15 - LAC-US load plan approvals from MEM hub engineers still at 85%. Missing MDE and confirmation for MTY. MDE has to be approved by Miami Engineer. 4/8/2024 - LAC Ramp Ops Mgmt FLC videos training at 100%; Instructor led training workshop being launched for ramp management; Load Plans for LAC – US ramps updates 100% complete. Hub Engineer approvals: 85% complete 4/1/2024 - All LAC-US load plans updated. Load plans currently under review by MEMH Engineering. Met with MEMH Engineer responsible for Load Plan training to review US training process. | K: L5 | Completed | L5 | 2024-02-01 | 2024-05-31
Business w/ Tech Initiative: MD11 to 767 Flight Leg Downgauge MEM-SEA-OAK-SEA-M | 3509 | 7936 | Business w/ Tech Initiative | FXE AN - Network Transformations | Airline | Bradford Wilson, Stephen Levine |  | Reviewing for JUN23 and beyond Tracking FEB23 actual loads in a non response schedule 033123 Update Winston and Brad have completed their review and the flight schedule has been updated to reflect a 767 for the MD11 beginning in MAY23 and beyond Flights have been downgraded to a 767 for all days reviewed and placed into the MAY23 schedule going forward MEM-SEA-OAK-SEA-MEM TWTF FX1423 / FX1223 / FX3824 / FX3884 for MAY23 | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-03-13 | 2024-12-25
Business Only Initiative: Review MEM-VCP-MEM as a 777 vs a 767 | 40048 | 7963 | Business Only Initiative | FXE AN - Network Transformations | Airline | Bryan D'Souza, Stephen Levine, Bryant T. McBride | On Track | Needs to be put on hold until further notice. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Review 767 BQN-SJO-MEM removing the SJO stop and r | 40275 | 7973 | Business Only Initiative | FXE AN - Network Transformations | Airline | Juan Gomez, Stephen Levine |  | n/a | E: L2 | On Hold | L2
Business Only Initiative: Combine MEM-YWG-YEG onto (1) 767 from (2) A300s | 68784 | 7978 | Business Only Initiative | FXE AN - Network Transformations | Airline | Roland Zupancic, Stephen Levine |  | Initiative 88722 to take place of this initiative. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-22 | 2024-09-19
Business Only Initiative: YOW optimization - MEM-ROC-YOW-MEM |  | 89679 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Hawaiian Punch |  | 93289 | Business Only Initiative | FXE AN - Network Transformations | Airline | Hannah Herring, Chuck Pounders | On Track | Intra-HI flights launched September 3rd. We are already moving more volume than before with the CLH carriers. CLH carrier contracts cancelled after September (gone in October). 2 of the 3 CLH carriers have been cancelled. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-08-01 | 2025-10-01
Business Only Initiative: Removal of INDH Twilight Flights - JAN23 Only | 10357 | 7922 | Business Only Initiative | FXE AN - Network Transformations | Airline | Chuck Pounders, Stephen Levine | On Track | Flights removed from the JAN23 schedule for efficiencies Waiting on L5 approval | K: L5 | Completed | L5 | 2022-11-14 | 2022-12-30
Business Only Initiative: ANC-MEM/EWR-ANC Takedown |  | 165706 | Business Only Initiative | FXE AN - Network Transformations | Airline | Hannah Herring | On Track | Already implemented. | K: L5 | Active | L5 | 2025-06-02 | 2025-06-02
Business Only Initiative: Evaluate Insourcing vs Outsourcing of Heavy Aircra | 84451 | 6995 | Business Only Initiative | FXE AN - Tech Ops | Airline | Curt Gobbell, Marion Maund, Christopher Darr, Robert Broom, Pattilynn T. Brasfield | On Track | Analysis by Mx Planning plus hangar management projects excess AMT manhours in MEM and IND after Oct-24 which can be redeployed to support a second 767 HMV line at IND. This additional line will require no incremental headcount to either MEM or IND. The MEM excess will be "transferred" to IND by MEM taking on a gear change line that is presently at IND. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-20 | 2025-02-04
Business Only Initiative: Reduce 767 Engine Lifecycle Cost- FY24 | 66865 | 7402 | Business Only Initiative | FXE AN - Tech Ops | Airline | Adam Beaugh, Rebecca Behrends | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2024-03-29
Business Only Initiative: A300 Brake Workscope Optimization | 69585 | 7447 | Business Only Initiative | FXE AN - Tech Ops | Airline | Tommy Johnston, Joe Lee | On Track |  | K: L5 | Completed | L5 | 2023-11-09 | 2024-09-30
Business Only Initiative: Insourcing of repairable A/C parts to FDX internal | 85091 | 7656 | Business Only Initiative | FXE AN - Tech Ops | Airline | Tommy Johnston, Marion Maund | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-05 | 2025-01-31
Business Only Initiative: Third-Party Aircraft Maintenance Service Provider | 84764 | 7675 | Business Only Initiative | FXE AN - Tech Ops | Airline | Dan Parent, Michael Sanford | On Track | Positive Revenue recorded for 17 consecutive months. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-01 | 2026-01-30
Business Only Initiative: French Carbon Taxes compensation | 21893 | 8020 | Business Only Initiative | FXE AN - Tech Ops | Airline | Barbara Iglesias, Suzanne Sabbatini | On Track | This initiative has been completed and the saving is $ 462K for Calendar year 2022 (January-December 2022). We keep identifying projects for calendar year 2023. Final invoice from the vendor to be received. The concept is based on finding project eligible according to the French Law Resilience that can offset the penalty on a full credit payment estimated in February in 100EUR per tone. | K: L5 | Completed | L5 | 2023-09-29 | 2023-09-29
Business Only Initiative: PMA/DER Incorporation in Engine LRUs/Externals | 17366 | 8088 | Business Only Initiative | FXE AN - Tech Ops | Airline | Adam Beaugh, Tommy Johnston | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-01 | 2023-12-15
Business Only Initiative: Landing Gear Mx Sourcing | 51185 | 8089 | Business Only Initiative | FXE AN - Tech Ops | Airline | David L. Wrushen, Adam Beaugh, Tommy Johnston | On Track | RFQ for landing gear contracts was released. Bids must be fully analyzed so value cannot be calculated at this time. | K: L5 | Active | L5 Feedback Requested | 2023-08-28 | 2024-08-30
Business w/ Tech Initiative: Evaluate Component Servicing/Repair for other airl | 84453 | 8090 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | Sarah Subick, Tommy Johnston | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Reducing A300 GE Engine Mx Expense | 30721 | 8255 | Business Only Initiative | FXE AN - Tech Ops | Airline | Adam Beaugh | On Track |  | K: L5 | Active | L5 Feedback Requested | 2023-06-01 | 2024-05-31
Business Only Initiative: Reduce 777 Engine Mx Expense- FY24 | 67864 | 8256 | Business Only Initiative | FXE AN - Tech Ops | Airline | Adam Beaugh | On Track |  | K: L5 | Completed | L5 | 2023-09-01 | 2024-04-30
Business Only Initiative: Parts Rationalization | 1457 | 8377 | Business Only Initiative | FXE AN - Tech Ops | Airline | Tommy Johnston | On Track |  | K: L5 | Completed | L5 | 2022-11-29 | 2022-12-30
Business Only Initiative: A/C Line maintenance Canada | 84244 | 8820 | Business Only Initiative | FXE AN - Tech Ops | Airline | Antonia Rivera, Aman Razzaqi | On Track |  | K: L5 | Completed | L5 | 2024-03-22 | 2024-09-13
Business Only Initiative: EMR - Phased Supplier Negotiation | 87325 | 8823 | Business Only Initiative | FXE AN - Tech Ops | Airline | Vincent Coutoumanos, Michael Wilson | On Track | Finalizing savings with Material Management team. Next step will be to amend contracts with Direct Ship Suppliers before the end of 2025 / early 2026 | G: L3 | Active | L3 | 2026-10-29 | 2026-10-29
Business w/ Tech Initiative: Vendor Management Optimization | 17421 | 9352 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | Tommy Johnston, Joshua Canfield | On Track |  | K: L5 | Active | L5 | 2023-10-06 | 2026-04-30
Business Only Initiative: Optimize POSHs | 17453 | 9354 | Business Only Initiative | FXE AN - Tech Ops | Airline | Leo Warmuth, Jennifer Baker | On Track |  | K: L5 | Completed | L5 | 2023-01-31 | 2023-06-15
Business Only Initiative: Optimize shipping costs | 17502 | 9356 | Business Only Initiative | FXE AN - Tech Ops | Airline | Joe Lee, Craig Smith | On Track | Money Milestone needed | K: L5 | Completed | L5 | 2023-06-01 | 2023-07-31
Business Only Initiative: POSH Optimization - APUs and Thrust Reversers | 84402 | 9363 | Business Only Initiative | FXE AN - Tech Ops | Airline | Leo Warmuth, Adam Beaugh | On Track |  | K: L5 | Completed | L5 | 2024-05-01 | 2024-08-19
Business Only Initiative: Parts Regional Rationalization | 71474 | 9374 | Business Only Initiative | FXE AN - Tech Ops | Airline | Tommy Johnston, Adam Beaugh | On Track |  | K: L5 | Completed | L5 | 2024-05-14 | 2024-06-07
Business Only Initiative: Reduce 777 Engine Mx Expense- FY25-27 | 77214 | 9385 | Business Only Initiative | FXE AN - Tech Ops | Airline | Adam Beaugh, Joshua Canfield | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2023-09-01 | 2024-06-21
Business Only Initiative: Reduce 767 Engine Lifecycle Cost- FY25-26 | 77240 | 9396 | Business Only Initiative | FXE AN - Tech Ops | Airline | Adam Beaugh, Joshua Canfield | On Track |  | K: L5 | Active | L5 Feedback Requested | 2024-07-22 | 2026-05-29
Business Only Initiative: CF6-80C2 LLP Sale |  | 85727 | Business Only Initiative | FXE AN - Tech Ops | Airline | Rebecca Behrends | On Track | Contract executed and assets transferred to buyer | K: L5 | Active | TEMP L5 - Enter L5 | 2025-05-19 | 2025-05-19
Business Only Initiative: 767 HMV6 Interval Escalation |  | 87503 | Business Only Initiative | FXE AN - Tech Ops | Airline | Christopher Darr | On Track | Escalation was completed 12/5 with publication of General Maintenance Manual (GMM) revision, and Aircraft Records has updated Workbench tracking of HMV6. There are no stand-alone HMV6 visits on the heavy maintenance schedule for any location, including IND Hangar. More than 3 months of actual savings have been recorded. | K: L5 | Completed | L5 | 2024-12-31 | 2025-02-28
Business Only Initiative: RRC Tactical Rationalization |  | 89245 | Business Only Initiative | FXE AN - Tech Ops | Airline | Tommy Johnston | On Track | on track | K: L5 | Completed | L5 | 2024-11-18 | 2025-05-30
Business Only Initiative: Vendor Management Optimization- Phase 2 |  | 89976 | Business Only Initiative | FXE AN - Tech Ops | Airline | James McCloskey, David L. Wrushen, Michael Wilson | On Track | On track | G: L3 | Active | L3 | 2025-04-22 | 2028-05-31
Business Only Initiative: Trunk Aircraft Fleet Warranty Capture |  | 96584 | Business Only Initiative | FXE AN - Tech Ops | Airline | Michael Wilson | On Track | 90% of warranty capture claims associated with this project have been filed and approved for issuance of a credit memo from the OEM. | K: L5 | Completed | L5 - Restarted Initiative | 2025-02-03 | 2025-05-30
Business w/ Tech Initiative: Accumulating Risk |  | 103866 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | David Frassinelli | On Track | 10 March 2025 Requirement gathering in progress. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AI Optimization for A/C Engineering Tech Support |  | 106233 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | Craig I. Greer, Erin Purnell, Kristen Geiger | On Track | Justin Williams' Data Science team working on analysis for LBC estimates and GenAI POC. | E: L2 | Active | L2
Business w/ Tech Initiative: Aeroxchange (AeroRepair) functionality improvement |  | 109264 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | David L. Wrushen, Tommy Johnston | On Track | 10/9/2025 QA Review with Nawal Harris/IO David Wrushen. Next steps, determine appropriate next steps for Milestone and Epics for SCO and to connect with Commercial PEO on Greenlight Status 6/3/25 After further discussion with Emma Holmes in Enterprise Portfolio Management, moving forward as Business with Tech instead of Local Enhancement demand type. | E: L2 | Active | L2 Feedback Requested | 2025-11-03 | 2026-05-29
Business Only Initiative: EMR - a/c handling |  | 142225 | Business Only Initiative | FXE AN - Tech Ops | Airline | Anthony Castro | On Track | transferred ownership to Mx team | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR-a/c parts suppliers to mkt - late phase |  | 155429 | Business Only Initiative | FXE AN - Tech Ops | Airline | Wayne Nash, Michael Wilson | On Track | Per Anmol Rajvanshi INC033748257 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR-a/c parts suppliers to mkt - early phase |  | 155432 | Business Only Initiative | FXE AN - Tech Ops | Airline | Wayne Nash, Michael Wilson | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR - Honeywell Alternative |  | 155435 | Business Only Initiative | FXE AN - Tech Ops | Airline | Wayne Nash, Michael Wilson | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Aircraft Maintenance Swaps and Trades |  | 161257 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | Nicole Craig, Kristen Geiger | On Track | 4/22/26: We are currently meeting with other stakeholders for this initiative and have come to a point where we need to engage with someone within the EA group. Because METEOR is nearing end of life, we are trying to decide the best path forward on how to accomplish this high-visibility initiative. The current options are 1) build in current Meteor application but the issue is with the payroll pre-processor and the work required to accomplish this effort. 2) Wait until all timekeeping functionality is moved to Workforce Pro. 4/1/26: This request is no longer cancelled. Initiative status was updated to Active in November 2025 per the request of team/management. 10/20/25: Met with MD in Airline Technology - requested to cancel this initiative because we can capture this work as an epic in another initiative (Meteor to UKG). 10/3/25: Currently working on the LBC | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: METEOR to UKG |  | 104755 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | Nicole Craig, Janet Wilson | On Track | 2/12/26: QA Review with QA Expert Nawal Harris. Received feedback on changes required prior to submitting to SL2. 11/7/25: Working with the team to get a better understanding of the cost of the project. Next Meeting: November 24th. 10/3/25: Currently working on changing from GCS to SCO/Air Ops. 9/26/25: • Arch Assessment changed to SCO - approved on 9/19. • Met with Tahiarah Gettis and team to discuss moving initiative to SCO/AirOps on 9/24. Currently in progress. Will submit to SL2 when move has been confirmed. * Name change PDSM approval on 9/25.(Meteor to UKG) 8/29/25: Our team met with Keith Cofield and his team to discuss the EA information. My team has some feature additions and a title change was suggested. I will work on those items next week. 8/22/25: Meeting has been rescheduled from 8/18 to 8/27. 8/8/25: Keith Cofield reached out to provide an update on the Enterprise Architecture information. Meeting has been scheduled for 8/18/25 to discuss in more detail. 7/18/25: Met with our IT team and Keith Cofield to discuss project at a high level. Most work has been completed pending a PDSM change for demand subtype. Waiting on team to review before submitting. 7/11/25: Met wtih Keith Cofield last week for the initial EA meeting. We have another meeting scheduled on July 16th to discuss with my IT team and other stakeholders. Related to planview, I am currently working on gathering more information to update this initiative in order to provide more detail. 6/27/25: Since this initiative can not be linked to the parent UKG project, I have been working with JJ Garcia and Kendra Yarbrough to determine the best course of action. More detail is needed for the demand description and I am working on that information. I also met with Keith Cofield this week and will schedule a meeting with Keith and my leadership to discuss in more detail. 5/23/25: Reviewing feedback from LBC. 5/15/25: Still in ealy stages of researching current feeds. In process of making updates to LBC. In early stages of researching current feeds. | E: L2 | Active | L2
Business Only Initiative: POSH Optimization FY 2026 |  | 186959 | Business Only Initiative | FXE AN - Tech Ops | Airline | Joe Slavinsky, Jennifer Baker | On Track | On Track | G: L3 | Active | L3 | 2025-06-02 | 2026-05-29
Business w/ Tech Initiative: ADAPT Modernization |  | 190914 | Business w/ Tech Initiative | FXE AN - Tech Ops | Airline | Kristen Geiger | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: HS Auto-Classification - Inbound Clearance with FT | 1405 | 7830 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Elizabeth Perez | On Track | 04/03/26 Reopening this inittiative, delivery by SCO 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads 9/24/25 - Initiative moved to On Hold due to prioritization from Dataworks and the limited use of the tool 9/22/25 - Nothing new to report at this time. 9/15/25 - Nothing new to report at this time. 9/8/25 - Nothing new to report at this time. 9/1/25 - Nothing new to report at this time. 8/25/25 - Nothing new to report at this time. 8/18/25 - Nothing new to report at this time. 8/11/25 - Nothing new to report at this time. 8/4/25 - Nothing new to report at this time. 7/28/25 - Nothing new to report at this time. 7/21/25 - Nothing new to report at this time. 7/14/25 - Nothing new to report at this time. 7/7/25 - Nothing new to report at this time. Round 1 of testing on the other tool was done, but another round has been ordered. 6/30/25 - Waiting to see if current version of the tool in Jupiter is replaced with external tool. Testing still going on with other version of the tool. 6/16/25 - Waiting to see if current version of the tool in Jupiter is replaced with external tool demo'd last week. Requested access to the new tool, but it is not operational at this time. 6/10/25 - Intorduced to new predictive tariff tool created by Thomas Seipp's group. Instructed by FXL Leadership to request access and begin using this tool to help it's development. Thomas's version was created a couple of weeks ago and runs on a separate platform than the Jupiter system. Not aware of what that will mean for the version that was originally developed. 6/3/25 - Nothing new to report this week. 5/26/25 - Nothing new to report this week. 5/19/25 - April data input. Nothing further to report. 5/12/25 - Nothing new to report this week. 5/7/25 - Completed rebaselining. 5/5/25 - Nothing new to report this week. 4/28/25 - Received March KPI information will enter it in shortly. Just received word that despite FXL indicating that it was a requirement to have the newest most updated version of the tool integrated into Jupiter system, Dataworks provided the old unmaintained and unupdated version, which explains why performance numbers mirror the poor performance it was prior to integration. 4/21/25 - Updated financials using projected into actuals per Jacob. Sent email to engineering to see if we had any performance statistics. March would be the first full month of the tool being integrated into Jupiter, so checking if feedback loop was closed and we have data to report. 4/14/25 - Working to get the Feb/Mar actuals to have everything in compliance, otherwise nothing new to report at this time. 4/7/25 update - Nothing new to report. Financial issues have been updated and corrected. 3/25/25 update- Nothing new to report this week. Group looking into financial concern has made progress, but still no timeline of when issue will be corrected. 3/17/25 update - Nothing new to report this week. Group looking into financial concern has made progress, but still no timeline of when issue will be corrected. 3/10/25 update - Nothing new to report this week. Still trying to track down financial issue that is currently showing in Planview. 3/3/25 update - Was provided first set accuracy numbers of the current version of the tool. Minimal increase over the previous version. Match rate percentages for a fully qualified HS number is 34% for the top 1 and 50% for top 4. This is up rougly 6% from the previous version of the tool. Still working with Trey to track down financial information and determining where the error might be although it is still believed to be in the transistion from Waze to Planview. 2/24/25 update - Reporting is still being looked at and discussed. Currently just able to see how often the tool is being used and what is being searched. Still many more details to work out to get a proper evaluation | G: L3 | Active | L3 Data Migration - TEMP | 2022-11-08 | 2028-10-09
Business w/ Tech Initiative: Streamline EU D&T Prepayment and ROD Process | 57217 | 7790 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Matthew Evans, Robbert Miltenburg, Sean Brady | Attention Needed | Cancelling as part of initiative rationalization for GC Domain - 11/24 30.07.2025 placed on hold pending leadership decision on preferred way forward for Prepayment and ROD globally 11.07.2025 removed forecast for FY26 as still in re evaluation phase 30.06.2025 L1 baseline changed to FY25 as per acc & controls 23.06.2025 Review of project in line with Gemini - RMS to be held. FY26 priorities to be set with Erik. Metrics and reporting model to be agreed. (First update by Matt Evans) 05.06.2025 STC reassigning IO to this project - project QATs continuing; business case to be finalised with new IO - project to recovine w/c 23 June 24.04.2025 STC reassigning IO to this project - project QATs continuing; business case to be finalised with new IO 06.02.2025 SB Value case prepared to bve submitted to L3 - Robbert to align with Anita for STC Bad Debt portion POC roll out underway in DE QAT for UK underway | E: L2 | Cancelled | L2 | 2023-11-27 | 2026-05-01
Business w/ Tech Initiative: Scale Duty&Tax Online Payment Solutions (DOPS) to | 7062 | 7783 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Aseem Khanolkar, Dora Silva, Alix Perret, Frederic Dalloz | On Track | September 15 2025 - DS: No additional rollouts at this stage. Soft launch countries are not yet using FiT due to unresolved dependencies: * ENS: Awaiting global template alignment and translations. * ETA: English by early September; all languages by end of September. * CREDO: e-Invoice enablement is still pending in several markets: IT, CH, AT, LT, GR, RO, PL, SI. * HOPE: Testing is paused for PT*, TR*, SK*, CY*, BG* due to limited G2D test capacity, expected to resume in October. * Risk: Manual clearance remains necessary in some markets. Re-launch will follow notification review. * MTP: Sign-off pending for payment link expiration logic. Results: * Total Shipments Paid via FIT (USD/month): $15,851,765 * Bad Debt reduction + Paper invoice saving in USD / month: $1,057,000 * % Of Total Fedex D&t Due Paid Via Dops Portal: 15 * Customer Notification Success Rate (%): 87 * Conversion Rate From Notification To Payment (%): 64 ________________________________________________ August 13 2025 - DS: No further rollouts yet; soft launch countries not using FiT due to key dependencies: * ENS: Awaiting global template alignment & translations (ETA: English by early Sep, all languages by end Sep). * CREDO: e-Invoice enablement pending in multiple markets (IT, CH, AT, LT, GR, RO, PL, SI). * HOPE: Testing paused for PT*, TR*, SK*, CY*, BG* due to limited G2D test capacity until Oct. * Risk: Manual clearance still required in some markets; re-launch planned post notification review. * MTP: Payment link expiration logic pending sign-off. Results: * Total Shipments Paid via FIT (USD/month): $18,603,535 * Bad Debt reduction + Paper invoice saving in USD / month: $1,247,000 * % Of Total Fedex D&t Due Paid Via Dops Portal: 14 * Customer Notification Success Rate (%): 86 * Conversion Rate From Notification To Payment (%): 62 ___ July 11 2025 - DS: **Risk** **Manual Processing Still Required**: Some markets lack automated clearance feeds, necessitating manual intervention. The process will be re-launched after the notifications review (target: MTP 12 July). **In Progress** * **ENS Email Notifications:** Content is being revised to ensure global consistency and adaptability across all shipment types. * **Target**: MTP 12 July. * **DOPS Payments – Invoice Delivery:** Transitioning from paper to email invoices in Italy and other upcoming markets. Gareth Millichap is awaiting confirmation of which countries are still pending. Testing will follow, but Gareth is currently tied up with other projects and production issues. He hopes to allocate time later this summer. * **Cash-Based Account Holders:** Planning to expand to these users. Testing is still pending. **Next Steps** * **Broaden Rollout:** Extend to more account holders based on status. * **EU Market Expansion**: Pending HOPE enablement. * L3 configurations are complete for the three country MIDs. * However, GSP2DS testing support in the July CSR is unavailable. * Earliest testing window: October. * Until then, only FBO/paperless invoicing is active. * Payments cannot yet be processed in FedEx systems for these markets. Jun 13 2025 - AP : RISK: The manual activities required in markets not having automated clearance feed IN PROGRESS •Conversion of the paper invoice sent by Post to email invoice for all DOPS payments - Italy + the Mar-Apr-May new markets to be planned •Expansion to account holders having accounts on cash - Testing to be planned NEXT STEPS •Expansion to more account holders based on account statuses •Expansion to more EU markets as follows: oJune 2025 : PT as direct served is planned to go-live in May 25 and if HOPE is enabled oJuly 2025 : TR as direct served is planned to go-live in June 25 and if HOPE is enabled oAugust 2025 : SK as direct served is planned to go-live in July 25 and if HOPE is enabled oFrom November 2025 : CY & BG as direct served is planned to go-live in October and if HOPE is enabled COMPLETED •Expansion to LT, EE, GR, RO, PL, SI, LV, HU, CZ, SE, NO | K: L5 | Active | TEMP L5 - Enter L5 | 2023-04-03 | 2025-06-02
Business w/ Tech Initiative: US - Customer Contact & Engagement (Non-SBP) | 1132 | 7827 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Paul Dewey, Mike Lytle | On Track | Nov: Revised scope due to the gathering of documents, taking case ownership for the aforementioned and not double counting realized savings / expenses from overlapping initiatives. Validated savings over a 4-year period. 11/12/22: Added KPIs and Milestones 11/08/24: Updated actuals on financials 11/15/24: No updates this week 11/21/24: No updates this week. 12/05/24: No updates this week. 12/11/24: Submitted for L5 approval 12/23/24: approved for L5 status 01/08/25: No updates this week. 01/14/25: No updates this week. Submitted for L5 approval. 01/28/25: No updates this week approved for L5 02/10/25: No updates this week. 2/27/25: No updates this week. 03/06/25: No updates this week. 03/13/25: No updates this week. 03/26/25: No updates this week. 04/11/25: No updates this week. 05/02/25: No updates this week. 05/07/25: Rebaseline completed on May 7, 2025. 06/03/25: No updates this week. | K: L5 | Completed | L5 | 2022-10-25 | 2024-09-30
Business w/ Tech Initiative: Scale Clearance document upload solution to reduce | 4762 | 7805 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Sonika Tiwari, Dora Silva, Frederic Dalloz, Aseem Khanolkar | On Track | **September 15 2025 - DS** Operational Updates * Defects: Sync issues, document visibility errors, and incorrect status flags in EasyCustoms & FiT causing delays and manual work * New Features: POAP - Early Power of Attorney collection from residential recipients in Europe Performance Results * Cage reduction: 3.32% * Dwell days reduction: 0.95 * Clearance FTEs saved: 17.6 (+5% vs previous month) * Clearance savings: $62,863 (+1% vs previous month) * No August savings reported due to incomplete P&E model; plug 0 in Planview. Results * Pre-Clearance Rate Improvement: 3 * Dwell Time Reduction: 1 day * % Customers Uploading Missing Info: 52% * FTE Reduction: 18 * August Savings: $0 (P&E model still WIP; new reporting expected end of August) ________________________________________________ August 13 2025 - DS **Defects Impacting Operations**: Major issues with Email/Status sync, document visibility, and incorrect status flags in EasyCustoms & FiT systems are causing delays, manual work, and operational risk. **Performance Results**: * Cage reduction: 3.59% * Dwell days reduction: 1.26 * Clearance FTEs saved: 16.8 (-35% vs previous month) * Clearance savings: $62,359 (-34% vs previous month) * No July savings reported due to incomplete P&E model; plug 0 in Planview. **CZ DocUpload Re-enablement 🇨🇿:** * Recommended Start Date: 14 Sept 2025 * Delay Reasons: * No testing capacity (holiday season) * Key staff (e.g., Jiri) on vacation until end of August * Users need retraining post-holidays * Pending IT feedback on unresolved EC/RC issues * Language code issue resolved **Results**: * Pre-Clearance Rate Improvement: 4 * Dwell Time Reduction: 1 day * % Customers Uploading Missing Info: 50% * FTE Reduction: 17 * July Savings: $0 (P&E model still WIP; new reporting expected end of August) ___________________________________________ July 19th 2025 - Clearance IT team (Genius team), unable to commit on a resolution time to fix the issues preventing to launch the solution in CZ due to capacity. As a consequence Milestones 19880 (Deployment of DocUpload in non-Genius full or Gemini countries (IT, CH, PL, HU, FI, NO, CZ, SE, DK) and money step have been updated with a July 31st end date. End date will be re-adjusted when we have better visibility on the resolution date. - Inititive will be moved to L4, once the solution can be relaunched in CZ. ----------------------------------------------------------------------------------------------------------------------------------------------------------------------------- June 10th 2025 - Milestone 19880 "Implementation in non-Genius or Gemini countries (local cleaarnce systems):Deployment of DocUpload in non-Genius or Gemini countries (IT, CH, PL, HU, FI, NO, CZ, SE, DK)" end date updated to June 30th. End date postponed due further development required in order to launch CZ. No date confirmed at this stage, the milestone will be completed once CZ is moved to produstion. ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- May 27th 2025 - CZ was launched on May 19th but had to be rolled back. More configuration changes on the Clearance system are needed before it can be re-launched. No date available yet. As a consequence the Money step had to be be postponed (by 1 month - will be adjusted once relaunch date is known). ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------ May 7th 2025 - CZ launch scheduled for May 19th ----------------------------------------------------------------------------------------------------------------------------------------------------------------------------- April 24th 2025 - CZ templates finalized - CZ UATs ongoing and will be completed by April 25th. - CZ launch date being discussed with local team (first hal | K: L5 | Active | TEMP L5 - Enter L5 | 2023-04-17 | 2026-05-12
Business Only Initiative: US - Inbound Customer Service Calls | 1133 | 8822 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Paul Dewey, Mike Lytle | On Track | 11/12/22 - Updated KPIs and Milestones for L3 validation 11/8/24 - Updated Finances 11/15/24 - No updates this week 11/21/24 - No updates this week. 12/5/24 - No updates this week. 12/11/24 - Updated actuals & submitted for L5 approval. 12/23/24 - Moved into L5 status. 01/08/25 - No updates this week. 01/14/25 - No updates this week, in L5. 01/28/25: No updates this week. 02/10/25: No updates this week. 02/27/25: No updates this week. 03/06/25: No updates this week. 03/13/25: No updates this week. 03/26/25: No updates this week. 04/11/25: No updates this week. 05/02/25: No updates this week. 05/07/25: No updates this week. 06/03/25: No updates this week. | K: L5 | Completed | L5 | 2022-10-25 | 2023-08-01
Business w/ Tech Initiative: SBP Customers through CFS | 1122 | 7749 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Dawn-Renee Powell, Christy Nicholas | On Track | 1) Need to re review the method used to determine 13.5 M as potential Cost Avoidance - completed - estimated Cost reduction changed to 1.35M 4/5/23 - Note: We are no longer "targeting" specific SBP customers to move to CFS routes as volumes do not support. We are adding (manually) origins to CFS routes and SBP customers will be captured in those, and we will see increased CFS clearance. This initiative #1122 is tied closely to #1121 Route-based general express CFS volume initiative under Scott Wilson Prior to the shift in approach noted above, we completed the below. Initial focus on SBP customers that approve ET86 entries: 1) Identify SBP customers with high Informal entry counts (HTS already required) 2) Identify SBP customers with high SEC321 releases (old and new SBP customers) 3) Customers that ship from minimal origins or have one origin that has good volume and are existing CFS lanes Marketing is continuing to support with the below ask (Customer Clearinghouse review required) 1) Development of formal Customer communication on CFS initiative and benefits is critical Completed - Received approval from Finance on removal of the SBP Fee from ET86- PPM approved and submitted. 3/31/23 - Updated PPM to include removing the trigger for Additional Line-item fee on ET86 entries. | K: L5 | Completed | L5 | 2022-11-02 | 2023-07-31
Business w/ Tech Initiative: [MEISA] [Enabler] IPLV/IPHV capture in department |  | 92772 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Kranthi Chennamsetty | On Track | Cancelling as part of initiative rationalization for GC Domain - 11/24 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: APAC Digital Requirements for US Tariff changes |  | 103069 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Priscilla Karen Yau, Mark Ruddock | On Track | Cancelling as part of initiative rationalization for GC Domain - 11/24 Ongoing discussion with other regions, as this initiative covers asks related to other regions' needs as well | E: L2 | Cancelled | L2
Business Only Initiative: [APAC] iClear Import promotion in NCN region | 59695 | 8186 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Shao Wei Cui, Fei Faye Ning, Yan Pan | On Track | On Track | K: L5 | Completed | L5 | 2023-03-01 | 2024-06-28
Business w/ Tech Initiative: [APAC] iClear collaboration with Dataworks | 73182 | 6897 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Cash Shen, Lorida Bejleri, Nicholas Havens | On Track | 3/9, update monthly finance numbers(savings) since December which has been balanced in BP response reate 99% avg. resonse time 85secds avg. 12/9 iClear export enhancment completed and MTP on Nov. 9. will move to L5 10/10 Accuracy Improvement •Achieved an average accuracy of 83.5%, tested and confirmed by Li Jie. OCR Response Time •We were able to return responses for 85–90% of documents within 5 minutes（replied to Dataworks team that only 68% in Sep) Polygon Information GModel Changes •Changes have been completed and are also awaiting testing confirmation from Li Jie. He tested the old version , requesting him to test the new version. •Please note: this is a complex enhancement. It is difficult to achieve 100% accuracy as it has lot of edge cases. For this rollout, we are targeting 60% as an acceptable benchmark. Concurrent Run •Successfully tested for 50 batch uploads and 20 documents at peak for the external customer use case. UAT testing results: response rate issue which is raised to DWs. Go-production: target on 10/12 but pending for EVP approval 9/15 1. UAT OCR broker session by end of Sep 2. Production in Oct 3. Dataworks enahnce accuracy for 31 fields and Gname/model by end of Oct 7/7 1. The OCR enhancement was completed in June, leading to increased customer adoption. However, accuracy still requires further improvement, currently at 71% compared to eBao's 81% Multiline HS code support – done Merged PDF handling – done 88% of documents processed within 2-3 minutes – done Concurrent processing capability & Batch upload functionality - done 2. Looking ahead to Phase-2, with few spillovers : Improving the accuracy of the G-model Adding polygon information for the remaining fields Customer OCR was delivered in March but suffers from low accuracy and slow response. Dataworks improve quality first, so China IT has paused broker OCR development. (Note: Broker OCR requires backend auto-audit functionality dependent on OCR results, making accuracy critical for this feature.) Broker OCR was originally scheduled for June delivery alongside Dataworks' enhancements. Due to US tariff issues requiring top-priority development, China IT began work in July with September completion targeted. Cost savings will be realized starting October. Our project has delivered $672K value in FY25 in Planview. With enhanced broker OCR from October, FY26 savings are forecast at $2.9M. Continued Dataworks accuracy support (including G-model) remains essential. Meanwhile, we will see more opportunities leveraging our OCR solution not only improving China inbound clearance efficiency but extend to other markets in APAC. 6/24 1. Local enhancment has been approved as L3 for OCR for Broker 2. development would be started since mid of July according to China IT , no involvement of Dataworks 3. the planned develiry date would be end of Sep according to IT 4. the Saving updated according to CANIP/SZXIP feedback. some saving started since Dec last year, majority from iclearexport Cat D vol incrased. 6/17 1. local enhancement still pending approval for L1, Chetan has pushed PEO US team OCR quality improvement with DWs update 1.Production Issue: The reported issue in the production environment has been resolved. The team may proceed with testing. 2.Performance & Accuracy Testing: Penny and team will share the performance and accuracy testing results by next Monday/Tuesday. Cash will consolidate the results and share them with Ayush. 3.UAT Environment: The reported issue in the UAT environment will be resolved within the next 15 minutes. Testing can begin thereafter. 4.Batch Upload Success Rate: A test batch of 50 documents was uploaded; responses were received for 30+ documents. The goal is to achieve a 50/50 success rate. Additional configuration and code optimizations are required and will be included in the July 4 release. 5.GModel Logic Fix: The fix for the GModel logic is currently in progress and is planned for deployme | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-10 | 2025-11-28
Business Only Initiative: APAC_RPA Solution - PEDRO Invoice Check | 55998 | 7813 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Shan Shan Li, Hugh He | On Track | 20250328: in L5 and exempt from rebaseline | K: L5 | Completed | L5 | 2023-09-01 | 2024-04-30
Business Only Initiative: APAC_RPA Solution - PEDRO Advanced Contact | 56001 | 7814 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Shan Shan Li, Hugh He | On Track | 20250328: in L5 and exempt from rebaseline | K: L5 | Completed | L5 | 2023-12-15 | 2024-05-31
Business Only Initiative: [APAC] Customized Clearance Process for IMP | 81411 | 7817 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Jim Jiang, Shan Shan Li | On Track | Cancelling as part of initiative rationalization for GC Domain - 11/24 Clr process alignment completed. waitting for contract with coustomers and AUZ last mile SPS delivery process | I: L4 | Cancelled | L4 | 2024-06-05 | 2024-10-31
Business Only Initiative: [APAC] TW B2B D/T e-payment | 48227 | 8048 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Beatrice Pan, Terry Cheung | On Track | 10/3/2025 Cancelling at the request of the IO due to no value. Approved by finance in the US. 10/1/2025 On hold until we hear from finance on the status of requested cancellation 7/8/25 Actual benefit for June updated 5/18/25 Actual benefit for April updated 4/21/25 Updated Mar2025 saving, there were 299 B2B shpt with D/T paid online, so saving = 2991.09=326, saving is going up but still not meeting target as customer need more time to get registered before pay DT online ------------------------------------------------------------------------ Online DT payment for B2B (Commercial) customer has already launched, customer adoption is slower than expected, Ops is helping customer to register and enroll the service to improve adoption rate for scale up the benefit | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-02-01 | 2026-04-01
Business Only Initiative: D&T Pre and Post Payment Processes Change in Japan |  | 90955 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Kengo Taguchi | On Track | **March 30, 2025:** - This initiative is dependent on DRIVE#33094, Plainview Strategy Sequence ID: 7837, and DRIVE#1235 (Global Bad Debt Reduction). This initiative is not urgent as of now, as the FiT DT (D&T online payment system) must be implemented in the market to begin this initiative. - The current estimated timeline for JP FiT DT (Phase 1 – without pre- & post-payment process changes) is to be enabled in FY26 Q1. - JP FiT DT (Phase 2 – with pre- & post-payment process changes) is planned for implementation in FY26 Q2. **Progress Made:** - Aligned with leadership and the ISD team to complete ACCS JP enhancements (interfacing with the FiT online platform to send and receive Duty & Tax information/notifications), scheduled for CY25-PI02 (April–June 2025). **Upcoming Milestones:** - Development, UAT alignment, and facilitation for JP DOPS Phase 1 (April–June 2025). | C: L1 | Cancelled | L1
Business w/ Tech Initiative: APAC: FiT - Deploy clearance self-service platform | 33094 | 7837 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Kengo Taguchi, Shawn Chan | On Track | **Apr 21st 2026 Update** **Financials:** •Revenue earned: USD 37K (March 2026) **Adoption:** * All initially scoped features under APAC FiT Phase 1 & 2 have now been fully delivered as of March 2026, including the remaining carry-forward items deployed by FiT IT. * In addition, FiT IT launched the Pre-clearance Notification feature in Japan as a pilot on April 21, 2026, following a delay of more than 6 months. * The market-level adoption strategy remains in progress, and the realization of savings will depend on each market’s customer adoption plan and actual uptake. * Given that all scoped features have been delivered and more than 6 months have passed since the rollout of Phase 1 & 2 across all 10 APAC markets, I will proceed with moving this business case to L5 and recognizing the full savings bank-in as committed by APAC. * Further enhancement items, along with adoption improvement and performance monitoring, will be transitioned to PV#154881 to continue driving the intended business value and digital clearance contact expansion across APAC. **Mar 13th 2026 Update** **Financials:** •Revenue earned: USD 36.4K (February 2026) **Adoption:** •FiT updated reason code templates for AU/ID/PH/TH/JP •FiT initial doc missing email engagement is not standardized across APAC. Try to mandate all APAC CCO to customer contact through FiT intiail email. **Feb 11th 2026 Update** **Financials:** •Revenue earned: USD 36.1K (January 2026) **Adoption:** •APAC 10-market adoption strategy is WIP •FiT Clearance Contact Guideline: APAC GTS is preparing standardized guidance to improve document upload ratios. •Sales Enablement Webinar Facilitated a FiT webinar for APAC Sales (collaboration with sales enablement team), with 600+ employees in attendance. •Customer Education Outreach: FiT customer education emails were sent to scoped customers in JP and MY in Jan 2026. PH and other APAC markets are planned for rollout in Feb–Mar 2026. --- **Dec 13th 2025 Update** •$ earned: - 33.1K USD (Nov 2025), 32.7K USD (Oct 2025) Just around 50% vs. original target. We will make it 100% by end of FY26. --- **Oct 30th 2025 Update** •$ earned: - 28.9K USD (Sept 2025) --- **Sep 3rd 2025 Update** •$ earned: - 20.7K USD (August 2025) --- **-RAG (Red, Amber, Green) Status: is the project on track (green), in caution (amber), or at risk (red) of meeting its L4 date?** Status: Green --- **-Complete: Items/tasks completed over the last 2 weeks.** * Submitted "Strategic ID: 9746 APAC FiT: Phase 2.5 enhance for customer adoption" for additional APAC FiT enhancement for FY26. (Currently, SL2 review) * FiT ID MTP and GTM on Aug 28th. *As of Sep 3rd, 9 APAC markets (AU/ID/JP/KR/MY/NZ/PH/TH/TW) go live already. --- **-In progress: Items/tasks occurring/in progress over the next 1-2 weeks** * FiT Phase 2.5 enhancements (another PV#154881) demand intake session for CY25-PI05 --- **-Next steps: Items/tasks planned for in the next 2-3 weeks** * Move "Strategic ID: 9746 APAC FiT: Phase 2.5 enhance for customer adoption" to L3 * SG: MTP target date: Sept 17th * APAC FiT customer adoption plan at each market will be aligned among stakeholders in 15th of Sept. --- **-Awareness: ** Strategic ID: 154881 APAC FiT: Phase 2.5 enhance for customer adoption must be moved L3 for IT development by 10th Sep 2025. ---- **Aug 26th 2025 Update** •$ earned: **-RAG (Red, Amber, Green) Status: is the project on track (green), in caution (amber), or at risk (red) of meeting its L4 date?** Status: Green **-Complete: Items/tasks completed over the last 2 weeks.** * Submitted "Strategic ID: 9746 APAC FiT: Phase 2.5 enhance for customer adoption" for additional APAC FiT enhancement for FY26. (Currently, SL2 review) * APAC FiT Dashboard to measure customer adoption ratio. (Power BI 2nd draft version ready for internal review) * FiT PH MTP and GTM on Aug 26th. *As of Aug 26th, 8 APAC markets (AU/JP/KR/MY/NZ/PH/TH/TW) go live already. **-In progress: | K: L5 | Active | L5 | 2024-01-01 | 2025-08-29
Business Only Initiative: [APAC] Deflect clearance requests to FiT(JP/KR/MY) | 18792 | 8200 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Yen Shen, Grace Quan | On Track | On track | G: L3 | Active | TEMP L3 - Enter L3 | 2023-04-04 | 2025-08-29
Business Only Initiative: [AMEA] Clearance Task Volume Reduction | 93658 | 7854 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Shu-Hui Chen | Some Issues | Cancelling as part of initiative rationalization for GC Domain - 11/24 MX new regulation and US new tariff brought uncontrollable impacts to this project. After discussions with MD and Sr mgr., we decided to put this project on hold. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: FD – Clearance Documentation Guidance |  | 91233 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Doug Mahan, Sanjoy Dutta | On Track | Cancelling as part of initiative rationalization for GC Domain - 11/24 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Simplified commodity shipping within European Unio | 18177 | 9395 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Geraldine Van Outryve d'Ydewal, Natalia Sanchez | On Track | Cancelling as part of initiative rationalization for GC Domain - 11/24 05/03/2025 submit to L4, pending Dylan Davies approval 07/02/2025 Start of L3 testing from Feb2 as per schedule for Republic of Ireland & the results look good so far for MAGIC, GSM, VACS, Trade Tools, CRSV More results from rest of the applications expected to come prior to the launch planned on Feb 17th. 31/01/2025 Approval received from Alex Ferrier and Terri Tennison on the new scope (including IE and exclusing Northern Ireland) on Jan 22nd. Now we are targeting February 14, 2025, to load the new policy grid changes and activate the functionality in production for the initiative. Additionally, for FUSE/EDI/FLAGS, there is a documentation change: the Republic of Ireland will be included in Intra EU, while Northern Ireland will remain unsimplified (meaning customers will need to enter all the commodity details). Meeting taking place with GTM/GTS team to agree on new dates for comm around launch date. 24/01/2025 Simplify Commodity Shipping has been loaded on January 11th, but decoupled, meaning the new functionalities are swithed off. This is due to a last minut change of scope request by Clearance. New business requirements need to be provided, after approval on the new scope definition is given by Clearance Team. New timelines to be defined pending the complexity of the new business requirements. | I: L4 | Cancelled | L4 | 2023-06-01 | 2025-05-30
Business w/ Tech Initiative: HS classificaion and validation |  | 107512 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Bryan Bunker, Stephanie Waltman | On Track | Initiative to be cancelled | C: L1 | Cancelled | L1 | 2024-07-22 | 2026-07-09
Business w/ Tech Initiative: Document flow creation, management |  | 107516 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Naveen Mamidipalli | On Track | Initiative to be cancelled | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Estimation of duties and taxes |  | 107519 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Deepesh David | On Track | Initiative to be cancelled. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [MEISA] FiT launch in Saudi Arabia |  | 110060 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Jyotsna Wadhwa , Mohamed Ali | On Track | On track Impacted CE ESI KPIs: - Improve EDD Accuracy: Streamline clearance process through automation to enhance on-time clearance, hence improve delivery within committed delivery date - Reduce Recurring Problem Rate: Reduce clearance under wrong ID/entity numbers as the customer can proactively share clearance information or notify the broker on special requirements | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-20 | 2026-06-29
Business w/ Tech Initiative: Process & systems review for broker clearance |  | 110943 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Mark Ruddock | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads | C: L1 | Cancelled | L1
Business w/ Tech Initiative: MAGIC - Clearance ¦ Customs AI |  | 112934 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Obbe Bangma | On Track | 09/15/2025 - Connected with Domain QA Expert (Trey S.) to review L1 LBC | E: L2 | Active | L2
Business w/ Tech Initiative: VCC - Simplify Int'l Shipper Experience w/ fdx |  | 113585 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Anantha Venkatesh | On Track | Linda Fitch requested the cancellation All, Please cancel the following Planview Initiatives by EOD, Tue Aug 5th. If needed, please refer to Kim’s email below. Setting Initiatives to On Hold-Cancel.pdf NameStrategy Seq. IDPodDomainInitiative Owner HS classificaion and validation107512Customer ExperienceGlobal ClearanceBryan Bunker, Stephanie Waltman Document flow creation, management107516Customer ExperienceGlobal ClearanceNaveen Mamidipalli Estimation of duties and taxes107519Customer ExperienceGlobal ClearanceDeepesh David VCC - Simplify Int'l Shipper Experience w/ fdx113585Customer ExperienceGlobal ClearanceAnantha Venkatesh VCC - Simplify Int'l Shipper Experience w/ fdx113586Customer ExperienceGlobal ClearanceAnantha Venkatesh (VCC) - Consolidation Engine113589Customer ExperienceGlobal ClearanceDeepesh David Downstream auto- population of clearance systems108369Operational ExcellenceGlobal ClearanceRobert Heatley | C: L1 | Cancelled | L1
Business w/ Tech Initiative: VCC - Simplify Int'l Shipper Experience w/ fdx |  | 113586 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Anantha Venkatesh | On Track | Linda Fitch requested the cancellation All, Please cancel the following Planview Initiatives by EOD, Tue Aug 5th. If needed, please refer to Kim’s email below. Setting Initiatives to On Hold-Cancel.pdf NameStrategy Seq. IDPodDomainInitiative Owner HS classificaion and validation107512Customer ExperienceGlobal ClearanceBryan Bunker, Stephanie Waltman Document flow creation, management107516Customer ExperienceGlobal ClearanceNaveen Mamidipalli Estimation of duties and taxes107519Customer ExperienceGlobal ClearanceDeepesh David VCC - Simplify Int'l Shipper Experience w/ fdx113585Customer ExperienceGlobal ClearanceAnantha Venkatesh VCC - Simplify Int'l Shipper Experience w/ fdx113586Customer ExperienceGlobal ClearanceAnantha Venkatesh (VCC) - Consolidation Engine113589Customer ExperienceGlobal ClearanceDeepesh David Downstream auto- population of clearance systems108369Operational ExcellenceGlobal ClearanceRobert Heatley | C: L1 | Cancelled | L1
Business w/ Tech Initiative: (VCC) - Consolidation Engine |  | 113589 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Deepesh David | On Track | Initiative to be cancelled. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: APAC Flight Details Web Tool Replacement |  | 113709 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Kwan-Hung Leung | On Track | Cancelling as part of initiative rationalization for GC Domain - 11/24 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Project Michelangelo |  | 131235 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Anantha Venkatesh, Sheila Graven, Robert Heatley | On Track | .Post MVP, this Alpha phase product is currently translating VOC into feature enhancements for a series of post MVP iterative releases through September. This development is in progress but incomplete. Additionally, the team is working through a scaled pitching, onboarding, and adoption campaign to maximize market acceptance. Lastly, the team is working though operational readiness and GTM processes to validate the post MVP launch. | E: L2 | On Hold | TEMP L2 - Enter Portfolio Greenlight | 2025-04-30 | 2026-08-21
Business w/ Tech Initiative: RISK Classification KPI |  | 131242 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Deepesh David | On Track | Can be cancelled - Initiative no longer a requirement due to Project Michelangelo | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Project Michelangelo - VCC |  | 136567 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Dakota Sebourn, Sheila Graven | Some Issues | New initiative will be created at a later date. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Project Michelangelo - MVP1 |  | 144040 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Sheila Graven, Wade Stack | On Track | The work for this request is included in 131235 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FIT - GEMINI Global Platform - Customer Contact |  | 144795 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Susan Rowland | On Track | 27/11/25 - This initiative will be cancelled due to decision to stop all work on GEMINI program On hold per IO - 11/18 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Retroactive transmission of export MRN |  | 152250 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Ariane Kreitmeier, Wilfried Faust, Sascha Heber | On Track | 22.4.26 changed end date to 31.3.27 as requested by April Zhou 30.03.26 SCO PEL held 25.03.2026, approval received. Met with Karen McConnico on commercial and addressed CCH concerns. CCH approval received. Platform approval received 26.03.2026 Commercial Greenlight needed. All submissions made, awaiting decision. 30.7.25 Updated sections: Financial, Key Stakeholders&Groups, Implementation, Demand Shaping Business with Tech, Add Info. VP clearance approved. working on LBC | E: L2 | Active | Portfolio Greenlight | 2026-02-23 | 2027-03-31
Business w/ Tech Initiative: FiT D&T Expansion - Israel Implementation |  | 154878 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Aseem Khanolkar, Sonika Tiwari, Dora Silva | On Track | The solution is already developed and successfully deployed in the EU and other regions. Current activity is a geographic expansion to a new country, leveraging existing capabilities. The only new feature being introduced is the New Payment Gateway, which is progressing as planned. No major risks or delays identified; implementation is following the expected timeline. | G: L3 | Active | L3 | 2025-12-31 | 2026-06-16
Business w/ Tech Initiative: APAC FiT: Phase 2.5 enhance for customer adoption |  | 154881 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Kengo Taguchi | Some Issues | **April 21, 2026** Status: Green Completed: Items/tasks completed over the last 2 weeks ・JP Pre-clearance Notification – MTP has been completed. Japan will begin a customer pilot on 4/21 (Tue) with 8 corporate customers. The feature will be officially announced to the market during the week of 5/11 to begin broader adoption. Other APAC markets are expected to leverage this feature after 5/11 onward, subject to local clearance system enhancements. ・Conducted the CY26-03 APAC demand intake preview session for the Batch Upload feature with FiT demand owners from FedEx EU Digital Marketing (Nick / Erik), IT Architects (Bruno / Eva), and APAC Marketing (Nikki). A high-level overview was presented, and alignment was reached to proceed with the PI03 demand. In Progress: Items/tasks occurring over the next 1–2 weeks ・APAC GTS and Digital Marketing are working to complete the requirement templates. ・Waiting the month of April MTP (Release feature TBA by FiT IT) Next Steps: Items/tasks planned for the next 2–3 weeks ・Gather the remaining APAC PI03 demands (e.g., reason code updates). ・Clarify the PI02 release / UAT schedule for the Multiple AWB Search and Batch Download features. ・Align with FiT APAC IT on how to maintain APAC release notes in one place (new features / defect fix list). ・Define and align the global customer eligibility scope for FiT features, both for future demand intake and customer adoption strategy. ・Establish a customer / sales inquiry follow-up structure in each market to sustain customer adoption. Risks / Awareness ・No critical system issues have been reported over the last two weeks. ・PI02 development may be delayed depending on technical challenges within IT (TBC). **April 3rd, 2026** Status: Green Complete: Items/tasks completed over the last 2 weeks: ・Workd ID#0117113 APAC Doc Upload PI Enhancements (PI02) EPIC is associated with this PV# for tracability of APAC demand intake status. ・FiT MTP on March 24th released - eOps Fix rejection issue when requestor name contains DBCS characters. - Reason code template layout and configuration update (AU, JP, NZ, ID, TH) to cover more FIT eligibility (Feb) - Triggering SMS/SM notifications to consignee if shipper/importer not available - Sending confirmation email for pro-active upload - Allow importer to access docs after CP match - "Pre-clearance notification" (Not fully satisified original requirements and still has some defects, FiT IT team need to fix. In progress: Items/tasks occurring/in progress over the next 1-2 weeks: - JP "Pre-clearance notification" (Not fully satisified original requirements and still has some defects, FiT IT team need to fix. - JP start local engagement session with local Sales/CE/CCO/LMD for promotion of "Pre-clearance notifcation with proactive upload" feature to the market. Next Steps (items/tasks planned for the next 2–3 weeks): - FiT IT to enable pre-clearance notificaiton config for other markets. - Update March 2026 APAC FiT performance to the APAC FiT performance dashboard. Risks/Awareness: - On April 3rd, send email to FiT ART PMO and managers as... •A regular release note, including delivered features and bug fix status (e.g., March MTP release note have not shared to the team yet.) •A consolidated list of released (fixed) features for FiT - APAC FiT Experience defect (customer was not able to submit missing document via FiT, received certain # of customers feedback call in CE)on March 26 after MTP on March 24th. It was fixed in half day - 1 day later after reporting. Unless FiT ensures the stable usability, we will loose the credibility from customer, operations are extremely difficult to promote FiT to the market. **Match 14th, 2026** Status: Amber Complete: Items/tasks completed over the last 2 weeks: * CY26 PI02 (Enhancements): Submitted some of demand requests for “multiple AWB search on the FiT dashboard (up to 10 AWBs)”, “batch download” defined under this business case. * New Market Prioriti | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-24 | 2026-11-30
Business w/ Tech Initiative: FIT new features in EU |  | 154885 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Dora Silva | On Track | 09/23 (DS) This initiative has been cancelled because it attempts to consolidate unrelated items into a single request. These items do not impact the same application, nor are they interconnected or necessary for the complete processing of the intended request. Proceeding with them as a unified initiative would compromise clarity, efficiency, and alignment with system architecture. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: APAC FIT D&T new features/adjustments |  | 155473 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Dew Sangkarat | On Track | Cancelling initiative as all work is moving under a different work ID # 29.08.2025 : submit L1 01.09.2025 : Update ability statement as SL2 feedback request. 16.09.2025: As discuss with PV owner of EPIC1B as value declared in Epic 1 B (APAC) work ID#0107018. So this PV will enabler for EPIC1B only. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: COM - GDX - FiT DocUpload Genius Integration Fix |  | 157091 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Dora Silva | On Track | Decided with Paula Cadle to change from BWT to Local Enhancement. Creating new request. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: COM - GDX - FiT DocUpload templates changes |  | 157094 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Dora Silva | On Track | This initiative has been cancelled as it pertains to a Local Enablement (LE), not a BWT. Additionally, FiT is actively developing a solution that will allow Business Owners (BOs) to directly configure the DocUpload template, eliminating the need for this request. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FIT Admin - CSK Communication |  | 161066 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Anna Przybylska, Agata Skrok | On Track | 1/15 - On hold per Pod PM 08/29 on track- no risk determined | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Easy ways to pay duty & tax | 12135 | 9159 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Nick Spijkerman, Dew Sangkarat, Marilyn Taylor | On Track | 3/27/26 -Epic 1B - 8 additional APAC countries target launch remains- Apr'26; Epic 1C - LAC - Colombia target launch remains Jun'26 Next phase - new country rollout (including Mexico, Costa Rica, Dominican Republic, Honduras, Panama, Bahamas, Turks & Caico’s) target launch Aug'26; Epic 1D - KSA launch deferred from Feb'26 to Mar'26 to correct errors; Epic 1E - Canada - Target launch remains Apr'26. Epic 2 ROD - Business case in progress 3/6/26 - Epic 1B - 8 additional APAC countries target launch - Apr'26; Epic 1C - LAC - Colombia target launch Jun'26 (delays due to SCO ART - FGC resource issues); Epic 1D - KSA target launch Feb'26; Epic 1E - Canada - Target launch- Apr'26. Epic 2 ROD - Business case in progress (Iain Cairns) ## **2025 Updates* 11/10/25 - Epic 1: Provide FIT payment link (for D&T) to non-account holders •Epic 1A Launched 9/5/25 - Since launch, the D&T collected from non-account holders is more than $11M Estimated annual economic benefit (from ~3.5M) to ~ $6.5M. oTesting in progress to extend the FIT payment link from 48 hours to 4 days (Target: Nov’25) oTeam is researching enhancements to "shift left" and inform the customer earlier in the package lifecycle. •Epic 1B - APAC - JP and SG launched; Country rollout continues •Epic 1C - LAC - CO target launch. Today – Working to update the link of expiry. LAC moved to April. Action: Nick to send the PFS doc to Tom •Epic 1D – MEISA – KSA on target for Jan’26 Epic 2: Enable courier devices to collect D&T payment upon delivery •Need an update. Opportunity – Redo the business case (rev and costs involved) among Mark, Marilyn, etc. . Goal to accelerate in next 3 months. This needs to be reranked. AI: Sang will rewrite the business case and start conversations with finance to rework the benefit (include De minimis removal and make Global (add US) 10/22/25 - Epic 1C - LAC -CO has been deferred (from Jan'26) to April'26 due to late requirements, etc. Deadline for Jan'26 E2E testing was missed so project will move to Apr'26 launch 10/20/25 - Epic 1A US launched on 9/5/25. Payment collection results better than expected.- Team is researching enhancements to "shift left" and inform the customer earlier in the package lifecycle. Epic 1B - APAC - JP launched; SG to launch Jan'26; Epic 1C - LAC - CO target launch Jan'26; Epic 1D - MEISA - KSA target launch Jan'26; Epic 2 - ROD - Enterprise prioritization continues to drop (for PRT) and expected to be more than 6 months before starting PRT. **7/24/2025** - A missed requirement with reconciliation was identified that prevented proper invoice settlement and revenue posting for D&T payments via FiT, laying the US launch. Teams are working on solving this and providing a revised timeline **7/17/2025**- Singapore launched with the capability to pay duties and taxes online. * **5/28/2025**- U.S.- PI03 development in progress for the US with expected completion by July CSR. Decision was made to expedite FIT component development to June 16th to accomodate RMIC testing cycle. APAC- APAC to proceed with PEACE payment gateway. **5/5/2025**- U.S.- Solution handed off to manage shipmnent ART; last action item completed for RMIC ART, waiting for commited timeline for development in PI03. SG and JP- Development in progress for SG and requirement gathering nearing completion for JP. CO- Solutioning in progress. **4/18/2025**- Solutioning still in progress for US, expecting SC&I documentation handoff this week. Connected with Rick Crawford and Ed Cabrera to discuss solutioning for other countries like JP,SG and Co with the outcome being creating sub epics for each clearance system in a similar format to GSP to direct serve. **3/11/2025** - US solutioning in progress. CPEL update was presented on 3/09/2025 and we officially received a greenlight for Epic 1 for all countries starting with Japan, Singapore and Colombia. **3/27/2025 -** Ownership of initiative has been transferred to Digital Marketing (Advait Cherian, I | E: L2 | Active | L2 & CCH | 2023-08-01 | 2027-01-15
Business w/ Tech Initiative: LAC FIT Acceleration (FGC) |  | 92475 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Geremy Solis | Some Issues | 3/4/2026 - On hold per Pod PM request (Doneika Mondaine) 11/5/2025 Status Consolidated within existing initiatives Commercial 108661 and GC Rev Gen 9159 **9/5/2025 STATUS** STATUS: Project remains at risk. BLOCKERS: Project is now at #180 in the enterprise priority queue for IT Architectural Review. It is much lower in priority than before. RISK DETAILS: Same as last update SUPPORT REQUESTED: Same as last update. PROGRESS MADE: Effort is currently being considered in another project, specifically Global FIT "Easy Ways to Pay" project. More details on next update. **8/25/2025 STATUS** STATUS: Project remains at risk. BLOCKERS: Project is now at #160 in the enterprise priority queue for IT Architectural Review. It is much lower in priority. RISK DETAILS: Same as last update SUPPORT REQUESTED: Same as last update. PROGRESS MADE: Team addressed concern in most recent CWAR meeting and sent further explanation to JW Mayberry. Team requested from FIT owners to develop a global project for "Doc Upload" feature for LAC and rest of the world that require it in order to combine all benefits for EPC prioritization. **7/18/2025 STATUS** STATUS: Project is at risk. BLOCKERS: Project is at #129 in the enterprise priority queue. Two weeks ago, it was at #133. The planview process to move the project from L2 to L3 is taking longer than expected. RISK DETAILS: With recent and looming new regulatory requirements and enforcements in MX, CL and other countries in LAC that require comprehensive details and new data elements on shipments, the need to implement FIT is growing more critical by the day. The interim solution of temporary resources contacting customers and capturing these data elements for Customs (e.g. 179 MX temp agents) is not sustainable. In addition, timely realization of other gains, including improved clearance for Central America and Caribbean Pillar strategy and LAC lower 'Drive' costs, is increasingly uncertain. SUPPORT REQUESTED: Team addressed this concern and requested for LAC VP's (Basil Khalil) support to escalate this project on 7/10. Work is in progress to finalize and submit the documentation for Enterprise Prioritization Council by 7/18. PROGRESS MADE: Team established proposed process with FIT and 90% of standardized core user stories for LAC, including cage code notification template, completed by business team. **5/1/2025 STATUS** Team completed current and desired state process for FGC-FIT for Doc Upload and D&T Payment features. Team working on L2 items to move project to L3. Business team providing IT team answers to their inquiries on the process. **3/28/25 STATUS** FY26 rebaseline activity completed. As per David Spradlin, all is good. No rebaseline activity needed as this project is still in L1. | E: L2 | On Hold | L2 & CCH
Business w/ Tech Initiative: HS Auto-Class – Product Catalog Classification Com | 70661 | 6805 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Jason LaRocca, Sanghamitra Panda, Cami Fields, Janice Caudill | On Track | 4/16/2026 - Per Karla Sommers, initiative to be put on hold due to combining these into another initiative 2/19: Working session scheduled on 2/26 to discuss and get stakeholder inputs on scope definition and next steps 4/12: Submitted for L1 approval 8/8: Business case is in progress 9/9: Engagement with Shein continues for initial POC. Product demo is scheduled with sales team this week in prep for customer demo the following week. Work in progress with corp strategy team on bus case 9/16: Product demo completed with sales last week. Team is preparing for customer demo by next week. Bus case discussion is in progress 2/14: Shein engagement for POC is paused for now. Team is exploring additional customers to do POC. Commercial ownership is under discussion 2/28: Capability build out: Expanding PCC with more capabilities is in progress. The enhancements needs to be finished out first before customer onboarding. Timelines for completion - 8 weeks from now POC customer: Discussion in progress with WT and sales team 3/7: Bland has confirmed that exe leadership has approved the resources. It will take couple of months to fill in positions to take commercial ownership 3/14: Sales discussions continue to identify POC customers 3/31: No additional updates this week. I spoke with Finance and dont need to rebaseline 4/11: Need support from leadership to streamline efforts between Michelangelo and Global clearance for this item 4/11: Same as above 5/19: Alignment with digital marketing is in progress 7/11: No new updates 10/10: Bus case revised with adoption rates by FYs to show incremental revenue | E: L2 | On Hold | L2 & CCH | 2024-08-15 | 2024-11-08
Business w/ Tech Initiative: Estimated Landed Cost (ELC) Commercialization | 93292 | 6807 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Jason LaRocca, Sanghamitra Panda, Cami Fields, Janice Caudill | On Track | 4/16/2026 - Per Karla Sommers, initiative to be put on hold due to combining these into another initiative 9/2: Init submitted for L1 approval 9/9: Init is in L1 now. Working on POC readiness with ShipHero as identified customer. Figuring out more pilot customers. Roles alignment in progress with cross functional teams for commercialization. Bus case development in progress 9/16: Pre-read sent out for VP/MD review on 9/17 in prep for DJ meeting this Friday 10/8: Team presented in CDR meeting and officer hours; received feedback and working on next steps 2/14: Commercialization ownership is under discussion. Bland asked to keep the commercial effort on hold until resources assigned in her team to take effort. In the meantime, when we discussed ELC offering, there were two parts - the actual capability and the commercialization plan/efforts. The commercial component is the part on hold, however, on the Capability side, Dataworks along with other groups are looking at evolving the capability 2/28 update: ○ Ownership: Bland is seeking Brie level approval for resource assignments ○ Capability build out: Expanding ELC with more capabilities is in progress. The enhancements needs to be finished out first before customer onboarding. Timelines for completion - 8 weeks from now POC customer: Sales alignment in progress 3/7: Bland has confirmed that exe leadership has approved the resources. It will take couple of months to fill in positions to take commercial ownership 3/14: Sales discussions continue to identify POC customers 3/28: No additional updates this week 3/31: I spoke with Finance and dont need to rebaseline 4/11: ELC/GLC is scheduled for discussion in the O/D meeting on 4/16 to align on next step. Need support from leadership to streamline efforts between Michelangelo and Global clearance for this item 4/18: Michaelangelo team is enhancing ELC capability via fdx as part of MVP1 targetted this month. Marketing is working on a fact base on 'assessing financial risks with a guarantee in duty/tax calculation' with revenue, Trade Tools and Dataworks 5/19: Alignments in progress with the digital marketing team 7/11: Fact base complete on duty/tax and HS classification and reviewed with leadership 10/27: in L2 now. Working with digital marketing to transition as part of GTN | E: L2 | On Hold | L2 & CCH | 2024-07-22 | 2024-08-16
Business Only Initiative: Project SHEPHERD - Standardisation & Harmonisation |  | 184014 | Business Only Initiative | FXE GC - Digital Products | Global Clearance | Paul McAdam | On Track | On Track | G: L3 | Active | L3 | 2025-10-01 | 2026-04-30
Business w/ Tech Initiative: DE Export Clearance System |  | 187348 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Sascha Heber | On Track | The goal of this Initative will be covered under the EU request 0019083. There is a general roll-out plan for several countries including DE. Therefore this Initiative can be cancelled. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: On-Demand Customs Clearance Documents Download |  | 187352 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | SIMONA BERTELLO | On Track | We involved the Shawn Chan in order to build similar capability that iTrack is currently offering to customers into FedEx Import Tool using the APIs. We contacted the Finacial Team review the Finacial data. | C: L1 | Active | L1
Business w/ Tech Initiative: FIT Capabilities Enhancement-EU De Minimis Removal |  | 189479 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Aseem Khanolkar | On Track | The ability to statements will be tracked under the broader EU De Minimis removal initiative #187281. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Doc Upload | 87102 | 8848 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Nick Spijkerman, Marilyn Taylor | On Track | 3/27/26- FDA codes (FDA, FDAPN, and DBT) launched 3/23/26; Batch 3 target remains Apr'26; Batch 4 target Jul'26; Batch 5 (final batch) is TBD; Team is discussing potential scope add - Epic 2 -SBP; Epic 3 - Email addresses. Addition will require CPEL approval. 3/6/26 - FDA codes tested. FIT target launch- March. SCO launch target Mar/Apr. Batch 3 codes - FIT target launch- March. SCO launch target Mar/Apr. Batch 4 codes - Target late iterationin PI 02 - launch: June/July; Batch 5 codes - Final batch - Requirements in progress. Target launch TBD 2/16- FDA codes are targeting Feb'26 launch. Batch 3 (10 additional shipper codes) is targeting Apr'26 (pending available SCO resources); Batch 4 (final cage codes) is TBA. PV8848 was repurposed for fast track inititiave (after original intent was canceled). *** 12/19/25 - Reason codes are rolling out in a phased approach. To date - 16 top shipper codes have launched. The teams are working on resolution to launch FDA codes (target Jan'26), and then Recipient codes - Target TBA. 11/6/25 -•Top 8 codes loaded (starting 10/27) by 11/3. •Target launch for next 10 codes in Nov’25 •FDA code (FDAPN and DBT) requires development effort. Target launch: TBA **10/22/25 - Doc Upload for US launched the MVP (with one reason code (INVMS) on 10/22/25; Ph2 to include fix for missed requirement to include broker comments (from Jupiter to FIT) is targeting 10/31/25. At least 7 additional Reason codes will be added at this time **10/20/25 - Doc Upload for US - Target launch for MVP 10/22/25. "Show stopper" missed requirements found. Team will launch with one Cage code (INVMS) only on 10/22. Full solution will follow (targeting pre code freeze on 11/3 - but TBA) 20 Nov 2024 - submitted to L3 18July2025 - Development completed on VB1 in November 2025. Additional guidance has been provided by U.S. CBP to implmeent a rejection message in August 2025. IT teams are developing and testing right now in preparation. There is no financial value associated with this project as it is a regulatory requirement. | E: L2 | Active | L2 | 2026-01-01 | 2027-01-08
Business w/ Tech Initiative: EDT Ancillary Fees |  | 192353 | Business w/ Tech Initiative | FXE GC - Digital Products | Global Clearance | Pamela Lynch | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Country Configuration - EU - Belgium - TIER1 | 32020 | 6814 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2025-03-03 | 2025-10-02
Business w/ Tech Initiative: Country Configuration - EU - Switzerland - TIER1 | 32022 | 6815 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-12-02 | 2025-07-03
Business w/ Tech Initiative: Country Configuration - EU Czech Republic TIER2 | 32024 | 6816 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-09-01 | 2026-04-02
Business w/ Tech Initiative: Country Configuration - EU - Germany - TIER1 | 32025 | 6818 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-06-02 | 2026-01-01
Business w/ Tech Initiative: GEMINI - EU FY26 | 32026 | 6819 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 12/23/25 - The GEMINI program has been cancelled. 07/25/25 - Updated name to reflect GEMINI - EU FY26 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-12-01 | 2026-07-02
Business w/ Tech Initiative: Country Configuration - EU - Spain - TIER1 | 32028 | 6820 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2026-01-01
Business w/ Tech Initiative: GEMINI - APAC FY27 | 32029 | 6822 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - APAC FY27 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-12-01 | 2026-07-02
Business w/ Tech Initiative: Country Configuration - EU - France - TIER1 | 32030 | 6823 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-09-01 | 2026-04-02
Business w/ Tech Initiative: Country Configuration - EU - Hungary - TIER2 | 32032 | 6824 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-06-01 | 2027-01-01
Business w/ Tech Initiative: Country Configuration - EU - Ireland - TIER2 | 32033 | 6826 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-06-01 | 2027-01-01
Business w/ Tech Initiative: Country Configuration - EU - Israel - TIER2 | 32034 | 6829 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-09-01 | 2027-04-01
Business w/ Tech Initiative: Country Configuration - EU - Italy - TIER1 | 32035 | 6830 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2026-05-14
Business w/ Tech Initiative: GEMINI - MEISA FY27 | 32036 | 6831 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - MEISA FY27 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2026-01-01
Business w/ Tech Initiative: Country Configuration - EU - Luxembourg | 32037 | 6833 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 27/11/25: Requesting cancellation due to decision on the GEMINI program 27/11/25: All milestones have been set to cancelled status due to the decision to stop all work on the GEMINI program 07/25/25: Development is in SIT testing; rollout pending successful SIT and UAT. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-07-22 | 2026-12-30
Business w/ Tech Initiative: Country Configuration - EU - Norway - TIER2 | 32040 | 6835 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 07/25/25 - Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-03-02 | 2026-10-01
Business w/ Tech Initiative: Country Configuration - EU - Romania - TIER1 | 32043 | 6837 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2026-01-01
Business w/ Tech Initiative: GEMINI - US & CA FY27 | 32044 | 6838 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - US & CA FY27 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-03-02 | 2026-10-01
Business w/ Tech Initiative: Country Configuration - EU United Kingdom - TIER1 | 32049 | 6841 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2025-03-03 | 2025-10-02
Business w/ Tech Initiative: Country Configuration - Americas - U.S. TIER1 | 32050 | 6843 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Eyad Bahhur, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2025-03-03 | 2026-02-11
Business w/ Tech Initiative: Country Configuration - Americas - Canada | 32051 | 6844 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Renate Jalbert, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2025-10-01 | 2027-05-14
Business w/ Tech Initiative: Country Configuration - AMEA - Singapore - TIER1 | 32052 | 6845 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-03-01 | 2026-03-16
Business w/ Tech Initiative: Country Configuration - AMEA - New Zealand - TIER1 | 32053 | 6846 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker, Laurentius Adi-Kurniawan | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-03-01 | 2025-11-13
Business w/ Tech Initiative: Country Configuration - AMEA - Thailand - TIER1 | 32054 | 6847 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2024-10-24
Business w/ Tech Initiative: Country Configuration - AMEA - Malaysia - TIER1 | 32055 | 6849 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-03-01 | 2025-10-15
Business w/ Tech Initiative: Country Configuration - AMEA - Taiwan - TIER1 | 32056 | 6852 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2023-09-01 | 2025-11-13
Business w/ Tech Initiative: Country Configuration - AMEA - China - TIER1 | 32057 | 6854 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2024-10-23
Business w/ Tech Initiative: Country Configuration - AMEA - Australia - TIER1 | 32058 | 6856 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker, Laurentius Adi-Kurniawan | On Track | 03/03/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-03-01 | 2026-07-15
Business w/ Tech Initiative: Country Configuration - AMEA - Japan - TIER1 | 32059 | 6858 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2023-09-01 | 2025-11-13
Business w/ Tech Initiative: Country Configuration - AMEA - Hong Kong - TIER1 | 32060 | 6859 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-01-24 | 2025-12-01
Business w/ Tech Initiative: Country Configuration - AMEA - Korea - TIER1 | 32061 | 6860 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-09-01 | 2026-04-02
Business w/ Tech Initiative: Country Configuration - AMEA - Indonesia - TIER1 | 32062 | 6862 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-12-01 | 2027-05-14
Business w/ Tech Initiative: Country Configuration - AMEA - India - TIER1 | 32063 | 6863 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tushar Raibagi, Liz Parker | On Track | 3/3/25 - Per direction from TO, all GEMINI country configurations planned for later than FY26 Q2 will be moved to on hold status until their implementation dates are closer. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2026-05-01 | 2026-10-01
Business w/ Tech Initiative: Country Configuration - AMEA - UAE - TIER2 | 32064 | 6864 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tushar Raibagi, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-07-02 | 2029-12-13
Business w/ Tech Initiative: Country Configuration -AMEA - South Africa - TIER2 | 32065 | 6865 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Wayne Petersen, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-07-02 | 2030-03-13
Business w/ Tech Initiative: Country Configuration - AMEA - Vietnam - TIER1 | 32066 | 6867 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH | 2024-09-02 | 2025-04-02
Business w/ Tech Initiative: Country Configuration - Americas - Mexico - TIER2 | 32068 | 6869 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jorge Chiros, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-01-01 | 2025-12-25
Business w/ Tech Initiative: Country Configuration - Americas - Brazil - TIER2 | 32069 | 6870 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-12-01 | 2026-07-02
Business w/ Tech Initiative: Country Configuration - Americas Argentina TIER3 | 32070 | 6871 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas - Chile - TIER2 | 32071 | 6873 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-12-31
Business w/ Tech Initiative: Country Configuration - Americas Colombia - TIER2 | 32072 | 6875 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2025-12-31 | 2027-04-01
Business w/ Tech Initiative: GEMINI - EU FY27 | 32073 | 6876 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker, Susan Rowland | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - EU FY27 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-12-31
Business w/ Tech Initiative: Country Configuration - Americas - Costa Rica | 32074 | 6878 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jorge Chiros, Liz Parker | On Track | 12/23/25 - The GEMINI program has been cancelled. 07/25/25: Development for pilot is in SIT testing; rollout pending successful SIT and UAT. 04/02/25: Updated milestones 30553 Platform Phase 1 Import Capability and 30555 Improt Go-Live Hypercare to reflect updated end dates based on current trajectory for CR pilot. 03/03/25: Cancelled the export / transit milestone as this has been removed from the CR pilot rollout; export / transit capabilities are slated for future development at a platform level. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2025-01-07 | 2026-01-22
Business w/ Tech Initiative: Country Configuration - Americas - Jamaica - TIER3 | 32075 | 6880 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-12-31
Business w/ Tech Initiative: Country Configuration - Americas Trinidad TobagoT2 | 32076 | 6882 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-12-31
Business w/ Tech Initiative: Country Configuration - Americas - Panama - TIER3 | 32077 | 6884 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-06-01 | 2030-01-03
Business w/ Tech Initiative: GEMINI - LAC FY26 | 32078 | 6886 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 12/23/25 - The GEMINI program has been cancelled. 07/25/25 - Updated name to reflect GEMINI - LAC FY26 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-12-31
Business w/ Tech Initiative: Country Configuration - Americas Guatemala - TIER3 | 32079 | 6888 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25: On hold per TO guidance to move all country config initiatives that will implement post-FY26 Q2 to on hold. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-09-03 | 2030-04-02
Business w/ Tech Initiative: GEMINI - MEISA FY26 | 32080 | 6890 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - MEISA FY26 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-09-03 | 2030-04-02
Business w/ Tech Initiative: Country Configuration - Americas - Bahamas - TIER3 | 32081 | 6892 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-12-03 | 2030-07-03
Business w/ Tech Initiative: Country Configuration - Americas - Curacao - TIER3 | 32082 | 6896 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1 | 2029-12-03 | 2030-07-03
Business w/ Tech Initiative: GEMINI - Global Platform | 32804 | 6938 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Pilot countries' development is in SIT testing. 08/08/25 - Pilot countries' development is in SIT testing. 08/01/25 - Pilot countries' development is in SIT testing. 07/25/25 - Pilot countries' development is in SIT testing. 05/14/25 - Added Thompson Chin as a temporary IO to allow him to link GEMINI and Physical Handling in Planview 05/13/25 - Removed Paige Carter as IO, updated initiative name and description to align with guidance from TO Finance and EBA which was to condense the global platform into a single initiative (versus two). | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-06-01 | 2027-11-30
Business w/ Tech Initiative: Country Configuration - AMEA - Philippines - TIER1 | 32067 | 7218 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jean-Marc Klecha, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: Country Configuration - Americas - Aruba - TIER3 | 32083 | 7222 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas Saint Lucia TIER3 | 32084 | 7223 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas Martinique TIER3 | 32085 | 7224 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas Turks & Caicos T3 | 32086 | 7225 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas Virgin Islands T3 | 32087 | 7226 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas Guadalupe TIER3 | 32088 | 7230 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas - Grenada - TIER3 | 32089 | 7232 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas - Uruguay - TIER3 | 32090 | 7233 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 07/25/25 - Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: GEMINI - LAC FY27 | 32091 | 7235 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 12/23/25 - The GEMINI program has been cancelled. 07/25/25 - Updated name to reflect GEMINI - LAC FY27 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas British VI | 32092 | 7236 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas St Kitts Nevis T3 | 32093 | 7237 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas St Maarten TIER3 | 32094 | 7238 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - Americas St Vincent TIER3 | 32095 | 7240 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jenyree Del Carmen Garcia, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Austria - TIER2 | 32019 | 7241 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Bulgaria - TIER2 | 32021 | 7244 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Cyprus - TIER2 | 32023 | 7246 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: GEMINI - APAC FY26 | 32027 | 7248 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - APAC FY26 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Greece - TIER2 | 32031 | 7252 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: GEMINI - US & CA FY26 | 32038 | 7253 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI program has been cancelled. 08/15/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/08/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 08/01/25 - Rollout timeline is pending successful pilot rollout, complete development, successful SIT and UAT. 07/25/25 - Updated name to reflect GEMINI - US & CA FY26 as aligned with TO Finance and EA that we would no longer have country-specific inits but rather one init per region per FY for GEMINI. Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Netherlands - TIER 1 | 32039 | 7255 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Poland - TIER2 | 32041 | 7258 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Portugal - TIER2 | 32042 | 7260 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Slovenia - TIER2 | 32045 | 7264 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 07/25/25 - Rollout is pending successful pilot rollout, complete development, successful SIT and UAT. 03/04/25 - EU leadership confirmed this will be one of the first eight EU countries to implement after LU pilot success. 03/03/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Slovak Rep. - TIER2 | 32046 | 7265 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Turkey - TIER2 | 32047 | 7266 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Country Configuration - EU - Ukraine - TIER2 | 32048 | 7267 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Susan Rowland, Liz Parker | On Track | 3/3/25 - Per TO guidance, all GEMINI country configurations planned for post-FY26 Q2 to be put on hold status. Per Doug Belding, Liz Parker is the backup IO for all 77 country configuration initiatives. CK change to CC title. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: TO BE REMOVED - GEMINI - FY26+ | 32805 | 7620 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Paige Carter, Liz Parker | On Track | 5/13/25: Updated title and description to indicate this initiative is going to be removed per guidance from Finance TO and EBA. | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: Route-based General Express CFS Volume-Automated | 1121 | 7771 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Douglas Stubbs, Cynthia Jones | On Track | 15May25 - April numbers were low due to the implementation of Tariffs for China and Hong Kong 10MAR2025: due to additional tariffs on Feb 4, 2025, volume was moved away from CFS to ECF clearance. With DeMinimis being excluded from tariffs, volume has slowly moved back to CFS clearance 28FEB2025: continue to process 1.2M shipments monthly in CFS facility with reimbursable voidance $1.9M Leverage reimbursable Avoidance for All CFS enabled ports. | K: L5 | Completed | L5 | 2023-02-14 | 2024-10-02
Business w/ Tech Initiative: Launch - Automated Billing And Clearance (ABACUS) | 7063 | 9062 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Sean Brady, Matthew Evans, Stephanie Waltman | On Track | 02.03.2026 Awaiting L5 review, all items undertook and completed 10.02.2026 Jan actuals added 03.02.2026 Internal FP&A review ongoing regards moving to L5 22.01.26 Numbers updated and corrected using new average yearly bad debt number Ready for L5 10.12.25 Actuals updated - L5 submission targetted for 14.12.2025 Application to be reviewed for 'shift' to clearance use within Broker Recon 18.11.25 L5 scheduled to review stagegate progression 13.11.25 Oct actuals added - SB Discussion to be arranged for L5 progression 11.07.25 June actuals added Status Rationale 23.06.2025 - ME May numbers added - The May number calculation followed the previous reporting model, and everything was recorded in the KPI and baseline document in Planview and the downloads are saved locally for audit. Bad Debt - download of the data from ABACUS, filtering records impacting bad debt, cash checking for paid vs nonpaid. Then use the FedEx and TNT monthly bad debt % provided by Acc & Controls as the baseline and take the difference we could positively attribute to ABACUS. •$682k saving taken. Ancillaries - ABACUS downloads were used and the disbursement related ancillaries removed to just record the pure ancillaries. •$259k additional revenue recorded. Discussion to be had on L5 step Status Rationale 21.05.2025 Financials: •$ 517k banked April in line with forcast (-30k) •Bad debt below forecast but ancillaries above • May forecast updated and accurate. Progress Made •Project in L4 so all IT work has completed. •Baselines to actuals updated in line with Acc & Controls request for FY26 and beyond Milestones •No Active milestones until moved to L5 Working round the lack of retrigger in various ways so now removed as a blocker. 30.04.25 Baseline and Exit rate corrected Awaiting SL4 to L4 progression. 17.04.25 March Actuals added Baseline updated to reflect fy25 Exit rate updated for FY27/28 Work ongoing to assess ability to get paid data from ATLAS Discussing with Canada and Gemini global about expanding or migrating to Gemini 2.0 14.03.25 NO CHANGE ME 10.03.2025 Feb values entered and ready for L4 ME 26.02.2025 L4 moved forward to 28th March 2025 ME 19.02.2025 Dataworks are now hands off this project and long term maintenance and support is still not formalised. Infosys development teams are leaving and being replaced by Accenture - knowledge transfer gaps may occur. Details on the highlighted weekly adjusted OI for 9062 / ABACUS ASAP. Last week there was a negative 21.9% variance of -$1M+. For ABACUS the value to recover has decreased due to the below three contributing factors 1)Abacus data analysis highlighted a German Clearance system failure that was impacting 20k to 40k records per month a.This ADT drop out issue was permanently fixed in a Clearance IT change on January 18th, 2025 b.A good news story but the impact to numbers is worth circa 50% of the ABACUS monthly run rate c.We cannot take any value for the fix as its stopped the issue occurring in the first place 2)D&T Bad Debt performance has improved in most of our Abacus markets, so we have a smaller division between the Broker Recon billing and the standard Bad Debt rate a.The ABACUS bad debt calculation lets us take the difference between our billing and business performance Example: i.If for last month GB Bad Debt = 10% and Abacus Bad Debt for GB = 6% ii. We get to take 4% improvement on the value we bill iii.If when we forecast the GB Bad Debt was 15% that improvement to 10% means the value we can take is decreasing, and our 6% is not worth as much as it was. 3)We suffered a delay in the delivery of the solution, and we have been told we cannot have the RPA solution that would have automated the remedial action a.Volumes in ABACUS still out strip Billing Broker Recon abilities b.We cannot work everything we identify in ABACUS early enough to avoid Bad Debt SB 06.02.2025 Updat | K: L5 | Active | L5 | 2022-11-21 | 2025-03-28
Business Only Initiative: Reduce facility footprint | 9901 | 8345 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Olivia Trotter | On Track | 3.26.24 - Impact #11809 has an estimated one time benefit of $650k for March 2023. When the FY24 rebaseline occurred and the property had not sold in FY23, the updated one time benefit of $482k was added by Brian Teepee in February 2024. This results in the overall impact incorrectly showing a $1.13M one time benefit, when the benefit should have either remained $650k or the $650k impact removed in favor of the $482k one time benefit. 3.29.24 - Dearborn property sale closed 3/29/24 and funds received same day. Due to month end close, one time benefit will be included in the WAVE submission in May for the April actuals. | K: L5 | Completed | L5 | 2022-08-01 | 2024-05-01
Business w/ Tech Initiative: Improve Broker Reconciliation by reducing Gross Wr | 57255 | 7229 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Sean Brady, Matthew Evans, Stephanie Waltman | On Track | 22.05.25 Financials: 5.9M full project value fy25 value delivered (total initiative value relalised = 7.2M) May forecast to 0 as value aligned in full years actuals Accounting and Controls validation of financials complete - ready for L5 Over achievement has been realised based on work for DCG references for France (previously a process that local Clearance could not complete) and through access to addtional data sources enabling higher AP-AR) 19.05.25 Accounting and controls advise actuals update based on provision release calculations - resulting in increased actuals for the year 12.05.25 Line item data supporting provision release values recorded in actuals uploaded - submitted to L4 Work in NL ongoing with a view to firther release this month 17.04.25 March Actuals added Baseline not updated as reflects fy24 and we close this piece out at the end of fy25 (Exit rate not updated for same reason) Speak wqith Sean regards updating fy25 forecast after easter weekend. Work ongoing to assess ability to get paid data from ATLAS Discussing with Canada and Gemini global about expanding or migrating to Gemini 2.0 31.03.25 Due to delays in finacial reconciliations (Accounting and Controls) alongside a delay for IT data - the final value release/and L4 forcast have been moved to May 31 14.03.25 NO CHANGE 10.03.2025 1 month delay to full bad debt value due to Netherlands data issue, now forecast for release in April. Full value to still be taken in FY25 so no roll back on project value. 26.02.2025 Values for one time release under review to determine whether value is entered under 'Broker Recon' KPI or ABACUS KPI - decision to be made close of 28.02.2025 - does not impact financials; Accounting and Controls to align with ahead of L4 activation 19.02.2025 Explanation in the adjusted OI changes for 7229 / Improve Broker reconciliation for $180K. The 7229 initiative has two elements a.One is a 1.6m one off release of value which was originally forecast for January, but we had a delivery delay, and I believe this should now be March i.I need to align on this point with Sean when he is back from vacation so for now, I have moved it February but note it could move again b.The second element is a monthly Broker Recon release that Seans central team deliver (forecast for 180k) i.For January the Accountants advised me, we did not see a release in provision, so this value was not taken. Ramkumar Sarangapani Friday 14.02.25 10:46 "Hi Matt no bad debt released this month" 06.02.2025 Actuals for Broker Recon updated Actuals (1.6M) for ABACUS scale reforecasted based on ABACUS main initiative; Actuals here will be entered by Feb close On course for FY25 delivery 16.01.2025 Broker Recon progressing with monthly value capture; ABACUS scale reviewing value capture approach potentially based on EPDSM ticket process. Update to Genius system scheduled for 19 01 - following this ABACUS team will assess impact on unbilled and ADT dropout 10.01.2025 Broker Recon progressing with monthly value capture; ABACUS scale reviewing value capture approach potentially based on EPDSM ticket process 03.01.2025 Broker Recon Monthly capture of unbilled values continuing; ABACUS EPDSM ticket to be raised for GIF countries this month UAT testing for data accuracy for ODS - completed 20.12 | K: L5 | Completed | L5 | 2023-11-24 | 2025-05-30
Business Only Initiative: EU Centralization of operation/tasks already in pl | 2481 | 8916 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Terri Tennison, Lukasz Utylski | On Track | 3/31/25 FY26 rebaseline activity completed on Mon, 3/31/25 Confidence in delivering value on time: High Confidence in delivering the full value: High On track: UK - Completed NORD - Completed ATT - Completed CMOD - Alignment with FR team - discussion with Works Council by the end of August DE - Completed IT - Completed | K: L5 | Completed | L5 | 2022-07-04 | 2023-09-29
Business Only Initiative: Canada GTS Migration to GCSSC Opportunity | 1523 | 7838 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Ghita Palij, Sue J. Lee | On Track | Weekly update: 14July25 - L5 approved so status quo moving forward Weekly update: 07July25 (Active and In-Progress Tasks) *Status Quo*** Weekly update: 30June25 (Active and In-Progress Tasks) Awaiting approval of SL5 submission request (submitted 25June25). Weekly update: 16June25 (Active and In-Progress Tasks) As per David Spradlin, this initiative have 2 years of actuals, May actuals will be the last ones to be entered (in June) and then we will be moving to L5. Financials: May-25: -104K The savings underperformance is primarily attributed to the following factors: •Increased volume of de minimis shipments, this volume was previous exempt but under the updated surtax/tariff rules an entry is required (~10%+ volume, reducing the scope of applicable savings). •Required system surtax/tariff changes led to multiple production issues and the need for temporary workarounds, impacting efficiency. •Ongoing changes to surtax and tariff requirements created a steep learning curve for users, leading to delays and errors in applying the correct processes. •Automation impact on new de-minimis submissions from US shipments. Existing automation platform does not have any historical data to feed automation causing decrease in productivity. •Vacation Month many employees on vacation causing an increase in over-time hours to complete the required work Continuing to identify additional importers/opportunities. Productivity and Quality KPI targets for PH Productivity is consistently on target or better. Quality is consistently above 95%. Weekly update: 02June25 (Active and In-Progress Tasks) Status Quo After discussing with David Spradlin, as we now have 2 years of actuals, May actuals will be the last ones to be entered (in June) and then we will be moving to L5. Hiring One replacement team member to be hired - likely in June. Training Looking into having the PH team do the broker assigning for the RODs. Eyewear - still awaiting legal approval for the customer prescription verification letter. Continuing to identify additional importers/opportunities. Productivity and Quality KPI targets for PH Productivity is consistently on target or better. Quality is consistently above 95%. Weekly update: 09June25 (Active and In-Progress Tasks) ***Status Quo*** After discussing with David Spradlin, as we now have 2 years of actuals, May actuals will be the last ones to be entered (in June) and then we will be moving to L5. 1. Hiring - One replacement team member to be hired - likely in June. 2. Training - Looking into having the PH team do the broker assigning for the RODs. - Eyewear - still awaiting legal approval for the customer prescription verification letter. - Continuing to identify additional importers/opportunities. 3. Productivity and Quality KPI targets for PH - Productivity is consistently on target or better. - Quality is consistently above 95%. Weekly update: 02June25 (Active and In-Progress Tasks) ***Status Quo*** After discussing with David Spradlin, as we now have 2 years of actuals, May actuals will be the last ones to be entered (in June) and then we will be moving to L5. 1. Hiring - One replacement team member to be hired - likely in June. 2. Training - Looking into having the PH team do the broker assigning for the RODs. - Eyewear - still awaiting legal approval for the customer prescription verification letter. - Continuing to identify additional importers/opportunities. 3. Productivity and Quality KPI targets for PH - Productivity is consistently on target or better. - Quality is consistently above 95%. Weekly update: 26May25 (Active and In-Progress Tasks) ***Status Quo*** After discussing with David Spradlin, as we now have 2 years of actuals, May actuals will be the last ones to be entered (in June) and then we will be moving to L5. 1. Hiring - One replacement team member to be hired - likely in June. 2. Training - Looking into having the PH team do the broker assigning for the RODs. - Eyewe | K: L5 | Completed | L5 | 2022-10-18 | 2024-11-29
Business Only Initiative: DICE: Project Windsor (initiative to reduce FTN QA | 32877 | 8280 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Bill Schweitzer | On Track |  | K: L5 | Completed | L5 | 2023-03-01 | 2023-05-31
Business Only Initiative: Phase II - Reduce Facility Footprint | 55555 | 7213 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Olivia Trotter, Luiz Vieira | On Track |  | K: L5 | Completed | L5 | 2022-05-02 | 2024-02-01
Business Only Initiative: Improve Operations Training | 9309 | 9094 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Sharon Ponder, Nickie Larson | On Track | 2025-6-10: Project should have completed L5 and been closed inJanuary 2025 but apparently there was an issue not allowing projects to be closed at L5 and I was instructed to continue updating financials. The biggest factor for continued increases in impact savings is due primarily to the fact that FXL is hiring well over the head count per month initially anticipated. | K: L5 | Completed | L5 | 2022-11-15 | 2024-03-29
Business Only Initiative: Acceleration of AMEA migration to Global Shared Se | 1522 | 8858 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Dhivyaa Ashvynna Jeyakumaran, Chetan Khorana | On Track | 28/10/2025 Actuals update Initiative is submited to L5 (SL5) 11/7/2025 All projects and milestone completed. 30/6/2025 **MY SSC** **SG CDN** Project completed. Initiative is submitted to L4 (SL4). 16/6/2025 **MY SSC** **SG CDN** New hires hired. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 9/6/2025 **MY SSC** **SG CDN** New hires hired. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 26/5/2025 **MY SSC** **SG CDN** New hires hired. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 19/5/2025 **MY SSC** **SG CDN** New hires hired. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 12/5/2025 **MY SSC** **SG CDN** Interview in progress. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 5/5/2025 **MY SSC** **SG CDN** Interview in progress. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 29/4/2025 **MY SSC** **SG CDN** Interview in progress. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 29/4/2025 **MY SSC** **SG CDN** Interview in progress. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 22/4/2025 **MY SSC** **SG CDN** Interview in progress. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 14/4/2025 **MY SSC** **SG CDN** Interview in progress. Tentative is to complete this project by Jun 30th, 2025 due to hiring and training lead time requirement. 8/4/2025 **MY SSC** **SG CDN** 4HC Approved for hiring. Hiring has started in MY SSC. Target to complete this project by May 31st, 2025. 4/4/2025 **Re-baseline COMPLETED** 20/3/2025 **MY SSC** **SG CDN** To schedule a call with SG MD and GTS MD on additional 4 HC for SG Transition. Expected to have this call on 3/24/2025. 10/3/2025 **MY SSC** **SG CDN** Manning model updated based on actual volume. According to the updated model, 4 FTE additional are required due to volume growth. This has bee re-aligned with both Sr Mgrs in SG and MY SSC. Request has been re-submitted to SG Sr Mgr. 3/3/2025 **MY SSC** **SG CDN** Manning model updated based on actual volume. According to the updated model, 4 FTE additional are required due to volume growth. This has bee re-aligned with both Sr Mgrs in SG and MY SSC. Request has been re-submitted to SG Sr Mgr. 24/2/2025 **MY SSC** **SG CDN** Highlights on 21st Feb, 2025 with SG Ops and MY SSC Ops: 1) SG Ops has highlighted that a portion of the incremental trace volume used to justify the additional 3 FTEs may continue to remain at SG and will affect the incremental FTEs required in MY. 2) P&E is working on validating above justification. 17/2/2025 **MY SSC** **SG CDN** 1. Latest manning model input: Increase MY SSC HC by 3 FTEs. 2. SG Sr Mgr supports HC increase based on model provided and will raise it to SG MD – need to check update of the discussion by 21st of Feb. 2025. 10/2/2025 **MY SSC** **SG CDN** 1. Latest manning model input: Increase MY SSC HC by 3 FTEs. 2. SG Sr Mgr supports HC increase based on model provided and will raise it to SG MD – need to check update of the discussion by 21st of Feb. 2025. 3/2/2025 **MY SSC** **SG CDN** 1. To present latest manning model to SG Sr Mgr. 2. Latest manning model input: Increase MY SSC HC by 3 FTEs. 27/1/2025 **MY SSC** **SG CDN** 1. KULGC Management has requested to delay night shift transition due to recent turnover. Team requires to ensure staffing is at full capacity. 2. Exploring possibilities to migrate Night Shift to PH SSC using GC3 infrastructure. 20/1/2025 **MY SSC** **SG CDN** 1. KULGC Management has requested | K: L5 | Completed | L5 | 2022-03-01 | 2025-10-31
Business Only Initiative: EU New process introduction to SSC | 2483 | 8918 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Terri Tennison, Lukasz Utylski | On Track | 3/31/25 FY26 rebaseline activity completed on Mon, 3/31/25 Confidence in delivering value on time: High Confidence in delivering the full value: High ICS2 - the most recent analysis bring the number of required FTEs up to 12 FTEs + 1 Supervisor SAL - completed FR - completed | K: L5 | Completed | L5 | 2022-09-01 | 2023-09-29
Business Only Initiative: CCII Flux Capacitor | 1461 | 8844 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | George Sundin, Erica Carpenter | On Track | On track | K: L5 | Completed | L5 | 2022-10-10 | 2023-08-17
Business Only Initiative: AICTS Manifest Reconciliation Center | 1401 | 8839 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Brian Campbell, Heather Coolican, Douglas Stubbs | On Track | 04/13/2026: No Change 04/06/2026: No Change 03/30/2026: No Change 03/23/2026: No Change 03/16/2026: No Change 03/09/2026: No Change 03/02/2026: No Change 02/25/2026: No Change 02/18/2026: No Change 02/09/2026: No Change 02/02/2026: No Change 01/26/2026: No Change 01/19/2026: No Change 01/12/2026: No Change 01/05/2026: No Change 12/29/2025: No Change 12/22/2025: No Change 12/15/2025: No Change 12/08/2025: No Changes 12/01/2025: No Changes 11/24/2025: No Change 11/17/2025: No Change 11/10/2025: NO CHANGE 10/31/2025: No Change 10/16/2025: Preparation to push to L5 10/06/2025: KPIs updated 09/29/2025: NO CHANGE 09/22/2025: NO Change 09/11/2025: KPIs updated. Financials zeroed out 09/02/2025: Awaiting updated KPIs to load. Financials zeroed out 08/22/2025: No Change 08/14/2025: July Financials Zeroed Out in preperation for L5 move in OCT 08/08/2025: JULY KPIs updated 07/28/2025: No Change 07/21/2025: No Change 07/13/2025: No Change 07/092025: June actual financials and KPIs uploaded 06/30/2025: On Track for a L5 move on 10/15/2025, as 3 Months of "mature benefits" are needed. 06/23/2025: No Changes 06/16/2025: No Changes 06/09/2025: May Actual Financials & KPIs updated 06/06/2025: Initiative at L4 MAY 29 2025: Initiative submitted for L4 acceptance review MAY 26 2025: Initiative Review to push to L4 MAY 19 2025: No Changes MAY 12 2025: April Financials & KPIs updated MAY 08 2025: Preparations being made to move to L4 APR 28 2025: No Change APR 18 2025: FY26 rebaselined APR 04 2025: NO change. Monthly Financials and KPI actuals continue to be added MAR 21 2025: No change MAR 14 2025: No change MAR 05 2025: Financials updated. No other changes FEB 14 2025: All Work Groups have completed their respective tasks some time ago. Currently updating the Financial Monthly Reimbursables (Feb, March ) until April | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-10 | 2025-04-18
Business Only Initiative: LAC Clearance Shared Services II - Center of Excel | 70300 | 7102 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Geremy Solis, Jorge Chiros | On Track | **10/27/2025 STATUS** STATUS: Project is close to completion. PROGRESS MADE: Project moved to L5 recently. The financials were updated with additional labor savings (~$47K USD yearly per agent) from Aug-2024 to current. These additional savings are from shifting the clearance case call work by two agents in Puerto Rico/US to the Clearance Shared Center agents in the Dominican Republic, which is a lower cost served market. Team was pending for the approval of the replacements for some time in FY25 that they were missed inadvertently to be included in the Planview financial updates. BLOCKERS: None RISK DETAILS: None SUPPORT REQUESTED: None FY26 rebaseline activity completed on Fri, 3/28/25. * 4/4/25 - System enhancements (PScan replacement) in BM and fixes in AW and CW completed. Interviews with potential new hires for resource replacement. Team reviewing process to further increase same day clearance. * 5/1/2025 - Team working on justification to lift work from 3 PR agents and shift to STIGC. In addition, team reviewing with Properties department on setting up additional desks in STIGC for the shift. Evaluation of current process is in progress. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-09-01 | 2025-07-22
Business Only Initiative: Automation of entry currency corrections | 10191 | 9103 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Steve Ashbaker, Melissa O'Brien | On Track |  | K: L5 | Completed | L5 | 2022-12-13 | 2023-06-27
Business w/ Tech Initiative: Systemically cage on arrival where Prevent reasons | 10190 | 9102 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Steve Ashbaker, Melissa O'Brien | On Track |  | K: L5 | Completed | L5 | 2022-12-06 | 2023-06-06
Business w/ Tech Initiative: Enhance and Automate Jupiter | 10163 | 9100 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Cindy Shadburn, Nickie Larson | Some Issues | L3 submission originally delayed for further attempts to determine cost-center at Director level. Director cost-centers are identified & outlined within supplemental spreadsheet attached, however, due to multiple sub-initiatives & overall initiatives impacting same/similar group of workers across Director organizations, Finance is proposing VP cost-center for FTE reduction accountability/measurements. UPDATE 11/11/24 - Remaining projects on backlog with our I.T. Resources as they are working on Gemini UPDATE 12/2/24 - Confirmed again with Agility that remaining sub initiatives are on backlog due to Gemini UPDATE 12/12/24 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE 12/19/24 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE 12/30/24 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE 1/14/25 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE 1/21/25 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE - 1/28/25 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE - 2/11/25 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE - 2/18/25 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE - 2/25/25 - Two remaining sub-initiatives on hold until I.T. resources are available UPDATE - 3/11/25 - Two remaining sub-initiatives on hold and are est < $100K/year savings and will be separated at a later point if/when they materialize. Ready to move to L4 UPDATE - 3/26/25 - Two remaining sub-initiatives on hold and are est < $100K/year savings and will be separated at a later point if/when they materialize. Moved to L4 UPDATE - 4/14/25 - Iniative is L5 | K: L5 | Completed | L5 | 2022-12-13 | 2025-05-30
Business Only Initiative: Clearance Shared Services LAC Pilot - Dominican Re | 24645 | 9528 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Geremy Solis, Jorge Chiros | On Track |  | K: L5 | Completed | L5 | 2022-05-02 | 2024-02-05
Business Only Initiative: Route-based General Express CFS Volume-Manual | 1746 | 8886 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Scott Wilson, Douglas Stubbs | On Track | Leverage highly accurate manifested routes with high HS codes included that are already established to take advantage of Custom's reimbursable fee. | K: L5 | Completed | L5 | 2022-12-13 | 2023-08-31
Business Only Initiative: Customer-Driven CFS Fast Lanes | 1124 | 8815 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Douglas Stubbs | On Track | Savings summary (Mar 9): -Pilot to date is $4.6M -February savings was $897.7K -March savings to date are $446K -Actualized savings of $21,488.52 in Oct 2022, actualized savings of $2.47M in Jan 2023. -Next actualization April 2023 | K: L5 | Completed | L5 | 2022-09-01 | 2023-04-28
Business w/ Tech Initiative: Manifest Recharged Information (MRI) | 86392 | 7847 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tyler Ross, Sheri Gaines | On Track | Updated - 3/11/26 **Status Rationale** * 3/3/2026: Epic 2, Cap 3 milestone pushed out one month to 03Apr as team awaits legal approvals. * 3/11/2026: Epic 1 Rollout Purple Tail pushed out to 4/30/26, working to coordinate with VISA admin teams to adjust complicated routing that is preventing rollout. * 3/11/2026: Epic 1 Truck Conveyance code complete pushed to 3/27, so rollout is pushed to 4/30/26 * Epic 1 Cap 3 - Continuing to rollout shortages for activated conveyances * Epic 2 Cap 1 - Aiming to lock another conveyance on 3/12 and then hoping to progress rollout speed * Epic 2 Cap 2 - Updates made to report with demos continuing to show expanded functionality **Financials ** * Reviewed financials with with David Spradlin * No financials to report until all three epics are completed **Progress Made** * Shortage and Overage rollout continues. * Sweeps running to help prepare for locking * Successful proof of concept for locking **Milestones** * Milestones updated to reflect delay due to tariff work that is taking priority * MVP1 - Globally rollout all Purple Tail Conveyances - 3/13/26 * MVP2 - Globally rollout all Commercial Converyances - 4/30/26 * MVP3 - Globally rollout Trucks Target Date - 3/27/26 **Key wins** * 53% of all purple tail flights intialized * Overage reduction for the Epic 1 Capability 1 by manifesting shipments with PUP/PUX missing and auto-deriving destination location ID **Blockers and Risks** * Risk - Milestone dates being moved further due to tariff work prioritization **Support Requested** * None **Other status information** None FY26 Rebaseline activity completed on Mon, 3/31/25 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-30 | 2026-10-30
Business w/ Tech Initiative: GTS Canada Clearance System Fixes & Enhancements | 35643 | 8159 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Eric Abadie, Waseem Saleh | Some Issues | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads 8Apr25 - working on recalculating savings based on FY24 financials. Rebaseline will be completed once this analysis is complete. Nov-2024 - filling in the appropriate information to start the move to L3. New financial information calculated and update to the demand description to clarify the ask. July-2025 On hold after recomendation from Oliver Weiman and executive review | E: L2 | Cancelled | L2 | 2025-01-07 | 2025-06-18
Business w/ Tech Initiative: Auto-indexing | 67024 | 7831 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Timothy McEnnis, Sharon Ponder | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads 9/3/25 - Putting initiative on hold for now due to the uncertain future of tariffs with this current administration and the court cases surrounding them. It doesn't look like indexing will be going away any time soon. 8/22/25 - Deminimus for the rest of the world goes away next week, 8/29/25 and FDA auto may proceed for low-value shipments goes away soon after, probably before the end of the year. That means indexing is going to double maybe even triple in volume soon so we are adding more indexing teams. I will be adding 3 more indexing teams to my org and other teams will be adding indexing staff as well to compensate for the additional volume. Efforts are still under way by our IT partners to add more automation but I do not know when any of those new systems will be in place. I do not foresee any cost savings in the near future so I do not know when I will be able to advance this initiative. 7/17/25 - I don't know when project FXLD01086 will be be completed yet. There is so much going on with all the tariff changes and de minimus going away that the IT/Engineering groups are focused on other, more important things now. I do not have a timetable for when any financial values will be loaded into Planview. Again, with all the tariff changes and elimination of de minimus for CN/HK and possibly the rest of the world, processes and procedures are changing too fast to make any sort of prediction. While we still do some traditional indexing, the introduction of auto entry processing has changed the landscape considerably and until we can get a handle on the huge increase in volume and fully implement some of our auto processes that are in development it is difficult to predict even how much traditional indexing there will be left to automate. We are also hamstrung by the fact that this current administration adds/modifies/removes tariffs with little to no notice making it very difficult to plan for the future. We have added some automation to help reduce workload but the sheer volume of work coming is overwhelming so we have had to add hundreds of vendors and enlist the help of our SSC partners to process the volume. 3/11/25 - To boost shipment clearance and reduce clearance delays for Peak ’23 we implemented a change to indexing. Starting in early Dec. '23 most formal entries over $2500 bypassed the indexing step and went directly to the CF3461 PROCESS step instead. A number of indexing personnel were diverted from indexing to entry processing to work the added volume in the CF3461 PROCESS step. We've seen a savings of 13 FTE's from this indexing change. Currently, we have an equivalent of 11.5 GO FTE's working CF3461 processing. We are working to increase that number to match the 13 FTE's we saved. FXLD01086 Duty and Tax Table Enhancement project which was scheduled to be done in Mid-October was delayed in favor of a higher prioritiy project. No eta on when FXLD0101086 will be done. Internal indexing data reviews are continuing and pending further discussion with GO/ECP/SBP on the remaining indexing processes. In order to accomodate impact from impending de minimus enforcement, Adeeb Pasha will be taking over the GO indexing and I will be bringing Adeeb into the auto-indexing discussions. I am in the process of scheduling meetings with GO/ECP/SBP to determine the next indexing processes to convert to auto-indexing taking into consideraton Peak and de minimus increases/changes. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2023-11-28 | 2024-10-23
Business Only Initiative: Move FTN Sec321 to lower cost channels | 67014 | 7404 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Roland Rogers, Nickie Larson | On Track | Data reviews with IE are continuing for opportunity. Weekly IE meetings currently ongoing to vet data, cages, realistic opportunity minus (-) true cages and prevents that fall within the value buckets due to either missing descriptions and/or missing values. Expected savings per transaction = $4.20 ($4.45 FTN Cost - $0.25 SEC321 Manifest Release or ET86) Manifest Releases (SEC321) = 93.09% On Time Clearance (16276 not on time 6.91% DEC) ET86 = 77.04% On Time Clearance (4905 not on time 22.96% DEC) 21182 Opportunity (Not On Time) x $4.20 expected savings = $88,965 Est Mthly (x12 = $1,067,583.00) Per last Pod Call meeting prior to movement into Plainview, discussed having this initiative closed. This initiative was cancelled in Sept of 2024. With DeMinimis cessation, this is no longer a viable initiative. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2023-11-01 | 2024-04-22
Business w/ Tech Initiative: SBM Value Bundle #1 SBM 010 Clearance Routing Grou | 12873 | 7821 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Douglas Stubbs, Christina Dunphy, Shane Bradley | Some Issues | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads 15May25 - April numbers were low due to the implementation of Tariffs for China and Hong Kong 28Apr25 due to Tariif requirements this has reduced benefits for CFS 10MAR2025 - Challenege still within Visa Prime to solve for issue of Multi-routes when 1 route is a CLH and other route is Purple Tail on same flight. The conflict internal to VP 03JAN2024 - SBM 010 is still turned off in production. Meeting on 1/6/25 to discuss with Martin Hubert and Shane Bradley 09DEC2024 - Issue with DEL-YVR-MEM route uncovered an issue with SBM 010 that was compounding issues. SBM 010 was turned off on 12/4 so they can review and fix defects. No info on when this will be fixed and turned back on 19NOV2024 - SBM 010 was turned on, on 12NOV2024. Still monitoring for defects but none found so far 11NOV2024 - Defect fixes were loaded. MEM is being turned back on, on 12NOV2024. We will monitor for any issues on 13NOV2024. Should be able to enter L4 this week 30OCT2024 - Defect fixes were tested and business passed the results today. Moving to production before peak freeze on 04NOV2024 | I: L4 | Cancelled | L4 | 2023-09-26 | 2024-10-23
Business Only Initiative: Streamline Clearance EU Process using RPA [ECTS] |  | 88479 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jonathan Pertzborn, Aleksandra Woch | On Track | 02/13/2026 Increased Productivity between the start of the Project and January on the 20% growth; Evaluation Phase being currently processed in the OPO FR Import market - Team is using the scripts, however, High Volumes and recent System change are preventing to move forward with the final steps of the Evaluation process. Expected to have a complete Update by March; Mailbox Automation for Italy and Belgium still being used To push forward to L3 - we are pending P&E Support with Savings Calculations. Process is being timed and measured. Meeting held on the 12th of February 2026, where P&E presented the first sketch of the Savings Calculation Excel and all the considered factors. Next step is to validate with the other Country P&Es regarding time measurements, aiming for standardization. Once Savings are obtained, it is projected to make the move in Planview to L3. 01/29/2026 Increased Productivity still between the 20-25%, Evaluation Phase being currently processed in the OPO FR IMport market Mailbox Automation for Italy and Belgium still being used To push forward to L3 - we are pending P&E Support with Savings Calculations. Process is being timed and measured. Next Alignment Meeting on the 4th of February 01/05/2026 : scripts running aleady in DE market in OPO SSC, increased productivity 25% observed , scripts are deployed in FR, undergoing Evaluate Phase. also mailbox automation for Italy and Belgium - License Obtained To push forward to L3 - we are pending P&E Support with Savings Calculations. Process is being timed and measured. Next Alignment Meeting on the 4th of February | E: L2 | Active | L2
Business w/ Tech Initiative: Customs Data Automation (CDA) - Europe POC Exp. |  | 89068 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Przemyslaw Feliksiak, Terri Tennison, John Stoten | Some Issues | 04.14.2026 - We've learned that there is plan to rollout Genius in Europe countries. It's in early phase so there are no target dates yet. Currently P&E is working on analyses for each country. New functionality for Genius is under development. It should allow to automate consolidating items by tariff heading and country of origin. Currently undergoing tests in one country on one Customer. If succesful it can be implemented in other countries where we use Genius for clearance. Above information is important because goal of this initiative is to expand CDA to more countries (whether they use Genius or not) and to develop possibility of consolidating items per tariff heading and country of origin. There is no feedback from Management team yet on how we should proceed. Our architects followed up on this question. 03.27.2026 - Issue with using contract events data for clearance is now resolved. We have confirmation that we can move forward with our initiative and use this data. Architects has been informed and they reached out to their management team to get their direction on how to proceed. 03.12.2026 - Issue with using contract events data for clearance is still being disicussed on MD and VP level. OCR - we had a call with a team and agreed on next steps. Team will do some testing on shipments of selected by us Cusotmers/Shippers. We have provided two Shippers account and once OCR team will be ready we will monitor tests. 02.23.2026 - There was a call between VP's regarding legal issues (using contract events data for clearance). There is no outcome yet. OCR had some questions on CDA, we've provided answers and shared all available information. There is a call scheduled to discuss next steps. 01.23.2026 - Discussion with legal ongoing. We had a call explaining how CDA works, what data it uses. Decision still pending, follow up call has been scheduled. Higher leadership is now also involved in this discussion. 12.19.2025 - We've had a call with OCR team, where they presented us live how this tool works. In our QAT team, there is agreement we should include OCR in our project and we will be working on it. We also continue discussion with Legal regarding using Contract Events data. After several e-mail exchange, we agreed it's best to arrange call, so we can answer all questions and clarify any unclear apsects of CDA. 11.28.2025 - Call with architects where we were working on updating project documentation. Since GEMINI 2.0 has been cancelled, we were also discussing about possibility of using CDA in more countries than initially agreed. OCR Team ran tests with invoice examples we provided for Customer that are alrady onboarded to CDA. Results are goods and we think this might be good alternate source of CDA data. 11.21.2025 - Calls with architects to discuss next steps and updating business rules. Continue working on getting confirmation if EDI feed and cotnract events source of data can be used for clearance activity. 11.14.2025 - We've had a discussion with OCR team and they confirmed they might be able to help with our initiative. I've shared with them invoices and shipments AWB numbers for the testing purposes. We are also still working on getting answer from legal and marketing perspective regarding source of data that are being used for clearance. 11.7.2025 - We've had a follow up call with Eric Barnes and further discussion about how FedEx shipment creation works and what data is provided Customer. There is still question if from legal perspective if we can use this data for clearance. There has been also set up call with OCR team for next week. 10.31.2025 - We had a meeting with Eric Barnes. He expressed the same concerns as Rober. He advised we should discuss: - with legal if using EDI feed data instead of invoice is allowed from their point of view. - with OCR team if they can help digitalize invoices, so we can use this data instead of contract events. I've contacted them and waiting for their feedback. CDA | E: L2 | Active | L2 | 2025-07-31 | 2025-07-31
Business w/ Tech Initiative: US Broker Automation, FXL Brokerage |  | 90021 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Bryan Hertz, Nickie Larson | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads Three* POCs identified and in exploration stages; on track with anticipated progress. WE 3/21/25: - Concentrating on obtain the needed information for LBC on POCs - POC 1.a, POC 1.b, POC 1.c WE 3/17/25: - Bryan: Working to understand the expectations and how to progress from L1 to L2 WE 2/24/25 - Adding third POC 1.C SIAUTO Assist uses automation to file single commodity line as a single informal. WE 1/31: - Description updated to clarify existing POCs & potential addition for others as exploration continues - IO to be updated from N. Larson (461022) to B. Hertz (438699); ** B HERTZ NOT IN PLANVIEW - POC 1.a nets minimal efficiency/savings due to low accuracy level of VISA ingested manifest data; unable to utilize to populate broker entry - Expanding to include OCR for FXL to digitize entry data elements from CI & addtl. documents for ingestion and population into broker entry Working w/ Naveen & DW team to define scope & logic for ingestion Submitted a Regulatory priortized demand request for ITAR keyword OCR development 08/11/25: Per Nickie - It’s possible, with the number of enterprise clearance initiatives stood up since Feb/Mar ’25, this specific one may be due for cancellation as inits such as Michaelangelo, Touchless, etc. encompass the original objectives as outlined in the initial 3 POCs. Pending next step to verify if this can be cancelled. | C: L1 | Cancelled | L1 | 2025-10-01 | 2025-11-28
Business w/ Tech Initiative: Intl Soln for Warehouse Automation & Mgmt (iSWAM) | 88733 | 7581 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Julian Albritton, Valenta Nichols | On Track | 3.25.26 - MTP completed 3/12/26 2.25.26 (JA) - Dev complete, MTP planned for March - date is TBD 2.5.26 (JA) - Dev complete; MTP planned for 2.27.26 1.26.26 (JA) - Dev complete; pending MTP that is TBD as dev team is working to resolve issue observed during previous MTP 1.15.26 (JA) - Dev complete; pending MTP tentatively planned by end of January 11.4.25 (JA) - Development in progress 10.23.25 (JA) - In L3, Development will start and complete in PI5 that starts 10/28/25 10.15.25 (JA) - PEL Greenlight on 10/9; Submitted to L3 9.10.25 (JA) - PEL SCO review is cancelled on 9/18. Targeting PEL review on 10/2 (next open slot). 9.10.25 (JA) - Working towards moving to L3. Targeting PEL SCO review on 9/18. 8.22.25 (JA) With GoScan not approved, determining next step to move capability to add package detainment location to iCAGE to L3; Accessing capability value to change request type from Enabler to Efficiency 8.15.25 (JA) Architecture approved 8.1.25 (JA) Solution Architecture reviews planned for 8/5/25 7.25.25 (JA) Architecture analysis MD review completed for capability 3 - Cage Reporting tool update on 7/22/25. Pending Solution Architecture completion. 7.16.25 (JA) Architecture review pending L3 analysis reviews scheduled for week of July 21 3.31.25 (JA) Zeroed out Mar 25 forecast; Architecture review in process, timeline will be updated when complete. 3.13.25 Workinig through architectural documents and aligning on a timeline. Will have multiple Value Bundles with an MVP. 2.28.25 Requested Updates to ESI, Strategic Theme and Type through PDSM: ESI= Clearance Strategy Strategic Theme = Run and Change our Business Request Type = Enabler 2.12.25 Zeroed out Feb 25 forecast, as was not able to enter $0 value in Actuals 2.12.25 With Clearance Architecture. Working to determine how this fits with other Cage Automation initatives. 1/31/25 Still will Clearance Architecture 1/13/25 Updated financials to remove forecasted savings from months that have passed; Still with Clearance architecture for review. 1/9/25 With Clearance Architecture for Ability-To Statements and Epic Creation. 1/6/25 Currently with Robin Taylor for Clearance Architecture. He will then send on for IT Architecture once Clearance work is complete. Once IT Archtecture documents are complete, we can request move into L3. All costs for this initiative are development related (CCII, iCage, and new GoScan application). Dataworks to stand up and maintain the GoScan application for mapping in cages. 2/19 Changing status back to "On Track" as we met with Business and IT archticture 12/16. Robin Taylor is finalizing the ability-to statments and will send to Markus Reimers to define the IT archtecture once complete. 12/3: Need to get to PRT in order for architect assignment and to begin Decomp/Analysis which is requred for L2. | I: L4 | Active | L4 | 2025-10-28
Business w/ Tech Initiative: Global Screening Scanning and Intercept (GSSI) | 1136 | 9341 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Linda Fitch, Erica Carpenter | On Track | 01/06/2025: CEW - Do not cancel. Leave on hold as GCSI and other teams evaluate to identify synergies. 2/16/24 - Direction from Leadership is to pause GSSI through FY25. Initiative has been placed on-hold in Wave. 1/22: Epic A - Team worked on PHLD, DB and UI work. PI Planning event is this week where team will plan for GSSI features and stories. The Application Architect time is being pulled in other directions, including Max Whitetail. Epic B - Rob approved the SCI. However, general message to the consuming systems and ART is to hold off on planning Epic B work other than research due to its dependency on Epic A. We don't want the consuming ARTs and systems to work on B and then have to do rework. EPIC D - Team continues to work SCI document and trying to close gaps. Epic E and F - Received information from PRT team that issue is not just about priority, but GSSI team may need to quantify value of Epics E and F before continuing with PRT efforts on these epics. Team will meet with Express Portfolio to discuss WJSF> New team direction will be to focus what can be reasonably done and what it will take to replace CCII and GRSIS. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2022-10-04 | 2026-01-08
Business Only Initiative: Add GRSIS in Secondary 12 |  | 92107 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Ernest L. Sowell III | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads | C: L1 | Cancelled | L1
Business Only Initiative: Add GRSIS in Secondary 12 |  | 92110 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Ernest L. Sowell III | On Track | Duplicate initiative | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FRAME (Financial Reconciliation and Management Eff |  | 92116 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Wayne Daniells, Sean Brady, Renu Maheshwari | On Track | 22/04/2026 Platform Architect Sanjay Kumar and Enterprise Architect Joey Cline have been working to obtain the EAI number. Sanjay has also informed us that the costing has been submitted to PEO for greenlight approval. 04/01/2026 Architectual review board meeting set for today with Platform architects. Hoping this will determine the T-shirt size and any other information now needed to move the initiative into SL3. Currently in talks with Sean Bird in order to create EAI numbers via the ENGAGE process. 03/17/2026 Architect Sanjay Kumar has been assigned to FRAME. We have a technical discussion meeting with him and the team tomorrow 03/18/26. In preparation we have shared more tech flows and mermaid charts created by the team whilst waiting for an SA to be assigned. 03/10/2026 Added the L4 Money step into the milestones, as requested by Kelly Rowland. We still do not have architectural support assigned, so the project completion date remains an estimate only. In the GC High Priority Initiative Tracker slide deck, the next steps currently show “Pending D&AI architectural support – new resource to be assigned by 2/27.” However, we have not received any update on this. The initiative is currently ranked 110 in the Enterprise Rankings. 02/27/2026 Email conversation between Kelly Rowland and Tarun Grover asking if SA resource has been assigned to us as notes state this will happen today. Tarun then asked Zahra Taqi if we have been prioritized for architectural assignment. No answer received as of yet 02/20/2026 No follow up received regarding architect support. Currently 110 ranked in the portfolio Power Bi so going in the wrong direction. 02/12/2026 Kelly Rowland is working to 'boost' this initiative (again) w/ Platform 02/02/2026 No follow up received regarding architect support. Currently 105 ranked in the portfolio Power Bi. 01/20/2026 * The group discussed the need to clarify ownership and accountability (business and IT) for the effort, with finance and data/AI stakeholders needing representation. * Key requirement: ensure proper architecture oversight for data and AI to protect data, preserve integrity and accuracy, and meet regulatory/controls needs. * ETAC will provide technology patterns and recommendations (e.g., APIs, file interfaces), while Data & AI teams are responsible for applying those patterns and implementing solutions. * SAT (solution/side) architects in Data & AI should handle technology decisions and solution design; they also need to coordinate estimates and commitments with AI directors and build teams. * There’s some ambiguity about which team owns final technology decisions and implementation; the line between ETAC (patterns) and Data & AI (realization) is blurry. * Next steps: put the work on the side-architect backlog, assign an architect (blocked until assignment), and seek additional EA architecture support as needed. Michael will follow up and provide clarity on why the support is required. 01/15/2026 Action items and next steps: Prolaborate link to Conceptual Architecture: https://fedex.sparxcloud.us/LQu1IB Current Blocker: Data & AI architecture input on Conceptual architecture Estimates and Financial input for Planview (to move from L2 to L3) Action Items: Michael/Sandeep: Data & AI light weight overview of Conceptual architecture Michael/Sandeep: to provide MD names impacted by Speedcargo Raye: reach out to identified MD’s to discuss SAD architecture support to move forward to L3 ALL: Walk-through of Conceptual architecture with ESAC [scheduled for 1/16/26] 01/06/2026 Reached out to our PM Raye Paul as we have not seen or heard any progress. A call has been set up on 01/07/26 with Senior Enterprise Architects from Data Engineering and Data Science. We hope this will yeald more progress to move to L3. 12/17/2025 Assigned to Sandeep Bahadur per Chris Enzor; however it falls behind EU Modernization. 12/04/2025 Email from Claire Wilkinson stating: FRAME was discussed | E: L2 | Active | L2 | 2025-04-22 | 2026-10-01
Business w/ Tech Initiative: DE Exit Clearance System |  | 92121 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Sascha Heber, Wilfried Faust, Lukasz Utylski | On Track | 14.04.2026 BRS Document has been finalized and reviewed by Business. 19.03.2026 Finalisation of BRS Document and start to review Conceptual Architeture 23.02.2026 BAs to review the requirements with local team to refine the L2 documentation. Sessions scheduled for the coming weeks. 06.02.2026 Review session with Enterprise Architect scheduled on February 19. 03.02.2026 Meetingwith BAs and local team to review L2 Capabilities 05.01.2026 no update 16.12.2025 Enterprise Architecture engaged and developing capabilities. Expected completion Mid January 2026 for SCI. L2 review complete except these remaining dependencies. 03.12.2025 L2 Capabilities List to be finalized, Meetings scheduled with BAs. 12.11.2025 Change - Significance changed to moderate. Aligment Call with assigned Architects tool place to discuss the T-Shirt Size and impacted Portfolios. 10.11.2025 Updated Exit Rate 2028. Received Feedback from David Spradlin to leave it at 0 as this Initiative has soft savings only. 31.10.2025 L2 Details updated 08.10.2025 Submitted to L2 and received approval for Business Continuity prioritization 26.08.2025 added L1 Architecural documentation 21.08.2025 Money step details updated with more details. 30.07.2025 PPM Project Number: 1229043 The initial request primarily focused on export clearance. Accordingly, all financial figures referenced thus far pertain to this area. However, the provision of export clearance services fundamentally depends on the existence of a functioning exit clearance process. As Germany is currently still relying exclusively on Excel-based tools for exit clearance, the focus of this request is now shifting towards the development and enhancement of the exit clearance system. 15.07.2025 Financials are under Review as the Scope is changing to the Exit System instead of the Export System. 15.07.2025 The original request pertained to the export solution. The focus is now shifting to the exit system, while the export part is planned to be covered by Gemini 2.0. Germany should be the POC for the EU Exit Solution. 04.07.2025 No Update 30.06.2025 No Update 20.06.2025 No Update 12.06.2025 No Update 30.05.2025 No Update 16.05.2025 No Update 08.05.2025 No Update 02.05.2025 No Update 23.04.2025 No Update 11.04.2025 No Update 04.04.2025 No Update, Milestones still to be discussed and agreed. 31.03.2025 Workshops for MVP-1 completed. Discussed business requirements, scope and workflows with IT and P+E. Next steps still to be agreed. 21.03.2025 No Update 17.03.2025 No Update 26.02.2025 No Update 18.02.2025 Workshops for MVP-1 detailed analysis and requirement definition scheduled for March'25. 12.02.2025 No Update 07.02.2025 the GEM P2 Kickoff Presentation does include all requirements for a DE Exit Solution based on the workshop held in Feb. 2024 (attached to this request) What is not included is the Presentation of EADs at Inland customs offices what is covered by MVP-0 currently as this requirement was not existing at that time. During the MVP-0 Analysis the team also drafted MVP-1 in High level. For this a workshop during this PI will be planned to analyse the current requirements to be able to start development of MVP1. In this discussion we will also analyse how the already accomplished parts of GEM P1 and MVP-0 can be merged into MVP-1. | E: L2 | Active | L2 & CCH | 2024-07-22 | 2028-06-01
Business w/ Tech Initiative: IOSS Centralisation |  | 90006 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Sean Brady | On Track | 8/21/25 - Initiative on hold 16.01.2025 - Call completed to assess next steps. Data pull from P&E to assess what is required to submit request for followup to initiatial P&E review 08Jan2024 - Current discussions taking place to determine IO/backup IOs and bring in relevant SMEs to support 19DEC2024 - Current discussions taking place to determine IO/backup IOs and bring in relevant SMEs to support | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-07-22 | 2026-02-27
Business w/ Tech Initiative: Automate EEI Filing |  | 93676 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jeremy Denton | On Track | 04/06/2026 - Financials entered - NEXT UPDATE will be first week of May 03/12/2026 - Financials entered - NEXT UPDATE will be first week of April 02/09/2026 - Financials entered - NEXT UPDATE will be first week of March 01/12/2026 - Financial entered - NEXT UPDATE will be w/c 02/03/26 12/08/2025 - CEW - Pod PM/Lead met with IOJeremy Denton and Finance David Spradlin to discuss drop from 408k NRB to 60k NRB due to CIL completed staffing actions based on business loss impacting financials for this initiative. KPIs also revised from 96 FTE/yr to 8 FTE/yr. 12/05/25 - November financials updated 11/17/25 - Need to amend forecast to $5K per month based on current business needs and effects on the team we are supporting due to lost business. Will be reviewing with my Sr Management this week, expected update 11/21/25 11/07/25 - October financials entered. 10/15/2025 - Money step moved, still evaluating the system affects on workload for EEI, change in management of CIL where staffing will be affected and additional work needed to be scoped out 10/03/2025 - Sep Financials entered 09/11/2025 - No additional Update 09/05/2025 - Aug Financials entered 08/22/2025 - Moved the Milstone for employee actions to match the changed money setp. 08/08/25 - July financials entered and "Money Step moved to October because of a number of changes currently taking place within the teams. Any Issues I am in Europe on Business week of 8/11 to 15 07/31/25 - No change 07/18/25 - Work still in evalauation, time value currently not as great at originally anticipated due to multiple shipments in one email unable to "Split and Staple" in MEE. 07/10/25 - June financials entered 06/09/2025 - Milestones Updated Triage meeting with David Walker today. May Financials updated. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-01 | 2026-05-27
Business w/ Tech Initiative: CH Regulatory Changes & Vendor Replacement |  | 85946 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Lukasz Utylski, Silvia De Sousa, Julie Oeosterle | On Track | **Date:** 02/13/2026 **Progress Made:** * Initiative completed. GEF and GITR implemented **Upcoming Milestones:** **Blockers and Risks:** **What is keeping the initiative from moving forward and steps taking to mitigate** **Date:** 04/04/2025 **Progress Made:** * Split Initiative to Import * Complete GITR workshop * L2 provide documentation of CORE SOLUTION to system Art – March 25th •Risk assessment (Ops impact) – March 4th **Upcoming Milestones:** •L3 HO documentation CH country kit to system art – June 25th •Update project details to progress into L3 •Development completed August 25th •Change management , testing . training completed Sept 25th •Soft Launch completed Dec 25th •Go Live Dec 25th **Blockers and Risks:** •Short Lead time •Complexity of legacy system to move on GENIUS •Lack of clarity on Dependencies (ACE migration, Quantum retirement) **What is keeping the initiative from moving forward and steps taking to mitigate** •Involvement of various system Expert (Quantum, IT architect, Sort, DH2) Support Requested 3/31/25 FY26 rebaseline activity completed on Mon, 3/31/25 **Date:** 03/19/2025 **Progress Made:** •Business case assessment completed •Initiative progressed to Planview L2 •Risk assessment ongoing: on-track (incl. Ground Operations Impact ) •PPM number approved and added in the details •Approval for F2F workshop received **Upcoming Milestones:** •L2 provide documentation of CORE SOLUTION to system Art – March 25th •Risk assessment (Ops impact) – March 4th •L3 HO documentation CH country kit to system art – June 25th •Update project details to progress into L3 •Development completed August 25th •Change management , testing . training completed Sept 25th •Soft Launch completed Dec 25th •Go Live Dec 25th **Blockers and Risks:** •Short Lead time •Complexity of legacy system to move on GENIUS •Lack of clarity on Dependencies (ACE migration, Quantum retirement) •GITR development capacity TBD – Business trip required for F2F workshop **What is keeping the initiative from moving forward and steps taking to mitigate** •Involvement of various system Expert (Quantum, IT architect, Sort, DH2) Support Requested •MD support requested – MD call set up 4th March. Risk assessment presentation, complexity, effort required while integrating orange **Date:** 02/26/2025 **Progress Made:** •Business case assessment completed •Initiative progressed to Planview L2 •Risk assessment ongoing: on-track (incl. Ground Operations Impact ) **Upcoming Milestones:** •L2 provide documentation of CORE SOLUTION to system Art – March 25th •Risk assessment (Ops impact) – March 4th •L3 HO documentation CH country kit to system art – June 25th •Update project details to progress into L3 •Development completed August 25th •Change management , testing . training completed Sept 25th •Soft Launch completed Dec 25th •Go Live Dec 25th **Blockers and Risks:** •Short Lead time •Complexity of legacy system to move on GENIUS •Lack of clarity on Dependencies (ACE migration, Quantum retirement) •GITR development capacity TBD – Business trip required for F2F workshop **What is keeping the initiative from moving forward and steps taking to mitigate** •Involvement of various system Expert (Quantum, IT architect, Sort, DH2) Support Requested •MD support requested – MD call set up 4th March. Risk assessment presentation, complexity, effort required while integrating orange | K: L5 | Active | L5 | 2024-10-03 | 2028-05-11
Business w/ Tech Initiative: [S2 Enabler][TH] Clearance Revolution |  | 94275 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Visut Punsukumtana, Mellyana | Some Issues | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads 10/10/2025 * Change to no impact to Enterprise Services Portfolio advice by Joe Nassar * L1 Architecture Alignment step has been completed and update Link in Initiative Support Architectural Documentation * Change T-shirt size from XS to L * Wait Lean Business Case and all requirements listed on the Planview_Stage-gate_Checklist - Business with Tech & Business Only are fulfilled will consult with Linda Fitch/Trey Schenzel before submission to SL2 09/26/2025 Pending Enterprise Demand Prioritization. ranking 214 09/19/2025 Pending Enterprise Demand Prioritization completion. ranking 208 09/12/2025 Pending Enterprise Demand Prioritization completion. ranking 270 Respond Zachry Boles email on project description and detail for mapping prioritization. 08/29/2025 Pending Enterpirse Demand Prioritization completion. ranking 282 07/18/2025 Checking Enterprise Demand Prioritization Dashboard still have not been reivewed by Architec. Enterprise ranking 295. 04/21/2025 Update annual baseline and target using potential customer and forcase. However, as an enabler type. the amount should not be added in the total target as it would duplicate with Grow Inbound. Strategy Seq. ID 89934 Strategic Parent APAC-SEA as per comment by finance. 04/18/2025 Update Ability to Statement and impacted portfolio that may be impacted and update operational and business process impacted and update Baseline Value and the Target Value. Baseline Fiscal Year been change from FY24 to FY25 as per recommended. 04/16/2025 Update link to Initiative Supporting Architectural document and indicate portfolio that may be impacted. 3/31/25 Rebaseline is completed as of 3/31/25. Talked with Finance and rebaseline is ok which could leave 0 as this is an enabler for ID 89934 so it will not duplicate. Add backup IO | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: [MEISA] [SA] HS Code Auto-Fill in GRACE |  | 103629 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tushar Raibagi, Klaudia Palgan, Akshay Kumar, Palanivel Guruswamy | On Track | ongoing, marketing requsted to move to next stage 4 Apr - who is EPM? as per EPM feedback this wasalready marked as 2 potfolio marked as impacted. The ability to statements are already properly drafted in original request, pls refer. Hence not sure why it is marked as not ready for SL2. 7 Apr 25 - The request is again sent back to L1, please contact IT team responsible under Deepal Wadhwa for architecture doc. 7 Apr 25 - I do not understand what is the feedback and what is expected here from me. I do not see any priortization list. I have been asked by marketing Klaudia to submit to L2. And also understand that solution is already ready so not sure what review is being still done. Pls connect with Klaudia. 24 April - done 8 Sept 2025 - Solution in scope was implemented in April 2025 – working with SCO PEO to obtain a SCO portfolio greenlight (SCO PEL is required) and fast-track to L4. 10 Oct 2025 - Evaluating next steps for this initiative as the accuracy of the solution is low From: David Spradlin <david.spradlin@fedex.com> Sent: Wednesday, October 29, 2025 12:07 PM To: Valenta Nichols <valenta.nichols2@fedex.com>; Macie Kate Walters <macie.walters@fedex.com> Cc: Claire Wilkinson <claire.wilkinson@fedex.com>; Stephanie Waltman <stephanie.waltman@fedex.com>; Linda Fitch <linda.fitch@fedex.com> Subject: RE: #103633 & #103629 - SCO and Data & AI Portfolio Greenlight Hi Valenta, These should be fine to close. From: Valenta Nichols <valenta.nichols2@fedex.com> Sent: Wednesday, October 29, 2025 9:01 AM To: David Spradlin <david.spradlin@fedex.com>; Macie Kate Walters <macie.walters@fedex.com> Cc: Claire Wilkinson <claire.wilkinson@fedex.com>; Stephanie Waltman <stephanie.waltman@fedex.com>; Linda Fitch <linda.fitch@fedex.com> Subject: RE: #103633 & #103629 - SCO and Data & AI Portfolio Greenlight David / Macie We are asking the IOs to cancel PV#103633 and 103629. 1.These initiatives have monthly IT costs going all the way to 2028 but no forecasted benefits. 2.These are just costing money with no discernable captured benefit at all. Do you see any impact from a financial perspective or is there something the IOs need to do in the Financial Plan before they cancel the initiatives? Please let me know so that I can inform them. Thanks. | E: L2 | Cancelled | L2 Feedback Requested | 2025-04-16 | 2025-06-10
Business w/ Tech Initiative: [MEISA] [SA} OCR-Driven Data Update in GRACE |  | 103633 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tushar Raibagi, Klaudia Palgan, Akshay Kumar | On Track | on going - marketing requested to move to next stage 4 Apr - who is EPM? as per EPM feedback this wasalready marked as 2 potfolio marked as impacted. The ability to statements are already properly drafted in original request, pls refer. Hence not sure why it is marked as not ready for SL2. 24 apr - done 8 Sept 2025 - Solution in scope was implemented in April 2025 – working with SCO PEO to obtain a SCO portfolio greenlight (SCO PEL is required) and fast-track to L4. 10 Oct 2025 - Evaluating next steps for this initiative as the accuracy of the solution is low From: David Spradlin <david.spradlin@fedex.com> Sent: Wednesday, October 29, 2025 12:07 PM To: Valenta Nichols <valenta.nichols2@fedex.com>; Macie Kate Walters <macie.walters@fedex.com> Cc: Claire Wilkinson <claire.wilkinson@fedex.com>; Stephanie Waltman <stephanie.waltman@fedex.com>; Linda Fitch <linda.fitch@fedex.com> Subject: RE: #103633 & #103629 - SCO and Data & AI Portfolio Greenlight Hi Valenta, These should be fine to close. From: Valenta Nichols <valenta.nichols2@fedex.com> Sent: Wednesday, October 29, 2025 9:01 AM To: David Spradlin <david.spradlin@fedex.com>; Macie Kate Walters <macie.walters@fedex.com> Cc: Claire Wilkinson <claire.wilkinson@fedex.com>; Stephanie Waltman <stephanie.waltman@fedex.com>; Linda Fitch <linda.fitch@fedex.com> Subject: RE: #103633 & #103629 - SCO and Data & AI Portfolio Greenlight David / Macie We are asking the IOs to cancel PV#103633 and 103629. 1.These initiatives have monthly IT costs going all the way to 2028 but no forecasted benefits. 2.These are just costing money with no discernable captured benefit at all. Do you see any impact from a financial perspective or is there something the IOs need to do in the Financial Plan before they cancel the initiatives? Please let me know so that I can inform them. Thanks. | E: L2 | Cancelled | L2 Feedback Requested | 2025-04-16 | 2025-06-10
Business w/ Tech Initiative: International Cage RFID |  | 88397 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jonathan P. Talley, Julian Albritton, Nathan Tonkinson | On Track | 09.12.25 - Planview request for Enabler initiative was made on 09/08 and approved for L1 on 09/10. **Going forward status updates will be seen on International Cage RFID Enabler (162488).** 09.05.25 **Equipment** - Firewall request still pending. **Printers** - Zebra delivered on new firmware. Zebra printer was tested on third floor of International Building at MEMH with a USB connection and found to print faster than the non-RFID Honeywell PM45 printers currently in use. Next step is to determine if Zebra printers can print on the network and if the mobile printers can print quickly on a bluetooth connection. **Software** - Discussions continue on the possibility of moving to an enabler/enabled model. Feedback from RFID Project Managers was positive and a Planview request will likely be made next week. 08.29.25 **Equipment** - IT still needs to a firewall request for the devices in the East Cage. This could take up to two weeks. Once completed, data should start flowing into Atlas and more testing can be conducted. **Printers** - Both Honeywell and Zebra firmware still pending. **Software** - Project ranked 172 with no architect assigned. IO met with Enterprise Demand Management and Governance to discuss the possibility of breaking up this initiative into an enabler and enabled iniatitives. The enabler initiative would need to be requested in Planview and would serve as a POC for the current initiative. There are more meetings next week to discuss and a final decision is still pending. 08.22.25 **Status Unchanged Since Last Week** - (**Equipment**) - Still waiting on Networking Engineering to resolve firewall issue with Zebra equipment in East Cage. Once resolved, more extensive testing will resume. (**Printers**) - Both Honeywell and Zebra set deadlines for the beginning of September to provide firmware that should enable RFID-enabled fixed printers. Testing will commence once completed. (**Software**) - Project ranked 160th and no architect assigned. Meeting set Monday to discuss the possibility of breaking up the initiative into smaller bits in order to offset the large IT effort versus small value that the initiative currently calls for. 08.15.25 **Progress** - Zebra set target date for new printer firmware of 09.05. Plan is to determine if Zebra represents a better option for printing RFID labels. **Blockers** - Initiative is ranked 158th in Enterprise Ranking and no architect is assigned. **Next Steps** - While Phase 1 and 2 equipment is installed in East Cage, Network Engineering is working on a possible firewall issue preventing the devices from being hooked up to Atlas. Once resolved, more extensive testing will be conducted on the equipment installed. 08.08.25 **Progress**: Testing on Zebra fixed printer was conducted in lab in order to obtain label profiles for Zebra to encode. While Honeywell is trying to enable their fixed printers to read off Port 515, Zebra fixed printers already do this and so efforts are underway to pursue Zebra as a backup option. **Blockers** - Still no architect assigned. Enterprise ranking at 132, so no IT development work. **Next Steps**: Installation pending two anennaes and hook up to Atlas. Once completed, more extensive testing of the equipment in the East Cage will be conducted. Continue to work on Honeywell and Zebra printers. 08.01.25 Meeting held Monday to discuss testing results from last week. Larger scale testing will resume once the equipment in the East Cage is connected to Atlas. Next week there are plans to test out Zebra fixed printer on network. No architect has been assigned. 07.25.25 Initial testing was conducted on Wednesday showing positive results for both RFID readers and Geiger counters. Testing also continues on PM45 printer. Project still needs a archictec assigned. 07.18.25 All Phase 1 and 2 equipment has been installed except for a few antennae. Testing of equipment is planned to start on Wednesday. 7.16.25 Working with Finance to get Financia | E: L2 | Active | L2
Business Only Initiative: Eliminate IND Sunday clearance sort | 451 | 7914 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Chuck Pounders, Stephen Levine | On Track | Entered Impacts and KPI's for JAN23 actuals Prioritization of Initiatives 102022 ![](inline-attachments/451/image/f26165d8-18b4-4755-a302-c97e6d1e47b3-image.png) | K: L5 | Completed | L5 | 2022-11-07 | 2022-12-09
Business Only Initiative: AOD - Custom Clearance optimization China | 26304 | 8221 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Stefano Baratella, Zakaria Qureshi | On Track | FY26 rebaseline activity completed on March 31st 2025 values are not incremental to FY25, therefore forecast has been set to zero according to instructions | K: L5 | Completed | L5 | 2022-11-08 | 2023-09-11
Business Only Initiative: Removal of SkyLease at MIAX | 8110 | 9063 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Maurice Settles, Dan Doherty | On Track | .continued progress | K: L5 | Completed | L5 | 2023-03-01 | 2024-02-08
Business w/ Tech Initiative: Australia & Indonesia - D&T bad debt reduction | 33370 | 8144 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Chetan Khorana, Hardiansjah Rizal Kristanto | On Track | On track . | K: L5 | Completed | L5 | 2023-09-11 | 2024-05-13
Business Only Initiative: APAC_China export PVG-CAN cargomanifest RPA submit | 66083 | 7815 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Shan Shan Li, Hugh He | On Track | 03/28/25: in L5 and exempt from rebaseline 100% in production | K: L5 | Completed | L5 | 2023-11-20 | 2024-03-15
Business Only Initiative: APAC Clearance OSC Reduction - Phase #2 | 33947 | 9496 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Aaron Zhang, Blaine Chen | On Track | No issue, updated Apr actual. This initiative has been in L5 for 12 months and will be closed soon. No need rebaseline as this initiative is in L5 and has been reporting actual for one year. Finished rate negotiation for the vendors (total 11 vendors) in scope in this phase and is ready for L4. Estimated annual saving is $1.4M and will monitor the actual result. | K: L5 | Completed | L5 | 2023-08-01 | 2024-05-23
Business Only Initiative: APAC [OSC Savings]CCCO-CANIP OB Clr Optimization | 84334 | 8884 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jun Cheng, Pinky Jiang | On Track | No re-baseline is needed as no larger than 250k incremental benefit in FY26 expected. 2025/12/9: With much less shpt outsourced to vendor, the saving from this initiative will muc less than projected amount. 2025/11/10: The outsourced volume has reduced a lot that resulted the saving amount reduced. But total OSC cost has reduced a lot as well but that part not counted in this initiative. 2025/9/18: All cost saving actions have been completed and the saving has been realized and running stable. Money step has been achieved. It has been in L4 since May 2025. 2025/8/15: The total savings were less than the planned amount because the savings are directly related to volume. SHEIN's volume decreased significantly — by around 75% — since May 2025, due to changes in the U.S. de minimis tariff policy. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-05-30
Business Only Initiative: APAC Clearance OSC Reduction - Phase #1 | 33505 | 9485 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Aaron Zhang, Blaine Chen | On Track | No issue. April actual is updated. This initiative has been in L5 for 12 months and will be closed soon. No need to rebaseline as this initiative is in L5 and has been reporting actual saving for one year. Submit the initiative for L5 as we have completed the milestones for the vendors in this Phase I and tracked 3 months of actual saving, total saving in Oct - Dec is $174K, which is higher than L2/L3 value estimation ($147K) including: 1. DGM vendor ?? new contract rate with average 9% reduction. 3 months actual saving $61K 2. PVG vendor ??? new contract rate with 7% reduction. 3 months actual saving $37K 3. DGM vendor volume convert to CANIP (with lower vendor rate). 3 months actual saving $76K | K: L5 | Completed | L5 | 2023-05-01 | 2023-09-29
Business Only Initiative: APAC [OSC]CCCO-CANIP IB | 90101 | 7739 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Pauline Yao, KK Yan | On Track | FY26 rebaseline activity completed on 4/4/2025 | K: L5 | Completed | L5 | 2024-06-14 | 2024-12-31
Business Only Initiative: [APAC] CCCO-SZXIP Clr Structural Cost Optimization | 81093 | 8168 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Wen-Jun Chen, KK Yan | On Track | No additional value (April 11, 2025) | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-04-18
Business Only Initiative: APAC_CN Export Formal Entry Clearance Automation | 54748 | 7811 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Shan Shan Li, Hugh He | On Track | on track 03/28/25: In L5 and exempt from rebaseline 100% in production | K: L5 | Completed | L5 | 2023-11-16 | 2024-07-31
Business Only Initiative: APAC CCCO- DATIP Clearance Optimization | 84193 | 7657 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Xiao-Gang Yang, Mark Li | On Track | 1. We launch the CAT D insource from 01Dec, now we track the volume and performance 2. no additional value (11Apr2025) | K: L5 | Completed | L5 | 2024-04-16 | 2024-12-31
Business Only Initiative: APAC (Manning) CCCO - CANIP IB | 83953 | 7712 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Pauline Yao, KK Yan | On Track | FY26 rebaseline activity completed on 4/4/2025 | K: L5 | Completed | L5 | 2024-06-12 | 2024-11-29
Business Only Initiative: APAC [OSC Savings] CCCO-NCW Clr Cost Optimization | 83955 | 8206 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Chunyong Zhang, Bryan Wei | On Track | Mar 21, 2025 Rebaseline is no need due to YOY incremental saving is less USD 250k (USD 176k FY25 vs baseline) | K: L5 | Completed | L5 | 2024-07-09 | 2025-05-30
Business Only Initiative: APAC[OSC Savings]CCCO - CTUIP/CKGIP IB+OB Clr Op | 83957 | 9225 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jack Xu, Amelia Wang | On Track | All milestones had been fully implemented as planned with health by Apr 11.2025. | K: L5 | Completed | L5 | 2024-08-01 | 2024-12-31
Business w/ Tech Initiative: [APAC] Process Evolution Clearance - OB Automation | 43576 | 7009 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Lorida Bejleri, Clement Francony, Hardiansjah Rizal Kristanto, Koushik Das | On Track | This initiative has been decided not to proceed - and to be cancelled. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-12-31
Business Only Initiative: APAC: Japan Export new EDI MEC | 48899 | 8050 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Kengo Taguchi | On Track | Submitted L4 since observed steady savings last over several months already ---- May 12 2025: April 2025: 16K USD cost saving, 5K cost avoidance (OT reduction) April 4, 2025: FY26 rebaseline activity completed on 4/4/25. **Financials:** ・$ saved: March 2025: 16.8K USD cost saving, 5K cost avoidance (OT reduction) Oct24-Mar25: 91.3K USD increment cost saving 10K cost avoidance **Progress made:** • Highlight progress made in the last week: - Reviewed JP customs EDI invoice and updated saving update for March. - OT trend for bothe EJP and KIX gateway's export CCO team was reviewed - Baseline 4.8M USD -> Current 4.7K USD (100K USD saving/avoidance) **Milestones:** • Transaction cost saving is counted more than 6 month. Once OT saving is confirmed in May 2025, move forward to L5 ---- Mar 7 2025: Start conting on OT reduction. Feb 2025 total OT 1200 hours, Feb 2024 Feb OT 1700 hours. Dec 5, 2024: Confirmed $14.7K cost saving in Nov 2024 at BP25 exchange rate 151.62 JPY. Unless the system defects (creating workflow task for MEC LB check task takes 3-7min), JPCCO team may not able to improve the productivity for LB check task. *ISD is planning to fix in Jan 2025 release. Nov 2, 2024: Confirmed $9.2K cost saving in Oct 2024 at BP25 exchange rate 151.62 JPY Oct 24, 2024: MTP on 10/7(Mon) and JP Export CCO started the MEC ramp-up by targeting FICP SHP as a first step. Now declare around 30-40% of FICP in MEC, achieving 500USD/day saving. Oct 2, 2024: Recurring benefits #53685 #57032 for Sep 2024 is zero as implementation (ramp-up) date changed to Oct 7th, 2024. | K: L5 | Completed | L5 | 2023-06-01 | 2024-11-29
Business Only Initiative: [APAC] CCCO-SZXIP Clr OSC Cost optimization | 90930 | 8169 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Wen-Jun Chen, KK Yan | On Track | No additional value (April 11, 2025) | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-04-21
Business Only Initiative: APAC [OSC savings] CCCO – XMNIP + IB/OB CLS optim | 83956 | 9221 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Francis Kong, Amelia Wang, Pinky Jiang | On Track | Complete the rebaseline for FY26 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-01 | 2025-02-28
Business Only Initiative: APAC CCCO - XMNIP Clearance Cost Optimization | 90938 | 9223 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Francis Kong, Amelia Wang, Pinky Jiang | On Track | Complete the re-baseline for FY26 | K: L5 | Completed | L5 | 2024-06-03 | 2024-11-01
Business w/ Tech Initiative: [ASPIRE] Improve IB customs clearance performance | 73546 | 6893 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Betty Kumala, Lorida Bejleri | On Track | 10/24/25: As part of aligning the Global Clearance Domain and the Pods to the overall Clearance strategy, the team recently underwent an initiative rationalization exercise for the Operational Excellence Pod. The goal of this exercise was to streamline the pipeline of initiatives to ensure focus and resources are allocated to the correct initiatives. During this exercise, it was determined that initiative #6893 – ASPIRE Improve IB Customs Clearance Performance Enhancements will not move forward in the Operational Excellence pod at this time. Therefore, the initiative is cancelled and will no longer be required to provide updates in Planview. The Launch of the Main Growth Initiative which was earlier FedEx flight arrival in Jakarta , Indonesia was launched on Oct 29th . Hiring for the manpower had been done gradually in order to support the launch . Meanwhile the automation for CP match and HS code match has been replaced with other solution | I: L4 | Cancelled | L4 | 2024-07-22 | 2025-01-01
Business w/ Tech Initiative: [APAC] Medtronic Automation | 88278 | 7270 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Barbara Lim, Hardiansjah Rizal Kristanto | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads Since there are no financials associated with this initiative and the work is already completed, we will cancel the initiative 1 Oct 2025: might need to bring this initiative back again to do further automation for Medtronic | E: L2 | Cancelled | L2 Feedback Requested | 2024-07-22 | 2025-04-01
Business Only Initiative: [APAC] CN YRD miniGW Clr Cost Optimization | 84046 | 7713 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | George Weng, Qi-Feng Huang | On Track | No re-baseline is needed(updated on 4 Apr. 2025). Now all of aligned actions have been stablizing to implement to achieve the designed target of $4k/month as the savings. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-29 | 2024-11-29
Business Only Initiative: APAC_SWIFT for Clearance | 55995 | 7812 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Hugh He, Shan Shan Li | On Track | GREEN | K: L5 | Completed | L5 | 2023-10-02 | 2024-05-31
Business Only Initiative: [APAC] SG TNT Clearance by ACCS | 56017 | 8053 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Terry Cheung | On Track | 4/9/2026 Mar actual updated 6/13/25 June actual financial updated 5/6/25 Updated FY25 baseline value in Strategy detail tab 4/5/25 Rebaseline completed on Friday, 4/5/25 Initiative fully launched - vendor contract terminated on 4/1/25, saving started by April2025 Updated initiative owner due to personnel change | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-04-01
Business Only Initiative: [APAC][ASPIRE]PerformCustomscClearanceSenai instea | 73549 | 8202 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Yong Wee Chin, Kheng-Tek Lee | On Track | 10 June 2025 Volume increase y-o-y Up to April 2025 Revenue +19.8% pkg +20.40% ship +11.7% billed weight +52.9% Cost savings reduced due to more truck activation April 5th Update : No values for this initiatives; therefore no re-baseline is needed. POCONO Go Live on 29th October 2024 1) 1st 2 weeks of the implementation , 29th October to 10 November 2024 Heightened Scrutiny of Inbound Goods by Customs: Customs in Senai initially increased scrutiny on inbound goods as part of their risk profile assessment. Action taken : A productive call to State Deputy Director of Customs , Tuan Sharuddin to feedback on the delay resulting in the act of additional scrutiny was discontinued on 7th Nov 24 2) Limited Customs Operating Hours in Senai: Customs in Senai operates between 7:00 AM and 10:00 PM, with 2 officers operate daily, and only 1 officer work on Friday, official weekend of Johor. Inbound truck from SIN scheduled arriving at JHBIP latest by 12pm, hence “golden window” to catch pre-arrival clearance is between 7am to 11am but initially was not fully utilized, leading to low pre-clearance volumes. Additionally, poor coordination and staffing further hindered efforts to expedite the process, resulting in increased backlogs and delayed clearances uring the first 2 weeks post launch. Action taken : "Discussion held with Customs on 13th Nov 24 led by SM/IO resulted in better alignment and understanding of process between Senai Customs and FedEx . a) Ensure tasks critical to customs operations (e.g., finalizing paperwork, submitting forms) are completed before 7:00 AM to fully utilize the customs ""golden window"" from 7:00 AM to 11:00 AM. b) Adjust declarant and runner schedules to provide overlap during high-volume periods. c). Batching of paperworks according to the assessment types ie SG inbound, LMW, LV, non-duty(ND), dutiable, C8 and OGA, while only ND and dutiable will be batched according to 25 jobs per submission" 3)Lack of Monitoring Mechanism for Customs Clearance Data Flow •Challenge: Disruptions in the ACCS and ALDEC data flow between KLIA and JHB teams led to confusion and duplicated efforts. •Resolution: a)The introduction of a shared file to track progress and enforcement of scan codes discipline between KUL and JHB team ensured seamless traceability and reduced redundancies. b)Review and restructure work shift schedule for clearance team customs form preparation, printing, and submission, ensuring seamless handovers between shifts and set specific cut-off times for form transferring between station and gateway. c)Clear segregation of roles for customs runners in Senai on customs K1 assessment and OGA, cut down waiting time and ensured accountability . d)Enforce monitoring mechanism to cut down incidents of K1 wrongly cleared under W20 e) Close engagment with the ACCS to speed up the changes to reflect the 'Entry No' and 'Entry Status' in the ACCS instead of waiting for phase 2. 4) Reflow of the IE shipments to CAN-KUL from 11 Nov to 24 Nov to ease the backlog at JHBIP. On 25th Nov resume the IE shipments to CAN-SIN after the clearing the backlog. 5) Company wide Restructuring exercise impacting Johor Operations on 19 Nov 2024 resulted in Clearance Manager position being vacated where workloads of clearance been redistributed to the remaining 2 station manager. Immediate measures take to ensure speedy transition of clearance knowledge and loads, while maintain the momentum of the Pocono project rollout, at the same time reinforcing morale and team work within Johor. 6) Delay in IT network set up due to external factor led to most of inbound process within JHBIP have to resort to manual handling. IT network only fully set up on Dec 6. 10 Dec - update pending items 1) The warehouse scanning module expected to be fully completed by 12/31 2) IE EU shipments still flowing to KUL instead of SIN. NPI team already secure the CLH space from EU to KUL till end of March 2025. Impa | K: L5 | Completed | TEMP L5 - Enter L5 | 2024-08-01 | 2025-04-30
Business Only Initiative: APAC CCCO – MSD Mini Clr Location Clr cost | 90351 | 9227 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jack Xu, Amelia Wang | On Track | milestones had been fully implemented with health by Apr 11.2025. | K: L5 | Completed | L5 | 2024-07-01 | 2024-08-30
Business w/ Tech Initiative: SCN Warehouse management system with RFID |  | 91193 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Alan Liao | On Track | 25/32026：with conclusion from portfolio business architect team that the inititiative doesn't have need to develop global system, should not be used demand type "Biz w/ tech", instead, recommend to change the demand type to "Local Enhancement". as the initiative is in L2, cannot change the demand type directly, a new PV request has to be created while cancell this PV request. 2/4/2026: Aligned on technology approach with Jeremy Gettman (MEM Cage RFID project). Requires Okta + no additional development. Jim Franklin reaching out to Platform on direction which could result in reclassification to local demand. 04/10/2025: On Track | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: [APAC] Develop & Deploy Physical Handling in APAC |  | 92172 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | King-To Chin (Thompson) | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads - FY26 rebaseline activity completed on Wed 3/26/25 - As this initiative is classified as "Stop Work" due to high effort low value from US DRIVE team, we have put this as an Epic of GEMINI now. So, this initiative will be on hold until further decision from APAC Management. 07/18/25 | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: APAC Process Evolution for Cage Handling | 32773 | 6935 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | In-Woo Ha, Matthew Au | On Track | 08/09/25 MTP is on hold no IT owner who can raise the ticket to APAC HCH for MTP. 08/08/2025 Updated the 3months' estimated actual saving (USD 3,250/month = USD130/day x 25day/month). 5.73hr/day saving from reducing ppwk printing time (incl. traveling time btw office and warehouse). USD130/day saving = (5.73hr/day x USD22.5/hr)+USD1/day paper saving. 07/03/2025 under usage in actual operation. at the same time, the team will move to MDM production (currently the solution is operating under MDM UAT environment) 2025-05-21 offically launched the solution in live operation at IB freight cage first and it will expand to all IB cage handling in phase. 2025-05-16 Found an error at the server during the latest test, considering additional testing and error resolution, we defer the implementation by 1week. 2025-05-07 plan to use the tool with current available network connection from May 19th. 2025-05-02 proceeding legal review (working with Dave Brown) for MDM production use. 2025-04-25 okta connection and MDM set up are still on-going. there are several on-going trials with tests and fails and re-checking of the guildance. 2025-04-11 under resolution of NULL WiFi connection issue and Okta connection. but not clear guide who we need to contact and what to do. 2025-04-07 No values for this initiative; therefore no re-baseline is needed | K: L5 | Completed | L5 | 2023-12-01 | 2025-05-23
Business w/ Tech Initiative: [APAC] Clearance Intelligent Automation (AIML) | 35867 | 7008 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Yee Yong Tan, Lorida Bejleri, Hardiansjah Rizal Kristanto, Koushik Das | On Track | Overall go-live status * CP Match is live and in BAU support model for all countries (expect AU), as per plan. * JP, KR, TW HS Code and DAC are live and in BAU support model, as per plan * AU HS Code and DAC MTP on 16 Sep 2025. CP Match still pending MTP. * CN HS Code and DAC are live and in hypercare 29/10/2025 * AU HS Code and DAC MTP on 16 Sep 2025. Currently in hypercare. CP matching planning for MTP in 2 weeks' time. * CN Class D OCR in UAT. Timeline for MTP TBD 01/07/2025 update * CN DAC live * AU ACCS fixes are still pending and undergoing UAT. Timeline for MTP is still TBD 17/06/2025 update * AU ACCS fixes are still pending and undergoing UAT. Timeline for MTP is still TBD * CN business go-live is scheduled for 23 June * Business value for JP, KR, and TW HS Code and DAC remains 0. ACCS UI fixes have been developed and launched for JP, are under development for TW, and are under requirement gathering for KR. 16/05/2025 update * AU UI fixes are planned for full MTP by 29 May * No update from ICE on CN go-live date. IDP milestone has been pushed back for a month with no concrete / confirmed new date. * Business value for JP and KR for HS Code and DAC is confirmed to be 0 due to various OCR inaccuracy and ACCS UI issues. UI fixes have been identified and are being worked on / prioritised by local GTS and ACCS IT teams. 02/05/2025 update * AU UI has been fixed and deployed to incognito users, pending confirmation from Ops for full-MTP * No update from ICE on CN go-live date 25/04/2025 update * Money-step pushed to end-May / indefinite, due to not set date from ICE team regarding CN go-live 18/04/2025 update * No new updates 11/04/2025 update * Updated the actuals since Jan 2024 with the results of GTS' timestudy, which is confirmed by Ops. Previous actuals had been assumptions made on the planned savings, which had not been approved by Ops. The difference between the timestudy and the assumptions are due to (1) delays in launch, (2) pre-existing automation not accounted for in initial calculations, (3) lower time saving per shipment than anticipated. * Went live for TW HS Code and DAC * Announced move to BAU Support for other existing capabilities, starting 21 April * Pending confirmation from ICE on TW and AU volume handling for this week + CN volume / go-live for next week -> potential extra delays / complaints from Ops, might need support escalating as ICE team is not communicating with us 04/04/2025 update * Rebaseline is complete * CP Match is live and BAU for all countries expect AU, as per plan. * CP Match value was confirmed by Ops (with support of GTS time study) and added to Planview for FY25 * Negative variance due to (1) delays in launch, (2) pre-existing automation not accounted for in initial calculations, (3) lower time saving per shipment than anticipated * JP, KR, and TW DAC and HS Code are live and in hypercare, as per plan. No major feedback from Ops * AU DAC and HS Code is live in the backend but pending code fixes for the front end. * CN DAC and HS Code is on track to launch next week, pending ICE confirmation | K: L5 | Completed | TEMP L5 - Enter L5 | 2023-09-15 | 2025-07-24
Business Only Initiative: [AMEA] APAC - Expediting automation of Clearance c | 93759 | 6983 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Cong Fairy Liu, Lance Tam | On Track | 09Apr2026 - Mar actuals updated 05Mar2026 - Feb actuals updated 09Feb2026 - Jan actuals updated 13Jan2026 - Dec actuals updated 09Dec2025 - Nov actuals updated 10Nov2025 - Oct actuals updated 10Oct2025 - Sep actuals updated 09Sep2025 - Aug actuals updated 08Aug2025 - Jul actuals updated 09Jul2025 - Jun actuals updated 06Jun2025 - May actuals updated 17May2025 - May forecasts reviewd 14May2025 - Apr actuals updated 15Apr 2025 - Mar actuals updated 11 Apr 2025 - Implementation on track 25 Mar 2025 - FY26 rebaseline activity completed | K: L5 | Active | TEMP L5 - Enter L5 | 2024-01-01 | 2025-09-30
Business w/ Tech Initiative: WS1 - [1A] Keep clearance and sort instructions Sy | 82584 | 6780 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Gianna Abello, Maria sim | On Track | 23.04.2026 Dependent on Dataflow to Sort to complete first. Still required. Entered in with Wave and requires re-evaluation for potential Platform impact and movement to EU Sort. That decision will be based on lessons learned from Dataflow to Sort work/dependency. Value Benefit/Driver is to ensure timely and correct communcation between clearance systems and sort. Alban Dalberto Clearance SME. Marine Lampaert Sort SME. Jun23'25:Change to onHold discussed with Architects -Dataflow to Sort solution design and 82584 Reliable Intercepts solution design will be kept separate -Dataflow to Sort solution design document will have separate section or chapter listing down topics that are out of scope, such as the issues on toggling intercept state, invalid status/out of sync with source system, missed messages (due to lost in transport, incomplete/invalid, gets discarded, lost in application) -the taskforce that @Maria is building will decide which initiatives/topics to be looked into next, after Dataflow to Sort is live in all locations -Dataflow to Sort should be live and will need feedback from taskforce, before 82584 can start any solutioning sessions. For now 82584 remains on hold Apr/7:this one is an enabler with no recurring costs so no base lining required prior updates: Changed status to on track, awaiting results of new Data Flow initiative which will determine way forward/next steps for 82584 initiative. Issues identified that prevent business validation testing. new timelines approx midMay go live vs midMarch. Request for resources and confirmation of approach raised to sponsor | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-08-19 | 2026-03-23
Business Only Initiative: [IN] [Cost] Inhouse Regulated Screening (BLR) |  | 87584 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Sunil K P, Sudhir Rana, Shrikant Nikam | On Track | FY 26- no rebase line needed as completely driven by capacity-Ex BLR on NB( Indigo Freighter) &CLH. | K: L5 | Completed | L5 | 2024-07-22 | 2025-02-28
Business Only Initiative: In-house Exp & Imp Clearance from Cargo to Courier |  | 87576 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Subodh Randive, Shrikant Nikam | On Track | On Track: 10/04/26 - All the below 3 initiatives: 1. CEC Clearance through FedEx Express terminal. 3. IPHV self Clearance from Express facility. 3. Increase R.B.E Clearances. are being overachieved. Against a forecasted amount of USD 800,923 we have achieved USD 10,93,479 (from June'25 to Mar'26). This is primarily as all the initiatives are Volumes based, there have been good incremental volumes / tonnage and more than projected shipments are being cleared through RBE and additional tonnage being handed over to CLH airlines resulting in Savings / overachievement. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-15 | 2025-05-30
Business w/ Tech Initiative: [IN][Enablers]Reimagine the import clearance proce | 36315 | 7172 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Vishal Rastogi, Abhishek Shetty | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads Spoke to Finance "No values for this initiative; therefore no re-baseline is needed." All Key milestones are completed. MVP1 is rolled out for RPA Phase 2 in Feb'25 | I: L4 | Cancelled | L4 | 2022-09-01 | 2025-05-30
Business Only Initiative: [MEA] [RT] Clearance Digital Transformation | 91628 | 7661 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Melissa Pinto, Jignesh Joshi | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads On track Money Step Updated | H: SL4 | Cancelled | SL4 Finance Domain Lead Approval | 2023-05-01 | 2027-04-09
Business Only Initiative: MEA Clearance IT Spend Reduction |  | 91335 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jignesh Joshi, Melissa Pinto | On Track | On Track. Initiative has been aligned and approved by our management to be logged in PV as cost avoidance. Achieved in FY25 and Closed please assist to close as not applicable in FY26.Submitted for cancel | E: L2 | Cancelled | L2 Feedback Requested | 2024-07-19 | 2024-07-19
Business Only Initiative: [APAC]Big Mac for TW IB X3/X4 Entry Build with OCR |  | 106789 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jim Jiang | On Track | 1/23/2026 MTD adoption rate 35.22%, keep on track and meet the goal. Review and align with ops on the FTE saving calculation. Initiative runs with expected outcomes, submit to L5. 1/8/2026 Dec,2025 adoption rate 40.84%, saving $3781, beat the target and updated actuals in Financial Plan already. 12/26/2025 MTD adoption rate 40.66%, keep on track and meet the goal. 12/5/2025 Nov adoption rate 37.07%, saving $3781, beat the target and updated actuals in Financial Plan already. 11/20/2025 MTD adoption rate 36.37%, keep on track and meet the goal. 11/6/2025 Oct adoption rate 34%, saving $3781, beat the target and updated actuals in Financial Plan already. 10/24/2025 MTD adoption rate 34.22%, keep on track and meet the goal. 10/10/2025 Update acutal performace(47% adoption rate) and saving($3781). 9/30/2025 adoption rate 47.26%, keep on track and meet the goal. submit to L4. 9/25/2025 adoption rate 47.26%, keep on track and meet the goal. 9/18/2025 the notificaiton is not stable, need further work on the NDS process to make sure the notificaiton send to the audiences timly, current the adoption rate is s47.81%. 9/4/2025 The digitial solution is running smoothly, current the adoption rate is 30%. continue enhance on process stable and timely notification to imporve the adoption rate. 5/23/2025 the L1 Net Recurring Benefits ($, annualized)-P&L/Hard is locked when I revise the number last time, however, it's available now and the benefits number has been moved to the P&L/Hard item. the target value is calculated by incrementally saving vFTE in FY26(39707 is base on 9 months), but the recurring benefit could be annual saving by total 4 vFTE( 90760) from FY27. 5/21/2025, regrading to the question does the scope of this work require any IT development? Just want to confirm it is a Business Only initiative. it's not require any IT development or system change. coordinate and generate new ops process base on current available applications. Discussed with ops owner, aligned the estimating aving of BigMac and the timeline of the plan. | K: L5 | Active | L5 | 2024-11-14
Business w/ Tech Initiative: Trade and Tariff Impact Analysis Tool |  | 107528 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | David Spradlin, Macie Walters | On Track | 04/07/26 VB1 UAT phase completed 3/23/26. Scope expanded to a second value bundle and L4 date moved to Sep 30th, 2026 01/13/26 UAT phase extended to March 27, 2026 12/23/25 Currently in the UAT phase 07/17/25 Next steps are complete PPM, Epic, D&A Portfolio Greenlight, enter portfolio implementation costs before moving to L3. Progress is being made for now. 05/06/25 Submitted SL2 04/18/25 Submitting L1 LBC to move along L gates | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-26 | 2026-09-30
Business w/ Tech Initiative: [MEISA] SA clearance & sort transition with automa |  | 107540 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Abhilakash Mahajan | On Track | 11/18/25: - Progress made: Completed: Soultion is deployed in KSA. Actuals for financials were updated for the month of September and October 25. Key wins: All the milestones are on track. Blokers & Risks: No risks and blokers | K: L5 | Active | L5 | 2025-07-22 | 2025-12-26
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-MISArchive Deprecation |  | 107546 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | David Schlitt, Amanda Nevins, Vincent J. Romeo | On Track | 1.20.26 Per Adam Smith (Enterprise VP): The parent Planview #98380 (TS-VL3-EIW Retirement) has been cancelled and all initiatives under this parent have been cancelled. 1.7.26 Per Amanda Nevins: The parent Planview #98380 (TS-VL3-EIW Retirement) is currently on hold. We as the EIW platform owner organization, EDA, have been moved back to FEC and the decision to retire the platform is under strategic review. As a result, this Planview request and all associated enablers, like PV#107546, might need to be reviewed after a decision has been made. We expect communication regarding a final decision within the next two weeks. 8.14.25 - Dependency has been added and financial items were added. Submitting to L2. Still unable to add dependency initiatitve due to planview for this enabler. Planview #98380 TS-VL3-EIW Retirement Got feedback from Finance and was given the green light to move forward with current figures provided. All other feedback items have been addressed. 8.5.25 Updated description with summary of major milestones and steps for completion of the initiative. 7.22.25 Unable to add dependency initiatitve due to planview admin restrictions for this enabler. Planview #98380 TS-VL3-EIW Retirement 7.22.25 initiative is to deprecate the Teradata platform and this effort will not generate any revenue nor cost savings as we move from old technology to newer. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Downstream auto- population of clearance systems |  | 108369 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Robert Heatley | On Track | No longer required. Thank you. | C: L1 | Cancelled | L1
Business Only Initiative: [APAC] SG Clearance System Simplification |  | 93413 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Terry Cheung | On Track | 4/9/2026 Mar actual updated 11/17/2025 submitted to SL4 11/4/25 Updated Oct actual, milestone and KPI 7/8/25 June actual updated 5/18/25 Submitted SL3 review 4/18/25 submitted initiative to L2 but reject as architect request for 'ability to' statement, however this project is about discommissioning a IT system so there is no IT development or feature required, raised ticket INC030327596 request to change this from business w/ tech to business only per US project team advice, also requested to change this initiative from confidential to non-confidential as the reason for keeping confidential is becox it involve reducing 20+ OSV, now the initiative already launched and reduction has began so no necessary to keep confidential 3/31/25 Rebaseline activitiy completed on Friday, 3/28/25 Initiative fully launched - SG G1 confirmed discommission by 01April2025, all operation has already swiched back to ACCS starting 01March2025. IT has started release 12 OSV in March, release 7 more (total release 19) in April, the last 2 OSV stay till May so eventually all 21 OSV will be released by June2025, total saving till end of FY26 Q3 (March2026) shall be USD1.5M | K: L5 | Active | TEMP L5 - Enter L5 | 2025-02-03 | 2025-03-31
Business w/ Tech Initiative: Opportunities for RPA implementation in EU [ECTS] |  | 109586 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jonathan Pertzborn, Aleksandra Woch | On Track | 03/06/2026 Alignment with APAC on track - Next steps: IO to align with Country Representatives and arrange Shadowing Sessions to initiate Genius mapping flow Such was agreed due to the need to add more Genius countries to the flow. Alignment with P&E still undergoing. An Excel has been created with the Savings estimation. P&E to provide by end of March the final calculations. 01/29/2026 : Alignment undergoing with APAC, with focus on top 2 initiatives mentioned below, Meeting scheduled for the 30th of January to go over recent developments and necessary adjustments in the future project. Both processes are mapped and being currently subjected to review from Users and Specialists. To push forward to L2 - we are pending P&E Support with Savings Calculations. Savings Calculator was shared, and process is being mapped and timed. Next Update Meeting on the 4th of February 01/05/2026 : Alignment undergoing with APAC, with focus on top 2 initiatives: - Customer Profile Bot Development; - CP Maintenance Bot Development; Both processes are mapped and being currently subjected to review from Users and Specialists. To push forward to L2 - we are pending P&E Support with Savings Calculations. Savings Calculator was shared, and process is being mapped and timed. Next Update Meeting on the 4th of February | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: GCSI Global Clearance Screening & Intercept (GCSI) |  | 110056 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Rohini N. Kala, Jonathan P. Talley | On Track | 04.02.26 - Add the individual bundles to the parent initiative of 110056 02.18.26 - Added the cost savings 01.26.26 - Team working on Soft Benefits to be added 12.15.25 - Bundle B, Inventory Control presented to the triage and received approval to move forward 12.02.25 - Worked with the regional team members to capture the AB2s and the preferred future state requitements for all four bundles. For Bundle B, Inventory Control, team is working on prioritizing into categories. Ready to be submitted to triage. 10.10.25 - For bundle B, Inventrol Control, team to work with the regions to review and revise the AB2s. Once complete, move the initiative to L1. 8.29.25 - For Inventory Control - Successfully completed PFS sessions with the Enterprise enablement team. Awaiting approval on updated Global Cage PFS & AB2 from the leadership. Have to schedule PFS sessions for the remaining bundles. The financials will be updated post PFS workshop to align the four bundles associated with this parent initiative. 7.18.25 - The GCSI initiative is broken down into four key bundles and team has been actively working with the Enterprise Architecture Team to schedule workshops and ensure alignment with other ongoing initiatives across the organization. We have conducted a workshop on 7/15 to define the prefrerred future state (PFS) for **Bundle B - Inventory Control (0006450)** and shared the outcomes of the ability to statements with the leadership. We now need support with scheduling the PFS workshops for the remaining bundles. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: ZA Clearance process RPA automation |  | 113169 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Bianca Theresa McGee, Mamotsumi Makhutle, Laxmi Sravanthi Bhagavatula | On Track | 17/04/2026 - EAI # 3531027 Value bundle expected to be added to LAC value bundle 3/10/2026 - uploaded updated commercial & sco financials 2/27/2026 - Renamed epic, added L2 architectural document. 2/11/2026 - Added EPIC,followed up with SCO team for greenlight review schedule/date and it's currently pending solution alignment from Clearance. Once solution alignment is verified it will be presented at PEL for awareness prior to EGC. 2/09/2026 - Reviewed with Pod PM team. Need to Add EPIC for business with tech work. Submitted Greenlight form. Commercial is awaiting SCO PEO review. 3 December 2025 - Process design document completed | E: L2 | Active | L2 Feedback Requested | 2026-01-05 | 2026-06-29
Business w/ Tech Initiative: PFS BSO Shipment Handling |  | 113354 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | 12/23/25 - GEMINI porgram has been cancelled. 08/15/25 Pending businss architects to begin developing businss case and identify soft savings opportunities. 08/08/25 Pending businss architects to begin developing businss case and identify soft savings opportunities. 08/01/25 Pending businss architects to begin developing businss case and identify soft savings opportunities. 07/25/25 Pending businss architects to begin developing businss case and identify soft savings opportunities. 07/16/25 LP - This initiative is in L1 and business case has not been drafted nor vetted by Finance. It is TOO EARLY for any finance forecast info to be input. In order to make this status rationale update, NRB figures had to be entered and domain leads advised to input $1 as a placeholder. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Intl Soln Wrhse Autom & Mgmt (iSWAM)-Value Bund 2 |  | 113593 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Julian Albritton | On Track | PV# 113593 can be cancelled as it's going to be handled with another initiative - PV# 110056 - Global Clearance Screening & Intercept (GCSI). | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FXL Transformation Brokerage |  | 114172 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Pieter Kop | Some Issues | Update: 13 April 2026 **USA deployment** Planning next deployment phases 2, 3 and 4 (2: clearance none FXL Transportation transactions; 3: Southern Border US/MX; 4: Northern Border US/CA) signed off by Leadership. Plan presented estimates completion US Conventional Brokerage organization will be fully transitioned to CW by July 2027 Recruition resources supporting the deployment plan is work in prgress Phase 1, pilot completed. **Canada Deployment - Go Live 7/1/2026** Risk: DN/SOA indegestion approved by Infosec, Wisetech (provider CargoWise) to start IT development, we are waiting for expected delivery time to understand whther Go Live on July 1, 2026 is realistic | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2028-05-31
Business w/ Tech Initiative: FXL digital product and services development |  | 114176 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Debbie Chatzistergioglou, Pieter Kop | On Track | April 9, 2026 Highlights: 1. FXL Portal - Aerospace- FACE - MVP - In Deployment 2. FXL Portal - Aerospace - FACE - Quote Dashboard - In Deployment Current Status: 1. FXL Portal - US Brokerage - Entry Verification - in Execution 2. FXL Portal - US Brokerage - ISF - In Execution 3. FXL Portal - CA Brokerage Data - In Planning 4. FXL Portal - CA Brokerage - Operational Reports - In Planning 5. FXL Portal - CA Brokerage Manifest Tool - In Planning 6. FXL Portal - Aerospace- FACE - MVP - In Deployment 7. FXL Portal - Aerospace - FACE - Quote Dashboard - In Deployment 8. FXL Portal - Aerospace - FACE - Admin - In Planning 9. FXL Portal - eBooking - released to production, beginning Pilot rollout 10. FXL Portal - Insights - Transit Time - In Pilot 11. FXL Portal - Insights - On Time Performance - In Pilot 12. FXL Portal - Billing Center - In Planning To Be Planned: 1. FXL Portal - Insight - Cost and Spend 2. FXL Portal - Insights - Brokerage 3. FXL Portal - Insights - Reporting 4. FXL Portal - Sustainability 5. FXL Portal - Insights & Analytics 6. FXL Portal - eMaps 7. FXL Portal - FMC Tariff 8. FXL Portal - Retire myGTD 9. FXL Portal - Billing - Online Payments 10. FXL POrtal - Billing - Disputes & Claims 11. FXL Portal - Online Rates & Quotes 12. FXL Portal - API Developer Portal 13. Process Automation (Document Digitization, Entry Creation) 14. VAS - Order Mgt & Lead Logistics Solutions 15. FXL e-Commerce HVLV scan app 16. Retire myGTD March 20, 2026 Highlights: Entry Verification – Finalizing the wireframe conept. eBooking – eBooking Feature demo provided to APAC and EU leadership teams. FXL Portal - Billing Center [invoices, statements] – Proj Charter was aligned on Febr 26. Current Status: 1. FXL Portal - US Brokerage - Entry Verification - in Design phase. 2. FXL Portal - US Brokerage - ISF - is in the Development phase. 3. FXL Portal - CA Brokerage Data in Progress 4. FXL Portal - CA Brokerage - Operational Reports - In requirements phase 5. FXL Portal - CA Brokerage Manifest Tool - In Design phase. 6. FXL Portal - Aerospace- FACE - MVP - Released to Production 7. FXL Portal - Aerospace - FACE - Quote Dashboard - In Development Phase 8. FXL Portal - Aerospace - FACE - Admin - In requirements phase 9. FXL Portal - eBooking - released to production, beginning Pilot rollout 10. FXL Portal - Insights - Transit Time - In Pilot 11. FXL Portal - Insights - On Time Performance - In Pilot 12. FXL Portal - Billing Center - Invoice Statements To Be Planned: 1. FXL Portal - Insight - Cost and Spend 2. FXL Portal - Insights - Brokerage 3. FXL Portal - Insights - Reporting 4. FXL Portal - Sustainability 5. FXL Portal - Insights & Analytics 6. FXL Portal - eMaps 7. FXL Portal - FMC Tariff 8. FXL Portal - Retire myGTD 9. FXL Portal - Billing - Online Payments 10. FXL POrtal - Billing - Disputes & Claims 11. FXL Portal - Online Rates & Quotes 12. FXL Portal - API Developer Portal 13. Process Automation (Document Digitization, Entry Creation) 14. VAS - Order Mgt & Lead Logistics Solutions 15. FXL e-Commerce HVLV scan app 16. Retire myGTD March 4, 2026 1. FXL Portal - US Brokerage - Entry Verification - in Design phase. 2. FXL Portal - US Brokerage - ISF - is in the Development phase. 3. FXL Portal - CA Brokerage Data in Progress 4. FXL Portal - CA Brokerage - Operational Reports - In requirements phase 5. FXL Portal - CA Brokerage Manifest Tool - In Design phase. 6. FXL Portal - Aerospace- FACE - MVP - Released to Production 7. FXL Portal - Aerospace - FACE - Quote Dashboard - In Development Phase 8. FXL Portal - Aerospace - FACE - Admin - In requirements phase 9. FXL Portal - eBooking - released to production, beginning Pilot rollout 10. FXL Portal - Insights - Transit Time - In Pilot 11. FXL Portal - Insights - On Time Performance - In Pilot To Be Planned: 1. FXL Portal - Insight - Cost and Spend 2. FXL Portal - Insights - Brokerage 3. FXL Portal - Insights - Reporting 4. FXL Portal | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2026-12-31
Business w/ Tech Initiative: FXL Finance Transformation |  | 114179 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Pieter Kop | On Track | Project started in 2022 Billtrust system implemented for USA (Transportation), USA Brokerage and Canada Transportaion & Brokerage will implment as well. Integrations with FCF in place (MDM) | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: FXL reporting, analytics, performance management |  | 114182 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Pieter Kop, Arthur Nolte | Some Issues | 1/4/2026 Need to delay start this initiative due lack of availability resources due to competing initiative 9195. Resources will be transferred from other team to support this initiative. Start initiative planned for May 3, 2026. 3/19/2026 Waiting for acceptance to L3 stage 1/12/2026: Per discussion with Pieter Kop today, data already exists within Atlas. No additional development for Data & AI expected. Global Clearance ARTs are not impacted. FXL CX team will work, Suresh Kotta. Going through Global Clearance Domain because Lisa Lisson and Kewal's predecessor (Doug Belding aligned), to add to brokerage Global Clearance Domain. Request is for internal performance reporting supported by Karen Stendardi's development team. 12/01/2025: Scope for this initiave validated and aligned with IT for effort (to read: T-Shirt size: S. Greenlight approval request expected soon. | G: L3 | Active | L3 | 2026-05-04 | 2027-06-02
Business w/ Tech Initiative: China Gateway Threshold Project |  | 131603 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Shao Wei Cui, Peng-Chao Wang | On Track | L1 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: AS/RS in MEMH East Cage #7584 | 93037 | 7584 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jonathan P. Talley, Rohini N. Kala, Jamie Johnson | On Track | 04.20.26 - All remaining software requirements were submitted to FedEx on 04.14. Of the 19 files that needs FOSS approval, 3 files have already been approved. The goal is to get approvals for the remaining files by 05.01. Honeywell's deployment of its server should started shortly thereafter. 04.13.26 - Team has developed milestones and roadmap to finish the project with a go live date on 7/24/26. Immediate goal is to ensure that all open source software requirements have been submitted. Currently, there are six software going through the FOSS approval process. HW has committed to delivering all other software needs by Wednesday, 4/15/26. 04.03.26 - While the HW software installation is stalled, there has been some developments: 1) Kubernetes 1.35.3 has been approved by InfoSec with one critical vulnerability. The team is evaluating the vulnerabilty conditions set forth by the InfoSec team. 2) InfoSec had previously recommended the use of Docker 2.2.1. Team is currently trying to get the software files loaded into InfoSec's scanning site (doesn't accept rpm files at the moment). With the team finally settled on more recent versions of the core software required (Kubernetes, Docker, and RHEL 9.7), the team will push to get all remaining software (that results from the core software) submitted and approved next week. 03.27.26 - Started daily touchpoints with Honeywell team to resolve software issues. 03.26.26 - Changed the Money Step to 07.27.26, due to ongoing hurdles with InfoSec issues. Honeywell is working to find a solution. We had a meeting with Honeywell today and HW has noted that they will internally convene to come up with a soluation. 03/02.26 - Discussion on going regarding the best combination of RHEL, Kubernetes, and Containerd for both Honyewell and FedEx InfoSec. So far, here are the facts below: **Reviewed** RHEL 8 or 9 = FedEx approved Kubernetes 1.32 = FedEx approved Containerd v 2.2.1 = Recommended by InfoSec due to less vulnerabilities, final approval pending **Not yet reviewed** Kubernetes v 1.31.4 **Many vulnerabilities** Containerd 1.6.28 Containerd 1.7.24 02.20.26 - Honeywell has responded with their required versions of Kubernetes and Containerd software. Majid Ali has submitted those versions back to FedEx InfoSec to run their scans in an effort to get FOSS approval. 02.06.26 - Updates going to leadership every two days. Concerning Containerd, InfoSec noted that a newer version of containerd would be better since it has less vulnerabilities. Question went out to Honeywell if newer version is acceptable and they are still evaluating. 01.30.26 - Determination was made to proceed with Containerd as a substitute for Docker. A FOSS request was submitted on 1.29.26. Meetings will be held next week with FedEx Supply Chain FLARE team to dicuss "Day 2" Support. 01.23.26 - (1) Honeywell now asserting that Podman will not work from them as it cannot power a production Kubernetes cluster because it does not implement the Container Runtime Interface. Kubernetes requires a specialized runtime like containerd or CRI-O to handle automated orchestration at scale. As a result, another meeting has been set up for 01/27 with InfoSec, Honeywell, the EDGE Compute team, and other pertinent stakeholders to clarify how Podman (or another solution) can meet Honeywell's requirements. (2) Project leads met with Satya Proddaturi, who noted that FedEx Supply Chain FLARE IT team will be taking the IT ownership of this project. FLARE team will attend meeting on 01.27. 01.12.26 - Meeting held on 01.08 in which Honeywell confirmed that they require 3-4 weeks to replace the use of Docker (not approved by FedEx) with Podman. Once Podman is available, there may be a need for URL whitelisting for Podman, which may represent a few additional weeks. As a result, with UAT still pending, that puts an L4 date of approximatly the middle/late March. 01.02.26 - Meeting was held on 12.22 with Honeywell representatives, | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2026-07-24
Business Only Initiative: Custom Clearance & Brokerage (Mexico) |  | 132990 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Vaibhav Srivastava | On Track | 04/15/2026: There was a bit of delay in contract activation and FCF configuration. Business team is working on getting this done, and hence I am pushing the Money step date to next month. 01/29/2026: Contracts are being implemented and the savings is expected to begin in Feb 25'. 11/13/2025: Updated NRB, soft benefits, and milestones. 05/05/2025: RFP is being conducted to drive savings and efficiencies for Custom Clearance category in Mexico. Business stakeholders meet every other week to discuss the progress and to address any challenges. We should be able to finalize the anticipated savings by the end of Sep 25'. Savings will be realized when the new/amended contracts will be implemented which will be somewhere around Feb 26'. | G: L3 | Active | TEMP L3 - Enter L3 | 2026-02-16 | 2026-05-14
Business w/ Tech Initiative: LAC-BR-3-Csath-COLO-migr-plan |  | 132995 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Leticia Feitosa, Anselmo Comaru, Roger Cooley Jr. | Attention Needed | - 14april2026 - this project will be on hold until the end of this month, due to Competing priorities with infra team, who needs to support this initiative. -9Feb2026 - Uploaded the reccomended architecture template. -13Jan2026 - Reviewing architectural alignment . Pending final approval from EA to proceed to next phase. -04Nov2025 - Due to impact to Platform Portfolio for infrastructure, it was recommended to move this one from Local to Business with Tech. 4 applications impacted (PV 132995, 133002, 133006, 131844). On track - As discussed in team status meeting. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: LAC-BR-VCP-SOLUTIONS-COlo migration plan |  | 133002 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Leticia Feitosa, Anselmo Comaru, Roger Cooley Jr. | On Track | On trck - As discused in team status meeting. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: LAC-BR-ConsultaCS-CEP-COLO-migr-plan |  | 133006 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Anselmo Comaru, Roger Cooley Jr. | On Track | This demand is being considered at the Planview 131838 - LAC-BR-Clearance-apps-move from VCP to RECIFE DC. Can be cancelled. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Automation of SOIL process- AIIP |  | 136375 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Kanan Sood | On Track | date 07/18/25 : There is internal alignment on-going with IT on this project and based on the feedback , this will be changed to local enhancement and I will be raising a new request as local enhancement. Once the new request is accepted, I would be canceling this request. date 10/08/25. A new demand 0111543 was cleated so cancelling this PV id. As per the latest the new demand was vetted on 20th august and offline discussions are happening as recommended by global team. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Connection to EDM (Enterprise Document Management) |  | 143821 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Martin Goergel (Tinus) | On Track | 22.4.26 PPM 1837780 Architect is ooo this week>; tbc 2 KPI´s added; Epic & Milestone 1/26/2026: Pod PM/Lead reached out Dec23 with Jan09 reply that an update will occur the folllowing week. Reached out again on Jan20, response added Description (1/22/26 pro forma PPM No. 183xxx to be approved next week. Calculation of bad debt ongoing. Not ready for review and L3 just yet). EPR ranked 183. Has 65k of one-time soft benefit with a higher expected cost. Need financials to boost ranking and obtain L2 architecture support. 8/25/2025 Financial Calc. is being worked on tbd: owner: EDM, EDI, EIStC or Genesis team 7/24/2025 : For upload of clearance related files (CCORR & CLRI) into EIStC (EMEA Ship to Collect) we need automated connection to EDM. In Vendor countries there is no upload off paperwork, comercial invoices via the GENESIS scanner. Instead, uploads are done in sending images/pdf via email to EIStC. The result is that: all files (comercial invoice, export/import documents, customs response, billing files, etc) are shown in the same format and no easy identificaton is possible for brokers and billing. They need to open every attachment until they find the right one. We need direct connection to EDM. This will enable full visibility of file types for Clearance and Billing and enable semi-automation as well. Status: started in June 2025: Financial impact t/b evaluated with finance. Biz with Tech: additional inormation t/b gathered Enabler: EDM team, EA team | E: L2 | Active | L2 & CCH | 2027-01-15 | 2027-01-15
Business w/ Tech Initiative: Leverage earlier scans for IG clearance |  | 143824 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Nancy J. Wadding | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads 07/21 a.What assistance is needed to move forward to the next stage gate, are there any bottlenecks? Assistance with financial analysis is needed. b.The month you are expecting to have a financial value loaded in Planview? Dependent upon when financial analysis is provided, but I will estimate August. c.Are there enablers associated with this initiative? None that I know of, but that will be determined during architecture review. 8/29/2025 - This initiative is paused due to Tariff and deMinimis elimination and the support that is required from the Intl Engineering team members. 9/30/2025 - This initiative is still paused pending decisions that still need to be made regarding the future of the IG product. 10/15/2025 - This initiative is still paused pending decisions that still need to be made regarding the future of the IG product. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: ES outsourced data entry ACTIVATION |  | 153233 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Timothy P. Hartless, Pablo Sala | On Track | 02/10/2026 Imaging Solutions Team: Yes, this work is part of our current PI. Emile started working on to identify the requirements and expected to complete this by 20th Feb . We can target to come back with timelines and next steps, tentatively by 27th Feb. 01/14/2026 @Emile will be leading this from an imaging perspective and will aim to reach-out next week to engage with you and discuss next steps. @Sreenivasa will be the PM to coordinate build work, testing and delivery. Aiming to have ES completed in this 10 week sprint. Emile will confirm this once he has worked through the requirements and understood the technical approach. 8/6 - Pablo added as IO during Tim's holiday | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: GCCS rollout for KSA |  | 153969 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Abhilakash Mahajan | On Track | 4/08: The feedback from the EPM was addressed, waiting for movement to L3 2/10: Greenlight recieved from SCO PLE and work underway to get the same from Commercial PEL 9/11: The initiative is ARB approved and submitted for the greenlighing to the impacted portfolios 7/31:request has been approved by the Pod Lead – Stefanie Schwegman and This initiative has been dispatched and is now in L1, available for you in Planview. | E: L2 | Active | L2 Feedback Requested | 2026-01-12 | 2026-07-31
Business w/ Tech Initiative: Redirect ECI Data Flow from VISA to EDM |  | 156807 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Dora Silva | On Track | Raised request as LE | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [GW]APAC-China Project Own |  | 157203 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Shao Wei Cui | On Track | SL1 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: LAC GRSIS System Implementation |  | 157784 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jason Trimble | On Track | After considerable research and analysis, we have decided that we will not pursue this initiative as no significant cost savings were identified with the implementation of GRISIS in LAC. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Export and Exit - NL - Netherlands |  | 160525 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Alan C. Prunty | On Track | Should be Local enhancement, new request raised | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Export and Exit - IE |  | 160531 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Alan C. Prunty | On Track | Should be local Local Enhancement | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Operations Visibility to Bayan & ROD details |  | 160787 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Abhilakash Mahajan | On Track | 4/08: The in initiative was put on hold because GRACE feed being GEN0. IT has recommended to put it on hold untill this is chnahed to GEN2 8/27: Initiative was approved by triage 2/4: We have to put the initiative on hold because of the ongoing migration of Gen0/1 feed of the GRACE application. | E: L2 | On Hold | L2 Feedback Requested | 2026-01-01 | 2026-04-30
Business w/ Tech Initiative: Auto Broker Entry Capture |  | 161140 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Nancy J. Wadding, Jason Shatz | On Track | Initiative reassigned to Clearance domain. 3/2/2026 - The plan was for a third-party vendor to automate a manual process that they are currently performing for FedEx as part of a pilot test. Although they have only provided the cost to FedEx for a portion of the development effort, it was expected that the all-up dev cost would either exceed the savings or not yield enough savings to make it viable. In addition, International Ground volume has been on the decline due to Sales efforts in selling other products, which would further erode the savings opportunity. 1/14/2026 - International Engineering does not yet have enough information to make a decision on whether to give the vendor the approval to develop automation for the current manual process that they are performing. The vendor will have to provide an all up estimate for all of the development phases and IE has not yet received that. 12/8/2025 - Intl Engineering manaagement has not yet decided if the vendor will be given the greenlight to automate the manual process. A quarterly meeting with Surface Intl Engineering and the vendor is scheduled for Friday Dec. 12 during which automation will be reevaluated. 11/18/2025 - A meeting was held on 11/4 that included Valenta Nicholsyou, Claire Wilkonson, Jason Price, and Nancy Wadding. We explained that we are still in the pilot phase of the project, and our management has not yet decided if they are going to give the vendor the green light to develop the RPA automation. We said that we would continue with the pilot through November at a minimum and then our management would reevaluate. My notes state that if the decision is yes, then we will move forward with the Planview process, but that it should be a Local demand request. And if the decision is no or not at this time, I will cancel the request or put it on hold. 10/24/2025 - A meeting is scheduled for next Wed. 10/29 during which the vendor that is performing the manual process for the pilot test will present their results to date. In addiition, they will provide the FDX costs to date as compared with the estimated future costs if they automate the manual process. International Engineering management will then make a decision as to whether or not FDX will have the vendor move forward with development of the automated process. If yes, the future cost estimate will be used to develop the financials for the Planview request and I will reach out to David Spradlin for assistance with that. 9/30/2025 - Jason Shatz and I met with Enterprise Architect Kannan Kamarajan on 9/24. We indicated that this was entered as Business Only but changed by someone to Business with Tech. He said that he would schedule another call to include Alexander Ventura, Portfolio Program Mgmt Principal, to further discuss the appropriate demand type. That meeting has not yet been scheduled. 09/19/2025 - waiting on Clearance Domain PMO or lead to reach out for next steps. Need to resolve the Biz w/ tech demand given as original demand was business only since dev was being outsourced due to De Minimis Elimination. 09/08/2025 - Vendor began pilot with a single gateway shipments on 9/9. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: GRISIS Clearance Relabeling Reduction |  | 161532 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Azri-El I. Sellers, Dave Metelko | On Track | 01-21-26- Alternate solution currently under testing. Using the directional sort function on ring scanners in ANC primary allows for correct package routing without relabeing at the inputs. 10-31-25 - A.S. Completed QA review and submitted to L2. Added initiative owner | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: IN ACCS Clearance system Automation |  | 161663 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Shobin Varghese, Vishal Rastogi | On Track | 08/04/26- Engagement Data and AI team- Discussion on possible arch diagram recommendations, data sources and data flow between agents 18/03/26- Engagement with Data & AI team- Detailed discussion on framework for Agentic AI use case 12/02/26- Engagement with Data & AI team- Overview of the clearance framework Agentic AI use cases Enagagement with architecture team delayed, ranking at 114 | E: L2 | Active | L2 Feedback Requested | 2026-05-21 | 2027-11-30
Business w/ Tech Initiative: International Cage RFID Enabler |  | 162488 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jonathan P. Talley, Nathan Tonkinson | On Track | 04.20.26- (a) Seven additional Zebra fixed printers were moved to network mode on 04.15. There are now a total of 10 of 60 printers on the Third Floor that are RFID enabled and printing on the network. The plan it to install another 10 within the next week. By 4.29, we will make a decision on installing the remaining printers in one final batch. (b) Weekly meetings continue with Zebra and Xemelgo to discuss software solution for processing RFID data. 04.13.26 - (a) Three Zebra fixed printers were moved to network mode on 04.07. (b) A time study was conducted on 04.06, showing SWP scanning taking longer than 2 seconds per scan. Phillip Pettit is formalizing the findings. 04.03.26 - International Building is now open again. As a result, (a) time study is planned for Monday (04.06), (b) Zebra printers will be switched to network mode on Tuesday (04.07) and (c) on site visit from Zebra will be held on Tuesday (04.07). Ron Wiggins also confirmed his testing results of 95% accuracy of the RFID devices in the East Cage. 03.27.26 - (a) Once International Building is open again, fixed printers will be installed on the network. (b) Testing was conducted by Ron Wiggins in last week showing a 95% accuracy rate on RFID devices installed in East Cage. (c) Meeting held with Phillip Pettit to discuss plans to conduct time study. That time study is now planned for Wednesday, 4/1, pending approval from East Cage management. 03.02.26 - Testing seems to confirm that a configuration is only requred to enable fixed Zebra printer at MEMH. However, testing at the MEMH was blocked due to mercury spill at the International Building. Once spill is cleaned up, testing will resume. 02.20.26 - a) GRSIS IT team believes there is the possibility that the Zebra printer can connect on the network with only configuration changes and no code changes. IO will test the printers on the third floor on 02.24 to determine. b) Zebra was in town to test equipment in the East Cage and found the readers with a 99% accuracy rate. 3) Meeting has been set up for 02.24 to discuss how testing will be conducted going forward and to redo an East Cage time study that could increase the follow proposed by the initiative. 02.06.26 - Status remains the same as we wait for all printers and labels to get to offshore team. Plan is still to deploy code enabling fixed printer by end of February. 01.30.26 - Last's week update continues to hold other than the labels have been shipped to the overseas team. 01.23.26 - No real updates since last one. The code enabling the Zebra network printers will likely be deployed at the end of February. One fixed printer has arrived to our IT overseas team but they are still waiting for the rest of the fixed printers, the labels, and the mobile printers. Once the mobile printers arrive, the IT team will complete the remaining code fixes required to use the mobile printers. 01.12.26 - The mobile Zebra printer is now printing in the lab since 01.06.26. There are a number of code changes that are still required: 1) The pairing process does not currently mimic Operation's experience and 2) the templates have to be loaded directly into the printer instead of being loaded when the printer is paired. Also, one fixed printer without the labels has arrived to the overseas GRSIS IT team in India. 01.02.26- No updates since last one. The printers and labels have not been shipped to the overseas team and the new estimate is that that will take place some time in January. A Zebra representative will be onsite at the GRSIS lab on 01.06 to assist with pairing the mobile printer to GRSIS. Talks are ongoing regarding when the code enabling the fixed printer will be deployed. 12.15.25 - **Network Printers** - All regression testing passed, other printers are performing as expected with code change that enables the Zebra network printer. **Mobile Printers** - Zebra mobile printer still no pairing with GRSIS. IT team believes a code change is require | E: L2 | Active | L2
Business w/ Tech Initiative: K2 enhancement to support up to 5000HAWB per MAWB |  | 162491 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tsz-Ki Jacky Chin | On Track | 02/20/2026- Request has been moved to L2, working on additional input for L2 01/22/2026- Financials: •After the latest calculation from FP&A, the margin for this request came in negative Progress Made •Worked with FP&A and confirmed the margin is negative Blockers and Risks what is keeping the initiative from moving forward and steps taking to mitigate? The profitability calculation came back as negative 10/10- Updated required field to progress to L1 Triage 10/20- This is an enabler of initiative #12358 | E: L2 | Active | L2
Business w/ Tech Initiative: KR ACCS Export - InHouse Broker_Mass Upload Entry |  | 162547 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Dong-Sik Woo | On Track | 12/18/2025: CEW, worked with IO on call and discussed this project is tracking under APAC Ground inititiave 163253. IO to work with financial rep before canceling. 12/18/2025 requested IO at least place on Hold if more time is needed to make the decision to cancel. working through checklist to move to L2 01/08/2026 Dong-sik, Woo: I've communicated and aligned with KR CCO management, and I'd like to request the cancellation of PV# 162547. It will be included under PV# 163253 - KR Gateway Cost Saving (Business Only) after further review. 1) further analysis is needed for the hard benefit of 12.4M currently presented in PV# 162547, and we need to confirm how the actual cost-saving impact will be reflected within PV# 163253. 2) further Operation process alignment is required, as significant system changes may not be required. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: K2 Autopopulate Departure and Arrival Times |  | 167816 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Marcos Heredia, Todd C. Frazier, Patricia Affholter | On Track | 04/21/2026 Shane Bradley request per Todd Frazier. Delays can cause downline stoppage and reduced visibility until times are corrected. Includes pre-assignment, ULD loading and others. 02/12/26 Awaiting Architecture Review in order to finalize LBC for submission On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: APAC - Clearance Case Automation Tool Expansion |  | 170492 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Jun-Ya Ripple He | On Track | On Track | E: L2 | Active | L2 | 2026-08-28 | 2026-08-28
Business w/ Tech Initiative: Express Connect (former iConnect) expansion |  | 170711 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Si-Ying Chen, Shan Shan Li, Chetan Khorana | Some Issues | 04/21: Still pending on the completeness of migration. Also, pending EA review to be completed before moving to L3. 03/17: Per guidance, pending migration to a cloud native solution before expansion 02/28/2026: EA had to pull the architecture team to work on the scope of the first value bundle moving through the Clearance program. Looking to schedule a meeting with this group the week of March 9th and 10th to get thoughts and input as to clearly layout the work for value bundle 2. The value bundle model and the strategic program structure is new to all. 01/28/2026: team is awaiting the EA team’s assessment on the overall Value Bundle for Clearance Modernization. 01/15/2026: JP, HK expansion work in local enhancement 0016934. This initiative expands the capabilities. Financials reviewed and awaiting EA L2 feedback to see if any adjustments are required. Reference email from Sara Barnes. 12/23/2025: Sara Barnes is reviewing FIN costing request 12/17/2025- CEW - Escalated and completed items to submit to L2: L1 Architecture obtained and linked in Planview, SCO PEO rep obtained. Si-Ying submitted to L2. 12/15/2025 - CEW- Team met with Pod PM/Lead to discuss outstanding itmes. L1 Architecture completion to be escalated to move to L2. Financials refined. 12/04/2025: Thursday 2pm Central Time call is cancelled. Raye Paul is working now to accommodate the time zone request. Has dropped email message to regional finance representative David Spradlin on the Benefits and Costs alignment. 12/01/2025 - CEW: Teams are working in parallel to get this initiative the resources assigned. •EA Architecture – Audra is reviewing to assign resources •Clearance Development SME Support – Satya Proddaturi •My manager (Jennifer Choate) is working with Brandon Slone to request L1 Architecture completion this week What we need to complete this week: •Complete the L1 Business Case: Job Aid_L1_Entering LBC_BwT.pdf •Submission to L2 is dependent on completion of the EA L1 architecture and uploading any changes and their documentation link •Weekly status update for Thursday 2pm Central Time meeting (also ongoing) | E: L2 | Active | L2
Business w/ Tech Initiative: ExpressClear for All |  | 177354 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Liz Parker | On Track | On Track | E: L2 | Active | L2 & CCH | 2025-02-03 | 2028-05-31
Business w/ Tech Initiative: FedEx Butler |  | 177373 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Bryan Hertz, Regina Stone, Eyad Bahhur | On Track | On Track 03/26/2026 Updated Financials, added Initiative Milestones and Dates, added Epics and associated to initiative, reaching out to EAs as they need to update L1 architecture to remove SCO portfolio as stated on EA tracker and complete L2 architecture. Solution Architect = Pavan Kumar Akula. Removed benefits from Financials tab monthly values since they are soft benefits only ~$6M. Added KPI baseline, forecast, and confirmed actual line items. Roles & Responsibilities Work item incorrectly routed to Eyad, there may be an issue with missing STE (Solution Train Engineer) roles. Full Domain QA review needed after all entries are completed and prior to Enter L2 submisstion to next step. 12/29/2025 (BH) * Received and updated Soft Savings details. * Added abilty to information * Attached Soft Savings document to intiative * Pending Architectual review. 01/22/2026 (BH) * L1 Architecture Alignment Weekly Sync - IO Invite scheduled for 01/23/2026 * Added LBC attachment 02/05/2026 (BH) * L1 Architecture Alignment call completed. Pending the information from EPM needed to move initative to SL2 02/26/2026 (BH) * Updated Ability-To in suggested format. EPM provided details/attachments as required. * Intiatitve moved to SL2 and currently pending Domain approval to proceed. 03/25/2026 (BH) * Updated financials submitted for PEO review. 03/30/2026 (RS) * Additional feedback requested and provided. Submitted and pending L3 approval. | G: L3 | Active | L3 | 2026-07-13 | 2026-10-16
Business Only Initiative: SSC 3.0 - FY26/FY27 Roadmap |  | 177933 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Catarina Costa, Beatriz Gomes, Piotr Ptaszek, Lukasz Utylski | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: CUBE |  | 92782 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Alivia Malone | On Track | 13Apr: India ACCS app team will be providing access to non-prod and DR prod access on 4/14. Team received APAC Prod access for 3 countries, Dev access for all countries -- firewall request completed. MISA team is working on loading data into ATLAS for 3 APAC countries, as the team has requested Prod access to other 9 countries (3/9 have given access). 40 of 90 fields currently mapped for APAC countries. Offshore is working with APAC team to get additional fields mapped. Containers to write back to ATLAS were created in non-prod ATLAS and Prod ATLAS environments. For Tunsia, mapping for some fields has been identified and work is in progress to map others -- leadership support needed: team is having ongoing sessions to identify data elements with Tunisa SMEs as the source system for Tunsia is government/vendor. 3/19 - EPC meeting to review the exception for CUBE to move forward with EPIC 1&2 while we work to define Epic 3. 3/18 - IT team tried to connect with architect to align on next steps but architect declined. 3/17 - MD Gen0/1 rejected by Satya Proddaturi. No reason given except to reach out to Rob Turner. 2nd Architecture review cancelled because of this rejection. The MD Gen0/1 request stated that the all 5 impacted Gen0/1 systems were going to require major changes, which is not true. IT team corrected the architect by stating, Cube does not read data directly from the source systems (SEP, CII Intercept, CIM, Genius, or PCClient/ACCS). Instead, Cube reuses existing downstream feeds, SEP via ATLAS, CCII and CIM via MISA, Genius via ODS/ATLAS, and ACCS via their DR system. As a result, no changes or modifications are required in these source systems for the Cube project. This rejection was esclated to multiple Mgrs, MDs and VPs to correct what was presented in the request. 3/17 - Sent to JW & Sri Lakshmi Tadepalli as an ask from GC Domain call Two Key Issues Impacting CUBE’s Ability to Move Forward with ACCS data ingestion; 1.Pending ACCS Access Details for Remaining APAC Countries: For the remaining APAC countries, progress is blocked due to outstanding ACCS access and connection details, which are needed before data ingestion can begin: oNZ (New Zealand) oMY (Malaysia) oPH (Philippines) oKR (South Korea) oTH (Thailand) oID (Indonesia) oTW (Taiwan) oHK (Hong Kong) oVN (Vietnam) 2.L3 Support Dependency & Delphix: The ACCS India team confirmed they cannot support access provisioning or data mapping until CUBE reaches L3. This dependency is currently blocking all data ingestion and mapping activities. 3/11/2026: SCO Architecture was not approved on 3/3. Next meeting is ASR, Architect Stakeholder Review, on 3/17. Blocked because APAC provided DB access for 3 countries, 9 are still required. ACCS India requires use of Delphix, however it is not the architecture for APAC currently and would require rework. Blocker for ACCS data until architecture decisions are made and ACCS access to remaining 9 countries is provided. 3/3/26: SCO Architecture rejected - architecture missing full list of impacted systems 2/23: Comm architecture approved 2/12: COM ASR - 2/23 SCO ASR - 3/3 Once both are complete, we will submit for an exception for EPIC 1 & 2 to move forward. Epic 3 will remain a work in progress from architecture. Solution Arch will be needed for COM to help with Infosec reviews. One will be assigned once expection is approved. 2/6/26: Started conversation to submit for an exception to move Epic 1&2 forward while more research is pending for Epic 3. Epic 1: Reporting availbility through Fedex Reporting Online Epic 2: Documentation PoC through Magic Epic 3: API & Pay wall reporting Arch review to be scheduled for Feb 23. Efforts to move to L3 by March. Data availbility for baseline countries in ATLAS by end of PI (April) to kick off development work for Commerical teams in their next PI. Commerical currently has a spike to research the capabilties in Epic 1. 2/4/26: Conceptual arch | E: L2 | Active | L2 | 2026-04-06 | 2026-10-02
Business Only Initiative: APAC iClear Export promotion in NCN region | 58692 | 8185 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Yan Aaron Kong, Jimmy Zhang | On Track | 1. iClear Export adoption rate has been kept at 90% for NCN, and 77% for SCN basing on May reading 2. The team has been testing Auto RDE functionality which shows 95% of iClear shipment are being captured by ACCS and submitted to broker automatically, bypassing RDE workflow. 3. target launch date of RDE automation has been delayed to Jul.1st given additional fix and testing will have to be done | K: L5 | Active | L5 | 2023-11-01 | 2024-11-12
Business w/ Tech Initiative: LAC SB: Customs clearance streamlining |  | 162634 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Jorge Chiros | On Track | 09302025> Primary owner updated | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: APAC CLR GC3: migrate MY,TH,KULGC to lower license |  | 92775 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Man-Ting Simone Sze, Blaine Chen | Attention Needed | 4/2/2026: global GC3 team converted already. Not requried. 1.13.2026 Sent instructions to Simon Sze and Blaine Chen on how to Cancel. Replaced by Local enhancement (0009607), making this one a duplicate. Placing On Hold until IO can cancel. Reference emails 3-5Jan2026. Undated (2025): Submit to L2, pls. proceed asap that we can move to L3 asap to faster the saving realization | E: L2 | Cancelled | L2 | 2025-02-28 | 2025-09-04
Business Only Initiative: [MEISA] [ZA] CEP Clearance adoption | 94492 | 7207 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Clyde Francis, Dewald Hattingh | On Track | 2026.04.15 - Customs Regulatory Specialist hiring in progess. Interview processes are still ongoing. Aiming to close off by April 30, 2026. 2026.03.19 - reg specialist hiring in progress - posted and closed for applications, interviews to commence from next week. 10/29/24 - Quanitfying impacts and completed L1 LBC 02/17/24 - Resubmission of L1 Business Case. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-11-21 | 2026-04-30
Business w/ Tech Initiative: Virtual Clearance Consolidation - Canada |  | 156546 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Nitin Menon, Rod Polako | On Track | 12/15 - Initiative put **on hold** for now to evaluate the following: 1.Determining what the other regions are doing to address this need 2.Looking for alternative solutions that we may be able to employ to address this need for Canada 3.Regrouping with the team on the global initiative where it was suggested that Canada may be able to be a POC 12/05 - Business continuity PDSM ticket completed, changing BC value to No 10/28 - Init has been greenlighted after CCH review with Karen. 10/27 - Init has moved to L2. Filled the L2 CCH portion already, awaiting costing estimates from the impacted portfolios - SCO, Commercial & Platform. 10/20 - Got the sign off from Finance and Solution architechts for SL1 - need QA review before submitting to SL2 09/30 - Disscussed with Megan Stone and agreed to wait until next week when both Nitin and Sanghmitra are back. 09/26 - Reviewing demand with business owners and stakeholders due to need to update original request. Updates to request still in progress. 09/19- Assigned secondary IO and will be working on LBC to push to L2 | E: L2 | On Hold | L2 & CCH
Business w/ Tech Initiative: GCSI Bundle B: Inventory Control |  | 184692 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Rohini N. Kala | On Track | 01.26.26 - On Track. Team is working on gathering the soft benefits | C: L1 | Active | L1
Business w/ Tech Initiative: MWMS |  | 184697 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Simon Caffry | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: CCII Manifest Dashboard |  | 184700 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Darin P. Campbell | On Track | 4/21/26 Cancelling because needs to be moved as a local enhancement Development has already been worked on and new planview request is: 0019920 4/14/26 * Mappings - Completed * Development - Completed * Post Launch Enhancements - In Progress 1/22/26: * Sources Identified * Mapping - In Progress | C: L1 | Cancelled | L1
Business w/ Tech Initiative: GRACE integration with SEFS |  | 184706 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Karthikeyan Manivannan | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: ExpressClear (formerly Touchless Clearance) |  | 143818 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Claire E. Wilkinson, Alivia Malone, Kim McFadden-Effinger, Kelly Rowland | On Track | 4/23/2026: Update from Dana Alridge and Eric Duncan; All 3 vendors touched ExpressClear Volume in March. Have Datamark (DMI) and XBP March numbers but not WNS. Separately, SMO Kelly Rowland added as IO to add items for Value Bundle alignment. 4/06/2026: 3 vendor invoices involved. Only one has committed to be able to modify the invoices to support splitting of the costs by project on the FedEx side. Dana Aldridge is the new manager over the OCR contracts. Eric Duncan continues as SME. 2/27/2026: Awaiting new forecast and GenAI OCR analysis. Discussed with upper management if we need to move forward to L3 for visiblity and adjust afterwards and they requested to wait, that the costs are known and we need to get the revisions. 01/19/2026: GenAI OCR solution testing completed 1/16/2026. Evaluating impact on contract needs over the next four weeks. Finance, IT, Claire need to evaluate the split of development costs between this and the new ExpressClear for All. Laurie Kimura and team evaluting new OCR solution and impact of lower volumes experienced versus forecast. 12/22/2025. Multiple updates made. 12/15 Ability To statements from Jaime Munch and discussed direction. Ability to reduced to: Ability to digitize shipment data and access it early in process Ability to compile master dataset for entries Ability to automate creation & submission of entries to CBP Ability to auto submit verified entries & flag those needing broker intervention Capabilities reduced to: ExpressClear - 01_Digitization Milestones and Epics reduced as relates to reduced scope. Reduced portfolio impact as Commercial impact is now stictly on ExpressClear for All and not this initiative. Benefits updated for Nov from David Spradlin. Oct/Nov actual OCR requested from Eric Duncan. Forecast needs to be adjusted to reflect volumes not reaching expectations. Proposal needed from APAC team. 12/08/2025 New work will be placed on a new initiatve request (ExpressClear for All) 11/06/2025 Gen0/1 VP Approvals finalized (Harsh Garg) 10/27/2025 CEW, Cost Avoidance is $120M annually 10/14/2025 Added Commercial Financial Items to Jan-May2026 07/28/2025 Added all associated financials from SCO, Data & AI and Clearance (FTEs). 07/28/2025 Added L1 Architecture Assessment document link. Adding Kim as secondary IO. Required to enter in Value. | E: L2 | Active | L2 | 2025-02-03 | 2028-05-31
Business w/ Tech Initiative: FGC Implementation for GSPs |  | 187956 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Tina M. Jones | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: LAC Clearance Automations |  | 187959 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Ana Paula R. Lima, Kyle R. Gilbert | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: 15k and over Duty & Tax Bad Debt Mitigation |  | 190516 | Business Only Initiative | FXE GC - Operational Excellence | Global Clearance | Elizabeth Roberts | On Track | 4/24/26 Project has saved over 30m since Feb 16th. On Track. 04/17/26 Dashboard created to provide KPIs to the team. Financials updated and entered into PV. | F: SL3 | Active | SL3 Domain Lead Approval | 2026-02-16 | 2026-08-14
Business w/ Tech Initiative: Agentic AI Pilot Single Infrml Clear Prep |  | 192509 | Business w/ Tech Initiative | FXE GC - Operational Excellence | Global Clearance | Regina Stone | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: VIRGO - Global (Under)Valuation Infringement Reduc | 4947 | 9047 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Paul McAdam, Luiz Vieira | On Track | 6 Oct - updated Sept KPIs 11 Sept - added Aug KPI and ready for L5 14 August - Final KPI for July upated from ledger details 11 August - Updated KPIs for July , just waiting for the ledger details for the final KPI 11July - Updated the final KPI for June 7 July - Updated financials and KPIs, just waiting for the Ledger details for one of the KPI's (from D Spradlin) 9 June - now in L4, and KPIs and financials updated for May 30 May - Submitted to L4 as per plan 16 May - KPIs updated for April 14 May financial entries checked 8 May - April financials and KPIS added, milestones complete and ready for L4 15 April - March financials added and KPIs updated 31 March - removed the double count of the resource from the global project finances as it applies to the EU pilot, updated the 2025 exit rate of the opex IT costs and added 0 to the may 2028 exit rate. 4 March - work under way with Americas comm setup, and need to add the Feb KPIs this week 25 Feb - KPIs completed last week and still on track 11Feb2025 - Finances updated for Jan, just waiting to get some figures to complete the KPIs too 3Feb2025 - VIRGO being used successfully for various investigations into shipments and accounts. Slides still being drafted for POD lead discussion. 27Jan2025 - initial Discussion on strategy and future Expansion and enhancements for VIRGO taken place, so now preparing slides for POD lead discussion 20Jan2025 - KPIs added for Dec. 16Jan2025 - KPIs mostly popoulated, just waiting for the Extract of the FCF figures to populate the final KPI row. Gathering details for furture development and stabilising end to end processes to ensure we are in BAU mode. 9 Jan2025 -Finance figures removed but not yet repopulated back into KPIs. KPIs for December being compiled. 19Dec2024 - Currently reviewing the financial figures previously submitted in WAVE as they can now be populated correctly under cost avoidance in Planview. Money step being moved back 3 months to cater for the completion of the financial figure discussions and to allow resource to be migrated to BAU. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-21 | 2025-05-30
Business Only Initiative: VIRGO - EU APAC Pilot | 54371 | 7206 | Business Only Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Paul McAdam, Leendert Creyf | On Track | 7 Oct - Updated Sept KPIs 11 Sept - updated the KPIs and moved into L5 11 August - Updated the KPIs for July 7 July - Financials updated and KPIs updated for June 9June - Financials and KPIs updated for May 16 May KPIs updated for April 14 May - financials updated for April and forecast added for May 15 April - Financials and KPIs for March added 28 March 2025 Exit NRB updated as instructed, exit 2028 added as 0, milestones adjusted and Feb financials added the previous week. 4 March 2025 - all ok, presentation to EU MDs/VPs being drafted about Move to BAU, + need to add Feb figures 25Feb 2025 - KPIs added before the 17th. all ok and no change. 11Feb2025 - Approved by Finance into L4. KPIs details for Jan to be added 3Feb2025 - Awaiting approval/sign off by Lisa Lisson into L4. 27 Jan 2025 - Submitted to L4 20 Jan 2025 - still collating BAU evidence and gain approval for inclusion. Submission to L4 target is before the end of January. 14Jan2025 - completed milestone and updated the KPIs and financials for this project. all ready to go into L4, so just collating BAU evidence to attach and then will submit into L4 next week. Calls with APAC leadership took place on 10/17 and 10/26 and pilot was launched on 11/1. First focus was on aligning process documentation with assigned APAC team. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-01-01 | 2024-11-01
Business w/ Tech Initiative: Export Shipment Analytics | 35863 | 7013 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Michael Wallen, Karen Bruntrager | On Track | 11/12/25- This initiative is being closed as it is being moved to LE: 16061- Red Flag Export Shipment Analytics. 11/3/25- Per Suresh, his team will take over ownership of this initiative. They are working to get it transitioned to correct team in PV. 10/31/25- Meeting cxld by Gordon Turner. Rescheduled for Mon 11/3. 10/31/25- Suresh Kotta and team have worked on dashboard. Presented demo. 10/24/25- Meeting cxld by Gordon Turner. 10/22/25- Met with Gordon Turner (DW) to reivew the envisioning document and answer outying questions. Next meeting 10/24. 10/20/25- Awaiting Gordon to schedule discussion. Have since spoken with Naresh's team to support. Spoke with Beth Houben & Kathy Torode who will engague with Godron to assiste moving into L3. 10/02/25- Gordon held envisioning meeting/discussion. He is taking a few items back for research and will reschedule time to regroup week of 10/13-10/17. 09/30/25- Gordon rescheduled envisioning session to 10/2. 09/25/25- Gordon rescheduled envisioning session to Tue 09/30. 09/19/25- Gordon sent eml to Clayton Clouse to become engaged. Clayton replied: I have several open positions right now and am not allowed to backfill, and the Clearance domain has massive demand right now. Consequently, we have a growing backlog of work that we are unable to engage in. However, I would like to have someone from my team and if possible, Kasi's team, join the sessions to understand the work. To be clear, I am not committing to this work at the moment, but I want to have a good understanding of what will be needed. 09/19/25- Met with Gordon to refresh him on details of initiative. He scheduled more in depth envisioning session 9/25/25 to progress forward with architect. 09/08/25- Sent another email to Gordon Turner requesting that he schedule a call to discuss, per his request. Gordon scheduled call 9/9/25 to discuss further. 08/26/25- Gordon Turner requesting a catch-up meeting to discuss initiative. Provided dates to schedule call. 08/25/25- Results boosted from 216 to 23. Sent email to Rachel Wood inquiring what is needed to progress initiative forward. 08/21/25- Demand was presented at EPC and agreed to get a priortization boost. 08/05/25- Trey was requested that we complete two templates prior to being re-reviewed. 08/04/25-Trey will submit to be re-reviewed at next Global Clearance Regulatory Priority Decision. 07/28/25- Rcvd inquiry of PDSM. I provided updated business case language and Planview was updated. 07/22/25- No update. Determining how to udpate business case. 07/14/25- Trying to determine how to update Business Case. Trey is investigating as well. I opened PDSM ticket# INC031455839 inquring how to edit the Business Case. No replies regarding PPM#, so I submitted new PPM proposal #1228935 and added in PV. 06/26/25- Spoke with Karen. We'll update business case and provide clarity there is no "manual process" being done. 06/25/25- Received clarification from Daniel Knopfmacher on prioritization decision. Will discuss with Karen on next steps. 06/16/25- Sent another email to Gordon Turner added Briana Burdick & Karine Osborne inquiring PPM# info. 06/02/25- Updated Planview items to progress to L3. Need PPM#. Sent email inquiry to Gordong Turner for the PPM# so I can submit to L3. 05/08/25- Kicked back again. Eryn requested to change Primary Type of Value to Cost Avoidance. Made change and re-submitted to L2. 05/08/25- Kicked back to L1. Sent email to Eryn Walter, made updates and re-submitted to L2. 05/05/25- Rcvd email from Ryan Gover with IA link. Updating PV and submitting to L2. 04/29/25- Awaiting EA assignment. Sent email to Gordon for an update on EA being assigned for this initiative. 04/17/25- Spoke with Trey regarding the IA requirements needed to submit to L2. Link to IA should come from EA, which has not been assigned yet. Sent email to Gordon requesting EA be assigned and the IA link be provided so we can submit to L2. 04/14/25- Awaiting the IA link fro | E: L2 | Cancelled | L2 | 2023-09-01 | 2025-05-30
Business w/ Tech Initiative: US CBP ACAS Vague Description Enforcement | 96723 | 7310 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | William G. Cooper, Douglas Stubbs, Brian Campbell | On Track | 28MAR25 - updated baseline using 2025 18MAR25 - at the architects to provide length of duration and effort of work and costs. - February payment submitted to ATOS vendor - $4,541.00 - No future payments to be made to ATOS 10MAR25 - at the architects to provide length of duration and effort of work and costs. 10FEB25 - at the architects to provide length of duration and effort of work and costs. - January payment made to ATOS vendor - $54,486.00 21JAN25 - at the architects to provide length of duration and effort of work and costs. 15JAN25 - continued discussions with Enterprise Services Portfolio, SCO Portfolio and Data & AI Portfolio for Greenlight approval. Triage with Data and AI happened 1/15. Approval to pick up review was assigned to Sarah A. 08JAN25 – Waiting for L2 greenlight from Enterprise Services Portfolio, SCO Portfolio and Data & AI Portfolio | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-19 | 2025-12-01
Business w/ Tech Initiative: BSO Intercept | 21062 | 7822 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Brian Campbell, Douglas Stubbs, Shane Bradley | On Track | 04/20/2026: E to E Teasing completed. Due to multiple systems impact necessitating a "weekend loading" MTP has been bumped to 5/2 04/16/2026: Update Pending 04/09/2026: No Change 04/02/2026: E to E Testing to begin 4/09. Scheduled MTP 4/24/2026 03/26/2026: E to E Testing bumped out a week to 4/09/2026. MTP bumped out to 4/24/2026 03/19/2026: New Test Lead assigned. E to E Testing to begin by 4/02/2026 03/09/2026: No Change from last week 03/04/2026: E to E Testing bumped to 3/19 02/25/2026: No Change from last week's update 02/18/2026: Project post review, reactivated: UA and End to End Testing to start 3/9/2026 02/09/2026: No Change 02/02/2026: No Change 01/26/2026: No Change 01/20/2026: Initiative reverted to L3, until production release 01/12/2026: No Change 01/05/2026: No Change from below 12/29/2025: BSO is being removed from the PI 1 priority list.one of the lean leaders stated they would assist in determining if CIM-US defect was fixed, what surface work is still needed, and EA review to determine if piece level was completed or was solution based on shipment level. 12/22/2025: Prodcution Load on 1/17/2026. Go Live 1/19/2026 12/15/2025: No Change 12/08/2025: Tresting continues sans Architectual Review. FXG Systems still delaying progress 12/01/2025: No Change 11/19/2025: Ground Testing: ON HOLD, due to architectural review on missing locID/StationID 11/12/2025: E to E testing has run into hurdles w/ FXG. behind schedule on release 11/03/2025: PI4 End to End Testing continues 10/27/2025: PI4 End to End Testing continues. Push to L4 10/13/2025: NO CHANGE 10/06/2025: Phase 1 ( FORGE enhancements ) Scheduled delivery date Early Nov. / Pre-Peak. Phase 2 ( LEO enhancements ) -Post-Peak 09/29/2025: NO CHANGE 09/22/2025: PI:4 Neighbor testing ongoing. FRO(LEO) application missing. more to follow 09/11/2025: No Change- All work w/in PI:4 09/05/2025: No Change- All work w/in PI:4 08/29/2025: No Change- All work w/in PI:4 08/22/2025: All work w/in PI:4 08/14/2025: All Work *aligned* for PI4 08/04/2025: No Change 07/25/2025: No Change 07/18/2025: No Change 07/13/2025: SCO Portfolio Financial Actuals added 07/09/2025: No Change 06/30/2025: No Change 06/23/2025: Updated "Not Started" Project work to expected Start Date of 8/20 ( PI-4) w/ a 10/28/25 completion Date 06/16/2025: No Change 06/10/2025: Milestones updated to reflect PI4. end date 10/28/2025 05/27/2025: Accepted in Stage L3 MAY 22 2025: Acceptance to L3 pending final SCO approval MAY 15 2025: Submitted to L3 PI 4 begins on 08/20 & ends on 10/28 May 08 2025: SCO PEL votes to move Initiative forward. L3 acceptance housecleaning needed, PI4 Testing approved APR29 2025 - EOR to FORGE sample review bumped to Week of 5/04. Delivery date of Initiative: FY26 H1 (Jun-Nov) APR17 2025 - FORGE Team to confirm EOR sample message. APR04 2025 -Architecture still valid, Solution Council to determine prioritization MAR28 2025 - Re-baselined. No Change. MAR 21 2025 - SHLD review w/ Program Management Advisor MAR 14 2025 - Awaiting Architectural Review MAR 05 2025 - Due to continious deprioritization over it's lifespan, the Initiative's Architecture has *aged out* and will need reviewing. Solutions Manager to advise / assist in group call. As such, Initiative will remain in L2 until review completion and all parties satisfied FEB 24 2025 - Epic details updated, Planview ID # added to the PPM Project #489164 FEB 14 2025 - Multiple Teams development work reported as *complete* with the exception of the needs, if any, of FORGE Work. FEB 07 2025 - New Solutions Manager aligned. Identification / regrouping of all effected systems and POC to jumpstart initiative. OPs Communication team identified for future engagement. New cadence for weekly updates as above. JAN 21 2025 - New IO alinged 08JAN2025 - Same status 03JAN2025 - Same status 19DEC2024 - Same status as last week 10DEC | G: L3 | Active | TEMP L4 - Enter L4 | 2023-01-31 | 2026-10-28
Business w/ Tech Initiative: U.S. Inbound BSO Redesign | 68410 | 8847 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Joshua Jaffe, Coy Alter | On Track | Cancelling due to extended period of time "on hold" 05/21/25 - transferring ownership to Josh Jaffe. Financials and assumptions to be reviewed. 01/15/25 - USI BSO Redesign is on hold, pending team realignment and review. | E: L2 | Cancelled | L2 | 2024-03-01 | 2024-10-25
Business Only Initiative: Regulated Shipment RFID Solution | 66238 | 7096 | Business Only Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Joe Sepich | On Track | 09/22/2025 - Cancelling due to the initiative only being a POC and the PFS initiative is currently being stood up. No longer need to track the POC. 03/25/2025 - Exit Rate has been updated 03/03/2025 - KPIs for POC have been entered. 02/05/25 - Submitted PDSM request to update initiative from Business with Tech to Business only. 01/30/25 - Money Step has been adjusted from March 2025 to June 1, 2025 to account for testing and monitoring of RFID technology. 01/22/25 - ITAR: Labels shipped to Lockheed Martin, should begin application to packages within a week or 2. Firearms: printers have shipped to RSR and should be installed by mid feburary. Tuning of the RFID equipment at AFW will occur the week of 2/9 and testing can then being. Due to recent changes in the Memphis Hub operations, (AMS container initiative and the S25 building becoming operational this fall) we are shifting our mounted RFID reader rollout strategy. We are leveraging the Enterprise RFID team strategy and funding to install mounted RFID readers in the AFW hub first, and then will hold on installing readers in the S25 building until after peak. OP&E does not have the exact rollouts determined in S25 for the EU and APAC country lanes, so we will wait to decide which runouts to install the RFID readers until they have a plan. Initial testing will be done at the AFW hub, and we will continue with the handheld solution pilot at the Memphis Hub, and first handheld solution rollout at the MEMH. | G: L3 | Cancelled | L3 | 2024-01-02 | 2025-09-30
Business w/ Tech Initiative: Know Your Customer | 35864 | 7015 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Mark Rodriguez, Karen Bruntrager, Tom Ludwig | On Track | Initiative re-launched in January 2026 | C: L1 | Active | TEMP L1 - Create L1 LBC | 2023-10-02 | 2024-10-25
Business w/ Tech Initiative: FPOE - Animal and Phytosanitary clearance | 49843 | 8045 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Bernard Stanley, Terri Tennison | On Track | 2nd February Updated to On Hold as agreed with POD Lead. New DRIVE initiative to be raised in Planview covering iPFS development of system intercept capability. Hold to be lifted once development work has been completed. Expected May 25. 27th January Request for new DRIVE entry for iPFS solution has been received from IT. Awaiting input for EU Clearance leadership on opportunity definition due to regulatory demand for this requierment. 20th January **Dependant on iPFS solution** Latest status on iPFS is detailed below: 82584 Solution update / ****New Timelines**** •Solution new developments: Approx 22 Jan - 5 Feb •IT integration testing: Approx 5-12 Feb •BV testing : Approx 17 Feb - 30 Apr •MTP: Approx mid May/15 May | C: L1 | Cancelled | L1 Data Migration - TEMP | 2023-11-06 | 2025-10-23
Business w/ Tech Initiative: China UEL/MFA Routing |  | 89968 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Man-Ting Simone Sze, Trey Schenzel, Chetan Khorana, Karen Bruntrager | On Track | 11JUN2025 - Submitted to L2, feedback requested. Finalizing the 6 items needed to move to L3. Has been reviewed/approved by Domain QA Expert and will push to L3 by 6/12. 31Mar2025 - FY26 rebaseline activities completed on 31Mar2025 07JAN20025 - Cannot complete the LBC until we receive the EA Rationilization. This project is currently #162 out of 336 L1 initiatives waiting for EA rationilization 03JAN2025 - Submitted LBC today Initial info provided to architecture. Legal and management support obtained. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-04-30 | 2025-09-30
Business Only Initiative: South African customs penalty rationalization |  | 91811 | Business Only Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Clyde Francis, Clinton Steyn | On Track | 10/27/25 - Cancelling initiative based on Operational Excellence initiative rationalization exercise. This has been approved by Global Clearance MD/VP Leads Moving initiative to on hold - 8/18/25 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: UCC-Export Followed By Transit Data availability |  | 96300 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Gonzalo De Dios, Silvia De Sousa | On Track | 30th March - We have scheduled an alignment session with SCO Architects for the 7th April. 18th March - PM from SCO was assigned. We have requested EA to support this initiative too. Assesment and Decomposition is 95% completed. Conceptual Architecture is progressing. 27th February - Initiative Decomposition is almost completed. We are starting with the Conceptual Architecture. We have requested a PM through the "AEOE Resource Request Form" so that we get extra support. Request was sent on Wednesday 25th and it will be reviewed on Monday by the AEOE team. 17th February - still working with the Architects on L2. 4th February - Keep having 2-3 sessions/week with the Architects on L2. All the team is aligned and we are progressing. 11th November- Last week we had the Kickoff session with the Artchitects assigned to the Demand. 10th October - Adding extra information before submitting to L2 because the system doesnt allow to modify L0 information: What is the type of risk? Customs might reject Truck movements because we declare wrong information on the Truck declaration. What is the risk exposure? Incompliance on Truck movements would bring fines and put at risk the AEO Certificate. What is the risk of not completing the work? To remain compliant, Ground Operations would need to offload the whole truck, remove the rejected shipments and load again the remaining shipments. The rejected shipments would need to be manually keyed in into the system before loading them again into another truck. Expectation is that this process is not feasible for Ground Operations (time, space, manpower,…) so they might move the truck with the non-compliant shipments in it. Which will result in fines and risk to the AEO Certificate. What law or regulation is impacted? EU UCC (Union Customs Code) Attorney/SME who can attest to risk: Name & FDX ID. John O’Mahony 3518928 Is there a manual solution? No If there is a manual solution, explain: 8th October - Confirmation received from Finance Team. I have just sent an invite to Trey for Friday 10th so that we can to review the Demand before submitting to L2. 7th October - Demand was reviewed with Christian Visschedijk. All the fields have been reviewed and agreed except the financials. Finance team needs to align internally before commiting to a figure. Figure is expected to be available today so that we can meet the deadline of 10th October. 2nd October - After several review sessions with Finance team, we are aligned on the figures and the approach. We have scheduled a review session with Christian Visschedijk and if that is satisfactory I will proceed to book the review session with Trey before applying to L2. 22nd July - Under review with Regulatory/Compliance EU Team to validate assumptions used for the financial impact. 9th July - Under review with Finance to agree on the figures to report. Next call scheduled for tomorrow (10th July). 24th June - L2 submission rejected by EPM. Need further details on the finance. Call is set up with Antony B. for Wednesday 25th. 19th June - Created Unified Project Request in PPM #9013026 10th June - Still having troubles creating the Unified Project Registrartion in PPM. I have escalated to the PPM team. 4th June - Green light received for L2 submission. Having some troubles creating the Unified Project Registration in PPM. 26th May- Some fields have been updated/added following the example of another demand that got quicker review with the Architects. Waiting for Architects review to progress Escalated through Brian Marie | E: L2 | Active | L2 & CCH | 2024-11-13 | 2027-01-01
Business w/ Tech Initiative: NCTS p5 HS Code - iSearch functionality |  | 96303 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Siddharth M. Tripathi | On Track | Work has already been completed - 11/24/2025 **30/09 -The request for ES 8 Digits can be put on Hold while we are working on other priorities impacting regional level (sensitive HS Code). ** 31st March - Talked to David Spradlin and confirmed the financials. | C: L1 | Cancelled | L1 | 2024-07-22 | 2027-02-25
Business w/ Tech Initiative: EU Deforestation Regulation (EUDR) |  | 96352 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Edward Chan, Michele Allison, Malcolm G. Easton, Sean Brady, Stephanie Waltman | On Track | 19/6 - Case was turned back mentioning that a target/baseline value is still required. Used the initial assessment of 94m USD revenue protect as the target and baseline value. The Net recurring soft benefits is approx 3.5% of the revenue, which results in 3.3m USD cost avoidance. Also changed the case to Financial - revenue protection for submission 17/6 - Reviewed with Finance and PMO. Agreed that this is a legal/Safety and should have no target/baseline value. Case submitted 4/3 - LBC partially completed. Additional meeting scheduled this week with core team and finance. In process of pulling numbers to support impact and possible opportinities. 11/3 – Core team met with Finance and were given guidance on the best approach to completing the LBC for a regulatory driven demand. The guidance provided was to focus on at risk revenue if we are unable comply. Numbers of impacted shipments (using published HS codes) by country and by top customers has now been collected for major countries for import (December 2024-February 2025). These number will be used to determine at risk revenue. Gaps exist with export many third-party clearance system reporting capabilities (No viable reporting mechanism to capture this level of data currently). Assumptions based on existing data will need to be made to arrive at the potential at risk revenue risk for these countries as well as all export. Further meetings planned this week to get estimated revenue impact. Still waiting the architectural work to be assigned. 25/03/2025 - L1 Architecture alignment step completed. Managed to secure export impacted volumes by lane, so now have full view of impacted shipments both inbound and outbound from the EU. Meeting scheduled with Finance this Friday with the aim of completing to LBC for submission to L2. 28/03/2025 - FY26 Rebaseline activity completed Friday 28/03. 31/03/2025 -PPM ceated by Paul# 843507. | E: L2 | Active | L2 & CCH | 2025-11-06 | 2025-12-30
Business w/ Tech Initiative: Transport Cost Inaccuracies [ECTS] |  | 97525 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Caroline Coyne, Michal Gotkowski | On Track | 04/20/26 On the L2 Enterprise Priority list current ranking is 179 (last week - 178 (lowest ranking 114)). 04/13/26 On the L2 Enterprise Priority list current ranking is 178 - no change (last week - 178 (lowest ranking 114)). Scheduled call for April 17th with Jennifer Driver, Manager Portfolio Architects Enterprise Business Architecture, this comes after David Walker, Product Management Advisor, stated the initiative is showing that the EA owner is Commercial EA. We also have a call scheduled with Joey Cline and LAC on April 17th - This call is to discuss the possibility of pulling the Transport Cost Inaccuracies needs into the US Manifest Quality Requirements solution. We are looking to extend our European initiative into a global rollout, as other regions (LAC and APAC) have identified a very near same/similar issue. 04/06/26 On the L2 Enterprise Priority list current ranking is 178 (last week - 181 (lowest ranking 114)). Scheduled call for April 17th with Jennifer Driver, Manager Portfolio Architects Enterprise Business Architecture, this comes after David Walker, Product Management Advisor, stated the initiative is showing that the EA owner is Commercial EA. We also have a call scheduled with Joey Cline and LAC on April 17th - This call is to discuss the possibility of pulling the Transport Cost Inaccuracies needs into the US Manifest Quality Requirements solution. We are looking to extend our European initiative into a global rollout, as other regions (LAC and APAC) have identified a very near same/similar issue. 03/30/26 On the L2 Enterprise Priority list current ranking is 181 (last week - 194 (lowest ranking 114)). We are looking to extend our European initiative into a global rollout, as other regions (LAC and APAC) have identified a very near same/similar issue. 03/23/26 On the L2 Enterprise Priority list current ranking is 194 (last week - 194 (lowest ranking 114)). We are looking to extend our European initiative into a global rollout, as other regions (LAC and APAC) have identified a very near same/similar issue. It had been previously proposed to combine initiatives with US Manifest Quality Requirements #110215. However, following a meeting this approach will not be pursued, as it is a local project outside of the Planview process. Additionally, Pat Sculli will reach out to Joey Clein to review the situation, and if a suitable solution is identified, they will follow up accordingly. 03/16/26 On the L2 Enterprise Priority list current ranking is 194 (last week - 199 (lowest ranking 114)). Awaiting update from Trey Schenzel and Elizabeth Roberts. 03/08/26 On the L2 Enterprise Priority list current ranking is 199 (last week - 198 (lowest ranking 114)). Awaiting update from Trey Schenzel and Elizabeth Roberts. 03/02/26 On the L2 Enterprise Priority list current ranking is 198 (last week - 196 (lowest ranking 114)). Had a meeting with Karen Bruntrager, Terri Tennison, Trey Schenzel and Elizabeth Roberts to review the initiative and next steps. Trey and Elizabeth will revert with outcome of a meeting this week. 02/23/26 On the L2 Enterprise Priority list current ranking is 196 (last week - 203 (lowest ranking 114)). A call has been scheduled with Karen Bruntrager, Terri Tennison and Trey Schenzel to review the initiative with regards to making it a Global Initiative and the financial requirements. 02/16/26 On the L2 Enterprise Priority list current ranking is 203 - no change (last week - 203 (lowest ranking 114)). Acknowledgement of the synopsis (for global initiative) from Trey Schenzel. 02/09/26 On the L2 Enterprise Priority list current ranking is 203 (last week - 194 (lowest ranking 114)). Provided a synopsis to Trey Schenzel on Transport Cost Inaccuracies and included information from our calls and findings with LAC and APAC - Trey will share this with management. 02/02/26 On the L2 Enterprise Priority list current ranking is 194 (last week - 192 (lowest ranking 114)). 01/26/26 On the L2 Enterprise Priori | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: ELVIS - e-commerce Low Value Inspection System |  | 98476 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Stephen Ross, Renate Jalbert | On Track | April 15/26 - In our weekly update meeting with the IT team (incl surface architects) and it seems that we will have 2 new financial costs around Surface inclusion work during May-Oct/26: 1)D&AI Portfolio – Additional costs based on adding Surface - this we knew about. 2)SCO Portfolio – We have the AIR in the financials now, but the SCO IT MD advised me that they will have additional costs when adding Surface to ELVIS. The Business Arch for ELVIS raised that there is an L2 Conceptual Architecture Review Board Meeting that has to take place before we go to the Solution Council requesting L3 approval. April 10/26 - Have cpnfirmed with Andrea Ards that the portfolios will combine into 1 approval meeting called "Enterprise Greenlight Committee Meeting". Andrea has asked me to send the PEL approval slide to the Solution Council and the Solution Manager will review and reach out if they have any questions prior to scheduling for the next ent Greenlight meeting. I will schedule a review with Trey Schenzel and Elizabeth Roberts for the Planview QA Domain Expert Review for next week. April 8/26 - Working on L3 info collectioon and prep for SCO PEL and D&AI VDC meetings to request approval to move to L3. THis will take several weeks to gather all of the information and get scheduled on both meeting cycles. Have received SCO Financials, requested D&AI Financials asap. Will be working to generate milestones to go with money step. Phase 1 (iPFS) solution go live withthe CBSA most likely late May or early June due to their training time (up to 5 weeks required) . Other rioll out phases/ports to be determined with CBSA in July to generate roll out schedule with Surface included. Architects are now working with Surface on what that will look like in their environment, with a CBSA API messaging going direct to CLIP (Regulatory Platform) as it is being evaluated by the architects now whethre they will need to use CCII as is done for AIR. Mar 17/26 - Have received a request to complete a new ini for local enhancement for iPFS (Phase 1) from Dataworks to have their cost approved of $245k for the next 6 months. I have asked them to consider including that on the EPIC 1 that I created for that reason and await their decision. I would prefer not to open another PV ini for ELVIS at this time. Mar 10/26 - Arch decision is to move forward with iPFS for all phases of ELVIS. I have sent a message off to David Spradlin to see if he can provide a IT Financial contact we can work with to develop the IT costs needed to move to L3. I have also booked a QA Review with Trey and Elizabeth for Mar 11 to review the ini as is to make sure we have everything covered for L3. Mar 4/26 - Have confirmed that the $245K is just for Phase 1 (iPFS) for DW for YVR AIR only. Scoping needs to commence asap with the surface group to understand what the cost is to merge their version of CCII into Phase 1 and beyond asap. Email sent to Satya Proddaturi, MD for SCO IT to review for architectural review priority. Feb 26/26 - Have added new money step of Oct 1/26 based on latest directive from the CBSA. Also have received $245K funding request to cover their costs until Oct/26. Still waiting for cost estimate from SCO. Feb 13/26 - Still waiting for direction from the EAs on next steps beyond the Phase 1 (iPFS). Testing is still underway with the CBSA as both sides work through the issues with messages. Jan 30/26 - Testing with the CBSA has proceeded this week as prep for moving into Phase 1 (iPFS) with the Reg BA's (Cyndee and Kyle) coordinating with the ELVIS team. Jan 26/26 - no update on the systems dev plan from EAs to update L2 details and move forward with proposed milestones and estimated money step. Testing on phase 1 (iPFS) is planned to begin this week with the CBSA. Jan 12/26 - Waiting for EAs to finalize both system cost and estimated milestones to completion. The EAs have advised that they are waiting for direction from the IT Executive beofre they can finalize the | E: L2 | Active | L2 Feedback Requested | 2024-07-22 | 2026-12-30
Business w/ Tech Initiative: Windsor Framework |  | 98472 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Edward Chan | On Track | This PlanView is done retrospectively. Some of the development work has already been done (the clearance application) while some still require further development work (Document check app). The additional development work has a workaround but should ideally should be in place for smooth operations. No longer needed in Planview. The work is done. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: [MEA] [RT] Obtain AEO certification and onboard de | 36307 | 7054 | Business Only Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Jignesh Joshi, Melissa Pinto | On Track | On track | K: L5 | Completed | L5 | 2023-08-01 | 2024-01-09
Business w/ Tech Initiative: UCC ICS2 Release 3 |  | 106149 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Bhavin Patel | Some Issues | MVP development complete and ready for deployment. Phase 2 (to complete initiative delivery) is in architecture discussions to define the development need for full compliance to regulatory requierments. For a bit of background, the ICS2 initiative (EU regulatory requirement) has been in development for over a year and will be going live with phase 1 (MVP) as from 1st April). The initiative has been entered into Planview for visibility to leadership, and to ensure the phase 2 work is prioritised accordingly, to ensure this final piece of development for full regulatory compliance is met by EU Commission deadline of Aug 2025. The figure stated in the NRB is the potential minimum cost in fines for shipment not or incorrectly declared to EU customs authorities if the initiative is not fully delivered. The worst-case scenarios would be the loss of FedEx operating licence in the EU, as this initiative and regulatory requirements are related pre-arrival risk assessment for safety and security of all shipments prior their entry into the EU territoy. Regulatory requierments have been met by EU regulatory deadline, however final enhancements to support linehaul operations for CLosed Unit tiggers to provide effiancy in truck departures and earlier ICS2 processing has been delayed due to environment issues dueing testing. E2E testing continues to be delayed due to upsteram environment issues, pushing out timelines for final solution delivery. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-22 | 2026-11-10
Business w/ Tech Initiative: CBAM |  | 108308 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Edward Chan, Michele Allison, Sean Brady, Stephanie Waltman | On Track | Initiative no longer needed | C: L1 | Cancelled | L1
Business w/ Tech Initiative: CH Regulatory Changes & Vendor Replacement- Import |  | 108834 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Julie Oeosterle | On Track | Date: 09/11/2025 Progress Made: • Business case assessment completed * Architectural documentation 80% completed Upcoming Milestones: * Complete ARchitectural documentation and move to L2 • L2 provide documentation of CORE SOLUTION to system Art • Risk assessment (Ops impact) | D: SL2 | Active | SL2 Domain Lead Approval | 2026-01-01 | 2027-06-30
Business w/ Tech Initiative: China UEL/MFA Routing-value bundle #2 |  | 110206 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Man-Ting Simone Sze, Chetan Khorana, Christina Dunphy, Karen Bruntrager | On Track | 7/2/25: (1) FY25 UEL volume transit via China: assume 90% of UEL/MFA volume will be stopped to route via China after VB2. (2) T-shirt size changed to "M" per initial articulature document provided by EA with link update. (3) Portfolio: add "Data & AI" and "Platform" as "Yes". (4) This is to ensure we can continous with current bussiness, not cost saving. The KPI will be there is no UEL/MFA transiting China. 5/23: project sponser target to complete the solution by Jan.2026 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: EU Exit Process |  | 110211 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Gonzalo De Dios | On Track | 18th March - Still waiting for Architects to be assigned to this initiative. 17th February - Still waiting for Architects to contact on this Initiative. 4th February - Still waiting for Architects to contact on this Initiative. It has been escalated to Terri and I am hoping for reprioritization. 2nd December- Reviewed the figures with Rob Davidson and he gave the green light to submit to L2. 24th November - Moved back to Active. The new scope and strategy has been reviewed with Financial team (Rob D.) Only dedicated FTEs will be used for cost savings (dropping the non dedicated FTEs). I have reached out to HR to get support translating the FTE's to euros. 30th October - Changed to "On Hold" until there is an alignment on the figures that should support the financials. Alignment needed with Compliance team, once that is done and we start the discussions with Finance team then the Demand will be changed to active again. 7th October - Not expected to be submitted to L2 in the coming 1-2weeks. We still need alignment with EU Regulatory/Compliance team to agree on the benefits, impact and priority of this demand. Then we will start the reviews with Finance team. 2nd October - This Demand is still under review with Regulatory/Compliance EU team. There is no alignment on the specific benefits that this will bring to the company. Once it is agreed, if the draft financial figures make it profitable then we will start the reviews with Financial team. 22nd July - Under review with Regulatory/Compliance EU Team to validate assumptions used for the financial impact. 9th July - Under review with Finance to agree on the figures to report. As per request from Finance team, once we have agreed on the figures for the other Demand (96300 - UCC EFBT), we will review the figures for this demand. 24th June - L2 submission rejected by EPM. Need further details on the finance. Call is set up with Antony B. for Wednesday 25th. 19th June - Created Unified Project Request in PPM #9013027 10th June - Still having troubles creating the Unified Project Registrartion in PPM. I have escalated to the PPM team. 4th June - Green light received for L2 submission. Having some troubles creating the Unified Project Registration in PPM. 13th May - "GC RC Pod Priority List" has been filled in. Drafted L1 fields. Aligning with Financial team to validate the figures while we wait for Enterprise Architects. | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: U.S. Manifest Quality Requirements |  | 110215 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | William G. Cooper, Douglas Stubbs | On Track | US govt implementation timeline has moved up from Sept to July 2025. This initiative needs to be accellerated. | E: L2 | Active | L2 & CCH | 2026-06-01 | 2026-06-01
Business w/ Tech Initiative: Clearance Common Data Model |  | 130966 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Pedro Pacheco, Kerri Slater | On Track | 8/20/2025 - Feedback to Archecitecture - the solution is to be delievered by DW in the CLIP Clearance insight Platform, this is aligned with Gemini and CIM, and already requested as SVP level, if this area is impacted does the AI portfolio not also have to be referenes in the documentation ? 8/20/2025 - Reviewed and approved by Domain QA Expert to move to L2 7/07/2025 - LBC update by IO | E: L2 | Active | L2
Business w/ Tech Initiative: LAC-BR- Brazil Tax Reform - NT Fiscal Documents |  | 131607 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Maiara Gomes De Sousa Ferreira | On Track | Urgent demand - regulatory compliance in Brazil | E: L2 | Active | L2 Feedback Requested | 2025-06-09 | 2026-01-05
Business w/ Tech Initiative: Kenya PIN No. Indication on FWB |  | 143350 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Bianca Theresa McGee, Wayne Petersen | On Track | 7/29/25 - Domain QA Expert (Trey Schenzel) reviewed & provided requirements to move to L2 IO | E: L2 | Active | Portfolio Greenlight | 2026-02-27 | 2026-02-27
Business w/ Tech Initiative: Missing TNT shipments from ITIH to FBC |  | 144050 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Thanmaya R. Malligemadu | On Track | Approved in L0 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: CLASS Auto Replan on All Cons# |  | 152247 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Ammar Ziara | On Track | Progressing | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: UCC ETD |  | 96452 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Michal Gotkowski | Some Issues | 04/13 - Development on Phase 2 capabilities continues - Architectural discussions in progress regarding changing the GETD source of shipment data to Vessel Cons data 04/06 - Development on Phase 2 capabilities continues - Architectural discussions in progress regarding changing the GETD source of shipment data to Vessel Cons data 03/30 - Development on Phase 2 capabilities continues - Architectural discussions in progress regarding changing the GETD source of shipment data to Vessel Cons data 1/26 -Phase 1: getting the application live with the minimal functionality to be compliant -Phase 2: adding all the quality-of-life features and increasing the data accuracy 9/15 * GETD Feature decomposition in progress 9/1 * Architectural activities in progress 8/18 * Architectural activities in progress * Confirmation required if Data & AI portfolio can support the ETD EDI requirements using Touchless Customs 8/11 * Architectural activities in progress * Strategic Parent field still shows FXE GC - Operational Excellence after move to the Regulatory POD 8/4 * Business Continuity approval granted * Strategic Parent field still shows FXE GC - Operational Excellence after move to the Regulatory POD * Architectural review scheduled 7/21 * All soft benefits removed from the Financial tab following advice from the FP&E team * Business Continuity approval not granted * Strategic Parent field still shows FXE GC - Operational Excellence after move to the Regulatory POD * Awaiting architectural review 7/5 - Filed a Data & Technology Finance Costing Request 6/16 - Updated the Demand description to include the risks of noncompliance after 1/1/26 05/30 - Architectural review completed. Submitting initiative to L2. 03/03 - Awaiting architectural review 03/10 - Awaiting architectural review 03/17 - Awaiting architectural review 03/24 - Awaiting architectural review 03/26 - FY26 rebaseline activity completed 04/09 - Updated the L1 Net Recurring Benefits ($, annualized)-Soft based on the amount of Customs fines which can be prevented by having a UCC compliant solution. | G: L3 | Active | TEMP L3 - Enter L3 | 2019-12-02 | 2026-08-31
Business w/ Tech Initiative: CPSC PGA Message set |  | 163090 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Doneika Mondaine, Charles R. Dionne, Kim McFadden-Effinger, Jon Olswanger | On Track | **April 2026** * Brokers will be ready to work shipments manually in Duplex​ * Project is at-risk due to unknown development timelines​ * Expect 3K/day cage rate with no customer automation * SCO PEL REview 4/16 * Complete solution architecture by 4/17​ * Official kickoff for development on 4/16​ * Accelerated customer outreach and communication plan **March 2026** * Complete L2 refined financial plan, benefits, and cost- 3.20.26 * Start L2 business architecture Workshop- Complete- 2.19.26 * Artifact: Conceptual Architecture Doc Requirements- 3.13.26 | F: SL3 | Active | SL3 SVP Finance Approval | 2026-01-01 | 2026-08-28
Business w/ Tech Initiative: UCC ETD - EDI + DE SUMA |  | 163628 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Michal Gotkowski | On Track | 04/13 - Architectural activities continue 04/06 - Architectural activities continue 03/30 - Architectural activities continue | E: L2 | Active | L2
Business w/ Tech Initiative: RFID Solution for Regulated Shipments |  | 164080 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Lene' M. Proenza, Maria Taylor, Daniel Bonnett | On Track | IO Updated | E: L2 | Active | L2
Business w/ Tech Initiative: COM Clearance FAPI MAGIC MID&FICP recipient Acct# |  | 164084 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Brian Mack, Arvind Reddy | On Track | 1/27 - Cancelling this ask due to the fact that for FAPI channel the code change for this ask is already implemented. The only pending E:E integration testing is being performed through Epic # https://www19.v1host.com/FedEx/assetdetail.v1?number=E-553618 This epic is for "E2E Integration Testing support Feature for OCI Team. FAPI Channel expect to do MID testing once Deepesh David’s team has completed their MID code work sometime early in CY26 PI01" 12/19 - New IO identified and added to the initiative 10.24.25 This PV was sent to the exception process as work has been completed. It was an urgent project approved by the MDs and senior leadership in response to the DeMinimis law changes. Meeting with Trey Schenzel and ESPM team week of 10/27 on the exception process. This was an escalated request due to business continutiy critical state to mitigate impact of increase in 200K + daily package to be cleared through CBP. This solution will provide necessary data points to eliminate bottlenecks due to requirement to submit the clearance data. The solution also offers a list of Whitelisted Customers who are in agreement with FedEx to pay the recipient Duties and taxes, which mitigates revenue loss when mandating a recipient bill to account. | E: L2 | Cancelled | L2 & CCH - Feedback Requested
Business w/ Tech Initiative: API for World Tariff |  | 109578 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Stephen Ross | On Track | Feb 13/26 - Still waiting, however have discovred taht there was a fix put in place for an identified issue. I am working with World Tariff to determine if the fix has rectified the problem and we are ready for the next API from CBSA to auto update the tariffs in CA Clearance Systems. Jan 26/26 - Now in L4 and waiting for the min 3 month reporting period before we can move to L5. Nov 20/25 - Updating actuals for Oct Nov 14/25 - Go live complete and will report out in L4 for 3 months before we can move to L5 Nov 10/25 - Per IT " All post-MTP activities have been successfully completed. The scheduler is now enabled to perform daily background checks for updates. Editors can utilize the On-Demand Sync feature available in the WTE UI to fetch HTS and Tariff data via API whenever needed." I am following up on IT costs to date to update the financials for L5. Will contnue to track the effectiveness and manual updates that may be required by WT staff over the comiung weeks and update this initiaitive accordingly. Nov 7/25 - Moved to SL4 and working to update to comply with L4 requirements. Moved to production on Oct 31 and will finalize and go live today. EPIC entered in Agility # E-551526 Oct 30/25 - After meeting today with stakeholders, it was determined that the MTP will go forward for Oct 31 with the go live for Nov 7th. Oct 24/25 - Now in L3 and entering L3 information to prepare for L4 coming in the next few weeks. Oct 17/26 - Have received SCO PEL Greenlight approval and now waiting for Shelby Stockbridge to approval to move to L3. Have adjusted milestones and money step to Oct 28th to align with new MTP date of Oct 28th from Kiran Andey. Oct 2/26 - Presented to SCO PEL for greenlight on Oct 1. The arch diagram was requested from Rob Turner before he woudl approve. The arch diagram was sent to Rob late on Oct 1 and Andrea Ards has advised that we may receive off line greenlight to move forward to L3 in coming days, otherwise we will have to wait until next PEL meeting in 2 weeks. Andrea will advise. Sept 26/25 - THe initiaitive is scheduled for PEL SCO Greenlight meetings next week. Have reviewed the data entered so far with Trey Schenzel, who agreed that we are ready to go to PEL. He has suggest that I add some KPIs, which I will do asap. Sept 18/25 - this initiaitive will be moved to the Regulatory POD and Trey Schenzel, POD lead, is working on it. We are also waiting for Kiran Andey to come back from vaaction so he can have a discussion with Swapnil Mantri around level of effort by IT resources to confirm costs. Once we get that alignment, we can move forward to PUL SCO greenlight approval meeting. Sept 12/25 - Draft SCO PEL Greenlight Meeting document shared for input with CA team and copy sent to Andrea Ards. PPM approved by Kiran Andey and issued as # 1634880. Will send finalized SCO PEL document this week to Andrea to schedule for next available meeting. Sept 3/25 - Arthur D is off on vaca this week. Will send him the PPM request so he can create when he returns next week. Next step is to complete the PEL Greenlight Template prior to joining a weekly PEL meeting. Aug 26/25 - Met with Arthur DiFranco with PPM who agreed that if we supply him with the info, he wirll create a new PPM and send off for approvals. He advised that our previous PPM request was not viewed by anyone and was stuck in request status. Therefore a new PPM needs to be submitted. I have completed the information page he sent with my best guess on many answers. I will have to send out to IT to have them confirm my answers as correct. Aug 13/25 - Followed up with Andrea and Anum Khan around estimated IT Development costs for L2. Anum is working on putting the financial estimate around costs. July 28/25 - I am not sure if this initiative needs to go to the PEL. I have sent a note to Andrea Ards for some more details on what is required for PEL. July 21/25 - updated financials per Valenta's email with IT one time cost details from Kiran | K: L5 | Active | L5 | 2024-07-22 | 2025-11-07
Business w/ Tech Initiative: UCC NTCS HS Code Trade Tools update |  | 126278 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Siddharth M. Tripathi | On Track | 21/04 - We now have Financial Impact of this request being not in place. The issue has been escalted to Sr Leadership (Mark Ruddock and Jorn van de Plas). Below is clearance-related costs observed since December 2024 (please refer to the table below). Top sites by cost (Dec 24 – Mar 26): SiteCountCostDowntimeRollover Multiple Sites27EUR 756K30h30,220 Barcelona85EUR 405K2,133h16,192 Prague31EUR 381K132h15,249 Rotterdam15EUR 90K13h3,564 Budapest6EUR 60K16h2,381 01/21/2026: Triage session held with CCH Lead (Karen McConnico). CCH question resposes revised and there is no commercial value proposition impact. While automation changes will be required to capture the correct information to publish to downstream systems to include clearance there is no impact. Value proposition impact changed from Yes to No. CCH Review not required 08/Sept - We discussed with the Process Engineer and Finance lead. It was identified that the request should be listed as 'Regulatory' and not as Operational Excellence' due to its impact on compliance KPIs related to NCTS p5. We have provided the table showing the no of truck delays, AWB stuck and how is will impact the NCTS p5 compliance if this functionality is not in place. May we please request the POD lead to change the category of this request to 'Regulatory'. We The Arch review is completed and documented. The link is attached to the PV request. Business case is accordingly updated. A/w for further review of next stage L-02. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: K2 allow up to 999 HS code per HAWB |  | 168321 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Tsz-Ki Jacky Chin | On Track | 02/20/2026- Continue checking with sales team and see if they can get the customer acceptable rate before the K2 solution is available, and find some other confirmed profitable business that needs similar development to support 01/22/2026- Financials: •Currently unable to obtain the approved rate from customer for our FP&A to calculate profitability, the customer stated they wont provide us a rate unless the solution is developed, and to move on and develop the solution a approved rate from customer is needed for the profitability calculation Progress Made •Continue working with FP&A and trying to figure out other way to move this forward • Talked to Temu sales team to see if there is any way to get the customer to get the rate without the K2 solution • Exploring with EU team if there is any other business opportunity that will be benfit by this requested development Blockers and Risks what is keeping the initiative from moving forward and steps taking to mitigate? We do not get the approved rate from Temu which is needed for the profitability calculation. the customer wont give us the rate unless the solution is already developed and the solution will not be developed if they do not provide us the rate. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: To add new iCage cage code for EUDR goods |  | 184155 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Edward Chan | On Track | INC034383336 - request to cancel was submitted by Edward Chan. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: CBP HTS Association increase 8 to 32 |  | 154554 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Charles R. Dionne | On Track | 4/6 - On hold per IO due to prioritization of CPSC work 9.16 medium no work around 12-29 If CBP where to make it so we had to report more than 8 HTS codes on a single line right now we would have no way to handle it. This programming is needed to catch up to what CBP has already made allowable on within their edits. | E: L2 | On Hold | L2
Business Only Initiative: EMR OTC - ACAS Vague / Missing Desc Prevention |  | 93440 | Business Only Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Raul Cardenas, Joshua Jaffe | On Track | **12-3-2025** * July 2025: 8,572 shipments (286 ADV) * November 2025: 4,372 shipments (146 ADV) This reflects an ~50% overall reduction in vague description shipments transiting the US since EU/APAC hard-stop enablement in August 2025. Note that the 4,372 shipments in November are largely tied to LAC destined countries where Error/hard-stop is not yet enabled, so shipments can still move. Additionally, some customers are still using older GSMW versions (24XX+). These versions do not enforce a hard-stop on vague commodity descriptions. **11-21-25** - Working with APAC/EU regions to get data to show impact on vague descriptions HARD STOP implemented in Aug 2025. **9-6-25** - Production change rolled out to exclude intra-EU movement **8-23-25** - Capability live as of 8/23/25 for inbound EU and APAC regions **7-21-25** - EU team targetng Aug 23 implementation date for EU destiantions only to meet the Sept 1st end of the transition window for the ICS2 Release 3. - 1st September 2025 is the end of the transition window for ICS2 Release 3. ICS2 is part of the UCC (Union Customs Code) EU Regulations enforcing Safety and Security requirements for goods into and transiting the EU. The stop words introduced by the EU are to strengthen this regulation and support the wider UCC regulations covering import, export and transit. Fines are up to €7000 per shipment and jeopardise our AEO approvals and approvals to operate. - Assessment ongoing by APAC team - No feedback from MEISA/LAC regions **6-6-25** - Follow up meeting with stakeholders to go over any open questions and ask support for feedback/approval by 6/27/25 - Goal is to implements by August if approved - P&E, GTS and Commercial contacts in APAC, LAC and MEISA to review and approve recommendation - Support requested from POD owner to help identify remaining contacts **5-28-25** - Follow up meeting set up with stakeholders on 6-5 to get status update **5-20-25** - Approvers for EU region received **5-5-25** - APAC P&E creating analysis and socializing with APAC leadership **4-25-25** Meeting held with the regions to review initiative, scope, completed milestones and next steps - Identify contacts in the regions for go/no-go decison - Align on implementation date - Provide country specific data for regions to complete their own analysis **4-21-25** Meeting scheduled 4/23 with the regions to review recommendation **3-29-25** Contacts in the regions identified and made aware of initiative. Next step is to schedule meeting with the regions review proposal and begin to record their questions/concerns 3-21-25 Demand type changed to business w/o tech based off feedback from Trade Tools team. Working with POD PMO to identify contacts in the region to review proposal to add all countries to the vague description commodity check. 3-6-25 Met with finance this week and working to finalize the LBC Last week, we discussed the opportunity of taking this initiative “Global” Based on initial discussions, we do think we can globalize this. 2-17-25 Vague/missing descriptions remain at a manageable level for manual intervention, goal is 400 or less per day. Gathering data elements to complete LBC EU team has reached out for assistance with vague descriptions related to EU Commission’s UCC mandate to use HS, discussion taking place to see if any of the ACAS tools can be expanded to other regions | E: L2 | Active | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: EIN/VAT # Field Change - AWB |  | 136570 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Adrienne Campbell-Porter | On Track | 3/10/26- Extend Technology start date milestone due to awaiting handoff to ART for work to begin 3/10/26- Received update from Architect and Solutions Manager that SC&I has been documented and waiting on review with ARTs. **2/19/26**- Moved to L3; Solutions Mananger and Architect working on SCL documentation and handing capabilities to the Commercial ARTs. **2/4/26**- Completed a preliminary SL3 readiness check with Karen McConnico **2/4/25**- Commercial GL was set in PV and submitted to next level for approval **1/28/26**-Received note from team with estimated release date of** May 26 2026 ** Request from April to update release date in the milestones/risk section of L2 and share Greenlight request in Planview. **1/26/2026**- Received PPM# 1837854 and updated in Planview **1/26/2026**- Submitted PPM request and sent to Management for approval **1/14/2026**-Epic ID created-0115946 **1/14/2026**- Worked with Yogesh to create Epic in Planview (Commercial Platform) **1/5/2025**- Determined Commercial was only impacted, DIrect to Single, and no PRT was needed. **12/19/2025**- Prioritization moved from 161 to 2 (Global Clearance Domain) based on EPC decision **12/18/2025**- Attended Triage meeting and Attorney Joseph McKinney also presented during meeting **9/30/2025**-(activated & moved to L2) **9.18.25**- CCH review with CCH lead Change of IO **5/8/2025**-Resubmitted planview request | G: L3 | Active | L3 | 2026-04-01 | 2026-07-06
Business w/ Tech Initiative: Duty Deminimis removal in the European Union |  | 187281 | Business w/ Tech Initiative | FXE GC - Regulatory/Compliance | Global Clearance | Daniel Roca, Sara Lizama, Emily Woestenenk | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2026-07-01 | 2027-03-02
Business w/ Tech Initiative: EMR OTC - Optimize Inbound Ancillaries Offer | 9104 | 7794 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Liya Yakupova, Dora Silva, Alix Perret, Aseem Khanolkar | On Track | **09/15 DS** Service Launch * Now available for shipments to Germany, France, Ireland, Great Britain, and Northern Ireland * Applies only to purple shipments with interception requests * Fee: €3 / £2.50 per shipment * Discount issue resolved – fees now applied correctly Operational Notes * Clearance teams must apply surcharge per logic groups: * DEFR, DEFR AUTH, DEFR AUTH_A, DEFR DETAILS, DEFR_A * LC CLR INST, LC CLR INST REQ, DEFR AUTH_A (GB/XI) * HOLD & Variants * Systems and billing updates in progress * FAQs available in attachments * Errata: CCRs removed from logic before Belgium launch due to ambiguous usage Results: * Waived Revenue: 38% * Storage Revenue: $358,860 * Hold & Notify Fee: $13,280 ________________________________________________ **08/13 DS:** * Belgium Live: Discount issue affecting customers outside 5 markets; Ship-to-Collect teams informed. Limited impact expected. * GB/IE/FR/DE: Service offered without charge. EU approved MTP for Aug 18. * Comms: Sales Q&A update needed; no customer comms required; Ops comms completed. * Implementation: UAT readiness pending confirmation; access to L5 test may be needed. EU HPU validation covered during absence. UAT 'Go' decision Aug 13, pricing load Aug 15, clearance & HPU upload Aug 18. Results: * Waived Revenue: 34% * Storage Revenue: $319,616 * Hold & Notify Fee: $1,578 ___ June 24 2025 - AP : L4 Date is still October, 3 months after HOLD & NOTIFY introduction planned in July RISK: Hold & Notify fee: delay from either EU Clearance or US REV. AWARENESS: We won’t achieve full scope due to limited country coverage in this initiative, expansion to be covered by new initiatives e.g. Gemini 2.0 and/or Harmonizing vendor application. IN PROGRESS •Prepare introduction of Hold & Notify new fee in GB, IE, BE, FR & DE (1) EU Clearance development - Change in the logic agreed on June 17th - New development ETA on June 25th (2) New charge code load by REV in the US on July 13rd - UATs on going (3) GoToSales / GoToMarket comunications request sent by Ji Mariano on June 13th (4) https://www.fedex.com/en-gb/ancillary-clearance-service.html change request sent by Liya Yakupova to Renita Banks on June 10th (5) Clearance operations communication shared by Dora Silva to the team for review on June 18th COMPLETED •Storage fee automation in GB IE FR DE & BE CANCELED •Storage fee automation in DK PL FI CZ & HU May 13 2025 - AP : L4 Date is still October, 3 months after HOLD & NOTIFY introduction planned in July RISK: Hold & Notify fee: delay from either EU Clearance or US REV. AWARENESS: We won’t achieve full scope due to limited country coverage in this initiative, expansion to be covered by new initiatives e.g. Gemini 2.0 and/or Harmonizing vendor application. IN PROGRESS •Prepare introduction of Hold & Notify new fee (1) EU Clearance development - Completion now expected by the end of this week on May 17th (2) New charge code load by REV in the US on July 25 COMPLETED •Storage fee automation in GB IE FR DE & BE CANCELED •Storage fee automation in DK PL FI CZ & HU Feb 19 2025 - AP : Only update is status being "On Track" instead of "Attention Needed". All other Jan 23 2025 updates remain the same. Feb 03 2025 - AP : No further update. All Jan 23 2025 updates remain the same. Jan 23 2025 - AP : L4 Date has been updated to October, so 3 months after HOLD & NOTIFY introduction planned in July RISK: Hold & Notify fee: delay from either EU Clearance or US REV. Chris Gibney updated Mark Ruddock on Jan 23, 2025, that Hold and Notify cannot make April 2025 as stated before, but July 2025. AWARENESS: We won’t achieve full scope due to limited country coverage in this initiative, expansion to be covered by new initiatives e.g. Gemini 2.0 and/or Harmonizing vendor application. IN PROGRESS •Prepare introduction of Hold & Notify new fee •EU Clearance analysis for DK PL FI CZ & HU Storage fee automation - Delayed to April 2025 NEXT STEPS •Introduce Hold & Notif | I: L4 | Active | TEMP L4 - Enter L4 | 2023-04-03 | 2026-04-10
Business w/ Tech Initiative: Radius - Revenue And Duty tax Improvement with Uni | 28222 | 8046 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Sean Brady, Terri Tennison | On Track | 01/04/25 ON HOLD - Information still pending from EBS (Bad debt and uncollected D&T data) Follow up request to EBS scheduled 02/04/25 On Hold - waiting for EBS/STC to provide data and resource to commence project - Meeting to be held Mond 3 March to review | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2023-05-15 | 2025-04-30
Business Only Initiative: Global Duty Drawback Expansion - United Kingdom | 67317 | 6803 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Janice Caudill | On Track | EU Marketing re-organization in progress; Pending EU Marketing resource assignment for I/O ownership. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-01-12 | 2024-10-18
Business Only Initiative: US Expansion of Special Brokerage Processing (SBP) | 64809 | 6791 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Ashu Rawat, Janice Caudill | On Track | 5/14 0 mature benefits. The scope of this init changed to product promotion. All planned milestones are completed and this init needs to be closed out now. 5/5 Working to close out this init. The scope was changed so there is no financial results attributed to this initiative. 4/11 - Fee trasition and waiver reduction will both be owned by pricing in FY26. This initiative has been updated to US SBP promotion, is completed and will be closed out. | K: L5 | Completed | L5 | 2024-06-03 | 2025-04-30
Business Only Initiative: Drawback - Retail & B2B | 2841 | 8932 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Erica L. Hanson, Heather Szwajda, Ashu Rawat | Some Issues | 04.08.2026 - Export reporting and documentation for shipments when FedEx serves as the export carrier and/or export broker continues to be a significant bottleneck. As highlighted during last month’s DRIVE call, the Drawback team is currently unable to support customers requiring this reporting, resulting in missed customer opportunities and potential revenue loss. At this time, this remains a material risk to the Drawback initiative. Any progress or guidance on how the Drawback Department can obtain access to the necessary export reporting and documentation would be critical to mitigating this issue. 03/27/26 - Changed IO to Erica Hanson, I will be the back up. Revenue: * January = $1,250 * February = $104,796 02/02/26 - December revenue total = $20,754 12/15/25 - November revenue results = 125,244 11/24/25 - Finally received actual finance numbers; and updating Planview for all of FY26. Changes to July through October as follows * June = $79,981 * July = $148,811 * August = $37,611 * September = $39,880 * October = $153,838 Duplex programming issue is reason for low numbers, not able to capture all of MYT drawback to the zero quantity issue. Issue continues to be an open item for IT. 9/24/25 - August revenue was $40,813, actuals have been updated. The revenue is low this month because our largest retail account, (MYT) is currently having problems as broker entries are reporting zero quantity due to smelting tariff changes allowing users to input zero quantity. On 9/23/25 Bill Schweitzer moved this isse to Karen Standardi for resolution. Cannot file any claims with CBP until this issue is resolved. 8/7/25 - Received plan from Bill Schweitzer: FY24FY25FY26FY27FY28 $1.9m$3.2m$4.5m$6.2m$8.5m Moving to L5 7/15/25 - Bill Schweitzer is waiting on business case from Larry French, (Sales - Brokerage Overlay Team) and Dan Lange, FXL Finance). Oncer we have this approved, this initiative can move to L5, and completion. Updated June Financials at $79,981. 5/19/25 - FXL Sales continue to work on drawback opportunities as schedules allow, but no dedicated time allocation (e.g., 12 hours/week) is currently enforced. Team has presented to 7–10 customers so far, with ~$1.75M in potential revenue identified from five qualified leads. At least two customers are self-filing and several others are likely with competitors. Tracking is being done via iSell. 5/19/25 - Updated April financials - $191,304 5/5/25 - Negative variances are due to dips in data and claim filing from customers. Drawback is not a business that can be expected to bring in the same amounts of money month over month. Entirely possible to make zero dollars one month, and over $500K the month after. Revenue needs to be reviewed at an annual viewpoint instead of monthly or we will always have a negative variances. We have seen an increase in Sales from the Brokerage Overlay Team, 8 potential new customers in the past 2 weeks from Account Executive Ryan Fajen: Pro-Spin Sports Inc Mark Zumbahlen Inzawa Tech Koenig & Bauer US Inc ATS Electrolube Bobst North America X-Ray Optical Systems (XOS) Genadyne Biotechnologies 4/15/25 - Added actuals for March - $159,506 from department numbers, have not received the final from Finance. 4/9/25 - * Per Dan Lange, MD of Finance, Bill Schweitzer requested Larry French review the business case with Thayne to narrow in on the FY28 financials. Cannot move to L5 without this update from Finance. * Still waiting for March financials from FXL. 4/2/25 - Still waiting for March financials from FXL; Waiting for 3 months of revenue from moving to L4 to L5, expected timeframe July 1, 2025 to receive financials. 3/17/25 - Dutycalc software payment of $54K to be paid this month in March 3/3/25 - Febraury Financials not available yet from FXL; will update as soon as available 2/24/25 - Moving to L4 Status with current financial reporting attached. 2/17/25 - Total revenue for January is $85124 01/02/25 - List | K: L5 | Active | TEMP L5 - Enter L5 | 2023-02-17 | 2025-05-30
Business w/ Tech Initiative: FedEx Clearance and Trade Solutions | 93475 | 9237 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Janice Caudill, Ashu Rawat | On Track | 6/13 Changing status to "On Hold". Initial effort that was supposed to be requested through this init is already completed, but keeping the init in PV for future development work. 5/14 Updating from Enabler to Growth init since it doesn't meet the new Enabler requirements. 5/5 iSell development complete with 1 error that will be resolved in May. We can go ahead with it. Working on Sales communication. 4/11 - POC is running (starting 1/20) on a temporary workflow until iSell development is complete. Expected by 4/21. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-05-21 | 2025-05-20
Business Only Initiative: ETD - Increase Global Adoption FY'25 goal | 84833 | 6792 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Harsha Thokala, Zahra Taqi, Janice Caudill | On Track | March 21st 2025 - KPI's for FY'25 were recorded in #8817 as part of L5 reporting. That will be deleted in #8817 and now be reporting in #6792 to ensure FY relevant KPI's are recorded appropriately, as advised by ESPM. Continuation of #8817 - ETD-Increase Adoption by 10%, ETD global adoption goal being pursued and accomplished. Aug 4th 2025- This initative will be cancelled based on leadership direction to track the adoption through QBR's reporting and not through Planview | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: Global Expansion of Special Brokerage Processing | 71068 | 6790 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Sanghamitra Panda, Ashu Rawat, Janice Caudill | Attention Needed | 4/27: Analysis in progress on EU anciallry services similar what US SBP provides in response to Mark Ruddock's question on existing offerings in EU. 4/20: No new update for this week. 4/13 update: Met with APAC leadership on SBP. APAC wants to do SBP, but operational alignment is needed as part of their pre-work to avoid issues that US SBP is currently dealing with. They will also identify bigger markets (Japan, Taiwain) for pilot where the clearance is complex. 4/6 update: Per leadership meeting with EU, they cannot support SBP expansion due to higher priorties with EU Deminimis. CA has decided to pause the work due to resource constraints. 3/30: Still waiting on next steps from SCO team. Dependency on finance to provide inputs for bus case. Working on updating milestones in PV. 3/23: No new updates for this week. Waiting to get inputs from finance for Bus case refresh. EU/APAC alignment scheduled early April. 3/16 update: Regional alignment discussion with EU/APAC pushed by 2 weeks. Waiting to hear back from SCO team on next steps. Bus case revision in progress. 4/11 - Working with LAC to finalize potential SBP bundle. Working with APAC from POC customer. EU resource update by the end of May. 10/27: Met with regional marketing leads on 10/15 to discuss SBP expansion opportunity. APAC has assigned resources for SBP expansion. Other regions: reevaluation of the opportunity needed 12/29: APAC continues evaluations of SBP expansion. CA and LAC teams started assessment on SBP expansion opportunity; meetings scheduled with respective marketing partners early Jan to align with. No updates for EU team. 1/12 update: Ability Tos and Financial fields have been entered in PV. Sang attending the L2 triage meeting this afternoon to discuss the init with architects and commercial teams. Met with regional marketing partners over the last week and there is some traction from regions on this effort •APAC, CA, and LAC are evaluating SBP expansion •EU wants to reassess the business case for EU scope of work to see the size of the prize before taking action on priority discussions with leadership 12/19: From the first initiative assessment for L2, RMIC determined the RMIC impact is too small. SCO perspective – has reviewed ownership and will do another L2 assessment to determine if PRT is right path. From regions: EU and CA assessments/bus case still in progress. LAC: meeting to gather updates. APAC: no update 1/26: System impacts analysis work in progress. A wholistic framework for Global SBP (WIP) 2/9 update: Implementation cost assessment done by finance team. 'Global Clearance' ESI approval complete by Jennifer. Jonathan helped create a PDSM ticket to update ESI field in PV. Working on global SBP framework and roadmap for regional review and alignment later this month. 2/16 update: ESI updated in PV for the init. Global SBP template and draft roadmap created for regional review and feedback this week. EU most likely not proceed with SBP at this time due to other priorities. 2/23 update: Reviewed Global SBP roadmap and template for gathering regional requirements with regions (some more follow up scheduled this week). LAC: Re-evaluating the target countries and pilot country for SBP. CA - Started looking at the bus case. APAC; meeting this week to align. 3/2 update: Pushing for CA and APAC regions to submit their assessments with SBP requirements, pilot countries etc. Meeting finance this week to review existing bus case with assumptions and get feedback for any revisions. Waiting to hear back from SCO team on next steps. Next: align with regional team for business case completion for L3 3/9 update: Met finance (David) this week to review existing bus case with the original assumptions and received feedback - Working on updating business case with latest volume numbers (David will provide this for FY26), SBP fee rate, costs associated etc. Reached out to FXL finance asking for US SBP resource related numbers/costs that can be used | E: L2 | Active | L2 & CCH | 2025-01-01 | 2025-02-13
Business Only Initiative: Global Broker Select Option(BSO) Fee Improvement |  | 92503 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Joshua Jaffe | On Track | **4.16.26** - L3 QA completed on 4/16/25. Approved to submit to L3. Janice Pittman/Domain QA Expert Review **4.9.26** - Submitted for L3 QA **4.3.26** - No updates **3.27.26** - MEISA received approval from Marketing MD to proceed with fee change. Updating timeline for implementation. **3.20.26** No updates **3.13.26** No updates **3.6.26** - Working on EU/APAC specific updated impact assessments to improve implementation timing, current target FY27. **2.27.26** - Received feedback from EU target date for BSO fee change will be FY27 - Current fee change implementation schedule: - US/CA - implemented Jan 2026 - MEISA - Target Apr 2026 - LAC - Target FY27 - EU - Target FY27 - APAC - TBD **2.20.26** - Working with EU/APAC contacts for implementation plans/timing on fee structure change **1-29-26** - MEISA plans to implement fee structure change in April 2026. Comms work underway for the change. **1-12-26** •Pending implementation timing from APAC, EU and MEISA regions, update request sent week of 1-5-26. **12-3-25** MEISA (Next update in 2 weeks) - April 2026 still looks achievable - Going to local RMC for feedback/approval, no date set yet - Determine GTM/GTS needs APAC - No timeline yet but will have a similar timeline with Europe - P&E and GTS also reviewing BSO fees, call to take place to better align. **11-25-25** - US/CA implementation Jan 2026 - US – Announcement went out with GRI updates in Sept - CA – Announcement going out 12/5 - MEISA – Targeting April 2026 to implement change - EU – Reviewing with rest of commercial initiatives in Jan to determine priority and timing - LAC – Targeting CY27 to implement change - APAC – Pending timeline details(Last f/u sent 11-14 to Mimi Yiu) **11-17-25** MEISA - Targeting to make update April 2026 EU - Will review in Jan2026 with the rest of the commercial initiatives LAC - Targeting CY27 for implementation **11-14-25** Follow ups sent to APAC, EU, LAC, MEISA regions for implementation timing plans **11-3-25** US/CA - target implementation Jan 2026 Pending plans from APAC, EU, LAC, MEISA regions to finaize timing **9-22-25** US/CA - target implementation Jan 2026 EU/LAC - target implementation Jul 2026 APAC - pending feedback, Betty working directly with Maureen Hoo to align; Josh to follow up this week for update **9-4-25** - Init brought to MD GPRICE to present recommendation to the regions, gain alignment on implmentation date and support from Pricing in the regions to set BSO flat fee for their region: - US/CA - confirmed Jan 2026 implementation date and rate - Pending confirmation from remaining regions. **7-3-2025** - Updated revenue impact analysis completed **5-30-25** - followed up with remaining regions for list rates - LAC - John Rodriguez - EU - Robert Anghel **5-16-25** - List rates received from APAC region **5-12-25** - Pending list rates from regions to update revenue impact assessment(received from CA, Josh followed up with remaining regions for updates) **4-30-25** Held meeting with regional marketing and pricing contacts; working on below action items from the meeting. - Update revenue impact assessment to include current capture rate for BSO surcharge fee and invoice adjustments - Request made to regions to provide missing list rate for Broker Document Transfer fee - Take to RMC in July i/o Spetember to give regions more time to work on system/service guide udpates **4-7-25** Pricing team confrimed BSO rate is determined by country-specific rate scales; each region will need to approve new flat rate. Not an IT impact but a commercial decision that each region will need to make. Meeting scheduled week of 4/21 to review proposal Marketing/Pricing in the regions **4-4-25** BSO fee change to flat rate approved by Betty Feng/Hrishikesh Yaligar; Pricing confirming if their approval was for Global pricing or US only. Unknown if BSO fee rate is determined by origin country, destination country or payor country; | F: SL3 | Active | SL3 Domain Lead Approval | 2026-01-01 | 2027-02-01
Business Only Initiative: ETD-Increase Adoption by 10% | 1126 | 8817 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Harsha Thokala, Zahra Taqi, Janice Caudill | On Track | The initial concept was that increased adoption would reduce cage rates and volume of cages, resulting in lower costs of labor with fewer FTEs required. However, labor costs have been rising. Init #1126 owners and stakeholders (from Marketing Clearance Products and Solutions, GTS P&E, and Ground Ops Finance) met with our McKinsey consultant to understand the outcome and determine the best course of action. The metric used to measure the cost of labor to be attributed to DRIVE #1126 is an approximation, using total clearance labor costs minus those for the Flux Capacitor DRIVE initiative. This hypothesis implies that *total* labor costs would decrease, but they have increased. The reason for this is that there are several factors that influence labor costs and there is no way to isolate labor impacts from Init #1126. Further, it is not likely that the FTEs would be reduced with a reduction in cages - it is likely that they are not dismissed but that their focus changes to a different type of clearance function. The team recommends abandoning the use of labor costs as a KPI to measure the effective of this initiative. It is agreed that it is implicit that an increase in ETD adoption and reduction in overall cage volume will reduce costs. The team recommends setting the labor cost reduction objectives and reported data to zero retroactively and onward. This recommendation has been taken to the FO team and approved. Once the FO team zeroes out the target KPIs, we will set the actual KPIs to zero. The team will continue to use adoption rates and reduction of ETD-related cage rates to compare the actual cage numbers versus what the expected cage volume would have been if no ETD efforts had taken place. This difference, multiplied by the cost per cage, gives us a way to compare results with the original business case to determine success. Now that the initiative is in L5, the data from 2 FY's for ETD indicate a reduction in cages by a factor of up to 5.2X (non-ETD has 1 cage in 10 shipments, while ETD has 1 in 52 and EWO has 1 in 47. | K: L5 | Completed | L5 | 2022-09-01 | 2024-05-31
Business w/ Tech Initiative: EMR OTC – Storage Fee (Canada) Enhancement |  | 104469 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Kadambari Bahl, Cristina A. Pallotta | On Track | 3/27: • Submitted for greenlight step for L3, awaiting addition to 4/8 CPEL from Commercial. SCO wants further information before giving greenlight on Planview . Last communication from them on 3/24: L2 Architecture has not started yet with SCO-Clearance, we informed them just yesterday. It’s early to arrive for Greenlight step. 3/23/2026: • Architectural Review Meeting (3/23) where SCO, RMIC and all teams aligned that this init is ready to go direct to solutioning and go to L3. Christopher Watts supervised edits on Planview. •Awaiting next steps from Christopher Watts, certain processes to be followed to get to L3 on Planview which need to be init by his team. 3/20/2026: •Architecture Review meeting on Monday before the pod call scheduled by SCO & including RMIC •CARE team met with CA GTS Team to share IT findings and ask for more technical details to continue their testing 3/13/2026: Kaleigh / Demand shaping team looking at getting this moved to commercial from SCO lead to ensure we can get to L3 quickly- update expected next week (16th March) 3/9/2026: Demitra has looked at having the CARE Art do the calculations and they’ve agreed that they can do it 2/25/2026: On High Priority Initiatives for FY26 (Kelly Rowland), flagged that we are waiting for architectural resource assignment since Sept 2025, Enterprise Ranking 103, Domain: 17 1/30/2026: Recent update given to Global Clearance Team (Enterprise Architect Enablement Team, Kelly Davis) also flagged to Domain Lead Janice Caudill that no response from SCO 1/26/2026: No update given from SCO team , exploring alternatives ***2025 Updates*** Week of February 10, 2025 * Storage fee request/business case presented by Initiative Owner (Cristina Pallotta) in Triage Meeting - Air & International Domains (February 12, 2025) validating demand type (business with tech), reported value ($1-5M), Drive Domain/Pod (Global Clearance Domain/FXE GC - Revenue Generation) * Decision submitted to SL1 * Request sent to Pod Lead (VP, Thomas Wicinski) for approval and initiative owner assignment in Canada (Cristina Pallotta) Week of March 10, 2025 * Confirmation by Enterprise Demand Management & Governance lead (Paula Cadle) that Storage Fee Strategy Sequence ID 104469 approved by Pod Lead (Tom Wicinski) Week of March 17, 2025 * Planview request approved for L1 lean business case development * Added to Global Clearance Revenue Generation Pod (weekly meeting) Week of March 24, 2025 * Solidify & update financial required fields in L1 lean business case development with domain finance lead guidance (David Spradlin) * Review Planview status & prioritization in Global Clearance Revenue Generation Pod (weekly meeting) * Senior leadership visibility on prioritization and alignment on business need from Canada Product & Digital Marketing (MD, Manjit Virdee), U.S/Global Products, Solutions & Business Agility (VP, Thomas Wicinski) and U.S Revenue Planning & Engineering (MD, Chris Gibley) Week of March 31, 2025 * IT & billing process review/alignment meetings to understand/define existing U.S billing process including Canada dependencies (Regulatory, Global Trade Services, Planning & Engineering and Product/Digital Marketing) & U.S dependencies (Revenue Strategic Programs, Revenue Planning & Engineering, IT & Revenue Services and Operations) Week of April 7, 2025 * Updated t-shirt to further support IT architect assignment Week of April 14, 2025 * Requested to Global Revenue Clearance Pod for IT architect assignment priotization in order to complete business with tech and business with tech additional info Week of April 21, 2025 * Update financial impact & estimated caged shipments due to CARM non-compliance/softsavings associated with penalizing caging shipments in result of CARM launch in alignment with Canada (GTS & Planning & Engineering) * Follow up on architecture assignment (connect with U.S, Cindy Gaspard to assist further) * Testing existing cage | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: EMR OTC– CARM Fee |  | 104475 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Kadambari Bahl, Cristina A. Pallotta | On Track | **Cancellation Request Initiated 18 August 2025:** **After reviewing with Canadian Regulatory, we have come to the conclusion that it is better to offset the loss of disbursement fee revenue through Storage Fee (Canada) - PV #104469 instead. After October 2025 there will no longer be customers in this category.** Week of February 10, 2025 * CARM fee request/business case presented by Initiative Owner (Cristina Pallotta) in Triage Meeting - Air & International Domains (February 12, 2025) validating demand type (business with tech), reported value (Max>$35M), Drive Domain/Pod (Global Clearance Domain/FXE GC - Revenue Generation) * Decision submitted to SL1 * Request sent to Pod Lead (VP, Thomas Wicinski) for approval and initiative owner assignment in Canada (Cristina Pallotta) Week of March 10, 2025 * Confirmation by Enterprise Demand Management & Governance lead (Paula Cadle) that CARM Fee Strategy Sequence ID 104475 approved by Pod Lead (Tom Wicinski) Week of March 17, 2025 * Planview request approved for L1 lean business case development * Added to Global Clearance Revenue Generation Pod (weekly meeting) Week of March 24, 2025 * Solidify & update financial required fields in L1 lean business case development with domain finance lead guidance (David Spradlin) * Review Planview status & prioritization in Global Clearance Revenue Generation Pod (weekly meeting) * Senior leadership visibility on prioritization and alignment on business need from Canada Product & Digital Marketing (MD, Manjit Virdee), U.S/Global Products, Solutions & Business Agility (VP, Thomas Wicinski) and U.S Revenue Planning & Engineering (MD, Chris Gibley) Week of March 31, 2025 * IT & billing process to understand if opportunity to leverage existing fee and evaluate IT/development scope including Canada dependencies (Regulatory, Global Trade Services, Planning & Engineering, Brokerage Servicesand Product/Digital Marketing) & U.S dependencies (Revenue Strategic Programs, Revenue Planning & Engineering, IT & Revenue Services and Operations) Week of April 7, 2025 * Updated t -shirt sizing * Require architecture assignment to support/complete business with tech requirements and business with tech additional requirements Week of April 14, 2025 * Requested with Global Clearance Revenue Generation Pod for architecture assignment Week of April 21, 2025 * Requested architecture assignment in order to validate business with tech requirements & additional information fields (follow up with U.S, Cindy Gaspard to assist further) Week of April 28, 2025 * Review meeting (April 30, 2025) including Canada dependencies (Financial Planning & Reporting & Brokerage) & U.S (Brokerage & Trade Solutions) related new services offerings addressing needs arising from CARM as customs brokers to provide added value in evolving landscape as FTN Canada (FXL) as broker including: CARM Client Portal registration assistance, financial security consulting for RPP participation, training & Support for navigating CPP, compliance audits & risk assessments & development of digital tools for duty/tax calculations * Updated CARM impact cage analysis to solidify business value Week of May 5. 2025: * Review meeting (Target: 5 May 2025) including Canada dependencies (Financial Planning & Reporting & Brokerage). related new services addressing needs arising from CARM and what type of fees can be explored. | C: L1 | Cancelled | L1
Business Only Initiative: [APAC] Extend D&T Disb Fee to ROD AU PH | 33511 | 7861 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Si-Ying Chen | On Track | 5/18/25 uppdated April benefit USD240607 Initiative completed, will be closed 4/15/25 Updated March benefit USD239210 4/5/25 No rebaseline required - initiative launched since FY24, no incremental benefit in FY26 vs FY25 Obtain legal approval for pricing of disbursement fee Estimate the incremental revenue by the new pricing of disbursement fee Obtain FP&A approval of the estimated revenue Obtain legal, marketing, sales enablement approval for GTM material Approval from CMC/AECM of the new pricing and target launch date | K: L5 | Completed | L5 | 2023-05-02 | 2024-03-15
Business w/ Tech Initiative: [APAC] D&T Disbursement Fee rate adjustment (BTA) | 33509 | 7858 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Si-Ying Chen | On Track | 5/18/25 Updated Mar benefit (final) USD168350 Updated April benefit (initial) USD168431 Initiative consider completed and will be closed 4/18/25 Updated Feb benefit (final) USD150145 Updated Mar benefit (initial) USD167835 4/5/25 No rebaseline required - initiative launched since FY24, no incremental benefit in FY26 vs FY25 Obtain legal approval for pricing of disbursement fee Estimate the incremental revenue bring by the new pricing of disbursement fee Obtain FP&A approval of the estimated revenue Obtain legal, marketing, sales enablement approval for GTM material Submit PPM to MEM Rev IT to load the new rate of disbursement fee Approval from CMC/AECM of the new pricing and target launch date | K: L5 | Completed | L5 | 2023-05-02 | 2024-01-16
Business Only Initiative: [APAC] SCN Clearance Ancillaries | 65778 | 8051 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Jie-Ming Yang, Terry Cheung | On Track | 5/18/25 April benefit updated USDUSD288206 Initative completed, will be closed 4/5/25 No rebaseline required - initiative launched since FY24, no incremental benefit in FY26 vs FY25 Alignment with Finance for revenue estimation and validation logic for L2/3 approval Completed alignment with SCN Ops, APAC STC and WUH billing ops team to set up billing process Alignment with CN Marketing for GTM support Raised request to MEM GTS to update global ancillary webpage | K: L5 | Completed | L5 | 2023-03-01 | 2024-01-16
Business w/ Tech Initiative: [APAC] AU BTA Advancement Fee logic rectification | 89230 | 7863 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Si-Ying Chen | On Track | 4/16/26 Mar actual updated 4/6/26 Feb actual updated 8/13/25 July actual updated 7/8/25 June actual updated 5/18/25 April initial benefit updated 138390 March benefit adjusted to 136540 4/18/25 Updated Feb (final) benefit to USD119216 and March (initial) USD134085 4/11/25 Leakage due to seasonal lower vol in Jan/Feb by CNY also Feb number is lower due to lag of billing record, will update Feb record by next week 4/4/25 Rebaseline completed 04/05/25 At AU inbound clearance, there is a setting in corp billing system ADT since 1993 which waive the BTA advancement fee for account customer when the DT amount is less than AUD299, while the intention of advancement fee should apply to all customer whenever there is DT or Entry Fee advanced by FDX. Based on actual data in FY24, there are 150K shipment waived for advancement fee by this old set up, removing the waiver will allow us to resume charging advancement fee for shipment with DT<AUD299 and generate 150000*AUD20=AUD3M, divide by FY24 X-rate 1.43, the estimated recurring incremental benefit is ~USD2M/year Target launch date is Oct2024 or Jan2025 depending on prioritization of IT corp load | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2024-10-15
Business Only Initiative: [APAC] NCN/ECN Clearance Ancillary | 73611 | 8052 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Jie-Ming Yang, Terry Cheung | On Track | *Update March 26, 2026* The initiative has been running smoothly since entering L4 in October 2025, and the actual returns have well met the forecast. We plan to submit a request to move it to L5. *Update January 5, 2026* The initiative has been progressing smoothly as planned. It remains on track to move to L5 as expected. *Update August 1, 2025* Clearance ancillary launched in NCN/ECN on July 28. (Personal Luggage clearance surcharge in CN extended to the last GW of PVGIP) *Update May 1, 2025* Rebaseline completed, assume surcharge delay to June2025 (subject to development of CN & US tariff and market change) *Update April 1, 2025* The same ancillary is launched in SCN and this initiative is to launch the same ancillary in NCN/ECN. original plan to launch in March but now deferred due to uncertainty of US tariff on CN goods ----------------------------------------------------------------------------- Following the success of clearance ancillary in SCN that yields incremental revenue USD150K/month (>USD1.7M/year), we are determined to expand the ancillary portfolio to NCN/ECN. Data from operation shows the expected revenue for NCN/ECN is targeted as ~1.9M/year, leverage the same operations and billing process established in the SCN launch | K: L5 | Active | L5 | 2024-03-01 | 2025-07-28
Business Only Initiative: APAC Non-ETD Surcharge for APAC Non CN | 32771 | 6934 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Puteri Zamri, Tony Jin | On Track | 04/16 - Received email from Kiany Zhang, Sr. Marketing Specialist handling this initiative- informing the following: •Although APAC had an incremental revenue growth, but there is 7.8% loss of existing customers •The shipment vol and rev of existing customers dropped •Global team also suggested that we discontinue the surcharge and they’re not going to expand to other markets. IO has requested for a discussion; especially to understand better on how they linked the drop as direct impact to this particular initiative, and not on other reasons. Kiany will organise a meeting with the Global team tentatively on 04/30. 01/07 - Dec '24 numbers are lower than usual/expected, due to system down on Dec 3 and 4. Hence MAWB/Non-ETD shipment ship on those dates are exempted from MDH fee. 12/30 - Removed SG Ancillary from this initiative, as required by management and for Terry to reorganize the benefit for revenue related to DRIVE initiatives. The SG ancillary benefit is moved back to PV#91210 MY/SG/KR Ancillary Charges Review. All benefits associated with 12/12 requirements will be removed back to original input for Non-ETD Surcharge for APAC Non CN only. 12/12 - Added the SG Ancillary revenue. SG has a clearance solution for Google (Import Permit with Exceptional Handling) where we will charge SGD80 per shipment. It will go live on 1 Jan 2025 but trial run has started with Google since Nov 2024. 1 month has around 300 shipments so monthly benefit is around SGD24K (USD18K), with one year estimated benefit of USD261K. The plan is to also increase the price of 3 old ancillaries that will bring some benefit but volume is not so high, so total benefit for SG ancillary will be about USD250K/year. For now, forecast has been updated to include 16k for Dec 2024, and 18k for Jan 2025 to May 2025. This ancillary revenue is estimated to recur until Oct 2025. 11/05 - Approved for L5. No further reporting required for weekly, but to continue to input in Financials KPI and Impact until May 2025. 11/04 - Presented to Philip Cheng (VP Finance AMEA) to progress to L5 because the ETD adoption rate has reached a consistent full run rate starting June 2024. As of Sept 2024, ETD Adoption rate is at a steady 90%. The proposal to progress to L5 is approved. Amendment to be done on slide is to add on planview the benefit of ETD adoption to operations; of which is 'ETD adoption reduces failure on OS50 and more efficiency on pickup, cage and clearance processes'. 10/23 - Aligned with Aaron on requirements needed to present to Philip for L5. Since the revenue shows a stable recurring pattern, we will extend the revenue (which was previously planned to stop by May 25 at 85% adoption rate) until the point of Global Surcharge kick-off in Oct 25, and to compare the numbers against total forecast. Booked Philip's review on 4Nov. Copied from Wave: 2024-10-07: Based on the investigation, the following is observed and presented to FP&A on Sept 19, and further clarification provided on 20/9. Awaiting for feedback on next action: a. Customers converted to ETD to avoid the surcharge. The current adoption rate of ETD is exceeding the projections made in July which is quicker than estimation. b. Customers that are in scope continue to reach out to Sales for exemption. the exclusion of Hong Kong, Japan, South Korea, Singapore, and Taiwan. The sales team is adhering the exclusion process, with MD approval, to submit nearly all exclusion accounts between February and May. The submission is also quicker than estimation. c. Also to note that the why the revenue goes down drastically, while the adoption rate increases gradually, is because the denominator is factoring in the exclusion sales, which was very high starting June. Changes to MAGIC and ACCS required for TW will be taken up separately, as agreed with TW GTS lead and manager. It was never part of this initiative's milestone / objective. 2024-09-04: Escalated to IO to review the adoption rate difference (betwee | K: L5 | Completed | L5 | 2023-09-01 | 2024-05-31
Business w/ Tech Initiative: EMR OTC-[APAC] TW New Clearance Ancillaries | 89231 | 9428 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Beatrice Pan | On Track | 4/16/26 Mar actual updated 4/6/26 Feb2026 actual updated, Jan2026 actual updated upward as billing record mature 8/12/25 System is fixed, TW team has alignment with Sales and CE for how to answer question from customer, now the team is targeting to start charging the fee on 18Aug 7/22/25 The fix for ancillary rate calculation is loaded to production, team will perform re-test in next week, plan to start charging the new fee by 01Aug if the Fix works well in production 7/8/25 Latest update Ops find the ancillary calculation in clearance application has some error, IT is researching, will determine the actual launch date after fix the issue 6/11/25 IT features MTPed to enable the billing of new ancillary Align with TW Sales/Marketing to start charge offshore customer by mid-July, financial forecast updated 5/18/25 First batch of system feature support ancillary collection is MTPed 04/18/25 UAT testing still ongoing, target get system ready by end of May to launch the ancillary, but actual launch depends on marketing condition due to uncertainty of US Tariff to the market Update 01Apr2025 Original plan to launch in April2025, TW face a linehaul change that impact TW->US WCO cutoff time from 7pm to 5pm, TW mgt work with Sales to defer the ancillary to avoid multiple negative impact to TW customer at same time. New estimate launch date end of May, revenue start by June ----------------------------------------------------------------------------- TW is planning to introduce 4 new clearance ancillaries Storage Fee - NTD5/Kg/day with minimum charge at NTD50 per shipment starting on the 4th day of storage - estimate USD100K/year Additional Line item - NTD1000/shipment - estimate USD900K/year Returned goods - NTD800/shipment - estimate USD20K/year Abandoned goods - NTD100 (base) + NTD60/Kg - estimate USD2K/year The execution require ACCS interface with BFC for automated rate calculation and billing, target launch date April2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2026-03-31
Business w/ Tech Initiative: EMR OTC-[APAC] SG/PH Ancillary Charges Review |  | 91210 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung | On Track | 4/16/26 Mar actual updated 3/25/26 Feb actual updated 8/13/25 July actual financial updated 7/8/25 June actual financial updated 6/11/25 May actual financial updated 5/18/25 . Received approval and try submit L2 again, system ask to select name of approver for review impacted portfolio, looking for guidance 5/6/25 Resubmitted for L2 4/18/25 Completed Architect alignment, submitted to L2 but received feedback say rebaseline need to adjust, sent email to David Spradin to clarify as the rebaseline was done per his instruction Updated actual March benefit USD35615 4/11/25 Architect review completed, initiative fully launched, submit to next L2 3/31/25 Rebaseline completed on Friday, 3/28/25 SG Import Permit surcharge fully launched in Nov2024 and PH Disbursement Fee rate has increased in Jan2025 | I: L4 | Active | L4 | 2023-12-01 | 2024-12-31
Business w/ Tech Initiative: [APAC] Singapore - D&T bad debt reduction | 34891 | 6999 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Barbara Lim, Jean-Marc Klecha, Hardiansjah Rizal Kristanto | On Track | Go-Live is adjusted to Feb 2025 due to adjustment needed on customer communication verbiage as requested by Legal | K: L5 | Completed | L5 | 2023-09-01 | 2025-07-21
Business Only Initiative: [APAC] D&T Disbursement Fee rate increase (ROD) | 33510 | 7859 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Si-Ying Chen | On Track | 4/18/25 Updated March benefit USD10486 4/5/25 No rebaseline required - initiative launched since FY24, no incremental benefit in FY26 vs FY25 Obtain legal approval for pricing of disbursement fee Estimate the incremental revenue by the new pricing of disbursement fee Obtain FP&A approval of the estimated revenue Obtain legal, marketing, sales enablement approval for GTM material Submit PPM to MEM Rev IT to load the new rate of disbursement fee Approval from CMC/AECM of the new pricing and target launch date | K: L5 | Completed | L5 | 2023-05-02 | 2023-11-01
Business Only Initiative: [APAC] ROD admin fee for NZ | 33513 | 7862 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Si-Ying Chen | On Track | 4/16/26 Mar actual updated 3/25/2026 Feb actual updated 6/11/25 May actual benefit updated 5/18/25 Updated April actual benefit USD38,335 4/18/25 Initiative moved to L4 4/11/25 initiative fully launched on 3/17/25, actual revenue collected NZD37500 (~USD23734), beat plan 4/5/25 Rebaseline completed oN 4/5/25 Approval from CMC/AECM of the new pricing and target launch date Draft the GTM for the new fee Fully MTP of Gemini-BFC for all FDX inbound shipment at NZ to support the calculation and collection of the ROD fee | K: L5 | Active | TEMP L5 - Enter L5 | 2023-05-02 | 2025-03-31
Business Only Initiative: [APAC] TW Clearance Solution for AIDC | 89233 | 9430 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Beatrice Pan | On Track | 6/11/25 Latest update from TW Sales/Ops team, expect sign contract with customer in Aug, surcharge start by Sep 5/18/25 Latest update from TW Sales - contract with customer to be sign by July/Aug 4/18/25 Sales still working with customer AIDC to sign the contract, target to complete is still within May 4/5/25 Rebaseline completed 4/5/25 Launch delayed as pending customer to add FDX as their approved vendor while all operational and billing setup at FDX is ready. Sales is working with customer to sign the contract, new target launch date in May2025 ----------------------------------------------------------------------------- A local customer AIDC in TW demand special clearance and warehouse service and is willing to pay for additional service fee. We will set up NSB billing with new service catalogue to bill the customer on monthly basis, estimated vol 600shpt/month, each shipment charge NRT3500 - cost NTD200, margin=NTD1500. Estimated profit = 600121500=NTD10.8M, apply FY24 X-rate 30, estimated incremental revenue = USD360K Target launch date Nov2024 | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-06-03 | 2025-12-30
Business Only Initiative: EMR OTC-[APAC] Clearance Ancillary Waiver Review |  | 91187 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung | On Track | 5/18/25 Check the query of data and find that payor account data is missing, try work on the query to get the data and find that access right to specific EDW table required, apply access right 4/18/25 Received first cut of data query from Aditya Datla for waived ancillary record, will check after back from leave on 28April 4/4/25 No rebaseline needed as the start date is not confirmed yet Finding way to find the raw data of waived ancillary record in order to identify the top waiver accounts | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [WIN] CN Ecommerce digital solution by iClear |  | 91190 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Shan Shan Li, Vivien Zhang, Hugh He, Cash Shen, Katrina Yeung, Xiao-Lan Kathy Pei, Si-Ying Chen, Kathleen Tiu | On Track | 04/21/2026: Discussed with IT, this initiative has been open for quite some time, and the final gateway PVGIP requirements are still not finalized. IT recommends using a new Plan View ticket to cover PVGIP once the development scope is confirmed. Therefore, submit this Plan View to L4. 04/17/2026: on track, in progress collecting local requirements and preparing the development quotation 04/07/2026: CN holiday 04/06/2026, The team is currently working on the final export gateway, PVGIP, which has not yet onboarded the self e-commerce clearance system. We are collecting local requirements and preparing the development quotation. 3/22/2026: Export clearance: 4 new Customs EDI files MTP 3/6/2026: The e-commerce clearance system completed in import; export 4 new Customs EDI files will demo on 09 Mar, plan MTP by Mar. 2/9/2026:The e-commerce last mile delivery system Complete： The last version is released on Feb.8th 2026. And no further update for the e-commerce last mile delivery system. 2/9/2026: The e-commerce clearance system iClear development contract renewal process in on track; 4 new Customs EDI files are being developed, expect March 2026 UAT, taking account of Chinese Lunar New Year week. 1/26/2026:The e-commerce last mile delivery system In progress (next 1-2 weeks): The project team has UAT test for integate with SF. Next steps (next 2-3 weeks): And the last version is planning release on Feb.8th 2026. 1/12/2026: The e-commerce clearance system New development will commence after the competitive bidding process among the three development vendors is completed. The milestone may be delayed until the end of FY26 (May 2026). 1/12/2026: The e-commerce last mile delivery system In progress (next 1-2 weeks): The project team has SIT and UAT tests for integate with SF. Next steps (next 2-3 weeks): And the last version for e-commerce last mile delivery system plans to go live at the end of January.2026. 12/15/2025The e-commerce last mile delivery system Complete (last 2 weeks): Integrate with SF has been completed the development/coding task. And it allows user to book/cancel last mile and first mile delivery/pickup service to SF. In progress (next 1-2 weeks): The project team will have SIT and UAT tests in the following 2-3 weeks. Next steps (next 2-3 weeks): The system development for e-commerce last mile delivery system will be completed by the end of the Dec.2025. 11/25/2025: The e-commerce clearance system MTP is gateway-based, PVGIP export capability is still pending because: Requirements and quotation are incomplete. No contract supports new payment; renewal is in progress. This poses a risk of delaying the L4 gate on Dec 31, as noted in PV. 11/11/2025: The e-commerce last mile delivery system Complete (last 2 weeks): Go to production for integrate with JDL and enable user book/cancel order to JDL and capture JDL scanning events post to eOPS systems. In progress (next 1-2 weeks): Fix some online veriosn issues Next steps (next 2-3 weeks): Business requirement study and vender API analysis for the last one vender SF. At the same time, plans to breakdown to user story level. 11/11/2025: The e-commerce clearance system Complete (last 2 weeks): 3 new requests discussions In progress (next 1-2 weeks): put new requirements to stories Next steps (next 2-3 weeks): start development (1. export a list for imported returned goods 2. new customs EDI file for modify 3. simulate customs audit response when customs system down) 10/30/25:The e-commerce last mile delivery system Complete (last 2 weeks): integrate with JD logistis has completed the coding work and will go to SIT and UAT test. In progress (next 1-2 weeks): the IT team is testing the JD version and plans to release in next month. Next steps (next 2-3 weeks): Business requirement study and vender API analysis for the last one vender SF. 10/28/25: The e-commerce clearance system Complete (last 2 weeks): Export Operations: Transition export volume from | H: SL4 | Active | SL4 Domain Lead Approval | 2024-10-08 | 2026-05-29
Business w/ Tech Initiative: EMR OTC-[APAC] Regulatory Fee in AU NZ |  | 91207 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Terry Cheung, Liya Yakupova | On Track | 7/28/25 US marketing checked with Rev IT confirm feasible to set up auto charge code to support, continue to proceed this PV to next L gate below are the details of 3 new charges 1.AU DAFF Fee – auto surcharge for AU inbound LV, <awb value less than AUD1000> (AU gov already started charging) – AUD1.4M/year (AUD0.37 per shpt) = ~USD900K/year impact 2.NZ Low Value Import Air – auto surcharge to NZ inbound LV, <awb value less than NZD1000> (NZ gov will start by April2026) – 469564*NZD2.54 per shpt=NZD1192693=~USD700K/year impact NZD2.21 excl gst 3.NZ Low Value Export Air– auto surcharge for NZ export LV, <awb value less than NZD1000> (NZ gov will start by April2026) – 342887*NZD2.85 per shpt=NZD977228=USD590K/year impact NZD2.48 excl gst 5/8/25 Escalating to marketing VP for solutioning, hold back from submit to L2 as the solution will require global marketing support and global team may want to create a new initiative for this 4/18/25 Working on the tax treament advice for NZ LV Fee 4/4/25 No rebaseline needed as the start date is not confirmed yet Seeking alignment with AU/NZ leadership team to obtain support from APAC marketing to set up the surcharge | G: L3 | Active | L3 | 2026-01-01 | 2026-07-01
Business w/ Tech Initiative: Regulatory Fee to Compensate for CBP Fee |  | 84563 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Liya Yakupova | On Track | 4/7/2025 - Approved by RMC on 3/27/2025 to include FICP service in scope 3/31/2025 - Added Feb-25 revenue actuals, re-baselined to FY28 2/25/2025 - Jan-25 Revenue Actuals are in progress, implementation cost actuals entered 1/28/2025 - development compleeted by 11/18/2024, testing competed by 1/8/2025, launched to production by 1/13/2025 11/25/2024 - Development complete, testing starts 11/25; SL2 financials approved, submitted for Domain lead approval 11/11/2024 - Solutioning complete, Development in progress, targeting 11/18 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-31 | 2025-01-13
Business w/ Tech Initiative: Implement Storage Fee for FXE US In-Bound Caged Sh | 40649 | 7106 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Derek Barfield, Jonathan Tam | On Track | 9/26/23--In L1 stage. Verifying Business Case inputs for L2 approval. 10/06/23--Submitted for L3 (Planned) approval 12/12/23--Awaiting RMC review planned for Jan '24 2/1/24--Recurring Benefits updated to $1.9M to reflect updated scope: Cage reason codes: COMPO, DESCI, MFG, POA, with exceptions for shipments that contain one or more of the following PGA-related cage codes: ANTID, ATF, AGRI, FDA, FDAP, MEDS, TOXIC, and WILD. Previous NRB of $3.6M based on initial recommendation to add the following to the cage code logic that triggers storage fees: COMPO, DESCI, MFG, POA, INVMS, FDAPN. However, NRB has been updated to $1.9M based on three updated recommendations: 1 - Remove INVMS from scope because it's often misused and too many complex system concerns around the cage code. 2 - Remove FDAPN and TOXIC from scope, because both are PGA-related (i.e., should not be charging storage due to potential extended delays caused by a govt agency). 3 - Build an exclusion or "override" code for shipments that have cage codes that qualify for storage fees, but later end up with an additional PGA-related cage code, such as COMPO, DESCI, MFG, POA, INVMS, FDAPN, TOXIC (i.e., these shipments are exempt from storage fees because even though they initially were customer-driven cages, now they're primarily govt agency driven cages). 4/3/24 - L4 date has changed from Apr 30 to Oct 30, 2024, based on Chris Gibney decision to move to a later date. Initiative is waiting to be prioritize and approve to move forward. 4/9/24 - Made changes to the forecast costs that reflects the initiative until the project move to Oct24. Forecast cost from Apr24 - Oct24 is $0.00. 4/22/24 - Updated the one-time Implementation costs on the actual that reflects the plan forecasts for FY25. 5/6/24 - Updated the milestones since the initiatives has moved to a later CSR date 6/21/24 - Sizing completed 6/26/24 - Updated the milestone completion for RMIC prioritization 8/21/24 - Sales lead added to project 9/30/24 - Closed out the testing and development milestone 9/30/24 - Closed out Increased training for broker on cage coding | K: L5 | Completed | L5 | 2024-01-01 | 2024-10-30
Business w/ Tech Initiative: Implement Storage Fee for FXE US In-Bound Caged Sh | 1127 | 8049 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Derek Barfield, Jonathan Tam | On Track | 8/5/2024- On track with no new update. RMC decision to decouple from July CSR due to implementation concerns that the right cage codes/triggers upstream have not been identified. Clearance & Marketing teams reassessed cage code triggers to minimize impact to SMB customers. RMC approved the updated cage codes and new revenue estimate of $2.2M for Oct '23 CSR. Will go back to L2 and resubmit for L3 with new revenue estimate. 9/15/23--Uploaded updated business case for $2.2M and submitted for L3 approval. 10/16/23--Milestones complete. Project loaded in the Certified Software Release (CSR) over the weekend. Submitting to L4. 11/13/12--$68K in revenue for month of October (lower than target revenue due to fee launching Oct 20th i.e., not a full month) 12/12/23--$199K in revenue for month of November 12/8/23--$198K in revenue for month of December 1/16/24--$150K in revenue for month of January (lower than target revenue likely due to variance in cage rates) 3/9/24--$198K in revenue for month of January | K: L5 | Completed | L5 | 2022-01-03 | 2023-10-17
Business w/ Tech Initiative: Clearance PLC - Offshore D&T Disbursement Fee | 33044 | 6947 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Nick Bragorgos, Demitra Woodard | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2025-01-17
Business w/ Tech Initiative: EMR OTC - Global Export Clearance Fees | 33043 | 6946 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Liya Yakupova, Demitra Woodard | On Track | 8/27/24 updated L4 target date to Oct 2025 due to PRT backlog 8/5 pending PRT priority; revenue baseline will stay as is until L3 7/29/24 moved L3 and IT Assessment milestone to Sept 30th as PRT prioritized #6 in Commercial and #8 in Clearance PELs 6/4/24 attending Clearance Portfolio intake on 6/5, TCH next step is PEO Tech Sequencing, PRT assessment is still targeting July. Plan to update Revenue estimates with FY24 baseline by end of June 5/9/24 at the TCH Architecture review on 3/21 it was determined that commercial PRT assessment is needed to complete TCH. PRT assessment target is June/July based on commercial priority 3/19/24 Pending TCH Architecture Assessment, the next TCH Architecture Meeting will be held Thursday 3/21. On track for L3 on May 31, 2024 3/12/24 Initiative still on track to hit L3 by May 31, 2024. Global workshop is scheduled on 3/13 to discuss fee rationalization. 3/5/24 attached TCH questionnaire for DRIVE Domain Architecture assessment; moved L4 date to July 2025 based on updated prioritization 2/19/24 ready to TCH ready; requested Commercial Clearing House Approval via email 12/26/23 $25.9M estimated annual revenue Submitted request for L2 approval. Business case reviewed by finance. 9/22/23. $15M estimated annual revenue Submitted request for L1 approval. Working on business case. | E: L2 | Active | L2 & CCH | 2023-07-03 | 2025-07-21
Business w/ Tech Initiative: EMR OTC-Create New Fees for Other Partner Gov Agen | 1911 | 8071 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Nick Bragorgos, Demitra Woodard | On Track | 5/8/23--RMIC is looking at starting Other PGA next year due to higher priority regulatory items. 3/26/24 - Updated monthly impacts to reflect Jan '25 CSR launch 10/24/24 - This work is targeting April '25 CSR due to resources and revenue amount adjustment 4/2/25 - Due to the identified revenue valuation decrease, this work has been delayed to be work until likely Jan '26 and due to this change it is in the best interest of the project to move to the "On Hold" status for the time being. **NB** | G: L3 | On Hold | TEMP L3 - Enter L3 | 2022-12-01 | 2027-12-01
Business Only Initiative: [AE, ZA] [RT] Review the ancillary charges portfol | 36282 | 7042 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | Jignesh Joshi, Melissa Pinto | On Track | On track | K: L5 | Completed | L5 | 2023-06-01 | 2024-10-31
Business w/ Tech Initiative: EMR-OTC-Broker Document Transfer Fee Expansion |  | 108301 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Joshua Jaffe | On Track | **4.23.26** - Gathering system information from US ADT team to share with regions to determine if existing systems/processes can be used in the regions to expand BDT fee usage. **4.16.26** - No updates **4.10.26** - No updates **4.3.26** - Initiative presented at 4/2 MD GPrice - US findings presented to EU and LAC regions for validation - MEISA may already have a similar fee called Delivery Order, further research needed to determine if it covers same activities as BDT **3.27.26** - Targeting 4/3 GPrice to allow Pricing team time to review with leadership **3.20.2026** - Request made to be added to agenda for 3.27 GPrice **3.13.26** No updates **3.6.26** - Initial BDT expansion opportunity assessment completed, reviewing findings with Pricing this week to refine. Once completed will present findings for consideration to take to GPrice. **2.27.26** - Reviewing data received this week from Pricing to determine global opportunity for expanding BDT fee in new markets. - Received confirmation from APAC GTS they are also exploring the introduction of BDT fee for APAC inbound shipemnts. **2.20.26** - No updates **2.6.26** - Support and alignment request will go through GPrice. - Working with Pricing to gather data needed for that meeting. **1-12-26** - Working with regions to gather potential revenue opportinities for broker document transfer fee expansion to complete LBC. - Feedback received from APAC, pending details on which countries present largest opportunity. **9-22-25** - Initial assessment completed for Canada - Fee billable in Canada from Market and Legal perspective - Projected incremental annual revenue $2.9M for Canada - Identified 74 other countries not charging BDT fee, assessment underway to determine potential additional revenue opportunities - Enable non-US payor for BDT fee initiative created under PV#0007992 - Will need owner to be assigned; Josh setting up time with Demitra to review. **6-16-25** - Enable non-US Payor for BDT fee moved under its own initiative, PV#0007992 - Assessment to introduce BDT for Canada inbound scheduled to be completed by end of July 2025 **5-12-25** - EBS team advised no barriers to enable non-US payors for the Broker Document Transfer fee. Demitra checking with Betty/Chris one what the next step will be. Will be broken out as its own initiative. **4-9-25** CA assessment - Gap analysis for 3 billing scenarios completed; billing IOR, external brker or shipper - CA regulatory is researching regulatory requirement to share documents with external broker **3-20-25** CA Assessment - alignment that CA assessment would roll up into global planview init **1-9-25** Introduced Canada Marketing to the BSO initiatives and discussed dependendencies **Dec 2024** BDT assessment completed by US Pricing for US inbound BSO - No operational/billing gaps identified for Broker Document Transfer fee - $4.4M to $7M opportunity if we enable non-US payor for BDT fee - Feedback from the regions on enabling non-US payor for BDT - APAC GTS - Review by global and regional legal, if approved G2S/G2M new fee campaign - EU EU Marketing - No issues. vast majority of BDT fee in EU is billed to brokers doing clearance and then passed on to their end customer | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Building Core Ship APIs in FDX |  | 111199 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Robert Heatley | On Track | No longer needed. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Add Customs Value to Disbursement Fee Calculation |  | 114096 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Sakshi P. Pandey | Some Issues | 04/09/2025- Update 1. Ability To Statement: **As a Revenue Systems (ADT) stakeholder, I would like to be able to receive and integrate customs value data from regional broker systems so that fee structures dynamically align with shipment value, enable region-specific pricing strategies, and improve revenue accuracy across global markets.** 2. This initiative serves as an enabler for the following dependent initiatives: Both initiatives require the availability of customs value integration from regional broker systems into ADT to support Disbursement and D/T forwarding fee calculation and threshold-based pricing. At this time, based on the current Clearance roadmap, these are the only identified dependent initiatives. Additional dependencies will be incorporated as visibility into other regions becomes available. * **#91207 – APAC Regulatory Fee (AU/NZ) * #0018788 – EU Handling Fee** 3. NRB Alignment: NRB values for the dependent initiatives are currently being validated. * **For #0018788 – EU Handling Fee, confirmation has been requested from the initiative owner and will be updated once available. * NRB for #91207 –$2.19M** 04/03/2026- **Business Need & Justification**: Capability positions FedEx to respond more effectively to volatile tariff regimes, supports scalable international growth, and establishes a reusable framework that can be leveraged for future regional initiatives beyond the EU. The EU handling fee (18788: EU Handling Fee) is dependent on customs value thresholds to correctly enable, price, and operationalize low‑value shipments. Without this capability, these EU initiatives cannot progress, as downstream financial models and clearance strategies rely on this value. 07/22- QA review completed. Ready to be submitted to L2. 05/29- Submitted to L2 | E: L2 | Active | L2
Business w/ Tech Initiative: EMR OTC - Update IL Exp Declaration Fee (Reshumon) |  | 130313 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Arye Nitzan, Glenn Harris | On Track | Estimated cost received and loaded | E: L2 | Active | L2
Business w/ Tech Initiative: EMR OTC-Cage Reason Codes Storage Fee Computation |  | 130735 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Hakan Copur | On Track | This is Business w/tech which is not the desired state. That is why we have created a new one (10864 – assigned to SCO). Cancelling this one. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: COM - RMIC - Paper Commercial Invoice Surcharge |  | 180004 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Liya Yakupova | On Track | 1/29/2026 Per feedback updated baseline to FY25 and reviewed with Pod QA lead | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: US PGA Ancillary Fees |  | 180007 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Christina N. Finch, Brett Perry | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: APAC - Ancillary Services Fees |  | 180010 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Barbara Lim, Blaine Chen, Tan Han-Khoong, Abigail Lim, Mellyana | On Track | Dec’25 - Mar’26 Quick Win (Rate Increase, US$ 4.3M/Year) BSO: AU, ID, MY, PH, KR Storage: CN, ID, NZ, TH, TW, PH Multi-line Items: JP, TW =============================== Mar’26 – May’26 Top Revenue Drivers (US$1.1M/Year) SG: BSO, Storage, Multi-line TW: Enhanced Entry, BSO =============================== Beyond May'26 CN & Other Markets (US$ 1.7M/Year) CN: BSO, Multi-line (US$ 792K/Year) | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Test BwT_IO Splash_bkunwar |  | 180706 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Bibhusha Kunwar | On Track | On Track | K: L5 | Cancelled | L5
Business Only Initiative: [FD] Internal Consulting Dept. about Clearance, Re | 38483 | 7089 | Business Only Initiative | FXE GC - Revenue Generation | Global Clearance | John Stoten, Myrna van Wier | Some Issues | 04.10.2026 March requests = 6 (CN=1; KR=1; JP=3; TW=1) 03.10.2026 The Planview is still in L4. We should look to move it t L5 for sure but there is currently no benefit being recorded; the last 4 months are all negative YoY. February requests = 6 (JP=5; VN=1) January requests = 6 (TW=1; JP=4; KR=1) 13.01.2026 Program is not performing to plan. Requests are coming in but revenue generation is sluggish. December requests = 8 (JP=6; CN=1; TW=1) 12.12.2025 November output remains negative but request continue at a reasonable rate. 10 requests JP=5; CN=2; Hk=2; KR=1 11.09.2025 A number of customers have down traded compared to 2024 including the largest account moving away from FedEx to Europe. Result, negative recorded outcome. 7 requests CN=2; JP=2; KR=1; SG=1; HK=1 10.21.2025 - Positives. * Final Revenue figure for Septemeber is the highst ratio of target posted so far at 0.69%. * September requests were responded to within 24 hours for the 1st time 10.21.2025 - Formula fail has created an incorrect output for August this information has been re-dreafted. 10.21.2025 - Septemeber Revenue Figures are in and being posted Files for this month are low at 6 requests however this also reflects 6 more than September 2024 KR = 3; CN, JP and TH at 1 each. 08.14.2025 - Revenue is over 300,000 USD behind target this month and is set against a reduced shipping as compared to last year. As reported some issues with calculation have been found and this is being addressed. July files to be reported in Septembers figures will be a complete reversal thanks to one shipper supported. 08.13.2025 - Revenue figures are now being generated by Marketing in Europe. Some calculation issues still exist. Requests for July=16: JP=8; CN=3; ID=2; HK=1; IN=1; AU=1; The request from India will dramatically change revenue figures moving forward. 07.15.2025 - Requests for June=9: HK=4; JP=4; KR=1 07.15.2025 - Re-valuing oif June's figures required as calculations tool didn't capture all data. 06.12.2025 - May provided a better month in terms of requests numbering 12. Breakdown: AE=1; CN=2; HK=4; JP=4; TW=1 A positive turn is being marked to support manufacturer migration under project name 'Sinocare' AMEAEnquiries will look to align with CN Manufacuturers' relocationg to MY,TH & VN and prioritise these cases over the next 6 months. 06.06.2025 - Requests remain below target and revenue likewise. Furher exposure is being sought. Initiative is added to AMEA PPQA regional awards. 05.16.2025 - April 25, pressure constraints have prevented AMEA Helpdesk promotion/webinar Q&A sessions. April 25 provided 6 requests from origins as follows: HK=3; JP=3. 04.23.2025 - March 25 value increasd as compared to February but remains down on the overal initiative ambition. Points to note: * The initiative was not supported with additional resource to provide dedicated focus and responses. Activity comes from hours sacrificed within Clearance Solutions Network (Europe) activities. * Additional promotion is required through APAC sales enablement. New webinar to be arranged. 04.17.2025 - Request level improved in March to 13 from origins as follows: JP=6; CN=4; HK=3 04.10.2025 - March figures in build 03.31.2025 - Re-baseline calculations completed. KPI drifts to 2 days to respond to a request due to no dedicated resource and internal Europe pressures. Further promotion to extend the number of requests in to AMEAEnquiries@FedEx.com is required. Targets to remain ambitious through FY26. 03.11.2025 - Feb KPI revealed less usage, request origins: CN = 6; JP = 2 02.15.2025 - Januray KPI's loaded. More challenging in terms of results than expected. Variances of request are: JP = 5; CN = 4; HK = 1; KR = 1; PH = 1 01.24.2025 - Webinar presented 01.23.2025 with apprroval from the APAC Sales Advisory Board. Puropse and scope was clearly understood. Follow up actions due next week. New IOM planned fro March. 01.14.2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-02-05 | 2024-12-10
Business w/ Tech Initiative: Duty Drawback Tech Solution |  | 92478 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Heather Szwajda | On Track | 8/21 - On Hold | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: EMR OTC-Collect deserved BSO and DR Fees |  | 140199 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Barbara Lim, Chien-Hung Chen, Abigail Lim, Blaine Chen, Tan Han-Khoong | On Track | 2025/12/23: The new IO has been updated. Progress Update by Aaron 2025/12/23 2025/12/08: CEW - Aaron Chien-Hung Chen is no longer the IO. Aaron is checking for replacement name. L1 Architecture is noted as complete on PowerBi report; however, there is not a date or architect listed. Aaron to check email to see if he received the architecture document. Progress Update by Aaron 2025/10/16 On 2025/10/16, Update the “Ability To Statements”and the "Business Process and/or Operational Impact" fields. On 2025/10/8, there is both an opportunity and a risk that some local consignees may ask us to handle their shipments through our broker instead of relocating to another warehouse, as they want to avoid paying the BSO fees. On 2025/9/30, highlight the added value of this proposal—it helps protect our existing customer ASML, who prefers to hand broker tasks to another broker while still routing shipments through our warehouse. ASML contributes approximately USD 145K in monthly revenue. On 2025/08/14, Ashu provided feedback that the value is rather low. We plan to review this with the local CCO after the ancillary go-live stabilizes to determine whether additional value can be delivered for this request. Value Update by Aaron 2025/07/15 For IT: To have ISD's support to enhance TW IMP ACCS (local clearance application) to identify BSO shipments and calculate the corresponding fees based on our charging policy and the customer's profile. Without this enhancement, additional manpower would be required to manually calculate and upload the fees. For Business: To align CE, Sales, LMD, and Finance on the fee-charging structure and secure their support in driving revenue growth through effective fee collection. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: ATA Shipment for SHEIN from CN to LAC via US |  | 161887 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Tsz-Ki Jacky Chin, Marcos Heredia | Some Issues | 03/13/2026- Blocker remains the same, the profitability calculation came back as negative 02/20/2026- has been moved to L2, working on the additional input for L2 01/22/2026- Financials: • After the latest calculation from FP&A, the margin for this request came in negative Progress Made • Worked with FP&A and confirmed the margin is negative Blockers and Risks what is keeping the initiative from moving forward and steps taking to mitigate? The profitability calculation came back as negative 10/10- Updated required field to progress to L1 Triage The requestor has initated the Demand request and we in the beginning of triage 9/9: email received on 9/9, pending architects to process IT information, like Tshirt size, architectural documents, etc. to submit for next step (SS) | E: L2 | Active | L2
Business w/ Tech Initiative: Request Dev team for enabling ETD with IPD and IED |  | 97502 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Sreyoshi Bhattacharya, Meagan D. STONE | On Track | N/A | E: L2 | Active | L2
Business w/ Tech Initiative: BSO Transformation |  | 184881 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Joshua Jaffe | Some Issues | **4.23.26** - Enterprise ranking: 95 - Domain ranking: 17 - Current state, pain points and AB2 material reviewed with architects(Dana Coles, Mike Kneeland, Joffrey Lambergs, Chris Carlson) in preparation for BSO WS scheduled for next week. **4.16.26** - Enterprise ranking: 97 - Domain ranking: 16 **4.10.26** - Pending architect resources, EA focused on VB 1&2 - WS planned for end of April to align on key capabilities, high-level requirements, scope and dependencies. **4.3.26** - Moved to L2 3.31 - Working with Katie Wade for architect support for BSO workshop **3.30.26** - Document Feedback Provided/Included Janice Pittman/Domain QA Expert Review **3.27.26** - Enterprise ranking: 196 - Domain ranking: 9 - Reviewed in L1 Architecture Alignment weekly call, pending next steps from EPM for L2 submissions **3.20.26** - Enterprise Ranking: 186 - Domain Ranking: 9 - Archictect(Shahab) assigned for L1 review, onnce completed will be presetned at L1 Architecture Alignment call **3.11.26** - Exception request approved by Enterprise Business Architecture to allow Commercial to complete L1 architectural alighment to get moved to L2. Working with Portfolio Demand Shaping on updates needed in Planview. **3.6.26** - Enterprise ranking 184 - Resource needed for Enterprise Architecture review/document to proceed with L2 submission. - ESI changed from Global Clearance to Revenue Growth **2.27.26** - Enterprise ranking 148 - Primary Type of Value updated from "Customer Experience" to "Revenue Growth" - Reviewing global business plans for business case/NRB refinement opportunities and inclusion of transportation revenue associated with BSO volume. **2.20.26** - Enterprise ranking 149 - Reviewing global business plans for business case/NRB refinement opportunities. **2.16.26** - Enterprise ranking 150 - QA audit for L2 submission will be completed by EOB 2-17 **2.6.26** - Financials have been reviewed - AB2 statements provided to OW team, will be brought to EA team to be included in finalized value bundles - Pending IT owner assigment to submit PPM request, Jake reached out to Emilee James for guidance | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Virtual Clearance Consolidation Global Solution |  | 186545 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Meagan D. STONE | On Track | 04/10/26: Met with LAC team the week of 4/30 to understand the Southern Border distribution operating scenarios and ability tos that will be needed as part of the global distribution model. Meeting with EU week of 4/13 to discuss how the FXE/FXL IDD Max model may fit the EU's needs for a drop-ship solution vs the SpS Dedicated vehicle service option. Discussion on ability tos and value delivery of each scenario. 02/16/26: working with FXL to determine costs to provide VCC and other clearance 'widget', working on L1 deliverables 03/16/26: Met with FXL team on 3/9 for SHEIN model workshop. Met with APAC marketing team to discuss expansion of SHEIN pilot and collaboration on expansion opportunities from CN. Action items in progress: Specification documents for Pre-Paid SHEIN model and Collect FXL model. Enablement work needed to scale the Pre-Paid model to be discussed with APAC VCC team on 3/17, to understand the automation requirements for creating a virtual CCI. Cost comparisions between SHEIN/FXL shipments and standard FICP from CN to US analysis, week of 3/16. \ 03/23/26: Some deliverable delayed (costing model) due to APAC team being OOO. Discussion with APAC team on Pre-paid FICP model and expansion of Express Connect (VCC) outside of CN/HK OB determined that there is no "on-boarding" documentation for customers. Business rules in Express Connect are very specific to US IB. Team did get the systems diagram, which will need to be discussed with IT teams to determine whether CN systems can be used by other regions to expand the OB locations. 03/30/26: Met with APAC marketing team to determine roles for expansion of Pre-paid FICP model to other customer from CN to US, and then determine what needs to be true to to expand to other regions. Will be attending the Southern border workshop the week of 3/30 to assess S border needs (dropship distribution model), GAF and FXL future orchestration plan) with the VCC and Pre-paid FICP model. | C: L1 | Active | L1
Business w/ Tech Initiative: APAC - Pre-Payment (Direct Payment Processing) Fee |  | 190606 | Business w/ Tech Initiative | FXE GC - Revenue Generation | Global Clearance | Abigail Lim, Barbara Lim, Tan Han-Khoong | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Integrated Network Demand Technology |  | 128031 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Rodrika Thompson, Roshelman Breakfield, Geovanni Gopar Reyes, Marvin S. Elliott, Fawzi Cheikh Bessaih | On Track | 03/03 - As we clean up Planview, I am cancelling this initiative and we will utilize 157709 to represent this work. 01/16 - Approx. $18M Palantir contract in the works. 10/14 - Entered in Enterprise KPIs for initiative 06/20 - Spoke with Brandon Slone (IT Mgr) to ensure that I have covered everything on my end for the L1 LBC. 07/10 - Just received access to the architectural folder to attach to the initiative in Planview. Also, in the process of changing ownership over to the designated assignee of this initiative. 09/11 - The $500M is coming from an assessment that McKInsey did when we began this initiative. | E: L2 | Cancelled | Portfolio Greenlight
Business w/ Tech Initiative: LHIF - EU Bunker KPI |  | 106792 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Chuck Pounders | On Track | .This Initiative will be cancelled per Andy Pratt - INC034083765 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC | 2024-07-19 | 2024-07-19
Business w/ Tech Initiative: URSA/LSSI Rethink- Track 1 - LSSI and URSA Build | 58284 | 7247 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Stacey Robinson, Sudheer Kumar Pendem | On Track | 5/31/26 OFACT Approval UI with (Location, Postal/USPS, OD Matrix datasets) for current monthly process pushed to production for (July URSA) 6/15/26 OFACT Controller – monthly process (data providers use OFACT Controller; files backfilled to current URSA builder to produce URSA5 files beginning with July; Cherwell URSA-WMS retired); Bi-monthly URSA5 File Builds with current URSA File Builder starting mid-July.​ 7/31/26 Transit data to be provided using the new OFACT approval UI starting with September URSA​ 9/30/26 OFACT File Builder with automated smoke testing (automated validation of critical functionality post-release, replacing today’s 12+ hour manual production checkout) and weekly URSA5 releases 12/31/26 Updated Consumer Guide 3/31/27 OFACT6 with effective dating, supporting daily releases 12/8/25 **Overview and current posture** •Track 1 remains on track with near-term milestones focused on data readiness, process validation, and stakeholder alignment. The plan emphasizes completing key data readiness activities (OFACT datasets, daily file enablement, and validated data processes) while advancing business process validation and documentation tools. •The program is actively progressing through Phase 1 and into Phase 2 activities, with a continued emphasis on delivering a robust data and process foundation to enable later production rollout. •URSA is getting rebranded to OFACT (Operational Fulfillment and Availability Coordination Toolkit). The reasoning behind this is that the URSA acronym stands for Universal Routing Sort Aid. From that context, URSA is just the Routing Prefix used by operations to aid in the sortation of packages. OFACT terminology is more applicable to the overall purpose of this data that is provided for Shipment Creation and Operational fulfillment of the shipment requirements. **Key near-term accomplishments and focus areas** **•Technical updates:** oOFACT daily file enablement MVPs are progressing, delivering validated data flows (Postal/USPS/other data enables) and data-validation dashboards. oO&D Matrix data refinement, and UAT of Postal, USPS, and Location files in progress oValidation tooling and business process drafts are in flight to support accelerated decision-making and alignment with LSSI. **•Business process updates:** oValidation and governance processes are being refined, with documentation tools for (GSAA, GSRG) progressing in parallel to ensure consistent handoffs and traceability. oCollaboration routines are being clarified with the data providers and consumers to ensure timely feedback and issue resolution. Upcoming milestones (next 2–4 weeks) •Complete the next set of OFACT data validations and UAT readouts. •Finalize the business process validation drafts and align cadence for ongoing reviews. •Complete the data change and validation process plan for the GSAA/GSRG business processes. •Prepare for the next round of consumer adoption discussions and readiness reviews with key stakeholders. Top risks and issues •Consumer adoption: Some consumers may not commit to daily OFACT consumption at initial rollout in early 2026. Ongoing engagement and phased onboarding will be critical. The rollout plan for the adoption is available in the Daily OFACT Integration Migration Guide for Consumers. The rollout will be similar to the URSA4 to URSA5 adoption plan. •Alignment and collaboration: Continued coordination between OFACT, and partner teams (including data providers) is essential to maintain momentum and avoid delays. •Scope management: Balancing the level of data changes with validation timelines to prevent scope creep while ensuring data quality. **Decisions / support needed** •Confirm prioritization and funding for early consumer onboarding activities and associated change management. •Decide on cadence and ownership for cross-team validation reviews to maintain alignment as data and process changes accelerate. •Approve any necessary trade-offs be | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-01 | 2027-03-30
Business Only Initiative: Commercial Linehaul Scan Visibility | 67238 | 7410 | Business Only Initiative | Tricolor - NPET | Tricolor | Geovanni Gopar Reyes, Chuck Pounders | On Track | Removing one initiative owner as they have transitioned jobs and are no longer involved. | K: L5 | Completed | L5 | 2024-01-09 | 2024-09-30
Business w/ Tech Initiative: Chairman's Challenge 2.0: Dataworks Air Freight RF | 69607 | 7453 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Tyler Woolley, Ryan Kellerhouse | On Track | Being rolled into larger initiative #133016 | C: L1 | Cancelled | L1 | 2024-07-16 | 2024-11-25
Business w/ Tech Initiative: CLHQPI: CLASS Phase 3 - Tri-Color Enablement | 72816 | 7524 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Geovanni Gopar Reyes, Danny Jones | On Track | Both Christine Belling and Kevin Harris agreed on 4/1 that this is an enabler and there is no value quantification. All comments within the PV related to value have been edited accordingly to move to L4. | I: L4 | Active | L4 | 2023-06-01 | 2026-01-30
Business w/ Tech Initiative: CLH KPI Dashboard – DW Execution Initiative | 73904 | 7602 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Clayton Williams, Michael Thompson - 533244 | On Track | Jul-22-2024 - Initiative pending TCH final approval and prioritization. As this is a KPI dashoboard the NRB is zero. It enables better management and buying of CLH, however, those $ benefits are captured in other initiatives. | K: L5 | Completed | L5 | 2024-05-01 | 2025-03-19
Business Only Initiative: Airline Performance KPIs - GPN (POC) | 33993 | 8019 | Business Only Initiative | Tricolor - NPET | Tricolor | Clayton Williams, Suzanne Sabbatini | On Track | Initiative complete prior to transition to Planview. Future work part of intiative 7602. | K: L5 | Completed | L5 | 2023-11-01 | 2023-12-15
Business w/ Tech Initiative: OneView | 90035 | 8810 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Steve Johnson, Alun Cornish | On Track |  | E: L2 | Active | L2 Feedback Requested | 2024-08-20 | 2024-09-16
Business Only Initiative: Tricolor TWINS 2.0 - Enhanced Development | 63795 | 8845 | Business Only Initiative | Tricolor - NPET | Tricolor | Michael Thompson - 533244, Clayton Williams | On Track | Closing out the TWINS 2.0. The milestones within the ticket are complete. A new ticket will be created to represent a new structure which identifies various functionalities of the TWINS toolset so that it can be built in a more robust manner versus developing the tool through various business cases as it has been done up until now. We are moving the ticket to L5, thus to close this ticket out, with the new focus being developing the toolsets over developing around business cases. | K: L5 | Completed | L5 | 2023-10-02 | 2024-03-29
Business w/ Tech Initiative: Enhanced Flight Profitability Dashboard |  | 89455 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Patrick Green | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: System Form Analysis Toolset (TWINS) - DW Planning | 75151 | 9128 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Jordan Mayberry | On Track | 11/20 Cancelling per leadership. | E: L2 | Cancelled | L2 | 2023-11-01 | 2024-10-31
Business w/ Tech Initiative: Tricolor - Network Performance Management Dashboar | 97972 | 9131 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Amanda Hewgley, Jasmine Hudgins | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Tricolor TWINS Planning Tool | 16856 | 9310 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Michael Thompson - 533244, Saeed Zamiri | On Track | We are using an iterative (Business Case) approach with the tool, whereby the leadership is providing business case scenarios to pursue validation of in regards to what volume could theoretically make service being moved via commercial methods. | K: L5 | Completed | L5 | 2023-03-27 | 2023-10-31
Business Only Initiative: JAN25 Network Efficiency |  | 93285 | Business Only Initiative | Tricolor - NPET | Tricolor | Chuck Pounders, Stephen Levine | On Track | N/A | K: L5 | Completed | L5 | 2025-01-01 | 2025-01-01
Business Only Initiative: Americas - IND-YMX (Density Size of Prize) | 58680 | 6783 | Business Only Initiative | Tricolor - NPET | Tricolor | Ryan Ruble, Jake Dorris, Curt Gobbell | On Track | Drive Density | K: L5 | Completed | L5 | 2023-11-01 | 2024-01-11
Business Only Initiative: Eliminate ad hocs and rolled volume on MEM-SEA (FL | 30331 | 6769 | Business Only Initiative | Tricolor - NPET | Tricolor | Vinnie Collura, Cody Gadd | On Track | Finance could not provide numbers to support savings costs. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2023-09-01 | 2024-05-31
Business w/ Tech Initiative: CLASS Operational Planning/Booking |  | 133013 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Geovanni Gopar Reyes, Sanford Swagerty | On Track | DCM work repurposed this initiative Operational Planning/Booking. The work ID is 116218 is the new work ID in which Geovanni is an Epic Owner. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: DCM - Global Air Freight - Data Engine |  | 133016 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Rodrika Thompson | On Track | 07/10 - I am in the process of searching for an architect to help me complete the architectural documentation. 08/13 - I reached out to our EPM, Shelby on today for assistance on making this an enabler to DCM. 11/20 - Cancelling per leadership request to clean up PV. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Integrated Network Planning Technology |  | 157709 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield, Rodrika Thompson, Fawzi Cheikh Bessaih | On Track | 02/04 - Since the epic has been titled DCM Flow Planning Engine, I am changing the initiative name to reflect the vision of Kevin Harris. 01/26 - Currently working with Solution Manager to ensure that all information is being capture and documented to ensure a safe flow through the L-Gates. This initiative is in support of Tricolor. 11/06 - Adjusted Architectural documentation to reflect D-45 to D-1 window for DCM Flow Planning Engine focus. | G: L3 | Active | L3 Feedback Requested | 2025-08-01 | 2026-09-30
Business w/ Tech Initiative: E2E DCM Workflow Use Case |  | 159195 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield | On Track | Due to direction from leadership, this initiative is no longer needed for what we are trying to accomplish moving forward. Its removal also allows the primary parent/child hierarchical relationship in Planview to remain intact for the Tricolor - Digital/DCM pod. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Capacity Visibility |  | 159199 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield | On Track | This interim initiative is no longer needed as part of ongoing DCM/Tricolor work and has been deprioritized. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global Weekly Forecast Management (WFM) |  | 161254 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Marvin S. Elliott, Forrest B. Treadway, Rodrika Thompson | On Track | Added Forrest Blake Treadway as the secondary IO to ensure update coverage 12/18 - Cancelling this initiative and merging with initiative 113481. (RT) | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Transits - visualization and aggregation |  | 161877 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Stacey Robinson, Steve Fraser | On Track | Decomp in L2 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Value Bundle C - What-If Engine for Transit Change |  | 162500 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Rodrika Thompson | On Track | 11/10 - Had a call with Dominic Bowman, David Weaver, and Rick Dembowski. It was decided to transfer ownership over to their team. David stated that he will be reaching out to Jasmine to see if she can take on ownership until they are able to get trained on PV. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: One FedEx Postal Routing Workflow |  | 164231 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Sudheer Kumar Pendem, Steve Fraser | On Track |  | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Surgical Demand Shaping (SDS) |  | 164581 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Rodrika Thompson, Jordan Mayberry | On Track | 01/26 - Cancelling due to prolonged delays in obtaining buy‑in from potential customers. We will revisit this work at a later date if needed. 10/06 - Creating this initiative, scaling the APAC but from a global perspective. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Modernized Air Routing IntegratedNetwork Optimizer |  | 184254 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: RFQ Assessments & Integration |  | 184261 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: AIR Network Design & Simulation Platform |  | 184293 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield | On Track | PV initiative #164613 will be utilized instead of this one. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: CLH Contract Intelligence |  | 163714 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Shawn Bernhard, Katrina Mossafayan, Yoyo Yeung | On Track | The scope will be well defined in the workshop with sneior leadership in Jan 8. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Monthly Operating Plan (MOP) Automation |  | 164343 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Colin Ta, Fawzi Cheikh Bessaih, Ying Hao Koo | On Track | The solution had been developed for CN and NPAC origin for primariy routing. Currently, it's being developed for SPAC and to be expanded to secondary & tertiary routing Cancellation rationale: MOP automation initiative is to be closed and included it as part of Integrated Network Planning Technology (#157709) | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Integrated D&C Dashboard Phase 2 |  | 169303 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Fawzi Cheikh Bessaih | On Track | On Track | F: SL3 | Active | SL3 Domain Lead Approval | 2026-04-20 | 2026-11-12
Business w/ Tech Initiative: Weekly Forecast Management (WFM) |  | 113481 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Katrina Mossafayan, Eun-Suk Ahn, Tarun Madan, Rodrika Thompson, Alon David Honig, Forrest B. Treadway, Marvin S. Elliott | On Track | 03/05 - Cancelling this initiative as this work is being covered under P# 157709. 1/6: LBC submitted (KM) 12/29 Just requested for a PPM number, waiting on Tarun and Fawzi's approval. (RT) 12/24 Combine Global Weekly Forecast Management (WFM) with this initiative. (RT) | E: L2 | Cancelled | L2 | 2025-05-01
Business w/ Tech Initiative: AirPath+ | 38430 | 7085 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Ming-Wai Suen, Zee-Yu James Yung, Yoyo Yeung, Gali Lee | Some Issues | Load Plan Generation in adoption and enhancement. Shipment Assignment UAT in Prodcution has been extended due to allocation logic and delay issue | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-14 | 2026-07-31
Business Only Initiative: Air Network Management System |  | 170277 | Business Only Initiative | Tricolor - NPET | Tricolor | Xiaomeng Fan | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-23 | 2026-02-27
Business w/ Tech Initiative: Air Network Design & Simulation Platform |  | 164613 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Roshelman Breakfield, Rodrika Thompson, Julian Man, Fawzi Cheikh Bessaih | On Track | 01/19/26 It is on track for proof of value status | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Surgical Demand Shaping |  | 127948 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Rick Yu, Paul Cheung, Puteri Zamri, Matthew Au, Abby Ang | On Track | 04/17 - All portfolios have provided greenlight. Pending on advice from EGC to proceed forward to L3. 04/15 - Current Greenlight Status: Platform - Greenlighted by Zahra Taqi on 3/18 Commercial - Greenlighted by April Zhou on 3/13 SCO - Approved at SCO PEL on 4/3 D&AI - Pending Update by Zahra Tai 04/03 - SCO-PEL has approved for greenlight. After DataAI approved for greenlight (expecting by the week of 4/13), the initative will go to EGC for formal approval. 03/30 - Had meeting with DataAI team. Expecting greenlight from DataAI team at week of 4/13 and SCO team on 4/2 once approved by SCO-PEL. 03/27 - Pending greenlight from Data AI & SCO teams. Commercial & Platform teams have provided greenlight. 03/19 - ODS team identified one of the root cause to SDS latency issue require Data AI support. New milestones have added to Data AI portfolio per instructed by Ayush Dayal 03/13 - Submit to Greenlight step 02/10 - Updated Money Step End date to Mar'27 per Commercial PEO April request. 02/04 - updated Commercial PEO costing. Pending actions from SCO & Data AI PEOs. 01/30 - updated Platform PEO costing. Pending advice and actions from PEOs of SCO, Commercial and Data AI. 01/15 - Alignment done with SCO PEO on items required to be added to PV. Further advice and actions to be completed once received architects advice on solution and architecture details. 01/14 - Alignment done with Commercial FP&A on P&L, for internal and external Commercial costs. Ref notes on email for details. 01/13 - Replied to SCO PEO for SCO PEL prep. 01/09 - Platform PEO reached out requesting to change Platform Impact to Yes, to allow L2 review and greenlighting. 01/08: SCO PEO reached out requesting for several actions to be completed towards Portfolio Greenlighting. Also, having the Architecture Review Board tonight to review the Conceptual Architecture for SDS, to get the architecture alignment and stakeholders approval. 01/07: Commercial PEO reached out requesting to work on costing with their FP&A towards Portfolio Greenlighting. Having discussion with the team on 14th Jan. 01/06: Created the Epic and submitted to next steps for Portfolio Greenlighting. 12/23: Undergo RMIC Impact Review. To additionally seek commercial input on capabilites in Epic 2 that are needed by the business. 12/19: Kiran Alemada was assigned by commercial to SDS. 12/15: Presented to the Architecture Stakeholder Review (ASR) team, for Epic 2 approval. No objections received from the attendees. 12/03: Presented to the Architecture Stakeholder Review (ASR) team, for Epic 1 approval. Epic 2 will be presented on 12/15 for approval. 12/02: 1.The team has completed the following works: a.L2 Decomposition document b.L2 Conceptual architecture – Epic 1 is done, Epic 2 interim conceptual architecture options identified. Paul presented the Leadership decision required: -To confirm if we should go forward with the initiative with splitting Epic 1 and 2 into separate initiatives so that the initiative can move forward with only Epic 1, and Commercial can take up Epic 2 separately. -The risk identified however, is that rolling out the initiative without Epic 2 will require manual workarounds to perform the demand control actions. -The initiative is currently at priority No. 26 in Commercial, and 46 in Enterprise. 2.Abdullah presented the current initiative plan and of which the project has been soft launched in MY, HK, JP. KR, SG, TW and TH, and CN is planned for March 2026. Of the markets being launched, the proposal to drop Epic 2 will pose a high risk to HK due to the operational process needs and to CN especially, due to their high volume. 3.In view of this, the initiative needs to proceed with Epic 2. 4.Next step: Joe Stephan will follow up with Mike, who has taken the action from Kawal last week, to get this initiative prioritized accordingly with Commercial, and to get a better estimate for when this work can be done. Abdullah to be included in the commun | E: L2 | Active | L2 Feedback Requested | 2025-06-16 | 2027-03-31
Business w/ Tech Initiative: CLASS Multi MAWB Enhancement (India/China) |  | 136600 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Geovanni Gopar Reyes, Sanford Swagerty | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: WS1 - [1C - Project Zenith ] Forecast Solution | 82589 | 8442 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Rodrika Thompson, Marvin S. Elliott, Jordan Mayberry, Sanford Swagerty, Forrest A. Smith, Forrest B. Treadway | On Track | On track, no late milestones. Ran EU test month with EU domestic. Working on the EU dashboard. Adoption meeting results were Firefly forecast ready to move environment from Development to Test. Users want an opportunity to verify forecast prior to movement to Production environment. Also need 'Actual Lbs.' forecast included in that the 'Pieces' forecast is not enough by itself. Based on Sep 2025, Roadmap: 1/ Piece count data, curation, and ingestion is complete for all Regions 2/ Weight and Cube data, curation, and logic is on track for completion by end of Oct 2025 for all Regions 3/ Model training and intial run complete for EU and N. Amer (Air + Surface); on track for APAC, MEISA and LAC by end of Oct 2025 4/ Ready for user adoption moving from Development to Test environments--by end of Oct 2025 for EU, end of Nov 2025 for APAC, and Jan 2026 for rest of the Regions. | E: L2 | Active | L2 | 2024-06-03 | 2025-05-20
Business w/ Tech Initiative: URSA Prefix Character Limit |  | 190426 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Jesse Elsea, Megan C. Silva, Roshelman Breakfield | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: WS1 - [1C - Project Zenith ] Network Definition | 90146 | 6775 | Business w/ Tech Initiative | Tricolor - NPET | Tricolor | Ben Galle, Andrei Hidigan, Michael Penfield | On Track | **2026 March 24** SUCCESSES * Closed out Phase 1 - Capabilities 1.1 - 1.5 IN PROGRESS / NEXT STEPS • Build a proposed plan for global data validation MILESTONE TARGETS • Global expansion RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 March 17** SUCCESSES * Capability 1.5 approved by ARB * Successfully reviewed FMT and OMT EU pilot and will incorporate feedback to improve systems IN PROGRESS / NEXT STEPS • Build a proposed plan for global data validation MILESTONE TARGETS • Global expansion RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 March 10** SUCCESSES • Present 1.5 to ARB:ASR on Monday 3/9 IN PROGRESS / NEXT STEPS • Awaiting approval from ARB:ASR for 1.5 MILESTONE TARGETS • Global expansion ○ Data is being evaluated for verification process RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 March 3** SUCCESSES • 1.5 Solutions complete, present to team on Monday 3/2 IN PROGRESS / NEXT STEPS • Present 1.5 to ARB MILESTONE TARGETS • Global expansion ○ Data is being evaluated for verification process RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 February 24** SUCCESSES • Reviewed a Change Management Request, target to bring to Core Team next week IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by March MILESTONE TARGETS • Global expansion ○ Data is being evaluated for verification process RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 February 17** SUCCESSES • Met with properties on adding certain costs for facilities, core team will evaluate IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by March MILESTONE TARGETS • Global expansion ○ TBD RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 February 10** SUCCESSES • Good initial discussions with global retail and integrating ADM with NDS IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by March MILESTONE TARGETS • Global expansion ○ TBD RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 February 3** SUCCESSES • Communication sent to Regional P&E VPs to start the Facility, Location & Operation data validation process IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by March MILESTONE TARGETS • Global expansion ○ TBD RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 January 27** SUCCESSES • Capabilities identified during OSC Retirement Workshop to moved from OSC to NDS IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by end of January MILESTONE TARGETS • NA CSFP ○ None at this time RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 January 20** SUCCESSES • Participated in Odyssey workshop this past week • LSSI created a Feature for populated Facility Core with additional attributes for Odyssey to be stored in NDS IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by end of January MILESTONE TARGETS • NA CSFP ○ New test data came in last week and is being tested RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 January 13** SUCCESSES • Good progress made on solution work for Locations with Odyssey IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by early-mid January MILESTONE TARGETS • NA CSFP ○ New test data came in last week and is being tested RISKS • None at this time LEADERSHIP ASKS * None at this time **2026 January 6** SUCCESSES • No major updates for this past week as many team members were off for the holidays IN PROGRESS / NEXT STEPS • Capability 1.5 is in Decomp targeted to be complete by early-mid January MILESTONE TARGETS • NA CSFP ○ New test data came in last week and is being tested RISKS • No | G: L3 | Active | L3 Feedback Requested | 2024-08-19 | 2026-07-31
Business Only Initiative: CYCLOPS- TransPacific - Non-Linehaul Savings |  | 106735 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Hannah Herring | On Track | Finance instructed to cancel. | I: L4 | Cancelled | L4 | 2025-03-03 | 2025-03-03
Business Only Initiative: CYCLOPS- TransPacific - Linehaul Savings |  | 106747 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Hannah Herring, Bryan D'Souza, Chuck Pounders | On Track | Already in money step execution-wise, just need to catchup in Planview structure | I: L4 | Cancelled | L4 | 2025-03-17 | 2025-03-17
Business Only Initiative: ANC-SIN reroute for network efficiency |  | 107395 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Bryan D'Souza, Bryant T. McBride | On Track | Tyler Sherman requested this Initiative should be cancelled - INC034343710 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Load Quality Advisor (LQA) tool to support ULD den | 31464 | 6799 | Business w/ Tech Initiative | Tricolor - Intl Air | Tricolor | Fanny Yang, Pinky Jiang | On Track | Update the initiative owner to Fanny Yang | K: L5 | Completed | L5 | 2023-08-01 | 2024-07-22
Business Only Initiative: Reduction in Trans-Pacific flying from P14 to P12 | 1251 | 7920 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Chuck Pounders, Stephen Levine | On Track | Prioritization of Initiatives 102022 Move to L3 as soon as possible. Combining Initiative 1251 /1252 together Flights were removed from the schedule and tracking for 3 months as the WAVE guidance to submit for L5 | K: L5 | Completed | L5 | 2022-10-03 | 2022-11-21
Business Only Initiative: AMEA PEAK flights for TPAC FY24 Additional Lift (2 | 24251 | 7950 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Andy Yuen, Stephen Levine | On Track | 2 MD11 pattern CAN-ANC-MEM-SEA-ANC-CAN (5X) CAN-ANC-MEM-ANC-CAN (1X) | K: L5 | Completed | L5 | 2023-04-03 | 2023-07-28
Business Only Initiative: Trans-Pacific Takedown Convert CAN-ANC-MEM SHEIN E | 59454 | 7964 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Bryant T. McBride, Bryan D'Souza, Stephen Levine, Megha Susan Alex | On Track | On Track | K: L5 | Completed | L5 | 2024-04-05 | 2024-04-05
Business Only Initiative: Tricolor Tokyo Tomorrow (P10 O4) Marshall | 64670 | 7966 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Bryan D'Souza, Stephen Levine, Bryant T. McBride, Megha Susan Alex | On Track | n/a | K: L5 | Completed | L5 | 2024-04-18 | 2024-04-18
Business Only Initiative: HNL-SYD Frequency Optimization | 97249 | 7969 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Bryan D'Souza, Stephen Levine, Bryant T. McBride, Megha Susan Alex | On Track | This initiative was reimagined as the OAK-SYD US direct flight and it has already been implemented. The HNL-SYD initiative becomes redundant and void. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Tricolor Trans-Pacific Review - Apr'23 - 1st P tak | 16319 | 7980 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Shrikant Sharma, Stephen Levine | On Track | All available information is in WAVE at this time. Working with APAC to shore up Milestone end dates but they have visibility as we move through each one for the total Trans Pacific Review. Will make adjustments as needed for each stage. ![](inline-attachments/16319/image/7405e913-03fe-4dbf-8262-56837a470315-image.png) | K: L5 | Completed | L5 | 2023-01-20 | 2023-03-27
Business Only Initiative: Tricolor Trans-Pacific Review - May’23 – 2nd P ta | 18365 | 7981 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Shrikant Sharma, Stephen Levine | On Track | 032823 - KPI's updated to ensure CLH is tracked for spend, lbs in millions and cost per pound This is for May’23 CAN-ANC-MEM-ANC-CAN takedown ![](inline-attachments/18365/image/270f72d3-017b-4fdc-a72f-d9b56ace63ec-image.png) | K: L5 | Completed | L5 | 2023-01-30 | 2023-04-28
Business Only Initiative: Chinese New Year CY2023 Temporary Purple Tail redu | 1501 | 8397 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2022-09-30 | 2023-03-01
Business Only Initiative: Chinese New Year CY2024 Temporary Purple Tail redu | 66160 | 8827 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Gary Webb, Clayton Williams | On Track | 2024-03-04: Initiative complete. No more updates occurring. 2024-02-26: CNNY CLH cancelled after 1 week dur to low volumes. Results for the 1 week added to Wave. 2024-02-15: CNNY implementation started. Moving to L4. 2024-02-02: Lanes awarded. Business case developed. RFQ closed. Awarding lanes to carriers. | K: L5 | Completed | L5 | 2023-12-13 | 2024-02-29
Business Only Initiative: HNL to US Mainland CLH Capacity Purchase link to # | 72916 | 8831 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Gary Webb, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2024-02-12 | 2024-03-08
Business Only Initiative: Tricolor White Trans-Pacific CLH Enabler CX - Air | 19011 | 8836 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Jochen Krug, Clayton Williams | On Track | Decision whether to sign the BSA will be taken this week; by that time the baseline value will be known as well and the financial impact can be defined. BSA will start in April with about 400 tons and increase in May to 1000 tons per month going forward. | K: L5 | Completed | L5 | 2023-03-17 | 2023-08-11
Business Only Initiative: Master Yoda - Phase 2 HKG |  | 106979 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Hilary Tse, Paul Sousa | On Track | Conducting business case with cross-functional teams | E: L2 | Active | L2 & CCH - Feedback Requested | 2025-04-25 | 2025-04-28
Business Only Initiative: Front Door & TransAtlantic Network Redesign |  | 97499 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Bryan D'Souza, Bryant T. McBride, Clay Kasdorf, Stephen Levine, Patrick Green, Megha Susan Alex, Hannah Herring | On Track | Business case worked. Implementation planning in progress. | K: L5 | Active | L5 | 2025-04-28 | 2025-04-28
Business Only Initiative: Tech Stop to Improve Front Door Payloads - DWC/IST | 71415 | 7970 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Colin Ta, Stephen Levine | On Track | 28-Oct-2024 Weekly cadence call among project teams (GNP, APAC/EU/ME ANP, IST Ops, GOC, AODF, AirNav) happening since Feb 2024. The latest cedence call happened on 29-Oct-2024 where all teams confirmed the 100% ready status for new IST techstop launch from 5-Nov-2024 4-Nov-2024 The first flight with IST techstop for HKG-IST-CDG had been successfully launched on 5-Nov-2024. It helped to gain additional 38Klbs net payload compare to previous flight without IST stop, achieved 300% more than the plan only 10Klbs/flight. 7-Jan-2025 Successfully changed to IST stop as D16 CAN-IST-CDG and D23456 HKG-IST-CDG/LGG | K: L5 | Active | L5 | 2024-05-01 | 2024-12-31
Business Only Initiative: [FD] F5 New Structural Flight |  | 153012 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Kai-Yong Tan, Colin Ta | On Track | The P&L had been approved on probationary basis for six months; approved by International Air Pod Lead Shrikant Sharma to progress initiative in Planview to L3 even though negative NRB. F5 launched effective Oct'25 schedule month; 1st flight 28th September 2025. Initial post-mortem done for Feb'26 GANS; due back in GANS in Jul'26. | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: D&C Intra-Asia |  | 166381 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Matthew A. Green, Megha Susan Alex | On Track | This is not my initiative. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: ROO Reroute |  | 166382 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Sally Lam | On Track | Pending officers review | E: L2 | Active | L2 & CCH
Business Only Initiative: CAN-KIX/CAN-NRT Optimization |  | 165174 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Sally Lam | On Track | To be defined and submit again. | E: L2 | Cancelled | L2
Business Only Initiative: CI TPE-CAN-TPE Charter Flight |  | 165165 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Justin Lee | On Track | 10/3 - Charter price discussion has yet to start. Entering intake form with tentative P&L assumptions. 1/29 - Change to On Hold. Pending further lobbying with CN CAAC for the D7 CAN slot approval. | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business Only Initiative: OAK-SYD |  | 133009 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Bryan D'Souza, Bryant T. McBride, Clay Kasdorf, Megha Susan Alex, Patrick Green, Stephen Levine | On Track | Tyler Sherman requested this Initiative be cancelled - INC034343710 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC MIA Conexion-Maya Loop Upgrade |  | 159189 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Jorge Palacios | On Track | Full BC completed and socialized. Will be presented to the CPF November 6, 2025 | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: KE ICN-ANC |  | 89536 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Eun-Suk Ahn, Sisi Jin, Takeshi Ishikawa, Clayton Williams, Matt Mocek, Michael Thompson - 533244 | On Track | On track | K: L5 | Active | L5 | 2024-11-25 | 2028-01-19
Business Only Initiative: APAC+EU via ROO+T1 |  | 168413 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Jiak-Hui Ronnie Ng, Sisi Jin | On Track | On Track | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-10-22 | 2025-12-01
Business Only Initiative: PEK-CAN-CRK-PEK Charter Flight |  | 189709 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Sisi Jin | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: 2026 CLH RFQ |  | 191962 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Takeshi Ishikawa | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: SINDBAD |  | 191972 | Business Only Initiative | Tricolor - Intl Air | Tricolor | Mustafa Assaf | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: CYCLOPS- TransAtlantic - Non-Linehaul Savings |  | 106738 | Business Only Initiative | Tricolor - Density | Tricolor | Hannah Herring | On Track | Finance instructed to cancel. | I: L4 | Cancelled | L4 | 2025-03-03 | 2025-03-03
Business Only Initiative: CYCLOPS- TransAtlantic - Linehaul Savings |  | 106744 | Business Only Initiative | Tricolor - Density | Tricolor | Hannah Herring | On Track | Finance instructed to cancel. | I: L4 | Cancelled | L4
Business Only Initiative: Purple FALCON, Marshall | 497 | 7948 | Business Only Initiative | Tricolor - Density | Tricolor | Arun Bakshi, Stephen Levine | On Track | 091123 Follow up with TRW and Finance next steps AMEA: Vijay/FALCON are focused on growth, but the proposed impact just unwinds the WBRTW CLH and offers no incremental revenue - we are not debating WBRTW again, that decision has been made and implemented. We need to look at this differently with the following assumptions: •Keep all WBRTW CLH (Max White) •Need incremental revenue that will move because of the change in allocation in on the MXP-MEM flight oPlease supply product, actual lbs, pieces, destination region for a 3 year view oInclude comparison of incremental revenue to base (existing) revenue (please see attached yield bands for all products IN-Americas) Europe: ·Revenue risk should be minimal as it can be protected via CLH and/or transfer to outbound capacity from CDG ·Separate detail between volume directly affected by loss of MXP-MEM capacity as well as volume attributed to CDG overflow oAssume 50k lbs/week of volume protected by TK - Please supply rate or make best assumption if rate is unknown oClearly identify risk by product, origin, and day of week; Note - FICP should not be prioritized on Purple Tail as FICP is assumed to flow 100% on CLH as of next month oSupply projected CLH capacity/rate required to protect remaining volume that cannot be protected by TK, Other CLH, CDG Capacity (CDG-MEM, CDG-EWR-MEM, CDG-STN-IND), and re-allocating volume to other flights oVolume that cannot be protected by any of the above can be shown as at-risk 090123 COnf call info Airline Schedule •Recommend VP approval of the airline schedule •The schedule (as planned) is extremely tight (refer to attached schedule) oCDG will not accept any fewer than 90 minutes ground time ?Expect more ICS selections than MXP, also the arrival is during the sort oMXP request 90 minutes ground time ?90 minutes is not available in all seasons oME outbound flights do not all have typical 90 minutes •Additional concerns oSlots – DXB ?Can the specific slot time be approved to meet the schedule as proposed ?Slot time availability will drive the available ground time MXP & CDG •This schedule is wound really tight – potentially, MEMH should expect late arrivals regularly and have a plan to manage D5 options 1.FALCON arrival – tech stop only a.50K lbs. additional Express overflow will reflect negatively on the case 2.ME allocation 1 full flight – all freight available for CDG/LGG outbound (some ME freight sorting / transporting via LGG) a.Will result in 55K lbs. Express overflow (weekend) b.EU will lose Saturday delivery freight option for CDG local c.This will maximize all available capacity; only EU Express would flow on any changes for CDG-MEM. LGG has an early AM departure for IND, this sorting will help to maximize this flight 3.EU: 3 upper deck positions, remaining ME allocation – all freight available for CDG/LGG outbound (some ME freight sorting / transporting via LGG) a.Will result in 45K lbs. Express overflow (weekend), 34K lbs. Express overflow (weekday) b.Saturday Delivery options (CDG local) would be protected c.This will maximize all available capacity; only EU Express would flow on any changes for CDG-MEM. LGG has an early AM departure for IND, this sorting will help to maximize this flight •Flows & EU revenue impacts have been developed for the D5 options •When Tri-color flows are completed (late October), reassess plan for above D5 options •CLH has meeting scheduled with Turkish Airlines ( mid/late September) to discuss CLH options oNo rate information / potential space allocations are available at this time Timeline •It appears that there is discussion that the P&L will be available for Sr. Mgmt. review mid-September. This does not correspond to the published timeline (below) •To meet a mid-September date, all needed data/information would have to be available today September 1 to build / review / finalize the P&L DateFunction completed August 14Airline Schedule August 21Volume flows Augu | K: L5 | Completed | L5 | 2024-01-31 | 2025-03-25
Business Only Initiative: Tricolor Transatlantic Commingle Initiative | 500 | 8774 | Business Only Initiative | Tricolor - Density | Tricolor | Gary Webb, Geary Hamm | On Track | Initiative placed on hold pending Tri-Color network design. Hold removed. Adding ORD-FRA commingle lane Arpil one followed by JFK-FRA May 1. | K: L5 | Completed | L5 | 2022-11-01 | 2023-03-29
Business Only Initiative: Tricolor White TA Iceland Air | 17345 | 8811 | Business Only Initiative | Tricolor - Density | Tricolor | Clayton Williams, Christian Tengs | On Track |  | K: L5 | Completed | L5 | 2023-03-27 | 2023-03-31
Business Only Initiative: Nova Lite US Export | 22457 | 8825 | Business Only Initiative | Tricolor - Density | Tricolor | Gary Webb, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2023-05-08 | 2023-06-16
Business Only Initiative: US to EU Winter RFQ 2023 | 36023 | 8826 | Business Only Initiative | Tricolor - Density | Tricolor | Gary Webb, Clayton Williams | On Track | RFQ complete. Utilized sourcing tool Coupa for the process. | K: L5 | Completed | L5 | 2023-08-22 | 2023-11-03
Business Only Initiative: US to EU Summer 2024 RFQ | 70018 | 8829 | Business Only Initiative | Tricolor - Density | Tricolor | Gary Webb, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2024-02-19 | 2024-04-05
Business Only Initiative: European Peak Season avoiding Extra Section using | 4892 | 8832 | Business Only Initiative | Tricolor - Density | Tricolor | Jeff Euler, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2022-11-21 | 2022-12-22
Business Only Initiative: Nova Lite EU Export | 22776 | 8837 | Business Only Initiative | Tricolor - Density | Tricolor | Christian Tengs, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2023-03-27 | 2023-04-07
Business Only Initiative: EU Winter RFQ 2023 | 34296 | 8840 | Business Only Initiative | Tricolor - Density | Tricolor | Christian Tengs, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2023-07-03 | 2023-11-03
Business Only Initiative: EU to US Summer RFQ 2024 | 70521 | 8842 | Business Only Initiative | Tricolor - Density | Tricolor | Christian Tengs, Clayton Williams | On Track | RFQ to be sent to all carriers | K: L5 | Completed | L5 | 2024-02-19 | 2024-04-05
Business Only Initiative: EU to US Incremental CLH Feb/Mar 2024 | 71082 | 8843 | Business Only Initiative | Tricolor - Density | Tricolor | Christian Tengs, Clayton Williams | On Track |  | K: L5 | Completed | L5 | 2024-01-23 | 2024-02-23
Business Only Initiative: DEL-YVR-MEM IP Growth Enablement |  | 89069 | Business Only Initiative | Tricolor - Density | Tricolor | Prateek Nath, Roland Zupancic | On Track | adding new IO owners at destiantion Update: DEL-YVR-MEM lane approved for first leg on Air India DEL-YVR Ops will be 5x weekly on D23456 Potential opportunity to secure 36 klbs weekly at $1.46 per pound | K: L5 | Completed | L5 | 2024-08-01 | 2025-02-28
Business Only Initiative: EU negative density impacts due to load plan non c | 30192 | 9068 | Business Only Initiative | Tricolor - Density | Tricolor | Alun Cornish, Luca Talarico | On Track | .This Initiative will be cancelled per Andy Pratt - INC034083765 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: TA WB - MXP-MEM (Density Size of Prize) | 58649 | 9072 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams, Dan Gleason | On Track | Estimated initial annualized impacts figure based on reaching 68% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2026-02-12
Business Only Initiative: TA WB - FRA-MEM (Density Size of Prize) | 58650 | 9075 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams, Dan Gleason | On Track | Estimated initial annualized impacts figure based on reaching 72% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2026-02-12
Business Only Initiative: TA WB - STN-MEM (Density Size of Prize) | 58651 | 9076 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams, Dan Gleason | On Track | Estimated initial annualized impacts figure based on reaching 72% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2026-02-12
Business Only Initiative: TA WB - STN-IND (Density Size of Prize) | 58652 | 9078 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams, Dan Gleason | On Track | Estimated initial annualized impacts figure based on reaching 68% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2025-10-14
Business Only Initiative: TA WB - LGG-IND (Density Size of Prize) | 58653 | 9079 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish | On Track | Estimated initial annualized impacts figure based on reaching 68% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2026-02-12
Business Only Initiative: TA WB - CGN-MEM (Density Size of Prize) | 58654 | 9081 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams | On Track | Estimated initial annualized impacts figure based on reaching 72% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2026-09-21
Business Only Initiative: TA WB - CDG-MEM (Density Size of Prize) | 58656 | 9084 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams, Dan Gleason | On Track | Estimated initial annualized impacts figure based on reaching 68% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2026-07-14
Business Only Initiative: TA WB - LGG-MEM (Density Size of Prize) | 58657 | 9086 | Business Only Initiative | Tricolor - Density | Tricolor | Danielle Kirby, Alun Cornish, Clayton Williams, Dan Gleason | On Track | Estimated initial annualized impacts figure based on reaching 68% box stack efficiency, but calculation logic is subject to refinement at L3. 19/04/2024 - L3 calculations complete and ready for entering into WAVE - logic in attachment document **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-06-03 | 2025-10-13
Business Only Initiative: EMR CT Air COE FY26 |  | 143920 | Business Only Initiative | Tricolor - Density | Tricolor | Clayton Williams, Michael Thompson - 533244 | On Track | This is a continuation of an FY25 initiative, with new target for FY26. | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval | 2026-03-27 | 2026-03-27
Business Only Initiative: Tricolor - CLH Base Business Pivot Optimization | 75186 | 8121 | Business Only Initiative | Tricolor - Density | Tricolor | Amanda Hewgley, Tyler Woolley | On Track | . | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-01 | 2024-08-30
Business Only Initiative: TP EB - CAN-ANC (Density Size of Prize) | 58659 | 9548 | Business Only Initiative | Tricolor - Density | Tricolor | Bob Chen, Pinky Jiang, Bryant T. McBride, Clayton Williams, Mathew Mazhuvancheryparambath | On Track | Measures are implementing. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-04 | 2026-05-29
Business Only Initiative: TP EB - NRT-ANC (Density Size of Prize) | 58670 | 7852 | Business Only Initiative | Tricolor - Density | Tricolor | Yoshiaki Takagaki, Yoshitaka Ito, Shinsuke Tanaka, Kei Alan Kubota, Bryant T. McBride, Clayton Williams, Mathew Mazhuvancheryparambath, Katsutoshi Ueda | On Track | Performance is stable after the initiative started. Below the target only if we don't have enough volume (e.g. during the holiday) | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2024-01-22 | 2026-05-29
Business Only Initiative: TP EB - HKG-ANC (Density Size of Prize) | 58667 | 7992 | Business Only Initiative | Tricolor - Density | Tricolor | Steven Ying, Anthony Leung, Clayton Williams, Mathew Mazhuvancheryparambath, Bryant T. McBride, Dan Gleason | On Track | Business Case Defined | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2023-11-01 | 2026-05-29
Business Only Initiative: TP EB - KIX-IND (Density Size of Prize) | 58660 | 7254 | Business Only Initiative | Tricolor - Density | Tricolor | Katsutoshi Ueda, Naoji Ogawa, Bryant T. McBride, Clayton Williams, Mathew Mazhuvancheryparambath, Dan Gleason | On Track | Measures are implementing. **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2023-09-01 | 2025-01-01
Business Only Initiative: TP EB - KIX-OAK (Density Size of Prize) | 58661 | 7256 | Business Only Initiative | Tricolor - Density | Tricolor | Katsutoshi Ueda, Naoji Ogawa, Bryant T. McBride, Clayton Williams, Mathew Mazhuvancheryparambath, Dan Gleason | On Track | Measures are implementing. **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2023-09-01 | 2025-05-22
Business Only Initiative: TP EB - KIX-ANC (Density Size of Prize) | 58662 | 7257 | Business Only Initiative | Tricolor - Density | Tricolor | Katsutoshi Ueda, Naoji Ogawa, Bryant T. McBride, Clayton Williams, Mathew Mazhuvancheryparambath, Suzanne Sabbatini, Dan Gleason | On Track | Measures are implementing. **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2023-09-01 | 2024-10-31
Business Only Initiative: TP EB - KIX-MEM (Density Size of Prize) | 58663 | 7259 | Business Only Initiative | Tricolor - Density | Tricolor | Katsutoshi Ueda, Naoji Ogawa, Bryant T. McBride, Clayton Williams, Mathew Mazhuvancheryparambath, Suzanne Sabbatini, Dan Gleason | On Track | Measures are implementing. **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2023-09-01 | 2024-10-31
Business Only Initiative: TP EB - TPE-ANC (Density Size of Prize) | 58664 | 7262 | Business Only Initiative | Tricolor - Density | Tricolor | Kevin Teng, Michael Chu, Clayton Williams, Mathew Mazhuvancheryparambath, Bryant T. McBride | On Track | Our current goals are to get to 72% stacking efficiency for boxes in identified lanes as opportunity. **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2023-08-01 | 2026-05-29
Business Only Initiative: TP EB - ICN-ANC (Density Size of Prize) | 58669 | 7263 | Business Only Initiative | Tricolor - Density | Tricolor | JY Kim, Wonbin Park, Clayton Williams, Mathew Mazhuvancheryparambath, Bryant T. McBride, Dan Gleason | On Track | Our current goals are to get to 72% stacking efficiency for boxes in identified lanes as opportunity **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-03-01 | 2026-04-28
Business Only Initiative: Americas - MEM-YYC (Density Size of Prize) | 58682 | 7020 | Business Only Initiative | Tricolor - Density | Tricolor | Cody Gadd, Vinnie Collura, Bryant T. McBride, Clayton Williams, Dan Gleason | On Track | Working with management to realign with the goals of this initiative. **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-12-02 | 2025-07-16
Business Only Initiative: Americas - MEM-YYZ (Density Size of Prize) | 58683 | 7021 | Business Only Initiative | Tricolor - Density | Tricolor | Cody Gadd, Vinnie Collura, Bryant T. McBride, Clayton Williams, Dan Gleason | On Track | Density has improved. Detailed plan was laid out and agreed upon by the DR, SR, and Manager of the YYZ market. **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2025-02-07 | 2026-04-30
Business Only Initiative: Americas - MEM - DWC (Density Size of the Prize) | 65504 | 7023 | Business Only Initiative | Tricolor - Density | Tricolor | Cody Gadd, Vinnie Collura, Bryant T. McBride, Clayton Williams, Suzanne Sabbatini, Dan Gleason | On Track | On track. Verifying data from from drive. **FROM TO FINANCE: There is no longer a requirement to track the value for "Volume" related initiatives such as Density in Planview.** **Moved to L5 and completed as per PDSM ticket INC034285190** | K: L5 | Completed | L5 | 2024-12-02 | 2026-06-16
Business Only Initiative: Americas - MEM-SJU (Density Size of Prize) | 58681 | 7019 | Business Only Initiative | Tricolor - Density | Tricolor | Vinnie Collura, Cody Gadd | On Track | Awaiting further review prior to continuing on to L3. | E: L2 | On Hold | L2
Business Only Initiative: Asymmetric Loading Configuration |  | 169999 | Business Only Initiative | Tricolor - Density | Tricolor | Saarth Bhanot | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Global-ULD-Introduction of Collapsible ULD |  | 106998 | Business Only Initiative | Tricolor - Density | Tricolor | Saarth Bhanot | On Track | To be merge into overlapping initiatives lead by Global ULD | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Global-ULD-ULDs with internal shelving |  | 106992 | Business Only Initiative | Tricolor - Density | Tricolor | Saarth Bhanot | On Track | To be merge into overlapping initiatives lead by Global ULD | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global-Autoslip Enhancements:AMS Movements |  | 109270 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Tiffany Franklin, Saarth Bhanot, Jordan Mayberry | On Track | n/a | E: L2 | Active | L2 Feedback Requested | 2026-07-07 | 2026-09-07
Business Only Initiative: Setting up ULD deep storage in APAC |  | 106989 | Business Only Initiative | Tricolor - Density | Tricolor | Jeromy Lai | On Track | Deprioritized for other initiatives | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Global-ULD-Pallet Base Sheet Reduction |  | 164062 | Business Only Initiative | Tricolor - Density | Tricolor | Saarth Bhanot | On Track | .Pallets will be delivered by the end of October. | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: Manage Excess ULDs |  | 157790 | Business Only Initiative | Tricolor - Density | Tricolor | Saarth Bhanot, Carl E. Nichols | On Track | Relocating ULDs to required location to reduce cost incurred. Scrapping out of life ULDs. | E: L2 | Active | L2
Business Only Initiative: Remove Lower pallet in Upper Deck in TPAC PT |  | 97482 | Business Only Initiative | Tricolor - Density | Tricolor | Julian Man | On Track | Cancel per latest alignment with the sponsor. | E: L2 | Cancelled | L2
Business Only Initiative: Resource RequestULD Strategy and Innovation |  | 160951 | Business Only Initiative | Tricolor - Density | Tricolor | Rodrika Thompson, Jordan Mayberry, Kevin Harris, Suzanne Sabbatini | On Track | 04/01 - This initiative is no longer needed as IOs are no longer over ULD planning. Just initiated request. LBC developed 9/12/25 | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business Only Initiative: ULD Planning by HUB & Ramp |  | 163724 | Business Only Initiative | Tricolor - Density | Tricolor | Carl E. Nichols, Mario Magparangalan | On Track | Adding Carl E. Nichols as Primary Initiative Owner. | K: L5 | Active | L5 | 2026-01-05 | 2026-02-27
Business Only Initiative: Global-ULD-Purchase AMS Containers for 777 | 461 | 7915 | Business Only Initiative | Tricolor - Density | Tricolor | Saarth Bhanot | On Track | This will need properties review, GLAD or Density team review and not a quick turn as it requires major capital to initiate | J: SL5 | Active | SL5 TO Finance Approval | 2023-11-29 | 2024-09-16
Business w/ Tech Initiative: APAC Speedcargo Density Solution |  | 109589 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Yao Kevin Liu, Jose Ignacio Ibarguen, In-Woo Ha | On Track | IO governance is established, action points with SMEs are in progressm and the initiative timeline has been drafted. | G: L3 | Active | L3 | 2026-04-01 | 2026-11-30
Business w/ Tech Initiative: Ingest SenseAware Asset Tracking Data |  | 187141 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Andrew Werner | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: ULD Manager / ULD IntelliTrack |  | 188045 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Robert Blackstone, Andrew Werner | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: TransPacific East Bound - Densification |  | 188557 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Darshak Raimangia | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: TransAtlantic WestBound - Densification |  | 188561 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Darshak Raimangia | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: TransAtlantic EastBound - Densification |  | 188575 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Darshak Raimangia | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: FrontDoor WestBound - Densification |  | 188579 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Darshak Raimangia | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: FrontDoor EastBound - Densification |  | 188588 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Darshak Raimangia | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: TransPacific WestBound - Densification |  | 189966 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Ethan Schek, Darshak Raimangia, Gwynne Riggen | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Real Time Visualization of Stack Efficiency |  | 190731 | Business w/ Tech Initiative | Tricolor - Density | Tricolor | Julian Man | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Density improvement EU-AMEA - Splits/Load plan | 18419 | 9409 | Business Only Initiative | Tricolor - Density | Tricolor | Luca Talarico, Paul Sousa | On Track |  | K: L5 | Completed | L5 | 2023-07-03 | 2023-07-03
Business Only Initiative: CYCLOPS- FrontDoor - Non-Linehaul Savings |  | 106741 | Business Only Initiative | Tricolor - Density | Tricolor | Hannah Herring | On Track | Already in money step execution-wise, just need to catchup in Planview structure | H: SL4 | Cancelled | zz SL4 SVP Finance Approval | 2025-03-17 | 2025-03-17
Business Only Initiative: CYCLOPS- FrontDoor - Linehaul Savings |  | 106751 | Business Only Initiative | Tricolor - Density | Tricolor | Hannah Herring | On Track | Already in money step execution-wise, just need to catchup in Planview structure | D: SL2 | Cancelled | zz SL2 SVP Finance Approval
Business Only Initiative: Cyclops Front Door Optimization |  | 89387 | Business Only Initiative | Tricolor - Density | Tricolor | Bryan D'Souza, Bryant T. McBride | On Track | This Initiative will be cancelled per Andy Pratt - INC034083765 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: F2 Specific Customer Push |  | 141943 | Business Only Initiative | Commercial - Automotive | Commercial | Pratheeshhkumar Chinnasamy Nag | On Track | 08/21 - LBC is finalized and we are working with teams to start the promotional efforts. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Aerospace ECC and AOG Desk |  | 135304 | Business w/ Tech Initiative | Commercial - Automotive | Commercial | Debbie Chatzistergioglou, Pieter Kop, Amy Faye | On Track | April 24, 2026 FACE Updates: •Aero IQ Tool in Production – April 1, 2026. This is still an internal process. Testing the tool with all capabilities prior to face the customer globally. •Hypercare – In progress – April 1 to May 1, 2026. •No major Production incidents •Next planned Production Deployment – Apr 22 and it will include fixed incidents and enhancements. •FACE Official Launch – May 15, 2026. Facing the customer. •Also, a Workshop will be hold in Miami for AOG manager first week in June. AOG Updates: •AOG Soft Launch without the tool: 8/3/2026 •AOG Soft Launch with the tool: 10/1/2026 •AOG Go Live – Phase 1: 1/4/2027 •AOG Go Live – Phase 2: 4/1/2027 •AOG Go Live – Phase 3: 7/1/2027 April 10, 2026 FACE - Engines solution: Focus of the next few weeks: * Hypercare daily calls have been scheduled until May 1, 2026 to support our Aero IQ tool. Teams are working on issues/enhancements. * FACE Official Launch – May 15, 2026. Facing the customer. * Team is currently working with sales and marketing for the official Go Live - May 15 - 2026 facing the customer. AOG: AOG Managers have been hired for all regions. Workshop will be hold in Miami for AOG manager first week in June. AOG managers are working towards the real estate places for all 4 regions. March 31, 2026 FACE - Engines solution: Focus of the next few weeks: * Hypercare daily calls have been scheduled for April 1 to May 1, 2026 to support the Soft Launch – April 1, 2026, which is still an internal process. Testing the tool with all capabilities prior to facing the customer globally. FACE Official Launch – May 15, 2026. Facing the customer. * Marketing communication has been initiated between Patrick Boy and the marketing team. Need to support Patrick on May 15, 2026 offical launch of the Aerospace Enginees service. Sales, Marketing materials, etc. AOG: * AOG Managers have been hired for all regions. * Workshop will be hold in Miami for AOG manager first week in June. * AOG managers are working towards the real estate places for all 4 regions. March 20, 2026 FACE: Second Soft Launch – April 1, 2026. This is still an internal process. Testing the tool with all capabilities prior to face the customer globally. FACE Official Launch – May 15, 2026. Facing the customer. Next Training for the FACE managers will take place in: CDG 23-27 March. AOG: AOG Managers have been hired for all regions. Also, a Workshop will be hold in Miami for AOG manager first week in June. March 3, 2026 •IT Deliverables: Milestone: (March 2, 2026) F.A.C.E. Solution went to Production for the internal teams. We are currently working on PVT (Production Validation Testing) throughout this week (March 2 – 6, 2026). •Training: Next week, March 9 – 13, 2026, training will take place in Miami. An additional training session will follow up in France (CDG) on March 23 – 27, 2026. •Official F.A.C.E. Go Live date - May 15, 2026. •Marketing meetings will be scheduled to prepare for F.A.C.E. Go Live. •Tentative AOG Go Live Date – September 21, 2026 February 18, 2026 * Soft Go Live Performance Update: Patrick Boy to provide the most updated data. * IT Deliverables: The IT team delivered the development on FACE this week, and the rest of the teams are currently working on the UAT. * Training: Training will take place in two phases: a. in Miami (9 - 13 March) with 8 attendees and b. in CDG (23 – 27 March) with 5 Attendees. February 13, 2026 * Soft Go Live Performance Update: Patrick Boy to provide the most updated data. * IT Deliverables: IT will be delivering the rest of the feature development by the EOD Friday 2/13/2026. Next week 2/17/2026 we will have the presentation on those features. In the meantime, we are on the Integration Testing phase for F.A.C.E. * Training: Training will take place in two phases: a. in Miami (9 - 13 March) with 8 attendees and b. in CDG (23 – 27 March) with 5 Attendees. * Tampa - Florida Aer-Engine Tr | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-15 | 2026-05-29
Business w/ Tech Initiative: Tire Tab Label Tracking and Visibility |  | 188735 | Business w/ Tech Initiative | Commercial - Automotive | Commercial | Caitlin Moore | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: [LAC] Optimize call center service level target to | 635 | 6706 | Business Only Initiative | Commercial - CX | Commercial | Gabriel Kayser, Fernanda Guerra | On Track |  | K: L5 | Completed | L5 | 2022-11-01 | 2023-01-06
Business Only Initiative: [AMEA] CN Wuhan Call center rental cost reduction | 28300 | 6729 | Business Only Initiative | Commercial - CX | Commercial | Joseph Chow, Elsa Kwan | On Track | Draft contract has been apporved by Legal and Controller. Sign off from Landloard and FedEx is under progress | K: L5 | Completed | L5 | 2022-12-05 | 2023-08-31
Business w/ Tech Initiative: [AMEA] Optimize Quality Assurance and training sup | 664 | 6761 | Business w/ Tech Initiative | Commercial - CX | Commercial | Shan Xiong, Daisy Gao, Lance Tam | On Track |  | K: L5 | Completed | L5 | 2022-11-21 | 2023-12-29
Business Only Initiative: [CA] Eliminate use of preprinted manual AWBs | 639 | 6817 | Business Only Initiative | Commercial - CX | Commercial | Peggy Ramoutar, Kyle Tiemann | On Track |  | K: L5 | Completed | L5 | 2022-09-06 | 2023-02-28
Business w/ Tech Initiative: [EU] POD 1.6 Chat Centralization and Translation | 676 | 6828 | Business w/ Tech Initiative | Commercial - CX | Commercial | Daniel Seemann, Ravi Van Roy, Dennis Atkins, Philipp Muenchenberg | On Track | 2023-07-14: The money step (Validate Resource Shift) is being moved to align it to the milestone plan (that was already updated). This is due to dependencies on Labor Relations Consultations and updates for the technical solution readiness in CED (the end-state chat tool). | K: L5 | Completed | L5 | 2022-11-14 | 2024-06-28
Business w/ Tech Initiative: [AMEA] Purplize Domestics to enable TNT domestic p | 696 | 6839 | Business w/ Tech Initiative | Commercial - CX | Commercial | Andrew Symington, Joseph Chow | On Track | UAT will commence one week late. Issues identified during SIT by development team currently being investigated. | K: L5 | Completed | L5 | 2022-01-10 | 2023-05-01
Business w/ Tech Initiative: [US] Create case and ability to automate issue res | 653 | 6850 | Business w/ Tech Initiative | Commercial - CX | Commercial | Kara Sheeves, Gina Maiden | On Track | 2025-5-08: Per discussion with Aysha, April will be the last month for entry of actuals. 2025-4-16: Financial forecasts for the next 12 months are correct. 2025-4-15: Received invoice from Five9 for the remaining costs for the integration/implementation work for outbound. Three months of benefits have been tracked since moving to L4. Ready to move to L5. 2025-3-07: Awaiting invoice from Five9 for the remaining costs associated with this body of work. 2025-1-09: AHT improved for December to 258 seconds, which is 30 seconds better than goal. 2024-12-09: IT is still working with Five9 to ensure the LSP licenses are billed to the correct contract. Katherine Adams identified the charges for the month of November. 2024-11-25: The work associated with this initiative is an enabler for additional DRIVE value. The integration of Five9 with Salesforce enabled the launch of the CED desktop, as the soft phone component within the new desktop was a requirement for telephony capabilities. For the past year, the pilot of the Five9 outbound dialer for escalations from the Virtual Assistant (Incomprehension intent) also supported the digital transformation strategy by facilitating a live agent contact from the channel in which the customer started the interaction. Learnings from these efforts helped identify customer behavior and established best practices for business rules, staffing and agent training. Critical Five9 system defects were isolated and resolved; these were dependencies for expansion of outbound for future use cases. 2024-11-15: Project expansion strategy is currently under review per CE MD Alignment meeting on 11/13/24. Katherine Adams provided the September and October invoice amounts for Five9 LSP license usage on 11/15/24; these were billed to the wrong contract; she is working to resolve the billing error for future timeframes. 2024-10-7: For the month of September, AHT improved by 2 seconds. This may be due in part to the load of the automated outbound agent greeting on 9/25/24. Will continue to monitor progress. 2024-9-13: AHT is on target for the month of August. 2024-8-19: AHT is trending higher than goal. CE Vendor Management is researching root cause with the BPO WFM team. Received update from CEDL on the forecasts for FY' 25 spend; updated the actual for June and adjusted the forecast for the FY. 2024-6-12: Actual expense for May was higher than forecast due to the Five9 invoice for the outbound dialer being received in May. The billing was previously delayed due to contract revisions and the Legal approval process. May AHT was 200, which is better than forecast of 288. 2024-5-16: AHT was better than forecast for April, with the actual being 243 vs. the target of 288. 2024-4-5: CEDL expense for March was slightly lower than forecast due to vendor out of office credits. 2024-3-28: Per discussion with Elizabeth Paige, revised the forecasts - removed costs for Five9 implementation and Five9 licenses (; updated CEDL projections for cloud subscription; removed projections for recurring benefits. Once the revised plan for this initiative is finalized, the forecasts will be updated with the new targets. 2024-3-14: Variance Information: Five9 has not yet billed for the Salesforce connector licenses at $24k per month. Five9 implementation costs projected at $366k for February also have not been billed; SOW changes are still in Legal review. 2024-2-28: CEDL provided demo of Outbound dashboard on 2/28/24; this milestone has been completed. MD meeting conducted with EU team on 2/24/24 to align on strategy for 653. Next step is to review EU's analysis on VA intents to identify which may be best handled via chat escalation and which may be appropriate for an outbound call. 2024-2-19: Variance Information: Five9 has not yet billed for the Salesforce connector licenses at $24k per month. Five9 implementation costs projected at $732k for January also have not been billed; SOW changes are s | K: L5 | Completed | L5 | 2022-10-17 | 2024-12-02
Business w/ Tech Initiative: [AMEA] Optimize current service level standards to | 647 | 6861 | Business w/ Tech Initiative | Commercial - CX | Commercial | Anthony Liaw, Helen Chan | On Track |  | K: L5 | Completed | L5 | 2022-09-22 | 2023-02-28
Business w/ Tech Initiative: [EU] POD 1.2 Increase IVA Containment (PolyAI) | 672 | 6872 | Business w/ Tech Initiative | Commercial - CX | Commercial | Mark Wareham, Dennis Atkins | On Track | Initiate wrap up ready for L4 submission | K: L5 | Completed | L5 | 2022-08-01 | 2024-06-28
Business Only Initiative: [AMEA] Automate proactive notifications when there | 660 | 6883 | Business Only Initiative | Commercial - CX | Commercial | Edward Ow, Nico Mong | On Track | Please find below justification. The reason for the savings to be below plan was due to: 1.Significantly lower TNT account volumes for markets like CN, IN, MY, SG, TH and rest of MEISA due to aggressive customer migration effort to Purple. 2.A big portion of TNT customers in CN were non-account holder hence fell out of the scope of Auto-PN Email which relies on a valid Account number and contact in Salesforce and there was a request to scale down Auto-PN volume in CN due to Operations and Customer Feedback. 3.Lesser than expected effectiveness in markets like AU where there were large numbers of TNT accounts than forecasted. We maay review few months later to see if AU savings can be more and update the numbers. AMEA FP&A had reviewed and provide there following approval to proceed to L5 based on the following considerations 1)Two KPIs meet the target for 3 consecutive months 2)In terms of VFTEs savings, we can only save by 1.8 VFTEs (vs. target 7 VFTEs) mainly due to significantly TNT volume drop and the reason as below 3)Net recurring benefit is now as $0.05m (vs. target $0.36m) | K: L5 | Completed | L5 | 2022-10-25 | 2023-12-08
Business w/ Tech Initiative: [US] Automate claims processing | 684 | 6917 | Business w/ Tech Initiative | Commercial - CX | Commercial | Shirley Turner, Karen Bryant | On Track | 9/25/2024: Impacts and KPIs have been tracked from 7-2023 through 7-2024. Unless requested by the TO, continued updates on this initiative will stop. | K: L5 | Completed | L5 | 2022-07-01 | 2024-02-07
Business Only Initiative: [AMEA] Optimize CE footprints in APAC to achieve r | 625 | 6972 | Business Only Initiative | Commercial - CX | Commercial | Kevin Cheung, Lance Tam | On Track |  | K: L5 | Completed | L5 | 2022-08-01 | 2023-05-05
Business Only Initiative: [AMEA] China Guangzhou Premium Call Center Optimiz | 56621 | 6994 | Business Only Initiative | Commercial - CX | Commercial | Ada Chong, Kevin Cheung | On Track |  | K: L5 | Completed | L5 | 2023-09-01 | 2024-01-31
Business Only Initiative: [AMEA] Resize call center team in AU, ID & IN | 70339 | 7006 | Business Only Initiative | Commercial - CX | Commercial | Ada Chong, Kevin Cheung | On Track |  | K: L5 | Completed | L5 | 2023-11-01 | 2024-03-29
Business Only Initiative: [AMEA] APAC FFTE SG&A reduction | 81321 | 7017 | Business Only Initiative | Commercial - CX | Commercial | Ada Chong, Kevin Cheung | On Track |  | K: L5 | Completed | L5 | 2024-03-01 | 2024-06-28
Business Only Initiative: [AMEA] APAC- China Shanghai CE Office Rental Cost | 73206 | 7025 | Business Only Initiative | Commercial - CX | Commercial | Grace Quan, Maggie Ma | On Track | none | K: L5 | Completed | L5 | 2024-04-01 | 2024-08-30
Business Only Initiative: [US] Increase outsourcing of trace labor (geograph | 619 | 7028 | Business Only Initiative | Commercial - CX | Commercial | Doug Berry, Eric Krug | On Track | 11/18/22 - Wave 0 training has begun to train the vendor training staff in support of the LOBs that are moving. Wave 0 training is a key step in achieving our timeline for this initiative. In addition, training 25 FTEs for the INTL Reps move to IBEX Jamaica has also started - so this part of the initiative will accelerate from the committed timeline for implementation in January vs February plan. 8/4/23 - All actions completed for L4 - forecasted value "# of FTEs moved to new rate" KPI was adjusted to actuals that were needed to realize the benefits of the project. Re-baselining to FY23 actuals produces a $7.1M benefit for FY24 1/23/24 - based on discussions with Domain leadership. this project is being reforecast to incorporate increasing hourly rates to the baseline analysis. | K: L5 | Completed | L5 | 2022-09-01 | 2023-08-01
Business Only Initiative: [US] Optimize PRR Operations | 622 | 7039 | Business Only Initiative | Commercial - CX | Commercial | Julia Selph, Piotr Lorenc | On Track | 10/8/24: KPIs updated for September. | K: L5 | Completed | L5 | 2022-11-01 | 2023-06-01
Business Only Initiative: [LAC] Reallocate US outsourced labor back to exist | 624 | 7050 | Business Only Initiative | Commercial - CX | Commercial | Norma Suarez, Ricardo Asteinza | On Track | All on Track | K: L5 | Completed | L5 | 2022-11-04 | 2023-05-01
Business Only Initiative: [US] Optimize call center service target level | 626 | 7083 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Larry Taylor | On Track | Validating impact amount - updates will be completed by Wed 2/22 12/1/23 - Continues on Track 12/20/23 - note, we had reduced performance/savings due to peak ramp up (temps) resulting in higher than goal service level, expect to return to normal in January | K: L5 | Completed | L5 | 2022-09-19 | 2022-12-01
Business Only Initiative: [AMEA] Optimize CE footprints in MEISA to achieve | 627 | 7105 | Business Only Initiative | Commercial - CX | Commercial | Patrick Peter Makwana, Hussain Khanbhaiwala | On Track | L5 | K: L5 | Completed | L5 | 2022-05-23 | 2023-05-01
Business Only Initiative: [CA] Resize/cancel new hire classes in Canada | 632 | 7128 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Peggy Ramoutar | On Track | Started the evaluation of money savings. There will be a third class cancelled. Due to the drop in call volume, we will not be hiring the January'23 new hire class so, savings in training costs will be increasing in this iniative. | K: L5 | Completed | L5 | 2022-09-20 | 2022-11-30
Business Only Initiative: [LAC] Centralize report generation and segment DCC | 636 | 7139 | Business Only Initiative | Commercial - CX | Commercial | Gabriel Kayser, Fernanda Guerra | On Track |  | K: L5 | Completed | L5 | 2022-11-16 | 2023-02-15
Business Only Initiative: [US] Claims Controls and Fraud Prevention | 70973 | 7491 | Business Only Initiative | Commercial - CX | Commercial | Tammy Brungardt, Karla Venegas Martinez | On Track | Initiative on track 08/11/2025 Initiative on track 08/04/2025 Initiative on track 07/28/2025 Initiative on track 07/21/2025 Initiative on track 07/14/2025 Initiative on track 07/07/2025 Initiative on track 06/30/2025 Initiative on track 06/24/2025 Initiative on track 06/18/2025 Initiative on track 06/12/2025 Initiative on track 06/05/2025 Initiative on track 05/28/2025 Initiative on track 05/05/2025 Initiative on track 04/29/2025 Initiative on track 04/21/2025 | K: L5 | Completed | L5 | 2024-06-25 | 2025-05-30
Business w/ Tech Initiative: [AMEA] Single Desktop with Automation (CN) | 74890 | 7626 | Business w/ Tech Initiative | Commercial - CX | Commercial | Edward Ow, Nico Mong | On Track | expense is being included in #73235 and not this initiative | E: L2 | On Hold | Portfolio Greenlight | 2024-04-01 | 2026-03-02
Business Only Initiative: [AMEA] APAC - FedEx Support Hub (FSH) APAC Develop | 79198 | 7755 | Business Only Initiative | Commercial - CX | Commercial | Ada Chong, Ramona Dawood, Edward Ow | On Track | Since FSH is being rolled under a single initiative, APAC initiative is no longer required. Thank you. | G: L3 | Cancelled | L3 | 2024-08-01 | 2029-05-21
Business Only Initiative: [LAC] FedEx Support Hub (FSH) implementation in LA | 80173 | 7757 | Business Only Initiative | Commercial - CX | Commercial | Gilbert Padin, Norma Suarez, Ricardo Asteinza | On Track | 08/04 - Requesting to cancel initiative as all regional FSH initiatives will be bundled under one US/Global FSH initiative (#152982). 07/31 - Changing Status to "On Hold". Rationale: Regional FSH initiatives are being bundled under one US/Global FSH initiative (#152982). 04/28 - Changed Type of Value to Cost Savings/Reductions and added L1 FY28 NRB annualized exit rate P&L hard benefit 04/25 - Expected savings are comparable to Canada's as we are projecting to save about half the number of FTEs and our salaries are 3-4x lower. 01/10 - Added Gilbert as IO | E: L2 | Cancelled | L2 Feedback Requested | 2027-08-31 | 2027-08-31
Business Only Initiative: [AMEA] APAC Trace Volume Reduction through elimina | 75900 | 7819 | Business Only Initiative | Commercial - CX | Commercial | Daisy Gao, Shan Xiong | On Track | Keep track FY25 performance | K: L5 | Completed | L5 | 2023-04-03 | 2024-09-30
Business Only Initiative: [AMEA] MEISA Trace Volume Reduction through elimin | 75901 | 7820 | Business Only Initiative | Commercial - CX | Commercial | Daisy Gao, Shan Xiong | On Track | Keep track FY25 performance | K: L5 | Completed | L5 | 2023-04-03 | 2024-09-30
Business w/ Tech Initiative: [EU] Pod 3.2 One-Click Expedite / Service Recovery | 692 | 7832 | Business w/ Tech Initiative | Commercial - CX | Commercial | Sharon Bustin, Philipp Muenchenberg, Dennis Atkins | On Track | SB: 13/8/25 - all on track nothing to add SB: 28/5/25 - All on track KPIS updated. :26/3/25 all on track KPIs updated SB: 10/3/25 KPIS updated SB: 17/2 all kpis updated SB: 5/2/25: all kpis updated. 15/11 latest kpis updated. Process launched in Summer, supporting System Capabilities launched end of October to deliver full savings. | K: L5 | Completed | L5 | 2022-11-01 | 2024-01-31
Business w/ Tech Initiative: [EU] Pod 3.3 Standardize TNT Processes | 693 | 7833 | Business w/ Tech Initiative | Commercial - CX | Commercial | Sharon Bustin, Philipp Muenchenberg, Dennis Atkins | On Track | SB: 16/4 On track kpi updates added SB: 10/3/25 KPIS updates. SB: 17/2/25 KPIS updated SB: 5/2/25: will continue to update kpis. but all work complete. Currently finalising evidence for L5 submission. | K: L5 | Completed | L5 | 2022-11-22 | 2024-04-30
Business w/ Tech Initiative: [US] Enforce online customer profile utilization f | 686 | 7853 | Business w/ Tech Initiative | Commercial - CX | Commercial | Drew Kelley, Shirley Turner | On Track | 11/1/24: Load was completed on 10/26 with post-load validation continuing into this week by Hannah Thurmond's team and Claims Operations. Met with Claims Ops (Hannah Thurmond's team), Bo Hale, and Peggy Cleary on 11/1 to determine next steps towards the vendor reduction and timing to be expected - we are on target for our L4 estimated date and Money Step completion for vendor reduction. Vendor Lock has been scheduled for end of November, with reduction taking place 12/1/24. | K: L5 | Completed | L5 | 2022-11-09 | 2024-11-29
Business w/ Tech Initiative: [US] Revise and standardize CE Hours of Operation | 623 | 7901 | Business w/ Tech Initiative | Commercial - CX | Commercial | Kyle Tiemann, Stephanie Boddie | On Track | Impact to be updated by 2/22/23 EOD - recent access to reporting necessitates a better understanding before completing January Impact actuals. 12/1/23 - Continues on Track | K: L5 | Completed | L5 | 2022-08-04 | 2022-11-25
Business Only Initiative: APAC - RPI/RPR Offline Process Revamp | 73761 | 7984 | Business Only Initiative | Commercial - CX | Commercial | Dark Li, Stephen Ye, Lance Tam | On Track | 03/11 - initiative moved to L4 .Monitoring for financial KPI before move to L5. | K: L5 | Completed | L5 | 2024-03-18 | 2025-01-31
Business Only Initiative: [AMEA] APAC – Reduce Rep overtime cost by hiring i | 93783 | 7985 | Business Only Initiative | Commercial - CX | Commercial | Stephen Ye | Some Issues | China team won’t have intern hiring plan in FY26 due to actual CN VFTE 552.4 is more than the headcount in Glidepath file provide by Anthony , unless there’s increase in package volume forecast & VFTE requirement. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-08-01 | 2025-05-30
Business Only Initiative: [EU] Pod 3.7 Static Wrap-up time optimization | 56654 | 8083 | Business Only Initiative | Commercial - CX | Commercial | Tomas Drasar, Philipp Muenchenberg, Dennis Atkins | On Track | Business Case / Benefits drafted for ACW Reduction Time to move into l2 approval process. Minor updates required from IT perspective in Telephony System to optimize EU Static Wrap Time (and potential reporting) | K: L5 | Completed | L5 | 2024-02-12 | 2024-05-31
Business Only Initiative: [EU] Pod 3.8 Reduce AHT (ATT) for Voice | 57670 | 8084 | Business Only Initiative | Commercial - CX | Commercial | Tomas Drasar, Philipp Muenchenberg, Dennis Atkins | On Track | Business Case for L2 Submission has been updated and prepared relevant information / input for L2 submission. | K: L5 | Completed | L5 | 2024-02-01 | 2024-05-31
Business Only Initiative: [US] De-layer the resolution process to remove Tra | 682 | 8173 | Business Only Initiative | Commercial - CX | Commercial | Julia Selph | On Track | March KPI # 3702 (341) Is an estimate will update at later date | K: L5 | Completed | L5 | 2022-10-03 | 2023-02-01
Business Only Initiative: [AMEA] APAC Occupancy improvement to achieve savin | 73985 | 8176 | Business Only Initiative | Commercial - CX | Commercial | Helen Chan, William Sun | On Track | 4/17 - approved by Finance (Anthony Bok) to move to L2. 5/15 - email communication shared to CE MDs on market OCC goals and target. 6/1 - Started the dynamic call support planned in scheduled 7/15 - Shared the WFM Command Centre process during AMEA CEMA calls 8/1 - Sharing of OCC and SA performance for Jun / Jul 9/2 - Finance Anthony Bok approved to move it to L3. 10/23 - presented updates to VP MDs - vftes saving achieved vs target of 69.5vftes in APAC was : Jun 19.52, Jul 29.37, Aug 34.06, Sep 60.93, % of vfte saved : Jun 28%, Jul 42%, Aug 49%, Sep 88% 10/24 - meeting with Finance Anthony Bok to presented the saving calculation and agreed. 11/18 - Oct Total OCC at 93% and Total Schedule Adherence 93% Based on finance report, overall VFTE saving achieved in Oct is -65.68 vs 69.5 or 94% achievement, in terms of vfte savings $107,958.98 or 97% acheivement. 12/18 - Nov Total OCC at 90.9% and schedule adherence at 94% Projected overall VFTE savings achieved in Nov is -66.99 vftes vs 69.5 or 96% achievement. VFTE saving cost will be $108,821.77 or 98% achievement. 4/22/2025 - meeting with Finance (Shweta Ravichandran) seeking endorsement to move to L5. Explained the achievement and saving resutls. | K: L5 | Completed | L5 | 2024-01-31 | 2024-10-31
Business Only Initiative: [LAC] Optimize call center service level target to | 638 | 8398 | Business Only Initiative | Commercial - CX | Commercial | Erika Alejandra Loyola, Ma Luisa Vega | On Track | * | K: L5 | Completed | L5 | 2022-11-30 | 2023-01-31
Business Only Initiative: [LAC] Optimize call center service level target to | 642 | 8399 | Business Only Initiative | Commercial - CX | Commercial | Erika Alejandra Loyola, Ma Luisa Vega | On Track | After reviewing the KPI #5184 we have updated for May the forecast from 45K to 343K that is the real pkg volume that we received during December. For this reason from now on we will see the adjustment. | K: L5 | Completed | L5 | 2022-11-01 | 2023-01-31
Business Only Initiative: [LAC] Achieve operational efficiencies through per | 643 | 8400 | Business Only Initiative | Commercial - CX | Commercial | Erika Alejandra Loyola, Ma Luisa Vega | On Track | * | K: L5 | Completed | L5 | 2022-11-01 | 2022-11-30
Business w/ Tech Initiative: [US] Case EBS Value Bundle 5 | 77392 | 8430 | Business w/ Tech Initiative | Commercial - CX | Commercial | Lynn Kloker | On Track | 1/29/2026: Uploaded money step documentation, set money step to completed 11/14/2025: Successful load to productions for Sept and Oct releases 9/04/2025: Planning for Sept 20 release is underway 8/12/2025: Successful CY25.4 release on 8/09 7/31/2025: The planned July 2025 release has been pushed to August 9 so that the MPS Service Change functionality can be removed from the release and regression testing completed 6/24/2025: Continuing PI 3 development and July release activities 5/28/2025: Code complete for July release. Team demoed features planned for July release. PI 3 planning event June 3-5. 5/21/2025: Successful May release to production. Preparations for July 19 release continue. 4/30/2025: On track for May 17 release 4/14/2025: Development work continues, defect load planned on 4/17 4/02/2025: Successfully completed 3/27 defect/production release. KT continues 3/24/2025: Completed PI 2 planning event 3/17/2025: Successful CEBS release on March 15. PI 2 Planning Event is this week, 3/18-3/20 3/13/2025: Received Go for March 15 release 3/03/2025: March 15 release scope finalized. Regression testing completed and defects fixed. Go/No Go deck finalized. 2/17/2025: PI 1 development and March 15 release planning activities continue. CEBS ART transition to Accenture is underway. 2/10/2025: PI 1 development continues. Release planning and activities underway for March 15, 2025 release 1/30/2025: Success load to production on Jan 18, 2025. Feature development continues in CY 25 PI 1. CEBS ART transition to Accenture begins this PI. | I: L4 | Active | L4 | 2024-08-01 | 2026-01-30
Business Only Initiative: [LAC] Resize HQ customer analytics team | 640 | 8460 | Business Only Initiative | Commercial - CX | Commercial | Norma Suarez, Ricardo Asteinza | On Track | All on Track | K: L5 | Completed | L5 | 2022-10-17 | 2022-11-16
Business Only Initiative: [CA] Revise CE Hours of Operations in Canada | 645 | 8471 | Business Only Initiative | Commercial - CX | Commercial | Stephane Robillard, Kyle Tiemann | On Track |  | K: L5 | Completed | L5 | 2022-08-23 | 2022-12-23
Business Only Initiative: [CA] Optimize call center service level target to | 646 | 8482 | Business Only Initiative | Commercial - CX | Commercial | Stephane Robillard, Kyle Tiemann | On Track |  | K: L5 | Completed | L5 | 2022-10-11 | 2022-12-01
Business Only Initiative: [US] Route all customer facing phone numbers throu | 651 | 8537 | Business Only Initiative | Commercial - CX | Commercial | Rich Mauney | On Track | [RM] 4/30/25 KPI and Impacts (Actuals) updated through March. [RM] 3/10/25 KPI's for February are estimates. [RM] 2/17/25 KPI's are estimates. [RM] 10/7/24 KPI's and Impacts for September are entered and Estimates. Actual data may not be available until 10/17 [RM]8/20/24 All KPI's and Impacts have been updated to reflect actual values. IMPACT higher due to higher than forecast AR [RM] 7/17/24 All KPI's and Impacts have been updated to reflect actual values [RM} 7/15/24 KPI's and Impacts for June are estimates. Waiting for dashboard updates which should be by 7/17/24 [RM} 6/12/24 KPI's and Impacts for May are estimates. Waiting for dashboard updates [RM] 5/7/24 The team working on this initiative became aware of two separate endeavors recently where CS Operations teams contemplated standing up new TFN's for the purpose of bypassing the IVR ang going directly to agents. Obviously, this is contrary to the business case used to justify this initiative. The team is concerned that other similia endeavors may be underway that we are not aware of. As a consequence, we are raising this concern to determine how best to communicate to CS Operations that new TFN's bypassing the IVR may result in a negative impact to this initiative. [RM] 3/20/24 Pursuant the the NLIC POD meeting today, this initiative is ready for L5. I am initiating that process. [RM] 3/15/24 Update: Significant changes were made to OSC Calculations. See Attached Document (I-651_Savings_Recalculation) for explanations. These changes were reviewed and approved by Domain finance and at the IO Director level. [RM] 2/20/24 The IVR CSAT score for January only goes through the 22nd. (That was used as the estimate for January 2024 and may be revised.) Data Science team is looking into it. Note: January Pickup automation rate was lower than forecast. This was due to loosening of business containment rules in R45 as well as negative operational impacts due to weather. [RM} 2/5/24 Uploaded attachment 4 (Three month run rate at money step) in anticipation of advancing this initiative to L5 [RM] 1/22/24 Initial forecasts contained a 90 day offset from when we planned to migrate phone numbers to the IVR. However, we began seeing cost savings as soon as the migration was completed. Additionally, the automation rate for these calls was higher than forecast . [RM] 1/19/24 %Calls bypassing the IVR KPI's are estimated. [RM] 12/19/23 CSAT and %Calls bypassing the IVR KPI's are estimated. [RM] 12/19/23 Advancing this initiative to L4. There is more analysis underway but all L4 guidance has been met. [RM] 12/19/23 pursuant to the discussion in Email, the following changes will be made in WAVE: **Update the name of Milestone #22054 – to read Containment rate of 25%. This milestone is currently scheduled to start January 15, 2024. Once Containment rate is verified at 25% that Milestone will be marked "Complete" and this initiative will advance to L4. Since the money step is now tied to containment rate, milestone #24641 will be cancelled. [RM] 11/21/23 KPI % of calls bypassing IVR is an ESTIMATE. [RM] 11/7/23 - Additional Call routing changes were made in an effort to reduce rep to rep transfers. These changes were made on 11/2/23. We are currently monitoring the impact of these changes. Forecasting team was notified. [RM] 10/19/23 - Met with the Forecasting team and decided to continue the call reduction analysis until the end of next week. Moving the completion date out until then. This WILL impact the money step. Once we conclude whether we can meet the February or March "Lock" deadline, the money step will be updated. [RM] 10/17/23 - The three remaining TFN's were migrated [AG] 9/13/23 -Planning to point these FRTTFNs 866-393-46 85, 866-393-4585, 800-332-0807 to Nuance IVR on 10/16/2023 [RM] 8/31/23 - Still working with FXF to solidify the remaining number migration plan. Due to this delay the money step will be impacted. CE leadership is aware. [RM] 7/31/23 - CE Leadersh | K: L5 | Completed | L5 | 2023-02-24 | 2024-01-16
Business Only Initiative: [CA] 1-800 number from Google search | 665 | 8626 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Peggy Ramoutar | On Track |  | K: L5 | Completed | L5 | 2022-10-10 | 2022-12-01
Business Only Initiative: [CA] Enable polite disconnect for shipments not pa | 667 | 8648 | Business Only Initiative | Commercial - CX | Commercial | Jenny Chan, Kyle Tiemann | On Track | 4/17/2026: There was a meeting with Jenny Chan, Aysha Maaghul, Samantha Baltodano, and Juan Udarbe on 4/16/26, to discuss the rebaseline and reforecast for FY26-FY28. In the Canada IVR, similar to the US IVR, the original direction was to update the IVR to allow call transfers for account holders only (i.e. with a call transfer restriction for non-account holders). The IVR automation rate forecast was initially based on this approach. However, considering the customer experience, management has decided to update the IVR functionality to make it easier for callers to reach a customer service agent. For the FY26–FY28 rebaseline, we will use the average FY25 Jan - May to reflect the latest IVR enhancements, which enable more callers to transfer to agents. With the direction of making it easier for callers to transfer into the call center, the automation rate may decrease, and future saving for this initiative is projected to be zero (as the updated baseline has higher call savings than the forecast). Updated the FY28 exit rate based on this rationale. Also, FY26–FY28 rebaseline and reforecast values have been updated accordingly. •FY26 – FY28 Rebaseline = 201 calls/day •FY26 – FY28 Forecast = 141 calls/day (estimate is based on comparing the FY25 call volume YOY changes) | K: L5 | Completed | L5 | 2022-10-17 | 2023-02-01
Business Only Initiative: [CA] Enable polite disconnect for unidentified cal | 669 | 8671 | Business Only Initiative | Commercial - CX | Commercial | Jenny Chan, Kyle Tiemann | On Track | 4/17/2026: There was a meeting with Jenny Chan, Aysha Maaghul, Samantha Baltodano, and Juan Udarbe on 4/16/26, to discuss the rebaseline and reforecast for FY26-FY28. In the Canada IVR, similar to the US IVR, the original direction was to update the IVR to allow call transfers for account holders only (i.e. with a call transfer restriction for non-account holders). The IVR automation rate forecast was initially based on this approach. However, considering the customer experience, management has decided to update the IVR functionality to make it easier for callers to reach a customer service agent. For the FY26–FY28 rebaseline, we will use the average FY25 Jan - May to reflect the latest IVR enhancements, which enable more callers to transfer to agents. With the direction of making it easier for callers to transfer into the call center, the automation rate may decrease, and future saving for this initiative is projected to be zero (as the updated baseline has higher call savings than the forecast). Updated the FY28 exit rate based on this rationale. Also, FY26–FY28 rebaseline and reforecast values have been updated accordingly. •FY26 – FY28 Rebaseline = 737 calls/day •FY26 – FY28 Forecast = 713 calls/day (estimate is based on comparing the FY25 call volume YOY changes) | K: L5 | Completed | L5 | 2022-09-05 | 2022-11-07
Business Only Initiative: [EU] POD 1.1 Channel Guidance Email | 671 | 8715 | Business Only Initiative | Commercial - CX | Commercial | Dennis Atkins, Daniel Seemann, Marcin Kuzma | On Track | Submitted for L5 - proof captured in Attachment 7 | K: L5 | Completed | L5 | 2022-10-03 | 2023-08-31
Business Only Initiative: [US] Redirect callers to self-serve option | 678 | 8770 | Business Only Initiative | Commercial - CX | Commercial | Amanda Nicholas, Julia Selph | On Track | 10/9/24: Impact and KPI data for Sept '24 is placeholder only, as full data wasn't available before decommission of Wave. Will update in Planview when available. | K: L5 | Completed | L5 | 2022-10-13 | 2023-07-28
Business w/ Tech Initiative: [US] Transition FXE loss claims directly to Claims | 680 | 8778 | Business w/ Tech Initiative | Commercial - CX | Commercial | Jeff Acree, Julia Selph | On Track | 3/21: API that will bypass Trace and create claims cases directly to claims is scheduled to load 3/25. On track for 4/1 move to L4. | K: L5 | Completed | L5 | 2022-10-18 | 2023-03-31
Business Only Initiative: [US] Delay agent assignment on cases for self reso | 681 | 8781 | Business Only Initiative | Commercial - CX | Commercial | Denise Norden, Julia Selph | On Track |  | K: L5 | Completed | L5 | 2022-09-29 | 2023-02-03
Business Only Initiative: [US] Eliminate paper form filing for claims | 685 | 8788 | Business Only Initiative | Commercial - CX | Commercial | Darrin Mcbee, Julia Selph | On Track | 3/30/2023: KC articles being finalized and scheduled to review for publication. 4/07/2023: Impact estimate provided, will update with actual data once available from invoicing 4/12/2023: KPI's updated with actuals for March. 5/17/2023: KPI's updated with actuals for April | K: L5 | Completed | L5 | 2022-09-22 | 2023-11-07
Business Only Initiative: [US] Optimize search and recovery | 688 | 8791 | Business Only Initiative | Commercial - CX | Commercial | Mickey Rainey, Julia Selph | On Track | May KPI 3463 estimated | K: L5 | Completed | L5 | 2022-11-08 | 2023-05-31
Business Only Initiative: [AMEA] Improve CE Ops Productivity | 695 | 8796 | Business Only Initiative | Commercial - CX | Commercial | Chen-Yen Yew, Joseph Chow | On Track |  | K: L5 | Completed | L5 | 2022-08-01 | 2024-11-29
Business Only Initiative: [AMEA] Standardize employee work scheduling proces | 698 | 8798 | Business Only Initiative | Commercial - CX | Commercial | Anthony Liaw, Helen Chan | On Track |  | K: L5 | Completed | L5 | 2022-01-03 | 2023-06-01
Business Only Initiative: APAC - Optimize Clerical Activities | 75107 | 8814 | Business Only Initiative | Commercial - CX | Commercial | Angela Deng, Aiman Khan | On Track | 10/28 - Submitting for L4 approval in Planview 10/21- APAC-wide alignment workshop - Billing Processing Surcharges Round 2 (with more markets) 10/14- APAC-wide alignment workshop - Billing Case Follow-Ups 10/07- APAC-wide alignment workshop - Billing Processing Surcharges 09/30- Savings quantification walkthrough with APAC Domain Finance 09/23- Clarification call with Korea on Billing Case Follow-Ups process 09/16 -Submitted for L3 approval in Wave 09/09- Preparing for Billing Case Follow-Ups process alignment workshop 09/02- First APAC-wide alignment workshop - Invoice Disputes process 08/26- Requesting all markets to refine process information related to Pickup (PUP), Space Booking (DMQ), and Dangerous Goods(DG) tasks 08/19- Requesting all markets to refine process information related to Account Opening (BDG) tasks, Retrieving documents, and Billing-Related (CSI) tasks 08/12- Completed process mapping using Microsoft Visio and prepare cross-selection matrix for alignment workshop 08/05- North Pacific (NPAC) Clerical kickoff with process data collection 07/29- China sub-region Clerical kickoff with process data collection 07/22- Pilot back office synergy discussion in Malaysia and Singapore 07/15- Started Clerical task categorization across markets and populating recorded times, daily volumes 07/08- Review data collection from SPAC sub-region 07/01- South Pacific (SPAC) sub-region Clerical kickoff with process data collection 06/24- Captured daily Clerical% improvement in Thailand after June rollout. 06/17- Review Roles & Responsibilities for Billing tasks between CE/STC/Ground Ops functions in Thailand 06/10- Confirmed process optimization action plans in Thailand 06/03- Captured process SOPs from China for top clerical tasks 05/27- Request for developing daily Clerical BI tool for China 05/20 -Submitted for L2 approval in Wave 05/13- WFMCLERK pilot with Thailand market - kickoff 05/06- Explore Clerical% data from both IPCC/GC3 by agent and market 04/29- Illustrate process mapping for Clerical activities for APAC & MEISA 04/22- Explored process mapping method using QDM tools 04/15- RPI bulk case automation discussion with China 04/08- Kickoff email to Senior Managers 04/01- Created APAC Clerical process collection template 03/25- Submitted for L1 approval in Wave 03/18- L0 generated in Wave | K: L5 | Completed | L5 | 2024-04-02 | 2024-10-31
Business Only Initiative: MEISA - Optimize Clerical Activities | 75202 | 8816 | Business Only Initiative | Commercial - CX | Commercial | Aiman Khan, Anthony Liaw | On Track | Focus on delivering value on the same initiative in APAC first in FY25 (Strategy Seq. ID #8814 and #7094) | E: L2 | On Hold | L2 | 2024-04-02 | 2024-12-31
Business Only Initiative: [AMEA] CE Operating Hours Optimization | 15820 | 8818 | Business Only Initiative | Commercial - CX | Commercial | Helen Chan, Anthony Liaw | On Track | Reviewed done and in scope markets acquired approval from local commercial team to proceed the changes. Phase 1: (JP, KR, SG, VN, WUH) JP, SG, VN implemented in Dec 2022 and monitoring the result from Jan to Mar and will adjust from BP24 WUH implemented in Jan 2023 and monitoring the result from Feb to Apr and will adjust from BP24. KR will implement in Mar 2023 and will monitor the result from Mar to May and will adjust from BP24. Phase 2: AU NZ (Target by Mar 2023 after PSPB review in Feb 2023), WUH in CN (further to shortening to 21:00 and target to implement by Dec 2023 after local alignment) AU target saving 0.6 VFTEs, NZ target saving 0.7 VFTEs WUH target saving 1.6 VFTEs Feb VFTEs: FY22 Actual: (636 JP/ SG / VN /WUH) vs Feb 23 Actual (574), assumed savings achieved Phase 2: WUH 2nd phase changes : Got endorsement from PSP to make the changes from Jun 1 with Gateway to support emergency inquiries Communication done and system changes will done on May 31 Changes done on Jun 1 that CN WUH call center changed the ops hr to 9pm and customers are directed to call CN Gateway for urgent assistance needed. | K: L5 | Completed | L5 | 2022-10-03 | 2023-11-30
Business Only Initiative: [US] Reimagine dedicated claims inbound call group | 1467 | 8846 | Business Only Initiative | Commercial - CX | Commercial | Drew Kelley, Jeff Acree | On Track | 12/20/23: All work complete - tracking savings. | K: L5 | Completed | L5 | 2022-10-03 | 2023-05-01
Business Only Initiative: [CA] Redirect callers to self-serve option | 1589 | 8877 | Business Only Initiative | Commercial - CX | Commercial | Melissa Zehr, Peggy Ramoutar | On Track | On track. - Introduced Canada Sales to ACE application for Lululemon, and verified usage by the customer has started. - Introduced Canada Sales to ACE application for Samsung (Sales to present concept and processes to customer this week) - Meeting with Canada Sales to implement ACE application for Aritzia after a successful Sales presentation to the customer on the application | K: L5 | Completed | L5 | 2022-10-03 | 2023-08-31
Business Only Initiative: [CA] Digital Enhancements | 1591 | 8878 | Business Only Initiative | Commercial - CX | Commercial | Ana Goncalves, Peggy Ramoutar | On Track | 4/22: initiative rebaselined to FY25 | K: L5 | Completed | L5 | 2022-10-24 | 2024-03-07
Business Only Initiative: [US] Optimize Virtual Data Capture (VDC) | 1696 | 8882 | Business Only Initiative | Commercial - CX | Commercial | Josh Russell, Julia Selph | On Track | Tracking Productivity/Quality and updating Impact/KPI (on target) | K: L5 | Completed | L5 | 2022-09-01 | 2023-03-01
Business Only Initiative: [US] Eliminate Manual Processes of Freight Claim D | 2419 | 8911 | Business Only Initiative | Commercial - CX | Commercial | Karen Bryant, Drew Kelley | On Track | 12/20/23: All work complete - tracking savings. | K: L5 | Completed | L5 | 2022-11-01 | 2023-05-31
Business Only Initiative: [US] Improve offshore/onshore mix for outsourced o | 8834 | 9006 | Business Only Initiative | Commercial - CX | Commercial | Margaret Cleary, Eric Krug | On Track | Allocation and realignment are reviewed on a monthly basis as a normal part of operations, further movement to be evaluated at a later date. 2/28/23 - updating Wave to meet L3 requirements | K: L5 | Completed | L5 | 2022-06-01 | 2023-04-28
Business Only Initiative: [CA] Optimize handle time to reduce call work and | 16637 | 9014 | Business Only Initiative | Commercial - CX | Commercial | Peggy Ramoutar, Kyle Tiemann | On Track |  | K: L5 | Completed | L5 | 2023-01-10 | 2023-06-01
Business w/ Tech Initiative: [CA] Build additional self-service capabilities & | 20365 | 9015 | Business w/ Tech Initiative | Commercial - CX | Commercial | Sabrina Dragon, Kyle Tiemann | On Track |  | K: L5 | Completed | L5 | 2023-03-15 | 2024-05-31
Business Only Initiative: [US] Develop flexible schedule to match demand wit | 8931 | 9025 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Larry Taylor | On Track | Feb 13th - Providing preliminary business case for Finance review to move to L2. Feb 24th - Updated Wave to support L3 requirements. 12/1/23 - Continues on Track 12/20/23 - note - impacts have been slightly negative recently due to ramp up in peak staffing, expect to return to positive impact in January | K: L5 | Completed | L5 | 2022-10-03 | 2023-03-10
Business Only Initiative: [US] Develop flexible schedule to match demand wit | 10355 | 9027 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Larry Taylor | On Track | Feb 13th - Providing preliminary business case for review with Finance and move to L2. Feb 27th - Updated Wave to support L3 requirements. 12/1/23 - Continues on Track 12/20/23 - note, we had reduced occupancy performance/savings due to peak ramp up (temps), expect to return to normal in January 1/19/24 - variance update - we had drastically reduced occupancy performance/savings due to peak temps and high OpCo service level, we reduced staffing levels going into January and expect to return to above goal 2/20/24 - variance update - we had drastically improved occupancy performance/savings due to the NSD, we expect rates to return to a more normal level for February 3/28/24 - variance update - forecast updated based on lower hourly rate that was not in line with baseline. 6/24 - variance update - We had vendor staffing shortages that raised occupancy for all lines of business supporting Domestic skills | K: L5 | Completed | L5 | 2022-10-03 | 2023-03-10
Business Only Initiative: [US] Adopt best-practices forecasting and scheduli | 69411 | 9028 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Larry Taylor | On Track | 4/2 - updated documentation and resubmitted for L2 approval with relevant numbers updated for FY23 baseline 7/19 - Variance explanation, due to understaffing issues in June, occupancy is extremely high, resulting in additional savings for this initiative 8/22 - L5 date updated to end of September to allow for 3rd month of actuals to post 9/17 - Variance explanation - We continue to be understaffed, driving Occupancy and Savings higher, this is largely due to the increase in Tracking handle time as compared to what was originally forecast when vendors were locked. 10/7 - Variance explanation - We continue to be understaffed, driving Occupancy and Savings higher, this is largely due to the increase in Tracking handle time as compared to what was originally forecast when vendors were locked. | K: L5 | Completed | L5 | 2023-01-03 | 2024-07-16
Business Only Initiative: [US] Create dynamic forecasting and staffing proce | 69412 | 9031 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Larry Taylor | On Track | 5/3/24 - we are still working on a definition to measure and create reporting on this initiative 9/19/24 - Measures and reporting have been created continuing with business case 10/7/24 - Slight downtick in cases per rep last month due to brief routing issue which caused cases to get stuck in system before making it to a rep | K: L5 | Completed | L5 | 2024-01-01 | 2024-10-31
Business Only Initiative: [US] Optimize identification process and resolutio | 9183 | 9033 | Business Only Initiative | Commercial - CX | Commercial | Kyle Tiemann, Anthony Butler | On Track | Mar 17th - Updates to support L3 including finalized business case. Providing preliminary business case for Finance review and approval to move to L2. Conducting to validate AHT impacts from process changes to further refine the business case. On target to have data to support finalized business case by March 17th for move to L3. 5/25/23 - Milestones and Moneystep time line extended. Large numbers of new hires, due to post peak attrition backfills, at the vendor level have delayed the expected benefit timeline until these new reps gain experience using systems. We are already seeing the improvements expected on the badged side. 6/30/23 - Vendor operations is adopting new Bridge strategy as well as updating PCS verbiage while working through operational issues relating to the number of new hires, still seeing sustained performance improvements on the badged side and expecting improvements on the vendor side in the coming month. We are seeing sustained performance improvements on the badged side, but over-all handle times are still high due to volume of new hires on vendor side. Vendor Performance Management is hopeful improved performance will be seen in July in which action can be taken. 7/24/23 - CE continues to see AHT higher than baseline due to the tenured rep population at time of measure (Jan 23, no new hire classes had been allowed at vendor for several months). Finance and CE have aligned and expect to overhaul business case and savings numbers this month to better align cost per call and savings numbers with initiative 650, since both are targeting the same skills. 7/31/23 - Milestone Timelines updated to adjust for revisiting baseline with Finance 12/1/23 - Continues on Track 12/20/23 - Note - we are seeing increase AHT for November, and thus reduced impact $ due to a multitude of factors mainly from new hires on boarding at both badged and vendor temp locations, as well as CED training 2/20/24 - Nov and Dec variance exceeds $50k threshold, we believe this is a combination of reps being more tenured following peak (no new hire ramp up) as well as potential gains from CED (all DOM reps have been trained on CED phase 1 and should be utilizing the new desktop) | K: L5 | Completed | L5 | 2023-02-01 | 2023-09-29
Business Only Initiative: [EU] Pod 3.6 Improve Training practices/processes | 17516 | 9099 | Business Only Initiative | Commercial - CX | Commercial | Christina Alevizou, Dennis Atkins | On Track | 2024-03-29: FTE realized and initiative ready for L4 submission as planned. Evidence uploaded and EU FP&A advisor has given approval to L4 submission status. | K: L5 | Completed | L5 | 2023-04-03 | 2024-03-29
Business Only Initiative: [AMEA] APAC Optimize identification process and re | 57562 | 9140 | Business Only Initiative | Commercial - CX | Commercial | Chen-Yen Yew, Joseph Chow | On Track | ok | K: L5 | Completed | L5 | 2024-02-19 | 2024-10-31
Business Only Initiative: [AMEA] Deflect China Domestic Business General Cus | 18790 | 9410 | Business Only Initiative | Commercial - CX | Commercial | Lance Tam | On Track | ontrack | K: L5 | Completed | L5 | 2023-03-01 | 2023-10-27
Business Only Initiative: [AMEA] Release China CE RPI Fraud Control resource | 18791 | 9412 | Business Only Initiative | Commercial - CX | Commercial | Grace Quan, Nico Mong | On Track |  | K: L5 | Completed | L5 | 2023-03-23 | 2024-02-28
Business Only Initiative: [AMEA] Increase AMEA VA conversation volume and De | 18793 | 9415 | Business Only Initiative | Commercial - CX | Commercial | Tod Fu, Grace Quan | On Track | N/A | K: L5 | Completed | L5 | 2023-03-10 | 2024-05-31
Business Only Initiative: [AMEA] Reduce Mobile toll free IB cost in TW | 22929 | 9490 | Business Only Initiative | Commercial - CX | Commercial | Joseph Chow, Elsa Kwan | On Track | Already remove the toll free access for mobile callers. | K: L5 | Completed | L5 | 2022-12-23 | 2023-04-28
Business w/ Tech Initiative: [US] Global Customer Experience Platform Consolida | 25200 | 9533 | Business w/ Tech Initiative | Commercial - CX | Commercial | Rachel Wolfson, Amy Alfieri | On Track | 4/22/25: Rebaselined Initiative vs FY25 and also noting that we had to fix some financials from the import from WAVE on 4/17/25 that took a little while to figure out but confirming they are matching business case from WAVE now. There were expense lines in WAVE that were reporting as savings in planview which caused financial impacts to report 4x higher than the original business case. The RFP associated with this project signed the contract at the end of December 2023. When init 25200 was first created in WAVE, we did not truly grasp the full nature of the scope of the project. The OpCos involved in the effort switched around throughout 2023 and the contract we signed included more OpCos than we thought. WAVE activity was put on hold until the contract was signed + technology implementation requirements determined. With more clarity, we are now revisiting our impacts, business case, and milestones. | K: L5 | Completed | L5 | 2023-04-05 | 2024-10-31
Business Only Initiative: APAC - FY25 CE FFTE SG&A reduction |  | 91063 | Business Only Initiative | Commercial - CX | Commercial | Lance Tam | On Track | Business case approved by Finance, Initiative milestones & KPI added, ready to proceed to SL3 | K: L5 | Completed | L5 | 2024-11-15 | 2025-03-31
Business w/ Tech Initiative: Package Research Case Reimagined |  | 92086 | Business w/ Tech Initiative | Commercial - CX | Commercial | Sherveen Masghati, Melissa K. Bongiolatti, Bradley H. Gay | On Track | Pilot complete and ready for US rollout. Rollout approved by Surface SVPs and Brie Carere at July 2025 CESC. Central Florida and North Atlanta completed. South Atlanta launching 2/16/26. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2027-03-31
Business w/ Tech Initiative: [US] Case Automation Expansion |  | 92202 | Business w/ Tech Initiative | Commercial - CX | Commercial | Denise Norden | On Track | Breaking this request into more focused individual requests which will provide better clarity in the business case and scope | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [US] Automate Case EBS Callbacks |  | 92308 | Business w/ Tech Initiative | Commercial - CX | Commercial | Matthew Brooks, Kara Sheeves, Kimla Hill | On Track | Placing on hold as we determine the business case and overall global outbound calling strategy. This use case may eventually be rolled into a larger outbound calling initiative. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: APAC Trace Productivity Improvement (SCQ) |  | 90606 | Business Only Initiative | Commercial - CX | Commercial | Qiu-Hong Cheche Xia, Sharif Rafflee | Some Issues | According to the put a hold reason:US issued an executive order eliminating de minimis treatment for low-value shipments for all APAC countries. I will keep tracking the case vol in Sep & Oct and review the QDM with Sr manager. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Continue - CEDL to Atlas Migration |  | 93162 | Business w/ Tech Initiative | Commercial - CX | Commercial | Stephanie Vaughan, Jenny Varghese | On Track | Initiative Owner assigned Sensitive Data has to be properly handled. Example: Call Transcript | C: L1 | On Hold | L1 Feedback Requested | 2025-10-01 | 2025-11-28
Business w/ Tech Initiative: AU PCC Customer Self-Serve Portal |  | 89676 | Business w/ Tech Initiative | Commercial - CX | Commercial | Andrew Symington, Leeanne Michelle Pellow | On Track | 2026-03-06 - project will not be required due to AU Domestic Transformation. Once AU domestic data is integrated into FedEx environment, PCC team will adopt existing purple solutions (eg Surround). | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: MEISA - FedEx Support Hub (FSH) implementation |  | 96469 | Business w/ Tech Initiative | Commercial - CX | Commercial | Patrick Peter Makwana | On Track | FSH MEISA PART OF GLOBAL ROLLOUT AND INITIATIVE | C: L1 | Cancelled | L1
Business Only Initiative: GC3 Customer Experience Enhancements |  | 96542 | Business Only Initiative | Commercial - CX | Commercial | Kimla Hill, Marvin White | On Track | 04/09/26 - KH - Updated Service Optimization Actuals for March 2026, as contract for new hours was completed at the end of the month. 03/13/26 - KH - As of March 13th we had a pending contract, but had not purchased any new Service Optimization hours for month of February. Therefore, no updates to Actuals were made. 02/13/26 - KH - Updated January 2026 Revenue with Service Optimization Actuals. 07/17/25 - Met with Aysha Maaghul and adjusted the Money Step as advised in feedback. Money step will be realized when contracted system changes are complete. Also confirmed that there is no material action from FedEx IT. 07/11/25 - Met with Aysha again this morning. Made EPM Lead aware that all GC3 CE Enhancements are built into the new lower cost contract with the vendor Five9 and Production code changes are included in the calculations for the projected savings as the Money Step. 07/09/25 - Edited financials to include one-time benefit and recurring annual savings starting in FY26. These are Global Savings. Met with Aysha Maaghul to review and confirm. 07/07/25 - Received Feedback from EPM regarding Financials. Met with Aysha Maaghul and Jenny Mooring to clarify specifcs of ask. Resolution Pending. 06/30/25 - Final Review with Finance (Aysha) completed on Monday, 06/30/25. 06/23/25 - Received a conditional 'GO' for SL3. However, received feedback requesting an additional review with Finance. Meeting scheduled for 06/24 with Aysha in Finance, who provided a new template to use. 06/16/2025 - Updated PPM Status to 'Executing Project' and met with Finance Team to review KPIs financials. 06/11/2025 - Submitted PDSM Ticket INC031038079 to get 'Commercial' added to Technology Milestone. Marvin will have to update the PPM to relect Planview id as 96542 since he is the primary Project Manager. 06/09/2025 - Submitted IMAGE Request to have my PPM Access upgraded so that I can make any needed changes in the future. 06/09/2025 - Completed SL3 Domain QA Expert Review with Samantha Baltodano 04/28/2025 – Samantha Baltodano, Domain QA Expert Review | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-04 | 2028-06-09
Business w/ Tech Initiative: Verint Cloud Migration |  | 98451 | Business w/ Tech Initiative | Commercial - CX | Commercial | Nicole Sandlin, Marvin White, Kimla Hill | On Track | 01/19/26 Cancelling the request, as the decision has been made to remain with the current vendor. LBC needs to be redone as contract is moving through Five9 and not with Verint directly. Pricing negotiations with Verint were successful and realized through Five9 reseller relationship. Implementation plan 18+ in future. FIRST request domain questions need to be moved to IT resources and this is no longer a CE initiative. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: FCF - Phone System |  | 103348 | Business w/ Tech Initiative | Commercial - CX | Commercial | Anik Dam | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Rohan RFP - Generative AI Platform Proposal LLM |  | 103897 | Business w/ Tech Initiative | Commercial - CX | Commercial | Svetlina Yankov, Sandy Whitten | On Track | POC to earn additional $22M and support $217M in EU Sales POC: one year pilot ($137.684 licence costs; this would be the only recurring costs if pilot succesful and extended for more than 1 year) | G: L3 | Active | L3 | 2025-11-24 | 2026-07-01
Business w/ Tech Initiative: Case EBS Value Bundle 6 |  | 106820 | Business w/ Tech Initiative | Commercial - CX | Commercial | Lynn Kloker, Ronald Scot McMinn | On Track | 4/24/2026: CY26.3 release activities underway. UAT 58% complete. On target for May 16 production release 4/06/2026: CY26.2 successful load to production on March 28 3/12/2026: CY26.2 (March 28) on track. PI 2 Planning event 3/17-3/19 2/24/2026: Successful CY26.1 release on Feb 21. On track - continuing PI 1 development, testing and training 1/26/2026: CY26.1 release pushed to Feb 21 due to Pega upgrade 1/13/2026: PI 5 development completed. Jan 21, 2026 release activities - underway. PI 1 planning completed and will start Jan 14 10/22/2025: PI 5 development underway 9/18/2025: Received VDC approval, pending CLEAR approval 9/04/2025: Entered L3, completed VDC submission 8/27/2025: Updated business case benefits/financials 8/21/2025: Updated business case/financials 7/08/2025: Updated business case/financials 6/11/2025: Entered L2. Commercial Triage on 6/16 6/06/2025: Reviewed LBC with CE Finance 3/27/2025: Received notification this initiative has been dispatched and is now in L1 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-23 | 2027-08-31
Business Only Initiative: CA FedEx Support Hub Implementation |  | 108432 | Business Only Initiative | Commercial - CX | Commercial | Wendy Entwistle, Melissa Zehr | On Track | FedEx Support Hub has been rolled up into a single Planview request for all regions, with the request owned by the US team. This individual request for Canada needs to be cancelled. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: DFD Digital Support Manager |  | 112902 | Business w/ Tech Initiative | Commercial - CX | Commercial | Doug Mahan, Gayathri Ashok, Sanjoy Dutta, Kara Sheeves, Hiram Shepard | On Track | Work is planned to be included with Initiative 152953 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: COM-CSX-ARMOR |  | 113849 | Business w/ Tech Initiative | Commercial - CX | Commercial | Shaun Wilson, Bettie A. Abernathy, Harold Winbush, Kelsie Jones | On Track | Planning is on track. Moving through phase-gate. 1/23/26 - updated LBC to remove the 5% YOY revenue growth and updated other financial details. LBC reviewed by Aysha M. and approved to submit to Finance. Resubmitting. 12/10/25 - LBC reviewed by Aysha M. Approved to submit to Finance. Resubmitting. 3/11/26 - Initiative was accidently submitted to L4. Will submit when we reach our Money Step. | G: L3 | Active | L3 Feedback Requested | 2026-01-14 | 2028-03-24
Business w/ Tech Initiative: FXE Canada Claims worked in ECD |  | 130411 | Business w/ Tech Initiative | Commercial - CX | Commercial | Khashayar Namiranian, Steven Holt | On Track | 06/12 - On Track. ¦¦ 12/17 - Initiative is on hold per Danny’s request. Tentatively planned for PI02 per PM’s (Drew) email: “Claims CY26 PI01 Priority Sync.” Email attached. – KN (12/17/2025) | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-10-22 | 2026-01-30
Business w/ Tech Initiative: Global CE Reinvention - Digital Resolution Journey |  | 142092 | Business w/ Tech Initiative | Commercial - CX | Commercial | Gayathri Ashok, April L. White | On Track | 4/23/2025 - CPEL update completed for additional load dates. 4/10/2026: Updated the business case with new cost and added actuals for March. Reviewed the changes with Aysha Maaghul from finance. Changes with business case communicated to Mark Mantaro and he is good with it - he mentioned toupload the new spreadsheet and forecast expense and benefits appropriately and that's completed 3/11/2026 - Actuals (based on available info) updated for Feb 2026 for IT costs( entered the actuals to match with the forecast for Feb). 3/12: For Recurring business Expense (CE Data Lake and Analytics) line items, the February forecast amounts were moved to March, leaving the total unchanged for that line item. For the One-Time Business Expense, entered actuals for Jan and Feb for Adobe analytics and moved the pending forecast amount to March. Reviewed the changes with Aysha Maaghul from finance. 2/12/2026: Actuals (based on available info) updated for Jan2026. For IT costs, entered the actuals to match with the forecast for Jan(based on Jenny Mooring's feedback). For the One-Time Business Expense and Recurring business Expense (CE Data Lake and Analytics) line items, the January forecast amounts were moved to February, leaving the total unchanged for those line items. Reviewed the changes with Aysha Maaghul from finance. 2/11/2026: Updated the start date of WhatsApp milestone to Jan and marked it in progress. 2/3/2026 : Changed the Milestone date for DSM US MVP to pre peak. Moved the DSM MVP to in progress as GRIT ART started the development work in CY26P01. PI planning event completed on Jan 21. 1/20/2026: Commercial Portfolio Kick off completed - All 5 epics has been moved to solution analysis for commercial portfolio. 1/5/2026: Secured L3 approval 12/10/2025: Submitting to L3. Architect sizing is XL. Commercial costing aligns with Large. This was reveiwed and agreed by all relevant stakeholders. 12/10/25 : All financial fields in Planview has been updated with latest Lean Business case figures. 12/9/2025 : Document Feedback Provided/Samantha Baltodano/Domain QA Expert Review 10/23/2025: PPM project number is approved and updated in Planview. 10/20/2025: Solution team members have been assigned to both initiatives from Commercial side.They will prepare the solutioning document and L2 deliverables in collaboration with the IOs. 10/16/2025 : Current Enterprise Ranking is 146 10/15/2025 : PDSM resolved and Value impact changed to High. 10/14/2025 : Amy approved to change the Primary Type of Value Impact to High. PDSM submittted. 10/10/2025: Held CCH triage with CCH Lead to support CCH greenlight review/approval. Updated brief demand description and CCH questions and finalized the CCH overview pptx. 10/09/25 - Changed the Request Type to Gen AI,based on Finance and Drive PMO approval 10/07/2025 - Changed the Primary type of Value to Customer Experience – Problem resolution based on ESPM/DRIVE PMO recommendation and will reach out to Amy Alfieri about changing the Value impact to High. 9/25/2025 - Started conversations with ESPM to begin the booster process aimed at increasing the enterprise ranking, as this ranking sets the priority order for subsequent steps. 9/24/2025 - ttended the Data and AI DRIVE Triage session, and they indicated they cannot support the project at this time due to its low enterprise priority ranking. (#204). 9/22/2025 - After entering L2 , attended the Commercial L2 triage meeting, and the architectural assessment was carried out. Next step is L2 workshop as the path was determined to be D2CP (Direct to Solution, Cross Portfolio) 9/15/2025 - Enter L2 9/12/2025 - Revised Submission to L2 9/11/2025 - Feedback Requested for Lean Business Case 9/9/2025 - Submitted to L2 (SL2). 7/22/2025 - L1 Architecture Alignment step has been completed | G: L3 | Active | TEMP L3 - Enter L3 | 2026-01-01 | 2027-11-04
Business w/ Tech Initiative: FedEx Support Hub (FSH) |  | 152982 | Business w/ Tech Initiative | Commercial - CX | Commercial | Teresa L. Ramsey, Christina P. Ngo | On Track | This initiative was put on hold 12/10/2025, until we hear from the Global Purpose, Customer Centricity (GPCC) team. Since FSH is no longer under CE Reinvention and is falling under GPCC, FSH work is being planned for their roadmap and they have to work through whether we will continue with our initiative or submit under their initiative. | E: L2 | On Hold | L2 | 2025-06-02 | 2028-12-29
Business w/ Tech Initiative: Collection Letters Archive and eCIS update BwT |  | 154549 | Business w/ Tech Initiative | Commercial - CX | Commercial | Patrick Spence, Dasrat Seodyal | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: COM - IA - CIS - Support on APIF Country API (New) |  | 154901 | Business w/ Tech Initiative | Commercial - CX | Commercial | Hong-Ping Alex Zhang | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: (EU) GC3 Five9 Technology |  | 157221 | Business w/ Tech Initiative | Commercial - CX | Commercial | Ryan McVey, Agnieszka A. Fiolna, Simon Caffry | On Track | Five9 workshop completed,next step BRS - Business Requirements Specification to be designed on 08/10/25 | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: LAC BR Telecom Cost Reduction |  | 162338 | Business w/ Tech Initiative | Commercial - CX | Commercial | Willian Augusto de Souza, Ricardo Asteinza | On Track | 01/13 WS: Cancel due to the exit of Brazil Domestic from FedEx portfolio 12/15 WS: On hold as the telephony cost have moved from LAC to HQ. 10/24 WS: LBC updated, waiting on Architecture review ( current ranking within domain: 44 and enterprise ranking: 161 ) 10/10 WS: PV changed from Business Only to Business with tech (PDSM: INC032512177) as after furter investigation it was identified that Diana Teow / Scott Wong will need a PPM to priorityze/work on the demand with Five9, 09/23 WS: Added Ricardo Asteinza (LAC CE eng.) as second I/O | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LAC CE WhatsApp implementation |  | 162649 | Business w/ Tech Initiative | Commercial - CX | Commercial | Willian Augusto de Souza, Ricardo Asteinza | On Track | 09/23/2025 WS: Adding Ricardo Asteinza (LAC CE Eng.) as second I/O 10/31/2025 WS: Feedback from CE reinvetion team: We had the WhatsApp social experience scope already embedded into the AB2s for Digital resolution journey (142092), so that scope will now be part of one of the epics under 142092 initiatives. So, the separate regional WhatsApp inits can be put on hold. 1.162649 - LAC CE WhatsApp implementation – L2 2. 106755 - WhatsApp capabilities for CE – L2 3. APAC initiative number, 7719 (planview )94468 (drive) 01/19/2026 WS: e-mail [Action Needed: Request for Cancellation of WhatsApp Initiatives in Planview] was sent requesting to cancel the initiative due to a consolidation under initiative "Digital Resolution Journey (142092)" please see attached | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Five9 phone system for New Zealand Clearance |  | 163329 | Business w/ Tech Initiative | Commercial - CX | Commercial | Man-Ting Simone Sze, VIAN VAN NIEKERK, Blaine Chen | On Track | 10/15 - Status is green. 3/12/26: request should be local enhancement | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Using Predictive Technology to Enhance the Custome | 27253 | 8780 | Business w/ Tech Initiative | Commercial - CX | Commercial | John Murray, Deidre Thompson, Richard Cruse, SriPadma Chikkam | On Track | 3/26/2026 Finalized Milestone updates 3/19/2026- Milestones updated 3/13/2025 February financials completed 2/16/2026 Working on Milestone(s) update. Completed 40. 2/12/2026- Financials completed. Current Experience - FedEx’s current process for handling lost shipments is reactive, placing the burden on our customers to notify us of a lost or missing package and initiate the resolution process. Loss packages cause confusion, frustration and anger to our customers. By investing in predicting lost and resolving problems in timely manner we will enable savings while improving the customer experience, building customer loyalty and increasing NPS. Future ExperienceA predictive model has been developed to identify packages at risk of loss. If a package in the network lacks scan activity for 48 hours (or 24 hours for MEMH), the model will flag it at the tracking ID level. The model will them provide an output that includes the loss probability for each tracking ID. This information will be provided to the DlaaS (Customer Experience Decision Engine – owned and built by CE). The decision engine will assess whether the package meets the criteria to create a proactive case (considering factors such as loss probability percentage, service characteristics, and more). If the criteria is met, a case will be created and automatically routed by existing rules for resolution, all before the customer calls 1-800-Go-FedEx. Benefits -By investing in predictive technologies and timely problem resolution, we can reduce costs, enhance the customer experience, build loyalty, and increase our Net Promoter Score (NPS). Lost packages cause confusion, frustration, and anger, eroding customer trust and loyalty. Predictive solutions will improve customer satisfaction, strengthen relationships, and increase retention. This initiative supports our broader strategy of leveraging technology to improve operational efficiency along with customer satisfaction (recipient experience), positioning us as a market leader in reliable delivery services. As we transition to Network 2.0, it's crucial to address packages at risk of loss. By doing so, we will not only prevent potential disruptions but also ensure we maintain high customer satisfaction and loyalty. Competitive advantage - Competitors are increasingly adopting advanced tracking and predictive technologies to minimize lost packages, boosting their customer satisfaction and market share. The rise of e-commerce has heightened the demand for reliable delivery services, making effective loss prevention crucial. Our current system struggles with predicting and resolving lost packages, resulting in increased costs and customer dissatisfaction. Note by Stephanie Vaughan - Jan 28,2028: Financials Savings is based on Claims Paid on Loss Packages with No POD. Claims are estimated at a cost of $105. June - Oct are representative of 5 FXE districts: Bay Area, Capital, Delaware Valley, Mississippi Valley, Northern Cali Added in Nov: Carolina, Delta, Houston Metro, Mid-South, North Atlanta, South Atlanta, Panhandle, South Florida, Red River Added in Dec: Peidmont 29 Districts added to measurements in march (launched in Feb) ATLANTIC BUCKEYE CENTRAL FLORIDA CHICAGO METRO COLUMBIA RIVER DESERT EAST TEXAS GATEWAY GREAT LAKES GREAT PLAINS GULF COAST HUDSON INLAND EMPIRE LIBERTY LOS ANGELES METRO MOUNTAIN NEW ENGLAND NEW YORK METRO NORTH CENTRAL NORTHTOP PACIFIC NORTHWEST PLAINS PRAIRIE SOUTHERN CALIFORNIA TRI-STATE UPSTATE NEW YORK WABASH WEST TEXAS WESTERN ROCKIES | G: L3 | Active | L3 Feedback Requested | 2023-11-20 | 2026-06-05
Business w/ Tech Initiative: Whatsapp and Direct messaging channels for CE |  | 106755 | Business w/ Tech Initiative | Commercial - CX | Commercial | Saee Mehta, Kranthi Chennamsetty, Adhir A. Varma, Ayushi Chirania, Vinay Gopalan | On Track | MEISA WhatsApp initiatives has been embedded within the Global CE Reinvention initiative Digital Resolution Journey (142092). The work originally intended for those initiatives is now being delivered under that program.s | E: L2 | Cancelled | L2 Feedback Requested | 2025-05-19 | 2027-10-15
Business Only Initiative: [IN] [Enabler] CE Predictive identification and pr | 81793 | 7676 | Business Only Initiative | Commercial - CX | Commercial | Patrick Peter Makwana | On Track | The predictive capability covered here is now being developed as part of the broader GPCC initiative, and to avoid duplication of scope and benefits, this work will be tracked and realized through GPCC instead. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-09-30 | 2027-05-28
Business Only Initiative: [MEA] [Enabler] CE Predictive identification and p | 84836 | 7722 | Business Only Initiative | Commercial - CX | Commercial | Patrick Peter Makwana | On Track | Inititiave on hold due to dataworks prioritization | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-09-02 | 2026-05-29
Business w/ Tech Initiative: LAC VA Expand Native app chat to LAC countries |  | 166453 | Business w/ Tech Initiative | Commercial - CX | Commercial | Willian Augusto de Souza, Ricardo Asteinza | On Track | 11/04/2025 WS: Added business case file. 11/07/2025 WS: LAC Financial review (Natalie M.) 11/10/2025 WS: LAC QA review (Samantha B.) 11/11/2025 WS: Financial Review (Aysha M.) requested to update the calculations including the whole FY25, and re-submit for review 11/13/2025 WS: #2 Financial Review (Aysha M.) 12/12/2025 WS: Ask to be on-hold prior to the L2-Triage. 01/13/2026 WS: Not approved by Hiram due to efforts. | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: Contact ID Support |  | 107794 | Business w/ Tech Initiative | Commercial - CX | Commercial | Ting Huang, Santhosh B. Korambeth, Jeffrey Tullis | On Track | I have reviewed the LBC with David Johansson back in August. Reviewed by L1 Architecture Alignment: This is a need related to Address Intelligence development (our address and recipient fraud intelligence tools). ​ The Contact ID is an internal data entity managed by the EFS team. It is essentially the unique identifier we have for an individual. ​ It's important in building profiles/awareness of unique names associated with an address. Our team discovered "noise" in the contact ID entity - duplicates created for seemingly the wrong reasons, leading to multiple records for the same individual. We also discovered the records don't persist beyond 90 days. ​ This initiative is asking for support from the owning team to resolve this issue via code. ​ This will likely be a change to business rules​ One variable could be retention - if we retain that ID for longer it might imply more need for data storage | E: L2 | Active | L2
Business w/ Tech Initiative: COM - OTC - Common Support Platform |  | 167915 | Business w/ Tech Initiative | Commercial - CX | Commercial | Leslie McNeil, Tanya Lulla | On Track | **01/07/26 Update** * L1 Architecture Alignment - IO - met 12/19 and were confirmed * ES Portfolio - met on 1/5 and approved to move forward. * Updated the BDD to align with the QA format provided by Karen McConnico. **01/12/26 Update** **QA CHECK** - meeting with QA Expert (Karen McConnico) on 01/12 - SL2 readiness is approved pending 168196 moving to L2 **L1 LBC** - met with Financial analyst, Joseph Nowell, and confirmed an LBC for L1 is not required since this is an enabler **Data and AI portfolio** - Confirmed no impact to DAI. We will use AgentForce AI in CED instead. **01/18/26** **Submit to L2 as the Enabled ID#168196 in Stage L2** **02/04/26** L2 Triage scheduled 2/5 and PRT scheduled 2/11 NOTES *L1 Arch Alignment Mtg Results* L1 Priority Rank: 16 Architecture Owner: Commercial Presenter: TK Krishnan Domain: Commercial Pod: Commercial - CX Decision: Complete *CONTACTS* Primary PO - David Walker COM CE PM - Samhita Marella COM CE SME - Bettie Abernathy COM CE SME - Shelly Guy Domain Finance Contact - Joseph Nowell, Aysha, Megan Lightford COM Domain QA Expert (PMO) - Karen McConnico Enterpise Portfolio Mgr (EPM) - Jodi McDowell ES - Megan Wolf and Rick Paige | G: L3 | Active | L3 | 2026-03-02 | 2027-02-01
Business w/ Tech Initiative: LAC - ALPS Migration to FDS |  | 177030 | Business w/ Tech Initiative | Commercial - CX | Commercial | Alison Cooper | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: APAC Clearance: GC3 and Salesforce to Clearance |  | 180459 | Business w/ Tech Initiative | Commercial - CX | Commercial | Man-Ting Simone Sze, Blaine Chen | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Global Premiere Customer Care (GPCC) |  | 186979 | Business w/ Tech Initiative | Commercial - CX | Commercial | Mickey Rainey | On Track | On Track 3.19.2026 (dfw) asked IO to update LBC so that L1 architecture alignment can be completed. 3.24.2026 (mlr) added ability to statements and began populating other L1 fields. Finalizing LBC for entry this week. | C: L1 | Active | L1
Business w/ Tech Initiative: Data Monetization – AdTech |  | 111235 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Regina Chen, Kartik Chandran, Theresa O'brien | On Track | 6/16/25 : Commercial impact triage session with CCH lead, confimed no commercial impact to the value prop. CCH review not required. 12/1/25: Data Monetisation and related initiatives will be now handled entirely by Dataworks (Tony > Chip C >> Tim Flood). | G: L3 | Cancelled | L3 | 2025-08-15 | 2028-07-04
Business w/ Tech Initiative: Data Monetization - Shipping Tech |  | 111240 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kartik Chandran, Michael Scheid | On Track | 12/1/25: Data Monetisation and related initiatives will be now handled entirely by Dataworks (Tony > Chip C >> Tim Flood). | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Global Airfreight - parity |  | 114082 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Vincent Lafeber, Laura Hill, Gahlawat Arpit | On Track | 13 apr 26 We are in L3! Thanks to all the people who supported this initiative! 16 Mar 26 Had a few sessions and up and down convo to perfectionize the Drive bus case. Removed some older directions like the 10% OM which was lateron replaced by a OM per origin region as well as all verbiage directed to fdx as our northstar shifter now to Polaris: idear remains the same: get to one single shipping solution for our customers who today get lost by our fragmented landscape. 20 Feb 26 All financials agreed with finance and put in the finance tab. All data is broken out per origin region now. Feedback points being handled and re-sumbitted 2 Feb 26 - Greenlight process underway - Continuing to work with Domain Finanace and breaking down costs by region - Some numbers are being updated in PV while some continue to be defined - Requested meeting with Tara Sheeder for review of GAF Digital Sales (US) impact Enterprise Rank 53 Domain Rank 7 Portfolio Rank 34 12 Jan 26 L3 DRIVE requirements in progress, approvals and information from Finance pending + other dependencies. Continued risk to resources & FY26 development til L3 is achieved. Enterprise ranking #101 -Socialization is going well of Business case. APAC (Marcus and Joey) and EU (Scott and Dan) provided their support for the case. Next step is to get to Tara. Then it goes to Denys. -Ops Finance is working on getting the regional Margin information so the business case can be broken down by region. It was scheduled to be done last week but David Spradlin asked for an extension. Meeting to be scheduled asap -Costing is underway by finance; however business case numbers that were estimated for dev do not seem to be taken into consideration. Meeting to be scheduled asap. -Meeting with Architects complete. Based on results, no PRT is required. -Regarding GDX vs Enterprise IT – only about 10% of IT work will come from Randy Scarborough and Aimee Di Cicco. 2 Dec 25 We are in L2: good news. Working on the L2 checklist to get to L3. So far so good but all in all behind schedule. 21 Oct 25 All requested actions are done and Megan approved that her questions where answered. 7 Oct 25 Met with Finance TO office. They found an error in the BC values. Total value is 418M not 6XX and the NRB is therefor 41.4M and not 6X. This explains the 20M too high NRB. Also a set of non financial KPI's where required to add. 17 Sep 25 Corp strategy and Finance met to review the LBC and agreed it was achievable Finance approval to resubmit for L2 received Documents of the above uploaded in content part of this drive init No changes made to the LBC or any other part of the init 11 Aug 25 Received EPM approval for L2 Finance denied. Email sent to Ben Saul. 07 Aug 25 Finance review complete and approved. Informaton updated in PV. Scheduling QA review prioir to submission to L2. (LH) 30 Jul 25 Unable to update L1 Financial Field - PSDM ticket INC031673656 has been opened. Pending final finance review for moving to L2 | G: L3 | Active | L3 | 2025-09-01 | 2028-05-31
Business w/ Tech Initiative: COM-GIX-MQ Broker Manager Solution |  | 114709 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Brenda Shuryan | On Track | No longer needed. If our business partners require an MQ Brocker solution and new request will need to be initiated at that tome. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [VIS] Integrated Visibility 2.0 |  | 103334 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nannette Branigan, Grace Stafford, Sri Kandikonda, Phuc Nguyen, Bharghava Sarabu, Himabindu Peeyeti, Riccardo Sbabo, Haritha Pendli | On Track | 4/13/2026 - Work in PI 2 is now underway. 2/12/26 - CY25 PI01 is underway. Updated actuals for the month 1/6/26 - Awaiting PI 1 Planning ceremony Feb 3-4 EPICs are groomed and ready. 12/22/25 - All epics have been resolved. The development and associated timeline has been pushed from June 2025 to Oct 2025 to coincide with the actual scheduled work approved. This may trigger a change request that may need to be approved by D&T Finance. 12/16/25 - The one EPIC has now been pushed to EPM Update 12/3/25 - All but One EPIC has been pushed to L3. Working with STE to add resources. 11/25/25 - We are in L3! Update 11/17/25 - Still awaiting Matt Hicks TO Finance approval Update 11/10/25 - Now only needs Matt Hicks approval in TO Finance Update 9/22: Delivery team has planned to take this to VDC this week for Data & AI greenlight Update 9/10 - completed CPEL. Standard Duration Model dates as Feb-Apr 2026. Updated milestones & moneystep in Drive to align with SDM dates from CPEL Update 8/28 - completed SL3 readiness QA review with QA lead. Only thing remaining is the portfolio greenlight ans the one-time implementation cost from Commercial portfolio Update 8/27 - preliminary QA review Update 8/15 - completed L2 Commercial portfolio review and greenlighted for concenptual architectural diagram Update 8/8 - completed finance review with finance director Update 8/1 - completed milestones, risks, KPIs Update 8/10 - completed EPICs review with architects and uploaded all EPICs in Planview Update 7/30 - waiting for architect review and precise cost estimate. If we do not get to L3 by mid-Aug, we risk the FY26 revenue goals of $18.5M Update 7/21 - CCH greenlight approved, added PPM# | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-08 | 2027-11-11
Business w/ Tech Initiative: Sirius-Onboard&Upsell-Upsell |  | 103648 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Amanda Engel, Quentin Mace, Miguel Baumann, Roger Reeuwijk | On Track | We are in the process of figuring out if this initative will be folded into the larger Adobe Business Case Init. | E: L2 | On Hold | L2 Feedback Requested
Business w/ Tech Initiative: DFD - fdx Support Experience |  | 103860 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jeff S. McIntosh, Doug Mahan, Sanjoy Dutta | On Track | Cancel because Project Sirius was cancelled. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Sirius-Shipping-FSM/GSM to fdx Replatforming |  | 104065 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Karen E. Vogel, Chiedo Ugorji, John T. Walker | On Track | Asking for the initiative to be included in MAGI backlog. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Semi-automated Account Creation on Invoice on .com |  | 105766 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Linda Bremmers, Ulco Keegstra, Kateryna Lazarenko, Teun Rovers | On Track | 10/21 initiative put on hold 08/15 - alignment needed with CE organisation 07/22 - waiting on approval from DJ Miller 07/18 - resubmitted to L3 approval after EPM feedback about Financial plan 07/17 - submitted for L3 approval 07/10 - waiting for greenlicht from Finance and EPM before hitting the submit button. 06/20 - changing the value 'do you have cross functional resource dependencies?' to 'marketing' is not working, hence cannot submit to next step. 04/15 - Work is 80% complete, remaining work is pending this process and resources | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-09-01 | 2026-06-29
Business w/ Tech Initiative: FedEx Developer Portal Customer Experience |  | 107696 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Amber Phillips, Randy Grodsky, Arvind Reddy, Russell Heady | On Track | Future strategy still TBD. Designs have been started. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Sirius-Onboard and Upsell - FDX/FDP Portal Integra |  | 107704 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Randy Grodsky, Arvind Reddy | On Track | No longer needed. Initiative will be run with a mix of other projects and local demand. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: LAC-BR-BRECO-BDE: Dangerous goods qualification |  | 107712 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Alzira Baptista Borges, Natasha Barbosa Xavier, Sandra Parras, Tatiana Farias, Rhina Marte | On Track | Jan 20th 2026 - canceled as per Sandra Parras' Instructions From Sandra Parras OIC, VPS + ESPM cc FYI Dear BDE Core and Extended Team: With the recent announcement regarding Brazil Domestic Exit, it means the Brazil Domestic Enablement and Domestic Customer Integration (BDE) Project is canceled Some of you have asked me what should be done with the requests in Planview, Onspring and/or PPM as it relates to Brazil DOM or the other portfolios. Below please find a list of the Planview initiatives that should be canceled NLT Jan 31, 2026. A copy of this email should be attached to each initiative canceled. Job aid link: Setting Initiatives to On Hold-Cancel.pdf I want to thank you for all your efforts in the last few years with BDE and I hope we get to work together in the future Any questions please let me know Thanks Sandra Initiatives to be canceled in Planview by Initiative Owner Rationale: BDE project canceled as of Jan 5, 2026 Initiatives where a PDSM should be entered to cancel the request: Enter a PDSM under Enterprise Tools/Planview to cancel request, email to send to Lisa Rolfe with PDSM # entered Rationale: BDE project canceled as of Jan 5, 2026 Sandra Parras Manager, Program Management Office¦ LAC Marketing¦(786) 473-3605 -------------------- 26 Nov 25 - Per BDE PMO Sandra Parras (488838) , this project is on hold until mid Jan 2026. Next steps to be confirmed after that 24 Oct 25 - Waiting for ARC feedback BACKLOG 17 Oct 25 - Waiting for ARC feedback BACKLOG 09 Oct 25 - Waiting for ARC feedback BACKLOG 03 Oct 25 - Waiting for ARC feedback BACKLOG 26 Sep 25 - LBC removed in link based on Taylor M recommendation. Request in Backlog by ARCH 23 Sept 25 - LBC and Planview data was updated as David J (MKT & Finance) recommendation. Submited on Sept 23rd 19 - Sept - 25 Meetig with David J for LBC approval schedulled to Sept 22nd Backlog - Waiting for ARCT team feedback 12 - Sept - 25 - LBC was submitted to David Johansson based on Taylor P recommendation Backlog¦ Waiting for ARCT team feedback (Rachel Vigna) by Sandra Parras 05 - Sep - 25 - Backlog¦ Waiting for ARCT team feedback (Rachel Vigna) by Sandra Parras 29 - Aug - 25 - Backlog¦ Waiting for ARCT team feedback (Rachel Vigna) by Sandra Parras 22 - Aug - 25 - Backlog¦ Waiting for ARCT team feedback (Rachel Vigna) by Sandra Parras 15- Aug - 25 : Backlog¦ Waiting for ARCT team feedback (Rachel Vigna) by Sandra Parras 7/31/2025: Added to this initiative enabler to PV 103177 - Brazil Domestic Optimization; Continue PENDING Architecture Review to move to L2 05/15 - updated L1 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: METL FedEx Net Modernization |  | 107715 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kudzai Tunduwani, Brenda Shuryan, Marisa Broome | On Track | 7/10/25 Business case revised and uploaded following conversation with Mark Mantaro. 6/12/25 Lean business case uploaded showing costs and benefits (nrb) uploaded following meeting with David Johansson 6/11/25. 5/26/25 L1 Architecture Assessment document linked, and mpacted Portfolios and T-Shirt Size fields updated, pushed to SL2. 5/20/25 Financials updated and resubmitted for SL2. Pending architectural documentation. 5/16/25 Submitted to SL2 based on feedback from Bal Reddy Gurram 4/8/25 Submitted LBC | E: L2 | Active | L2 Feedback Requested | 2024-07-22 | 2026-12-31
Business w/ Tech Initiative: Clearance Doc/info uploadTAXID |  | 108661 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nick Spijkerman, Marilyn Taylor, Geremy Solis, Shikha Sood | On Track | 3/27/26 - Requested changes to financials complete. Awaiting leadership approval to move to L3. Target PI 02 Epic 1 - US - T; Epic 2 - LAC - Target PI 02 launch - May'26 upon successful UAT; Epic 3 - CA - target launch Jul'26 3/6/26 - Epic 1 US - Expected to move to L3 (awaiting financial update by IO) this week. Kick off deck has been sent and ready to begin Solution Analysis; Epic 2 MX - On target with target launch date Apr'26 On track **2025 Updates** 12/19/25 - Completed PRT; CPEL on 12/17 for Solution prioritization. SCOPEL on 1/8. US need solutioning work and is targeting PI 02 for development MX does not require Solutioning. DEV is work complete (FIT and FGC) - target of Feb'26 launch 11/6/25 - Epic 1 – US: Target TBA •SCO Architects rejected proposed solution with “new rules engine,” but proposed delay until Doc upload (reason codes) were rolled out. •Meetings in progress (Escalate to Tom if no resolution). Epic 2 – MX: Target Jan’26 •Confirming that FGC ART can complete development by mid December 10/22/25 - MX - on target for Jan/Feb'26 timeline US - The L2 Conceptual Architecture Review was held on 9/30/2025 where the architectural design was rejected by the Clearance Enterprise Architects (Robin Taylor, Tracy O’Brien). The main reason being around ownership of solution components between commercial and clearance and some additional clarity required. The architects have several tasks to complete to resolve ownership concerns which is being project managed by @Manjula Devi. Once the ownership concerns are resolved we should be able to finalize the L2 Conceptual Architecture across the impacted portfolios and hopefully fully complete the L2 deliverables needed for this initiative to progress it to L3 by the end of October. 7/14/2025- PRT workshops scheduled for the week of 21st July to flesh out end to end solution/ 6/19/1996- Detailed requirement gathering sessions in progress with AB2 statements worked out based on changed scope/ 5/21/2025- Based on joint recommendations of MDs- Shobha, Anshuman and John W, the scope of the end to end project was split between .com and fdx flows with tentative solution ironed out. 5/20/2025- MD level techical architecture solutioniong workshop help between FIT and Michelangelo to outline holistic solution. 5/1/2025- Design workshop held based on existing reactive architecture to outline end to end solution 04/21/2025 - Business with Tech initiative where it is a critical exception and did not need to indicate financials. Key assumptions and Money Step are defined. The proper L1 architectural documentation has been submitted and the Commercial, Data & AI, and Supply Chain Operations portfolios are impacted with a T-Shirt size of Medium. Remaining L1 data is populated appropriately. 04/14/2025- Initiative entered on PV based on leadership recommendation. | G: L3 | Active | L3 Feedback Requested | 2026-01-01 | 2027-01-08
Business w/ Tech Initiative: Supplies Modernization 2.0 |  | 109768 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Juyoun Chung, Jeremy Muhiu, Frances Leos | On Track | There has been changes of the direction of this initiative. It is big and complex project. The supplies core team is going to split up the initiative and focus on cost savings first. The first item is restructuring the algorithm with help from the DataWorks team, which is new. It changes the scope drastically. Thus, the team has decided to cancel this one and enter a new one when we has a revised business case with a new scope and necessary alignment. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Sirius-Shipping-Integration |  | 110712 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Lammert van de Bospoort, Taylor McPherson, Leanne Logan, Debby Vrijburg, Obbe Bangma, Amber Phillips | On Track | 10-13-2025 - Init is still on hold pending ongoing discussion 9-25-2025 - Next steps are being discussed in a IT workshop (together with Marketing) 9-16-2025 - Placing this init On Hold based on the below update and conversations with Obbe. Asked team to work towards a permanent decision on whether this should move forward or be cancelled due to remaster mentioned below. 6-3-25 - Sirius-Shipping-Core will remaster all of MAGIC shipping, including SIrius-Shipping-Integrated components. Working through with Product and DRIVE teams how this will be reflected in DRIVE. 5-29-25 - Remastering plan underway. Aligning on adding Pickup and #94166 changes for rest of MAGIC shipping to fdx 5-27-25 - Received L1 Architecture approval 05-19-25 - Remastering plan underway. Uploaded in PlanView architecture illustrations for two paths forward so architects can begin their evaluation this week as David Walker was scheduling. 05-13-25 - Product workshop today resulted in some changes to be updated in PlanView L1 while working to build the business case, financials and PowerPoint overview to attach to L1. 05-13-25 - Name change from Sirius-Shipping-Integration to Sirius-Shipping-Integrated 05-06-25 - Now in L1 05-05-25 - Approved by Rebecca Fowler for L1 04-28-25 - Submitted from L0 to L1 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Digital Front Door (DFD) Tracking Call Reduction |  | 114086 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Doug Mahan | On Track | Work is planned to be included with Initiative 152953 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Increase Mobile Engagement | 29219 | 6751 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Holly McCloskey, Komal Kapoor | On Track | 9.16.25 Aug actuals entered. Will continue to enter actuals for 9 months, through April 2026. 9.2.25 Closing this initiative out. All feature work has been completed. 5.12.25: Release date of final feature will be in PI03 (targeting 7/30/25) which is later than the original estimate of 5/30/25. Other included features that have not been completed are due to blockers, and "stop work" mandates. No new updates. On track. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-08-01 | 2025-07-30
Business w/ Tech Initiative: eLock: 2-factor authentication for 3rd party payme | 84177 | 6842 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Carrie Ng, Vijayanand Krishnamurthy, Hanh Trieu | On Track |  | E: L2 | Active | L2 | 2025-04-01 | 2027-03-01
Business w/ Tech Initiative: Notification Modernization | 89519 | 6877 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Bikram Virk, Amber Phillips | On Track | Work with Renee Clark on the architectural process diagram | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Mobile Messaging (Phase 1) | 89518 | 6879 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Tracy Abrom, Joe Pascal | On Track | Old request, no longer moving forward | C: L1 | Cancelled | L1 Data Migration - TEMP
Business w/ Tech Initiative: Sirius - Segment/CX - Branded Returns | 59484 | 6885 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Like Li, John W. Bishop, Riccardo Sbabo | Some Issues | 11/17/2025: On Hold given strategic pivot to stop development of fdx Branded Returns solution in-house. 8/12/2025: Insufficient resourcing and feature delivery velocity to achieve FY26 revenue goals. Feature prioritization and resourcing requirements are being reviewed by FEC and Dataworks leadership. 6-6-25 Approved for L3 6-3-25 Neil Lanasa (SVP Finance) approving now 6-3-25 Michael Hicks approved (TO Finance) 5-22-25 Moved to Michael Hicks to approve to SL3 5-22-25 DJ Miller approved 5-19-25 - Moved to DJ Miller for Domain Lead approval 5-19-25 - EPM approval received 5/19/25 5-16-25 - EPM review recommends multiple PlanView updates. 5-15-25 - Data and AI Portfolio Greenlight received. 5-14-25 - Data and AI Portfolio Review underway 5-14-25 - Received CCH approval completed 5-13-25 - Completed second review with Ben Saul and David Johansson to finalize business plan with financials before submitting to L3 today. 5-13-25 - Submitted new PDSM to update L2 NRB and Implementation costs 5-13-25 - Swarming around this init to move to L3. Updated financial costs (Mike Scheid) and forecasted revenue (Data and AI Portfolio financials from Jacob Kellog). Updated business case with financials and the associated financials and fields throughout Planview. PDSM ticket of required changes also completed 5-13-25. **1/21/2025** We are moving forward with nothing major to report. The old (original) Business Case needs to be reworked with more realistic and relevant numbers now that we have some. Karishma Patel (MD Marketing) is going to get with her team and get more realistic numbers to be used for the Business Case. We have a meeting scheduled this Friday Jan 24, 2025 to discuss and get our next steps. **Features that are Off track** * None **Features that are At Risk** * **fdx-Experience Manager 2.0** **All other features are On track** * **RGG - Display Basic Reasons for Ineligibility (Final Sale, Return Window)** * **Multi-carrier Returns w/ Branded Tracking (USPS) MVP** * **RGG - Simplified Label Generation Backend API** * **Returns Multi-Org Display Of Returns Dashboard** * **Component Library: Config Updates to support Returns Tracking Pages (RGG 1.5)** * **Returns Web SDK (Returns APIs) For Mobile SDK Consumption** * **Custom Return Reasons/Conditions MVP** * **USPS returns tracking pages and notifications changes** * **Multi Order AP** * **RGG - APIs Access Via Gitbook + DevX** * **RGG - Print Custom Codes on Return Labels** * **Advanced Credit** * **RMA Creation Functionality** * **Returns Settings] Migrate certain rules from Return Policy to platform-level Orchestrator** * **RGG Business Rules: New Returns Triggers, Conditions, Actions** * **Platform-level Orchestrator MVP** * **Even Exchanges: Automated Processing for Exchanges)** * **Display Item Tax in Returns Flow** * **RGG Product Rec - Data Readiness** * **Returns** * **Universal Notification Service: Webhooks Configuration** **1/13/2025** **Features that are Off track** * None **Features that are At Risk** * None **All other features are On track** * **fdx-Experience Manager 2.0** *On track* Design in progress, targeting to start POC in the coming PI * **Returns Multi-Org Config** *On track* Returns team is building dashboard view of returns data based on parent org which will allow all child org data to be viewed within the parent org and allow the customer service portal feature to access returns from all child orgs * **RGG - Display Basic Reasons for Ineligibility (Final Sale, Return Window)** *On track* Pass data on which items are ineligible due to Final Sale or Return Window to RGG so that they can display the reason to consumers in frontend * **Custom Return Reasons/Conditions MVP** *On track* Feature to release to PRD Jan 14th * **Multi-carrier Returns w/ Branded Tracking (USPS) MVP** *On track* Feature to launch Jan 14th * **Returns Web SDK (Returns APIs) For Mobile SDK Consumption** *On track* The team is actively deve | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-06-02 | 2028-05-30
Business w/ Tech Initiative: 300 DPI label print option in CT solutions | 32204 | 6899 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jamie Dean, Tommaso Barbieri | On Track | * 11/18 - Financials updated with costs based on the T-Shirt sizing. * 11/05 - 56k FedEx API requests made over the last 30 days using the 300DPI label functionality. Financials & KPIs updated. Now we have to wait for the remaining TNT customers to be entered into the migration batches (completion should be by Dec 2027) and also any existing Web Services customers that require this funcitonality to be migrated to FedEx APIs (completion should be by Sept 2026). * 09/08 - All CT Automation now allows for the customer to use 300 DPI as a label printing option. We will now look to close the initiative as this now enables TNT customers to migrate once they have been added to the relevant migration batch. * 08/08 - MAGIC development complete, now in post load testing. Still awating identified ACE O2P migration customers to be included in the migration batches. Over the last 30 days 102.3k API transactions have been created globally with the 300DPI resolution included in the request. * 07/10 - MAGIC development release delayed. Still awating identified ACE O2P migration customers to be included in the migration batches. Over the last 30 days 98.3k API transactions have been created globally with the 300DPI resolution included in the request. * 05/28 - MAGIC development completed, awaiting testing to be comple. Still awating identified ACE O2P migration customers to be included in the migration batches * 04/30 - Still waiting on the MAGIC development to be completed. Still awating identified ACE O2P migration customers to be included in the migration batches. Over the last 7 days, 75.5k API transactions have been created globally with the 300DPI resolution included in the request. * 04/17 - Still waiting on the MAGIC development to be completed. Still awating identified ACE O2P migration customers to be included in the migration batches * 04/10 - Still waiting on the MAGIC development to be completed. Still awating identified ACE O2P migration customers to be included in the migration batches * 03/10 - First customer for the list identified as requiring 300 DPI is now creating shipments using FedEx APIs. Still waiting on the MAGIC development to be completed. Still awating ACE O2P migration customers to begin their migration. * 02/27 - 45 FedEx API Organizations have created 24,570 API transactions created over the last 7 days with 300 DPI print resolution. Still waiting on the MAGIC development to be completed. Still awating ACE O2P migration customers to begin their migration. * 02/10 - Added FedEx API Customer Comm document for the July 2024 CSR when 300DPI labels was introduced. FedEx Server v20.09 and GSM Software v25.01 will be released in the coming months, both with the 300 DPI funcitonality. MAGIC development is backlogged. Customers requiring 300 DPI labels with FedEx APIs have been made aware, but majority are awaiting to start O2P migration. * 02/05 - Submitted for L4 approval * 01/22 - Updated L4 date to be 31st Jan 2025. Due to the delay in MAGIC development with no update as to when it will be released, we will move the initiative to L4 with FedEx APIs (GSMW and FXRS have both been tested and expected to be released to market in the coming months * 12/19 - L4 date delayed due to the feature release in MAGIC, GSM and FXRS versions being delayed until 2025. FedEx.com (MAGIC) – Development was targeted to be in place by the L4 date, unbeknownst to us due to other commitments the 300 DPI development was moved back and is now, tentatively, expected in January 2025. As fedex.com has the largest reach, I believe this would be the main reason for delaying the move to L4 and setting the L4 date to end of January. * 12/12 - L4 date delayed due to the feature release in MAGIC, GSM and FXRS versions being delayed until 2025. FedEx.com (MAGIC) – Development was targeted to be in place by the L4 date, unbeknownst to us due to other commitments the 300 DPI development was moved back and is now, tentatively, expected in January 2 | K: L5 | Completed | L5 | 2023-11-01 | 2025-01-31
Business w/ Tech Initiative: Reporting Modernization - Differentiation | 88343 | 6915 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Tiffany Miller, Ned Kumar | On Track | This project will be broken into multiple initiatives since they are local demand. | C: L1 | Cancelled | L1 Data Migration - TEMP
Business w/ Tech Initiative: [VIS] Driver Name & Photo MVP | 40458 | 7103 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nandini Shenoy, Komal Kapoor | On Track | 10/25/24 DNP launched in US on 10/13 Driver participation currently at 24% - Goal is 50% EDM Sep actuals entered 8/7/24 All June Impacts and KPI actuals have been submitted EDM actuals will use methodology to allocate On track for Oct. launch 7/25/24 June Impacts actuals not available yet. Working to have them by early next week. KPI June actuals have been entered. Testing set to start on 7/26 | K: L5 | Completed | L5 | 2024-03-04 | 2024-10-14
Business w/ Tech Initiative: [VIS]Tracking Quality | 40733 | 7108 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Clifton Pappas, Prakruti Joshi | On Track | 2025-01-22: Digital Marketing is reassesing research and our consumer strategy plan and as such the remainder of Tracking Quality is being put on hold until these plans can be finalized. 2025-01-07: Working through some internal re-prioritization, this item is being paused momentarily as we discuss these in the digital space and will resume the commercial greenlight process after those discussions occur in the next few weeks. 2024-12-16: Approvals provided to April Zhou for greenlight, awaiting next steps. 2024-12-09: Sent communication and summary to local and domain architects, after approval will forward to April Zhou to continue with Commercial Greenlight. 2024-12-03: Submitting to Commercial Greenlight to continue towards L3 with the assistance of April White and Neetu Malik for creation of EPIC and tying information to the initiative. 2024-11-12: Still waiting on support for EPIC creation to submit to L3. Team/Donna is aware of this roadblock. 2024-11-06: Connected with Commercial team and Donna/Bonnie/Danny to walk through status of initiative and next steps to get to L3 in new Planview experience. Awaiting architect assignment in order to process and add an EPIC(s) to the initiative and submit to L3. 2024-10-10: Got CCH Greenlight on Friday of last week! Submitted architecture details to TCH and hoping to get into the forum either this or next week. Updated the init in WAVE with some of the finer details needed for TCH as well. 2024-09-25: Successfully made it to L2! Working with the various PMs on Visibility in order to build out a milestone roadmap then will be checking what forums are needed to continue moving through towards L3. 2024-08-21: Business case updated, met with Arul/Megan to review L2 checklist. Final review Friday with goal of submission by EOW. 2024-08-14: L2 work initiated by new IO, no updates, documents received from Arul/Megan | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-08-01 | 2025-12-31
Business w/ Tech Initiative: CASCADE 3.1-API Enabler | 89698 | 7137 | Business w/ Tech Initiative | Commercial - Digital | Commercial | John T. Walker, Chiedo Ugorji | On Track | Need your help please to cancel #7137 CASCADE 3.1-API Enabler —it was entered in by Chiedo but appears to be no longer with the company, but Chiedo already submitted this work as a Local enhancement back in Aug 2025, so we need the BwT initiative cancelled now, so we don’t confuse the Portfolios. The work is getting done via the Local demand type, so this BwT init is no longer valid and must be cancelled. | E: L2 | Cancelled | L2 Feedback Requested | 2025-07-01 | 2025-10-07
Business w/ Tech Initiative: Customer Account Security Privileges | 43265 | 7140 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Vijayanand Krishnamurthy, Hanh Trieu | On Track | 2/6/2026 - cancelling this initiative as the requested capabilities will be covered under 6842 eLock 12/02/2024 - Awaiting architect assignment to complete epics and architecture documentation 11/19/2024 - Awaiting architect assignment 11/13/2024 - Awaiting architect assignment to complete epics and architecture documentation 10/08/2024 - Re-baselined value based on VCPP numbers from various regions. 09/27/2024 - Awaiting VCPP details from Finance to re-baseline. Working with AMEA to define preferred future state by combining the ask with 84177 to assist in TCH greenlight 8/7/2024 - No change: Commercial will not provide feedback until the project is in the Solution Analysis of Commercial process. Need burden cost to recalculate financials 07/10/2024 - Awaiting FXO portfolio review of the initiative, followed by TCH greenlight. Need burden cost for FY24 to recalculate financials | E: L2 | Cancelled | L2 | 2025-01-01 | 2025-07-11
Business w/ Tech Initiative: [VIS] Residential Delivery Instructions Enhancemen | 74823 | 7167 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Gabriela Martucci Salles, Shobha G. Iyer | On Track | 1/13/25: Attended Commercial Triage on 1/13/25. Next step will be to attend CPEL on 1/29/25. 1/29/25: Attended CPEL today to recieve prioritization of the initiative. We were asked to align with Delivery PFS project and report back so they can understand where to sequence this initiative in relation to the DPFS value bundle work. 2/10/25: Meeting to align with DPFS team to align as a phase of DPFS program. 2/21/25: Attended Data & AI Triage, team will follow up with me week of 3/3/25. 3/24/25: This initiative will be considered part of phase 1.2 of the Delivery PFS roadmap. | C: L1 | Cancelled | L1 | 2025-01-01 | 2026-03-13
Business w/ Tech Initiative: [VIS] GBL PPOD phase 2 | 65472 | 7168 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Erin Wichtoski, Nandini Shenoy, Komal Kapoor | Some Issues | 11/4/25: after review and refinement with Finance Domain lead and CE team, determined that claims data cannot be attributed to PPOD solely and therefore not applicable to BV. Will proceed without, as enablers do not technicaly need their own financial benefits. Ready for return to CCH, as we enable "Remove Commercial Signature" going to CCH on 11/6. 10/21/25: have rec'd claims information, will work on L1 financials and L2 as possible with commercial prioroity. PDSM ticket required. 9/29/2025: ESI (Cust Exp) and missing elements added via PDSM tickets, additional new financial data to be updated asap via PDSM tickets. 9/22/2025: per David Johansson, remove hard and soft benefits, enablers do not have those, can leave NRB $0 unlcess claims data is significant. 9/19/2025: CDR on 9/12, leadership agreed to move forward (!), now completing fields with new information, working with David J on financial, Neil on ESI, and CE/Kunal for new info on claims data. With all the alignment now I am able to work on data hygeine from the transfer of wave to planview and other changes. 9/10/2025: was scheduled for deep dive at CDR/CCH 3x, but all rescheduled. Still awaiting Commercial prioritization 7/11/25: Returned to CCH, not able to finish presentation - addressing enabled scope and will seek to attend again. 1/15/25: no update, awaiting Commercial prioritization 1/08/25: no update, awaiting Commercial prioritization 12/17/24: no update 11/19/24: no update 11/06/24: in L2, awaiting Commercial prioritization (home portfolio). Attended TCH prior to the Wave freeze, all portfolios id'd. | E: L2 | Active | L2 & CCH | 2024-07-22 | 2025-05-30
Business w/ Tech Initiative: [VIS] Picture Proof of Delivery Attempt (PPODA) | 70649 | 7169 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Erin Wichtoski, Komal Kapoor | On Track | 12/31/25: no change - will closeout in new year! 2/12/25: no change 12/3/25: ready for closeout! :D 11/12/25: 12 months KPI data completed, as well as estimated financials entered as actuals for cloud storage, per EPM office approval as cloud storage actuals are not possible 10/21/25: will be populated latest available data, looking to closeout shortly 9/19/25: init is launched, no issues, as-is expansions occuring, Money Step reached Oct 2024, ready to close out 1/15/25: no updates 1/08/25: no updates 12/17/24: no updates, product is live, getting ready to report on available data 11/19/24: no updates 11/06/24: submitted to L4. 10/10/24: in L3, launching to all US and Puerto Rico locations on 10/13. Will begin tracking actuals in Planview. 9/6/24: no updates, still waiting on Domain Lead approval 8/28/24: SVP, and Finance approved for L3 - Domain Lead and Domain Executive Sponsor pending 8/23/24: Recieved Technology greenlight, updating Wave requirements, and submitting for L3 but 8/23 deadline 8/16/24: Still waiting for TCH greenlight - attended a secondary TCH leadership review meeting, changes were made, confirmed all steps completed and awaiting TO Technology greenlight 8/9/24: Still waiting for TCH greenlight 8/1/24:: Attended TCH review meeting on 8/1 and was greenlit. Waiting for the toggle and will submit for L3 immediately. Work is either nearing completion in development or in testing. Drivers are using the photo prompts, although photos are internal until launch. The work has moved forward ahead of the DRIVE process, however we want to stay aligned, and are expecting to be in L3 by the August 23rd deadline. | K: L5 | Completed | TEMP L5 - Enter L5 | 2024-08-30 | 2024-09-02
Business w/ Tech Initiative: Exposing shipment level carbon emissions in rating | 48393 | 7175 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Heli Luoma, Rachel Spicer-Green | On Track | Showing carbon emissions in the MAGIC rating and shipping is going through the local demand process. For tracking, we are working with the Dataworks team to investigate a potential solution that may decrease our dependency on Shipment Fusion. We are targeting mid-June to determine which path to pursue. | E: L2 | Active | L2 & CCH | 2024-07-22 | 2024-10-01
Business w/ Tech Initiative: [VIS] GBL Guest Authentication | 49848 | 7189 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Tracy Abrom, Clifton Pappas | On Track | 12/18/23 - L3 date delayed; waiting for TCH greenlight 8/21/24 - Original scope to launch Global Authenticated Guest included launching in both US and CA. FDM CA was delayed in launching which resulted in moving back to L3. Added dependency on enabling Global Authenticated Guest for Rest of World to extend to CA as a milestone and schedule adjusted accordingly. 9/18/25 - GA launched July 2024. The global capability was launched in March 2025. Financials need to be updated to match the change from the original init in WAVE. Working with EPSM team to update Financials. Will review with Domain Finance and QA Expert prior to L4 submission. 10/3/25 - Updated Financials to reflect actual Guest Authentication usage since launch August 2024 through August 2025. Baseline, Forecast and Actuals are Actual numbers for Mapview/Redirect to Hold (RTH)/Indirect Signature Release (ISR). | K: L5 | Completed | L5 | 2023-09-15 | 2025-05-30
Business w/ Tech Initiative: Zuora Subscription Management for Digital Products | 81919 | 7407 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Dipesh Dinker, Harvey Zhang, Joshua Hamblin | On Track | **As of the week of 5/26/2025** US, PR, HK, SG, CA, CN, and JP in production and live. IN in production and live. (Both Zuora and PeopleSoft) EU Templates and Notifications for BE, LU, NL in production and live for all languages. For the EU Tax compliance and Invoice Repository Requirement - Invoice files will be sent to EISTC, test successful and approved,and Tax file will be sent to OITC, testing is completed, awating regional sign-off. *Region is veriying the files for OITC and FedEx net connection to OITC via Zuora.* **As of the week of 5/19/2025** US, PR, HK, SG, CA, CN, and JP in production and live. EU Templates and Notifications for BE, LU, NL in production and live for all languages. For the EU Tax compliance and Invoice Repository Requirement - Invoice files will be sent to EISTC, test successful and approved,and Tax file will be sent to OITC, testing is completed, awating regional sign-off. IN in production and live. (Both Zuora and PeopleSoft) **As of the week of 5/12/2025** FastBill changes in production with Apr'25 CSR. US, PR, HK, SG, CA, CN, and JP in production and live. The templates (English and translated) for EU is completed and testing is completed. Translation for Credit note and reason code provided to Zuora. Zuora to implemented the changes in the system. Awaiting regional sign-off. For the EU Tax compliance and Invoice Repository Requirement - Invoice files will be sent to EISTC, test successful and approved,and Tax file will be sent to OITC, testing is completed, awating regional sign-off. Template for India has been implemented in Zuora. Testing from Zuora completed. RevTav configuration is not required. Tax to be calculated downstream in PeopleSoft. PeopleSoft UAT is in progress. **As of the week of 5/5/2025** FastBill changes in production with Apr'25 CSR. US, PR, HK, SG, CA, CN, and JP in production and live. The templates (English and translated) for EU is completed and testing is in progress. Translation for Credit note and reason code provided to Zuora. Zuora to implemented the changes in the system. For the EU Tax compliance and Invoice Repository Requirement - Invoice files will be sent to EISTC, test successful and Tax file will be sent to OITC, testing in progress. Template for India has been implemented in Zuora. Testing from Zuora completed. RevTav configuration is not required. Tax to be calculated downstream in PeopleSoft. PeopleSoft UAT is in progress. **As of the week of 4/28/2025** FastBill changes in production with Apr'25 CSR. US, PR, HK, SG, CA, CN, and JP in production and live. The templates (English and translated) for EU is completed and testing is in progress. Translation for Credit note and reason code provided to Zuora. Zuora to implement tthe translation in the system For the EU Tax compliance and Invoice Repository Requirement - Invoice files will be sent to EISTC and Tax file will be sent to OITC. Template for India has been implemented in Zuora. Testing from Zuora completed. RevTav configuration is not required. Tax to be calculated downstream in PeopleSoft. PeopleSoft UAT is in progress. **As of the week of 4/21/2025** FastBill changes in production with Apr'25 CSR. US, PR, HK, SG, CA, CN, and JP in production and live. The templates (English and translated) for EU is completed and testing is in progress. Translation for Credit note and reason code provided to Zuora. Zuora to implement tthe translation in the system For the EU Tax compliance and Invoice Repository Requirement - FedEx Net interface is set up. Zuora to start testing. Template for India has been implemented in Zuora. Testing from Zuora completed. RevTav configuration is not required. Tax to be calculated downstream in PeopleSoft. India StC team to test the Peoplesoft downstream process. **As of the week of 4/14/2025** FastBill changes in production with Apr'25 CSR. US, PR, HK, SG, CA, CN, and JP in production and live. The templates (English and translated) for EU is complete | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-01 | 2025-04-30
Business w/ Tech Initiative: E-commerce platform connections with MAGIC | 24799 | 7439 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Obbe Bangma, Gwen Roelofs | On Track | 9/12: L2 submitted - finance lead approved for L2. 7/01: already in consultation with regional finance leads to get regional approval as prep for L3, US ground finance approved it (biggest impact on business case). | E: L2 | On Hold | L2
Business w/ Tech Initiative: Address Intelligence Suite | 78438 | 7640 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jeffrey Tullis, Kartik Chandran, Rebecca Fowler, Ting Huang | On Track | Org changes. Leadership should decide whether this initiative is to be continued and determine staffing, if applicable. | E: L2 | On Hold | TEMP L2 - Enter Value Prop | 2024-04-10 | 2025-11-28
Business w/ Tech Initiative: [VIS] Secure Tracking Modernization | 81298 | 7665 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Chad Girnus, Grace Stafford, Rupesh Agrawal | On Track | **8/21/2024: IT CLEAR at risk ( loss of experienced vendors) if we don't get FCH approval. Need to escalate.** 08/14/2024: Awaiting updates from FCH for L3 approval **08/08/2024:** TCH greenlit today. Working with Arul for submission to L3. FCH review and approval planned for Tuesday 8/13. Have socialized the financial impacts with Mark M in advance. Enabler initiative which enables projects with $4.12M NRB. The CLEAR for Project 9012477 is expiring on 8/31, we will have work stoppage on 9/1 if this initiative isn’t in L3 by then. NOTE: Inability to get this initiative to L3 approved state by end of July will impact the approval of Visibility CLEAR being approved by August 2024. 70% of support for Tracking Initiatives will CEASE if the Visibility CLEAR is not approved before August 31st 2024 INITIATIVES AT RISK DUE TO CLEAR DEPENDENCY (Need CLEAR approval by August 31st which is contingent on this DRIVE initiative being L3 approved) 1.Driver Name & Photo MVP - DRIVE 40458 2.Picture Proof of Delivery Attempt (PPODA) - DRIVE 70649 3.Package Service Delays - Weather Delays, EDD Expansion - DRIVE 40646 4.CASE status in Tracking 5.VA 100K Large Shipper Tracking - DRIVE 16865 | G: L3 | Active | TEMP L3 - Enter L3 | 2026-02-03 | 2026-05-29
Business w/ Tech Initiative: [VIS] Ground Fusion Retirement | 81349 | 7668 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Chad Girnus, Lisette Souza | On Track | 4/3/2028 Required end date for Iseries has been moved out to May 2028. 9/17/2024: Submitted for L3 approval on 8/31. Received Finance approval on 9/3. Received DJ approval on 9/16. Submitted for FCH approval on 9/16. 9/10/2014: Awaiting Domain Lead approval for L3. Will then need FCH approval 8/28/2024: Got the commercial portfolio greenlight at CPEL today. We need the TCH greenlight TODAY ( all impacted portfolios have greenlit the initiative), so that we can submit to L3 today. The IT CLEAR approval is dependent on getting the initiative in L3, failure to which, we will lose out IT resources supporting TSV/Ground Fusion. 8/26/2024: Update L3 forecast. Presenting at CPEL on 8/28 and hopeful that high prioritization from CPEL will help move things forward for other impacted portfolios. At the moment, Surface portfolio is not reviewing our initiative since it does not have FY25 value > $1M. 8/14/2024: Platinum LPM scheduled for 8/19. DW portfolio working on steps for approval. IT CLEAR approval will need executive support since #81349 is not on path to L3 approval by end of August 8/12/2024: Updated L3 date since CPEL/PRT required based on TCH review. PRT on 8/14. ATTN: This initiative needs to be L3 approved by August 1st to avoid stoppage of work from vendors on Sept 1st. CLEAR 901422 will expire on August 31st 2024 and this initiative needs to be L3 approved for the new CLEAR to be executed. NOTE: Inability to get this initiative to L3 approved state by end of July will impact the approval of Visibility CLEAR being approved by August 2024. 70% of support for Tracking Initiatives will CEASE if the Visibility CLEAR is not approved before August 31st 2024 Updated L2 date to incorporate feedback INITIATIVES AT RISK DUE TO CLEAR DEPENDENCY (Need CLEAR approval by August 31st which is contingent on this DRIVE initiative being L3 approved) 1.Driver Name & Photo MVP - DRIVE 40458 2.Picture Proof of Delivery Attempt (PPODA) - DRIVE 70649 3.Package Service Delays - Weather Delays, EDD Expansion - DRIVE 40646 4.CASE status in Tracking 5.VA 100K Large Shipper Tracking - DRIVE 16865 6. EU Bunker Visibility initiatives 7. Global EDD rollout 8. Monetize Track Data and many more | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-01 | 2028-05-30
Business w/ Tech Initiative: [US] Implement visibility enhancements on FedEx.co | 649 | 7727 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Vinod Nair, Roglly Centeno, Advait G. Cherian | On Track | 04/16/26: L4 Approved. We have the acutals for the last 9 months and all the money step has been completed. We are submitting to L5. IMPACTS AND KPIs WILL BE UPDATED AFTER THE 20TH OF THE MONTH 11/21/22: Cost savingactual for October not available so the forecast value was used. It will updated as soon as October actual vaue is available. 11/7/25: Moved Money Step date out to Jan 15 2026 per Vinod's request. 10/1/25: There is a lag on the reporting of one of the items needed for cost calculations. I used forecast for July. Aug and Oct and will update as sooon as the actual numbers are available 9/22/25: Money step has been moved to end of October and a new initiative owner will be assigned this week. 3/24/25: Updated Jan cost saving numbers to correct a mistake on calculations 2/10/25: Updated CAPEX and Expenes for Nov and Dec 2024. jan numbers for costs and revenue are not ready. 10/28/24: UPdated impacts and KPIs for september. Ease of use KPI scale was decreased from 1-11 to 1-5. Forecast was updated with new goal with the new scale that we will reporting moving forward. 9/23/24: KPIs add impact for Aug had been updated 7/29/2024: KPIs and impacts have been updated 7/17/24: Launched of GPS POD and Map view in July 2024 CSR completed. 6/18/23: Impacts and KPIs were adjusted to reflect the EDD Supression change. Money step was moved 6 months out 6/6/24: Updated impact tab for expenses. Money step will have to be moved 6 months and changes on the forecast due to EDD supression timeframe change still need to be completed. IO coordinating how to change the forecast. Once changes are completed I will update the status. 5/21/24: KPIs and Impacts were updated. Follow up about expenses numbers for April is happening to understand if that should be part of the reporting and how to report that. Also there might be a new forecast and move out of the money steps later to the current date due to a change of EDD supression implementation. Leadership is currently working on agreement on new timeline for completion, Forecast and milestones will be revised appropriately as soon as the decision is completed. 4/11/24: Updated impacts for March 2024. 4/1/24: Decision from leadership was to cancelled EDD Supression (Delays Phase 3). All milestones related to the project will be cancelled. There might be changes on impacts and if so, those will be updated on the next days. The decision was based on that fact that EDD suppression could cause inconsistencies among different channel experiences that were going to negatively affect the surround customers, to avoid having such inconsistencies the Dataworks team and the Digital leadership team agreed not to launch EDD and continue to increase accuracy of the model in order to enhance the experience. 3/13/24: impacts and KPis for Feb. had been updated. No new target for Ease of Use KPI has been estimated with the new survery. Team still working on completing greenlight. 2/16/24: VB7 and Stop counts work has been removed from this initiative. The impact will not change as those two features do not have significant value compared to the features already delivered or to be delivered. The goal is to greenlight the initiative since we do have VB4 in testing, targeting April '24 and VB5.1 and 5.3 with assigned resources with development targeting July '24. With the removal of this two pieces the initiative should be able to be greenlighted. The IT lead is working with TCH to ensure this happen soon. 1/18/24: Got confirmation that the DOTS survey substituted the Intercept study and the ease of use will now be measure via DOTs survey. Added new values for Sep-Dec 2023. Additionally, we have delays on certain milestones. Even when we completed the production load of 2hr and 1 hr window, the only piece that have been released to market is 2 hr for Express only. The 2 hr for Ground and 1 hr confirmation has not yet been released to market and the Dataworks team is working with the OpCo to have GPS data c | K: L5 | Active | L5 | 2022-11-01 | 2026-06-23
Business w/ Tech Initiative: Package Service Delays - Phase 4 - Weather Delays, | 40646 | 7744 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Bikram Virk, Amarpreet Singh, Vinod Nair | On Track | Currently in PRT backlog waiting for architect assignment, ranked #7 as of 3/18/2025 | E: L2 | Active | L2
Business Only Initiative: Day of Delivery (Last Mile) Phase II | 74331 | 7764 | Business Only Initiative | Commercial - Digital | Commercial | Vinod Nair | On Track | Define Strategy and the Ability to's for the phase 2 | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Rate Caching - Make rates available to offline cus | 15392 | 7766 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Emmy Kitolo, Ryan Ridgway | On Track | This effort is being cancelled in lieu of the Rating Containerization effort which is moving forward as a separate PV init. | C: L1 | Cancelled | L1
Business Only Initiative: COP UI Enhancement/HOPE 2.0 Adoption | 95885 | 7773 | Business Only Initiative | Commercial - Digital | Commercial | Jake Brannon, Sanjoy Dutta | On Track | This work was already completed | C: L1 | Cancelled | L1 Data Migration - TEMP
Business w/ Tech Initiative: Modernize Online Claims Experience Drive #15525- P | 96307 | 7774 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Sanjoy Dutta, James McCloskey, URSULA MARKS | On Track | Mike Schween put this on hold for now | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: [VIS] Global Integrated Track Data MVP | 92141 | 7874 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nannette Branigan, Grace Stafford, Bharghava Sarabu, Sri Kandikonda, Taylor McPherson | On Track | 4/12/26 - Work has completed with PI 1 - however there is some cleanup needed before moving to L4. Expect the defect fixes to load in May 2026 2/12/26 - CY26 PI1 underway - next update at end of PI will reflect what has been released to customers. Expect his in April. 1/6/26 - PI planning preparation - confirmed EPIC is included in PI1. Work to begin in January and actuals will be started at that time. 12/22/25 - Awaiting PI Planning for CY25 PI1 to confirm the EPIC for localization on FDP will be worked. Next update will be after 1/22/25 when the PI work is committed. 12/3/25 week - In L3 - EPIC will be worked in CY26 PI 1-2. 11/17/25 week - Attend Cross Porfolio on 11/13 to officially reduce scope to just localize developer.fedex.com. The EPIC for localiation was dropped down in Agility on 11/18. Working with PM to determine exact dates of coding. - Pushed the forecast out begin Dec 11/10/Week - Strategic decision has been made to exclude from scope the Fastbill Product Code Creation. Instead we will focus ONLY on developer.fedex.com localization. 10/16/25 week - Still pending Enterprise Portfolio Management decision on how to move forward. 10/7/25 week - Met with RMIC, Fastbill, Contract to Collect and Commercial PMO - A CRI: Commercial Response Impact will be added to flag these gaps that remain: a). Reduce scope to CA only b). RMIC needs revenue for CA only and thru Fast bill to help justify the work c). One gap for all digital products is that Contract to Collect will requires a product code for each tax impacted country/region - 7874 will only now solve for Canada 4. Agreement from commercial and digital product on the path forward 9/29 week - While this is in L3, the blocker of obtaining RMIC resources remains. RMIC is awaiting 103334-Sirius Visiiblity Integrated Visibility 2.0 to be in L3 as the revenue tied to it helps them justify we work. Thus, the one EPIC associated with this effort has not been pushed down into Agility and teams are unable to 'work it'. 9/22 week - No change. Our blocker is below. 9/17 week - RMIC has not yet prioritized the work to add Fastbill product codes for billing, taxation, and accounting purposes.. RMIC requires 103334 - Sirius Visiblity IVP 2.0 to be in L3 before work is added to their backlog and prioritized. There is risk to our timeline as resources are consumed with other prioirties like Contract to Collect. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-12-15 | 2026-09-01
Business w/ Tech Initiative: Prevention of Counterfeit Labels in FedEx Network |  | 79804 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Vijayanand Krishnamurthy, Hanh Trieu | On Track | 12/10/2025 - Reviewed with CPEL on 11/05. Project in PRT backlog with rank#55. Meeting scheduled with Digital Pod PMO members and architects on 12/17 to discuss business continuity aspect of the initiative 10/06/2025 - Reviewed business case and financials with David Johansson. Submitted to next step. 10/02/2025 - Working with finance to finalize business case 06/16/2025 - Submitted to SL2 06/11/2025 - Received email that L1 architectural alignment has been completed 02/10/2025 - Awaiting EA alignment to complete biz w/ tech section 01/07/2025 - Awaiting EA alignment to complete biz w/ tech section 12/02/2024 - Awaiting EA alignment to complete biz w/ tech section 11/19/2024 - Awaiting EA alignment to complete biz w/ tech section 11/13/2024 - EA alignment needed to complete biz w/tech info section updating to the correct Primary IO | E: L2 | Active | L2
Business w/ Tech Initiative: COD Retirement for FSM Software (cafe') | 80629 | 8000 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Susan Carnes | On Track | 1/28/25 waiting on Architectural Documentation for FSM Team. 3/4/25 work has been picked up by the FSM team. 3/11/25 - FSM team will be removing the View / Edit COD button so the whole dialog box will go away. 3/18/25 - No change 3/25/25 - No change 4/1/25 - working on getting architectural documentation needed to move forward. 4/22/25- still waiting on documentation from FSM team. BOL update is moving forward with April CSR. 4/30/25- FSM team has started the Freight build portion of FSM Software and will remove the COD portion as a part of their work. 8/6/25 - Cancellation request due to Freight Separation | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Customer Label Creation Threshold | 42812 | 8139 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Hanh Trieu, Vijayanand Krishnamurthy | On Track | 4/10/2026 Continue to record financial and KPIs actuals for all regions 3/12/2026 No update. recording financial and KPIs actuals for all regions 2/2/2026 No update...feature is rolled out to all regions (Americas, MEISA, APAC and EU) 1/29/2026 Gradual rollout for EU began on 1/28/2026. 1/15/2026 Project pending rollout to EU as the last region. Resource constraint is still the challenge for EU. 1/5/2026 Project is pedning rollout to EU as the last region. Resource constraint is still the challenge for EU to launch this capability there. 12/22/2025 project is pending rollout to the last region, EU. There is resource constraint in EU. 12/17/2025 project is pending rollout to the last region, EU. There is resource constraint in EU. 12/2/2025 project is pending rollout to the last region, EU. There is resource constraint in EU. 7/14/2025 global rollout to CA completed 5/12/2025 global rollout to MEISA completed 5/7/2025 Capbility implemented by IT on 4/12; global rollout is in progress with LAC, US and APAC completed 3/24/2025 L3 testing continues with target completion of 4/8. 3/10/2025 L3 testing continues. 2/24/2025 L3 testing continues. 2/19/2025 L3 testing continues. 2/10/2025 L3 testing in progress. 2/3/2025 Development (except EIW) have loaded code into L3 and ready for test execution. EIW will have code move to L3 on 3/8/2025 with MTP date of 4/12/2025. 1/29.2025 Development have either loaded code into L3 or target to load code by L3C1 for APR CSR L3 testing schedule. 12/30/2024 No Update.ARTs countinue development and testing activities. Target launch date remains for APR25 CSR. No blocker raised by IT to complete for targeted CSR. 12/26/2024 No Update.ARTs countinue development and testing activities. Target launch date remains for APR25 CSR. No blocker raised by IT to complete for targeted CSR. 12/17/2024 No update. ARTs countinue development and testing activities. Target launch date remains for APR25 CSR. No blocker raised by IT to complete for targeted CSR. 12/9/2024 No update. ARTs countinue development and testing activities. Target launch date remains for APR25 CSR. No blocker raised by IT to complete for targeted CSR. 12/3/2024 No update. ARTs continue development and testing activities. Target launch remains for APR25 CSR. No blocker raised by IT to complete for targeted CSR. 11/26/2024 No update. Solution/ART continues development and testing work. Target launch remains for APR25 CSR. IT have not indicated any blocker to complete for target CSR. 11/18/2024 No change. Solution/ART are continuing development and testing work in current PI with target launch of APR25 CSR. 11/12/2024 No update. Solution/ART are continuing development and testing work in their CY24.PI05 with target launch of CSR APR25. 11/5/2024 No update. ARTs are continuing development and testing work in their CY24.PI05. 10/29/2024 IT teams have planned the work in their CY24.PI05 9/4/2024 waiting on the cost per package data to recalculate financials from FY23 to FY24 before submitting for L3 approval. 8/28/2024 waiting on Finance for the FY24 cost per package to recalculate financials from FY23 to FY24 before submitting for L3 approval. 8/22/2024 greenlit from TCH but still waiting on FY24 cost per package to recalculate financials. 8/14/2024 no update. Still waiting on FY24 cost per package to recalculate financials. Still waiting on TCH greenlight. 8/7/2024 no update. Still waiting on TCH greenlight. All portfolios provided feedback. Need burden cost for FY24 to recalculate financials. 7/10/2024 Waiting on TCH greenlight which still has Commercial feedback in Wave as outstanding before providing the greenlight. 1/16/2024 Met with Mark to review the 94% projected savings and the basis for the %.; recommendation to re-evaluate and lower the projected savings % 2/6/2024 Met with Mark to review the adjusted projected savings of 72% along with the use cases used as basis for the updated project savings %; Mark is | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-30 | 2026-09-29
Business w/ Tech Initiative: Missing-in-Transit / Package Theft Tool | 91774 | 8154 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Brian Hanson, Vivek Varadarajan | On Track | Project is on track/ahead of schedule | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: RPI Digital Enabler - Identifier / Billing Party I | 80694 | 8208 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng, Youn-Ji Suh | On Track | We received the notification earlier in June that this initiative is classified as "low value / high effort", thus a Stop Work has been put to the initiative. So it is not being worked on at the moment. The asks in this initiatives are being pursued under another larger initiative. | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2024-09-17
Business w/ Tech Initiative: Automated Account Creation on Invoice via .com | 97124 | 8241 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Linda Bremmers, Ulco Keegstra, Kateryna Lazarenko, Rob Smit | On Track | 13-JAN-2026: actuals are 0 as invoice account creation was paused earlier (see below comment) 20-NOV: Added actuals for EU (rest is not live yet). Note that in October we saw an increase in fraud and have turned off the invoice account creation option until we have better fraud prevention in place. This will result in lower actuals for the time in between until we can turn it on again. First work on fraud prevention is completed. 3-NOV: L3 approved since Oct 23rd. Plan to have additional resources shifted from HOPE 2.0 and extend G2D for this work. 20-OCT: waiting on approval from Brie (since Oct 14) 9-OCT: SL3 QA readiness check revalidation with QA Expert, Karen McConnico. Also discussed TO Finance approval escalation with Karen as Commercial Domain PMO. TO Finance approval has been pending for 9 days. 2-OCT: waiting for TO Finance approval 25-SEPT: adjustments made as requested by David Johansson on Sept 18th, waiting for approval from Mark 4-SEPT: finance adjustments made, resubmitted for finance approval. 15-AUG: waiting for DJ his approval. 28-JUL: still waiting for approval 16-JUL: waiting for approval from Mark 11-JUL: resubmitted for L3 approval after feedback EPM - waiting for Finance to approve 9-JUL: submitted for L3 approval 27-JUN: awaiting for last PDSM ticket to be resolved (input correction) 20-JUN: awaiting finance input to submit to next step 12-MAY: finishing the last pieces for L3 submission. Expected this week. 21-FEB: we've asked to back-fill the Ability To statement and Business Process field via a PDSM ticket, but they have put us back to L1 to resubmit with the new info. The Demand Shaping Business w/ Tech fields are the only changes we have made. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-01 | 2026-08-28
Business w/ Tech Initiative: iSell to JOIN Onboarding Platform connection | 97999 | 8242 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Ulco Keegstra, Kateryna Lazarenko, Linda Bremmers, Teun Rovers | On Track | In assesment to combine with ARMOR initiative | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Improve FedEx One Rate discoverability and grow re | 97195 | 8243 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Mels Wolf, Mariana Whitaker | On Track | Waiting alignment with new rate strategy direction | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Notification Intelligence (MVP) | 40640 | 8302 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Joe Pascal | On Track | 2025-12-17: The work has been completed and launched since late summer / early fall of CY24. Cancelling due to changes in tracking. 2024-10-10: Waiting on approved FY24 baselines from finance to submit to L3 2024-08-14: Attended TCH priority overflow session on Aug 13; revising business case to get into L2; received confirmation from Sales on final Apple volume for NPI event (118 tons) - this effort is tied to iSell Case O-14125909; NRB has been updated to reflect Op margin / profit | E: L2 | Cancelled | L2 Feedback Requested | 2024-04-22 | 2024-09-27
Business w/ Tech Initiative: RPI Digital Experience Improvement - MAGIC / Notif | 43266 | 8303 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng | On Track | Business case updated with ww scope and resumit for L3 | K: L5 | Active | L5 | 2024-01-01 | 2025-02-28
Business Only Initiative: Migrate existing JO use cases due to rationalizing | 94511 | 8310 | Business Only Initiative | Commercial - Digital | Commercial | Ellen Oude Lashof | On Track | This was moved to 106340 | G: L3 | Cancelled | L3 | 2024-12-02 | 2025-05-30
Business w/ Tech Initiative: FXIA: Improve the self-serve integration experienc | 89734 | 8341 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Keith Kline | Some Issues | Placing on hold while we further evaluate existing GDX and CT integration tools and look for opportunities to consolidate redundant offerings. This includes metrics used to measure the value resulting from these requested capabilities and customer experience improvements. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Digital-Enablers-Analytics | 93415 | 8420 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Vincent Arzoni, Roger Reeuwijk | Attention Needed | 15 Oct: Still pending architecture review. we were for a short while priority 49, now bac to 67. Still waiting for architecture assignment 21 Aug: Blocker meeting, Stephanie cannon Assigned Jason Shaw for architect review. Architecture resource association is taking a long time (pending since 4/22) Architecture review: ranked 213 in the enterprise priority list of D&AI SAD (teams are able to assign resources only to the top 50, high priority initiatives currently) 13 March: Talked with Domain Finance, they are aligned that this Enabler has no value | E: L2 | Active | L2
Business Only Initiative: FedEx Technology Marketplace Expansion - FaS updts |  | 89429 | Business Only Initiative | Commercial - Digital | Commercial | Taylor McPherson | On Track | Per Karen Kind regarding this and another init - "i had a conversation with Alan yesterday. I think our consensus is that if the tasks have been in for over a year and haven't moved forward we think its best to end and then move forward again. So much of the project seems to be in flux - not just from project changes but also from system changes and audit changes. that likely there are at least one or two key things that have changed from the prior year." | C: L1 | Cancelled | L1
Business Only Initiative: FTIP-FXR Connected Experience |  | 89433 | Business Only Initiative | Commercial - Digital | Commercial | Taylor McPherson | On Track | Per Karen Kind regarding this and another init - "i had a conversation with Alan yesterday. I think our consensus is that if the tasks have been in for over a year and haven't moved forward we think its best to end and then move forward again. So much of the project seems to be in flux - not just from project changes but also from system changes and audit changes. that likely there are at least one or two key things that have changed from the prior year." | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Hope Enablement- Part 2 (Additional Payment Method |  | 89754 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Steven Naple | On Track | Please cancel request. Work will be completed via new inititives. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: FedEx Integrator Global Launch & Commercialization |  | 89853 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Chandler McCay, William W. Brown Jr | On Track | Created and executed a local enhancement initiative for this request. This one is no longer needed. Please cancel. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Shopify Engagement |  | 90231 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Russell Heady, Wiley Oscar, Rajwinder Virdee, Benjamin Donsbach | On Track | 01-DEC-2025: Our team continues to make progress with furthering the Shopify initative with global expansion. We are pending Shopify's collaboration, which is expected to start up again in January. In the meantime, the team are making improvements to the implementation and internal needs like boilerplate migration and metric reporting. 18-SEP-2025: Money step was moved to a further date due to Brie Carere's direction of expanding the integration with Shopify in Europe. 4/29/2025: Gained OpCo Finance approval on Inernational Express projections. Submitted numbers for revenue and cost into Planview Financials section. 4/16/2025: Updating financials with International revenue projections. All technical development work is done, so there is no additional cost associated with adding International as a product offering within Shopify Shipping. Making progress within L1 - LBC | G: L3 | Active | L3 Feedback Requested | 2024-07-22 | 2026-08-31
Business w/ Tech Initiative: FD – Addressing Missed/Late Pickup |  | 91229 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Tina Foltmer, Doug Mahan, Sanjoy Dutta | On Track | Dependent on Pick Up PFS VB2 which won't be launching for a year or more | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FD – Billing Dispute Resolution |  | 91236 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Doug Mahan, Sanjoy Dutta | On Track | Current focus is on Tracking and Pickup related Support initiatives and resources are not available. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FD – Damaged Claim Resolution/Reshipment |  | 91239 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Doug Mahan, Sanjoy Dutta | On Track | Current focus is on Tracking and Pickup related Support initiatives and resources are not available. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: [VIS] Driver Name & Photo - Phase 2 |  | 91393 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nandini Shenoy, Erin Wichtoski, Komal Kapoor | On Track | Project no longer to be worked on. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-07-22 | 2026-07-06
Business w/ Tech Initiative: HoPE Enablement- Part 1 | 15134 | 9190 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Steven Naple, Michael Schween | On Track | Work will be entered in a new initiative. | E: L2 | Cancelled | L2 | 2024-07-22 | 2025-10-15
Business w/ Tech Initiative: [VIS] Integrated Track Data MVP | 15380 | 9220 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nannette Branigan, Grace Stafford, Sri Kandikonda, Bharghava Sarabu, Haritha Pendli | On Track | 2/12/26 - Updated actuals for January - all is good. 1/6/26 - It is working! We onboarded and received revenue from a major 3rd party - Narvar! 12/22/25 - No issues. Reported a great revenue gain as we billed Narvar (a third party software company) for this first time. We will continue reporting actuals as needed. 12/16/25 - Now in L4 - DO need to make another update in the weekly section as this has been closed by CPEL 12/8/25 - Same status - just need Brie's sign off to be in L4 12/3/25 - SL4 approved all the way to Brie Carere. Just need one more approval to be in L4 11/24/25 - Meeting wtih TO 1inance leads and Digital finance leads to verify L4 readiness. 1/17/25 - Added in expense cost related to profees. Pending Matt Hicks approval for L4. 11/3/25 - Submitting to L4. Money step evidence has been attached 10/22/25 - Moving to the money step. Woring with Finance on capturing actuals. 9/18/25 - decision was made that the CA product code will be tied to 103334. The money step load will Next week. 9/16/25 -Meeting with Finance today to discuss original NRB included US and CA. These financials were approved originally in L3. However the lack of a product code for CA has prevented rollout to that region. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-01 | 2026-12-18
Business w/ Tech Initiative: FedEx account creation via 3rd party digital chann | 15383 | 9222 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kalpan Dalal, Arvind Reddy | Some Issues | 09-25-2025- Op Margins for US/CA approved by the US finance. Operating maring for US SAM segment has been updated to -0.77% (Source Ben and David from Finance) 09-16-2024 In assessment phase. Workshop session on 9/17 and then decision will be made to move to the next phase 08-01-2024 -Still in assessment phase. The revenue projected for FY'25 will be delayed to sometime in FY'26. No ETA on that yet. The money step amount in FY'26 will also be different based on when the CSPs can implement the feature. Will update when there is more visibility into the details In assessment phase. Currently the direction for solutioning is that FedEx will be performing the credit card validation for accounts created on Compatible platform. The revenue projections needs to be revised with the baseline year as FY 25 TCH review completed this morning .Waiting on the next steps Waiting on next steps and further progress on this CPEL complete. Tentative timelines for analysis and implementation provided L2 approved Getting ready to submit to L2 Final draft of business case is ready. Will submit for L2 approval end of Oct Working towards L2 submission L2 submission delayed to second week of September. Still waiting on AMEA details on baseline value L2 submission tentatively for first week of September. Waiting on details for the revenue projections from all the regions and alliance partners L2 submission delayed to get the revenue details from alliance partners. Updated the impacts with the assumptions that the operating margins are 25% Extended to April 30th per directive from Mark. Submitted again for approval Initiative was delayed pending alignment with SAM enablement POD. Now in L1, with unknown timeline for L2, as we are still verifying the key inputs for the size of the opportunity and business case. Will strive for March 31st. The key inputs are not readily available due to multiple business leadership changes this month, the input gap is material: not only is the solution design impacted by the inclusion of correct SAM Alliances - AMEX opportunity, it could generate at least 50% the total business opportunity for this initiative. | G: L3 | Active | L3 Feedback Requested
Business w/ Tech Initiative: MAGIC: Modernize online shipping experience | 15386 | 9224 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Marc Tollens, Nathalia Valencia Jordan | On Track | The new Initiative Owner is Nathalia Valencia Jordan. As of June 1, 2023 Nannette Branigan will no longer represent MAGIC. Initiative has been submitted for L3 approval and waiting for approval to move forward. | I: L4 | Active | L4 Feedback Requested
Business w/ Tech Initiative: CIAM: Modernize online authentication & security | 15388 | 9226 | Business w/ Tech Initiative | Commercial - Digital | Commercial | James Sherman, Isha Bhushan, Renee Couch, Jerry Smiddy | On Track | Device Management Released in January 2025. Capability removed to address defects identified in Production. Impacts have been updated to reflect current proposed FY25 Budgets. Proposed FY25 budgets will remain at FY24 levels (vs. an +10% increase originally). 2024-08-08 - 2FA Features are prioritized in PI04 to be completed to enable email validation process to be released in late October. 2024-14-08 - Loading 2SV email verification flows into production for phased market launch tonight 8/14. 2024-27-08 -We are targeting to release 3 features on 8/29. Teams are currently doing the regression testing. The features are: * Device Management * Expanding min password from 8 to 12 (WPRO) * Active Email Validation to turn on 2SV (Two -Step Verification) - Phase 1 (LAC countries with email as a default option) 2024-06-09 Successfully release on 8/29 * Device Management * Expanding min password from 8 to 12 (WPRO) * Active Email Validation to turn on 2SV (Two -Step Verification) - Phase 1 (LAC countries with email as a default option) 2024-12-09 Successfully released Email Validation to turn on 2SV (Two -Step Verification) - Phase 2 AMEA countries with email as a default option) 2024 - 19-09 - No Update 2024-26-09 -- No Update 2024 -4-10 Preparing to launch Email Validation in EU countries. 2024-10-10 Preparing to enable Active Email Verification with 2SV is now in EU countries on Oct 17th which only has email as a default option. Testing in progress to enable Active Email/Call/SMS verification with 2SV in US on Oct 17th. (Dependency on defect # 613404) 2024-12-11 No Update 2014-19-11 WIP for Passkey Implemantion. No Other Update. 2014- 26-11 We have received confirmation from Mike that all DRIVE AUTHENTICATION work is on containment effective immediately. We will revisit this work if it becomes a requirement for FDX under Project Sirius. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-08-02 | 2025-07-21
Business w/ Tech Initiative: CIAM: Modernize online customer profile experienc | 15398 | 9232 | Business w/ Tech Initiative | Commercial - Digital | Commercial | James Sherman, Rob Smit, Ulco Keegstra | On Track | FY25 Budget Updated to reflect current plans. Monthly budgets to remain at FY24 levels (vs. +10% YOY) and budgets extended to include the months of February-May 2025. Money Step pushed out into FY25 Q4 due to dependencies with HoPE Value Bundle 1. 2024-05-23 - Delivery Manager usability testing continues. Due to alignment with other partners, we have adjusted the Market Release date to the weekend of June 1&2. 2024-08-08 - Features added to Development cycle to address gap identified during testing are prioritized to be delivered in PI04. Testing and Market Release are planned for October. 2024-14-08 - On track...no update 2024-14-15 - On track...no update 2024-14-22 - On track...no update 2024-2-10- WPDM on track for 10/5 customer face release 2024- 9- 10- WPDM released customer facing on 10/5 2024- 15-10- no update 2024- 22-10- no update 2024-29-10- no update 2024-5-11- no update 2024-12-11 no update 2024-19-11- WPAP on stop list so no update 2024- 2-12 WPAP work will continue for PI01. 2024-9-12 no update 2024-16-12 WPAP work planned for PI01- PI planning taking place this week 2024-24-12- WPAP work in progress for PI01 2024-31-12- WPAP work in progress for PI01 2025-8-1- WPAP work in progress for PI01- no update 2025-14- 1 Potential API work identified. Meeting on 1.16 to get more information on impact 1.27.25 API dependency identified- in research phase of impact, reviewing HoPE end to end flows this week, no changes to timeline at this time 2.4.25 API dependency identified for invoice billing address and HoPE URL consumption- in research phase of impact- no update yet. no changes to timeline at this time 2.11.25 API dependency identified for invoice billing address and HoPE URL consumption- confirmed plan for url consumption- no changes to timeline at this time 2.18.25 on track for UAT in March 2025 2.25.25 on track for UAT in March 2025 3.4.25 on track for UAT in March 2025. On track for customer release May 2025. 3.11.25 HoPE link is in L3 and testing is in process. on track for UAT in March 2025. On track for customer release May 2025. 3.18.25 Releasing to L6 and Production- non customer facing on 3/30. UAT will start 3/31 with a planned release to customers on 5/18. 3.26.25 RISK- HoPEs Smartling's automated translation system had an issue and didn't pull translations in time so HoPE release will not take place on 3/30 as planned. WPAP will continue to release on 3/30 with the Manage Payment component flag off and will enable flag when HoPE is ready. This effects full end to end UAT testing. 4.2.25 Internal production release on 3.31 of WPAP. There were URL issues that prevented from us starting UAT. Teams are working on a resolution so UAT is delayed. 4. 22.25 UAT has started in production and logging findings in Centercode. on track 4.29.25 Issue identified in UAT with accounts showing properly. Working with APIF team to resolve. 5.2.25 On track to be delivered this month. 5.7.25 We are still in alpha-production testing and are targeting full launch in Production on 5/17 5.13.25 We are still in alpha-production testing and are not targeting full production release in first week of June. 6.2.2025 - WPAP loaded into Production for US customers on 5.31.2025. Next market is LAC with goal of 6.5.2025. Other regions are still testing. 9.30.2025 - Waiting on CE reports that are needed to update actuals. 9.30.2025 - Received CE report and updated financial actuals for June - Sept 2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-07-18 | 2025-05-02
Business w/ Tech Initiative: Modernize Online Administration Experience | 15500 | 9236 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jerry Smiddy, Renee Couch | On Track | 12/17/2024: No new updates. 12/10/2024: No new updates. 12/3/2024: No new updates. We may place project on hold, or cancel, pending FDX requests. 11/26/2024: No new updates. 11/19/2024: Meeting with Mike this THUR for his approval to submit to L3 due to recent FDX requests that may need our resources. 11/12/2024: Sent greenlight requests. 11/4/2024: Still waiting for Commercial Triage meeting to determine if we need to go through CPEL/PRT process. Date TBD 10/29/2024: Waiting for Commercial Triage meeting to determine if we need to go through CPEL/PRT process. Date TBD 10/8/2024: Moved L3 Submission date to 10/31/2024 due to CPEL/PRT submission need. 9/24/2024: Updating annualized totals and business case to resubmit for L3 9/10/2024: Team is wrapping up socialization deck and strategy review with Mike this week. No other updates. 9/4/2024: No new updates 8/28/2024: No new updates. 8/21/2024: No new updates. Team still working on socializing with key stakeholders. 8/13/2024: No updates. 8/7/2024: Team is still researching sequencing of resources to align with other CIAM projects in WAVE. Once remedied, this will alter our timeline and milestone dates. Should have research findings complete by end of August. | E: L2 | On Hold | L2 | 2023-08-01 | 2026-10-19
Business w/ Tech Initiative: Modernize Online Claims Experience | 15525 | 9238 | Business w/ Tech Initiative | Commercial - Digital | Commercial | LD Taylor, Sanjoy Dutta | On Track | 01/07 - Team is currently at 50% throttle for modernized eClaims in CA. We are looking to throttle up to 100% on 01/13. Once we are at 100% throttle we will commence with legacy retirment activities. 09/26 - 15525 - Code for MVP is being loaded in to production in a turned off state. The turn on for customers is dependent on green light from Claims CE IT from their confidence in a stable state post CoLo Migration. Finical impact plan will be updated through at least Nov. with expectation that more funding is needed to extend further. No update still trending toward release of MVP Sep 22. 11/14 Currently performing UAT activities, approval granted to load to production on 11/22 and go/no-go will take place next week 01/29 - Application has been moved to production and currently being throttled to 20% of claims users up from 10% two weeks ago. 02/07/2025 - Working with finance to review cost change to move out the Money Step. 02/13/2025- Still working with Finance Domain lead on next steps needed to shift the money step and any updates to the financials needed 02/26/2025 - On 2/22/2025 The team succesfully loaded Single Claim Enhancements, Help Section and Claim Center Enhancemnts. The team is trending on track for the next release to include Batch Claims mid March. This will give us feature parity with legacy eClaims and achieve the Money Step. | I: L4 | Active | L4 | 2023-03-14 | 2025-12-31
Business w/ Tech Initiative: DIBE: Modernize online billing experience | 15526 | 9239 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jake Brannon, Joshua Hamblin, Sanjoy Dutta | On Track | **2/10/2024 - 2/14/2024** - Project is in L4 and is currently monitoring monthly metrics. - Project is an enabler project with no direct financial benefits. So KPIs being monitored are Ease of Use scores and Customer satisfaction ratings from DOTS - Project began monitoring metrics in June 2024 but these numbers do not reflect a true picture as users were not fully migrated to new application until end of August 2024. - September 2024 is the first true measure. - There are now 5 months of monitoring so now to determine whether project is ready to progress to L5. **12/2/2024 - 12/6/2024** - Project is in L4 and is currently monitoring monthly metrics. - Project is an enabler project with no direct financial benefits. So KPIs being monitored are Ease of Use scores and Customer satisfaction ratings from DOTS - Project began monitoring metrics in June 2024 but these numbers do not reflect a true picture as users were not fully migrated to new application until end of August 2024. - September 2024 is the first true measure. - There are now 3 months of monitoring so now to determine whether project is ready to progress to L5. **11/4/2024 - 11/8/2024** - Project is in L4 and is currently monitoring monthly metrics. - Project is an enabler project with no direct financial benefits. So KPIs being monitored are Ease of Use scores and Customer satisfaction ratings from DOTS - Project began monitoring metrics in June 2024 but these numbers do not reflect a true picture as users were not fully migrated to new application until end of August 2024. - September 2024 is the first true measure. **Last update prior to Planview migration in October '24:** STATUS: - All planned code complete with APR '24 CSR - All customers are default landing into the new application. REMAINING STEPS: - NOTE: Retirement of the legacy application is not in-scope for the DIBE project. This item is listed for awareness only. - Remove the link that allows users to return to legacy and fully retire the legacy application. Original cost forecast explanation: - The projected cost of $3.37M was based on the cost calculator. This amount was spread evenly across the projects forecasted timeline which was scheduled to end with the April '24 CSR. After the April CSR was finished. There was additional work identified via missed requirements that required a contract extension within the IT team stood up to support the development of the new application. This request for extension was reviewed and approved with leadership. So the actual costs extend beyond the original forecast timeframe. Even with the extension, the total actuals are at $2.92M which is below the $3.37M that was originally forecast. | K: L5 | Completed | L5 | 2023-07-28 | 2024-08-30
Business w/ Tech Initiative: Introducing the Pay as you Ship (PAYS) cust. type | 15601 | 9245 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Ulco Keegstra, Filippos Koulyras | On Track | JAN-23: ON HOLD due to the fdx platform/strategy and the unclear strategy for IND customers. Once there is more clearity we can assess if this ask is still relevant or not. OCT-1: Transformed #15601 to reflect the discussed new initiative split (4 DRIVE initiatives to cover the old #15601) | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2023-04-03 | 2026-04-01
Business w/ Tech Initiative: Onboard RegCXS to CVM |  | 92646 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kateryna Lazarenko, Ulco Keegstra | On Track | Onboarding product team puts this item on hold to invest time in items with more priority | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: WS8 - T4 – Online case creation (link with GS) | 82229 | 9279 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Doug Mahan, LD Taylor, Minna Arminen | Some Issues | 2/6/2026 - Cancelling as per direction of Bethany Veach and on the criteria listed below: Approved ________________________________________ From: Taylor McPherson <taylor.mcpherson@fedex.com> Sent: Thursday, February 5, 2026 11:23 AM To: Bethany Veach <bethany.veach@fedex.com> Cc: Doug Mahan <jdmahan@fedex.com>; Amber Phillips <amber.phillips@fedex.com>; Grace Ann Aldridge (OSV) <grace.aldridge.osv@fedex.com> Subject: PV #9279 Cancellation Approval Request Bethany, I’d like your approval to cancel init 9279 WS8 - T4 – Online case creation (link with GS). •Digital-owned init in L4 that originated with EU-NPS and has since bounced back and forth between CX and Digital. Currently, the Primary IO is Doug Mahan from Customer Experience. He supports cancellation. •Original scope included EU, who then decided to utilize Digital Support Manager instead of Support Ticket. •The remaining work (US and CA) launched last fall. •Value appears to be NPS-based and is quantified in a master (apparently P&C) init that we can’t see. Forecasted costs were less than $6K a month (for SMS) and the actual costs were likely, at most, $100 a month. If you approve, I will pass that on to Karen M and DJ for approval and then we can cancel the init rather than spend time trying to get it to L5 just for the sake of it. 2/4/2026 - Placing on Hold while we determine actual SMS costs. 1/26/2026 - Initiative ownership changed. Dispute Delivery for US started on 10/24/2025 after issues noted below were addressed. EU does not plan to adopt Support Ticket for now and has moved to the Digital Support Manager option. That is currently operating in 2 EU countries with more countries coming online for the remainder of FY25. 09/18/2025 - Team is working on resolving testing issues with the last feature release which was scheldued to be completed at the end of this PI (10/07) as issues have been ideentified we expect a delay with a new release date in the following month. 07/18/2025 - Team has submitted CAB request and been approved to Lauch OCCM expereince for delayed shipment case creation. The MTP is scheldued for 07/22/2025 06/09/25 - Team working to identify new Money Step Date by 06/13/2025 25th March - Initiative transfered to LD Taylor & moving out of the NPS POD 5th of March - EU removed out of scope for the MVP 18th Feburary - scope for the MVP has been limited to the UK and US. BE & NL moved to the next release (date TBD). Team continues to work through issues (Visbility & OCM). Date for the UAT of the complete functionality TBD once current defects fixed. 11th February - Intergation testing kick off & assessing the opportunity to launch MVP earlier for US & UK 3rd February - MVP postponed to 22nd March to allow time for resolution of identified defects 29th January - Defect resolution on-going, MVP postponed w. new date TBD pending defects resolution 21st January - UAT on-going, MVP release scheduled for 22nd of Feb 16th January - project on track. Visibility ART, Guest Authentification flow, Get Support ticket development completed, UAT on-going, identified defects being resolved. 20th November - Project on track. Approval of the budget for guest authentification received. 24th Oct - Project on track with MVP planned for Jan'25: MVP scope confirmed, development work on-going; architecture developed for the Shipment/Case Eligibility rule to satisfy MVP and scalability. | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-10-01 | 2025-10-30
Business w/ Tech Initiative: Shipping-Dynamic Pickup |  | 92856 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Obbe Bangma, Wiley Oscar | Some Issues | 6-16-25 - pushed back to L2 for completion prior to resubmitting to Portfolio Greenlight (see 6-16-25 email) 5-13-25 - submitted to Data & AI Portfolio Greenlight Jan 30, 2025: * Product Strategy Roadmap WIP- review with FEC leadership week of Feb 10th * Commercialization strategy draft built and waiting for a resource allocation, follow up planned for Feb 3rh week * Next steps and scaling plan in discussion week of feb 10 Feb 19, 2025 *discussed on the Beta and pilot launch for customers * Demo sessions getting lined up * Finance discusssions are on * clarify on DPU and RFID is being hashed out March 18 2025 * approval to mvoe from commercial healthcare to comemrcial digital approved * Waititng for the update to activate and work with the new POD lead * March 21, 2025 * There is no edit button to update content. * TO open a ticket the link is not working May 12, 2025 * Got the IMAGE access for PPM approved * Clarity on PPM is needed * sync up with Enginenring for architectural desing is on the wait for this week July 30, 2025 * ADS figmas -WIP * Sizing to be defined after the figmas. * Clarity on Funding approval (VDC or not) to be clarified * *GTM process kickstarted- Onboarding, Implementation and custoemr support to be set up * August 8, 2025 * Sizing step on hold, clarity needed on greenlight process, protocol and ownership for approval [ engineering or Product] * Key architect approval to be confirmed * Sept 18, 2025 * Impacted portflolios now need to give a green light with no clarity on how to go about- ciritcal step to move forward * October 02, 2025 * Only D&AI is impacted. Gaurav will be back on Monday. He will take this to VDC. Rest o the portfolios are not impacted. the evaluation is old and the conclusion at only Data&AI is impacted *October 15, 2025 * PI planning for the next build scooped out* * Nov 11, 2025 * Current IO will be transitioning out of DPU and will be given to Shipping team under ( Kim van der Velden),. the new IO will be identified by Kim if the initiative will be continued | E: L2 | Active | L2 Feedback Requested | 2025-06-02 | 2026-02-02
Business w/ Tech Initiative: Address validation override in customer onboarding |  | 93588 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kateryna Lazarenko, Teun Rovers, Ulco Keegstra, Lauryan Feijen | On Track | 12-JAN: · Item will not proceed; team has decided to cancel and remove it from the work plan. Reason: solution was technical debt, required changes in CAM to adopt Global Address Services; timeline and investment not justified since CAM will eventually move anyway. 21 OCT Green lighted by PPEL 25 sept Pending architectural review Pending financial review with David Johansson for 3d week | E: L2 | On Hold | TEMP L2 - Enter Portfolio Greenlight
Business w/ Tech Initiative: Unified Platform - Customer Onboarding & Growth |  | 93592 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Linda Bremmers, Ulco Keegstra, Kateryna Lazarenko, Lauryan Feijen, Amanda Engel | On Track | 19-Mar - putting init on-hold. Breaking up the init into smaller requests and/or OTC will take over the scope 3 Nov - further refinement of initial work and updating plans in progress 14 Oct - moving customer to fdx is off the table, hence part of this init needs to be updated (incl. the business case). 29 Sept - had first scoping session with John Wesley and others, need for another session 16 Sept - trying to get a meeting planned with John Wesley and others. 8 Sept - had a triage meeting with Swetha on Sept 5th, requires further architectual session with John Wesley and others 27 Aug - planned architectural review 1 July - getting ready to enter L2 16 Jun - architecture review received and ready for L2 3 June - waiting for architecture review | E: L2 | On Hold | L2
Business w/ Tech Initiative: DFD -Pick Up Quick Wins: Pre-Paid/Returns & Missed |  | 93957 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Tina Foltmer, Doug Mahan, Sanjoy Dutta, Jeff S. McIntosh | On Track | Work is being tranisioned into the CE Reinvention initiative (#152953). Once completed, this initiative will be deleted. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: E-Commerce Rating Response Improvement |  | 93961 | Business w/ Tech Initiative | Commercial - Digital | Commercial | John T. Walker, Forrest Hughes | On Track | 2/18 - Stakeholder meeting to cover details before proceeding to next stage 2/26 - Working on financial details. Have had conversations with Ben Sauls and David Johanssen on financial expectations for L1 to L2. Contacted similar initiative to gauge methodology and framework but concluded their methodology would not be a fit for this initiative. Working with API Digital Product team to gain additional details to help frame financial conversation while pursuing additional alignment with stakeholders on the scope and path forward. 3/3 - Met with Kristian Conway to discuss DRIVE messaging alignment, proper value driver, and associated financial methodology. 3/4 - Pursued answers to what proper value driver would be and best financial methodology with David Walker & April White. 3/18 - David Walker assisted with T-Shirt size assignment for L1 Commercial Triage/EA Architectural review. Still need to answer type of value, request type, and forecast finances. 3/26 - Based on stakeholder feedback, value changed to Customer Experience. This is to reflect the degradation of customer experience occuring by having an API that does not consistently avoid rating timeouts. Pursuing financial forecast data. 4/9 - Gathering data that could impact financials before I loop Ben and David in for further analysis. The recent organizational shifts have also thrown a bit of a wrench in here. 4/29 - Working to set aside a time with EasyPost to get better context on rating timeout frequency and value in order to inform financials. 5/5 - Reviewed with product teams planning rating containerization solutions that seek to tackle the customer problems experienced in this DRIVE use case. 5/20 - Reviewed with finance (David Johansson) and product (Mark Depperschmidt) and requesting final review from David, Mark, and April White/Taylor McPherson before submitting to SL2. 6/6 - Have gone through some revisions with Finance and re-submitting for SL2. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-01 | 2026-04-30
Business w/ Tech Initiative: FedEx Sustainability Insights (FSI) |  | 93964 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kathryn Richey, Coresa N. Hogan | Some Issues |  | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Visibility-Core |  | 94149 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nupur Gupta, Peter Sola | On Track | 12-24-2025: Costs actuals had been updated with forecast value. Confirmed actuals will be updated as soon as the team has the values for the IT groups. 12/22/25: This initiative change from developing hte capabilities on fdx to developing them on FedEx.com. Although some of the work had been completed in fdx, now that work has to be moved to fdx and the remaining work for the initiative has to be completed. We expect the new time of completing for July 2026. In addition there might be some extra work on fedex.com to distinguish currenct business from consumer customers so we can present the correct experience, the team is discussing options as this also might be a platform needed capability. We are in the process to complete requirements and definition for PI 1 in January. 12-17-2025: The Direction of the visibility business product has been decided, the work that was done in fdx will tranfer to fedex.com and we will complete the remaining features desired for core experience with the new architecture in fedex.com. Details on the changes needed will be attached to this initiative when ready. For now the team is working on define the worked needed, we do not expect major changes in teams impacted or scope of work. 10-23-25: Initiative is on hold due to decision by leadership to stop fdx visibility work. Next steps will be determined within the next few weeks. 9/25/25: Added milestones for Pi5. Moved money step for next year. Some of the epics have dependency of new architecture and cannot be developed by orignal timeline. Further updates will be provided as team assess the work and solve the dependencies. 6/13/25 Team is working remaining features for delivery, identifying some impacted groups and alignment on delivery timelines. 6/5/23 Met with David Jonhanson to go over details of financial spreadsheet. The standard spreadsheet has been uploaded and two supporting emails regarding portfolio costs have been uploaded. David will review before resubmitting to Mark by tomorrow EOB. 5-6-2025:Depednecy on SCO has been removed. Last approvals to submit to L3 are in progress 3/17/25: Project is at risk due to 1- alignment with SCO needed to be able to submit to approval of portfolio ans secured SCO resources , 2-Dependencies on architectural infrastructures has delayed Pi1 features delivery. This will put Pi2 features at risk. 3- This will negatively impact the start of migration in June 2025. Delays 3/12/25: We completed CPEL and VDC on 3/12. We submited the epics impacts commercial and data and ai portfolios. However we are still waiting for SCO epic details to add that epic and being able to submit to next step for portfolio greenlight. Costs for implementation for commercial and data and ai are also added. Review with finance pre submission to L3 will be completed in the next days, This initiatve is already in the development pipeline due to the leadership urgency for migrating customers. Need to submit to L2 ASAP | G: L3 | Active | TEMP L3 - Enter L3 | 2024-11-04 | 2026-07-31
Business w/ Tech Initiative: Sirius-Shipping-Core |  | 94166 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Obbe Bangma, Leanne Logan, Miguel Baumann, Kateryna Lazarenko | On Track | 12-2-25: Asked by Amber to put init on hold after discussion with Mark and Ulco. 6-20-25 - Both Commercial (Jenny Mooring) and Data and AI (Jacob Kellogg) confirmed that I update forecast with actuals until this is included in Data and AI dashboard and Commercial determines data sources and can provide actuals 6-16-25 - Awaiting first actuals to be available to update Commercial and Data & AI forecasts. (Already on the late actuals list.) PMO working with Product for new remastering value bundles/epics. Agility and Epics are aligned and reporting progress today. 6-3-25 - Sirius-Shipping-Core to remaster all of MAGIC (including Sirius-Shipping-Integrated components). Working through how we reflect this in DRIVE initiatives. 5-29-25 - Remastering plan underway. Aligning on DRIVE approach to reflect changes together with #110712 with remaining MAGIC shipping features. 5-19-25 - Remastering Sirius-Shipping-Core plan is underway. EPICs are now drafted. Working to define Ability To statements, and revenue associated per EPIC to redefine in DRIVE. 5-6-25 - With the decision to remaster (aka reskin) shipping on fdx, the product/IT team are reworking the plan for Sirius-Shipping-Core to remaster instead of rebuildingit on fdx per this DRIVE initiative. 5-5-25 - Updated Milestones in advance of Leslie Benner's weekly TO meeting reviewing project status on 5-6-25 (changed milestones from "Not started" to "In Progress" for all those with a past start date and pushed out schedule finish dates that were in the past or in May to June 30, 2025) 4-29-25 - Sirius-Shipping-Core is fully approved for L3! 4-29-25 - Neil Lanasa, SVE Finance, approved to L3 4-29-25 - Matthew Hicks, TO Finance, approved to L3 4-25-25 - DJ Miller, Domain Lead, approved to L3 4-24-25 - Mark Mantaro, Finance Domain Lead, approved to L3 4-18-25 - Eryn Walter, EPM, approved to L3 4-17-25 - Added KPI; Reviewed with Financial team (David Johansson /Ben Sau) in Digital Pod Deep Dive session to confirm KPI in PlanView financials entered correctly. Submitting to L3 again NOW. 4-16-25 - EPM feedback requested KPIs added and assurance that both Portfolio greenlight financials are reflected in PlanView. Confirmed with EPM portfolio greenlight financials are included and okay. 4-15-25 - PDSM tickets have now been implemented to update DRIVE with Data and AI to "Can Support" and update the Money Step to new FY25 baseline. Modified early milestones to follow May kickoff with resources. Submitting NOW to L3 for final approvals. 4-11-25 - Waiting on two PDSM tickets to implement changes before submitting to L3: - Data and AI Portfolio greenlight (Valerie submitted 4-10-25 to change to "Can Support") - Money step update (Leanne submitted 4-10-25, to update the money step finances to the FY25 rebaseline figures, as updated throughout PlanView business case and EPICs) 4-8-25 - Received VDC approval for Data and AI for JLabs data resource request from 3.12.25. Updating DRIVE with support costs for final greenlight and approvals from Data and AI as well as Finance to move to L3. 3-31-25 - Still awaiting Portfolio Greenlight for Data & AI. IT working with IT contractors to finalize needs for VDC review. 3-31-25 - Submitted PDSM ticket #INC030081395 to update PlanView with updated financial FY25 baseline by March 31 as requested. Also requested change to new PPM #842889 to track progress of this initiative. 3-28-25 - Engaged Finance (Ben) to help identify financial updates to rebaseline from FY24 to FY25 with the recommendation to change Baseline and Target values to 0. NRB remains the same. 3-18-25 - PlanView is updated with both Commercial and Data & AI portfolio financials awaiting greenlight from VDC / Dataworks. 3-18-25 - Porffolio Greenlight step: Confirmed with Valerie Patterson that VDC greenlight is still pending VDC ongoing review. 3-11-25 - Portfolio Greenlight step: For Data & AI (Dataworks), on hold awaiting final VDC greenlight. Details | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-01-20 | 2027-02-01
Business w/ Tech Initiative: Sirius-Onboard&Upsell-Re-platforming journey |  | 96317 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kateryna Lazarenko, Ulco Keegstra, Isha Bhushan, Kim van der Velden, Lauryan Feijen | On Track | 21-OCT Due to the strategic pivot announced by Jason Brenner and Anthony Norris, this initiative will be cancelled | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-04-01 | 2026-05-04
Business w/ Tech Initiative: CX- Predictive Delivery Estimates PDE |  | 97174 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Ajay Srinivasan Ravi, John W. Bishop, Riccardo Sbabo | Some Issues | 8/21- Arch. assessment underway. Resourcing for new features is yet to be secured. 8/12 ADS completed. Sizing estimates are ready while delivery teams are working on architecture diagrams. DW SAD team has separately requested another round of envisioning sessions that may span a few weeks. Support needed to expedite/proceed to next step. 8/5 LBC is being updated to get ready for SL3. ADS is scheduled for 8/5. Note- PDE is a product used in production by paying customers. To meet DRIVE requirements of being in L3, we currently do not have product enhancement or implementation support leading to unmet customer feedback and needs. | E: L2 | Active | L2
Business w/ Tech Initiative: FedEx SameDay Local |  | 97178 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Somer Butler, Robert Brooks, Wiley Oscar, William C. Dando (Bill), John W. Bishop | On Track | Money Step entered, epics entered with all requested information, PPM number recieved and added. Waiting for Commercial domain to update on next steps. | E: L2 | Active | L2 & CCH | 2026-01-30 | 2026-05-29
Business w/ Tech Initiative: China UEL/ MFA Shipping Control |  | 97381 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Yu-Lin Kiany Zhang, Taylor McPherson, Cathy Tee | On Track | 1/20/25: Init is in L5 and Lifecycle Status is "Completed". 12/3/25:Added money step evidence and resubmitted to SL4. 11/6/25: Moved money step date out after conversation with Cathy Tee Nov.21, 2025 by Kiany Zhang 1. Lean Business Case has been revised with the operating margin % from APAC Finance. 2. Development work is done and now full launch in CN. 3.Completed Architectural Review with Enterprise Architect and Finacial review with Financial rep. | K: L5 | Completed | L5 | 2024-07-22 | 2025-11-28
Business w/ Tech Initiative: Sirius-Visibility-Premium |  | 97795 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Nupur Gupta, Peter Sola | On Track | 9/25/25 Temporarily on hold while team reasses priorities for FY16 2/19/25 Added Nupur as primary owner | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Contract to Collect |  | 97870 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Riccardo Sbabo, Frank Vulpis, Joshua Hamblin, Keerthi Kandadi | On Track | * 4/24/26 The initiative remains in High status. The team has attended CPEL and is currently awaiting confirmation of approval for the requested scope change. Decouple planning and Feature and Story definition is nearing completion, and the team is beginning execution readiness activities. The GDX SCI first draft was handed off to ARTS on 3/20/2026, enabling ARTS to begin Feature and Story development to begin. Final GDX SCI draft was handed off on 4/17/2026. RMIC advanced its SCI contributions, reviewed the draft with the core team on 3/24/26, and completed final handoff to ARTS on 4/9/2026. * 4/17/26 The initiative remains in High status. Near‑term focus on finalizing scope alignment and securing formal signoff. The GDX SCI first draft was handed off to ARTS on 3/20/2026, enabling ARTS to begin Feature and Story development to begin. Final GDX SCI draft was handed off on 4/17/2026. RMIC advanced its SCI contributions, reviewed the draft with the core team on 3/24/26, and completed final handoff to ARTS on 4/9/2026. * 4/10/26 The initiative remains in High status, with near‑term focus on finalizing scope alignment and securing formal signoff. In parallel, the team continues to mature the SCI documentation while defining cross‑cutting capabilities and solution high‑level designs, establishing a strong foundation for solution development and upcoming delivery planning. The GDX SCI first draft was handed off to ARTS on 3/20/26, enabling ARTS to begin Feature and Story development. Final draft will be handed off on 4/17/2026. RMIC has advanced SCI contributions, reviewed the draft with the core team on 3/24/26, and is preparing for final handoff to ARTS. * 3/27/26 - The initiative remains in High status, with near‑term focus on finalizing scope alignment and securing formal signoff. In parallel, the team continues to mature the SCI documentation while defining cross‑cutting capabilities and solution high‑level designs, which together will establish the foundation for solution development and upcoming delivery planning. The GDX SCI first draft was handed off to ARTS on 3/20/26, enabling ARTS to begin Feature and Story development. RMIC has progressed its portion of the SCI and reviewed the draft with the core team on 3/24/26; RMIC is now preparing to complete handoff to ARTS. Next steps include advancing decouple planning, error handling, role‑based security for My Subscriptions, implementation planning, execution timeline definition, FIRST, test planning, and test case development. * 3/5/26 -EPIC 6 has been de-scoped. Part of the contracting automation functionality will be included in PV 7111 -The initiative remains in High status. Updated PRT Architectural flows were delivered on 2/25/2026 and final revisions are underway. -Near‑term priorities focus on aligning scope and securing formal signoff. In parallel, the team is collaborating on the SCI document template and defining cross‑cutting capabilities and solution high‑level designs, which will guide both solution development and delivery planning. * 2/27/26 -PRT team completed updated Assessment, Decomposition, and Architectural Flow artifacts for Epic 1, incorporating refinements from downstream reviews. -Final PRT Architectural Flows delivered on 2/25/2026, marking a key milestone. -Scope alignment and formal signoff are the next immediate priorities. -All PRT artifact reviews and AIV/FDP/Zuora demos are complete, and the team is now advancing work on the SCI Document Template, Cross‑Cutting Capabilities, and Solution High‑Level Designs to support solutioning and delivery planning. * 2/6/26 -Initiative remains High status, with updated Assessment, Decomposition, and Architectural Flow artifacts completed for Epic 1, including refinements from downstream reviews. -Contract to Collect Epic 1 kickoff occurred on January 27, 2026. -Near‑term focus is on finalizing scope alignment and obtaining formal signoff. -The team completed the CPEL Charter and joined | E: L2 | Active | L2 Feedback Requested | 2025-03-26 | 2027-05-31
Business w/ Tech Initiative: APAC Online Latency & Reliability |  | 98404 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Cathy Tee, Kai-Bon Derrick Chan | On Track | Added the supplementary information and resume the L1 process | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Digital-Enablers-Data collection & Analytics tool |  | 98435 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Erik Hagreis, Roger Reeuwijk | Attention Needed | 15 Oct: Still pending architecture review. we were for a short while priority 49, now bac to 67. Still waiting for architecture assignment 21 Aug: Blocker meeting, Stephanie cannon Assigned Jason Shaw for architect review. Architecture resource association is taking a long time (pending since 4/22) Architecture review: ranked 213 in the enterprise priority list of D&AI SAD (teams are able to assign resources only to the top 50, high priority initiatives currently) 13 March: Talked with Domain Finance, they are aligned that this Enabler has no value | E: L2 | Active | L2 Feedback Requested | 2025-10-01 | 2026-09-30
Business w/ Tech Initiative: Migrate Revenue Supplies to Five9 |  | 98458 | Business w/ Tech Initiative | Commercial - Digital | Commercial | JAMES HALE IV, Lauri Bates, Scott Wilson | On Track | in PI03 as local enhancement | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Sirius- Segment/CX - Branded Order Tracking |  | 98708 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Coresa N. Hogan, Leanne Logan, Riccardo Sbabo, John W. Bishop | Some Issues | * 8-12-25 - In L3 and actively monitoring. Awating the decision on resourcing and prioritization to hit our FY26 goals. * 7-21-25 - Approved for L3 * 6-18-25 - VDC is scheduled for today * 6-16-25 -With Data and AI since 6-6 with Rachel Wood. Valerie Patterson engaged last week to support. No VDC scheduled or known reviews yet. * 6-6-25 - Officially moved to Data and AI Portfolio Greenlight to Rachel Wood. * 6-6-25 - Scheduled for courtesy CRD presentation * 6-3-25 - Data and AI began their review. Determined no need to attend Data & AI Triage 6-4 as scheduled. Justin Shaw is reviewing continuing updates in PV for L2 to L3 * 6-4-25 - Submitted PDSM ticket to remove commercial impact #INC030946612 * 6-2-25 - Commercial Triage determined no Commercial impact. A PDSM ticket will be submitted to remove Commercial review. * 5-29-25 - Awaiting L2 Commercial Triage June 2, then Portfolio Greenlights * 5-28-25 - CCH greenlight received * 5-28-25 - Scheduled for courtesy CDR review Friday June 6. * 5-27-25 - Brie Carere (Exec Sponsor) approved to L2 * 5-15-25 - Business case being updated with financial rev forecast. PlanView updates inclusive of financials, ability to statements and other infomation consistent with PlanView requirements underway. Review with GD finance today. * 3/20: Working on fast track to L2 | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-06-16 | 2028-05-31
Business w/ Tech Initiative: Digital Media Commercialization |  | 133494 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Aria Bai, Benjamin Janney | On Track | 02/13/26: Completed QA check feedback items and reviewed with Commercial Domain PMO, Karen McConnico. Received approval to submit for SL3 approval. 02/06/2026: Conducted SL2 and SL3 QA readiness check with Commercial Domain PMO, Karen McConnico. Require L0 and L1 data hygiene clean up. L2 data hygiene is clean. Once PDSM ticket is resolved approved to submit for SL3 EPM review. 01/30/2026: Google portal T&C and general advertising terms review on hold until mid Feb due to legal bandwidth. Awaiting for finalized ROKT contract draft and FedEx DPA. T-Mobile will like to buy advertising once we have more ad units inventory. 01/19/2026: Advertiser restriction in place in GAM. Finalizing ROKT contract work and planning a meeting for both parties’ counsels to meet for liability. T Mobile & ParcelLab lead. Google portal T&C in progress. 01/05/2026: Internal alignment with Legal on Rokt Contract Redliening (2nd round). Started FedEx digital inventory refresh with 2025 numbers. 12/18/2025: In person 2026 Google Roadmap Planning Workshop. CPEL overall ranking #41 with solution ranking #16. Identified necessary legal involvements and set timeline. 12/08/2025 Status: Disucssed Google Ad Manger revenue receiving set up with accounting department, not resolved, pending on Google's payment policy. Met with the new mobile app stakeholder to re-introduce the team and initiative. 11/24/2025 Status: Walgreens marketing team agreed to pilot the complimentary campaign with us for 2-3 months to test & learn. Domain Finance: Added in small estimated web platform hosting fees & incremental headcount associated costs. 11/17/2025 Status: Google contract exeucted. Four content page ad containers pushed to production before peak code freeze with CEM, DUX and Brand alignment. We're in the process of setting up Google Ad Manager portal and reaching out to pilot partner prospects. In additon, we are mapping personalized data pipeline and awaiting for the right data team to come in and help with the project. The project remains on track with strong executive sponsorship that ensure strategic alignment for global digital commercialization. Cross-functional teams including customer experience, marketing, applications, email, Office, analytics, and legal team remain engaged, setting solid foundation for collboration and steady execution in the future. Vendor commercial contracts are in legal review. In addition, current global digital advertising landscape continue to validate the opportunity. | G: L3 | Active | L3 | 2026-03-25 | 2026-10-23
Business w/ Tech Initiative: Tracking Modernization |  | 133498 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Sonam Sharma | On Track | 08/04 - status update | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Tags Enablement Platform |  | 143157 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Cade Seeholzer, Elliott Fodi | On Track | This work is already in progress, the tags team is working through this before a customer adopts tags AND before we start development on any new tags. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Visibility Lifecycle Experience Improvements |  | 143160 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Rupesh Agrawal | On Track | On track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: CIAM PAYMENT SOLUTION APAC |  | 143167 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Janes-Ronald D. Corpuz, Yash Chaturvedi | On Track | Chnage of initiative owner from Lukesh Chhandwani to Yash Chaturvedi as Lukesh has moved into a new role. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FXL Shipment Data Ingestion to Atlas |  | 143185 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Suresh Kotta | On Track | Thi sis no longer needed due to recent dataworks restructuring. Commercial will submit new PV if FXL data ever needed to integrate with FedEx.com. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Unified Platform - Identity, Preference & Org Mgmt |  | 153148 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Lauryan Feijen | On Track | L1 architecture review completed L1 finance case draft ready, aligned on further refinement in L2 | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Free to Fair |  | 153151 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Arvind Reddy, Rajwinder Virdee | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: MAGIC China Data Localization (CDL) removal |  | 153245 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Launa Morris | On Track | The China resurce work was tracked as local demand but the cross portfolio work had to be managed outside of the Drive process due to lack of priortization. The out of band work was needed to meet the required timelines to keep the China busienss functioning. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: COM - Connected Ecosystem Strategy |  | 157742 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Lisa M. Stratton, Angela Howlett, Griffin S. Gillam, CHRISTY TARONI, Hannah Rogers, Murad Akmanligil | Some Issues | *04/17/2026 - - Implementation costs updated - Confirmed epics,milestones and risks are entered - Confirmed architectural documents updated - Christy provides an update on a recent meeting with Anthony and Amy regarding bridge funding, which received their support. -Follow-up meeting with Bree, Vishal, and Jason was scheduled and Murad Akmanligil reported that Bree and Vishal approved moving forward with selecting an implementation partner and creating a statement of work for the entire implementation process rather than just three months - Pending review thisnext week before making any further updates - Christy - Validate Licensing and if any changes to licensing cost and SAM margin - Lisa, Angela, David *04/10/2026 - no new updates *03/20/2026 - No new updates . - Still pending updated ESI and Domain Lead approval to proceed further. - Teams have created project roadmaps, documented Epics, Risk and Assumptions for each workstrem: - Journeys, Analytics, Sites and Assets *03/16/2026 adding our Marketing Partners to this Stratgey as Owners - Christy and Hannah *3/13/2026 - Gathering details for Business case Benefits to date and Expected Benefits for Finance and starting conversations to narrow down how we will measure the growth *03/11/2026 - Updated the Target value field from $134,735,788 to $101,952,940 as requested by David *03/09/2026 - Business case document updated - The DRIVE business case template has been updated: •Soft benefits for Churn figures amounting to $9.8M have been outlined below the DRIVE case for easy tracking on Business Values Roll-up tab •Additionally, the correct figures are listed for NRB ($30.6M) and Soft Benefits line items on the Business Case tab. *03/06/2026 - Financial Review held - updated the Revised Business case financial document - We’ve removed churn as a value driver from the financial model as discussed. *03/02/2026 - Marketing team met with Randy to review the business case, and we are good for submission to L2. *02/27/2026 - During the review with the Directors and VPs yesterday they asked that we verify a couple of the figures before submitting to L2, team is working on this and expect to submit to L2 by mid next week. The team is also working on project plans to start defining Epics and details needed to prepare in advance for L3. *2/20/26 - We’re currently experiencing delays in collecting the information required for our finance updates. We’re in the process of pulling the FY25 ALV figures and expect to have them by next week. Once received, we’ll review and update the business case accordingly. Additionally, our QA check has identified further adjustments needed in the Planview details; a PDSM ticket will be submitted as soon as all finance numbers are available. * 2/12/26 - Delays in L1 based on the factors listed below. Targeting to move to next phase by end of next week. * The initial submission was done quite urgently as prior leadership was in negotiations with Adobe on the overall contract to consolidate several contracts. Accenture initially drafted the LBC based on the overall Adobe contract which was with an assumption that we would get certain products. We ended up with more products than we initially anticipated so that required us to go back through the LBC. * This project is made up of 4 workstreams, each workstream is in a different place in the lifecycle. Sites and Analytics are development ready where Assets and Journeys still have some major decisions and POCs that have to be completed to determine how they will proceed. Given this information, in October and November we were assessing whether or not to separate the workstreams into separate inits in order to enable those ready for development to proceed. Ultimately it was decided by leadership and finance that it would be best to leave it as a single init so that we do not lose site of the overall value assessment and outcomes. At that point we were gi | E: L2 | Active | L2
Business Only Initiative: Increase Bulk Label Accenture Resources |  | 157745 | Business Only Initiative | Commercial - Digital | Commercial | Mark Hodges, Justin Cagney | On Track | Due to FXF conveyance, this initiative no longer aligns with the direction of the program. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: ISO Currency Code Standardization for Automation |  | 159036 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jamie Dean, Tommaso Barbieri | On Track | 2026-03-31: Working with Finance to obtain the financials for the customers highlighted for the KPIs 2026-01-28: Submitted for L2 2026-01-28: Added KPI details to the L1BC, we'll be monitoring the adoption progress of 19 customers accounts and 3 Integrators 2025-12-16: Awaiting finance review of the L1BC in order to progress to SL2 2025-11-11: SL2 QA readiness check 2025-11-05: Awaiting L1BC review before submitting to next step 2025-10-16: L1BC completed, 2025-09-08: Awaiting for Architects to conduct the Architecture Alignment step 2025-08-26: Updated initiative with the required infomation | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: FBO Batch Disputes |  | 163187 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jake Brannon | On Track | Requires enablement work in other external systems that has no plan to be completed at this time. We cannot proceed with this request, so will cancel and re-request when the prerequisite work is completed in other systems. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FBO - DOTS Enhancements for CBS Phase 2 |  | 163191 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jake Brannon | On Track | This work will not be prioritized. A local demand enhancement request will be submitted for other features instead | C: L1 | Cancelled | L1
Business w/ Tech Initiative: fdx Reporting |  | 163194 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Ting Huang, Regina Chen | On Track | Ting and I are no longer working on this project. | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: Bridging the API & Web Service Gap |  | 163197 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Venkatesh Gurupura Pai, Arvind Reddy, Kalpan Dalal, Matt Conlon | On Track | 01.08.2026 - This request will be cancelled as we chose alternative route. 12.30.2025 - Product team is exploring the alternatives. Based on alternatives, we might decide the future of this planview. 11.07.2025 - Updated the finantials. Attached the architectual document. 11.05.2025 - Updated this Initiative. Only the work item related to fixing the 10 must-fix identified **functional gaps**. Rest of items such as field level gap analysis & fix of field level gap analysis are made out of scope for this planview. 10.23.25 Roopa Mallu (Enterprise Arch) asked two questions - answers list below questions. Q: From what I heard from you and what is stated in Planview is that the Gap analysis is performed already to enable client migrations. And as per your statement now, Field level Gap analysis doesn't include the backend dependencies. My question to you is the scope question. Do you want this initiative to just bridge the identified gaps? or perform detailed gap analysis with respect to functional and/or field level in backend as well and then bridge the both new and already identified gaps? A: Perform the gap analysis at the field level, that's a definite yes. Bridge the GAPs identified Versus fill the GAPs identified? My understanding is bridge both new field level gaps identified through this request and also bridge the functional gaps already identified. Fixing/building out the changes identified would be included. Q: Are you also expecting any support from Shipment/product/customer EFS or URSA/UVSDK/LSSI...etc A - Bagya "Roopa, you had question for Kimberly on "gap analysis". Between FAPI and WS, the only downstream flow difference we are aware of is SHPC before the rest of the backend are the same for Ship and RATC for Rate. All we want is to make sure the behavior on API mimics the behavior on WS with respect to functionality. So we are only planning to audit SHPC and RATC. Any other back end support like EFS /URSA/UVSDK is not needed as they all follow the same protocol for both WS and API" 10.23.25 Per status call with Matt & team: 1. Reduced # of functionality fix from 19 total to 10 must-haves. 2. Removed Capability 4 - fix known defects. 3. Removed these priorities for Capability 2: Address Validation, Service Availability, Pickup Request, FedEx Locations Search; Ground End of Day Close, Postal Code Validation; Trade Documents Upload Updated IO | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: Adopt GDPP EDD predictions for Ground Economy |  | 164151 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Vinod Nair, Bikram Virk, Grace Stafford | On Track | **2/10/2026** * Finalized update LBC and submitted PDSM ticket to change financial estimates * Worked with Visibility Engineering team to understand GDPP model consumption flows **1/13/2026** * Requested to provide additional documentation regarding the work coverd by this initiative. See documentation below: Went to L1 Arch Alignment for T-shirt size reassessment. Team recommended changing from L to S-M. We have already completed the prediction work. The only part outstanding is to consume the EDD from GDPP and publish it to the Visibility channels. No UI aspects required for this change – all backend. For context, GDPP [Global Delivery Predictions Platform] has completed their predictive model. Only Data & AI and SCO involvement is required for identifying how to consume and integrate the data across systems (hard modeling work is done now it's just systems feeding the right systems and knowing what that architecture is). Init #164151: Adopt GDPP EDD for Ground Economy shipments has 2 major parts: EDD prediction for Ground Economy packages from GDPP (completed by Dataworks) Consumption of GDPP EDD by the downstream and publish it to Shipment Fusion (Outstanding/Pending) Need Data and AI / SCO involvement for the architecture and solutioning Note: No impacts to the Visibility layer - .com tracking, notifications, and other channels **12/23/2025** * Met with Liz Umstot to align on booster process * EPM request submiited for this initiative **12/18/2025** * Contacted April Zhou, Rachel Wood, and Monika Kowalska to understand hold-up re this initiative * Worked with Rachel Wood to identify next steps for a boost **Prior to December 2025** * Approval received to proceed to L2 * Met with Tracy Christoffersen (VP) to align on the initiative and incremental revenue * GDPP / Global Delivery Predictions Platform has completed the model work for predicting Ground Economy EDD (customers have been complaining about incorrect EDDs for Ground Economy especially during Peak) * Met with Jason Brenner (SVP) and Austin Luhman (VP) to discuss this initiative and received leadership approval to fast track based on significant gains for customers * Submitted Financial Input Document * Met with David Johansson to recieve final approval * High-level concept finalized * Request in L1 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Dataworks Salesforce Operations |  | 169497 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Naya Woods | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: RPI Digital PFS VB1A – Collab (MAGIC) |  | 170483 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng | On Track | On Track **Note on 24-Mar-26:** Modified NRB to OM: -$1.1M VM from this project is +$20M | E: L2 | Active | L2
Business w/ Tech Initiative: SAP Business network for logistics integrations |  | 177461 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kalpan Dalal, Arvind Reddy | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Visibility Product Family |  | 177479 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Grace Ann Aldridge, Andrew Balan | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Advanced Monitoring & Intervention |  | 179799 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Sumika Singh | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: [VIS] Delivery Instructions Enhancement - Resi FDM |  | 180530 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Gabriela Martucci Salles, Grace Stafford, Bhushan Ramesh Shiwankar | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: EMEA CAL7 API Gateway & Portal Upgrade |  | 180533 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Andrew Williams, Krishna Yerra, Sandhya R. Urlam | On Track | On Track 04/02 DJ Miller has approved Some Issues 03/23/2026 Still waiting for DJ Miller approval to move in to L2 - cannot proceed until approved and been waiting for 3 weeks On Track 03/02/2026 Commercial triage meeting attended 02/24/2026 Submitted for L2 | E: L2 | Active | L2
Business w/ Tech Initiative: RPI Digital PFS VB2 – Pickup Status In The Know |  | 184051 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: RPI Digital PFS VB1B – Collab (Others) |  | 184059 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: RPI Digital PFS VB5 – FedEx System / SOP |  | 184066 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: RPI Digital PFS VB3 – Standard RPI Capabilities |  | 184069 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Harry Cheng | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Onboarding - Additional payment methods |  | 184743 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Linda Bremmers | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: COM - Track - Safety Adjustments for FDM |  | 184747 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Gabriela Martucci Salles, Grace Stafford, Bhushan Ramesh Shiwankar | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Stripe One-Time Payment integrations with HOPE |  | 185589 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Joshua Hamblin, Riccardo Sbabo | On Track | This work is now part of 97870 - Contract to Collect - Epic 4. This request is to be cancelled and all work will be covered with 97870. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Digital Platform Modernization - Frontend/Backend |  | 188601 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Chris Elipas, Grace Stafford, Eelco Meuter, Marina Scott, Amanda Engel, Paul Visser | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: COM - VIS - CDOs via Integration Products |  | 188609 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Gabriela Martucci Salles, Bhushan Ramesh Shiwankar, Grace Stafford | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Transform CX Program |  | 152953 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Kathy Lawn, Taylor McPherson, Doug Mahan, Radhika Jadcherla, Like Li | On Track | 4/20/26- Updated the Brief Description and Ability Statement sections now that the scope of work is under the Digital Product Org. 1/12/2026 - Completing mode of this initiative to Digital. Scope for the following areas have either been removed or mograted to Initiative 142092 - Global CE Reinvention - Reactive: - fdx integration was removed because this is not a focus area for Digital or CE - OCCM Expansion shifted to 142092 and contained in sope of the GRIT ART - Content Management shifted to 142092 and is being delivered by the DCC team. Any Ability To statements in this initiative should be removed for these categories. 1/7/2026 - Initiative to be migrated to Digital due to scope being adapted to deliver on avoiding CX support through better Digital customer experiences. 10/10: Held CCH triage with CCH Lead to support CCH greenlight review/approval. Updated brief demand description and CCH questions and finalized the CCH overview pptx. 10/6 - After entering L2 , attended the Commercial L2 triage meeting, and the architectural assessment was carried out. Next step is L2 workshop as the path was determined to be D2CP (Direct to Solution, Cross Portfolio) 10/4 - Approved for L2 9/9 - Submitted for L2 Approval | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: BEACON Scan Upload/GetManifest IT Support |  | 189871 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Jyoti K. Narayanan | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Fraud Mitigation in the CIAM space |  | 190325 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Lauryan Feijen, Ulco Keegstra | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Modernize First Mile Vis Status & Notifications |  | 190786 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Megan Aurin, Alexander King | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: GAF Visibility - Get ALH scan from SEP to SFusion |  | 190789 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Sanjay Manaktala, Vincent Lafeber | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: COM - VIS - CDOs via Guest Authentication |  | 193145 | Business w/ Tech Initiative | Commercial - Digital | Commercial | Gabriela Martucci Salles | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Global Cold Chain Validation | 15276 | 6698 | Business Only Initiative | Commercial - Healthcare | Commercial | Dale Douglass, Brandon DePamphilis, Tyrone Simpson | On Track | 11/14/24: 19 inital target location have been identified. Project will review and estimate equipment costs necessary at each location and estimate the cost of validation and monitoring to meet GDP and CEIV requirements. 11/21/24: Presenting to CDR on Friday, 11/21/24. 12/5/24: Working with Jennifer Liu to get this pushed to L2 by Friday 12/6 and into L3 by end of December. 12/12/24: CDG provided greenlight at CDG to support audit on Feb 5. Working to push to L3 by 12/31/24. 12/19/24: Coodinating vendors and work at CDG to support audit on Feb 5. Met with Finance today at 2:30 PM CST to review submission for L3. Submitting Help ticket to remove soft benefit error. Once removed ready to submit to L3. Working to push to L3 by 12/31/24. 1/10/24: Update on CDG Validation efforts: -3 of their Cold Chain containers will be replaced with new and upgraded containers next week on Tuesday, January 14th. -The vendor Eupry will be at CDG the following week on Wed, January 22 to map and validate all of their cold chain equipment. 1/16/25: We received the following Finance Domain Lead (Mark Mantaro) feedback yesterday from my L3 submission: “”If this doesn’t require any technology and does not have an NRB, why is this in DRIVE? Seems to create work without any benefit. Just prioritize funding it and do it.” Working on approach with Exec Management. 1/22/25: We are working to find an alternative way to finance this effort. Meeting with Megan Lightford (Finance Executive Advisor) to discuss effort on Monday, Jan. 27. 3/26/25: Project has been re-activated and submitted sucessfully to L3. We are working with FedEx legal to approve ENCORE contracts with the two required vendors (Eupry and Titan). FIRST submission completed for all regions and approved. Expect contracts to be executed in 10 to 14 days. 4/2/25: We expect Eupry contract to be fully executed this week. This contract will cover 17 locations with the exception of CAN, KIX, LGG and MXP. These countries will require their own separate legal contract/language. Awaiting feedback for Titan on first draft of contract from FedEx. 4/9/25: Eupry contract fully executed on 4/2/25. This contract will cover 17 locations with the exception of CAN, KIX, LGG and MXP which require their own separate legal contract/language. Awaiting feedback for Titan on first draft of contract from FedEx. 4/16/25: Working with Eupry to begin validations at ready locations. Also working with Legal to execute Titan Global contract. First drafts have been passed between both companies and second round will be submitted to Titan today 4/16/25. 4/23/25: Validations will begin in Memphis at the MEMH CCC and GRIZZ on May 5. Other locations to be scheduled in the coming weeks. Titan returned second draft and I am working with FedEx legal to continue negotiations. 4/30/25: Validations will begin in Memphis at the MEMH CCC and GRIZZ on May 5. MIA validation expected to occur the week of May 12. Titan Contianer contract remains under negotiation. Optimistically it could be completed this week. 5/8/25: Validations underway in MEMH and Grizz this week. MIA will occur next week. The Titan Container contract remains under negotiation with both legal entities. 5/15/25: Work completed in MEMC1. Additional temp monitors required for Grizz location. MIA validation is underway this week and expected to be complete by Friday 5/16/25. The Titan contract remains under negotiation with both legal entities. 5/22/25: Installation completed in MEMC1. Additional temp monitors for Grizz location expected in mid-june for installation. MIA installation complete and supporting documentation is being prepared. The Titan contract remains under negotiation with both legal entities. 6/5/25: Additional temp monitors for Grizz location expected in mid-june for installation. MIA installation complete and supporting documentation is being prepared. The Titan contract remains under negotiation with both legal entities. 7/1 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-02-12 | 2026-06-12
Business Only Initiative: Global On-Demand Dry Ice Machines | 25526 | 6834 | Business Only Initiative | Commercial - Healthcare | Commercial | Al Cienfuegos, Dale Douglass | On Track | Initiative 29739 has been combined with this initiative. 11/14/24: ANC is ready to begin with approval. STN and CDG location are still evaluating the cost feasibility. 11/21/24: ANC is ready to begin with DRIVE approval. CDG meeting scheduled tomorrow to review with DG Management; feasibility pending. STN is conducting vendor screening to ascertain costs. 12/5/24: ANC is ready to begin with DRIVE approval. CDG costs have escalated and now shows negative finacial return. STN working with vendors to determine installation and lease costs. 12/12/24: ANC is ready to begin with approval greenlight. STN is the last location in analysis and STN Engineering is scheduling meeting with Dry Ice Machine supplier. 12/19/24: ANC is ready to begin with approval greenlight. STN is the last location in analysis and STN Engineering is scheduling meeting with Dry Ice Machine supplier. 1/16/25: ANC is ready to begin with approval greenlight. STN is attempting to secure time with vendor to discuss. 1/22/25: Anc is ready to begin with approval. Arja Virtanen (STN) has provided feedback that installation progress will not be quick tdue to current and proposed acility constraints. He is working on a high-level assessment to drop STN out of this project. 2/12/25: ICN, SIN and CDG show negative returns based on their project feedback. STN is opposed to moving forward due to time constraints. ANC is ready for greenlight. Will set up some time with jenifer Liu to review status. 3/26/25: CDG team communicated that they can get any quantity of dry ice within one hour and they don't use half of their supply on any given day, plus the facility size constraints. Based on this information this project will now focus to the major US locations (ANC). 4/2/25: Working to update Biz case to include ANC only. 4/9/25: Working to update Biz case to include ANC only. 4/16/25: Working to update Biz case to include ANC only. 4/23/25: Working to update Biz case to include ANC only. 4/30/25: Re-evaluating costs for ANC. Reaching out to Dry Ice Machine vendor for updated pricing to update business case. 5/8/25: Continuing to re-evaluate costs for ANC. Reaching out to Dry Ice Machine vendor for updated pricing to update business case. 5/15/25: Continuing to re-evaluate costs for ANC. Reaching out to Dry Ice Machine vendor for updated pricing to update business case. 5/22/25: Re-evaluating costs for ANC. Contacting vendor ASCO for updated pricing for this location to update business case. 6//5/25: Re-evaluating costs for ANC. Contacting vendor ASCO for updated pricing for this location to update business case. 7/17/25: Continuing to re-evaluate costs for ANC. Reaching out to Dry Ice Machine vendor for updated pricing to update business case. 7/2/25: Alignement with ANC Properties and dry ice machine vendor. 8/7/25: Working to shift this initative to a new team under David Cienfuegos (Network Implementation). 8/21/25: Working to shift this initative to a new team under David Cienfuegos (Network Implementation). 9/3/25: Working to shift this initative to a new team under David Cienfuegos (Network Implementation). 9/11/25: Working to shift this initative to a new team under David Cienfuegos (Network Implementation). 9/18/25: Meeting with David Cienfuegos to determine timing for shift of ownership to his team. 9/25/25: Meeting with David Cienfuegos to determine timing for shift of ownership to his team. 10/1/25: No change. 10/8/25: No change. 10/22/25: No change. | E: L2 | Active | L2 & CCH
Business Only Initiative: Global Healthcare Quality | 15277 | 6836 | Business Only Initiative | Commercial - Healthcare | Commercial | Dale Douglass, Lewis E. Judd | On Track | Hired Managers and Healthcare Quality Advisors in each mega region. Set up a Healthcare Quality management system specific to Good Distribution Practices and CEIV/Pharma regulations. 12/19/24: Will hold L3 submission to align with pharma business case timeline. 1/28/26: Goal of project is to complete the hiring and develop the structure of the Global Healthcare Quality team. This project will add a total of 59 additonal positions globally. To date we have hired 21 incremental postions (35% of goal). We exct to have all hiring complete by June 2026. 3/4/26: Goal of project is to complete the hiring and develop the structure of the Global Healthcare Quality team. This project will add a total of 59 additonal positions globally. To date we have hired 29 incremental positions (50% of goal). We expect to have all hiring complete by June 2026. 4/22/26: Goal of project is to complete the hiring and develop the structure of the Global Healthcare Quality team. This project will add a total of 59 additonal positions globally. To date we have hired 48 incremental positions (80% of goal). We expect to have all hiring complete by June 2026. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-14 | 2026-06-30
Business w/ Tech Initiative: Monitoring & Intervention with HC ID and CT- US | 40778 | 7111 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Virginie Lasnier, John Bennett, Stephanie V. Yong Velarde | Some Issues | April 21st 2026 *Operation: Urgent need for Operation PMO / Lead ( US/ Global) to address RefresherTraining, Ops communication, MI and SAID SOPs compliance, day to day Ops support including N2.O MI, MSTs usage and service levels. Now impacting all new customers especially large accounts such as Motorola, Google, Costco. Ask included in CCH Deck May 7th but based on global in market challenges, immediate adhoc support is recommended while long term ownership is addressed . In Escalation since June 2025. *Working on transition plan to Digital Marketing and Product Marketing while still keeping FY26 and TY 26 deliverables on track. Escalation Requested: Confirm Leads to pass project too and final transition ETA. April 30 *M&I Walk the Wall - Completed actions items list by stakeholders. Awaiting management sign off for release. Working on CCH PPT for May 7. IT Projects Updates *CEBS US/ USI Task controller enhancements needed asap Oct 25. CEBS IT submitted request to acquire resources April 6th. Onboarding of IT resources 6 weeks out. July 2026 Release Date unlikely. New Date TBD * Rex 83 surcharges project - Lost revenue and EO resources after start of solutioning. Awaiting updates from PRT * MI automated Onboarding - in PRT Backlog. in Escalation. Back to CPEL on 2/25. Architects not available to engage . Awaiting Updates from PRT On Hold * Digital Marketing and MI Marketing executives to align and finalize commercial approach format by June 30, 2026 * Pricing/ Legal working session to finalize global pricing and contracting processes and US pricing requested changes in progress. Awaiting commercial approach decision expected in next 90 days to finalize. will work on implementing areas of no impacts. June 30 April 15th 2026 Working on transition plan based on re org announcement of MI to Digital Marketing ( Commercialization, Run business, Product Capabilities/ IT) and Product Marketing ( Interventions/ IT interventions) while still keeping April. May and TY 26 deliverables on track. Management Working on acquiring names of new team leads to pass project too and to confirm ETA.May 30 *M&I Walk the Wall - Complted actions items list by stakeholders. To release shortly. Awaiting managemebt sign off. Working on CCH PPT forMay 7. MI MKT to update Scope and Roadmap updated awaiting sign off. May 30 * Digital Marketing and MI Marketing executives to align and finalize commercial approach format by June 30, 2026 * Pricing/ Legal working session to finalize global pricing and contracting processes and US pricing requested changes in progress. Awaiting commercial approach decision expected in next 90 days to finalize. will work on implementing areas of no impacts. June 30 * *CEBS US Cold chain IB enhancement needed asap. July 26 to be confirmed. Budget approved. John Bennett and CEBS Team working on implementation for IT resources to be hired. * Rex 83 surcharges project - Lost revenue and EO resources after start of solutioning. Awaiting updates from PRT * MI automated Onboarding - in PRT Backlog. in Escalation. Back to CPEL on 2/25. Architects not available to engage . Awaiting Updates from PRT April 8th 2026 * Completed M&I Walk the Wall activities. Recap, actions items and executives slide for action. Information collected to be used in the Network and Service disruptions for workstream #4, as well as the M&I program update scheduled for CCH on May 7. MI MKT to update Scope and Roadmap. May 30 * Digital Marketing and MI Marketing executives to align and finalize commercial approach format by June 30, 2026 * Pricing/ Legal working session to finalize global pricing and contracting processes and US pricing requested changes in progress. Awaiting commercial approach decision expected in next 90 days to finalize. will work on implementing areas of no impacts. June 30 * *CEBS US Cold chain IB enhancement needed asap. July 26 to be confirmed. Budget approved. John Bennett and CEBS Team working on implementation for | G: L3 | Active | TEMP L3 - Enter L3 | 2022-10-31 | 2026-05-26
Business w/ Tech Initiative: Special Services - US | 63810 | 7160 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Kathy Jimenez, Chris Swearingen | On Track | 4-15-2026: Team continues to work on defects that have been identified. Preparations on under way for Tier 2 country roll out by May 15. 3-23-2026: War Room/Hypercare week 4 has been going well. Defects found and are being worked through quickly. We have extended the War Room meeting through Friday. March 27. 3-11-2026: War Room/Hypercare week 2 has been going well. Defects found and are being worked through quickly. We are going to extended the War Room meeting through Friday. March 20. 3-4-2026: Marketplace for Epic 1 is now live. We have stood up a War Room/Hypercare to work through any issues that arise now in move to production. 2-26-2026: Epic 2 On Hold due to Ability Tos review in progress to ensure comprehensive scope capture. Per Reinaldo Perez - Email David Murray 2-10-2026 2-24-2026: Go No Go meeting ocurred on Monday, 2/23 Marketplace Go Live is Tuesday, March 3. This applies to Air Expedite portion of Marketplace. War Room between Janus and AE product team is schedule for March 3-13 7am- 4pm cst. 2-18-2026: Epic 1 Marketplace tool launch, GO NO GO decision meeting is Friday, 2-20-2026. 2-11-2026: Marketplace UAT Testing with in AE continues, Train the Trainer sessions have been completed. Marketplace training for Air Expedite agents is in progress. Epic 2 Sales Compensation and Financial Reporting discussions are also in progress. 2-2-2026: Business cost- one-time expense 2 OSC testers, started January 2026 1-29-2026: Updated commercial forecast per Portfolio guidance due to delay of epic 2 timeline. 1-27-2026: A new Commercial Portfolio forecast has been received for the initiative. The cost remains the same but the financial spread will now run through May 2027 due to timeline slippage for Epic 2. We have determine due to middleware work within the SCO portfolio is now impacted with Epic 2. We are meeting with SCO portfolio to prepare for SCO PEL and get approval for additional funding to cover Epic 2. D&T finance will be contacted to review and provide a SCO portfolio forecast for epic 2. We have also begun meeting with Sales and Data & AI portfolio to discuss creating a Sales Compensation engine (connection between EIW and iSell) for recognition of revenue for Air Expedite and Special Services US for epic 2. Epic 1: UAT testing began 1/19 and continue to 1/30. Train the trainer sessions began 1/28 -1/30. 1-21-2026: User Acceptance Testing began this week and is going well. Defects have been identified and in the work queue. We have also started conversations for Epic 2 financial reporting and Sales compensation. These calls will be ongoing. 1-15-2026: We will soon begin discussion to pivot to Epic 2. We have determined that Epic 2 will impact Supply Chain Portfolio which was not previously identified. Epic 2 is set to begin June 1, 2026 and run through May 31, 2027. Commercial Portfolio forecast spread will need to be extended to May 2027. 01-07-2026: Team is engaged with G2M and G2S to finalize communication plan. UAT testing is set to begin on January 19. End to End testers onboarding has started. Epic 2 timeline has slid to May 2027 due to Epic priotirization. 12-17-2025: Attended CPEL today 12/17 for Epic 2 priotirization, CPEL decision is to take it back and discuss priotirization. Epic 2 start date 6/01/2026. 12-02-2025: Marketplace testing is being performed by RMIC Communication plan is under development with Marketing for Marketplace Implementation plan is being finalized Attending CPEL on 12/17 for EPIC 2 pritiriozation 11-19-2025: Confirmed actuals have been entered in to Planview Financials screen June - October 2025 11-11-2025: SpS US initiative is now in L3. 11-05-2025: The initiative is still in SL3 awaiting TO Finanve approval. 10-30-2025: We are still in SL3 awaiting TO Finance approval. 10-20-2025: We received feedback from Domain Finance regarding demand type. The question asked was that the inittiatve is a candidate for Lifecycle Management du | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-27 | 2027-05-31
Business Only Initiative: Monitoring & Intervention with HC ID - CA | 16819 | 8044 | Business Only Initiative | Commercial - Healthcare | Commercial | Bryan Jimenez, Tejas Shah | On Track | Date / Update **12/10/2025** **Current status:** - No major updates. Aritzia customer training ongoing (setting up views and usage). Paid contract setup to follow. - Other GTM updates undergoing revisions (industry 1-pagers, new description table based on US, pricing hidden URL) Items below raised on Global MI Issue Tracker: - *new* US WWS SDI support ending by 2025. Canada Customer Solutions team requesting resources to support WWS onboarding. - Sales Compensation process: Need clarity on Sales compensation for digital subscription sales (cost center TBC; data source will be manually done via Dataworks US Pricing tracker). Working with Sales Solutions to confirm the process. - Service level data review support required. Current plan is to review via PowerBI dashboard. For follow up: Any service level template to be shared by US GSQA. Currently Canada is getting service levels manually (extracted by Solutions Marketing) Other action items: - For review: Additional Finance validation needed on costs for Freight. US MI team shared US costs for reference. **Archive** 12/3/2025 - Aligned with US Field SDI team to support Canada Field Sales onboarding. - Business case to be cleaned, meeting to be set with Finance to review. - Service Description on fedex.ca hidden URL updated. Other GTM updates undergoing revisions (industry 1-pagers, new description table based on US, pricing hidden URL) - Pipeline opportunities updated: Aritzia 90 day trial signed and onboarded on 12/2 (paid contract to follow in Feb'26). Other onboarding ongoing: Cirion (pending CT confirmation), Amgen (onboarding pending); Nicoya Lifesciences (onboarding pending) 11/21/2025 - Business case to be cleaned, meeting to be set with Finance to review. - Postponed to following week due to other executive requests. - Legal contracts updated and finalized (new surcharge order form and subscription-only form; service description update). Service Description update to be refreshed on fedex.ca hidden URL - GTM updates undergoing revisions (industry 1-pagers, new description table based on US, pricing hidden URL) - Pipeline opportunities updated: Cirion signed and to be onboarded pending CT confirmation; targeting Aritzia in coming weeks. Innomar/Cencora on hold until new calendar year. 11/12/2025: - Business case to be cleaned, meeting to be set with Finance to review by next week. - Legal contracts to be reviewed and finalized by next week. - GTM updates undergoing revisions. - Pipeline opportunities updated (Cirion signed; targeting Innomar/Cencora and Aritzia in coming weeks) 10/30/2025 - No other new updates. Other customer meetings ongoing. (Aritzia, etc) - Business case to be refreshed and reviewed with local Canada management. Initial review with Finance done. - Cencora opportunity - pricing being finalized and offered by CA Sales to customer. 10/22/2025 - Cencora opportunity to be also focused on by US/Global Sales leadership (from Accelerate HC call 10/22). 10/16/2025 - Customer updates: Aritzia contract - aligned with Legal, Sales on exception (90 day free trial only). Succeeding months - new contract must be signed. In parallel, alternative payment/billing method being finalized. 10/8/2025 - Updating business case for L3 (cleaning up monthly view and KPIs). Other customer meetings ongoing. - Customer updates: Aritzia contract - aligned with Legal, Sales on exception (90 day free trial only). Succeeding months - new contract must be signed. Payment/billing method being finalized. Completed: - CE contact email updated and tested. - Fix implemented by US dev team on PowerBI dashboard. Testing showed no further questions. We will continue using and raise any issues if needed. 9/24/2025 - No major updates. - New customer signed on Premium - Mejuri Inc. Onboarding process initiated. - Ongoing discussion with internal stakeholders to discuss alternatives for digital subscription (interim) for specific customer need (Aritzia) 9/17/2025 - No major upda | E: L2 | Active | L2 | 2023-11-01 | 2026-05-29
Business w/ Tech Initiative: Set HCID shipment internal commit time prior to pu | 89958 | 8319 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | John Bennett | On Track | The FXG on-road optimization tools make this not possible without de-optimizing routes or adding too many additional routes. The package scoring app will be used to move cirtical/perishable volume to Legacy Express couriers for delivery. Date / Update 7/15/2025 - Shared with Tucker and John Bennett impact analysis of rolling out to fewer destinations based on those that support a large amount of HCV volume. Pending feedback. 7/9/2025 - I am reviewing impact of rolling out to less destination stations based on healthcare destination volume. 7/1/2025 - I am reviewing impact of rolling out to less destination stations based on healthcare destination volume. 6/23/2025 - Meeting to be setup with leadership team to discuss this initiative due to the costs associated. 6/11/2025 - Meeting to be setup with leadership team to discuss this initiative due to the costs associated. Pending guidance on attendees. 5/29/2025 - Meeting to be setup with leadership team to discuss this initiative due to the costs associated. 5/19/2025 - Enabler can move forward per ESPM. Pending PDSM ticker resolution to tie to main M&I Project then ready to submit for SL2. 5/14/2025 - Enabler can move forward per ESPM. Business case confirmed with finance. 5/7/2025 - Still reviewing business case changes with finance. Because this is an enabler, I will need input on how we should move forward as the project it enables is already in L3. 4/29/2025 - Submitted for SL2 but there are additional items needing updates. I am reviewing with finance for the LBC changes and have reached out to the Domain PMO to help with tying this item as a dependency to the MI US initiative. 4/22/2025 - The LBC has been confirmed with finance and we have received the L1 architecture review. Submission for SL2 is pending dependency addition. 4/15/2025 - The team is still working on the LBC. The initiative is on the L1 architecture assignment list. 4/8/2025 - The team is still working on the LBC. I have reached out to schedule time to triage with architecture team. 4/1/2025 - The team is still working on the LBC. 3/26/2025 - We are completing the LBC with finance, pending input from Surround on imapct of less RDLs. 3/18/2025 - We have received the cost per route and mile from finance. Finalziing the LBC and then validating with finance. 3/11/2025 - We have received the cost per route and mile from finance. Reviewing with solutions team on how to accurately represent in LBC. 3/4/2025 - We have received the cost per route and mile from finance. Discussing with team how to add to the LBC. 2/25/2025 - We are pending info from Liz Lee in finance on cost of additional routes or mileage associated to this initiative to help complete the LBC. 2/18/2025 - We are pending info from Liz Lee in finance on cost of additional routes or mileage associated to this initiative to help complete the LBC. 2/11/2025 - We met with Steven Woolard who directed us to Elizabeth Lee. I will reach out to her for her input on cost of route additions. 2/5/2025 - We have met with Jennifer Liu. We will change this to an enabler type. I have reached out to contact she provided to help identify the cost of additional routes (Steven Woolard). 1/29/2025 - Testing is complete. We are meeting with Jennifer Liu in Finance on 1/31 to help complete the LBC. 1/22/2025 - We have to go back and re-test the scenarios. This should be completed this week. 1/10/2025 - Testing is complete, and we are reviewing the testing results before engaging finance to get an esitmated impact. 12/17/2024 - New scenarios were identified that needed to be tested. This is in progress, expected to be completed by tomorrow 12/18. We will then review the results again to identify estimated cost vs. benefit. 12/4/2024 - Testing is completed by engineering on impact of earlier commit times in 4 identified markets; we are reviewing results to identify estimated cost vs. benefit 11/19/2024 - Testing is ongoing, nearing complet | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Global Clinical Trials | 15274 | 9193 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Bob Matthews, Michael Ely, Oscar Zuluaga | Some Issues | 3.25.26 - regional leads met with MAGIC and Digital teams on 3/6 to discuss alignment of feature requirements submitted last September. At regular twice-monthly call with regional leads on 3/17, discussed resetting capabilities and corresponding forecasts. Started weekly meetings with Marcus Freeman in Finance on 3/18. 2.5.26 - Global Clinical Trials - #9193 - The business case is fully re-launched to L2. Bob Matthews has replaced Michael Ely as Primary and will begin working with Finance and the regions to create a new forecast. 1.29.26 Global Clinical Trials - #9193 - With the assistance from TO Finance, GCT now has Scott Higgins (Finance VP) approval to move the GCT business case (#9193) from L3 back to L2. Also completed the final step in the process by executing a PDSM ticket to outline the changes, further articulate reasoning and provide documented Finance VP approval. This change request will allow for a reset of GCT priorities and forecasts, along with changes to the scope to align as the premium parcel solution for Pharma. This change should be visible in Planview in a few days. 1.15.26 Global Clinical Trials - #9193 - Over the holiday break completed the final touches on the business case rewrite to make it easier to understand for Finance. The journey to move the business case back to L2 is one step closer to completion with the approval from Finance VP Scott Higgins. The final step is a PDSM ServiceNow demand request submission to alert the Planview team and change the L status. 12.11.25 Global Clinical Trials - #9193 - The Global Clinical Trials FY26 Q1 leadership call on 12.8 went well. Good attendance and engaging conversation about the overall direction of Clinical Trials. Chris Gant challenged the team to double revenues in FY27 ($490M), then double that again in FY28 ($980M). That level of results will require analysis to understand the necessary investments needed to accelerate major growth in less than three years. The team and the regions will complete the assessment and report back to leadership for next steps direction. The business case will proceed with movement back to L2 and reset the move-forward plan. 12.4.25 Global Clinical Trials - #9193 - There is a a Global Clinical Trials Leadership review call scheduled for Monday 12.8.. The call is scheduled to update leadership and other key stakeholders about the health of GCT. The call will focus on Q1 financials, the status of the business case, the preferred future state along with updates from each region about the individual work being done in the respective global areas. 11.20.25 Global Clinical Trials - #9193 Still in revenue validation stage for AMEA. We have had one call with the region but a follow up call is needed with thier Finacne teams. The LAC revenue concerns were reconciled. Waiting on Finance to give the green light to submit the business case to move back to L2. Finalizing NRB and Money Step. 11.13.25 Global Clinical Trials - #9193 Another step to validate revenue quality for AMEA and LAC....both regions had unusually high margins that need to be defined. 11.6.25 Global Clinical - #9193 Finalizing stops to have business case moved back to L2. Went over all finacials and the bsuiness case rewrite with Jennifer Liu. She made a few recommendations that need finalized and I need to share with my leadership before submitting to Finance VP for approval to move back to L2. 10.23 25 Global Clinical Trials - #9193 Updated revenue and still working through Milestone updates and revisions. Currently, completing the recreation of the business case so that we can present the case to go back to L2 to reset the forecasts and the priorities. The game plan is to have the L2 reset completed by the first week of November. 10.16.25 Global Clinical Trials - #9193 Met with the APAC team again along with the Digital team to review requirements specifically aligned to TrialDat. We had the region demo of the tool and p | E: L2 | Active | L2 - Enter Value Prop | 2022-01-03 | 2026-05-29
Business w/ Tech Initiative: EUM - [EUM] Global SpS | 15278 | 9195 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Lisa DeMali, Christopher M. Watts, Andrew Rudman, Eric Joyner, Theju Chikkathamme Gowda, VB Joshi, Pieter Kop, Aashish Goyal | Attention Needed | Attention needed due to ExCom decision: ****ExCom decision made not to renew vendor contract 10/3 oRequires development of Special Express, Dedicated Vehicle and NFO by end of CY26 to support the migration of customers in CY27** Specific direction from Tom Wicinski to push this to L3 as quickly as possible. ****9 digit unification is being added as milestone work, needed to support SpS/CargoWis-added 3/19/26, Pieter Kop will have responsibility **** **Escalated to OW-Pending feedback: Costs related to CargoWise/SPOTS build all falling under Global SpS #9195, including FXL finance needs (headcounts etc…). Business case impacts and lack of justification on spend vs. ROI. Global SpS cannot take any benefits from system retirement, those benefits have been allocated to EU modernization** **4/21/26** Global SpS #9195 •EPIC.gov scheduled for 4/22 •Several ongoing RMIC discussions taking place, there is some confusion around the work needed from this team as scope has changed and the SPOTS bridging concept is playing into this as well. Working with Gokcen and Fatia Qadri to bring everyone together and ensure clarity on the path forward. •Products, options, and charge codes have been defined, upcoming socialization calls with impacted teams to be scheduled for week of 4/27 •Brand re-engaged to review product names/options 4/20 •Clearance discussion scheduled for 4/23 to address open questions •Insurance and insurance capabilities discussion scheduled for 4/23 to address open questions •User story kick-off scheduled for 4/22 L3 •All EPICS have moved to L3 **4/14/26** •Productization Q&A meetings taking place this week Tues-Thurs 4/14-4/16, purpose is to answer outstanding SpS/FXL questions, complete AB2’s and finalize options. We will schedule calls everyday with the stakeholders until this action item is completed. •EPIC.Gov form completed, pending meeting invite 4/6 •Regional stakeholder meeting cadence set up, starting 4/23 •New Epic Owner assigned: Fatima Qadri L Gate Status: L3 Call out: SpS is taking on all the costs for the build and none of the legacy system retirement benefits. Need to ensure that this is properly positioned in the HC POD or if it is a better fit in EU Modernization or GAF, escalated to OW for leadership review 4/13. Needs further discussion/decisions **4/7/26** Global SpS •Commercial workstream meeting cadence and kick-off completed 4/7 •Will feed back progress, next steps, risks, and blockers to OW for weekly Steercom meetings oOwners: Commercial PMO-Lisa DeMali •Product-Clara Lamatta Digital: Arial Vargas •Digital.com Visibility: Peter Sola •API Integration: Kalapan Dalal •Pricing: Alex Ohta •Product AB2’s progressing with the evaluation by enterprise architects, AB2’s due for completion by 4/17 •Currently in Solutioning •Achieved L3 4/6 **3/31/26** •All costs have been provided for impacted portfolios •Heath status review scheduled for 4/4 •Greenlight: oEPIC owner actions needed, OOF until 4/4 PPM status change •Business case vs. costs oWorking to realize additional costs and updating business case Updated assumptions for additional value oAdding cost saving from retiring legacy TNT systems, although there is some additional discussion taking place about the accuracy of the information provided oCW going back to FXL, cost may change based on updates oGlobal SpS is taking on all costs for migration, including FXL non-IT related costs. Will further discuss during the HC Pod call **3/24/26** Global SpS #9195 •Productization workshops are currently in progress oOutcome readout will be provided 3/26 L3 •Pending costing from Platform-currently in progress. This is the last need item before greenlighting estimated by 3/26 •SCO information for Pel has been submitted, costing updated in Planview •Non-it related costs entered into Planview •Milestones updated •Comm | G: L3 | Active | L3 | 2025-12-01 | 2025-12-01
Business Only Initiative: Monitoring & Intervention with HC ID - APAC | 16820 | 9303 | Business Only Initiative | Commercial - Healthcare | Commercial | June Wang, Nirupam Pandya | On Track | Zuora process for M&I invoicing opened on 09 JAN in SG, HK & JP; So far, credit card payment option only, actively working with global team on alternative plans. Planning FY26 innitiatives and timeline, CN launch tend to be in Aug-Oct 25 and Elite launch tend to be in FY26 Q2. Targeting to finalize re-baseline and FY28 projection input by mid-Jun 2025. | E: L2 | Active | L2 & CCH | 2023-08-01 | 2025-05-30
Business Only Initiative: Monitoring & Intervention with HC ID - LAC | 16821 | 9305 | Business Only Initiative | Commercial - Healthcare | Commercial | Pedro Garcia Leoni, Juan Marcos Gutierrez, Federico Del Real | On Track | 10/7 - Farmacam from Panama is actively shipping; 3 more contracts pending onboarding (2 in Panama, 1 in Mexico); updates on Milestones, KPIs, and financials to be updated NLT mid November 8/27 - 6 countries (PR, CR, DO, PA, MX, CO) fully launched and selling. BR & CL pending sales enablement. Continuous progress for international market enablement and completion by end of FY26. Working on a total of 28 countries, then reviewing capabilities with GSPs to define whether they can match the services within the value prop and not risk our premium services. CL, MX, CO Domestic markets to be included as well. 7/9 - MX, CO, BR training scheduled for week of July 28. First customer (Asofarma) officially onboarded and 4 other opportunities have been raised. Surround demo to sales on 7/9. Working with Strategic Marketing team on updating forecasts to submit L3 business case - timeline tbd 6/25 - PR, DO, PA, and CR sales has been trained. PA has 1 customer being onboarded. MX, CO, and BR sales training is planned mid-July. Expansion into remaining international markets is in progress and MX Domestic enablement is planned to begin work in July. 4/24 - AR & CL still pending ops approval due to AR regulatory requirements and CL domestic enablement of purple systems; PA onboarding of AsoFarma as first M&I customer is in progress; Sales training scheduled for June 19 & 20 in Spanish & Portuguese 2/5 - AR, CO, CL SOPs developed, Splits created, and ops training in progress; rollout plan for rest of LAC completed; planning meeting with MX Marketing for Domestic 1/23 - CE Intercept training completed for all sub-regions (MX, BR, ASC, CCA); MX service agreement approval granted; presented to HC Leadership and Accelerate Healthcare forums 1/21 & 1/22 1/16 - M&I Training materials being reviewed for approval and sales training date planning in progress; AR, CO, CL ops training in progress - Test shipments planned for Feb; Expansion Plan to rest of LAC and Domestic markets - In Progress 12/5 - M&I GTM/GTS materials translated to Spanish & Portuguese received from agency. Test shipments to PA, DO, BR completed. Working on controls to ensure CEBS responsibilities are completed by local ops to avoid open items. Legal approval of service agreements completed for PR,CR, PA, DO and pending resolution for BR and MX. 11/12 - MX and CR OB shipments 1st round completed with shipper user errors (2nd round being completed today); BR, DA, PA test shipments also in progress 9/12 - Sales training held on 9/11; GTM adaptation for CR & MX to be completed and provided to sales education team for CR & MX Sales training NLT 9/20; Test Shipments for CR & MX underway; L3 business case completion target 9/20 9/5 - First round of test shipments into CR shipped; CR & MX SOPs completed and uploaded to EKO; Call with MX Ops 9/5 to discuss any open questions before test shipments 8/22 - PR Enablement completed on Tuesday 8/20; PR Operations fully enabled to handle MI shipments; Sales enablement still in progress so commercialization in PR is pending; CR & MX Ops and CE teams are engaged and in training and weekly meetings are being established; Bi-weekly meetings are being established for full engagement of remaining countries (BR, DO, PA, CO, CL, AR) 8/15 - CE coverage of PR being confirmed with US team, pending response; Received US Project plan and confirmation of completion of activities in progress - Finalize NLT 8/20; Received final Surround contracts 8/8 - PR launch will proceed with a controlled POC, defining specific customers and proceeding with limited volume to ensure the product features are fully compliant with the value proposition; CE training is completed for CCA; MX, BR, ASC CE teams in progress of definition 8/1 - RMC presentation 7/31 was successful; US delayed International launch, PR is ready for IB shipments and testing OB shipments; US communicated on 7/31 that all employees including couriers, service agents, DG specialists, others) w | E: L2 | Active | L2 & CCH | 2023-03-17 | 2025-01-10
Business Only Initiative: Launching FedEx Surround MI service in Europe | 16822 | 9308 | Business Only Initiative | Commercial - Healthcare | Commercial | Conny van Regenmortel, Joep Rutten | On Track | Launching FedEx Surround MI service in Europe - Wave Init. #16822 / Planview Strat ID# 9308 04/13/2026: March estimate for actuals entered. Check on commercialization impact GPCC Select and Mosaic / 4 Kites Controll Tower projects. Constraints to be addressed: Invoicing solution with viable (EFT) payment options for Surround digital subscription fees, Priority Clearance processes for MI shipments, OPS compliance to priority handly process for MI shipments, low network SVL, MST rollout in Europe. 03/25/2026: Check on commercialization impact GPCC Select and Mosaic / 4 Kites Controll Tower projects. Constraints to be addressed: Invoicing solution with viable (EFT) payment options for Surround digital subscription fees, Priority Clearance processes for MI shipments, OPS compliance to priority handly process for MI shipments, low network SVL, MST rollout in Europe. 03/18/2026: February actuals entered. Check on commercialization impact GPCC Select and Mosaic / 4 Kites Controll Tower projects. Constraints to be addressed: Invoicing solution with viable (EFT) payment options for Surround digital subscription fees, Priority Clearance processes for MI shipments, OPS compliance to priority handly process for MI shipments, low network SVL, MST rollout in Europe. 03/12/2026: Febuary PKI estimates entered in Planview. Constraints to be addressed: Invoicing solution with viable (EFT) payment options for Surround digital subscription fees, Priority Clearance processes for MI shipments, OPS compliance to priority handly process for MI shipments, low network SVL, MST rollout in Europe 03/02/2026: Constraints to be addressed: Invoicing solution with viable (EFT) payment options for Surround digital subscription fees, Priority Clearance processes for MI shipments, OPS compliance to priority handly process for MI shipments, low network SVL, MST rollout in Europe 02/24/2026: Constraints to be addressed: Invoicing solution with viable (EFT) payment options for Surround digital subscription fees, Priority Clearance processes for MI shipments, OPS compliance to priority handly process for MI shipments, low network SVL, MST rollout in Europe 02/16/2026: January real actuals updated in Planview. We received the bi-weekly “newsletter” on billing, including global billing enablement to track progress on billing solution for Surround subscription 02/10/2026: Introduction complex opportunity checklist, refresher training for Europe CT Surround SME team by US team (12/2), January estimated actuals entered. Stryker and Revvity pending signature and launch, ongoing concern and discussion on Surround Preferred on IEF service. 02/02/2026: Working on refresher training for Europe Surround CT SME team by US CT team. 01/27/2026: Need for refresher training for Europe Surround CT SME team. Concern on Zuora invoicing method availability and new options via Contract to Collect or Fastbill for invoicing monthly subscription fee. Also concern on Surround offered by US team on IEF for GE Healthcare. Resources taken from Surround developmen team to work on new digital platform. 01/20/2026: Concern on Zuora invoicing method availability and new options via Contract to Collect or Fastbill for invoicing monthly subscription fee. Also concern on Surround offered by US team on IEF for GE Healthcare. Resources taken from Surround developmen team to work on new digital platform. 01/13/2026: Concern about providing again info on invoicing methods in Europe; still no date for Zuora invoicing method availability and new options via Contract to Collect or Fastbill for invoicing monthly subscription fee. Also concern on Surround offered by US team on IEF for GE Healthcare. 01/06/2026: December estimate date entered as preliminary (to be updated with actual revenue for December after Jan 15th.). Preparing Commercialization update for December - pending final december data on SVL and # shipments (plus comparising date FPA and MBG Priority SVL) 12/16/2025: Updated November esti | G: L3 | Active | TEMP L3 - Enter L3 | 2023-03-31 | 2027-05-31
Business Only Initiative: Grow Pharma Air Freight |  | 91351 | Business Only Initiative | Commercial - Healthcare | Commercial | Karl Kussow | On Track | 2026/04/22 •We have aligned across EU and APAC regions to use this drive initiative for all lanes/customers/container types (active, passive, blankets) across the global project (vs. having separate regional pharma initiatives). •The finance leads (Clay Kasdorf, Jennifer Liu) with Jun Xie are working to align on a global business case template that can be used to finish L1 requirements and move the initiative to L2. Next step in developing the business case is dependent on knowing the SO for pharma so that the business revenue targets in the business case will be aligned to the SO. •Facility builds required for cold corridor expansion will also planned to be in DRIVE under this global initiative (#91351) using Milestones or Child initiatives as appropriate So far, there is one Child initiative entered: Cold Chain Solutions IND-MEM, #161478, currently in L1, no revenue separately from Grow Pharma Air Freight. •P&E (David Cienfuegos) also created an initiative to support facilities expansions supporting IND-DUB temperature control corridor 2026/04/15 •DUB-IND corridor nearing completion. Test shipments to prove the solution are being planned to start on April 28 and run through May 15 •Roadmap Lanes currently being actively developed are: DUB-IND LGG-IND LGG-MEM ICN-IND ICN-MEM 2026/03/24 •The “cold corridor” is still under construction – target for completion end of April to add value to customer shipments starting early May •Cold Chain Center in DUB (operated by Fynes Logistics) has completed their 2-8C room oThe 15-25C room is under construction - completion targeted for mid-end of April with subsequent PQ completed by early May •Cold Chain Center in IND is in place and tested completely operational to support FCF shipments in both 2-8C and 15-25C handling/staging rooms. •Temperature controls in aircraft (aka ,“cold plane”) is in progress. First test flights successfully achieved target temperatures in each cargo hold. 2026/03/11 • Cross‑functional teams progressing DUB–IND end‑to‑end temperature‑control implementation. • Aligned with officers to partner with FSC to expand cold corridor storage and handling capacity in IND. • Irish licensing requirements in DUB, cold plane development and 15-25C workspace build in DUB, are still pending completion. Launch is targeted for April 30 2026/02/25 • Cross‑functional teams progressing DUB–IND end‑to‑end temperature‑control implementation. • Initial cold corridor temperature tests completed - follow-up actions in progress to fill identified gaps. • Met with FedEx Supply Chain, agreed to collaborate across opcos to add capacity for cold corridor operations 2026/02/11 •Cross functional teams continue work to implement the temperature controls during all steps door to door DUB-IND •Cold corridor testing kicked off 10Feb for 2-8C corridor. Test will be used to create temperature profile that will assist HC Sales in closing Pharma sales opportunities. 2026/02/05 •Cross functional teams continue work to implement the temperature controls during all steps door to door DUB-IND •Cold corridor temperature profile gathering postponed to start week of 9 Feb to align with cold plane thermal mapping. •Continue to work with APAC, EU and US to align on structure for global business case. •Working on commercialization processes to speed customer adoption and onboarding 2026/01/14 continue to refine/finalize plans for cold corridor tests now planned for first week in Feb. coordinating across US, APAC, EU marketing leads to align on DRIVE strategy for global pharma. Options being considered are 1) single global initiative with milestones for each shipping lane or location - or - 2) three initiatives, one for each region. 2025/12/11 Working on business case - revenue and volume forecast EU team obtaining quotes from DUB vendors to confirm costs. Reviewing operations process through IND. Began preparing for cold plane and end to end corridor ambient profile data tests to be com | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Grow Pharma Temperature Solutions |  | 91356 | Business Only Initiative | Commercial - Healthcare | Commercial | Karl Kussow | On Track | Recommendation is to cancel this initiative that is not active. FCF including last mile temperature control delivey solutions (e.g., TCN and FCC in US) are being addressed via other initiatives. 2025/08/28 • will not achieve L2 in Sep. Pending resource assignment. current team is prioritizing effort into 91351, Grow Pharma Airfreight initiative. • FCF and TCN are anticipated to be utilized within the scope of the solution being built for Grow Pharma Air Freight. • I have entered $0 in the NRB fields for L1 (below) as a placeholder pending completion of financial estimate. 2025/03/05 • working to understand FCC (TCN and Temperatrue Controlled Validated) solutions and assess requirements for growth • working to align initiatives: Pharma will take advantage of the existing initiatives for FCF and SPS to also leverage those capabilities in our plan. • aligning with officers on target shipping lanes to focus Pharma requirements assessment 2025/02/25 • beginning to develop L1 LBC 2025/02/19 • working to compare SPS capabilities with Pharma/bio lane analysis 2025/02/12 Reviewing SPS documentation and drive project plans to understand how SPS (including AE/FCF) can be applied to solve Pharma opportunities. Reaching out to collaborate with SPS and FCF project leads to understand where (in what regions and on what shipping lanes) do SPS capabilities align with Pharma expectations. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Grow HC US Domestic Parcel |  | 91359 | Business Only Initiative | Commercial - Healthcare | Commercial | Karl Kussow | On Track | Pending assignment of project resources and future prioritization (TBD). The Pharma project team is prioritizing effort into 91351, Grow Pharma Airfreight initiative. 2025/03/05 • continuing to meet with Sales to gather 3PL requirements • aligning with officers during weekly update call (Friday afternoons) on priority and next steps for this workstream • I have entered $0 in the NRB fields for L1 (below) as a placeholder pending completion of financial estimate. 2025/02/19 • continuing to meet with Sales to gather 3PL requirements • shipping lane analysis is using recent Healthcare (Pharma/bio) RFQ data 2025/02/12 Project team is gathering information about 3PL needs and FedEx capabilities on high volume Pharma shipping lanes in order to identify gaps, solve for the gaps, and create compelling messaging to present to 3PLs to drive sales. Next steps: 1) gain clarity on 3PL shipping requirements via Sales interviews. 2) complete shipping lane analysis to identifiy available capabilities | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Monitoring & Intervention with HC ID - MEISA |  | 92357 | Business Only Initiative | Commercial - Healthcare | Commercial | Sumit Singh | On Track | 23rd April: * 7 new customers in pipeline with contract shared * Contract under review for updating as per global * Next country launch under review 10th April: * 41 customers onboarded * Another session planned for sales in KSA * 1st KSA customer onboarding initiated 19th Jan: * Operations training completed : 2 sessions * Sales training completed * Geofencing for SAID completed for KSA stations * KSA Launch on 20th 8th Jan: * Saudi launch on 20th Jan * Infra readiness for SAID WIP * Business case approved and numbers will be updated early next week 15th December: * Saudi launch on track * SAID infrastructure WIP * Business case updated and shared with finance for approval 2nd December: * Pricing uploaded for MEISA markets * Saudi MI SOP under review with P&E * Sales awareness session planned * SAID infrastructure WIP 13th Nov: * MI contract ready and approved * Saudi launch : * On track with few check points pending * WIP for business case 6th Nov: * Business case KPI to be updated as per comments * On target to move to L3 by Nov mid * MI Launch for SA market initated. * New contract for MI customer approved. 28th Oct: * Working with finance on updated financials of the business case. * Plan to launch SA market for MI * GTM/GTS to be updated * Targeting L3 by nov mid. 16th Oct: * Business case updated and shared with finance for approval * Financial to be updated in Planview once biz case approved 6th Oct: * KPI and milestones added in Planview * Financials updated in Planview * To be submitted to L3 * MNI contract pending approvals 26 sept: * Financials KPIs defined to be submitted in planview * Manual billing started for IN, approval submitted for AE, ZA and SA. * New contract pending for approval 18 sept: * Moved to L2 * Risk, KPI, milestone to be updated * Planning to move to L3 28th Aug: * Business case created * Business case approved by finance * to move to L2 10th July 2025: * 9 customer signed the contract. * Pipeline of 50+ customers * Working towards moving the Initiative to L2 26th May 2025: * Test shipment completed * GTM/GTS updated * Training sessions completed * Launched for ZA 5th May 2025: * South Africa launch date fixed on 20th may. * Sales training planned 6th and 7th May. * Operations training planned 6th and 7th May. * CMOD training session 13th May. 1st April 2025: * Regulatory check in import/export of SAID WIP. * WAP accesspoint mapping to be completed this week * Pricing to be uploaded to system. 27th March 2025: * South Africa launch planned in May. * Weekly cadence started with ZA team. * To check regulatory compliance on SAID. * MNI ZA SOP WIP. * Access point mapping and geofencing WIP. 5th March 2025: * South Africa launch prep for MNI * Weekly cadence from next week * GTM/GTS to be updated 20th Feb 2025: * Successfull launch in UAE * GTM-GTS approved and updated for UAE * Next markets planned : Saudi and South Africa under evaluation. 12th Feb 2025: * Sales training completed for UAE launch * GTM/GTS updated and shared with legal * MNI SOP for UAE WIP * FLC courses for ops training circulated. * UAE Surround page WIP 30th Jan 2025: * MNI successfully launnched in India on 20th Jan * Update call completed with leadership on HC-POD * UAE planned next for the launch on 20th Feb 13th Jan 2025: •Pricing rate cards finalized and loaded •Contract – finalized and ready •M&I SOP, SA ID SOP finalized •Automation tools ready for M&I •GTM material – Brand and Legal Approved •GTS Material – Brand and Legal Approved | E: L2 | Active | L2 | 2025-06-02 | 2026-05-29
Business w/ Tech Initiative: Enable Inside Pharmacy delivery for FXG Shipments |  | 98408 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Makynn Ellison | On Track | Cancelling this initiative. 6/13/25: Received permission to change sizing to Medium from Large. 6/11/25: This was identified as impacted by Stop Work. The benefits ahve been re-evaluated with finance. I am pending a response from the triage team on if we can change sizing from Large to Medium. It went through L2 traige on Monday June 2nd. 5/29/25: Scheduled for L2 triage on Monday June 2nd. 5/14/25: LBC is finalized. Submitting to SL2. 5/7/25: Architecture review has been complete. Finalizing the inputs and will submit to SL2 soon. 4/29/25: The LBC has been confirmed with finance. We are pending L1 architecture review. 4/22/25: The LBC has been confirmed with finance. We are pending L1 architecture review. 4/15/25: The team is still working on the lean business case. 4/8/25: The team is still working on the lean business case. 4/1/25: The team is still working on the lean business case. 3/26/25: The team is still working on the lean business case. 3/18/25: The team is still working on the lean business case. 3/11/25: The team is still working on the lean business case. 3/4/25: The team is still working on the lean business case. 2/25/25: The team will begin business case creation this week using Finance's template. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: SenseAware IoT Platform |  | 113084 | Business Only Initiative | Commercial - Healthcare | Commercial | Varma Kosuri | On Track | We plan to create new request for this. | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business Only Initiative: Pharma Growth Strategy - HC Sales |  | 126734 | Business Only Initiative | Commercial - Healthcare | Commercial | Karl Kussow | On Track | 2026/02/11 updated L4/money step date based on COE ability to produce January actuals data at end of Feb (1st week of April) 2026/01/15 preparing report for January actual revenue to be entered next month 2026/01/08 updated cost actuals for Dec. moved "money step" to 2/12/2026 2025/12/3 updated actual costs using "estimated' actuals. 2025/11/05 updated actual costs using "estimated' actuals. 2025/07/29 Updated financials with improved business case showing positive NRB $87,140 2025/07/23 approved and in L3 on 7/21 notified team so that Sales hiring can begin. 2025/07/08 L2 updates completed. Initiative is submitted for approval to L3 2025/07/03 Changed initiative name FROM: Add new MD team to HC Sales org TO: Pharma Growth Strategy - HC Sales achieved L2. entering financials, KPI etc. before submitting to L3. Money Step is in January, when the new HC EG sales team is in place and revenue from that team begins to be realized. Monthly report from Sales analyst will show baseline (starting in Aug when hires are in place) and monitor for incremental revenue in subsequent months. - 1st incremental revenue is anticipated in January due to long HC sales cycle. 2025/06/25 updating L1 LBC and re-submited to L2 on 6/24 2025/06/11 Submitted for L2 approval Finance has questions - working to resolve them and complete the business case template. 2025/06/05 Triage approved for L1. Confirming revenue #s for FY25 baseline. for L1 business case. | I: L4 | Active | L4 | 2026-03-05 | 2026-03-05
Business w/ Tech Initiative: SpS Migration Project Continuation to SPOTS v2 |  | 148178 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Melisa Dicker, Richard Holloway | On Track | 24/07/25 - some resources still doing some works on this project | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: FCF transformation: Epic 1 | 15487 | 9235 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | John Bennett, Oxana Dudina, Michael Ely, Kelly McAnally | On Track | 12/19/2025: Costs have been entered and will work with TO Finance to close out the Project. Commercial has this init as closed. Per TO Finance, Domain Finance, EPSM, and EPM guidance: Epic 1 is to become an enabler to Epics 2 & 3. Epic 1 will have zero revenue and value will be transitioned to Epics 2 & 3 (#6763) 3/19/2025: PHASAR update delayed due to delays in CONDOR migration. FCF cannot be loaded to production until CONDOR changes are made. FCF currently only has financial data for Q2. Re-baselining will need to be postponed until Q3 data is available. 3/5/2025: working to enter trued up Q2 FY25 data (still missing Q3) 1/20/24: Decision made in Int Freight POD to enter into L4 with open PHASAR impact/milestone to be completed post money step 1/13/24: Epic 1 service option code actively applied to live shipments 1/11/24: Epic 1 loaded into production 11/1/24: All FCF financial data comes from USI Finance and is typically on a two month lag. September actuals should be available now but we have not received them. 10/9/24: SRB was pushed to 10/8; determined that we will move forward with testing on October 28 to be ready for January CSR. In preparation for wave freeze, Revenue/Cost impacts and KPIs have been updated for June through August. 10/1/24: Attending SRB (Surface Review Board) on Thursday, October 3 to determine if we'll be ready for testing in time for the January CSR. Delays past this CSR will impact our NBR in FY25. All values prior to money step is enabled by milestones for work done outside of development. FCF Global Product team continues to work through development process for Epic 1 and expects to surge soon. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-02-01 | 2025-05-30
Business w/ Tech Initiative: FCF transformation: Epics 2 & 3 | 96273 | 6763 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | John Bennett, Oxana Dudina, Michael Ely, Kelly McAnally | On Track | 12/19/2025: Q1 FY26 financials have been entered. Decomp work for Epic 2 is progressing with Enterprise Architecture involved. Work continues on diagrams and prep for the various review boards. Tentative target for submission for prioritizartion is March 2026. Current plan is to leverage what has been built for Surround Monitoring and Intervention to reduce the number of capabilities that will need to be developed. 4/8/2025: Epics 2 & 3 going to TO this week to align team to the 3.6 CCH boost and enter PRT work. Re-baseline will happen in parallel but will not hold up progress. 3/19/2025: FCF currently only has financial data for Q2. Re-baselining will need to be postponed until Q3 data is available. **IMPORTANT** FCF Epics 2&3 were boosted at CCH by Brie and DJ. EPC team last week delayed that boost until re-baselining is complete. This only further delays value delivery of Epics 2&3 and continues to place this init at risk. Cannot re-baseline at this time due to lack of data. Being escalated to TO. 3.5.2025 - request to attend CCH to request "boost" for Epics 2 & 3 to fully realize FCF Transformation value (epics 1-3) as well as support key B2B segments (pharma and auto) FCF Transformation broken out in DRIVE in August of 2024 in order to move Epic 1 into Solutioning - Guidance given by Commercial Demand Team Business case approved by Domain Finance 11/22/24 | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Releye RLP |  | 177442 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Briana Fisher | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Global Cold Chain Validation - Phase II |  | 187278 | Business Only Initiative | Commercial - Healthcare | Commercial | Dale Douglass | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: ServiceNow CRM for FedEx Healthcare Quality Team |  | 189942 | Business w/ Tech Initiative | Commercial - Healthcare | Commercial | Adam Said | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Enhance 4 Freight Flavors - GAF PFS | 57156 | 6723 | Business Only Initiative | Commercial - International Freight & GAF | Commercial | Laura Hill, Brian Marie | On Track | **11/25** Approval for L5. For L5 requrement is to report KPIs for 9 Months. - KPIS reported since August 2024 Submitting for L5 Review. **11/10** received input from Michelle Hull to identify IT contract spend. $68k To dos: - Enter into Finance template - Resubmit for L5 **11/3** To dos: - Work with Michelle Hull to identify IT contract spend - Enter into Finance template - Resubmit for L5 - **10/28** - Confirmed DAL API Launch to close defect - Updated 4FF % KPIs - KPIS reported since August 2024 **10/27** To do this week - Confirm positive launch for COM - GDX -DAL API Enhancement for Express Freight - Update 4FF figures Target L5 to begin Dec 1 (attend socialization to be scheduled) **9/8** No change for this init. Gap closure with 0105843 Work ID for local enhancmetn COM - GDX -DAL API Enhancement for Express Freight moved to L3. EPIC Plan /Execution in process. ***7/30*** No changes **6/11** - All major updates have been completed for MAGIC and Locator on fedex.com that were requested in this Drive Init. - Additional work on APIF will be tracked in separate Drive Init 0105843 which is a local tech demand. - All of APAC enabled and non-postal countries are showing correctly. Exception is TW which continues to be worked. - Finalization of checklist to be complete and will request to move this init to L5. Plan to summarize what was completed as well as outstanding improvements and capabilities needed for 4FF. 5/13 - Progress underway for improving the results being returned in Magic and on Locator. - APIF changes pending approval to move into L3. - Launched DAL in China, Thialand, Austrailia, Japan, Korea. - Work continues on resolving defect for Non-postal countries **4/21** - Current status is pending assignent of Local resources for APIF changes for LOCCS - all other work specific to HAL/DAL for Magic and Locator App is complete or on hold for confirmation when this is implemented. *** 3/17 DAL Expereince Enhancements are underway. DAL APIF changes for LOCCs is in process is in L2 (Local Demand). Continuing to test other changes in Visionary to improve customer experience and accuracy of DAL locations in Magic. *** 1/13 HAL/DAL loaded and launched globally, except for APAC. Concern from APAC is around Girth not being calculated to differeniate between Onsite/FSC and Ramp capabiliites. Working with APAC marketing, HAL/Onsite Parcel team, Locator team and Digital Team for resolution. 12/9 - DAL is moving again. UAT scheduled to begin week of 12/9. go live date post peak 11/25 - no change 11/15 Locator Loaded with no issues and LSSI Ramp locaitons have been published globally based on ROC and HAL hours in LSSI. HAL is working as designed in MAGIC to display the appropriate locations (package or freight) based on weight of shipment. ** Additional investigation continues for locations where there were questions about details in LSSI. Target Completion end of Nov. Impact is that these locations are not yet published. DAL is on hold until development team complete an unexpected priority. Will monitor on a biweekly basis | K: L5 | Completed | L5 | 2024-02-16 | 2024-12-31
Business w/ Tech Initiative: Design Air Freight Portfolio - TRI-COLOR Network | 15518 | 6724 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Sarah Welch, Brian Marie, Laura Hill | Some Issues | This initiative is dependent on the Tricolor Network and will need input from the network design to determine short- and long-term benefits. The Tricolor Network design is projected to be completed in April 2023; therefore, this initiative will not be able to move forward until after network design is provided. | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: Updating Weight Restrictions with Automation Platf | 69600 | 7053 | Business Only Initiative | Commercial - International Freight & GAF | Commercial | Kelly Franks, Laura Hill | On Track | Updated weight restrictions for IPF and IEF for CA went live 7/29 shifting the allowable wight in GPR enabled customer automation platforms from 2200lbs to 4400lbs. In process of updating FDF. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FedEx Air Freight Premier Care - USI | 66051 | 7396 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Claudio Genua, Amanda G. McMinn, Lee Hardy II | On Track | - Global airfreight strategy being coordinated amongst mutiple teams, Marketing, CE, FXL, SDI, Sales etc. - AFPC specific system improvements are in process of being defined. The team has been refining the ask for sizing with Dataworks. - Regional expansion continues to be on track. | E: L2 | Active | L2 | 2024-01-02 | 2024-11-15
Business w/ Tech Initiative: Launch International Deferred Freight 1A & 1B | 15532 | 9240 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Sarah Welch, Laura Hill | On Track | **Update for 02.06.2026** Origin Consolidation 'Ability To's' for APAC OB / US OB handed off to SCO PRT Aug. 28th - pending prioritization to move forward with PRT scoping & development Mixed Unit Shipping Capability - beginning P&E scoping for APAC OB / US OB in beginning phase - defining requirements, possible interim state and needed core team resources **Update for 03.17.25** FDF MMP1A launched to market July 29th, 2024, however, since both 1A and 1B are in one init, we were advised to keep overall init in L2 until 1B is fully in Solutioning, hence current L2 status **FDF MMP1B Commercial:** • Commercial PRT has been completed and is on-hold pending open SCO caps 4 & 5 • There may be a need to revisit PRT work, based on outcomes of SCO PRT on open caps 4 & 5 **FDF MMP1B SCO:** SCO capabilities on track: Capability 1: 'Ability to accurately quote FDF commitment (including double digit calendar day commits)' • Development is being handled outside of FDF development - broader LSSI system issue Capability 2: 'Ability to distinguish FDF volume from IEF volume for internal forecasting' • Testing for the PHX -> InfoFactory -> CargoRes flow is still in progress as related to the CargoRes piece. Testing has has passed 100%, MTP most likely this week. Capability 3: 'Ability to identify FDF shipments in external systems (France & Poland)' • 1B test lanes were loaded for Apr25CSR; discuss/plan testing for FR/PL destinations • If testing goes well can move FR & PL destination lanes into production post-CSR * Some initial testing work has begun to create test shipments for PO Open SCO Capabilities still in pre-PRT: Capability 4: 'Ability to ship both heavy-weight loose parcel (no weight & DIM minimums) & palletized freight on the FDF product code' • Cap 4 is paused to be picked up after Cap 5, on hold status is pre-PRT P&E discovery still needed • Possible Commercial impacts, to be determined in SCO PRT work • Also possible considerations for other on-going work within Enterprise on how we handle mixed unit shipments - will need to re-align with this when we pick this capability back up Capability 5: 'Ability to consolidate FDF shipments at origin - taking advantage of additional transit time to hold and consolidate shipments with other freight and parcel shipments, to achieve operational efficiencies & lower cost" • P&E will put initial focus on this capability prior to solving for cap 4 • Recieved new P&E resource this week, we are meeting 03.18 to begubn discussions - first focus once new resource is up to speed will be determining feasible timeline to complete P&E discovery • July25CSR feasibility still at risk, but may not need a CSR for this work ○ 1B test lanes will be uploaded into Jul25CSR just in case needed • As of now no Commercial impact with this capability | E: L2 | Active | L2 & CCH | 2023-03-21 | 2025-07-18
Business w/ Tech Initiative: GAF PFS -4FF Operational Transit Time Differential |  | 86874 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Gahlawat Arpit, Laura Hill | Some Issues | **4/13** Enterprise Ranking: 152 (was 148) Domain: 39 (was 38) Commercial: 88 (was 83) PRT Backlog: 29 (was 29) **4/6** Enterprise Ranking: 148 (was 151) Domain: 38 (was 39) Commercial: 83 (was 84) PRT Backlog: 29 (was 30) **3/30** Enterprise Ranking: 151 (was 159) Domain: 39 (was 39) Commercial: 84 (was 86) PRT Backlog: 30 (was 29) Back up IO to be Arpit Gahlawat (pending access) **3/23** Enterprise Ranking: 159 (was 106) Domain: 39 (was 32) Commercial: 86 (was 66) PRT Backlog: 29 (was 27) **3/9** Enterprise Ranking: 106 (was 86) Domain: 32 (was 25) Commercial: 66 (was 54) PRT Backlog: 27 (was 28) **2/23** Enterprise Ranking: 86 (was 103) Domain: 25 (was 32) Commercial: 54 (was 63) PRT Backlog: 28 (was 28) **2/16** Enterprise Ranking: 103 (was 85) Domain: 32 (was 25) Commercial: 63 (was 51) PRT Backlog: 28 (was 27) **2/9** Enterprise Ranking: 85 (was 80) Domain: 25 (was 23) Commercial: 51 (was 46) PRT Backlog: 27 (was 27) **2/2** Enterprise Ranking: 80 (was 194) Domain: 23 (was 47) Commercial: 46 PRT Backlog: 27 (was 28) **1/26** Enterprise Ranking: 194 (was 100) Domain: 47 (was 28) PRT Backlog: 28 (was 28) **1/20** Enterprise Ranking: 100 (was 98) Domain: 28 (was 29) PRT Backlog: 28 (was 35) **1/12** Enterprise Ranking: 98 (was 100) Domain: 28 (was 29) PRT Backlog: 35 (was 35) **1/6** Enterprise Ranking: 100 (was 90) Domain: 29 (was 27) PRT Backlog: 35 (was 35) **12/17** Enterprise Ranking: 90 (was 127) Domain: 27 (was 38) PRT Backlog: 35 (was 41) **12/8** Enterprise Ranking: 127 (was 127) Domain: 38 (was 39) PRT Backlog: 41 (was 41) **12/1** Enterprise Ranking: 127 (was 128) Domain: 39 (was 42) PRT Backlog: 41 (was 43) **11/17** Enterprise Ranking: 128 (was 116) Domain: 42 (was 37) PRT Backlog: 43 (was 43) **11/10** Enterprise Ranking: 116 (was 119) Domain: 37 (was 39) PRT Backlog: 43 (was 33) - Updated project description and primary value type. 11/10 - Will try to adjust value impact - currently unable to do so. **11/3** Enterprise Ranking: 119 (was 114) Domain: 38 (was 34) PRT Backlog: Yes 33 - no change 10/27/25 86874 – GAF PFS – 4FF Operational Transit Time Differential – (L2) Enterprise Ranking: 114 (was 220) Domain: 34 (was 50) PRT Backlog: Yes (AG) 33 enbaler for – 114082 Sirius GAF pending move to L2 9/8/2025 No change. Init remains in PRT backlog at 23. It is 166 for Enterprise Ranking. 47 for Commercial ranking. Dependent upon Sirius GAF parity init 114082 moving to L2 to gain higher prioritization. This init is pending CDR dicussion and approval of Finance to move forward. 7/30/2025 we’ve taken this to CPEL this a.m. and have rec’d an updated ranking of 19th in backlog – moving it up from 123rd. We’ve identified this as an enabler for our GAF digital initiative and are working to get that biz case refined and moved into L2. Unfortunately PV error was found on GAF init and a PDSM ticket has been opened. Pending resolution & final finance review 6/11/25 Pending assignment of an Architect to complete Assessment & Decomposition, Conceptual Architecture, Envisioning (as necessary), and Value Delivery Bundles/Epics. Current Ranking - Enterprise - 110, Domain - 32, Commercial Port 55 5/13/25 - Pending Portfolio Greenlight eval/response. Submitted 5/1. 4/12/25 Pending Commercial Triage and assignment of resources | E: L2 | Active | L2
Business w/ Tech Initiative: Updating Allowable Weight & Dims for GAF Products |  | 141617 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Gahlawat Arpit, Sarah Welch, Michelle Lee | On Track | 01/29/2026 Working to identify and enter all required fields for enabler init to submit for L2 11/10/2025 Completed L1 Architecture review and working through L1 enabler business case | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: APAC Freight Ancillary System Design |  | 141787 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Shu-Nga Cheung, Siu-Man Peggy Tang | On Track | 15/09 APAC Revenue forecast in progress | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Alcon - EDI 990 Reply Transaction Support |  | 143199 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Cherish Thyot | On Track | Experimentation is not moving forward. Canceling request. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Alcon - EDI 204 Data Mapping Ingestion Support |  | 143204 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Cherish Thyot | On Track | Experimentation is not moving forward. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: US FICE Enhancements to Enable IEF | 95935 | 7052 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Sonja L. Richardson, Cami Fields | On Track | 4/20/26 Enterprise ranking 59 (was 58), domain 14 (was 15) Portfolio 39. PRT backlog 7 (was 9). Performing tweaks to LBC for final approvals by finance and moving through L2 checklist for PPM proposals, etc. 4/13/26 Enterprise ranking 58 (unchanged), doman 15 (unchanged), PRT backlog 9 (unchanged) 4/7/26 PDSM Ticket approved 4/6/26, FICE updated from LG to MED. Enterprise ranking 58 (was 85), domain 15, PRT backlog 9 (was 12). 3/30/26 Enterprise ranking 86 (was 91), domain 26 (was 28), PRT backlog 12 (no change). 3/25/26 Resized during second triage to Medium vs large. Need ticket in order to make adjustments for scoring. Enterprise ranking 91 (was 98), domain 28 (was 27), PRT backlog 12 (was 8). 3/16/26 Enterprise ranking 99 (was 98), domain 27 (was 28), PRT backlog 8. Karen M presented in CDR 3/13/26 (leadership only), triage re-evaluation meeting scheduled for discussion 3/16/26. 3/9/26 Enterprise ranking 98 (was 94), domain 28, PRT backlog 8. Discussed init in POD call in preparation for CDR 3/13/26. 3/2/26 Enterprise ranking 95 (was 94), domain 28, PRT backlog 8. Received CCH greenlight, performed SL2 QA Check with Commercial Domain PMO (Karen McConnico) to verify data hygiene in L0 and L1. PDSM ticket will need to be submitted to update required PV fields. Once complete, an L2 data hygiene check will be scheduled. 2/23/26 Enterprise ranking 94 (was 91), domain 28, PRT backlog 8 (unchanged). 2/16/26 Enterprise ranking 91 (was 89), domain 28, PRT backlog 8 (no change). 2/9/26 Enterprise ranking 89 (was 94), domain 28, PRT backlog 8 (was 7) 2/2/26- Enterprise ranking 94 (was 88), domain 28 (was 26), PRT backlog 7 (was 21). 1/27/26- Enterprise ranking 88 (was 210), doman 26 (was 51), PRT backlog 21 (was 20). Ticket approved, ESI updated to Tricolor. 1/19/26- Enterprise ranking 210 (was 202), domain 51 (was 48), PRT backlog 20 (was 24). Refining LBC, NRB increased to $27M, request for ESI update via PDSM ticket. 12/29/25- Enterprise ranking 202 (was 195), domain 48, PRT backlog 24. Awaiting finance validation of NRB increase for higher prioritization. 12/15/25- Analysis for waiver rate information on government accounts to support increasing NRB. Enterprise ranking: 194 (was 195), Domain 48, PRT backlog 24 (was 26). 12/8/25 Enterprise ranking:195 PRT backlog: 26 12/1/25 - Enterprise Ranking: 190 (was 195) PRT Backlog: 26 - (was 21). Working with revenue to obtain surcharge info to validate increased NRB calculations from finance. 11/17/25 - Emailed Suzanne Sabbatini for authorization to update ESI to tricolor in support of opened ticket REQ7057975. Awaiting response from revenue for waiver rates & surcharge rev per shipment info to validate increased NRB. Ranking 195 Domain 53 Commercial 116. 11/10/25 - Met with finance and have recalculations for increased NRB, will update PV after POD finance meeting and validation. Enterprise ranking 211, PRT backlog #20 (was #21) 10/27/25 - Enterprise ranking #211 10/20/25 - Awaiting finance for improved NRB, presented to Data and AI triage 10/15/25 -ranking currently 200+, Data and AI only has resourcing for top 50. Due to internal reorganizations, leadership/ownership for this opportunity still being determined within Data and AI. 10/13/25 - Current ER is 190 which is not aggressive enough based on the revenue this init anticipates. Working to ensure the correct figures are in Planview and working with Finance and Sales to align on updated numbers. 9/26/25 - Completed CPEL this week; next steps Data & AI triage call 8/8/25 - FICE progressed to L2, Enterprise ranking - 165, Domain -49, Commercial 99 8/4/25-Working through requirements and LBC preparation and finalization; ongoing conversations with Finance 7/28/25 - Meeting with URSA/UVSDK/CPP/DDI on interim solutions and possible sizing. 7/24/25 POD changed to commercial and status updated 7/21/25 Needs to be moved from clearance POD to Commercial; pending leadership discussions | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: J&J EDI Conversion to JSON & Data Updates |  | 114078 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Cherish Thyot | On Track | Experminetation is not moving forward. Canceling request. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: GAF Time Specific Delivery |  | 161857 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Michelle Lee, Kelly Franks, Cami Fields | On Track | 03/19/26, 03/26/26 - Gathered data on how FCF handles time specific delivery. Will speak to Air Expedite team about logistics. 02/19/26, 02/26/26, 03/05/26, 03/12/26 - Spoke to Operations about scope and 3PL vs 2PL logistics. Will reach out to Bunker and Sales to collect data on customer demand. 01/29/26, 02/05/26, 02/12/26 - No update. Collecting data for Problem Statement and Value Proposition. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: VAS Cross Dock / Consol & Deconsol |  | 164116 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Sarah Welch | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: VAS - GAF Cargo Insurance |  | 166434 | Business w/ Tech Initiative | Commercial - International Freight & GAF | Commercial | Loni Y. Tully, Kelly Franks | On Track | xyz | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global Residential Database & Surcharge | 38872 | 6868 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Grant Heyman, Mark Cockerell | On Track | 11/3- Business case and Global Resi Database investment was approved by finance team to advance to L2 11/6-11/10- Submitted for L2 on 11/6, now awaiting approvals 11/13-17- Team presented at CCH, recieved verbal approvals to move to L2 11/20-24- awaiting final L2 approvals, Confirmed 11/30 completion date for refreshed resi surcharge analysis from pricing (intl' portion) 12/4-12/8- Team presented to Nick Davignon Pricing Staff Meeting and obtained approval for MVP internal data solution for Resi Database, Awaiting final L2 approval 12/18-12/22- Updated Residential Surcharge Analysis (International only) was finished by Pricing and incorporated in Wave business case, Resubmitted for L2 approval 12/25-12/29- Awaiting L2 approvals 1/1-1/5- L2 approval recieved 1/8-1/12- Project submitted to CPEL on 1/12 1/22-1/26- Resi Surcharge Intra-country added to business case (+$3.3M), CPEL intake meeting scheduled for 1/25 1/29-2/2- Project will be presented at 2/14 CPEL, Project submitted to EP Intake for AEFS impact 2/26-3/1/24- Presented project at LPM intake for AEFS impact, labled as ready for assesment 4/18- Presented at Request Confirmation meeting; Received greenlight and project moved to assesment phase in PRT 5/9/24- Initiative remains in assesment phase in PRT, Worked with business architects this week to refine AB2s, submitted project surface portfolio for Express impacts 5/30/24- Initiative remains in assessement phase in PRT, Strategic Initiative Review (SIR) meeting will take place next week to end assessment phase. next phase is decomposition with IT/Enterprise architects 6/27/24- Commercial portfolio PRT assessment phase is now complete; Next steps include PRT architecture review, XPEL and decomposition phase for system impacts and further solutioning 7/11/24- PRT decomposition phase has begun; Commercial IT architect (Jason Miller) has been assigned to the project. 7/25- Project remains in decomposition phase for Commericial PRT; Project is 3rd in line to be moved out of "ready for assessment" phase in platinum portfolio 8/9/24- Project remains in decomposition phase for Commercial PRT; Project is 4th in line to be moved out of "ready for assessment" phase in platinum portfolio; 8/15/24 - Commericial Portfolio, Working through PRT process, decomposition phase; Platinum Portfolio- Project is 4th in line to be moved out of "ready for assessment" phase; Alignment meeting with Commercial & Platinum took place on 8/13-Outstanding item of who owns and implements business rules for global resi database- Is it AEFS or another IT team?; Submit for TCH Greenlight by end of week 8/23/24- Commericial Portfolio, Working through PRT process, decomposition phase; Platinum Portfolio- Project is next in line to be moved out of "ready for assessment" phase; 2nd Alignment meeting with Commercial & Platinum will take place 2nd week of September 9/6/24- Commericial Portfolio, Working through PRT process, decomposition phase; Platinum Portfolio- Project is next in line to be moved out of "ready for assessment" phase; 2nd Alignment meeting with Commercial & Platinum will take place 2nd week of September; Looking into engaging Dataworks and Supply Chain (operations) portfolio in this initiative 9/19/24- Commericial Portfolio, Working through PRT process, decomposition phase. Initiative has been moved to "blocked" status until alignment is complete with Platform portfolio. Once we've nailed down which requirements are owned by Commericial, project will be unblocked and resume decomposition. Platinum Portfolio- Project is next in line to be moved out of "ready for assessment" phase; 2nd Alignment meeting with Commercial & Platform will take place 9/20 10/2/24- A series of alignment workshops is being scheduled with Platform & Commercial Portfolios to nail down ownership and exectuion of key requirements for this initiative. Platinum Portfolio has moved this initiative to assess phase and has assigned an IT architect 10/10/24- half day works | E: L2 | Active | L2 & CCH | 2024-12-31 | 2027-06-15
Business Only Initiative: Global Enablers -Customer Support Structure | 88007 | 7679 | Business Only Initiative | Commercial - International Parcel & E-Commerce | Commercial | Jay Bhatt, Zachary Audet | On Track | **Rationale to Cancel this Init:** There is no need additional need (development or business request) associated with this initiative. In Feb of FY25, we obtained approval via CCH (both Brie & Neil Gibson) for the 6 dedicated Customer Experience (CE) vendor resources required to grow this program from a US outbound perspective. The CE vendor resources were already within the CE budget; they were re-allocated to our program so there was no incremental hiring or spend. Throughout FY26 we've have experienced significant growth with Global-e, who has been the main Global Enabler we have been focused on to build out the overall program. From a YoY (Jun-Feb) perspective, US outbound revenue has increased 2,309% (or +$5.5M) & volume grew by 2,496% (or +277K). Futhermore, FY26 (full year) Global-e US outbound revenue is forecasted to surpass $7.6M & volume will come in at or above ~385K. The team also expects the momentum of growth to continue as we head into Transition Year (TY) 26 and Calendar Year (CY) 2027 as incremental gains will come from several efforts that are currently in-flight with Global-e. In closing, since there isn't a need for any additional development or business support & the capture of this incremental growth is being observed in the International Parcel Product P&Ls (e.g., IP, FICP, IE), we are requesting leadership approval to cancel this init. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: HS Auto-Classification-Pre-Shipping with WorldTari | 1130 | 8038 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Sanghamitra Panda, Cami Fields, Janice Caudill | On Track | 2/8: The reassessment of the financials is still in progress. We met with FXE finance (Brian / Bill) and FXS finance (Kendra) today (2/8) to discuss on the revisions FXE finance came up with. Brian and Bill are going to discuss with their mgmt on the incremental revenue considerations and cost avoidance duplications if any (since heads reduction is not part of it) & let us know the outcomes. This will help us update the final value into Wave 2/9: Additional revisions needed in the business case per feedback with FXE finance to show the incremental revenue opportunity that the tool will provide. We are working with World Tariff team on the next step and revising the business value 2/16: World Tariff team is finalizing the report from their finance team by 2/20 and then we will meet to review to make sure it shows the incremental revenue opportunity coming from the tool. After internal review, we will pass it to the finance team for further review and approval. CPEL intake form submission in progress 2/22: Spring and I met yesterday to review and update the business case. After necessary updates, I have shared the revised case with Spring. Internal review will happen with Cami/David to align on the new numbers (2/24) 2/24: After internal alignments, we are going to meet FXE finance to review the revised business case and value coming Monday (2/27) 2/28: As part of finance review on 2/27, they have asked additional info on current rates, rates of competitors for similar classification service, more details on the model build out costs and a bigger picture of the initiative in relation to global auto-class solution. Working to get these info from respective stakeholders 3/10: Based on conversation among Cami and Jenny (FXE finance), we agreed to show it as a 100% enabler initiative with impacts as ‘0’ and the KPI laid out with target match rate of 60% for decision support. As recommended, after making the necessary updates in Wave, I will run this through Jenny and Brian Teepe before L3 submission 3/14: Reviewed the details with FXE finance (Brian Teepe), updated impacts tab to show implementation cost breakdowns. Finance showed go-ahead for L3 submission 4/3: Working with World Tariff team on plan for next set of verticals for model training and target completion this week. Prelimary review scheduled today or early tomorrow. After internal alignment, we will review with Pradip/Mark later this week for alignment from e-commerce perspective. Also this topic is being included as an agenda topic for auto-class O/D meeting on April 12th 4/13: FXS finance has not approved it at L3. We are working through putting the requested info and resubmit for L3. L3 estimated date is TBD for now 4/19: Discussions in progress with our stakeholders (Dataworks product team) in order to finalize ownership for a larger drive initiative of model commercialization that the current initiative will be linked to. This will take a few more weeks to level set on the ownership and next step which will drive the L3 submission of the current initiative 4/28: Received FXE finance approval for the initiative to be attached to the initiative. Ownership discussion is in progress and next alignment is scheduled tomorrow 5/2. From model build out perspective - need to discuss further with the World Tariff team if they have any change in plan and/or timelines for decision support. Per Thursday call, they are working on a POC with ShipStation and Faire commodity data 5/4: Ownership discussion for the new initiative of commercialization is in progress - DW product team to set up meeting next week with leadership from Marketing, DW, EC, World Tariff and 3rd party compatibles team for alignment and decision making. Working with World Tariff team to refine the milestones and add additional for next sets of verticals training/testing through the model (5/12) 5/12: Awaiting on Drive and Tech greenlight. DW team is working on providing access to WT to use the UI. DW/WT are wor | K: L5 | Completed | L5 | 2022-11-15 | 2025-11-28
Business w/ Tech Initiative: FICP - Enable Import / Global 3rd Party Pricing | 15347 | 9213 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Chris Burr, Mark Cockerell | On Track | ***Comments from 4/23*** **(Comments will no longer be updated weekly unless necessary)** LAC launched 14 countries in Apr’25; AMEA will be setup in early FY26. ***Comments from 9/26*** With successful CSR on 4/15, Import/G3P is now available in ePRS for US and CA. Approved for L4. One time implementation costs have been adjusted to a Small T-shirt size. Reporting to begin when May'24 data is complete. EU enabled 10 countries in ePRS on 7/1/24, 15 more to follow in Oct'24. LAC targeting Jan'25 and AMEA TBD. This was approved for L5 week of 9/9. ***Comments from 4/10*** L3 validated, go live (moneystep) on track for Monday, 4/15 ***Comments from 3/21*** Moved to L3 on 3/18, pending approvals ***Comments from 2/29*** Pricing has advised that Import/G3P pricing enablement in ePRS has been prioritized for Apr'24 CSR. This will be reflected as the L4 money step date. Milestones have been updated. Pending Finance review prior to submitting to L3 ***Comments from 1/4/24*** This has been prioritized above Short Term pricing in RMIC, but low confidence level for Apr'24 CL. Targeting to move forward with commercializing current Import/G3P net rates for US pilot. USI Marketing as approved of the strategy. Next step is to create a slide to share with Pricing and Marketing leadership for buy in (socialize week of 1/8 or 1/15). Also, the business case for ePRS enablement will be bolstered with OTB impacts. Note, the interim solution will help with some customers, but this is not the desired solution. ***Comments from 10/12*** Currently #5 for Apr'24, confidence level is medium at best. Reviewed with MD's week of 10/9, alternative options exist and will be reviewed the week of 10/16 ***Comments from 10/5*** Pricing will not allow Marketing to present our recommended approach at CORE the weekend of 10/9. Executive forum for review is TBD and will firm this up week of 10/9. ***Comments from 9/27*** Pricing has communicated that this has not been prioritized for Jan'24, so has been bumped to Apr'24. Various options to be assessed and will be socialized with leadership. Still pending feedback from TCH which was on 6/22 ***Next step is to take our options to Pricing CORE and MD and VP meetings, targeting week of Oct 9. Recommended approach is to move forward without a pop up message, with commercialize the current structure as a backup*** ***Comments from 7/27*** Currently ranked #8 RMIC priority for Jan'24. Milestones have been added, and validated with Nil Mishra in Pricing. Also, monthly Impacts have been added as well. Pricing will advise end of Jul'23 if this will be prioritized for Jan'24 or Apr'24, this will be a requirement for Apr'24 OTB strategy. KPI's need to be added. This was reviewed at TCH on 6/22. It was determined that it will move to the next steps of the TCH process, but has not been greenlit yet. Pricing will advise on 7/31 if this will be included with Jan'24 CSR. If not, other options will be reviewed ***Comments from 5/11*** Currently slotted at #7 for Jan'24 CSR, but still pending feedback if Oct'23 is still a possibility. Need to determine next steps for L3 and money step date. ***Comments from 4/27*** Pricing to provide feedback regarding CSR prioritization by 4/28. This will determine milestones. Currently slotted at #7 for Jan'24 CSR, pending discussion if CPEL will be required. Need to determine if we move forward with Jan'24 CSR as our money step date. ***Comments from 3/9*** Next steps include working with Finance, Pricing, and Corporate Strategy on the Business Case and Impacts. Specifically, this requires alignment and validation for market share gain, revenue, yields, and margins. | K: L5 | Completed | L5 | 2023-06-06 | 2024-04-19
Business Only Initiative: FICP - Migrate to a non-contractual product (Mains | 15365 | 9216 | Business Only Initiative | Commercial - International Parcel & E-Commerce | Commercial | Chris Burr, Mark Cockerell | On Track | ***Comments from 8/15*** **Comments will no longer be updated weekly unless necessary** Mainstreaming has been included with FICP dashboard and revenue is being reported out in Impacts tab. One time implementation costs reflect Small T-Shirt size. Validated for L5. Will continue to report out. Pricing program mainstreaming OM is 30% ***Comments 2/1/24*** FICP was officially mainstreamed on 1/22/24 and available in automation. Proof has been updated in the Attachments and moved to L4. Mark Mantaro has approved, pending DJ approval. ***Comments from 1/18/24*** Mainstreaming as been approved for L3 (Actions planned). Testing is underway for Pricing and Rating systems with 100% pass rate to date; automation testing was completed successfully in Sep'23. RMIC has approved for Jan'24 CSR, which is now January 22nd. Go-To-Sales materials are being created. Will move to L4 on 1/22, this will include screenshot of policy grid change and L5 date of 5/31. Working with Pricing on getting Mainstreaming Pricing program CHT info to be able to report for L5. Received the official 'Go' week of 1/15. ***Comments from 11/9 to move to L3*** Attachment added from David Murray that his team will be changing the policy grid to be effective 1/13/24. This is the only work that needs to be done, as IT testing has been completed. One time cost of $400K is very overstated. However, this will be indicated on the 'Impacts' tab, since that number aligns with a small t-shirt size. this was requested from Kendra. L4 date to be moved to 1/15/24, to align with Jan'24 CSR, as additional testing will be completed. Pending feedback from Pricing next week about what changes will be needed in systems for AMEA/LAC discount loads ***Comments from 9/27*** Assessment from various demand forums and PRT completion week of 5/22. Inputs will be populated for L3, targeting a money step date of Jan'24. **Testing has been completed and was successful. Feedback from Kendra is that once testing is completed, get confirmation that all is needed is a policy grid change; one time set up costs are a small t-shirt sizing. Waiting on email confirm from David Murray** ***Comments from 5/3*** Coming out of LPM on 5/1, and PARM on 5/2, there is a 3 hour ComPRT Analysis Workshop for Mainstreaming on 5/8. Next steps include t-shirt sizing assessment, and feedback from CEFS Demand Mgmt Review Session on 5/10 ***Comments from 4/27*** Coming out of CPEL on 3/29, Business and IT architects have started to assess of system impacts and high level milestones. Intake was submitted to Enterprise Platform for CPP assessment, and Lean Portfolio Management (LPM) meeting is scheduled for 5/1. Portfolio Architecture Review Meeting (PARM) for is scheduled for 5/2. Also, a PPM needs to be submitted. Finally, a business description template was sent to Pricing for assessment What is the purpose of the PRT PARM? The PRT Portfolio Architecture Review Meeting is for the Business and IT Architects assigned to an initiative to present the draft of the Portfolio Epic Context and Specification document and obtain the other PRT architects' input and feedback prior to Analysis phase. ***Comments from 4/13*** Business and IT Architects have been assigned, and kick off session with Global Marketing (Chris Burr - Business Owner) to start the assessment on the Commercial Impacts is scheduled for Friday 4/14. High level milestones to be determined by 4/28 ***Comments from 3/30*** Initiative was presented at CPEL on 3/29, Global Marketing will get an update on prioritization from Portfolio Operations Demand Shaping (David Murray's team) by April 21. ***Comments from 3/9*** Next steps include working with Finance and Corporate Strategy on the Business Case and Impacts. This will include refining our assumptions for modeling the margins. In addition, regional inputs are needed for yields and volume. Initiative will be presented at CPEL on 3/28 | K: L5 | Completed | L5 | 2023-08-01 | 2024-01-22
Business w/ Tech Initiative: Enhance Global Returns | 15366 | 9219 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Jamie W. Bailey, Mark Cockerell | On Track | Comments 4/22/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #8 in the Commercial PRT Backlog. Comments 4/20/2026 - #9219(#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #8in the Commercial PRT Backlog. 1. 30 day to 1 year expansion still in progress with testing 2. ETD testing and research - ability-tos 3. CA to US FRT plan Jan 2027 - Jamie following up on this possibility. Comments 4/15/2026 - #9219(#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #8in the Commercial PRT Backlog. Comments 4/8/2026 - #9219(#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #9 in the Commercial PRT Backlog. Comments 3/27/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #9 in the Commercial PRT Backlog. A. Managing the research of impacted systems for ETD capability. Reviewed with Ryan Ridgway on his impacts. Discussed returns being their own flow to Clearance. Meeting 3/27 with Brett Perry and Whitt Beretta to understand those flows with ETD and Clearance systems. Comments 3/16/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #10 in the Commercial PRT Backlog. Managing the research of impacted systems for ETD capability. Comments 3/9/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #10 in the Commercial PRT Backlog. Initial analysis complete for Automatino Dev impacts for introducing ETD. Meeting with Digital this week taught us that too many systems impacted for us to do a Local Enhancement. Scheduled a call with Shobha and Ryan Ridgway for March 20th to discuss the work needed for his team. Comments 3/2/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #11 in the Commercial PRT Backlog. Initial analysis complete for Automatino Dev impacts for introducing ETD. CSHP is a common impact for all customer facing automation platforms for confirming ETD validity. Comments 2/25/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #10 in the Commercial PRT Backlog. Init went to Digital Request Intake Triage where it was determined that another call would be needed. The request was to inform the team of ETD for MAGIC as a local enhancement request. Comments 2/16/2026 - Out of town this week. Comments 2/9/2026 - #9219 (#15366) – Enhance Global Returns (NRB $12.6M in FY26) – L2 – Awaiting PRT prioritization & architect engagement; currently ranked #8 in the Commercial PRT Backlog. Init will go back to L2 Commercial Triage meeting on 2/9 to determine if Epics can be broken off & ran separately. 1. Attending Commercial L2 triage call Monday 2/9 2. ETD pre-testing all automation platforms on Monday 2/9. Comments 1/19/2026 - #9219 Enhance Global Returns (NRB $12.6M in FY26) - L2 - Awaiting engagement of PRT Architect; #8 in PRT Priority. 1. ETD+Print Returns - continue with these in the requirements. next step: follow up with Joey to refresh data to support Print returns need with this feature. Print Return is very big with Healthcare. 2. Regional updates with CA - they are looking into the CA Boxless Returns concept. I am lining up comparison with the US Easy Returns model to determine if this should be local-only or built into the global roadmap. 3. EU readiness - planning for new resource to support 9219 from EU and reviewing GTM documen | E: L2 | Active | L2 & CCH | 2024-07-22 | 2027-02-05
Business w/ Tech Initiative: Banded Commit for Competitive Profitable Network | 15541 | 9243 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Chris Burr, Mark Cockerell | On Track | ***4/22/2026*** It was determined that MVP1 is a 'Go' on 3/18/26, and subsequently a new band was sent to GSAA for FICP US-CA (targeting May26 URSA load). Coming next will be IP TR-US. For CVM MVP2 features, PI 2 Planning is currently underway for 11 enchancements, targeting move to production 6/16/26. Additional enhancements for PI 3 and 4 planning are being assessed. ***Comments from 3/25/26*** CVM was moved to production on 2/19 to allow for additional testing in production environment and bugs are still being identified. It has been determined that MVP1 is a 'Go' and the next band has been sent to GSAA (FICP US-CA). For the pipeline, DUB-IND IPF was loaded with Mar'26 URSA. Next band will be IP TR-US. MVP2 requirements are currently being documented, targeting PI planning early Apr'26. Jun'26 is currently the L4 date. ***Comments from 3/11/26*** CVM UAT started on 1/12/26 and is still ongoing. CVM was moved to production on 2/19 to allow for additional testing in production environment with a focus on stability. Three critical defects have been documented and are currently being reviewed to determine MVP1 launch and timelines. Go/No-Call call is being targeted for 3/18. For the pipeline, DUB-IND IPF quoting faster was implemented for Mar'26 URSA load, and FICP US-CA is being assessed. Jun'26 is currently the L4 date. ***Comments from 3/4/26*** Commit Visualization and Modeling Tool (CVM) Use Cases 1-4 were delivered in FY26 H1. UAT started on 1/12/26 and is still ongoing. CVM was moved to production on 2/19 to allow for additional testing in production environment with a focus on stability. Three critical defects have been documented and are currently being reviewed to determine MVP1 launch and timelines. For the pipeline, DUB-IND IPF quoting faster was implemented for Mar'26 URSA load, and FICP US-CA is being assessed. Jun'26 is currently the L4 date. ***Comments from 2/25/26*** Commit Visualization and Modeling Tool (CVM) Use Cases 1-4 were delivered in FY26 H1. UAT started on 1/12/26 and is still ongoing. CVM was moved to production on 2/19 to allow for additional testing in production environment with a focus on stability. 14 critical defects have been documented and are currently being reviewed to determine MVP1 launch and timelines. For the pipeline, DUB-IND IPF quoting faster has been implemented for Mar'26 URSA load, and FICP US-CA is being assessed. Jun'26 is currently the L4 date. ***Comments from 2/18/26*** Commit Visualization and Modeling Tool (CVM) Use Cases 1-4 were delivered in FY26 H1. UAT started on 1/12/26 and is still ongoing. CVM will move to production the week of 2/17, to allow for for additional testing in prod environment with a focus on stability. Critical defects are being documented and will be reviewed with MD's during the week of 2/23 to determine MVP1 launch and timelines. For the pipeline, DUB-IND IPF quoting faster has been implemented for Mar'26 URSA load, and FICP US-CA is being assessed. Apr'26 is currently the L4 date. ***Comments from 2/11/26*** Commit Visualization and Modeling Tool (CVM) Use Cases 1-4 were delivered in FY26 H1. MVP1 launch is being targeted for Feb’26. UAT is underway with a two-week extension to allow for additional testing through 2/13/26. The recommended approach will be to extend testing for one more week, with full go live slated for the week of 2/23/26. For the pipeline, DUB-IND IPF quoting faster has been implemented for Mar'26 URSA load, and FICP US-CA is being assessed. Apr'26 is currently the L4 date. ***Comments from 1/28/26*** Commit Visualization and Modeling Tool (CVM) Use Cases 1 & 2 were delivered in Aug’25. Use Case 3 was delivered on 9/15/25 as expected, UC 4 has been delivered as well. MVP1 launch is being targeted for Feb’26. UAT is underway with a two week extension; Go/No-Go is set for 1/30/26. For the pipeline, DUB-IND IPF quoting faster has been implemented for Mar'26 URSA load, and FICP US-CA is being assessed. Apr'26 is currently t | G: L3 | Active | TEMP L3 - Enter L3 | 2023-05-23 | 2026-04-30
Business w/ Tech Initiative: EEI Filing Enhancements |  | 84577 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Cammie Berman, Venkat Prasath Sekar | On Track | 4/22/26: Still working toward a June 1, 2026 solutioning date; however, the business architect will be moving teams on May 1, 2026, which may cause delays in completing the PRT stage, originally due April 30, 2026. 4/15/26: Target post-peak launch is January 2027, with ongoing PRT decomposition and analysis working sessions for Epic 1, and a target to move to L3 (Solutioning) by June 1, 2026. 3/25/26: PI 03/Oct ’26 is at risk due to scope, complexity, resource constraints, and ongoing learnings, likely pushing launch to post-peak (Jan ’27), with mitigation-dependent potential for pre-peak delivery and added L3 delay risk due to unavailable RMIC resources. 3/11/26: EPIC 1 is the priority and should be completed and reviewed by the end of March. A two-hour work session is planned for 3/12. The project timeline will be discussed and approved on 3/11. 3/4/26: Working session for 3/5 on Capability #1: EEI Filing Not Required at Shipment Creation 2/25/26: Working session planned for 2/26 to P&C capability 2/18/26: Met with the team on 2/16/26 to discuss EPICS. Met again on 2/18/26 to ensure we have the requirements aligned for P&C 2/11/26: Two new capabilities have been added to the initiative: a P&C Ask and a Port of Export MAGIC fix. Epics are being created to separate capabilities that are ready for solutioning. A working session is planned for 2/12 to break out the epics. 1/21/26: Several working sessions are scheduled for the weeks of 1/12 and 1/19 to wrap up the Assess & Decomposition phase, with the goal of completing it during the week of 1/25 12/17/25: Request from APAC leadership to move quickly on this request 12/10/25: The architects met on 12/10. Would like to set up a few working sessions to review the document, gather any feedback, and begin having the IT architects work on the conceptual architecture 12/3/25: Business architects working on document 11/25/25:Business architects met on 11/24 to work on the document 11/19/25: Completed two work sessions on 11/17 and 11/18. Updated the change request to: “Allow for an ITN or FTR exemption on each CRN for an IPD shipment,” and confirmed the scope to include all products and all platforms 11/12/25: Worked with the SME and Operations to map out the PFS for IPD and EEI filing. Work sessions are scheduled for 11/13 and 11/14 to finalize process mapping 11/5/25: Met with architects, regulatory, and operations teams to better understand the EEI filing request with IPD; identified which systems are impacted by the re-keying issue 10/15/25: Work sessions are scheduled for 10/16 and 10/17 to learn more about IPD and the FedEx AgentFile tool 10/8/25: First work session rescheduled to 10/10 10/1/25: Kickoff call held on 9/25 with all architects and SMEs. First work session scheduled for 10/6. 9/17/25: Kickoff call scheduled for 9/25 9/10/25: Meeting with commercial business architect on 9/11 9/3/25: Meeting with Commercial Business Architect on 9/11ss Architect has been assigned, along with the SCO Business Architect, PISA, and Clearance SME. The Commercial Architect will be coordinating with all architects to restart the work 8/20/25: Still waiting on SCO Architect assignment and backlog number; Commercial architect moving teams - waiting for new assignment 8/13/25: Still waiting on SCO Architect assignment and backlog number 8/6/25:The Commercial and SCO Architect teams are working with Data & AI to assess solution status, identify gaps, and define what can be done in FY26 7/30/25: Still awaiting SCO Architect assignment; EEI REST API kickoff on 7/30 with Global-e testing solution 7/23/25: Business architect has identified an SCO architect is needed at this stage of the decomposition phase. There seems to be some confusion within the team, as SCO had assumed the architect would come from the Data & AI team. Need support in aligning on this. Data & AI pod has inputted their financials into Planview. 7/16/25: Kickoff call with Business Architect held on 7/10 to review roles and resp | E: L2 | Active | L2 & CCH - Feedback Requested
Business w/ Tech Initiative: OTB : Parcel Non-conveyable & Limited Quantity |  | 94177 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Iain Cairns | On Track | 3/19/2025 Requesting assistance from BA for Demand shaping for SL2 3/14/2025 Reviewed with Finace for L2 submission 3/5/2025 Completed L1 Commercial Triage / EA Architectural Review and submited for EPM review Working through Drive process | C: L1 | Cancelled | L1 Data Migration - TEMP
Business w/ Tech Initiative: Instant Scan uploads for OTB Shipments |  | 110081 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Daniella M. Dias | On Track | This will be included in initiative #9092 as incremental development | C: L1 | Cancelled | L1
Business w/ Tech Initiative: LSSI Quote Weekends |  | 130448 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Chris Burr, Mark Cockerell | On Track | **4/15/2026** SCO has been idenfified as the home porfolio, currently ranked #77 on Enterprise ranking. Revised business case to be reviewed with Finance. Presented to CPEL on 4/8/26, with an action item to review with the Marketing team and architects who support ZAXIS to assess International feasibility. After discussing with ZAXIS IO, international requirements will be built into the feature as well. **3/25/2026** SCO has been identified as the home portfolio, currently ranked #76 on Enterprise ranking. Business case to be revised to include IE for US IB and US-CA. To be reviewed at CPEL on 4/8 **2/25/2026** SCO has been identified as the home portfolio, currently ranked #76 on Enterprise ranking. Business case to be revised to include IE for US IB and US-CA. To be reviewed at CPEL on 3/25 **10/22/2025** This was approved for L2 on 9/2 and has been assigned to the Data & AI portfolio (not Commercial or SCO). This init went to Data & AI Triage on 10/8 and it was deemed D&AI is not the home portfolio. Currenlty working with SCO to see if that s the landing spot. Value Prop/ Customer Service Risk has been entered and targeting to move to L3 Jan'26 **9/3/2025** Approved for L2 on 9/2. Will align at pod meeting on 9/8 for next steps. Targeting 11/3 to move to SL3 **7/30/2025** Reviewed with Finance and will move to L2. Next steps for business case include further details on true incremental, as well as what surcharge revenue would be lost for those currently being selected for Saturday Delivery. **7/23/2025** Reviewed LBC with Finance on 7/22 and revised with requested updates. Pending Finance review and targeting to move to L2 week of 7/28 **7/16/2025** Still pending review from Finance, targeting to move to L2 week of 7/22 **7/9/2025** Will move to SL2 once Finance approves, targeting week of 7/14 **7/2/2025** L1 Architecture Alignment has been completed. Indentified Commercial, Data & AI, and SCO as impacted portfolios. Also estimated as a Medium t-shirt size. Targeting to move to SL2 week of 7/7 once checklist is completed and Finance reviews. **6/25/2025** Presented at EDM&G Triage on June 3; moved to L1. Currently working through Lean Business Case and Demand Shaping for L2. Pending Portfolio Architect review and then will establish timelines for L2. Currently no roadblocks while moving through the L1 process. | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: US-PR Enablement for FICP |  | 139955 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Cammie Berman, Venkat Prasath Sekar | On Track | 4/8/26: Leadership has decided to keep the initiative in Planview; however, no new weekly updates will be made, as this project is not currently a priority 3/25/26: A decision needs to be made on whether to cancel the DRIVE initiative 3/13/26: I’m hitting a wall on this initiative and don’t think I can find the data we’re looking for. Should we consider canceling it? 2/18/26: Met with Bella Villorente on 2/17 to review the IP and IE connection for PR. IP and IE use the same service code as a domestic product, so for US–PR moves, LSSI/URSA would use that code on the back end. For pricing, transitioning from package-level to shipment-level pricing was identified as a challenge. Bella recommended meeting with Kathy Sachs and Kari Collier to discuss the current connections and what would be required to support FICP. 2/11/26: Met with stakeholders on 2/10 to determine if we can move work forward to the ARTs. Leadership decided to review the IE documentation to assess the scope and work required for this initiative. We will meet in a few weeks to go over the findings. 1/21/26: Working to update the ask of the DRIVE initiative to determine T-shirt size and impacted portfolios. The current initiative will either be placed on hold with two local enhancements submitted, or fast-tracked 12/17/25: Making updates to the request based on CCH feedback. We will also have a discussion to determine whether this can be changed to a Local Enhancement. 12/10/25: Meeting with Finance on 12/11 to review the business case 12/3/25: Data is being pulled 11/25/25: Waiting on data pull 11/19/25: Asked Analytics to pull weight data for IE B2C shipments from US to PR 11/12/25: Met with Finance on 11/10 and received additional guidance to update the business case 11/5/25: Received US Virgin Islands FICP OM, cannibalization costs, and US-PR forecasts 10/15/25: Still working on updating the business case 10/8/25: Met with David Johannson on 10/8. To update the business case, need to find the US Virgin Islands FICP OM, assess the effects of cannibalization, gather any US-PR forecasts, and determine implementation costs. 10/1/25: Drive initiative entered into L2 on 10/1 9/17/25: L2 triage determined this will impact RMIC and possibly PCC in commercial; RMIC architect expressed concern about the amount of work required and recommended sizing as large; Architects also noted impacts SCO and Platform for configuration changes only; Attaching updated PowerPoint to files (PV -139955 - US-PR Enablement for FICP.pptx) was not given a new link 9/10/25: Working with Commercial Architects to finalize the conceptual solution design and redefine the t-shirt size; continuing to build the business case with new opportunities. 9/3/25: Still in "stop work" status. Requested a review of the L1 architecture documentation to determine if a smaller t-shirt size can be justified. Also asked if this initiative could be taken off Drive but was told it cannot. May need leadership support to advance to L2. Attended the Enterprise Services triage call and identified this would not impact Enterprise Services 9/2/25: Changed t-shirt size from XL to S. I won’t know how the company would like to proceed with the initiative until L2 weighs in. One alternative could involve a smaller t-shirt size. This change was made after consulting with ESPM 8/20/25: Submitted initiative for L1 approval but received a “stop work” response. I have updated the business case to present two possible solutions: a low-cost option of enabling US–PR in current systems, and a high-cost option of reclassifying PR across all FedEx internal systems. 8/13/25: Working with Finance for final approval of L1 LBC 8/6/25: Working with finance to create LBC 7/30/25: Working with finance to create LBC 7/23/25: Finance is pulling financials for the identified customers who would benefit from US-PR enablement. Finance suggested that this initiative may be a Business Only initiative. USI sales will send additional customers names | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Delivery PFS- Global Expansion |  | 143488 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Grant Heyman, Mark Cockerell | On Track | 10/29/25Working on alignment with regions and business case development | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Own The Border - Northbound Requirements |  | 157208 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Cristina A. Pallotta | On Track | In alignment with Enterprise Demand Management/Governance and Senior Leadership (CA Marketing & Global Products, Solutions and Business Agility), initiated change control process within existing Own The Border #9092 which reverted from L2 status to L2 in order to assign accurate resources/architects and prioritization to support. In result, Own The Border #9092 updated initiative including Northbound value requirements including missed requirements identified through business/L3 testing and end to end production test. Therefore, this seperate Planview enabler/dependency can be cancelled since request details are reflected in Own The Border #9092 instead. | C: L1 | Cancelled | L1
Business Only Initiative: IPE (2A) Geographical Expansion |  | 157276 | Business Only Initiative | Commercial - International Parcel & E-Commerce | Commercial | Maya A. Hayes, Anand Newadkar | On Track | After review from RMIC Lead (Cortney Gonzales) it has been determined that no IT work is needed to complete this project and recommended that it be canceled in Planview. Work will continue as Run the Business, with agreed upon pricing prioritization pathway for any pricing support needed. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Broker Select Option for IPD/IED for Americas |  | 157280 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Sreyoshi Bhattacharya, Meagan D. STONE | On Track | Focussing on developing higher-priority features of service in IPD/IED. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Pickup PFS Global Enhancements |  | 157285 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Jamie W. Bailey, Mark Cockerell | On Track | 3/16/2026 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and Regional partners working through requirements and objectives for US vs Global. Combined Roadmap with US/CA Pickup PFS and Global Pickup due April 1st. 12/15/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and REgional partners working through requirements and objectives for US vs Global. 12/7/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and REgional partners working through requirements and objectives for US vs Global. 11/30/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and REgional partners working through requirements and objectives for US vs Global. 11/15/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and REgional partners working through requirements and objectives for US vs Global. 11/7/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and REgional partners working through requirements and objectives for US vs Global. 11/1/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, and REgional partners working through requirements and objectives for US vs Global. 10/27/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, working through requirements and objectives for US vs Global. 10/20/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, working through requirements and objectives for US vs Global. 10/13/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, working through requirements and objectives for US vs Global. 10/6/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, working through requirements and objectives for US vs Global. 9/29/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, working through requirements and objectives for US vs Global. 9/21/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS US team, working through requirements and objectives for US vs Global. 9/15/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS team. 9/8/2025 - Developing our strategy and identifying key features for regional expansion of Pickup PFS. Meeting with Pickup PFS team planned for later this week. 9/3/2025 - Need Regional resources in order to build requirements, ability to's before creating Lean Business Case. 8/22/2025: Additional discussions needed with my Regional support team to know more about what this will be covering. Comments 8/15/2025: Submitted as an initial idea. Still need to form a team and come up with the full details for this initiative. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: IG BSO Importer of Record Name Issue |  | 179932 | Business w/ Tech Initiative | Commercial - International Parcel & E-Commerce | Commercial | Raul Cardenas | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [Max Cap/Util of Footprint]: Zero Package Notifica | 28168 | 6725 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Valerie McCoy, Jamie Heath | On Track | 6/10/25: * As of6/6//25, have saved $48.51K in non-productive Ground stops, June 2025 forecast was $242K 5/31/25: * As of 5/31/25, have saved $202.1K in non-productive Ground stops, May 2025 forecast was $276.9K * Total Savings for FY25 is $3.03M 5/27/25: * As of 5/23/25, have saved $166.56K in non-productive Ground stops, May 2025 forecast is $276.9K * 5/19/25: * As of 5/16/25, have saved $115.7K in non-productive Ground stops, May 2025 forecast is $276.9K * April actuals have been entered into Planview 5/12/25: * As of 4/30/25, have saved $237.3K in non-productive Ground stops, April 2025 forecast is $267.4K * As of 5/9/25, have saved $65.2K in non-productive Ground stops, May 2025 forecast is $276.9K 4/28/25: * As of 4/25/25, have saved $200.2K in non-productive Ground stops, April 2025 forecast is $267.4K 4/21/25: * As of 4/18/25, have saved $146.7K in non-productive Ground stops, April 2025 forecast is $267.4K 4/14/25: * As of 4/11/25, have saved $95.9K in non-productive Ground stops, April 2025 forecast is $267.4K 4/7/25: * As of 4/4/25, have saved $42.0K in non-productive Ground stops, April 2025 forecast is $267.4K * As of 3/31/25, have saved $241.8K in non-productive Ground stops, March 2025 forecast is $313K. 3/31/25: * FY25 baseline and FY28 NRB has been updated - per Megan and Amy Fletcher, only needed to update FY26 and FY27 Forecast since have been in L5 5+ months. I did go to update the KPI's, but the KPI's are based on % of pickup cancellations for the year for each month, so left them as is for FY26 and FY27. * As of 3/28/25, have saved $231.4K in non-productive Ground stops, March 2025 forecast is $313K. 3/15/25: * Updated the FY26 and FY27 Forecast (since have been in L5 for almost 6 months), under the direction of Megan Lightford and Amy Fletcher. I did go to update the KPI's, but the KPI's are based on % of pickup cancellations for the year for each month, so left them as is for FY26 and FY27. * As of 3/21/25, have saved $174.1K in non-productive Ground stops, March 2025 forecast is $313K. 3/17/25: * As of 3/14/25, have saved $114.8K in non-productive Ground stops, March 2025 forecast is $313K. 3/10/25: * As of 3/7/25, have saved $57.8K in non-productive Ground stops, March 2025 forecast is $313K. 3/3/25: * As of 2/2825, have saved $242.5K in non-productive Ground stops, Feb. 2025 forecast is $356.5K. 2/17/25: * As of 2/21/25, have saved $182.2K in non-productive Ground stops, Feb. 2025 forecast is $356.5K. 2/17/25: * As of 2/14/25, have saved $120.1K in non-productive Ground stops, Feb. 2025 forecast is $356.5K. 2/10/25: * As of 2/7/25, have saved $58.7K in non-productive Ground stops, Feb. 2025 forecast is $356.5K. 2/3/55: * For Jan. 2025, have saved $244.3K in non-productive Ground stops, forecast was $253K for Jan., so there was a -3.4% difference. Revised forecast for FY25 savings is $3.3M. * 173 OnSite locations had FXG ZPN disabled on 1/31, as they will be part of station optimization on 2/3 1/27/25: * For Jan. 2025, as of Jan. 25, have saved $185,5K in non-productive Ground stops, forecast is $253K for Jan. * 173 OnSite locations will have FXG ZPN disabled on 1/31, as they will be part of station optimization on 2/3 1/13/25: * For Jan. 2025, as of Jan. 10 have saved $65.2K, forecast is $253K for Jan. * 173 OnSite locations will have FXG ZPN disabled on 1/31, as they will be part of station optimization on 2/3 1/6/25: * Updated Planview Financial Actuals and KPI for December'24 to reflect $233k in savings (Forecast was $249K) 12/31/24: * For Dec. 2024, as of Dec. 27 have saved $211K, forecast is $249K for Dec. 12/23/24: * For Dec. 2024, as of Dec. 20 have saved $166K, forecast is $249K for Dec. 12/16/24: * For Dec. 2024, as of Dec. 13 have saved $111.6K, forecast is $249K for Dec. 12/12/24: * For Dec. 2024, as of Dec. 7 have saved $54.3K, forecast is $249K for Dec. 12/2/2024: * For Nov. 2024, a total savings of $230.4K was realize | K: L5 | Completed | L5 | 2024-01-30 | 2024-03-29
Business w/ Tech Initiative: Staples Retail Alliance Shipping Integration | 88556 | 6764 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Ashley Clark, Jamie Heath | On Track | Retail expansion exploration with Staples is on hold until Staples is able to provide documentation in writing they have overcome the exclusivity obstacle that caused the 2024 negotiation to end. Expectation is for sold, hold, drop off & returns services to be available to FedEx. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-08-20 | 2024-10-17
Business w/ Tech Initiative: [Retail PFS] FedEx Unified Experience Label | 68301 | 6765 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Edward Barchak, Jamie Heath | On Track | 5.12.25 Update financial with April actuals and uploaded new input template with April Actuals. *Note: With the CSR Load that occurred late night on April 12th, IT had to update the configurations that allow / disallow certain label prints at certain locations / applications. During this update, the configuration setting for ONSITE WAG was inadvertintly updated to its "pre FUEL Lite" enablement setting to allow only FRT label prints. This caused the decrease in label print requests during the highlighted weeks above. The fix was implemented on the night of April 24th. 4/17.25 Updated financials with March actuals and ssubmitted to L5. 3.28.25 FY25 baseline and FY28 NRB has been updated. In the process of determining feasablity of changing value type to Customer Experience. 1.20.25 Submitting to SL4 with updated forecast. 1.14.25 Uploaded the actual label creation to the Content "FUEL Lite Weekly Trend 20250107 (1).pptx" Reforecast the business case and uploaded the new Input file, "Input template - FUEL FY24 v8.xlsx" Sent email to Amy Fletcher for review. ________ Walgreens launching to 499 location on 11.25.2024 Chainwide by 11.8.2024 Updated business case and NRB based on finance margin and yield Preparing for SL3 in Planview Working on data for reporting on label requests | K: L5 | Completed | L5 | 2024-06-18 | 2025-01-01
Business Only Initiative: Refined F1R at FXO Pilot | 48802 | 6976 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Jamie Heath, Chris Werner | On Track | Placing on hold. February 28, 2024 Now that the RMC has approved a national rollout, we'll start the following discussions with leads in preparation for the national rollout. -Process to move pricing from interline to regular the regular POS process -Possible updates to pilot FXO talking tracks -Volume performance tracking -Marketing plans -Rollout process Management will also provide guidance regarding managing the program in Wave/etc. February 7, 2024 - The project's weekly ADV continues to grow. As of February 2, for the Dallas market, the ADV/location was 6.5 and 6.3 for Chicago. - The team continues to see more consumers using the offering than businesses. (92% in Dallas and 87% in Chicago) - The ADS team is updating the weekly dashboard to show how the program is tracking towards the 50% incremental volume growth. January 11, 2024 * F1R Pilot volume to date: 21,538 (Dallas) (49% boxes) and 23,436 (Chicago) (49% boxes) * Dallas market ADV = 582; ADV/store = 6.5 * Chicago market ADV = 633; ADV/store = 6.4 * Team preparing for mid-Feb. RMC update on performance where the team will provide recommends for the pilot. * Similar market FXE Sold ADV is -10% YOY, total US FXE Sold is -13% YOY, 20% YOY for Dallas, and 9% YOY for Chicago (Similar markets ADV includes average for New York, LA, DC, and Miami) January 3, 2024 •F1R Pilot volume to date: 19,000 (Dallas) (49% boxes) and 20,937 (Chicago) (49% boxes)* •Dallas market ADV = 576; ADV/store = 6.4 •Chicago market ADV = 634; ADV/store = 6.4 •Finance (Ben Sauls and Megan Lightford) now involved to assist team with determining profit neutral volume needed for pilot. *Incremental to be determined during midpoint analysis December 29, 2023 •Program continues to perform positively in both markets; full market recommendation to be shared end of January. •F1R Pilot volume to date: 16,843 (Dallas) (49% boxes) and 18,633 (Chicago) (49% boxes)* •Dallas market ADV = 581; ADV/store = 6.5 •Chicago market ADV = 643; ADV/store = 6.5 •Week of December 17, both markets saw a 24% YOY increase in SOLD volume. *Incremental to be determined during midpoint analysis **December 13, 2023** The incremental volume gained from the F1R Pilot continues to increase. The program’s first email was released Dec. 11 to 844K targets. (Breakdowns below) The email highlights the program’s clear and simple pricing for two-day shipping anywhere in the U.S. starting at $9.50. It also mentions the convenience of longer store hours with FXO, which are generally open later than USPS. The two subject lines being tested are “Flat rates. Shorter Lines. Longer store hours.” and “Two-day, flat-rate shipping as low as $9.50.” **Email distribution breakouts** 770K FDM enrollees: non-account holders OR micro customers who have subscribed to FDM communications. 74K Non- FDM enrollees: consumers + non-account holders in the FXO zip area, who have subscribed to receive FXS promotion emails and have opened other FXS emails in last 12 months. 168 Micro customers: email list mapped to the EANs from the FDM & Non-FDM lists. **Email address counts by market** Chicago: 404,576 (3.3K are micro shippers) Dallas: 439,435 (4.5K are micro shippers) **Performance to date: (November 12 - December 9) (90 stores)** Dallas: 7,654 incremental volume; ADV = 403; ADV/location = 4.5; Pkging type used = 46% Box Chicago: 9,126 incremental volume; ADV = 480; ADV/location = 4.9; Pkging type used = 45% Box **December 6, 2023** A bag stuffer to support the program was released Dec 1. The team is also preparing to release the first program email on Dec 11 to 800-900K potential customers. (non-account holders, FDM enrollees, and Dallas micro-shippers) The FXO CEO Letter included another F1R update this week; it focused on marketing collateral created to support the pilot. Performance to date shows that the market without paid media (Chicago), is outperforming the Dallas market which | E: L2 | On Hold | L2 & CCH | 2023-11-01 | 2024-04-15
Business Only Initiative: [Max Cap/Util of Footprint]: FY24 Contribute to an | 23705 | 7619 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Valerie McCoy, Jessica Millsaps |  | This initiative is being tracked by a Steercom for Retail n2.0. 5/15/24: * Placement Strategy / N2.0 Steercom held on 5/14, team is proceeding to work on Action items 5/8/24: * FORGE app reporting issues still present, it appears that FXE RTH packages associated with a LocID at Retail locations will be resolved in June 2024, whereas IT is advising us Pre-Peak 2024 for the FXE customer drop off packages. Valerie has escalated to Chris for further support since FORGE app continues to be deployed to FXE standalone stations with 69 stations targeted by end of June, and remainder by March 2025. * 5/1/24: * Planning for May 14 Steercom * Updating information to accurately reflect number of locations impacted in FY25 * Continuing to work with extended team to understand and resolve issues * Alignment with Taylor Prakash's team on gaps needing resolution, and to work on Retail gaps tracking accuracy 4/17/24: * Held Steercom for N2.0, beginning work on May 14 Steercom * Continuing work on reported issues 4/10/24: •Team is preparing for the Placement Strategy N2.0 Steercom on 4/15 * Transformation Office recommends removing from DRIVE, as there is now a monthly Steercom meeting. 4/3/24: * Yuchen and Priyanshi from ADS have completed the KPI data for L3 submittal, Megan has reviewed and is asking if we need to breakdown baseline data by quarter, to match how we are reporting monthly, Jane is checking with TO on this. * N2.0 team is working with Placement Strategy team for 4/15 Steercom update * Work continues to research RCPA and OnSite scan compliance issues 3/28/24: * Work continues on entering into L3, ADS has supplied KPI data, Yuchen and Valerie have reviewed together, and Yuchen is making a few tweaks 3/20/24: * Multiple meetings (Retail, McKinsey, ADS) and emails on how to setup KPI's, ADS is now working on completing information * Placement / N2.0 Steercom deck sent to Steercom on 3/18, next Steercom is 4/15 3/13/24: * Work continues with ADS, McKinsey, and Finance on how to measure and track KPI, so that we can submit to L3 3/6/24: * Continued work with ADS on KPI measurement and tracking 2/29/24: * Updated Placement N2.0 Steercom on FY25 locations status, next steercom is 3/20 * Met with Jane, Ajaz & Yuchen, and Megan about potential KPI's to enter into WAVE to proceed to L3, further discussion needed between all parties * Anticipate receiving additional FY25 locations in April 2/21/24: * FY25 updated list of impacted stations under review, will submit new Initiative for these locations * Team to provide detailed update during 2/27 Placement Strategy / N2.0 Steercom meeting * Focus for past week has been on retail discrepancies. Two defects have been resolved to date; one network wide, other will be cover impacted stations by 3/3 * Other issue under review still (i.e. If FXO commissions impacted, RCPA payouts) 2/15/24: * Alignment with Jane at McKinsey for planning how to submit to L3 * Work continues on reporting challenges related to closed FSCs and net new FSC locations at CSSPs * Received list for remainder of CY24, and a few locations in Feb / March 25 - (currently under review by counter team, including FXO Real Estate) 2/8/24: * Retail reporting discrepancies still being researched, one already resolved by ADS * Partial FY25 list received end of day yesterday, Jessica is currently assessing * Will work with new McKinsey lead and Finance on L3 submittal 1/31/24: * Retail Reporting discrepancies being researched * Anticipate receiving N2.0 CY24 schedule by end of this week. First new launches in CY24 will be 9/2/24, with launches in Sept / Oct / Nov 2024 * Advised that there will be an exclusively courier workforce to support same day on call, healthcare, DG, and FO shipments 1/24/24: * Expect to hear decisions made by Executive Committee regarding N2.0 rollout by end of this week * Submitted updated capital ask information to Aimee (and Brian Phillips) for his | E: L2 | Cancelled | L2 & CCH
Business Only Initiative: [Grow E-comm]: FER w/ Blue Yonder | 27270 | 7842 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Chris Slivinsky, Shawn Taxter | On Track | 11/12/25 - Updated OCT actuals to $0. Anticipating first FER revenue capture in NOV 2025. 10/23/25 - Proof of Money Step (screen pic of FER on fedex.com) provided on 10/13. Initiative now in SL4 and with DJ Miller for approval. 11/4 FER in-person (Plano, TX) business review meeting scheduled with Blue Yonder and FXO Ops; meeting focused on pipeline activity, merchant migration and revenue capture. 10/08/2025 - Missed initial L4 date due to extended SL3 approval. Updated actuals for JUN, JUL, AUG and SEP. 7/24/25 - Review responses with leadership, then submit to next step. A. Schuler Domain QA Expert Review 02/06/25 Weekly POD Update As a result of recent FedEx Returns Technology 2.0 scheduling changes, the FedEx Easy Returns launch has pushed out from April to June 2025. 01/16/25 Weekly POD Update On 1/9/25 DHL (press release) announced their acquisition of Inmar Supply Chain Solutions. FedEx is contracted with Inmar Post Purchase Solutions for the solution FedEx Easy Returns. Leadership is aware of this news and the path forward is to continue with FedEx Easy Returns as planned. 01/09/25 Weekly POD Update Meeting with FXO finance on 1/10 to continue discussion (from pre-holiday break) for "all shoes" merchants financials. FXO finance is also currently working on a secondary financial assessment assuming use of 3 Inmar sort facilities vs. (current) 5 facilities. Finalization of the business case, in prep for L3 submission, pending results of these two financial activities that will roll into next week. 12/12/24 Weekly POD Update Good news: The FedEx and Inmar agreement is fully executed! Go-to sales materials are being updated (from FCR to FER). Submitting a Project Mangement Plan early next week to determine go-to-market activites including creation of a video. Next: initiaitve activities to be adjusted as go-to-market plan forms; to reconnect with FXO finance to finalize all shoes merchants (10% of forecast) financials to update business case. 11/21/24 Weekly POD Update Making final adjustments to FedEx and Inmar Agreement this week in prep for signatures. FedEx and Inmar IT in-person (Plano) meetings 11/20 and 11/21 to align on FedEx and Inmar integration plan In prep for IT development to begin post executed agreement. 11/7/24 Weekly POD Update Reviewing revised all shoe merchant financials with FXO finance on 11/6 to determine profitability in $6 - $7 range. Pricing structure (shoe and apparel merchants vs. small/medium/large merchants) tbd before finalizing first 12 months forecast, FY25 forecast (APR, MAY), DRIVE business case and submitting for L3. New product name "FedEx Easy Returns" is brand and legal approved. 10/3/24 Weekly POD Update Active negotiations in progress on the contract with Inmar. Discussions on how to treat 3rd party platforms in progress as well in order to help scale volumes once solution is live. Targeting post peak go-live. 09/19/24 Weekly POD Update Meeting with finance on 9/19 to adjust floor price for all shoes merchant before updating FY25 forecast in business case and Wave. 09/11/24 Weekly POD Update Adjusting apparel/shoe mix in business case from 85%/15% apparel/shoes to 90%/10% to more accurately align with market conditions. Updating financials this week, including pricing for all shoes merchants, to update business case. 09/06/24 Weekly POD Update Revised business case FY25 forecast with 85/15 apparel/shoe merchant mix; to review forecast with Megan Butler on 9/5. 08/22/24 Weekly POD Update To revise business case FY25 forecast and WAVE portal inclusive of 15% all shoes merchants, and recently revised Inmar retail cost, for next week. 08/15/24 Weekly POD Update Filtered FCR 1.0 completed merchant qualification checklists to determine merchant mix of 85% "apparel" merchants and 15% "all shoes" merchants. Finance to provide price per RMA for all shoes merchant, marketing to revise business case and WAVE portal inclusive of 15% all shoes merchants for next week. 08/08/2 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-01 | 2025-11-14
Business w/ Tech Initiative: Implement Customer Service Tracking Tools (Print) | 96690 | 7846 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Shea Morrow | Some Issues | 7/17/25 Cancelling initiative due to the following: Team has been able to improve cusotmer service through building of relationships, additional training/knowledge transfer, and well documented processes. Now that the new CE Desktop has launched, the CE organization will work within their structure to request any additional requirements needed to support customer service for Print. Cancellation was approved by the Retail Print & Returns POD. 7/16/25 No change 7/9/25 No change 7/2/25 No change 6/25/25 No change 6/18/25 No change 6/11/25 No change 6/4/25 No change 5/28/25 No change 5/21/25 No change 5/14/25 No change 5/7/25 No change 4/30/25 No change 4/24/25 Moved to L2, CCH tab completed 4/16 No change - awaiting approval to move to L2, submitted 3/26 4/9/25 No chnage 3/31/25 FY25 baseline and FY28 NRB has been updated - they are zero as there are no hard benefits 3/26/25 Attached required architecture documentation and submitted for review to move to L2 3/19/25 Attended Commercial EA Triaging Meeting on 3/17; EA advised that this initiative would need to go to PRT based on its prioritization (currently 366), but that the lack of hard value will be a challenge for receiving prioritization at any time. Shea to address in the 3/20 pod meeting to see if leadership has any recommendations on how to move forward this initiative, which will improve the customer experience. 3/12/25 Fields previously not mandatory were made mandatory without any communication to IO; completed fields and discussed architecture needs . Will follow up before next week's update 3/5/25 No change 2/26/25 No change 2/19/25 No change 2/12/25 No change 2/5/25 No change; initiative is #346 in line, so I do not expect any progress - should it be cancelled? 1/29/25 No change 1/22/25 Initiative waiting for Commercial review before it can move forward. 1/15/25 Having difficulty getting architecture documentation in the required format and therefore cannot submit to move forward. 1/8/25 Waiting for architects to put architecture docs that were previously supplied into the desired format for review. | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: Dye Sub Omni-Channel (FXO) | 90495 | 8335 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | AARON LEVINSON, Kayla Donner | On Track | 2023/04/22: No new updates. Cumulative dye sub eComm revenue MTD is at 105% of forecast. 2026/04/17: No new updates 2026/04/07: March actuals have been entered. March sales delivered 167% of forecast, putting cumulative revenue at 112% of forecast launch-to-date. eCommerce transactions are at 23.28% of all dye sub transactions (vs. 20% goal). Refunds remain well below the 5% max, finishing the month at 1.56%. Dye Sub FUSE development may be delayed as system architecture concerns have been raised. Digital Platforms is working with IT to confirm the possible impact to our timeline. 2026/04/01: March final revenue is a few days away, but currently, eComm revenue sits at 112% of the cumulative forecast. 2026/03/25: eComm revenue is currently at 109% of the cumulative forecast and 8' table throws were enabled earlier this week, bringing additional opportunities for eComm revenue capture. No new updates on FUSE development. 2026/03/18: eComm revenue is currently at 103% of the cumulative forecast. No new updates on FUSE development. 2026/03/11: eComm revenue has surpassed the forecast and is currently at 101% of the cumulative forecast! No new updates on FUSE development. 2026/03/02: February actuals have been entered. February sales delivered 133% of forecast, putting cumulative revenue at 99% of forecast launch-to-date. eComm transactions are at 21.36% (above 20% goal). Refunds are at 1.46% (vs. goal to stay below 5%). 2026/02/26: FUSE development has been pushed back to 6/2. 2026/02/25: No new updates this week. Dye sub eComm revenue continues to climb and get closer and closer to 100% of forecast despite the 6-month release delay. Month end numbers will be recorded early next week. 2026/02/18: No signficant updates this week. FUSE development remains on track. 2026/02/11: January actuals have been entered. January sales delivered 105% of forecast, putting cumulative revenue at 93% of forecast launch-to-date. eCommerce transactions are at 19.96% of all dye sub transactions (vs. 20% goal). Refunds are at 1.51% (vs. goal to stay below 5%). 2026/02/04: Dye sub in FUSE development remains on track. Preliminary January eComm performance exceeded forecast and eComm revenue is at 93% of forecast launch-to-date. 2026/01/28: No significant development updates this week. Revenue forecast for remainder of year has been updated to reflect revenue shortfall to ensure that the FY target remains the same. 2026/01/21: No significant updates this week. 2026/01/12: Based on updates from the PI 26.01 planning, the updated pilot for Dye Sub in FUSE has been pushed back from 2/27 to 3/31. 2026/01/05: December actuals have been entered. Revenue performance is at 89% of forecast through the end of December. eCommerce transactions are at 18.9% of all dye sub transactions (vs. 20% goal). Refunds are at 1.61% (vs. goal to stay below 5%). 2025/12/31: No significant updates this week. 2025/12/24: No significant updates this week. 2025/12/17: Received word that development resources are being pulled to support an Enterprise project, delaying other work until that is complete. Current estimated impact is a one month delay, so the money step deliverable is being moved out to 3/31. 2025/12/10: FUSE support for dye sub remains in development. No major updates this week. 2025/12/3: November actuals have been entered. Revenue performance is at 85% of forecast through the end of November. eCommerce transactions are 18% of all dye sub transactions (vs. 20% goal). Refunds are at 1.66% with the goal to stay below 5%. One epic (E-311595) within this Init is still in progress to support omnichannel/FUSE dev. Init currently showing late for L4, we will move Money Step to 2/27 to allow for FUSE work to be completed and adjust Init name/description to reflect the complete omnichannel development effort. No change to forecast or IT scope from initial plan. 2025/11/28: Fix was put into production and all product types were able to be migrated to the | G: L3 | Active | TEMP L3 - Enter L3 | 2024-11-06 | 2026-07-13
Business Only Initiative: Amazon Consolidated Returns | 35456 | 8396 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Shawn Taxter, Joe Kilgore | Attention Needed | 11/7/25 This is an old Initiative that has been replaced with an new Amazon initiative Week of 3/11 Initiative has been put on indefinite hold, pending a larger engagement with FedEx. No tentative timelines to share for when/if the project will move to L4. Week of 3/4 Contract pending. Infosec language was accepted; Amazon team has updated the agreement and is reviewing internally. Response expected soon to discuss next steps. Will determine Phase 1 launch, etc. once contract is executed. Week of 2/26 Contract pending. Infosec language was accepted; Amazon team has updated the agreement and is reviewing internally. Response expected soon to discuss next steps. Will determine Phase 1 launch, etc. once contract is executed. Week of 2/19 Contract pending. Infosec language was accepted; Amazon team has updated the agreement and will review internally. Response expected this week to align on next steps. Week of 2/12 Contract pending (Infosec alignment). Amazon Infosec team reviewing most recent redline. Response TBD. Week of 2/5 Contract pending (Infosec alignment). Amazon Infosec team reviewing most recent redline. Response TBD. Week of 1/29 Contract pending (Infosec alignment). Amazon Infosec team reviewing most recent redline. Response expected by EOD 1/31. Week of 1/22 Contract still pending (Infosec alignment). AMZ leadership teams to meet 1/22 to discuss mutual path forward. AMZ currently reviewing most recent redline. Response expected this week. Week of 1/15 Contract still pending (Infosec alignment). Teams meeting this week to discuss a path forward. Dave Morales will present to RMC 1/18. Week of 1/8 No change from previous week. Week of 1/1 Contract still pending alignment on Infosec language. Also aligning on a joint PR strategy. No further updates as of 1/4/24. Week of 12/18 Contract is pending alignment on Infosec language. Also aligning on a joint PR strategy. No updates as of 12/19. Week of 12/11 Contract is still pending. Phase 1 launch is pushed to mid-January, pending contract execution. Infosec and outlining a joint PR strategy are the topics being resolved. Week of 12/4 Contract is still pending. Both parties working to finalize language for contract execution. Meetings are scheduled 12/7 and 12/8 to discuss/resolve open items. Week of 11/27 Contract is pending. Amazon is reviewing internally and plans to provide a response by 12/4. FedEx Infosec is still reviewing Amazon Infosec appendix. Modifications could potentially delay completion and signing of the agreement. FXO targeting launch on 12/11. Phase 1 will launch post-peak if 12/11 date is missed. 11/30 - Approved for L3 submission Week of 11/13 Continuing to work through contracting, Expecting Amazon response to redlines by 11/20. FXO EDI setup is still in progress. Updating business case in preparation to submit to L3. Plan to share with finance for review by 11/21. Week of 11/6 Continuing to work through contracting. Targeting 11/9 to share FedEx redlines with Amazon. Amazon projects approx. 1 week to review and respond to FedEx redlines. FXO EDI setup is still in progress. Finalizing KPIs and milestones in preparation for submission to L3. Week of 10/30 L2 approval received. Meeting invite sent for week of 11/6 to discuss KPIs and other L3 checklist items. Final IT features required for launch deployed on 10/29, testing is in progress. Contract negotiations and EDI discussions are still ongoing. Week of 10/24 Received approval from Ground Finance that is required for L3. No change in contract status or EDI discussions from previous week. IT dev feature deployed 10/22. Prod testing is ongoing. Week of 10/16 Meeting with AMZ on 10/20 to continue contract discussions. Liability for lost items continues to be a key concern for both sides. IT dev feature to include AMZ Facility ID in API pass will deploy on 10/22. Will conduct more end-to-end testing on 10/23. EDI discussions are ongoing. Revised Phase 1 launch dat | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-09-12 | 2024-12-06
Business Only Initiative: Retail Competitive Product Positioning at Office D | 71923 | 9321 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Jaime Cunningham, Ashley Clark | On Track | 2/12/25 - On hold due to Pitney development costs required to build FGE into the Office Depot automation platform. 2/22/24- Discussed next steps with Jane, with the margin opportunities for F1R vs FGE coupled with the expense for integration into POS, we are looking at what the potential impact would be to utilize the F1R product instead of FGE to compete at the counter. For this, price comparisons and cost analysis would have to be done with price ceiling calculations. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Non-Traditional FASC Format Expansion | 38065 | 9322 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Shari Jones, Ashley Clark | On Track | 4/23/2026 - Initiative no longer needed at this time. 2/12/25 - On hold - awaiting alignment on plans forward. 2/15/2024 - The second deployment of the survey was deployed on 2/15. Next step is to ask our Partners to send the survey to new stores owners in order to increase participation. 2/7/2024 - The onboarding experience survey will be deployed on 2/8. This survey was sent to targeted FASC locations to gain customer insight on our current experience, type of resources needed, and determine if cost is a factor on hardware and software when starting a new location. 1/24/2024 - No new updates this week. In progress. 1/18/2024 - In progress. Next step is to discuss approach for a new or additonal Provider at non-traditional exisiting locations. 1/10/24 - Survey to targeted FASC locations is scheduled to deploy on 2/8. The survey will also be included in the 1/29 edition of ShipSource. Confirmed Provider used in UPS rural locations is exclusive to UPS. 12/14/23 - In progress. Next step is to connect with Provider to gauge interest in working with FedEx. 12/7/23 - Meeting held with CSP Lead to discuss the process to become a certified provider and timeline. 11/30/23 - Discussions on shifting from the "how" to "where" to place Non-traditional FASCs. 11/20/23 - Reviewed survey draft and requested intake form for Salesforce projects. The requested date for survey deployment is 1/10/24. Working on outlining the possible role and responsibilities needed by a Representative to support the non-traditional formats. 11/8/23 - Meeting scheduled for 11/10 to review survey draft. The next step is to submit the survey to Legal for approval and secure a date for Salesforce deployment. 10/19/23 - Reviewed the quotes for automation and cost to support per location. 10/11/23 - Received quotes for automation. Next step is the review the quotes and work on putting a technology package with cost per location. 10/4/2023 - Work in progress. Convention feedback about FASC program benefits/onboarding from new Store Owners. 9/29/23 - Met with CSP Lead to answer additional questions about the request so the providers can continue to scope the project. The next step is to follow up and finalize the software portion. I was also granted access to our survey tool and working with SalesForce to block a date to send the survey. 9/21/23 - Survey questions for targeted FASCs finalized. Next step is to submit for Brand and Legal approval and request a date for SalesForce deployment. 9/14/23 - Meeting held with the CSP Lead on September 13th to discuss technology options and cost for FASC locations. The CSP Lead will reach out to software providers for a quote per location and bulk rate. The next step is to reach out to the FedEx Technology Incentive Program (Ftip) or Sales to discuss cost for printers and scanners. 9/7/23 - Meeting scheduled with the CSP Lead for September 13th to discuss technology package options and cost for FASC locations. Crafting survey questions to send to existing FASC locations. 8/31/23 - Two key areas underway. 1) Customer Experience: Survey existing rural, new, and pilot FASC locations to find out what would be an idea start up package for a non traditional format. Also consider a Focus Group with FASC Store Owners to gather more detailed information if needed. 2) Automation: Conduct a brainstorming session to discuss technology package options and cost. 8/24/23 - Submitted for L1 to Aimee and awaiting approval. Referencing work on process to identify locations, approach, onboarding, and support. f | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Returns Technology (FRT) 2.0 Rewrite | 17556 | 9360 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Joe Kilgore, Prabesh Pudasain | On Track | 7/15/25: * FedEx Office (FXO) RMA processing capabilities pushed to production for in-store pilot test in FXO Region 39 - 7/13 * Dev team is collecting user feedback to identify defects and other opportunities for improvements * Dev team is actively working high-priority defects to prepare for General Release (GR), currently scheduled for 7/27 * Team will then prioritize updates and lower-priority defects for future iterations * FUSE team also implemented the new FRT 2.0 getFormattedLabel API; enables stores to print label-only returns direct from FUSE (no need to log into FRT) * FUSE has been using older API version; new API allows FRT to track the specific location which received the return to improve RMA data reporting * End of Q1-beginning Q2 (FY26) teams will begin migrating existing retailers from using Legacy to 2.0 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-01 | 2027-03-22
Business w/ Tech Initiative: Parcel Management Enhancements in FUSE | 91056 | 9380 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Andrew Halligan, Kayla Donner | On Track | 01/15/2026: Continued work on the initiative with a 2/14 release planned for Charge Slip Creation. NYOY growth for storage fees for December was 88%, and January MTD is 54.4% NYOY growth in storage fees since the feature was implemented EOM November. 01/07/2026: Updated financials to incorporate the new business case financials provided in December. This change is based on moving the money step out and the need to update the FY26 revenue. Extending L4 date from 1/30 to 5/1 due to changes in IT resource allocation and late start to beginning IT development in L3. Impact is $929k net benefit forecast reduction in FY26. Benefits to begin to be realized in March. This will not change the NRB. Next step:Continuing to work with IT to see what features can be pulled forward to make the money step date. 12/10/2025: Charge sliip automation feature is now slated to deploy in the March timeframe due to a sudden change in developer resources and unforeseen complexity in implementing the solution. Requested through GAT to push the money step date out to 5/1 to avoid IT resource ramp down before in-scope features are completed. 11/17/2025: Currently working on second parcel software release, targeted for 11/20. This will provide storage fees and quick quote functionality, with storage fees being an enabler for charge slip work. This initiative was delayed quite a bit when we entered L3. We were supposed to receive developer resources to complete the work, but didn't have an IT team staffed until mid-July, with ramp up and learning curve making mid-August the timeframe for getting actual work out. 10/4/2025: First release successfully deployed including Parcel Notes, 2D barcode scanning, and other small enhancements 09/29/2025: Worked with FXO Finance to revise the business case based on the new money step date. Fiscal year '26 revenue changed from $2.829M to $2.122M. Fiscal year '27 and '28 remained unchanged along with an unchanged NRB of $4.204M 09/23/2025: Updated Money Step date to push out. Currently working on updateing the financial plan. Money Step new date is 1/30/2026. 7/29/2025: First release pushed to September and will only include the Parcel Notes functionality. Features dependencies still being worked by IT to code the remaining features in the first planned MMP release. 07/10/2025: Development progressing. Additional work is being groomed and planned into sprints. Backend design and work is also being started. Working toward a release in August for the first set of capabilities. 07/01/2025: Development has begun on parcel work, with additional feature decomp and planning underway as dev resources are added. 06/18/2025: Stories have been written, pointed and assigned for developers to start work today. We are still awaiting backend developer resources we were supposed to have at the start of the PI. 06/03/2025: VDC process still underway, but developer resources have been acquired to start work in 25.03. Backlog refinement being done and PI objectives being created. 05/08/2025: Reviewed high level UX with developers and IT manager. Further meetings will be required. IT manager Riz states these are necessary to assess LOE and get resources assigned. 04/15/2025: Initiative in L3 and awaiting developer resource assignments 03/27/2025: Updated FY28 exit rate in financial plan. No revenue forcasted for FY25 baseline. Updated KPIs. 03/12/25: * Finalized KPIs and submitted for SL3. Waiting for initiative approval from the Domain Lead. 02/28/25: * Received CoP and updated L2 LBC, received FXO finance approval * Reviewing in 3/4 GAT for approval for SL3 * Meeting scheduled 3/5 with Cresha to tie off business case in Planview 02/20/25: * Initiative remains at L2 * Waiting on CoP from finance * Expecting to submit for SL3 once CoP is obtained 02/06/25: * Initiative reached L2 * Working through portfolio cost and other L2 requirements 01/23/25: * Architectural summary document completed with provided estimates fr | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-23 | 2026-05-01
Business w/ Tech Initiative: FXO Online Chatbot Pilot | 92119 | 9381 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Josh Hans, Kayla Donner, Darlene Chang | Some Issues | 04/03/2026: Requesting cancelation of init. 07/07/2025: Current solution is being placed on hold while alteratives are explored through Adobe Commerce and Sidekick. 05/29/25: SOW received from HCL Tech and contracting is kicking off with goal of completion in June to start working on getting in the queue to have FXO content added to VA. 05/14/25: As we are still waiting on a SOW to move forward the VA implementation, we still do not know when we will be able to launch this initiative. I am following up with our leadership on what next steps should be. 05/07/25: Still waiting on SOW from Microsoft. Asked for it to be provided this week but did not get assurance it would be. 05/01/25: Waiting for SOW from HCL Tech (formerly Microsoft) so setup can begin and business case can be formally updated with new costs. 04/23/25: Continuing to update business case based on new Microsoft proposal. Will need to move out money date. Targeting revised submission to SL3 by next week. 04/16/25: Decision made to move forward with Microsoft proposal so associated costs are being added to the business case to submit for SL3. Will need to add dependencies with FedEx.com VA team as we will be utilizing their testing environment and our releases will be dependent on them. 03/28/25: FY25 Baseline and FY28 Exit Rate Updated 03/26/25: Microsoft costs have been provided for the work needed to add and maintain FXO content in the VA, meeting being scheduled for next week to align on next steps. 03/18/25: We are still waiting for additional cost information to update the business case before SL3 submission, Microsoft has said they would provide the costs this week. 03/13/25: We are waiting for additional cost information from Microsoft to understand how the business case might need to be changed. This is related to the 24 questions we are trying to get added to the VA not getting "prioritized" to support the original launch date. 02/05: SL2 approval received, continuing to work through SL3 checklist. There is an emerging issue with the FXO requested content not getting prioritized into the VA solution - meeting with MD scheduled for Monday 2/10 to discuss options. 01/29: Still waiting on final SL2 approval. 01/23: Working through cost of portfolio and SL3 checklist and waiting on final SL2 approval 01/15: L1 Business case approved by FXO finance, now working to get it added to Planview for POD finance to sign off on submission | E: L2 | Cancelled | TEMP L2 - Enter Value Prop | 2025-03-03 | 2025-04-11
Business w/ Tech Initiative: FXO API Revenue Initiative: Adobe Express & FDP | 89331 | 9382 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Catharine Hoover, Kayla Donner | Some Issues | 03.30.2026. Canceling init following alignment with Josh Hans. Will open new init in the future if needed. Per FXO meetings with Adobe, additional meetings with FDX Enterprise will follow since FedEx has an Enterprise Contract with Adobe. FXO Leadership advised holding on the project since the discussions may impact the Adobe Express project. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Employee Asset Returns Program (EARP) | 77033 | 9384 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Maria Brock, Kayla Donner | Some Issues | **01/23/26** Received Commercial Domain Lead approval in 1/23/26 CDR to cancel L4 init expansion due to sustained de-prioritization of enterprise G2S support, resulting in materially stagnant performance (NRB declining from $5.6M to approx. $200K). The EARP program will continue independently outside of DRIVE (~$3.5M TTM FXO revenue) and remain available to enterprise customers. **01/21/26** Scheduled to attend CDR on 1/23/26 to align with leadership on cancelling this initiative. **01/14/26** Two new engagements this week with January revenue flat, but from mostly one customer, Lowe's. We are expecting to align on cancelling this initiative in the 1/23 CDR meeting. **01/07/26** No new engagements since 12/15. Future of EARP in DRIVE pending CDR alignment on 1/9. Expected FY28 NRB is ~$200K as compared to $5M in plan taking the initiative outside DRIVE parameters. **12/31/25** - No new engagements this week, no updates on DRIVE progress. **12/24/25** - No new engagement this week. Will provide an update on 1/9 CDR call to align with Domaine Finance lead on request to cancel the initiative. **12/17/25** One new engagement this week for large senior care network. Most engagements have been for Pack N Return with EARP as back-up. Returns pod leadership is aligned on cancelling this intitiative out of DRIVE. Will hold request until January and discuss in next CDR call. **12/10/25** Working on leadership alignment on best way to exit DRIVE given Sales deprioritization and direction to discontinue G2M efforts resulting in expectation for current low revenue levels to continue. **12/3/25** Aligned with Finance on process to cancel this initiative in DRIVE. Provided update in GAT and got guidance to stop efforts to gain G2M support given Sales de-prioritization. Will be providing an update in DRIVE pod 12/4 to gain approval for cancellation. From there, we will align with Domain Lead on cancellation. Program will continue to be available and supported by FXO with current configuration and no G2S/G2M support. **11/26/25** One new engagement this week, but no other updates on moving the program out of L4. Direction from Finance is pending leadership review and Returns team is evaluating taking ownership of the program. Activity from existing customers in November looks strong. **11/19/25** No new engagements this month. There are seven customers in various stages of contracting. Mostly small opportunities and many have EARP as a complement to Pack N Return. Direction from Domaine Finance on best way to move the initiative out of L4 with change in projected outcome is pending. **1/14/25 Initiative Progress Overtime rationale:** Initiative has been stalled in L4 because the program was de-prioritized by Sales leadership after it was launched. This caused the G2S and G2M efforts to be stopped. We are working with Returns team to explore broadening the program to include priority customer segment use cases, but this would prompt a new initiative in DRIVE. This initiative is not likely to meet it's potential with current support. Finance has been consulted about how to move the initiative through L4 or possibly remove from DRIVE. Guidance is pending their team review. **1/12/25** Met with Domaine Finance team for guidance on moving the initiative through or out of L4. Team will need to escalate for direction. In parallel, met with Returns Product Marketing to explore the possibility of moving the program to their team with expansion to a broader audience (e.g. healthcare medical devices, electronics returns). Team will review and respond by next week. Updates from Finance and Returns teams will be brought to pod alignment meeting for input. **11/5/25** Reviewed L4 status with GAT and was directed to work with Finance to determine best way to enable the initiative to move through L5 or possibly stop the initiative all together. Factors: 1) we are not asking for any resources, the program is up and running. 2) Sales has deprioritized the | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-07-22
Business Only Initiative: [Optimize pricing]: Retail Third Party Sold Pricin | 23717 | 9512 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Alexandra Schuler, Jaime Cunningham, Jamie Heath | On Track | 3/26/25 - Updated to reflect FY25 baseline through FY26. TO Finance provided guidance to leave FY28 Exit Rate blank because this initiative will complete L5 actuals reporting requirements in Q3FY26 and automatically be removed from Planview. 3/5/25 - Reviewed actuals and updated forecast with pod finance. Confirmed cost calculation. Updated forecast in PV. Pod finance aligned to move to SL5. Updating weekly status to note the approval by the Transformation Office on 7/15/24 for the Express portion of the impact to be removed due to F1R rollout, which has effectively negated this pricing change on the Express side. 7/26/24 - Removed Express impacts starting at July 24, uploaded proof of money step. 7/11/24- Entered impact for May 24 and KPI. Cost for Feb, April, and May awaiting cost analysis from Finance. 6/18/24- Positive Revenue impact identified for Ground sold for February (Up 6.7%) and April (up 14.6%) YOY. Working with Megan to get ground finance to calcuate current OP cost/ Op Margin 5/21/2024 - Retail portal doesn't have April Actuals, will update once the dashboard updates. 4/23/24 - F1R is set to impact the initiative. As a lower cost option, it will move volume from the standard express service to F1R. F1R data is not currently captured in the impacts and KPI. this will need to be accounted for moving forward. 4/17/24 - F1R launched to FASCs on Monday 4/15 with the nationwide rollout. We will continue to gather data for the next 3 months. 4/11/24-Met with Jane and Megan to determine next steps. Confirmed the F1R impact will not be counted for two initiatives. Megan and i are in agreement that with the launch of F1R, we should wait for another 3 months, gather data to determine how forecasted impact needs to be updated prior to L4 submission. 4/4/24 - Looking to discuss options in weekly call with ADR/RS for gathering data and updating forecasting as it relates to the F1R launch through Retail. 3/20- We are proceeding with Finance's recommendation and gathering a few months more data to inform our forecasted impact adjustments. 3/7 - Received additional clarification from Jane on option 2, no specific data behind which factor to use to reduce. Finance (Ben + Megan)'s recommendation is to hold and gather additional data for the next 2-3 months. Use that data to figure out if there is a reduction that makes sense based on this information 2/29- Met with Jane and Megan to review L4 requirements, we were given 3 options to move forward. 1. Hold, gather 3 months more data 2. Adjust forecasting to 20% 3. Cancel initiative Spoke with Aimee and we both agree #3 is off the table, because loss of volume and revenue needs to be addressed and this is the evaluate phase of ABLE. If adjustments need to be made, we can make them. Megan is getting clarification on #2 with Jane. I am also gathering additional competitive data from Sales as i have received several cases recently stating that we are no longer competitive with a UPS update. Asked for clarification from a corporate and was told there was no update, need to validate this further. 2/22/24- Discussed initiatives with Jane + next steps for this initiative. They still need to remove the assumptions for FGE from wave, otherwise ready for L4. 2/14/24-Received approval to remove FGE component from this initiative. Updated Excel file and cancelled Milestones pertaining to that portion of the initiative. Requested Mackenzie remove the assumptions as that section is locked to me. 2/8/24 - Met with Megan and McKinsey to confirm separation of initiatives. Working on pulling the FGE portion of data out of the file and removing the mentions/assumptions from the Wave initiative + Milestones. 1/14/24-Met with FDX, Depot, and Pitney Leads to go through scope. Scope requirements are due to the way the Pitney system was built. They are treating FGE as an entirely separate product/request from the FDX standard portfolio and as such, requires a very manual process to | K: L5 | Completed | L5 | 2023-09-27 | 2023-11-16
Business Only Initiative: Digital Signage |  | 86238 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Jacob Pendleton, Maria Brock | On Track | 7/30/25 - CANCELED - approved on 7/17/2025 POD call. - Switching paths on this initiative as it has been difficult to find customers will to make the large upfront investment and/or agree to the long contract terms associated with digital signage - With that, we feel like we are not ready to productize digital signage as an offering and will remove from DRIVE - Change responsibilities to Commercial side to vet opportunities under Mohan’s team and follow the S&G installation process with BIG - HC opportunities will be managed through the existing HC team as well - Use CX feedback to refine the approach 7/9/25 - Continuing to work with sales to identify addiotonal POC clients. 7/2/25 - Continuing to work with sales to identify addiotonal POC clients. 6/25/25 - Continuing to work with sales to identify addiotonal POC clients. 6/18/25 - Currently working with sales to identify addiotonal POC clients. 6/11/25 - Currently working with sales to identify addiotonal POC clients. 6/4/25 - Submitted Lean Business Plan to finance for review on 6/3. Currently pending their findings. 5/28/25 - Still working with vendor and internal stakeholders to identify if a six month POC is viable. 5/21/25 - Marco Island has requested a six month pilot test to demonstrate the value of installing digital signage and to prove revenue avaliable revenue streams this would enable. We are working with the vendor/customer/FXO to determine if this would be avaliable. 5/14/25 - MD in Sales has been engaged to help identify an additional POC customer we can work with while Royal Canin works through their budget restrictions. 5/7/25 - Meet this week to get an update on Sales efforts, and determine when Marco Island readout can be scheduled with the customer. 4/30/25 - Sales is working to find another POC customer since Royal Canin has pushed their timeframe for their POC. 4/23/25 - 3P media release enabling presentation of their past work in Sales presentations is pending their legal review. Received concept deck from Duggal (3P) on JWM Marco Island and are working through process to reformat to FXO brand for customer presentation. Team agreed we would share concepts and get feedback from customer then develop pricing proposal. 4/16/25 - Royal Canin has informed us they may need to move this POC back to after the first of the year due to budget issues on their end. The team will be looking for an additional commercial POC customer. We have identified a potential additional HCO POC customer and will be further exploring that oportunity in the coming weeks. 4/9/25 - Duggal has completed a fact finding trip to research new technologies that will be used in the Royal Canin POC this week. A meeting to get a full read out of their findnings will be scheduled in the next few weeks. 4/2/25 - Meeting with Marco Island was a success, details will be presented to the core team later this week. 3/31/25 - FY25 baseline and FY28 NRB has been updated (no change in value range, working through L1 LBC) 3/19/25 - Initial Discovery call with Royal Canin, our commercial POC customer, has been setup between the customer, Duggal, and FXO on 3/21. We have started the process to have Dugaal setup as a supplier in iNSupplier. Meeting scheduled to update lean business case inputs scheduled for 3/21. 03/12/25 - An in-person meeting is setup for 4/1 with FXO, Dugaal, and JW Marriot Marco Island, our HC Proof of Concept location, to discuss their requirements and walk through the property. 03/05/25 - Spend Control Tower approved effort. A MSA has been signed with the Vendor. Currently scheduling a FXO/Duggal visit with a Proof of Concept customer. 02/26/25 - Transitioning to new Inititative Owner (Jacob Pendleton). Spend Control Tower approval is still pending. Meeting with HC POC customer delayed until contract is signed. 02/19/25 - Submission to Spend Control Tower pending approval. Our HC POC customer tour is pending contract signature with target date of Mar 6-7. 02/1 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FedEx Office Design On Demand |  | 86360 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Josh Hans | Some Issues | 12/1/25: This request will be cancelled. A new local enhancement request will be entered for the new explorationg into the Adobe Express SDK. 05/07/25: Remains on hold due to contract terms not being agreed to. 05/01/25: Contracting with Adobe has hit an impasse and project is on hold until terms can be come to. 04/23/25: The business case is on hold while the details of the contract between Adobe and FedEx continue to be worked out. The ROI of the business case will be materially impacted by how the contract is structured. 04/16/25: Ongoing discussions with Adobe on how the Design On Demand project's contract will be set up. This will inform the business case and allow this to move forward to SL2. 03/28/25: FY25 Baseline and FY28 Exit Rate Updated 03/18/25: Meeting with Adobe on Monday 3/24 to review preliminary cost structure of Design On Demand. Planning an early IT review on Friday 3/28 to begin understanding the capabilities we will deliver with MVP. 03/13/25: Adobe has presented a vision demo for their solution and we are now working through a preliminary business case. The FIRST is in progress. We have changed the name of this initiative to Design on Demand. 2/5: Alignment with Adobe continues between Firefly and Express. FedEx Office is looking to create an integrated experience between the two experiences. Received confirmation we will need a FIRST for Adobe Firefly. 1/29: Meetings with Adobe continue to explore what capabilities we can expose and how we want to handle in our own POD experience. Inputs for the business case should be provided soon to start moving this forward. 1/15: Continuing to meet with InfoSec and Adobe on Adobe Firefly solutioning for AI-generated content. Next meeting on 1/23. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FXO Omni-Channel Experience - Profile Unification |  | 86367 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | BRANDON NAVINSKEY, Kayla Donner | Some Issues | 04/22/2026 - The follow-up meeting with the Polaris team was rescheduled from 4/17 to 4/22. During this meeting that included architects from Polaris and Retail Solutions, we determined that FCL/WREG work does not have a Polaris dependancy. The PO from FCL/WREG is currently researching if the requested functionality is available with the existing API service. The PO will move the OCP FCL/WREG work to Backlog, however there are many urgent Enterprise priorities that must be worked first. Waiting on an estimated PI from the PO. The PI cadence for this team is slightly different from Retail solutions, the next PI runs from 6/22-8/5. 04/15/2026 - A follow-up meeting with the Polaris team and Retail Customer Architects for 4/17. We will use this meeting to determine if the OCP work needs to wait for Polaris to be completed before FCL/WREG teams begin work. UX Phase 1 mock-ups are currently being finalized with an Architect review scheduled for 4/22. This review will be completed before the documentation and feature creation in Agility is done. Received confirmation from Customer IT that FIRST for FCL/WREG has been started. 04/03/2026 - Met with the Polaris team to understand the upcoming changes to FCL and .com. Another meeting will be set for the coming weeks that will include Polaris team and Customer IT. FCL team is suggesting that OCP wait for Polaris foundation (worked in PI03) before starting development. Another pre-requisite before FCL team can accept the work is to complete the FIRST request, waiting on Sharad to complete. Agility record updated with details discussed with Customer IT regarding Phase 1 features. 03/11/2026 - Another working session with Customer IT has been scheduled for later today to refine a few features related to Phase 1. These open questions came up during UX validation sessions with the field. 03/04/2026 - Meeting with Customer IT to review open questions from the FCL/WREG team. IT will also be creating a FIRST request for the FCL/WREG piece. This work is the dependancy for starting Phase 1 development that is currently slated for 26.03. 02/25/2026 - Completed our first bi-weekly alignment meeting with stakeholders and key IT teams involved in OCP. During this initial meeting, the other 'customer profile' related initiatives were all reviewed. While these other inits do not tie directly to OCP, they provide cleaner profile data for developing the OCP profile matches. 02/18/2026 - Reviewed FCL/WREG work with corresponding demand teams. FIRST request will be opened to support this portion of the work. There is an existing FIRST in-progress for the opt-in piece. We received updated information from the SFMC team that will help finalize the FIRST for submission. UX is conducting field interviews over the new functionality during the 2nd half of February. 02/11/2026 - Met with Customer owner and PPM to discuss next steps for OCP. We are focused on developing the features in Agility that align to business requirements. We will meet bi-monthly to make sure resources are aligned. Meeting with Customer IT next week to discuss feature development in Agility for Phase 1. 02/04/2026 - Met with FCL/WREG team to discuss requirements for RTLI matching and FCL creation. Providing business justification for prioritization of FCL/WREG work. Based on these conversations, updates to the UX for FCL to RTLI match filtering needs to be added to the mock-ups. 01/28/2026 - Met with UX team to review interations of Customer Lookup/Add for OCP. No additional updates for this week. 01/21/2026 - Met with Portfolio PM to discuss team assignment of OCP Phase 1 in the current PI. Additionally we are focused on confirming the impacted teams will be prioritizing OCP work for 26.02. Customer IT primary contact has changed again from Manish Sing to Sharad Vernekar. 01/14/2026 - OCP Phase 1 UX has been mocked up and will be reviewed during the Retail Program Team Workshop meeting this Thursd | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-05 | 2028-12-01
Business w/ Tech Initiative: Warehouse Order Fulfillment Optimization |  | 88849 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Monica K. King, Jake A. Gouge | On Track | 4/13/2026 - Actuals updated for March 2026 1/13/2025 - Updated actual cost savings for December 2025 and updated forecast through FY28 based on reforecast from Finance. 1/2/2026 - Updated actual expenses because we received a 50% discount from the vendor from their unresponsiveness on this project. Actual Equipment expense reduced from 59K to 38K and Internal and External IT Dev expense reduced from 83K to 46K. 12/12/2025 - Updated forecast and actuals based on finance recommendations. 11/14/2025 - Moving to L5 note. Initiative is in steady state, fully ramped, with benefits being realized above plan each month since July 1, 2025. *Note: Implementation costs lower than expected due to poor vendor execution towards contract. Moving project forward to L5 as these funds are unlikely to be billed at this point. 11/14/2024 - Initiative Progress Overtime rationale: L1 delays were driven primarily by planview being a brand new system which required significant time to determine what was needed to advance the initiative; L2 and L3 experienced additional delays due to the complexity of coordinating our IT team with the third‑party vendor and slower-than-expected vendor responses; and although we reached a steady state in L4 with meaningful cost savings, we delayed formal transition out of L4 because one of our distribution centers still required fixes to ensure the automated integration worked as intended to which we are still waiting on vendor support. 11/13/2025 - No significant change. Entering actuals 11/5/2025 - No significant change. 10/29/2025 - Automated diverts are now operational at the Greensboro location, but manual consolidation activities are still happening at the Camarillo location. Continuing to work with technicians. NO IMPACT TO FORECASTED COST SAVINGS OR L4 BUSINESS PLAN TARGETS 10/22/2025 - Cost savings are enabled through consolidated shipments at both FedEx Office Distribution Centers (DC). However, since launch the automated diverts have been down due to a connection issue, forcing manual consolidation that adds extra work for team members, which is not sustainable long-term. We have since had technicians from Autstand, SICK and FedEx Express out at the DC's troubleshooting and the automated diverts have become operational, though still not operating at an acceptable run rate. We are currently monitoring run rates, working on some scanner replacements for certain DCs as recommended by the technical experts, and fine tuning the automated operations. NO IMPACT TO FORECASTED COST SAVINGS OR L4 BUSINESS PLAN TARGETS 10/16/2025 - No significant change. The 9/3 update still applies. 10/13/2025 - Actuals entered for September. 10/8/2025 - No significant change. The 9/3 update still applies. Added actuals for September as an estimate. I should get September data on Monday 10/13 so I should be able to enter the true Sept actuals by 10/14. 10/1/2025 - Technician from SICK was able to be sent out to one of the DC's today. The 9/3 update still applies (no significant change) 9/17/2025 - No significant change. The 9/3 update still applies. 9/10/2025 - Actuals entered for August 2025. 9/3/2025 - cost savings are enabled through consolidated shipments at both FedEx Office Distribution Centers (DC). However, since launch one DC’s scanner has been down due to a connection issue, forcing manual consolidation that adds extra work for team members, which is not sustainable long-term. Awaiting vendor (Autstand) recommendation for potential scanner upgrades and connection resolution to reach full steady-state in L4. We are continuing to troubleshoot the scanner issue and push the vendor for replacement recommendations. NO IMPACT TO FORECASTED COST SAVINGS OR L4 BUSINESS PLAN TARGETS 8/27/2025 - initiative entered L4. Both DCs automated diverts are now down and we are waiting on support for scanner replacements. Team is meeting with Autstand this week to discuss immediate needs. 8/20/2025 - Waiting on approval | K: L5 | Active | TEMP L5 - Enter L5 | 2025-04-01 | 2025-11-26
Business w/ Tech Initiative: Single Point of Sale Completion |  | 90113 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Derrick L. Sullivan, Kayla Donner, Darlene Chang | On Track | 09/10/2025 - Epics are in L3c status 08/27/2025 - Working on team allocations for L3a 08/06/2025 - Initiative under review. 07/30/2025 - Initiative under review. 07/23/2025 - Initiative under review. 07/11/2025 - Completed QA check and submitted for Portfolio Greenlight. 07/09/2025 - Preparing to submit to SL3 07/02/2025 - Finalizing updated business plan and 06/25/2025 - Awiaing final COP worksheet 06/18/2025 - Working to complete L3 submission. 05/14/2025 - Cost of Portfolio submitted. Confirming estimate, dates and non-labor costs. 04/16/2025 - Cost of Portfolio analysis is ongoing 04/02/2025 - Cost of Portfolio analysis is ongoing 03/26/2025 - Cost of Portfolio analysis is ongoing 03/21/2025 - Initiative it up-to-date based on new requirements. Current baseline FY25. There is not a NRB as benefits are soft. 03/12 - Cost of Portfolio analysis is ongoing 03/05 - Initiative is in L2. Gathering Cost of Portfolio and PPMs for associated epics. 02/19 - Discussions on outstanding questions and hard vs. soft benefits are ongoing 02/05 - Submitted to SL2. Outstanding questions regarding capital and FY25 benefits. 01/29 - Submitted to SL2 01/22 - Awaiting Domain Finance approval to submit to L2 and gathering requirements for the L2 checklist. 01/15 - Reviewing business case from FXO Finance and preparing to submit to L2. This effort is 80% complete. The request is to ensure required resources are allocated through project completion. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-01-29 | 2026-10-20
Business w/ Tech Initiative: Product Bundling - FedEx Office |  | 92305 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Naga Sowmya Agnihotri Adiraju, AARON LEVINSON, Jonathan Jamison, Josh Hans, Darlene Chang | On Track | 4/22/26- New bundle pages are being tested in POD staging. Updated business case is being reviewed. 4/14/26- No new updates this week. WIP for customer research and new bundle pages. 4/8/26- No additional updates this week. 4/1/26- Postcards were removed from the small biz starter kit. The first bundle now contains 3 products. 3/25/26- Made some local enhancements to starter kit landing page, highlighting financial value proposition and added starter kit to fxo.com megamenu. Goal was to increase discoverability of bundles. 3/18/26- We engaged CXI team to conduct customer research on product bundles to identify areas of improvement to drive higher revenue. 3/11/26- Additional 2 bundles (real estate kit and indoor event kit) are planned to be developed in PI02. There is a proposal to remove notecards from first bundle, team is determining feasibility. Organic social posts are planned for March 2, 5 and 11. Bundle discount updated to 25% in Jan. 3/2/26- Entered Feb actuals. We're working on reforcasting financials by Q4 2/25/26- The 1/27 small biz bundle focus email was rescheduled and delivered on 02/03. 1/14/26: Paid Search went live 1/13, Paid Social will be live on 1/19 and Product Bundle focus email will launch on 1/27. 1/07/26: Team is working on increasing the bundle discount from 5% to 15%, targeting 1/23. 12/17/25: In production, no additional updates. 12/10/25: In production, no additional updates. 12/03/25: In production, no additional updates. 11/26/25: In production, no additional updates. 11/18/25: The delay in L3 is due to development time and we have limited resources 11/11/25: Updated the forecast numbers to align with the Marketing tactics. 11/06/25: Working with Product to identify additional bundles. 10/29/25: In Production 10/22/25: In Production 10/15/25: In Production 10/07/25: Product Bundling is in production. I updated the Go to Market date to reflect the email campaign launch date of 11/24. 09/30/25: Product Bundling launched to production yesterday and the money step evidence has been attached, which shows the receipt of a purchased product bundle. Money step milestone marked complete, forecast updated, and submitting for SL4. 09/26/25: Money step date changed from 9/29 to 9/30 as IT is pushing the launch due to a production issue that requires a testing environment, slightly delaying testing for launch of product bundling. 09/24/25: Updated the Product Bundles release from 9/25 to 9/27 to release over the weekend 09/17/25: Team are currently testing this feature which will be included in a release later this month 09/10/25: Feature is developed and set to be released later this month. 09/03/25: Development is wrapping up and team will begin testing by EOW 08/27/25: Development is set to wrap up by early next week 08/20/25: Development is ongoing 08/13/25: Development is ongoing 08/06/25: Updated the new release date (9/25) and dev complete date (9/09) 07/30/25: Working with IT leads on a new dev complete date and launch date. Should have an update next week 07/23/25: Development is ongoing 07/16/25: Development is ongoing 07/09/25: Development is ongoing 07/02/25: PI Timelines show Product Bundling complete 6/26/25; working with IT to come up with an updated launch date and will update the complete date accordingly 05/29/25: Updating finanacials to reflect capital in FY26 vs FY25 05/14/25: Financials are updated to reflect new money date. 05/07/25: Working with finance on new business case to update financial and new money date based on delayed resources. 05/01/25: Resources approved by IT. Onboarding to begin but new dates will need to be updated for this initiative. Targeting to have new dates updated by EOW. 04/23/25: Still working to obtain resources to work on this initiative. 04/16/25: Not clear when this initiative will start development, discussions and decisions are ongoing for how funding will be allotted for the resources to work on this in | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-02 | 2026-01-26
Business w/ Tech Initiative: Retail Account Creation and Warnings in FUSE |  | 92862 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | DeAndrea Forrest, John T. Walker | Some Issues | 3/9/2026-Updated Forecast accordingly. looking to begin work in PI 26.02 1/20/2026- Account Warnings was not worked in PI 25.05 due to Jan 25 CSR testing/rollout. Updated initiative, to show work to began in PI 26.01. Moved milestones start dates and money step dates. Updated forecast accordingly. 10/16/2025-Moved milestones start dates and money step dates. Solution Train alinment required to determine start date. 8/12/25 - Starting L3 Documentation. Changed IOs to DeAndrea Forrest from Tanner Walker 6/26/25 - Agility # to be added to associated epic by Epic Owner. Domain QA Expert review Alex Schuler. 5/6/25 - Changed the Revenue Type to Protected Revenue from Incremental Revenue 4/8/25 - Updated LBC based on FY25 baseline and forecasted out to FY28 | G: L3 | Active | L3 Feedback Requested | 2025-08-27 | 2027-03-01
Business w/ Tech Initiative: FedEx Office Upload to Quote - Retail |  | 93474 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | John Scott, Josh Hans, Kayla Donner, Darlene Chang, Jonathan Jamison | On Track | 04/01/26: March Results: 5,663 quotes w/2,841 (50%) approved equaling over ~$522K in revenue slightly missing expected revenue growth of $573K for March 2026. 03/04/26: February Results: 4,133 quotes w/2,140 (52%) approved equaling over ~$431K in revenue slightly missing expected revenue growth of $455K for Feb 2026. Moved to L5 02/18/26: approved for L5 02/10/26: Initiative launched 11/4/25 (initially planned for 9/30/25 but pushed back due to IT delays). Even with the delays, initiative performing above forecast since launch and full FY26 benefit expected to be realized. Currently have a positive variance of $104K FY26 OI in Planview in comparison to plan. Submitting to SL5. 02/04/26: January Results: 4,534 quotes w/2,042 (45%) approved equaling over ~$460K in revenue surpassing expected revenue growth of $337K for Jan 2026 01/06/26: December Results: 4407 quotes w/1782 (40%) approved equaling over ~$305K in revenue surpassing expected revenue growth of $218K for Dec 2025 12/17/25: Month to date, U2Qr has received a total of 9,481 quotes, of which 3,340 (35%) have been approved equalling ~$376K in revenue. Have exceeded expected revenue growth for December which was forecasted at $218K. 12/10/25: Month to date, U2Qr has received a total of 1658 quotes, of which 629 (38%) have been approved equalling ~$64K in revenue. Currently on pace to exceed December forecast which is $218K. 12/03/25: Since go live, U2Qr has received a total of 3,767 quotes w/1,511 (40%) being approved and ordered totaling ~$175K in revenue. Expected revenue growth for Nov2025 was $100k 11/18/25: Initiative Progress Overtime rationale: U2Qr is deployed in production as of 10/30 with a go live date of 11/03. Biggest factors impacting the initiative to remain in L3 for an extended period of time was due to prioritization between Dye Sub and Product Bundling ahead of U2Qr and with limited resource availability development timelines were extended out. 11/12/25: Since go live on 11/03, U2Qr has received a total of 1297 quotes w/ 467 being approved and ordered totaling $58,413.53 in revenue. 11/06/25: Revised forecast in financials to reflect more accurate ramp period. attached revised business case to planview. fiscal year 26 and NRB not changed. 11/03/25: deployed code on 10/30 and enabled stores to receive U2Qr on 11/3 10/29/25: Development remains on track for deployment end of week. 10/15/25: Development remains on track 10/08/25: Development is ongoing and on track for deployment on 10/23 or 10/30 10/01/25: Development is ongoing and on track 09/24/25: Development is ongoing and on track. FUSE deployment will align with POD October release on either 10/23 or 10/30 as of today 09/03/25: Development is ongoing and on track 08/20/25: Development is ongoing and on track as of 8/20 08/13/25: Development is ongoing 08/06/25: Development is ongoing. forecasts have been adjusted to align with changes in the development schedule to reflect 10/31 07/30/25: Development is ongoing 07/23/25: Development is ongoing. 07/16/25: Development is ongoing 07/09/25: Development is ongoing 05/29/25: Confirmed dates are still on track 05/14/25: Remains on track, new resources have contracts being worked. 05/07/25: Remains on track as long as resources are brought on board this PI. 05/01/25: Resources secured for FY26, remains on track. 04/23/25: Still in SL3 04/16/25: Submitted to SL3 on 4/16/25, Yay! 03/28/25: FY25 Baseline and FY28 Exit Rate Updated 03/21/2025: Updated NRB to reflect FY28 profit inpact as the NRB. FY25 baseline already in place. 03/18/25: Submitted to SL2 on 3/17 - had to update financial to FY28 benefits, resubmitted on 3/18. 03/13/25: Business case being finalized for SL2 submission this week. 2/5: Continuing to refine business case with Finance. | K: L5 | Active | L5 | 2025-06-18 | 2026-03-24
Business w/ Tech Initiative: Globalizing Retail Automation Tools (RCPA) | 81099 | 6866 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Keith Stegall, Mark Cockerell | On Track | 4/23/26 - Cancelling based on updated DRIVE program structure. Global Retail Business and IT are aligned on the direction for globalizing RCPA. 7/28/25 - working with EBS Strategy to pursue support through OnSpring. Updated request #1361 and included reference material/sample files for Deloitte to reference IB and OB Objects 3/31 - initiative updated to "On Hold" - team has determined to create new requests to break init into smaller pieces. will create new L0 focused on Retail Tech 3/26/25 - aliging with IT on Friday - 3/28 around breaking initiative into smaller pieces to streamline management 3/13/25 - updating scope to remove FRT (included in init 9219: Enhance Global Returns). New Business w/ Tech init 103293: Retailship- Webservices to API Migration was entered by Canada Digital Access Marketing to migrate Retail Ship from WSDL to API. Scope overlap between 6866 and 103293. Next Step: Teams to align on 3/14. 1/31/25 - Initiatve sent back to L2 with feedback. Working with architect to develop Capability and API Rationalization Epics and Milestones 1/31/25 - Working with the team to move init #6866: Global Retail Tech Enablers from the “International Parcel” pod in the commercial domain to the “retail & returns” pod in the commercial domain 1/24/25 - Tech Greenlight Approved 1/21/25 - Completed Portfolio costing exercise - milestones for July CY26 CSR under Associated Work. Ready for Tech Green light 1/8/25 - Working with Finance through Portfolio costing exercise for Tech Greenlight & L3 submission **Costing Inputs for the below ARTs:** * COM – RS – Store ART * COM – RS – Returns Technology ART * COM – RS – Platform ART * COM-RS-Convenience ART * CP – Purple Common Core ART **2024** 12/11/24 - Reviewed ask with IT MD for funding sign-off. Ready for L3 12/4/24 - Getting sign-off on funding request with Retail IT leadership & working to push initiative to L3 11/13/24 - Deep-dive sessions complete for Retail Tech, Retail Compensation, Inventory Management. Next step: bring back to RS architecture team for review 10/31/24 - Global Retail Tech Enablers – Approved priority of #48 in overall Build to Launch list (straight to Solutioning). Next Steps: scheduling info-session to review scope with architects 9/18/24 - Presented initiative to architects for Technology Greenlight on 9/18. Working with CPEL team on prioritization - next step: CPEL Intake. 9/5/22 - CPEL placing pause on new demand that does not meet the $1M NRB criteria. Updating business case to reflect growth via retail technology. 8/22/24 - L2 Validated. Next steps: CPEL review - intake form submitted 8/7/24 - Updating initiative based on review with Finance Leadership, estimated to submit back to L2 on 8/9 7/29/24 - Reviewing approach with Finance leadership 7/19/24 - Submitted to L2 as Enabler with implementation costs after review with Finance 7/8/24 - working with Finance for L2 submission | E: L2 | Cancelled | L2 Feedback Requested | 2025-04-01 | 2026-05-29
Business w/ Tech Initiative: Global ARTH | 15361 | 9215 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Keith Stegall | On Track | 4/6/26 - Discussed data hygeine with CCH Lead & working on updating key metrics. Fraud in CA is escalating as of 3/26 - driving the need for FARM > FORGE integration, which is a critical requirement for this initiative. 3/13/26 - Awaiting PRT Prioritization 3/6/26 - Awaiting PRT Prioritization 11/14/2025 - Ranked #29 in the PRT prioritization backlog. Awaiting prioritization. Overview: * $9.84M projected annual cost reduction * Canada $3.2M, Europe $5.6M, AMEA $880K, LAC $153K * Savings comes from the avoidance of subsequent deliveries (after 1st attempt) and minimizing re-sorts Estimated ART Impacts • SHIPMENT • FRO • iROADS • VISION (make sure design is in line with expectations) • FORGE • CSI • SEP - LEGACY EXPRESS 8/18/25 - per EU request & alignment with EU ESI - removing the "On Hold" status to determine prioritization ranking and next steps for initiative 3/31/25 - per review with Finance, initiative was put "On Hold" status due to prioritization of FORGE global roll out 3/26/25 - awaiting prioritization 3/13/25 - awaiting prioritization 1/8/25 - currently ranked #172 in Enterprise Priority List **2024** 11/13/24 - Reviewed Initiative with Enterprise Demand team. Next steps - Engage PEO’s to align on MVP & reduced scope, including updating the business case. 8/5/24 - Initiative On Hold as of 7/29 per DJ's office hours. Will review with Surface in mid October 7/29/24 - Presenting Global ARTH at DJ's office hours to discuss Canada manual solution 7/26/24 - Global ARTH will go into the Parking Lot until it can be reviewed by Surface in October/November 7/8/24 - Surface PEL is unable to take in Global ARTH based on current bandwidth. Recommendation from the team is to bring the initiative back to surface in October/November 6/4/24 - Met with Delivery PFS team and Business Agility teams. Discussed MVP solution and path forward for Global ARTH. Provided detailed MVP to team to take back to Surface. 6/3/24 - Reviewed with Delivery PFS team and identified synergies. Team evaluating including Global ARTH as part of their workstream 5/20/24 - Reviewed P&D Roadmap with Surface team. Due to higher priority capabilities in the timeline Global ARTH was given a few options to move forward. 1. See if we can align with Delivery PFS 2. Revisit init with Surface PEL in 6 months 5/13/24 - Working with Surface PEL team to identify where Global ARTH can fit within the P&D roadmap for FORGE 4/29/24 - Working with Commercial/Surface to outline the plan for ARTH eligible locations 4/18/24 - Presented Global ARTH at TCH - next steps to develop portfolio cards 3/18/24 - DECISION: The PRT/PEO recommends this demand request be evaluated for a definitive direction with LEO/FORGE. 3/7 - Surface Portfolio intake meeting scheduled for March 13 2/23 - Submitting init to Surface Portfolio - Expected intake meeting is mid-March 2/19 - Aligning Global ARTH for Canada with the CTP, identifying resource/owner. Submitting demand intake with Surface Demand for the rest of globe 2/8/24 - Working with the CA team on aligning Global ARTH with the CTP initiative. 1/29 - Discussions ongoing regarding next steps for Canada. Working with Architect to schedule Express intake meeting. 1/4 - Completed demand intake with FXG/Common Portfolio. PEO Recommendation: Due to the lower business value (relative to other work in the Portfolio), Value Rank score, and the fact that this effort impacts a number of constrained ARTs, our recommendation is to NOT bring this request to the Portfolio Executive Leadership (PEL) Team at this time. This requet can be resubmitted in 9-12 months for reconsideration. Next Steps: Continue to without Canada - impact to value would be -$2.2M, bringing Annual Cost savings to $6.6M 12/4 - In assessment phase, input demand request with impacted areas - FXE, FXG (demand intake scheduled for 1/3) , and Enterprise Platform (demand intake scheduled for 12/18) 11/15 - received Greenlight to move to Assessment phase of PRT 11/13 | E: L2 | Active | L2 & CCH | 2024-07-22 | 2025-04-01
Business Only Initiative: Promotional Products Company Store RFP |  | 103652 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Andrea Caballero, Drew Ray | On Track | RFP was conducted and are now in the process of exectuing a contract with new vendor. Rebaselining complete. | K: L5 | Active | L5 | 2025-10-01 | 2025-10-01
Business w/ Tech Initiative: Packaging - Offer for Purchase (US) | 31804 | 7845 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Katie McAuliff, Shea Morrow, Darlene Chang | On Track | 4/24/26: Reviewed Essendant wind down impacts with Finance; adjusting forecast to represent the next 12 months for the three scenarios - current, impacts of piloting Veritiv, and impacts of integrating ODS – and will review once again. 4/17/26: Sent impacts of Essendant wind down to Finance for review. Following up with Essendant on limited box replenishment to get some of the top sellers back in stock until we can get the POC up with Veritiv. 4/10/26: Working with Essendant to order boxes from PCA to help mitigate revenue loss as we are working to integrate Veritiv and ODS on Marketplace. Working on revised business case to quantify impacts of transition and will review with GAT and TO Finance for guidance. 4/03/26: Meeting with IT teams to determine how we can cut time out of the timeline to move quicker on integrating ODS as a Seller on Marketplace. With ODS in place, it may lessen the urgency to integrate with Veritiv as it relates to packaging for purchase so in a holding pattern confirming Veritiv costs/fees until we can get a better idea on the feasibility of accelerating the work for ODS. 3/27/26: Researching revenue impacts due to current in-stock levels and run rates to determine when Essendant will be out of stock on FedEx retail brown boxes and if a reorder will be required before we can get the pilot stood up with Veritiv. With this pilot, FedEx retail brown boxes will be available for ordering with Veritiv for fulfillment. Negotiating latest cost proposal from Veritiv, specifically the fee. 3/20/26: Veritiv submitted round three of cost proposals for items to add to Marketplace for the Veritiv pilot. Reviewing costs with additional metrics such as FXO selling retail and comp shops to see where this round of costs/fees lands us with competitors in the market. 3/13/26: Pulling potential impacts of new local initiative (ODS as a Seller) to this initiative for review with Finance. We will gain alignment with GAT before proceeding to next steps, which will most likely involve a review with TO Finance. 3/6/26: Still working through cost proposal with Veritiv, in the interim, met with Bunzl to explore their capabilities. Also met with Finance to review the business case assumptions for ODS as a Seller, which can potentially replace the current Seller, building out models to determine impacts to Offer for Purchase. 2/27/26: Working with Veritiv in the test environment to import skus. Next step will be to build pages. Pushed back on initial costing as the MP fee Veritiv is applying is exorbitant. 2/20/26: New item adds are on pause while we research alternate options for fulfillment of packaging and office supplies online. 2/13/26: No significant updates for this week. 2/06/26: Researching ODS as an option for order fulfillment. Working on business for that initiative and there may be some impact to the current OFP financials. Will continue to collaborate with Finance to ensure that everything is accounted for accurately. When completed, will bring for review to align on potential impacts, if any, before making any adjustments. 1/30/26: Researching internal distribution options for packaging and office supplies on Marketplace. 1/23/26: No significant updates for this week. 1/16/26: Financials have been updated in Planview per note from 1/9, below. There was a system issue with the supplier in December, causing orders to be rejected and therefore not filled, losing out on revenue from these orders so December is coming in with a shortfall to the revised forecast. The supplier has fixed the issue and mitigations plans are in place to ensure that this does not occur in the future. 1/09/26: Gained alignment on financial reforecast. With the findings that customers were still searching for complimentary packaging even after entering the for-purchase site, a few variables to the business case were adjusted - •Reduced the attachment rate from 15% to 2.5% based on customer behavior •Increased the percentage | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-01 | 2026-01-15
Business w/ Tech Initiative: LAC Retail Chile invoicing integration Dom & Int |  | 106776 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Daniel Boubet, Sandra Parras | Some Issues | 10/17/2025: Team in Chile will reopen request when resources are avaiable to define what is needed; 7/28/2025: This request is on HOLD to allow local Chile team to research and document the requirements | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Global Retail Tech Modernization |  | 114125 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Kevin Bates, Alexandra Schuler, Keith Stegall, Louis Noisette | On Track | 4/23/26 - Cancelling based on new DRIVE program structure - the team has satisfied each pieces of the value estimate with the alignment on the Global Retail Tech Strategy (U.S. RetailShip, Global RCPA enablement). Teams and workstreams are in place to support future enhancements. 3/13/26 - Working with Business and IT teams to create IT demand funnel while awaiting PRT resources 3/5/26 - The Global Retail Tech Modernization initiative is pivoting from re‑platforming third-party technology to enhancing and unifying the retail technology already in market. 1/27/25 - Awaiting prioritization. Ranked #18 in PRT Prioritiztion backlog. Identifying and prioritizing tech needs by capability for each region in advance to expedite PRT outcomes. Aligned with IT leadership on approach. 8/18/25 Presented at L2 commercial architecture triage meeting 8/4. Determined full PRT is needed, and tentative CPEL presentation scheduled for 8/27. IOs met with IT Tech Simplification team (action item from TO strategic narrative discussion). IT Tech Simplification team reviewing identified EAIs, mapping to each domain, and reviewing with Enterprise Architecture and the Foundational Design team to determine next steps. Next step: CPEL presentation 8/27. 7-24-25 Alined with domain finance TO finance and IT leadership on LBC. All input from the regions have been incorporated into the Ability To statement document and shared with the stakeholders. PPM# 857065. Ready for L2. A. Schuler Domain QA Expert Review. 6-4-25 working to obtain base line cost from IT for L1 LBC. | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: Gen AI FedEx Office Retail Account Lead Generation |  | 114133 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Lauren Axon, Lavanya Goteti | On Track | 12/18/2025 - Cancelling inititative as it has been combined with initiative "Gen AI FXO Account Spending Pattern Insights" (Strat Seq ID 131809) 11/12/2025 - DRIVE PROGRESS ON HOLD PENDING COMPLETION OF TECH FEASIBILITY STUDY * Microsoft Intro meeting scheduled for Friday 11/14. Initial questions to be discussed and rough next steps to be outlined. DME & ACC representation is included on this call. * Currently holding on the Booster process engagement for VDC resource assignment. Will proceed after tech plan is fully finalized following the CoPilot feasibility study conclusion. 11/05/2025 - TECHNICAL BLOCKER CLEARED. DRIVE ASSISTANCE REQUIRED. * A sandbox environment for CoPilot Studio has been provisioned. DME and DSA developers are testing access and familiarizing this week. Firm next steps for development to be decided next week. * The AI team has been made aware of challenges we have faced with lack of process clarity. They are partnering with the Gen AI CoE team to work towards enablement of our use cases. They have asked that we provide the results of our CoPilot Studio feasiblility study for further insights into this tool as an early, test adopter. * The Data & AI DRIVE Domain team has confirmed that we must complete SAD and VDC to get Portfolio Greenlight. Due to low use case ranking and lacking DRIVE resources, we will not be able to complete VDC in our current state. Instead we need to coordinate with Liz Umstot to engage in the booster process. 10/09/2025 - BLOCKED. (full blocker description on 9/26 update). Completed Data & AI Triage. It was determined no Solution and Architecture Design (SAD) involvement is required as all Gen AI inits are being handled specifically by the Gen AI team under Nick Havens. Next steps include Nick taking the inits to VDC for greenlighting. Quick processing is expected as DSA is acting as the primary developers and asking for little to no additional resources. Greenlighting in the commercial domain will also be required before work can officially begin. We are also currently provisioning a sandbox environment through the Microsoft team and granting access to the DSA and DME teams to begin assessment of CoPilot as a feasible alternative solution. 09/26/2025 - BLOCKED. Facing issues related to technical architecture. Original architecture was based on the use of Sidekick with the promise of using MARS data via TAG methodology. According to the Gen AI team, they will no longer be moving forward with provisioning this functionality. The next option that we are currently pursuing is the use of TAG with CoPilot, this option has been proposed by the Gen AI team, the PPCoE team, and Microsoft and has yet to have been attempted. Details on architecture and process are undefined. We are currently in conversation with PPCoE, Microsoft, and InfoSec to see if we would be able to provision a Sandbox environment with CoPilot to fine-tune the technical architecture and determine the feasibility of committing to this tool for our three Gen AI use cases. 08/22/2025 - Uploaded approved LBC. Approved to submit to SL2, A. Schuler, Domain QA Expert Review 08/15/2025 - Completed the QA check with a QA expert. Awaiting final financials from FXO Finance. 06/18/2025 - Inititial finance meeting completed on 6/6 with Cresha Reed & Sumit Kapoor. Business Case currently being put together. Awaiting follow up from architect. 06/03/2025 - Testing in SideKick and FIRST submission currently in progress. The following use case is recently approved by Triage team. Working on timelines and other details. | E: L2 | Cancelled | L2 - Enter Value Prop
Business w/ Tech Initiative: Daily HAL Delivery at Dollar General |  | 130230 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Komal Patel, Alexandra Schuler | On Track | 7/17/25 Received leadership approval to cancel initiative, based on low value LBC. 6/16/25 Change primary IO to Komal Patel | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FedEx Office - DSA Team - GenAI Use Cases |  | 131809 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Lavanya Goteti, Moumita Saha | On Track | 4/20/2026 - Our usecases are currently on hold and waiting for priorizaton by Data & AI team. 4/7/2026 - Canceling the FIRST request as we've been told by Data and AI team that Fabric Data Agent is considered as throwaway work and Genie via DataBricks would be a viable solution. We are currently waiting on use case prioritization. 3/25/2026 - Initiated FIRST to incorporate Fabric Data Agent along with Copilot studio. Questionnaire is in progress. 2/19/2026 - Following continued conversations with Microsoft, Fabric Data Agents (FDAs) was still being recommended. After in depth conversations between myself and technical Microsoft SMEs, we have landed on a recommended solution that leverages CoPilot Studio as the interactive layer and FDAs as the multi-agent, deep analytical orchestration layer. We have confirmed financials are to be of no additional cost to set up technology and run costs will be contained within our existing capacity. FDA is in preview mode but is set for a mid-March release to general availability. This has all been captured in documentation provided by Microsoft. Lavanya has coordinated with peer managers and gained approval. Next steps include seeking approval from the Retail & Returns Pod for this action plan and to proceed with a FIRST request for FDA. 1/22/2026 - Earlier this month, Microsoft raised concerns regarding the use of CoPilot Studio instead wanting to proceed with their new tool, Fabric Data Agent. Following guidance from the Retail & Returns Pod and Aimee DiCicco's direct instruction, Christy Taroni & Lavanya Goteti continued discussion with Microsoft pushing back on this pivot. The Microsoft team is ready to proceed with the CoPilot Studio POC. Initial Microsoft Engagement meeting occurred yesterday, 1/21/2025. During this call the preference for Fabric Data Agent was raised again. Given the presence of more technical staff on the call, we reiterated the need to have these concerns explained in high technical detail and in writing. In the interim, we will be proceeding with the CoPilot Studio POC which will begin with Microsoft defining what governance documentation they require from FedEx. Our next steps will be procuring that documentation and following Microsoft's guidance on how to best connect MARS data to CoPilot Studio. 12/18/2025 - COMBINED ALL 3 USE CASES. We combined all three use cases because it was determined that the work required would enable all 3. The 2 closed use cases are the Gen AI FedEx Office Retail Account Lead Genration (Strat Seq ID 114133) & Gen AI FXO Promo Code Template Generator (Strat Seq ID 131885). We adjusted the Demand Description to show all original descriptions and also changed the L2 soft benefit to the total sum across all three use cases. 11/12/2025 - DRIVE PROGRESS ON HOLD PENDING COMPLETION OF TECH FEASIBILITY STUDY * Microsoft Intro meeting scheduled for Friday 11/14. Initial questions to be discussed and rough next steps to be outlined. DME & ACC representation is included on this call. * Currently holding on the Booster process engagement for VDC resource assignment. Will proceed after tech plan is fully finalized following the CoPilot feasibility study conclusion. 11/05/2025 - TECHNICAL BLOCKER CLEARED. DRIVE ASSISTANCE REQUIRED. * A sandbox environment for CoPilot Studio has been provisioned. DME and DSA developers are testing access and familiarizing this week. Firm next steps for development to be decided next week. * The AI team has been made aware of challenges we have faced with lack of process clarity. They are partnering with the Gen AI CoE team to work towards enablement of our use cases. They have asked that we provide the results of our CoPilot Studio feasiblility study for further insights into this tool as an early, test adopter. * The Data & AI DRIVE Domain team has confirmed that we must complete SAD and VDC to get Portfolio Greenlight. Due to low use case ranking and lacking DRIVE resources, we will not be able | E: L2 | Active | L2
Business w/ Tech Initiative: Gen AI FXO Promo Code Template Generator |  | 131885 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Lauren Axon | On Track | 12/18/2025 - Cancelling inititative as it has been combined with initiative "Gen AI FXO Account Spending Pattern Insights" (Strat Seq ID 131809) 11/12/2025 - DRIVE PROGRESS ON HOLD PENDING COMPLETION OF TECH FEASIBILITY STUDY * Microsoft Intro meeting scheduled for Friday 11/14. Initial questions to be discussed and rough next steps to be outlined. DME & ACC representation is included on this call. * Currently holding on the Booster process engagement for VDC resource assignment. Will proceed after tech plan is fully finalized following the CoPilot feasibility study conclusion. 11/05/2025 - TECHNICAL BLOCKER CLEARED. DRIVE ASSISTANCE REQUIRED. * A sandbox environment for CoPilot Studio has been provisioned. DME and DSA developers are testing access and familiarizing this week. Firm next steps for development to be decided next week. * The AI team has been made aware of challenges we have faced with lack of process clarity. They are partnering with the Gen AI CoE team to work towards enablement of our use cases. They have asked that we provide the results of our CoPilot Studio feasiblility study for further insights into this tool as an early, test adopter. * The Data & AI DRIVE Domain team has confirmed that we must complete SAD and VDC to get Portfolio Greenlight. Due to low use case ranking and lacking DRIVE resources, we will not be able to complete VDC in our current state. Instead we need to coordinate with Liz Umstot to engage in the booster process. 10/09/2025 - BLOCKED. (full blocker description on 9/26 update). Completed Data & AI Triage. It was determined no Solution and Architecture Design (SAD) involvement is required as all Gen AI inits are being handled specifically by the Gen AI team under Nick Havens. Next steps include Nick taking the inits to VDC for greenlighting. Quick processing is expected as DSA is acting as the primary developers and asking for little to no additional resources. Greenlighting in the commercial domain will also be required before work can officially begin. We are also currently provisioning a sandbox environment through the Microsoft team and granting access to the DSA and DME teams to begin assessment of CoPilot as a feasible alternative solution. 09/26/2025 - BLOCKED. Facing issues related to technical architecture. Original architecture was based on the use of Sidekick with the promise of using MARS data via TAG methodology. According to the Gen AI team, they will no longer be moving forward with provisioning this functionality. The next option that we are currently pursuing is the use of TAG with CoPilot, this option has been proposed by the Gen AI team, the PPCoE team, and Microsoft and has yet to have been attempted. Details on architecture and process are undefined. We are currently in conversation with PPCoE, Microsoft, and InfoSec to see if we would be able to provision a Sandbox environment with CoPilot to fine-tune the technical architecture and determine the feasibility of committing to this tool for our three Gen AI use cases. 08/22/2025 - Uploaded approved LBC. Approved to submit to SL2, A. Schuler, Domain QA Expert Review 08/20/2025 - Completed Strategy Detail Fields folllowing guidance from QA expert. Awaiting final financials from FXO Finance. Will need final QA check from QA expert following final financials inclusion. 7/2/2025 - LBC currently being put together. Still awaiting architecture. | E: L2 | Cancelled | L2 - Enter Value Prop
Business Only Initiative: Drop Box ADA Compliance |  | 133506 | Business Only Initiative | Commercial - Retail, Print, and Returns | Commercial | Felicia C. Stringfellow, Valerie McCoy, Mark Enfield, Terri L. Smith-Anderson | On Track | 4/20/26 * Sales Weekly Update Article planned for 4/2426. * Next SVP update scheduled for May2026 4/6/26 * Legal Councel( Deni Hansberry/Collen Wilson advised w meet w/Business Transaction Attorny to develop plan on how to notify customers of removals * Visionary is reviewing contract language for targeted dbx removal to help identify the customer notice requirements. * Plaintiff's Councel has agreed to extension of dbx to Aug 2029 - Legal team is working to obtain court approval 3/28/26 * Retail Strategy Team identified inital 916 Non compliant dbx's for removal based on profitability 1/28/26 * No update from Plaintiff's council on agreement to extend the remediation timeline. Colleen is in discussion with her leadership. 1/13/26: * Drop Box Non Compliant List is being reassed by JSneed 1/13/26 * Drop Box Team Completed New Remediation Agent training (6 Weeks) 1.5.26 * Plaintiff's counsel postoned meeting with Legal (Colleen Hitch Wilson) 12/16/25 regarding tracking of remediated drop boxes until Jan26 12/18/25: * Legal (Colleen Hitch Wilson) is drafting a counter proposal for Plaintiff's counsel regarding tracking of remediated drop boxes to be discussed in January 2026 (postponed from 12/16/25) * Drop box team is training 5 new remediation agents (contractors) to assist with workload to manage remediation effort for each individual drop box. Training takes 5 weeks, and they are currently in week 3. 12/10/25: * Legal in discussion with Plaintiff's counsel how to keep them up to date on progress quarterly 12/4/25: * On this week's Dropbox team call, Attorney's advised that they have not heard back yet from the plaintiff's counsel on agreement with remediation plan. * Drop box team is focused on training new remediation agents through December. 10/1/25: * SVP meeting held on 9/29. Team challenged to develop a comprehensive plan by end of Oct. for Legal to take to Plaintiff's council, after socialization at CDR. 09/17/25 * Work continues for SVP update on 9/30/25 * Currently analyzing list of non-compliant, compliant, not yet audited locations to see where there may be opportunities to focus on high priority drop boxes vs. others * As of 9/15/25 * 131 drop boxes that have not been audited * 12,510 drop boxes are compliant * 11,310 are non-compliant, 9,486 of those have failed the landing area and slope tests 09/10/25: * Approved by Commercial Domain Lead for L2 * Work continues for SVP update planned for 9/30/25 * Team is drafting and reviewing workflow / timeline for final drop box remediation with Legal on 9/15/25 * Team is reviewing customer comm regarding removal / relocation of non-complianct boxes with Legal on 9/15/25 08/25/25: * Approved by Finance for L2, now in Queue for Domain lead review and approval * Next SVP update planned for Tuesday, 9/30/25 08/19/25: * 8/19/25 - Ready for L2. A. Schuler Domain QA Expert Review * As of 8/18/25, drop box audit review is at 96.1% completion. 930 boxes still need to be audited * Compliant boxes 12,104 (53%) * Non-Compliant boxes 10,911 (47%) * Legal team has prepared a response to Plaintiff (currently being reviewed internally) to be sent Friday, 8/24/25 08/04/25: * Cross functional team met on 8/4/25 to recap and discuss next steps as a result of SVP update * Team continues to focus on completing audit of all drop boxes by end of Aug 07/29/25: SVP Update was on 7/28, some of the actionable items included: * Continued focus to complete audit of all non-compliant boxes by end of August * alternative solutions to resolve slope issue * quantify P & D savings tied to removal of drop boxes * request further breakdown of removal options (1 ADV, 2 ADV, 3 ADV) Next Steps: * Next SVP meeting to be late Aug / early Sept, am working on scheduling * CCH Update to be scheduled after audit complete 07/23/25: * Preparation for SVP meeting on July 28 at 2 p.m. 07/15/25: * SVP meeting scheduled July 28 at 2 p.m. * Cross functional | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Project FORCE (FY28 Openings) |  | 139945 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Jennifer Becsei, Kayla Donner, Heather R. Ronk | On Track | ***June BOD approved project/initiative*** 03.16.2026 Received CCH greenlight and final Platforms costings. Updated financials, milestones, risks, epic, and L2 LBC. Completed QA check. Attached FXO Financials and D&T Costing to init. Aligned with Finance on final Financial entries and KPIs. Submitting for Portfolio Greenlight for 3/24 EGC meeting for final approval. NOTE: Positive NRB begins in FY29 following FY28 store openings ramp. 03.13.2026 Received COP from Platforms Portfolio. Working on prepping financials with FXO Finance for 3/24 greenlight meeting. 02.27.2026 Continuing to wait for costing from Platforms portfolio. 10.02.2025 Completed alignment with Commercial & Platforms architecture teams on 9/26. It was determined that the Commercial portfolio is not impacted, and they would like Platforms to take over as the lead portfolio. Platforms is confirming with EPM that Commercial & Supply Chain portfolios impacts can be removed from Planview, then IO will submit PDSM ticket to update. Platforms team arranging a call with the Networking Engineering team that supplies infrastructure, network turnup, and hardware. Ongoing discussions regarding budgeting resources for networking and hardware installation (not included in BOD approved CLEAR) for all FY26 store openings (including those outside of FORCE) to ensure required hardware will be available. IO to provide forecast for FY27 & FY28 for budget planning. Project update: 12 locs REC approved; 3 leases executed and opening dates set; 23 LOIs in place. Additional opportunities identified in LA and Houston - site visits underway next week. Estimate 30 total FORCE locs open by end of FY26 with remaining 20 to roll over to early FY27. Finance working to revise projections. 09.18.2025 •We were prioritized at CPEL last week (4th, 5th, and 6th) and are anticipating a Commercial architect to pick up the initiatives next week (week of 9/22) to begin L2 requirements •They will help with coordinating assessing impacts from the Platforms and Supply Chain Ops portfolios as well •We are also in communication directly with the Platforms portfolio as they are working on getting costing for the networking by looking at the costs tied to previous store openings •We met with TO Finance last week as well to get guidance on forecasting for the L2 LBC down to the monthly level •We are continuing to identify sites for LOIs with 17 LOIs, 2 going through REC approval, 10 locations fully REC approved, and 2 opened •FXO Finance is working on the monthly forecast and adjusting based on that store target •Once we have the Platforms costing and revised financials, we will plan on sharing the final business case projections before completing the Planview entry and moving to L3 (targeting to meet the November L3 goal for the FY26 initiative) 09.12.2025 CPEL completed via read-only. Architect to be assigned and work with Platforms and SCO portfolios to complete L2 architecture requirements and costing. CLEAR for test store openings sent to Platforms portfolio for costing. Meeting with TO Finance and FXO Finance to get recommendations on structure for L2 financial plan (monthly forecast). TO Finance confirming several open questions. FXO Finance to update business case forecast. Additional L2 requirements (KPIs, milestones & risks being worked through). 07.29.2025 Received confirmation from TO Finance to leave initiative classified as a Growth intiative, despite not showing a positive NRB for FY28. This is due to the 3-year initiative being bucketed into store openings by FY. The store openings taking place in FY28 will be ramped in FY29 and being to show profit at that time. Aligned with EPM on the approval. Attaching email from TO Finance to Content. 07.24.2025 •We received L1 architecture alignment documentation back from the enterprise architects for all 3 initiatives •They have all been sized as a Medium and both the Commercial and Platform portfolios were identified as im | G: L3 | Active | L3 | 2027-01-01 | 2028-05-31
Business w/ Tech Initiative: Project FORCE (FY26 Openings) |  | 141899 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Jennifer Becsei, Kayla Donner, Heather R. Ronk | Some Issues | ***June BOD approved*** 04.04.2026 Moved money step from June 1 to June 30 to allow time to reconcile final financials and store count before submitting to SL4. 03.06.2026 Received CCH greenlight and final Platforms costings. Updated financials, milestones, risks, epic, and L2 LBC. Completed QA check. Attached FXO Financials and D&T Costing to init. Aligned with Finance on final Financial entries and KPIs. Submitting for Portfolio Greenlight for 3/10 EGC meeting for final approval. 02.27.2026 Continuing to wait for costing from Platforms portfolio. 02.05.2026 Continuing to wait for costing from Platforms portfolio. 11.13.2025 Network Services needs to finalize the Bandwidth utilization assessment first and then we will provide a determination on if FXO BW standard needs to change with associated cost model. At which time, we’ll engage finance to provide guidance on how we move forward considering any increase in Hardware and/or FITC expense was not budgeted in FY26 for this initiative. We are currently waiting on Lisa Railes. We received favorable updated SIMM guidance that roughly offsets the higher D&T costs. Coincidentally, we’re at 163 average baseline ADV per store, compared to the originally approved 164. We’ll plan to coordinate this version for the Dec ExCom deck, as well as rolling up the 300-store program business case based on latest opening timing as back pocket information Project Update: * 3 Stores Open * 25 Locations REC Approved * 5 leases signed * Next to Open is Charlotte after peak Jan 2026, Parrish FL March opening 11.06.2025 Platforms team determined each store will need additional bandwidth to support FUSE. Project costing for equipment, network turn-up, and additional bandwidth in progress. Project update: 3 stores open, 23 REC approved, 15 LOI. Presented to BAC this week and will update BOD on ROI, impact to FedEx & FXO. Real Estate hiring to support site visits. Next step: Platforms Portfolio team response on costing and Greenlight. 10.09.2025 Working with Platforms team on resourcing and impact on network traffic, and costs for network turnup and hardware order. Meeting 10/16 with IT Finance and FXO Performa team on financial impacts - will confirm FY26 is on track and budget for FY27-28. Potential risk - need to confirm FY26 budget for network turnups given recent addition of OnSite locs. Real estate update: 3 leases executed (1 store will open pre-peak, 2 post-peak), 9 leases pending execution. 4-5 packets of stores received per week. Some require new construction. Overall, store pipeline is healthy. FY26 forecast lowered from 50 to 30 stores; financials and initiative to be updated accordingly. 10.02.2025 Completed alignment with Commercial & Platforms architecture teams on 9/26. It was determined that the Commercial portfolio is not impacted, and they would like Platforms to take over as the lead portfolio. Platforms is confirming with EPM that Commercial & Supply Chain portfolios impacts can be removed from Planview, then IO will submit PDSM ticket to update. Platforms team arranging a call with the Networking Engineering team that supplies infrastructure, network turnup, and hardware. Ongoing discussions regarding budgeting resources for networking and hardware installation (not included in BOD approved CLEAR) for all FY26 store openings (including those outside of FORCE) to ensure required hardware will be available. IO to provide forecast for FY27 & FY28 for budget planning. Project update: 12 locs REC approved; 3 leases executed and opening dates set; 23 LOIs in place. Additional opportunities identified in LA and Houston - site visits underway next week. Estimate 30 total FORCE locs open by end of FY26 with remaining 20 to roll over to early FY27. Finance working to revise projections. 09.18.2025 •We were prioritized at CPEL last week (4th, 5th, and 6th) and are anticipating a Commercial architect to pick up the initiatives next week (week of 9/22) to begin L2 requirements | G: L3 | Active | L3 | 2025-01-01 | 2027-02-26
Business w/ Tech Initiative: Project FORCE (FY27 Openings) |  | 141902 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Jennifer Becsei, Kayla Donner, Heather R. Ronk | On Track | ***June BOD approved project/initiative*** 03.06.2026 Received CCH greenlight and final Platforms costings. Updated financials, milestones, risks, epic, and L2 LBC. Completed QA check. Attached FXO Financials and D&T Costing to init. Aligned with Finance on final Financial entries and KPIs. Submitting for Portfolio Greenlight for 3/10 EGC meeting for final approval. 02.26.2026 Received final Platforms portfolio costing from Platfroms finance. Updated initiative accordingly. PEO is preparing to present this initiative at the Platforms PEL on March 4th. Once it is approved by the Platforms VP’s, we will be ready to present at an upcoming EGC for approval to move #141902 to L3. 02.05.2026 Continuing to wait for costing from Platforms portfolio. 10.02.2025 Completed alignment with Commercial & Platforms architecture teams on 9/26. It was determined that the Commercial portfolio is not impacted, and they would like Platforms to take over as the lead portfolio. Platforms is confirming with EPM that Commercial & Supply Chain portfolios impacts can be removed from Planview, then IO will submit PDSM ticket to update. Platforms team arranging a call with the Networking Engineering team that supplies infrastructure, network turnup, and hardware. Ongoing discussions regarding budgeting resources for networking and hardware installation (not included in BOD approved CLEAR) for all FY26 store openings (including those outside of FORCE) to ensure required hardware will be available. IO to provide forecast for FY27 & FY28 for budget planning. Project update: 12 locs REC approved; 3 leases executed and opening dates set; 23 LOIs in place. Additional opportunities identified in LA and Houston - site visits underway next week. Estimate 30 total FORCE locs open by end of FY26 with remaining 20 to roll over to early FY27. Finance working to revise projections. 09.18.2025 •We were prioritized at CPEL last week (4th, 5th, and 6th) and are anticipating a Commercial architect to pick up the initiatives next week (week of 9/22) to begin L2 requirements •They will help with coordinating assessing impacts from the Platforms and Supply Chain Ops portfolios as well •We are also in communication directly with the Platforms portfolio as they are working on getting costing for the networking by looking at the costs tied to previous store openings •We met with TO Finance last week as well to get guidance on forecasting for the L2 LBC down to the monthly level •We are continuing to identify sites for LOIs and based on the number that have been identified for the expansion so far, we are adjust our FY26 forecast from 50 stores to 30 stores with the remaining 20 rolling into FY27. •FXO Finance is working on the monthly forecast and adjusting based on that store target •Once we have the Platforms costing and revised financials, we will plan on sharing the final business case projections before completing the Planview entry and moving to L3 (targeting to meet the November L3 goal for the FY26 initiative) 09.12.2025 CPEL completed via read-only. Architect to be assigned and work with Platforms and SCO portfolios to complete L2 architecture requirements and costing. CLEAR for test store openings sent to Platforms portfolio for costing. Meeting with TO Finance and FXO Finance to get recommendations on structure for L2 financial plan (monthly forecast). TO Finance confirming several open questions. FXO Finance to update business case forecast. Additional L2 requirements (KPIs, milestones & risks being worked through). 08.08.2025 Completed L2 Commercial EA traige on 8/4. They requested that an impact to Supply Chain Ops is also added. Submitted PDSM ticket to add that portfolio. Completed L2 Platform EA trage 8/8. They have requested the CLEAR and trial store opening numbers to leverage data we already have to know how Platforms is impacted to estimate the labor cost tied to store openings. Sent to Danielle Lindberg. 07.24.2025 •We received L1 | G: L3 | Active | L3 | 2026-04-01 | 2028-05-30
Business w/ Tech Initiative: Amazon Returns FY26 |  | 142940 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Shawn Taxter | On Track | 07/10/25 - Triage approval received for L0 07/22/25 - Awaiting contract signatures and financials before moving forward in Drive 3/30/26 - The current Amazon Drive Initiative will be cancelled. There are no decisions or resource allocation or dev work that currently needs Drive oversight. The initiative cannot remain open for future work; which must demonstrate its own incremental value. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LAC-3-POS LAC Expantion-Retail POS to ASC and CCA |  | 162796 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Midori Miramon, Michel Capuano | On Track | needs to go local will do new one | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Service-now integration with MARS platform |  | 166096 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Ajay Kumar Bethi, Jeetendra Kumar Pandey | On Track | progressing well | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Retail Self-Serve One Rate Shipping |  | 171044 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Alexandra Schuler, Jamie Heath | On Track | 4/20/2026: Walgreens approved May 18-20 in-store prototype testing. Material will be delivered to Plano Office 4/22 to build mockup display. Continue to hold in L1 until in-store prototype testing results indicate strong consumer acceptance. 4/8/2026: Walgreens agreed to support in-store prototype testing. Working to obtain necessary Walgreens store ops approvals for testing. Contract for market research/in-store prototype testing in progress by CXI. In-store prototype test pushed to May to accommodate Walgreens governance processes. Continue to hold in L1 until in-store prototype testing results indicate strong consumer acceptance. 3/18/2026: UX testing complete. Screens will be modified based on results. Contract for market research/in-store prototype testing in progress by CXI. Walgreens meeting set for 3/26. On track to complete live in-store prototype testing between 4/13-4/24. Continue to hold in L1 until in-store prototype testing results indicate strong consumer acceptance. 3/4/2026: Pilot UX testing completed 3/2. Screens modified and usertesting scenario updated based on pilot results. On track to complete remaining unmoderated UX tests (10) in the next week. Contract for live in-store prototype testing in progress by CXI. Plan to pitch in-store prototype testing to Walgreens week of 3/16 using storyline developed by CEM. Physical display prototype in development. Continue to hold in L1 until in-store prototype testing results indicate strong consumer acceptance. Final phase of market research (live in-store prototype testing) ETA 4/15. 2/17/2026: Finalized LBC and validated with Domain Finance. Will hold to submit to SL2 until market research is complete (ETA 3/31/2026). Consumer IDI complete and concept tested well with average 4/5 highly willing to try. UX designs to be tested with consumers online and refined as needed before in-store prototype testing. 1/27/2026: 6 consumers IDIs complete. Most respondents highly likely to try experience. Grocery category top ranked preference for access. UX prototype development on track for initial user testing in early Feb. LBC pending finance F1R profitiability analysis update. 1/20/2026: Finance updating F1R retail profitability analysis to separate 3rd party retail alliance compensation from blended costs. Target LBC complete by Feb. CXI created a 3 phased learning plan, drafted IDI moderator guide, began recruiting for pilot IDI, began developing UX prototype for research. Phase 1 of research on track for completion by mid-Feb. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Fee for Service Same Day Customer Retrieval |  | 177439 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Michael Silvio, Adam Cook | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Chile Domestic Freight to Collect Enablement |  | 178435 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Sandra Parras | On Track | 12/29/2025 - Initiative should be canceled; see supporting documentation added to this initiative | C: L1 | Cancelled | L1
Business w/ Tech Initiative: COM-S&CDE-CDE-Omni-Channel Profile Uni Opt-in Pref |  | 178442 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Eric Powell | On Track | Duplicate of Work ID # 0115057 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: New Account Type - Retail Counter |  | 186154 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Alexandra Schuler | On Track | 4/8/2026: Pricing guidance is to maintain City Center account type. Leadership approved strategy at 3/26 RMC. Will move init to hold status pending completion of LE work item #0115879. Will cancel this init when work item #0115879 is complete. 3/4/2026: Reviewed L1 Architecture alignment output, finalized L1 LBC and submitted to SL2. Elevating/validating non-quantifiable value guidance in coordination with upcoming RMC presentation on topic (3/26). 2/17/2026: Consulted with TO Finance and Domain Finance on value quantification. Benefits from future price promotions made possible by the new account hierarchy of the new account subtype are considered non-quantifiable. L1 LBC completed based on guidance provided. Ready for L1 Architecture Alignment. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Ground Economy Returns - 2.0 |  | 188738 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Monica J. Magee, Timothy Sutherland | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: LAC-3-RetailPOS-Shipping Application Decommission |  | 190635 | Business w/ Tech Initiative | Commercial - Retail, Print, and Returns | Commercial | Blanca Edith Cisneros | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Enhancing existing Apollo Dashboards and Expanding | 91129 | 7324 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Janet L. Pascoe, Dawn Komoroski, Soumyadeep Ray | On Track | removed enabler | I: L4 | Active | TEMP L4 - Enter L4 | 2024-10-01 | 2025-05-30
Business w/ Tech Initiative: Payment Acceptance Integrating Demand (PAID) - Cre | 55373 | 7737 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Michael Milligan, Paula Pearson | On Track | N/A | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global Spot Modernization | 14645 | 9176 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Murtuza Hasan, Andrei Ion, Chris Strickland | On Track | Business case has been aligned with regions, capturing both cost saving benefits and incremental revenue With funding approval for FY24 & FY25 can seamlessly continue Quote Platform development and start detailed planning on Digital deliverables 16th Dec 2025- Discussed with FP&A Advisor along with operation strategy consultant and revenue principal-we have to revisit the data and align with FY25 baseline | G: L3 | Active | L3 Feedback Requested | 2023-03-13 | 2026-05-29
Business w/ Tech Initiative: EPD ( Expiring Pricing Dashboard) Lift & Shift to | 79159 | 9338 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Janet L. Pascoe, Dawn Komoroski, Chris Strickland | On Track | 2024.07.18 Received VDC approval 2024.07.26 Received TCH approval 2024.07.23 Working with DW on Data ingestion | I: L4 | Active | TEMP L4 - Enter L4 | 2023-10-05 | 2025-02-18
Business w/ Tech Initiative: LAC Costa Rica e-Invoicing Regul Changes 6/25 |  | 91469 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Consuelo A. Polonio | On Track | This request is the original request, and is not a BIZ with TECH it is being done using request 0111890 | C: L1 | Cancelled | L1 | 2024-07-22 | 2024-07-22
Business w/ Tech Initiative: Apollo EPD Improvements |  | 109407 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Janet L. Pascoe, Dawn Komoroski, Soumyadeep Ray | On Track | 07/31/25 - Added the requested items from the EPM team , changed back to Innovation per guidance from ESPM and EPM team. PPM project number has been executed Both EPICS updated 7/25/2025 - Granted VDC approval - attached meeting minutes provided 7/17/25 Suvro advised we are on VDC agenda for the 24th. Worked with TOM, Sravanthi and Suvro on the Drive scope. 6/26/25: After discussions slimmed down this Initiave to specify APOLLO EPD. Other APOLLO Use cases needed to have a separate Drive. Adjusted Demand Desciption and Value of APOLLO EPD 06/18/25: Suvro (DW) is taking this to VDC on 6/25/25 for resource approval on the contract extension 06/16/25: Had Commercial Triage meeting with approvals for next steps I believe. No need to for CPEL or RMIC since DW owns the vendor contract extension doing the work. Have not gotten official documentation from that meeting , going off understanding from meeting. 06/11/25: Had Data & AI Drive Triage call was approved for next step of VDC process 6/5/25: Feedback from MM and JL Change Value type back to Customer Experience Remove Soft Beneift Add Target Value and Baseline in Days (days it took to detect and correct customer invoices before Apollo was created to Target Days with Apollo) Changed the Implementation Range to LOW to reflect the Implementation cost of $444k Once changes made submit to L2 6/2/25 : feedback given from MM, setting up call with Jennifer Liu for additional information. 5/28/25: Received further feedback from EPM prior to moving to L2. Updated the IMpacted Portfolios to reflect Commercial as well as Data A&I. Reached out to Domain Finance on the request that values are needed in the Baseline/Target Value fields. When building LBC was advised by Domain Finance that no values would be needed in these fields. Reached out to confirm and waiting for DF reply. DF advised to follow EPM instructions. Updated Baseline and Target Values , re-uploaded the updated LBC Submitting to L2 with all requested changes. 5/20/25: Waiting on changes to be made in INIT per my PDSM ticket. Spoke with Eryn regarding the Architectual Review pending. Dashboard shows we are in a backlog. Concerned as we are in a time crunch to get this into L2 prior to Apollo Vendor contract expiring. Domain Finance has approved for L2 , waiting on EPM and Architectual Review to be completed for the continuous enhancements and use cases to the existing architecture PDSM ticket is still outstanding 5/15/25: Submitted to L2 - received feedback from EPM. Spoke with Domain FInance regarding EPM feedback. Agreed to change the Type of Value from Customer Experience to Revenue Protection. Submitted a PDSM ticket to update the Ability Statements and Business process, as well as change the Type of Value. 05/9/25: Met with Domain finance on LBC. Determined that we will position position this init as generating soft benefit – such as avoiding invoice adjustments of $xxxM in US and $xxM in participating regions in FY25. Since the vendor contract is yearly per DW direction, we will treat FY26 estimated vendor contracted cost as one-time cost. Working on the updates in the LBC with the supporting documentation and then will re-connect with Domain Finance (Jennifer Liu) early next week for final planview numbers and moving initiative to L2. Created PDSM ticket INCINC030601497 to change the ESI from NONE to Customer Experience. 05/08/25: Had conversation with ESPM team about natural boosting since this did not meet the new definitation of business continutity. This is a continuation of PV # 9338 & #7324. Adding placeholders in Value (not finalized) and setting up meeting with Domain finance to continue working through the LBC. 5/2/25: Spoke with Domain Finance on how to quantify this initiative since it was not built to create revenue, rather protect it. Discussed Protect Purple direction as Director and VP felt this Initiative fell in that category. Reaching out to ESPM team to determine the Purple | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-06 | 2026-03-31
Business w/ Tech Initiative: Global Spot Modernisation - Part 2 |  | 113616 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Murtuza Hasan, Kuldeep Bhan | On Track | Updated Initiave Owners | E: L2 | Active | L2 & CCH | 2026-02-02 | 2027-05-31
Business w/ Tech Initiative: Add 'Single Use Account' as a new account type |  | 141948 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Pratibha Kumari, Aashish Goyal | On Track | Address challenges with temporary customer accounts, primarily those opened for duties and taxes and accounts opened with Minimum Data Standards. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Visa Commercial Enhanced Data Program Error Codes |  | 186742 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | Trinidad M. Soldano | On Track | This initiative is placement on hold. It is believed that this functionality can be implement as a Local Enhancement. Placing on hold until confirmed if it can proceed as a Local Enhancement. Pending confirmation we will cancel this initiative. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Change in INT SEZ VAT table |  | 193041 | Business w/ Tech Initiative | Commercial - Revenue Management | Commercial | ANJALI S. DEO | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Completing Ground Economy Rating Modernization | 61547 | 6754 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Jamie Johnson, Sushma B. Pattanshetty | On Track | 03/27/26: Regroup on initiative now that GRM VB2 had market launch successfully complete on 3/15/26. 09/19/25: No Hard savings for project, won't be part of TS Pod. 08/26/25: submitted form as requested to gain approval for ESI assignment (tech simplification) request ID 24 07/9/25: Primary Type of Value has been updated to Cost Avoidance; opened additional help ticket to update ESI to "Tech Simplification" INC031406559 07/8/25: Tried to update baseline KPI to 0%, as advised by domain finance, but tool is not showing any value. Architectural document supplied for Portfolio Greenlight was from Commercial L2 PRT meeting- no additional architecture required. 07/2/25: Submitted help ticket to change primary type of value to Cost Avoidance instead of Cost Savings, as advised. 06/20/25 Updated business case and submitted for Portfolio Greenlight. 05/12/25: Advised to update to Efficiency instead of Enabler 05/05/25 Attended L2 alignment workshop to socialize the scope with impacted areas- updated PPM in Epic 04/28/25: Attended L2 Triage to see if COM PRT support needed, answer is no. I was asked to update financials, and add NRB from the application that is retiring. 04/16/25: Redefined the name, description and scope of the initiative. 03/21/25: Updated the baseline fiscal year, it should be FY25 10/08/24: Reevaluating Business case- looking to add 'Economy Rate Engine moving over to REBS' proposal to this initiative when new PPM is created 08/20/24: PPM created and entered into WAVE, no other updates 07/09/24: ComPRT on 7/1. Next step to get PPM created and move work forward ** this initiative is old, has moved from WAVE as you see it. | G: L3 | Active | TEMP L3 - Enter L3 | 2026-05-01 | 2027-03-04
Business w/ Tech Initiative: Weight Based Fuel Surcharge for Intl. Express | 85588 | 6755 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Isha Gupta, Manasa Kondaveeti, Clark Grantham, Nekia Thomas | On Track | -11/5: Medtronic and Abbott added as 2 new customers successfully onboarded to WBF -5/14: GSA customer onboarded that will use WBF capability -5/5: Added the Money Step (GTS communication proof) and moved the intiative to L4. -4/29: Awaiting the GTS communication (from Bradley) to be sent to Sales Management. This will be the proof of Money Step. -4/16: Based on Jennifer's email on rebaselining, adjusted the baseline year to FY 2025. However, since this is an enabler, financials don't need any changes for this initiaitve. -4/14: Pending Domain Lead's (DJ Miller's) approval. -4/3: Per Jennifer's note, approved to be submitted to L3. -3/25: Received feedback from Finance Domain Lead to add costing inputs. I have added the costing information (email attachment) in the contents folder. This information was received from D&T team (as advised by Jennifer). -3/24: Meeting with EPM to review the feedback on SL3, made the changes as recommended (added KPI, description to Initiative Milestones). Ready to be moved to SL3. -3/14: Incorporated the feedback from the SL3 review, moved it back to SL3. Changes made: Added a new EPIC with details. Added Money Step Financials: The business value of this project is linked to the overall GAF benefit from initiative#95174 named 'Global Air Freight P&RS Business Case'. This doesn't need a business case of its own. Cost: Added to the financials. -2/24: Awiating costing team input from D&T team (per PEO-April). Project Implementation (Development is on track) -2/17: Issue with updating the milestone dates (adding tasks to it) and updating money step date. Need to raise a PDSM ticket. Pending Commercial Portfolio Greenlight, APril Zhou is the PEO. She is needs confirmation from Cortney to approve the milestone dates. -On track with development work, testing to start by C5 (3/5) | K: L5 | Completed | L5 | 2024-07-22 | 2025-10-20
Business w/ Tech Initiative: CY 2024 Demand Surcharges (US Domestic Express, Gr | 93482 | 6757 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Isha Gupta, Clark Grantham, Ethan Huber | On Track | This initiative is on track and the surcharge capability is in Production, the surcharge goes in effect on Oct 28th 2024. 2/17: The initiative is completed, it was effective from Oct'24 2024-Jan 16th 2025. The actuals have been updated. Ready to be moved to L5. 1/16: Uploaded another money step proof: Please see this link on fedex.com as the Money Step proof- https://www.fedex.com/en-us/shipping/rate-changes/demand-surcharges.html The upload from 1/14 is from other project, kindly ignore that. Sorry about the confusion. 1/14: I have updated the Money Step completion proof (Sales communication and fedex.com communication-screen shot). | K: L5 | Completed | L5 | 2024-07-01 | 2024-10-28
Business w/ Tech Initiative: Dynamic Pricing Min/Max Threshold Pricing | 83844 | 6759 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ramki Iyer, Clark Grantham | On Track | update week of 5/6/25 initative progressing well. key points/updates : a) MVP items delivered for April 25 CSR b) VB#2a is slated for Sept '25 delivery (original plan was July '25) c) VB#2b is still on target for July '25 delivery d) VB#2b spillover items from PI#03 would be lined up as part of Oct '25 e) there are backlog items from VB#2a, those items considered beyond MVP for Sept '25 would be positioned as part of Jan '26 delivery f) VB#3 items are positioned for Jan 26 delivery ----------- update week of 3/17/2025 Project progress well; updated confirmed actual cost for the months of Oct '25 thru Feb '25 ------------------------------------ update week of 3/10/2025 Project progressing well - no new updates for this week further, still waiting on cost information for Oct 24 and Jan '25 from VMO -------------------------- update week of 3/3/2025 a) received actual cost from VMO for the months of Nov '24 and Dec '24; still waiting on actual costs for Oct '24 and Jan '25 outside this, initative is going good with medium confidence for April '25 and with low confidence for July '25 (primarily within the DANCER billing space ---------------------------------- update week of 2/24/2025 - Reached out on 2/18 to share (IT Team Nitin Mahajan) for capturing actual costs for Oct, Nov, Dec, and Jan for DP Min Max Threshold Pricing. - per latest update per Bindu, they are waiting on VMO to get the details ----------------------------------------------- Update week of 2/17/2025 April '25 CSR - On track for Delivery with no concerns July '25 CSR - Solutioning is in progress Oct '25 CSR - Not Started -------------------------------------------------------- 1/8/2025 - Minutes from meeting w/TO - Finance - Matthew Hicks, Domain Finance (Ben Sauls, Jennifer Liu), and IO (Ramki Iyer) at 11.30 am CT - TO Finance Requested Feedback on 1/3/2025 as part of SL3 Approval 1) Please Explair or adjust the benifit ramp up from April '25 - July '25 in excel business case. The 12 month ramp up value is $208K. Does montly start in April or September ? Not sure why there is a 8 month benifit if starting in April 25 - Team shared the rationale for the 8 months ramp up. Essentially, team would be manually monitoring UC#4 Min/Max contracts starting Sept '24 thru Mar '25, and starting April '25 release, it would be partially systematic monitoring and post july '25, and its all going to be systematic, hence the variation in these numbers - Closed and aligned w/Mattew Hicks 2) under the financial section in Planview, please update the FXE/Intl/Air Impacts by adding the additional digits (remove rounding from excel) - Team is not introducing any new products or service as part of this initative and there are no operational impacts due to this. - Closed and aligned w/Matthew and team 3) for KPI, please add line note/details on what is being measured and extend forcast through at least FY '27. Baseline should be 'if we do nothing scnerio - team explained 'if we do nothing scnerio and aligned - further, IO- Ramki Iyer connected on 1/9/2025 with Ben Souls and working on gettinng KPIs updated with ADVs and yield/pkg updated - ETA 1/30/2025 or sooner Comments from IO : feedback has been addressed/provided by the the team and aligned with TO- Finance Matt Hicks and is good for SL3 submission ------------------------ Status Update - Week of 8/12 - Revisit Incremental Revenue numbers. There is opportunity to for Additional $10M for this business Ask for a combined $30M Vs. $20 M incremental revenue during initial submission. Analysis team is doing the due-diligence and ETA is 9/15/24. With this, the L3 date wrap up date is expected to be moved from 9/30 to more like 10/15. Status update 8/26/24 Done with revised business case; waiting for TCH Greenlight to go to L3 Status update 8/26/24 wrapping up revised business case. Once there is alignment with finance, | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-16 | 2026-06-29
Business w/ Tech Initiative: Dynamic Pricing Use Case #1 Enhancements (Enabler | 89096 | 6762 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ramki Iyer, Clark Grantham | On Track | update week of 5/6/25 -initative progressing well Key points: a) delivery was split into two phases (slice & dice approach) to acheive business value sooner as part of peak season 2025, Original plan was to get this all delivered as part of April '26. i) Phase 1 - July '25 (all items within RMIC) ii) Phase 2 - April '26(changes related to GDX/offline automation) There is 100 % commit from RMIC leadership and team, including testing resource for delivering Phase 1 as part of July '25 CSR without any tradeoffs to any other initative currently in-flight in RMIC for July '25 --------- update week of 3/31/25 EPMO requested to update ppm 594981 with PV6762 but unfortunately, IT Manager, IT lead, Business lead are able to update PPM tool with PV number. It appears to be non editable field update week of 3/24/2025: - submitted for SL3 gate and its going thru approval process - update week of 3/17/2025 a) created new bucket in PV to capture profession fees, and with this, we have separate bucket for wages & salaries and the other one for professional fees costs b) Cortney Gonzalez and David Walker aligned on architecture documentation link and are good with next steps ------------------------------------ update week of 3/10/2025 Still waiting for architecture documentation from Trevor this is one of the pre-requisite deliverables to get to L3 submission ----------------------------------------------- Update week of 3/3/2025 Received Greenlight from CPEL for SL3 submission (Dav Murry/April Zhou) EPMO needs below pending active steps completion for L3 submission in PV a) update portfolio cost for the initative and seeking finance review - done b) reached out to RMIC architects for latest SHLD/Architecure documentation (Trevor/Pankaj) - w/Pankaj/Trevor and in-prgress c) reached out to IT team for update PPM w/latest planview details - w/Santhosh - in-progress --------------------------------------- * update week of 2/24/2025 received portfilio cost from finance team and green light from Commercial for proceeding for L3 ; will submit SL3 post finance update in planview this week. ---------------- Update week of 2/17/2025 July '25 CSR - Solutioning within RMIC (Pricing ARTs) in progress Oct '25 CSR - Not Started (any backlog items from July '25) Jan '26 CSR - Not Started (mainly Offline Automation/GDX changes) --------------------------------------------------------- Status Update - Week of 8/12 Expected L2 Approval 8/31 Status update 8/26 - continuing to work on the business case and once fully vetted with finance, we will submit for L2 (ETA 9/13) Status update 9/2/24 1) continuing to work on business case with analysis team 2) Submitted CPEL commercial intake form Status update 9/10/24 ) continuing to vet on finance business case; addressed concern around GRI revenue.. it would be considered as part of 'Keep lights on' bucket Status update : 9/23/24 per finance recommendation, we changed the initiative as "Enabler Initiative" as this initiative is protecting revenue of $49.8M | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-16 | 2026-04-30
Business w/ Tech Initiative: LAC - DIM Weight Capture Initiatives | 30800 | 6789 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Silvia L. Gonzalez Alonso | On Track | 4/13 - Updated Mar'26 Financials. Second month in L5 3/12 - Updated Feb'26 Financials. First month in L5 2/11 - Updated Jan'26 Financials. This is the 3rd months of mature benefits required before submitting to SL5. Submitted to L5 1/19 - Updated Dec'25 Financials 12/16 - Updated Nov'25 Financials 11/18 - Initiative approved to move to L4 10/10 - SJORT machine was moved into SRSP production enviroment 10/8 - Replacement APU component delivered. Installation to start on 10/8 10/1 - SJORT hasn't MTP due to fatal failure of APU component. Vendor ordered new part from Germany and installation should be complete before the end of October. As a result, L4 date moved back one month. 9/5 - SJORT installation completed, but pending move to production due to the vendor reviewing file transmission issue.As a result, L4 date moved back one month. 5/6 - QROR - Installation to be completed this week. SJORT manufacturing in process and will be shipped in June (July Installation). 3/11 - QROR - Shipment to be received in May. SJORT - Invoice received, payment to be completed this week. TLCR - Installation completed and moved to production. 2/18 - QROR - Payment completed, shipment to be received in May. SJORT - Purchase order sent to vendor, manufacturing to begin. TLCR - Installation continuing and expected to be finished this week. 2/11 - QROR - Payment completed, shipment to be received in May. SJORT - Purchase order sent to vendor, manufacturing to begin. TLCR - Installation has begun and expected to be finished this week. 1/28/2025 - QROR - Payment pending; 2/4/2025 - QROR - Payment pending; Manufacturing will begin once received SJORT - Activated in Encore, pending purchase order. TLCR - Installation has begun and expected to be finished this week. 1/28/2025 - QROR - Payment pending; Manufacturing will begin once received SJORT - Activated in Encore, pending purchase order. TLCR - Payment received; Installation on track for first week of Feb. 1/21/2025 - QROR - Invoice is approved and payment will process this week; SJORT - Activated in Encore, pending purchase order. TLCR - Invoice is approved and payment will process this week; Installation on track for first week of Feb. 1/14/2025 - QROR - Invoice is with finance for checking and payment processing Legal is reviewing bonds; SJORT - Activated in Encore, pending purchase order. TLCR - Payment was being reviewed for REPSE approval. Installation to be completed 1st week of Feb. 1/7/2025 - BQNRT- Completed. QROR - Legal is reviewing bonds; SJORT - SOW signed and returned to FedEx to be activated. TLCR - Payment was being reviewed for REPSE approval. 12/17/2024 - BQNRT- Approved to Move to Production. QROR - Vendor signed SOW and pending activation in Encore; SJORT - Socializing to vendor for signature of SOW. TLCR - Pending PO to be generated in Encore for vendor to issue invoice. 12/10/2024 - BQNRT Testing taking place today; TLCR-Pending VP approval to move forward with payment. QROR - Vendor signed SOW and pending activation in Encore; SJORT - Advised requestor to send for signatures. 12/3/2024 - BQNRT Additional testing is being performed this week; TLCR-SOW acitvated in Encore, issue paying invoice (call set up with teams to resolve). QROR - SOW has been signed by FedEx, sent to vendor to complete; SJORT - SOW pending sourcing to issue for signatures. 11/26/2024 - BQNRT -File issue resolved, completing testing for MTP; TLCR-SOW acitvated in Encore, pending vendor invoice to complete payment. QROR - FedEx legal and SICK have agreed to SOW, socializing for signatures; SJORT - SOW approved by Accounting, will now be sent for signatures. 11/19/2024 - BQNRT - Installed and pending move to production (vendor investigating issue with file); TLCR Pending activation in Encore to initiate Purchase Order to vendor. QROR - FedEx legal has responded to vendor feedback; SJORT - SOW approved by Legal and is now pending Accounting aproval. 11/12/2024 - BQNRT - Scheduled to be installed this w | K: L5 | Active | L5 | 2024-01-01 | 2025-11-03
Business w/ Tech Initiative: Split Billing IncoTerms (Linked to GAF #95174) | 30050 | 6963 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Sharon Pewitt, Chris Gibney, David Athow, Nekia Thomas | On Track | January 2026- RMIC elevated to Sr. Management that this initiative requires a pricing initiative to be in place prior to Split Billing Incoterms being enabled. The decision on pricing methodology is P2P with no commercial priroity to work at this time. Pricing needs to make a decision as to the status of this initiative which may be renamed to support the P2P pricing work thus the decision to put this initiative On Hold until a P2P initiative priority is confirmed. March 2024 - To be prioritized as a result of initiative re-review. Previous status rationale: Will be pursued after high priority items are implemented. | E: L2 | On Hold | L2 & CCH
Business w/ Tech Initiative: Canadian MSDS Dimensional Data Capture Expansion | 33259 | 6966 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Negar Solgi, Gunter Loh, Mehraj Saju | On Track | 10/30/2025 All units are online and in production. 8/19/2025 All units are online and in production. 07/09/2025 All the DIM units are now in production and capturing scans and dimesions. 07-Jul-2025 YIBA800 & YKZA728 in production, no change YYZR 3rd FLR Sort System EOL * Both units (AS01 and AS02) installed and live. * FDX signoff complete. Pallet DIM YYZRT - In production, no change. Waiting on steady state to report performance. Pallet DIM YMXRT- In production since May. Pallet DIM YYCRT- Measurement Canada inspection completed and they certify the unit and we are waiting for the system to go to production and move to L4. 02-May-2025 YIBA800 & YKZA728 in production, no change YYZR 3rd FLR Sort System EOL * Both units (AS01 and AS02) installed and live. * FDX signoff complete. Pallet DIM YYZRT - In production, no change. Waiting on steady state to report performance. *YYCRT & YMXRT The issue on the PC communication has been resolved and now we needc to do the production test for both system so that we can generate the invoice for Measurement Canada and then Measurement Canada needs to come onsite for inspection. YMXRT is scheduled for next week. 10-Mar-2025 YIBA800 & YKZA728 in production, no change YYZR 3rd FLR Sort System EOL * Both units (AS01 and AS02) installed and live. * FDX signoff complete. Pallet DIM YYZRT - In production, no change. Waiting on steady state to report performance. *YYCRT & YMXRT - the systems have been installed but the YYCRT840 and YMXRT860 have been delayed to what has been described as communication issues; no communication is coming from the PCs. MT technician has cloned one of the devices that was not communicating at YYZR to the good Windows 10 that is working. Apparently there were some differences between the PCs that were set up in YMXR and YYCR from what they set up in YYZR. The good news was that the system communicated on Port 22 after the clone. MT needs to installed the new cloned PCs in YMXRT and YYCRT and test to see the issue is resolved. When the issue is resolved, we can move forward with production testing and Measurement Canada inspection in order to put the units in production. 11-Feb-2025 MSDS - In production, no change. YYZR 3rd FLR Sort System EOL * Both units (AS01 and AS02) installed and live. * FDX signoff complete. Pallet DIM YYZRT - In production, no change. Waiting on steady state to report performance. *YYCRT & YMXRT - the systems have been installed but the YYCRT840 and YMXRT860 have been delayed to what has been described as communication issues; no communication is coming from the PCs. These 2 systems are not connecting to the COLO. We have escalated the issue. We are having joint working sessions with FedEx and Mettler technical experts to resolve the issue. I can not provide a firm date on when we are able to move from L3 to L4 but we are doing everything we can to have these 2 units issue resolved and move them to production ASAP, it depends on when the team will be able to find the solution for the issue. 08-Jan-2025 MSDS - In production, no change. YYZR 3rd FLR Sort System EOL * Both units (AS01 and AS02) installed and live. * FDX signoff complete. Pallet DIM YYZRT - In production, no change. Waiting on steady state to report performance. *YYCRT & YMXRT - Waiting on commissioning step, unable to generate heartbeat connection. Expanded to FedEx Network team and Firewall teams--They confirmed that no firewall is blockedf from FedEx side and vendor is blocking one of the ports and vendor has been requested to propose a solution ASAP. 09-Dec-2024 MSDS - In production, no change. YYZR 3rd FLR Sort System EOL * Both units (AS01 and AS02) installed and live. * FDX signoff complete. Pallet DIM YYZRT - In production, no change. Waiting on steady state to report performance. *YYCRT & YMXRT - Waiting on commissioning step, unable to generate heartbeat connection. Expanded to FedEx Network team and Firewall teams--They confirmed that n | K: L5 | Active | TEMP L5 - Enter L5 | 2023-12-19 | 2025-07-30
Business w/ Tech Initiative: Add Taxes to Offline Rate Quotes from Rating EBS R | 80818 | 7034 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Chris Wilson, David Athow | On Track | We are in the beginning of this project. Expecting to pick up the pace. 8/6/2024 - Had a great conversation regarding the financials. Need to get a better understanding about the cost associated with this project. Will be reaching out to impacted teams to get a better idea of how much this will cost. 8/13/2024 - Had a meeting with IT stakeholders who gave a Medium T-Shirt size. I will update the cost estimate and will send this information to Mark and Jennifer for review. 9/5/2024 - I updated the L3 date. To go to L3 the project will need be planned out. Theis will require CPEL and PRT. Since CPEL is not looking at project that have small or no NRB, the L3 date will need to be pushed. Pushed out a month. 9/24/2024 - I have the CPEL meeting tomorrow for prioritization. 11/12/2024 - This project needs a IT owner and a IT lead. This project will be worked in CPEL order. 12/9/2024 - Submitted Portfolio Greenlight. 11/20/2025 - Project does not rank high enough to be picked up. Will remain as is until higher priority is given. | G: L3 | Active | TEMP L3 - Enter L3 | 2026-04-24 | 2026-07-21
Business w/ Tech Initiative: Global Air Freight Contract Exchange Rates | 94076 | 7036 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Nekia Thomas, David Athow | On Track | Project Execution | K: L5 | Completed | L5 | 2025-05-02 | 2025-07-30
Business Only Initiative: GAF - Global Air Freight P&RS Business Case | 95174 | 7038 | Business Only Initiative | Commercial - Revenue Quality | Commercial | Nekia Thomas, David Athow, Douglas J. Mengwasser | On Track | Completed Business Case, will submit to L2 soon | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Express Freight Multiple Shipment Detection | 83779 | 7088 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ian Freshwater, Daniel Newton | On Track | Delayed until January due to higher priority items like duplicate data within our databases. That issue needs to be addressed first before MO can continue. Original scope included Dataworks impact which has now been deprioritized. Updated implementation costs to reflect the development conducted by vendor for manual MO detection process. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-19 | 2026-06-10
Business w/ Tech Initiative: New Extra Small Box Package Type: Express Services | 58586 | 7251 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Jermaine Pope, Kelsi W. Neeley | On Track | 2/2/2026 - MARKET LAUNCH 11/6/2025 - Talked to ESPM and Domain Finance. Had contribution margin in the system previously (Finanace and Pricing alignment and approval). Changing it to operating margin because it is the required margin to use in Planview. 10/23/2025 - Changed Initiative name and clarified Scope Description 10/14/2025 - Moved to L3 - Solutioning in Progress 4/23/2025: Moving towards L3 - Changing Owner to Jermaine Pope | I: L4 | Active | L4 | 2024-04-01 | 2030-12-06
Business w/ Tech Initiative: Offer flexibility on pricing (bid platforms) to be | 70788 | 7289 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Daniel Montenegro, Kalyan Bhavaraju | On Track | 06/26/25 Initiative is ongoing, but the need for IT has not appeared. On Planview I am changing the status to cancel. There is another Planview request that is moving for SPOT PRICE API which will benefit Bid Board Initiative. 08/27/24 3rd Party Bid Board Status: Pursuing participation on AOD Platform. FedEx legal and AOD legal working through aligning on an agreement to participate on platform Shipper Owned Bid Board Status: As of 7/25 Concierge Desk took over process to support Energizer Bid board and initial results has been positive securing over $130K in revenue and winning all bids submitted. Concierge Desk team turning attention to supporting Edgewell and also assessing other bid boards to apply same process as Energizer 06/26/24 As per management this Drive initiative will be cancelled. Once the API is built (which is already in progress) this initiative will not require heavy IT investment. Growth of this initiative will depend on adoption and can be handled by both Sales & Marketing pursuits. The initiative will still be reported and reviewed at the RMC 04/23/24 Met with Ben Sauls and Jennifer Liu on 4/22 to ask if its ok to add a negative OM as the impact, because right no Global Air Freight is running at negative margins which could change in the future once network and costing for the network are aligned. Current Global Air Freight business results in positive CM% 4/19/24 Update provided that AOD and Freightos are the first 2 platforms that will be pursued to join. Both platforms have provided forms to complete and review in order to join that will be sent to legal for review and guidance **Previous Status** Three 3rd party vendors have Demo'd their platforms. Vendors not willing to release data that can help with a revenue estimate. Due to absence of data from platform, I have asked Sales folks on our core team if there is a high-level revenue number they are willing to commit if we were to participate on a bid board platform | C: L1 | Cancelled | L1 Data Migration - TEMP
Business w/ Tech Initiative: ANCHOR PLC - Change International AHS/OS Surcharge | 9458 | 7875 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | David Athow, Srinivas Reddy Busi | On Track | 8/12/2024: Project on track. Money-making portion is making money and remaining support features being worked. 8/19/2024: Project on track. Money-making portion is making money and remaining support features being worked. 8/26/2024: Project on track. Money-making portion is making money and remaining support features being worked. 9/2/2024: Project on track. Money-making portion is making money and remaining support features being worked. 9/9/2024: Project on track. Money-making portion is making money and remaining support features being worked. 9/16/2024: Project on track. Money-making portion is making money and remaining support features being worked. 9/23/2024: Project on track. Money-making portion is making money and remaining support features being worked. 9/30/2024: Project on track. Money-making portion is making money and remaining support features being worked. 1/14/2025: Final features loaded with Jan. '25 CSR. | K: L5 | Completed | L5 | 2022-10-12 | 2024-04-15
Business w/ Tech Initiative: Surcharge - Oncall Pickup Waivers | 2363 | 8060 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Nil Mishra, Helen Long | On Track | Team is working to pull together financial details for L2 Finance approval. Repair systematic Oncall Waiver Application. Team will work IT systems to repair/fix application to query if Shipper Account is currently in Regular Status with either FXE or FXG. Seek to systematically or manually remove misaligned Oncall Surcharge Waivers. Update 9/29/23: Around 95K accounts had On-Call waivers erroneously removed during July '23 CSR implementation, impacting 336,713 Dom/Intl Express shipments which were re-rated for credit/refund. The waivers for impacted accounts were restored by 9/1 and credit/refund are being processed. Post measurement will start in mid-October for period starting on 9/1 due to this issue. Update 11/22/23: Based on the latest 2 months (Sept-Oct’23) performance, Incremental Revenue Impact from Dom On-Call Pickup attributed to waiver cleanup initiative is estimated at $9.7M, ($1.5M) below estimate. We have updated the forecast for November 2023 onwards. Update 12/20/23: Based on the latest 3 months (Sept-Nov’23) performance, Incremental Revenue Impact from Dom On-Call Pickup attributed to waiver cleanup initiative is estimated at $10.2M, ($1 M) below estimate. We have updated the forecast for December 2023 onwards. Update 1/23/24: Based on Sept’23-Dec’23 performance, incremental revenue impact from Express On-Call Pickup attributed to waiver cleanup initiative is estimated at $11.1M, ($0.1M) below estimate. We have updated the forecast for January 2024 onwards. Update 2/26/24: Based on Sept’23-Jan’24 performance, incremental revenue impact from Express On-Call Pickup attributed to waiver cleanup initiative is estimated at $10.7M, ($0.5M) below estimate. We have updated the forecast for February 2024 onwards. Update 3/22/24: Based on Sept’23-Feb’24 performance, incremental revenue impact from Express On-Call Pickup attributed to waiver cleanup initiative is estimated at $9.9M, ($1.3M) below estimate. Despite all-up Dom Exp ADV decline of (3.7%) and Dom On-Call ADV decline of (24.0%), $9.9M Incremental revenue is realized due to removal of On-Call waivers from customers no longer on regular pickup. We have updated the forecast for March 2024 onwards. Update 4/11/24: Based on Sept’23-Mar’24 performance, incremental revenue impact from Express On-Call Pickup attributed to waiver cleanup initiative is estimated at $9.3M, ($1.9M) below estimate. Despite all-up Dom Exp ADV decline of (3.5%) and Dom On-Call ADV decline of (22.0%), $9.3M Incremental revenue is realized due to removal of On-Call waivers from customers no longer on regular pickup. Forecast for April 2024 onwards has been updated. Update 5/20/24: Based on Sept’23-Apr’24 performance, incremental revenue impact from Express On-Call Pickup attributed to waiver cleanup initiative is estimated at $8.8M, ($0.5M) below the revised forecast annualized impact. Despite all-up Dom Exp ADV decline of (3.6%) and Dom On-Call ADV decline of (21.0%), $8.8M Incremental revenue is realized due to removal of On-Call waivers from customers no longer on regular pickup. Forecast for May 2024 onwards has been updated. Update 7/10/24: Based on the post period of Sept’23 to May’24 performance, the actual annualized incremental Revenue is at $7.7M, which is ($3.5M) below estimate. Significant decline in the On-Call volume prior to July’23, primarily contributes to the revenue gap. The Actual On-Call Waiver % is 69%, which is 2% higher than the commercial waiver (67%) used in Incr. Revenue estimation was an additional factor contributing to the revenue gap. Update 7/25/24: Based on the post period of Sept’23 to June’24, the actual annualized incremental Revenue is at $7.6M, which is ($3.6M) below estimate. Significant decline in the On-Call volume prior to July’23, primarily contributes to the revenue gap. The Actual On-Call Waiver % is 69%, which is 2% higher than the commercial waiver (67%) used in Incremental Revenue estimation was an additional factor contributing to t | K: L5 | Completed | L5 | 2023-02-14 | 2023-08-16
Business w/ Tech Initiative: Delivery Area Surcharge - Zip Changes | 61595 | 8133 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Sameer Mohammed, Venkata Peraka | On Track |  | K: L5 | Completed | L5 | 2023-11-13 | 2024-01-01
Business w/ Tech Initiative: Dynamic Pricing - Spot Pricing Reco. Engine | 13376 | 8195 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Yang Tan, Yaqin Li | On Track | * 08/07/2024 - Finance reviewed and approved the numbers. Waiting for TCH greenlight which is expected soon. * 08/20/2024 - Still waiting for TCH greenlight. Got approval from DW team and will follow up on the progress. * 02/17/2025 - Launched 12 US Export lanes. Plan to launch the remaining lanes in April. On track. * 03/19/2025 - US validation in progress. On track. * 03/26/2025 - Additional 32 lanes will be launched for US in April. On track. * 04/02/2025 - Additional 32 lanes were launched for US on April 1st. On track. * 04/14/2025 - Performance tracking for the 32 lanes in progress. On track. * 04/22/2025 - Vlidation of remaining lanes in progress. On track. * 06/05/2025 - Additional 92 lanes were launched for US today. On track. * 06/09/2025 - Completed UAT cycle 2 for regions. Will provide cycle 3 output this week. * 06/26/2025 - Provided US rates generated by business rule logic. Testing in progress. On track. * 07/21/2025 - Incorporated feedback for business rule logic output. Testing in progress. On track. * 08/08/2025 - Finalizing around 150 US Export lanes for launch. On track. * 08/20/2025 - Launched 151 US Export lanes using business rule logic. * 09/10/2025 - Finalizing the remaining US Export lanes for launch. On track. * 10/08/2025 - Launched another 235 US Export lanes in PROD. On track. * 11/10/2025 - Feedback loop implementation in progress. On track. * 12/09/2025 - Picking 5-10 lanes from each region to test out the market. On track. * 01/05/2026 - Implemented 5 lanes fof Feedback loop. Awaiting feedback. On track. * 01/19/2026 - All US lanes are launched for SPRE. * 02/09/2026 - Working to provide rates for regions. On track. * 03/11/2026 - Provided rates to non-US regions. Awaiting feedback. * 04/08/2026 - SPRE rates have been shared across multiple export lanes for non‑U.S. regions, and the regional teams are currently identifying lanes to test the market. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-07-17 | 2028-07-12
Business w/ Tech Initiative: Dynamic Pricing - Early Warning System for Shippi | 14562 | 8236 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Aswin Kumar Ramanathan, Sohail Mohammad | On Track | 4th April, 2025: All milestones completed. Financials Actual Complete. Ready to submit to L4, need architecture documentation and costs. Old: Completed the review with Jennifer and Halirou from Finance team. We have been asked to submit for L2 approval. | K: L5 | Completed | L5 | 2022-10-17 | 2025-04-04
Business w/ Tech Initiative: eMBP Transformation | 14185 | 8407 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Chris Strickland, Padmaja Soundararajan, Jiayu Pi, Songnian Zhao, Rahul C. Tiwary | On Track | Extending through 5/27, all current builds on track | G: L3 | Active | TEMP L3 - Enter L3 | 2023-03-01 | 2028-01-31
Business w/ Tech Initiative: SAP BO Replacement | 96066 | 8424 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Donyae Scott, Vasudevan Gopal, Scott M. McQueen, David Athow | On Track | **2/17/2026** - Outcome of Friday - 2/13/26 - The team was able to nail down 3 options to present to leadership - SAP BO Upgrade, Power BI + Databricks, and Power BI Fabric. They are meeting again on Wednesday to finalize on the solution matrix presentation that will be used to help make a decision on a solution. **2/13/2026**- Meeting with Architects to finalize solution options for upcoming presentation to leadership. **2/3/2026** - EA made progress on the conceptual architrecture using Power BI + Databricks as a solution. Next steps, EA to present the Power BI + Databricks proposal to a solutioning team for further analysis. They plan to finalize the technical documentation and submit it to the team today. Architecture option assessment and risk matrix - WIP - Pending Results from EA. **2/2/2026** - RITM7916076 Accounting SAP BO Migration (Planview 8424) Solution Feasibility Discussion meeting scheduled. Reviewing LBC. Prepping for submission to L3. **1/30/2026** - Two solutions identified - 1. Power BI + Databricks and 2. 2.Migrate to SAP BO SaaS / BO 2025+. Technology owners notified for engagement. Held MD & Manager meeting - MD plan to escalate due to critical timeline. **1/20/2026** - First technical Deep Dive Meeting held on 1/19/26 with the second Deep Dive meeting being held today. The second Deep Dive meeting will focus on reviewing the SAP BO Universes in-scope for DRIVE Initiative 8424 and discussing the migration of GREEN/RevRec and Enable/AR reporting off legacy SAP BO. • Highlevel Timeline: Next 7 days: Universe review + data validation Next 14 days: Architecture option assessment and risk matrix By Jan 31: Leadership alignment on direction **1/6/2026** - Followed up with Sandeep Bahadur (EA) on the architectural items. • Sandeep informed us on 1/5/26, that he reached out to the team and the Tech Lead with Power BI expertise to get an answer on “Validate the Power BI governance patterns for SOX compliance”. **11/11/2025** - Updated 'Request Type' field and added David A. as an IO. Submitted PDSM ticket to get the following fields updated - Primary Type of Value Impact, Enterprise Strategic Initiative (ESI), Business Process and/or Operational Impact, Ability To Statements, What is the time criticality?, and Impacts Data & AI Portfolio?. Also, cleaned up the Brief Demand Desciption. **10/23/25** - Financial section and attached the Commericla Financial file. **10/22/25** - Updated Milestones and Money Step dates to align with Jan 2027. Submitted PDSM ticket to update PPM # to 1811981. **9/29/2025** - Submitted for L3, however, forgot to add KPIs before submitting. But the Financials were updated for the implementation cost to reflect the T-Shirt size. **9/26/2025** - Updated Demand Description, Impacted Region(s), Updated Primary Value Type, and Uploaded Architectural Documentation. * Working with Accounting team on Business Case to submit extension of SAP BO. | E: L2 | Active | L2 Feedback Requested | 2025-08-11 | 2027-01-01
Business w/ Tech Initiative: Modernize Ground Rating Engine For Ground Commerci | 9459 | 9097 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Jamie Johnson, Sushma B. Pattanshetty | On Track | 04/09/26: Coordinating with Platform to delete Epic for Duplicates, received confirmation on timeline for Epic for eRD to EIW Epic. 03/25/26: Return to CPEL to cancel Epic for Duplicates, add Epic for eRD data to be populated in EIW for GRI Analysts. Epic for Duplicates can be done at a later date, if needed- but there are other intiiatives in flight that should reduce the impact of the duplicates. 03/15/16: Market Launch for GRM VB2 Billing 03/11/26: Go/No Go decision meeting- GO was approved 03/10/26: Updated milestones to reflect new market launch date for the first part to 3/15/26, even though the tool does not allow for weekends to be completion dates. 09/03/25: New Money Step identified, updated to 10/31/25 with delays in project due to data gaps and testing challenges 07/09/24 - Conditional go for moving online rate quotes to prod, target date 7/19. Target CPEL on 7/17 to triage additional scope for Collect payor 8/20/24 No updates 9/20/24 Actuals entered for August 2024 are only for external, not both external and internal resources combined like previously reported 9/27/24 Added new milestone for accounting reporting/revrec solution needed 10/8/24 In-progress of determining if we need to go to TCH for new milestone (above), added actuals for Sept 2024 10/10/24- Advised to move back to L2 for evaluation of storage needs for RevRec data 11/22/24 - Financials have been adjusted for additional cost- for revrec storage. Estimated implementation cost is now $8.8M. CLEAR 9012182 will cover additional cost needed, comments from IT MD: "Yes, there is enough in the CLEAR to cover the $822k ask in either FY26 or FY26. Here is a summary: •Overall program CLEAR oApproved in the CLEAR: $27M oActual projected spend: $11M ($9M surplus) •FY25 Forecast: oApproved CLEAR spend: $7M oActual projected spend: $5M ($2M remaining)" Enabeling future intitiatives: Backhaul pricing for market place growth, and Day of the week pricing (inits tbd) KPIs reflected in Finances are related to savings from a projected reduction in recoveries as a benefit from this project. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-02-14 | 2026-07-31
Business w/ Tech Initiative: DP/BRE - Apply Global Peak Surcharge by Origin/Des | 9463 | 9098 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Isha Gupta, Clark Grantham | On Track | -2/25/2025: Updated the actuals till Jan 31st. Submitted to L5. -2/17/2025: Updated the actuals till Jan 26th. Need to wait for a few more days to capture actuals for the month of January, post that the initiative can move to L5. -1/16/2025: Updated the actuals till Dec 2024 -11/15/2024: Updated the actuals from Sep. 16th-Oct 27th 2024 -9/16/2024: Global Demand surcharge was successfully launched in the market on September 16th for US, CA and LAC outbound to AU, NZ at the OD country lane level. -8/21/2024: in consultation with team, noted that costs associated with this product to date are from baseline IT capacity. therefore, inputting 0 incremental cost in "impacts" section -5/21/2024: Updated the Business Case with Fy2024 Numbers. -4/1/2024: Uploaded the responses to the TCH Questionnaire -3/28/2024: L3 date has been moved from 4/1/2024 to 4/22/24 as the initiative needs to get the TCH green light. -2/16/2024: L3 date has been pushed from 2/1/2024 to 4/1/2024 as this was a late entry for July'24 CSR and analysis and solutioning work got pushed to Feb. --Reopened on August 2nd 2023 as requested by CPEL team (David Walker). This initiative needs to be brought back into the pipeline and reprioritized for Oct 2024. Sohail will go back to Jennifer to review. Finance will review later after they have bandwidth. low priority now. Betty: effort in Global Peak by O&D is paused, due to prioritization & resource constraints. | K: L5 | Completed | L5 | 2023-12-27 | 2024-10-31
Business w/ Tech Initiative: Increased Capture of Express Operational Data | 11994 | 9155 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Benjamin Stuart, LJ Bowman, Cortney Gonzalez, Jeff Maddern | On Track | 2/3/25: GoldenEye report testing is still in flight. HCH DA team, Dataworks team and the business team are all engaged in the comparison testing between the existing HCH DA report and the new Dataworks report. Based on testing this week we expect to have an idea on the new L4 date. 1/10/25: GoldenEye report testing is continuing. HCH DA has high priority items that is limiting availability for testing. We have requested dedicated testing support from the team for the next PI. 12/3/24: All spend is complete and revenue is being delivered with the completion of the first phase of GoldenEye. The only remaining item to migrate to L4, is the completion of the new GoldenEye report by Dataworks. Business is working through testing the reports and is waiting on the HCH DA team to be able to support continued testing. 10/4/24: Due to Wave freeze and vacations, Sept data loaded early. Due to invoicing cycles, there is a potential that some numbers are lower than actual. After the migration to Planview these numbers will be reevaluated for accuracy. 10/1/24: Updated DW milestone perr feedback from Preet 9/16/24: GE is continuing to be worked in expedited manner and discussed weekly at SVP level for prioritization. 8/28/24: GoldenEye is being expedited to try and catch back up. Also expanding scope to include 10 more devices. Updated milestones and financials for DW based on feedback. 8/20/24: July numbers loaded. Need to add costs from GoldenEye Phase 1. Waiting on Properties PM to provide data. 7/18/24: June numbers loaded. DW dev complete so $0 monthly now. Waiting on cost updates for GoldenEye Init from Properties PM. 5/20/24: All impacts and actuals for April updated except DataWorks, request sent and waiting on response. Impacts and Actuals reduced from March to April due to volume reductions in INDH. 4/29/24: Updated DW numbers in Impacts tab for March. Completed milestones for PIP US and Multi-side. 3/22/24: DW Milestone updated. "[3:40 PM] Preet Abraham Hey LJ could you please move this milestone out to end of March as we are still working through the deployments of MVP1 tasks." 3/8/24 This effort is 6 projects. 2 projects have completed rolling out. 3 are in flight with the last of those just launching last month. 1 project is delayed due to documentation required for construction and facility modifications. Not expected to impact L4 date, but will report back if it gets closer. | K: L5 | Completed | L5 | 2023-01-24 | 2026-05-29
Business w/ Tech Initiative: Pickup PFS Value Bundle 1: One FedEx Rating | 15306 | 9204 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Harvey Zhang, Ayushi N. Sheth, Dawn Komoroski, Dana Story, Yen Ju Chiang | On Track | 4/2/26 - Greenlighted from EGC to swarm Epic C defect on Ground Data. Kickoff assessment and decomp. -Hosted all Sales webinar on 9/29; using Q&A list to update HighSpot and inform other Go-To-Sales support activities -Per customer feedback, adding messaging into Standalone Pickup scheduling flow to clarify that pickup fees will apply | G: L3 | Active | TEMP L3 - Enter L3 | 2023-08-01 | 2026-07-31
Business Only Initiative: Short Term Contracts (Enabler for GAF #95174) | 30045 | 9342 | Business Only Initiative | Commercial - Revenue Quality | Commercial | Chris Strickland, Nil Mishra, Nekia Thomas, Dawn Komoroski, Znan Ram Harish Gutta | On Track | On Track | K: L5 | Completed | L5 | 2024-05-21 | 2025-07-25
Business w/ Tech Initiative: FXF Dimensional Capture Processes to Send FXE Dime | 83783 | 9481 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ian Freshwater, Benjamin Stuart | On Track | Development moved to production week of Jan 13th | K: L5 | Completed | TEMP L5 - Enter L5 | 2024-09-02 | 2025-01-15
Business w/ Tech Initiative: Reactivate Philippines Fuel Surcharge | 23707 | 9510 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Hannah Vandermaas, Mimi Yiu | On Track | Project has been launched and is currently being applied to all shipments that are applicable as of January 1st, 2024. | K: L5 | Completed | L5 | 2023-10-31 | 2024-01-01
Business w/ Tech Initiative: QP Spot - Ground and US Domestic Freight |  | 85719 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Katarzyna Bielanska, Jamie Johnson | On Track | Business case completed. Tech review on Thursday, 12/19/24 impacted: QP, Rating, Invoicing conversation with Trevor/Joel: QP was going to retrieve the US domestic rating datautilizing one of the existing interfaces that QP currently consumes (CRSV, VRS) Per Adi Banga: RMIC + QP, no GDX, no clearance (domestic shipments), no supply chain (US express product codes only F1, F2, F3) | G: L3 | Active | TEMP L3 - Enter L3 | 2026-04-01 | 2027-02-08
Business w/ Tech Initiative: Minimum Billable Weight for AHS Dim |  | 79817 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Yvette D. Woody | On Track | Status Update week of 4/21 -Actuals for month of Mar'25 have been entered Status Update week of 4/14 - No change still waiting on actuals for Mar'25 Status Update week of 4/7 - No change still waiting on actuals for Mar'25 Status Update week of 3/31 - No change still waiting on actuals for Mar'25 Status Update week of 3/24 - No change in status Status Update week of 3/17 - Received actuals for month of Feb'25 entered Status Update week of 3/10 - Waiting for actual for Feb'25 Status Update week of 3/3 -Actuals for month of Jan'25 have been entered Status Update week of 2/24 - Will include actuals this week Status Update week of 2/17 - No change in status Status Update - Week of 2/10 - Project is launched and results are pending on track - all good | K: L5 | Completed | L5 | 2025-01-13 | 2025-01-13
Business Only Initiative: Adding Dangerous Goods and Address Correction to F | 92708 | 8711 | Business Only Initiative | Commercial - Revenue Quality | Commercial | Dana Story, David Athow, Cortney Gonzalez | On Track | 08/23- On track for L2. We plan on submitting the Business Case and submitting the project for L2 by the end of next week, 08/30. 09/03- Submitted to L2. There's no CCH this week, so we will be going to CDR and presenting. Working towards L3, due date 09/13. This project went to CCB, Tech Surge, and we are working on getting it into CPEL. 09/10- awaiting L2 approval. 09/18- In L2 status. Split the init into 2 phases. This init #92708 is Phase 1 and its scope is Domestics and PR-US, US-PR, and PR-PR. Phase 2 init #95974 is International Express and Ground which launches in January 2025. 09/24- Awaiting approval for L3. L3 is required before we can launch in October. 10/01- Awaiting approval for L3. 10/31- Launched on 10/14/2024. Going to submit proof of launch and submit to L4. 11/18- Waiting on approval for L4 11/26- Waiting on approval for L4, approval right now sits with Matthew Hicks 02/18- We've tracked 3 months of revenue, so we are submitting for L5 | K: L5 | Completed | L5 | 2024-08-22 | 2025-01-31
Business w/ Tech Initiative: Adding Dangerous Goods and Address Correction to F | 95974 | 8712 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Dana Story, David Athow, Cortney Gonzalez | On Track | 09/18- Initiative created. This init is Phase 2 for the "Adding Dangerous Goods and Address Correction to Fuel Surcharge Calculation" project. Phase 1 is Init #92708. Submitting to L2. 09/24- Awaiting approval for L2 10/01- Awaiting approval for L2 10/31- We won't have Architectural Documentation since this is such a simple change. Need to progress to L3 without it. This init Demand Type should be listed as Business impact only since we do not need to attend the tech review. 11/08- Need this init to be public, not confidential. This is causing significant issues, and there is no intuitive way to change this setting in Planview. 11/18- Still waiting on this to be made non-confidential. 01/13/25- Launched to production today on January 13th. Sumbitting for L4 today. 05/05/25- Submitting to L5 status 09/01/25- Input non-rounded actuals. Resubmitting to L5 09/25/25- Feedback was that there are no actuals reported. There are actuals reported. Please check the Financial Plan section. Resubmitting to L5. | K: L5 | Completed | TEMP L5 - Enter L5 | 2024-09-18 | 2025-01-24
Business w/ Tech Initiative: Legal - Remove Minimums and Stop Rounding (in HCH) |  | 89357 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Heidi-Jo Shuttleworth, Phyllis K. Burns | On Track | 12/16 - Ready for L2 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Leverage legacy Ground autosorter images and data |  | 91294 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Scott Wallis, Carol Eskew | On Track | 4/22/25 - completed steps for L1 submission to L2. | E: L2 | Active | L2
Business w/ Tech Initiative: Modernize Express US Domestic Rating |  | 92081 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Jamie Johnson, Sushma B. Pattanshetty | On Track | 03/26/26: Project has not been solutioned, even though some enabler work has begun. Baseline was not available for updates in L2. L2 NRB includes cost savings from applications that will be retired when the project reaches the money step. L1 NRB- savings from retiring old system may offset cost of maintaining the new system- will fine tune costs in L2 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-10 | 2026-10-23
Business w/ Tech Initiative: Modernize Express Rating Data Source |  | 93041 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ian Freshwater, Jamie Johnson, Daniel Newton | On Track | 10.30.2025)/Update ESI and Update Enterprise KPI to none./Donyae Scott/Domain QA Expert Review L1 EA review complete with Bill Forcht | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: RIVITAI Phase 1 |  | 93319 | Business Only Initiative | Commercial - Revenue Quality | Commercial | Scott Wallis | On Track | 6/3/2025 - Financials and KPIs updated for May 2025 MVA 04/14/25 Updated KPIs and savings for March 2025 MVA. This project is already completed, and launched November 2024. We want this in Drive to formally track monthly savings for this project, along with providing insight to Dataworks for feedback in the work they provided to this project. | K: L5 | Completed | L5 | 2024-11-04 | 2024-11-04
Business w/ Tech Initiative: Dim Logic Selection Modernization |  | 94137 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Benjamin Stuart | On Track | Init is still in its early phase and remains on track. I do not expect the health status to change until demand planning and dev work begins. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: LAC - Chile DOM Enablement / Surcharge Activation |  | 96208 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Federico Del Real, Sandra Parras | On Track | Dec 29, 2025: Based on CPEL Review Nov 18, 2025 a SCO PRT is needed; SCO needs to prioritize the PRT There is currently no other information available from the local Chile Commercial team that would allow to boost this request in ranking; request to continue open until it can be prioritized with SCO; attached answers to Liz Umstot, EPM Oct 31, 2025: Updated Financials tab to remove FY28 exit rate of ~$11M and FY25 Costs of ~$6.6M USD as these are related to the Transportation revenue and not related directly to the surcharges revenue; updated soft benefits to -0-, loaded latest LBC and deleted old versions; Next Step: CPEL Nov 18, 2025 Oct 13, 2025: SP: Reviewed business case with Jennifer Liu, Marta Alarcon [Finance team] and Federico Del Real; changed baseline and L1 to reflect only the surcharge revenue that needs to be protected [not transportation + Surcharge as originally understood] ; changed request type to Innovation non AI Aug 18, 2025: SP: to ensure FP&A can access/ have a license Power BI Pro under Marta Alarcon' s team; use this project as basis for future reporting needs in Power BI as financials will need to be tracked in L5 Jun 6, 2025: Clarified that these are existing surcharges in the current portfolio, not new Apr 29, 2025: based on Eryn's feedback update the soft benefits to be the same as the baseline for revenue protection; updated the information based on architectural review of Mar 14, 2025; uploaded a new LBC with assumptions based on Amy Fletcher's feedback in PV93477 LAC Chile Freight to Collect initiative Apr 28, 2025: Updated P&L Soft Benefits to -0- and provided Portfolio list impacts for DOmain Business with Tech. Please note link for architectural review will be replaced after Triage meeting with David Walker's team Mar 11, 2025: Updated FY25 Baseline based on FY25 P&L forecast and expenses provided by FInance; Updated at very high Level T-shirt size and estimated portfolio impacts; attached summary of request, high level operational flow and High level P&L spreasheet for FY25 only; submitted to SL2 Updated for weekly report the PEO Name for Commercial | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: Unauthorized Surcharge Manual Capture |  | 104047 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Benjamin Stuart | On Track | this a duplicated effort. No longer needed. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FXF Earned Discount Decouple from Parcel |  | 96463 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Jagannadha R. Vuppalapati | On Track | There was a busines and MD alignment meeting as part off the project kikc-off on 02/10/2025 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2026-06-30
Business w/ Tech Initiative: Non-stackable Shipment Experience |  | 104645 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Christopher Seem, Nekia Thomas, Michelle Lee | On Track | This is an enabler that is just getting started up to support the GAF overall project, based on information gathered from the ANCHOR PLC project | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Enable Oracle ATA (LXF) 3rd party billing Solution |  | 105953 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Andrew Pellegrino | On Track | 12/23/2025 - Cancelling Planview initiative 105953 – “Enable Oracle ATA (LXF) Consignee & 3rd Party Billing Solution” due to AFI complexity and the low customer volume/limited return on effort. Recommendation is to cancel this request and for Marketing to create a new product for this service. Accounting has agreed to continue with the interim process for Samsung. Approval by Accounting is needed before any future customers/revenue uses the interim process. 10/08/2025 - Provided L2 documentation (https://myfedex.sharepoint.com/teams/EnterpriseArchitectureCommonRepository/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2FEnterpriseArchitectureCommonRepository%2FShared%20Documents%2FOps%20Model%20Architectural%20Artifacts%2FCommercial%2FRevenue%20Quality%2F105953%20%2D%20Enabler%20Oracle%20ATA%20LXF%203rd%20party%20billing%20solution&p=true&ga=1) and resubmitting to L3. 7/02/2025 - working to get the L1 LBC approved by Finance. 4/08/2025 - Woking with David Walker to get this intiative (Enable Oracle ATA (LXF) 3rd party billing Solution) on an architects list to create the impact assessment. 3/27/2025 - The planview initiative is currently not showing up in the prioritization dashboard because the dashboard has been frozen from 3/15-3/31 due to the ongoing FY25 to FY28 rebaseline efforts. The prioritization dashboard should be refreshed on 4/1 and this initiative will populate at that point in time. 3/21/2025 - This initiative recently was approved for L1, and has not been prioritized on the Enterprise Priority List. Will continue to monitor that list for initiative prioritization. Once prioritized this initiative will be pulled in by the assigned EA owner for review and creation of the Impact Assessment required during SL2 review. Please expedite due to associated revenue and low level of effort, targeting April 25' CSR. 3/20/2025 - Working to ensure this project has been entered into the demand management pipeline correctly. Completed Planview LBC for L1. Planview Seq. ID 105953 PPM Proposal #841244 | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: MBG Accuracy for MPS Shipments |  | 106202 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Laura C. Terranova | On Track | Update LBC | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: COM-RMIC-Invoice Delivery Flow |  | 108080 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Sharon Pewitt, Andrew Pellegrino | On Track | Iniative is well underway with concrete capabiltities at 100% completion and most if not all requirements documented reflective of each regions input. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-18 | 2026-05-29
Business w/ Tech Initiative: Global Dim Capture KPI Reporting (Golden Eye) |  | 109195 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Heidi-Jo Shuttleworth, CHAITRA ANNE | On Track | 05.13.25 - Primary Owner updated to Heidi-Jo Shuttleworth 1/12/26 - Initiative fell under Stop Work Criteria | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: COM-RMIC Extend Rated Charge Amount Field Limits |  | 109411 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Pamela Phillips, David Athow | On Track | 2/26/26: Added SCO as an impacted Portfolio, ART: LETS LAC 4/8/26 attached Data and AI requested Feedback data - spreadsheet of impacted EIW Revenue tables for Invoicing and Settlement and resubmitted for L3 Greenlight approval. 4/24/26 received email from EPG, stating that to be a candidate for EPG, I need to xcomplete the Initiative Milestones and Risks, specifically at least one Technical Milestone, as well as the Moneystep. The initiative has not been assigned an IT lead yet. Once that happens, I will enter the technnical milestones and notify EPG. | E: L2 | Active | L2 Feedback Requested | 2026-12-04 | 2026-12-04
Business w/ Tech Initiative: EMR OTC- LAC-BR-BRECO-BDE-Creation ancillary charg |  | 109419 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Alzira Baptista Borges, Natasha Barbosa Xavier, Tatiana Farias, Sandra Parras | On Track | Jan 20th 2026 - canceled as per Sandra Parras' Instructions From Sandra Parras OIC, VPS + ESPM cc FYI Dear BDE Core and Extended Team: With the recent announcement regarding Brazil Domestic Exit, it means the Brazil Domestic Enablement and Domestic Customer Integration (BDE) Project is canceled Some of you have asked me what should be done with the requests in Planview, Onspring and/or PPM as it relates to Brazil DOM or the other portfolios. Below please find a list of the Planview initiatives that should be canceled NLT Jan 31, 2026. A copy of this email should be attached to each initiative canceled. Job aid link: Setting Initiatives to On Hold-Cancel.pdf I want to thank you for all your efforts in the last few years with BDE and I hope we get to work together in the future Any questions please let me know Thanks Sandra Initiatives to be canceled in Planview by Initiative Owner Rationale: BDE project canceled as of Jan 5, 2026 Initiatives where a PDSM should be entered to cancel the request: Enter a PDSM under Enterprise Tools/Planview to cancel request, email to send to Lisa Rolfe with PDSM # entered Rationale: BDE project canceled as of Jan 5, 2026 Sandra Parras Manager, Program Management Office¦ LAC Marketing¦(786) 473-3605 -------------------------------- 26 Noiv - 25 Per BDE PMO Sandra Parras (488838) , this project is on hold until mid Jan 2026. Next steps to be confirmed after that 24 Oct 25 - We are waiting for the EA team to start working on the L2 review 17 Oct 25 - We are waiting for the EA team to start working on the L2 review 09 Oct 25 - We are waiting for the EA team to start working on the L2 review 03 Oct 25 - Updated impact portfolios (Suoply and Commercial). Waiting for next step in L2 - Triage session 26 Sep 25 - EAI system impacted provided by finance local team. Based on Joe Nassar informations as Oracle AR only impacts commercial Portfolio, the Enterprise Services is not impacted by this initiative, Joe Nasse will submited a PSDM ticket to remove us Plan vire as impacted. 19 - Sept - 25 - Requested to loical finance team the list of EAI system impacts (based on Joe Nasser request - Entrerprise funance team) 12 - Sept -25 - Requested to loical finance team the list of EAI system impacts (based on Joe Nasser request - Entrerprise funance team) 05 - Sept - 25 - Meeting ES PEO & Architect Stand up tiook a place on Sep 03rd. As next step: Enterprise Services Considerations: Integration with FDF. Need to confirm detailed impacts. ART Impact: Follow-up needed to identify ART(s). T-Shirt Size: Follow-up required. 29 - Aug - 25 - Meeting with ES PEO team and Archited schedulled to Sept 03rd ( Request in L2 pendind D&T finance costs). 22 - Aug - 25 - Submitted to L2 and waiting for next steps. 20 - Aug -25 - Confirmation received via PDSM ticket ( INC031840990) that had a change in the demand subtype for Protect Purple and submitted to L2 as Liz Umsot recommendation. 18 - Aug - 25 - Triage session with ES PEO team. Next step defined: Shared Copy requested of: LAC BR BRECO BDE Creation of ancillary charges L1 Architectural Assessment.pptx A meeting needs to be scheduled with Justin Conley, Gopi, and Raji once architecture diagrams and answers are readyvto confirm impacts, dependencies, and testing readiness. 15 - Aug -25 - Received invite to ES PEO triage session in Aug 18th and I'am waiting for feedback from PDSM ticket. After that I will submit for SL2 as Liz Umsot instructions. 13 - Aug - 25 - Opened a PDSM ticket (INC031840990) requesting to enter Protect purple in sub demand type 12-Aug-25 received exception for stop work. 06/24/25 - value updated | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: Local Zone - Contract only |  | 97873 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Katarzyna Bielanska | On Track | 01/27 - Testing completed. Funcionality will move to production in decoupled mode during Feb 26 MTP 08/11/25 - Triage and QA expert session with CCH Lead to clarify Brief Demand description and CCH questions. 05/05 - Triage. Impact assesment attached in Content Feedback :Architectural diagram attached in the Content if link doesn't work. Diagram created by Rating IT that will work on the initiative. L1 Architectural impact assesment documents attached in Content | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2028-10-16
Business w/ Tech Initiative: LAC-BR-BRECO: Pricing tables |  | 110272 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Luciele Wu, Tatiana Farias | Some Issues | Due to strategic realignment in Brazil, this request is canceled. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: PLC - FHD Convenient Delivery Option (CDO) Change |  | 110716 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Aubrey Jacobs | On Track | 05/08/25: Created first pass at business case to send to domain finance | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Pricing Recommendation Engine |  | 113087 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Aswin Kumar Ramanathan, Sohail Mohammad | On Track | Submitting for L2 | E: L2 | Active | L2 & CCH | 2026-01-01 | 2027-12-31
Business w/ Tech Initiative: LAC_Martinique&Guadeloupe_ e-Invoicing Implement. |  | 114090 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ted Bushur | On Track | This project is being rolled into another DRIVE initiative. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: LAC-BR-TNT-LMS Biling processes and financial Enha |  | 114129 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | EVELLYN OLIVEIRA | On Track | 10/28/25 - This request has been cancelled as confirmed by Revenue Planning & Engineering. The initiative will be reentered as a Local Enhancement under the Supply Chain Portfolio, since the scope and required IT support are fully managed by the local Brazil IT team (LMS system). No additional global IT support is needed. 10/10/2025 - Request cancelled. This initiative will be re-entered as a local enhancement demand under the Supply Chain Portfolio, since it will be handled by the local IT team in Brazil (LMS system). 09/16/2025- The L1 Architecture Alignment has been completed, and the required documentation has been uploaded to the Enterprise Architecture Common Document Repository. The initiative folder link has been added to the “Initiative Support Architectural Documentation” field in Planview. Additionally, the T-Shirt Size and Impacted Portfolios fields have been updated accordingly. With the Lean Business Case and checklist requirements fulfilled, the initiative is now ready to proceed with submission to SL2. 08/18/2025 - Status Rationale – L1 Initiative This initiative is on track. We are optimizing LMS billing processes and automating manual tasks to improve workflow efficiency, reduce errors, and support the migration of customers from TMS/EBS to LMS. Financial Impact & Calculations: Hard Benefit: Automation of tasks currently performed by 1 analyst (R$ 2,000/month) results in $4,364 USD/year. Soft Benefit: Productivity gains, faster reporting, and reduced errors are estimated at $5,000 USD/year. Total Annualized Benefit / Measure & Unit: $9,364 USD/year. Effort & Implementation: Localized process change in SCO and Commercial areas. Coordination with Billing and Collection teams required. Moderate complexity: automation of manual billing tasks, system updates, and process consolidation. Change magnitude: Medium – affects billing workflow efficiency and financial operations. Team willingness: High – motivated to reduce manual effort and increase throughput. Assumptions: Savings based on 1 analyst workload and USD 1 = BRL 5.5. Migration to LMS continues as planned. No impact on other regions or portfolios outside SCO and Commercial. Measurement of Success: Reduction in manual hours and errors. Workflow time saved and billing accuracy improved. Faster completion of customer financial services tasks. Summary: The initiative delivers measurable cost savings ($9,364 USD/year), efficiency gains, and improved service quality. Implementation is straightforward, localized, and aligned with strategic goals. Risks are mitigated through clear ownership and cross-functional coordination. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Custom Template Pricing Restriction - List Rate |  | 114712 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ayushi Malewar | On Track | 05/09 - Planview Request Raised 05/20 - Planview forum discussion 05/26 - Planview SL1 approved by POD Lead Chris Gibney 06/01 - L1 steps shared by Monica McMorise 06/11 - As on present, working on the L1 Intake form 06/28 - Cancelling this request and raising fresh request with demand type as Local Enhancement | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: High Value Edits |  | 132873 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Chris Wilson | On Track | This project is for Local Enhancment. I mistakenly selected biz w/ tech. I will reopen this project under local enhancment. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: AHS OS Cubic Volume Thresholds |  | 148173 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Manasa Kondaveeti, Debra Y. Taylor, Isha Gupta | On Track | 1/27: Moved this initiative back to L3 (All the steps have been previously completed), the brief shift from L3 to L2 was done only to help move the enabler (CIA enhancements) forward into L3. 1/12: Moved this initative back to L2 from L3, based on the discussion and alignment with RQ Pod team (Cortney, Liz), Betty, Kalyan and Clark. This is a temporary movement to ensure that the enabler initaitve 154446 (CIA Transformation) can be progressed to L3. Isha initated a PDSM ticket: INC033687086 This should not impact the progress/post any risk to this project. 8/19: Awaiting Domain Lead's approval (DJ Miller) 7/22: Request moved to L1, working on LBC. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-10-01 | 2026-01-09
Business w/ Tech Initiative: CIA Tool Transformaton |  | 154446 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Debra Y. Taylor, Landon Willard, Sandy Whitten, Jyotiprakash Nawalkishor Choud | On Track | 1/20/2026 - PPM 1836327 10/10/2025 - Reviewed with Sales IT Resource Requirements, 9/11/2025 - Entered milestones, 9/22 - HIgh level Architecture Solution | G: L3 | Active | L3 | 2026-01-05 | 2027-07-30
Business w/ Tech Initiative: Cons Bag Detection Rex Posting |  | 154753 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Benjamin Stuart | On Track | Init is on track because existing code base is being repurposed for this logic | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: International Ground to REBS |  | 155422 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Jamie Johnson, Sushma B. Pattanshetty | Attention Needed | 12/17/25: There are two initiatives in Planview for the same demand, canceling this redundant request. 10/23/25 Per Eryn "EPM reviews initiatives that are Business Continuity or Enablers have exceptions to not require baseline/target values" this is for business continuity 08/26/25- updated link for architectural documentation provided from arch alignment meeting | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Ground Non-US Payor Account |  | 157603 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Donyae Scott | On Track | **3/9/26** - Submitted to L2. Updated Brief Demand, Key Assumptions, Money Step, and more. LBC attached. **3/1/26** - Reviewed Efficiency LBC with Finance. Finanace gave their approval. Next steps, update initiative veribage and fields before submission to L2. **2/28/26** - Reviewed "Growth' LBC with Finance but due to a shift of the initiative presented as cost-savings - Finance provided updated 'Efficiency' LBC Template. **2/17/26** - Discussed the finance portion with my manager to see how we can calculate it with the limited information we have after reaching out to multiple people. The goal is to review the estimated NRB calculation with my MD this week and to have Finance review it before I submit it L2. My goal is to submit it to L2 EOW. **1/20/26** - We have a meeting with Rhupesh to discuss potential customer profiles that will help build the Business Case and support the financial analysis of customers who would benefit from enabling this functionality. **1/6/26** - Had an internal meeting to discuss the next steps for moving this initiative forward since the NRB amount is in question by Finance and the LBC are delaying the submission to L2. The outcome of the discussion was to work with Betty's team to create a customer segment/profile that can be used revenue assumptions and to build out the LBC. **10/21/25** - Working on updating the LBC. Need justfication for Baseline Target and Incremental Revenue from Sales. KPIs will be ADV and will be dependent on Sales. This initiaitve will be enabling a payor type that is not used in Domestic Ground today. Services impacted will be Ground Commercial and Home Delivery. **10/7/25** - Updated LBC excel. Scheduling time to review the LBC with Finance. **Please note: The Baseline is '0' due to the enablement of a capability that does not exist today for FedEx Ground.** **10/1/25** - Updated 'Target Value' after consulting with my manager. **9/10/25** - Unable to update the 'One-Time Implementation Cost Estimate Range' to Small. Please note, the implemenation cost will be considered 'Small'. And will need to work with Sales to captured updated Financials. The Baseline will remain at '0' due to the enablement of a capability that does not exist today for FedEx Ground. **9/9/25** - Updated Financial and updated Architectural Documentation link. **8/27/25** - Working on completing the LBC. Need to add Financial Information. **8/26/25** - Updated the Demand Shapeing portion. | C: L1 | Active | L1 Feedback Requested | 2026-07-08 | 2026-07-08
Business w/ Tech Initiative: AI Deal Management |  | 113092 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Pradeep Kumar Kothimbakkam, Achyuth Muthyam, Sohail Mohammad | On Track | Feb 12 2026: Negative NRB of $(60,000) reflects D&T allocated support costs. Per TO Finance, all recurring costs should be included in NRB. December 30, 2025: Conducted VP level meeting to discuss next steps compensation design etc. Working to complete the L1 LBC | G: L3 | Active | L3 | 2026-01-01 | 2026-12-31
Business w/ Tech Initiative: Customer Agreement Experience |  | 109817 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Alexander T. Ohta, Kalyan Bhavaraju | On Track | 05/08/25: Received a GO decision from Executive Sponsor at Commercial Clearing House | G: L3 | Active | TEMP L3 - Enter L3 | 2026-03-02 | 2028-02-29
Business w/ Tech Initiative: ICPC for US child account |  | 163046 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Rohit Rajesh Naik | On Track | 10/13/2025 - Updated Finance part, final review of LBC pending. 9/22/2025 - Demand Shaping section completed. working on completing the LBC, need to fill financial feilds. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: COM - CSR to CVD (Continuous Value Delivery) |  | 163049 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Robert Turanchik, Abhishek Navneet | On Track | CVD has been stood up as of January 2026 | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Minimum Network Utilization Charge |  | 164382 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Vijish Vijayakumar, Srinivas Reddy Busi | On Track | On-Hold | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Tiered Additional Handling Surcharge |  | 164389 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Vijish Vijayakumar | On Track | 10/21 Updated IO to Abhinav Anil Tendulkar | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Zip-zone Project |  | 164392 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ramki Iyer, Srinivas Reddy Busi | On Track | we received clearance from our leadership to position this initative PV #164392 Zip-Zone Project as part of Jan '27 CVD (Market launch date is currently TBD). with this, a) we changed the status from "On-Hold" to "Active" b) we will kickstart the next steps to move thru L2 gates. | E: L2 | Active | L2 - Enter Value Prop
Business w/ Tech Initiative: GAF Pricing Transformation |  | 165808 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Rohini Verma | On Track | Received a GO decision from Executive Sponsor at Commercial Clearing House | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Collect AHS-packaging GRD NC Pckgs w' Bndng/tape |  | 168030 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Scott Wallis | On Track | 10/29/25 - Per Monica, created this one in error. Will keep initiative 168036 - SAW | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Collect AHS-packaging GRD NC Pckgs w' Bndng/tape |  | 168036 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Scott Wallis, Carol Eskew | On Track | Submitted new request as a local enhancment. Removed references to data science work. | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: PCRS - eMBP Transformation |  | 168039 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Rahul C. Tiwary, Chris Strickland, Songnian Zhao | On Track | RCT - 12/02/2025 All the related work was recently approved as part of #8407 : eMBP Transformation. Note the additional information in 8407 - regarding impact to Enterprise Services Portfolio. Related portion from #8407 included below for reference - *Impacts Enterprise Services Portfolio? Yes Enterprise Services Portfolio Greenlight Can Support Enterprise Services Portfolio Greenlight Notes Approved by Enterprise Services PEL 10/29/25 as a change request to original scope with Enterprise Services being identified as impacted after the initiative was already in an L3 status Enterprise Services Portfolio Costs 315,540 Enterprise Services Portfolio Size Estimate S(1 to 4 teams, .75 to 1 Pls)* | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Introduction of additional charges in Fiji |  | 168042 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Hye-Rim Lee | On Track | Changing Demand Type | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Smartpitch |  | 168169 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Katarzyna Bielanska | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: Charge for Global Paper Air Waybills |  | 170206 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Chris Wilson | On Track | 11/20/2025 - Reaching out to Jennifer Lui for LBC template and review. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Agentic AI driven Pricing Workflow |  | 170955 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Sohail Mohammad | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Sandbox - DIM Validations Dashboard |  | 170958 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Ian Freshwater | On Track | Project is being moved to a different team under Angie Leider (Mgr). They have submitted their own PV initiative. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: EMR OTC - Capture Revenue for Unbilled Shipments |  | 130638 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Allyson Zimmerman, Chris Gibney | On Track | 11/18/2025: Based on research and potential benefits, this effort should be canceled. Cancellation was agreed by Nick Davignon and Leslie Benners. LBC filled out and submitted for L2. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Bring RQM into MyPricing app in iSell |  | 179959 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Agreement Processing Engine (APE) |  | 186478 | Business Only Initiative | Commercial - Revenue Quality | Commercial | Shankar Dokula | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: EDI Invoice Update – Add O/D Postal Codes for GAF |  | 186746 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Nekia Thomas | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: New SAF (Sustainable Aviation Fuel) surcharge |  | 92778 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Vijish Vijayakumar, Robert Anghel, Ethan Huber, Harvey Zhang | On Track | **7 April 2026:** Business Case reviewed with Jennifer Liu and received go ahead to update PV. **6 April 2026:** Business Case was approved by Aashish Gahlaut. **14 Jan 2026:** Was decided this initiative will become a Global one, led by Clark Grantham. Added Vijish as owner. **17 June:** Changed from Cost Avoidance to Revenue Growth. **5th June 2025:** Agreement on surcharge calculation method. **31 Jan 2025:** Working on moving the initiative to L2 | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: CRSV RATC Promotional Rates |  | 189201 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Mels Wolf | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Surcharge waiver charge codes |  | 189208 | Business Only Initiative | Commercial - Revenue Quality | Commercial | Abigail Lim | On Track | On Track | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Payment Processing Fee |  | 189518 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Liya Yakupova | On Track | On Track Per EPM: Primary Type of Value Financial - Revenue Growth (Yield) Request Type - Efficiency | E: L2 | Active | L2 - Enter Value Prop
Initiative: Wt Based Fuel - EXP Intl. Service (Freight/Parcel) |  | 192846 |  | Commercial - Revenue Quality | Commercial |  | On Track | On Track | C: L1 | Active
Business w/ Tech Initiative: Wt Based Fuel - EXP Intl. Service (Freight/Parcel) |  | 192850 | Business w/ Tech Initiative | Commercial - Revenue Quality | Commercial | Vijish Vijayakumar | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Project Firefly - Enhancing Data Privacy and Reduc | 79762 | 7387 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Shannon Battle, Taylor M. Prewitt, Esra Yuksek | On Track | 03.30.2026 - 04.03.2026 - Cookie Consent - (Team reviewing SDK Configuration) Privacy Request - (Continued progress through Colo Connections. Further research on DSAR Report to determine accuracy. Discussion with BigID team on the need to capture and manage outcomes from data sources in BigID when responding to Data Subject Access Requests (DSARs) in the Delete workflow, specifically when a data source. BigID stated that it would take further development) 03.23.2026 - 03.27.2026 - Privacy Request - ( Worked to determine needed triggers from BigID to FedEx systems. Continued work to set up colo data sources) 03.09.2026 - 03.20.2026 - Cookie Consent - (The privacy notice and update banner are in place, and link redirects appear to be functioning correctly. Kick-off meeting held for Mobile App Cookie Consent. GPC discussion held for California processing.) Privacy Request - (Development environment successfully connected to Salesforce; production connector planned for release in July 2026. CAM mapping completed in non-production environment) 03.02.2026 - 03.06.2026 - Cookie Consent - (Adoe issues (Demdex and Everest) can be closed. Standard French translations need to be obtained. Implementation of sweepstakes is in progress. Cookie Catagory info to be developed where teams can download category info) Privacy Request - Discussion with Privacy Team on which workflows should contain automation in BigID. Also discussed if automatic responses would be for all stages to keep customers informed about processing of requests. Talks with CED and iSell teams to discuss possible API triggers from BigID to FedEx and reverse. Also, discussed additional ER needed for Privacy Portal). 02.16.2026 - 02.27.2026 - Cookie Consent - (Marketing tags for Chinga pages are being developed. Adobe issues are being worked on. French and Spanish intake form has been developed. Waiting on approval from Legal. Meeting with BigID on contact usage update. Universal Consent is not in scope of contract. More talks to be held. Adobe issues should be addressed by March 4. Aligned with web steering committee to proactively identify new sites to ensure proper compliance) Privacy Request - ( Data & AI made progress in connecting FedEx data sources by creating the production infrastructure for on-prem and establishing connections to FCL, CAM, and Contacts in non-production.BigID is delivering features requested by FedEx for the Privacy Portal intake process. Two features were delivered in February. The remaining two features are scheduled for April 5. Met with BigID to determine needed API triggers. FCL and CAM are trying to determine if work arounds can be done in FedEx to use the out of the box API calls from BigID. BigID is still working on open cases.) 02.09.2026 - 02.13.2026 - Cookie Consent - (February loads will push several clean-up items through. Implementation guidelines being developed on key sites such asSweepstakes, Newsroom, Routesmart.) Privacy Request - ( Team in the process of executing FireFly requirements across multiple Arts. Enterprise level priorities are impacting some timelines and deliverables. Critical enhancements are still being developed by BigID. Rough Draft of BigID workflow developed. Possible triggers to FedEx from BigID are being developed.) 02.02.2026 -02.06.2026 - Cookie Consent - (Updated UserCentrics integration) Privacy Request - DSAR manual request is now showing results. BigID recommended capturing a HAR the issue but we were unable to duplicate the failure. Extended team meeting with Arcs to discuss any impediments to FireFly work) 01.26.2026 - 01.30.2026 - Cookie Consent - (Team agreed that updated privacy notice rollout. Initial languages will be English, French, and Spanish. Other language/translations to follow. There is an issue with FXO staging which is preventing testing and a solution.) Privacy Purge - ( Case #60534 DSAR returning 0 records. ForgeRock connector is ready for the team to tr | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2028-07-04
Business Only Initiative: Customer Acquisition: Grow revenue by identifying | 31971 | 9432 | Business Only Initiative | Commercial - Sales | Commercial | Deric D. Hunt, Chris Nichols | Attention Needed | 11/19/2025 - At this time, we are cancelling this current initiative based on our decision to not renew our contract with Equifax that will be expiring in December 2025. We gave notice to the Equifax team of this decision in September. While the partnership with Equifax was good, it was ultimately determined due to the minimal revenue gains we expected to have from unknown B2B leads did not warrant a continuation of the partnership. Both remaining FTE's hired to support this initiative have been moved to other program Manager work within DDC, and we will plan to maintain communication with Equifax in case anything changes with future iniatives for DDC while also working through our cost reduction strategy for the remainder of FY26. 6/2/2025 - There is still significant concern on the overall ROI from the Equifax program. There are now two FTE's instead of the initial 3 due to a voluntary departure in March 2025. The main focus has been ensuring both remaining FTE's are able to contribute to the DDC segment by continuing to have them focus on other responsibilities as previously outlined. While we have not achieved the desired outcomes with Equifax, this does not have any impact on the segment's overall revenue due to this initative being self funded and not any incremental costs associated. At this time, the contract is in it's final months and we do not anticipate renewing the program moving forward. 9/9- We have great concern over the success of this initiative. So far, the data from Equifax has not yielded the results we anticipated. We are continuing to work with the GSO-Data Science team and the OSC vendor to refine the data, in hopes that we're able to identify better (quality) leads. Due to the low success rate, we are starting to (partially) transition the 3 FTEs to other responsibilities to ensure we're receiving adequate return on that particular investment. We're also thinking of other ways we can monetize the Equifax data. Enigma data will be utilized in the Segmentation/Potential model. As a reminder, the DDC self-funded this initiative by reducing headcount. The reduction has not impacted the segment's revenue return. 7/2- We are in the process of refining/adding filters to the Equifax leads to improve the quality. This is an iterative process and will take some time. Actual revenue from closes will be tracked via Closed Business Tracking, which runs ~6 weeks behind the original close-date. As revenue starts to show up from prior month closes, I will update the revenue for those months. At this time, we are closely monitoring this initiative as the initial Equifax leads have not lead to the expected outcomes, and there is some concern around the quality of leads. Status as of 6/11: Due to delays in ingesting the Equifax data into CDP, we decided to manually run the matching and use manual excel files temporarily. Today, 6/11, the first file was delivered. We will monitor the success of the leads moving forwards. The initial batch contains 1,800 leads; this is the main driver behind our current results Status as of 5/20 -Starting in April, the team of 3 did begin their function and did start to identify and close some opportunities (no ADNR showing up yet as that calculation is ~6 weeks behind) -However, they still don't have access to the Equifax data, which is being ingested into CDP and that work is being prioritized -Since the delay is impacting numbers, we are working to manually provide the data leads while the CDP work is being completed Status as of 3/4 * The 3FTEs have completed Sales training and will begin execution this week (week of 3/4) * The money step will occur whenever the first opportunity is identified and closed- projected sometime in March * Equifax data is being matched to our Salesforce database and is being integrated into the CDP * The PreSales department/team is self-funding this initiative. Although, the money step is delayed, we're already seeing cost-savings due to head | I: L4 | Cancelled | L4 | 2023-08-15 | 2024-01-31
Business w/ Tech Initiative: COM - S&CDE - CRM - Project Clarity |  | 84393 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sandy Whitten, Dawn Komoroski, Megan Dillon, Tina Visconti, Jagannadha R. Vuppalapati | On Track | 09.02.25 Pricing (RMIC) has not prioritized this work; therefore, no PI date is available. Planning to prioritize for Feb CY26. Money step will not be realized until Feb CY27. 06.11.25 - Mark Mantaro, MD Finance, requested the use of a 6.7% operating margin and 44% variable margin to calculate value. The LBC reflects those changes. Per Mark 01.24.25 Updated LBC and target value/measure & unit per request of Mark Mantaro, Finance 01.06.25 Updated architectural documentation to include Impact Assessment documentation template; Did not add PEOs as no roles & responsibilities or CCH section (project is not directly customer impacting) 12.20.24 LBC reviewed with Finance, ready for L2 submission | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-30 | 2027-02-01
Business w/ Tech Initiative: COM - Sales/CDE - CRM ART Sales Modernization POC |  | 88561 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sandy Whitten, Colt Snell, Tina Visconti | On Track | Duplicate entry | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Field Sales & Digital Sales Activation |  | 88616 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Ryan J. Miller | On Track | N/A | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: eContact Retirement and Mastering of Contacts |  | 97425 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Santhosh B. Korambeth, Devin Lewis, Tina Visconti | On Track | Changing out the primary IO. | E: L2 | Active | L2 Feedback Requested | 2026-05-11 | 2027-03-26
Business w/ Tech Initiative: TS-VL3-EIW Migration - Sales Data Warehouse to Atl |  | 97428 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Charles M. Weinman, Sandy Whitten, Amanda Nevins, Vincent J. Romeo | On Track | 1/21/2026 - PV request cancelled to do EIW migration to ATlas being cancelled. 03.05.25 - Prep for L1 in progress 03.06.25 - Beginning LBC 3.10.25 - Discussed with Landon Willard determing fincials for vendor cost to do the same work we do today to make changes in SDW. That includes DB cahnges and ETL. | C: L1 | Cancelled | L1 Feedback Requested | 2025-07-30 | 2025-10-07
Business w/ Tech Initiative: Automate Internal user Account Creation in ECAM |  | 106328 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Devin Lewis | On Track | This initiative will be addressed under another DRIVE initiative. | C: L1 | Cancelled | L1
Business Only Initiative: DDC Nearshore Cost Savings |  | 106333 | Business Only Initiative | Commercial - Sales | Commercial | Deric D. Hunt | On Track | Cost savings realized during FY25. Seperate initiative for Agentforce and reductions tied to that entered on initiative in August 2025. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-DART Reporting - PSSTRPT |  | 106336 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Giancarlo Pacini, Thomas Davis, Amanda Nevins, Vincent J. Romeo | On Track | cancelling init as parent init 98380 has been cancelled. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: COM - S&CDE - CORE ART - IPHW/IEHW Split - CRP |  | 114731 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Eric Powell, Sandy Whitten, Ashwini Chenreddy | On Track | We were able to get this through Planview as Local Enhancement. This Business with Tech is now invalid and not applicable. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: COM-S&CDE-CDE-Unified Customer Profile Enhancement |  | 114734 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Terrell Goldsmith, Eric Powell, Punitha Sekar, Sandy Whitten, Vikram Manchala | On Track | On track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Pricing Analysis and Intelligence Suite |  | 126689 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Justin Williams, Lee Skelton | On Track | 7/23/25 Alpha testing of report-based features starting, model development ongoing. Alignment with COE and iSell team ongoing. | E: L2 | Active | L2 | 2026-04-13 | 2027-10-29
Business w/ Tech Initiative: Unauthorized Reseller Detection Enhancements |  | 132153 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sally Landham | On Track | work did not need to go through Drive | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: COM - S&CDE - CORE - cView Application |  | 148198 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sandra W. Dolce, Sandy Whitten, Deborah T. Johnson | On Track | 4/3/26- Updated NRB in LBC and email response, with additional details, sent to Mark C 11/03/25 -Project moved to SL2 Triage 10/10/25 - The Platform portfolio is NOT impacted. This is an application used exclusively by Sales or Sales Support. I discussed the same concern with David Walker as indicated on the architectural document and he still wanted to review during SL2 triage. I'm not sure why. 10/07/25 - Performed QA check with QA lead, Karen McConnico; updated architectural documents. Changed t-shirt size to S. Added KPI. 09.23.25 - Awaiting EBA review 9-18-25 - Backlog for Impact Assessment required to validate Portfolios 09.16.25 - Review L2 entry with pod lead. Loaded LBC and Arc Docments 09.11.25 - Pre-review of LBC by Finance 08.21.25 - Initial cView LBC critical components, meeting with finance lead 08.20.25 - SR&A Dashboard information for reason codes on HDIAs 08.14.25 - TDAC-Solution Architecture sync review 08.06.25 - Creation date of cView FIRST (7735) 08.05.25 - Creation date of cView EAI (3541559) 07.29.25 - cView SL1 review 07.17.25 - L0 Triage review with | E: L2 | Active | L2
Business w/ Tech Initiative: COM-S&CDE - CDE - EWS alerts through JO |  | 154451 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sohail Mohammad, Eric Powell, Sandy Whitten, Punitha Sekar | On Track | On track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS - COM-S&CDE- CDE -Globalization of MyTerritory |  | 160675 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sandy Whitten | On Track | duplicate entry | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Customer MDM Migration from OnPrem to SaaS |  | 167115 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Devin Lewis | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FTC DNC Process |  | 169167 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Hitesh S. Chache, Aashish Goyal | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: VIETNAM ECIS Updates Alpha ID |  | 163533 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Janes-Ronald D. Corpuz | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FCL Integration into Customer Contacts |  | 187673 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sowjanya Nimmagadda | On Track | On Track 3/18/2026 Asked IO to update LBC fields. (DFW) | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: ZoomInfo - New Capabilities |  | 190928 | Business w/ Tech Initiative | Commercial - Sales | Commercial | Sandy Whitten, Colt Snell | On Track | 04.15.26 - Per David Walker, required to add the words "future state" and "current state" and personas to ability to statements before an arch review could be scheduled. 4.15.26 Asked Sandy Whitten to update demand shaping fields according to Job aid instructions. 04.15.26 - Asked David Walker what additional information was needed as the requirements he sent were included in the initial submission. 04.13.26 - Awaiting ennterprise architecture review. 04.07.26 - Status is current with completion of the LBC draft. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Proactive Retention (PR) Journey Migration | 93616 | 7071 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Dan Pereira, Clayton Taylor, Traci J. Stubblefield, Punitha Sekar, Sandy Whitten | On Track | 7/28: This purpose of this initiative was to migrate the data required for the Canadian Proactive Retention Journey to CDP. However, upon further investigation, the data in question already exists in CDP via a new Canadian journey, SAM Growth. As such, this migration is no longer required. 6/24: Implementation costs of $1.4M too high and does not cover incremental profit. Revisiting/validating Commercial and Data/AI costs. 6/6: Advised that a new PPM must be created. 5/27: Updated costs to include Data/AI, KPIs added, PPM ticket updated to include PV ID #7071. Submitted to L3. 5/14: Dates updated in milestone section (confirmed by Sandy) 5/7: April requested target dates for completion in order to proceed to Commercial greenlight. 4/22: Uploaded updated Business Case (updated for FY25 rebaselining) 4/17: Uploaded L2 Data Architecture and L2 Costing Estimate documents. Now confirming FY25 baseline numbers and will update accordingly. | E: L2 | Cancelled | L2 Feedback Requested | 2025-05-21 | 2025-08-29
Business w/ Tech Initiative: [US] SAM Pick Your Plan | 76763 | 8082 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Matt Firetto, Abby Geisel | On Track | Cancellation rationale: Project has been completed and launched without the need for additional resources. Future expansions of Pick Your Plan will continue as a part of existing teams work and where necessary aligned with other DRIVE initiatives. In pilot phase stage 2 9/8/25 Revised version of PYP test launched on 9/5 focused on increasing overall account creation. Initial results will be available in early October Net revenue per account for v1 of PYP has increased for PYP customers, performance will continue to be monitored. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: 3rd party platform alliances: Indirect Programs | 15323 | 8093 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Bradley Hamilton, Adam Hamburger | On Track | Moving to L5. This program has been tracking revenue since 2023. We will continue to pursue additional Indirect Programs going forward as a regular course of business | K: L5 | Completed | L5 | 2022-03-01 | 2025-10-17
Business Only Initiative: Stensul Platform | 95842 | 8295 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Clayton Taylor | On Track | Submitting to L4 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-04-28 | 2025-12-01
Business w/ Tech Initiative: My FedEx Rewards 2.0: FedEx Freight Integration (P | 15862 | 8704 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Ee-Laine Cheong, Alan Kirk | On Track | Submitted to L3 on 3/13/25. Discussion on 6/18/25 - Finance to provide confirmation if rebaseline is necessary due to FXF spinoff this fiscal and that the initiative has launched and generating revenue for a year. | E: L2 | Cancelled | L2 & CCH | 2022-12-05 | 2025-05-30
Business w/ Tech Initiative: My FedEx Rewards 2.0: FedEx Invoice Reward FBO Int | 31693 | 8737 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Ee-Laine Cheong, Alan Kirk | On Track | Revisions being made to business case. Rebaselining to FY25. Discussion on 6/18 to determine cancellation of initiative due to dependancies on HoPE and reinstate with new initiative to determine impacted portfolios. | C: L1 | Cancelled | L1 Data Migration - TEMP
Business w/ Tech Initiative: #15336 Click to Enroll - SAM Pricing Offers via Em | 15336 | 9210 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Esfand Mazhari, Pam Gray | On Track | 4/4/2025 All current usecases work as expected. CA growth Journey still in testing. 3/28/2025 CA Growth Journey still in testing. Test accounts are being suppressed by C2E engine, and this needs a change from engine side to resume testing. 3/21/25: Team is working with CA on testing of CA growth journey release.​ 11/14/23: Business case file is uploaded as attachment to Business Case tab. Revenue, and cost(s) are added in the Impacts tab. | K: L5 | Completed | L5 | 2023-01-16 | 2024-05-31
Business Only Initiative: Customer Data Enablement – Omnichannel Customer Jo | 15342 | 9212 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Traci J. Stubblefield, Mariano Lepori, Ryan J. Miller | On Track | 10/31: Submitting for L5 10/22: Ensured updated financials. Will not have Sept. actuals until November. Secured confirmation of all milestones from EPIC owner 9/30: Sept financials and Oct financials added 9/12: Financials updated for month 6/8: Financials updated for month 5/5: Secured L4 approval - April actuals loaded in Financials - tracking to plan. 4/30: In SL4 awaiting Brie's approval. 4/22: Secured Finance approval on money step. Awaiting DJ approval to enter L4. 4/15: No update. Still waiting to reach L4 status. 4/7: FY25 baseline has been updated along with business plan. 4/1: Had meeting with Finance and confirmed actions in Planview. Forecasts and Actuals have been updated per their direction. Let me know what else is needed. 3/26: Meeting with Commercial Finance on 4/2 to revisit financials and take necessary actions. 3/10: Waiting on input from finance on how to update financials. Becuase this has been in L2/L3 for so long, some of the originally entered forecast dates have past. I need guidance on if I delete those and only focus on the forecasts and acutals I can report on moving forward. I'd also like to update/remove two of the additional KPIs. | K: L5 | Completed | L5 | 2023-08-08 | 2025-11-28
Business w/ Tech Initiative: Commercial Data Migration - Journey Enablement |  | 88108 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Clayton Taylor, Amanda Nevins, Vincent J. Romeo | On Track | Feb 2025 – L1 Commercial Triage – T-Shirt sizing Small Sept 2025 – Added and approved from Tech Simplification Oct 2025 - Removed from Tech Simplification Oct 2025 – Data and AI business case/financial plan review/approval Dec 2025 – Added as an enabler to Journey Orchestration Drive Initiative Feb 2026 – QA review with Leslie; Updated EPICs and PPM # | E: L2 | On Hold | L2 Feedback Requested | 2026-03-02 | 2026-11-27
Business w/ Tech Initiative: Loyalty Rewards RFP - New Vendor Onboarding |  | 110719 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Rachel Guenther, Alan Kirk | On Track | 4/24 - Request to update Money Step MS date to 6/1/2026 4/22 - CPEL Level-Set 3/4/2026 Submitted second FIRST for technical configurations and connectivity: * FIRST-8683 - Loyalty Rewards - Kobie Marketing Inc. Integration 3/2/2026 Sales & CDE finalized solutions analysis​ Access to Agility has been granted​ 2/25/2026​ ​Kickstarted conversations with Kobie and the Sales & CDE teams regarding the iSell integration. ​Held the first solutions meeting for the EO and ART teams; additional follow‑up and alignment with the appropriate stakeholders is needed.​ ​Conducted an Agility overview and ARTs breakdown session with Michelle Franke.​ Submitted a request to obtain Agility observer access 2/17 Connected with Sales & CDE to begin defining scope of work. Meeting scheduled with Kobie to start integration discussions. 1/28 Connected with Solution Teams (Drive Governance): Completed orientation; no new downstream impacts identified.​ PI Alignment Identified as Key Risk: ARTs reviewing where KALC‑related work will land in PI1/PI2.​ Kickoff & Governance Cadence: ​ Rachel (IO/Epic Owner) will schedule bi‑weekly working sessions with Solution Teams.​ Rachel to join Logan’s bi‑weekly governance call for ongoing status reporting.​ GDX Solutioning Complete: Awaiting ART confirmation on PI scheduling.​ Sales Enablement Impacts: Confirmed no changes required (iSell/CEC flows remain the same). Deck & Technical Diagram: Will be distributed to all attendees for reference. 1/14 * Connected with G2S / CDE team to discuss impacts (confirmed none) ​ * GDX analysis is complete​ * Rachel/IO to schedule kick off call with Project Solutions Discovery Team as Epic Owner. 12/19 PI01 Start Date: Under discussion; tentative options are January 7 or January 14. Commitment Status: No official commitment yet for PI01. Decision pending at PMT level.. ART Bundles ART Bundles have been passed to the CAMP team. Awaiting confirmation on whether CAMP ART has started preliminary planning. Key Notes from John PMT is actively discussing PI01 timing and scope. Decision will be communicated early once finalized. 12/2 Updating financial lines for 2025 to meet compliance Approved for L3 on 11/25 11/19 Returned financials with new splits and submitted. 11/14 - EPM Greenlight Finance review - Kicked back to inlcude OpCo split 11/12 There’s an urgent timing conflict between the Planview approval process and the Agility delivery cycle. While we’re expected to wait for Planview to generate the official Epic, that process can take 3–5 weeks, which would push the work into Calendar Year PI02 (March). If that happens, teams would only have March–April to complete the work—and given competing priorities (Sundance, Odyssey, Firefly, Genesis, and Fairway), our initiative would be deprioritized. To stay on track for delivery by May, the work needs to be entered into Agility now so that teams can begin feature and story decomposition ahead of the early-December PI Planning session. However, this is only feasible if the solution is fully decomposed and ready for consumption by the delivery teams. Confirm Planview status to identify where the Epic creation stands and what approval steps remain. Engage leadership support to help shorten the 3–5 week approval cycle. Coordinate with Shelby Stockbridge (EPM) on timing and process for the final L3 approval submission. Prepare for early December PI Planning by ensuring the initiative is visible in Agility so delivery teams can begin feature and story decomposition. Finalize the decomposed solution to ensure it is ready and consumable by the delivery teams. Evaluate a parallel path option if Planview delays persist, allowing the Epic to be entered into Agility in draft form. Reassess delivery feasibility if approvals extend into CY PI02 (March), considering competing priorities such as Sundance, Odyssey, Firefly, Genesis, and Fairway. Communicate potential timeline impacts and dependencies to leadership a | G: L3 | Active | TEMP L3 - Enter L3 | 2026-01-14 | 2026-06-30
Business Only Initiative: Project Horizon Digital Marketing Optimization |  | 130233 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Aurora E. Villasante | On Track | This initiative was created to achieve Spend Control Tower approval for the McKinsey 6-week initiative (Project Horizon). The 6 weeks are now over and the work will be executed through request ID 0013262: FY26 Commercial Journey Orchestration. This initiative will be put on hold in case any future McKinsey engagement is needed as the teams start to execute on the work. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SAM - SMART and Loyalty |  | 153157 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Kimberly Winston | On Track | Not familiar with this request. Cancelled at the request of Tara Sciulli. | C: L1 | Cancelled | L1
Business Only Initiative: SMART and High-Potential Digital Sales Customers |  | 153160 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Melissa Bolshinskaya, Romilly Robinson | On Track | 4/22/2026: 108 DS customers enrolled. Need to go back and add some missing details for L3. 4/15/2026: 106 DS customers enrolled. 4/7/2026: 100 DS customers enrolled. 3/25/2026: At least 68 DS customers enrolled so far. 2/4/2026: No updates; SMART team is still reviewing list and connecting with Sales AEs on potential new additions to program. 1/28/2026: Sent initial customer list to SMART team for review. 1/14/2026: Currently pulling lists for Digital Sales customers to assess potential cohort sizes. 1/7/2026: Approved for L2. 12/17/2025: Aligned with pod PMO and Finance lead on inputs and submitted business case to L2. Currently awaiting approval for L2. 12/10/2025: Business case ready for submission to L2; in process of completing L2 submission checklist and confirming with Finance that inputs are correct. 11/12/2025: Updated business case in response to finance questions; submitted back to finance with additional source documentation. 11/4/2025: Submitted business case for finance review. 10/8/2025: Initiative type has been changed to Business Only. Business case completed and ready to submit for finance review. 10/1/2025: Still waiting on PDSM to update initiative to Business Only. Good progress with business case, estimating it will be ready to submit for review within next 1-2 weeks. 9/17/2025: Received new, much larger data file which is still under review. Submitted PDSM request to change initiative to Business Only. 9/3/2025: Completed preliminary review of data currently available for SMART and exploring potential to approach initiative from a cost savings perspective rather than (only) revenue growth. Reached out to SMEs who can consult on this approach; awaiting responses. 8/19/2025: Business case in progress. Contacted major stakeholder with request for information to support business case development. 8/13/2025: Initiated work on business case. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: SAM Claims Experience Modernization |  | 153907 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Gavin McKay | On Track | Cancelling the SAM Claims Experience Modernization (153907) initiative, as its scope and objectives are being addressed through the ECD Preferred Future State (104641) initiative. I have ensured no elements of my initiative were overlooked in CE’s assessment and documentation of their initiative. This alignment will allow CE to move forward without duplicating efforts. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Consumer Insights Platform- CIP |  | 153911 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Ning Zhao, Nathan Carter | On Track | Request cancellation due to data privacy concern and cost and benefit analysis. | C: L1 | Cancelled | L1
Business Only Initiative: SAM - Integrated Tactics for Key Seasons - Ph1 |  | 153916 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Ning Zhao | On Track | This initiative will be combined with DRIVE initiative 161043 FY26 Commercial Journey Orchestration. | C: L1 | Cancelled | L1
Business Only Initiative: SAM - Prioritization for Sales Call Cycle - Ph. 1 |  | 153919 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Ning Zhao | On Track | This initiative will be combined with DRIVE initiative 161043 FY26 Commercial Journey Orchestration. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FedEx Rewards for Canada |  | 153923 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Romilly Robinson, Nathan Carter | On Track | 02/23 - Reviewed TY and CY27 estimated Financials with CEM budget lead for inclusion into budget needs. There are identified shortfalls with requested budget that are being reviewed with VP and SVP to determine approach for CCH 01/06 - Reviewed initative w/Portfolio Strategy & Bus Arch. team; began work on EPIC but need to get PPM approved before submitting; approved to go directly to Sales ART as D2SS and does not require CPEL review 12/23 - Determined that Data & AI are not required; Romilly requested removal of that portfolio from the init and removed on 01/05 12/11 – David & Kaleigh reached out to inquire if init truly needs to be in Data & AI; they are requesting a quick review to determine actual work needed; awaiting feedback 12/03 – Planview updated w/L2 Costing info 12/03 – Now that the Loyalty init has hit L3, we can start having conversations w/Leadership on potentially boosting the project; note, the LBC indicated 4 incremental FTEs are needed for the project but with current hiring, this is not feasible. Team believes launch can be done with less; to discuss w/Loyalty team on needs in late January 11/05 - Init moved to PRT backlog (#57) **11/05 - Init is dependent upon Init #110719 being moved to L3 to begin. This init will leverage the same new vendor and once that project moves into L3, we'll be able to move forward** 9-30-25: Ready for SL2. A. Schuler. Domain QA expert review. 9-17-25: Updating demand shaping | E: L2 | Active | L2 & CCH | 2026-01-12 | 2026-06-01
Business w/ Tech Initiative: FY26 Commercial Journey Orchestration |  | 161043 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Traci J. Stubblefield, Clayton Taylor, Jessica G. Rogers, Ellen Oude Lashof | On Track | 4/24/26: Secured L3 approval. 4/13/26: Forecasts and actuals have been updated. Waiting to secure official L3 approval. 4/2/26: Reviewed with DAI leads (Anil/Madhu) and confirmed there are no DAI impacts given the strategic direction to focus IT resources on only new AJO development. Updated init and on track for 4/7 Commercial Greenlight. 3/27/26: Received feedback that Data/AI portfolio will be impacted and will need to go back to L2 to secure the D/T costs, sizing, and necessary approvals. Reached out to Rachel Vigna for direction, will revisit on Monday. 3/24/26: Received finance approval from SAM Pod Finance Jennifer Liu and TO Finance Megan Lightford. April Zhou approved submitting for Commercial Greenlight. Submitted to L3. 3/19/26: Followed up with PDSM request of changes and Finance for approval to proceed. 3/13/26: PDSM submitted for addtional changes based on Finance review with Warner Anthematten 3/9/26: PDSM updated information in ini. Checking with SAM POD lead and Finance lead. Will sumbit to Commercial Greenlight when have approval. 3/2/26: Determined with EPM/Pod lead that will decouple from 88108 and made the adjustments. Made financial adjustments impacting NRB due to business decisions that will impact journey performance. 2/12/26: Received financials approvals and QA with POD PMO. Entering in PDSM ticket for Epic date entries. Holding on greenlight until enabler 88108 reaches L3, and he's submitting to greenlight 2/13, 2/2/26 - Financials, Epics entered and reviewing with Finance this week. May need to hold on SL3 due to 88108 Enabler needed to reach L3 first. 1/30/26 - As we head into L3 important reminder, on 8/19/25 - Per decision of EPM/ESPM/D&T Finance leadership approved this init being an exception with the money step with 12/30/26 being the money step to provide a full year of FY26 incremental revenue. The goal is to have a DRIVE init each FY for the work required in the program moving forward, which is why we will not provide FY27, 28 forecasted financials. 1/26/26 - Requested PPM #, loading Epics, secured Commercial pricing - pending Finance Mgr/MD approval to finalize finance L2 requirements 1/5/26 - Nearing SL2 final approvals - secured Commercial Architect agenda on 1/13 to continue through L2 12/23/25 - Finalized LBC with Finance and submitting for L2 12/3/25 - Working on LBC and looking to secure L2 by 12/31 9/15/25 - Meeting with EPM team on 9/18 at 8 a.m. to discuss how to proceed. Have not been able to reach alignment on financial approach for this specific exception. Need troubleshooting/guidance at higher level. 9/10/25 - Meeting with Finance to review LBC, attend triage meeting 9/12 8/28/25 - Secured L1 and working on next requirements. 8/19/25 - TO leadership (Marco Aletto, Alex Scott, John Jamison, Emilee James, Daniel Knopfmacher, Benjamin Glenn) approved the money step being 12/26/2026 to provide a full year of incremental revenue. The goal is to have a DRIVE init each FY for the work required in the program. ** | G: L3 | Active | L3 | 2026-01-01 | 2026-12-31
Business w/ Tech Initiative: Global Digital Asset Manager Sourcing |  | 161514 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Blaire Smith | Some Issues | Updated Breif Demand Description based on feedback from David Walker. 10.22.25 - On hold until a DAM vendor is selected. Unable to complete the LBC without pricing info etc. 11.13.25 - A sourcing partner has been identified. He will be helping with the business case for DRIVE, creating an estimated timeline and preparing for a RFP. 11.21.25 - We are still on hold as we don't have the info (pricing) needed to move to L2. Before we can conduct an RFP to get vendor costs for DRIVE L2, we need to get consensus with IT that RFP is the best route by participating in IT’s Connected Ecosystem workstream on Content Supply Chain. This stream will explore connecting and consolidating all marketing technology, and DAM considerations will be included. RFP next steps to come after workstreams end in early January. 1.6.26 - We are still on hold for now. Potential DAM vendors have been identified, and demos will be held and conclude the week of 1/12. 1.28.26 - Vendor demos were completed and a formal recommendation to proceed with an RFP was presented to Jeff Maddock and Christy Taroni (content and localization workstream leads). The recommendation will be shared with Brie early next week. Pending approval to move forward with RFP. 2.17.26 - Awaiting feedback and/or approval from Brie Carere to move forward with formal RFP 3.25.26 - We have begun working on a project charter and have a tentative target distribution date of May 4th to send the RFP to the selected vendors | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Commercial Data Strategy Engagement |  | 161659 | Business Only Initiative | Commercial - SAM Enablement | Commercial | CHRISTY TARONI, Clayton Taylor | On Track | Commercial Data Strategy initiative not moving forward under this initative. If needed will open a spearate initiative. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Marketing & Comms Agency RFP |  | 169802 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Darbi E. Padbury | On Track | 03/03 Cancelled as per PDSM ticket INC034244320 On Track | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SAM - Click to Enroll Multichannel Enablement |  | 178438 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Kimberly Winston, Romilly Robinson | Attention Needed | Correct the initiative Owner | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Earned Discount for Marketing sales segment |  | 184751 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Walter Saunders | On Track | 12/23/25 – Approved via Triage 01/20/26 - assigned IO and approved for L1 2/20/26 – completed updates on LBC based on Jennifer Liu feedback 2/27/26 – met with pricing to align on discount 3/9/26 – meeting with Go-To-Market to align on potential overlap 3/12/26- QA review before submitting to L2 3/20 - Revised LBC based on Jennifer Liu feedback 4/2 - meeting with solutions and pricing to evaluate ED viability | C: L1 | Active | L1
Business Only Initiative: POC Leverage Mkt to Bld Direct Cust Relationships |  | 188074 | Business Only Initiative | Commercial - SAM Enablement | Commercial | Romilly Robinson, Kevin A. Chung | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Shipment Optimizer |  | 190630 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Kevin A. Chung | On Track | 3/17 - assigned IO and submitted for L1 approval​ 3/24 – conducted an LBC work session with Doug Shaver and SAM Strategy​ 3/25 - approved for L1​ 4/5 - Briefed revenue management on the concept and encouraged to move forward recognizing data issues (enterprise level)​ 4/8 - Pricing alignment gained and confirmed how this init is different from spot pricing and focused on demand shaping​ 4/20 - Met with architect for L1 assessment (Technology Platforms). ​ 4/24 - L1 architecture alignment completed | C: L1 | Active | L1
Business w/ Tech Initiative: fedex.com Global Homepage Redesign |  | 190638 | Business w/ Tech Initiative | Commercial - SAM Enablement | Commercial | Chris Criswell | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Pickup QAT (Enabler for Pickup PFS) | 94378 | 6840 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Jorge Jaramillo, Yen Ju Chiang | On Track | 11/20/27 ¦ 11/13/25 - Updayted by CE on the next release (R51 currently targeted for November 18, 2025) 10/22/25 - Pending confirmation of EPIC PI03 completion (finish date 10/21/25) for IVR & CED changes implementation. 10/16/25 - No update 9/2325 - Updated EPIC timelines to align with Project voerall status. 9/18/2025 - No update 9/12/2025 - PI 03 work still in progress. STE stated Oct. 21 as new date. 9/11/2025 - Waiting on confirmation from CE on completion of EPICS to update. 9/04/25 - No update 8/14/2025 - Compliant 8/07/2025 - Working with Planview administrator to update "IO" ownership (IO left the company) and "Forecast" / "Actuals" data. 6/12/2025 - No update | G: L3 | On Hold | L3 Feedback Requested | 2025-03-26 | 2025-09-12
Business Only Initiative: SO Saturday | 88736 | 7152 | Business Only Initiative | Commercial - US Product | Commercial | Richard Wilkes, Alfredo Moran, Julie Lavelle-Acor | On Track | 10/16/25 - Submitted request to advance from L4 to L5. 10/9/25 - September '25 Cost Savings = $971K; Revenue Impact = -$989K; NRB = -$18K. Migrating PO to SO volume = 39.3K ADV which is 15.4% migration rate. Also working with Heather Z. to advance this initiative from L4 to L5. 10/2/25 - No updates to report. Awaiting Sept '25 actuals. 9/25/25 - No updates to report. Awaiting Sept '25 actuals. 9/18/25 - No updates to report. Awaiting Sept '25 actuals. 9/11/25 - August '25 Cost Savings = $0.993M; Revenue Impact = -$0.989M; NRB = +$4K. Migrating PO to SO volume = 36.5K ADV which is 14.9% migration rate. July '25 Cost Savings = $1.0M; Revenue Impact = -$0.99M; NRB = +$17K. Migrating PO to SO volume = 29.0K ADV which is 13.7% migration rate. 8/14/25 - Will include July actuals next week once they become available 8/7/25 - No updates to report. Awaiting July '25 actuals. 7/31/25 - No updates to report. Awaiting July '25 actuals. 7/17/25 - Received confirmation from Leslie Jason that the software release of FSM SO Saturday is fully complete. June '25 Cost Savings = $1.01M; Revenue Impact = -$0.99M; NRB = +$19K. Migrating PO to SO volume = 31.3K ADV which is 13.0% migration rate. 7/10/25 - 1) June 2025 actuals have not been loaded. 2.) Met with Karen Vogel and Katrina Carrigan to confirm July software release of FSM inclusion of SO Saturday. Karen confirmed that a slow rollout occurred in April (slow rollout releases take about 6-8 weeks). Critical mass (87K+ customers have access to SO Saturday via FSM) was reached in June; therefore, the rollout is considered complete, and no additional automation is needed. 6/26/25 - Submitted to L4 for approval on 6/25/25. 6/18/25 - Ticket submitted to PDSM on 6/12/25 has a status of "In Progress." 6/12/25 - Submited a ticket to PDSM to advance this initiative as an enabler from L3 to L4. May '25 Cost Savings = $1.10M; Revenue Impact = -$1.16M; NRB = -$62K. Migrating PO to SO volume = 47.7K ADV which is 17.5% migration rate. 6/5/25 - No updates to report. Awaiting May '25 actuals. 5/15/25 - April '25 Cost Savings = $1.03M; Revenue Impact = -$1.2M; NRB = -$126K. Migrating PO to SO volume = 19.2K ADV which is 8.9% migration rate. 4/24/25 - Revised Ops cost savings (March) -$138k loss vs forecast of +$21k. FY26 Rebaselining Review scheduled for 4/24/25 with Cristina Cirneanu. 4/16/25 - FSM Cafe April release is on track - March Ops cost savings = $29k - March PO to SO migration 7.7% - SO SDR March incremental = 1.2k | K: L5 | Completed | L5 | 2024-10-21 | 2024-10-21
Business Only Initiative: Dominate in Rural | 74727 | 7625 | Business Only Initiative | Commercial - US Product | Commercial | Tanay Das, Julie Lavelle-Acor | On Track | 2026-04-23: * No new updates 2026-04-10: * In Feb, delivery volume exceeded the baseline by ~12%, generating an incremental ADV of ~7000 * YoY Yield growth ~4.5% * * Total incremental profit was ~$24K, came in below the ~$54K target, largely due to elevated FHD CPP * FYTD (thru Feb'26) delivered $524K in total operating profit against a target of $433K. 2026-03-12: * In January, delivery volume exceeded the baseline by ~10%, generating an incremental ADV of ~5,800. * YoY Yield growth ~7% * Total incremental profit was ~$24K, below the ~$50K target, largely due to elevated FHD CPP * FY26 Total Incremental profit target was ~650K and we're at ~500K FYTD ~76% of the target * New Weekday Delivery Claim update: G2S Sales Weekly updated launced. G2M launched first external tacttics through Linkedin page, which has 2.3M followers. More G2M tactics will be launched in April and May. 2026-02-12: * G2S communications scheduled for 2/19 & 2/20 * G2M .Com claim update is scheduled for 2/19 * Other G2M tactics launch plan is in March 2026-02-03: * In December, delivery volume exceeded the baseline by 20%, generating an incremental ADV of 15,733, the highest since launch. * Monthly total incremental profitability was impacted by higher FHD cost-per-package pressure; however, Dec’25 FYTD incremental profit remains ~ 46% above the DRIVE target. * FXG and FHD combined yield continues to outperform the baseline, reaching $15.49 in December—6.7% above target. 2026-01-29: * New legal approved claim based on rural defered program- "FedEx delivers every weekday to over 4,000 ZIP codes that don’t receive daily delivery for most UPS services" * G2S starts on 2/5 with Sales Managers Headline * G2M starts with live .Com claim on 2/9 and creative assets are in progress, teams can begin preparing for the planned rollout, including but not limited to: - Copy deck and creative concepts coming for multi-channel use and variations by audiences (b2b, b2c, consumer/recipient, top verticals) - FedEx.com claim replacement and placements on site - Why Choose FedEx page updates -Homepage feature (March) -Vertical landing pages and service pages -Email newsletter content blocks -Social – LinkedIn Post -LLM Hive inclusion -Paid Media / Search -B2B/B2C Newsletter -Consumer Email – TBD -Tracking Emails -Retail Store Promotions - TBD -Corp Comm placements -Alliance Marketing Placements – TBD -Vertical Campaign Placements – TBD -DA Marketing Communications – TBD -Other 2026-01-15: * In Nov, monthly delivery volume came above the baseline target by ~6.5% with an incremental ADV of 5,070. * Incremental total profit (-$47K) came in below DRIVE profit target of ~$50K. FHD profitability impacted as CPP came in $1.25 higher than FHD yield. 2026-01-07: * PLP data is not published yet. Expected by early next week. 2025-12-17: * ·In Oct, monthly delivery volume came above the baseline target by ~16% with an incremental ADV of 9,052. * Total operating profit increased to $2.2M from $355K last year, and incremental profit was 5 times higher than the DRIVE profit target. * FHD profitability improved and the combined yield for FXG and FHD continues to outperform the baseline. In October, the combined yield reached $15.84, which is 6.7% above the baseline target. 2025-11-13: * There was CCH dicussion on Alternate Day Service (ADS) and Rural Advantage last week. Given the favorable performance of Rural Advantage, CCH asked to cancel ADS in Planview. 2025-11-06: * In Sep, monthly delivery volume came above the baseline target by ~7% with an incremental ADV of 4,367. * Total incremental profit delivered ~10% gain over the baseline profit targets. * The combined yield reached $15.67, which is 4.3% above the baseline target. 2025-10-23: * No new updates 2025-10-16: * No New Updates. 2025-10-09: * Moved Dominate in Rural to L5 stage gate per Chris's direction. 2025-10-02: * In Aug, monthly delivery volume came above th | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-15 | 2025-01-31
Business Only Initiative: FY26 Ground Transit Improvements | 74781 | 7648 | Business Only Initiative | Commercial - US Product | Commercial | Tanay Das, Libby Malloris | On Track | 2026-4-23: * After evaluation, the recommendation is to defer any transit improvements at this time. There is limited opportunity where lane improvement is feasible and the market opportunity has the potential to pay off the lane improvement * Ops have improved linehaul efficiency and we’ve maxed out 1- and 2-day lanes. Improving 4- and 5-day lanes is too expensive. 2026-02-12: * Met with Chris and Peggy to review Brian's recommendation. * Ops made significant optimizations to reduce cost. Many of the top lanes use rail and purchased Transporation. It's proving to be costly to move those lanes from rail/purchased transpotaion to our CSP linehaul. * Chicago is the top origin marekt for accelration. But peggy mentioned Chicago is dealing with hub performance issues. Also, Chicago's N2.0 timeline also needs to evaluated * Meeting mid-March to decide on the next steps 2026-01-29: * No new updates 2026-01-13: * Brian is still finalizing the final recommendations * Working with Finace team to model net gains for UPS/OnTrac wins in Zone 3-5 * Working with India COE team to pull the data for all carriers to prove the hypothesis that demand lies in 20-24 hr drive time radius more than coast-to coast 2026-01-07: * Meeting with Linehaul engineering team on 01/09 to understand their transit recommendations 2025-12-17: * No new updates 2025-12-09: * Transit recommendations from Brain will be delayed. * Brian confirmed it would be ready in early Jan to review. 2025-11-20: * Brian is also looking at the potential transit improvements from Philadelphia to match OnTrac. * Pulling COE team to conduct a market share gain analysis from Philadelphia market. 2025-11-13: * No new updates. 2025-11-06: * Network Engineering to take November to finalize lane acceleration opportunity/costs for final recommendation. * Tentative end of December for moving to L2. 2025-10-23: * COE team is uploading the data into the Transit dashboard to make it available for further analysis of the potential opportunities by network engineering team. 2025-10-17: * Network Engineering to take November to finalize lane acceleration opportunity/costs for final recommendation. 2025-10-09: * UPS and USPS data pull is completed. Brian B. requested if we could add OnTrac data as well. India COE team is working on to include OnTrac data as well. This competitive data insights on volume opportunity will highlight which are the most lucrative OD pairs for transit improvement. 2025-10-09: * Continue to make progress with the transit dashbaord to capture the UPS and USPS estimated vol in specific lanes. * Brian asked if India COE team could OnTrac vol as well. We don't have accurate OnTrac commit times like we have have UPS or USPS. India COE team is going to investigate how best to include Ontrac volume. 2025-10-02: * With the help of India COE team, we're trying to evaluate lane level volume for UPS and USPS from NIQ sample data. Facing some challenges with extrapolation as we're seeing higher variances with FedEx internal data. 2025-08-25: * Dashbaord updated with USPS and UPS Data. Meeting with Brian tomorrow (09/25) to continue the discussion. 2025-08-07: * Poonam is updating the transit dashbaord to capture USPS data along with UPS data. Goal is to identify potential 3-day lanes that could be coverted in 2-days. Meeting with Brian Buchanan on 9/19. 2025-08-07: * Meeting with Brian B. and India COE team tomorrow(8/8) on the market share opportunity from coverting 3-day parity to 2-day advantage lanes. 2025-07-31: * Met with India CoE team to develop a dashboard to estimate potential maket opportunity from being from 3-day parity to 2-day advanatge lanes. 2025-07-10: * Met with Brian B. to kick off the discussion. * Meeting with India COE next week to evaluate the market opportunity from NIQ database. 2024-10-31: Per discussion at Domestic Product Pod meeting, we're putting this initiative on hold due to Ops resource avaialabilit | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FedEx Authenticated Delivery | 33936 | 7777 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Jennifer Stringfellow, Sarah Mayfield | On Track | **4/23/26** - #7777 Epic 1 - on track, no updates - #7777 Epic 2 and Epic 3 * Discussions underway across Comm teams to define pre-peak launch feasibility * Solutioning kick-off anticipated for week of 4/27 for Epic 2 and Epic 3 **4/16/26** - #7777 Epic 1 - on track, no updates - #7777 Epic 2 and Epic 3 - Path forward recommendation at DJ OH on 4/15 - support to move forward with solutioning / implementation, targeting pre-peak date. - Legal should have feedback on support for path forward following the 4/24 firearms task force meeting - no longer a blocker and will be communicated at next CPEL. **4/9/26** - #7777 Epic 1 - On track for our August 3rd launch date - Testing has started (tracking #'s and QR Codes being developed and tested with functional teams) - Commercial testing to start April 15th - End to End product testing to start June 1 - #7777 Epic 2 and Epic 3 - Path forward recommendation at DJ OH on 4/15 - solutioning to begin pending greenlight - When approved, teams anticipate accelerated ask for pre-peak launch of Epic 2 / Epic 3 but timing is TBD **4/2/26** - #7777 Epic 1 - On track for our August 3rd launch date - Testing has started (tracking #'s and QR Codes being developed and tested with functional teams) - Commercial testing to start April 15th - End to End product testing to start June 1 - #7777 Epic 2 and Epic 3 - Path forward with Firearm / ASR recommendation - pending greenlight - going to DJ Office Hours on 4/8 - When approved, teams anticipate accelerated ask for pre-peak launch of Epic 2 / Epic 3 but timing is TBD **3/26/26** - #7777 Epic 1 on track for our August 3rd launch date (Pricing Strategy being finalized) - Epic 2 and Epic 3 path forward pending alignment with Prod Marketing teams and Legal approval **3/12/26** * Init on track for our August 3rd launch date **3/4/26** * Init on track for our August 3rd launch date * Epic 2/3 - Path forward discussions underway to define best solution to implement Epic 2 - digital release on DSR. **2/26/26** * Init on track for our August 3rd launch date * Epic 2/3 - Path forward discussions underway to define best solution to implement Epic 2 - digital release on DSR. **2/19/26** - Init currently going through all L3 greenlight approvals, shooting for full L3 status by 2/20/26. **2/11/26** - Init currently going through all L3 greenlight approvals, shooting for full L3 status by 2/13/26. - Epic 2 and Epic 3 solutioning will begin the week of 3/2 **2/5/26** - Submitted #7777 for L3 Greenlight on 2/4 - reviews underway and pending confirmation if we need to kick back to L2 to add CSX data that wasn't included in Commercial costing, or if that can be added in L3. **1/29/26** #7777 Epic 1 - Finalizing Financial details in Planview for SCO and Platform - data will be reviewed week of 2/2 #7777 EPIC 2 / Epic 3 - Solutioning will begin late January for Epic 2 and Epic 3 - SCO resource requeset submitted to officially roll Epic 1 core team resources into Epic 2 / Epic 3 - Risk - need legal feedback / approval on proposed FARM solution to handle firearm restriction as interim solution as we wait on ECV firearm flag **1/22/26** #7777 Epic 1 - EGC greenlight to move initiative to L3, officially - Finalizing Financial details in PV for TO Finance approval #7777 EPIC 2 / Epic 3 - Solutioning will begin late January for Epic 2 and Epic 3 - SCO resource requeset submitted to officially roll Epic 1 core team resources into Epic 2 / Epic 3 - Risk - need legal feedback / approval on proposed FARM solution to handle firearm restriction as interim solution as we wait on ECV firearm flag **1/15/26** #7777 Epic 1 - EGC review for overall init on 1/20 to move everything to L3, officially - Pricing teams are currently reviewing the list rate of $20 and will provide approvals ASAP - Product Marketing has requesting acceleration to avoid delays with launch implementation work (G2M, G2S, all testing) #7777 EPIC 2 / Epic 3 - Received SCO PEL g | G: L3 | Active | L3 Feedback Requested | 2025-09-24 | 2027-05-18
Business w/ Tech Initiative: DPFS Customer Multi-Stop Location Management | 34979 | 7835 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Shaun McNeely, Joey Lucchesi, Katrice Manley | On Track | 4/16/26 - Post Workshop - Defining Initiative Roadmap, Re-Assessing Busines Value based on identified scope. 4/2/26 - Preparing for Mulit-stop workshop to support N2.0 Program conceptual architecture scheduled for April 7-9 3/26/26 - Mulit-stop workshop to support N2.0 Program conceptual architecture scheduled for April 7-9 3/5/26 - Preparing for CDR and CCH. Continuing conversations with Ops partners and architects on Ops impacts of init. 2/26/26 - Vintage Address Init is going to position itself as an enabler for Muti-Stop. Need to assess if any NRB should be added to the Multi-Stop Init. CDR is now Mar 20 and CCH Mar 26. 2/19/26 - Presenting at CDR on Feb 27 and CCH on Mar 5 2/12/26 - Submitted to SL2. Requested to present at CDR and CCH 2/9/26 - Submitted to SL2 2/9/26 - QA Review for SL2 with L. Malloris, need to add the EA Common Repository Architecture Document 2/4/26 - Business case Hard/Soft Benefit needs determined, Awaiting PPM # to add to Planview, Meeting scheduled to review Planview prior to L2 Submission. 1/29/26 - Obtained CX ESI approval, PDSM ticket submitted to update planview. Requested PPM acces to create PPM#. Working to finalize Ops cost reduction business case & Init T-shirt size doc for submission to L2. 1/22/26 - Precisely evaluation and benefits will be pulled into Multi-Stop as opportunity to hydrate Customer Location. This will have positive impact on L2 business case value. Seeking Customer Experience ESI as well. 1/15/26 - Precisely workshop outcomes determined vendor address data wil not accelerate timelines for modern address GAS. It does have potentioal to accelerate hydration of the customer location data product and support Mulit-Stop capabilities. Strategic Design architecture effort is ongoing. 1/7/26 - Init pulled into Strategic Design Arch efforts. Meeting this Wednesday to discuss scope of effort. Precisely workshop next week to explore 3rd party location data opportunity. Init ownership being transitioned to Joey Lucchessi. 12/18/25 - Continuing to finalize business case and scope 12/11/25 - No substantial PU Rev Value. Turning attention to Ops Efficiency (MRL Reduction, GPS Pin) and Customer Experience for Value. 12/4/25 - Targeting L2 submission by End of Year. Current Est. Value $26-31M. Shea will become Primary IO upon submission of L2 business case. 11/20/25 - Targeting L2 submission by End of Year. Current Est. Value $26-31M. Shea will become Primary IO upon submission of L2 business case. 11/13/25 - Held meeting with key stakeholders in Precisely evaluation. Provided Commercial Business Requirements to be consolidated with Ops and IT Requirements. 11/6/25 - Continuing effort to build L2 business case. In tandem, working with Ops IT to pursue alt. path outsourcing location capabilities to Precisely. 10/31 - Continuing effort to build L2 business case. In tandem, working with Ops IT to pursue alt. path outsourcing location capabilities to Precisely. 10/23 - New push to generate L2 business case. Buckets under evaluation (MRL Reduction, System Retirement, Ops QA Reduction, CE Case Reduction, Pickup Revenue Growth) 10/17 - Commercially exploring multi-stop P&D at hospitals, operationally working to define future state of Tender Ops RDB, TOM, i-Series, etc. 10/9 - Commercially exploring multi-stop P&D at hospitals, operationally working to define future state of Tender Ops RDB, TOM, i-Series, etc. 10/2/25 - Narrowing focus of initiative to define specific sub-classifications under Business. Specifically targeting Multi-Stop initial release for Healthcare sub-classification, hospitals that have pickup and delivery for Med Tech, Pharma, and Labs/Diagnostics. 9/25/25 - Identifying specific companies across industries to analyze current distribution of ops MRL. 9/18/25 - Established initial customer journey flow. Researching to understand the current distribution of ops MRL stops by postal address and sub-classification. 9/11/25 - Established initial customer | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Delivery PFS - Commercial Delivery Management Phas | 15982 | 7836 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Joey Lucchesi, Shea Anderson | Some Issues | 4/23/26 - EPIC 1 - ENS team has agreed to pull in EPIC 1 deliverables for the end of PI2 or PI3 Sprint 1 in order to meet timeline, new intake process caused this work to be missed for initial PI planning. Team has provided email content and working with the design team to create templates for Bulk Upload notification process. EPIC 2 - Decision has been made to use the Ship Admin role for MVP version of .com UI, this wil allow current Ship Admin to designate additional admin users to manage delivery preferences. **Noted risk** all admin users wil have visibility and management access to all locations set for that organization. A long term solution that allows admins to be tied to certain EAN's will solve this issue but won't be available in time for EPIC 2 release whic is currently Sept '26, accepting this risk keeps us on track for this timeline. Enagagement by key stakeholders continues to be an issue with completing EPIC 2 Solution work. 4/16/26 - Phase 1 work approved at Go to Market governance meeting, resources and support have been assigned to work on all Phase 1 work. EPIC 1 - Bulk Upload template has been sent to 3 customers to collect data early to do some internal testing on provided address information. EPIC 2 - CSD review planned for 4/17, need engagement from all impacted areas, still struggling to get consistent aligmenet with digital team. .com UI design discussions need to begin as soon as possible to make September timeframe. 4/9/26- EPIC 1- working with Sales and Customer Success teams to find 3-4 beta customers that are willing to complete Bulk Upload template now in order to do preliminary valdiation of address data. EPIC 2 - CE team has confirmed that EPIC 2 work will impact FedEx Support Hub (customer interface) and Customer Experience Desktop (internal management) abd is working to support the Sept/Oct timeframe to match the .com release. Digital team stated that DPFS will be added to current ShipAdmin flow if they cannot add to new My Locations tab in time to meet fall release. Adding to current flow would limit creating/managing customer locations to only those with Admin capabilites in ePP. Weekly meetings have been scheduled to work through the .com UI experience. 4/2/26- EPIC 1 - Capabilities 1.8 Metrics & Reporting and 1.9 Address Quality are now on track for July/August timeframe. Some work for 1.9 Address quality for creating reference addresses, promotion of addresses and type ahead functionalty will be done in EPIC 2, address matching and providing Share & GAS ID's will remain in EPIC 1. EPIC 2 CSD review with CE complete, support via ARMOR the new CE desktop is at risk, their MVP release date planned for October but not confirmed. Working with Platform finance lead to add additional costs for CEFS inclusion. 3/26/26- EPIC 1 - all work has been confirmed for PI1 or PI2 which will keep us on track for relaes in late July or early August for Bulk Upload. Additional solutioning work is needed for 1.8 Metric/Reporting but the Data & AI team is engaged an working through it. EPIC 2- 1.1 Recipient Management of Prefernces on .com CSD is complete and being handed off for solutioning. Work still needed on capabilities 1.7 Internal Management of Preferences and 1.12 Authorization/Profile setup. Work sessions are planned for week of 3/30 to continue with CSD completion, still targeting Sept/Oct for EPIC 2 3/12/26- Data & AI resource engaged with Solution architect for 1.8 Metrics & Reporting, handoff complete on 3/13. Still awaiting completion of the Solution document to include architecture changes for SCO and gain commitment for development work in PI2, work that will not change is being worked in the current PI to help keep project on track. AU Domestic project has taken resources from Phase 1 and slowed progress with EPIC 2 CSD completion. 3/5/26- SCO team working to complete re-Solutioining to incorporate changes in the architecture. Changes are expected to be minimal and th | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2028-09-04
Business Only Initiative: FY25 FHD Sunday Coverage Expansion | 89266 | 8035 | Business Only Initiative | Commercial - US Product | Commercial | Libby Malloris, Tanay Das | On Track | 4/23/26 - Request made to submit to L5. Will target by end of this week 4/24. 4/16/26 - No further financial updates until early May 4/10/26 - Feb. final actuals updated and March preliminary actuals entered 4/9/26 - Waiting for Feb. final actuals and March prelim actuals from Finance as they had unexpected changes in PLP. Should have them by 4/13 deadline. 4/1/26 - Waiting for Feb. final actuals and March preliminary actuals week of 4/6 3/26/26 - No further updates until early April 3/10/26 - Jan. actuals updated and Feb. preliminary actuals entered 3/5/26 - CCH update today; final Jan. actuals and Feb. preliminary actuals will be entered before 3/13 2/26/26 - CDR update 2/27 and CCH 3/5; Final Jan. actuals will be available early March. 2/19/26 - Preparing for CDR update on 2/27 and CCH on 3/5. 2/11/26 - Financials updated with Dec. final actuals and a Jan. projection. Jan. volume low YOY because of the storms and alot missed being delivered/invoiced in Jan. 2/5/26 - No further updates until final Dec. actuals and Jan. projected actuals are available from finance; targeting 3/5 for CCH update 1/29/26 - No further updates until early Feb. when we will have Dec. final actual and Jan. projected actuals; CCH update late Feb./early March 1/22/26 - No further updates until early Feb. when we will have Dec. final actuals and Jan. projected actuals 1/13/26 - Entered updated Nov. actuals and a Dec. projection. Stronger revenue driven by WMT yields being higher than LY (and used for the Dec. projection) along with peak volumes. 1/6/26 - There is a delay with PLP, so Nov. final actuals and Dec. projected actuals will not be available until week of 1/12/26 12/18/25 - No further updates until early Jan. when we will have Nov. final actuals and Dec. projected actuals 12/8/25 - Oct. final actuals updated and Nov. projected actuals added. 12/04/25 - Waiting on data for Oct. final actuals and Nov. estimated actuals 11/20/25 - no updates until October final actuals and Nov. projections revised early Dec. 11/10/25 - October projected actuals added. 11/4/25 - September final actuals in Planview. Waiting until next week to enter the October projected actual. 10/23/25, 10/20/25 - September actual "projection" corrected and revised, changing the NRB from negative to a positive $694K. Final actuals will be available early Nov. 10/16/25 - Next actuals update early Nov. Walmart volume shortfall remains driver for missing forecast targets. 10/6/25 - Revised final August actuals and entered the Sept. actuals estimate. 9/25/25, 9/18/25, 9/2/25 - Revised final July actuals and estimated Aug. actuals entered. 8/28/25, 8/14/25 - Next actuals update early Sept. Walmart volume shortfall remains driver for missing forecast targets. 8/4/25 - Revised June actuals and estimated July actuals entered. 7/24/25 - CCH decision to stay the course despite softer than expected Walmart volume; continuing to track performance and waiting June actuals early August. 7/3/25 - May actuals updated and a revised June forecast put in for June actuals in Planview 6/26/25 - May "forecast" was entered as actuals and will be revised with actuals in July when available from PLP 6/19/25 - May actuals will be available early July from PLP 6/12/25 - May actuals will be available early July from PLP 6/4/25 - Waiting Domain Lead L4 approval 5/29/25 -Submitting to L4; April actuals not available until early June (PLP) and all Milestones current 5/22/25 - Re-submitted 5/21 for L3 5/15/25 - Revised business case is complete reflecting lower costs and working to re-submit to L3 as quickly as possible. 5/8/25 - Finance is revising the business case and will have available by 5/14 to then put in Planview for L3 submission. 5/1/25 - Finance and Linehaul Eng. are reevaluating cost assumptions before we resubmit for L3. 4/24/25 - Finance and Linehaul Eng. are reevaluating cost assumptions before we resubmit for L3. 4/17/25 - PDSM ticket | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-04 | 2027-02-25
Business w/ Tech Initiative: Delivery Window Solution | 72906 | 8036 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Julie Lavelle-Acor, Tanay Das, Sushant Misra | On Track | 4/23/26 - Continuing to work with legal on contract language and defining customer enrollment process flow to the ISP - Continuing to update the SCO template 4/16/26 - Working with Chelsea Chase, Legal, to fortify ISP contract language to support Delivery Windows and Vanity ZIPs - Updating SCO template for Delivery Windows (U.S./Canada) and Vanity ZIPs 4/9/26 - Continuing collaboration with Brad Car to complete the SCO L2 IO template - Reviewing a newly introduced EDD feature from Ralph Lauren; partnering with Vinod Nair to assess feasibility 4/2/26 - Refined AB2s to include Vanity ZIPs and ops system touchpoints - Completing Business scenarios and Scope statements for SCO 3/26/26 - Completed an end‑to‑end ops system walkthrough with Brad Car (SCO Architect) to review impacts and considerations. - Gained UPS insights on the Ralph Lauren Delivery Window pilot from Tracy Christoffersen, highlighting new operational features. - Assignment of architectural resources has been pushed back until mid-April 3/12/26 - Architectual ownership discussion 3/10; Approved to change lead architect to SCO from Commercial - CMAT Governance advised that CSP settlement is not needed if they: fortify CSP contract language by adding delivery compliance language, including language to support Vanity ZIPs, raise visibility within L&P and Medals and assess the impact to productivity. - Walk through of Ops systems impacts with actions to assess FORGE capabilities; Need to determine if Delivery Windows will need some sort of identifier since it is not product driven. - Batch update tool is needed to avoid single entry into FRO - FXG Customer Engineering not in support of additional pilots until it can be supported by Tech 2/26/26 - Architectural resource assignments underway: - Data & AI assigned - Commercial - available March 2nd - SCO - available mid-March pending completion of current assignment - Accepted as an RFID Use Case as they build out the product; No DRIVE initiative 2/12/26 - Added to Strategic P&D bi-weekly meeting to provide line of sight to prioritized initiatives; update provided 2/3/26 - Continuing to make progress on Vanity ZIP alignment with Hailey Cobb 1/29/26 - #44 on enterprise list - 1/27/26 - Aligned with Hailey Cobb on Vanity ZIPs "ability to" statements; she's verifying with FXE ops that verbiage is correct - 1/26/26 -Initiated process to develop Canada's financial business case layer 1/22/26 - #46 on enterprise list; still awaiting architectual resources to be assigned - 1/16/26 - Vanity zip overview with FXE Ops engineering; opportunities, alignment, capacity constraints & identifying customer conflicts 1/15/26 - 2nd boost to Top 50 on Enterprise list; awaiting architectual resources - P&D strategic design review 1/12/26 - CMAT governance rescheduled for 3/2/26 - Assessing if Surround or Advanced Tracking is a better inbound visibility option for recipients 1/7/26 - No Update; OOO on vacation 12/18/25 - CMAT presentation was well received and will advance to governance meeting on 1/12/26 - Rationalizing process flows and capabilities with Canada and Delivery PFS #7836 12/11/25 - CMAT project review with Chelsea Chase from Legal - 12/18 CMAT presentation scheduled - Canada customer interviews underway to confirm desired features (S. Misra) - H. Cobb validating current processes, customer usage, identifying ops resources, etc for vanity ZIPs 12/4/25 - Officially boosted and awaiting architectual resources to be assigned. - Hailey Cobb assigned as resource to support Vanity ZIP code work - Reviewed new reporting option with Surface engineering - Will complete side-by-side audit of new vs old pilot reporting - Submitted request to get on CMAT schedule to discuss new contractor settlement 11/20/25 - Received Surface Ops approval/support to advance in L2 from Scott Ray 11/17 - Provided additional information to Heather Zaiontz for boost meeting 11/20 11/13/25 - Removed from PRT backlog and will be boosted | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Expand First Overnight to Hawaii | 15678 | 8149 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Richard Wilkes, Alfredo Moran | On Track | 6.12.25 This initiative (#8149) is considered complete, and no further updates are needed. 6.525 No updates to report. 5.29.25 April actuals have been entered. 5.15.25 No updates to report. 5.8.25 Steady state. Trending as expected. 1.16.25 Gained approval from TO to advance initiative from L4 to L5 eventhough initiative has not reached money state. Submitted request in Planview 1.16.25 to advance initiative to L5. 1.9.25 - Awaiting Dec2024 actuals from Finance Team (ETA after 1.15.25). Asked McKinsey Team to proceed with submission of "read-only" request to advance initiative from L4 to L5 to TO for approval. 12.19.24 - Monthly FO to HI volume returned to average levels in November 2024. Will resume approval process to advance initiative from L4 to L5 without reaching money state in January 2025. | K: L5 | Completed | L5 | 2022-11-01 | 2023-10-05
Business w/ Tech Initiative: Unified FXE and FXG Delivery Door Tag with QR code | 15305 | 8409 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Madeline Virden | On Track | Commercial Parking Lot decision - updated title and status to reflect accordingly on 8/11. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-07-22 | 2024-10-03
Business w/ Tech Initiative: Enhanced Commodity Visibility | 23553 | 8548 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Stephen P. Joyce, Amber K. Redmont | On Track | Update (4/23) - Dan Ruth is the assigned architect to develop our solution, and we have been having meetings this week as we work through the process of identifying all of the impacted ARTs and who the appropriate contact will be. Given the complexity of our project and the number of systems impacted, we are finding areas that need to be considered than originally anticipated. Zack, our EA lead has suggested to me that he feels we should be finishing up the Solution part in June, leading us to request to move to L3. Update (4/16) - Solution Architect Dan Ruth has started the process of developing our solution by reviewing documentation to determine the ARTs that will be impacted and will be lining up resources to move forward. Update (4/9) - Team turned over the BA Activity Diagram based on our AB2 Statements to our Solutions Architect to begin work on Conceptual Architectural Design. Update (4/1) - Team continues to meet with stakeholders to review and gain approval for AB2s. Per Zack Sherman, we can begin the handoff with Dan Ruth to beging Solutioning as soon as Karen is completed with the Business Architecture Map, which she has committed to completing by 4/3. Update (3/26) - Meeting at Manager and MD level between the Business and BA Architecture was held on Monday where it was decided the project will remain as is and intact and will not be broken up. Team will finalizing AB2s and turning over to EA to begin Solutioning. Update (3/12) - no new update, team continues to finalize AB2s. Presented project capabilities to MDs Chris and Taylor (3/9). Update (2/26) - no new update. EBA team met with MDs and there will be a follow up meeting to be scheduled. Update (2/19) - current status: AB2's consolidated down to 57, due date and review with EBA MD 2/20. Update (2/12) - current status: working to consolidate AB2s where possible as currently have 135 AB2s. EA lead is going on medical leave and replacement will begin joining meetings 2/12, further pushing out the scheduling of the Conceptial Architect Design for ECV. Update (1/29) - no new update Update (1/22) - no new update. Update (1/15) - no new updated, team continues to make progress in Decomp/Analysis stage. Update (1/7) Continuing working sessions with Enterprise Architects and stakeholders to developing AB2s and Capability statements for all commodies that included in this initiative. Update (12/11) Work with the Enterprise and SCO architects continues with bi-weekly working sessions. Update (12/4) Provided update to DJ on project status Monday (12/1) Met with EPSM (12/3) team to review project regarding reclassification of ECV to Business Continuity, where it was determined to be unnecessary as we are already engaged with architects from Enterprise and SCO and advised to update Planview – created ticket in PDSM to go back to complete missing L1 data points and update L2. Enterprise and SCO working sessions began and teame is meeting twice a week as part of concept and decomposition work with an estimated completion date of April. Completed initial version of LBC, as this will remain a working document and will be updated throughout the concept and decomposition process. Working with Environmental Waste team to develop AB2s and Capabilities for inclusion within ECV. Update (11/13) Kicoff meeting with IT scheduled on 11/13 to discuss path forward to creating PFS solution for replacing handling codes Update (11/6) Financials have been entered for FY28 forecast as we do not have a firm timeframe for when our project will be ready to be launched. Project is still dependent upon a solution for the replacing service codes, as a result, no new update on when the PFS work to identify and define a new replacement for service codes will begin. Update (10/23) No new update. Update (10/16) No new update, team continues work on AB2s. Update (Oct 9, 2025) Team continues to work to build AB2 statements so that we can build our requirements do | E: L2 | Active | L2 & CCH | 2023-09-06 | 2026-06-24
Business w/ Tech Initiative: Dangerous Goods/HazMat PFS Phase I - Surcharges | 81667 | 8920 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Stephen P. Joyce, Benjamin Glenn | Some Issues | Initiative is currently delayed as we are waiting for a resource to fill the role of project (Epic) leader. Team was informed a resource is expected to be made available by end of February, 2025. Until a resource is available, inititiave remains on hold. (DATE; January 16, 2025) | E: L2 | On Hold | L2 & CCH | 2024-07-22 | 2026-04-01
Business w/ Tech Initiative: Dangerous Goods/HazMat PFS Phase II - Automation | 88865 | 8921 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Stephen P. Joyce, Benjamin Glenn | Some Issues | Project is officially on hold as agreed upon by marketing leadership due to resource constraints. (Date: April 3, 2025) Project is on-hold temporarily as Product Marketing team has been without a manger to make recomendations on next steps for building the application that will need to be integrated into FedEx automation systems. (Date: March 7). Project was presented to the weekly Commercial Triage meeting explaining the desire for a process to build the solution which includes the "HOW" which includes identifiying the best approach to either build internlly, buy a solution from a vendor or a combination of the two. Architects on call determined we need to complete that effort before requesting guidance on internal system impact and t-shirt size. (Date: Feb. 6, 2025) | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-08-14 | 2025-04-28
Business Only Initiative: Ground Economy Label Adoption | 15285 | 9197 | Business Only Initiative | Commercial - US Product | Commercial | Jason Shepard, Miles Perry | On Track | The project has been under way for over two years, and the new FedEx Ground Economy label is in market and customer upgrades are complete. Monthly FGE label compliance is consistently above 99%. | K: L5 | Completed | L5 | 2023-04-03 | 2024-04-30
Business w/ Tech Initiative: Rationalize On-Call Pickup Product and Scheduling | 15295 | 9200 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Emily Marcinkowski, Jorge Jaramillo, Ayushi N. Sheth | On Track | 4/23/26: Ongoing deocmp sessions. The team put forth a plan on how to expedite 9200 and is evluating ways to capture busienss value earlier. 4/16/26: Ongoing decomp sessions. L2 end est 12/11, L3 solutioning 1/18/27-11/8/27 4/2/26, 3/26/26, 3/12/26, 3/5/26: Resuming decomp sessions as planned on 3/9. Updated Money Step to Jan 2027, will not be delivered prior to then 2/26/26: Agreement on sequencing of 7100 and 9200 work. Team is continuing to plan the work betwen the initiaitives for decomp sessions resuming week of 3/9. 2/12/26, 2/5/26: Continuing to work on open items, resuming decomp sessions on 2/12. Awaiting to hear decision on next steps for Strategic P&D Design work. 1/29/26, 1/22/26, 1/13/25: Decomp sessions are currently on hold as this initiative is being worked as part of the Strategic P&D efforts. I will be working with Enterprise Architects to refine the scope in the meantime. 12/18/25, 12/11/25, 12/4/25, 11/20/25, 11/13/25, 11/6/25: Ongoing decomp sessions to complete L2 deliverables. Sessions scheduled through the end of January 2026 with 3/15/26 assessment and conceptual architecture completion date. 10/30/25, 10/23/25, 10/16/25: Ongoing decomp sessions to complete L2 deliverables. Sessions scheduled through the end of January 2026. 10/2/25: Initiaitive launch date is July 2026 at the earliest. Financials have been updated to reflect this change. 10/9/25, 9/25/25, 9/18/25: ***Completed*** Limited channel launch of FXG SDOC SSP pilot while other channels are being looked into for enablement issue. Working through capability refinement for 9200 with architects and business partners **Next steps:** continue to refine 9200 capabilities 9/4/25: **Completed**:Working on testing plan for FXG SDOC SSP pilot. Continuing to work on the business case and refining metrics that will be used. **Next steps:** working on Go-to-Sales plan and testing for pickup scheduling enablement. 8/28/25: **Completed**:Working on SDOC pilot in 2 SSP stations (Fort Myers, FL and North Portland, OR) pre-peak 2025. Held meetings with impacated VPs, no concerns so we will move forward with launch. Provided update to DJ. Continuing to work on the business case and refining metrics that will be used. **Next steps:** working on Go-to-Sales plan and testing for pickup scheduling enablement. 8/14/25: **Completed**:Working on SDOC pilot in 2 SSP stations (Fort Myers, FL and North Portland, OR) pre-peak 2025. Held meetings with impacated Sr Mgrs and MDs, station mgmt and district staff. Continuing to work on the business case and refining metrics that will be used. **Next steps:** working on Go-to-Sales plan, presenting to impacted VPs on 8/25, working to get on CDR agenda, quick update to DJ on 8/18. 8/7/25, 7/31/25, 7/24/25, 7/10/25, 6/26/25: Ongoing workshops to address TO ask items. Continuing to refresh the business case, ongoing conversations with Ops to validate assumptions. Working on a SDOC pilot in an SSP market for pre-peak launch. 6/19/25: Continuing to refresh the business case, ongoing conversations with Ops to validate assumptions. Working on a SDOC pilot in an SSP market for pre-peak launch. 6/12/25: Refreshing business case 6/5/25: met with Enterprise demand management and entered multiple initiatives into Planview in support of Pickup PFS roadmap. The new initiaitves will go to triage next week. Commercial architects are working on the documentation for #9200. 5/15/25: asessing how to reshape the Pickup PFS demand, meeting with Op Model experts for guidance on our defined business needs. 5/1/25, 4/24/25: Planning for alignment meeting week of 5/5 to align on priorities of Pickup PFS and Common DIspatch dependecies to have a joint roadmap refreshed and move work to decomp. 3/20/25: Meeting with portfolios to understand data needs, discuss Atlas direction, refreshing Automated pickup business case. 1/16/25: Identifying work to move into decomp, a majority of work is dependent on SCO Common Dispa | E: L2 | Active | L2 & CCH | 2023-05-24 | 2026-12-31
Business w/ Tech Initiative: FedEx Ground Economy (FGE) Transit Quotes | 17267 | 9337 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Tarun Kumar, Miles Perry | On Track | 01-28-2026: * Initiative submitted for SL5. * Per yesterday discussion, there was an agreement to move the initiative to L5. Vanessa and Warner will work with TO finance leadership to obtain written approval. Upon TO finance approval, Heather will work with Planview team to mark the initiative as ‘completed’. 01-27-26: Scheduled discussion with TO finance and EPM team for initiating the process to move to L5 per directions from POD lead. 12-11-2025: No new update. Working on details for initiating process to move the initiative to L5 as per POD lead's directions. 12-04-2025: No new update 11-20-2025: Still tracking last two CSPs - Proship and Shipstation. The API certification for Proship is paused until comprehensive rate and transit time API is fixed. Shipstation is still in negotiation with FedEx to sign global service agreement. 09-25-25: No new update. Tracking the last two CSPs - Proship and Shipstation. 09-11-25: Tracking last two CSPs - Proship and Shipstation in terms of progress of API certification process. Proship is at 60%. ShipStation is going through contract execution and assignment of production credentials from FedEx. ProShip's delays are due to challenges with how F1R rating works today with comprehensive rate and transit times API. There are teams working on updating the API to improve the F1R experience, and that's what ProShip is waiting on. 09-04-25: Tracking last two CSPs - Proship and Shipstation in terms of progress of API certification process. Proship is at 60%. ShipStation is going through contract execution and assignment of production credentials from FedEx. 10-29-24: Follow-up is on-going with the CSPs on the progress of API certification process Adoption of FGE transit quote is tracked based on API certification (as part of webservices migration to API). FGE transit quote has been incorporated as one of the requirement for API certification. Currently, API certification process has been delayed as CSP feel that there is lack of testing solution from FedEx side. Potential the general timelines for API certification has been pushed to Dec'24. | K: L5 | Active | L5 | 2023-04-19 | 2023-07-28
Business w/ Tech Initiative: Canada - Domestic Ground Weekend Delivery |  | 87034 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Mahmoud Fahmy, Nipa Pandya | Some Issues | 20260423 - •The zip to station process is facing issues by the SSAMI team and is at risk of not making the URSA L3 Test load for May •The Architect team is suggesting utilizing only co-located stations as a solution for Final Commit calculation as a solution to the HD service type codes not being returned. Solution needs to be finalized and requires: oURSA team to return the 2K series co-located station as a destination – URSA team has indicated on 4/23 that this may require 3 sprints and may only start in next PI oTesting of solution requires a dix to defect #338139 which continues to block testing - SVM is unable to generate commit dates. Data & AI team is working with the PCF team and has identified an issue with the JVM on the service-days API. This defect is not unique to the initiative but impacts it. •SCO team is escalating today to Rob Crane (MD IT Network Planning) and will take the issues to Tracci Schultz SCORED meeting next week for visibility and support. 20240416 - *Architect team is researching a solution to address the service type code issue *Commits not flowing to SVM in test environment, defect root cause identified and in process of being fixed. This is not an issue related to the project, but a general issue and is blocking some of our testing. *Issue for test scenarios in new Rating engine addressed and testing will be completed before end of April *Financials update in Planview to reflect new Money Step of August 3, 2026 20260409 - * URSA team analyzed the two remaining defects from last week’s update and reported they have a fix for one. **The second defect #308055, where the HD service type codes are not being returned was communicated by the URSA team as a bigger challenge and requires additional attention and possible more effort in solutioning and development that may require extended time.** Lead architect will organize a call this week or early next week with URSA team for further discussion. * Regression testing for Rating is not possible in legacy rating system as we have moved to new rating engine. Rating ART team will meet Friday 4/9 to agree on test cases requirements. * Ground Maps WGSM defect has been resolved and defect closed, maps now successfully showing Saturday commit for Canada residential deliveries. 20260402 - Awaiting open two defects resolution following call scheduled with URSA/UVSDK on April 2 20260326 - *E2E testing continues. Currently two defects not yet resolved and require further investigation with URSA/UVSDK teams (discussion scheduled for April 2) *Money step revised in Planview to August 3, 2026. 20260312 - *UVSDK will attempt to do Zip-to-station validation during PI1, and target end of March for completion. *Launch date now estimated as August 1, to allow for e test cycles of URSA *E2E testing continues this week and next, most previous defects are closed, but a few new ones have emerged and the teams are working through them. 20260305 - *E2E testing continues. 6 defects under EPIC 1 (Saturday Commit) currently open and classified as high severity. These defects are under analysis by URSA, LLSI and VACS teams. *252216 - High - RATC: Not getting Saturday Commit details for Intra Canada Ground rate quotes on L3. Under analysis by VACS team *275136 (new) - High - Mobile: Unable to perform shipping for CA-CA in both ANDR and IOS *277057 - High - ROSS: getOperationalData returns deliveryDate of SATURDAY with 4 or 5 days transit lane i.e with Shipdate of Monday or Tuesday. Under analysis by URSA team *277059 - High - LOCS: lookupLocationByStoreNumber is returning Error 163, No data matching the lookup criteria was found for storeNumber-2142(New FXH location for Canada). Under analysis by LSSI team *278038 - High - LOCS-ValidateServicingLocationForAddress is returning Error 006,No result returned for with the new Canada FXH Terminal's. Same root cause as defect 277059 *282002 - High - VACS: Incorrect locationNumber returned in reply | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-18 | 2027-01-20
Business w/ Tech Initiative: Per Order Delivery Instructions |  | 108601 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Madeline Virden, Joey Lucchesi | On Track | - 4/23/26 - Concerns with Epic 1 timing from an API prioritization aspect / Epic 2 alginment with Digital in progress - 4/16/26 - Continuing to map Epic 2 / No updates for Epic 1 - 4/9/26 - Modifying Epic 2 scope to include business hours factoring into route planning, but still targeting May for L3 - Wayfair has requested tech specs document for Epic 1 by Aug. or they cannot commit resources. Architectural team is aware and planning accordingly - 4/2/26 - L3 approved for Epic 1 - Epic 2 updated L3 date has been moved to May 4 - 3/26/26 Awaiting final Platform approval to move MVP into L3 (exception process) - 3/27 - L3 Kickoff - 3/12/26 Leadership approved spillting epics and prioritizing MVP - Progressing to L3 asap - Commercial - 3/9 - Approved - SCO - 3/10 - Approved - Platform - 3/11 - finalizing impacts to each system before approval - 3/5/2026 finalized scope for MVP / leadership meeting 3/6 to socialize - 2/26/26 Solidifying MVP scope to meet Oct. launch and continuing with L2 architecture for future state launch in Jan '27 - PPM request submitted 2/25 - Leadership meeting to share scope 3/6 - CPEL escalation for MVP on 3/11 - 2/19/26 Data and AI cloud strategy solidified and awaiting announcement. Architects are aware of PNC selection are are continuing with CA - Repositioned scope to prioritize a limited API to launch pre peak leaving the full scope to launch Jan. '27 - 2/12/26 Data & AI resource assigned - getting caught up to speed on project status - Pending leadership approval by 02/13 for scope resequencing or continue on current path with launch pushed to Jan. '27 - 2/5/26 Pending final key decisions from Adam Smith/Ali Zaidi regarding cloud platform and Data - AI engineer assignment escalated and waiting for resolution - L3 submission and proposed launch of Oct. 2026 is at high risk - 1/29/26 Solidified that pfs will be built on Gen 2 systems - Need assitance gaining Data Engineer (EO and IO have taken correct path to recieve resource, but have not been successful) - 1/22/26 Proposed workaround: ETAC decision to move forward without SAD Architect. Will require Data Scientist and Data Engineer to join team - SAD architects are only used at an exception based on project priority. Project is ranked 81 so internal team proposed a workaround moving forward without a SAD Architect but will need to request a D&AI scientist and engineer to agree and complete L2 architecture and outcomes - 1/15/26 New ETAC lead assigned (Mike Smith) - Data & AI leads have been reassigned and we now need new leads - Decsion to move forward with Shipment Demand Order for customer delivery instruction intent - 1/7 - Gained Lead Business Architect - Roopa Mallu - L3 date will pushed back due to ramp up and architect change - 12/18 - Alignment for Enterpirse Architecture on N2.0 P&D Strategic Design. Could possibly impact our L3 timeline. Still hosting Architecture sessions beg. in Jan. - 12/11 - Lead Architect reassigned for 2+ weeks. Will delay L3 launch date by a few days. - Data & AI multi cloud strategey decsion in the works and must be decided to proceed L2 conceptual architecture - FORGE team alignment on display redesign - 12/4 - Data & AI MD leadership discussion to highlight risks, issues and gain alignment on platforms 12/9 - 11/20 Assessment and Decomp approved / began conceptual architecture - 11/17 Assessment and Decomp Review - Planned Data & AI leadership disucssion on GCP/Azure and AI strategy - 11/6 - Event storm completion & L2 Decomp Final Draft Review - 10/23 target dates: L2 Initiative Assessment and Decomposition Target Completion: 10/30/25 and L2 Initiative Assessment and Decomposition Final Review Meeting: 11/17/ 25 - 10/16 Business architect solidifying what gaps are left to finish L2 assessment and decomp - 10/9 - Solidifying scope through Epic Hypothesis statement - 10/2 Esitmated L2 decomp completion week of 10/13 - L2architectural design w | E: L2 | Active | L2 & CCH | 2025-05-14 | 2027-05-13
Business w/ Tech Initiative: Mainstream FedEx Ground Economy (FGE) Service |  | 126286 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Tarun Kumar, Julie Lavelle-Acor | On Track | **03/12/2026:** * No new update **03/05/2026:** * No new update. Current entrprise ranking for the initiative is 115. **02/12/2026:** * No new update **02/05/2026** * No new update **01/29/2026** * No new update **01/22/2026** * No new update **01/15/2026** * No new update **01/08/2026** * No new update **12/18/2025** * No new update **12/11/2025:** * No new update. **12/04/2025:** * No new update. Mainstream FGE priorirty in PRT backlog has not changed. Awaiting next steps from architects/EPM team on cross domain discussion. **11/20/2025:** * No new update. Mainstream FGE is still 10th in PRT backlog. Awaiting next steps from architects/EPM team on cross domain discussion. **11/13/2025:** * Awaiting next steps from EPM/architects on the cross-domain discussion. Mainstream FGE is still 10th in PRT backlog. **10/23/2025:** * Received official CCH greenlight approval. * Initiative moved to 10th position in PRT backlog. Waiting on the next steps from EPM/architects on the cross-domain discussion that is supposed to be scheduled for mainstream FGE. **10/17/2025:** * Initiative formally submitted for CCH greenlight approval via planview. **10/16/2025:** * CCH lead confirmed submission for CCH greenlight. It seems that approval was obtained based on previous RMC discussions on 02/13/2025. Will submit the initiative formally for next steps soon. * Awaiting invite for cross portfolio discussion. Mainstream FGE is 12th in PRT backlog and 3rd for light touch. **10/09/2025:** * Commercial L2 triage was complete. Architect requested to take the initiatve to cross portfolio domain meeting to better assess the size of artchitectural changes on revenue management/pricing side. Based on the cross portfolio domain discussion, the next steps will be determined. Awaiting invite for cross-portfolio discussion. * Initial review with CCH lead is complete. CCH lead is working on best path forward for CCH greenlight for the project. * Working with TO finance to refine L2 financials based on Mark Mantaro's feedback. **10/02/25:** * Initiative has moved to L2. All required approvals have been obtained. * Completing steps and preparing content for CCH greenlight. Scheduled initial review with CCH lead. * Working to get a review session scheduled with DJ as part of CCH greenlight process. **09/16/25:** * L1 architecture assessment is complete. * QA check is done for submission to SL2. **09/11/25:** * Awaiting final assessment on project t-shirt size and portfolio impacts from architects as part of L1 architect assessment - Organized manager level alignment call as some of the architects had questions about similar Ground initiative in the pipeline and wanted clarity on the intent of different Ground initiatives. * PPM number creation is complete. * L1 business case financials are complete. **09/04/25:** * L1 business case financials are complete. * L1 arthitect alignment is ongoing. Awaiting final assessment on project t-shirt size and portfolio impacts. * Initiated PPM proposal creation process. **08/27/25: ** * Reviewed final L1 business case financials with TO finance. The financial approach is based on incremental surcharge revenue for address correction and RTS approved by TO finance. * Initiated L1 architect alignment process. **08/14/25: **Enagaged TO and Surface finance teams to evaluate baseline and target value. Awaiting TO finance guidance on the approach for the L1 business case financials. **07/31/25:** Enagaged TO and Surface finance teams to evaluate baseline and target value. Call with TO finance will be scheduled for further evaluations. **07/24/25:** Enagaged TO and Surface finance teams to evaluate baseline and target value. | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Roadmap Local (ROLO) - Same Day Route Delivery |  | 132009 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Michael Shansky, Miles Perry, Libby Malloris, Tanay Das | On Track | 4/23/26 - With FHD Extra Hours Working with Ops Planning and Engineering to evaluate operational, financial feasibility, the technology impact to enable FXG/FHD product sorting at the ramp. PO Service Recovery - Working with Ops Engineering to define threshold at stations with eligible overnight volume. As well as evaluating the 60 stations where Walmart is looking to inject volume midday. Ops engineering and Finance refining elligbile volume and modeling cost to serve given PO + Walmart Volume in targeted stations. 4/16/26 - FHD Extra Hours - Ops Leaders provided feedback at Service Council on the concept, Given that feedback we are working to evaluate Express Ramps as the consolidation point for concept as opposed to Ground Hubs. Due to difficulty for Hubs to processes volume at a time when they are catching up on midnight sort volumes. Ops leaders feel as if this is a better time to leverage Express Ramps. - Working with Ops Planning and Engineering to evaluate operational, financial , the technology impact to enable FXG/FHD product sorting at the ramp; UPDATE ON PO SERVICE RECOVERY WITH MID DAY SORT Gather locations where we are targeting for PO service recovery via a Mid-Day sort. To understand what markets we could be leveraging the mid-day sort and how that pairs up with incremental sameday business. 3/19/26 - Continuing evaluating and socializing concept with several Ops Engineering teams, including the Customer Logistics team, who noted existing late‑induct lanes in ETNA and DFW for Walmart occurring today. No major operational constraints listed for existing late - induction lanes which cover way overnight footprint today. Working to be added to an upcoming Service Council agenda to share and gather feedback on a concept with ops leaders before planning pilot in market. 3/12/26 - Met with the Service Excellence team who manages Weekend Advantage Program and how the FHD Extra Hours concept would mirror this process for enrolling accounts in transit acceleration. Mapping how Weekend Advantage works today, including onboarding, CLS rule configuration, and out of scope volume management. Help us in understanding the technical requirements if i 2nd rule set is needed for our concept. As well as understand the lift required to Stand-up and Manage FXG Extra Hours as well. Additionally met with Ops Territory SR Manager to socialized the concept as well as get feedback and buy-in for testing concept with a pilot. Very receptive to the concept, open to piloting concept. Connected with Customer Engineering Teams on FHD Concept, raised concerns on timing constraints of full overnight footprint. Additionally mentioned Late Induct lanes right now with Walmart with thoughts of expanding. Meeting with them to review and align on the work that team is doing. 3/5/26 - Reviewing Extra Hours concept with Service Excellence team who assisted on weekend advantage on potential CLS rules and enrollment process needed. There are no changes to CLS Rules if the scope stays with just FHD however expanding to FXG would require changes. Working thought details of what: - Enrollment in a specific market could look like. - Handling of volume outside of scope and the impact to service. - What would be required for CLS Rules to enable commercial volume be accelerated in the same fashion? Additionally Met with Digital Team around the impact to EDD. After enrollment how would we flag these packages that needs to be accelerated. Likely would work similarly to that of Weekend Advantage, and working to understand what that looks like today. 2/26/26 - Reviewing the Extra Hours FHD concepts at CDR this Friday. Continuing with: Business Case development. Reviewed Extra Hours concept. with Service Excellence team who assisted on weekend advantage on potential CLS rules and enrollment process needed. Preliminary thoughts are minimal to no additional tech requirements needed to support this concept. Ops Engineering teams have reviewed | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: ZAXIS |  | 142089 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Ramos Barreda, Alfredo Moran | On Track | 04/23/2026: Completed COM Architecture Review for Ability 2 with no issues; still awaiting IT resource assignment. Aligned with F1R on future differentiated pricing needs. Ops Planning & Eng initiated surface volume analysis; we will request a timeline to engage Finance. Meeting with the Canada Team today to explore "Own the Border" synergies. 04/16/2026: Finalized commercial Ability 2 statements and developed ZAXIS US Domestic Parcel Strategy slides for Mark. Met with Chris Burr to align an L2 International initiative with our Ability 2 statements for quoting ZAXIS weekend deliveries. Today's focus includes discussions with Air Ops on testing SO ground movement, and evaluating LMO data scalability for ZAXIS/E3 volume with GNP Tech Transformation. 04/09/2026: Aligned Ability Level 2 statements to support repurposing Express Saver with added operational and commercial capabilities. Incorporated contingency‑event considerations into the project scope. Held discussions with Air Ops, and separately initiated conversations around weekend operations. Continued alignment planned with Ops, Pricing, and Commercial. 04/02/2026: Commercial discussions on portfolio fit continue, including exploring repurposing Express Saver versus creating a new product. This has been aligned with architects, with documentation covering both paths. Additional sessions next week will focus on operations, pricing, contingencies, and air ops. 03/25/2026: Continuing to define ZAXIS product placement within the portfolio and refine the target customer experience. Additional resources have been assigned, including a PRT‑PM and PISA‑SCO support. 03/12/2026: We expect a PRT PM to join the workstream by the end of March. We continue shaping the ZAXIS value proposition and positioning. 02/26/2026: Architects continue Assess & Decomp and stakeholder reviews; workshops will start once IT is assigned. Ongoing data work on 1‑day/2‑day lanes to clarify customer choice and ZAXIS positioning to avoid margin erosion. 02/12/2026: Architects continue progressing through Assess & Decomp. Met again with Pricing to clarify additional questions and maintain engagement. 02/05/2026: Met with Pricing to introduce the project and address initial questions; follow-up session scheduled to continue engagement. Architects continue work on Assess & Decomp and further PISA assignments. 01/29/2026: Continued working with engineers as they progress through Assess & Decomp. Scheduled an additional session to clarify project questions. Still awaiting assignment of an IT architect. Planning to engage Pricing to provide an overview and align on next steps. 01/22/2026: Met with Network Engineering to align on ZAXIS LMO/Automation requirements. Jeremy assigned Mike Harris, and we held an intro discussion with him to outline next steps. 01/15/2026: Had second session with architects to finalize “Ability to” statements and begin assigning them. Network Engineering meeting scheduled for Friday to align on LMO and Automation requirements. 01/07/2026: Met with architects to set next steps. Reviewing data to gauge volume shifts, including 2Day. Meeting with Network Engineering next week to align on LMO/Automation “Ability to” statements. 12/18/2025: Completed two sessions with engineers to define first steps and draft “Ability to” statements for ZAXIS. Team will pause for holidays; I’ll focus on volume analysis. 12/11/2025: Commercial kickoff scheduled for Friday; provided feedback and additional inputs on the financial business case for SVP+ review. 12/04/2025: Continuing to work with Finance to confirm alignment on the business case. Commercial kickoff completed; architects now being assigned across portfolios. 11/20/2025: ZAXIS approved for boosting at EPC. Enterprise rank is 46, highest for US Prod pod. Next step: continue to update L2 fields, refine business case while awaiting PRT invitations across portfolios. 11/06/2025: Updated data higyiene items in preparation for boosting r | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Customer Pickup Platform - Problem Resolution |  | 154890 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Yen Ju Chiang, Emily Marcinkowski, Jorge Jaramillo | On Track | 12/11: Set to On-Hold due to IO working on other intiatives and aligning with like-intiatives in the Global Digital and CE organizations. 12/4: Went through Transform CX Jira logs with Digital Team to touchbase on the One Journey Truth concept that includes resolution of PU. Agreed to re-align on plans going forward in next few weeks. 11/26: Worked with CE team on re-evaluating relevancy between #154890 and #152953 - Digital Proactive & Preventative Engagement, identified major PU call intent - MPU was dropped, but problem resolution not limited to PU is being developed into Digital Support Manager under Transform CX, and thus should seek to align and collaborate. 11/20: Worked with CE team on LBC, confirmed MPU IVR launch on Nov 18th. Gather data from CEDL and implement to PU Dashboard for Call Intents to further address in Problem Resolution. Epic for FedEx Support Hub MPU Automation will be pushed to Jan 2026 due to bandwidth constraints. 11/13 - 11/7: Confirm data source adjustment from EIW to FWR for consistency with NPR and ATLAS presenece. 10/30: Validated data with CXPC team, aligned discrepancy < 5% 10/9/25, 10/2/25, 9/25/25, 9/18/25, 9/4/25, 8/28/25, 8/14/25, 8/7/25: Approved at triage on 8/5, working on lean business case | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Customer Pickup Platform - Scheduling & Management |  | 154895 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Ayushi N. Sheth, Yen Ju Chiang, Jorge Jaramillo, Paisley Williams | On Track | 4/23/26: Ongoing alignment with Digital on co-IO ownership and regional scope (Global v.s. US/CA) 4/17/26: Ongoing alignment with Digital, in discussions on regional scope (Global v.s. US/CA) 4/9/26: Communicated co-ownership with digital, will need further alignment on pickup and digital roadmap to segment digital-only epics (accelerate) v.s. others (request resources) 4/2/26: Ranked at #39 in the PRT (L2) backlog, with CPP components heavily digital, was recommended to split epics for digital only and other portfolios. Need architect review on some capabilities tied to what other solutions/portfolios are doing. Also in discussion on how to formally bring Digital as co-IO 3/26/26: Awaiting CPEL results, initial feedback was to split Epics for Digital only and an epic with other portfolios. Architects review required. 3/19/26: Had Triage with commercial architects to assess initiative size and dependency. Attending CPEL next week. 3/12/26: No change 3/5/26: EA response wouldn't expect formal kickoff until April at the earliest, once team completes 9200 and 7100. 2/27/26: Deep dive on CPP capabilities with global pickup team (Jamie), Digital (Matt, Like) 2/26/26: Intro to CPP with Kaleigh on supporting Commercial Porftolio and EA communication 1/29/26: Walked through CPP business case with COE to request resources on enabling analytical tools 1/22/26 - 1/15/26: Met with Strategic P&D groups to align on architecture design alignment and streamline the initiatives in support to that effort. Also had preliminary conversations with new GDX>Pickup Digital Product ownership (under Brady Marchionne) and Visibility (Andy Balan) to ensure momentum is kept through levelsetting the status and next steps, as well as defining who the co IO(s) will be for the digital intiatives. 12/11/25, 12/18/25: No change 12/4/25: Submitted to L2 on 12/3; pending DJ's approval ¦ Need to figure a path for co-IO ownership from GDX (Kim van der Velden > Marc Tollens) due to very high Digital impact 12/2/25: SL1 QA specialist review by Libby Malloris; ready to submit for L2. 11/20/25: Added on the agenda for 11/21 L1 Architecure Alignment review; EBA Leena Wagle initiaited L1 impact assessment 11/13/25: the init has been added to L1 architecture review this week for Commercial. Will hear on next steps / outcomes next week. 11/6/25: Waiting for Commercial EA assignment to review the init in SL1 10/23/25: LBC is WIP and validations with Finance are underway; need EBA assignment for t-shirt sizing and portfolio impacts to progress to L2 10/16/25: LBC is WIP - validating data gathered and doing an initial review with Warner 10/9/25, 10/2/25: Finalizing scope based on 9204 and 9200 work; LBC is WIP; working to get formal assignment of Digital team (critical) 9/25/25, 9/18/25: No new updates; on-track with LBC (still WIP) 9/11/24, 9/04/25: On-track with LBC (still WIP), assessing a new 'third-party billing' gap from VB1 discovery as potentially in-scope for a PFS solution, and documenting business processes for demand shaping 8/28/25: Gathering data for LBC and working on it 8/14/25: Approved at triage on 8/5, working on lean business case | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Enhanced Notifications & Driver Comm |  | 154898 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Ayushi N. Sheth, Jorge Jaramillo | On Track | On-hold: The initiative has been marked 'on-hold' due to shift in team's topline pickup product priorities. Alignment is needed with Digital / Visibility for right resource assignment. 11/6/25: No new updates due to resource constraint and more topline pickup priorities. 10/23/25, 10/16/25, 10/9/25, 10/2/25, 9/25/25, 9/18/25: No new updates 9/11/25, 9/04/25: need to initiate LBC, will be worked after 154895 LBC is finished 8/28/25, 8/14/25: Approved at triage on 8/5, working on lean business case | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FXG Comm Saturday Delivery |  | 156825 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Sarah Kam, Julie Lavelle-Acor | On Track | 2/5/26 following enterprise priority; no other changes 1/29/26 continuing L2 checklist, awaiting enterprise priority 1/15/25 continuing L2 checklist, awaiting enterprise priority, updated financials 12/04/25 continuing to L2 checklist; awaiting priority #20 on Commercial PRT; over #100 for Enterprise 11/13/25 continuing L2 checklist, spoke with Beau for architecture 11/6/25 continuing L2 checklist; going to review financials 10/29/25 meeting was cancelled 10/23/25 CPEL complete on 10/22/25; ranked 14th in backlog 10/16/25 commercial triage complete; completing L2 checklist, preparing for CPEL next week 10/09/25 working on SL2 check list 10/02/25 notification of SL2 is active 9/25/25 project was submitted to SL2 9/23/25 QA Expert Review for SL2 Submission 9/19/25 working with finance on financials; planning L2 submission tomorrow (pending QA expert review schedule) 9/4/25 continuing to work on the business case financials 8/28/25 added express data for the business case 8/12/25 approved in planview as a project | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Customer Pickup Preferences |  | 157451 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Kristy Otto, Jorge Jaramillo | On Track | 4/23/26 - Putting together transition plan for init; Pickup Preferences appears to have moved down in the PRT backlog to #12 as of today 4/16/26 - PM advised effort moved up again in backlog and should be able to get architectural resources prior to 9200 decomp completion 4/9/26 - attended Multi Stop workshop this week to ensure preferences considerations (+ 9200 discussions) 4/2/26 - moved to PRT backlog at a ranking of #9; initiative moved from on hold to caution to ensure resourcing until 9200 decomp is complete 3/26/26 - attended CPEL triage week of 3/16 and CPEL on 3/25; officially in the PRT backlog at a ranking of #10 3/11/26 - No significant changes / updates this week. 3/5/26 - Alignment meetings with EA and Commercial IT architects post Strategic Design - confirmed dependencies and hold status due to resourcing for 9200; continue working on scenarios that can be used in assessment 2/26/26 - Initial meeting with Port Mgmt completed on 2/24; PPM created - 1839838; submitting PDSM to get this # added to PV; sequencing discussion set up for Friday 2/27 with architects post Strategic Design 2/19/26 - Ongoing sessions with Ops to detail preference scenarios for consideration; PM assigned (Kaleigh Conrad) and first alignment set up for week of 2/23 and will discuss getting IT Owner for PPM (William Redmond said it's not him) 2/12/26 - Updated PPM IT owner request to William Redmond and sent awareness e-mail; aligned with Ops regarding customer flows and processes for consideration; additional discussions being established to review Customer Location 2/5/26 - Identifying IT Owner and resource for PPM request; expecting Strategic Design outcome in next week to understand path forward with sequencing 1/29/26 - Created PPM request and identifying if a FIRST is needed; Strategic Design sessions have wrapped up and architects are working on recommendations and documentation of overlaps, synergies, dependencies 1/22/26 - Strategic Design sessions continue and scope is being refined for Pickup Inits in Pickup PFS Phase 2 with Enterprise Architects; raised need for PM once 9200 is through assessment, preferably before and in line with PM for 9200 and CPP 1/15/26 - Strategic Design reviews (2) for preferences are completed; awaiting finalization of other reviews for Ideal P&D state overlap identification etc. Specific preference capability flows were mapped out with Enterprise Architects in prep for next phase + scope confirmed / refined 1/7/26 - Architectural working session on preference flows scheduled for 1/7; Strategic Design scoping session established for 1/9 with Amy B, Kelby, and Jordan M. 12/18/25 - Working through end to end details of all up Phase 2 views, inc of 9200, CPP, and Pref 12/11/25 - CCH review planned for 12/11; leadership reviews of commercial approach being socialized; process flows still in progress 12/4/25 - High level overview of Pickup PFS Phase 2 inits (inc this one) going to CDR on 12/5 and CCH on 12/11; process flow working sessions established with architects 11/26/25 - Plans to bring to CCH with other Pickup PFS Phase 2 inits (12/11); init on hold until 9200 resources are available; process flows will be compiled in the meantime 11/20/25 - Potential risk identified; persistent preferences may require either tech debt or waiting for RPO rationalization; exploration ongoing 11/13/25 - Alignment ongoing with Delivery PFS to understand enablers / dependences; expected to send an e-mail resourcing request for a pre-decomp assessment over next few weeks 11/4/25 - Officially moved into L2; architects are aligning on pre-decomp assessment needs as P&D leads define a combined P&D value roadmap 10/28/25 - Submitted for L2 Progression; sent follow up to Warner and MGR to advise Mark of submission for approval 10/24/25 – Completed QA Expert Review for SL2 Submission; waiting on PDSM ticket to change L0 value prop to Yes 10/23/25 - Architectural alignment required post 10/17 session; dis | E: L2 | Active | L2 & CCH
Business Only Initiative: Roadmap Market Expansion Plan |  | 112944 | Business Only Initiative | Commercial - US Product | Commercial | Michael Shansky, Miles Perry | On Track | 11/19/25 - Submitting request to cancel intiative #112429 Roadmap Market Expansion Plan from Planview / DRIVE, as it does not meet the criteria of Business Only demand, since it is not transformational work, there is no longer a Roadmap ESI to track to and it will be alternatively tracked in the base business reporting as well as RMC. 11/6/25 - No update Pending review of intiative placement. 10/30/25 - No update Pending review of intiative placement. 10/23/25 - No update Pending review of intiative placement. 10/16/25 - Had a QA check on this initiative and when walking though the Business case with Liz and Karen. With no change from how we are currently operating within this specific initiative. They are recommending to remove from DRIVE and track in the base business Surface reporting instead. 10-9-2025 - Initiative has been moved from P&D Domain to the Commercial domain. Preparing to Submit to SL2. TikTok ramping up to 27K GE ADV as of last week 9-15-2025 - TikTok ramping up to 9K GE ADV as of last week. Following up with sales on the rampup timing. For a full ramp up, id expect it to be later than the original expectation of end of Sept, but theres not too much information from Sales on exact timing yet - just that they are continuing to push the customer. -9/2/2025 - TikTok shipped 6.1K Economy ADV. TikTok continues onboarding both their Fulfillment by Merchant (FBM) channels more recently Fulfillment by Merchant channel, which will be the bulk of their volume. -8/25/2025 - TikTok has officially begun onboarding their Fulfillment by TikTok channel volume. For the week ending 8/23, TikTok shipped 5.2K Economy ADV. Sales is aiming for an 8/28 start date for the Fulfillment by Merchant channel, which will be the bulk of their volume. -8/18/2025 -We are estimating start ship date of 8/18 and are expecting to full ramp up to the 100k by the end of September - 8/4/2025 - Sales sign/onboard TikTok 100K ADV. 5/29/2025 RMC - Sales alignment to pursue an incremental 84K ADV beyond the FY26 revenue plan at a target yield of $5.72 or higher for target Roadmap accounts. There are accounts in the pipeline with the potential to achieve the incremental volume goal. | C: L1 | Cancelled | L1 | 2025-06-02 | 2025-09-29
Business w/ Tech Initiative: Overnight Air Sunday Delivery |  | 167124 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Jarrett Seibel, Alfredo Moran | On Track | 2/4/26 - Changes being made to LBC based on feedback received from different stakeholders. Targeting completion by mid March. 1/28/26 - On Track. LBC ~70% complete. Need to flushout Target Value and NRB aganist B2C Benchmarks. Generate supporting documents, PPM Project #, and begin L1 Architecture development. Currently ranked 31/366 L1 projects. 1/20/26 - On Track. Editing LBC and reviewing metrics/data for current offerings (FO/PO/SO/E2/ZAXIS). 1/15/26 - Just assigned as IO, beginning work on L1 checklist. 10/23/25 - On Track. Gained requisite approval to advance to L1-Lean Business Case stage. Will work with key stakeholders to properly complete LBC. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AI-Assisted Support for Sales Reg: Pickup |  | 189974 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Paisley Williams, Jorge Jaramillo | Some Issues | 4/23/26- No updates. Still waiting on ESI alignment. 4/15/26- In Stop Work. Looking for ESI alignment to N2.0 to remove block 4/7/26- Architectural alignment received. Submitted for SL2. 4/1/26 - Waiting on Architecture Sizing from L1 team. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Rationalized Recurring Pickup Order (RPO): NAP |  | 191984 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Kristy Otto | On Track | 4/23/26: No updates this week. 4/14/26: Init submitted in Drive last week and moved to L1 On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Specialized Pickup Window Commercialization |  | 192840 | Business w/ Tech Initiative | Commercial - US Product | Commercial | Yen Ju Chiang | On Track | 4/23/2026 - Approved in Triage, working on LBC. Connected with FHD Extra Hours to synergize Later Pickup resources, FXG overnight sorting might be fully-utilized, looking into opportunities in FXE ramps. Aiming high volume REG customers direct back to ramp to make same day commit. | C: L1 | Active | L1
Business w/ Tech Initiative: Retire iCIMS and build out Paradox as the Enterpri | 42958 | 6927 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Claudia Versey, Cindy Wallace | On Track | 3/31/25 Rebaselined to FY25 with Sara Barnes. 3/26/25 Cindy Wallace updated benefits for FY25 rebaseline - guidance from Finance (SB). 1/23/2025 - Reduced benefits starting January, as we had to contract with iCIMS to retain historical data. A yearly cost of about $230K to host and maintain the support of recruiting historical data. Development started in December as scheduled. Everything is on track to complete the iCIMS migration by 5/31/24. | K: L5 | Completed | L5 | 2023-08-07 | 2024-05-31
Business Only Initiative: APAC IT Business App & End User Services | 18071 | 8962 | Business Only Initiative | IT - Application Optimization | Data and Tech | Marie Mangin, Alex Vasilevski | On Track | 5/15: Actuals updated, no changes. Rebaselined to FY25 as of 04/01/25 | K: L5 | Completed | L5 | 2022-01-03 | 2025-01-01
Business Only Initiative: Reduce duplicate application across regions that p | 14913 | 9184 | Business Only Initiative | IT - Application Optimization | Data and Tech | Ken Johnson, Taner Akbulut | On Track | Re-Baseline to FY25 (05/02/2025) Closed all milestones (including Money Step), updated all Actuals) Need to progress to LS4 | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-01 | 2024-11-29
Business w/ Tech Initiative: LAC Application Rationalization | 19956 | 9445 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Mary Ann Campanile, Tammy Castine | On Track | 25MAR25 - has been rebaselined to FY25. 09AUG24 Reset initiative to continue at FY24 value and close the initiative; these reset actions were joint decisions with the DTDO team and pod leads based on new strategic priorities. NRB value at May 2027 changed from $0.529M to $0.335M, forecasting out July 2024 actual benefits achieved at time of reset request. 22FEB24 3531306 LAC-APOYO-Neptune retired. 07FEB24 FY24 Planned Savings: $153.K. On track for minimum FY24 cost savings on track for $143K, pending application decommission of 4 applications ($6K annual). 29JAN24 INFOR WMS licenses: Contract Negotiation (22695) - cancelled. Unable to reduce contract. Week Ending 24JAN24 On track. Week Ending 19JAN24 On track. KPIs and Actuals updated. 08JAN24 7552 LAC-MX-3-eAcctApp team updated estimated decommission date to May-24 897 LAC-LDP-GIPSYSApp team updated estimated decommission date to 24-Mar 3534590 LAC-MX-3-ePayCApp team updated estimated decommission date to 24-May 3531306 LAC-APOYO-Neptune App team updated estimated decommission date to 24-May 22685 Cost savings to begin 24-Feb instead of 24-Jan 22690 Implementation expense of $40K not required 22695 Infor WMS license cost savings is cancelled. Team advised - Due to commercial conditions INFOR couldn't reduce the contract. 19DEC23 Team advised INFOR WMS licenses: Contract Negotiation (22695) is at risk. They will provide additional details ASAP. 07SEP23 On track, no issues or concerns to raise. 01SEP23 On track, no issues or concerns to raise. 23AUG23 Sub-initiative 22685 #25599 milestone complete. Based on Analysis and discussions, it was decided to retire ThoughtSpot by converting/migrating Thoughtspot reports to PowerBI. #25671 milestone Title updated to "LAC ThoughtSpot feed to PowerBi Solution - LAC ThoughtSpot on-prem Decommission (22685) - versus SaaS solution Purpose updated FROM: Enable feed from LAC IBIS to Dataworks or Corporate GCP/Azure datalake Migrate Thoughtspot from on-prem to ThoughtSpot SaaS LAC ThoughtSpot on-prem decommissioning process (Money Step 6/17/24) TO: Finalize Migration strategy from TS to Power BI Data Mart migration from TS Falcon DB to IBIS DB Reports Migration from TS to POWER BI LAC ThoughtSpot on-prem decommissioning process (Money Step 6/17/24) 16AUG23 Sub-initiative (#25599) started as "LAC ThoughtSpot to SaaS or to Corp Solutions like PowerBI”. Later, with the need of LAC Customer Experience team to use ThoughtSpot, we changed to SaaS option and hence the Tech review was marked and the presentation was prepared based on it. Last week, an update was received from Corp Management to possibly retire BI Tools like ThoughtSpot. Accordingly, after discussing with Customer Experience, the plan is now not to convert ThoughtSpot to SaaS option and instead to have reporting's to be migrated to PowerBI and to retire ThoughtSpot. Hence, this might fall off Tech arch review process as we are going to use existing solution (PowerBI) for replacement."LAC ThoughtSpot to SaaS or to Corp Solutions like PowerBI”. TCH indicator removed, will add in future if need develops. 04AUG23 Mary Ann and Tammy performed all required functionality in Wave to remove POS (23041, 23043, 25655). Met with Didun, McKinsey, and Sita to review financials, no additional action required for Initiative #19956 for 23041, 23043, 25655). 5 other sub-initiatives remain in #19956 02AUG23 Milestone 25599 started. TCH: Added Portfolio Dependencies & uploaded arch review PDF. TCH Arch review meeting to be scheduled the week of 21AUG23. Sub-initiatives 23041, 23043, & 25655 - pending guidance on removing impacts in Wave. Concept only and will not move forward at this time, will be added as L0 as applicable in the future. MD owner will advise. (Milestones approved for decoupling 18JUL23 and successfully cancelled 19JUL23). 27JUL23 Sub-initiative "Align on a single POS platform (23041, 23043, & 25655)" milestones removed. Didu | K: L5 | Active | L5 Feedback Requested | 2023-01-03 | 2024-07-31
Business w/ Tech Initiative: AppOpt-ES-FY25Retired |  | 84297 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Loveena Goel, Sita Achanta | On Track | Applications are already retired 3/21/2025 - Initiative has been rebaselined to FY25 | K: L5 | Completed | L5 Feedback Requested | 2024-10-01 | 2025-04-25
Business w/ Tech Initiative: SCO Apt Opt – Weis – Completed FY25 |  | 86937 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Tom Brien | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FXNAI Retirement |  | 87719 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Kudzai Tunduwani | On Track | Request Type updated | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opp– Weis–Completed FY25:Shipment (5 EAIs) |  | 87722 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Tom Brien | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opp -Kwasigroh- 3535900 Driver Enablement |  | 88609 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Ramyasine Boominathan, Brandy Mears, Avril M. Riley, Karen A. Lucarelli | On Track | Application decomission and 3rd Party contract cancellation was dependent on Canada N2.0 completion 12/18: Since this init was part of FY25 (where no savings was recorded), it is now out of scope and will be cancelled moving forward | E: L2 | Cancelled | L2
Business w/ Tech Initiative: SCO App Opt 2 - Wilhelm - Completed FY25 |  | 89123 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Shawn Weis | On Track | . | C: L1 | Cancelled | L1
Business w/ Tech Initiative: SCO Apt Opt – SANDEEP – AU Domestic Mobile Worker |  | 89567 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Alex Vasilevski | On Track | 02/26 - PDSM Change CHG088391 for Decommissioning with DXC. No further work required | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: SCO Apt Opt – SANDEEP – AU Domestic exit HELIX WMS |  | 89570 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Alex Vasilevski | On Track | 05/14 - Servers decomissioned. No further work required. 02/26 - PDSM Change CHG088391 for Decommissioning with DXC. 11/11 - Decommision requests raised - aumahlx201 RITM6559194, aumahlx201 RITM6559196, aumasql218 RITM6559197, aumasql219 RITM6559198 11/04 - Request for Decommision submitted 1st Nov 2024 - aumahlx201, aumahlx201, aumasql218, aumasql219 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: SCO Apt Opt – SANDEEP – AU Domestic replace AU-FMS |  | 89591 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Alex Vasilevski | On Track | 08/28 PDSM Change CHG0934580 for Decommissioning with DXC. No further work required 05/14 Reviewed plan and savings will be moved to FY26 02/26 Plan confirmed | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: SCO Apt Opt – SANDEEP – AU Domestic replace AU-ISS |  | 89595 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Alex Vasilevski | On Track | 04/15 - Server decomissioned. Contract ceased. No further work remaining. 02/26 - PDSM Change CHG0892062 for Decommissioning with DXC. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: SCO Apt Opt – SANDEEP – AU Domestic replace CUCM |  | 89602 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Alex Vasilevski | On Track | 05/14 Reviewed financials, and this will now be rebaselined to FY25 cost of USD$18,615. Additoinal cost avoidance of USD$57k. (Baseline AUD$28,296, cost avoidance AUD$86k) 02/26 Submit LBC | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: SCO App Opt –Weis–Committed FY25- CIE Collector |  | 89615 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Rob Crane | On Track | . | C: L1 | Cancelled | L1
Business w/ Tech Initiative: SCO Apt Opt –Weis–Committed FY25- Consldte HUR WRR |  | 89628 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Rob Crane | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt – Weis – Committed FY25: Retire eNotes |  | 89631 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Rob Crane | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt –Weis– Committed FY25: Retire OPF Prep |  | 89634 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Tom Brien | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt – Weis – Committed FY25: Retire DLM |  | 89637 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Tom Brien | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TradeNet Retirement |  | 89640 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Mahesh Dey | On Track | Currently dependent on the Request: 107715 - METL FedEx Net Modernization. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: SCO App Opt – Weis – SSCSO |  | 91928 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Rob Crane | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Cargo Purchased Transportation (PT) Consolidation |  | 91948 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Shonn Isitt | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Dynamic Profile Service Retirement |  | 92250 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Rajiv Subramaniam | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: CustomerAcct.Mgmt.CAM/UnifiedSvc.LayerUSL Ret. |  | 92253 | Business w/ Tech Initiative | IT - Application Optimization | Data and Tech | Rajiv Subramaniam | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC | 2025-07-30 | 2026-01-30
Business Only Initiative: FedEx History Manager Retirement |  | 92257 | Business Only Initiative | IT - Application Optimization | Data and Tech | Thomas P. Thornton | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Walk-me Product FXL Salesforce Retirement |  | 94088 | Business Only Initiative | IT - Application Optimization | Data and Tech | Ohm Prakash Ramasami, Todd Hethmon | On Track | Product was retired at end of FY25 which coincided with the end of the contract. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-06-02 | 2025-06-02
Business Only Initiative: EIW/EDW App ID required for DSAR automation |  | 106273 | Business Only Initiative | IT - Application Optimization | Data and Tech | David Omar Osman | On Track | If we obtain the AppID in the coming days we will be on track to complete the automation in time for the changes in the legislations to take effect and lower the amount of manual work. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Fedex Freight (FXF) Arch,Eng&Gov of Info Sys AEGIS |  | 91377 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Taylor Robinson | On Track | 20250905: Initiative 91377 AEGIS (specifically the WTC-retirement component) has been majorly impacted by Project Fairway / FXF Spinoff and the initiative needs to be cancelled, as FXF will be remaining in WTC for the foreseeable future. 20250701: Added cost forecasts from Enterprise Services Portfolio. 20250322: Link to document following Architectural Alignment meeting on 3/20 is now attached. All Portfolios are now marked as impacted by this initiative. T-Shirt Size updated to XL. 20250305: Link to FXF Estate Architectural Documents is added. Also, added Platforms as an impacted portfolio. 20250224: SCO Portfolio added as an impacted area / expanded Ability To Statements. Please see two attached PowerPoint decks outlining the AEGIS project objectives and current status of FXF application and PureScale Db2 stability improvment work. 20250219: Financial review with John Jamison completed. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: OpEx E2E Assessment & Observability |  | 91537 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Komal Panduji, VB Joshi | On Track | 9/3/2025: Komal Panduji: Rationale: There are other business initiatives catering to the Observability pins. Hence closing this duplicate. Additional IO Rebaselined to FY25 as of 4/17/2025. | E: L2 | Cancelled | L2 | 2025-02-03 | 2025-05-30
Business w/ Tech Initiative: AIOps Intelligent Apps for Operational Excellence |  | 91543 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Joshua Anderson, Mark C. Janociak | On Track | I am trying to go to L2. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-08 | 2026-05-25
Business w/ Tech Initiative: InfoSec - Secure by Design - Phase 1 |  | 91820 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Angela Heffner | On Track | 3.27.25 - Rebaselined to FY25 Project has started and all efforts are on target 7.31.25 - Request was entered to cancel this effort, however it was entered incorrectly 8.01.25 - This effort was reinstated and cancellationw as corrected. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2029-09-13
Business w/ Tech Initiative: IT Excellence in Service Mgmt |  | 92637 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Rajshri Vispute, Deborah A. Saverson, Cathey Cooper, Chris Floyd, Donna Dangerfield, John Hoult | On Track | Work to build business case 03/20/2025. Renamed initiative to Service Management Transition to accurately reflect the global nature of the project. 07/09/2025 - Added Paul R. Luker and Lanny Jeffries as sub I/O. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Svc desk trans to GENAI plat to replace IBM Watson |  | 96409 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Jayashree Shankar | On Track | MVP Moved to production | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: VDAP x GenAI: Metadata Augmentation |  | 96569 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Patrick Brown, Amanda Nevins, Vincent J. Romeo | On Track | No issues at this point, we want to reach the point where we can receive feedback from info security and SAD teams prior to delivery | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Accenture GenWizard |  | 104268 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | David Zampini | On Track | Erroneous entry | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Global entry pt for FDX to acc GENAI Bot ESD Asst |  | 105695 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Jayashree Shankar | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Adoption of PactFlow as Contract Testing standard |  | 107791 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Laurent Michaud | Some Issues | June 30th 2025: * I requested the cancellation of this initiative in PDSM, under INC031290317. After meeting with Stephen Byers and in agreement with my MD Murad Akmanligil, we agreed that SDLC team will not support this initiative and their support is absolutely essential to create the system environment for PactFlow. June 20th 2025: * Stephen Byers and his team are not willing to support this demand to roll out PactFlow across all Portfolios / regions. So my MD Murad Akmanligil and I decided to scale down and refocus the project on his group only (CIAM / JOIN ARTs under Commercial portfolio). This DRIVE init will be updated in consequence. It needs to go back to L1, because the NRB will be much lower with only 2 ARTs adopting Pactflow. April 18th 2025: * Updated all fields required for SL2 and uploaded all documentation on Sharepoint. April 28th 2025: * L1 architectural documentation added by Ryan Glover and initiative submitted to next step April 29th 2025: * Updated impacted Portfolios and Money Step, as requested May 2nd 2025: * Worked with Jamie Heller to update financial details. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: InfoSec - Cyberdata Strategy |  | 104315 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Dinesh Prabhu Sakkarai, Nimisha Gohil, Thuy Trang L. Doan, Ahmed Jamiel Ahmed | Some Issues | **3/31/26**-Delay with implementation timelines for few EAIs. Revised timelines shared to impacted portfolios **2/25/26 **- Update Primary IO to Nimicha Gohil due to management change **2/13/2026 **- SCO held Q&A with portfolio. pending greenlight **2/5/2026** - Updated SCO resource cost **1/7/2026** - Engaed Commercials - Digital (GDX) Arts **12/08/2025** - Engaged Commericals All COM Arts **11/25/2025** - handed draft capability to ES portfolio **11/24/2025 **- finalized SCO capability scope with Ben Silva to update agility **11/20/2025** - Encounter issues with agent deployment. Need to engage architect support **11/11/2025** - Green light review with SCO portfolio. pending costing from SCO - ETA 2 weeks **11/7/2025** - identified Services Platforms as impacted - Obtained approval from Daniel to add to scope to add to green light meeting **10/30/2025** - identified Commerical and SCO as impacted porfolio. Obtained approval from Daniel Knofmacher to remain in L3 **10/14/2025** - Platform granted manual access to demand for Data&AI **10/8/2025** - cross porfolio demand access issue with Agility - unable to add work for Data & AI in Agility **9/18/2025** - Delay up ADO set up. Adjusted forcasted spending from Aug to October **9/17/2025 **- updated Splunk cost per Apoorv's feed back into Planview **9/16/2025** - additional compliance data Splunk cost identitifed. Worked with Finance Apoorv **9/9/2025** - Due to needed discovery, the ATLAS configuration milestone need to be adjusted from 8/29 to 10/13/25. **9/2/2025 - Team encountered slight delay to build datalake; Workshops are session being held to gather additional details. **8/7/2025** - passed quality check. PDSM is not required for enabler **8/6/2025** - Data & AI Greenlit **05/02** - At risk of meeting stand-up date. **03/14 **- Completing the L1 LBC in preparation for L2. | G: L3 | Active | L3 Feedback Requested | 2025-08-01 | 2029-06-01
Business Only Initiative: SolidCore Replacement |  | 108485 | Business Only Initiative | IT - Excellence | Data and Tech | Angela Freeman-Jones, Kevin Gautreaux | On Track | CCH Triage with CCH Lead - Confirmed no commercial value prop impact. CCH review not required. 6/17/25 QA Expert Review conducted and shared with Kevin Gautreaux on 5/14 by Steve Kastner 11/25: Financial review is complete. 13K is approved. 11/25: Money Step is updated 11/25: Unable to remove PPM. Requested assistance from the PEO team: Sai | G: L3 | Active | TEMP L3 - Enter L3 | 2026-09-29 | 2026-09-29
Business w/ Tech Initiative: Integrated Solutions Environment (KPI Dashboard) |  | 110207 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Patrick Brown, Amanda Nevins, Vincent J. Romeo | On Track | no issues at the moment, we want to have a technical review with SAD + infosec teams prior to development | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: LCM - PurpleID Passwordless - Sign in Changes |  | 111261 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Daniel R. Laughlin | On Track | This work was completed and moved to production. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: (GEN AI) GenAI Hub |  | 113891 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Abiola Abraham, Pankil Shah, Nicholas Havens, Gayathri Daniel | On Track | Sidekick V2 Contract for delivery in June 2025 | E: L2 | Active | L2 Feedback Requested | 2025-03-03 | 2025-10-31
Business w/ Tech Initiative: (GEN AI) GenAI Core |  | 113894 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Abiola Abraham, Gayathri Daniel, Nicholas Havens, Pankil Shah, Robert Heatley | On Track | Core API's are currently in use across several business teamsn adn TAG API"s are scheduled to be launched mid June | E: L2 | Active | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: Vendor Risk- Vendor Monitoring (SecurityScorecard) |  | 126043 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Paula Pearson, Taylor Seaman | On Track | On track to execute Security Scorecard within the fiscal year and implemenation of the vendor complaince program with seucurity scorecard. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: InfoSec-Global Segmentation Program |  | 126105 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Kimberly Godden, Nicholas Shansky | On Track | Per caller Kimberly Godden PDSM ticket#INC033706019 | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: InfoSec - Prevention of Security Misconfig |  | 126729 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Xuan Liu | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: InfoSec - Risk Assessment for Public Cloud-PI 3-5 |  | 126732 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Xuan Liu | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR CFT - IT / Data and Technology Increase SUM |  | 126738 | Business Only Initiative | IT - Excellence | Data and Tech | Laurie Turner | On Track | This initiative was created in support of Enterprise Margin Recovery and was considered a placeholder. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: DRIVE Surge - Palantir |  | 128515 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Ashley Laird | On Track | Cancelled as Palantir efforts were support through other DRIVE initiatives. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: InfoSec - EventHub Policy & Operationalization |  | 132865 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | URSULA MARKS | On Track | 06/30 - We are actively working to get this moving towards completion. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: LAC Internal Controls / RCM - Chat Bot AI usage |  | 141437 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Ingrid Mitzka, William Carvalho | On Track | On track - 07/29/25 | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: InfoSec new WAF capability/solution |  | 143732 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Kevin Beitler, Robyn Ballard | On Track | 1/5/2026: Cancelling as directed by ESPM/Pod PM. Teams are continuing to move forward with planning for POC and meeting with the two vendors Q/A review held 8/5/2025 with Steve Kastner | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: Atlas Pipeline Metadata Consolidation |  | 153526 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Shalivahana Mitta | On Track | We have all the metadata consolidated in an excel file currently which we are trying to automate using this planview request | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Retail Security & Fraud Prevention Data Ingestion |  | 153529 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Scott Douglas | On Track | 08/25 - New Request | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: InfoSec-Wiz Container Security Evaluation(DevTest) |  | 154569 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Donn Janes, Karel Koster | On Track | Waiting on resource availability dependant on demand approval | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Network and Information Security Directive (NIS2) |  | 154597 | Business Only Initiative | IT - Excellence | Data and Tech | Margaret A. Hughes | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Cybersecurity Maturity Model Certification for DoD |  | 154602 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Margaret A. Hughes | On Track | Per Margaret Hughes PDSM Ticket#INC032403674 requested for cancellation. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: DDI - Global Standardization of DNS/DHCP/IPAM |  | 161848 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Christopher Miller | On Track | 10/7 develop standards for all of FedEx for DDI | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: QDM/AI |  | 163671 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Rebecca Getsfrid, Justin Williams, James Dye | On Track | 10/09: Delay in demo readiness | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Supply Chain Transition to New WMS |  | 166048 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Steven Elks | Some Issues | Current WMS is already End of Life with extended support finishing in Sep 27 and migratoin must be complete in advance. Some stability issues and potential infosec/patching concerns means this needs to be addressed asap | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: InfoSec - Risk to Remediate Initiative |  | 166051 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Karel Koster, Chance Privette, Tanya Mosley | On Track | <Enter> | G: L3 | Active | L3 | 2026-01-01 | 2026-12-31
Business w/ Tech Initiative: TS-VL2-Con-ServiceNow-DB perf.+scalability–license |  | 169785 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Michael J. Heys, Allan Goddard, Richard Lomas | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: APAC Digital Innovation Lab |  | 170016 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Hendy Leong, Alon David Honig | On Track | Alignment from Leadership team (Abdullah) with D&T team that this initiative had been initiatied and taken over by another team. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AutomatePro |  | 171172 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Simon Baxter, Shashi Banangada | On Track | On Track | F: SL3 | Active | SL3 Domain Lead Approval | 2026-05-04 | 2026-07-03
Business w/ Tech Initiative: Infosec Akamai EdgeIP Binding |  | 176993 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Kevin Beitler | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Wiz CMDB Integration |  | 184538 | Business w/ Tech Initiative | IT - Excellence | Data and Tech | Donn Janes, Jordan Barber | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: IT Excellence In Service Management |  | 186992 | Business Only Initiative | IT - Excellence | Data and Tech | Rajshri Vispute | On Track | On Track | G: L3 | Active | L3 | 2026-02-26 | 2026-06-30
Business Only Initiative: HCL Database Support Cuts | 29736 | 6758 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Ben Tarver, Philip Rencher | On Track | 3/31/2025 - re-baseline to FY25 4/29/2025 -- on track. database decoms to be processed through the month of May 2025 5/14/2025 - -- on track. database decoms to be processed through the month of May 2025 6/12/2025 - -- on track. database decoms to be processed through the month of June 2025 -- extended from previous date due to Condor migrations slipping. 8/21/2025 -- decoms complete. moving to L4/Money step 9/25/2025 -- submitting for SL5 | K: L5 | Active | L5 Feedback Requested | 2023-01-02 | 2025-09-29
Business w/ Tech Initiative: Cell Phone Usage Reduction | 29733 | 6948 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Amy Pickens, Laurie Turner, Kirt Satam | On Track | Due to legal and HR concerns, we will put this initiative on hold and concentrate on price reduction thru init 16881, milestones #25795 and #25794. Now requesting cancellation. | G: L3 | Cancellation Request | L3 Data Migration - TEMP
Business Only Initiative: Resident profee reductions | 38529 | 7091 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Shawn Keys | On Track | Pat is responsible for moving thru phase gates & updates | K: L5 | Completed | L5 | 2023-09-01 | 2023-11-10
Business Only Initiative: Reduce HPE On-Site Support Costs | 33604 | 7840 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Shawn Keys, Franklin Beattie | On Track | Added Pat Frizzell. | K: L5 | Completed | L5 | 2024-05-31 | 2024-05-31
Business w/ Tech Initiative: J2C Initiative: PCF to FedEx Cloud Platform (AKS) | 16143 | 7910 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Wes Smith, Stephen Byers | On Track | No longer a viable initiative as there is no centralized migration of applications from PCF to Azure. Please cancel. | C: L1 | Cancelled | L1 | 2024-07-22 | 2026-01-08
Business Only Initiative: Optimize NOC Resource Unit (RU) charges | 35950 | 8009 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Susan Ward, Kirt Satam | On Track | 3/21/25 - FY25 Rebaseline complete Dec 2024 Actuals entered, steady state and in L5 3 months of steady state achieved. | K: L5 | Completed | L5 | 2023-09-26 | 2023-12-15
Business Only Initiative: New- Consolidate the hundreds of individual DIRECT | 96849 | 8246 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Karl Kehr, John Schuman, Phil Scotti | On Track | The Enterprise Agreement with DirectTV was signed 3/24/25 providing the 20% pricing reduction. Monthly savings were $28K/mo in May and June (slightly above the $23K/mo forecast). | K: L5 | Active | L5 Feedback Requested | 2024-12-05 | 2025-03-14
Business Only Initiative: New APAC IT - Hosting & Compute/Network & Telecom | 96974 | 8251 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Chee-Pin Yong, Marie Mangin, Alex Vasilevski | On Track | 5/16/2025: Update actuals. No major changes, we had a contract for network optimization that was supposed to apply in March, it took a couple of month for the team to work on it, they finalized in it this month, so it will apply in Jun. There is a last main contract the team is signing soon to apply for the new FY for MPLS and this is what we define as our money steps, the rest will be BAU renewals in FY26 the team will try to leverage on to get some cost savings (a few 100s per contracts per month), but we will just add them to our benefits as they go in L4. Rebaselined to FY25 as of 04/01/25 | K: L5 | Active | TEMP L5 - Enter L5 | 2025-05-01 | 2025-06-13
Business Only Initiative: APAC IT Hosting & Compute/Network & Telecom | 18075 | 8410 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Kook Hing, Marie Mangin, Alex Vasilevski, Chee-Wai Gary Foong | On Track | 3/10/2025: Some of last month forecast was not proporly reviewed. Further discussion with team and management decided that we will keep the FY26 forecast for the dual link sub-initiative to it's original forecast. So the additional saving for FY26 of 200k were removed this month. This confirm our FY26 forcast. 3/05/2025: The infrastructure team has low capacity with the restructuration, they need to push the timelines for those milestones to the end of the FY. No impact on savings for now. 2/12/2025: update of Jan actual and forecast for BP26. On of the sub-initiative was at risk because when the team check with the vendors on cost to reduce by 50% the bandwith of the dual link, the vendor increase their rate cards and the savings plan didn't work. So the team changed tacticts reviewing every of ther contracts to futher negociate and manage to get more saving than originally planned with the dual link. There effort and savings are now illustrated in the model for actuals and forecast. Re-baselined to FY25 as of 04/01/25 Scope change to Pat Hopper's Org. Sandeep’s benefit now in initiative #8251 | K: L5 | Completed | L5 | 2022-01-03 | 2025-04-18
Business Only Initiative: Renegotiate / move FedEx Express Europe and legacy | 14935 | 9188 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Paul Beardmore, Cathey Cooper | On Track | 4/3/25 Met with Initiative lead and finance determine ready for L5 3/31125 Rebaseline completed 30/April/2024 On #14935 we have made the following adjustments from April’24 through to the end of the initiative. On sub initiative #15801. Forecast from April’24 has been adjusted from 1.113 to 0.5565 through the end of the initiative with the total now of $6.678 savings against FY’23 base. This is based on the minimum forecast of savings from the DXC contract and not tied to additional incentivised committed spend. On sub-Initiative #15802 Due to the cancellation of our CITRIX initiative, we have removed further savings as the activity is now switched to a migration from CITRIX to W365 / Zscaler and other products. At this stage we cannot forecast savings until Personas/Products have been defined with appropriate roll-out. On sub-Initiative #22126 Savings of 0.118 per month ($1.416) will continue through FY’25 against a locked baseline of FY’23. To summarise the FY’25 savings against #14935 will be $674,500 per month , a grand total of $8.094 for FY’25 against a locked baseline of FY’23. This is the minimum position based with no link to any committed spend incentives from DXC. Any Capital or Programme send with DXC will result in additional discount which will be added in March ’25 into the Actuals, at the end of Year 2 of the DXC agreement. We will keep this initiative for FY’25 and remain in L4 until the end of that period. __ We have reached a steady state with the cost savings achieved from the renegotiation and signing of the DXC contract, and as such we believe we have reached the required stages to now move to L5. * All Milestones have either been cancelled [either where they are no longer appropriate, or where their savings will be captured in a new initiative where needed]. * All KPIs have been completed. * All evidence required to prove to steady state value has been attached __ Requesting Finance Review to push to L3 and then L4 as contract signature has completed money step. | K: L5 | Completed | L5 | 2023-03-01 | 2023-03-31
Business w/ Tech Initiative: Implement SD-WAN based on Cisco Viptella | 15808 | 9249 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Jan Mertens, Sanna Karlsson | On Track | 16/02/2026: This initiative should have been cancelled since a long time ago already ! So please action as required. Annual cost added for spend (opex, capex) and saving expectation. Spend split between Express and Service. Sent for approval for Senior management in FIT Europe. Cost and BC attached now including regions Europe, MEISA and APAC Moved back to L2 on 11April2023 because of uncertainty of Cisco SFA signature and conditions | C: L1 | Cancelled | TEMP L1 - Create L1 LBC | 2024-07-22 | 2024-11-20
Business Only Initiative: Reduction of overall Infrastructure vendor needs a | 16864 | 9312 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Mac Raboudi, Kirt Satam | On Track | No longer valid , with cancellation of HCL,Atos/Syntel Mphasis Professional Service contracts. Moved to Manage Services Agreement with Accenture. added a new IO for this initiative | K: L5 | Completed | L5 | 2022-06-01 | 2023-11-30
Business Only Initiative: LAC Data Center/Infrastructure | 20820 | 9456 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Mary Ann Campanile, Tammy Castine | On Track | Submitted for L4/L5. This FY22 baseline initiative contained several other sub-initiatives "bucketed" into the over-arching #20820 initiative, as directed by Yaman at McKinsey. Removed sub-initiatives that were on hold (if/when they move forward, will be new, separate initiative with FY23 baseline). Received approval to move forward, fast tracked L3-L5 as remaining sub-initiatives had already been implemented and realized the cost savings. Actual L5 money bank date is July 2023. | K: L5 | Completed | L5 | 2023-01-02 | 2023-04-28
Business Only Initiative: LAC End user support/Help Desk | 20825 | 9458 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Mary Ann Campanile, Tammy Castine | On Track | Submitted for L4/L5. This FY22 baseline initiative contained several other sub-initiatives "bucketed" into the over-arching #20825 initiative, as directed by Yaman at McKinsey. Removed sub-initiatives that were on hold (if/when they move forward, will be new, separate initiative with FY23 baseline). Received approval to move forward, fast tracked L3-L5 as remaining sub-initiatives had already been implemented and realized the cost savings. Actual L5 money bank date is July 2023. 01SEP23 Discussed with leadership. Changes expected as baseline has shifted to FY23 versus FY22. | K: L5 | Completed | L5 | 2022-08-18 | 2023-03-31
Business Only Initiative: LAC Telecom | 20833 | 9460 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Mary Ann Campanile, Tammy Castine | On Track | 16MAY25 Updated milestones and financial actuals. 7April25 - rebaselined to FY25 16Sep24 Related to Impact # 23778, on 9/16/24 I re-entered the monthly Forecast of .005633 for the out months because on 9/12/24 I mistakenly deleted this from the monthly Forecast. 12SEP24 Milestone 25657 updated to 05OCT24, additional time required by LAC Network ENG team, as confirmed by Dawn Evans, manager. 29FEB24 Dawn Evans, Network ENG, confirmed cancellation: 25649: Complete Equinix expansion (23795). 07FEB24/14FEB24 25649: Complete Equinix expansion (23795) probable cancellation. Implementation might have more expense than expected cost savings. Network Eng manager to confirm. 29JAN24 25649: Complete Equinix expansion (23795) at risk. Implementation might have more expense than expected cost savings. Network Eng manager to confirm. 24JAN24 Work underway on 23795 to validate implementation cost and benefits. #23790 RFP approved to move forward. Timeline changed. Cancelling milestones 25660 & 25661 and adding 9 milestones with updated timeline. Week Ending 19JAN24 On track. KPIs and Actuals updated. 10JAN24 On track, no issues. 28SEP23 Milestone 49048 added: Initial Review and Analysis of Data links. RFP submission milestone dates updated with revised dates, project under review. Future milestones to be added next month in support of over-arching "strategy to be defined" cost savings initiatives. 13SEP23 RFP Submissions (23790) Milestone #25660 - Start date delayed, Eng Manager reviewing. Review meeting scheduled 14SEP23. 07SEP23 RFP Submissions (23790) Milestone #25660 - Start date delayed, Eng Manager reviewing and will advise 13SEP23. 01SEP23 RFP Submissions (23790) Milestone #25660 - Start date delayed, Eng Manager reviewing and will advise. | K: L5 | Active | L5 Feedback Requested | 2023-03-20 | 2026-05-26
Business Only Initiative: Load Balancer Global Strategy and Consolidation | 36232 | 9557 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Susan Ward, Bob Palmieri | On Track | 4/10/26 - updated Mar 2026 actuals (month 4 of 9 for L5 actuals entry) steady state reporting 3/10/26 - updated Feb 2026 actuals (month 3 of 9 for L5 actuals entry) steady state reporting 2/10/26 - updated Jan 2026 actuals (month 2 of 9 for L5 actuals entry) steady state reporting. 1/12/26 - Updated Dec 2025 actuals (month 1 of 9 for L5 actuals entry) 12/12/25 - Submitting for L5. Adjusting forecast to reflect only FY25 contract renewal. The scope of the initiative should be annual in nature otherwise the initiative will never close. If additional savings are to be realized from annual maintenance contract renewals, a new PV Init should be created for each year. FY26-FY28 forecasts will remain steady state based on FY25 contract renewals. Updated Nov 2025 actuals. Steady state reporting. 11/11/25 - Updated Oct 2025 actuals. Steady state reporting. 10/3/25 - Updated Sept 2025 actuals. Steady state reporting. 9/12/25 - Updated Aug 2025 actuals. Steady state reporting. 8/8/25 - Updated July 2025 actuals; canceled Strategy Milestone because new PV initiatives will be entered to cover this separately. Initiative has been re-baselined to FY 25. Baseline is $3.9M with the Target at $2.8M, Implementation Costs are $7.2M. The contract for F5 was unified with InfoSec. Our discount structure went from the standard 23% to 34% due to Network Engineerings use of FCP. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-20 | 2025-10-16
Business w/ Tech Initiative: DC Optimization Intl (Mainframe & Dev/Test) |  | 88767 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Cathey Cooper, Freke De Boer, Paul Beardmore, Oxana Klinkert, Piotr Buczkowski, Pip Fanning, Marit Heidemann | Attention Needed | 01/17/2025 - Added Freke de Boer and Oxana Klinkert as secondary IO's to align Enabler (ACE)/Enabled(DC Optimization) relationship with ACE. 01/27/2025 - Completed financial estimates and milestones for submission to L3. 01/28/2025 - Reviewed impacted portfolio assignments and submitted to Platforms PEO for review. 02/6/2025 - Added Milestones & Risks; Added KPI's; Updated PPM number. Resubmitted to L3. 03/3/2025 - ACE dependency - Until users are migrated away from using the Orange/TNT legacy applications, this initiative cannot proceed. Estimated user migrations could now take 2 to 3 years. | G: L3 | Cancellation Request | L3 | 2024-11-01 | 2027-01-29
Business Only Initiative: Replace Puppet Enterprise with open source Puppet | 58775 | 7268 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Shawn Keys | On Track | listed as primary to manage step progression | K: L5 | Completed | L5 | 2023-11-10 | 2024-01-12
Business Only Initiative: Block storage array maintenance contract reduction | 59488 | 7282 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Shawn Keys | On Track | ability to move initiative thru lifecycle gates | K: L5 | Completed | L5 | 2023-05-31 | 2024-05-31
Business Only Initiative: Complete Project Exit | 14817 | 9178 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Cathey Cooper, Patricia Frizzell | On Track | 03/03/2025 - Project is still on track for monthly tracking. | K: L5 | Completed | L5 | 2022-10-03 | 2024-06-28
Business w/ Tech Initiative: MS Windows Server 2012 LCM Upgrade |  | 106848 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Deborah A. Saverson, Cathey Cooper, Lanny Jeffries, Paul R. Luker | On Track | 07/30/2025 - Updating to complete for L2. 07/17/2025 - Update what is required to move to L2 and updated remaining device inventory count of 486 as of 7/17/2025 from initial submission. 03/28/2025 - Adding Deb Saverson as primary IO for project management. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: MS Windows Server 2008 and below LCM Upgrade |  | 106851 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Deborah A. Saverson, Cathey Cooper, Lanny Jeffries, Paul R. Luker | On Track | 12/4/2025 - Updating the financials and attached spreadsheet to be approved to move to L3. Awaiting greenlight 07/17/2025 - Update what is required to move to L2 and updated remaining device inventory count of 87 as of 7/17/2025 from initial submission. 03/28/2025 - adding Deb Saverson as primary I/O facilitator | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: SQL Server 2016 LCM Upgrade |  | 106858 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Shelia R. Lomax, Cathey Cooper, Deborah A. Saverson, Lanny Jeffries, Paul R. Luker, Alistair Culwick, KRISHNA PERI, Lewis Frape, Mark Purser | On Track | Designated Shelia Lomax as Primary I/O. 06/10/25 added Cathey Copper and Deb Saverson as IO 6/24/25 - Updated the Initiative Supporting Architectural Documentation with correct link. 06/24/25 - Updated the Estimated Annualized Value Range to High $10M-$35M 6/24/25/Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review 07/01/25 added Lanny Jeffries as sub IO 07/09/2025 added Paul R. Luker as sub IO PPM Request # 1633754 UPR 9013136 would go onto proposal 9/2/25 Submitted ePDSM ticket INC032133218 to update Demand Subtype None to Demand Subtype Protect Purple 9/4/25 Updated/Added Andrea Ards as the primary Supply Chain Operations PEO. 1/2/2026 Added KPIs 1/12/26 Uploaded L2 financials summary for Green Light review. 2/18/26 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: SQL Server 2017 LCM Upgrade |  | 106863 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Shelia R. Lomax, Cathey Cooper, Deborah A. Saverson, Lanny Jeffries, Paul R. Luker, Alistair Culwick, KRISHNA PERI, Lewis Frape, Mark Purser | On Track | 04/08/2025 - Designated Shelia Lomax as Primary I/O. 06/10/25 added Cathey Cooper and Deb Saverson as IO 06/24/25 - Update the Initative Supporting Architectural Documentation with the correct link. 06/24/25 Updated the Estiamated Annualized Value Range to High $5m-$35M 06/24/256/ Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review 07/01/25 added Lanny Jeffries as sub IO 07/09/2025 - added Paul R. Luker as sub IO. PPM Request# 1633753UPR 9013135 goes on the proposal 9/2.25 Submiited ePDSM ticket INC032132321 to update Demand Subtype None to Demand Subtype Protect Purple 9/4/25 Added KPIs 1/12/26 Uploaded Platforms financials summary for Green Light review. 2/18/26 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: SQL Server 2014 & Below LCM Upgrade |  | 106867 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Shelia R. Lomax, Cathey Cooper, Deborah A. Saverson, Lanny Jeffries, Paul R. Luker, Alistair Culwick, KRISHNA PERI, Lewis Frape, Mark Purser | On Track | 04/08/2025 - Added Shelia Lomax as Primary I/O 6/10/25 added Cathey Cooper and Deb Saverson as IO 6/24/25 - Updated Initiative Supporting Architectural Documantation field with the correct link. 6/24/25 - Upated the Estimated Annualized Value to High $10M-35M 6/24/25/Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review 07/01/25 added Lanny Jeffries as sub IO 07/09/2025 - added Paul R Luker as sub IO. PPM Request # 1633752UPR 9013135 goes on the proposal 9/2/25 Submitted ePDSM ticket INC032132562 to update Demand Subtype None to Demand Subtype Protect Purple 10/28/25 Added addtional EILCM team members as sub IO's 12/30/25 Added Andrea Ards as the Primary PEO for Supply Chain Operations. 1/12/26 Added KPIs Uploaded Platforms financial summary for Green Light review. 2/18/26 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: P & E International Support Transition |  | 106886 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Alistair Culwick, Cathey Cooper, Deborah A. Saverson, Lanny Jeffries, Paul R. Luker, KRISHNA PERI, Mark Purser | On Track | 18/11/2025 - Update via Ian McPhillips - note following conversations with both Mark & Alister and subsequently Paul – seeing as we’ve already secured senior leadership approval to proceed with both the P&E transition and take on, we’ve agreed to close out / cancel the P&E MTO plan view entry 106886. 07/01/2025 - Added Deb Saverson and Lanny Jeffries as secondary IO's. 07092025 - Added Paul R Luker as sub I/O. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: IBM Virtual Tape Library (VTL) Replacement |  | 106894 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Lewis Frape, Deborah A. Saverson, Cathey Cooper, Lanny Jeffries, Paul Beardmore, Paul R. Luker, Alistair Culwick | On Track | 07/21/2025 - Moved Primary I/O role from Cathey Cooper to Deb Saverson. 07/09/2025 - Added sub I/O | C: L1 | Cancelled | L1
Business w/ Tech Initiative: RedHat Linux 7 LCM Upgrade |  | 107093 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | KRISHNA PERI, Cathey Cooper, Deborah A. Saverson, Lanny Jeffries, Paul R. Luker | On Track | 02/24/2026: Update financial Actuals except for Commercial, waiting input from Commercial Finance team. We will update soon we receive updates from them. 04/08/2025 - Designated Krishna Peri as I/O. 04/21/2025 - We (Krishna Peri) reviewed with QA team (Steve Kastner) for L2 submission. 06/17/2025 - We removed financial data from the financial dashboard assisted by Jamie Heller. Rational, decoupling contract from initiative. 07/17: We have 11724 servers remaining to be upgraded or decommissioned. | G: L3 | Active | L3 | 2025-06-02 | 2027-01-29
Business w/ Tech Initiative: RedHat Linux 4, 5, 6 LCM Upgrade |  | 107382 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | KRISHNA PERI, Cathey Cooper, Deborah A. Saverson, Paul R. Luker | On Track | 02/24/2026: Update financial Actuals except for Commercial, waiting input from Commercial Finance team. We will update soon we receive updates from them. 04/8/2025 - Designated Krishna Peri as Primary I/O. | G: L3 | Active | L3 | 2025-04-01 | 2027-04-01
Business w/ Tech Initiative: NOS1 Migration to NOS2 - Europe |  | 109261 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Deborah A. Saverson, Cathey Cooper, Lanny Jeffries, Paul R. Luker | Some Issues | 4/14/2026 - Our leadership agreed to go ahead and cancel this request. 2/9/2026 - Placing on hold as approved by leadership until further notice. 1/28/2026 - Awaiting leadership approval before moving forward. Once approval has been received this initiative will be updated. 10/09/2025 - Changed L1 Target value to $1,358,800 to reflect new Baseline Value and L1 Net Recurring Benefit. 10/09/2025 - Confirmed that support (PDSM) reduced Baseline Value from $6,945,000 to $0. 10/07/2025 - Worked with Bob Noble to update L2 financials spreadsheet. Uploaded supporting documentation. 10/07/2025 - Uploaded updated costing spreadsheet to include one-time implementation costs (CAPEX) increase of $60,927 for Cisco Line Card. 09/18/2025 - Added Infrastructure Salaries & Wages to Financials. 09/15/2025 - Uploaded L2 costing for Platform implementation activites for Salaries and Wages and Professional fees. 09/15/2025 - Uploaded version 2 of SCO costing that aligns with 13 month instead of 24 month timeline for application migration activities. 09/10/2025 - Entered project KPI's. 09/09/2025 - Esther Kerns advised that KPIs be entered prior to submitting to L3. Each KPI should have three lines per baseline, forecast and actuals Feedback Provided 9/9/25/Esther Kerns/Domain QA Expert Review 09/09/2025 - Updated Initiatives Supporting Architectural Documentation with new folder location. 09/08/2025 - Added Actuals line item to financials tab for expenses. 09/02/2025 - Uploaded L2 Costing SCO spreadsheet as supporting financial documentation. 08/28/2025 - Updated project Milestones and Risks. 08/27/2025 - Added Andrea Ards as Primary for Supply Chain Operations PEO. 08/21/2025 - Removed impacts to Commercial portfolio. 08/21/2025 - Added Associated Epic 08/15/2025 - Added PPM # 08/15/2025 - Worked with Finance rep to complete L2 financials, Exit rate, costs, etc. 08/15/2025 - Removed portoflio impacts for all areas except Commercial, Platform, and Supply Chain. 06/23/2025 - Worked with Finance rep to correct the calculation of the Baseline Value and Target Value per currency conversion to US Dollars from Euro. 06/23/2025 - Worked with Finance rep to adjust the L1 NRB, Target Value, and Implementation costs; adjusted the Business Complexity Estimate to match Archtectural Review recommended t-shirt size. 06/17/2025 - Updated Impacted Portfolios to include Supply Chains to match direction from Architectural Review. 06/17/2025 - Updated Architectural Review document link. 06/17/2025 - Collaborated with Finance lead to update Primary Type of Value from "Service" to "Tech Reliabiity". 06/17/2025 - Added Initiative Supporting Architectural Documentation. 06/05/2025 - Collaborated with Finance (B.Noble) to enter L1 financials to complete LBC. Initiative ready to SL2 pending L1 Architectural review. 04/30/2025 - Updated Estimated Value range from high to minimal. 04/30/2025 - Provided documentation by QA Expert. 04/23/2025 - Entered preliminary data for LBC. | E: L2 | Cancelled | L2 Feedback Requested | 2025-03-17 | 2027-03-31
Business w/ Tech Initiative: Control M Upgrade |  | 111250 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Deborah A. Saverson, Shelia R. Lomax, Cathey Cooper, Lanny Jeffries, Alistair Culwick, Lewis Frape | On Track | 9/15/2025 - PEL triage determined to update impacted areas all to be no. 7/23/2025 - Provided information for LBC. 06/20/2025 added Cathey Cooper and Deb Saverson additional initiative owners 06/24/25 QA Reviewed with Steve Katsner. Recommendation: Update Ability to Statement and Expected Business Outcome fields. The option to edit the Expected Business Outcome field is not available. 07/01/25 added Lanny Jeffries as sub IO | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: LCM - CA Migration to BMC |  | 111257 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Deborah A. Saverson, Shelia R. Lomax, Cathey Cooper, Lanny Jeffries, KRISHNA PERI | On Track | 07/21/2025 - this initiative is to be cancelled due to time constraints, increased costs and increased operational risk. With less than two years to migrate and no slack in the schedule, the risk of missing the deadline and incurring higher renewal costs is too high. The cost benefits has shifted from being neutral to significantly negative and resource limitations make the disruption unjustifiable. The renewal is now seen as the lower-risk option. 06/10/25 Added Cathey Cooper and Deb Saverson as IO 07/01/25 Added Lanny Jeffries as sub IO | C: L1 | Cancelled | L1
Business w/ Tech Initiative: LAC-BR-Clearance-apps-move from VCP to RECIFE DC |  | 131838 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Leticia Feitosa, Anselmo Comaru, Roger Cooley Jr. | On Track | Due to decisions related to apps migration , still pending definition about Brazil datacenter decomission. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: LAC-BR-Brokeragebilling-COLO-migr-plan |  | 131844 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Leticia Feitosa, Anselmo Comaru, Roger Cooley Jr. | On Track | per team meeting. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: IT Room Compliance EU - EU-wide implementation |  | 131847 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Cristiano Santos | On Track | This Planview request was raised as "Business with tech" because, at the time of request, we were informed that it would need to be done this way, due to the cost amount involved. In the meantime, we were informed that a Local Enhancement could be raised instead, which we did, hence requesting this cancellation. Apologies for any inconvenience. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LCM Brazil Legacy Transformation & Modernization |  | 143378 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Shelia R. Lomax, Deborah A. Saverson, Cathey Cooper, Lanny Jeffries, Paul R. Luker, KRISHNA PERI, Lewis Frape | On Track | Added Cathey Cooper, Deb Saverson, Lanny Jeffries, and Paul Luker as secondary IOs. 7/21/25 Meeting with Bob Noble and Mike Mincer to discuss the project and financials for Lean Business Case (LBC). 7/29/25 LBC financials input discussion with Bob Noble and Mike Mincer. 7/30/25 Brief Demand description updated to reflect datacenters shutdown for (Porto Alegre and Recife) 9/2/25 Updated Primary Type of Value from Cost avoidance to Sustainablity per Mike Mincer 9/2/25 Created INC032103300 to update Demand Subtype to Protect Purple 9/2/25 PPM Request #1633662 UPR# 9013133 that would go onto proposal 9/2/25 Meeting has been scheduled on 10/13 with the Finance Domain Lead and the Doamin QA Expert for L2 submission review. 10/10/25 Finance Review with Bob Nobe and Mike Mincer. 11/6/25 L2 Financials uploaded with assisstance from Bob Noble and Mike Mincer 12/19/25 Sent an email to Xun Miao and Vaibhav Sharma requesting the labor cost to be included in the financial report. 12/29/25 | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: LCM NSX Advanced Load Balancer AVI Migration |  | 144007 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Lanny Jeffries, Paul R. Luker | Some Issues | Added Cathey Cooper, Lanny Jeffries, Paul Luker, and Deb Saverson as secondary IOs. 7/21/25 Meeting with Jamie Heller and William Wixon to discuss financials for the Lean Business Case 7/22/25 Updated Baseline Value per Wiliam Wixon 7/29/25 PPM Request# 1292201 8/5/25 UPR 9013089 that would go onto proposal 8/6/25 Added Pat Frizzell as secondary IO. 8/8/25 Uploaded the link for initiative supporting architectural documentation for LBC 8/19/25 L2 Feedback Provided/Esther Kerns/ DT QA Expert Review 8/22/25 Created INC032056258 to update Demand Subtype to Protect Purple 8/28/25 Transitioning IO Role from Shelia Lomax to Patricia Frizzell. 9/19/25 SL 11/17 Pending completion of FIRST Request DomainSME questions. Current state: answering and acceptance of Q&A. InfoSec requested detailed MicroSegmentation project plan. 11/17 Commercial PRT event completed 11/20 Change to "On Hold" during InfoSec/Infra (techArch) teams develop joint implemenation plan 11/26 Commercial PRT complete - rec'd email; requested L3 documents updated in repository and create L3 Epic -pending InfoSec segmentation alignment planning/approval 12/19Pending InfoSec alignment to proceed. Project risk is high due to the magnitude of effort as all NSX Load Balancer (LB) in the FedEX Network require LCM efforts . Level of effort identified an impact to micro segmentation rules. Identified not all PCI apps maybe included in current Network traffic flow. Required completion of LCM before LB devices are unsupported. 12/30 Pending FIRST approval - Q&A answered- Impact to FXF WTC buildout was identified 1/23/26 FIRST 8304 approved for FEC AVI project no longer on hold 1/27 QA Review (Tom Rush) advised to add Portfolio greenlight details. 2/3 On hold review of LCM vs sofrtware upgrade pending leadership direction 2/24 InfoSec Team created PV request for resources - pending resources. InfoSec Contract in flight. Current workshops in progress - may impact future state design, TBD 2/27 Platforms update PM (Pat F) no mutual agreement. Initiative moved back to L2. 3/10 Planning is on hold - 3/18 Per Donn Janes (Dir) AVI for CoLos is on hold. | E: L2 | On Hold | L2 Feedback Requested | 2026-03-23 | 2026-06-22
Business w/ Tech Initiative: RHEL 7 to RHEL 9 Oracle Migration |  | 154370 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Adam Jones | On Track | There was already another request created just like this one in planview. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: RHEL 7 to RHEL 9 DSE Migration |  | 154376 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Adam Jones | On Track | There was already another request created just like this one in planview. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: DDI - Freight & Express Migration to Micetro |  | 154396 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Christopher Miller | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: DDI - Global Infrastructure Standardization |  | 154402 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Christopher Miller | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Infosec - Firewall LCM |  | 154810 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Thuy Trang L. Doan, David Stephenson | On Track | **4/22/26** - Pending TO Finance approval **4/21/26** - Domain Lead approved - After manual Joe Jolly manual approval **4/16/26** - Met with Thomas and provided justification for Domain Lead approval **4/2/26 **- approved by finance **4/1/26** - in SL3 pending Finance Domain approval. Reached out to Apoorv **3/30/2**6 - Updated milestone from implementation to technology. Added clarity to money step and removed impacted portfolios from milestones per EPM request. **2/16/26** - approval/greenlight received from Nicholas Shanky **2/9/26** - costing completed **1/7/26** - provide financial update to Xun Miao **12/8/25** - met with Finance (Apoorv) to update costing **9/23/25** - pending finance review unable to obtain architecture diagram | F: SL3 | Active | SL3 SVP Finance Approval | 2026-03-02 | 2027-06-29
Business Only Initiative: Oracle Resident Reduction |  | 155311 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Mark S. Morgan | On Track | 10/9 Finance validated the init has achieved Money Step and ready to moved to L4 (approval in progress) 10/7 Contract was renewed; L3 wa achieved; Financial Sept 2025 updates complete contract renewal in progress, no concerns noted 3/18/26 updated actual financials for 2026. Will follow up to validate finance agree this is ready for L5 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-09-19 | 2025-09-30
Business w/ Tech Initiative: CoLo West LCM / BBG FY26Q2 |  | 155314 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell | Some Issues | 4/7/26 Initaitive is no longer needed directional change by Leadership- Cancel On hold - funds not approved to move forward ( at this time 9/22 Received Arch approvedl 9/22 Stop work applies 11/19 Pending Exec leadership approvals 11/25 Pending Initiative financial plan details. 1/5/25 Pending CoLo LCM scope decision, Shawn & Adam plan to review this week. per Bob N 2/6 Pending finance committe approval- pulled from Feb meeting 2/27 ON HOLD until finance approves | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: CoLo East LCM / FY26 Q2 |  | 155317 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell | On Track | 4/7/2026 - Directional change this initaitive is no longer needed - Cancel 8/26 Pendng EPM approval 9/22 Received Arch approval 11/19 Pending Exec leadership approvals 11/25 Pending Business Case Finance updates 1/5/25 Pending CoLo LCM scope decision, Shawn & Adam plan to review this week. per Bob N 2/6 pending finance committee approval - pulled from Feb meeting 2/24/26 Pending Finance approvals and Bob Noble Finance Principle to update PV financials for John's approvas. 2/27 ON HOLD until finance approves | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Reduce Redundancy Across Field and DC/Colo Network | 16884 | 8008 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Susan Ward, Kirt Satam | On Track | 4/10/26 - Mar 2026 actuals entered (month 3 of 9 in L5) - no add'l savings to report after FY26 rebaseline 3/10/26 - Feb 2026 actuals entered (month 2 of 9 in L5) - no add'l savings to report after FY26 rebaseline 2/9/26 - Entered L5 in Jan 2026; Jan actuals entered (month 1 of 9 in L5) - no add'l savings after FY26 rebaseline 1/12/26 - Dec actuals entered (month 3 of 3 in L4) - no add'l savings after FY25 rebaseline 12/12/25 - Nov actuals entered (month 2 of 3 in L4) - no add'l savings after FY25 rebaseline 11/11/25 - Oct actuals entered (month 1 in L4) - no add'l savings after FY25 rebaseline. 10/9/25 - approved for L4 10/3/25 - Submitted to SL4. Money step complete 10/3/25. Sept actuals entered. 9/17/25 - Updated end of money step from 5/25/25 completion to 10/31/25. All savings achieved as of 5/31/25 however still gathering money step evidence to move to SL4. Patience while the evidence continues to be compiled is appreciated. 9/12/25 - Aug actuals entered - no add'l savings after FY25 rebaseline completed. Still collecting money step evidence. Expect to move to L4 by end of Sept. 8/22/25 - Collecting final money step evidence to upload 8/13/25 - July actuals entered. All savings realized associated with this effort. Money step completed; uploading evidence to PV. Moving to L4 8/15/25. **3/28/25 - FY25 Rebaseline complete** 4/20/25 - Mar 2025 Actuals complete. 5/16/25 - Apr 2025 Actuals complete. $0 forecast for Pro Fees at Finance direction since these transitioned to Accenture resources 6/11/25 - May 2025 Actuals complete. Adjusted Mar/Apr actuals for Impact 17718 due to billing adjustments for closed facilities. Updated Dec 2024 Actuals. Adjusted Oct 2024 Actuals for Costs to Achieve due to missed Cisco Milestone payment that was accrued for Oct. | K: L5 | Active | L5 | 2023-01-02 | 2025-10-31
Business w/ Tech Initiative: LCM - TNTMS Active Directory Decommission |  | 163520 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Alistair Culwick | On Track | Latest Update 16/10/25 Meeting held with Calvin, Zia, Ross, Cathey and Deb, Mark P and myself. Discussed and aggreed to Cancel this planview request as the migration is no longer required due to the Legacy Decommsion push (which will be run under a separate project). Update 08/10 Call with myself, Mark, Zia and Neeraj Jain (Accenture Lead), talked through which steps need to taken to obtain costs assocaited to migration actvities. Neeraj to work with vendors over the 5 locations to obtain costings involved for migration activities, Zia advised at this point in time it will be very dificuly to establish baseline costings/savings involved for any decom work. This will be something we need to discuss further down the line with Bob Noble and all involved with this project. Awaiting Neeraj with his findings, next update call aggreed for 2 weeks time (Neeraj to schedule). Update 03/10 Myself, Zia, Mark P, Bob Noble and Deb, discussed and established what requirments are needed around the finance spreasheet. Zia will speak with Calvin to establish who will be responsible in obtaining info on hardware/quotes accross the 5 countries identifed on this project for either deom or migration which will then be built into a financial spreadsheet. Next call with Zia, myself and Accenture lead is scheduled for 8/10. Call sceduled for 2nd October to discuss (financial questions for Lean Business Case (LBC) - L1 for LCM - TNTMS Active Directory Decommission) with Finance Team (Hardware) | C: L1 | Cancelled | L1
Business w/ Tech Initiative: DDI - EU Migration of Infoblox to Micetro |  | 163524 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Christopher Miller | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: EDCW Hardware Decommissioning |  | 159995 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell, Franklin Beattie | On Track | 11/13 Pending financial modeling completion to identify Business & Target value. Financial model is in progress, Signficant level of effort & financial approvals required. 11/13 Initial scope was BwT, Tech completed. Current scope: infrastructure only (meaning no longer a DC as the network is disconnected.) Removing hardware, including facilities equipment that is not tagged to stay. Don't need a list of what will stay, reviewed approved by leadership (prior to my alignment with project). The building will be sold as is. Decommission of DC is scheduled for completion Mar 2026 on target Network/InfoSec vacated the building. No future impact known Name update as Initiative will be moved from TS Pod to Infrastructure Nov (? need to confirm actual date) moved init back to Infra POD. Cost savings impact identified the initiative belonged in Infra Opt POD 12/30 DCM Decom status is 90% of IT aseets removed from DC. Overall assets is 85% removed. Continue on track to exceed March exit plan date. Pending Finance details to complete business base to move to L2. 1/13 Team continues to remove not PDSM assets, including follow up with vendors to remove circuit hardware 4/15 Pending updates from RSC 4/17 Received RSC updates Dec-Mar $14 M | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: EDCW DC (Enterprise Data Center West)Property Sale |  | 166414 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | Patricia Frizzell | On Track | Changing primary IO to Pat. 11/14 Informed potential loss to current plan - records are in fnance review/updates. 11/21 Scope of sale is TBD; (2) Marketing options in disucssion Sell DC + 1 Parcel or Sell DC +3 Parcels. Pending update from William/Shawn. Current valuation is 1 1/2 yrs old may need new valuation, pending on decision how to market currlently listed as $24M 1 Parcel $3M. Mary providing monthly exp info Tara Goodwin Real Estate SME. Financial information required to complete L1 12/8 Updated valuation was requested 12/30 No update for updated valuation, on track to list in March. In addition, RE continues to sell the property "As-Is". Marjority of staff will finish this week with HVAC. Lead Electrician will remain, as responsible for managing the building systems. Vehicles/equipment transferring to Indy, will stay estimated coupleof months due to risk of snow . 2/3 No update from RE as of 1/30/25. RE confirmed they still plan on listing building in March, and once they have an interested buyer we will know more about any building condition changes we may need to make. Decom is still on track to finish in February (baseline activity expected before listing the property) LBC is on hold until approved information is provided for updates. 3/5 DC decommission activities is near completation. Hand off to Properties for listing planned foor 3/12 3/13, all EDCW decommission activities were completed and ownership was formally transferred from IT to Facilities/Properties. 4/8, Real Estate provided the building inspection report to the proposed broker and requested a valuation and listing agreement; the estimated timeline to sell the property is currently under evaluation. A strategic review to optimize value identified that marketing the data center with an optional adjacent parcel could provide additional negotiating leverage, with the potential to pursue a separate parcel sale should the buyer decline, thereby maximizing overall value realization. 4/13 property valuation and broker agreement remain pending 4/17 Property sell value is pending the broker selection and valutation.. If the property were sold today for $20M, it would be offset by the $23M Net Book Value (NBV), resulting in an approximate $3M loss, excluding selling costs. The $4M annual operating cost reduction is tangible, and the financials have been updated to reflect these forecasted savings. 4/24 Properties update: on site 4/23 pending valuation. Estimate listing agreement received week of 4/27. Attorneys continues to make progress on the boundary line matter. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Windows Automation |  | 167031 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Brian Glover | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Infosec - Micro Segmentation Enforcement |  | 170917 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Thuy Trang L. Doan, Laura Carpenter | Some Issues | **4/20/26** - Received email greenlight approval from Sandy Adams from SCO **4/20/26** - attended Commercial Archtecticture review - COM approved to **move to L3 to accept the work. 4/20/26** - uploaded ES portfolio cost. received 4/17/26 **4/7/26** - Met with SME to review LOE for Micro Machine. New compliance requirement to segment staging environment. LOE to include scope for L3 and L6 **4/6/26** - met with Apoorv to review financials. verbal signoff received to submit to next step from initiative costing perspective. **4/1/26** - EPM meeting completed. Emiliee James direction was to continue demand as BwT with guidance to identify # apps per portfolio to complete cost with default set hour (8) per app. **3/27/26** - after 8 months, L2 arch assement PRT sugggested for demand to be worked as LCM instead BwT. BwT triage review was held on the same day. follow up for PEO to schedule meeting for EPM guidance **2/25/26** - provided justification to DTO leadership for negative financial impact. -38k driven by FY26 savings of $191k which results from FY26 spend lower than FY25 baseline. **2/20/26** - Finance approved for L2 | E: L2 | Active | L2 Feedback Requested | 2026-04-06 | 2027-12-31
Business w/ Tech Initiative: LAC-BR-3-GIS - Application Migration to Corporate |  | 171060 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Elaine Moraes Queiroz | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: IT Infrastructure Modernization - International |  | 186162 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Alistair Culwick, Jade Russell | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: IBMi SRIOV - Atlanta |  | 188140 | Business w/ Tech Initiative | IT - Infrastructure Optimization | Data and Tech | Francis R. Michalik, Jim McMahon | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Cisco Video Conf equipment EOL upgrades |  | 190350 | Business Only Initiative | IT - Infrastructure Optimization | Data and Tech | John Schuman | On Track | On Track | D: SL2 | Active | SL2 Domain Lead Approval
Business w/ Tech Initiative: Service Now Vulnerability Response Enterprise Upgr | 89649 | 6675 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Launa Morris, Bobby Intharaksa, Dalton Schultz | On Track | 3/26/2025 - FY25 re-baseline complete | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-01 | 2025-03-31
Business w/ Tech Initiative: Telematics Vendor Selection and Integration - Peop | 26158 | 6685 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Cassandra Aguilera, Bobby Intharaksa | On Track | 04/10/2024 - B. Blevins: On 4/05/2024, the ITAM pod leadership approved change request (CR) to reforecast initiatives. CR is required to: 1. Shift one-time implementation costs of $4.77m from March 2024 to April 2024 due to contract execution delays. No impact to FY24 savings., 2. Revise FY25-FY27 forecast to reflect implementation plan - ramp down & up of existing & new vendor subscriptions (Trimble to Motive subscriptions), 3. Correct forecasts entered as costs instead of savings. Please see attached CR (file: 20240405 DRIVE ITAM CRs for approval) and email approval (RE_DRIVE ITAM Change Requests Approved 03_29 - Action Required in Wave) for more details. Working on completing the business case and defining money steps -defining safety administration hours worked FY25 / Rebaseline | G: L3 | Active | L3 Feedback Requested | 2023-02-14 | 2026-05-27
Business Only Initiative: Broadcom to SmartBear for Service Virtualization | 30729 | 6779 | Business Only Initiative | IT - ITAM | Data and Tech | Priyanka Kurapati, Bhaskara Chikkala, Bobby Intharaksa | On Track | 3/26/2025 - FY25 re-baseline complete. Added Bobby as backup | I: L4 | Active | TEMP L4 - Enter L4 | 2023-07-05 | 2024-12-31
Business Only Initiative: BI Consol - SAS - FedEx Office | 41710 | 6916 | Business Only Initiative | IT - ITAM | Data and Tech | Charlotte Huff | On Track | Rebaselined to FY25 completed and approved by Finance on 4/14. | K: L5 | Completed | L5 | 2023-10-02 | 2024-06-28
Business Only Initiative: Anti-Virus/EDR Replacement (Crowdstrike) | 57388 | 6920 | Business Only Initiative | IT - ITAM | Data and Tech | Nicholas Shansky, Charlotte Richardson | On Track | Rebaselined to FY25 as of 3/31/25 | K: L5 | Active | L5 | 2023-09-01 | 2025-03-31
Business Only Initiative: FY25 OCI Cost Optimization | 88557 | 6940 | Business Only Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin, Caitie Adams | On Track | 7/16/25 - added IO owner Caitie Adams | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2026-08-03
Business Only Initiative: Legacy Lumen Ring Decommission | 55718 | 6952 | Business Only Initiative | IT - ITAM | Data and Tech | Susan Ward, Kirt Satam | On Track | 3/21/25 - FY25 Rebaseline complete Dec 2024 Actuals entered. Steady state in L5. | K: L5 | Completed | L5 | 2023-10-03 | 2024-05-31
Business Only Initiative: Oracle Cloud Infrastructure Cost Optimization | 35217 | 7003 | Business Only Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin, Caitie Adams | On Track | 7/16/25 - added IO owner Caitie Adams | K: L5 | Completed | L5 | 2023-06-01 | 2024-10-04
Business Only Initiative: Retail Solutions - WebMethods retirement - Softwar | 61826 | 7057 | Business Only Initiative | IT - ITAM | Data and Tech | Michelle Daniel, Dalton Schultz, Prabesh Pudasain | On Track | 03/21- Dalton Schultz - Rebaselined FY25 completed 6/20 - Met with Dalton Schultz & Jerry Mason to align on updated FY24 baseline and FY25 savings forecast. Updates to be reflected in Wave, milestones to be added to reflect completion of execution, and timeline for L3 push to be determined. 3/12 Met with Adam Williamson and Jerry - need to push this forward. Recently negotiated the current renewal to 9 months beginning April 2024. After December 2024 we will not renew this contract following the retirement of WebMethods. Will get with Dalton on moving this forward. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-03-01 | 2024-12-31
Business Only Initiative: BI Consol - SAS - AMEA - AMEA Forecasting/Cust Ana | 41713 | 7074 | Business Only Initiative | IT - ITAM | Data and Tech | Chi-Fung Wong, Dana Wu, Bobby Intharaksa | On Track | Rebaselined to FY25 completed and approved by Finance on 4/14. Dec-02,2025 - QA Reviewed by Thomas Rush. | K: L5 | Active | L5 | 2024-07-22 | 2025-02-28
Business w/ Tech Initiative: BI Consol - SAP BO - FXG | 41697 | 7114 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Derrick Getter, Harold Moon, Sean Cahalan | On Track | Still figuring out a lot of things. . | G: L3 | Active | TEMP L3 - Enter L3 | 2025-01-01 | 2026-09-10
Business Only Initiative: BI Consol - SAP BO - FXF | 41698 | 7115 | Business Only Initiative | IT - ITAM | Data and Tech | Jim McBee, Shaun Bullock, Belinda Veach | On Track | Update IO's 4/15/25- Plan to start having meetings with business parnters on list of reports that needs to be migrated | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-10-02 | 2026-03-30
Business Only Initiative: BI Consol - SAS - Canada | 41708 | 7125 | Business Only Initiative | IT - ITAM | Data and Tech | Vishnuvardhan Reddy Panchaling, Kalyan Vempaty | On Track |  | K: L5 | Completed | L5 | 2023-10-02 | 2024-07-31
Business w/ Tech Initiative: BI Consol - SAS - FedEx Freight | 41709 | 7127 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Jim McBee, Shaun Bullock, Belinda Veach | On Track | Waiting on Corios contract to be signed 4/15/25- Contract has been signed | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-10-02 | 2027-10-01
Business Only Initiative: BI Consolidation Parent Initiative (Placeholder) | 41715 | 7133 | Business Only Initiative | IT - ITAM | Data and Tech | Eddie Patterson, Kalyan Vempaty, Charlotte Huff, Chi-Fung Wong, Devin Lewis, Robert Mears, Sujith Narayanan, Vardhan Kamat, Christopher Darr, Nicole Craig | On Track | Added IOs so they can show dependency on this as the parent | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-05-28
Business Only Initiative: Replace Workspace ONE with Intune for U.S. Knowled | 59615 | 7291 | Business Only Initiative | IT - ITAM | Data and Tech | Bobby Intharaksa, Ruwan Dealmeida, Vivian Hodges | On Track | 3/25/2025 - FY25 Rebaseline complete adding IO. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-08-01 | 2026-02-13
Business Only Initiative: FedEx.com Google Maps Demand Reduction and Contrac | 62740 | 7309 | Business Only Initiative | IT - ITAM | Data and Tech | Sarah Goodman, David Howell | On Track | FY25- Rebaseline complete 4/16/25 Change primary to Sarah Goodman 2/25/26 | K: L5 | Active | L5 Feedback Requested | 2023-11-16 | 2023-12-01
Business Only Initiative: VAN Migration and Provider Consolidation ¦ SURGE | 63643 | 7363 | Business Only Initiative | IT - ITAM | Data and Tech | Kudzai Tunduwani, Rebecca Jones | On Track | 5/16/25 Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review FY25 - Rebaselined Updated primary IO | I: L4 | Active | TEMP L4 - Enter L4 | 2023-03-01 | 2024-09-20
Business Only Initiative: Optimizely Contract Savings | 73243 | 7554 | Business Only Initiative | IT - ITAM | Data and Tech | Bobby Intharaksa, Melissa Sedlak | On Track | 3/25/25 - FY25 re-baseline complete | I: L4 | Active | L4 Feedback Requested | 2023-06-15 | 2025-06-10
Business Only Initiative: DRIVE - FY25 Cost Savings $30M - Commercial Tech - | 93618 | 7559 | Business Only Initiative | IT - ITAM | Data and Tech | Michelle Daniel, Hemant Arora, Prabesh Pudasain | On Track | 3/26/2025 - FY25 re-baseline complete FAME has been retired added tracked savings. Lucid will not be renewed in May, so actuals Oct are zero, savings will not be started until May. | K: L5 | Active | L5 | 2024-05-01 | 2025-06-27
Business w/ Tech Initiative: IT Technology Business Management (TBM) Global Pra | 97198 | 7645 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Sherona Spurlock, Nicholas (Nick) Wolf | On Track | 04/16/25 Removing Kenny as IO; adding Nick Wolf. Per evaluation of L0-L2 initiatives for the ITAM Pod the week of February 17th, initiative 7645 is to be placed on On Hold ASAP. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-11-01 | 2025-09-29
Business w/ Tech Initiative: Next-Gen GCCR Threat Detection Engineering & Respo | 96308 | 7662 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Lijing Xu, Jose Zapico, Keith O'Connor, Melissa Randolph | On Track | On track. Re-baselined FY25 on April 10th 2025 with Bobby and Kendra. 4/25/25/Document Feedback Provided/Lijing Xu/ D&T Domain QA Expert Review: Esther Kerns | G: L3 | Active | TEMP L3 - Enter L3 | 2023-09-01 | 2026-08-03
Business Only Initiative: FXG ReadyAPI SV Licenses Termination | 84099 | 7714 | Business Only Initiative | IT - ITAM | Data and Tech | Bhaskara Chikkala, Priyanka Kurapati | On Track | 3/24/2025 - FY25 re-baseline complete | I: L4 | Active | TEMP L4 - Enter L4 | 2024-03-01 | 2024-03-29
Business Only Initiative: Portfolio Surge - APAC&MEISA | 92378 | 7733 | Business Only Initiative | IT - ITAM | Data and Tech | Chee-Pin Yong, Marie Mangin, Patty Higginson | On Track | Rebaselined to FY25 as of 04/01/25 | K: L5 | Active | TEMP L5 - Enter L5 | 2023-10-31 | 2024-12-06
Business Only Initiative: Informatica Subscription Renewal Reduction | 91054 | 7745 | Business Only Initiative | IT - ITAM | Data and Tech | Jennifer Hood, Philip Rencher | On Track | FY25 - Rebaseline | K: L5 | Completed | L5 | 2024-05-01 | 2024-08-30
Business Only Initiative: SAP Migration | 16578 | 7839 | Business Only Initiative | IT - ITAM | Data and Tech | Ben Benaziz, Shawn Gardner | On Track | Following the requested transfer of init #30451 to init #16578, data, impacts, and timelines were updated accordingly to reflect the following. Implementation 'money' step completed Jan 31 2023 to complete replatforming activities. Invoice savings of $3.1m began Feb 2023 when old provider contract expired and new contract charges continued. Milestones and timelines updated to reflect the updated dates. Proof of savings uploaded to Attachments | K: L5 | Completed | L5 | 2023-01-31 | 2023-01-31
Business Only Initiative: Reduce CloudBees Flow Licenses by adopting RAPID D | 36244 | 7909 | Business Only Initiative | IT - ITAM | Data and Tech | Chris Warren, Stephen Byers | On Track | FY25 Re-baseline Complete | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-20 | 2024-02-29
Business Only Initiative: Dell TLA Contract - Consolidation Int'l to US | 59406 | 7987 | Business Only Initiative | IT - ITAM | Data and Tech | Bobby Intharaksa, Pamela G. McCloskey, Steve Laster | On Track | FY25 re-baselined Adding Pam McCloskey as primary IO. | K: L5 | Active | L5 Feedback Requested | 2023-11-03 | 2024-01-05
Business Only Initiative: Consolidate Network telecom services | 16881 | 8007 | Business Only Initiative | IT - ITAM | Data and Tech | Susan Ward, Kirt Satam | On Track | 4/10/26 - Mar 2026 actuals entered (month 6 of9 for L5 actuals entry) steady state 3/10/26 - Feb 2026 actuals entered (month 5 of9 for L5 actuals entry) steady state 2/10/26 - Jan 2026 actuals entered (month 4 of 9 for L5 actuals entry) steady state 1/12/26 - Dec 2025 actuals entered (month 3 of 9 for L5 actuals entry) 12/12/25 - Nov 2025 actuals entered (month 2 of 9 for L5 actuals entry) 11/11/25 - Oct 2025 actuals entered (month 1 of 9 for L5 actuals entry) 10/21/25 - L5 approved 10/3/25 - Sept 2025 actuals entered. 9/12/25 - Aug 2025 actuals entered. 8/13/25 - No additional savings or costs to be achieved. Begin steady state in June 2025. Plan to move to L5 in Oct 2025. July 2025 actuals entered 4/16/25 - FY25 Rebaseline complete 5/16/25 - Apr 2025 Actuals entered. Final employee wireless billing credit pending receipt; expect to hit May bill. 6/11/25 - May 2025 Actuals entered. Employee wireless billing credit received on May bill causing the larger than forecasted savings. Beginning June 2025, no add'l savings expected. Rebaseline indicates negative savings monthly due to billing credits realized in FY25 which will not continue. Dec 2024 Actuals entered; slightly under forecast due to accelerated employee wireless billing credits achieved in Oct/Nov. No risk to achieving FY25 target for this initiative. Nov 2024 Actuals exceeded forcast due to receipt of billing credits. Oct 2024 Actuals exceeded forecast due to additional savings for removal of EAC and Admin fee from employee wireless and operational devices from the new VZW contract. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-01 | 2025-03-19
Business Only Initiative: Telecom - Technology Migration and Audit FY24 | 58290 | 8010 | Business Only Initiative | IT - ITAM | Data and Tech | Susan Ward, Kirt Satam | On Track | 4/10/26 - Mar 2026 actuals entered (month 9 of 9 for L5 actuals entry) 3/10/26 - Feb 2026 actuals entered (month 8 of 9 for L5 actuals entry) 2/10/26 - Jan 2026 actuals entered (month 7 of 9 for L5 actuals entry) 1/12/26 - Dec 2025 actuals entered (month 6 of 9 for L5 actuals entry) 12/12/25 - Nov 2025 actuals entered (month 5 of 9 for L5 actuals entry) 11/11/25 - Oct 2025 actuals entered (momth 4 of 9 for L5 actuals entry) 10/3/25 - Sept 2025 acutals entered (month 3 of 9 for L5 actuals entry) 9/12/25 - Aug 2025 actuals entered (month 2 of 9 for L5 actuals entry) 8/13/25 - July 2025 actuals entered (month 1 of 9 for L5 actuals entry) 7/2/25 - enter L5 6/11/25 - move to SL5. Steady state since Nov 2024 3/21/25 - FY25 Rebaseline Complete | K: L5 | Active | TEMP L5 - Enter L5 | 2023-06-01 | 2024-10-31
Business Only Initiative: BI Consol - SAP BO - ELAC | 41699 | 8062 | Business Only Initiative | IT - ITAM | Data and Tech | Sujith Narayanan, Timothy Bryant | On Track | Rebaselined to FY25 completed and approved by Finance on 4/14. | G: L3 | Active | L3 Feedback Requested | 2023-10-02 | 2026-03-30
Business Only Initiative: Supply Chain Ops - Portfolio Surge - OSC Reduction | 92282 | 8064 | Business Only Initiative | IT - ITAM | Data and Tech | Denise Sottile, Timothy Comino | On Track | 3/31/2025 - FY25 Rebaseline complete | I: L4 | Active | TEMP L4 - Enter L4 | 2025-02-28 | 2025-02-28
Business Only Initiative: Supply Chain Ops - Portfolio Surge - OSC Reduction | 93264 | 8067 | Business Only Initiative | IT - ITAM | Data and Tech | Rachael Muldrow, Timothy Comino | On Track | 3.21.25 - FY25 re-baseline complete This initiative is ready to progress to L3 10.2.24: Actuals added; moving this initiative to L4; L5 estimated date is Jan. 4, 2025. | K: L5 | Completed | L5 | 2023-10-02 | 2024-06-28
Business Only Initiative: Portfolio Surge - Supply Chain Operations - Mainte | 91729 | 8072 | Business Only Initiative | IT - ITAM | Data and Tech | Ryan Nolette, Timothy Comino | On Track | FY25 Rebaslined - 3-27-25 | K: L5 | Active | L5 Feedback Requested | 2023-07-03 | 2025-02-28
Business Only Initiative: Portfolio Surge - Supply Chain Operations OSC Redu | 91998 | 8073 | Business Only Initiative | IT - ITAM | Data and Tech | Ryan Nolette, Timothy Comino | On Track | FY25 Rebaselined - 4/1/2025 **12/11/2024: Originally planned the initiative to have a 1-time purchase of prepaid credits for Azure which would allow for amortization for FY25. Purchase plan was updated to make 2 smaller purchases in FY25 which will keep spend in FY25 at $600K. Updated the financials to reflect this change, attached a new spend document comparing the original plan to the new plan. Savings achieved from the new plan is $107,687.** | I: L4 | Active | L4 Feedback Requested | 2024-09-09 | 2025-05-30
Business Only Initiative: BI Consol - SAS - Hong Kong - AMEA Strategic Cust | 41714 | 8143 | Business Only Initiative | IT - ITAM | Data and Tech | Lynn Tan, Vincent Ng | On Track | Rebaselined to FY25 completed and approved by Finance on 4/14.” | K: L5 | Completed | L5 | 2023-10-02 | 2024-04-12
Business w/ Tech Initiative: FedEx ITAM practice for the Enterprise | 2650 | 8204 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Dalton Schultz, Steve Laster, Brian Harris | On Track | FY25 - Re-Baseline 03/27/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-01-17 | 2026-05-29
Business Only Initiative: Contracts and savings for all BI Consolidation Ini | 29885 | 8215 | Business Only Initiative | IT - ITAM | Data and Tech | Eddie Patterson, Heidi-Jo Shuttleworth | On Track | Updating list of IOs Rebaselined to FY25, approved by Finance and completed 4/14. 5/01/25: Updated Baseline value = 9,036,236.64 and target value is $7,633,434.32 | G: L3 | Active | TEMP L3 - Enter L3 | 2023-06-01 | 2026-12-31
Business Only Initiative: Asset Disposal policy enhancement & enforcement fo | 3052 | 8265 | Business Only Initiative | IT - ITAM | Data and Tech | Stephane Vaslet, Colleen Stearns | On Track | The initiatve is re-baselined from FY'22 to FY'23 to realize the value/savings generated from increasing revenue split from 75/25 to 90/10. Previous baseline included in Wave/rolled over to PV for FY’22 was 0. As such, you would see a change in NRB from L1 to L3 since we re-baselined to FY’23 with baseline value of $812k. Mar 26 25: Rebaselined to FY'25 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-10 | 2024-11-29
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - Global Digital | 96527 | 8321 | Business Only Initiative | IT - ITAM | Data and Tech | Shankar Ramasamy, Hemant Arora | On Track | Project implemented on 10/12/24. FY25 rebaselined | K: L5 | Completed | L5 | 2024-07-22 | 2025-05-30
Business w/ Tech Initiative: FSC - Software (W17284 / P8347) | 17284 | 8347 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Patty Higginson | On Track | FY25 Re-baselined | I: L4 | Active | TEMP L4 - Enter L4 | 2023-04-04 | 2024-06-28
Business Only Initiative: PF Surge - FSC Outside Svc & Maint (W92919/P8350) | 92919 | 8350 | Business Only Initiative | IT - ITAM | Data and Tech | Patty Higginson | On Track | FY25 – Re-baselined | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2024-10-31
Business Only Initiative: Assess enterprise-wide peripheral consolidation | 3051 | 8526 | Business Only Initiative | IT - ITAM | Data and Tech | Stephane Vaslet, Heather Radics, Colleen Stearns | On Track | Updating IO due to transistioning off the IT souring team. Mar 28 25: Rebaselined to FY'25 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-04-03 | 2024-02-09
Business Only Initiative: Supplier consolidation for computers enterprise-wi | 3046 | 8851 | Business Only Initiative | IT - ITAM | Data and Tech | Stephane Vaslet, Colleen Stearns | On Track | Mar 28 2025: Rebaselined to FY'25. CAPEX Yearly entries (Negative or Positive) are spread equally over 12 months every fiscal. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-05-09 | 2024-02-09
Business Only Initiative: PC and Laptop LCM Refresh from 4 to 5 Years | 3058 | 8854 | Business Only Initiative | IT - ITAM | Data and Tech | Stephane Vaslet, Colleen Stearns | On Track | 7/5/2023 Sourcing schedule a meeting with Adam Smith and Bob Green on Monday 7/10/2023 to go over final analysis and get confirmation on 4-5 year lifecycle. 6/21/2023: Sourcing analysis was updated on 6/20 due to new logic from both the repair service center and guidance from Finance. This model is now showing a loss of money from moving to a 5 year lifecycle after including incremental costs associated with going from a 5-6 year lifecycle. Will need final confirmation from Leadership on next steps. 6/15 Sourcing received updated data to edit the savings model from the RSC. A meeting is scheduled with the director of finance John Jamison for Monday 6/19/23. Upon results from that meeting, Sourcing will schedule a call with Bob Green & Adam Smith for final approval on the PC Lifecycle. 6/7/2023 Sourcing met with Finance to review analysis on Monday 6/5/23. Sourcing is currently working on an update to the analysis based on feedback from Finance. Upon completion of new analysis sourcing will review again with Finance and leadership to make final decision on if we should move to a 5 year lifecycle for PCs. 5/24/2023 Deloitte updated/validated savings projection. Current projection is $1.2M. Sourcing presented this new savings number to the PC business team on 5/23/23. Additionally, sourcing presented this new number to finance manager on 5/23/24. The suggestion to move forward with a 4 year lifecycle was approved. Sourcing will be providing this forecasted savings, caveats & assumptions to leadership and will communicate lifecycle change upon approval from leadership. 5/17/2023 Due to change in logic that resulted from Deloitte's review of the analysis for moving from a 4-5yr lifecycle, this milestone is at risk. Currently the updated savings provided from Deloitte analysis is a $1.2M annually. Background information: Only about half of all devices that are currently on a 5 year lifecycle (FXS) make it to the full 5 years. This change to 5 years will increase the tickets for the tech team for breakfix and the PC lifecycle team (procurement) will increase their work load by 30 minutes for each PC purchased outside of the standard lifecycle. Meeting with leadership to determine next steps and updated timeline. 5/10/2023 Milestone# 11820 Gain consensus across the business team to make the change to 5 year PC Lifecycle This milestone is at risk due to change in logic for moving from a 4-5yr lifecycle. A 4 year lifecycle may be a more lucrative model than 5 years. Next steps: Finish analysis with new logic Review new analysis with Finance & make recommendation to either keep 4 year lifecycle or move to a 5 year lifecycle Mar 31 2025: Rebaselined to FY'25 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-03-06 | 2023-10-31
Business Only Initiative: RFP APAC IT Infra Network Services | 3061 | 8975 | Business Only Initiative | IT - ITAM | Data and Tech | Nidhi Sodhani, Heather Radics | On Track | Apr 24' - Updated. Mar 24' - Updated. Feb 24' -updated as received. Jan 24' -updated as received. Dec 23' -updated as received. Nov 23' -updated as received. Project proposed to move into L5 has been approved by Finance, hence status changed to L5 in WAVE Tool. Finance has requested a session for re-baseline. Oct 23' -updated as received. Project proposed to move into L5 has been approved by Finance, hence status changed to L5 in WAVE Tool. Sep 23' -updated as received. Reached out to Mcky team for the support on targets in Impacts and Baseline showing as zero in KPI Tab - TBD. Aug 23' - Updated as received. 18 July - In order to add the actuals for June 2023 by the given timeline of 21 Jul - moved the status back to L4 temporarily. July 2023 - - Worked together with the business and supplier side to review the billing accuracy and new rate card implementation. - The MRC rates differ for the Vendor invoices and FX Business teams. - With 50+ invoice for all 3 vendors, reviewed the FX Rates being applied. 27 June 2023 - Service Credit from Verizon received in Jun 2023, being reconciled for the actual savings to be updated in June 23' invoice. Status moved to L5 for the actual realized over the last 3-4 months. 13 Jun 2023 - Update the invoice corrections from Singtel. Previously Singtel provided USD 43404 as the Dec 22 bill. later corrected, stating that these charges calculated (~USD 43,404) are Dec 22 charges only for SHACDC site new circuit. The correct billing for Dec 22' stated it's USD 289989 instead. Dec 22 overall charges excluding old circuits from parallel upgrades, terminations, etc, the charge to FedEx is USD 289,989 9 May - Impacts on actuals added basis invoices for submitted by both vendors. 27/2 Leadership Attention: Flagged for leadership attention as these as pending approvals for over 2 weeks. 22/2 On Track: Aligned with APAC team and confirmed that SDWAN is not part of this initiative. Instead, professional services have been added to the deal to facilitate SDWAN in the event the team wish to move to this later. Confirmed Verizon costs are still being paid for in region until end of FY23 which impacts the BC. The team are working on updates to the BC to reflect this change. L5 dates are likely to move out until Dec 23 to account for this. 13/2 All actions have been completed to sign the contract and milestones have been updated accordingly. | K: L5 | Completed | L5 | 2022-10-17 | 2023-06-30
Business Only Initiative: MPS Canon/Ricoh Fleet Optimization & Contract Cons | 3063 | 8977 | Business Only Initiative | IT - ITAM | Data and Tech | Steffani Fondrk, Laura Bullion | On Track | 4/17/2025 - FY25 Rebaseline complete Reduction of expired lease, zero and low utilization devices has been occurring and ongoing at Corporate locations. Aligning with Real Estate & Facilities on Operational site contacts and co-location/closures to begin coordinating assessments. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-07-18 | 2026-12-31
Business Only Initiative: McAfee- ELA Assessment | 4016 | 9023 | Business Only Initiative | IT - ITAM | Data and Tech | Nicholas Shansky, Matthew Stratton | On Track | Dates updated to reflect a delay on McAfee's side. L4 shouldn't be affected but some of our milestone dates have been extended rebaselined to FY25 as of 3/31/25 | K: L5 | Active | L5 | 2023-01-18 | 2023-09-29
Business Only Initiative: IVR/VA - Nuance Application Usage and ProFee Spend | 16466 | 9056 | Business Only Initiative | IT - ITAM | Data and Tech | Matthew Brooks, Gina Maiden, David Laundre, Bobby Intharaksa, Pradip Patel | On Track | On track to meet FY24 spend reduction goals. FY25 - Re-baselined | K: L5 | Active | TEMP L5 - Enter L5 | 2022-06-01 | 2024-06-28
Business Only Initiative: Gartner Subscription Reduction | 36234 | 9112 | Business Only Initiative | IT - ITAM | Data and Tech | Caleb Williams, Ann Lamia | On Track | CMW Rebaselined 4.17.2025 | K: L5 | Completed | L5 | 2024-05-31 | 2024-05-31
Business Only Initiative: TNT Azure Data Warehouse Migration to US Azure Dat | 68946 | 9135 | Business Only Initiative | IT - ITAM | Data and Tech | Amanda Nevins, Lori Marchese | On Track | 4-23-25 FY25 - Rebaselined May 2028 exit rate $0 no incremental change between FY26-28 | K: L5 | Completed | L5 | 2024-01-08 | 2024-05-31
Business w/ Tech Initiative: BI Consol - SAS - EU TNT Mainframe | 49133 | 9137 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | James Bullock, Joanna Barnas, Lori Marchese | On Track | Alignment reviewed and local contract progressed in BAU | C: L1 | Active | TEMP L1 - Create L1 LBC | 2023-10-02 | 2025-01-06
Business Only Initiative: SaaS provider consolidation | 14834 | 9179 | Business Only Initiative | IT - ITAM | Data and Tech | Paula Pearson, Melissa Sedlak | On Track | 3/24/2025 - FY25 rebaseline complete | I: L4 | Active | TEMP L4 - Enter L4 | 2023-05-01 | 2024-07-26
Business Only Initiative: FXG HR and BDS SaaS Rationalization | 16437 | 9271 | Business Only Initiative | IT - ITAM | Data and Tech | Katherine Altieri, Bill Stanek, Bobby Intharaksa | On Track | 4/24/25 - FY25 rebaseline complete On track | K: L5 | Completed | L5 | 2023-02-15 | 2024-07-31
Business Only Initiative: Complete Enterprise Atlantis Launch | 16450 | 9273 | Business Only Initiative | IT - ITAM | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | 4/29/25 FY25 rebaseline complete Although green light has not been provided, effort continues to move forward and Finance has approved funding resource for post-launch. Agreements are in motion to execute for June, the project is on plan to complete for June to allow reduction in resources as committed, and business is aware of planned reduction in run rate from FY22 levels. Atlantis is replacement for CASH, TMS and SMS, (Legacy systems). Respective legacy applications would all need to upgrade to Condor Mins Backend and Frontend components for all would have to be updated. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-03-15 | 2023-09-15
Business Only Initiative: Retirement of WalkMe from Sales Platforms | 16452 | 9276 | Business Only Initiative | IT - ITAM | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | 3/24/25 FY25 re-baseline complete Contract has been allowed to expire with no renewal, and Money Step milestone has been marked as Complete. Pending Greenlight approval in order to capture DRIVE cost reduction. 5/24/23 update - no change, still pending greenlight but money step is complete. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-03-01 | 2023-05-31
Business Only Initiative: Renegotiation of SalesForce (HVS line item) | 16455 | 9278 | Business Only Initiative | IT - ITAM | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | 3/24/25 FY25 re-baseline complete Even thought Greenlight is still pending, the money step has already been achieved and contract re-negotiated. Business cost center owner is fully aware of the committed reduction from FY22 run rate. | K: L5 | Completed | L5 | 2022-09-15 | 2022-09-15
Business Only Initiative: Replacement of Everstring with Zoominfo | 16457 | 9280 | Business Only Initiative | IT - ITAM | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | 3/24/25 FY25 re-baseline complete Pending Greenlight status, but efforts have proceeded and contract renegotiations have completed and executed. Money step has already been achieved and will be evident in FY23 invoicing. | K: L5 | Completed | L5 | 2023-03-31 | 2023-03-31
Business Only Initiative: Global Tableau License Rationalization | 16460 | 9281 | Business Only Initiative | IT - ITAM | Data and Tech | Kudzai Tunduwani, Rebecca Jones | On Track | 4/1/25 FY25 rebaseline complete L4 date has been shifted multiple times due to delay in engaging user groups for migration to Enterprise tool, and away from Tableau. Scheduling, availability, and resourcing issues, should be resolved as of end of March to allow a refocus on completing this intiative. Work is underway, and each renewal is being reviewed to determine options to reduce license purchases to achieve targeted FY24 Cost Reductions in run rate. 5/24/23 - Efforts to review each renewal continue, on track to reduce to $100K in FY24. Final money step is end of FY24 to show the enterprise reduction in spend (spans ~30 unique contracts). 6/21/23 - Reviewed matrix with strategy planning advisor and strategy with legal counsel. Engagement with Premier Customer Care APAC, AOD & System Form Finance, and Content & Demand Generation departments on upcoming contract renewals ongoing. Discovery in process for additional POs that are on track to become contracts to reduce usage and engagement with active user groups to plan for reduction of use to 0. Cost may be affected by ongoing conversations with SF. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-03-15 | 2024-12-20
Business Only Initiative: Contract negotiation - Server Migration from ESUs | 16560 | 9282 | Business Only Initiative | IT - ITAM | Data and Tech | James Lawson, Bobby Intharaksa | On Track | Change #1:Revised the Impacts / financials FY24 forecast to reflect ~$800k cost (Azure credits) increase Dec. 2023 to May 2024. Change #2: Revise Money Step end date from Dec. 9, 2023 to May 31, 2024, to represent work & time to decommission, upgrade, migrate, or harden from Win. Svr. 2012. Adding IO. FY25 - Re-baselined | I: L4 | Active | TEMP L4 - Enter L4 | 2022-08-01 | 2025-03-28
Business Only Initiative: Contract management and negotiation - Oracle | 16562 | 9283 | Business Only Initiative | IT - ITAM | Data and Tech | Michael J. DiCriscio, Missy McGuire, Bobby Intharaksa | On Track | 2/3/2026 - added Michael DiCriscio as the new Primary IO. 10/24 - Dalton Schultz - Per IO Missy McGuire,"Recieved message from Philip Rencher on the Milestone #20923- I believe this decision will go to late October or even November. I'm not sure what Frank and Adam will decide. We have multiple databases where the apps won't be off of older Oracle versions by the end of the calendar year. It will come down to what level of risk acceptance they determine." While there is not yet any leakage identified given the renewal is not until January, we are delaying L4 / Money Step completion to 11/13 in alignment with this delay as we await confirmation. Once we have recieved confimation from Philip, we will escalate any risks to savings and reassess the need for reforecasting going forward. 3/25/2024 - B. Blevins: Worked with M. McGuire (Initiative Owner) to revise actuals for Jun-2023 through Feb-2024 and forecast through FY27. Change Request CR00063 approved by ITAM pod leadership on March 22, 2024. Please see 'Attachments' with copy of Oracle CR00063 (filename: 20240322 ITAM Pod Leads - CRs for review 1 - Oracle) and revised actuals & forecast numbers (filename: CR00063-Oracle-16562-DRIVE Estimates). FY - Rebaseline | G: L3 | Active | L3 Feedback Requested | 2023-01-02 | 2026-07-01
Business Only Initiative: Contract management and negotiation - IBM | 16563 | 9284 | Business Only Initiative | IT - ITAM | Data and Tech | Monika Siefring, Bobby Intharaksa | On Track | 3/27/2025 FY25 Rebaseline complete. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-07-01 | 2025-03-31
Business Only Initiative: Contract Management and Negotiation - Salesforce | 16565 | 9286 | Business Only Initiative | IT - ITAM | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | 3/24/25 FY25 re-baseline complete The project team is reviewing contract documentation related to the Salesforce Data Cloud and Marketing Cloud engagements. We are targeting completion of an updated Salesforce ELA by or before 2/29/24 COE collecting/confirming the available license count as input to our negotiations. Data collection is underway to assess impact upon enterprise spend plan for Salesforce. The review relates to Wave ID 2441 for Sales Technology. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-02-01 | 2024-02-29
Business Only Initiative: Contract management and negotiation - VMware | 16571 | 9287 | Business Only Initiative | IT - ITAM | Data and Tech | Vivian Hodges, Bobby Intharaksa | On Track | 4/3/2025 - FY25 Re-baseline complete 4/11/2024 - B. Blevins: On 04/11/2024, the ITAM pod leadership team approved the re-forecast of initiative 16571. The reason for the re-forecast is to realize a reduction in savings. Savings are anticipated to be reduced by ~$960k per annum, driven by re-classification of savings as pro fees. The Finance rolling forecast effort indicates a discrepancy between Wave and the Financial forecast. Therefore, Wave is being updated to reconcile to the rolling forecast & capture part of savings under pro fees. Please see attached change request (CR) (filename: 20240411 ITAM Weekly Pod Leads Meeting vF.pptx) and approval email (Re_ DRIVE_ Weekly ITAM Pod Lead Meeting 20240411.pdf). Additionally, the revised forecast is included in the attached filename: 16571 DRIVE Financial Inputs L3 VMware 040824 PF fix only.xlsx. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-04-04 | 2024-05-24
Business Only Initiative: Contract management and negotiation - UKG | 16582 | 9289 | Business Only Initiative | IT - ITAM | Data and Tech | Christy Koch, Kristy Mitchell | On Track | 9/19/25:Continuing architecture discussions to finalize conceptual architecture. 9/12/25: Continuing architecture discussions to finalize conceptual architecture. 9/5/25: Working through architecture discussions with all affected ARTs 8/28/25: Global framework sessions wrapping up 6/2/25: Weekly virtual sessions scheduled to continue global framework 5/19/25: Future global framework meetings to be scheduled 5/2/25: FY25 rebaselined 4/14/25:Global framework to start April 28th 4/7/25: Global framework to start April 28th 3/31/25: On March 27, 2025 we gained email approval from Adam Smith and Jeff Hurlbut to add the costs for the initial international licenses to the initiative. Costs for those will begin in April 2026 3/24/25: Global Framework kickoff scheduled for late April. 3/17/25: Global Framework kickoff scheduled for late April. 3/10/25: Global Framework kickoff scheduled for late April. 3/3/25: SOW to be signed any day. Contract expected to be excecuted by 11/8 11/11/24: Contract to be executed by legal 11/22: contract to be executed 12/16: Waiting for child initiative to be greenlit and have enterprise architecture reviewed in order for contract to be signed. 12/23: same update as 12/16 1/6/25: same update as 12/16 1/13/25: child moved to L3 1/20/25: working on paperwork for child to move through L3 1/27/25: hoping to understand SOW status for child 2/3/25: SOW for child is with IT for updates/signatures 2/10/25: SOW for child is with IT for updates/signatures 2/17/25: SOW for child is with IT for updates/signatures. Paperwork was sent to be routed through Encore 2/24/25: SOW for child is routing in Encore. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-05-04 | 2027-03-31
Business Only Initiative: Increase Public Cloud Reservations/Commit Discount | 16698 | 9295 | Business Only Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin, Caitie Adams | On Track | 7/16/25 - added additional IO Caitie Adams | I: L4 | Active | TEMP L4 - Enter L4 | 2023-02-07 | 2024-09-17
Business Only Initiative: Replace Kenna with ServiceNow for Vulnerability Ma | 16710 | 9299 | Business Only Initiative | IT - ITAM | Data and Tech | Paula Pearson, Daren Harrell | On Track |  | K: L5 | Completed | L5 | 2022-11-01 | 2023-12-05
Business Only Initiative: Cloud Services - resources move to nearshore locat | 20969 | 9462 | Business Only Initiative | IT - ITAM | Data and Tech | Joanna Barnas, Heather Radics | On Track | 03/24/2025 - FY25 resabeline completed Contract with supplier was signed in December 2022. The initiative requires Actuals updates that will be added after L3 approval. | K: L5 | Completed | L5 | 2022-10-03 | 2023-03-31
Business Only Initiative: IT Software Asset Management Global Practice | 94142 | 9480 | Business Only Initiative | IT - ITAM | Data and Tech | Dalton Schultz, Linda Curtis, Bobby Intharaksa, Swathi Koneru | On Track | 04/29/2025 - FY25 rebaseline complete. 4/29/25/Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review | G: L3 | Active | TEMP L3 - Enter L3 | 2024-10-15 | 2026-10-30
Business Only Initiative: IT Hardware Asset Management Global Practice | 94143 | 9484 | Business Only Initiative | IT - ITAM | Data and Tech | Frank Moore, Ryan Walsh, Russ Shenouda | On Track | 3/31/2025 - Fy2025 Rebaseline Complete Replacing Kenny Skubisz with Ryan Walsh | G: L3 | Active | TEMP L3 - Enter L3 | 2024-11-12 | 2026-10-30
Business w/ Tech Initiative: In Stock Asset Optimization | 88548 | 9487 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Ryan Walsh, Frank Moore | On Track | Dependent on standing up 9484 - 94143 - IT Hardware Asset Management Global Practice | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Establish Global Regional Stockrooms For IT Hardwa | 88549 | 9488 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Frank Moore, Ryan Walsh | On Track | Dependent on standing up 9484 - 94143 - IT Hardware Asset Management Global Practice. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Azure Reservations & Spot VM Purchasing |  | 85817 | Business Only Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin, Caitie Adams | On Track | 7/16/25 - added IO owner Caitie Adams | I: L4 | Active | L4 | 2024-10-24 | 2026-01-30
Business Only Initiative: Enterprise FinOps as a Practice |  | 85910 | Business Only Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin, Caitie Adams | On Track | 7/16/29 - Added additional IO Caitie Adams | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-13 | 2025-09-15
Business w/ Tech Initiative: Dataworks Azure Usage Optimization |  | 87973 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin | On Track | Azure rightsizing work should be tracked by teams that implement those optimizations | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Azure Usage Optimization |  | 88003 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | David Moore, Holly Chernushin | On Track | Azure rightsizing work should be tracked by teams that implement those optimizations | C: L1 | Cancelled | L1
Business Only Initiative: Software Asset Mgmt. - ELP / ILP recommendations |  | 88634 | Business Only Initiative | IT - ITAM | Data and Tech | Linda Curtis, Dalton Schultz | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Svc. Now SamPro - Utilise Spend Detect. in SamPro |  | 88637 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Linda Curtis | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: SW Surge-Comm FY25 Savings $30M - MikeK - P2NonMTS |  | 91984 | Business Only Initiative | IT - ITAM | Data and Tech | Pamela S. Graves, Hemant Arora, Arika Payne | On Track | 3/24/2025 - FY25 re-baseline complete | I: L4 | Active | TEMP L4 - Enter L4 | 2025-09-15 | 2025-09-15
Business Only Initiative: SW Surge- Platforms FY25 Savings |  | 91987 | Business Only Initiative | IT - ITAM | Data and Tech | Jennifer Hood | On Track | 4/21/25: FY25 rebaseline complete. Stop work efforts on track. | K: L5 | Active | L5 Feedback Requested | 2024-10-01 | 2024-10-01
Business Only Initiative: OMNI - Reduce vendor cost for PUD Transportation |  | 104246 | Business Only Initiative | IT - ITAM | Data and Tech | Daina T. Dalton | On Track | This project is on track. We will launch the new platform in July and our current vendor will be termed as of August 1st. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Salesforce SaaS Integrations |  | 113542 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Samuel Ware, Kyle Shanks | On Track | We have already submitted demand to the Soul train Art , we also have had technical conversation on what would it take to implement and the amout of work | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: WTC and EDCW Block Storage Array Decom Part 2 | 73049 | 7729 | Business Only Initiative | IT - ITAM | Data and Tech | Patricia Frizzell, JD Desmarius, Shawn Keys | On Track | 3/31 Re-baselined with FY26 - FY28 at $0 Decommissions on hold during peak, Additionally, Due to recent strategic decisions to change our vendor support service model from HCL to Accenture. The team is reviewing onboarding and revised timelines for storage data erasure. Original initiative 59488 all actions completed, currently at full run-rate value. Pending additional analysis review - to establish Initiative #73049. Decommissioning on hold during RED Change Level 3 status per FEC leadership direction as of 8/5/24 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Extend Colo Server LCM from 5 to 7-year cycle | 14909 | 9182 | Business Only Initiative | IT - ITAM | Data and Tech | Patricia Frizzell, Shawn Keys, JD Desmarius | On Track | 11/4/25 Dell noified FX extended support for the COLO servers is no longer available please cancel 3/31 Starting re-baselined to FY25 03/31/25 Initiative reverted to L2 - Approved in ITAM Pod leads meeting on 3/15/2024: This initiative needs to be returned to L2 for now and resubmitted for L3 approval (targeting June 2024) with updated business case to include depreciation and change baseline from FY22 to FY24 (steady-state run rate), which will result in a positive net recurring benefit of $4.2M. Pat Frizzell and Shawn Keys to make these updates in June 2024. | E: L2 | Cancelled | L2 Feedback Requested | 2023-01-16 | 2027-05-31
Business w/ Tech Initiative: Business w/ Tech Initiative: One FedEx Cartage App |  | 89463 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Heather Dornan, Vicki L. Ralish | On Track | Working through checklist to move through lifecycle to L2 | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval
Business Only Initiative: FY26 YOY Reductions - Network Plan Linehaul |  | 161373 | Business Only Initiative | IT - ITAM | Data and Tech | Ryan Nolette | On Track | 10/27/2025 - Updated KPI to reflect contracts that are stopped during this Initiative and added milestones. Added line notes for KPI to indicate the number of contracts Changing the IO to Ryan | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-15 | 2027-12-30
Business w/ Tech Initiative: FedEx Supply Chain - Azure .Gov Environment |  | 161454 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Mark A Ausse | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: FY26 - Global Field IT Cost Saving |  | 161831 | Business Only Initiative | IT - ITAM | Data and Tech | Chee-Pin Yong, Marie Mangin | On Track | Will start filling L1 | I: L4 | Active | L4 Feedback Requested | 2025-12-29 | 2026-07-31
Business Only Initiative: EMR - Strategic Enterprise IT Contracts FY26 |  | 161836 | Business Only Initiative | IT - ITAM | Data and Tech | Amy Pickens | On Track | 4/6/26: Updated actuals for June through March. February was short $27K due to month delay in disconnects for 3 circuits, now captured in March. March is short $15K in savings due to delay in 1 circuit disconnects. Remaining on track. All savings identified so far are tied to contract renewals that are completed. Continuing to work with Finance to finalize how to capture savings. | G: L3 | Active | L3 | 2025-06-02 | 2026-08-31
Business w/ Tech Initiative: Onboarding ONE PICKUP from PCF to Azure(FCP) |  | 162242 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Krishna Kamal Katarla | On Track | <Enter Status Rationale> | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: FY26DDCT Savings - A. Norris - DriveDayBatch1 |  | 164446 | Business Only Initiative | IT - ITAM | Data and Tech | Sarah Goodman, John D. Wade | On Track | On track | I: L4 | Active | TEMP L4 - Enter L4 | 2027-07-30 | 2027-07-30
Business Only Initiative: FY26DDCT Savings- Bhanu/Norris - DriveDayBatch1 |  | 164449 | Business Only Initiative | IT - ITAM | Data and Tech | Sarah Goodman, John D. Wade | On Track | On track. | I: L4 | Active | TEMP L4 - Enter L4 | 2027-10-29 | 2027-10-29
Business Only Initiative: FY26 Microsoft ECIF Credits |  | 166068 | Business Only Initiative | IT - ITAM | Data and Tech | Amy Pickens | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: MARS Azure Cost Optimization |  | 167899 | Business w/ Tech Initiative | IT - ITAM | Data and Tech | Manoj P. Badgujar, Jeetendra Kumar Pandey | On Track | Currently, this initiative is not on priority. It will be revisited by end of March 2026 | E: L2 | On Hold | L2 Feedback Requested
Business Only Initiative: Reduce Non-MTS Spend for ES Portfolio | 89536 | 6929 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Cindy Wallace, Karen Farrell-Shikuku | On Track | 5/23/25 - FY25 re-baseline had to be recalculated based on updated actuals received on 5/15 with assistance from Jamie Heller. 5/15/25 - Actuals entered for Nov-May with validatation from Jennifer Hood & Justin Manis. 5/6/25 - FY25 re-baselined with Jamie Heller. 4/22 Per Heather Sprague, changed External Spend Category to "IT" to align with Sourcing support. 4/21 Reconcilliation expected to complete by 4/25. Once completed, should be ready to advance to L4. 4/17 Pending validation of contract reductions by Technology Platforms & Infra. 4/2/25 updated Money Step from 4/1 to 4/30 due to resources being OOO to complete validation on reduction on ACN contracts. 3/31/25 Pending validation of contract savings by Technology Platforms & Infrastructure. Initiative submitted to L3 after receiving valuation guidance from the ESPM team. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-03-31 | 2025-05-30
Business Only Initiative: Inferno spend reduction | 60675 | 7032 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Caleb Williams, Jonathan Hardin | On Track | Contract owner will not renew contract in February. No action will need to occur prior to February. 3/15/2024 CW took over for Kristy Johnston as IO as contract moved. Upon reviewing the init, the 26k in February was a misinput of a full years value before splitting it out into June when the value accrues. This has been labeled 0 for an actual accordingly. | K: L5 | Completed | L5 | 2024-02-29 | 2024-02-29
Business Only Initiative: Eviden - Vendor Rate Reduction Opportunity | 62394 | 7308 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Grace Chiocco, Linda Epps | On Track | On track for a 11/14 Surge submission and awaiting Eviden Executive approvals. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-02-15 | 2024-05-31
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - Customer Tech | 93543 | 7446 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Justin Cagney, Hemant Arora | On Track | 3/31/25: rebaselined to FY25 Ready for SL2 | K: L5 | Completed | L5 | 2024-08-15 | 2024-12-16
Business Only Initiative: Portfolio Surge - Prof Fees/OSC Reductions: Karen | 92316 | 7653 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Mary Ann Campanile, Tammy Castine | On Track | 5/23/25 - On track On track 3/31/25 - rebaselined to FY25 | K: L5 | Active | L5 Feedback Requested | 2025-05-30 | 2025-05-30
Business Only Initiative: SCO Portfolio Surge - FTN - Pro Fees | 93067 | 7731 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Steve Scarbrough, Patty Higginson | On Track | 4/21/25 Updated with FY25 baselined amounts and FY25 Actuals for ProFees spend 5/15/25 - Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review 6/3/25 - updated missing actuals | K: L5 | Active | L5 Feedback Requested | 2025-06-30 | 2025-06-30
Business Only Initiative: Portfolio Surge: Air Ops & Clearance - Non-MTS Cos | 92146 | 7734 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Steve Scarbrough, Patty Higginson | On Track | 3/25/25: Re-baselined to FY25 | K: L5 | Active | TEMP L5 - Enter L5 | 2025-05-30 | 2025-05-30
Business Only Initiative: OW External Labor/Consulting | 16446 | 8059 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Tiffany Holland, Bradley Richardson | On Track | 5/6: Updated actuals 2025/04/29/Document Feedback Provided/Esther Kerns/ D&T Domain QA Expert Review 2/26: Administrative only, Working to update baseline and financials to match the updated business case by moving back to L1 8/20: Submitted to return to L2 to reset the baseline. Changed the weekly status to On Hold until this is complete. | K: L5 | Active | L5 Feedback Requested | 2024-06-03 | 2025-06-13
Business Only Initiative: Supply Chain Ops - Portfolio Surge - Profees Reduc | 92130 | 8063 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Denise Sottile, Timothy Comino | On Track | 3/31 - Rebaselined using FY25 10/8/2024 - Updated actuals June - September. Recognized all values in this month from initiative and re-forecasted later months as zero. Error made in planning in average across FY25. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-30 | 2024-11-29
Business Only Initiative: Supply Chain Ops - Portfolio Surge - Pro Fees Redu | 93030 | 8065 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Denise Sottile, Timothy Comino | On Track | 3/31/2025 - Rebaselined using FY25 0/8/2024 - Updated actuals June - September. Recognized all values in this month from initiative and re-forecasted later months as zero. Error made in planning in average across FY25. | K: L5 | Completed | L5 | 2024-09-02 | 2025-05-30
Business Only Initiative: Supply Chain Ops -Portfolio Surge - Profees Reduct | 92647 | 8066 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rachael Muldrow, Timothy Comino | On Track | 3.21.25 FY25 re-baseline complete This initiative is ready to progress to L3 10.3.24: Completed actuals in Impacts; updated estimated L5 date in Timeline; marked Milestone Money Step to Complete This initiative is ready to be moved to L4 Gate | K: L5 | Completed | L5 | 2023-03-01 | 2027-01-29
Business Only Initiative: Supply Chain Ops - Portfolio Surge - Profees Reduc | 93283 | 8068 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rachael Muldrow, Timothy Comino | On Track | 3.21.25 FY25 re-baseline complete Initiative ready to progress to L3 10.2.24: Put in actuals for Jun-Oct; updated L5 date to Jan. 4, 2025; submitting initiative to L4 | K: L5 | Completed | L5 | 2024-05-31 | 2025-05-01
Business Only Initiative: Supply Chain Ops - Portfolio Surge - Profees Reduc | 92918 | 8069 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rikkilynn Brown, Timothy Comino | On Track | 3/27/25 - rebaseline for FY25 | K: L5 | Completed | L5 | 2024-11-29 | 2025-01-01
Business Only Initiative: Supply Chain Ops - Portfolio Surge - Profees Reduc | 93230 | 8070 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rikkilynn Brown, Timothy Comino | On Track | 3/27/25 - Rebaselined to FY25. Just recently reduced the the savings from 140K to 100K. Updated all necessary numbers and paperwork. recently approved to L3. Submitted most recent actuals as of 10/1. | K: L5 | Completed | L5 | 2024-05-31 | 2024-05-31
Business Only Initiative: Portfolio Surge - SCO Pro Fees Reduction - IT Solu | 92075 | 8074 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Ryan Nolette, Timothy Comino | On Track | Re-Baselined 4/11/25 - CAI contract will be split between 2 new Directors. Pending confirmation of move but not incremental value expected. | K: L5 | Active | L5 Feedback Requested | 2023-06-01 | 2025-05-30
Business Only Initiative: PF Surge - FSC Pro Fees (W92690 / P8348) | 92690 | 8348 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Patty Higginson | On Track | FY25 Re-baselined | I: L4 | Active | TEMP L4 - Enter L4 | 2024-10-31 | 2024-10-31
Business Only Initiative: FSC - External Labor (W17287 / P8432) | 17287 | 8432 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Patty Higginson | On Track | FY25 Re-baselined | K: L5 | Completed | L5 | 2023-05-31 | 2023-05-31
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - International | 95841 | 9115 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Ioannis Zafeiropoulos, Hemant Arora, Ben Benaziz | On Track | 3/31/25: Rebaselined to FY25 Completing requirements to move to L2 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-03-17
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - Lever 1 - Busi | 93434 | 9122 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Hemant Arora, Ann Ocampo | On Track | Budget reduction has been noted by FInance team - Jenny Shah | K: L5 | Completed | L5
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - Cust Eng | 96887 | 9124 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Hemant Arora | On Track | 3/26/25 - Rebaselined to FY25 Ready for SL2 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-05-30 | 2025-05-30
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - Dataworks - Op | 96890 | 9126 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Hemant Arora | On Track | 3/27/25: Rebaselined to FY25 Ready for SL3 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-05-30 | 2025-05-30
Business Only Initiative: Cook Systems - contractor reduction | 19447 | 9425 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | Contract has been allowed to expire and not renewed, so Money Step has been achieved and noted as Complete. Pending Greenlight approval in order to capture impact to DRIVE cost reductions. | K: L5 | Completed | L5 | 2023-05-31 | 2023-05-31
Business Only Initiative: Allegis Contract | 19464 | 9427 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rebecca Jones, Kudzai Tunduwani | On Track | Contract has been allowed to expire - the Money Step has been marked as Completed but is pending greenlight approval in order to note the reduction. | K: L5 | Completed | L5 | 2023-05-31 | 2023-05-31
Business Only Initiative: IT Office Facility Closure - Lakeland, FL | 59491 | 9530 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Caleb Williams, Ann Lamia | On Track | 11/20/23 - Explanation for October Actuals - One time expense ($37K) for work incurred in FY23. Payment was submitted but rejected and invoice had to be re-submitted in September 2023 (FY24), thus incurring a one-time cost in FY24. This is an anomaly, and no further expenses for this location should be expected to be incurred going forward. 12/12/23 - Confirmation of Money Step Completion. Proof of sale of the location has been added to the Attachments file in the form of an email confirming the sale. Aside from the one time expense noted above in the 11/20/23 update, no additional costs associated with this facility are expected. | K: L5 | Completed | L5 | 2023-05-01 | 2023-06-01
Business Only Initiative: DRIVE - FY25 Cost Savings of $30M - Core Capabilit | 95832 | 9534 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Hemant Arora, Justin Shaw | On Track | 3/31/25: rebaselined to FY25 Assigning Primary IO to Hemant Arora | I: L4 | Active | TEMP L4 - Enter L4 | 2025-05-30 | 2025-05-30
Business Only Initiative: Workday Learning Implementation Cost Reduction |  | 85906 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Elizabeth E. Canale | On Track | Cancelling this initiative that wa created in former WAVE system and never used. All work, financial reporting and history for Workday Learning implemenation are being reported on #9288 - Contract management and negotiation - Workday that is currently in L3. | C: L1 | Cancelled | L1
Business Only Initiative: UMRF Reduction - Service Desk Savings |  | 86406 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Nicholas (Nick) Wolf , Ryan D'Souza | On Track | Impact on field operation activities and Impact on back office procedures fields were not editable Updated to upload the initial financial base analysis case for the savings confirmed with finance on 4.8.2025. - 4.18.2025 Rebaselined to FY25 - 4.8.2025 this is Service Desk Savings from completed work that was transitioned to HCL and eventually Accenture, HCL to Accenture savings was not captured as part of the Prometheus baseline. Since savings was not captured in Accenture, this initiative is entered to capture the savings. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2024-06-03
Business Only Initiative: SW Surge-Comm FY25 Savings $30M - AnnH - P2 NonMTS |  | 91884 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Justin Cagney, Hemant Arora | On Track | 3/31/25: Rebaselined to FY25 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-27 | 2025-06-27
Business Only Initiative: SWSurge Comm - FY25 Saving $30M - Taner - Ph2 MTS |  | 91887 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Ioannis Zafeiropoulos, Hemant Arora, Monica Coletta | On Track | 3/31/25: Rebaselined to FY25 Money step completed - January 2025 | K: L5 | Active | TEMP L5 - Enter L5 | 2025-01-15 | 2025-01-15
Business Only Initiative: SWSurge CommFY25 Savings $30M - TanerA - P2 NonMTS |  | 91890 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Ioannis Zafeiropoulos, Hemant Arora | On Track | 3/31/25: rebaselined to FY25 Contracts have ended | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-31 | 2024-10-31
Business Only Initiative: uDS transference to EU IT |  | 90615 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Thomas Chumney | On Track | 14-Jan: Confirmed PMO aspects of LBC with Dave Egan. Met with Rob D (Fin) to go through the cost savings: Dev contract: We will show the actual values spent in 2024 for dev vs. the expected costs of the new dev team (although he assumes we won't be able to use these due to loss of capitalization). Need help in finding what is the full cost for an ACC employee. Maintenance / Rollout contracts: We will also show the Maintenance/Rollout actuals and obtain a projection of Accenture costs for a similar amount of personnel for those 2 contracts. 20-Jan: Still gathering financials from ACC team for hiring costs and full cost for ACC employee. 28-Jan: All estimated costs and benefits have been populated and reviewed with Rob Davidson twice. Ready to submit to next gate. 3-Feb: Rob Davidson has filled in the checklist for moving to next gate. Ready for next gate. 11-Feb: Last week submitted to L2, and was rejected as the request was Business w/Tech without any Portfolio impacts. I have spoken with the EPM BJ McKee and made adjustments that should allow it to continue to L2. This initiative is still listed as Business w/Tech despite not have a significant architectural change for FedEx (definition of Business w/Tech). As this initiative is a 'weird one', I will stay in close contact with the EPM to prevent any further delays. 18-Feb: Still delayed in approval. US Team for SCO has proposed a Triage meeting to further discuss, no ETA. Attendees expected to include: Jimmy James, Pat Sculli, Brandon Slone, Rajan Thakur, Jennifer Choate, Sandy Adams, Scott Brumbelow, David Egan, Elbert Loubser, Shrestha Rath, Thierry Yimefak Tiwa. 20-Feb: Advised to upload a new ppt that shows we do not need architecture review and only the SCO Portfolio is impacted as we add 2 teams to the EU Sort ART. 25-Feb: Now awaiting Finance MD approval to go to L2. 4-Mar: For intake to SCO Portfolio, next steps are 6-Mar (Local Demand Review) and 18-Mar (Council). 11--Mar: Presented the initiative at the Sort Local Review, and now APPROVED to go to the Coucil next week (for awareness only). 13-Mar: Went through financials with Rob Davidson for L3 submission. 18-Mar: Awaiting L3 financial review and worksheet upload from Rob Davidson in order to submit for L3. 25-Mar: Rob is working on the financial support documents. After initial meetings with Gaurav from VI Support team and Accenture, it is has been recommended for the rollout team to have 2 members located in Europe (as is the case with vendor rollout team now). Requested Marin Troike from SPMO (Strategic Partner Management Organization) to provide new estimates for the Accenture team, so we don't start in a place of 'value leakage'. 8-Apr: Still awaiting financial checklist from Rob to submit to L3. 8-May: Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review FYI, after changing from Biz w/Tech to Biz Only: •EAI #: Not editable still - no longer applicable as Biz Only •Baseline Value: Not editable still, but should be $1,739,136 22-May: Updated actuals, only applicable for T&E at this time 6-Nov: Dev and Support will be fully transitioned by 31-Dec-2025. The commissioning part was not able to complete KT and will extend into CY26 (31-May-2026). As there are no new Hub site commissionings happening this year now (Taipei/Canton delayed), we requested Vanderlande to extend into next year with a skeleton crew of commissioning engineers. This will give the opportunity to the new team to "View, then Do" a new site setup in a large complex Hub environment. Financials were updated. I also discovered that Accenture is undercharging FedEx by 50% for the new support team. SPMO is investigating this now. 5-Dec: Sourcing team is still in process of extending the Vanderlande commissioning contract to May 2026 (2 more approvals remain in Encore). Have requested an update from Tammy Kirk on the Accenture team billing only including 1/2 of | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-14 | 2026-05-28
Business Only Initiative: Fraud Strategy & Solution Expansion |  | 130563 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Susan Roll, Natalie Wiley | On Track | On track to move through for onboarding to start in Q3FY26 | G: L3 | Active | L3 Feedback Requested | 2026-03-16 | 2026-08-07
Business Only Initiative: SPMO: DRIVE Savings Targets |  | 160709 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Nicholas (Nick) Wolf | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: FY26 Year over Year Savings - Airline Technology |  | 161604 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Steve Scarbrough | On Track | Forecast for 4 KPIs (4 contracts) show Year over Year savings compared to FY25 baseline | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2028-05-31
Business Only Initiative: FY26 Year over Year Kronos Reduction |  | 163381 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Denise Sottile | On Track | The YOY savings forecast is on track to achieve cost savings by May 31, 2026. | I: L4 | Active | L4 | 2025-12-25 | 2025-12-25
Business Only Initiative: FY26 YOY Reduction - Shipment |  | 163385 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Rikkilynn Brown | On Track | Forecast Reduction - there was no FY25 Baseline. Per Domain Finance who rejected initiative. | D: SL2 | Cancellation Request | Reject Initiative
Business Only Initiative: DRIVE Day Efficiency Lever |  | 164712 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Ashu Rawat, Judiny V. Moran | On Track | TBD | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: FEC Resource Conveyances |  | 165100 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Caleb Williams | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Forward Deployment Engineering Program Contract |  | 192805 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Lauren Krieger | On Track | On Track | G: L3 | Active | L3 | 2026-04-30 | 2026-10-28
Business Only Initiative: GCC in Navi Mumbai |  | 193093 | Business Only Initiative | IT - Workforce Strategy | Data and Tech | Lauren Krieger | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: TS-VL3-Data-FD-Enabler-Release2 |  | 106932 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ramachandran Krishnamoorthi | On Track | Due to recent org and portfolio updates. Also accenture contract has not been extended. | E: L2 | On Hold | L2 Feedback Requested | 2025-05-05 | 2025-06-30
Business w/ Tech Initiative: TS-VL3-Platform-POC-Infra DevX Data |  | 107208 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Eric Joyner | On Track | Moved to a Lifecycle Management item. | I: L4 | Cancellation Request | L4 | 2025-04-07 | 2025-10-06
Business w/ Tech Initiative: TS -VL2-SC-Retire-Wave1xxx |  | 107597 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brandy Mears, Hiral Patel, Ramyasine Boominathan | On Track | Re organized waves and will be entering a new initiative that aligns with the effort. Wave 1 will be already retired applications and require very different verbage and outcomes. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL2-Commercial App Retirement |  | 108247 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ryan Ridgway, CJ Ahuja, Arika Payne | On Track | On Track | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: TS-VL1-Resolve Issue or Inquiry |  | 108250 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | David Howell, Mark Gough, Robert I. Hitchens | On Track | initiative placed on hold until further decomp is available. | E: L2 | Cancelled | L2 - Enter Value Prop
Business w/ Tech Initiative: TS-VL1-Revenue Management |  | 108253 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Veeresh Jigajinni, Shahab Sadeghi Ghahroodi, Pankaj S. Vispute | On Track | On hold until further decomposition is available | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL1-Customer Order |  | 108257 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nicholas H. Matlock, Rajiv Subramaniam | On Track | Ontrack | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL1-CM-Ship Visibility-Build |  | 109393 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ramachandran Krishnamoorthi, Brandy Mears, Hiral Patel, Ramyasine Boominathan, Harsh Garg | On Track | The initiative has been cancelled with no clear roadmap or direction. Thus cancelling the request. | E: L2 | Cancelled | L2 | 2025-06-09 | 2025-09-29
Business w/ Tech Initiative: TS-VL1-CM-Ship Visibility-Consume |  | 109637 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Chad Girnus, Eric Joyner | On Track | New approach being taken.TS specific inits are no longer being sponsored | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL2-SC-Shipment- Con-Wave1 |  | 112954 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brandy Mears, Ramyasine Boominathan | On Track | Cancelling per Katie Doziers request no longer needed. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-Infra-TNT-LEGACY-DECOMM |  | 130263 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Venera Earley, Alex Moore, Anthony Morgan | On Track | TBC | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-Data requirements |  | 130268 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Arjan van den Broeck, Steve Miller, Amanda Nevins, Vincent J. Romeo | On Track | 98380 (EIW Deprecation) has been cancelled | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateODINDATA |  | 92469 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Michael Yatsco, John Robinson | On Track | Enterprise no longer migrating away from GCP. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateODINRetirements |  | 90974 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Amy Besserud | On Track | 10/8: Need architect review prior to L3 submission for Data & AI 8/5: Included architectual review documentation: GCP Odin Retirement - Surface Ops LH - Solution Plan On track per main initiative (98017) | E: L2 | Active | L2
Business w/ Tech Initiative: Facilitate FXO data through ATLAS and VDAP |  | 130277 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jeetendra Kumar Pandey | On Track | working on Drive | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateSurfaceEDD |  | 88631 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kim Listermann, Stephen Rose | On Track | May 2025 Update: Engaged with Dataworks GCP retirement project team. Sep 2025 Update: Submitted for prioritization boost to start architecture review and develop the migration plan. | E: L2 | Active | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-COM S&CDE CDP Migration |  | 130280 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Punitha Sekar, Sandy Whitten | On Track | This work will be covered under the Initiative # 88108 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-GSQA Data/App Migration |  | 130284 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Amadou Gaye, Amanda Nevins, Vincent J. Romeo | On Track | 06/36/2025 - Amanda EIW PO reached out to have the title updated. In order update the title, we submitted the below required values as zero. L1 Net Recurring Benefits ($, annualized)-P&L/Hard - 0 L1 Net Recurring Benefits ($, annualized)-Soft - 0 These values are not conclusive. We are still working on these as of date 06/26/2025 01/20/2026 - The deprecation of Enterprise Information Warehouse (EIW) has been canceled. Cancelling this as an enabler initiative under parent 98380. (A.G.) | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-Retail ecommerce Apps |  | 130291 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jeetendra Kumar Pandey, Amanda Nevins, Vincent J. Romeo, Sean Williams, Manoj P. Badgujar | On Track | 4th November 2025 - As instructed by Kelly Rowland, please update all EIW statuses to “On Hold” based on the email dated November 4, 2025. The initiative status has been changed from “Active” to “On Hold.” 23rd June 2025 - Behind schedule as May 2026 is EIW is retirment date and still we are at L1 | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-HR Tech-Safety |  | 130295 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Susan Henry, Amanda Nevins, Vincent J. Romeo | On Track | Instructed by EIW to Atlas Tech team per Kelly Rowland. Initiaitve Cancelled! | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-WAR App |  | 130300 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Padmaja Gharge, William F. Carruthers, Amanda Nevins, Vincent J. Romeo | On Track | Added Required by: TS-VL3-EIW Retirement Dependency and changed request type to "enabler". | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-AWS Azure Mig SR Cons Data |  | 130305 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | David Villavicencio | On Track | Decision was made to sunset ShopRunner and a migration from AWS will not be needed | C: L1 | Cancelled | L1
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-EDW App ID migration |  | 130310 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Charles M. Weinman, Sandy Whitten, Amanda Nevins, Vincent J. Romeo | On Track | 1/21/2026 - Cancellation rquest submitted to cancellation of EIW to Atlas migration. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL1-GAF-Innovation |  | 130454 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On hold due to VL1 being on hold. | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL1-Ideal Pickup and Delivery-Innovation |  | 130458 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On Track | E: L2 | On Hold | L2 & CCH
Business w/ Tech Initiative: TS-VL1-FDX Visibility & Sirius-Innovation |  | 130462 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On Track | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-Ground PLP MDW |  | 130467 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Marika Moore, Amanda Nevins, Vincent J. Romeo | On Track | EIW retirement has been cancelled | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-Sys Form Marketing App/Data |  | 130774 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Zachary M. Barker, Amanda Nevins, Vincent J. Romeo | On Track | EIW Deprecation Cancelled | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-COM-S&CDE-CRM App/Data Arch |  | 130782 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Sridevi Jampani, Aaron J. Krunszyinsky, Morgan A. Comeaux, Amanda Nevins, Vincent J. Romeo | On Track | 1/15/2026 - As per the latest guidelines cancelling the initiative 11/03 - As per the new guidelines changing the intiative to on hold 06/19/2025 - On Track Amanda EIW PO reached out to have the title updated. In order update the title, we submitted the below required values as zero. L1 Net Recurring Benefits ($, annualized)-P&L/Hard - 0 L1 Net Recurring Benefits ($, annualized)-Soft - 0 We are still working on these as of date 06/19/2025 | E: L2 | Cancelled | L2
Business w/ Tech Initiative: ATLAS Central Ingestion |  | 130789 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nicole Wilson | On Track | **9/24/2025** - After discussion, it was decided to cancel this request. Below are notes from the discussion Attendees: Sara Barnes, Athi Athinarayanan, Kelly Rowland, Jacob Kellogg, Jamie Heller, Kendal Greene •To avoid cost redundancy (double-counting), Strategy Seq. ID – 130789 (ATLAS Central Ingestion) will be cancelled. oThis initiative is already in DRIVE, just spread across several DRIVE initiatives •Cost resource will be tracked at the separate initiative levels oThe L2 costing calculator will be used to capture any high-level costing as it relates to the ATLAS Central ingestion resource funding *** History Status Below*** 9/15/25 - Discussion held with IO’s Amanda Nevins & Vincent Romeo on last week (9/12/25), and was agreed that Seq. ID# 130789 TS-VL3-DB-EIWMigration-ATLAS Central Ingestion should NOT be an enabler of Seq. ID# 98380 TS-VL3-DB-EIWMigration-EIW Retirement **Reason: **The scope of Seq. ID# 130789 not only pertains to the retirement of EIW, but also to provides ATLAS ingestion support to all area/domains and outlying analytic platforms (OAP) across the FedEx Enterprise. Information has been updated within this initiative. Seeking to rename the title to avoid confusion, and move foward to L2. 06/19 - Changed initiatiave name from "EIW to Atlas: ATLAS Ingestion" to "TS-VL3-EIW - ATLAS Central Ingestion" | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-CE Data Source Migration to |  | 130793 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Stephanie Vaughan, Amanda Nevins, Vincent J. Romeo | On Track | No update at this time. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-EIW - FDNA App/Data Migration to Atlas |  | 130796 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Sheldon Arbaugh | On Track | This is to combine, streamline, and reduce redundancy across the IT network 7.18.25 - Freight is separating from FEC so there will be no feed from Freight Data Warehouse to FEC and vice versa. Cancelling this request as it does not fall into the Freight Companies future. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-FSCApp/DatamigrationtoAtlas |  | 130799 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | John Oommen, Amanda Nevins, Vincent J. Romeo | On Track | 6/19 - Updated initiative title. Initiative just entering L1 6/24 - Modified "Brief demand description" 8/26 - Updating L1 LBC 11/6 - Asked to place request on HOLD while a decision on these requests is pending Jan 21, 2026 - EIW to ATLAS migration was canceled and hence the initiative also needs to be canceled. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-EIW - LAC-IBIS App/Data Migration to Atlas |  | 130802 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Paola Lemus, Sujith Narayanan, Thirumurugan Subramaniyan | On Track | 18JUN25 - Kickoff meeting, Attended weekly EIW deprecation calls. 20JUN25 - Feedback requested was provided.Regardding the benefits requested, this is an effort for analysis only. LAC-IBIS-Analytcis (EAI:886) is being used for 18 years, with 20+ different developers/contractors. Team has to do impact analysis to identify the different EDW tables used in IBIS and the corresponding business team. 24JUN25 - This request should be cancelled because this effort was only to perform an impact analysis of the EIW retirement in IBIS application. At this moment we don't need the involvement of EIW team and no other portfolios are impacted. After our analysis is completed, and based on the outcome we will submit a new request/initiative. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-TNT-FDX Packaging Validatio |  | 130805 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Sudeep Urmaliya, Remo Dey, Amanda Nevins, Vincent J. Romeo | On Track | 11/10/25 - Changing the status to "On Hold" as the timelines have moved to September 2027 06/19 - Title Updated EIW Deprecation is cancelled. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-ECAP App/Data Migration to |  | 130809 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nisha Singh, William Redmond, Bishwaraj Chaulagain (Raj), Amanda Nevins, Vincent J. Romeo | On Track | Leadership Message: Adam Smith Enterprise Vice President Enterprise Platforms & Technologies and Ali Zaidi Vice President Enterprise Architecture & IT Modernization "Officer & Director team and business partners, After an extensive analysis of our business and technology strategy, the previously announced deprecation of Enterprise Information Warehouse (EIW) has been canceled. We sincerely appreciate everyone who engaged with the EIW deprecation program, explored alternative solutions, or participated in Planview initiatives. What this means for you The Teradata Vantage-based EIW housed in Microsoft Azure will remain as the information warehouse at FedEx. Our focus now shifts to expanding integration with our partner platforms, applications, and teams. We are developing a roadmap that prioritizes seamless integration across data platforms to empower our data scientists, engineers, and analysts with simplified, secure data access.Actions & next steps •Planview initiative 98380 (EIW Deprecation) and all related project meetings are canceled. •If you own an enabler initiative under parent 98380, please cancel it in Planview immediately. •Look for future updates under the keyword EIW. For immediate support, reach out to oap_support@corp.ds.fedex.com. •Please attend an optional Q&A session for Jan. 20 from 10-11am CT. Click the button below to save this event to your calendar. " | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-GSP AppData Migration Atlas |  | 130812 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ragu Subbaian, Amanda Nevins, Vincent J. Romeo | On Track | 06/19/2025 - On Track Amanda EIW PO reached out to have the title updated. In order update the title, we submitted the below required values as zero. L1 Net Recurring Benefits ($, annualized)-P&L/Hard - 0 L1 Net Recurring Benefits ($, annualized)-Soft - 0 We are still working on these as of date 06/19/2025 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-Observability-Tools Modernization | 16734 | 9302 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Mark McAfee, Christopher Kellmeyer, Michael Horstmann, Larry Miller, Rachel D. Segura, Lijing Xu, Bobby Intharaksa | On Track | The actual financial journey is dependent upon the platform decided upon and we have recently gained leadership support to proceed with planning using the Dyantrace platform. We have recently conducted planning sessions with the vendor and Accenture - which has also been brought in for alignment. These working sessions were focused on obtaining the data needed to provide expected roadmap and finanacial numbers. Target is to be complete with such by end of March 2025. Early steps have been completed including migration of "default" monitoring policies off of OVO to alternate Splunk solution (zero incremental cost) which avoided April 2024 $1.9M license true-up; it also reduced HCL monitoring spend by $63k per month starting March 2024. This migration was executed/launched on Feb 7, 2024. | G: L3 | Active | TEMP L3 - Enter L3 | 2022-06-01 | 2028-08-21
Business w/ Tech Initiative: TS-VL3-DevX-FD-Enabler-Release2 |  | 131852 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Eric Joyner, Rachel D. Segura, Amanda Nevins | On Track | Moved to a lifecycle management item | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-Infra-FD-Enabler-Release2 |  | 131861 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Eric Joyner, Rachel D. Segura, Amanda Nevins | On Track | Transitioned to a Lifecycle Management item | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-PUX79/STAT79 Report to Atla |  | 132033 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Yan Pan, Amanda Nevins, Vincent J. Romeo | On Track | We propose to cancel the TS-VL3-DB-EIWMigration-PUX79/STAT79 Report to Atlas initiative, as it has become redundant. The TS-VL3-EIW to Atlas – GEIS multiple EAI Initiative already covers all EAI components owned by the GEIS team, including the PUX79/STAT79 Report, making a separate migration effort unnecessary. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-Security-PAM |  | 88193 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Steven N. Edwards | On Track | This project is currently on track, with a deadline of June 2026 to decommission the old Broadcom PAM product. | G: L3 | Active | L3 | 2025-06-30 | 2027-05-21
Business w/ Tech Initiative: TS-VL1-SC-Ship Visibility- Consume-POV |  | 132132 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brandy Mears, Harsh Garg, Karen A. Lucarelli, Ramyasine Boominathan | On Track | This is the initial entry of the Consume POV in order to tie it to the enabler | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL2-CM-Retire-Wave1 |  | 132138 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Joseph Cooper, William Redmond, Ryan Ridgway | On Track | There were no IT Cost Savings identified. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL2-SC-Retire-Wave2 |  | 136586 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ramyasine Boominathan, Brandy Mears, Karen A. Lucarelli | On Track | ==CANCELLED==As per DeAnn's request 10/06/2025 On Hold Reason: Per the application owner, this application doesn’t have any cost, as is purely managed by internal employee. For information, not development done on it, since at minimum 4 years. So last year, zero cost | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL2-SC-Retire-Wave1 |  | 136589 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ramyasine Boominathan, Brandy Mears, Karen A. Lucarelli | On Track | ==CANCELLED==As per DeAnna's request 10/06/2025 Since the cost savings was identified for 1 app was only 14k (3531739) No other apps had any savings - Hence the decision was made to put this init on hold | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL1-SC-Ship Visibility- Enabler - POV |  | 136623 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brandy Mears, Ramyasine Boominathan, Harsh Garg, Karen A. Lucarelli | On Track | Moving thru the Op Model as expected. | E: L2 | On Hold | L2 | 2024-07-22 | 2026-01-02
Business w/ Tech Initiative: TS-VL2-ES-Retire-Wave1 |  | 140150 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Elizabeth E. Canale, DeAnna Higgins, Karen Farrell-Shikuku | On Track | 10/6: Cancelling this init after confirming the cost savings associated with the retirement of the FXF-WalkMe (EAI# 3536825) application was already accounted for in scope of another Drive initiative: # 9276 [Wave# 16452] - Retirement of WalkMe from Sales Platforms that is currently in L4. MD Rebecca Jones as IO of the Drive initiative # 9276 confirmed. No other cost savings were identified for this Drive # 140150 scope of associated applications. 9/25: Initiative returned to Active state to proceed with entering L2 Financials for the $43k benefit. Added DeAnna Higgins as back-up IO to add Financials 9/16: Iniative progression in Planview is "on hold" while TS leadershipand Finance discussion underway as to whether this type of Cost Savings capture initiative for "retired" applications, where tech support/involvement is not required, should be in Planview and if so, is there a dollar threshold consideration. 7/2: LBC created | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-Migrate Enterprise Customer |  | 140153 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Santhosh B. Korambeth, Viswanath Yerramsetty, Amanda Nevins, Vincent J. Romeo | On Track | As per the email direction to cancel all enabler requests under parent request 98380 | D: SL2 | Cancelled | SL2 Domain Lead Approval
Business w/ Tech Initiative: TS-VL4-Network-StrategicTelecomFramework | 88666 | 9316 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Ashley Akil, Laurie Turner, Joseph (Bailey) Wimberley, Jordan B. Norton | On Track | 4/24 - US Audit, $590K in credits received to date which is an additional 90K in last month. $1.73M in go forward annual savings approved and confirmed on invoices, which is an additional $200K in last month. Provided Accenture Implementation team feedback on TPPF report. Reviewed with Accenture team and pending additional responses from their team. Met internally to document Global Opportunity Assessment feedback. Provided Accenture team those notes and questions on 4/24. Held and facilitated call with new Customer Experience contacts and discussed audit process. CX team followed that meeting up and provided Accenture audit team all requested contract information. Finally, provided Calero our final requested changes to the Global SOW. They are working to get updates completed by EOB on 4/24. Currently anticipating the SOW will be entered in Encore by May 1st 4/17 - Held second planning session with EBS team on 4/6. Discussed core aspects of FCF development that Calero will need from FedEx. Planning in progress for session with Finance as well to address FITC in Global. Held internal monthly update with MEISA region on 4/16. Reviewed updates to timeline regarding inventory development. Accenture held calls with EU and Canada to continue audit work and review latest finds and issues. Canada currently has $45k in annual savings and credits already completed and confirmed. $79k in approved savings are pending confirmation on invoices. Finally, $185k in savings remain open and are under review by FedEx team or pending dispute response from vendor. Regarding the US audit, provided several additional batches of Verizon Wireless zero use lines. Approximately 4,000 were declined and were approved this week. 4/2 - Several significant deliverables completed this week. Accenture reviewed the TEM Policy & Process Framework in Memphis on 3/31. Scheduling in progress for reviews at the regional level. Additionally, the Global Opportunity Assessment which provides strategic recommendations for savings across all regions down to the service and supplier level was reviewed for first time with Accenture and FedEx on April 2nd. Additional reviews with regions will be scheduled. Finally, the Initial Market Assessment, which was completed earlier this year and focuses on the EU/US SD-WAN strategy, is scheduled for review with Jan, Bob, and Deb on Friday April 3rd. The EU audit started and first official call was held on the 30th. EU inventory builds/reviews also slated to begin again this coming week. Canada held bi-weekly audit call with audit team. US continues to wrap up wireless recommendations. Provided Accenture responses on over 2k more zero use lines. Approximately 19,000 VZW lines remain under review for disonnect consideration. This makes up $4M of the remaining $4.4M potentially projected on the audit dashboard. An additiaonl $300K of the the $4.4M is VZW plan updates that are waiting to be approved until ammendment is signed. 3/26 - ROW Data Collection complete as of 3/25/26. Provided audit team updates on inactive site list. Provided MEISA and CX regions with internal project updates and timeline adjustments. Held internal call with LAC, EU and CAN regions to review timeline changes and next portions of projects for each region. 3/19 - Provided Accenture audit team ~500 ATT wireless and Verizon wireless line recommendation responses. Received approval for 2 of the final wireline disconnect recommendations as well. These two items accounted for over $100K in annual savings. Confirmed no open data collection items in MEISA and APAC regions and provided internal monthly updates to region MDs. Recieved draft contract from Customer Experience that is close to being finalized for Accenture to review. Held bi-weekly audit call with Canadian region. $25K in savings completed and recieved to date. $80K confirmed but not yet received, and ~$400K in potential open issues under review. 3/12 - Held call on 3/6 with Calero implemenation team an | G: L3 | Active | TEMP L3 - Enter L3 | 2024-10-01 | 2028-07-31
Business w/ Tech Initiative: TS-VL3-iSeries MPS Migration |  | 141555 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Aspen Thompson, Hunter McCormick | On Track | We are moving through this process at a good pace, and there is not a date for the iSeries shutdown yet. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: TS-VL1-DTDO-ARC-Enabler |  | 141631 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Kelly Rowland, Ryan D'Souza, Eric Joyner | On Track | No longer needed | E: L2 | Cancelled | L2 | 2025-07-31 | 2025-07-31
Business Only Initiative: TS-VL1-FD-ARC-Enabler |  | 141635 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Kelly Rowland, Ryan D'Souza | On Track | No longer needed | E: L2 | Cancelled | L2 | 2025-07-31 | 2025-07-31
Business w/ Tech Initiative: TS-VL3-Infra-CAMDM | 28918 | 6748 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Curtis Johnsey, Robert Newman | On Track | FY25 re-baselined. | G: L3 | Active | TEMP L3 - Enter L3 | 2022-06-01 | 2026-08-31
Business w/ Tech Initiative: TS-VL1-Clearance-Innovation |  | 141905 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On Track | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL1-EU Profitability-Innovation |  | 141908 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On track | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL1-LSSI-Innovation |  | 141911 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On Track | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL1-Zenith-Innovation |  | 141916 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | On track | E: L2 | On Hold | L2
Business w/ Tech Initiative: TS-VL1-SC-Ship Visibility- Consume-POV-ARCH-Enable |  | 141919 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kelly Rowland | On Track | Work will be absorbed in initative number 136623. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigration |  | 88640 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | David Moore, Holly Chernushin, Caitie Adams | On Track | At least one portfolio must be identified as “impacted”, and this will be determined through architectural review in L1. ---- Platform portfolio is identified as impacted. I'm not sure if this initiative went through a tech review. Please ensure that the Business Scenarios and Ability To statements are properly completed, as these are needed to facilitate L1 architectural review. Ability To statements should be written in the format: As a < type of user >, I want < some goal > so that < some reason >. ----- I am doing my best to craft this sentence, but this has been handed down to from leadership so roughly "As a user of GCP, i want retire or migrate all GCP functions, per leadership directive." If there are any issues with this initiative that requires further feedback, please reach out to me directly for further clarification. ----------------------------------- Initiative cancelled as benefits are largely already achieved or have been reduced by other initiatives also migrating away from GCP. | C: L1 | Cancelled | L1 Feedback Requested | 2025-06-02 | 2027-09-30
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateODINDecomm | 98017 | 7062 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Suvro Choudhury, Artis Taylor | On Track | 5/1/25/Document Feedback Provided/Esther Kerns/D&T Domain QA Expert Review FY25 Rebaselined Baseline Value: 3,780,724 Target Value: 4,715,407 | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-05-30 | 2026-05-29
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateSurfaceApps |  | 90439 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nathan Cybak, Jose Zenteno, Erika Paulson | On Track | No longer needed | E: L2 | Cancelled | L2 | 2025-09-01 | 2027-08-31
Business w/ Tech Initiative: TS-VL3-Messaging-NextGen Messaging Platform |  | 92246 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jim McMahon, Barry Harrald, Peter Murphy | On Track | There are several tasks that we will need to complete prior to moving Pulsar into a production environment including (no particular order with many being done in parallel): • Selecting a commercial vendor – Current candidates are DataStax and StreamNative • Negotiate and get approvals for commercial agreement • Completing functional, performance and failure testing (rough estimate is a period of 4+ months to complete) • Integrating Pulsar with PurpleID/IMAGE systems • Define, implement, validate monitoring/alerting configuration • Define/design reference architecture for Pulsar rollout • Build automation to fully provision Pulsar components (brokers, bookkeepers, zookeepers) • Use automation to provision reference architecture • Update FedEx JMS decorator to support Starlight JMS client library and complete testing • Establish criteria and select initial applications to migrate from AMQ to Pulsar • In Addition, I have no one available to work on this effort due to CONDOR messaging migration. This will resolve itself in April when we are done with CONDOR. Update 4/16/26 - Initiative being cancelled as all Pulsar related work is not going to be performed at all. | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateFinanceDecisionScienc |  | 88686 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Paul Papaiah, Shravan Kumar Gunti, Chris Kalbfell | On Track | 9/17/25 - The scope has changed now focussing on just the micro forecast application. 6/12/25 - Feedback requested for L2 approval 2/28/25- The move to get the initiative to L2 is still in progress. 2/21/25- We will be setting up a meeting with the parent initiative owners in order to get the correct LBC information and financials breakdown. 2/13/25- Our team is in the process of moving to L2. This initiative is tied to a parent initiative but this piece has been assigned to a different strategic parent/pod. We are working to change this and align the initiative to the parent to streamline future gate approvals. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-Infra-NextGen Connect |  | 142637 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Peter Murphy, Kelly Rowland | On Track | Updated Backup IO | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-DRE EIW Deprecation |  | 143321 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Gabriel Okoye, Amanda Nevins, Vincent J. Romeo | On Track | 07/17 - Working through the approval process. EIW Deprecation is cancelled | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-EIW Retirement |  | 98380 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Vincent J. Romeo, Amanda Nevins | On Track | Per Jan 15, 2026 email from Adam Smith and Ali Zaidi, the EIW Deprecation/Migration has been canceled, and EIW will remain FedEx's Information Warehouse. | E: L2 | Cancelled | L2 & CCH | 2024-08-05 | 2025-05-30
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi CANA |  | 91945 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | LBC is complete and Architecture alignment is in progress. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi COL3 |  | 110283 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | . | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi OPS1 |  | 110280 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | . | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi OPS2 |  | 91942 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | LBC is complete and Architecture alignment is in progress. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi PITT1 |  | 110277 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | . | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi PITT2 |  | 110271 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | . | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi PITT3 |  | 110268 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | . | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi PITT4 |  | 91939 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | LBC is complete and Architecture alignment is in progress. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi PITT5 |  | 91934 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | LBC is complete and Architecture alignment is in progress. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SCO App Opt - Weis - IBMi PITT6 |  | 91931 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tom Brien | On Track | LBC is complete and Architecture alignment is in progress. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL4-NETWORK-Office MPLS Carrier Change | 29732 | 6756 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Laurie Turner, Morgan McAndrews | On Track | updated to FY25 baseline on 4/10/25, the following fields are not editable in L1 section and cannot be updated: baseline value and target value, 5/8/25 on track, 6/12/25 completed FY24 and FY25 post and pre peak phased roll out, extended target date for final money step remaining. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-02-16 | 2026-05-08
Business w/ Tech Initiative: TS-VL4-SECURITY-ZSCALER | 72089 | 6951 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nicholas Shansky, Thuy Trang L. Doan, Kirt Satam | On Track | **4/9/26 **- Milestone ID 187551 with schedule start date of 3/16/26 and 11/30/26 as end date. removed Feb forecasted amount so actuals can show up on report. **2/18/26 **- Aligned with Rachel Kohr. Move out money step to Nov and add new work to cover for BCDR and failover cloud tenant set up **2/1/26** - old proxy server shut down on target 10/1/25 Delayed - Updated milestoned schedule finish date to reflect delay rebase lined to FY25 as of 3/31/25 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-15 | 2026-11-30
Business w/ Tech Initiative: TS-VL4-SECURITY-Zero Trust Campus Redesign |  | 88566 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nicholas Shansky | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL4-NETWORK-EdgeOptimization | 36336 | 8903 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Heather Pietrowski, Susan Ward, Amy Pickens | On Track | 12/1/2025 - Updated Nov-May savings to be $5.2M higher due to increased MRC costs for Cogent circuits which are being disconnected. 11/11/2025- October 2025 actuals entered. Costs started to hit, savings slightly lower than forecasted. 10/08/25 - Sep 2025 actuals entered. Higher savings than anticipated due to: 1. Savings that were supposed to hit in FY25 were delayed, 2. Implementation costs for large MPLS sites are delayed. Costs are starting to hit but at a slower rate than forecasted. 9/12/25 - Aug 2025 actuals entered; corrected June and July 2025 actuals due to entry as negative instead of positive numbers. Savings higher due to all head-end MPLS circuit billing not yet started. 9/4/25: working to split epics for solutioning. No change in work status. 8/22/25: no change from 8/15 updates 8/13/25: Jul 2025 actuals entered. Higher savings than anticipated due to: 1. Savings that were supposed to hit in FY25 were delayed, 2. Implementation costs for large MPLS sites are delayed. 07/18/25: Forecasting 445 installations for AVPN and DIA by peak. No sites currently at risk at this time. 07/11/25: June financials updated. Higher savings than anticipated due to: 1. Savings that were supposed to hit in FY25 were delayed, 2. Implementation costs for large MPLS sites are delayed. 04/08/25: PLEASE NOTE: The Brief Description has been updated to reflect the new financials based on the rebaseline as well as The Net Recurring Benefits in L1 section below. The following fields are not editable (all in the L1 section) and cannot be updated: Baseline Value, Target Value and Key Assumptions Made in Quantifying Impact. 04/03/25 Re-baselined to FY25 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2028-12-29
Business w/ Tech Initiative: TS-VL4-NETWORK-EU SD WAN |  | 91925 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Sanna Karlsson, Susan Ward | On Track | 05/02/26 - Milestones adjusted, KPIs added. PPM fixed. Full cost remains on $20m including $15m on-time + $5m recurring. 03/02/26 - Labor costing corrected. Total cost now $20.6m. Corrected files attached. 23/01/26-All documents uploaded - awaiting PEO green light 22/01/26 - Finance L2 costing approved and attachment added 13/01/26 - LCM de-coupled and finances adjusted accordingly 28/11/25 - Vaibhav Sharma assigned as the Platforms PEO - awaiting Greenlighting #91925. 27/11/25 - Portfolio greenlight requested from Zahra Tagi 27/11/25 - Finance entries completed and sent to Cindy Wilkes team. 26/11/25 - QA Reviewed by Swetha Burugual 11/26/25 21/11/25 - EA Review by Robbie Pike - sent to costing. 24/10/25 - QA Reviewed by Steve Kastner 10/23/25 24/10/25 - Description adjusted to further clarify the expected business outcome. Finances aligned with Apoorv Purohit. Change Management section completed and Money step adjusted to further clarify the timelines. 23/10/25 - Lean Business Case + Stage Gate checklist fullfilled. QA Expert Steve Kastner contacted for approval to proceed to L2. 22/10/25 - L1 Architecture Alignment completed 17/10/25 - See mail from Bob Palmieri who owns the Network Engineering Architecture globally that includes capacity and resiliency assessments. This team are the SME’s for SDWAN and set the corporate design and technical standards and specifications. This comes directly from our documentation and Aryo Kresnadi is the Technical Director who has reviewed and approved the Topology. 15/10/25 - Reference Architecture and related Corporate Standards signed off by Engineering. See attachments. 9/12/25 - Initiative name and brief description modified to reflect this effort is to support EU only. Sanna Karlsson will be the primary IO moving forward. Project funding requirements for EU SDWAN continue to be developed. 8/22/25 - Project funding needs for EU SDWAN under development. Scope for this effort is specific to EU SDWAN. Add'l inits will be opened for remaining regions. 8/15/25: On Track. Project funding needs under development; no project planning until funding approval in place 8/11/25: This initiative is led by Laurie Turner's organization as TEMS owner. 07/18/25: Resourcing concerns remain. Working with Aryo and Bob P. to identify solutions and timeline. Lacking resources. Aryo will be discussing possible solution with Frank Jary week of 3/3. | G: L3 | Active | L3 | 2026-06-01 | 2028-12-29
Business w/ Tech Initiative: TS-VL4-NETWORK-Optimize And Modernize |  | 91922 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Susan Ward | On Track | 2/19/26: placed effort On Hold pending add'l direction. Will not remain in on hold status. 8/22/25: Project funding needs under development; no project planning until funding approval in place 8/15/25: On Track. Project funding needs under development; no project planning until funding approval in place 8/11/25: We are in Assess state for network modernization. Site categorization completed, inventory capture (80% complete) both field and DC/Colo, standards v17 50%, and identifying required costs 30%. First 3 to be completed end of Sept. Costs will be end of Sept as need to gather costs from other areas (infoSec FW, perimeter, SD WAN cloud and connectivity costs) 07/18/25: Resourcing concerns remain. Working with Aryo and Bob P. to identify solutions and timeline. Lacking resources. Aryo will be discussing possible solution with Frank Jary week of 3/3. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-HybridCloud-OptimizeDelphixUnlimitedAgreeme |  | 114672 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Venera Earley, Anthony Morgan, Alex Moore, Naveed Khan | On Track | Added Initiative Supporting Architectural Documentation link | G: L3 | Active | TEMP L3 - Enter L3 | 2027-06-30 | 2027-06-30
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-Ent Sec Info Mgmt (eSIMS) |  | 105788 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Suzanne Moore, Amanda Nevins, Vincent J. Romeo | On Track | 1/19/2026 - suzanne moore/437423 - cancelling because parent request has been cancelled and this is no longer needed. 11/4/2025 - suzanne moore/437423 - placing on hold due to parent initiative status on hold, which prevents resources being assigned to these initiatives and allows them move on to other work that is progressing. 10/10/2025 - suzanne moore/437423 - pending enterprise architecture engagement 9/11/2025 - suzanne moore/437423 - pending enterprise architecture engagement 9/3/2025 - suzanne moore/437423 - pending enterprise architecture engagement 8/19/2025 - suzanne moore/437423 - linked to parent EIW retirement planview as an enabler. pending architectural review. 7/31/2025 - suzanne moore/437423 - changing request type to enabler, once the parent EIW retirement planview request is in L2 status, will add it as dependency. 7/25/2025 - suzanne moore/437423 - pending enterprise architecture priorization. 7/21/2025 - suzanne moore/437423 - impact analysis completed. waiting on architectural review 6/20/2025 - suzanne moore/437423 - impact analysis in progress. 6/1/2025 - suzanne moore/437423 - impact analysis in progress. 5/16/2025 - suzanne moore/437423 - impact analysis in progress 4/26/2025 - suzanne moore/437423 - still researching data impacts utilizing the atlas adhoc workspace. 4/11/2025 - suzanne moore/437423 - no status updates. 4/4/2025 - suzanne moore/437423 - no status updates. 3/24/2025 - suzanne moore/437423 - no re-baseline needed since financials not yet updated. 3/21/2025 - suzanne moore/437423 - working through data available through ATLAS to determine what, if any, additional data is needed for eSIMS that is not already available in ATLAS, which is replacing the EDW data source for loss claims, locations, disc shpiping, and customer. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-Messaging-POC Enabler |  | 152855 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Barry Harrald, Peter Murphy, Jim McMahon | On Track | 7/30/25 - finance review with Bob Noble | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-04-19
Business w/ Tech Initiative: TS-VL4-NETWORK-APAC IT-ANZ OneNetwork |  | 106844 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Dusan Berjanovic, Boon-Keat Ivan Yap | On Track | **04/01/2026 - Cancellation Request After discussion with MD NE, Sau-Pheng Cheong and Deepak Wadhwa, MD FIT MEISA, and with the agreement from Manoj Sekhar, Manage NE MEISA, aggrement is to cancell this initiative. **02/17/2026 - Optus Change Freeze Due to Optus internal change freeze, implementation for remaining Optus sites have stalled. No indication on releif, we are working on exception. **01/15/2026 - Implementation restatarted 1. Perth station planned for implementation Jan16 2. Financial template received last week to complete and move to L2 **10/02 - Optus change freeze 1. Optus implementation stalled, due to unrelated telco issues and overl change freeze. 2. Telstra remaing 4 sites in plannning **09/04 - initiative Tech Documentation Completed 1. Documentaiton updated 2. Implementaiton continues and planning with telcos progressing to finalise before peak period **08/28 - Implementation Continues 1. 1. inTune PC conversions and bew deployments continue 2. Optus (8 outstanding) and Telstra (4 outstanding) implementation progressing with agreed schedule: **08/14 - implementation Continues 1. inTune PC conversions and bew deployments continue 2. Optus implementation progressing with agreed schedule **08/07 - implementation Continues 1. inTune PC conversions and bew deployments continue 2. Optus implementation progressing with agreed schedule **07/31 - Implementation Continues 1. Optus scheduling and change approval in progress 2. Discussions with FIT for resource allocation for transition support 3. InTune PC transition continues with Intune now reashing 66% of the fleet vs the CORP. **07/24 - Implementation Continues 1. First Optus site implemented **07/18 - Implementation in progress 1. EDC/SDC configuration complete (enabler) 2. Telstra Adaptive Network implementation completed, few remaining sites to convert 3. Optus orders placed and implementation commenced https://myfedex.sharepoint.com/teams/ANZNE/Shared%20Documents/AU-BGP-AS-PE-CE%20_Carrier%20delivery%20tracker.xlsx **05/20 - Changes for site conversion commenced 1. NZ sites conversion progressing 2. AU Mayor sites changes scheduled **04/15 - Preparation work in progress 1. WAN Data Neworks configuraiton in progress for VRF enablement 2. Telcos configuraiton enabled and ready 3. Conversion to Intune PC build continues **03/31 - Initiative approved for L1** Added Primary Initiative Owner: Dusan Berjanovic Added Secondary Initiative Owner: Ivan Yap **03/23 - Implemented 2 technology enablers** Virtual Routing CHG0901968 VRF on Routers & Router Software upgrade CHG0902459 FDX AU - IOS upgrade for Core switches at Mascot SDC | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-CACTAEXT to Atlas |  | 154409 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Megha Satheesh Nair, Amanda Nevins, Vincent J. Romeo | On Track | Added as Required by TLS-VL3-EIW Retirement Dependency and marked as Enabler Added Amanda Nevins and Vincent Romeo as IO L1 Net Recurring Benefits ($, annualized)-P&L/Hard - 0 L1 Net Recurring Benefits ($, annualized)-Soft - 0 Cancellation request: Parent initiative has been cancelled | D: SL2 | Cancelled | SL2 Domain Lead Approval
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-EIW to Atlas_ETL |  | 154416 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Joshua Bunt, Amanda Nevins, Vincent J. Romeo | On Track | EIW deprecation is cancelled | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-PKI to Atlas |  | 154425 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jacqueline Leon, Amanda Nevins, Vincent J. Romeo | On Track | 11/03/2025 - per email from Kelly Rowland, all initiatives in Planview for EIW to Atlas work be put ON HOLD in Planview. Each of you have active initiatives in Planview, so please follow the attached instructions and put your initiatives ON HOLD as soon as possible. This prevents resources being assigned to these initiatives and allows them move on to other work that is progressing. Added Required By: TS-VL3-EIW Retirement dependency and changed request type to "enabler". 09/26/2025 - QA reviewd by Steve Kastner. Per Jamie Heller, we are using FY25 as baseline No longer needed as EIW deprecation is cancelled | D: SL2 | Cancelled | SL2 Domain Lead Approval
Business w/ Tech Initiative: TS-VL3-DB-EIWMigratin-Sales EnabDataSourcing |  | 154428 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Cliff E. Williams, Amanda Nevins, Vincent J. Romeo | On Track | Added Required By: TS-VL3-EIW Retirement dependency and changed request type to "enabler" QA Review completed on 9/17/25 -- Steven Kastner Setting to "ON HOLD" status until further directions are shared by the Planview team. | D: SL2 | Cancelled | SL2 Domain Lead Approval
Business w/ Tech Initiative: TS-VL3-Infra-Automation_Anywhere |  | 155362 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Georgios-Alexandros Anastasiou | On Track | 12/08 - On track | E: L2 | Active | L2 Feedback Requested | 2025-11-10 | 2027-06-01
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-AccessAtlasDatafromRecoverA |  | 155378 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Timothy Shunn, Amanda Nevins, Vincent J. Romeo | On Track | This is an enabler to the EIW retirement which has also been cancelled. Addded Required By: TS-VL3-EIW Retirement dependency and changed request Type to "enabler". | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL3-EIW to Atlas-Move tables used in FDX Report |  | 155381 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Linda Kincaid, Tiffany Miller, AARON LEVINSON, Amanda Nevins, Vincent J. Romeo | On Track | Please cancel the Planview request EIW to Atlas Move due to the understanding EIW is no longer going to be retired | D: SL2 | Cancelled | SL2 Domain Lead Approval
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-AppI-DCHERSPRCNGEXT |  | 156502 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | David J. Freeman, Amanda Nevins, Vincent J. Romeo | On Track | EDW Migration to Atlas is cancelled. | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: TS-VL1-CM-Ship Visibility-Retire |  | 156511 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Chad Girnus, Eric Joyner | On Track | New approach is being taken. TS inits are no longer being sponsored | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateMOBIUSSurfCoDataMigra | 73337 | 7563 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kevin Lofgren, Brian Pleslusky, Patrick Snyder | On Track | Updated to hold status per Amit Prabhu on 1.29.26. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-01-25 | 2027-03-31
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-LAC IBIS |  | 159284 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Sujith Narayanan, Paola Lemus, Thirumurugan Subramaniyan, Vincent J. Romeo, Amanda Nevins | On Track | 01/30/26 - Cancelled as requested by Corporate team. 11/07 - ON HOLD as requested by Kelly Rowland on 11/3. New date for EIW retirement is September 2027. 08/21-review started. Added required by TS-VL3-EIW Retirement dependency. | D: SL2 | Cancelled | SL2 Domain Lead Approval
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-SpotfireDashboards |  | 160260 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Vipin VP, Amanda Nevins, Vincent J. Romeo | On Track | EIW Deprecation is cancelled. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: TS-VL3-HPE-Onsite Support Contract Cancellation |  | 160263 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Kathleen Coman | On Track | The initiative is progressing as planned with no identified risks or issues impacting the timeline or deliverables Key milestone remain on schedule, and stakeholder engagement is ongoing to ensure succesful completion. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-05-30 | 2025-05-30
Business w/ Tech Initiative: TS-VL3-SDLC-CBFlowRetirement |  | 160266 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Chris Warren, Wallace Green (Wally), Amit Prabhu | On Track | 2/24- Platform PEO pendng greenlight- enterprise priority impacting PEO backlog. LBC is iniated. Roadmap and Plan needs to be defined. | E: L2 | Active | L2 Feedback Requested | 2026-01-07 | 2026-10-13
Business w/ Tech Initiative: TS-VL3-DB -EIWMigration to Atlas-APP ID - EU FOPD |  | 160616 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Matteo Squeo, Amanda Nevins, Vincent J. Romeo | On Track | Added Required By: TS-VL3-EIW Retirement dependency and change request type to "Enabler". | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-APILM-Apigee To Azure APIM |  | 96196 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kenton D. McCroskey, Ed Chaltry | On Track | Progressing to L2 | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration to Atlas-GEISMultiple EAIs |  | 160905 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Gregory Schaefer, Amanda Nevins, Vincent J. Romeo | On Track | Added Required By TS-VL-3-EIW Retirement depedency and request type is 'enabler'. Updated Initiiative Name as requested by Kelly Rowland. EIW Deprecation Cancelled | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-HybridCloud-MigrateDataIngestionsFromGCPToA |  | 88006 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nicole Wilson, Krishnan Athinarayanan | On Track | 1/12/2026 - Milestone and Risks, and Financial plan has been reviewed/updated. This iniatiaive has already been completed. Working with Athi to take deliverable through the planview process. I created this on Athi's behalf. But I'm not working it. I'm not in the same department anymore. | H: SL4 | On Hold | SL4 Finance Domain Lead Approval | 2025-04-01 | 2025-07-31
Business w/ Tech Initiative: TS-VL3-DB -EIWMigration to Atlas: LAC P&E PILOT |  | 161361 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Oliver H. Martin, Amanda Nevins, Vincent J. Romeo | On Track | Actions & next steps •Planview initiative 98380 (EIW Deprecation) and all related project meetings are canceled. •If you own an enabler initiative under parent 98380, please cancel it in Planview immediately. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration- Data Sources Chris Org |  | 161364 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Vasudevan Gopal, Amanda Nevins, Donyae Scott, Vincent J. Romeo | On Track | 1-28-26 - . EIW deprecation has been cancelled. Initiative is not needed. 9.9.25 - Title change. Trying to get requestor assigned as IO. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASBOFXS | 41696 | 7113 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Eddie Patterson, David Yuan, Donyae Scott | On Track | The CCII business team has not prioritized the migration away from SAP BO. RP&E – Revenue Planning & Engineering (#96066) has advised the proposed architecture design doesn’t fit their business model and will be escalating to their VP. 5/14/25 - opened PDSM ticket# INC030667520 to return initiative to L2 in order to add Data & AI to Impacted Portfolio due the nature of this request. | E: L2 | Active | L2 | 2023-11-01 | 2026-08-19
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExGPEGEIS | 41704 | 7119 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Keith Chism, Kelton Morris | On Track | 80% migrated | E: L2 | On Hold | L2 | 2024-07-22 | 2025-09-12
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExMarketing | 41706 | 7121 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Joseph Warner, Radha Krishnan | On Track | SAS license extension beyond March 2025 is needed to provide sufficient time to migrate code from SAS to future platform. | C: L1 | Active | L1 Feedback Requested | 2024-07-22 | 2026-07-31
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExGroundPLP | 41707 | 7123 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Stewart Burnam, Loveena Goel, John Gilbert, Derrick Robertson | On Track | There is a separate Enterprise Costing Drive init which is the replacement solution for SAS CPM platform. | C: L1 | Active | TEMP L1 - Create L1 LBC | 2024-07-22 | 2024-12-30
Business Only Initiative: TS-VL3-DATAVISUAL-SASFedLogisticsTradeNetwork | 41711 | 7130 | Business Only Initiative | IT - Tech Simplification | Data and Tech | James Warren, Michael Flippin | On Track | Parent Initiative rebaselined to FY25 completed and approved by Finance on 4/14/25 This Child Initiative rebaselined completed and approved by Finance on 9/11/25 QA Reviewed by Steve Kastner on 9/29/25 Per Rachel Kohr, this Initiative was moved from D&T to Data. Then, on November 25, 2025, met with Swetha Burugula, Barbra Grantham and others, and completed review with them to move to SL3. Our FXL(FedEx Logistics)/FTN(FedEx Trade Networks) SAS (Statistical Analysis System) EAI #3534721 (FTNTB-VENDOR-SAS) was retired, turned off (on November 29, 2025) and decommissioned as of January 6, 2026, It is all gone completely now, as was directed and planned by management and leadership. | E: L2 | Active | L2 | 2023-10-02 | 2025-11-28
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExExpressDigitalTwinPro | 41700 | 8132 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Vardhan Kamat | On Track | Project plan for transitioning from SAS to Python and AnyLogic has been setup. Resources ahave been assigned and work identified with timelines. The contract ends on 01/14/2026. The timeline for conversion of the code from SAS is set to be completed by June 2025. This will allow for sufficient time to test the solution. | C: L1 | Active | TEMP L1 - Create L1 LBC | 2024-07-22 | 2026-01-14
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExGround | 41701 | 8145 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Eddie Patterson, Kalyan Vempaty, Derrick Getter | On Track | 5 POCs were accomplished with Teradata. Additionally, evaluating other short listed BI tools such as MS Power BI. | E: L2 | Active | L2 | 2024-07-22 | 2027-04-30
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExAirOpsTechGRID | 41702 | 9390 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Nicole Craig, Janet Wilson, Eddie Patterson | On Track | 11/7/25: Met with Finance to discuss the financial estimates from the vendor to cover migration cost. We were asked to also get information on storage costs and training to get a complete picture of the cost of the project. 10/16/25: Received financial estimates from vendor, submitted PDSM ticket to update that one time implementation charge as well as the key assumptions. PDSM Ticket #: INC032692522. 10/3/25: Spoke with the vendor, still waiting to receive the final financial totals. Now expected to receive NLT 10/10. 9/26: Currently waiting on final financial totals from vendor. Expected to receive NLT 10/3. 8/29: I (NC) met with Srinivas Kamisetty (OSV) on 8/28 to review the LBC and EA. He understands we will not meet the 8/31 deadline to move to L2 due to the financial information and architecture information. He will schedule a meeting with finance for us to discuss and he will also update the EA with as much information he can provide. I will work with the team to fill out the remaining information. 8/22/25: Working with Vasavi Juvvadi, Eddie Patterson, and Srinivas Kamisetty to finalize some information on the Lean Business Case. Goal is to have this submitted by 8/31/25. 8/8/25: Still reviewing LBC needs. Will discuss needs with Eddie Patterson to figure out financial estimate. 7/18/25: Still reviewing information for the Lean Business Case. 7/11/25: Currently Reviewing LBC needs. 5.23.25: Reviewing LBC needs. Rebaselined to FY25 completed and approved by Finance on 4/14. | C: L1 | On Hold | L1 Feedback Requested | 2024-07-22 | 2026-12-30
Business w/ Tech Initiative: TS-VL3-DATAVISUAL-SASFedExAirOpsTechVIYA | 41703 | 9391 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Christopher Darr, Janet Wilson | On Track | The overall SAS Migration initiative was placed on indefinite hold effective January, 2026. | C: L1 | Cancelled | L1 Feedback Requested | 2024-07-22 | 2026-12-30
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration-USI Mktg Analytics Solution |  | 161466 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Zachary M. Barker, Amanda Nevins, Vincent J. Romeo | On Track | Not needed anymore, deprecation is cancelled | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIW Migration S&CDE-CRM-GSR |  | 161469 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Elbony Mathews, Amanda Nevins, Vincent J. Romeo | On Track | 09/04 - Add LBC by IO | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIW Migration S&CDE-CORE-eSOT |  | 161472 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Hannah Rogers, Amanda Nevins, Vincent J. Romeo | On Track | This init was cancelled | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateFraudDataLakeMigratio | 91415 | 7750 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brian Hanson, Vivek Varadarajan | On Track | Delayed until end of FY25. Scope increase since project began and EPAM team departure end of Nov 2025. Tech Simp team has been updated on latest plan. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-01 | 2026-06-01
Business w/ Tech Initiative: TS-VL3-DocMgt-Corporate Web Scanning |  | 103989 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Lucia A. Gascoigne, Martin Bamforth, Liam Bowden | On Track | QA Reviewed by Swetha Burugula Financial SCO Costs validated by Sara Barnes Note: Solutions and Portfolios. This iniative has been tagged with both SCO and Platforms impact. The ARTs which will be involved in this initiative are confined to: SCO- CLR- Regulatory (Team Purple Reign) – this team support and run the existing solutions to be replaced with Web Scanning. INTL-Imaging-CoE - (1 team) this team are an Independent ART (currently not sitting within a Portfolio) – this is the team who will be implementing the new Corporate Platform for all document scanning, using the Tungsten Total Agility Platform. INTL-Imaging-COE works across business units which is why it is currently independent/not aligned to a Portfolio (although the manager for this ART works for Matt Pegge (SCO). | E: L2 | Active | L2 Feedback Requested | 2025-11-25 | 2027-07-05
Business w/ Tech Initiative: TS-VL2-Con-ServiceNow-EA/APM Mod & PEX Migration | 89129 | 7759 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Michael J. Heys, Allan Goddard, Jason Bailey, Richard Lomas | On Track | Now have a project sponsor (Frank Jary) and a more complete view of benefits and cost avoidance | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL3-SDLC-PPMRetirement |  | 90032 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jacquelyn S. Bortters (Jackie), Leigh A. Kutil, Cathey Cooper | On Track | 9/4/2025 : On Track May 5, 2025 : QA Review : * Adjusted the 2028 exit rate per Domain Finance Lead. * Initiative Owner : Jackie Bortters * QA Reviewer : Steve Kastner Details on why this is important: This work directly supports the rollout and adoption of the new demand framework in Planview which began enterprise wide rollout for DRIVE initiatives in October 2024 under Project Focus. PPM has been the enterprise demand entry tool for IT work since June of 2017. In addition to IT Demand entry and approval, the PPM tool provides the following key functions: Implements the RAPID Compliance Process that all FedEx applications must adhere to Implements the IT labor capitalization/expense reporting for Finance, Account and Tax Provides timesheets and reporting for FSC to enable bill-back of hours to their customers As a result of the selection of Planview Portfolio for FedEx's demand framework and resource and capacity management and financial management, PPM must be retired. Its functions must be re-homed or discontinued (if determined to no longer be necessary) in order to decommission it. To accomplish PPM's decommissioning requires collaboration and support from the EBA Enterprise Portfolio Management team, Platforms Portfolio teams and potentially Enterprise Services teams. Functions targeted for re-homing: The rollout of Planview Portfolio encompasses the replacement of demand entry and project functionality in PPM. Until all key functions can be reimplemented elsewhere, duplicate entry in both Planview and PPM is required for IT work (Business w/Tech, Local Enhancements and Lifecycle Management) Some interim work to shut down some PPM functions early is also required to ensure that Planview remains the single source of entry Planview's resource and capacity management and financial management will be leveraged to capture labor reporting as capital and expense for Finance, Accounting and Tax The RAPID implementation is targeted for PDSM ServiceNow - this supports simplification of developer's tech stacks since they will work in PDSM only vs. PPM and PDSM for MTP NOTE: A solution for time reporting for FSC customer billback has yet to be identified. Why should it be ranked higher (historical perspective of the ask): Until all key functions can be reimplemented elsewhere, duplicate entry in both Planview and PPM is required for IT work. Users must follow both the Planview and PPM processes for demand entry. IT Managers must still approve demand in PPM for RAPID compliance and in order for labor capitalization reporting to function accurately. Users must enter both a PPM Number and a Planview Id number in Agility Developers have to use both PPM and PDSM in order to move code to Production Currently, Finance/Accounting recoup approximately 10 million annually from the labor effort reporting process. Its re-implementation in Planview may allow for additional work to be included since all work is in a single funnel. Contact who can work on the EA and portfolio architecture: Leigh Ann Kutil (manager: Jackie Bortters) Brendan Earley (manager: Allan Goddard / matrixed to Debbie Schuman) Allan Goddard Expected impacts to other portfolios: To accomplish PPM's decommissioning requires collaboration and support from the EBA Enterprise Portfolio Management team, Platforms Portfolio teams and potentially Enterprise Services teams. Overall User Impact Until Work is Done: Until all key functions can be reimplemented elsewhere, duplicate entry in both Planview and PPM is required for IT work (Business w/Tech, Local Enhancements and Lifecycle Management) | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2029-05-02
Business w/ Tech Initiative: TS-VL2-Con-ServiceNowAppPorfolioMgmnt |  | 107744 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Sunil Kadampally, Paul W. Adrien | On Track | Working to input data at this point to move to next steps. Transferring IO ownership to Paul Adrien and further data input will be completed by Paul. 1,000 Licences - (450 licenses will be utlized during Phase 1 - USA and CA Regions) & the remaining 550 licenses will be utlized/deployed in Phase 2 as part of future intiative for Global Regions. QA Reviewed by Swetha Burugula - Dated 12/19/2025 Financials reviewed by Jamie Heller and Xun Miao on 1/12/26 prior to resubmission. | G: L3 | Active | L3 | 2026-03-02 | 2026-08-31
Business w/ Tech Initiative: TS-VL3-HybridCloud-GCPMigrateGoogleStorage | 90505 | 6702 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brandon Jackson, Ryan Ridgway | Some Issues | Changing primary ownership to Brandon J [2/26] To Submit for SL3: * Reviewed at Commercial PEL on 02/26/2025 - expecting approval by 02/27/2025 in tool to move forward for SL3 * Pending approval from SCO PEL - Brandon is following up 02/26/2025 for that approval * WIll then submit for SL3 as we need to be L3 approved to execute the necessary POC to determine how the migration will happen. There are some gaps in functionality that need solutions. FY25 - Rebaseline 03-27-25 | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-10-01 | 2026-12-30
Business Only Initiative: TS-VL3 Cons and opt backup/recovery | 14887 | 8179 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Patricia Frizzell, Shawn Keys, William Wixon | On Track | 10/7/25 Business plan changes required updated financials. Updated 5/13/25 No concerns noted 5/8/25 Milestones updated 4/11/25 FY25 Rebaselined | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-26 | 2026-10-15
Business w/ Tech Initiative: TS-VL4-ENDUSER-Windows RDS (Citrix Replacement) |  | 84419 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Christian A. Paez, Clifton E. Gurlen, Jane N. Atkinson | On Track | 07/25 - Initial work plan is being built to have all applications and GRID moved off Citrix by 7/2026. | G: L3 | Active | L3 Feedback Requested | 2025-08-11 | 2026-07-13
Business w/ Tech Initiative: TS-VL4-ENDUSER-Cirtix Optimization (International) |  | 92747 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Cathey Cooper, Paul Beardmore, Deborah A. Saverson, Lanny Jeffries, Paul R. Luker | On Track | 4/9/2026 - Entered March actuals. 2/17/2026 - Entered February actuals. 2/17/2026 - Corrected Jan KPI actuals. 1/20/2026 - Entered December & January actuals. 12/5/2025 - Entered November actuals. 11/13/2025 - Entered October actuals. 10/6/2025 - Entered September Actuals. 10/6/2025 - Entered Enterprise KPI as # of Maintained Applications. 09/11/2025 - Worked with Bob Noble and Ian McPhillips to correct cost savings calculations. Lower costs savings compared to forecast due to actual start delayed for getting into PV L3. 08/05/2025 - Work with Bob Noble and Patricia Frizzell to modify financials to remove forecast lines to add actuals line items. Also, updated KPI's to reflect a negative number to reflect the actual number of users that were migrated. 08/05/2025 - Updated Initiative Milestones & Risks to reflect scheduled start date of 07/31/2025. 07/09/2025 - Added Lanny Jeffries and Paul R. Luker as secondary I/O. 07/09/2025 - Entered June Actuals 06/03/205 - Changed Milestone #107156 to "Completed". All users have been migrated as of 05/21/2025. 06/02/2025 - Deleted KPI Baseline per Sourcing. Not needed but tracking through spreadsheets. 05/20/2025 - Removed ($13520) for labor costs from plan for April and May. Having it there resulted in alerts on April actuals which cannot be negative. 05/15/2025 - Confirmed no forecasted reductions in user count from baseline for May 2025. 04/22/2025 - Updated Milestones & Risks status to "In Progress". 04/10/2025 - Confirmed that initiative is ONLY for migrating users, so no additional architectural documentation is needed. 04/10/2025 - Updated Financial Plan to include FY25 Portfolio Costs for April and May 2025. Added KPI's per items in the Financial Plan. Added approved PPM#. 04/9/2025 - Uploaded Cost Summary Table provided by Finance. 04/7/2025 - Changed financials to align with new DRIVE Operating Model requirements. 04/3/2025 - Updated one-time implentation costs for salaries and wages. Not incremental. 04/3/2025 - NOTE: Regions Impacted is Europe only. Planview tool would not allow me to delete the others. EPSM lead will open a ticket to report this as an issue. 04/01/2025- Worked with Fianance lead to add financial forecasting data. FY25 Baseline. 03/28/2025 - Submitting to L3. 03/24/2025 - Updated Financials to reflect FY25 baseline. 03/17/2025 - Worked with Finance lead to add financial information and money step. 03/03/2025 - Underway and still on-track. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-04 | 2026-07-15
Business w/ Tech Initiative: TS-VL3-IMAGECloudMigrate |  | 98665 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Daniel R. Laughlin, Brandie J. Hill | On Track | 2025-05-08 DL - Finalized pricing is being worked out. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-12-31
Business w/ Tech Initiative: TS-VL3-Security-EUCohesity |  | 111253 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Deborah A. Saverson, Shelia R. Lomax, Cathey Cooper, Lanny Jeffries, KRISHNA PERI | On Track | 4/14/2026 - Our leadership has agreed to cancel this request. 2/9/2026 - Placing on hold approved by leadership for now 1/28/2026 - Awaiting leadership approval before moving forward. once approval has been received this initiative will be updated. 12/12/2025 - Updated count of applicances and excluded TNT as part of the scope. Requested to update to Protect Purple but unable to update. 11/13/25 - Updated KPIs 11/10/25 - updated financials and KPIs 9/10/25 - updated architectural document link because a request was being made for an architectural review that had already been completed. The original link to the document was broken because the original documentation was moved from the original folder. 06/10/25 Added Cathey Cooper and Deb Saverson as Secondary IO 06/24/25 QA Reviewed with Steve Kastner. Advised to doube check ESI field with Finance "DO NOT USE - ONE FEDEX" 07/01/25 Added Lanny Jeffries as sub IO | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL4-Security-Laptop Encryption Retire Trellix |  | 162641 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | URSULA MARKS | On Track | This will be retired by September 30, 2025. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration S&CDE-CRM-iSellData |  | 162645 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Elbony Mathews, Amanda Nevins, Vincent J. Romeo | On Track | 9/11- Add Amanda Nevins and Vincent Romeo as IO | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration S&CDE-CRM-NSLT |  | 162652 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Elbony Mathews, Amanda Nevins, Vincent J. Romeo | On Track | 9/11 - Add Amanda Nevins and Vincent Romeo | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-Infra-OneAutomation |  | 163303 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Brian Glover, Amit Prabhu, Peter Murphy | On Track | Heath is leaving this project | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-DB-EIWMigration S&CDE-CORE-Revenue Comp |  | 163306 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Hannah Rogers, Amanda Nevins, Vincent J. Romeo | On Track | This init was cancelled at the enterprise level. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: EIW to Atlas: Need alt wrkspc Corp AWE in eAtlas |  | 163359 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Warner Anthamatten | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: TS-VL3-SDLC-CBJenkinsRetirement |  | 166417 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Chris Warren, Amit Prabhu, Wallace Green (Wally) | On Track | LBC is in progress | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: D&T AIQ Learning Contract |  | 167725 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Lauren Krieger, Sangeeta Rai | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-03 | 2026-06-30
Business Only Initiative: EU Tech Modernization Strategy |  | 167728 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Kelly Rowland | On Track | On Track | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-11-21 | 2025-12-16
Business w/ Tech Initiative: TS-VL3-Messaging-AMQ Migration |  | 167779 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jonathan O'Brien | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: TS-VL2-CM-Retire-Wave3 |  | 167871 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Joseph Cooper | On Track | TS-VL2-CM-Retire-Wave3 will need to be cancelled due to work happening under another initiative so Tech Simplification can’t claim IT savings. I was told by Riz Mehkari ¦ Manager IT ¦ Retail Shipping/Parcel/MDM that this work is being done under DRIVE request 90113 (Single Point of Sale Completion). | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: TS-VL3-Integration-SHARE WS Utilization |  | 168056 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Chad Girnus | On Track | On Track | G: L3 | Active | L3 | 2026-01-14 | 2026-06-25
Business w/ Tech Initiative: EUM - Quantum Retirement |  | 169174 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jade Russell, Paul Thomson, Eric Joyner | On Track | On Track **03/12/2025 - Paul T** - I have removed the Zellis cost line from this Planview, as it is not able to recover this license cost by retiring Quantum. It is being recorded in PV ID 170548 - EU Mod 6 Months Savings **05/12/2025 - Paul T** - Revised values fo rthe CY25 spend and updated relevant fields as requried. | G: L3 | Active | L3 | 2028-05-31 | 2028-05-31
Business w/ Tech Initiative: TS-VL2-Address EFS (SHARE) and Share Id Retirement |  | 169489 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Katrice Manley, Nathan Nicol, Ellaina Elshennawi | On Track | 02/04/2025: Seeking EA support 12/31/2025: Finance has approved the NRB calculations 12/26/2025: Meeting with Finance scheduled 11/12/2025: On Track | E: L2 | Active | Portfolio Greenlight | 2026-04-01 | 2027-11-30
Business Only Initiative: EUM - EU Modernization 6 Month Savings |  | 170548 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Eric Joyner, Jade Russell | On Track | No longer Needed | E: L2 | Cancelled | L2
Business Only Initiative: EUM - EU Modernization 6 Month Modernization |  | 170551 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Jade Russell | On Track | On Track | G: L3 | Active | L3 | 2026-01-01 | 2026-06-11
Business Only Initiative: FXL DuplEx Mainframe Ops Excellence Efficiency |  | 177657 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Tasha Hamilton, Evan Hinson | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2026-01-14 | 2026-04-23
Business w/ Tech Initiative: TS-VL2-ES-CON-Migrate Archer Solutions to Onspring |  | 177745 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Reginald J. Bowens | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2025-09-01 | 2026-09-29
Business w/ Tech Initiative: TS-VL3-Azure-Tanium Migration to Cloud |  | 166054 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tessa R. Goodhead, Jeanette Wray, Angela Curran | On Track | This initiative is time sensitive and currently behind schedule, as the initial DRIVE demand (Work ID - 0112035) was initially created under Local Demand and progressed to L3 without question or issue. We are now repeating the process, which has caused delays that may impact contract negotiations and hardware support. Although the work remains on track, it is critical that this is expedited to avoid further delays. | G: L3 | Active | L3 Feedback Requested | 2026-07-30 | 2026-07-30
Business w/ Tech Initiative: [EUM] – OSC Retirement |  | 180464 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Krisztina Bardos-Szeky, Matthew (Matt) Beeston, Johannes Hellegering | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: TS-VL2-ES-NetGen FOCtoOMTforLHE |  | 142111 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kelly Martenson | On Track | 7/29/2026 - made requested changes, resubmitted to SL2. Note to EPM - Help ticket submitted to change ESI to tech simplification. | G: L3 | Active | L3 | 2026-06-15 | 2027-05-14
Business w/ Tech Initiative: TS-VL4-FSCM Replatforming-Due to Citrix Retirement |  | 187302 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Steven Elks, Aslam Mohammad | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: Engaging Deloitte for SMO |  | 187773 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Ashu Rawat | On Track | On Track | G: L3 | Active | L3 | 2026-02-09 | 2026-05-01
Business w/ Tech Initiative: TS-VL2-Con-ServiceNow – Svc Map+Agent Client Conn |  | 188639 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Tessa R. Goodhead, Angela Curran, Jeanette Wray, Noel W. Broadhurst, Allan Goddard, Michael J. Heys | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2026-05-28 | 2026-07-31
Business Only Initiative: TS-VL2-Con-ServiceNow-Lic.Uplift-ITSM+CSM+ApEng |  | 189077 | Business Only Initiative | IT - Tech Simplification | Data and Tech | Michael J. Heys, Allan Goddard | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: EUM - Decommission – Pre Customer Migration |  | 190258 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Jade Russell | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: CM - FF - Global Clearance Modernization |  | 192575 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Kelly Rowland, Chrystal E. Short | On Track | 4/24/2026 - LBC Completed 4/23. Waiting on L1 assessment; architectural assignment is based on priority ranking. Currently ranked at 115. 4/17/2026 - Moved to L1 on 4/16. Started on LBC. Need assistance from Finance to complete LBC- meeting scheduled for 4/21. Added attachments that explain what this initiative is about. 4/10/2026 - Entered init into Planview; went to Triage on 4/15/2026 - approved to move to L1. | C: L1 | Active | L1
Business w/ Tech Initiative: ITSM-ServiceNow Modernization |  | 192870 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Rajshri Vispute | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Ground Economy Sortation Migration |  | 192875 | Business w/ Tech Initiative | IT - Tech Simplification | Data and Tech | Adam Fettig | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: International UKG Timekeeping Implementation |  | 88482 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Christy Koch, Keith Cofield, Terrence A. Fischer, Kathy Werner | Some Issues | 4/24/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** Send SOW to Legal for final routing in Encore **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 4/17/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** Send SOW to Legal for final routing in Encore **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 4/10/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** Meet with PwC on next steps **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 4/3/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** meet with PwC on next steps **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 3/27/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** meet with PwC on next steps **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 3/20/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** meet with PwC on next steps **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 3/13/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** meet with PwC on next steps **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 3/6/26 **Weekly Key Accomplishments** SOW in review **Next Week’s Key Activities** meet with PwC on next steps **Leadership Awareness** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. OSS is reviewing the clock SOW and determining their next steps. 2/27/26 **Weekly Key Accomplishments** Received updated SOW from PwC Met with extended FedEx team to review SOW (University, Clocks, Change management) Received SOW for clock installation from Balliwick partner. **Next Week’s Key Activities** Review updates with PwC and FedEx team **Leadership Awareness or Decision Needed** Resource gap currently exists for Ops Tech team in the international space (ie Clocks). Team is working with UKG for break/fix pricing and with eplus (Bailiwick international partner) for installation pricing. 2/20/26 **Weekly Key Accomplishments** Received updated SOW from PwC **Next Week’s Key Activities** Review updates with PwC | G: L3 | Active | TEMP L3 - Enter L3 | 2026-02-02 | 2028-08-01
Business w/ Tech Initiative: PLANS - US Air Planning Labor & Rostering | 66886 | 9066 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Megan Le, Kathy Werner, Oladimeji O. Ogunbayo | On Track | 4/24/26: Near-Term Value Accomplishments/on-going: - Open office hours for management continues - ERMA load time fix - in progress - Estimated time is tentative beginning of May. The push back is due to testing cases failed and need to be adjusted and re-tested - 100% Employee setup in ERMA - Delaplex intiative entered in PV #19501 - Currently with PEO Upcoming: - 4/27 Go Live & Hypercare - Schedule generated 4/16 and will post Sunday 4/19 - Dawn's team will be on-site week of 4/27 - Focus on hands-off model. Team will shift into light coaching to help drive adoption, encourage app usage, and support consistent logins. They will hand off their own SP that will house training material and quick access to the tools 4/17/26: Near-Term Value Accomplishments/on-going: - Open office hours for management continues - ERMA load time fix - in progress - Estimated completion was pushed from mid April to closer to May. Fix was pushed to Test. Completed first round of testing with a few issues. IT reviewing and will update. - 100% Employee setup in ERMA - 4/16 MAPS generated Demand - Provided updated XML file to be tested on feasibility of schedule creation - Delaplex intiative entered in PV #19501 - Currently with PEO Upcoming: - 4/19 soft launch (posted for handlers on 4/12) - 4/27 Go Live & Hypercare - Schedule generated 4/16 and will post Sunday 4/19 4/10/26: Near-Term Value Accomplishments/on-going: - Open office hours for management to prepare for soft launch - ERMA load time fix - in progress - Estimated completion mid April - 100% Employee setup in ERMA - 4/10 Eddie to provide MAPS generated Demand - Provided XML file to be tested on feasibility of schedule creation - Delaplex intiative entered in PV #19501 - Paula assisting with push through to the next stages Upcoming: - 4/19 soft launch (posted for handlers on 4/12) - 4/27 Go Live & Hypercare 4/2/26: Near-Term Value Accomplishments/on-going: - Onsite visit copntinues - focus on Handler training - Presented to Terry Brown and team on progess - Discussed phase 2 options for timekeeping - ERMA load time fix is currently being worked on - Estimated completion mid April - 100% Employee setup in ERMA as of April 3 Upcoming: - Week 4/5: Virtual SME support, Managers, Leads, and Ramp Agents will continue to promote adoption in preperations of soft lauch, and office hours will be held to support management - 4/19 soft launch - 4/27 Go Live & Hypercare - 4/10 Eddie to provide MAPS generated Demand Leadership awareness: Delaplex(timekeeping integration) not prioritized or funded, will impact value add of POC 3/25/26: Near-Term Value Accomplishments/on-going: - Onsite visit 3/23 validated managers were able to login to ERMA successfully and all functions work as expected - ERMA load time is 20 mins. Intake form for the SPaT has been submitted. 3/27 call with team to discuss path forward - HR TAPS first onsite training completed Upcoming: - Continued onsite training - 4/13 soft launch - 4/27 Go Live & Hypercare - 4/10 Eddie to provide MAPS generated Demand Leadership awareness: Delaplex(timekeeping integration) not prioritized or funded, will impact value add of POC 3/19/26: Near-Term Value Accomplishments/on-going: - Completed the ERMA/Blue Yonder setup for the Memphis hub in preperations for onsite training - Any changes will be made onsite 3/23 - HR TAPS completed drafted training matieral and presentations for onsite training week 3/23 Upcoming: - 3/23 start onsite trainings - 4/13 soft launch - 4/27 Go live & Hypercare - 4/10 Eddie to provide MAPS generated Demand Leadership awareness: - Duplex(timekeeping integration) not prioritized or funded, will impact value add of POC 3/13/26: Near-Term Value Accomplishments/on-going: - Memphis onsite visit 3/9 - 3/12 - Team met with 3 PoC managers to gather discovery information in preperations for training week - Staff meeting with Terry | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-04 | 2027-05-24
Business w/ Tech Initiative: Contract management and negotiation - Workday | 16575 | 9288 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Bill Stanek, Elizabeth E. Canale, Claudia Versey, Deirdra L. Royston | Some Issues | **12/22/2025** - Enterprise launch date has been moved to late February/early March 2026. The delay will allow HRIT and business partners more time to complete configurations to ensure a better user experience for learners. No updates have been provided regarding the GWC's approval of WDL in Germany. System updates have been made in WDL and are on schedule for the FLC for those learners and their managment chain to be restricted/remain in the proper LMS until the approval has been granted. Contract extension/Cost updates have been provided to HRIT leadership from SAP SuccessFactors if the aggreement needs to be extended beyond June 13, 2026. **11/6/2025** - No new updates this week. **10/23/2025** - We received an update regarding the (General Works Council) GWC approval for WDL. FedEx Management was able to speak with the Labor Relations team to get an understanding of the process for the conciliation linked to their refusal of Workday Learning. Unfortunately, there is no clear timeline on how long the conciliation process will take and it is highly dependant on multiple factors. First, the actual process could not commence until there was an official rejection by the GWC as the request must go to court for a judge to decide if the process can move forth or not. The team has already been collating the needed information/data to submit the case to courts for consideration. This information is with the FedEx legal team for review with an aim to submit to the courts by the end of October. Once submitted, a court date would be set for initial review. The process can take up to six weeks. The GWC will challenge the need for conciliation in the same way that FedEx will push for it. Worst case, the judge reject conciliation and rule that further negotiations are needed before it could proceed. This seems highly unlikely since the GWC have refused to negotiate to this point. If the judge agrees to conciliation, a chairperson would be elected to run the process. Based on their availability, it would take between 2-3 months to actually start the conciliation meetings. At the latest, these meetings could start at the end of March or beginning of April 2026. As for the conciliation, timing can vary depending on the level of information needed and the challenges put forward. This could potentially take up to 5 months (August/September 2026) which will impact the SAP SuccessFactors contract that is set to expire June 13, 2026. We will continue to receive updates as the process goes on and develop contengencies (contract extension) once we have a better understanding of timing. **10/2/2025** - Enterprise data conversion process has begun and will continue through October 17. Data validation taking place for completed conversions. Post data conversion, HRIT will configure the agreed upon catalog structure and grant production access to business partners with WDL security roles for validation and final production setup for their learners. Meeting with German Works Council scheduled for 10/10 to discuss use approval of WDL. **5/5/202** - Rebaseline with assistance from Patty Yardas. She instructed us on what to put in the various financial columns. **3/6/25** Financials are up to date and project is on track. This initiative is being placed on hold until a new Application Rationalization Back Office Initiative is stood up. Once the App Rat Initiative is stood up, this initiative will be moved. This was reviewed at the ITAM POD Lead Meeting on 2/23/24 and rationale for moving to a hold status was approved by John Jamison in Finance. **10/10/2024** - Child Initiative # 98683 created under Domain - Data & Tech; POD - IT Applicaiton Optimization to track the retirement of FLC and migration to Workday Learning, generating $3.2M savings per year beginning in FY27. **10/10/2024** - Child Initiative #98684 created under Domain - Data & Tech; POD - IT Workforce Strategy to track reduction in pro fees associated in movin | G: L3 | Active | TEMP L3 - Enter L3 | 2022-07-01 | 2026-12-31
Business w/ Tech Initiative: UKG Enterprise Implementation | 87012 | 6933 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Christy Koch, Keith Cofield, Kristy Mitchell, Edward Knotek, Bill Stanek, Nicole Craig | Some Issues | 4/17/26 **Weekly Key Accomplishments** Working with compensation on overall pay harmonization for U.S. and Canada - CRC & UKG requirements being discussed - expected completion 4/30 High level timeline created and then sequencing discussions started around all the dependencies occurring with UKG. Operation (location) mapping sessions kicked off with Enterprise Architecture. This will be bundled in the productivity value bundle: Roster management including worker assignment to operation/work zone first priority to work through with EA. **Next Week’s Key Activities** Continuing to build an integrated timeline with more detail. Develop list of open architecture decisions and assign owners and dates. Pay rule harmonization meetings to continue including Maintenance, Canada and Puerto Rico. Connect with Brad Bozman and Kevin Harris to secure long-term leadership ownership for Work Zones. Overall planning session with Payroll & Timekeeping: Payroll continues to actively engage business partners to assess impacts and complete business rationalization requirements, with a targeted handoff to Payroll IT by September 1. Meeting with FP&A and FIH teams to align GL accounts to one of the current processes or a preferred future state. Determination is for FEC overall and will address dollars and hours. Decision on approach is required by 4/30/2026 to ensure configuration for OneTime can continue. Engage PWC to define the end-to-end business process for timekeeping and cost allocation to avoid spinning on legacy Ground vs. Express differences. **Items needing additional focus** IT Architect Resource moved to FedEx Freight. High level impact to current architecture. Architecture work for Odyssey Changes to Legacy Systems and for OneTime are not completed. Pilot contract voting is opening soon and will run through early June. If approved, it will trigger necessary configuration changes for Crew Pay timekeeping. Payroll business team is completing a preliminary impact assessment. Final execution will require a shift in both Payroll Business and Payroll IT resources to support this priority initiative 4/17/26 **Weekly Key Accomplishments** Working with compensation on overall pay harmonization for U.S. and Canada - CRC & UKG requirements being discussed - expected completion 4/30 High level timeline created and then sequencing discussions started around all the dependencies occurring with UKG. Operation (location) mapping sessions kicked off with Enterprise Architecture. This will be bundled in the productivity value bundle: Roster management including worker assignment to operation/work zone first priority to work through with EA. **Next Week’s Key Activities** Continuing to build an integrated timeline with more detail. Develop list of open architecture decisions and assign owners and dates. Pay rule harmonization meetings to continue including Maintenance, Canada and Puerto Rico. Overall planning session with Payroll & Timekeeping: Payroll continues to actively engage business partners to assess impacts and complete business rationalization requirements, with a targeted handoff to Payroll IT by September 1. Meeting with FP&A and FIH teams to align GL accounts to one of the current processes or a preferred future state. Determination is for FEC overall and will address dollars and hours. Decision on approach is required by 4/30/2026 to ensure configuration for OneTime can continue. **Items needing additional focus** IT Architect Resource moved to FedEx Freight. High level impact to current architecture. Architecture work for Odyssey Changes to Legacy Systems and for OneTime are not completed. A tentative Pilot CBA agreement has been reached, and Payroll business team is completing a preliminary impact assessment. Final execution will require a shift in both Payroll Business and Payroll IT resources to support this priority initiative. 4/10/26 **Weekly Key Accomplishments** Working with compensation on overall pay harmonization for | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-12-31
Business w/ Tech Initiative: Labor Insights Platform (LIP) |  | 131685 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Kathy Werner, Dustin Gambino | On Track | 4/23/26 – Accomplished this week: Core HR LIP – First Advantage I-9s and First Advantage background check data (used for hiring stages and cost per hire metrics) – MTPs completed, ESG Employee Breakdown data (supports ESG reporting) – MTP completed; Datahub Migration – Overall Progress at 65%; Learning – Overall Progress at 90% (all ingestion in Prod; 9 tables being revised); Paradox – In progress with re-engineering data pipeline to enable dependencies for Hire to Retire strategy, MTPs completed on 4/20. Key accomplishments planned for next week: Core HR LIP – Ongoing activities including iterative progress on ingestions, curations, infrastructure; Datahub Migration – Standardized ingestion progress on tables; Continued data analysis for Curated layer; Unity Catalog batch progress including unit testing; Learning – Curated layer data validation and sign off; Paradox – Progress towards re-engineering data pipeline to enable dependencies for Hire to Retire strategy. Note: LIP continues to show a loss as costs are being incurred for (1) Outside Service Contracts, (2) Pro Fees, and (3) Salaries. This is anticipated as LIP is an enabler. 4/16/26 – Accomplished this week: Core HR LIP: VNDLY (contractor data for contingent workforce metrics) – MTP completed; Unity Catalog infrastructure created; Workday Performance Improvement and Workday Personal Development (enables personnel metrics) – Ingestion complete and released for UAT; Datahub Migration – Overall Progress at 65%; Learning – Overall Progress at 90% (all ingestion in Prod; 11 tables being revised); Paradox – In progress with re-engineering data pipeline to enable dependencies for Hire to Retire strategy. Key accomplishments planned for next week: Core HR LIP – Ongoing activities including iterative progress on ingestions, curations, infrastructure; Datahub Migration – Standardized ingestion progress on tables; Continued data analysis for Curated layer; Unity Catalog batch progress including unit testing; Learning – Curated layer data validation and sign off; Paradox – Progress towards re-engineering data pipeline to enable dependencies for Hire to Retire strategy. Note: LIP continues to show a loss as costs are being incurred for (1) Outside Service Contracts, (2) Pro Fees, and (3) Salaries. This is anticipated as LIP is an enabler. 4/9/26 – Accomplished this week: Core HR LIP: FEC Dock Engineering TLH Goals (enables total labor hours goals for analytics in the Workforce Management Dashboard) – post-Prod validation and sign off; FEC – TLH Actuals (total labor hours actually realized for goal attainment calculations in the Workforce Management Dashboard) – post-Prod validation and sign off; Cyber Security learning data (supports InfoSec reporting) – UAT in progress. Datahub Migration – Overall Progress at 65%; Learning – Overall Progress at 90% (all ingestion in Prod; 12 tables being revised); Paradox – In progress with re-engineering data pipeline to enable dependencies for Hire to Retire strategy. Key accomplishments planned for next week: Core HR LIP – Ongoing activities including iterative progress on ingestions, curations, infrastructure; Datahub Migration – Standardized ingestion progress on tables; Continued data analysis for Curated layer; Unity Catalog batch progress including unit testing; Learning – Curated layer data validation and sign off; Paradox – Progress towards re-engineering data pipeline to enable dependencies for Hire to Retire strategy. Note: LIP continues to show a loss as costs are being incurred for (1) Outside Service Contracts, (2) Pro Fees, and (3) Salaries. This is anticipated as LIP is an enabler. 4/2/26 – Accomplished this week: Core HR LIP: VNDLY (contractor data providing real-time visibility into contingent workforce metrics) – Unity Catalog tables created in non-Prod; FEC Dock Engineering TLH Goals (enables total labor hours goals for analytics in the Workforce Management Dashboard) – Unity Catalog tables and workflows created in | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-03 | 2028-02-08
Business w/ Tech Initiative: Odyssey (formerly Recharge Phase 3) |  | 86611 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Bill Stanek, Christy Begley, Lee Frye, Jay Boyles, William Lamar, Jeannie Idaughe | On Track | 24.Apr.26 Accomplishments • Closed several outstanding RAID items including ○ Job Architecture new job classifications. ○ Aligned and agreed upon default standard hours for future state Odyssey, with PT 20 and FT 40. ○ Determined ownership and alignment around peak management worker types like seasonal and special assignment, providing integrations and recruiting clarity for future state configuration. ○ International requirements on collection of personal information for recruiting completed. ○ Decision to move Customer Experience workers off Workday Timekeeping to Dimensions. • Completed configuration of performance rating calculated field and Leave of Absence plans. Next • Job Architecture at risk to complete design by Apr 30 deadline. Team will meet Monday to determine what items will remain. Timeline risk depends on what items are identified. • Learning audience alignment with the updated Job Architecture across WDL production and Odyssey testing tenant • Planning for Workday cutover and deployment execution • Alignment between HTR and Odyssey on Deployment Timeline, Operating Model, and Process Design • All design complete Apr 30 • Functional Testing June 22 What we are watching • Potential Pilot Agreement impacts on Payroll and Airline technology capacity. Assessment pending. • Remaining Job Architecture items • Infosec to analyze need for controls on sensitive data into ServiceNow - could delay integration. 21.Apr.26 * Additional $545,000 expenses added to extend timetable to March 2027: * SCO $50,000 (over 8 months) for FAMIS ACCN & Abinitio * D&AI: $495000 (over 10 months) for Odyssey-HR datahub migration to LIP extension 10.Apr.26 Accomplishments • Decision made to create "Silver Build" Workday test tenant to bring in more recent production data for testing and use as a practice for the "Gold Build" production tenant. • Job Mapping File received from Aon (to be confirmed). • Location Data Product development is complete and integration is being tested. • Merit and Leave of Absence plans completed. Validation of compensation and core configuration is being impacted due to resources working on Fairway, expected to be relieved after Apr 26. • Integrations testing overall end-to-end readiness at 60%. • ServiceNow is addressing a newly identified risk regarding sensitive data from Workday. • Odyssey updated presented to Commercial PEL for awareness. • Additional cost of $121,147 added to financial plan (Apr-Aug 2026) for Accenture work on the Compensation Rate Calculator (CRC). Next • All design decisions and functional configuration needs to be complete by end of April. • New core job setups to be published Apr 16-17. • Ongoing Timekeeping discussions about job code alignment and employee movement between Timekeeping systems. • Paradox build to begin Apr 13. • Discussions to include Capabilities for Worker assignment to operational zone and operational location hierarchy maintenance into GCS Value Bundle. * Proof of Concept exercise will apply AI to selected Odyssey impacted downstream systems to analyze, plan, and execute adoption. 3.Arp.26 Accomplishments • Payroll Testing Timeline has been agreed on. Discovery and Alignment will be complete by end of April and Testing will run July 6 through Nov 30. • Location workstream has decide to move two capabilities to a new initiative, to be owned by HR Timekeeping: Operational Zones and Operational Hierarchy. Decision was based on increased scope and complexity. • Timekeeping: concern over how to solution for issue of legacy Ground Exempt and staff hourly currently using Mytime that will also flow to Workday Timekeeping - how to identify and keep from entering two Timekeeping systems at once. Continue to work on Internation impacts to the Payroll PECi file. • Delay in expected Apr 1 delivery of Job Architecture workbook, which would provide IT additional profiles and details on Business Processes and systems need, i | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-08 | 2034-12-15
Business w/ Tech Initiative: PLANS - US Air Network Scheduling |  | 93165 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Megan Le, Samantha Hedges | On Track | 4/24/26: Near-Term Value Accomplishments/on-going: - Open office hours for management continues - Schedule creation continues to populate with minimal schedule changes - 90% of handlers have downloaded the Blue Yonder application as of 4/24 (up from 88%) - Login Dashboard: 65.6% complaint as of last update 4/22 - 5% at introduction on 4/16 - 33% as of 4/20 - Tablets still experiencing 403 error - impacting all users, not just Memphis. Identified the issue, working on the fix - provided management with workaround solution - Delaplex initiative entered in PV#19501 - With PEO Upcoming: - 4/27 Go Live & Hypercare - Schedule generated on 4/16 and will be posted Sunday 4/19 - Dawn's team on-site week of 4/27 - Focus on hands-off model. Team will shift into light coaching to help drive adoption, encourage app usage, and support consistent logins. They will hand off their own SP that will house training material and quick access to the tools - Continue to monitor login dashboard and BY audits to proactively reach out when they see concerns 4/17/26: Near-Term Value Accomplishments/on-going: - Open office hours for management continues - Schedule generation ran successfully for management to make any changes needed for week 4/27 - 88% of handlers have downloaded the Blue Yonder application. Above target of 80% - Login Dashboard has been available for management. Will start tracking % - Tablets still experiencing 403 error - impacting all users, not just Memphis. Open ticket with FedEX IT and Blue Yonder to investigate - provided management with workaround solution - Delaplex initiative entered in PV#19501 - With PEO Upcoming: - 4/19 soft launch (posted for handlers on 4/12) - 4/27 Go Live & Hypercare - Schedule generated on 4/16 and will be posted Sunday 4/19 4/10/26: Near-Term Value Accomplishments/on-going: - Open office hours for management to prepare for soft launch - Schedule generation ran successfully for management to make any changes needed prior to schedule postin gon 4/12 for week 4/19 - 87% of handlers have downloaded the Blue Yonder application. Above target of 80% - Tablets still experiencing 403 error - impacting all users, not just Memphis. Open ticket with FedEX IT and Blue Yonder to investigate - provided management with workaround solution - Delaplex initiative entered in PV#19501 - Paula assisting with pushing through to the next stages Upcoming: - 4/19 soft launch (posted for handlers on 4/12) - 4/27 Go Live & Hypercare 4/2/26: Near-Term Value Accomplishments/on-going: - Onsite visit copntinues - focus on Handler training - Presented to Terry Brown and team on progess - Discussed phase 2 options for timekeeping - Mock schedules have been successfully ran in preps for soft launch - 80% of handlers have downloaded the Blue Yonder application. Target we were shooting for as the app is not mandatory - Tablets still experiencing 403 error - impacting all users, not just Memphis. Open ticket with FedEX IT and Bluw Yonder to investigate - provided management with workaround solution Upcoming: - Week 4/5: Virtual SME support, Managers, Leads, and Ramp Agents will continue to promote adoption in preperations of soft lauch, and office hours will be held to support management - 4/19 soft launch - 4/27 Go Live & Hypercare - 4/10 Eddie to provide MAPS generated Demand Leadership awareness: Delaplex(timekeeping integration) not prioritized or funded, will impact value add of POC 3/25/26: Near-Term Value Accomplishments/on-going: - Flipped initiative back to active to align with the work being done for the Memphis PoC for scheduling - Onsite visit 3/23 validated managers were able to login to BY successfully and all functions work as expected - PHs were also able to login successfully. (handful were not - currently investigating) - HR TAPS first onsite training completed - Mock schedule were created to support training alignment and soft go-live readiness | C: L1 | Active | TEMP L1 - Create L1 LBC | 2027-01-08 | 2027-01-08
Business w/ Tech Initiative: FAMIS-R Timecard Entry for FAMIS (EU) |  | 131683 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Anupriya Jailaja Prem, Ronald Thies, Dimitrios-Agamemnon Christodou, Kostas Adamopolous, Ido Shmueli | On Track | 10/09/2025 **Accomplishments:** Oct 09 - Met with Finance to get an understanding of how to provide value; Adam Bahr will be our contact Oct 09 - Clarified scope of effort to just EU and updated title of request. Reviewed existing PFS functionality. **Upcoming Activities:** Begin Lean Business Case **Leadership:** Requesting leadership support for resourcing **Risks:** Need to offload items from FAMISR. The risk is high to miss financial targets in Operations, which account for a very big part of the overall operating expenses. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: MobileManager for One FedEx |  | 112923 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Ronald Thies, Gregory Schaefer, Anupriya Jailaja Prem | On Track | 4/23/2026 - Met with Architecture Enablement (Harsh Garg) and Technology Platforms & Infrastructure (Fawsy Bendeck & Gayatri Jadhav) to review effort. - Discussed approach to move apps in light of Azure to GCP changes impacting the next 6 months - Providing Architecture Diagram - Documenting db schemas in preparation for data discovery 4/17/2026 - Reviewing feasibility and number of contractors to assist with work - Finalizing project plan dates based on resource and contractor availability - Submit to L2 once plan is entered 4/9/2026 - Data discovery underway and will review results on 4/15 - Working with Data and AI to discuss go forward options with Azure versus GCP - High level MM development project plan internally reviewed and ready for submission - Completing RACI from POC with Data and AI as well as HR Analytics 4/2/2026 - Worked on Value Bundle with Enterprise Strategic Program Management. Contains 9 other efforts ready for submission - Finalziing high level plan for submission in Planview - Mapping database in prepartion for Data Discovery in Atlas 3/20/2026 - On 3/18, worked with Kendra Yarbrough and completed the following sections in preparation for L3 submission: - Step 2: Complete Cross Functional and Strategic Alignment - Step 3: Complete Initiative Milestones & Risks - Step 4: Reference L1 Estimated Financial Plan - Step 5: Complete L2 Refined Financial Plan - Step 6: Complete Internal Audit & Compliance - Step 7: Review Change Management - Step 8: Complete L2 Tech Requirements - Working to complete Step 9, Complete Epic Creation Post PRT - Continue to Work on the Value Bundle with Enterprise Strategic Program Management and the broader IO team to push this initiative forward 2/20/2026 - Submitted LBC 2/13/2026 - Updated LBC with enhancements and incremental time savings - Met with Katelyn Brinkman on Tue Feb 10th - updated KPI to # of Actively Maintained Apps as recommended by Adam Bahr Upcoming Activities: - Meeting w/Adam Bahr scheduled for Wed Feb 18th - Finalize Lean Business Case 2/5/2026 - Met with Dataworks and HR Analytics on 2/3 to review POC - Data transformation completed by Dataworks on 2/3 - IMAGE access granted to GEIS resources on 2/3 - Completing business case with Adam Bahr (met on 2/6) - Next steps: submit LBC 1/29/2026 - Current priority is 8 - Completing business case template provided by Adam Bahr - POC with Dataworks and HR Analytics is finalizing data transformation. - Currently documenting the enhancements we could provide utilizing the capabilities available within the Azure ecosystem and determining cost savings. Risks: - If the application remains in the SBE environment until IT mandates a migration, there is a significant risk of encountering the following challenges: 1) The absence of a viable target environment for migration and 2) Insufficient time and/or resources to execute the migration effectively. -If we are not permitted to migrate from the current SBE environment, we risk forfeiting the savings we have already achieved. Next Steps - GEIS finalze data transformations and connect via PowerBI 1/23/2026 - Recently updated to a priority of 8 - Adam Bahr providing templates for cost estimates, benefits, and business case so we can complete LBC 1/18/2026 - Met with Adam Bahr. Early this week, he will provide templates for cost estimates, benefits, and business case so we can complete LBC. - Recently updated to a priority of 8! 11/17/2025 MVP1 are the following apps: Autoverify BLADE Hours of Service Compliance Training eVIR DEX-STAT Exceptions ePST Fuel Compliance Stop Proximity Time Card Audit Time Card Exceptions Time Clock Issues Virtual Checkride 11/06/2025 **Accomplishments:** - Working on booster slide - Continued updates on the individual apps in MM 10/30/2025 **Accomplishments:** - Meet Tuesday Nov 4 with the HR Analytics team to determine current state and which numbers have been generated to identify gaps. - Dataworks has committed to pro | E: L2 | Active | L2 | 2026-04-01 | 2027-04-14
Business Only Initiative: One FedEx Common Tasks |  | 92013 | Business Only Initiative | SGA-GCS - Business Enablement | SG&A | Ronald Thies, David J. Dickinson | On Track | 11/6/2025 **Accomplishments:** - On Road tasks completed. Compiling results - Met with Planning system teams and confirmed regulatory and exceptions have already been covered within the other categories - Updated milestones - Planning POCs for post peak 10/30/2025 **Accomplishments:** - Continung to meet with team each Friday and work through task reduction for On Road tasks - Requested detailed scheduling tasks from VALET team for Regulatory and Exception Oct 10: Team meeting starting on On Road tasks 10/16/2025 Accomplishments: -Met with On Road team to review / reduce tasks -Updated: What is the Money Step and how will it be measured (proposed task reduction) -Working on POC for VALET and EDP Upcoming Activities: -Meet to discuss Regulatory -Meet to discuss Exceptions Oct 24: Start meeting for Exceptions TBD: Regulatory POCs for task reduction pilot - Ticket enetered for EDP - VALET POC Complete - Admin - Training - Inbound - Outbound - Sort Codes - Transport Remaining - Exceptions - Regulatory | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-01 | 2026-02-13
Business w/ Tech Initiative: Business w/ Tech Initiative: Launch Zone for One F |  | 108023 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Jimmy Helms, Gregory Schaefer | Some Issues | 4/16/2025 -Working with Kendra Yarbrough and Adam Bahr to complete LBC Leadership: Requesting leadership support regarding the hosting of Insights Launch Zone within the Dataworks ATLAS Ecosystem. Risks: -If the application remains in the SBE environment until IT mandates a migration, there is a significant risk of encountering the following challenges: 1) The absence of a viable target environment for migration and 2) Insufficient time and/or resources to execute the migration effectively. -If we are not permitted to migrate from the current SBE environment, we risk forfeiting the savings we have already achieved. --------------------------------------------------------------------------- 4/9/2025 Stalled: -Working with Kendra Yarbrough and Adam Bahr to complete LBC Leadership: Requesting leadership support regarding the hosting of Insights Launch Zone within the Dataworks ATLAS Ecosystem. Risks: -If the application remains in the SBE environment until IT mandates a migration, there is a significant risk of encountering the following challenges: 1) The absence of a viable target environment for migration and 2) Insufficient time and/or resources to execute the migration effectively. -If we are not permitted to migrate from the current SBE environment, we risk forfeiting the savings we have already achieved. ----------------------------------------------------------------------------- 4/2/2025 Stalled: -Working with Kendra Yarbrough and Adam Bahr to complete LBC Leadership: Requesting leadership support regarding the hosting of Insights Launch Zone within the Dataworks ATLAS Ecosystem. Risks: -If the application remains in the SBE environment until IT mandates a migration, there is a significant risk of encountering the following challenges: 1) The absence of a viable target environment for migration and 2) Insufficient time and/or resources to execute the migration effectively. -If we are not permitted to migrate from the current SBE environment, we risk forfeiting the savings we have already achieved. ------------------------------------------------------------------------------- 3/26/2025 Stalled: -Continue to Work on the Value Bundle with Enterprise Strategic Program Management and the broader IO team to push this initiative forward -Working with Kendra Yarbrough and Adam Bahr to complete LBC Leadership: Requesting leadership support regarding the hosting of Insights Launch Zone within the Dataworks ATLAS Ecosystem. Risks: -If the application remains in the SBE environment until IT mandates a migration, there is a significant risk of encountering the following challenges: 1) The absence of a viable target environment for migration and 2) Insufficient time and/or resources to execute the migration effectively. -If we are not permitted to migrate from the current SBE environment, we risk forfeiting the savings we have already achieved. ------------------------------------------------------------------------------- 3/19/2025 Stalled: -Continue to Work on the Value Bundle with Enterprise Strategic Program Management and the broader IO team to push this initiative forward -Adam Bahr to determine appropriate hourly run rate for operations management -Kendra Yarbrough to put focus on this initiative Upcoming Activities: -Finalize Lean Business Case Leadership: Requesting leadership support regarding the hosting of Insights Launch Zone within the Dataworks ATLAS Ecosystem. Risks: -If the application remains in the SBE environment until IT mandates a migration, there is a significant risk of encountering the following challenges: 1) The absence of a viable target environment for migration and 2) Insufficient time and/or resources to execute the migration effectively. -If we are not permitted to migrate from the current SBE environment, we risk forfeiting the savings we have already achieved. -------------------------------------------------------------------------------- 3/12/2025 Stalled: -Adam Bahr to determine a | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: One FedEx Common Calculations |  | 91980 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Jimmy Helms | On Track | 4/16/2025 -Team is conducting Data Discovery and Source-to-Target mapping -Team has identified and documented data elements needed for Timecards, Scans, Locations, and Employees -Meeting with Data and AI on Wed this week to discuss identification in ATLAS -Determine MVP1 -Data & AI to identify platform architects to engage ------------------------------------------------------------------------ 4/9/2025 -Team is conducting Data Discovery and Source-to-Target mapping -Determine MVP1 -Data & AI to identify platform architects to engage ------------------------------------------------------------------------ 4/2/2025 -Team is conducting Data Discovery and Source-to-Target mapping -Determine MVP1 -Data & AI to identify platform architects to engage ------------------------------------------------------------------------ 3/26/2025 -Continue to Work on the Value Bundle with Enterprise Strategic Program Management and the broader IO team -Conducting Data Discovery and Source-to-Target mapping -Determine MVP1 -Data & AI to identify platform architects to engage ------------------------------------------------------------------------ 3/19/2025 -MD level update with Data & AI, IT, People Analytics, and GEIS was on Tue Mar 17th -POC has been completed -Continue to Work on the Value Bundle with Enterprise Strategic Program Management and the broader IO team to push this initiative forward -Team is conducting Data Discovery and Source-to-Target mapping -Determine MVP1 -Data & AI to identify platform architects to engage ------------------------------------------------------------------------ 3/12/2025 -Working on the Value Bundle with Enterprise Strategic Program Management and the broader IO team -Architecture Diagram has been created -Service Principal and Power BI have been documented -Technical Retrospective has been created -Follow up meeting to review POC documentation scheduled for Fri Mar 13th -Progress Update with Data & AI, IT, People Analytics, and GEIS on Tue Mar 17th -Conduct Data Discovery and Source-to-Target mapping -Determine MVP1 ------------------------------------------------------------------------ 3/5/2025 -Data & AI, IT, People Analytics, and GEIS met on Tue Mar 3 to discuss POC progress -Data and AI targets Fri Mar 6 for completion of Service Principal changes -Meeting to Document POC scheduled for Fri Mar 6th -Conduct Data Discovery and Source-to-Target mapping -Determine MVP1 -Close this initiative and roll it into Operational Productivity Modernization (Request# 0018044) ------------------------------------------------------------------------ 2/26/2025 Accomplishments: -Items that went to CAB on Wednesday Adding Service Principal to Databricks Workspace Adding SQL Warehouse Adding Service Principal to Key Vault Pipelines for gateway registration/gateway installation Azure Virtual Machine setup to host gateway. Upcoming Activities: -Setup Service Principal once approved -Meeting to Document POC scheduled for Fri Mar 6th -Conduct Data Discovery and Source-to-Target mapping -Determine MVP1 -Work on Lean Business Case ------------------------------------------------------------------------ 2/19/2025 Accomplishments: -Waiting on CAB approval for the Service Principal changes -Met w/Data and AI team Tue Feb 17th Upcoming Activities: -Setup Service Principal once approved -Document POC -Conduct Data Discovery and Source-to-Target mapping -Determine MVP1 -Work on Lean Business Case ------------------------------------------------------------------------ 2/12/2025 Accomplishments: -We have a first draft of the Power BI report Upcoming Activities: -Setup Service Principal after Valentine’s Day Freeze 2/16/26 -Meeting w/Craig Monyhan scheduled for Tue Feb 17th -Finalize Power BI Report -Work on Lean Business Case utilizing Adam Bahr's assistance for the financials ------------------------------------------------------------------------ 2/5/2025 Accomplishments: -Developers have access to the Da | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Workday Learning Report Development |  | 177433 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Tracy Peto | On Track | Work has been completed with Accenture resources. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LIP Based AI Agent in Enterprise People Analytics |  | 179923 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Nathaniel Marlette, Jamie Nelson | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Operational Productivity Modernization |  | 188181 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Ronald Thies, Anupriya Jailaja Prem | On Track | 4/23/2026 - Value bundle being reworked as it exceeds the 18 month target time frame due to size and scope - Review underway to determine Value Prop and if Customer Service Risk may occur - Team continuing to meet and document capabilities. Results will become 1.) capabilities for existing PFS systems or 2.) capabilities for a new system - 4/17/2026 - Submitted LBC 4/9/2026 - Continuing to have mini-workshop meetings to understand timelines, capabilities needed, and future state metrics. Met with Time Keeping on 4/7. Next meetings are - 4/10 w/ Angela Julian - 4/13 w/ payroll - 4/14 w/ ERMA - 4/15 w/ Workday - Value Bundle ready for submission 4/2/2026 - Worked on Value Bundle with Enterprise Strategic Program Management. Contains 9 other efforts ready for submission - Enterprise Business Architecture completed the L1 Assessmenton 3/31 - Presenting on Friday 4/3 at the L1 Alignment meeting 03/20/2026 - Met last week on 3/17, 3/18, and 3/19 to work on the Value Bundle with Enterprise Strategic Program Management and the broader IO team to push this initiative forward. - Discussions on 3/18 with Chrissa Laib on the overall sizing efforts needed to retire three large systems and possibly submitting as smaller efforts of manageable size. | E: L2 | Active | L2 - Enter Value Prop
Business w/ Tech Initiative: Ops Engineering Planning Tool(s) Enhancements |  | 192974 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Zachary James | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: ERMA Automated Availability Changes |  | 159031 | Business w/ Tech Initiative | SGA-GCS - Business Enablement | SG&A | Kara E. Lombardo, Megan Le | On Track | 9/10/25 * Have not gone through any architecture review * Do not know answers to following sections * Financial * Key Stakeholders & Groups - Dependencies * Implementation * Biz w/ Tech Additional Info | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: EE 2.0 Global Assets Reorg - Lever A: SurfCo Prod | 96841 | 7603 | Business Only Initiative | SGA-GCS - Source to Pay | SG&A | Brian Schroeder, Jason Walton, Tamara Maresh-Carver, Charmaine Santarelli | On Track | 6/6 - Updated May actuals in Planview 5/9 - Updated April actuals were entered into Planview. 4/25 - Team is in L5 and will track savings. 4/11 - The team is now in L4 and will track savings. 4/4 - Submitted to L4, awaiting final approvals. 3/28 - The team continues to work through the financials and new attrition rates to be able to enter L4. The team will enter teh new financials by 3/31. 3/21 - Need to re-forecast to update planned savings for the initiative based off actual turnover rates as well as convert to the FY28 NRB. Met with FInance on 3/21 and will perform the re-forecast work next week and plan to submit to L4 within 2 weeks. 3/14 - Approved into L3, now monitoring attrition of impacted resources. 3/7 - Currently awaitng approval with Claude Russ to go into L3. 2/28 - Currently awaitng approval with Claude Russ to go into L3. 2/18 Just submitted to L3 on 2/14 and awaiting leadership approval. Will work with Finance to understand what is required for L4, as this initaitve is utilizing voluntary turnover as the savings driver. The Money step was submitted as February as that was the first month turnover savings was reported however turnover is still trending below re-forecast. 2/5 Entire Surface doing reforecasting due to lower attrition rate. Expected to capture $9M this year. 1/31/25 - Submitted to L3, however further work is needed with the FInancial Analyst to review initial feedback. 1/24/25- Continue to work with Finance and the business areas to reforecast savings to continue progression into L3. 1/17/25 - Working to reforecast the savings based off current turnover trends. Once we have the financials, we will submit to L3. | K: L5 | Completed | L5 | 2024-11-15 | 2025-04-25
Business Only Initiative: Project Forward-US-Operations-ExtraOpens | 81235 | 7628 | Business Only Initiative | SGA-GCS - Source to Pay | SG&A | Micah S. Peterson, Ana Whitten | On Track | ***3/28/2025*** Financials updated through FY28 ***3/5/2025*** Submitting to L5 ***1/31/2025*** Money step completed, savings matured and being reported. Should enter L5 | K: L5 | Completed | L5 | 2024-05-30 | 2024-05-30
Business w/ Tech Initiative: EMR IFT Purchasing Gateway |  | 153735 | Business w/ Tech Initiative | SGA-GCS - Source to Pay | SG&A | Sonel Klerk, Lucy Dolgy, Loveena Goel, Eric Joyner | On Track | 12 March * ARB Approval: Approval was granted during the meeting held on 11 March 2026. * Launch Planning: The team is currently assessing what can realistically be delivered for an August launch, given the 17 weeks remaining for development. The focus is on prioritizing features that provide the most value while ensuring a strong user experience. 25 February We began the week with 58 open action items resulting from the workshops. As of end of day Tuesday, 24 February 2026, we have successfully reduced this number to just 7 remaining items. Based on our current progress, we are well on track to meet our committed completion date of 27 February 2026. Key upcoming timelines are as follows: * Complete all actions and research items: 27 February * Start Architecture Solution Design: 2 March – 13 March * Architecture Solution Design Sign-off: 16 March – 20 March * Strat Story refinement and Sprint planning: 25 March – 3 April * Confirm new timelines and budgets: 10 April We will look to accelerate these timelines wherever possible. 22nd of January Sprint 2 started on the 20th of January. The two-week solution design workshop has been rescheduled due to the current snow conditions in Memphis, travel has unfortunately become impossible. These workshops are now scheduled from February 2nd to February 12th 2026. Architecture review and final sign-off are planned for completion by February 10th of February. 15th of January 2026 Sprint 1 execution is ongoing and on track, Sprint 1 concludes on January 16, 2026. A two week solution design workshop is being planned with ServiceNow and Deloitte, targeted for the week of January 26 through February 5. Architecture review and final sign-off are planned for completion by February 2 5th of January 2026 Overview: Enterprise tech platform for sourcing and procuring goods/services Issue: Change of scope and Deloitte resourcing to support Oracle integration due to other projects in play Risk: •Go-live delayed for Purchasing Gateway : oWorking towards August - October 26 for USA Canada & LAC oWorking towards Feb – April 27 EU MEISA & AMEA (In line with the end of Proc Ops Pheonix Contract) •$3.6M value will not be achieved in FY26 (expected to be realized in FY27) Mitigation Plan: Eliminate Convenience Purchase internationally to recover ~$2.4M in FY26 value, this will be under a different initiative 0016127 Next steps and potential mitigation: •9th January 26 - Deloitte to confirm when build information can be shared with Service Now oPotential mitigation: Asking Vendor Management team for potential resource with Oracle knowledge from Accenture to join the team for 1 month initially ($ in Planview budget for Deloitte ) If Deloitte cannot provide data in next 2 weeks, then this option will be taken – This will need to be agreed with EBS •MD50 will then need to be completed requesting when build can be completed by Deloitte oPotential mitigation: The above resource (if used) could be extended to assist with build and Deloitte / EBS sign off if build will impact August timeline. This will need to be agreed with EBS •SoX – meeting to be held 9th January 23: To discuss targeted roll out dates and change in scope 27 November Answered all questions from Finance domain lead. Charlotte Whitaker is work with Jermone to provide requested financials. 20 November Accomplishments this week: We have completed Requirements Review & Scope Gap Analysis Working Sessions with SN PDs & FedEx, completed Oracle Integrations "work ahead" call scheduled for 11/13.Kick off call with deliver team 11/20/25. Actions for next week: Work with SNOW delivery team on workshop prep and start Sourcing Category meetings. Risk: Purchasing Gateway timeline is now at risk due to late onboarding of the Delivery Team. Despite weeks of focused sessions to finalize requirements, extensive review of months of FedEx-provided data, and onboarding of additional ServiceNow res | G: L3 | Active | L3 | 2025-06-30 | 2027-06-30
Business w/ Tech Initiative: EMR IFT CLM |  | 153742 | Business w/ Tech Initiative | SGA-GCS - Source to Pay | SG&A | Ainara Alvarez, Lucy Dolgy, Loveena Goel, Sonel Klerk, Laura Pesta, Monica Rangaraj Mahesh Reddy | On Track | 12th March 26 Post workshop focus groups are being established to complete requirements / data gathering for the SoW signature. Icertis contract and Deloitte SoW for Implementation support in negotiation. To be signed end of March . 9th February 26 Planview is currently in L3 status. We are working with the implementation partner to finalize and sign the Statement of Work (SoW). Discovery workshops are scheduled to take place in Memphis during the week of 23 February. 21st January 26 Initiative submitted to L3 awaiting financial approval. Greenlights obtained in EGC on: •Enterprise Services: 1/13/26 •Platform: 1/14/26 Kick off meeting with internal stakeholders held on the 01/20 and 1/22. 12th January Financials received and uploaded to planview. EGC greenlight meeting will be held the 13th of January. 18th December Met with Architecture Review Board and gain approval. Awaiting FP&A approval of Purchasing Gateway to replicate the financials/savings in planview. No update will be provided until the week of the 5th of January 2026 27th November Waiting for financial approval. RFP for implementation partner launched. Closing date for submission of proposals December 5. Presentations/Demo will be held on the week of December 8, no update will be provided until week of 8th. 20th November Waiting for financial approval. RFP for implementation partner launched. Closing date for submission of proposals December 5. Presentations/Demo will be held on the December 15 13th November Resubmitted to L2 for approval (changed baseline to FY25 as finance asked). RFP for implemetnation partner in discussion for launch 17th November 5th November Resubmitting to L2 for approval. Icertis is the chosen tool. RFP for implemetnation partner in discussion for launch 17th November 23rd October 2025 Following the ServiceNow demo sessions, the project recommendations have been submitted to IT Leadership for review. A tool decision is expected by October 24. Targeting L2 approval in early Dec ’25 9th October 2025 Workshops booked for 15th and 16th October where Service Now will present Contract Pro for FedEx assessment by core team on viability of product. Tool decision to be made w/c 20th October, no update will be provided until week of 20th. 3 October Workshops to be held next week 10/19 with service Now to understand and align on Contract Pro capability. Tool decision and next update 10/15 19th September At final stages of collating full costs including, licence cost, internal support cost of build and maintenance, integration and implementation. Expected 26th September for decision making. 12th September 2025 StP architecture with D&T to agree integrations and internal support costs. Meeting with team on the 18th September 2025 (Incl Chris Floyd). Progress to proceed to be received soon after with proposed solution and vendors. 28th August Removing all value as an enabler initiative and moving $240M value under 153775. Meeting with Jerome Miller 29th August to agree financials. This shoudl then allow 153775 to pogress to L2 and this initaive to align. 20th August Submitting to L2 with architecture review attached 14th August CLM – In progress. 1st round RFP completed with highest ranking tool being Icertis $7.5m licence cost pa, 2nd GEP $900k pa and Service Now $700k pa. GAP analysis to be completed on requirements, when available and benefit released. This exercise to be completed week of the 26th August. No benefit expected until CY27. $100m run expected by CY28 (CY27 +$30M CY28 +$70M) 12th August 2025: Noted Freight SpinCo as Out of Scope. No consideration or impact to FXF. 7th August 2025: * Architecture documents submitted to Ryan Grover for L1 offline review * Supplier Presentations held, decision call to be scheduled. Expect decision to be made by 8/15/2025 * Potential RFP needed then for implementation partner. | G: L3 | Active | L3 | 2026-02-02 | 2027-06-30
Business Only Initiative: EMR IFT - Advanced S&P Policy Enabled by Tools |  | 153775 | Business Only Initiative | SGA-GCS - Source to Pay | SG&A | Lucy Dolgy, Sonel Klerk | On Track | 10th October 2026 This initiative was originally set to carry value for 3 tool enablers. This was not possible. All initiatives will carry a value and this can therefore be cancelled. 3rd October The value from this initiative is now being allocated to all 3 tools: 153735 / 153778 / 0011811 This is as the original 3 initiatives were classed as enabler under This Policy and now separated out. Value has been taken off. 23rd September Submitting the $140M part of the $240M NRB for L2 as this stage - will add the $100m from contracting thresholds next week. This will enable progression for the enabler initiatives 19th September Meeting held with Joseph Nowell and Jerome Miller on pre alignment of proposed benefit (including monthly ramp)and tracking. Detail being independently provided by A&S and will be submitted for L2 22nd September for full review. Will move ahead with initial request showing $140M benefit 12th Sepetmber: Data still being collated to show reasoning for $240M savings, monitoring and tracking. Charlotte Whittaker’s team are providing by 19th September. This will then be walked through with FP&A (Jerome and Joseph) 28th August Removing all value from enabler initiatives 153735, 153742 & 153778 and moving to this initiative $240M value under 153775. Meeting with Jerome Miller 29th August to agree financials. 14th August Tool decision for enablers as follows: Purchasing Gateway – Service Now. Architecture to confirm alignment then contracting to start. Supplier portal – Oracle. Implementation Partner to be confirmed. Accenture $3m, Deliotte $2m TCS $700k. 2nd round RFP this week for price reduction CLM – In progress. GAP analysis to be completed August FFPM policy to be published with the reduction of some sourcing category spend from $500k to $250k. Tracking needed. November release of FFPM to include additional reductions in convenience purchase, PO and invoicing thresholds. Currently establishing timelines, working group and RACI Reducing benefit to $81M (from $83) as spend reduced from £20B to 18.5B - still target met across all nititiave of $240M. Estimated / Proposed benefit (M): FY26 $5 FY27 $11 CY27 $25 CY28 $40 12th August 2025: Noted Freight SpinCo as Out of Scope. No consideration or impact to FXF. 7th August: changed format 83m (83,000,000) and updtaed to FY25 - the baseline numbers now shoudl be $18.6B (reduced from $20B). 31st July 2025 Submitted to L2 for approval - Requesting financials to be reviewed with FP&A Joesph Nowell. There is no cost associated with Policy , however, full monitoring and reporting will only be viable with the implementation of the Purchasing Gateway. The policy can only be changed every quarter - next change October 2025. August has proposed changes which we are waiting confirmation of completion. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: EMR IFT Supplier Portal |  | 153778 | Business w/ Tech Initiative | SGA-GCS - Source to Pay | SG&A | Laura Pesta, Lucy Dolgy, Loveena Goel, Celestine Evans, Sonel Klerk | On Track | 27 March 2026 Epics are in L3, still working on mega SoW 5 March 2026 Working on mega SoW with Deloitte to cover multiple initiatives 19 February 2026 gained L3 approval, routing Encore to enable signing of SoW 04 February 2026 gained EPM approval and submitted to L3 - pending finance approval 29 January 2026 working on updates to gain EPM approval 23 January 2026 Moved to Greenlight step and ready for EGC meeting on 1/127 15 January 2026 Received approval from Architecture Review Board. Added Money Step date. Preparing for EGC call. 8 January 2026 Preparing template for EGC call 19 December 2025 Met with Architecture Review Board for approval. 12 December 2025 Preparing architecture documentation for review by Architecture Board. 05 December 2025 Aligning financial info with other STP initiatives to seek approval from finance. 20 November 2025 Discussing FIP expansion and business bidding tool 12 November 2025 Updated financial information and attachments - new NRB of $7.2M, Added cost info from Deloitte in attachments for implementation of ~$2M and ongoing costs of ~$250k annually. To track savings, we will pull data for all POs with value of $50-100k that have received bids and assume 1% savings. 6 November 2025 Refreshing data to FY25 per finance request. Meeting scheduled with finance for 11/7 to review. 30 October 2025 Udated the baseline and target value then re-submitted to L2 - now pending finance approval. 23 October 2025 Working with finance to answer their questions so that we can gain L2 approval 17 October 2025 $6.9M NRB identified from January 2027 - breakdown attached and documents uploaded. Key assumptions now incorrect - resource impact is within Deloitte 3 October SoW detail being finalised with Deliotte for integration and meetings being held w/e 10/06 to finalise business case – expect to submit to L2 10/10 19th September To be noted as ‘No regrets work’ - move forward to be aligned with D&T 26th September 2026 Workshops to be held same week to finalise implementation SoW 12th September 2025 Working sessions with Deloitte to be held during the the week of September 22nd to align on requirements and finalize the SOW. Exection taegetd 10th - 17th October 28th August Removing all value as an enabler initiative and moving $240M value under 153775. Meeting with Jerome Miller 29th August. to agree financials, This will then hopefuly trigger the main initiative 153775 to be accepted at L2. Also requesting change to non-confidential. Key assumptions to be deleted 20th August Submitting to L2 with architecture review attached 14th August Tool decision is Oracle Supplier and Invoice Portal (existing module in the bundle purchased). Ist stage RFP closed for Implementation partner. Deliotte $2m Accenture $3m TCS $700k. 2nd round for price reduction to start this week. 8th August 2025: * Architecture documents submitted to Ryan Grover for L1 offline review * Implementation partner Supplier Presentations held, decision call scheduled for 08/12/2025 * Confirming numbers with Joseph Nowell and Joshua Croft | G: L3 | Active | L3 | 2026-03-16 | 2027-04-29
Business Only Initiative: EMR IFT Reduction of convenience purchase Intl |  | 169780 | Business Only Initiative | SGA-GCS - Source to Pay | SG&A | Lucy Dolgy | On Track | This benefit is now included in the Puchasing Gateway 153735 01/07 - requested cancellation | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Recon Transformation for US & LAC |  | 132812 | Business Only Initiative | SGA-GCS - Reporting | SG&A | Jay L. Thompson | On Track | 7/16/25 Team is continuing to meet every week discussing the next steps to implement recon transformation. The first step is a scoping excercise planned by Accenture. 8/11 - Project is on HOLD until December 2025 as we focus on other priorities. 10/21/25 - Put "On Hold" as per request via PDSM ticket INC032729689 12/11 - This project is canclled. It was entered based on the assumption we would continue operating with a BPO model for these transactional activities, where the hyper-automation projects at Accenture would be leveraged to improve reconciliation activities and lead to the estimated benefits. This is no longer the case. | C: L1 | Cancelled | L1
Business Only Initiative: Journal Entry Process Transformation |  | 132820 | Business Only Initiative | SGA-GCS - Reporting | SG&A | Jay L. Thompson | On Track | 7/16/25 Team is continuing to meet every week discussing the next steps to implement journal entry process transformation. The first step is a scoping excercise planned by Accenture. 8/11 - Project is on HOLD until December 2025 as we focus on other priorities. 12/11 - Project is cancelled. Initiative was submitted in Planview at the time based on the assumption we would continue operating with a BPO model for these transactional activities, where the hyper-automation projects at Accenture would be leveraged to automate these activities and lead to the estimated benefits. That is no longer the case. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: HyperAutomation ACCN RTR BPO Service (Deployment) |  | 153479 | Business w/ Tech Initiative | SGA-GCS - Reporting | SG&A | Chee-Heong Kerman Saw, Darshak Raimangia | On Track | 2 Oct 2025: Update the refined "Ability To Statements" shared by Paddy from discussion with Katelyn. 23rd Sep 2025: Drafted LBC and seek Domain QA Expert, Katelyn Brinkman to review. Suggest a couple of touch up on verbiage, and sugges to see advice from Joseph Nowell on Financial related area. 5th Aug 2025 : Accenture working on the business case. Working on to update the initiative owner to Deshal Shah | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: FP&A: Simplify FXS Chargebacks | 16878 | 8262 | Business Only Initiative | SGA-GCS - FP&A | SG&A | Adam Thomas | On Track | . | K: L5 | Completed | L5 | 2023-01-09 | 2023-03-07
Business w/ Tech Initiative: FP&A: Rationalize Financial Forecast/Plan/SO proce | 16913 | 8283 | Business w/ Tech Initiative | SGA-GCS - FP&A | SG&A | Kristina Kasich | On Track | Awaiting leadership decisions from Enterprise Planning workshops | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: FP&A: Optimize FXE FP&A Team | 21598 | 9064 | Business Only Initiative | SGA-GCS - FP&A | SG&A | Claude Russ, Angela Edwards | On Track | 4.1.25: FY25 rebaseline completed. | K: L5 | Completed | L5 | 2023-03-17 | 2023-03-17
Business Only Initiative: US & CA Paperless STC Procs - Quick Wins |  | 107385 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Enrique Mertins | On Track | 2026-01-14 Reviewed and adjusted for L3 Submission 2025-10-24 Reviewed w/J.Miller. Adjusted values in LBC and resubmitted for approval for L2 2025-10-21 Adjusted baseline and target values to fully match adjusted LBC and re-submitted for L2 2025-10-07 Uploaded LBC updated document and Re-submnitted for L2 2025-10-06: Met with George Oswald to go over all assumptions and calculations for the LBC. LBC to be updated in PV and resent for L2. 2025-09-16. Included potential implementation costs, that couyld result from elimination of on of the printed Past Due Invoices. 2025-08-06: This initiative has been aligned with the "Paper Invoice Fees" initiative to avoid intersection that could lead to "double counting" of savings. 2025-07-31: Business case has been finalized, Making necessary L1 entries and proceeding with submission steps for L2. | G: L3 | Active | L3 | 2025-05-30 | 2028-05-30
Business Only Initiative: LAC Brazil Serasa Credit Bureau Contract Reduction | 89363 | 6733 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Arthur Tavares Mattos, EVELLYN OLIVEIRA | On Track | 04/23/2025 - Updated Actuals from Dec/24 to Mar/25 after correcting the baseline cost, which triggered an automatic recalculation of savings values. Adjustments ensure alignment with accurate cost data. 04/17/2025 - March values have been updated; however, we need to wait for the closing of the remaining months to include actuals for april & may. While reviewing the data, I identified an inconsistency in the February value for the Serasa initiative, which was due to a missing currency conversion step. The corrected amount has been calculated and is ready to be updated, pending alignment. 04/02/2025 - FY25 re-baseline completed 03/25/2025 - The higher-than-average value is due to a significantly higher volume of consultations than usual. Below are the detailed amounts by company: FDX: R$ 20,913.69 TNT: R$ 54,152.82 Total Savings per month: R$ 75,066.51 (approximately USD 14,876.19, based on an exchange rate of R$ 5.04 to 1 USD). 03/10/2025 - Upon reviewing the addendum and requesting an updated financial analysis, we will need to wait until April for the value update. This is because the February 2025 values will only be issued and paid at the end of March 2025. 02/07/2025 - Planview L3 submitted for approval today. 02/03/2025 - Finalizing business case detais, anticipating move to L3 by end of week. 11/13/2024 - On october we got the OK from serasa that they took out the score information. At the begining of november we received the charges from services on october thru the NF and we have seen a reduction on the ammount due for this service. 09/30/2024 - All calculations have been set, as well as exchange rate. With all this information we have input all information regarding the savings. We are today waiting on the development from Serasa, and as soon as they are done, we will start seeing the savings on the charges for consultations on October's invoice. | K: L5 | Completed | L5 | 2024-09-13 | 2024-09-13
Business Only Initiative: Servientrega Contract Reduction | 78786 | 6735 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Eddie Utset, Carlos Lopez | On Track | initiative on track. pending the follow the drive process Mar28/25 rebaseline to fY25 has been completed. | K: L5 | Completed | L5 | 2024-04-01 | 2024-04-01
Business Only Initiative: Safran - FY24 Bad Debt Reduction | 62888 | 7010 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Brice Tropibani, Kelly Gibb | On Track |  | K: L5 | Completed | L5 | 2022-04-01 | 2024-05-31
Business Only Initiative: Thales - FY24 Bad Debt Reduction | 62865 | 7011 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Olivier Banchet, Kelly Gibb | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Sandvik Group Headquarters - FY24 Bad Debt Reducti | 62871 | 7012 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Rob Van Den Berg, Kelly Gibb | On Track |  | K: L5 | Completed | L5 | 2022-10-03 | 2024-05-31
Business Only Initiative: Schneider Electric SE - FY24 Bad Debt Reduction | 62855 | 7014 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Thijs Harbers, Kelly Gibb | On Track | completed | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: KERING INC. - FY24 Bad Debt Reduction | 62890 | 7176 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Christopher Bowden, Marta Montes Astudillo | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Richemont - FY24 Bad Debt Reduction | 62895 | 7177 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Gillian Desaever, Marta Montes Astudillo | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Samsung Electronics Co, Inc - FY24 Bad Debt Reduct | 62899 | 7178 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Marc Truyens, Marta Montes Astudillo | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Google LLC - FY24 Bad Debt Reduction | 62880 | 7180 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Mike Martinez, Marta Montes Astudillo | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Vestas Wind Systems A/S - FY24 Bad Debt Reduction | 62853 | 7181 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Christopher Smith, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Stryker Corporation - FY24 Bad Debt Reduction | 62869 | 7182 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Christopher Smith, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Deutsche Lufthansa AG - FY24 Bad Debt Reduction | 62894 | 7184 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Darren Ward, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2024-05-31
Business Only Initiative: Xpo Logistics, Inc. (Corp Freight Forwarder) - FY2 | 62872 | 7185 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Halima Begum, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Raytheon Technologies Corporation - FY24 Bad Debt | 62876 | 7186 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Johannes Rantala, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: ICU Medical, Inc. - FY24 Bad Debt Reduction | 62896 | 7187 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Lisa Machin, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2024-05-31
Business Only Initiative: DSV Panalpina A/S - FY24 Bad Debt Reduction | 62858 | 7188 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Niels Toeset, Gail Fazakerley | On Track | DSV is a decentralized, local P&L driven organization. We would need to be smart in our approach toward DSV and the contacts we have for escalation. Sending the total DSV statement with all details will work against us. We need a division by division & country by country approach. Currently Halima is building up a strong dialog with DSV providing info to local country contacts to make sure we progress with getting payments done. Long term awaiting of the customer to resolve billing issues is the main reason for the great outstandings. Current crediting and rebilling for DSV FR and DSV NL should be completed, but has taken nearly a year by our side to complete. | K: L5 | Completed | L5 | 2023-08-31 | 2024-07-05
Business Only Initiative: TE Connectivity Corporation - FY24 Bad Debt Reduct | 62856 | 7190 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Paul Slee, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Carrier Corporation - FY24 Bad Debt Reduction | 62870 | 7191 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Selmar Westra, Gail Fazakerley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-06-04
Business w/ Tech Initiative: Finance - Reduce Paper Invoice Costs | 2672 | 7305 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Angie Houston, Christian Lemon | On Track | 9/4/2025 - Per discussion in the GCS OTC meeting 9/3/2025, we need to cancel the legacy initiative Planview#7305 Reduce Paper Inv Costs (aka Paper Invoicing Fee), as it’s been replaced and enhanced by Planview# 114432: New Invoicing and Payment Fees. 4/1/2025 - FY25 Re-Baselining complete. 10/22/2024 - Moving back to on-hold after initiative was moved from WAVE to Planview. 6/10/2024 - Initiative still awaiting confirmation of RMIC IT Roadmap deliverable date; will need to update official forecast once the calendar is confirmed. 4/23/24 - Pushed back One Time Implementation Costs from March '24 to April '25. Target is awaiting RMIC Roadmap confirmation. Money Step moved from 11/1/2023 to 11/1/2024 due to prioritization needed in IT development (Roadmap). | G: L3 | Cancelled | L3 Data Migration - TEMP | 2022-11-16 | 2025-12-30
Business Only Initiative: General Electric Company - FY24 Bad Debt Reduction | 62857 | 7312 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Donata Van Denzel, Michela Chirico | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: International Business Machines Corporation - FY24 | 62859 | 7314 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Rene Zijp, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business w/ Tech Initiative: Finance - Expand US parcel late fees to Canada | 2669 | 7316 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Jane Onwudiwe, Joseph Puthukkeril | On Track | 09/04/2025: Initiative is being cancelled on direction of GCS OTC leadership as a new initiative has been created that includes Canada (Strategy ID: 130972). Late fees launch in Canada will be managed out of the new EMR OTC initiative. 03/21/2025: FY25 rebaseline set to Zero as the project is on hold and will require reassessment of financials when greenlit to begin. In a recent leadership meeting on DRIVE, Mike and other leadership indicated that certain Initiatives should officially be set to “On Hold” status, including #2669. Putting the Initiative in that status will allow Wave to filter out the Benefit amount from the values reported to leadership as well as keeping the Initiative from showing as late. While the Initiative should still be pursued, setting to “On Hold” will provide leadership with a more accurate understanding of the EBS portfolio. | E: L2 | Cancelled | L2 & CCH | 2023-04-17 | 2025-04-30
Business Only Initiative: Siemens Corporation - FY24 Bad Debt Reduction | 62860 | 7317 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Marina Simovska, Mike Silberreis | On Track | Account 156361682 we have found that the sender is not working according to the SOP we have in place which is leading to DT pmt issues. @Norman will get in contact with Mr. Markus Brantner week 49 week 49 weekly update :- The system is blocking so we cannot insert anything in the milestone nor can create new milestones fitting the Siemens dedicated action plan requirements. BP and me will go ahead and work with the SOA excel and work through each account and define actions based on account level. | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Volkswagen AG - FY24 Bad Debt Reduction | 62861 | 7319 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Sabine Seelinger, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2024-05-31
Business Only Initiative: LVMH MOET HENNESSY LOUIS VUITTON - FY24 Bad Debt R | 62862 | 7320 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Nuria Calvo Barbado, Ria Worley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: DH Business Services - FY24 Bad Debt Reduction | 62864 | 7323 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Luc Dezeure, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Mercedes-Benz Group AG - FY24 Bad Debt Reduction | 62867 | 7325 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Ulrike Siebenschuh, Mike Silberreis | On Track | # 65701: Installment plan was communicated with HWA by Sabine and accepted by customer. Waiting for first payment end Dec. Payment in progress. # 66192: Work in progress on the actions defined in tracker owned by Sabine. Focus on main accounts and apply next actions. # 66194: Work in progress on the actions defined with Ana Torres. # 66330: Ulrike setup Teams with MB Ms Gavrilovic/MBGSB to discuss central download of queries. Pending customer response. # 66586: Basware-setup & open cases need a faster response and resolution # 66589: Basware-setup & open cases need a faster response and resolution | K: L5 | Completed | L5 | 2023-07-03 | 2024-05-31
Business Only Initiative: Continental AG - FY24 Bad Debt Reduction | 62868 | 7328 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Jack Hamilton, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Johnson & Johnson - FY24 Bad Debt Reduction | 62874 | 7330 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Mette Ulrich, Michela Chirico | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Aptiv PLC - FY24 Bad Debt Reduction | 62875 | 7332 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Filip Jacobs, Mike Silberreis | On Track | -Weekly calls with APTIV. - Focus on top 3 countries PL HU PT - Noticed there are still wrong invoices being produced - Centrally loaded rate card however the countries are charging different surcharges (e.g. NS in HU) - Commercial has no idea who is checking the rates are loaded correctly and if the produced invoices are correct. Is this CAP Gemini task? - STC has no access to Mainframe and can't check if rates are loaded correctly | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: SONY CORPORATION - FY24 Bad Debt Reduction | 62879 | 7333 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Peter Kovacs, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Medtronic, Inc. - FY24 Bad Debt Reduction | 62881 | 7334 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Tugba Posul, Ria Worley | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-31
Business Only Initiative: Traton SE - FY24 Bad Debt Reduction | 62882 | 7335 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Connor Eddy, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Thermo Fisher Scientific, Inc - FY24 Bad Debt Redu | 62883 | 7336 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Dorette Haag, Michela Chirico | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: ESHOPWORLD - FY24 Bad Debt Reduction | 62884 | 7337 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Herman Van Eekeres, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: FORVIA - FY24 Bad Debt Reduction | 62885 | 7341 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Leon Watson, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-10 | 2024-05-31
Business Only Initiative: Chanel - FY24 Bad Debt Reduction | 62886 | 7343 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Christine Gibson, Ria Worley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Eaton Corporation - FY24 Bad Debt Reduction | 62893 | 7352 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Arjan Van De Scheur, Mike Silberreis | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: CORETRUST Europe - FY24 Bad Debt Reduction | 62897 | 7356 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Andy Michlmayr, Ria Worley | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Volvo AB - FY24 Bad Debt Reduction | 62898 | 7357 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Olivier Meert, Mike Silberreis | On Track | aligned with CFS Jack - focus on the biggest amount on 1 FR account - sent urgent request for payment to Volvo/Renault Trucks - don't have the impression collectors in FR did a huge job here as we still have unpaid invoices from 2020 | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: ITA SHIPPING GMBH - FY24 Bad Debt Reduction | 62901 | 7359 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Mariya Marino, Ria Worley | On Track |  | K: L5 | Completed | L5 | 2023-01-02 | 2024-05-31
Business Only Initiative: USA/Canada Going Paperless (Invoices, Dunning, and | 88165 | 7362 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Enrique Mertins, Eddie Utset | On Track | Statement of Accounts production was suppressed. Those documents are not printed anymore. Print/mail supplier not charging for those anymore. **Rebaselined to 2025 - 3/28/2025** | K: L5 | Active | TEMP L5 - Enter L5 | 2024-09-13 | 2024-09-13
Business w/ Tech Initiative: Phoenix - STC - DW | 66615 | 7389 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Ewa Bronowicz, Tanushri Chowdhury | On Track | 08/29/25 - ready to move to L5, no incremental value in FY26 as full run rate achieved in FY25 08/11/2025 - in L4, savings for FY26 to be recognized in subsequent initiative(s) 07/20/25 - in L4, savings for FY26 to be recognized in subsequent initiative(s) 06/12/25 - actuals for May'25 entered 06/04/25 - VP approval received to close the project, actuals for May'25 to be entered by June 12th 05/16/25 - all milestons completed except for money step, as per VP discussion the initiative should be ready for L4 by end May'25; actuals for April and forecast for May'25 updated 04/25/25 - all milestons completed except for money step, as per VP discussion the initiative should be ready for L4 by end May'25 04/18/25 - all milestons completed except for money step, as per VP discussion the initiative should be ready for L4 by end May'25 04/11/25 - all milestons completed except for money step, as per VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025 04/04/25 - all milestons completed except for money step, as per VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; Planview forecasts updated; note that numbers for this initiative are a % of overall Phoenix STC business case - overall contract performance is reflected in the numbers for both initiatives; This initiative is totally independant from "Phoenix A&C" 03/28/25 - Blackline LEES implementation ETA mid June, however as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; Planview forecasts updated; note that numbers for this initiative are a % of overall Phoenix STC business case - overall contract performance is reflected in the numbers for both initiatives; This initiative is totally independant from "Phoenix A&C" 03/14/25 - all milestones completed except for Money Step, as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; awaiting Pod Lead's feedback before confirming the numbers with Finance and updating Planview forecast - dates TBC; note that numbers for this initiative are a % of overall Phoenix STC business case (split into "Phoenix - STC" and "Phoenix - STC - DW", there are no dependencies on the other Phoenix STC initiative - overall contract performance is reflected in the numbers for both initiatives; This is totally independant from "Phoenix A&C" 03/06/25 - all milestones completed except for Money Step, as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; awaiting Pod Lead's feedback before confirming the numbers with Finance and updating Planview forecast. 02/28/25 - awaiting Pod Lead feedback for re-forecasted numbers 02/21/25 - re-forecasted numbers submitted for approval by Pod Lead 02/14/25 - re-forecasted numbers to be approved by Pod and Finance leadership 02/07/25 - reforcasting of the business case discussed, updated numbers to be available in w/e 02/014/25 02/03/25 - closed milestone "Finalize the EBS scope for use cases 1-6" as the FedEx teams agreed to develop related KPIs dashboards while not impacting Capgemini work; due to holidays and knowledge transfer activities the re-forecast will start on Feb 6th 01/27/25 - external spend category adjusted to "Prof fees" - referring to Capgemini costs (transferred from Wave as IT); due to holidays and knowledge transfer activities the re-forecast will start on Feb 6th 01/22/25 - actual benefits for Dec'24 come much low | K: L5 | Completed | L5 | 2023-09-01 | 2025-05-30
Business Only Initiative: Phoenix - A&C | 20707 | 8135 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Ashif Hamsa, Vijay R, Tanushri Chowdhury | On Track | 04/13: Mar'26 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. 03/30: Revised financials has been updated. Marginal change in numbers. 03/11: Feb'26 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. 02/25: There are no changes to the Jan'26 numbers and captured details are correct 02/13: Jan'26 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. 01/28: There are no changes to the Dec'25 numbers and captrured details are correct 01/13: Dec'25 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. 12/12: Nov'25 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. 11/25: There are no changes to the numbers and captrured details are correct 11/12: Oct'25 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. The delta between forecast and actuals is due to volume fluctuations. 10/27: Revised financials has been updated. Marginal change in numbers. 10/09: Sep'24 financials updated. These are close to accurate as the volume validation will be completed during the last week of every month. The delta between forecast and actuals is due to volume fluctuations. Enterprise KPI: None is relevant for this project and have selected "WIP" inalignment with PMO. This is one of the mandatory field so had to choose one. 09/30: Final numbers for Aug'25 updated. Marginal change in numbers. 09/11: Financials updated. This is volume based commercial model with BPO. Financials updated based on volumes provided and there might be a marginal change when volumes are validated. Normally, accurate volumes are posted during the last week of teh month (per contractual timelines & operational constraints). 09/08: All milestones are completed and we are asked to update financials until Mar'26 to close out this project. 08/28: All milestones are completed and we are asked to update financials until Mar'26 to close out this project. 05/21: Moved to L4. Attached money step evidences which includes working sheet from where the actuals are derived, Volume (from Vendor invoice) & cost centre details from where the costs are released. 05/02 - Working with EBS leadership and expected to close this action before 30th May 25. 04/29 - Working with the EBS leadership to move this to L4 and close out this project. Actions will be taken on or before 15th May 25. 03/28: Initiative is baselined to FY25. Transactional based contract, so volume updated based on FY25 numbers for FY26 forecast. Cost includes contingency cost as well. 03/17: Liaising with EBS leadership on continuing this Initiative. Target date: 03/31. 03/06: Initiative overperforming in FY25 due to following reasons: No contingency forecast used (refer business case) L4: There is a discussion with EBS leadership / TOM governance if we need to continue with this initiative. Action to be taken following the discussion. 12/10 - Actuals shall be updated on 18th Dec as the volume needs to extracted manually & validated by our team. **Initiative is overperforming in FY24 - actions & rationale below:** **IT cost**: Forecast adjusted for FY25 & FY26. The forecast was removed (updated as “0”) and added onto initiative #20708 as the IT costs are related to this initiative. **Other costs:** We are currently engaged in commercial negotiation with the Supplier at Sr. Leadership level and the outcome will have an impact on FY25 financials. Our recommendations is not to adjust the forecast at this moment as the impact will be seen once the negotiations & contractual formalities are completed. We anticipate the impact to start from J | K: L5 | Active | TEMP L5 - Enter L5 | 2022-01-03 | 2025-07-16
Business Only Initiative: Phoenix - StC | 20708 | 8136 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Ewa Bronowicz, Tanushri Chowdhury, Vijay R | On Track | 08/29/25 - ready to move to L5, no incremental value in FY26 as full run rate achieved in FY25 08/11/2025 - in L4, savings for FY26 to be recognized in subsequent initiative(s) 07/20/25 - in L4, savings for FY26 to be recognized in subsequent initiative(s) 06/12/25 - May'25 actuals updated 06/04/25 - VP approval received to close the project, May'25 actuals to be updated by June 12th 05/16/25 - Blackline LEES implementation delayed till mid-Aug, however as per initial VP discussion the initiative should be ready for L4 by end May'25; actuals for April and forecast for May'25 updated 04/25/25- Blackline LEES implementation delayed till mid-Aug (delay due to SAP and Oracle L5 connectivity issues and bank holidays), however as per initial VP discussion the initiative should be ready for L4 by end May'25; there are some issues with getting the actual numbers for Mar'25 hence approximation provided 04/18/25 - Blackline LEES implementation ETA TBC (3-week-delay due to SAP and Oracle L5 connectivity issues), however as per initial VP discussion the initiative should be ready for L4 by end May'25; there are some issues with getting the actual numbers for Mar'25 hence approximation provided 04/11/25 - Blackline LEES implementation ETA end June (2-week-delay due to SAP and Oracle L5 connectivity issues), however as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; 04/04/25 - Blackline LEES implementation ETA mid June, however as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; Planview forecast updated end March; note that numbers for this initiative are a % of overall Phoenix STC business case - overall contract performance is reflected in the numbers for both initiatives; This initiative is totally independant from "Phoenix A&C" 03/28/25 - Blackline LEES implementation ETA mid June, however as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; Planview forecasts updated; note that numbers for this initiative are a % of overall Phoenix STC business case - overall contract performance is reflected in the numbers for both initiatives; This initiative is totally independant from "Phoenix A&C" 03/14/25 - "Celonis purple disputes" milestone closed - report out available; Blackline LEES implementation ETA mid June, however as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; awaiting Pod Lead's feedback before confirming the numbers with Finance and updating Planview forecast - dates TBC; note that numbers for this initiative are a % of overall Phoenix STC business case (split into "Phoenix - STC" and "Phoenix - STC - DW", there are no dependencies on the other Phoenix STC DW initiative - overall contract performance is reflected in the numbers for both initiatives; This initiative is totally independant from "Phoenix A&C" 03/06/25 - 2 remaining milestone in progress (Celonis ETA mid-Mar and Blackline LEES implementation ETA mid-Jun), however as per initial VP discussion the initiative should be ready for L4 by end May'25; actual benefits come much lower than forecast as of Nov'24 due to change requests agreed with Capgemini in 2024/2025; awaiting Pod Lead's feedback before confirming the numbers with Finance and updating Planview forecast. 02/28/25 - awaiting Pod Lead feedback for re-forecasted numbers 02/21/25 - re-forecasted numbers submitted for approval by Pod Lead; Celonis draft report for purple disputes reviewed and comments provided, final report expected | K: L5 | Completed | TEMP L5 - Completion Approval | 2022-01-03 | 2025-05-30
Business w/ Tech Initiative: Optimize payment methods (e.g., implement e-invoic | 32396 | 8343 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Mike Callender | On Track | On hold - initiative needs a new home as it would apply to more spend than just pro fees | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: Implement Workday Time Tracking for non-exempt and | 31189 | 8759 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Adela Nazarova, Christian Lemon | On Track | **5/22/25** - Updated Baseline FY to FY25 per Domain Finance instruction 03/21/2025: updated for FY25 re-baselining. No future benefits are expected. | K: L5 | Completed | L5 | 2023-01-18 | 2023-05-26
Business Only Initiative: Finance - Reduce City Center Duty and Tax Bad Debt | 2676 | 8925 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Alicia Deere, Denise Bradford | On Track | 3-14-2025 : Executive guidance has been passed down from Brie in light of the recent executive orders changing duties and taxes from the White House. All Global duties and taxes will now be rebilled at day 45 to the shipper. | K: L5 | Completed | L5 | 2022-11-02 | 2025-04-01
Business Only Initiative: Arrow Electronics - FY24 Bad Debt Reduction | 62866 | 8937 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Liga Cipruse, Anabela Grade | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Cisco System - FY24 Bad Debt Reduction | 62892 | 8939 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Jorge Alves, Anabela Grade | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: TELEFON AB LM ERICSSON - FY24 Bad Debt Reduction | 62889 | 8942 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Niklas Larsson, Anabela Grade | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: TDK Corporation - FY24 Bad Debt Reduction | 62887 | 8943 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Ray Walker, Anabela Grade | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Apple Inc. - FY24 Bad Debt Reduction | 62863 | 8945 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Zoe Price, Anabela Grade | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: Robert Bosch GmbH - FY24 Bad Debt Reduction | 62854 | 8947 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Andre De Groot, Ana-Belen Alegre | On Track |  | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: ABB Ltd - FY24 Bad Debt Reduction | 62878 | 8949 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Arjan Van De Scheur, Ana-Belen Alegre | On Track |  | K: L5 | Completed | L5 | 2023-05-01 | 2024-05-31
Business Only Initiative: Parker-Hannifin Corporation - FY24 Bad Debt Reduct | 62873 | 8951 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Lukas Kleijne, Ana-Belen Alegre | On Track | 11-12 - milestones added | K: L5 | Completed | L5 | 2023-01-02 | 2024-05-31
Business Only Initiative: V.F. Corporation - FY24 Bad Debt Reduction | 62877 | 8954 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Karen Brauninger, Ana-Belen Alegre | On Track | 14mar24: Milestone 66910: SOA invoice status feedback received from VF - STC BP is reviewing Milestone 66909: CASS has created a Webform to upload the PDF invoices instead of sending them the Manual CSV files. STC BP has uploaded last 10 invoices pending from CZ. Created new MIlestone: 71191 for disputes - Sales VP approval considering the amounts based on the data availalbe. Now back to STC to process Credit notes. 06/feb24: Milestone 66910: SOA invoice status feedback received from VF - STC BP is reviewing Milestone 66909: CASS has created a Webform to upload the PDF invoices instead of sending them the Manual CSV files. STC BP has uploaded 52 invoices. Pending 10 CZ invoices to be uploaded. Created new MIlestone: 71191 for disputes. 30jan24:Milestone 66910 - SOA: feedback rcvd and undr review with StC Milestone 66909: expect files to be ready by 1st of February for payment till the end of the month. 23jan24: Milestone 66910 - SOA: reminder sent on 22jan if a new SOA reply (TNT) Milestone 66909: expect files to be ready by 1st of February for payment till the end of the month. 09jan24: Milestone 66910 - SOA : reminder sent to Laura/VF. Milestone 66909 for .csv file creation: StC already have all files /info to "build" .csv file to send to VF. 19dec23 Milestone 66910 - SOA : reminder sent to Laura van de Steene/VF - invoice status for freight on VF scope for TNTFX. Milestone 66909 for .csv file creation, StC had a call with Jack Hamilton to support reports creation. Both Stc and WWS will be out on holidays returning on jan/8th. Milestones will be then updated again. 14dec23 milestones added | K: L5 | Completed | L5 | 2023-08-31 | 2024-05-31
Business Only Initiative: PARCEL2GO.COM LTD - FY24 Bad Debt Reduction | 62900 | 8956 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | James Obrien, Ana-Belen Alegre | On Track |  | K: L5 | Completed | L5 | 2023-06-12 | 2024-05-31
Business Only Initiative: Honeywell Intl Inc. - FY24 Bad Debt Reduction | 62891 | 8958 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Sandra Santos, Ana-Belen Alegre | On Track |  | K: L5 | Completed | L5 | 2023-06-30 | 2024-05-31
Business Only Initiative: Kuhne Holding AG (Freight Forwarder) - FY24 Bad De | 62852 | 8960 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Sara Leiser-Bregy, Ana-Belen Alegre | On Track | 18.1.24: - Milestone 66209: 18.01.24 Call with KN on 11.1.24 to review SOP and updated SOP sent to KN on 17.1.24, I will keep this Milestone assigned to STC BP for the moment, before assigning it to Sales - Milestone 66922: reminder sent to collector katarzyna.gradziel.osv@fedex.com to get an update if Farkind has contacted her, assigned Milestone to Chloe Jordan as BPO collection - Milestone 66924: 18.01.24 reminder sent to Muddaliar, Ashwini Prabhu <ashwini-prabhu.muddaliar@capgemini.com>; Harikrishnan, Poornima <poornima.harikrishnan@capgemini.com> to get disputes for Purple UK handled in priority and waiting for feedback by 19.1.24, Milestone Owner changed to Johana Badillo as it's Dispute - Milestone 66923: 18.01.24 awaiting dispute 190825446 to be solved and payments applied, Milestone assigned to Chloe Jordan as it's more collection even if dispute + cash application are involved as well | K: L5 | Completed | L5 | 2023-01-02 | 2024-05-31
Business Only Initiative: EBS Training Temp Resource Reduction | 91346 | 8989 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Christian Lemon, Brian Keeney | On Track | **5/22/25** - Updated Baseline FY to FY25 per Domain Finance instruction 3/24/25 - Rebaselined financial to FY25. No further value to be captured. Initiative closed. 2/7 - Temp contract exit the end of FY24. All work has been exited and value captured going forward. Closing work. | K: L5 | Completed | L5 | 2024-05-31 | 2024-05-31
Business Only Initiative: Reduce FXF Agency Commission | 4708 | 9034 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Michael Gahagan, Linda Rose | On Track | Updated for the FY25 rebaseline. | K: L5 | Completed | L5 | 2022-11-14 | 2023-01-31
Business Only Initiative: Invoicing Profile Accuracy | 82199 | 9189 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Rudolph J. Pienaar, Eric Boyle | On Track | 9/23/2025: Domain lead request that this initiative be canceled due to the FXF transition. Aligned with FXF leadership to confirm that 9189 should be canceled. 07/03/2025: Per Freight Domain Lead, initiative to be paused until further notice. 3/13/25: 3/6/25: L3 approved. Logic complete. GUI in dev mode, with milestone on track to be hit 3/17. Pilot successful, prepared to pilot customer 2. Expected to meet L4 data of 3/31/25. 3/6/25: L3 approved. Logic complete. GUI in dev mode, with milestone on track to be hit 3/17. Pilot successful, prepared to pilot customer 2. Expected to meet L4 data of 3/31/25. 12/30: L3 approved. Logic compete, entering testing phase. Team working to operationalize and meet L4 date of Mar 2025. 12/16: L3 approved. Logic compete, entering testing phase. Team working to operationalize and meet L4 date of Mar 2025. 12/9: L3 approved. Team on track to meet L4 date of Jan 2025. 12/2: 12/2: L3 approved. Team on track to meet L4 date of Jan 2025. 11/11: L2 approved. Building out KPIs and milestones for L3 approval by mid November. Team on track to meet L4 date of Jan 2025. 11/4: L2 approved. Building out KPIs and milestones for L3 approval by mid November. Team on track to meet L4 date of Jan 2025. | I: L4 | Cancelled | L4 | 2024-05-23 | 2025-03-31
Business Only Initiative: EE 2.0 - Shift Market focus to Regional |  | 92108 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | James R Crawford | On Track | 5.27.25 Updated Actuals, savings as expected, submitting to L5 4.15.25 Rebaselined financials to FY28 3.10.25 headcount reductions completed November 2024. Monthly savings realized are in line with forecast. 1/9/2025 Completed in November | K: L5 | Completed | L5 | 2024-12-02 | 2024-12-02
Business Only Initiative: Finance Transformation - STC | 18795 | 9417 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Raja Nelavae, Tanushri Chowdhury | On Track | 24/03/25 - FY'25 rebaseling process is completed. 11/04/2024 - attempting to move L5. | K: L5 | Completed | L5 | 2022-06-01 | 2025-01-01
Business w/ Tech Initiative: Customer Attribute Expansion |  | 156562 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Aashish Goyal, Lauren Smith, Neelam Dagar | On Track | 09/29 - Review the request with the Domain QA Expert before submitting it for L2 approval 09/24 - Leadership has recommended including Legal and Regulatory 09/19 - Shared the architecture diagram, key details, and impacted systems during the L1 Architecture Alignment call 08/29- Successfully identified all downstream applications and updated the architecture diagram accordingly | E: L2 | Active | L2 - Enter Value Prop
Business w/ Tech Initiative: Modernize & Streamline Strategic Workflow Pricing |  | 157393 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | David S. Skipper, Maurcia Boone | On Track | Request needs to move out of GCS / OTC Pod and into Commercial / RQ Pod. DSS | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Finance / S2C - Customer Self-Service Case Submiss | 2679 | 9355 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Andrew Pellegrino, Linda Rose | On Track | 09/12/2025 - Cancelling the Customer Self-Service Case Submiss (Planview ID - 9355) initiative and folding it into the problem resolution effort. 08/27/2025 - Putting Finance / S2C - Customer Self-Service Case Submiss (Planview ID - 9355) on-hold due to the Freight spinoff. The scope of this project and business case were largely Freight email channels and phone numbers. Will need to assess priority without Freight scope. 04/08/25 - Completed all necessary steps in the Planview L1 checklist for this initiative to proceed to L2. 02/21/2025 - Several updates to the Customer Self-Service Case Submission initiative to ensure its accurate representation and facilitate prioritization. * Reassigned the impacted portfolio from Data & AI to Commercial. * Adjusted the t-shirt size to Small. * Revised the complexity estimate to Low. * Added the Ability To Statement to the Lean Business Case. * Populated the Business Process field in the L0 section. * Populated the Operational Impact field in the L0 section. We are currently awaiting the Enterprise Architecture review. The Enterprise Excellence domain system's recommended ranking for this initiative is currently 328. 02/14/2025 - DRIVE Initiative ID 2679: Despite strong support from Directors, Senior Managers, and Operations Managers who are eager to utilize these customer self-service webforms in production, we are encountering challenges in advancing this initiative through the Planview prioritization process. Currently has a low system recommendation ranking in L1 (330) with a benefit score of 3.0 and is currently on hold. We kindly request assistance in elevating the priority of this initiative within the Planview system. Once this initiative is in L3 an ART Bundle can be created and scrum team assigned to begin the refinement process for features, user stories, and acceptance criteria. 01/09/2025 - We are working with IT to develop a webform-to-case API connection between the Adobe Adaptive Forms on FedEx.com and Salesforce-CED. The development for the API is planned for PI1 (mid-January) with a target completion date of April 2025. A meeting is scheduled for January 14th to discuss specific requirements for the API connection between Adobe Adaptive Forms (AAF) and Salesforce-CED. A key requirement for launching the remaining webforms is an automated email reply to customers, providing a unique case ID. This auto-reply functionality is dependent on the successful implementation of the API connection. DRIVE initiative #2679 & PPM #755910. 12/18/2024 - Working to establish the Adobe Adaptive Form API connection and enable customizable auto-reply messages with unique case numbers. 8/30/2024 - DRIVE initiative #2679 has a dependency on the DART team to enable an Adobe Adaptive Forms API to properly handle case volume, doc. upload for reference documents, and auto-reply with a unique case number. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: GCS OTC Error Corrections EMR |  | 164243 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Andrew Pellegrino | On Track | 06-March-2026: Updated the PV desc., financials tab, target value, assumption fields according to the latest info: Current Monthly (as of March 1) for the Deloitte resources supporting the US corrections queues is approximately $205,000/monthly ($2.46M annually). Our conservative target is to reduce manual corrections by 20%, which represents a savings of approximately 41K per month, $492,000 annually). PDSMs will be submitted to update the L1 Baseline and NRB (Soft). 09-Feb-2026: moved to L3. 19-Dec-2025: Proceeding with soft benefits and develop the business case accordingly. If we later identify hard savings, we will update the Planview initiative to reflect those changes. 19-Dec-2025: Angela Edwards met with Deloitte on 12/18 to discuss project timing, IT requirements, and the business case. Deloitte confirmed that a 60-day notice is not required to reduce agents. This initiative overlaps with another Planview initiative/business case and aligns with our broader effort to consolidate vendors and reduce our vendor footprint. We explained to Finance that Error Correction Automation supports cost savings in Confidential Initiative 8575; however, since Initiative 8575 is about to enter L5, we cannot classify PV164243 as an enabler. Angela will work with Deloitte to base the business case on error correction queue volume reduction. 11-Dec-2025: Received approval from Deloitte to move forward with this initiative. Angela Edwards reviewed the Error Correction Automation IT Architecture with Deloitte and they agreed to proceed. 7-Nov-2025: Requested that this initative be brought to Vendor Ops Innovation process meeting on Monday 10-Nov-2025 before being moved forward in Planview L2. 20-Oct-2025: Jerome Miller's team is working the initiatives that came into their queue last week; this initiative did not hit the queue until Friday. Jerome will provide any appropriate feedback at the end of the week within the initiative as needed; one of his team members will likely reach out to the IO this week. 2-Oct-2025: Alex A. requested to update the intiative name from GCS OTC Error Correction Automation to 'GCS OTC EMR'. | G: L3 | Active | L3 | 2025-10-10 | 2026-06-01
Business w/ Tech Initiative: ServiceNow Implementation | 32681 | 8992 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Leslie McNeil, Brian Keeney | On Track | 3/13/25 Substituted new I/O to account for recent changes in department. Leadership meeting to determine next steps for initiative. 10/08/25 - Closing this initiative as the initiative was initially ours with creating the ability to replace Enwisen as the employee solutions portal (mostly for Payroll and HQ inquiries) and build base workflow for engagement with customers. However, it was entered about the time we launched One FedEx. Because I needed to purchase the HR module in SNOW for confidential cases (so security was limited), this was morphed into an enabling initiative to support the Employee Portal and Knowledge databases that HR launched as part of One FedEx, so it was funded quickly as part of One FedEx. Because the HR module license is an enterprise license, this also served as the basis for all things that HR needs to build in SNOW in perpetuity, therefore, the value is just going…meaning it doesn’t really fit the model of DRIVE anymore with value assignment, a money step, milestones, etc. | E: L2 | Cancelled | L2 | 2023-12-01 | 2025-04-30
Business w/ Tech Initiative: Onboard to Collect - Redefining Onboarding |  | 166707 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Lauri A. Dozier, Ross Montague | On Track | Initial requirements and journeys defined. Vendor starting to be engaged for capability discussions. 3/19/2026 (dfw) IO and Michelle Linton are working with OTC team to resubmit to L2. 4/15/26 Michelle Linton said that this is not on hold and going through the Purple Chip Process. Reach out to Michelle Linton with questions. (David Walker) | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Improved Cust Satisfaction thru Proactive Interven |  | 169177 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Sohail Mohammad | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Workforce Management - CE Global Expansion |  | 157382 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Kyle Tiemann | On Track | Combining into single initiative with 161370 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Workforce Management - Extend Beyond CE |  | 157387 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Kyle Tiemann | Some Issues | Need OTC contacts to begin establishing scope | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Cross Skilling and Skill Opt. in EU, APAC, MEISA |  | 161370 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Kyle Tiemann | On Track | Working on developing baseline for business case | E: L2 | Active | L2 | 2026-05-29 | 2026-05-29
Business Only Initiative: Modernize Training for rep Performance Quality |  | 157416 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Geri-Lynn Ryan, David Walker, Julia Selph, Melissa Zehr, Bettie A. Abernathy | On Track | We would like to pause this initiative in Planview, as we are going to run the pilot with Zenerate (for 9 months). Once we have evaluated the pilot results, we will determine the true cost savings and will complete the business case so that this can move to L2. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: EBS GBS Automation Opportunities – AMEA/ EU |  | 177893 | Business w/ Tech Initiative | SGA-GCS - Onboard to Collect | SG&A | Vishwanath C, Laxmi Sravanthi Bhagavatula, Michela Chirico | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2026-05-18 | 2026-09-11
Business Only Initiative: COM-CSX-Americas CE Shared Services Center MEXUS |  | 166443 | Business Only Initiative | SGA-GCS - Onboard to Collect | SG&A | Christina B. Hart, Larry Taylor | On Track | Work is in progress at GBS and we are hiring staff. We will transition to the new facility in June 2026. | G: L3 | Active | L3 | 2026-02-04 | 2028-06-02
Business w/ Tech Initiative: STA DocuSign transition to Service Now |  | 161367 | Business w/ Tech Initiative | SGA-GCS - Hire to Retire | SG&A | Ilazabeth Obi, Brandon L. Lake, Gloria B. Jones, Beata Gaye | Some Issues | 4/9/26 Plan to meet with Hire to Retire team to explore integration into Onboarding process. 4/8/2026 Met with Farrell-Shikuku's group to discuss initiative and how they may be able to support. 3/24/26 ServiceNow has determined that it can not support the system due to the volume of CDAS workers. It has been determined a new system will have to be selected or built to support the application. 3/5/26 PPM request submitted 1840252 2/6/26 First meeting with Deloitte and ServiceNow team for planning 1/28/2026 Had first kickoff meeting with ServiceNow, Deloitte, Image, CDAS, and badging team to discuss requirements. Weekly meeting cadence has been set. 11/20/2025 Sent email update to provide additonal details to SNOW team. 11/12/2025 Deloitte contract approved by finance, sourcing, and contract administration. Pending legal 11/6/2025 Met with ServiceNow and Deloitte, awaiting level of effort and timeline from ServiceNow team. 9/17 Awaiting architecht meeting 9/16 entered the additional figures and uploaded the designs and other supporting documents 09/15 met with Dev lead to run figures and financial impact with new STA volume announcement 09/13 difficulty getting the exact figures of what STA volume will look like (new normal) | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: ServiceNow HR Design |  | 179796 | Business w/ Tech Initiative | SGA-GCS - Hire to Retire | SG&A | Renae Scott, Kelly Wade | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2025-04-02 | 2026-07-30
Business w/ Tech Initiative: ESCC Infrastructure |  | 188962 | Business w/ Tech Initiative | SGA-GCS - Hire to Retire | SG&A | Melanie S. Corsey, Jason A. Mitchell, Kia M. Shaw | On Track | On Track | C: L1 | Active | L1 Feedback Requested | 2026-09-30 | 2026-09-30
Business w/ Tech Initiative: Day 1 Sys Access for US Surface Package Handlers |  | 190864 | Business w/ Tech Initiative | SGA-GCS - Hire to Retire | SG&A | Jun Wei Tan | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: SNow AI Enablement for HRSD – Employee Support Mod |  | 191286 | Business w/ Tech Initiative | SGA-GCS - Hire to Retire | SG&A | Jun Wei Tan | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: APAC Post Call Work Reduction |  | 166258 | Business Only Initiative | SGA - Commercial | SG&A | Andrew Symington | On Track | Investigating options to reduce AHT, data analysis underway. | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: Uniforms - Ordering Controls via Forced Allocation |  | 166420 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Tricia Frese, Pooja Patel | On Track | 12/3 submitted LBC | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: [CA] Adjust staffing level and eliminate training | 633 | 6695 | Business Only Initiative | SGA - Commercial | SG&A | Stephane Robillard, Kyle Tiemann | On Track | We will not see the impact of this drop in Vendor FTEs until we get to December and PEAK call volumes | I: L4 | Active | TEMP L4 - Enter L4 | 2022-10-10 | 2022-12-01
Business w/ Tech Initiative: [US] Enhance IVR capabilities and performance | 650 | 6728 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Rich Mauney | On Track | [RM] 1/15/26 - Financials for Dec 2025 will be ready next week [RM] 4/30/25 All KPI and Impacts should be updated through March. Rebaseline completed today in consultation with S.B. [RM] 2/17/24 Estimates entered for KPI's and Impacts. Will update actuals when they become available. [RM] 1/29/25 Attaching supporting documents and advancing this initiative to L4 [RM] 1/27/25 December actuals have been updated. Waiting final sign-off to submit to L4. NOTE: Actual savings this month (December) was higher than forecast due to high call volumes (PEAK) and consistent automation rate. [RM} 1/9/25 Actuals entered. [RM] 1/6/25 KPI's and impact are still estimates. I expect to be able to update actuals tomorrow or Wednesday [RM] 11/19/24 All Actuals entered yesterday [RM] 10/7/24 KPI's and Impacts for September are entered and Estimates. Actual data may not be available until 10/17 [AG] 9/25/24 Due to our FY25 Objectives another DRIVE project will be created to meet our goals (they are different than 650.) We will not implement any additional enhancements under 650. I moved the Money Step to Oct 22, 2024. Which also changed the L4 date to Oct 22, 24. [RM] 8/19/24 Non-Account Holder (NAH) deflection containment rules remain OFF in production. IVR team has been directed to relax some containment rules. [RM] 8/5/24 During our weekly meeting on 7/31 we determined that this initiative needs to be reforecast as a consequence of the company strategy shift to NPS score and away from containment. Please see note from 5/20/24 relative to OSC being lower than forecast. These reasons will remain constant. [RM] 7/25/24 Correcting Impacts for May and June. These were missed on the 7/17 update. [RM] 7/17/24 KPI's are all updated with actual values. One Impact still needs to be updated. [RM} 7/15/24 KPI's and Impacts for June are estimates. Waiting for dashboard updates which should be by 7/17/24 [RM} 6/12/24 KPI's and Impacts for May are estimates. Waiting for dashboard updates [RM] 5/20/24 - April 2024 OSC was lower than forecast. There are a number of contributing factors including slightly softer call volumes compared to April of last year (2023: 5.26M and 2024: 5.11M). Additionally the IVR transferred slightly more calls per 1K packages than last April (2023: 7.77/1K calls and 2024: 7.9/1K calls). The IVR team continues to navigate through OneFedex driven changes and other challenges with the Pickup application where the automation rate has fallen from 49.7% in April 23 to 38.6% in April 2024. Lastly, the IVR team has been directed to relax some containment rules. We've also developed Non-Account Holder (NAH) deflection rules pursuant to the initiative but those containment rules remain OFF in production. [RM] 5/20/24 OSC Actual is now updated [RM] 5/20/24 OSC for April is estimated - I should have the updated value today. [RM] 4/15/24 March OSC was lower than forecast. Several backend (FedEx) issues (Time outs or errors) in Tracking and Pickup are contributing to this problem. One issue with the CEBS API was identified and is scheduled to be fixed on 4/18. The IVR team is working with Reliability Engineering and Network Engineering to research and resolve the other issues. As a consequence, more calls are being transferred. [RM] 3/15/24 Update: IVR February OSC was lower than forecast due to two issues (defects) discovered post R45 load. These issues were identified and a load to resolve both is scheduled for the end of this month. Additionally, February 2024 volumes were extremely low. CSat KPI is an estimate and will be updated once CEDL data feed issue is resolved. [RM] 2/29/24 Today we made the decision that forecasts for impacts and KPI's needed to be adjusted. The principal reason for the adjustments is the change in direction with respect to turning on certain features that the IVR team has already developed but not been permitted to enable. These are the non-account holder (Disconnect and deflection) business rules. (pre | I: L4 | Active | TEMP L4 - Enter L4 | 2022-07-01 | 2025-10-31
Business Only Initiative: [AMEA] Centralize transactional tasks in CE and in | 628 | 6739 | Business Only Initiative | SGA - Commercial | SG&A | Ada Chong, Lance Tam | On Track | 2024 Jan's impact has over $50k variance from forecast because of the following: - CE Centralization has been cancelled after pilot due to complexity and limited benefit (original planned monthly saving $25.5k) - Avocado 2.0 has been delayed to start in 2024 Feb and complete by 2025 Feb (original planned monthly saving $80.6k) - PCC Centralization will be taken out as a new DRIVE initiative which is not yet input in Wave (original planned monthly saving $63.2k) Seagull 2.0 has been completed as planned and the saving & expenses have been updated. Due to the scope changed, the forecast of impacts, KPIs have been changed from March 2024 onwards, the past forecasts were for the past scope. Below please review the revised data: - annualized recurring VFTE saving is $1.4m - annualized recurring FFTE saving is $0.4m - One time cost - IT $0.048m - One time cost - T&E $0.12m - One time - S&W Variable severance - $0.75m - One time - S&W Fixed severance - $0.042m - One time - Variable Overlapping - $0.11m - One time - Fixed Overlapping - $0.031m | K: L5 | Active | L5 Feedback Requested | 2022-11-01 | 2025-02-28
Business w/ Tech Initiative: [EU] Pod 3.1 Simplify and automate the claims proc | 691 | 6750 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Graca Machado, Philipp Muenchenberg, Dennis Atkins | Some Issues | 23/04/2026 - Critical data point issue solved - UAT successful and signed off - POC planned to restart on April 27th - L4 still at risk (set for April 30th) 17/04/2026 - Critical data point still missing - Data team shared a new approach today - Development team assessing what needs to be updated in current code - Estimated date to restart POC: 27th April - L4 at risk (set for April 30th) 13/04/2026 - One critical data point is missing - carriage value currency - Not having this information leads to wrong calculation of claims value - POC is stopped until this is solved - L4 date at risk 2/04/2026 - POC continuing, critical issues solved - Expected deployment as from 13th April 12/03/2026 - Previous CQL critical issue has been solved - A new CQL critical issue has been logged - IBAN number being replaced when there is a previous claim from the same customer with a different IBAN to the one the customer submitted on the claim form - POC is currently stopped until this critical issue is solved. CQL team said it would take around 1 week to deploy the fix - No other critical issues have been found. Smaller issues have already been solved 06/03/2026 - POC has started in EE, LV, LT, DK, SE, FI, RO and AT - ELS in place, cases being closely monitored - One critical issue - connection to payment in CQL is not working, IT is following up - Claim flow working as designed and payment calculation is correct 27/02/2026 - UAT has been successful - POC to start on March 2nd 13/02/2026 - Revised timelines for FedEx claims automation tool * UAT: 17th–18th next week * CAB approval process: 23rd Feb * Production deployment: 27th Feb 5/02/2026 - iMade team completed the API development and test - API ready to be integrated with the FedEx claims automation tool - Provisional POC set to Fev 19th 23/01/2026 - iMade still working on the claims API. 28th Jan launch date in jeopardy - Claim centralisation in Turkey for Poland scheduled for Fev 2nd 07/01/2026 - Waiting for timelines to be confirmed by IT - Aim is to launch FedEx Loss and Damage automation in line with the DSM implementation - Claim centralisation in Turkey for Austria claims scheduled for Jan 13th and for Portugal claims on Jan 12th 17/12/2025 - Due to knowledge transfer between IT teams, the development and deployment of FedEx loss & damage claims automation is delayed once again. Escalation to CE MD and IT MD on-going - New timelines for UAT and POC still not available 11/12/2025 - MBG automation with DSM fixes under development - iMade team has a two week delay in completing the CEBS claims API development, which is impacting the FedEx loss & damage UAT. Because of this delay, the UAT will only take place in January - Impact to the FedEx loss & damage integration into DSM timelines under assessment - Usage of the MBG mass process is increasing the efficiency on MBG processing, driving up the kpi on % of MBG automation 28/11/2025 - MBG automation with DSM issue investigation completed, two issues to be solved before being able to deploy MBG automation with DSM: - multi awb MBG request in one claim. Bot is creating a SFC per AWB as per design, but these are not DSM cases. This means that, when solved, the customer is not getting any notification as these are not DSM cases and Marketing Cloud is no longer working for Austria - in certain situations, bot is opening a new SFC to send the information to the Shared Services team queue instead of transferring the initial case. This means again that the customer will not get the DSM notification, and the initial case is left in the DSM queue with no action - FedEx loss and damage claim automation UAT date set to 15th December in Spain - Integration of this automation with DSM in progress, expected UAT on January 15th in Austria and Sweden - The roadmap for deployment is to follow the DSM implementation 20/11/2025 - MBG automation with DSM still under investigation. Some cases progressed as e | G: L3 | Active | TEMP L3 - Enter L3 | 2022-11-14 | 2026-04-30
Business w/ Tech Initiative: [US] Enhance existing Virtual Assistant capabiliti | 652 | 6772 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Evelyn Sims, Kara Sheeves | On Track | [KS 4/3/26] - NRB entered for March 2026 [ES 4/3/26] - KPI entered for March 2026 [KS 3/10/26] NRB entered for February 2026 [KS 3/5/26] - NRB for this initiative will end with September, 2026 as the savings will be transferred to initiative 142092. The current VA will be replaced by Digital Support Manager; thus, the savings will no longer be realized for this VA initiative. [ES 3/4/26] - KPI entered for February [KS 2/12/26] - NRB entered for January [ES 2/9/26] - KPI entered for January [ES 1/13/25] - KPI entered for December [KS 1/13/26] - NRB is above forecast for December due to increased VA conversations during Peak. [KS 12/8/25] - NRB entered for November [ES 12/5/25] - KPI entered for November [KS 11/10/25] - NRB entered for October. Deflections are up slightly from the previous month. [ES 11/6/25] - KPI entered for October [KS 10/9/25] - NRB entered for September. Deflections are down 3.1% from the previous month. [ES 10/8/25] - KPI entered for September [ES 9/10/25] - KPI entered for August [KS 9/10/25] - NRB entered for August. Deflections are down ~2% from previous month. [ES 8/8/25] - KPI have been updated for July [KS 8/6/25] - NRB entered for July. [KS 7/11/25] - NRB entered for June. [ES 7/9//25] - KPI have been updated [KS 6/5/25] - NRB entered for May. [ES 6/3/25] - KPI have been updated [KS 5/14/25] - May '25 forecast is accurate. [KS 5/8/25] - NRB for April exceeded forecast by $63,798. [ES 4/25/25] - L4 Architechtual Document submitted - the document is located in the Money Step documents because i could not upload it to the architech document drop down [ES 4/15/25] - KPI have been updated [KS 3/7/25] - For the month of February, the recurring benefit is $240,370 better than forecast. [ES 2/13/25] - KPI have been updated [KS 1/15/25] - VA conversation volume for the month of December was up due to Peak. [KS 12/9/24] - Actual benefits for November were $506,900, which is $278,900 better than forecast. This improvement was impacted by: 1) The NDEP/Mix migration/rollout is now complete 2) Deflection rate for all regions improved from last month and 3) Conversation volumes were up for all regions except for AMEA. [KS 10/9/24] - Forecasted recurring benefits for September were $220,000; however, actual benefit was $451,900. Performance gains are ahead of target. US and EU both had greatly improved deflection rates for September - 2.4 and 2.2 percentage points greater than 5% improved deflection rate target. [KS 9/13/24] - Invoices for the AMEA NDEP migration were received in August. Total expense was $72,874. [KS 8/19/24] - Recurring benefits for July were $68,400 above forecast. Deflection rates remained strong; overall volume was up across the regions. [KS 8/14/24] - AMEA migration is complete. [KS 7/12/24] - Corrected spend for May as this should actually be allocated to June. Expense is related to the UAT for MEISA. Updated the target date for the AMEA migration based on the current project plan. [KS 6/12/24] - The actual spend for the month of May was related to the UAT for MEISA. [KS 5/16/24] - The actual spend for the month of April was higher than forecast due to the APAC UAT beginning earlier than originally anticipated. [KS 4/9/24] - The actual expense for the March implementation costs was related to the LAC migration to NDEP ($42,713); however, the forecast for this category for the month was $211k. This is due to the LAC UAT expenses being invoiced separately in January. The January actual implementation cost was updated to reflect the invoice amount of $170,853. [KS 3/26/24] - Completed LAC migration to the NDEP platform on 3/20/24 [KS 3/12/24] - Target date for Milestone 57487 for AMEA has been updated to 8/1/24 per the current project plan. [ES 2/29/24] - Forecast has been adjusted due to about a ~17% decrease in average monthly VA conversations globally (Aug'23-Feb'24) vs FY22 Baseline [ES 2/28/24] -All milestones are on target. [ES 2/20/24] - January 2024 variance explanation | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-11 | 2025-03-31
Business Only Initiative: [EU] POD 2.1 Outsourcing & Vendor Approach | 618 | 6784 | Business Only Initiative | SGA - Commercial | SG&A | Dennis Atkins, Ulas Likogullari | On Track | 06/21/2025 Initiative submitted for L4. The actual date of completion was set for 31 June 2025; IO needed until mid-July to confirm actual exits from June in Workday. This was finalized and the actuals were updated on time, but the L4 checklist/proof document wasn;t updated. All steps completed and EU FP&A has provided approval from local level as of 21 August 2025. Copy of email correspondance uploaded as document. 27/03/2024 L4 date shifted to the right, as has phasing plan, due to recent developments related EU LR/HR and European Works Council timelines. Approval of shift from POD Lead on 18 March 2024. 31/03/2023 As per recent internal CE agreement the direction on aimed outsourcing shares have been changed. The outsourcing shares will be increased in two phases. In phase 1 (now until end of FY25) we will return to the original business case with a less aggressive outsourcing approach. An extended scope of outsourcing for Europe will be reviewed in phase 2 beyond FY25. Therefore, the aimed saving in this initiative was reduced from $21,5M to $10.76M. Attached business case has been adjusted accordingly | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-03 | 2025-06-30
Business w/ Tech Initiative: [EU] POD 1.4 Channel Guidance Email | 674 | 6795 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Dennis Atkins, Daniel Seemann, Marcin Kuzma | On Track | ***2025-11-12: ***Initiative has been intentionally kept open past its L4 date. The Initiative was delivered and hit its fully financial obligation as of 30 June 2025, however, there were still gaps related to the solution that were being pursued/developed by IT. FTE were allocated from the EBO process, so it appeared as complete, but the function was still missing capabilities required for the future..The function couldn't close out the initiative as the PPM will also cloes out and it was needed to ensure that IT continued development on the initiative. It's been agreed that it could close out as there are other avenues of development opened from other initiatives. [2024-04-04] Due to further delay in CED migration and Webform integration with Sales Force, we have to adjust project timelines for Channel Guidance Email as well [2024-03-27] L4 date shifted to the right, as has phasing plan, due to recent developments related EU LR/HR and European Works Council timelines. Approval of shift from POD Lead on 18 March 2024. [2024-01-15] API integration to CED/CCD has some issues due to lack of required header informatio funcionality, DI is working on the fix that might come in 17th Feb release of DART - exact date TBC. This all means the POC has to be move to begining of March, but it does't mean we pospone everythig, as the lauch can be done in steps: step 1. adaptive webfor, step 2. launch of internal rules that will reduce some volumes already, and then step 3, which is the final feature where we block all external email and we guida customer to new adaprive webforms, and this can be done after we complete POC so somewhere late April. [2023-12-14] This week we have finally launched both EN and CZ webform. This will allow us to start next phases: setup autoreplies, rules to prevent internat email from comming to CE mailbox and to setup rules for external freeflow emails. We will not go live with Channel Guidance Email this year as of Peak, and also because of comming integration of AEF (webfrom) and CCD (salesforce) which would allow us to give better visuat experience for both customer and agents. Currently the plan is to go live with POC in first weeks of January. [2023-11-10] Due to the extended UAT process we had to move project phases for later date. New webform should be in from 20.11 and the actual go live with all CCDmail rules and autoreplies should be done by 4.12 [2023-10-27] Despite great effort it's impossible to achieve go live dedline and we are forces to delay phase 1 for at least another week. Next readiness go/no-go session will be held on Thursday, 2nd November in order to confirm we can move new webform to the production on Monday, 6th November. The go live for phase 2 is not affected by longer build porcess for new webform (at least at this stage) [2023-10-13] Go/no-go session has proven that we are not ready to go live on 16th. After individual meetings with CE OPS, DI and P&E Teams and Sponsor the new phased plan was drawn. First we go live with new webform (#7132) on 30.10, and then as phase 2 on 20.11 activate autoreplies, eCars and necesary configuration (#7131 ) to change the way how customers can communicate with us. [2023-10] The money step (Validate Resource Shift) is being moved to align it to the milestone plan and impact (that was already updated). This is due to dependencies on Labor Relations Consultations, Limited Digital Marketing resources and dependencies on technical solution readiness in AEM (webform design tool) and CED (the end-state e mail tool) [2023-08] DI resource commitment confirmed by Kim van der Velden [2023-07] No resource commitment / timelines not committed - escalation email will be sent on Tuesday next week (DS) [2023-06] dependency on Milestone #7126, new DI intake was submitted and we are awaiting for assessment (more details in milestrone #7126 description) [2023-04] Due to EU LR guidance any saving realization dependent on FTE reduction has been moved by appro | K: L5 | Active | L5 | 2022-10-03 | 2025-06-30
Business w/ Tech Initiative: [AMEA] Single Desktop with Automation (Non-CN) | 659 | 6806 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Edward Ow, Nico Mong, Lance Tam | On Track | CED base capability rollout completed, 1Source retirement done. Currently need Global CED team to prioritize Email Automation Capabilities to achieve Money Step. New Money Step date of 6/1/2026 updated. | G: L3 | Active | TEMP L3 - Enter L3 | 2022-10-25 | 2026-06-01
Business w/ Tech Initiative: AMEA Enhanced GC3 & IVA (Non-CN) | 661 | 6895 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Akir Othman, Edward Ow, Lance Tam | On Track | The varienace of actual and forecast was due to change in roll out approach by starting the distrubution of 5% and ramp up approach within3 months instead of 1 week. This appraoch is to protect customer experience in the event IVA doesnt recognise Customer intent during rollout | G: L3 | Active | TEMP L3 - Enter L3 | 2022-09-19 | 2026-06-01
Business w/ Tech Initiative: [US] Build additional self-service capabilities in | 656 | 6906 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Evelyn Sims, Gina Maiden, Kara Sheeves | On Track | [KS 4/3/26] - NRB entered for March 2026 [ES 4/3/26] - KPIs have been entered for March 2026 [ES 3/10/26] KPIs have been updated for February 2026 [KS 3/10/26] NRB entered for February 2026 [KS 3/5/26] NRB for this initiative will end with September, 2026 as the savings will be transferred to initiative 142092. The current VA will be replaced by Digital Support Manager; thus, the savings will no longer be realized for this VA initiative. [ES 2/10/26 Submitted to L5 [KS 2/11/26] NRB entered for January 2026 [ES 2/10/26] KPIs have been updated for January 2026 [ES 1/13/26] KPIs have been updated for December 2025 [KS 1/13/26] NRB is higher than forecast for December, 2025 due to increased VA conversation volume with Peak volumes. [KS 12/8/25} NRB added for November, 2025 [ES 12/4/25] KPIs have been updated for November 2025 [KS 11/10/25] NRB updated for October 2025 [ES 11/5/25] KPIs have been updated for October 2025 [ES 10/9/25] KPIs have been updated for September 2025 [KS 10/9/25] NRB entered for September. Deflection rate is slightly lower than previous month. [ES 9/10/25] KPIs have been updated for August 2025 [KS 9/10/25] NRB entered for August. Deflection rate is down by ~ 5% when compared to previous months. [KS 8/8/25] Reforecasted NRB based on average of VA conversations and associated deflection rates by intent for the months of Feb '25 - Jun '25. Outliers were removed. Data provided by CEDL team. [ES 8/8/25] KPIs have been updated for July 2025 [KS 8/7/25] VA conversations regarding package status intents were ~ 104k higher in July than prior month; deflection rate was 87.5%. This resulted in a higher NRB for the month of July. [KS 7/11/25] NRB for June was $113,200 better than forecast. [ES 7/1125] KPIs have been updated for June 2025 [ES 6/5/25] Moved Seq ID finished date to July 31. Had to add a requirement for validation for the account number. [ES 6/5/25] KPIs have been updated for May 2025 [KS 6/5/25] Entered NRB for May. [KS 5/14/25] Existing May '25 forecast can remain. [KS 5/8/25] NRB for April was $133,217 above forecast. [ES 4/22/25] Closed Milestones (93600, 93601, 93497) Pickup by Ground and Address Validation by Azure Map [ES 4/16/25] KPIs have been updated [KS 4/15/25] Conversation volume for "I'd like to provide feedback to FedEx" was higher than forecast for the month of March. [ES 4/8/25] Moved Milestone (93604 & 93605) Scheduled a Pickup Account Number dev/testing dates due to completing milestones 93600 & 93601 [ES 4/7/25] Moved Milestone (93600 & 93601) Scheduled a Pickup testing dates due to data issues and middle ware issue [ES 3/10/25] Moved completion date out to 3/25/25 for Seq ID # 93494 - Pickup Ground Testing. BLOCKER (middleware issue) continue from Feb 13th. (Iteration 1.3) . [KS 3/10/25} Deflection rate for "When Will My Package Arrive/My Package Status Hasn't Been Updated Recently/Scheduled Delivery is Pending" is higher than forecast. [ES 2/12/25] Milestone 93604 status was updated to "inprogress". Milestone was started on time (2/10/25) as system displayed but system was not updated. [KS 2/7/25] Benefits exceeded forecast for the month of December. Conversation volume for "I'd Like to Provide Feedback to FedEx" and "When Will My Package Arrive/My Package Status Hasn't Been Updated Recently/Scheduled Delivery is Pending" are higher for the month. Deflection rates for these intents are also higher than goal. [ES 2/5/25] KPIs have been updated [ES 1/25/25] New Milestones have been added for Scheduling a Pickup. [KS 1/23/25] To clarify the comments from 12/31/24, the baseline of the business case was not changed. This initiative was underperforming its forecasts due to changes in VA volume; thus, the forecasts were revised to more accurately reflect the remaining incremental value for this initiative based on current conditions. [KS 1/15/24] VA conversations increased during the month of December due to peak volume. [ES 1/15/24] KPI have been updated [KS 12/3 | K: L5 | Active | L5 | 2023-03-01 | 2025-09-30
Business w/ Tech Initiative: [US] Automate CE manual tasking to organization in | 683 | 6928 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Larry Taylor, Julia Selph | On Track | Status as of 10.08.24 * IT resources reallocated to another initiative to eliminate comfort cases, proactive creation etc *Vendor reductions implemented based on partial code load by IT; Case reductions verified by IT Team. *Savings realized - April 24 Status as of 08.19.24 * IT continues to work on remaining coding to complete this initiative. Status as of 04.26.24 •Drive 683 Phase 1 successfully loaded March 2, 2024. Phase 1 implemented business rules to drastically reduce pair queuing. Pair queuing for March was 92% lower than February and all tasks sent to the International Trace team were reduced 24.6% when compared to February results. The team continues to monitor results looking for further improvement opportunities. •Phase 2 is currently being developed to implement business rules to route primary cases on inbound shipments to the correct delivery operation teams to expedite action on behalf of the customer. Target load summer 2024. Status as of 03.18.24 •Drive 683 Phase 1 successfully loaded March 2, 2024. Phase 1 implemented business rules to drastically reduce pair queuing and account for approximately 80-90 percent of the tasks currently being manually routed. •Phase 2 is currently being developed and will implement business rules to limit primary case creation of these inbound to US cases targeting the elimination of “comfort cases” or inappropriately created cases. Target load summer 2024. Status as of 02.20.24 Phase 1 & 2: Coding continues as planned and on target. Status as of 01.16.24 Phase 1: Package Research Routing logic changes to the Auto Task creation (pair queuing) is code complete and scheduled for March release (80 to 90% of the volume) Phase 2: Package Research Routing logic changes for Primary cases. The Drive Champions are currently working these stories and are estimated to be completed within the next 6 weeks (March 1). Target load to be determined. The pilot for Delayed Holding Queue is ongoing and we anticipate automation requirements. The Ops team wants to complete the pilot before decided what needs automating. Status as of 12.14.23 •Case EBS Drive Champions scrum team is working on task pair queuing rules – target code complete Jan 2, 2024 for March 2, 2024 release •Case EBS PMT evaluating the consolidation of queues to streamline the routing rules to the Operations team with custodial control •Currently planning additional features in CY24 PI 1 (stars Jan 3, 2024) •OPEN ITEM: Access to Mission/CCII scans – no existing interface exists that can be leveraged. Case EBS Architects are working with the Mission team to explore sending Mission information to Track so we can have access from Case EBS. Status as of 11.29.23 Still in Progress... The goal for PI4 was to develop the first 9 decision rules. We are on track to accomplish this goal. The team is currently determining physical scans required and has a dependency on the Mission/CCII legacy systems that do not currently have an interface that we can leverage. The team and the CEBS Architects are working with the Mission team explore sending Mission information to Track so we can have access from CEBS. We are currently planning features for PI5, which will include functionality we can accomplish without the CCII/Mission data. Additional requirements being considered to accommodate DRIVE Initiative | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-10 | 2025-02-04
Business Only Initiative: [AMEA] CE offshoring consolidation within Greater | 28687 | 6939 | Business Only Initiative | SGA - Commercial | SG&A | Ada Chong, Kevin Cheung | On Track | - | K: L5 | Active | TEMP L5 - Enter L5 | 2023-03-01 | 2026-01-30
Business Only Initiative: APAC - Reimagine PCC support model | 71359 | 6950 | Business Only Initiative | SGA - Commercial | SG&A | Lance Tam, Kevin Cheung, Lu-Jin Lucy Zhang | On Track |  | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2024-04-01 | 2026-01-30
Business Only Initiative: [AMEA] APAC Improve forecast accuracy from 90% to | 75113 | 7061 | Business Only Initiative | SGA - Commercial | SG&A | Ayden Tay, Aiman Khan | On Track | ok | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-02 | 2024-11-29
Business Only Initiative: [AMEA] MEISA Improve forecast accuracy from 90% to | 75196 | 7072 | Business Only Initiative | SGA - Commercial | SG&A | Ayden Tay, Aiman Khan | On Track | ok | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-02 | 2024-11-01
Business Only Initiative: [AMEA] APAC - Task Productivity Improvement | 76699 | 7080 | Business Only Initiative | SGA - Commercial | SG&A | Francis Remigio, Joseph Chow, Lance Tam | On Track | On track | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-01 | 2025-05-20
Business Only Initiative: [AMEA] APAC – Lower Cost to Serve by Offshoring | 93778 | 7086 | Business Only Initiative | SGA - Commercial | SG&A | Joseph Chow, Lance Tam | On Track | 2025 Nov 27th - Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL3 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-12-02 | 2026-08-31
Business Only Initiative: [CA] Shift Canada work from near shore to off shor | 630 | 7117 | Business Only Initiative | SGA - Commercial | SG&A | Doug Berry, Kyle Tiemann, JAMES HALE IV | On Track | On Track | K: L5 | Active | L5 | 2022-11-07 | 2023-06-01
Business Only Initiative: [LAC] AHT Improvement | 60577 | 7295 | Business Only Initiative | SGA - Commercial | SG&A | Norma Suarez, Ricardo Asteinza | On Track | The $.088 will be recurring benefits. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-07 | 2024-05-31
Business Only Initiative: [AMEA]APAC-China Call Reduction Projects | 75375 | 7430 | Business Only Initiative | SGA - Commercial | SG&A | Stephen Ye, Grace Quan | On Track | rebaseline based on FY25 Actual call status | K: L5 | Active | TEMP L5 - Enter L5 | 2023-11-13 | 2025-04-14
Business w/ Tech Initiative: APAC Social Messaging Apps - Expansion to address | 94468 | 7719 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Kishan Gunaseharan, Nico Mong | On Track | Riding on as CE Reinvention Epic | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: [AMEA] APAC: DCR Productivity Enhancement (offline | 75132 | 7818 | Business Only Initiative | SGA - Commercial | SG&A | Shan Xiong, Daisy Gao | On Track | Kindly note that due to organizational restructure (APAC & MEISA split) we are working on how these initiatives will be managed within the region. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-31 | 2025-05-30
Business Only Initiative: [AMEA] APAC: Email Reduction Strategy | 34078 | 7997 | Business Only Initiative | SGA - Commercial | SG&A | Jian-Min Crystal Jian, Ada Chong, Lance Tam, Edward Ow | On Track | Completed the business rebasleine and reviewed with Aysha | I: L4 | Active | L4 | 2024-01-01 | 2025-12-02
Business w/ Tech Initiative: [US] CE Desktop FY25 Value Bundle - Phase B | 73235 | 8129 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Phillip M. Smith, Van Wilson | On Track | Deleted Global Email and Chat Release Milestone, Core Enhancements, and Bridge Enhancements in CED Milestones as those are covered in B2 project. Bridge enhancements became General enhancments in the milestones. * ART Team conducted PI-02 PI Planning the week of 3/17 * Benefits forecast shifted from starting in Feb 2025 to May 2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-15 | 2025-09-26
Business w/ Tech Initiative: APAC Enhanced CC3 & IVA CHINA | 73278 | 8166 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Yen Shen, Wei Mang Thum, Nico Mong, Edward Ow | On Track | 20250812 -Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL3 Launch | G: L3 | Active | TEMP L3 - Enter L3 | 2023-08-01 | 2026-12-31
Business Only Initiative: [AMEA] MEISA Occupancy improvement to achieve savi | 75226 | 8177 | Business Only Initiative | SGA - Commercial | SG&A | Helen Chan, William Sun | On Track | 4/17 - Approved by Finance (Anthony Bok) to move to L2. 5/16 - Market OCC goals communicated to CE MDs. 7/15 - Shared the WFM Command Centre process during AMEA CEMA calls 8/1 - Sharing of OCC and SA performance for Jun / Jul 12/18 - summarized the vfte savings as: Jun :8.93 / $4084.48, Jul : 10.09 / $4754.05, Aug: 9.9 / $4500.55, Sep : 9.35 / $4590..49, Oct: 11.82 / $5652.44, Nov : 9.63 / $4995.54 12/18 - sent email approval request to Finance Anthony Bok, MEISA Lead : Patrick Makwana, APAC Lead : Lance Tam to move to L4 12/19 got email apporoval from FInance and DRIVE lead to move this project to L4 . 4/22/2025 - meeting with Finance (Vineet Shastree, Jenessa Fernandes) to explain the project result and got the approval to move L5. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-02-27 | 2024-11-29
Business Only Initiative: [AMEA] PNQRC rental saving | 69482 | 8368 | Business Only Initiative | SGA - Commercial | SG&A | Vikeeth Kottari, Sharath Shetty | On Track | Pune saving already started | I: L4 | Active | TEMP L4 - Enter L4 | 2024-01-29 | 2024-09-13
Business w/ Tech Initiative: [AMEA] APAC - Supplies Orders process automation b | 93758 | 8445 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Xi Zhou, Jing-Ru Collin An | On Track | 8thOct2024- 23thOct2024:Align with Antony Liaw the saving calculation 23thOct2024- 24thOct2024:Align with Antony Bok the Business Case 25thOct2024-1th Nov2024:Submit L1 to L2 ,and align with EMP 1thNov2024 -23thDec2024:Push EA assignment 02Sep2024-29thAug2025:RPA development for CN 7th Jul 2025 - Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL3 23th Jul 2025-- L3 be approved 24th Jul 2025-15th Sep Wait EU IT development RPA tool and 1th Sep- 15th Oct 2025 ODC- CED Migration 15th Oct-28th Oct 2025 stage CN automation tool product and UAT 29th Oct 2025 CN go live 30th Oct- 3th Nov 2025 CN Tool Optimization & HK/JP Development Discussion 3th Nov 2025 -6th Jan 2026 The peak freeze period, cannot proceed with go-live during this time 6st Jan -13st Jan 2026 HK and JP automation tool UAT 13st Jan 2026 JP go live 13st Jan -27st Jan 2026 HK UAT Optimization 28st Jan 2026 HK go live 29th Jan-31th Mar 2026 HK and JP automation rate improvement | G: L3 | Active | L3 Feedback Requested | 2024-05-08 | 2026-05-28
Business Only Initiative: [CA] Coach agents on repeat call reduction | 670 | 8693 | Business Only Initiative | SGA - Commercial | SG&A | Chris Strickland, Denise Vourtzoumis | On Track | should be in L5 | I: L4 | Active | TEMP L4 - Enter L4 | 2022-10-03 | 2022-12-01
Business w/ Tech Initiative: [US] Migrate to email as mode of communication for | 679 | 8776 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Liz Neal, Julia Selph | On Track | 10/31/24: Ready to submit to L4 Email/SMS feature is available in CEBS cases; refinement of available templates continues with the most recent CEBS load adding additional templates for users. DL is consuming data with work toward incorporating into reporting. Email activity data available, analysis in progress. PRT Escalation pilot shifted to creating a CE GO team in MEMH. The intent is to have "boots on the ground" for high risk shipments with a last scan at MEMH, Pilot started 9/23, with access and environment training completed in October. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-11 | 2024-11-29
Business Only Initiative: [EU] Pod 3.4 COPC Adoption and Roll-out | 694 | 8794 | Business Only Initiative | SGA - Commercial | SG&A | Dennis Atkins, Andrea Mohrhardt, Philipp Muenchenberg | On Track | 2025-08-20: All exits occured as of 31 May 2025; then we took 1 month to verify the exits. L4 proof document is completed and uploaded. Document sent to local FP&A for approval on L4 submission. Local FP&A gave approval as of 25 August 2025. August24: Train 3 HPMT finished. Dependencies to #82155 for Quality Management Software managed. Extra Change Management effort for POC country UK required, currently no Lead from UK due to impact of project "Forward". New phasing of Softlaunched planned. Final Deployment date 2nd October scheduled with last remaining chapters for COPC´s feedback (last session on budget) July24: Self- Assessments executed in 8 x 0, 5 days & shared with COPC 3.4 approach did not work in practice (Verification of Skills during the PR Role play as defined in SOP/Approach from L&D ownership). Suggested was to add Skill verification into Quality what we did. This is now combined with Launching 3.6. June 24: Decision day took place. GATE DOCUMENTATION shared and stored on HP Sharepoint with all decisions, actions and simulations. Self- Assessments done for all POC teams, except Portugal on Quality Cluster. HPMT Group 2 is close to finish, continuous good progress in getting people certified. May 24: HPMT Group 1 finished with >90% completion and great feedback. Self- Assessment preparation kicked- off successfully. Alignment for Pre- read and preparation for Decision Day (17th May) took place half a day. Onboarding for COPC Advisors took place as planned. Quality Framework challenge on not 100% of SPV and Quality people calibrated, so TM´s might not count raised as a Risk to MD´s, as well as KMS (2.9) not being used by our people but also not connected to fedex.com = no deployment. April 24: HPMT Training Train 3 kicked of, Train 1 finished. Feedback is excellent and the change management impact remarkable, what a very good decision to adapt the Business case to a brouder scope and go for soft approach all Europe instead of just 3 POC countries. POC countries are preparing further for certification, HPD (High Performance Dashboard) is now giving most of required transparency and will allow successful Decision preparation at 17th May and then MD´s/VP decision 18th June for future FY impact on Drive 3.4 and with that HPD specific targets and metrics. 3 new COPC Advisors/Project Leads are selected out of >40 people with interest in the role, 30 1st round and 9 second round interviews (in a panel of 4: 1 MD, 2 MGR, 1 Analyst) incl. Case Study proof of ability. Next steps are onboarding and alignments with COPC on Advisor/Auditor certification. Deployment Session was successful, next one will be in June (and also the last one of Phase 1). March 24: decision to change the Project phasing from POC only to all Europe, so we softlaunch (80-85% compliance) all chapters to all Europe and accept a potential delay of POC certification but bringing the benefits of the High Performance to all Europe much sooner Feb24: HPMT (High Performance Management Techniques) Training for 501 CE People communicated and launched - 3 Trains (Change Management exercise & knowledge resource built Jan23: Deployment of WFM done with COPC. HPD Launch successfully with POC countries. 2.15 internal check in on Gaps with POC countries done. Planning for HPMT (501 trainings for SPV, Prof. Mgr. and above) sucessfully set up and in alignment with LR/EWC and MD´s now (except Germany) Dec.23: Preparation if CY2024 planning done for all chapters, sign- off of nearly all approaches. UK stopped Quality Framework due to peak without alignment, need to assess the consequences in January. Nov23: Deployment People chapters & Quality Wave 2 kick off Softlaunch successful and as planned, no issues Oct23: Gained 56 Decisions on "High Performance Decision Day" together with Glenn and all MD´s. Timelines for 3.4 remain, as well as Money Step but POC certification needs to be re- scheduled to November 2024 instead of February 2024 because our metri | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-03 | 2025-06-30
Business Only Initiative: APAC - Improve Attrition Shrinkage% | 75102 | 8812 | Business Only Initiative | SGA - Commercial | SG&A | Ayden Tay, Aiman Khan | On Track | 08/12 - Submitted for L4 approval in Wave 08/05 - Capture new hires and Attrition buffer% savings since Jun 2024 07/29 - Capture actual Attrition versus forecast 07/22 - Flex calls to APAC sub-regions with Service Outlook file 07/15 - Flex calls to APAC sub-regions with Service Outlook file 07/08 - Submitted for L3 approval in Wave 07/01 - Capture actual Attrition versus forecast 06/24 - Flex calls to APAC sub-regions with Service Outlook file 06/17 - Flex calls to APAC sub-regions with Service Outlook file 06/10 - Update HR attrition for May 2024 06/03 - Proactive hiring commences 05/27 - Alignment completed for proactive hiring in Service Outlook 05/20 - Flex calls to APAC sub-regions introducing Service Outlook file 05/13 - Planning Service Outlook file 05/06 - Planning Service Outlook file 04/29 - HR attrition data ready 04/22 - Fixing HR attrition data gaps 04/15 - Fixing HR attrition data gaps 04/08 - Fixing HR attrition data gaps 04/01 - Planning Service Outlook file 03/25 - Submitted for L1 approval in Wave 03/18 - L0 generated in Wave | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-02 | 2024-07-31
Business Only Initiative: MEISA - Improve Attrition Shrinkage% | 75197 | 8813 | Business Only Initiative | SGA - Commercial | SG&A | Ayden Tay, Aiman Khan | On Track | 08/12 - Submitted for L4 approval in Wave 08/05 - Capture new hires and Attrition buffer% savings since Jun 2024 07/29 - Capture actual Attrition versus forecast 07/22 - Flex calls to MEISA sub-regions with Service Outlook file 07/15 - Flex calls to MEISA sub-regions with Service Outlook file 07/08 - Submitted for L3 approval in Wave 07/01 - Capture actual Attrition versus forecast 06/24 - Flex calls to MEISA sub-regions with Service Outlook file 06/17 - Flex calls to MEISA sub-regions with Service Outlook file 06/10 - Update HR attrition for May 2024 06/03 - Proactive hiring commences 05/27 - Alignment completed for proactive hiring in Service Outlook 05/20 - Flex calls to MEISA sub-regions introducing Service Outlook file 05/13 - Planning Service Outlook file 05/06 - Planning Service Outlook file 04/29 - HR attrition data ready 04/22 - Fixing HR attrition data gaps 04/15 - Fixing HR attrition data gaps 04/08 - Fixing HR attrition data gaps 04/01 - Planning Service Outlook file 03/25 - Submitted for L1 approval in Wave 03/18 - L0 generated in Wave | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-02 | 2024-07-31
Business Only Initiative: [CA] Increasing Span of Control | 1585 | 8875 | Business Only Initiative | SGA - Commercial | SG&A | Chris Strickland, Denise Vourtzoumis | On Track | Should be in L5 | I: L4 | Active | TEMP L4 - Enter L4 | 2022-10-17 | 2022-11-01
Business Only Initiative: [CA] Outsource ROD Payment Calls to Vendor | 1588 | 8876 | Business Only Initiative | SGA - Commercial | SG&A | Doug Berry, Kyle Tiemann, JAMES HALE IV | On Track | On Track | K: L5 | Active | L5 Feedback Requested | 2022-10-31 | 2023-06-01
Business Only Initiative: [CA] Increase IVR containment | 21807 | 9011 | Business Only Initiative | SGA - Commercial | SG&A | Jenny Chan, Kyle Tiemann | On Track | 9/4/2024 - On July 2nd, there was a Phase 4 launch for CTP (Canada Transition Plan – Canada Network 2.0) in the Greater Toronto Area. Some delivery services have been impacted (Phase 4 accounts for ~61% of the overall shipment volume) and there were an increase of call volume into CS. Automation rate/savings were lower than the forecast (not accounted for CTP launches). 3/28/2025: In the Canada IVR, similar to the US IVR, the original direction was to update the IVR to allow call transfers for account holders only (i.e. with a call transfer restriction for non-account holders). The IVR automation rate forecast was initially based on this approach. However, considering the customer experience, management has decided to update the IVR functionality to make it easier for callers to reach a customer service agent. As a result, automation rate has decreased since we’ve been making the IVR changes, and the previous forecasted savings will not be applicable moving forward. Updated the following values to re-baseline/forecast: * Updated FY25 Forecast KPI (March - May '25) = 48% * Updated FY25 Forecast Revenue (March - May '25) = $60,211/month * Updated FY26 - FY28 Forecast based on using the FY25 Actuals 4/17/2025: There was a meeting with Jenny Chan, Aysha Maaghul, Samantha Baltodano, and Juan Udarbe on 4/16/26, to discuss the rebaseline and reforecast for FY26 - FY28. Following the full deployment of IVR Release 48 in the CA IVR on 3/21/26, new call flows and business rules were implemented to allow shippers/account holders to transfer into the call center to speak with an agent. Based on current automation rates, the estimated IVR automation rate for April and May 2025 is approximately 48%. For the FY26–FY28 rebaseline, we will use the average IVR automation rate of 49% from FY25 (January–May ’25 actuals) to reflect the latest IVR enhancements, which enable more callers to transfer to agents. Given this direction, the automation rate may decrease, and future savings for this initiative are projected to be zero (as the updated baseline has higher automation rate than the forecast). Updated the FY28 exit rate based on this rationale. Also, FY26–FY28 rebaseline and reforecast values have been updated accordingly. • FY26 – FY28 Rebaseline = 49% • FY26 – FY28 Forecast = 47% 7/8/2025: Noticed that the FY26/FY27 baseline and forecast is showing previous values. Updated the FY26/FY28 baseline and forecast to the following re-baseline values (calculated back in 4/17/2025): • FY26 – FY28 Rebaseline = 49% • FY26 – FY28 Forecast = 47% 9/18/25 - Considering the customer experience, management has decided to update the IVR functionality to make it easier for callers to reach a customer service agent. As a result, IVR automation rate has reduced since making the IVR call flow changes for customer experience, and the previous forecasted savings will not be applicable moving forward. We updated the financials to re-baseline/forecast for FY26 – FY28 in April and estimated no NRB after completion of the last milestone. | K: L5 | Completed | TEMP L5 - Completion Approval | 2023-02-01 | 2025-08-25
Business Only Initiative: [LAC] Customer Experience Brazil Domestic Enableme | 21258 | 9040 | Business Only Initiative | SGA - Commercial | SG&A | Gabriel Kayser, Fernanda Guerra | Attention Needed | 9040 - 21258 - [LAC] Customer Experience Brazil Domestic Enablement" is on hold due to some dependencies on BDE deployment in BR that is still not ready for full use. Once BDE is ready for use, this project will be continue and updated. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-01 | 2024-01-02
Business Only Initiative: [AMEA] APAC - KULSM Rental Cost Reduction | 93664 | 9144 | Business Only Initiative | SGA - Commercial | SG&A | Sri Ganesh Muthusamy, Chen-Yen Yew, Lance Tam | On Track | Repurpose initiatve with another facility rental reduction (from ECCC - KULRC Tower A to KULSM partial floor reduction). | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-26 | 2026-04-30
Business Only Initiative: [AMEA] MEISA Average Talk Time (ATT) Improvement | 57563 | 9145 | Business Only Initiative | SGA - Commercial | SG&A | Vikeeth Kottari, Sharath Shetty | On Track | Due to launch of GC3 in Q4'2025 approx. 30% of the calls which are short duration calls are contained on the IVR resulting in increase in ATT. The ATT has increased to approx. 260 sec against the agreed target of 227 sec. AHT has further increased with introduction of GC3. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-02-19 | 2025-02-28
Business Only Initiative: [CA] Optimize Email channel to reduce email volume | 12589 | 9166 | Business Only Initiative | SGA - Commercial | SG&A | Abdul Lawal, Oleg Machnyk | On Track | 4/29/2025: Baseline Fiscal Year of Initiative updated from FY22 to FY25. Initiative was re-baselined before 4/17/25 03/27/2026- the initiative has been at runrate since 2024 | K: L5 | Active | L5 | 2023-01-20 | 2024-08-30
Business w/ Tech Initiative: [EU] Pod 3.5 Proactive Notifications | 17515 | 9358 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Dennis Atkins, David Gascoigne, Philipp Muenchenberg | On Track | 24-September-2025; Initiative finalized for L4 as of 31 June 2025. Was delayed entry to finalize L4 document and had competing prioritiies from other L4 submission updates. EU FP&A approved. Need architecutre confirmaton. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-04-10 | 2025-06-30
Business w/ Tech Initiative: IVR Problem Resolution and Self Service Enhancemen |  | 87342 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Anuja Jadhav, Rich Mauney | On Track | We have a dependency on the Claims ART, their API isn't built in a way we can directly consume it, so they need to make few changes to their API. Now From Jan2026 they are rebuilding claims and so this API will be built from scratch and they do not have a timeline when it will be ready. | E: L2 | On Hold | L2 & CCH | 2025-07-09 | 2026-06-16
Business Only Initiative: Decommission Unused TFN's and Telephony Circuits |  | 91418 | Business Only Initiative | SGA - Commercial | SG&A | Pandiyan Durairajan, Rich Mauney | On Track | TFNs will be bundled together based on category. These categories will be used to develop the L3 milestones. 04/15/2025 - Updated the details from Cost Avoidance to Cost Savings. This is hard benefits vs soft. 04/16/2025 - Please find my comments for the below questions. to confirm, they state % Cost Reduction, but the values are in the thousandths. Should this be the case? **PD:**Yes, Cost Saving is the right flag, but I do not see this tag in the given option list to choose. Also, to note at this time no Exit Rate has been added for FY28. If there is no Exit Rate, then the Exit Rate row, FY28 column field can be blank. **PD: **Yes, Exit Rate row is blank. 04/16/2025 - I did review with our Financial person and upodated the Exit Rate and resubmitting now. Thank you. 4/17/2025 - Approved by EPM. Submitting for L3. 07/17/2025 - Planning to decommission the L3 back up circuits. This is another saving $3,642.38 monthly, ($43,708 annually). Updated the Financials & Milestones with existing DRIVE initiative ‘Decommission Unused TFN's and Telephony Circuits_0001883’. 1/5/2026 - Updated the 'Actuals' since to reflect increase in savings. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-05 | 2026-06-01
Business w/ Tech Initiative: LAC-Shipfast-Renewal - Mexico Dom T&C |  | 103910 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Carolina Ivette Lezama, Laura Carpenter, Amabel Adriana Osorio | On Track | Project assinged to Commercial POD and ready to follow the process. | I: L4 | Active | L4 | 2025-07-03 | 2026-01-30
Business w/ Tech Initiative: ECD Preferred Future State |  | 104641 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Drew Kelley, Kevin Lipe, Rushika Patel | On Track | 05-28-2025 / QA Feedback Provided / Samantha Baltodano / Domain QA Expert Review L0: * Update the Business Process and/or Operational Impact to explain the business process/app needing modification and the impacted business and tech environments. This should be 3-5 sentences * Update the Ability To Statements to be in the following format: As a <type of user>, I want <some goal > so that < some reason> For additional guidance and examples, please refer to this job aid: L1-ARCH-Demand_Shaping_Shaping_Job Aid. L1 * Update the Primary Type of Value * If there are hard benefits, please select a Type of Value of ‘Cost Savings’ or ‘Revenue Growth’. * Upload your LBC to Planview | G: L3 | Active | TEMP L3 - Enter L3 | 2026-01-01 | 2028-11-30
Business Only Initiative: APAC First and Repeated Call Reduction |  | 106437 | Business Only Initiative | SGA - Commercial | SG&A | Chen Qiu, Man-Yee Evelyn Lee, Man Mango Li | On Track | All tasks are progressing as planned, no major issues identified. 2026 Jan 14th - Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL2 | G: L3 | Active | L3 | 2025-12-01 | 2027-02-25
Business w/ Tech Initiative: CED B2 - Improving CE Desktop |  | 113306 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Phillip M. Smith, Van Wilson | On Track | 2/13/26 Adjusted Money step per approval from Megan Lightford based on delay in migrating ODC Channels. Adjusted other dates accorddingly. Single Solution initiative with the work primarily only on CED Art. Working on LBC. 7/11/25 Updated to reflect IT in benefits cash flow for license savings 7/11/25 Finance soft and hard savings have adjusted and updated per meeting on 7/10 7/10/25 Updated to reflect soft savings for SF licenses through Aug 2026; hard savings Sep 2026 through May 2028 when the SF Enterprise Agreement is renewed 7/9/25 Updated Money Step Description to Action within the Milestones. Added note related Salesforce Licenses: When the SELA with Salesforce expires next summer, any excess licenses we have at that time will be returned to Salesforce, thereby reducing our overall Enterprise spend. We will keep some licenses to deploy to non-CE users and do a chargeback to recover our cost. We anticipate there will be excess licenses but we don't have an exact number at this point. 6/27/25 Note: B2 is continuation of the original Phase B initative due to potential IT costs being incorrectly applied to Phase B and Phase B ending May 2025. However the benefits for B2 are different than Phase B with a focus on the value of the remaining work identified and savings from reduced Salesforce licenses. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-17 | 2026-06-30
Business w/ Tech Initiative: LAC_BRA_DOM_CE_Automation tools improvements |  | 114706 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Willian Augusto de Souza, Fernanda Guerra | On Track | * 8/1/25 - QA Expert SL2 review completed by Samantha Baltodano * 8/12/25 - Reviewed with Aysha Maaghul: - Tech T-Shirt size is "M", but as it will be developed by Local Brazil LMS IT the development costs will be comparable to "S" or lower. * 10/28/25 - Commercial L2 triage performed on 09/08/25 needed a second review, since the project aims not only to replace the Oracle Rightnow (EAI 3535657, until March 2026, date to renew the yearly contract) but also to replicate to BR DOM (LMS ops system) some tools already available in FedEx corp., on the following weeks it was compared the need for BR dom (please see the comm triage ppt in attachements), with the high level effort to develop a connection to LMS to Corp systems (CED, CEBS, etc) vs the effort to use a vendor (zendesk). The vendor would cost 15k usd to implement within a 3 months timeline, to develop corp tools could take +1yr, in both cases the efforts would be temporaly until the migration of BR dom to FedEx corp systems (BDE - migration timeline is in progress). On 10/27/25 there was a meeting that I got to an impass regarding the "IT Owner", since the project would be applicable only in BR Dom, it was recommended be manage locally (LAC BR) by the global CE team, but at it is a CE tool it was recommended to be managed under CE by the LAC team. * 12/12/25 - Project set to on-hold | E: L2 | On Hold | L2
Business Only Initiative: APAC - WUH CE Office Rental Cost Reduction |  | 159806 | Business Only Initiative | SGA - Commercial | SG&A | Yu-Heng Tang | On Track | 2025 Oct 23rd - Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL2 2025 Nov 6th - Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL3 | I: L4 | Active | L4 | 2025-10-01 | 2026-02-27
Business w/ Tech Initiative: [US] Increase user experience and adoption of fede | 648 | 7738 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Lindsay Roberson | On Track | 3/5/26 - Ready to complete initiative - have full 9 months of actuals reported 2/12/26 - reported dec actuals to complete L5 requirements; move to close out init 2/2/26 - no new updates 1/28/26 - no new updates 1/19/26 - no updates 1/12/26 - no updates; waiting to be able to report latest Nov/Dec actuals 1/7/26 - Report Dec actuals then can move to L5 to close out init. Originally the init was just submitted from L2 to L3 and then L3 to L4 in early June at the same time (I’m assuming due to the re-baselining exercise) in Planview, which was 5 months later than your money step timing of January 2025 was estimated to be, so we’ll need to work around that delay for our next steps. Since your money step was technically in Jan 2025, I think we can reasonably count the inputs from Jan to March as contribution to L4 requirements of 3 months and you can note that, and then submit to L5 for the remaining now. With that—we can say that Jan, Feb, Mar = L4 inputs for 3 months post-money step in Jan And then—April, May, Jun, July = L5 inputs so far-- 4 months inputted of the 9 months required for L5 Then you only need to input actuals going forward for Aug, Sep, Oct, Nov, Dec = remaining 5 months of the 9 month period required for L5 and then you’re done When I map the actuals values so far, since much of the actuals submitted so far were pre-L3, meaning they haven’t yet shown “consistent value”, which is part of the reason TO Finance requires a full 12 months of “mature consistent value” – when the value looks more consistent, which is the goal of L5, we’ll be able to close this one out as “completed”. ** My Next Steps:** Document my money step was technically in Jan 2025, and the actuals inputs for Jan-Mar should meet the L4 3 months requirement, and that April-Dec will be your L5 inputs for remaining 9 months requirement Submit the init to the next stage gate of L5 Enter actuals for June until Dec 2025 for next 5 months to close this one out to fulfil the requirements from L5 to Completed 12/22/25 - no updates 12/16/25 - no updates 11/10/2025 - no updates 11/3/2025 - no updates 10/27/2025 - no updates 10/20/2025 - no updates 10/13/2025 - no updates 10/6/2025 - no updates 9/30/25 - no updates; trying to move to L5 9/23/25 - no updates 9/16/25 - no updates 9/9/25 - no updates 9/2025 - no updates 8/2025 - no updates 8/15/25 - **My money step was technically in Jan 2025, and the actuals inputs for Jan-Mar should meet the L4 3 months requirement, and that April-Dec will be your L5 inputs for remaining 9 months requirement 7/14/25 - no updates 7/7/25 - no updates 6/23/25 - no updates 6/16/25 - no updates 6/9/25 - no updates 5/22/25 - no updates 5/15/25 - Met with David (Finance) and Roglly (Init 649) on rebaselining our business case. David instructed we take an average of our past actuals for FY26 (to date I have 11 months of actuals currently - May 2024 - Mar 2025). I will enter Planview Finacials for FY26 Forecast with 94,300 for my init. Also updated FY26 KPI for New calls/1k 7.69 for all months; Also updated Ease of Use metric to be 4.00 for FY26 (during FY25, we moved to a 5pt scale vs 11pt scale) 4/29/25 - meeting with David (Finance) and Roglly to discuss rebaselining to FY25 4/11/25 - no updates; still trying to get into L4 4/7/25 - Met with David; he recommended to create a clean excel sheet to help Mark understand our init (include milestones w/ proof of launch) 3/28/25 - Still getting flagged for not being in L4 when I am repeatedly trying to get into L4, have messaged FInance multiple times; Need solution to either go to L4 or stop getting flagged for not being in L4; init has comleted all required steps for L4, documented 9months of actuals, and uploaded & emailed Finance 'proof of launch' emails and documents 3/18/25 - Was told by Finance Lead, David, that my init needs 3 months of actuals POST money step, so will continue to report actuals until then and try again for L4 in May 2/12/25 - Met with David, waitin | K: L5 | Active | L5 Feedback Requested | 2022-10-17 | 2025-01-08
Business w/ Tech Initiative: Global Digital Plat - Simplify & Amplify Login |  | 92238 | Business w/ Tech Initiative | SGA - Commercial | SG&A | James Sherman, Senthil Karuppiah | Some Issues | 4.1.25 - Dev work is set to be complete by Jul25 with support for app retirement continuing until Jan26. Key stakeholders met today to agree on the next steps for moving the initiative into planview: * Data/AI will be removed as an impacted portfolio greenlight * April White will document the medium t-shirt size for the remaining work * Jim Sherman will create the epics/milestones in Planview * Porftolio greenlight needs to be given by Commercial before moving to L3 * CPEL is not required since this is no longer a cross-portfolio impact 5.2.25 - Now that the project is approved in L3, work from supporting teams will resume. FCL retirement is slated to complete in July, while work on ADMC retirement will continue until the end of the calendar year. 6.24.25 SSO (the legacy session management tool) is retired We are waiting for 39 clients to adopt new FCLA jar or CALC to shutdown FCLA Server WFCL - awaiting client integration for Account Linking and Invite user flow ADMC 3.0 - we have 100 plus endpoints to deliver to clients and have them onboard LGNC - yet to be made active/active FRCS - awaiting changes from USRC 3.0 and stopping JIT login 10.3.25 We are waiting for 39 clients to adopt new FCLA jar or CALC to shutdown FCLA Server WFCL - awaiting client integration for Account Linking and Invite user flow LGNC - yet to be made active/active FRCS - awaiting changes from USRC 3.0 and stopping JIT login 12.2.25 - FCLA/CALC jar adoption to retire FCLA: Still teams are working on adopting new jar versions and triaging the issues - Targeting to complete in test levels by end of Dec Jar adoption should finish next PI Goal is to complete project in prod by end of Jan'26 1.16.25 USRC3.0 is retired. ADMC is not yet retired but 100% of the login traffic has been migrated to LGNC. WFCL is scheduled to retire by 1/31/26. FCLA is scheduled to retire by 2/28/26. 4.8.26 Already Retired – USRC 3.0, SSO, WIDM, WSTM, FEDN, ADAT WFCL Retirement – In Progress 5/31 Legacy CIAM UI – Migrate to modern Angular UI Completed Invite User flow is Modernized using JOIN WREG Last flow of Account Linking in progress to JOIN WVAL FCLA Retirement – In Progress 5/31 Legacy CIAM Backend – Migrate to USRC Modern Rest API JAR dependent Retirement – Removes Traffic from FCLA servers and makes calls go to USRC. FCLA Adaptor Jar – 52 Clients/49 Completed Prod CALC with Adaptor Jar – 34 Clients/ 8 Completed Prod ADMC 3.0 - In Progress 5/31 Legacy ShipAdmin Backend that is being migrated to modern rest services(5) Dev work to complete 4/30, Final Client Onboard 5/31 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-01 | 2026-06-01
Business w/ Tech Initiative: Sales Incentive Compensation System Modernization | 24492 | 7848 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Sherman Snyder, Will Washington | On Track | Uploaded evidence of Money Step and submitting for L4 approval. Callidus/SAP contract ended on August 17, 2024 and Varicent contract renewal will occur on October 11, 2024. The annual license renewal amount is below the current contract amount. Recurring Benefits were originally expected to begin June and July, 2024, but Varicent contract wasn't fully executed until October 2023 versus June 2023. I adjusted the forecast for September, but was unable to change the forecast for June, July and August. | I: L4 | Active | L4 Feedback Requested | 2023-10-30 | 2025-11-17
Business w/ Tech Initiative: Account MDM Modernization | 36221 | 9067 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Devin Lewis, Raghavendra Dhanekula | On Track | Update 01/16/26: Submitted demand request for adopting team to assist in E2E testing starting next month. Wrapping up last development deliverables, and also doing match rate testing and tuning for new matching algorithim. Project is trending yellow, but still expected to complete within project timelines. Update 7/10/2024: Updated the spend forecast so that we start incurring expenses in September, which is when we're expecting to have the funds allocated. Cost schedule is still being finalized, so the monthly amounts could change between now and the September timeframe. Update 5/28/2024: Officially received TCH approval, and went through one last review session with Finance and McKinsey before submitting to L3. Update 02/19/24: Added milestones, KPIs and PPM into WAVE as per the required input to move to L3 approval. initiative has also be submitted for TCH review Update 12/19/2023: Submitted for L2 approval. Update 12/15/2023: Finance review in progress to ensure all requirements are present to move to L Update: 11/06/2023: Met with Finance to start getting input on how we get L2 approval from Jane Amaba (they sent over two files that we'll need to work on updating, and they asked for contract details regarding what we're spending on IBM Infosphere Update: 10/30/2023 - Updated fields to push effort to L2. In this step, we added all approved benefits, and the one-time implementation cost based off on-prem implementation. Also, requested a meeting with Finance to begin getting TCO input | G: L3 | Active | TEMP L3 - Enter L3 | 2024-10-09 | 2026-06-01
Business w/ Tech Initiative: COM - S&CDE - CDE ART - Relay42 Migration to Azure |  | 106340 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Ellen Oude Lashof, Sandy Whitten, Punitha Sekar, Vikram Manchala | On Track | 03.06.2026 Money step evidence added ( that is: no extension of Relay42 contract): Encore screen shot has been added + proof that EAI of Relay42 has been retired. 02.19.2026 All use cases that we intended to migrate have now been migrated and are fully working. The work is complete, the measurements are in place and the Relay42 tool is inactive sincd Sep 1, 2025. 12.08.25 Situation: a)EU onboarding: from start until recently, we were 50% of email addresses in DataCloud . Although the journey was working as planned, the audience was not correct. Vishal and others have been working on getting this resolved, In the meantime small changes have been requested. No more fundamental obstacles to move to L4 with respect to this journey b)Rate Quote retargeting : due to late delivery of this use case, we implemented an MCP/SFMC based solution as a contingency solution (Similar to CA Quote Retargeting). After MTP of the CDP/DC/SFMC solution, we have tested the journey and face the issue of latency of DataCloud – we can’t send an email within an hour after a quote has been done. We could only T do proper testing after MPT as to whether customers are getting the right experience. And due to the latency of DC, we identified at least 20% of customers would get an email with the message ‘ finish your quote’ but in fact finished already – thus wrong message. In several sessions in September, the teams worked together, got creative and agreed to see of a specific query would solve the problem. Nothing has been done since. We are not using the CDP/DC/SFMC solution as it doesn’t fit our quality criteria. c)For any of the omni-channel journeys, we are not able to set up AND measure experiments properly. We have implemented our own interim solution to measure incremental impact. What have we done in the meantime Based on all our PDD requirements, we compared the two solutions : MCP/SFMC based vs CDP/DC/SFMC based – conclusions and recommendations can be read in the deck attached. Impact on L4 A)Compare PDD requirements with the MPT delivery : it would not meet the definition of done in my respect. Especially the DataCloud latency is a topic that is so fundamental to the performance of the use case. We should keep this in L3, define corrective actions /development and change the mile stones in Planview B)Compare PDD with the interim solution: it would most likely get a definition of done; experimentation and analytics are not getting high grades – but it is working. We could move to L4 but any other further development (see deck) would require a new DRIVE init. Is that realistic? 03.25.25 - Submitting to next step. Note, previously approved as Business Only. PV8310. Data&AI requested new submission as Business w/Tech. Work was planned for CY25 PI02; however, stopped due to Data&AI last minute request. | I: L4 | Active | L4 | 2025-07-30 | 2025-10-07
Business Only Initiative: DiCicco FY26 APPO Cost Savings |  | 166675 | Business Only Initiative | SGA - Commercial | SG&A | Kayla Donner | On Track | 4/10/2026: March actuals updated. FY26 cost savings continue to be measured in the KPIs. 3/6/2026: Submitting initiative for L5 approval following alignment with FP&A Finance. Actuals logged for entire FYTD and costs savings towards $10M goal for FY26 capture since September 2025 (as shows in KPIs). DRIVE administrateive process responsible for the time it took to get to this stage. 3/4/2026: February actuals to be available week of 3/16. Moved February forecast to actuals line temporarily for compliance until actuals are received from Finance. Will revise week of 3/16. 2/16/2026: Received approval from Lorri Hughes and Aysha Maaghulon Money Step completion. Attached evidence and submitted for L4. 2/13/2026: January actuals entered. Emailed Financial Analyst (Aysha Maaghul) to confirm submitting to SL4, as actuals have savings began to be realized in September and tracked in the financials. FY26-specific savings logged under init KPIs. Waiting response from Aysha on progressing forward. 1/13/2026: Prepped initiative for SL3, inclding adjusting financial forecast to reflect the confirmed $8.133M in FY26 cost savings idetified & confirmed by FP&A Finance, revising the NRB to $1.297M. L2 LBC completed in Planview, Financials updated and file uploaded, KPIs added (will only track through FY26 based on alignment with Finance), Milestones & Risks added. Received confirmation from Financial Advisors (attached), Aysha Maaghul and Lorri Hughes, that initiative is ready for SL3 submission. 12/5/2025: Aligned with Financial Analyst (Lorri Hughes & Aysha Maaghul) again per Domain Finance Lead's request, extending financials to 2027 and 2028. Financial Analyst has reviewed and confirmed submission to SL2. Additionally, meeting took place 3 PM 12/5 with Mark Mantaro, Ben Sauls, and Jerome Miller to align on FInancials in Planview - received comfirmation that it was ready to be submitted based on meeting. Submitting again for approval. 11/21/2025: Received feedback from Domain Finance to align with Financial Analyst and resubmit. Aligned with Aysha Maaghul via Teams screenshare to review L1 LBC, Excel file, and Planview financials. Received approval to resubmit to SL2 based on review. 11/20/2025: Met with Aysha Maaghul and Lorri Hughes to confirm financials entered correctly. Aligned on the following: baseline is FY25 spend, but the $10M will be tracked in KPIs, which is the difference between the September forecast and current forecast/actuals. Net benefit is shown based on the difference between FY25 and Sept FF less the $10M, $3.3M. Updates have been made in Planview accordingly. 11/19/2025: Continuing to wait for Domain Finance to review SL2 financials to move forward to L2. 11/7/2025: Lorri Hughes provided FY25 spend (baseline), FY26 budget, and estimated monthly cost savings per APPO for three categories identified projects fall into. Completed L1 LBC template, attached and populated L1 LBC fields. Aligned with Aysha Maaghul on inputs, including baseline va. target value and using the $10M in FY26 budget reductions as the NRB, as these reductions will not come back in the future. Submitting for SL2 and will continue to refine monthly forecast in Planvew before submitting for SL3. 10/31/2025: Met with the Marketing team and Finance. Lorri Hughes helping to gather the FY25 baseline data (spend), FY26 plan + identified reductions (target value) to build out the LBC. Money step proof will be the P&L actuals. | K: L5 | Active | L5 | 2025-09-01 | 2027-06-18
Business Only Initiative: FY26 Customer Engagement Marketing Cost Savings |  | 166681 | Business Only Initiative | SGA - Commercial | SG&A | Kayla Donner | On Track | Cancelling this initative, as all FY26 cost savings for ADR are to be tracked under a single initiative (#166675). | C: L1 | Cancelled | L1
Business Only Initiative: SG&A JDR Brand & Comms FY26 APPO Budget Reduction |  | 166687 | Business Only Initiative | SGA - Commercial | SG&A | Kevin B. Reasons | On Track | Mar 19, 2026 -- Based on EPM request, updated financials to include baseline KPIs. The baseline for all KPIs is $0 as no FY26 savings would be captured without this initiative. Resubmitting for L3 Review. Sept 2025--$10M budget cut has already been reduced from projects in MAP tool where it was identified and moved to a single JDR giveback project to ensure it will not be spent. Dec 18 2025 -- aligned with Finance matrix (Michael Halley) who provided financials, baseline forecast, and KPI tracking numbers. Collab with Michael Halley, Lorri Hughes and Ben Sauls in Finance to ensure numbers input in financials are accurate and represent the appropriate forecast and KPIs for the giveback. Prepared to enter L2. | G: L3 | Active | L3 | 2026-02-02 | 2026-06-15
Business Only Initiative: EMR - Packaging - Box Competitive Event | 82191 | 9553 | Business Only Initiative | SGA - Commercial | SG&A | Mark West, Anchit Mahajan | On Track | 10/15 - Update this project has been now broken into sub sections. The first savings that was gained was from Switch to Direct Print from PrePrint with incumbent supplier who retained series 1, the second savings that will come on board in Oct. is from onboarding of the new non incumbent, and the final savings that will take effect is the material change with incumbent who retained series 1 which is reduction in board grade. 09/18 - All complimenatary will move to Kraft. Lab approved pricing recived. set to receive oct. 15. POs have been placed. 03/12 - Lab approved some reduced board boxes options (current kraft specs) Call with IP to be arranged ref Mottled White. Program Costings and savings opportunuties broadly established and shared with Product Makreting. Initial proposed recommendation. Final recommendation will be provided once confirmation from final timelines from IP. 03/07 - COMPLIMENTARY – Pricing validation and options reviewed with INTL PAPER and WEST ROCK (on $905/ton pricing) This will be proposed to the core team. MOTTLED WHITE BOARD sent to lab for testing. Awaiting official test results from lab for reduced board options. 03/07 - RETAIL – Pricing confirmation received from PCA with recent PPW pricing update from $865/tom to $905/ton This will be discussed with the core team. 02/20 - Mottled white board samples requested for Lab to review and advise. 02/20 - Plan of ETA for provision of initl boxes to be made by IP by 24 FEB 02/14 - Draft contract loaded onto EnCoRE, (without commercials) and base template shared with IP 02/11 - COMPLIMENTARY samples arrived at the lab. Lab has advised 1 week conditioning and then tests will be planned starting with the reduced board versions. 02/10 - COMPLIMENTARY BOXES - Pricing confirmation estalished with IP following querys. Samples prepared and ETA to LAB - 10th / 11th Feb to the lab. Request made to first test reduced board grade and give feedback urgently to determine savings opportunity. 02/10 -RETAIL BOXES - validation of pricing requested from PCA due to their change of PPW rate on last pricing request, which would add 6% onto the cost. 02/02 - Expected transport of samples to Lab 01/26 - Production scheduled for 75 samples 01/24 - BAFO pricing rec'd .. inital analysis done. 01/19 - Tooling ordered 01/13 - Sent out BAFO request to Intl Paper. Awaiting confirmation of sample timelines to Lab. 01/10 - IP advised that they do not currently have the material that the boxes will be made in. Pkg Lab and Team to discuss. 01/10 - Pkg Lab have proposed IP to either send CAD table samples in material that production boxes will be made in. 01/09 - IP replied back ref tooling and produciton. They advised 6 weeks to obtain tooling for samples + 7 days for sample production. 0/04 - Team validating Retail Box SKUs 01.03 - Pkg Lab highlighted that Kg Box and X1 & X2 box would need graphics changes due to manufacturing process by IP essentially inversing the design 01/03 - Final Dieline drawings sent to IP 01/02 - Team to review Retail Box portion for completeness 12/27 - Pkg Lab asked IP to confirm timelines on tooling proposition. 12/23 - 6 out of 8 CAD drawings sent to IP 12/14 - CAD samples due c13 JAN 25 12/06 - Requested conformation of ability to produce full SKUs and qty in one coastal facility 12/04 - Sample selection of boxes identified and requested from IP + requested ETA 11/22 - Pricing validation - IP responded, no response from PCA 11/21 - IP conformed pricing for full kit excluding plastic cover 11/20 - Requesto to validate pricing proposals sent (ETA 22/11) 11/12 - PCA sent in revised ideation proposals/costs 11/11 - IP sent in revised ideation proposals/costs 11/7 - Ideation session with PCA 11/1 - Ideation session with Intl Paper (IP) 10/30 - Ideation sessions booked with 2 short-listed bidders NOV 1, and NOV 7 10/23 - Ideation kick-off session to be held with shortlisted bidders .. Full ideation session to be scheudled w/c | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2024-08-26 | 2025-10-15
Business Only Initiative: EMR Packaging EU Paks (Switch to US Supplier) |  | 132128 | Business Only Initiative | SGA - Commercial | SG&A | Pankaj Kumar Singh, Jason Ng | On Track | 04/13- March Savings updated. 03/04 - Forecast readjusted based on the add. vol. Feb'26 actuals updated. 01/13/2026 - Moneystep evidence email / spreadsheet is uploaded. 11/12/2025 Savings date shifted to Feb'26 to deplete inventory from prior supplier. Business Case updated. | I: L4 | Active | L4 | 2025-06-05 | 2026-01-30
Business Only Initiative: EMR - Packaging - AMEA Pouch, Pak, Envelope RFP |  | 132147 | Business Only Initiative | SGA - Commercial | SG&A | Jason Ng, Anchit Mahajan | On Track | This project will overlap with another PV / DRIVE initiative - “EMR - Packaging - MEISA Supply Chain Change”. Hence, cancelling this one to avoid duplication. | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Packaging - Pouches Incumbent Renegotiation |  | 163585 | Business Only Initiative | SGA - Commercial | SG&A | Pankaj Kumar Singh | On Track | March’26 Savings updated. After aligning with the Finance team, we also captured the rebate of $143,742.15 in March,26 actuals that we realized in FY26. Feb'26 Savings updated. Jan'26 savings updated. After aligning with the Finance team, we also captured the rebate of $192,138.89 in January,26 actuals that we realized in FY26. Dec'25 - Partial savings captured due to transition completed in mid-Dec. 11/24/2025 - Money Step Evidence updated. 10/14/2025 - Exit Rate row, FY28 column field is populated as the NRB (Exit Rate) 2028 (Latest Estimate). Soft benefits removed. 10/14/2025 - Feedback incorporated in the intiative. KPIs added to the Financial Plan, Description added for the Money Step Milestone. 10/08/25 - CCH triage with CCH lead, determined no value proposition impact. Note: Planview prematurely submitted to EPM review after CCH lead submitted to next step. EPM requested feedback and need for QA expert review. Conducted QA expert review with commercial domain QA expert - Karen McConnico. Need to update the financila tabs and associated Epic alongwith financial KPIs. We have renegotiated the lower price for Pouch SKUs and will start capturing savings from Dec-25 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-09-08 | 2025-12-01
Business Only Initiative: EMR - Packaging - Veritiv Supply Chain Improvement |  | 163588 | Business Only Initiative | SGA - Commercial | SG&A | Anchit Mahajan | On Track | 04/13/26: March actuals updated. Captured FY26 rebates from Veritiv as well. 03/12/26: February actuals updated. Captured more than anticipated. 02/09/2026: January 2026 savings updated. January 2026 savings for this initiative is $125,107.44. Additionally, after aligning with the Finance team, we also captured the rebate of $907,384.82 in January 2026 actuals that was received from Veritiv in FY26 (Journal Attached). So total January actuals sum up to $1,032,492.26. 12/16/25: 1. Milestones added and completed. 2. No risks. 3. Attaching money step evidence. Initiative already accruing savings since May 2025. 4. Submitted for L4. 5. Will continue to track and record actuals and KPI in Financials tab on monthly basis. 11/21/25: P&L field is no longer available in PlanView. It still shows as astrisk. New P&L selection updated to "International / Air". Took out FedEx Corporate. 11/11/25 (Feedback Incorportated): 1. KPIs to not extend over the entire finanial period - DONE 2. If this project started savings in May 2025; actual data needs to be input from May 2025 to October 2025. And remove the forecast for this same period. - DONE 3. If this project has not started savings in May 2025, update forecast to the appropriate savings period. - N/A 10/30/25: 1. Money step description updated. 10/30/25: 1. Exit Rate row, FY28 column field is populated as the NRB (Exit Rate) 2028 (Latest Estimate). 2. KPIs added to the Financial Plan. 3. Milestons Updated. | K: L5 | Active | L5 | 2025-01-01 | 2025-12-31
Business Only Initiative: SG&A - Uniforms - Cintas SKU rationalization |  | 164299 | Business Only Initiative | SGA - Commercial | SG&A | Stefano Baratella | On Track | Jan 23rd: submitted for L4 after official confirmation by Supplier on refunds to be received and future savings (attached email) Nov 11th: updated the Financials as suggested (4 different OpCo’s + FXF zeroed after FY26) as shared with Jennifer Liu Oct 29th: adjusted the following points after "feedback requested": - Exit Rate forecast updated (entered 1 year amount in may 2028) - Added 1 line for KPI baseline (all values = 0) - Deleted soft benefits in Strategy View (entered by mistake) Oct 28th: submitted for L3 after getting guidelines by Aysha Maaghul on Financials (e.g. Freight share duration) Oct 10th: LBC shared with Analytics & Performance team, who agreed on next step | I: L4 | Active | L4 | 2024-09-25 | 2026-02-16
Business Only Initiative: Packaging - FedEx Tray & Freight Box Retirement |  | 164452 | Business Only Initiative | SGA - Commercial | SG&A | Mark West, Anchit Mahajan | On Track | 2/27 - P&L updated to Air/INTL for OpCo so that it is captured under the correct cost center. 12/3 - Updated initiative owners and provided feedback based on Jermone's feedback. Attached revised Financial Business Case. 1/29 - Adding the removal of FedEx Freight Boxes to this iniative. PLease note that no milestones have been adding as both of these projects are completed. Tray Removal is completed and we are realzing savings already as well as freight boxes that went active for savings on Feb 1st. Money Step is completed and we are actively tracking savings. | I: L4 | Active | L4 | 2026-01-01 | 2026-02-02
Business Only Initiative: Uniforms - Local Sourcing for Brazil & Mexico |  | 165104 | Business Only Initiative | SGA - Commercial | SG&A | Tricia Frese, Pooja Patel | On Track | Given changes to Mexico warehousing fees, NRB would be less than 30K. Recommend cancelling (for now) to focus efforts on higher value initiatives. | C: L1 | Cancelled | L1
Business Only Initiative: Uniforms - Uniform Designer Support Cancellation |  | 165107 | Business Only Initiative | SGA - Commercial | SG&A | Tricia Frese, Pooja Patel | On Track | Designer, Internal teams and vendor that depend on designer services (e.g., marketing, product, sourcing, procurement) are aware of the contract being discontinued for the fiscal year. 10/14 - attached the LBC requested. 11/28 - re-submitted business case with revised initiative and new ownership, Tricia Frese. 12/8 - corrected to full contract amount 225k and resubmitted. 1/6 - Per Finance updating L0 business impact withour PDSM ticket. Should say "Pausing contract starting in Jan 2026 and through FY28 with annual savings of $225K. FY26 saving impact is $163K." Re-submitting for L3. 1/16 - Contract ended; money step marked complete. Savings are being booked. Submitted for L4. 1/16 - Requesting cancellation as worked with Finance (Lorri Hughes) to sweep from MAP rather than set up as a recurring initiative in Planview. Do not want to double dip. | H: SL4 | Cancelled | SL4 Finance Domain Lead Approval | 2026-01-15 | 2026-01-15
Business Only Initiative: Packaging - Veritiv EU Model Savings |  | 170265 | Business Only Initiative | SGA - Commercial | SG&A | Anchit Mahajan | On Track | Cancelled based on additional feedback from Finance Leadership. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Lower Cost to Serve by Offshoring HKCE to China |  | 177360 | Business Only Initiative | SGA - Commercial | SG&A | Ka-Wai Catherine Chan | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: CC3 – CN IVA LLM Integration |  | 185501 | Business w/ Tech Initiative | SGA - Commercial | SG&A | Yen Shen | On Track | On Track 3/18/2026 (dfw) asked IO to update LBC | C: L1 | Active | L1
Business Only Initiative: Salesforce Enterprise License Agreement (SELA) |  | 186461 | Business Only Initiative | SGA - Commercial | SG&A | Rebecca Jones | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: APAC - Centralize AU Clerical & DCC tasks to MY |  | 187828 | Business Only Initiative | SGA - Commercial | SG&A | Sri Ganesh Muthusamy, Man Mango Li | On Track | All tasks are progressing as planned, no major issues identifled. 2026 April 22 - Planview input reviewed by Domain QA Expert Lance Tam, ready to be submitted to SL2 | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: Facility - Santa Fe Mexico Headquarters Relocation | 32680 | 7791 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Sebastian Forero | On Track | 07/25/2025: Finanacials cannot be updated due to locked screen. 04/01/25: No additional lease payments made after Aug 24 - No change to financials for cost savings. 03/13/25 - Capturing 12 months of savings. 03/04/25 - Multiple months of savings captured. Initative has been submitted for L5 approval. 01/21/25 - Follow-up request submitted for final invoices. 12/19/24: Final invoices requested before advancing to next stage. 10/10/2024 - Additional IT and security cost are pending for this initiative. 09/05/2024 - The PM for the MX HQ relocation has been assigned as a backup initiative owner. A review of the initiative will be perform to determine responsibility of future updates. 08/01/2024 - Based on monthly update provided, construction is still in progress. An updated schedule has been requested from the PM. | K: L5 | Completed | L5 | 2023-08-21 | 2024-08-30
Business Only Initiative: LAC FY25 CAPEX Savings | 94756 | 8227 | Business Only Initiative | SGA - Facilities | SG&A | Sebastian Forero, Adriana Peceno | On Track | 5/30/2025 - Financials reviewed with TO FIN and forecast aligned with current benefits 3/30/2025- There are no discrepancies between actual results and forecasts as the 3 projects were already delivered and unused CLEAR amounts/savigns were confirmed. | K: L5 | Completed | L5 | 2024-06-03 | 2024-07-31
Business Only Initiative: LAC Properties: FY25 MEX Lease Savings | 94758 | 8238 | Business Only Initiative | SGA - Facilities | SG&A | Sebastian Forero, Adriana Peceno | On Track | 5/30/2025 - 5/30/2025 - Financials reviewed with TO FIN and forecast aligned with current benefits 30/3/2025 - There are no discrepancies between actual results and forecasts. All 5 real estate projects have been delivered from 12/31/2023 - 6/30/2024 therefore savings are being accounted on a montlhy basis for the remaining lease term of each lease. | K: L5 | Completed | L5 | 2024-01-01 | 2024-01-01
Business Only Initiative: Facility - 1330 Greengate, Covington LA District O | 1086 | 8806 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/13/25: No new developments. 11/22: Savings forthcoming. | K: L5 | Completed | L5 | 2022-10-14 | 2023-04-28
Business Only Initiative: Facility - Marsh (1000 Ridgeway 4th, 5th, 6th Floo | 1513 | 8849 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 02/11/2026: Additional items ordered for the project which will take approximatelty 6 weeks for completion. 01/28/26: Milestone date adjusted to include 3 months of captured savings. 12/05/25: Office has been returned to landlord however additional work is required for the new work area which includes addition of more lighting. New target completion date is February 16, 2025. 06/18/25: Project cost updates provided by PM. 05/05/23. PM working on CLEAR submittal and to provide project cost for entry into Planview 04/04/25: This project has been broken into 4 phases. Phase 1 included a move to WHQ of Advanced Technology and Innovation. Phase 2: Legal relocation to WHQ.. Phase 3 Financia compliance will relocate to WTC. Phase 4 return of Marsh to landlord. Project cost and timeline will be finalized in July 2025 with a target return of office to landlord completion date of September 2025. 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: No additional updates. 03/04/25: A&E is almost completed and I will be able to bid out the construction portion. PM working on collecting data and security costs. AV and furniture labor costs have been submitted 02/25/25: PM is actively developing and finalizing project cost 02/03/2025 - Lesae extended to 12/31/2025. New facility exit date. 10/22/2024 - PM has been assigned for the relocation project and is developing an updated cost and schedule. 09/09/2024 - Cost estimate and floor plan has been provided to the sponsor for review and comments. Timeline has been updated to reflect the additional time required for sponsor approval. 08/01/2024 - Waiting on final decision from stakeholders (FedEx team) regarding office space planning. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-20 | 2026-05-29
Business Only Initiative: Facility - 920 West Poplar Ave (Collierville Learn | 1514 | 8850 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 07/30/25: Project complee. Verifying final invoices. 06/12/25: The project has some half cubicle panels that need to be installed and an issue with the access card mag locks that came up during the last fire drill. I expect both of those items to be completed in June, expect the invoices to be processed in July. 05/09/25: PM continues to work through the final items. No risk identified at this time. 04/01/25: No additional lease payments made after Jan 2024 - No change to financials for cost savings. 3/20/25: Currently working through the remaining items such as (Door hardware & gap fill on main door, Signage for both PH I & II, VSAT extension for GOC on 1st floor, CRS 36" panel installation Asset disposal from 90-249. 03/13/25: No new developments. 03/04/25: No additional updates. 02/17/25: Furniture and network installation complete. MOC, AOG, and CRS have been relocated to 2nd floor. Punchlist in progress. GOC expanding into MOC space on 1st floor. VSAT network lines to be extended to MOC for GOC. Signage layout for PH I and II in progress. 01/23/25: The internal reorganizations and recent layoffs have affected the project schedule, a bit. Anticipating IT and Sec can complete their scope by the end of the month, the MOC team will relocate to the 2nd floor the week of 2/3. 01/21/25 Awaiting turret installation schedule from IT. Turret system must be extended prior to relocation. Tech Security group experienced a lot of changes which has impacted project schedule. Cameras and card reader installation was to commence this week, awaiting feedback on schedule. Card readers must be installed and activated prior to relocatin on 02/02/2025. Initiative milestones to be adjusted to new schedule. 12/11/24: Construction is substantially complete. Awaiting arrival of security equipment and furniture. Network connectivity to be completed upon arrival. Noise mitigation system being installed this week. 11/15/24: Construction completion delay. The project will not be finished until December and the group will not relocate to the 2nd floor until January 2024 after peak. 10/24/24 Construction completes in Feburary however invoice payments are not expected to be completed until May. Schedule adjustment to account for invoice payments and new L4 date. 10/23/24: Construction near completion We are waiting on permit approval to start the construction for phase II which is expanding the team to the 2nd floor. I am currently anticipating relocation completion just prior to peak, 11.15.24. | K: L5 | Completed | L5 | 2022-12-06 | 2025-07-30
Business Only Initiative: Facility - 2601 Main Street, Irvine CA | 1516 | 8853 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/13/25: No new developments. 03/04/25: Over 12 months of savings captured. 11/22: Savings monitored over a 12 month period and calculated at $23,314 monthly lease savings. | K: L5 | Completed | L5 | 2022-11-22 | 2023-04-28
Business Only Initiative: Facility - 500 Corporate Center Drive, Coraopolis, | 1517 | 8855 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 07/25/2025: Financials cannot be updated due to locked screen. 04/04/25: More than 3 months savings captured. 04/01/25: No additional lease payments made after Nov 2024 - No change to financials for cost savings. 03/20/25: No additional updates. 03/13/25: Initative should be ready for L4 in April. 03/04/25: Initative should be ready for L4 in April. 121824: Space has been returned to Landlord Real estate report inability to negotiate an early lease termination with the landlord. FedEx is responsible for this location until lease expiration date of 11/30/2024. Any monitoring equipment must remain on site until the facility is returned to the landlord. | K: L5 | Completed | L5 | 2023-11-13 | 2024-12-31
Business Only Initiative: Facility - 680 American Avenue, King Of Prussia, P | 1518 | 8856 | Business Only Initiative | SGA - Facilities | SG&A | Brandon Tolbert, Glenda Webster |  | Currently unable to locate space to relocation dispatchers. Initiative will be placed on hold until future evaluation. | E: L2 | On Hold | L2 | 2024-07-22 | 2024-11-18
Business Only Initiative: Facility - 9311 San Pedro, San Antonio, TX | 1519 | 8857 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/05/25: Requested to place initiative on hold due to FedEx's responsibility to monitor the site until lease expiration date of 04/26. Landlord will not offer an early lease buyout. FedEx monitoring equipment will remain on-site until the office space is returned to the landlord. 03/04/25: The Landlord will not allow us out of the lease. FedEx will continue to lease the empty building until 04/30/2026. FedEx security and IT equipment will remain on site until the end of the lease. 12/11/24: Training has relocated to the Ground location. All remaining fec items out of the space by the end of November 2024. However telecom and security will remain inplace because according to Real Estate, the Landlord will not allow us out of the lease. FedEx will continue to lease the empty building until 04/30/2026. 111424: - - Given current market conditions, Landlord is refusing to engage in negotiations for a lease buyout until they have interest shown by other parties regarding the space. The building has about 50K SF of office space available currently (about 21% of the total building size). FedEx is expected to vacate the office by 11/30/24. 090424: PM stated Surface performed the work required to prepare the office however no furniture was included causing a delay. An additional delay is experienced due to ongoing training classes scheduled for completion mid October, The new target date for relocation is October 15. Once training has relocated, the original office will be renovated per lease agreement and returned to the landlord. 082724: Real Estate will be reaching out to the landlord to investigate the potential of an early lease buyout. Relocation is scheduled for completion in September and the office will be renovated per lease agreement in October. Although we are vacating the office space in October if a lease termination is not in place, we will be responsible for continued maintenance and monitoring of this office space until April 26, 2026. Real Estate to provide feedback on the opportunity for early lease termination. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-07-10 | 2026-07-31
Business Only Initiative: Facility - 1000 Omega Drive, Pittsburgh, PA | 1533 | 8860 | Business Only Initiative | SGA - Facilities | SG&A | Brandon Tolbert, Glenda Webster |  | Requested to place a temporary hold on project | E: L2 | On Hold | L2 | 2024-07-22 | 2024-12-20
Business Only Initiative: Facility - 785 Greens Pkw, Houston, TX | 1537 | 8862 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 04/04/25: More than 3 months of savings captured 04/01/25: No additional lease payments made after Nov 2024 - No change to financials for cost savings. 03/20/25: No additional updates. 03/13/25: Inititative submittal to L5 in April 2025. 03/04/25: Inititative submittal to L5 in April 2025. 12/19/24: The total was $44,055.04 to pay the landlord directly for renovations. The other costs were furniture removal and shipment back to Memphis (done through ReFormer with Office Interiors) $36,315, and Security and IT removal which were handled by those groups. 12/18/24: Final piece of equipment from the office was shipped on Monday (12/16/24) 12/11/24: PM is working with LL to contract GC for exterior building sign removal. Fee in lieu of restoration of suite has been paid and accepted by Landlord. 11/14/24: PM negotiated a return of office space without renovations as outlined in lease agreement. The owner will be paid by FedEx the estimated cost for renovations and perform the work. 09/20/2024: Initiative reopened due to decision to close office. Employees will work remote. 08/12/2024: Initiative cancelled. Office relocation due to the relocation of this office will lead to an increase in expenses and not a cost reduction. The relocation is centered around employee safety concerns and recruiting limitations based on the undesirable character of the current office. 08/08/2024: Initiative has been removed from on-hold status. Current plan involves relocating employees to a smaller office. Estimated completion date is January 2025 As we considered our plans for FY24 and FY25, CE has a number of major system changes and new initiatives that will require extensive in-office training. These include a completely new desktop that will be delivered in phases, training for One FedEx, new digital tools and other items that will run consecutively through all of FY24 and into much of FY25. We also are hiring about 300-350 new team members (nationwide) to offset current attrition as well as our inability to hire over much of the last three years. IAH is a key market for future new hires due to the large population. IAH already has a staff of approximately 65 existing team members and support staff. To minimize any incremental space needs, the plan for CE is to occupy our non Memphis call centers at 2x with teams working alternating weeks while completing the above activities. IAH has working space for about 50 individuals so we should be okay even with new hires. I know this landlord has been amenable in the past to rolling annual renewals and the same would fit our needs here. I know a one year renewal might not bring us a lot of leverage with the landlord but it would be nice if Real Estate could negotiate some minimal LHI – new paint or carpet as part of the transaction. Let me know if you have any remaining questions. LL Lex Lannom Vice President - Customer Experience Operations FedEx Services | K: L5 | Completed | L5 | 2024-09-20 | 2024-12-31
Business Only Initiative: Facility - 701 Waterford Way (LAC HQ), Miami, FL | 1538 | 8864 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/13/25: No new developments. 03/04/25:Multiple months of savings has been captured since office closure. | K: L5 | Completed | L5 | 2023-01-06 | 2023-10-31
Business Only Initiative: Facility - 920 West Poplar Ave, Collierville, TN ( | 1539 | 8866 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/20/25: No new developments 03/13/25: No new developments. 03/04/25: Initative is ready for next submittal level in April 2025. | K: L5 | Completed | L5 | 2022-12-13 | 2024-01-31
Business Only Initiative: Facility - 900 7th St NW, Washington, DC | 1541 | 8868 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 12/22/25: Move to L4 after capturing 3 Months of Mature Benefits. Expected L4 date is April 2026. 12/10/25: Landlord accepted the property as broom cleaned. The property was returned to the landlord on 11/28. All invoices have been paid excluding moving expense. Invoice payments are not reflected in eBuilder due to potential direct charges to the Sponsor's cost center. PM has requested copies of the invoices from the vendors to attach to Planview as proof of closure. 10/16/25: Sent photos and SOW to Rand Construction for picing on 10/7. For task items to complete to leave office space "broom clean". Pending quote. 09/21/25: Furniture demo completed 8/21. IT/Security demo completed on 9/5, including ITAD of all phones and computers. Building Engineer is to complete site inspection on 9/9 and will provide notes on final items to complete before FedEx returns the space to the landlord. Lease expires on Nov 2025. LL has refused to terminate lease early. 09/02/25: Furniture demo to commence on 8/19. Should wrap up by 8/21. Cubicle furniture to be disposed of locally. Too much already in stock in Memphis. Only Reg Affairs furniture is to be shipped back to Memphis for surplus. 07/29/25: The week of Aug 18th. network hardware demo will be completed along with packing up and moving the office supplies that are still there. There will be additional work to close the office in September. By Aug 22nd, the office should be close to ready to return to landlord. With possibly some additional efforts to clear out the space to take place in September. 06/12/15: Gov Affairs group has reserved storage space to receive furniture removed from old Reg Affairs Office, which is currently stored at 900 7th St. Will coordinate a date with Sales Team and Gov Affairs to schedule move of Reg Affairs furniture. Before arranging for Office Interiors to pick up all remaining furniture to have sent to surplus in Memphis. 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: PM to complete a walkthrough to develop a checklist of items to complete as part of closeout. Team will be in DC in mid-April. Walkthrough to be completed at that time. 03/13/25: No new developments. 03/04/25: PM to schedule furniture removal after April 2025, once Admin has a chance to complete site visit to confirm all personal belongings, computers, and printers have been removed from site. 02/12/25: PM to start decommissioning of office space for return to landlord by 11/2025. 01/22/25 - Due to lease expiriation occurring in Nov. 2025, sublease of office space is no longer being pursued. PM is preparing to decommission office space for return to landlord. 12/18/24 - No change to previous update 09/04/24 - no prospective subtenants have inquired about the site in quite some time. 08/01/24 - FedEx Real Estate is attempting to locate a subtenant to lease the space. Owner will not entertain an early lease termination. Lease termination date is 11/30/2025. | I: L4 | Active | L4 | 2023-04-04 | 2026-04-01
Business Only Initiative: Facility - 1901 Summit Tower, Orlando, FL | 1542 | 8869 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: No new developments 03/13/25: No new developments. 03/04/25: Currently capturing 12 months of savings before moving to the next stage. | K: L5 | Completed | L5 | 2023-05-01 | 2024-05-31
Business Only Initiative: Facility - 200 N. Sepulveda, El Segundo, CA | 1543 | 8871 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Ken D. White, Brad Courtney | On Track | 09/02/25: PPM # is 1292215 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: On track to vacate by 8/31/2025. Contractor quote for the closure recieved. PM developing contract. 03/13/25: No new developments. 03/04/25: Quote recieved for decommissioning office space for return to landlord by 8/2025. 02/12/25: PM to start decommissioning office space for return to landlord by 8/2025. 121824: No change to previous update 10/04/2024: FedEx responsible for site until 08/31/2025 The landlord will not entertain an early lease buyout. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-01-31 | 2025-08-29
Business Only Initiative: Facility - 1750 112th Ave NE, Bellevue, WA (Suite | 1544 | 8872 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/13/25: No new developments. 03/04/25: Savigns captured for 12 months. Initative ready for the next stage. Office space has been cleaned and cleared of all furniture except for the IT and Security assets. The lease will be paid until expiration date of August31, 2023 therefore IT and Security equipment will remain on premises until the lease expiration and the office space is returned to landlord. If the landlord locates a new tenant prior to lease expiration, a lease buyout will be negotiated. | K: L5 | Completed | L5 | 2023-01-31 | 2023-08-31
Business Only Initiative: Facility - 1 Mid Rivers Mall Drive, St Peters, MO | 10697 | 9106 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 4/05/25: Information updated to reflect FY25 lease & cam cost 03/20/25: Project is currently slated to begin in May. 03/20/25: No additional updates. 03/13/25: Currently capturing 12 months of savings before submittal to the next level. 03/04/25: Currently capturing 12 months of savings before submittal to the next level. 01/22/2025: Office closed. 3 months of savings captured. 09/11/2024: Site walk completed last week and the landlord has accepted the site. An original contact was established with a contactor in the amount of approximately 25K, however it was decided that no onsite work was required. 09/09/2024 Team to reviewed the site on 09/03/2024. Closure date revised by project team to occur on 09/29/2024 | K: L5 | Completed | L5 | 2023-03-07 | 2024-09-30
Business Only Initiative: Facility - 4660 Distriplex Cove, Memphis, TN | 16685 | 9201 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/13/25: No new developments. 03/04/25: Savings captured for more than 12 months. Initative is ready for the nexr level. 11/22: Savings monitored over a 12 month period and calculated at $10,785 monthly lease savings. | K: L5 | Completed | L5 | 2022-11-15 | 2023-01-30
Business Only Initiative: Facility - 1035 S Hwy 89, Jackson Hole, WY (JACA) | 16705 | 9291 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 03/13/25: No new developments. 03/04/25: More than 12 months of savings captured. Initative ready for the next stage. | K: L5 | Completed | L5 | 2023-02-07 | 2023-10-27
Business Only Initiative: Facility - 185 Plains Rd Ctr, Milford, CT (BDRWK) | 16730 | 9292 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 07/25/2025: Finanacials cannot be updated due to locked screen. 04/04/25: 3 months savings captured. Savings updated. 04/01/25: No additional lease payments made after Nov 2024 - No change to financials for cost savings. 03/20/25: No additional updates. 03/13/25: Initative ready for L5 in April 2025 03/04/25: Initative ready for L5 in April 2025 121824: PM Has confirmed project completion 111424: Facility is ready for return to owner upon lease expiration date of 113024. | K: L5 | Completed | L5 | 2023-04-20 | 2024-11-29
Business Only Initiative: Facility - 12657 Alcosta Blvd, San Ramon, CA (CCRS | 21865 | 9293 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 04/05/25: Updates made to cost savings 04/01/25: No additional lease payments made after Jun 2024 - No change to financials for cost savings. 032025: No additional updates. 031325: Currently capturing 12 months of savings before submitting to the next stage. 030425: Currently capturing 12 months of savings before submitting to the next stage. 111424: Lease expired on 06-30-24. Three months of matured savings has been captured. 09112024: Contract was established for $18,965 however the contractor only allocated cost totaling $7,290.00 target invoice payment date to occur in September. | K: L5 | Completed | L5 | 2023-03-07 | 2024-06-28
Business Only Initiative: Facility - Canadian Headquarters (YYZHQ) - Mississ | 57201 | 9294 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 12/11/25: Additional work requires permitting to complete. A schedule adjustment for construction completion targets the end of May 2026. 08/06/25: PM completing small construction related items before project closeout. 07/15/2025: Money Step milestone is currently marked as not started however the work is near completion. A schedule adjustment is needed to set the money step completion date for August 1. The schedule is locked and cannot be adjusted. 06/12/25: Project has been completed excluding a few minor construction related items which should be completed by the end of June. Original office has been returned to the landlord. 05/09/25: Office on track for target closure date. 04/04/25: Lease cost information still required from accounting to update finanacials. 04/01/25: Access to this lease cost is unavailable; information. Information requested from accounting 03/20/25: No additional updates. 03/13/25: No new developments. 03/04/25: Office closure on tract with no current delays. 02/18/25: L4 st age is expected to be requested by 7/1/2025. 02/12/25: Schedule remains unchanged. Project on track for return of office space to landlord on 5/31/2025. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-01-09 | 2026-05-29
Business Only Initiative: Facility - Regional Office - Richmond, BC (YVRRC) | 57203 | 9297 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 04/01/25: No additional lease payments made after Aug 2024 - No change to financials for cost savings. 03/20/25: No additional updates. 03/13/25: Currently capturing 12 months of savings before submittal to the next level. 03/04/2025: Currently tracking 12 months of savings resulting from office closure 01/22/2025: 3 months of savings has been captured | K: L5 | Completed | L5 | 2024-01-02 | 2024-08-30
Business Only Initiative: Facility - 800 17th St. NW, Washington, DC | 81230 | 9298 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 04/01/25: Office was subleased with no lease payments made after June 2024 03/20/25: No additional updates. 03/13/25: No new developments. 030425: Currently capturing 12 months of savings before submitting to the next stage. | K: L5 | Completed | L5 | 2023-03-24 | 2024-06-28
Business Only Initiative: Facility - 225 Washington Street, 3rd Conshohocken | 88831 | 9300 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brandon Tolbert | On Track | 07/25/2025: Finanacials cannot be updated due to locked screen. 04/04/25: Three months savings captured. 04/01/25: No additional lease payments made after Nov 2024 - No change to financials for cost savings. 03/20/25: No additional updates. 03/13/25: Initative ready for L5 in April 2025. 03/04/25: Initative ready for L5 in April 2025. 12/18/24: PM has confirmed project completion. 11-25-24: Fanatic has not responded to the project manager regarding scheduling a walkthrough and inspecting the space. Space is ready for return to the landlord.. 11-14-24: IT demolition is scheduled for 10/29/2025. The office can return to Fanatic after they conduct a walkthrough and inspect the space. 10-03-24: Per PM, 35,000 is the most accurate cost forecast at this time. 09-04-24: PM is awaiting quote from moving service to confirm project budget requirements. L3 target date adjusted. | K: L5 | Completed | L5 | 2024-06-10
Business Only Initiative: Facility - 730 Columbia Rd, Plainfield, IN (INDH C | 97663 | 9301 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 01/28/26: Initiative placed on hold until a potential sublease is secured. 01/13/26: The initiative pending a decision regarding subleasing. If the property is subleased, a copy of the lease agreement should be attached to the initiative before advancing to the next stage. 12/1025: No update. 10/31/25: FedEx Real esate reported they are listing the space for sublease. FedEx lease expiration date is 02/28/33. 09/21/25: Need information from real estate on the requirements to return the space to landlord. Once requirements are defined, a cost estimate can be generated. 04/04/25: Real estate has requested the space to be marketed for sublease and continues to work with the landlord to deremine if we can exit the lease early. Scope of work and cost for returning the space to the landlord is needed to complete the finanacials. 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: After INDH CSS Offsite has moved to Golden Eagle. The closeout of the office space is required. The Landlord of the site is working on a direct proposal with a neighboring tenant who is interested in leasing the space vacated by FedEx. 03/13/25: No new development. Real Estate continues working with landlord. 03/04/25: No additional update. Real Estate is currently working with the landlord to determine requirements for return of office space and any expected associated cost. 02/24/25: After INDH CSS Offsite has moved to Golden Eagle. The closeout of the office space is required. The Landlord of the site is working on a direct proposal with a neighboring tenant who is interested in leasing the space vacated by FedEx. If they come to an agreement any termination offer received will be vastly superior to one if there isn’t a backfill tenant coming in (ie they can’t come to terms). Real Estate is working on a termination but until they know whether or not the neighbor has a deal in place it doesn’t allow them to really get into the details of a termination. 01/15/25: INDH CSS Offsite cage to be operational at Golden Eagle on March 1, 2025. | E: L2 | On Hold | L2 Feedback Requested | 2024-10-03 | 2026-08-31
Business Only Initiative: Facility - Providence Relocation | 87233 | 9311 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Jared Herring, Brad Courtney | On Track | 01/12/26: The facility is required to be operational by 9/28/26. Schedules have been established to show a path to this date and coordination meetings are being held. Sort must start 5/11/26 for date to be hit. 10/16/25:Sort IFC drawing package complete. Sort Electrical IFC package in progress FedEx procured sort components POs have been issued. Modifications to the storm water retention require a lease modification that is in progress. Moltus submittal process continues. Foundations being dug and rebar set. Design Document Revision CCD #01 review meeting held. Agreement on foundations reached for construction to continue. MEP engineer to provide confirmation that change to radiant heat system meets all necessary FedEx Specifications, i.e., air turnovers. 09/23/25: Sort IFC drawing package in progress. Sort Electrical DPR drawings have been reviewed and approved by FedEx. FedEx procured sort components have been reviewed by Engineering and our ready for POs. FedEx access to the facility to begin sort install is currently slated for beginning of March. Modifications to the storm water retention require a lease modification that is in progress. Foundations scheduled to start week of 9/22. The foundation revisions in CCD #01 has delayed the their start by roughly a month. 06/12/25: Project has been permitted. Construction start date has pushed at least a month while Over-Under works through adjustments to their lending agreement. Sort Design continues. PDR mechanical design set has been received and reviewed by FedEx. Wit-Con is proceeding with CDR set development. Electrical plans to be submitted with CDR set. 04/04/25: Project is currently slated to begin in May. Permitting is in progress and expected in April. RIAC is currently working with the state to resolve a surveying issue. Sort Design has started. PEMB drawings needed for completion of sort drawings. Project will not be under an EAA. RIAC access control will need to be added to the building along the SIDA line. CHA will need to design the system to get RIAC network into the building. 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: Project is currently slated to begin in May. Permitting is in progress and expected in April. RIAC is currently working with the state to resolve a surveying issue. Sort Design has started. PEMB drawings needed for completion of sort drawings. Project will not be under an EAA. RIAC access control will need to be added to the building along the SIDA line. CHA will need to design the system to get RIAC network into the building. 3/13/25: No new developments. 03/04/25: Construction Schedule received from Moltus and is under review. Due to permitting, project is currently slated to begin in May. Sort Design has started. PEMB drawings needed for completion of sort drawings. No Comments received for FedEx Drawing review. Drawing set has been submitted for permit. Expected to take a minimum of (2) months. Airport is requires EAA from FedEx Security prior to Over-Under being able to commence work. EAA determination from security needed. Building is currently designed to EAA requirements. Redesign will be needed to add Airport security to SIDA line. 2/12/2025: Providence Relocation drawings are under review. Project schedule has not been finalized by the PM. Delays expected as a result of the permitting timeline which can impact the project start date. Current estimated completion date is 7/30/2026. | G: L3 | Active | TEMP L3 - Enter L3 | 2022-12-19 | 2026-09-30
Business Only Initiative: Facility - Office Chairs |  | 86924 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster | On Track | 110725: No reported chair purchases have been recorded over the past few months. As the potential savings are minimal, it is recommended that this initiative be cancelled. 04/01/25: Information currently matches FY25 financials 03/20/25: No additional updates. 03/13/25: No new development. 03/04/25: Researching methods on how to track/capture expenditures related to office chair purchases from the new vendor. To date no new chairs have been purchased for the new vendor. 01/14/25: 1. The net recurring benefits entry is not available in L2. The screen is locked an a value cannot be entered. 2. Some expected chair purchases are to occur in 2025 exact dates are unknown at this time. 12/20/24: 1. The net recurring benefits entry is not available in L2. 2. The purchase of the new chairs will occur throughout each fiscal year at the newly established purchase cost. | H: SL4 | Cancelled | SL4 Finance Domain Lead Approval | 2025-04-01 | 2025-05-30
Business Only Initiative: [Enabler] Office Space Utilization Dashboard |  | 87910 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster | On Track | 01/15/25 Initiative awaiting the abilty and availability of the data needed to continue. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: EE2.0-Lease term./exits (Denv, Mil Lease Jan-May) |  | 88496 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | Some Issues | 12/19/24: Note: The Denver initiative may not move forward. Real Estate is in discussions on an early termination, but that is only if they sign a lease with a new tenant. This initiative is on hold based on details provided above. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Standardize scope and supply base for Landscaping |  | 92678 | Business Only Initiative | SGA - Facilities | SG&A | Matthew Drummond, Brad Courtney | On Track | Savings and baseline figures are ready to be inputed. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-04-01 | 2028-04-28
Business Only Initiative: Facility - 3860 FHI Suites 102-105, 107, 110) |  | 97412 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 04/07/26: that 3860 Forest Hill Irene has been turned over to the landlord last Thursday, April 2, 2026. Savings should start 30-days after completion. 3-months of savings must be collected before move to L4. 02/17/26: PM change. Schedule adjustment made to account for 3 months of savings. 12/10/25: A final walk-through is supposed to happen in near future, but no date has been set with the Landlord representative. As soon as a walk-through is completed, we shall address any work that needs to be done per LL's expectation. 11/02/25: PDSM ticket submitted to update base line value from $1,238,730 to the new current value of $1,270,732. INC032914475 09/23/25: Decision made to vacate the property at lease expiration which occurs March 2026 04/07/25: A proposal for renewal/expansion of existing space has been provided by the landlord. PPD discussing the required capital with management to determine if they want to move forward. 04/04/25: Waiting for numbers from the landlord on an extension for the potential GOCC lease. 04/01/25: Information updated to reflect FY25 lease & cam cost 03/20/25: GL Accounting data requested for NRB calulations. Obtaining requested data is still pending. GOCC negotations with landlord. 03/13/25: No new developments. 03/04/25: No new developments. The plan is still for GOCC to move into FHI. They are currently negotiating with the Landlord. 02/24/25: GOCC is considering taking over the lease for this locaiton. Closure of this office is pending GOCC decision | G: L3 | Active | L3 | 2025-10-17 | 2026-07-03
Business Only Initiative: EMR CFT - Facilities Managed Services Increase SUM |  | 126294 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney, Patrick Snyder | On Track | This initiative was created in support of Enterprise Margin Recovery and was considered a placeholder. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR CFT - Facilities Network & Engin, Increase SUM |  | 128544 | Business Only Initiative | SGA - Facilities | SG&A | Larry Schamus | On Track | This initiative was created in support of Enterprise Margin Recovery and was considered a placeholder. | C: L1 | Cancelled | L1
Business Only Initiative: Document Shredding Enterprise Request For Price |  | 109440 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar, Karl Kehr | On Track | This initiative is already in it final implementation stage with no road blocks. The savings have started to trickle in from January 2025. All teh contracting and transition is completed. It is now also rebaselined according to FY25. | I: L4 | Active | L4 Feedback Requested | 2024-07-15 | 2025-12-01
Business Only Initiative: Standardize specifications and supply base for lan | 31702 | 6804 | Business Only Initiative | SGA - Facilities | SG&A | Tahza Eggleton, Matthew Drummond | On Track | This initiative was technically replaced by the Landscaping initiative we launched earlier this year (Seq ID 92678). So, any savings counted after April 1st, 2025, would be double counting savings (all sites from 6804 were put out to bid and re-awarded to new suppliers in initiative 92678). | I: L4 | Cancelled | L4 | 2023-07-31 | 2024-06-21
Business Only Initiative: CBRE Transformational Credit | 79846 | 6971 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney, David Knox | On Track |  | K: L5 | Completed | L5 | 2024-03-26 | 2024-04-26
Business Only Initiative: Standardize snow scope of work and supply base | 86679 | 7652 | Business Only Initiative | SGA - Facilities | SG&A | Matthew Drummond, Tahza Eggleton | On Track | Rebaseline to FY25 - completed 7/10/2025 | K: L5 | Active | L5 | 2024-01-09 | 2024-11-01
Business Only Initiative: Value Engineering for Legacy Ground N2.0 Retrofits | 93386 | 7747 | Business Only Initiative | SGA - Facilities | SG&A | Steve Muchko, Philip Simonetti | On Track | Direction from Surface Finance and leadership is to not move forward with entering CAPEX related savings in Planview. Depreciation savings schedule was never established for this initiative and the guideance is to cancel. | I: L4 | Cancelled | L4 | 2023-01-02 | 2025-01-10
Business Only Initiative: Facilities - FR utilities renewals | 80330 | 7900 | Business Only Initiative | SGA - Facilities | SG&A | Blazej Radwanski, Stefano Baratella | On Track | Submitted for L5: the actuals are entered. The actuals are constant for last months. Additional information: contracts are uploaded. Indeed it might be cost avoidance, the rates reduction are driven by market rates. The baseline is our FY24 consumption multiplied by FY24 rates. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-12-01 | 2024-09-30
Business Only Initiative: Top Down HQ/Hub Landscaping | 86651 | 8030 | Business Only Initiative | SGA - Facilities | SG&A | Matthew Drummond, Tahza Eggleton | On Track | On track | K: L5 | Active | L5 | 2024-06-03 | 2024-08-01
Business Only Initiative: Fire systems RFP | 83317 | 8031 | Business Only Initiative | SGA - Facilities | SG&A | Damodar Naik, Christopher M. Winans, Grace Ige, Vaibhav Srivastava, Tahza Eggleton, Brad Courtney | On Track | 11/12 - Money step date pushed to 11/28. FXF contract has been executed for 1 month and the FXO contract was just signed by both parties earlier this week. We are actively working to get the vendor implemented and sitatued in the system so that work can transition to new vendor starting 12/1. 9/30/35 - Money Step date has been pushed back to accomodate the signing and execution of the MSA with FXO. This initiative ID will only be for FXF and FXO, the surface/air baseline and projected savings will move to its own initiative ID. FXF contract has been signed/implemented on 9/1/25 , once FXO contract is signed/implemented money step will be reached. 8/1/25 - Pushing back L4 Start and Money step date back a month to September. Currently working through stakeholder challenges/concerns that have arose while getting final drafts of MSA aggreed and executed for both FEC and FXF. Some schedule adjustments may have to be made based on supplier negotiations. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-09-06 | 2026-05-01
Business Only Initiative: CBRE National Facility & Sort System Maintenance A | 84311 | 8080 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track | On track | K: L5 | Completed | L5 | 2024-06-17 | 2024-08-20
Business Only Initiative: Fiber-Filled Asphalt | 83869 | 8125 | Business Only Initiative | SGA - Facilities | SG&A | Jared Herring, Vaibhav Srivastava | On Track | Aligned with business on spend details from previous fiscal and FY25 projections | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-07 | 2024-10-25
Business Only Initiative: SLC and DEN FXF Paving eAuctions | 91828 | 8126 | Business Only Initiative | SGA - Facilities | SG&A | Karl Kehr, Daniel Vargo, Jared Herring, Vaibhav Srivastava | On Track |  | K: L5 | Completed | L5 | 2024-06-03 | 2024-12-20
Business Only Initiative: Optimize EV charging non-peak times (for last mile | 83322 | 8146 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Vivek Cheekoti | On Track | After considerable effort and collaboration with Finance, we are recommending the cancellation of the referenced initiative in Planview. While we explored multiple avenues to make this viable, we’ve identified several limiting factors that prevent us from moving forward effectively: •Limited Financial Impact: Based on feedback from the Finance team, the initiative is not expected to yield meaningful, reportable savings to contribute toward Drive goals. •Operational Dependency: The initiative relies heavily on the availability and functionality of EV charging stations. Given current delivery demands, aligning optimal charging times without impacting service performance remains a significant challenge. •Data Constraints: A high degree of variability in capturing reliable actuals further limits our ability to track progress or validate outcomes. Given these challenges, and despite our due diligence and efforts, we believe discontinuing the initiative is the most practical course of action currently. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-07-29 | 2025-06-30
Business Only Initiative: Tiger Natural Gas | 83920 | 8147 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Vivek Cheekoti | On Track | Reforcasted and rebaselined for Fy'25 on 6.18.25 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-01 | 2025-06-26
Business Only Initiative: Optimize EV charging non-peak times (for last mile | 90029 | 8148 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Vivek Cheekoti | On Track | After considerable effort and collaboration with Finance, we are recommending the cancellation of the referenced initiative in Planview. While we explored multiple avenues to make this viable, we’ve identified several limiting factors that prevent us from moving forward effectively: •Limited Financial Impact: Based on feedback from the Finance team, the initiative is not expected to yield meaningful, reportable savings to contribute toward Drive goals. •Operational Dependency: The initiative relies heavily on the availability and functionality of EV charging stations. Given current delivery demands, aligning optimal charging times without impacting service performance remains a significant challenge. •Data Constraints: A high degree of variability in capturing reliable actuals further limits our ability to track progress or validate outcomes. Given these challenges, and despite our due diligence and efforts, we believe discontinuing the initiative is the most practical course of action currently. | E: L2 | Cancelled | L2 | 2024-09-10 | 2025-06-30
Business Only Initiative: Waste & Recycling | 2167 | 8150 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar, Brad Courtney | On Track | 01/23/2026- Met with Finance and we are approved to submit the needed documents. Arun from finance will be taking a last look and the IO will then submit to L4 (SL4). 01/20/2026- Finance has requested more feedback in order to move this initiative into L4. Team has a meeting with finance this Friday, the 23rd, to discuss what's needed. This is re-baselined to FY25 on 06/25/2025 07/29/2025 : Since the contracting and final transition was completed on June 2025. There is a spike in monthly savings. Finance has advised to review the actuals for 3 months and then provide approval for L4 next stage. This initiative will remain in L3 for 3 months before moving to the next stage gate. 08/13/2025: Also a PDSM Ticket is submitted and the incident number is INC031500730. 1/5/2026: Finance is asking for rebaseline. It is prepared and submitted for approval now. No leakage in savings. 01/23: Finance is re-evaluating this since the RFP in FY23 the service levels, tonnage, equipment sizes and addition of new sites are impacting the baseline and savings. Meeting is due for this week to complete the exercise. | K: L5 | Active | L5 Feedback Requested | 2022-12-12 | 2026-01-27
Business Only Initiative: Waste & Recycling – demand optimization and proces | 31712 | 8151 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar, Karl Kehr | On Track | Re-baseline to FY25 on 06/25/2025 08/04/2025 : We have also reduced the monthly savings due to the rate normalisation readjustment from the orginal savings to avoid duplication of the savings calculation. Additionally, we have one part of the initiative which was CASS was removed due to the completion being that milestone not before FY26. | K: L5 | Completed | L5 | 2023-07-24 | 2025-09-01
Business Only Initiative: Eliminate tail spend for Waste & Recycling | 83313 | 8152 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar, Brad Courtney | On Track | Re-baseline to FY25 on 06/25/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-01 | 2026-06-15
Business Only Initiative: Electricity usage reduction through EMS for HVAC | 31710 | 8153 | Business Only Initiative | SGA - Facilities | SG&A | Tahza Eggleton, Vivek Cheekoti | On Track | Devices installed- measuring utility savings. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-07-03 | 2024-12-20
Business Only Initiative: ANCH and MEM Bonding Removal | 84267 | 8175 | Business Only Initiative | SGA - Facilities | SG&A | Jared Herring, Brad Courtney | On Track | Uploaded 2 invoices from MEM Sec26 that is evidence of the bond removal and the updated SOV that shows the bond removal from the vendor. | K: L5 | Completed | L5 | 2024-03-05 | 2024-08-16
Business Only Initiative: Separately sized CBRE initiatives for FXE | 31706 | 8281 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2023-08-03
Business Only Initiative: EWR Facility Savings | 89726 | 8282 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney, James Davis, Adriana Peceno | On Track | NA | K: L5 | Completed | L5 | 2024-05-01
Business Only Initiative: Pest Control RFP | 83318 | 8384 | Business Only Initiative | SGA - Facilities | SG&A | Jacob Shearer | On Track | Cancalling per Finance's direction as there are no cost savings resulting from the RFP. | G: L3 | Cancelled | L3 | 2025-03-11 | 2025-10-24
Business Only Initiative: Janitorial Services | 2154 | 8895 | Business Only Initiative | SGA - Facilities | SG&A | Vivek Cheekoti, Jacob Shearer | On Track | on track | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-23 | 2025-10-30
Business Only Initiative: FM&R Demand Mgt | 2164 | 8902 | Business Only Initiative | SGA - Facilities | SG&A | Blazej Radwanski, Brad Courtney, Karl Kehr | On Track | 4/13/2026 - inititaly the initiative was related to all opco's and to IFM implementation. The IFM implemention was put on hold, and as the result the inititative is related only to FXF and only to labour rate reduction at PVC incumbent supplier. The L1 savings was based on all opco's. Today it relates only to FXF, therefor you see significant diff on Baseline and NRB. The current Baseline and NRB is provided in excel sheet (FM&R Transition to IFM). In L2 it shows the value accurately. 3/30/2026 - alignment with Arun on the baseline, it needs to be updated to FY25, then the NRB need to be reviewed and forecast to be adjsuted. After this step initiative can be submitted to L4. 3/26/2026 - alignment with Dan Vargo on the financials 3/4/2026 - due to my sick leave last week, need to move the L4 submission till end of next week (03/13) 02/19/2026 - alignment meeting with FP&A on the missing requirements to re-submission to L4 12/18/2025 - L4 milestone date moved. This initiaitive should be adjusted financially and not be dependent on 3152. 12/4/202 - L4 milestone date moved. This initiaitive should be adjusted financially and not be dependent on 3152. 3152 is an initiative in itself. 8902 should not be held up due to another initiatives progress. 10/02/2025 - The L4 step would be pending us getting “Planview #3152 - Operation Purple Technician Transition-YYZR” into L3. At that stage, the savings will be removed from 8902 and captured in 3152 – the we can move 8902 into L4. The L4 date was postponed to 11/07/2025 5/24/2025- Rebaseline to FY25 with Exit rate of $2.9 million. As the teams have conducted research this initiative has changed and additional alignment/investigation needed. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2023-08-10 | 2026-04-23
Business Only Initiative: Transition Utility Bill Pay Supplier | 3006 | 8957 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Daniel Vargo | On Track | Re-baselined for Fy'25 | E: L2 | On Hold | L2 | 2024-04-01 | 2025-07-25
Business Only Initiative: Utility Price Reduction - Rate Optimization | 3007 | 8959 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Daniel Vargo | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2023-08-11 | 2026-05-25
Business Only Initiative: Reduce corporate janitorial services | 3015 | 8964 | Business Only Initiative | SGA - Facilities | SG&A | Jared Herring, Jacob Shearer, Vivek Cheekoti | On Track | n/a | K: L5 | Completed | L5 | 2023-02-27 | 2023-05-29
Business Only Initiative: Ent. Light Emitting Diode (LED) Retrofit Program |  | 90028 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney, Vivek Cheekoti | On Track | On track Will re-submit to L3 when KPI lines are added. Business Justificiation Document being sent to project management and finance for approval on 03/24/2026 L3 push (3/11/26) Scope of the Initiative includes 30 pilot Locations mentioned in the business case. Cost to Implement the solution is $4.15M | E: L2 | Active | L2 Feedback Requested | 2025-07-11 | 2026-10-29
Business Only Initiative: US Utilities savings target - Oakland Hub |  | 90427 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | NA | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: US Utilities savings target - DFW Hub |  | 90430 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | NA | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: US Utilities savings target - EWR Hub |  | 90433 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | NA | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: US Utilities savings target - Indy Hub |  | 90436 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | NA | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: US Utilities savings target - Eastern region |  | 90442 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | NA | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: US Utilities savings target - Memphis Hub |  | 90445 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | NA | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Investment Credit Annual Award for Federal Express |  | 90847 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track | This was submitted for a cancellation request. PLease cancel per Christine Belling, and Brad Courtney | E: L2 | Cancelled | L2 - Enter Value Prop
Business Only Initiative: Memphis Hub Facilities Vehicle Lease Reduction |  | 90850 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track | On track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Memphis Hub Reduction in Brock Services |  | 90853 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track | Initiative is not showing any savings due to ongoing needed work at the Hub. | C: L1 | Cancelled | L1
Business Only Initiative: Reduce Furniture Spend | 89899 | 9315 | Business Only Initiative | SGA - Facilities | SG&A | Nicole Aversa, Ryan Nelson | On Track | following the re-baselining exercise and alignment with FP&A, the projected savings were determined to be insufficient to justify continuation. Additionally, we anticipate a future RFP opportunity tied to the return-to-office initiative. | E: L2 | Cancelled | L2 Feedback Requested | 2026-02-16 | 2026-02-16
Business Only Initiative: New furniture warehouse | 83297 | 9411 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney, Mark Papachristou, William Clark | On Track | Re-baselined to FY25 on 05/23/25 | K: L5 | Active | L5 Feedback Requested | 2024-05-28 | 2024-12-27
Business Only Initiative: Janitorial - Specs rationalization Tier's 1 and 2 | 83314 | 9413 | Business Only Initiative | SGA - Facilities | SG&A | Jared Herring, Mark LeBlanc, Jacob Shearer, Vivek Cheekoti | On Track | On track | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-27 | 2024-11-29
Business Only Initiative: Janitorial - Pallet labor negotiations | 83315 | 9414 | Business Only Initiative | SGA - Facilities | SG&A | Jared Herring, Mark LeBlanc, Jacob Shearer, Vivek Cheekoti | On Track | on track | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-24 | 2024-11-15
Business Only Initiative: Janitorial - Specs rationalization Tier 3 | 85578 | 9416 | Business Only Initiative | SGA - Facilities | SG&A | Jacob Shearer, Mark LeBlanc, Vivek Cheekoti | On Track | Submitting for L4 with financials updated to reflect FY25 rebaselining. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-03 | 2025-03-31
Business Only Initiative: Vehicle Wash Scope Reduction | 89259 | 9419 | Business Only Initiative | SGA - Facilities | SG&A | Damodar Naik, Ryan Nelson | On Track | Re-baseline to FY25 on 6th May 2025. Made phone calls to all key vendors and discussed possibility of annual spend reduction. Productive discussions, reductions ranging from 8 - 20% with an average of 15% | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-06 | 2025-02-28
Business Only Initiative: EMR - Remove subsidy from food services agreement | 83306 | 9420 | Business Only Initiative | SGA - Facilities | SG&A | Nicole Aversa, Ryan Nelson | On Track | 10/20/2025 - Moved L4 date due to not executred contract. Will continue to track savings until we have a newly executed agreement 11/12/25 - Entered actuals for August, September and October all in October 2025. This was due to not having actuals until after due date had lapsed. August: $84,017.98 September: $73,520.25 October: $72,305.34. 1/5/2026 - Executed contract still going through both legal teams. Moved L4 stage gate to end of January to give enough time to finish MSA and get signatures. 2/4/2026 - Moved money step to end of February as contract is still going through legal teams. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-02-03 | 2026-04-24
Business w/ Tech Initiative: Utility Reduction through EMCS systems |  | 94340 | Business w/ Tech Initiative | SGA - Facilities | SG&A | Vivek Cheekoti | Attention Needed | Request: 94240 - Utility Reduction through EMCS Systems Architecture Owner: Platforms Presenter: Sanjay Kumar Decision: Canceled Notes: Initiative demand type is changing from Bus w/ Tech to Business Only | C: L1 | Cancelled | L1
Business Only Initiative: US Utilities savings target - Implementation playb | 83321 | 9502 | Business Only Initiative | SGA - Facilities | SG&A | Blazej Radwanski, Lohit Mundewadi, Brad Courtney | On Track | Re-baseline to Fy'25 | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: FM&R Software Transition | 96050 | 9505 | Business Only Initiative | SGA - Facilities | SG&A | Ryan Nelson, Vaibhav Srivastava, Brad Courtney | On Track | On track | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2024-11-01
Business Only Initiative: Physical Document Storage Consolidation |  | 97404 | Business Only Initiative | SGA - Facilities | SG&A | Karl Kehr | On Track | .RFP evaluation is ongoing, selection and negotiations will take place over next 90 days. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-30 | 2026-05-14
Business w/ Tech Initiative: Facilities - Global Database |  | 153194 | Business w/ Tech Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 01/12/25: Currently awaiting Feedback from NDS on the next steps for inclusion of additional variables in their Global database. .12/10/25: We are currently reviewing the feasibility of a partnership with another team that is leading a similar initiative—Project Zenith—focused on establishing a global single source of truth database. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR - Memphis Mailroom Spend |  | 153839 | Business Only Initiative | SGA - Facilities | SG&A | Nicole Aversa | On Track | 1/12 - On hold until early Spring | E: L2 | On Hold | L2 Feedback Requested | 2025-10-14 | 2025-10-14
Business Only Initiative: ANC Close Off-Airport Warehouse Facility |  | 160915 | Business Only Initiative | SGA - Facilities | SG&A | Ken D. White | Attention Needed | I have been informed by Finance this is a duplicate initiative and needs to be terminated. I am not sure of the termination process in Planview and will need help to complete. | E: L2 | Cancelled | L2 | 2025-11-28 | 2025-12-02
Business Only Initiative: Facilities - PAER Sublease (Boeing Dreamlifter) |  | 166057 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney, Ken D. White | On Track | 110725: Planview initiative placed on hold due to recent changes from SEATAC which requires a planning and engineering study is to determine if FedEx should maintain control of the Dreamlifter site vs subleasing to Boeing. 110225: Uploaded Active Rents & Payments report for Business Case support documentationm. Sumbitted a support ticket to revise baseline value from from 3,420,000 to 3,385,362. PDSM ticket request # INC03291542. Boeing will be assigned a site currently not used by FedEx. FedEx lease for site does not expire until 2033. | C: L1 | On Hold | L1 Feedback Requested | 2025-09-01 | 2025-12-31
Business Only Initiative: EMR - MPS Rightsizing (Facilities) |  | 166065 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | 02/27/26: Initiative has been revised to include savings resulting from Cannon. PDSM ticket INC034223730 submitted to update values. 02/19/26: Current savings only reflects Ricoh. Additional savings for Cannon to be added to thiis prior before submittal to L2. 02/11/2026: Savings updated based on information provided by MPS team. PDSM ticket submitted to update the Net Recurring benefits and baseline values. PDSM tick number: INC034044614 . 12/10/25: Awaiting finalization of savings to input into the Planview initiative in order to complete the Level 1 business case and progress to the next stage. 10/16/25: Revaluations underway to review current printer allocations. | D: SL2 | Active | SL2 Finance Domain Lead Approval | 2025-11-03 | 2026-12-31
Business Only Initiative: LAC Lease Savings FY26 |  | 169956 | Business Only Initiative | SGA - Facilities | SG&A | Sebastian Forero | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2025-03-31 | 2026-01-30
Business Only Initiative: Energy Management Control System - Columbus |  | 170367 | Business Only Initiative | SGA - Facilities | SG&A | Vivek Cheekoti | On Track | On Hold - Assessing Feasability of Initiative (Longer payback Period) | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR - FMR Regional RFP |  | 170564 | Business Only Initiative | SGA - Facilities | SG&A | Grace Ige | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR: Canadian Janitorial RFP |  | 131653 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Vivek Cheekoti, Jacob Shearer | On Track | on track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-03 | 2026-08-03
Business Only Initiative: EMR - MSA Addition in Deregulated Markets |  | 131657 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi, Daniel Vargo | On Track | Assigning IO as Lohit Mundewadi | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: EMR-Open Top Container Optimization-SMT |  | 131665 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar | On Track | This is to optimize the open top container sites by reducing the frequencies. | I: L4 | Active | L4 | 2025-12-01 | 2026-07-15
Business Only Initiative: EMR - Energy Consulting RFP |  | 131668 | Business Only Initiative | SGA - Facilities | SG&A | Lohit Mundewadi | On Track | . | E: L2 | Active | L2
Business Only Initiative: EMR - Consolidate/Reduce Water Supply/Vendor Base |  | 132133 | Business Only Initiative | SGA - Facilities | SG&A | Nicole Aversa | On Track | Will be holding an ideation session with VP's to discuss the course of this inititiatve. | E: L2 | On Hold | L2
Business Only Initiative: EMR-Optimize Document Shredding Services |  | 133063 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar | On Track | This is mainly changing the service level frequency across enterprise. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-10-15 | 2026-04-27
Business Only Initiative: EMR-Canada Waste RFP & Optimization |  | 133067 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar | On Track | There will be a RFI,RFP and Competitive Bidding. The spend has been taken from the Insight Spend Dashboard. I am attaching the link onto the buisness case. The tentative timeline is to launch the RFP by 11/15 and then complete the contractual process and execution by 03/31/2026. The initiative only involves 2 suppliers since they are contributing to 80% of the spend. The others are all tail spend suppliers which we cannot determine at RFP stage. | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2025-12-01 | 2026-12-01
Business Only Initiative: EMR-Solid Waste Optimization (FXE & FXO) |  | 133070 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar | On Track | To reduce and right siz the containers and optimize the service frequencies. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-11-10 | 2026-05-15
Business Only Initiative: EMR - Pest Control Scope Reduction |  | 131236 | Business Only Initiative | SGA - Facilities | SG&A | Jacob Shearer | On Track | .Placing on hold as initiative is dependent on ongoing implementation, scheduled to be completed by the end of FY26. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR-PALLET COMMODITY RFP |  | 131661 | Business Only Initiative | SGA - Facilities | SG&A | Mekhala Kar | On Track | Currently what we have added in the scope of this initiative is the Ground Green cycle ctredit GL code. This should get refined when we start receiving credits from the express sites as well. Now we are trying to have both Surface+Air sites iwthin this scope. | D: SL2 | Active | SL2 Finance Domain Lead Approval | 2025-11-03 | 2026-04-30
Business Only Initiative: EMR-FY26 - Regionalize Suppliers for Snow |  | 131673 | Business Only Initiative | SGA - Facilities | SG&A | Matthew Drummond | On Track | This intitiatve is being removed from Planview due to unreliable savings estimates. The savings are based on the amount of snow a site gets in a season, making it impossible to make an accurate savings prediction. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR - Print - Global Print Tender |  | 132139 | Business Only Initiative | SGA - Facilities | SG&A | Steffani Fondrk, Anchit Mahajan, Jason Morgan | On Track | Adding a initiative for global MPS RFP. | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business Only Initiative: EMR-Offsite Physical Document Inventory Cleanup |  | 155371 | Business Only Initiative | SGA - Facilities | SG&A | Jacob Shearer | On Track | Cancelling as net beneift is negative through the end of FY28. Net benefit is positive starting June FY29. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR-Agreement for Project Management |  | 133503 | Business Only Initiative | SGA - Facilities | SG&A | Nawal K. Dwivedi, Karl Kehr | On Track | The initiative provides low value due to the limited number of hub/automated projects in the pipeline. Additionally, the business team highlighted operational challenges with moving to a direc spend model with Grainger— including multiple invoices per order, staggered deliveries, and additional labor required to manage them. Given the low impact and added operational burden, the initiative should be canceled for now and revisited if larger projects enter the pipeline. | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business Only Initiative: MEMH Primary Matrix Scan Tunnel Upgrades [MEMH onl |  | 87908 | Business Only Initiative | SGA - Facilities | SG&A | Paul M. McCaulla, Holland Aguayo, Brad Courtney | Some Issues | 07/16/2025: Financial reforcasting complete to match revised schedule. 06/19/2025: Funding is moving forward; scheduled milestone dates are now being adjusted. 05/16/2025: **Subtstantial Funding Delays**: Efforts are still underway to obtain funding. Until funding is approved, updates to the the forcast/actual values in planview will be on hold. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-20 | 2026-06-01
Business Only Initiative: MEMH Non-Conveyable Decongestion [MEMH only] |  | 88206 | Business Only Initiative | SGA - Facilities | SG&A | Paul M. McCaulla, Brad Courtney | On Track | 01/19/2026 - Changed status to On Hold, budget cuts have pushed this project back, possibly to next Fiscal Year. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-06-30 | 2026-07-08
Business w/ Tech Initiative: NonCon Auto Secondary Sort [MEMH only] |  | 88407 | Business w/ Tech Initiative | SGA - Facilities | SG&A | Paul M. McCaulla, Kathryn D. Crighton-Smith, Brad Courtney | On Track | 12/01/2024 - Money step marked as complete now that we have three months of documented benefits. 11/17/2024 - The system has generated a total of $782,279 in benefits since it started in July. I am going to proceed to seek approval to push to L4. 09/05/2025 - System went operational in July. REX82-DIM and REX83-WT capture functional was enabled on 08/13/2025 Nightsort. Since startup, Night Ops has only been using one of the two sort lines. Dayside has started using both lines. Over 100,000 packages have been processed. We have generated 61,958 REX-82 DIM counts and 58,105 REX-83 Wt counts since 8/13. The PIP functionality has not been enabled yet to generate REX-83 AHS. 08/11/2025 - Planview scope reduced to only the two pilot sort lines (Secondary 25 Runouts 9 and 10). Net recurring benefits reduced to $3,987,168 for the pair of lines. 04/21/2025 - Updated L1 NRB for FY28 because only 2 lines will be functional at that time. Planview schedule does not currenlty look far enough ahead to reflect full project benefiits. Reduces NRB from $24M to $3.9M. 04/21/2025 - Project is on track. IT Sort Solution Council and Supply Chain SCO have approved to prooceed to PEL review. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-03-03 | 2026-03-03
Business Only Initiative: MEMH International Clearance Scan Automation |  | 88165 | Business Only Initiative | SGA - Facilities | SG&A | Paul M. McCaulla, Holland Aguayo | On Track | 11/11/2025: Changed status to on hold. Project is in the bid process without a firm date for when this will be completed. Once the date is known, all scheduled milestone dates will need to be updated in order to return the project to an active state. 11/06/2025: Technically the bid process/contracting process has begun, but it is not finished. 10/09/2025: Bid phase is taking longer than expected. Scheduled completion for bid phase has now been adjusted to show a date of 10/20/2025. Also, the Contracting phase has been adjusted to show a scheduled start of 10/20/2025 and scheduled finish of 01/12/2026. 09/05/2025: Project bidding process is behind schedule. Expected completion on 09/15. Planview milestones have been updated. 06/20/2025: Updated project schedule. 05/16/2025: Delay: We are pushing the sort bid completion date out from May 19 to tentatively August 1. This is due to the fact that we are waiting on FedEx Engineering to complete the DB Manual, which now isn’t scheduled for release until July 15. The sort design process is a tedious process. It will be released to the internal team for their review, comments are made throughout the review, then these comments have to be incorporated. Unfortunately, with the fiscal year ending, several team members are out of the office for big part of the month, others for the entire month, so this is a large contributing factor to the delay, as well. 04/01/2025 Rebaseline activity is not required. No changes to baseline information. No benefits will be received until 2027 or 2028. 04/1/2025 Milestones 103003 and 103004 have been updated to show as completed on 3/11/2025 Milestone 103005 is updated to show as "In Process." Recommend change to business without tech. Project scope should not require changes to ILS or CCII. Additional tech info should not be required to advance to L2. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-02-03 | 2027-03-03
Business Only Initiative: EMR - Facility Managed Svcs Tail Spend Analysis |  | 133521 | Business Only Initiative | SGA - Facilities | SG&A | Nawal K. Dwivedi, Daniel Vargo, Grace Ige | On Track | This initiative is intended as a strategic effort to consolidate tail spend vendors across multiple spend categories. However, we will not be tracking savings numbers associated with this effort. As such, the initiative does not meet the criteria for continued tracking in Planview and needs to be cancelled. | C: L1 | Cancelled | L1
Business Only Initiative: EMR-Hazardous Waste- Category Optimization |  | 134025 | Business Only Initiative | SGA - Facilities | SG&A | Rafael Rodriguez | On Track | Because this overlaps with another Haz Waste initiative, that is in progress. | C: L1 | Cancelled | L1
Business Only Initiative: EMR US MHE sort maintenance tender non-automated |  | 136577 | Business Only Initiative | SGA - Facilities | SG&A | Luigi Mastromonaco | On Track | Finance advised to cancel PV 136577 initiative on US sort maintenance and create a new initiative upon completion of the RFP for the pilot area. Original initiative was scoped to tender all 1188 US locations, while the RFP address a pilot area of 28 sites. Rationale for the decision: •Avoid keeping the initiative in Level 2 for an extended period. •Allow to appropriately rescope the project based on the pilot results. •Prevent running a full initiative process for a pilot with a limited scope and savings. | E: L2 | Cancelled | L2
Business Only Initiative: EMR-LAC Janitorial RFP |  | 155384 | Business Only Initiative | SGA - Facilities | SG&A | Rafael Rodriguez | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR-Consolidate DirecTV Packages |  | 153140 | Business Only Initiative | SGA - Facilities | SG&A | Karl Kehr | On Track | 07/25-Finished triage 07/28-Completing Create L1 LBC | K: L5 | Active | L5 | 2025-11-17 | 2025-12-05
Business Only Initiative: Implement Service Channel fully in Canada |  | 177176 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Memphis, Light, Gas & Water (TVA) Utility Credit |  | 178079 | Business Only Initiative | SGA - Facilities | SG&A | Brad Courtney | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: A-Plus Closed Locations RFP |  | 178082 | Business Only Initiative | SGA - Facilities | SG&A | Vivek Cheekoti | On Track | On Track | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2025-07-01 | 2025-09-30
Business Only Initiative: Legacy FXE Janitorial RFP (Phase 1-3) |  | 178085 | Business Only Initiative | SGA - Facilities | SG&A | Vivek Cheekoti | On Track | On Track | E: L2 | Active | L2 - Enter Value Prop
Business Only Initiative: LAC Properties: MEX Maintenance. Operation Purple |  | 184974 | Business Only Initiative | SGA - Facilities | SG&A | Sebastian Forero | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Facility - FedEx Supply Chain (FSC) HQ Relocation |  | 190353 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster, Brad Courtney | On Track | On Track | C: L1 | Active | L1 Feedback Requested | 2026-04-10 | 2026-07-02
Business Only Initiative: Facility - Canadian Reg Office (YULRC) - Montreal |  | 190358 | Business Only Initiative | SGA - Facilities | SG&A | Glenda Webster | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval | 2026-03-31 | 2026-05-29
Business Only Initiative: CBS - Outside Services Cost Reduction - Intl Payro | 30480 | 6776 | Business Only Initiative | SGA - Finance | SG&A | Baptiste De Dree, Kavita Singh, Danielle Gwin Allen | On Track | -- Apr 15, 2026 -- 1. 9 permanent FTEs were hired as of Feb-2026 2. France went live on the ADP GV payroll system in Jan-2026 and last phase of T&A implementation completed in Apr-2026 3. OSV exits have begun as of Mar-2026 -- Mar 10, 2026 -- 1) 9 permanent FTEs were hired as of Feb-2026 2) France went live on the ADP GV payroll system in Jan-2026 and is currently in the hypercare phase. 3) Part of T&A implementation completed in Dec-2025 and rest expected to be fully completed by Apr-2026 4) OSV exits are planned to begin in FY26 Q3 5) We will be assessing if Project Forward will have any impact on the Payroll OSV exit timing -- Feb 10, 2026 -- 1) 9 permanent FTEs were hired as of Jan-2026 2) France went live on the ADP GV payroll system in Jan-2026 and is currently in the hypercare phase. 3) Full T&A system implementation is planned for France in Feb-2026. 4) OSV exits are planned to begin in FY26 Q3 5) The France Project Forward initiative has been announced; we are assessing the payroll organizational impact and resource requirements, and will evaluate the implications for DRIVE in the coming month. -- Jan 2, 2026 -- 1) 8 permanent FTEs have been hired as of Dec-2025 2) 1 OSV, planned for FY26 Q1, exited in early July, completing our OSV exit milestone for Q1 3) All OSV exits across International Payroll have been completed except for France. The OSV exits in France are expected to begin, aligned with the completion of in-house hiring and training to ensure a smooth transition. 4) France went Live with ADP in January 2026, we will begin exiting the OSVs after the hypercare period of 3 months -- Dec 8, 2025 -- 1) 7 permanent FTEs have been hired as of the end of Nov, and 1 will begin in Dec-2025 2) 1 OSV, planned for FY26 Q1, exited in early July, completing our OSV exit milestone for Q1 3) All OSV exits across International Payroll have been completed except for France. The OSV exits in France are expected to begin in FY26 Q3, aligned with the completion of in-house hiring and training to ensure a smooth transition. 4) France implementation remains on track, with Go-Live with ADP planned for January 2026. -- Oct 6, 2025 -- 1) permanent FTEs have been hired as of the end of September, and recruitment is ongoing for the remaining positions. 2) 1 OSV, planned for FY26 Q1, exited in early July, completing our OSV exit milestone for this quarter. 3) All OSV exits across International Payroll have been completed except for France. The OSV exit in France is scheduled to begin in FY26 Q3, aligned with the completion of in-house hiring and training to ensure a smooth transition. The FY25 forecast has been updated accordingly. 4) France implementation remains on track, with Go-Live with ADP planned for January 2026. -- Aug 13, 2025 -- 1)FTE hiring planned for Jun-25 has been deferred to Aug-25, which is why the Jun and Jul actual value is zero on the Salaries and Wages. 2) 1 OSV as planned for FY26Q1 is exited in Jul begining, this completes our OSV exit milestone for FY26Q1 3) We remain on track to hit FY26Q1 targets 5) At overall INTL Payroll level, all OSV exits have been completed, except for France. The OSV exit in France is scheduled to begin in FY26 Q3, aligned with the completion of in-house hiring and training to ensure a smooth transition. The FY25 forecast has been updated accordingly. 6) France implementation is in progress, with Go-Live with ADP on tarck as planned for January 2026. -- July 10, 2025 -- 1)FTE hiring planned for Jun-25 has been deferred to Aug-25, which is why the Jun actual value is zero. However, we still expect to meet the overall Q1 hiring target. One OSV exited on Jun-30 and will be reflected in the July actuals. Overall, we remain on track. 2) At overall INTL Payroll level, all OSV exits have been completed, except for France. The OSV exit in France is scheduled to begin in FY26 Q3, aligned with the completion of in-house hiring and training to ensure a smooth transition. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-06-01 | 2027-05-31
Business Only Initiative: China purple dispute process automation | 37414 | 7065 | Business Only Initiative | SGA - Finance | SG&A | Judy Ju, Luvitta Chen | On Track | 2025/1/8- update for the milestone timeline change: the ITD completion date delay to 2025-3-31 due to the ITD resource arrangement. 2025/2/5 update the milestone timeline change: the ITD completion date and the roll out to production date delay to 2025-3-31 due to the ITD resouce arrangement 2025/2/12 update the milestone timeline change: the ITD completion date and the roll out to production date delay to 2025-3-31 due to the ITD resouce arrangement 2025/2/19 update the milestone timeline change: the ITD completion date and the roll out to production date delay to 2025-3-31 due to the ITD resouce arrangement 2025/3/4 update the milestone timeline change: the ITD completion date and the roll out to production date delay to 2025-3-31 due to the ITD resouce arrangement 2025/3/7 update the milestone timeline change: the ITD completion date and the roll out to production date delay to 2025-3-31 due to the ITD resouce arrangement 2025/3/12 update the milestone timeline change: the ITD completion date and the roll out to production date delay to 2025-3-31 due to the ITD resouce arrangement 2025/3/14 As P9 process is targeted to finish by Mar 31st, and 3 months is necessary for all the new process stabilization and team accommodate to these changes, so the target date to step in L4 would be Jul 1st. 2025/3/19 P9 timeline is delayed: Currently development is in progress. We should be able to complete Development and SIT by 31 March. Post that we will have UAT. Post UAT sign off in 10 days we should be live by 15 to 21 April. 2025/3/24 The initiative is now baselined to FY25. The RPA tools have been launched one by one started from Aug 2024. The salary savings are uploaded from Aug 2024 to Mar 2025. Previously estimate unit case time saving has been updated according to the time study after RPA tools launched. 2025/3/26 FY26 Financial forecast updated based on FY25 baseline. 2025/4/2 Bot file upload to S3 bucket: P4-RBV files missing issue is solved. 2025/4/3 Updated Work Status, and Schedule Finish and Start dates. As CN dispute automation includess a series of RPA tools and developed/rolled out one by one, so the start dates of IT development and roll out are revised to the first RPA tool, and the finish dates are revised to the last RPA tool's date. Money back start date is revised to keep consistent with Financials cost savings' start date as Aug 2024. 2025/4/11 We previously forecast in FY26 one additional OT FTE (1084USD/month) could be saved after P9 go live and agents get more familiar to RPA process. But due to CN in-sourcing project will roll out from May 26th, all the insourcing accts will move to Service Now system while the RPA is remaining on Salesforce. We suppose 40% awbs can't use the RPA tool which would bring OT increasing and offset the forecast savings. As a result, we removed the forecast saving in FY26. 2025/4/16 Have got CN FP&A's confirmation for the average 5 FTEs savings of this Drive initiative in FY25. 2025/4/17 Uploaded L3 money back step evidence. 2025/4/23 P9: MTP on Apr 24th. 2025/4/30 P4-P7 refresh training conducted on Apr 29th. Supporting filing simplified. 2025/5/4 No updates for the holiday from May 1st to May 5th. 2025/5/7 P9 Hypercare. 2025/5/14 P9: will conduct training to the team in this week. 2025/5/28 Changed the milestone of "Work: Roll out to production" to complete status. | K: L5 | Completed | L5 | 2023-04-03 | 2025-05-30
Business Only Initiative: Payment Processing - Working Capital Improvement | 90264 | 7099 | Business Only Initiative | SGA - Finance | SG&A | Celestine Evans, Marquis Ragland | On Track | 2/7/25 – Implemented change from daily to 2x per week payment frequency for non-critical suppliers in US, LAC, and CAN on 1-2-25. Estimated $5M in annual working capital benefits. 3/14/25 – Aligned with Treasury on calculation of working capital benefits. Met with EBS Strategy team for guidance on hard vs. soft benefits. Finalizing entries for completion of L1 Stage. 8/14/25 - The benefits could only be captured as soft benefits and the rigor of the Planview process was deemed to be not necessary for this project | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: DC QDRO fees charged to participants | 64309 | 7373 | Business Only Initiative | SGA - Finance | SG&A | Janet Phillippi, Renee Miller | On Track | 3/31/2025 - This project reached the full run-rate in FY25 and the ongoing savings for FY26-FY28 will be flat. Forecast savings for FY26-FY28 are zeroed out. 3/3/2025 - On track - All actions related to the Initiative have been completed, and all that remains is the tracking of value on a monthly basis. Actual savings are expected to be in line with Forecasts based on our current understanding of the number of non-pilot QDROs anticipated to be processed in a month. | K: L5 | Completed | L5 | 2024-09-13 | 2024-09-13
Business Only Initiative: Tax-CIP/CNS/CGL withholding tax handling fee compe | 86000 | 7595 | Business Only Initiative | SGA - Finance | SG&A | Jennifer Lin, Joyce Fan | On Track | on track- Oct 31st * 2/6/2025 tax team to discuss with tax accounting regarding preparation of withholding tax handling fee compensation application. * 2/14/2025 Witholding IIT handling fee compensation application has been submitted. Witholding CIT handling fee compensation application is under preparation by tax accounting. * 3/4/2025, 1. Withholding IIT handling fee compensation application has been submitted. 2. Withholding CIT handling fee compensation application for CIP has been submitted. 3. Withholding CIT handling fee compensation for CNS is under preparation by tax accounting, aiming to submit final application by 31/3/2025. * 3/21/2025 The initiative is now baselined to FY25. * 4/3/2025 1. Withholding IIT handling fee compensation application has been submitted. 2. Withholding CIT handling fee compensation application for CIP has been submitted. 3. Withholding CIT handling fee compensation for CNS is under preparation by tax accounting, target to submit final application by 16/5/2025. 4. Target to receive above withholding tax handling fee refund by 30/5/2025. 5. Above timeline have been reflected/updated in milestone Work Status and Schedule Start/ Schedule Finish date. *4/14/2025 0.24M US$ withholding tax handling fee refund was recieved from tax bureau, updated in the confirmed actial line on the financial tab, while clear relevant figure on forecast line. 16/5/2025 Money step has been completed. | K: L5 | Completed | L5 | 2025-03-03 | 2025-05-30
Business Only Initiative: Tax-TNT Cash pooling cease operation | 86001 | 7596 | Business Only Initiative | SGA - Finance | SG&A | Jennifer Lin, Joyce Fan | On Track | on track * 2/6/2025 Tax team to discuss with treasury&legal regarding cease TNT cash pooling next step. * 2/14/2025 Target by treasury, has chance to cease cash pool operation. * 3/4/2025 Further discuss with Legal/Treasury regarding next steps to cease TNT cash pool operation. As M++’s bank account is frozen, aiming to discuss solution for un-freezing liquidity of M++’s bank fund.. * 3/12/2025 Initiative on hold， plan of "TNT cash pooling cease operation" is on hold, due to M++'s bank account is frozen. | E: L2 | On Hold | L2
Business Only Initiative: Tax-Qingdao government subsidy -VAT | 86004 | 7597 | Business Only Initiative | SGA - Finance | SG&A | Jennifer Lin, Joyce Fan | Some Issues | On hold， Qingdao subsidy has been suspended until further notice | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-05-30 | 2025-05-30
Business w/ Tech Initiative: Financial Insights Platform (FIP) | 91087 | 7600 | Business w/ Tech Initiative | SGA - Finance | SG&A | Shevata Shanmugam, Heidi Garrett, Andrew Wiggs | On Track | 1/12 Work in progress. Complieted PI CY25_05. Starting PI CY26_01 9/30 Work is progressing. Completed mid CY25-PI04 review 9/12 Work is progressing; comprehensive G/L data available for actuals and plan. Current focus is still focused on supporting FIH data ingestion. 9/1 Work is progressing; comprehensive G/L data available for actuals and plan. Current focus is centered on supporting FIH data ingestion. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-22 | 2026-12-31
Business w/ Tech Initiative: Phire software for PeopleTools application change | 94998 | 7646 | Business w/ Tech Initiative | SGA - Finance | SG&A | Sita Achanta | On Track | 04/16/2026: Actuals added for March 01/06/2026: updated actuals for December. Submitting for L5 per direction from Kendra Yarbrough 12/12/2025: updated actuals for November 10/16/2025: Per comments from Jerome Miller, I have updated the Actuals till Oct. and Forecast for the future months. Since this is a one time annual payment, the forecast is the same for each month. Submitting the request for L5. 09/17/2025: It has been three months since the savings were realized. submitting the Initiative for L5. 08/06/2025: Initiative on track. STAT license has been discontinued. Phire is in use and STAT use has been discontinued. No Actuals to report for July as the purchase of PHIRE was a one time cost. 06/19/2025: Initiative on track. STAT license has been discontinued. Phire is in use and STAT use has been discontinued. 05/01/2025: Still on track for STAT retirement. STAT license is not being renewed in June. 03/28/2025: Updated FY28 exit rate 03/13/2025: The target date for L4 is May 31st. We have notified Quest that the STAT license will be discontinued as of May 31st. The savings will be realized on June 1st when the STAT livcense is not renewed. We are on track with this. There are no outstanding actions or dependencies. 03/04/25: Implementation of PHIRE is complete. the milestone has been marked as completed. 02/17/25: Reviewed financial profile with domain Finance and made edits as needed to most accurately represent initiative financials. This included adding costs for recurirng software license and adjusting cost and benefit attributes to align with new P&L segment. Financials tab should now be accurate and up to date. 02/05/25: Phire software installation is in progress. 01/07/25: Milestone start date for implementing PHIRE was moved to Feb 1st, as we are waiting on the PO to be entered for purchasing the software. 12/11/24: Milestone for legal approval was cancelled, per legal guidelines . This approval is no longer needed. 12/04/24: Milestone dates were changed, since L3 approval was delayed due to transition from Wave to PLanview. Current milestone dates are best estimates. They are dependent on legal bandwidth and how long it takes to work through the legal approval process. 10/21: Reviewed initiative post Planview import. Updated IO to remove incorrect owner | K: L5 | Active | L5 | 2024-09-25 | 2025-10-10
Business Only Initiative: Tax: FedEx WOTC ADP Fees | 18349 | 7850 | Business Only Initiative | SGA - Finance | SG&A | Misty Arinder, Sherri Swindle, Craig Foer | On Track | 3.31.25: Per discussion with Domain Finance, FY25 rebaselining not needed. Reporting roles off at end of FY25. Added Q1 and Q2 savings to Impacts area; uploaded invoices and excel calculation as support [updated in Oct 2023]. Updated Money Step date to March 31, 2024 due to timing of quarterly invoices. The last fee savings will be reflected in our Q4 invoice and at that time, the last Actual impact can be recorded and submitted for L4 [updated in Dec 2023]. | K: L5 | Completed | L5 | 2024-04-12 | 2024-04-12
Business Only Initiative: Tax: GA QJTC fees | 22190 | 7851 | Business Only Initiative | SGA - Finance | SG&A | Misty Arinder, Sherri Swindle | On Track | Initiative is complete, no other actions are required, and no future benefits are expected. | K: L5 | Completed | L5 | 2024-11-29 | 2024-11-29
Business Only Initiative: Eliminate Sr Manager Role - CBS | 17498 | 7870 | Business Only Initiative | SGA - Finance | SG&A | Christopher Terry, Spencer Ryan | On Track | 3/21/2025 - Confirmed rebaselined to FY25. Processed retirement for Todd Mortenson on 5/15/23. Uploaded attachment screenshot. | K: L5 | Completed | L5 | 2023-01-03 | 2023-05-15
Business Only Initiative: CBS - Employee Solutions Contact Center (ESCC) - P | 30953 | 7872 | Business Only Initiative | SGA - Finance | SG&A | Matt Geater, Spencer Ryan | On Track | 3/21/25 - Confirmed re-baseline to FY25. 11/12/2024 - Reviewed financials and determined future forecast not applicable due to scope of contract that would have ended in September FY25 without the work of the initiative. | K: L5 | Completed | L5 | 2023-05-01 | 2023-05-31
Business Only Initiative: CBS - Paperless W-2s | 30955 | 7873 | Business Only Initiative | SGA - Finance | SG&A | Collins Coltharp, Spencer Ryan | On Track | 8/13/2025 - No incremental value in FY26, FY27, FY28. Forecast zeroed out. 1/23/2025 - Solution moved to production summer 2024. Reviewed money step readiness, on track for move to L4 on 1/31/2025. Moved to L4 2/5/2025. On pace to submit actuals by 2/17/2025. Still on track 2.13.2025 2/17/2025 - Entered actuals for Jan 2025 based on estimate as guided by Finance. Revised actuals entered when invoice received (eta 2/28). Actuals came in under forecast as fewer employees than expected selected the paperless W2 option. Many employees prefer a paper copy of their W2. 3/16/2025 - Initiative progression to L5 was discussed with Domain Finance, and they have identified they would like the Initiative to remain in L4 at least through the end of the FY and then re-assess after baselining activities have been completed. Initiative value is expected to grow as more employees opt-in to paperless W-2 delivery. This value is tracked annually in accordance with the W-2 printing/billing cycle. Further discussions with Finance will determine when the Initiative is eligible to move to L5. | K: L5 | Completed | L5 | 2023-07-11 | 2025-01-31
Business Only Initiative: Treasury: Termination of Working Capital Consultin | 16260 | 7877 | Business Only Initiative | SGA - Finance | SG&A | Matthew Daniel | On Track | Temporarily on hold while determination between Deloitte and McKinsey is made. | E: L2 | On Hold | L2
Business Only Initiative: Treasury: Reduction in insurance premiums through | 16266 | 7878 | Business Only Initiative | SGA - Finance | SG&A | Chad Jackson | On Track | 2/6/25 - Tracking for contract to incept in March | K: L5 | Completed | L5 | 2022-11-15 | 2023-11-30
Business Only Initiative: Treasury: Interest Income from captive cash invest | 16277 | 7879 | Business Only Initiative | SGA - Finance | SG&A | Chad Jackson | On Track | 3/28/2025: Rebaselined to FY25. No additional benefits. Initiative closed. Monthly interest being received. February 2025 interest not yet received as we tend to receive reports mid-month. | K: L5 | Completed | L5 | 2022-10-03 | 2023-05-03
Business Only Initiative: Tax - India GST on LSF (Logistic service fees) - c | 56631 | 8188 | Business Only Initiative | SGA - Finance | SG&A | Parikshit Vyas, Yanmei Wang | On Track | We have revised the forecast savings downward. Originally when we included this project in Drive, we had forecasted the savings basis FY23 figures which I think was quoted at $4.592mn per annum. The current actual savings dialed in is $1.682mn for past 6 months starting Oct 2023. The savings are on account of VAT on LSF (Logistic Service Fees). LSF is a product of transfer pricing (TP) working which considers many expense GLs into its calculations. From FY23 to FY24, there has been significant changes in cost profile of India business, due to which, the overall value of LSF has gone down. We expect above trend to continue in future. Hence we have revised the monthly forecast figures to actual average monthly savings in last 6 months. The VAT savings on LSF, depends on the value of LSF. The value of LSF depends on value of all other expenses in the books. We have seen in past huge variances in accounting of expenses month over month, because of which, we used to miss the forecast in between. You can refer to actual of Feb & March, June & July. We have revised the forecast at 0.271mn being the average monthly savings basis last one year's actuals. Having said that there could be fluctuation in figures of actual savings month over month due to fluctuation in expenses bookings and we may see few months missing the forecast for that reason going forward. | K: L5 | Completed | L5 | 2023-11-30 | 2023-11-30
Business Only Initiative: Tax: KSA VAT refund project | 92176 | 8189 | Business Only Initiative | SGA - Finance | SG&A | Parikshit Vyas, Yanmei Wang | On Track | 11/27/2024 : Change in accounting treatment is implemented. Pursuing move to L4. 11/15/2024 : Added KPIs per feedback received. The KPI used is the % of VAT rate on LSF. This rate determines the VAT paid on LSF in any given month. The VAT % could change in future but 15% is our current best estimate. Money step is also added per feedback. 11.07.2024 : We have already received the refund for the period CY18 to CY23. The refund of $8.7m is received in Oct 24. Post receipt of the refund in concensus with RtR team and EY, we have decided to change the accounting treatment of these refunds from accounting them as expenses to P&L to accounting it as receivable. This change will be implemented from Nov 24 onwards. Accordingly we will reverse the cost of $2.2m booked in the first four months of FY25 in Nov 24 and will achive recurring benefit of $400K per month from Nov 24 onwards. 13/03/2025 : This project has been completed in Nov 24 and since then we are just updating the monthly savings in financials month over month. | K: L5 | Completed | L5 | 2024-11-29
Business Only Initiative: Finance - CRA Process transformation and eliminat | 3156 | 8274 | Business Only Initiative | SGA - Finance | SG&A | Elaine Gray | On Track | All steps were taken in order to terminate the temporary resource. The temporary's last day is 11/15/2022. | K: L5 | Completed | L5 | 2022-11-01 | 2022-11-16
Business Only Initiative: RTR - FXG Unbilled | 3164 | 8275 | Business Only Initiative | SGA - Finance | SG&A | Leane Giska, Leigh A. Pitts | On Track | 04.11.25 Reconciliation completed. Slight increase in variance. 04.04.25 Month-end close week. Reconciliation will be completed next week. 03.28.25 Variances may be related to month-end timing. Will see if variance decreases with March end. 03.21.25 Initiative is now baselined to FY25 03.14.25 Reconciliation completed. Variance decreased and will be investigated. 03.07.25 Quarter-end close week. Reconciliation will be completed next week. 02.28.25 Investigating whether unreconciled amount is due to January rating issues or timing of month end. 02.21.25 Reconciliation reviewed. Investigating unreconciled amount with rating team. 02.14.25 Completed Unbilled balance sheet reconciliation. It is showing an unreconciled amount. Will continue to investigate the unreconciled amount. 02.07.25 Detailed matching report ran on 02.01.25 Preparing the January balance sheet Unbilled Reconcilation. | K: L5 | Completed | L5 | 2023-03-06 | 2024-09-30
Business Only Initiative: Tax: Increase property tax appeals | 16589 | 8346 | Business Only Initiative | SGA - Finance | SG&A | Pamela Lindsley | On Track | 03/31/2025: FY25 Baseline Complete. 03/03/2025: It's Property Tax Compliance season, appeals opportunites will occur in the summer months. We continue to work with vendor to seek opportunties. 2/14/2025:Update financials with recent property tax savings. Continue working with vendors to seek additional opportunties. Upon review of the Initiative it was found that the true business operation change was the implementation of a new contract to expand the scope of properties that the vendor can appeal. As such, the Money Step was deemed to be the signing of the new contract. All other Milestones are more or less business as usual tasks to support the updated contract. Milestones and Forecast dates have been updated accordingly with this new understanding. 08/2024: There was an amendent to the contract to allow for additional property tax savings opportunites in 2025. The date has been updated to reflect this change. | K: L5 | Completed | L5 | 2022-11-30 | 2025-12-31
Business Only Initiative: Finance - Paperless pay - Payroll | 3160 | 8365 | Business Only Initiative | SGA - Finance | SG&A | Sam Martin | On Track | 3/21/25 - Confirmed re-baseline to FY25 | K: L5 | Completed | L5 | 2022-11-22 | 2023-01-31
Business Only Initiative: Tax: Eliminate Canada Tax MD position | 80742 | 8369 | Business Only Initiative | SGA - Finance | SG&A | Sherri Swindle | On Track | 2-7-2025 - All actions of the Initiative have been completed. There are no changes to the financials expected since the Initiative is related to the non-payment of a former salary; thus the financials will be steady month over month. | K: L5 | Completed | L5 | 2023-08-01 | 2023-08-01
Business Only Initiative: CBS - CRA Reduction in Third-Party Spend | 36070 | 8394 | Business Only Initiative | SGA - Finance | SG&A | Jessica Yatsula | On Track | 2/7/2025 – Third Party spend with PwC associated with ARCs program was eliminated in June of 2023. Value has been captured for 12 months and Actuals updated through the end of FY25. No further actions required. | K: L5 | Completed | L5 | 2023-05-01 | 2023-06-02
Business Only Initiative: IHQ - Professional Fees Reduction from LEES (CBS) | 18095 | 8411 | Business Only Initiative | SGA - Finance | SG&A | Darrell Davis | On Track | March 21, 2025: Rebaseline to FY25 | K: L5 | Completed | L5 | 2023-01-02 | 2024-03-15
Business Only Initiative: IHQ - Reduction of OSV/Contractor support in IHQ A | 18097 | 8412 | Business Only Initiative | SGA - Finance | SG&A | Darrell Davis | On Track | March 21, 2025: Rebaseline FY25 | K: L5 | Completed | L5 | 2023-03-01 | 2023-12-15
Business Only Initiative: CBS - LAC Insource Datamark Account Reconciliation | 58641 | 8414 | Business Only Initiative | SGA - Finance | SG&A | Daniel Lopez, Jay L. Thompson, Gopal Krishnamurthi | On Track | 1/30/26 Update - Actuals and forecast updated; and money step evidence attached. 2/13/25 Update - Working on business plan as we move to the next phase. We need to keep this moving to post jobs in advance. Contract does not expire until October 2025 3/4/25 Update - This project has been submitted for approval to enter SL3. I met recently with HR to let them kmow of the future hiring needs and they are on board. All is on track assuming we get proper DRIVE approvals to move forward. 3/24/25 Update - No baseline vs FY25 required as the major costs and cost savings will happen in FY26. This project is still on track with all milestones in progress. 7/22/25 Update - All is on track with hiring and the end of the contract set for later this year. 8/5/25 Update - All is on track with hiring and the end of the contract set for later this year. Hiriing is in progress and should be done by 9/15 | I: L4 | Active | L4 | 2025-06-02 | 2026-01-30
Business Only Initiative: Treasury: Termination of ESPP (Employee Stock Purc | 16253 | 8779 | Business Only Initiative | SGA - Finance | SG&A | Matthew Daniel, Christian Lemon | On Track | 5/22/25 - Updating FY to FY25 per Domain Finance Guidance 3/20/25 - Confirmed rebaseline to FY25. Removed Forecasts and Cost for FY26 | K: L5 | Completed | L5 | 2022-12-01 | 2023-04-28
Business Only Initiative: Treasury: Termination of LEES contract | 16264 | 8782 | Business Only Initiative | SGA - Finance | SG&A | Jeffrey Lewis, Christian Lemon | On Track | 5/22/25 - Updating FY to FY25 per Domain Finance Guidance 3/20/25 - Confirmed rebaseline to FY25. Removed Forecasts and Cost for FY26 2/7/25 - PwC support for PMO team of Legal Entity End State was released in September of 2022. Value has been captured for over 12 months and actuals are updated through the end of FY25. No further actions. | K: L5 | Completed | L5 | 2022-10-31 | 2022-10-31
Business Only Initiative: Treasury: Reduction in cash management positions | 16272 | 8783 | Business Only Initiative | SGA - Finance | SG&A | Jeffrey Lewis, Christian Lemon | On Track | 5/22/25 - Updating FY to FY25 per Domain Finance Guidance 3/20/25 - Confirmed rebaseline to FY25. Removed Forecasts and Cost for FY26 2/7/25 - In-scope members of Cash Management positions have left FedEx and are not being backfilled. Value has been tracked for 12 monthes and Actuals are up to date through the end of FY25. No further actions. | K: L5 | Completed | L5 | 2022-11-30 | 2023-01-31
Business Only Initiative: Replace BOBI | 21071 | 8784 | Business Only Initiative | SGA - Finance | SG&A | Robin Raju, Christian Lemon | On Track | 5/22/25 - Updating FY to FY25 per Domain Finance Guidance 3/24/25 - Christian rebaselined forecast values to FY25. No further value to be captured. Initiative closed. Updated the L5 Date based on the updated Forecasted value. | K: L5 | Completed | L5 | 2023-08-01 | 2023-09-29
Business Only Initiative: Tax: U.S. Income Tax Compliance - Vendor Contract | 18040 | 8915 | Business Only Initiative | SGA - Finance | SG&A | Jamie Pourciaux, Amy Wolfe, Christian Lemon, Sherri Swindle | On Track | **5/22/25** - Updated Baseline FY to FY25 per Domain Finance instruction **3/24/25** - Rebaselined to FY25. No further value to be captured. Initiative closed. **2/13/25** - Updated Actuals through the end of FY25. No further actions required. Adding Christian Lemon and Sherri Swindle as back up IOs to update initiative. | K: L5 | Completed | L5 | 2022-09-16 | 2022-11-15
Business Only Initiative: Tax: TN Aviation Fuel Tax Savings | 27844 | 8917 | Business Only Initiative | SGA - Finance | SG&A | Pamela Lindsley, Lida M. McNeely | On Track | 03/31/25: FY25 Baselining complete. 03/03/2025: The TN Sales tax savings data will be available at the end of this week to calculate the monthly savings next week. 02/14/2025: Reviewed the monthly tax savings data. The TN sales tax cap of $1M was met on July 10th, 2024. The sales tax exemption certificate was provided to Valero for the time period of July 11, 2024 through June 2025. FedEx paid $1.139 in TN sales tax and has filed for a refund for the $139K. | K: L5 | Completed | L5 | 2022-07-01 | 2025-05-30
Business Only Initiative: Finance - International Accounting Process transfo | 3155 | 8994 | Business Only Initiative | SGA - Finance | SG&A | Christian Lemon, Kimberly Aven | On Track | **5/22/25** - Updated Baseline FY to FY25 per Domain Finance instruction **3/24/25** - Rebaselined to FY25. No additional value to be captured. Initiative closed. $8k expense in Feb 23 is the final billing for work performed in early December. All work stopped in early December, just final invoice for that work did not hit expense until February. | K: L5 | Completed | L5 | 2022-11-01 | 2022-12-16
Business Only Initiative: Apex – International Adoption | 17676 | 9004 | Business Only Initiative | SGA - Finance | SG&A | Esmeralda Arellano, Tiffany R. Moore, Joshua Croft | On Track | 04/08/2026 Updated actuals for EU and AMEA. 03/04/2026 Updated actuals & KPIs for EU & AMEA. 02/04/2026 Updated actuals for EU and AMEA. 01/12/2026 Updated actuals for EU and AMEA. Money step has been updated to complete and evidence has been added. Submitting to L4. 12/12/2025 Updated NRB value to match the baseline value/APEX annual audit fee benefit . 12/05/2025 NOV 25 actuals & quarterly KPIs for EU were updated 12/01/2025 Final wave went live and the AMEA roll out has been completed. MIlestone was updated today to complete. 11/11/2025 Entered actuals for Europe 472,622 and we have already surpassed the expected total for FY26. AMEA did not have any actuals for October but we expect November actuals to exceed the forecasted amount and will cover October. 10/10/2025 Entered September actuals 417,035 and most milestones have been completed. We are currently rolling out the AMEA regions. Wave one went live on September 23 and wave 2 will rollout on October 14. 9/11/2025 EU rollouts complete. Legal letter was approved. AMEA internal communication to be sent out on 9/22/2025 & AMEA vendor letters to be sent out on 9/24/25. 8/22/2025 Adjusted July EU actuals & EU forecasts due to invalid calculation. Adjusted AMEA actuals & forecasts to reflect spend. EU final Wave 3 scheduled for 9/2/25. All resources were obtained for AMEA & now awaiting legal approval for letter. 08/12/2025 Updated actuals for July EU recoveries. APEX has completed all audit prep for the AMEA regions. We have received the AMEA vendor list and are doing a final review. Letters and internal communications have been submitted to legal. KPI's will be updated quarterly. 07/31/2025 Updated dates for AMEA milestones to align with the pending timeline. A finalized timeline for the AMEA roll out is expected by mid-August. Letters for the AMEA regions are pending legal approval and meeting have been scheduled to review AMEA vendor lists. 07/25/2025 Wave two went live on Monday July 21st. All items are completed for the final EU wave on September 1st except for the vendor list. The vendor list will be reviewed and finalized in the first two weeks of August. The actuals for July have been entered and exceed the mark. Meetings have been scheduled with AMEA management to finalize the roll out dates. We will update once the dates have been finalized. AMEA resource date extended due to delays in AMEA countries. 07/14/2025 Wave 2 is set to go live on July 21st. Received internal communication translated to German & French for Wave 2 & Wave 3 go-live. Moving forward with AMEA Prep, communication has been received in Mandarin. 07/01/2025 Reviewing audit processes with AMEA team members and working to assemble the AMEA team contacts for each region. Pushed the AMEA resource completion date a month while working to determine contacts/resources for each region. The EU wave 1 launched and we are moving forward with wave 2 set to launch on July 21, 2025. 06/20/2025 Meetings have been scheduled with the AMEA teams to review and go over key items required to implement the audit. EU wave 1 roll out for July 1, 2025 is on track and all items have been received for implementation. 06/18/2025 Adjusted AMEA authorization letter dates due to delays in the AMEA go live dates. 06/13/2025 Received and reviewed vendor list for July 1, 2025 rollout. Received signed vendor letter for July 1, 2025 rollout. Recoveries are starting to come in for GBR & NLD. 06/06/2025 The international team received a few inquires after EU first two countries (GBR & NLD) go-live. Vendor list from next rollout on July 1, 2025 to be vetted. 05/30/2025 Due to delays in the EU launch the forecast amounts were updated to reflect the phased rollout. AMEA numbers will be updated once the phased rollout dates have been confirmed. The first two countries for the EU (GBR & NLD) will go live on June 2, 2025. Wave one is on track to rollout on July 1, 2025. Received signed letter and the vendor l | I: L4 | Active | L4 | 2025-01-02
Business Only Initiative: Finance - Paperless Communication (Pension, 401(k) | 3158 | 9005 | Business Only Initiative | SGA - Finance | SG&A | Renee Miller, Janet Phillippi | On Track | 03/25/2025: FY25 Baseline completed 03/03/2025: Savings is on an annual process. Next annual process will occur in December 2025. No updates until then. 02/17/2025: Initiative included both a 401k piece (annual estimated savings of 35k) and retiree health enrollment (annual estimated savings of 38k). Savings have been entered for 401k only. The FedEx retiree health plan is no longer available for enrollment effective 1/1/2025. Only the Retiree Health Premium Account (RHPA) remains and the RHPA was not part of the original initiative. 02/14/2025: Awaiting vendor billing for December compliance mailing 02/06/2025: Annual FY25 costs incurred are being gathered for input into Planview to evaluate savings (note: costs are incurred annually at end of calendar quarter) 01/29/2025: Connected with FedEx Hardware Support (HS) team. HS team is creating dashboard Retirement Services can run on demand to indentify employees wired at work and compare it to Vanguard listing of those who voluntarily signed up for electronic delivery. Once report is available, we'll evaluate return on investment to build integration to Workday to store indicator. Objective is to improve savings. 2024: Confirmed that Workday can store a Wired at Work indicator, however it would need to be updated via an integration into Workday in real time. 02/20/2023: 401(k) status on SAR mailing as of 2/20/2023: Received bills from Vanguard and updated attachment 2 to reflect actual savings. Goal was to increase number of pieces delivered electronically by 10% for a savings of $35,000. Actual improvement was 5% for a savings of $16,808. Next step: Code and submit for payment. Will also be submitting HR Technology Demand Intake Form requesting Wired at Work indicator within Workday that can be passed to vendor. Retiree Health care enrollment guide mailing as of 2/2/2023: The retiree health print savings will begin to be realized in FY24 and not in FY23 as originally planned. Previous to the process change, multi-page enrollment guides were sent to all eligible retirees (those participating in the program and those who had not enrolled in the program). The total population is 12,000+. Unfortunately, The vendor had already printed the retiree guides (12,000+) based on a direction that occurred before the process change and 12,000+ books were produced instead of 1,800. The over-run has been used for those eligible who retired after the open enrollment period, but nevertheless the savings weren’t realized for FY23. | K: L5 | Completed | L5 | 2022-09-01 | 2023-01-13
Business Only Initiative: Finance - Retirement Vendor RFP | 3159 | 9009 | Business Only Initiative | SGA - Finance | SG&A | Kristen Hawkins, Janet Phillippi | On Track | 5/21/25 -- Adjusted baseline fiscal year to FY25 per instructions from Finance. 3/21/2025 -- Confirmed rebaseline to FY25. 2/10/2025 -- Reviewed FY25 financials and pre-filled actuals through the remainder of the FY. No additional actions are needed nor anticipated for the initiative other than to continue tracking the benefits. | K: L5 | Completed | L5 | 2022-10-31 | 2023-03-01
Business Only Initiative: Anomalous Airbill Review Automation | 3171 | 9010 | Business Only Initiative | SGA - Finance | SG&A | Judith Peterson, Auta Toney | On Track | We have updated the impact for September per discussion with Finance. The automation of AAR allowed us to take on an additional project (Daily Balancing) which had previously been performed by a contractor. The contract was terminated in April 2023. To properly reflect the savings from this contract, we recalculated the savings as follows: Contractor monthly rate x 5 months (May-Sept) = $14,400 x 5 = $72,000 Less: Savings previously recorded May-August = $1560 x 4 = 6,240 Savings recorded in September = $65,760 / $1M = .06576 Savings to be recorded from October going forward = $14,400 / $1M = .0144 | K: L5 | Completed | L5 | 2022-12-01 | 2023-02-10
Business Only Initiative: Tax: Compliance Savings Post One FedEx | 93737 | 9049 | Business Only Initiative | SGA - Finance | SG&A | Hannah Brown, Andrew Watkins | On Track | 3/12/25- Canada milestone no longer valid to project. 3/4/25-no current updates. 2/26/205-Met with different cosourcers to determine onboarding Canada reutnrs. 2/18/25-currently viewing potetial cosource providers for returns, progress towards L5. 2/12/25- No current updates at this time. 2/4/25- Currently awaiting final details for the Canada milestone to be complete to move initiative forward. We are on track to meet the last milestone by the due date and all financials are current. | K: L5 | Completed | L5 | 2024-07-01 | 2025-05-30
Business Only Initiative: Tax: Property Tax PTMS Rollout | 16593 | 9051 | Business Only Initiative | SGA - Finance | SG&A | Pamela Lindsley, Andrew Watkins | On Track | 03/31/2025: FY25 Baseline complete. 03/03/2025: All work is complete. Tracking value. 2/14/2025: All work has been completed. Tracking value for the next few months. The implementation of the PTMS software has occurred allowing us to release the OSV. Robert Half was notified in that the OSV would be released and no future OSV would be needed for this task. The OSV returned the FedEx equipment and badge on August 16, 2024. | K: L5 | Completed | L5 | 2022-09-01 | 2024-08-30
Business Only Initiative: Terminate Tradeshift | 6471 | 9055 | Business Only Initiative | SGA - Finance | SG&A | Jay Jeffers, Andy Beavers | On Track | 3/21/25 - Confirmed rebaselined to FY25. 11/13: Update IO to enter actuals for L5. | K: L5 | Completed | L5 | 2022-11-15 | 2022-12-30
Business w/ Tech Initiative: Tax: FXG Trimble Vusion Project | 16591 | 9290 | Business w/ Tech Initiative | SGA - Finance | SG&A | Alexandra Buechner, Andrew Watkins, Pamela Lindsley | On Track | 4.11.26 Cleared March 2026 forecast. The project remains delayed. 3.10.26 Cleared February 2026 forecast. The project remains delayed. There has been no significant change in the primary constraints identified in January. ELD device naming inconsistencies and equipment file data issues continue to limit the ability to reliably map GPS data to valid FedEx asset IDs. 2.9.26 Cleared January 2026 forecast. The project remains delayed. There has been no significant change in the primary constraints identified in January. ELD device naming inconsistencies and equipment file data issues continue to limit the ability to reliably map GPS data to valid FedEx asset IDs. 1.12.26 Cleared December 2025 forecast as requested by finance. The project remains delayed as data validation and parallel testing activities continue. The primary challenges continue to be ELD device naming inconsistencies and equipment file data issues, which limit the ability to reliably map GPS data to valid FedEx asset IDs. ELDs are frequently named using non-standard identifiers, while the equipment file contains missing, renumbered, or incomplete records, resulting in a high volume of ambiguous or non-reportable assets. These conditions require ongoing manual review and exception handling and continue to constrain automation, data completeness, and testing timelines. 12.12.25 Cleared November 2025 forecast as requested by finance. The project continues to experience delays. 12.1.25 The project remains delayed, with Go-Live targeted for June 2026 and parallel testing planned for January/February 2026. Integration with Motive continues to present significant challenges: Snowflake data retrieval performance is unacceptable, requiring compute size increases and query optimization; Motive’s two-day data lag disrupts start-of-month processes; and late-arriving records (e.g., 40,000 October entries surfaced weeks after month-end) introduce risk of duplicate travel and inaccurate tax calculations. Vusion has proposed using bulk mileage from FedEx supplemental files for October and possibly November to maintain 4Q comparison timelines while Motive issues are resolved. Additional data quality concerns persist, including Canadian kilometers requiring conversion to miles, missing timestamps in fuel transactions, and inaccurate IFTA reportable flags in the asset file. VPN setup for secure data exchange is still pending. These issues must be addressed before full automation and reporting can proceed. 11.5.25 Cleared October 2025 forecast to maintain compliance with actuals entry policy. The project remains delayed, with Go-Live now targeted for June 2026 and parallel testing planned for January/February 2026. Several data quality issues have been identified, including inconsistencies in the equipment file such as duplicate vehicle entries, missing vehicle records, and invalid or incomplete data fields impacting downstream validation. Duplicate dates were also discovered in the supplemental miles file for August 28 and September 21, and the team is investigating the source of these duplications. In addition, Canadian miles are being reported in kilometers instead of miles, requiring conversion and standardization. Verification of file generation processes and data consistency across jurisdictions will be needed to support accurate reporting prior to go-live. 10.7.25 Cleared September 2025 forecast to maintain compliance with actuals entry policy. The project remains delayed, with the Go-Live now targeted for January/February 2026. As project work continues to focus on data validation, integration testing, and API development, there were no financial activities driving actuals in September. The financial timeline will continue to be reviewed in alignment with the revised project schedule. The Enterprise KPI selected is Expense as % of Revenue, as this initiative supports enterprise efficiency through automation of fuel and mileage tax data and reporting, improving accuracy | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-05 | 2026-12-08
Business Only Initiative: Tax: Expand Vendor Billed Sales/Use Tax Analysis | 17385 | 9346 | Business Only Initiative | SGA - Finance | SG&A | Andrew Watkins, Pamela Lindsley | On Track | 4.18.25 Actuals updated for March activity 3.21.25FY25 rebaseline updated FY26-FY28 to 0. Milestone updates: 18332 Novita 6b go-live postponed until July by EBS to allow additional testing and adjustments post 6a. 21671,21672,21673,&21675 start delayed as a result of 18332. These milestones require input from EBS resources assigned to Novita implementation efforts. 2.11.25 Project in L5 since August 2024. Variations between actual and forecast tax savings result from timing of underlying IT contract purchases. Initiative continues to deliver projected savings on annualize basis. Projected $5-10M; FYTD actual $8M. 3.7.25 updated finanicals with actuals for February activity | K: L5 | Completed | L5 | 2022-11-01 | 2024-12-31
Business Only Initiative: EU - Outside Service Cost Reduction - A&C - CBS | 18086 | 9383 | Business Only Initiative | SGA - Finance | SG&A | Olivier De Waele, Laurence Maitrejean, Caroline Bosch | On Track | -**2025 March 26- Re-baselining to FY25 is complete. ** -2025 week 10 (March 7)- financial updated, on track for L5 -2025 week 9- No further updates -2025 week 8- No further updates -2025 week 7 - Updated monthly financials - 2025 week 6 - No updates -- update Sep 2024 -- All OSVs in scope exited for more than 3 months. Submitted for L5. -- update Jul 2024 -- L5 forecast date updated to Sep 2024, 3 months after L4. -- update Jun 2024 -- Final 2 OSVs exited on May 31st, 2024. --> submitted to L4. -- update Sep 2023 -- Money step has been pushed to June 2024. However, financial impact is limited. We had to extend a couple of OSVs until end of CY23 and a few more until June 2024 to cover for COE open positions that we have not been able to recruit yet and for long term absences (e.g. maternity leaves). The small overrun on this initiative is partially offset by the COE open positions that have not been backfilled and the long term absences whose S&W were included in BP24. -- update June 2023 -- FY24 actuals are at BP24 rate. FY23 actuals (and plan) are at BP23 rate. -- update April 2023 -- Due to small delays in recruitment of our permanent COE positions (mainly BE & FR), we had to extend 2 OSVs towards end of CY23. We therefore anticipate a small reduction of our projected savings for FY24 (estimated to approx. $0.5m so currently). #impact 18087: FY23 actuals are at BP'23 FX rate, FY24 actuals are at BP'24 FX rate. | K: L5 | Completed | L5 | 2022-10-03 | 2024-06-28
Business Only Initiative: EU - Russia A&C Wind down - CBS | 18098 | 9387 | Business Only Initiative | SGA - Finance | SG&A | Olivier De Waele, Laurence Maitrejean, Caroline Bosch | On Track | **-2025 March 26 - Re-baselining against FY25 is complete.Initiative should be closed** --- status update Nov 9th, 2023 --- Confirmed with local manager that all exits have completed effective July 2023 (earlier than plan). --> submitted for L4. ---------------------------------------- FY24 actuals are at BP24 FX. FY23 actuals are at BP23 FX rate. Completed 16 out of 17 exits as of May 31st, 2023. Final exit will take place in Nov 2023. Actual severance will slightly exceed plan ($50k impact) due to fringes recalculation. | K: L5 | Completed | L5 | 2022-11-01 | 2024-07-22
Business Only Initiative: APAC - A&C FTEs reduction - CBS | 18107 | 9389 | Business Only Initiative | SGA - Finance | SG&A | Darshak Raimangia, Laurence Maitrejean, Caroline Bosch | On Track | **-2025 March 26 - Re-baselining to FY25 is complete. Initiative should be closed. ** FY24 actuals are at BP24 FX rate. FY23 actuals are at BP23 FX rate. Completed all FTEs exits/transfers as of Jul 31st, 2023. Money step completed. | K: L5 | Completed | L5 | 2022-10-03 | 2024-01-01
Business Only Initiative: EU - Deloitte FS preparation fees reduction - CBS | 18121 | 9392 | Business Only Initiative | SGA - Finance | SG&A | Olivier De Waele, Laurence Maitrejean, Caroline Bosch | On Track | **-2025 March 26 - Rebaselining to FY25 is complete - initiative should be closed. ** -- Dec'23 update -- Deloitte FS production contract has been terminated. FY22 FS final fees are under negotiation. Total impact will be < EUR 20k (confirmed with Deloitte). On basis of the above, initiative is being submitted for L5. -- Sep'23 update -- • Deloitte FS production contract has been terminated. We can confirm that: oDeloitte will not perform any work related to FY23 (work carried on in FY24). oAny work related to FY22 FS production (in FY23) should have been accrued for at this point. Not all invoices have been received but amounts have been aligned with Deloitte. oLEES project completion – will be done end of CY23. However, LEES remaining work has been absorbed in-house for FY24 and Deloitte is not engaged anymore. Hence, remaining LEES countries are not impacting this DRIVE initiative -- July'23 update -- on track FY23 actuals not traceable to GL. However, we confirmed the total annual cost with the vendor. This is currently confirmed at EUR 221k for FY23, excluding overruns. We believe overruns should not exceed EUR 65k (in line with previous years). | K: L5 | Completed | L5 | 2022-11-01 | 2024-01-31
Business Only Initiative: Tax: Bringing Thomson Reuters Loan Staff Work in H | 18214 | 9398 | Business Only Initiative | SGA - Finance | SG&A | Marina Wirtz, Misty Arinder | On Track | No descrepencies between actuals and forecast. Everything is on track. | K: L5 | Completed | L5 | 2023-02-07 | 2023-05-31
Business Only Initiative: Tax: OneSource Intercompany Agreement License Tool | 18217 | 9403 | Business Only Initiative | SGA - Finance | SG&A | Marina Wirtz, Misty Arinder | On Track | No descrepencies between actuals and forecast. Everything is on track. | K: L5 | Completed | L5 | 2023-02-07 | 2023-05-31
Business w/ Tech Initiative: Enterprise Costing Model Development | 90211 | 9457 | Business w/ Tech Initiative | SGA - Finance | SG&A | Andrew Veal, Derrick Robertson | On Track | 09/15 Financials updated including partially updated CY26 and beyond. More information tbd on CY26 impact as project has been extended. 07/25 On track with continued model development. 07/18 Actuals for June updated with the exception ofOutside Service Contracts, awaiting confirmation from Dataworks on Azure billing expenses. Initiative on track with continued model development and increased project management. 07/10 Actuals for May and before updated, June expected on July 16th 05/15/2025 PPM # confirmed as 545926 04/14/2025 Updated with new costs. 03/31/2025- Rebaselined to FY25, no cost value changes, category field corrected from "reoccuring" to "one time". 03/14/2025- This initiative is expected to move to L3 by end of April. As part of a solution review another Portfolio may need to be added prior to submission. The team is reviewing the solution option to confirm prior to submitting for L3. PPM # also confirmed as N/A. 03/06/2025- On track for first P&D model development Leadership approvals gained | G: L3 | Active | TEMP L3 - Enter L3 | 2024-10-15 | 2026-12-31
Business Only Initiative: LAC OSC Reduction Target $3.06M | 88238 | 9476 | Business Only Initiative | SGA - Finance | SG&A | Benjamin Alexander, Darren Cantrelle | Some Issues | 3/13/2025 - no help needed nor blockers preventing progression. Reviewed entries and updated structural vs volume to "N/A" per guidance from finance. Additionally listed all benefits as one time and updated Exit Rate to 0 to match classification of benefits as one time. Submitting for L5 approval 5/19/2025 - Current progress indicates the initiative is most likely going to fall short of the goal by approx. $500K. | K: L5 | Completed | L5 | 2024-09-02 | 2024-10-01
Business Only Initiative: Tax: Potential VAT saving by offsetting LSF agains | 82858 | 9535 | Business Only Initiative | SGA - Finance | SG&A | Yi-Hui Chen, Blven Chan | On Track | 6 Feb 2025: We have consulted with local tax advisors on what kind of supporting documents that may be required, to support this TP policy change in case there is any challenges from tax authorities. Tax advisors suggested to have a memo prepared at central level to demonstrate the benefit/rationale from this change. We are checking with central team how to prepare such memo. 13 Feb 2025: We are still following with central team on the memo. Target to reach L3 when the memo is prepared. We will try to prepare the memo and reach L3 in March 2025 5 Mar 2025: We haven't received central team's feedback about the memo. We sent the follow up today. 27 Mar 2025: We've submitted the initiative to L3. We are not able to re-baseline FY25 since currently the initiative is not editable. We will re-baseline FY25 by zero out all forecasts on and after June 2025 after the initiative is editable. 19 Apr 2025: We've submitted the initiative to L4. We are not able to update the actuals for March 25 now. The actual tax saving for March 25 is USD35,772. 26 May 2025: We've drafted the internal memo and shared with central team on 15 May 2025, and waiting for central team's comments to finalize the memo (the supporting documents for this TP policy change). We will keep following up with central team for the finalization comments. 11 Jun 2025: We've finalized the internal memo on 9 Jun 2025. 4 Nov 2025: Since the memo is finalized, no further action is required and the initiative is treated as completed. | K: L5 | Active | L5 | 2024-03-01 | 2025-06-02
Business Only Initiative: 401(k) Vanguard Recordkeeping Fee | 29937 | 9560 | Business Only Initiative | SGA - Finance | SG&A | Renee Miller, Janet Phillippi | On Track | 05/16/2025: No update for April or May. Fees are billed quarterly based on the headcount at the end of the calendar quarter. The next bill will be received in July 2025, for the period April through June 2025. 03/25/2025: FY25 Baseline completed 03/03/2025: Savings are on a quarterly cycle. No more updates until next quarterly billing from Vanguard (CY Q1 will be billed in April). 02/14/2025: Fees are assessed quarterly. Savings continue to be higher than expected due to lower non-package handler head count compared to benchmark that was based on March 2023 average headcount for previous 12 months. Note: Spin-off of Freight will bring fees down further (37000 ees * $14/head = $518k). 02/06/2025: Continue to realize savings at higher rate than forecast due to decreases in headcounts (FedEx is charged a recordkeeping fee based on the number of active participants in the plan at the end of a calendar quarter). Note: recordkeeping fees associated with the package handlers are captured in the 401k Package Handler Alignment enabler. Legacy Ground package handlers were added to the plan 6/1/2024. Initiative is currently in L5. 11/20/2024: Updated to reflect quarterly expense instead of monthly. Vanguard bills on a quarterly basis, therefore actuals are not known on a monthly cadence. | K: L5 | Completed | L5 | 2023-01-02 | 2023-09-29
Business Only Initiative: CBS-2024 Retiree Health Benefit Changes | 30959 | 9561 | Business Only Initiative | SGA - Finance | SG&A | Kristen Hawkins, Lon Maynard | On Track | 5/21/25 -- Adjusted baseline year FY25 per instrcutions from Finance. 3/21/2025 -- Confirmed rebaseline for FY25. 2/10/2025 -- Reviewed FY25 financials and pre-filled actuals through the remainder of the FY. No additional actions are needed nor anticipated for the initiative other than to continue tracking the benefits. | K: L5 | Completed | L5 | 2023-05-30 | 2023-10-13
Business w/ Tech Initiative: Revenue Planning - International |  | 87392 | Business w/ Tech Initiative | SGA - Finance | SG&A | Salina Xu, Balaji Ramanathan | On Track | 4/3/26 Received request from Jacob Kellogg to upload Deloitte resources costing extension to Jan. 2027 vs previous Jun. 2026, due to contract extenstion request from Saurav Mohanty, by adding additional $250K 3/19/26 Updated Feb. forecast error % 2.12% based on Intl net revenue w/o fuel 3/2/26 Update: EU SAS migration is still ongoing and is expected to take longer to complete - the development of the EU data pipeline in FIP/CDP will be delayed -EU SAS migration timelines were further delayed due to changes in the design and approach. -As per recent updates, the data migration from EU to CDP including SAS processes is targeted for June 2026. -Post processed files (Step 1) from EU to CDP are made available from March and will be tested/validated for consumption in FIP. Develop consumption architecture on FIP/Atlas for multiple stakeholders – currently we have established this for Finance team. However, we would need to extend this to P&E teams as well as commercial teams in the US and other regions. -An initial assessment of the international tables, data structures and functional stakeholders has been completed. -As next steps, start designing or updating data pipelines to ingest and standardize the international datasets from FIP to ATLAS -Flash and Reporting enhancements are in progress 2/19/26 Updated Jan. forecast error % 0.31% based on Intl net revenue w/o fuel in Jan'26 1/12/26 Updated Dec. forecast error % actuals -3.16%, based on Jan. 12 billing actuals 11/28/25 Team is working on Flash enhancements, end to end automation and validation framework, and Step 3 for AMER 11/3/25 Flash reporting site went live successfully, team is working on Flash enhancements, end to end automation and validation framework, and Step3 (getting data from the authoritative sources) for AMER, and team is starting to work on EU Migration 10/6/25 We are approved to move to L3 9/30/25 Moving to L2 was approved by Neil and we are working on L2 moving to L3 documents 9/19/25 Met with EPM team to have Architectural document uploaded to Repository and will meet with QA expert on QA review next Monday 6/6/25 Americas launched, RoW will be launched in September 2/14/25 Actively engaged with the regional teams in AMERICAS, reviewing the baseline results 2/5/25 Checked with Finance contact on some of the sections on L1 LBC form, form sent to management for review. Once it's approved, we'll submit in Planview for approval 1/21/25 Working on L1 LBC form. Once it's finalized, we'll submit for approval. The Initiative is to change the way we do forecasting/planning, and our measurement is forecast accuracy, not on $ savings 1/7/25 Adding Salina as the Back up Initiative Owner | G: L3 | Active | TEMP L3 - Enter L3 | 2026-04-06 | 2026-08-31
Business w/ Tech Initiative: Revenue Planning - Domestic |  | 87396 | Business w/ Tech Initiative | SGA - Finance | SG&A | Salina Xu, Amala Annapureddy | On Track | 4/3/26 Received request from Jacob Kellogg to upload Deloitte resources costing extension to Jan. 2027 vs previous Jun. 2026, due to contract extenstion request from Saurav Mohanty, by adding additional $250K 3/18/26 Dom Express net revenue w/o fuel for Feb. 2026 forecast error% updated -6.2%, Ground netreve w/o fuel forecast error% for Feb. 2026 -0.9% 3/2/26 Update : The Ground Rating Modernization project is an upgrade of Ground rating to a brand-new system. The implementation has been delayed to an optimistic mid-March completion. This change requires a complete redesign and redevelopment of the current data pipeline set up for Ground in Revenue Planning platform, which is expected to be accomplished in three steps: 1.Converting the Accounting actuals accounts to pickup/deferral based instead of the current delivery/in-transit based approach. This conversion is well underway, with alignment with Accounting, Core Data, EPBCS, and Reporting teams regarding data pipeline flows and calculations. The current status is that the teams have completed most of the steps; however, issues are anticipated as data will not be available for testing until after GRM goes live. 2.Ingesting data sourced directly from GRM daily. This step is not as urgent since GRM will be populating current data tables within EIW, but the conversion to the new sources will make rated actuals available closer to a one-day lag like Express instead of the weekend-only lag of the current rating system’s feeds. 3.Revising reports and analyses to take advantage of the shorter lag time of data completion. Develop consumption architecture on FIP/Atlas for multiple stakeholders – currently we have established this for Finance team. However, we would need to extend this to P&E teams as well as commercial teams in the US and other regions. -An initial assessment of the international tables, data structures and functional stakeholders has been completed. -As next steps, start designing or updating data pipelines to ingest and standardize the international datasets from FIP to ATLAS -Flash and Reporting enhancements are in progress 2/16/26 Dom Ground KPI updated with 1.1% for Jan actual 2/12/26 Dom Express KPI udpated and Dom Ground will be updated next week when available 1/23/26 Dom Ground KPI updated with -2.1% for Dec. actual 1/12/26 Dom Express KPI updated and Ground won't be available until 1/19/26, will update by then 12/15/25 Updated Ground KPI forecast error -4.2% 12/10/25 Ground KPI forecast error will be available on 12/15/25. Will update by then. 11/28/25 Team is working on Flash enhancements, end to end automation and validation framework, and Step 3 for FXD and FXG 11/17/25 Ground KPI forecast error for Oct. was updated to 0.8% 11/11/25 KPI actual reporting for Ground: there is one month lag due to data availability, so, for Nov. 13 report, we are reporting the fcst number (5%) as the actuals and once the actuals available, we'll update 11/3/25 Flash reporting site went live successfully, team is working on Flash enhancements, end to end automation and validation framework, get data from the authoritative sources for Dom Express and Ground, start to work on GRM(Ground Rating Modernization) 10/6/25 L2 was approved and we are moving to L3 9/30/25 Moving to L2 was approved by Neil and we are working on L2 moving to L3 documents 9/19/25 Met with EPM team on moving to L2 and got Architecture Alignment document uploaded to Repository. Will meet with QA expert next week for review 7/23/25 Removed FXF from scope per email from Tara Sciulli on FXF separation from FedEx 6/6/25 Initiative was launched 2/5/25 Checked with Finance contact on some of the sections on L1 LBC form, form sent to management for review. Once it's approved, we'll submit in Planview for approval 1/21/25 Working on L1 LBC form. Once it's finalized, we'll submit for approval. The Initiative is to change the way we do forecasting/planning, and our measurement is forecast | G: L3 | Active | TEMP L3 - Enter L3 | 2025-12-15 | 2027-01-29
Business w/ Tech Initiative: Data Archiving IT Solution with MACRO4 |  | 88689 | Business w/ Tech Initiative | SGA - Finance | SG&A | Kavita Singh, Baptiste De Dree, Danielle Gwin Allen | On Track | Business Case prepared and submitted for L2 | E: L2 | Active | L2 | 2027-03-30 | 2027-03-30
Business Only Initiative: LAC EE 2.0 T&E Reduction |  | 88798 | Business Only Initiative | SGA - Finance | SG&A | Benjamin Alexander | Some Issues | 3/13/2025: No help needed nor blockers preventing progression. Reviewed entries and updated structural vs volume to "N/A" per guidance from finance. Submitting for L5 approval. 5/19/2025: Based on rate of spend in Mar and Apr for critical business activities, this intiative is unlikley to reach goal and could fall short by $700K to $1M. | K: L5 | Completed | L5 | 2025-01-31
Business Only Initiative: Tax: Sales/ Use Software Tax Exemptions |  | 92823 | Business Only Initiative | SGA - Finance | SG&A | Andrew Watkins, Hannah Brown | On Track | 1.13.26 Evaluating scope increase to utilize Power Platform for technology enhancements including automation and staff efficiencies. 10.1.25 Internal meetings planned for October include review of Accenture Demand Intake Process. Will work to capture required tax data elements in the tool. 6/2/25-attened QA review with JJ and Amanda and appears ready to move to next stages. 4/23/25-Review L2 with leadership and ready for submission. 3/25/25-Under L2 review. 3/12/25-submitted to L2, business case submitted. 3/4/2025-no current updates. 2/26/2025- finalizing KPI's for business case. 2/18/25-Waiting on approval for business case, working on milestones. 2/12/2025- Project is waiting app/roval for business case, submitted to L2. 2/4/25-Project iniatiing/ no current updates avaliable. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-01 | 2026-08-31
Business Only Initiative: Tax: Memphis Hub Modernization Tax Exemptions |  | 92826 | Business Only Initiative | SGA - Finance | SG&A | Andrew Watkins, Hannah Brown | On Track | 1.14.26 Placing effort on hold pending BOD approval. If approved and successful in obtaining tax exemptions, will reactivate and update financials scope for potential of $60M in hard savings benefits. 1.13.26 ECommerce building project BOD review/approval mved to March 2026. If approved, working with Government Affairs for legislation to result in building material exemption from sales/use tax. Separately will work with TN department of revenue for industrial machinery exemption from sales/use tax and TN income tax industrial machinery credit. 11.1.25 SPSS building refresh vendor (Beumer) calculated tax refund. $357K will be refuned to FedEx by Beumer as the tax was yet to be remitted to state of TN. An refund claim will be filed by Beumer with state on behalf of FedEx for additional $733k. Total P&L hard savings of $1.090M 10.1.25 Received exemption approval from TN Dept of Revenue for SPSS building refresh clearing the way to file for refunds of taxes paid, expected in range $1M-$2M (hard savings). Avoid prospective tax paid in range of $4M-$5M (soft savings). 10.1.25 ECommerce building project planned to go for BOD approval in September has been pushed back until December. 3.12.25 Entered project milestones 3.12.25 Entered project financials 3.12.25 Uploaded business case template 3.12.25 A review of active and projected hub projects along with tax research identified additional savings opportinities. Uploaded business case provides addiitonal details. Variance L1 vs SL3 of $90M summary increase in hard & soft savings: - L1 NRB $10M savings-$1M hard; $9M soft -SL3 $100M savings; hard (one-time) $4M FY26, hard (recurring) $9M FY27-; soft $60M FY25-FY30 Project initiating no updates available @ 2.4.25 | E: L2 | On Hold | L2 Feedback Requested | 2024-07-22 | 2026-04-01
Business Only Initiative: Bank of America (BOA) Bank Fees |  | 92941 | Business Only Initiative | SGA - Finance | SG&A | McCager D. Garner | On Track | 2/12/2025: Insert has been passed to ADP. Will be included in the 2/25 hourly run. Program will be active starting 4/1. 1/23/2026: No checks have been presented to a non-BOA bank since December 2024. Volume has been steadily decreasing since May 2024. After speaking with the team on 1/23/26, we agreed to cancel this request. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Wisely Paycards for Domestic |  | 94153 | Business w/ Tech Initiative | SGA - Finance | SG&A | McCager D. Garner | On Track | 1/23/2026 FXO and FSC pilot project slated to go live 2/2/26. FEC launch likely to be pushed beyond the April 2026 initial go live date. IT gathering requirements for L2 Architecture planning and scheduling. 7/21/2025 Changes made as suggested: L1 Net Recurring Benefits - Soft value has been deleted and moved into the Target Value number 7/15/2025 LBC completed in May. QA reviewed 7/11 and approved moved to L2. Pilot with Supply Chain and Office movine forward. 3/7/2025 ADP Wisely contract was signed 2/27/25. 2/11/2025 All parties have agreed to the contract language. Pending awareness conversations to be had before asking Legal to sign contract. | E: L2 | Active | L2 | 2025-10-01 | 2026-03-30
Business w/ Tech Initiative: LAC_BR_BDE_BRECO_EBS_Requirements_Alignment |  | 106245 | Business w/ Tech Initiative | SGA - Finance | SG&A | EVELLYN OLIVEIRA, Arthur Tavares Mattos, Sandra Parras | On Track | 01/06/26 - The initiative remains On Hold while we await formal confirmation regarding the potential discontinuation of Domestic operations in Brazil. Since this initiative (BDE/BRECO – EBS Requirements Alignment) is directly related to Domestic processes, proceeding without confirmation could result in rework or misalignment with the future operating model. No execution activities are currently blocked; the pause is a strategic decision to ensure alignment with business direction. Once the Domestic scope and operating model are officially confirmed, the initiative status will be reassessed and updated accordingly. 09/11/2025 – Status Update – Initiative We are still awaiting the submission of the appropriate architectural documentation from EPM, as previously requested. No resubmission to SL2 will take place until this documentation is received. In the meantime, we have reviewed the Enterprise Demand Prioritization dashboard and our initiative remains positioned as follows: Ranking with Domain: 39 Enterprise Ranking: 498 We will continue monitoring the status and provide updates once the documentation is available. 08/18/2025 - Status Update – Initiative We are currently awaiting the submission of the appropriate architectural documentation from EPM, as previously requested. No resubmission to SL2 will be done until this documentation is received. In the meantime, we have reviewed the Enterprise Demand Prioritization dashboard and our initiative is currently positioned as follows: Ranking with Domain: 39 Enterprise Ranking: 498 We will continue monitoring the status and provide updates once the documentation is available. 05/16/2025 - These figures were developed based on business logic, operational assumptions, and typical FedEx system performance. They reflect the intangible but measurable value brought by the project, particularly in terms of risk mitigation, revenue protection, and efficiency. ✅ Total Annual Soft Benefit: USD 3,600,000 Revenue Protection: USD 3,420,000 Assumption: Prevention of potential revenue leakage of 2% on USD 171 million. Calculation: 2% * 171,000,000 = 3,420,000 This represents avoided losses due to billing gaps or process inefficiencies, now addressed through system improvements. Compliance Risk Avoidance: USD 100,000 Assumption: Estimated value of regulatory fines or penalties avoided through improved auditability, tracking, and data governance. These improvements reduce exposure to non-compliance events. Operational Efficiency: USD 80,000 Assumption: Avoided cost of hiring 2 FTEs (Full-Time Equivalents), each at USD 40,000/year. Calculation: 2 * 40,000 = 80,000 The automation and streamlining of processes reduce the need for additional headcount. ✅ One-Time Soft Benefit: USD 260,000 Assumption: Avoided revenue leakage from delayed or missed billing of AWBs (Air Waybills). With enhanced AWB tracking, the system ensures timely invoicing and revenue capture that would otherwise be missed due to manual gaps. 05/13/2025 - The Finance scope of the BDE/BRECO initiative focuses on preserving USD 171M in annual recurring revenue, as outlined in the PNL. This is the baseline value and key financial impact for Finance, with no incremental gains expected. The estimate reflects current inefficiencies and the need for automation to avoid higher operational costs. Without automation, manual capacity would need to double to sustain operations. While no direct cost savings are projected, the initiative supports continuity, scalability, and compliance risk reduction. Migration impacts are tracked separately under project PV 103177. 09/04/2025 - Will have a call tomorrow with Frederico from Brazil Finance team, to get the information from the pending fields: - Baseline Value - Target Value - Measure & Unit - Net - Recurring Benefits (FY'28 Exit Rate, Annualized) - One-time Benefit and Implementation Cost 04/03/2025 - The following fields cannot be filled yet as we are awa | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Currency Code Request XCG for Curacao/St Maarten |  | 106783 | Business w/ Tech Initiative | SGA - Finance | SG&A | Noellia Sanchez, Margarita F. Neira, Giarelli Pieters | On Track | 5/7/2025 - Had QA review meeting with Amanda V and JJ G. Submitting to SL2. 4/10/25 - Met with EE PM to gain understanding Planview process and lean business cases. Revised certain entries per their suggestion, next steps is creating lean business case based on new understanding. ETA for bsuiness case is by 4/17/25 | G: L3 | Active | TEMP L3 - Enter L3 | 2026-04-13 | 2026-07-28
Business w/ Tech Initiative: PCRS - Network 2.0 features |  | 106786 | Business w/ Tech Initiative | SGA - Finance | SG&A | Daniel Pelichek, Loveena Goel | On Track | Initiative was replaced by another given progress with development of upstream systems | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Surface Courier Expense Model |  | 106898 | Business w/ Tech Initiative | SGA - Finance | SG&A | Justin Conley | On Track | 03.02.26 Cancelling request per Planview Support guidance. Project is complete. 01.15.26 Trying to complete changes requested by Planview support. 01.05.26 November 2025, this project has been completed. Initial scope vendor work and employee work is complete. EPBCS model can be accessed here with permission: https://fxgrevfld-fdxepm2.epm.us-ashburn-1.ocs.oraclecloud.com/HyperionPlanning/vb/index.html?page=ecvbs-v2&ecvbs-v2=efs&efs=efs-start&efs-start=blank&efsLandingPage=CST_CL_38%7ECST_CA_296&isHomePage=false Azure data exists within FIP at portal.azure.com in workspace eus2-fip-fin-kpi-prod-dbw 09.18.25 - Still waiting for approval emails to attach to ESPM request to change this initiative from OneFedex to Global Capabilities Strategy. The IMAGE issues with FIP that have occured over last 2 weeks are causing a 2-3 week delay for this project. 08.15.25 - Still waiting for approval emails to attach to ESPM request to change this initiative from OneFedex to Global Capabilities Strategy 07.22.25 - Still waiting for approval emails to attach to ESPM request to change this initiative from OneFedex to Global Capabilities Strategy 07.10.25 - Need ESPM approval to change from OneFedex to Global Capabilities Strategy. PDSM ticket 031202970 opened in June. 06.19.25 - Initiative downgraded to L1. Trying to edit to align with new Drive requirements. 05.13.25 - Working with vendor so they understand the ask. Refining the requirements documents. Determining exactly what math needs to be done by the tools. Trying to change FIRST # from 7245 to 5075 per Shaun's request. 04.23.25 - Impact Assessment connected to this initiative. This initiative allows for the creation of some I.T. tooling. Once complete it will: *Automate curation of actuals which is currently done manually in Excel. This initiative will combine more data that is at a much higher detail grain than current manual process. There will be orders of magnitude more data related to Express station operations in FIP (Financial Insights Platform) as it will curate and combine facility level info from FAMIS, the General Ledger, payroll, and revenue science *Generally automated transfers of data between systems. From raw sources into FIP for curation, to curated actuals in FIP out to FP&A cube and to FEC cube. It will also transfer forecasted dollars, that are tied to KPIs, from FIP Azure to FP&A & FEC cubes *Variance Analysis (VA) tools that show expense dollar impact of changes to operational KPIs, such as “X change in courier stops per hour results in $Y more/less expense for the time period Z” *Actuals and forecast will be tied to Revenue Science’s marketing volume automatically forecast for all Ground and Express product that are either picked up or delivered in US or Canada *Forecasts will accurately allocate forecasted marketing volume between the courier and contractor cost models within Surface minimizing duplicate or missing volume *All of Surface Finance will be better aligned around OneFedex, Network 2.0, and Drive changes *Finance will be able to speak to layers of KPIs and expense within the forecast, aka the impact of N2.0 changes, OneFedex changes, or Drive changes as they are layered into the forecast *Financial analysts will spend less time manually gathering, curating, transforming, transferring, and verifying actuals and forecasts and instead be able to spend that time analyzing and explaining forecasts and results * 04.17.25 - Data and AI review occured on 04.16.23 by Business and Technology Strategy. Dataworks stated that this initiative has an exemption for the Impact Assessment document. Financials updated. FIRST request is asking for input that can only be provided by IT. SSCT request approved in SSCT system. IT says this request needs to stay as Business with Tech. 04.08.25 - Initiative Supporting Architecture Documentation link should be: https://myfedex.sharepoint.com/:f:/t/EnterpriseArchitectureCommonRepository/ErTAL9OAz6tAuvA5s7NZvD0B | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: TMS-EBS retirement LACBR system replacement |  | 107117 | Business w/ Tech Initiative | SGA - Finance | SG&A | Arthur Tavares Mattos, EVELLYN OLIVEIRA | On Track | 12/12/25 - initiative needs to be cancelled 05/16/2025 - The initiative is currently focused on defining the replacement solution for the LACBR system by May 2025. At this stage, no implementation costs have been included, as execution will be addressed in future phases after the IT assessment (L2 review). Hard Benefits (USD 331,000/year): Estimated based on the decommissioning of current systems, including annual license and support cost savings once legacy platforms are retired. Soft Benefits (USD 350,000/year): Estimated soft benefits include: •Avoided revenue loss (USD 250,000/year): Prevents operational disruptions and revenue risk in case of legacy system failure and lack of vendor support. •Employee efficiency gains (USD 80,000/year): Anticipated gains in productivity by reducing system-related delays and manual workarounds. •Reduction in errors and rework (USD 20,000/year): Increased system stability and data accuracy reduce time spent on corrections. As highlighted by Carla and Jay, the key soft benefit at this stage is the risk avoidance from a potential system failure, which could result in revenue loss. Quantifying potential productivity improvements and error reduction also supports the business value of moving forward, even before a final solution and cost are defined. This rationale will be revisited and updated after technical scoping and solution costing in the L2 phase. 05/06/2025 - Issue: Financial values around $201k classified as annual support fees; unable to classify as hard or soft NRBs. Information provided by the IT team. 04/23/2025 - The "Effort Estimate - T-Shirt Size" field has been updated to "L," as per the input provided by the Architecture team. The value of USD 331,355 was reported by IT and validated with the Finance team. 17/04/2025 - The initiative details have been updated accordingly. The financial figures were adjusted following a recent update provided by the IT team, which clarified the total estimated annual cost associated with the decommissioned systems (TMS, EBS, and JDE). As a result, the projected savings now reflect the full scope of system retirement, ensuring alignment with the latest available data. 04/15/2025 - We obtained the information from Finance, and all POs are linked to the FCF system. JDE and EBS have no maintenance or licensing costs, as they are obsolete and no longer supported by vendors. Their continued use relies on INFOSEC exception approvals, which have reached the limit due to repeated annual extensions. TMS has an annual licensing cost of USD $130K 09/04/2025 - Will have a call tomorrow with Frederico from Brazil Finance team, to get the information from the pending fields: - Baseline Value - Target Value - Measure & Unit - Net - Recurring Benefits (FY'28 Exit Rate, Annualized) - One-time Benefit and Implementation Cost 04/03/2025 - We have updated the project scope to focus solely on replacing TMS and EBS. JDE will no longer be part of the initiative, as it is primarily related to TAX, while our focus remains on the financial business needs. This adjustment ensures alignment with our core objectives and optimizes resources for a more effective implementation. The following fields cannot be filled yet as we are awaiting information from the IT team regarding the business area: Baseline Value - Target Value - Measure & Unit - Net - Recurring Benefits (FY'28 Exit Rate, Annualized) - One-time Benefit and Implementation Cost This has been formally communicated via email to the expeditor in Planview. We will update once we receive the necessary data. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2025-12-31 | 2025-12-31
Business w/ Tech Initiative: Argentina Revenue Calculation Error |  | 107120 | Business w/ Tech Initiative | SGA - Finance | SG&A | Joel Garcia | On Track | Argentina is being moved from CALI to LAC42, therefore this request is no longer relavent | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Tax-Xiamen gov subsidy -VAT |  | 110085 | Business Only Initiative | SGA - Finance | SG&A | Jennifer Lin | On Track | 23/5/2025 *Yearly Xiamen Gov subsidy forecast of US$ 6,730,769, the potential VAT saving is : *US$ 6,730,769* 0.09 (VAT rate)=US$ 605,769m. * Once the subsidy received, the FEC Xiamen Rep-office will report VAT exemption and then the VAT saving will be realized. * Finance team is approved to move this initiative to the next level. 3/6/2025 * The initiative's Primary Type of Value has been updated to "Financial – Cost Savings/Reduction. 4/6/2025 *Xiamen Airport advise to apply for subsidy after operational yr end. Estimated subsidy to be applied in June 2025, estimated subsidy to be received in Aug 2025. 2/26/2026 * Xiamen gov subsidy application has been submitted, approval haven't been received. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: LAC-BR-TNT-LMS-Financial Reports migration to IBIS |  | 114214 | Business w/ Tech Initiative | SGA - Finance | SG&A | EVELLYN OLIVEIRA | On Track | 10/30/2025 - This initiative was cancelled as it will be consolidated with initiative 114129 (“LAC-BR-TNT-LMS Biling processes and financial Enhancements”) into a single local enhancement project. Both efforts are related to LMS system improvements and will be handled by the local LMS IT team in Brazil. The new consolidated demand will be created under the Local Enhancement category. 08/18/2025 - "The initiative has been updated following the feedback received. The Baseline and Target values have been corrected to USD 13,092/year and USD 0/year respectively, with Hard Benefits of USD 13,092/year, Soft Benefits of USD 5,000/year, and a One-time Benefit of USD 909. The L1 T-Shirt Size and impacted portfolios have also been updated based on the L1 Architecture Assessment. The initiative’s Lean Business Case is complete. We will monitor the Enterprise Architecture dashboard for the L1 documentation and upload it to Planview once received. All inputs will be reviewed with a QA Domain Expert prior to SL2 resubmission. .08/18/2025 - Status Rationale – Project L1 Hard benefits (USD 13,092/year) are based on automating manual report generation performed by 3 analysts (R$2,000/month each), converted at USD 1 = BRL 5.5. Soft benefits (USD 5,000/year) capture productivity gains, faster report access, reduced errors, and improved decision-making via Power BI. One-time benefit (USD 909) reflects the setup effort for IBIS automation. Assumes full replacement of manual reporting and adoption of self-service reporting without additional IT support. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: LAC_Costa Rica VAT on Outbound Letters&Documents |  | 114217 | Business w/ Tech Initiative | SGA - Finance | SG&A | Lourdes Espinosa | On Track | Since July 1, 2019, the Costa Rican government has required that VAT be applied to outbound letters and documents. However, FedEx’s current billing systems do not differentiate between documents (taxable) and packages (exempt) for outbound shipments. As a result, no VAT is being charged to customers on outbound documents, despite the regulatory requirement. A project to correct this logic (PPM #549631) was initiated in 2022 but remains on hold. The delay has resulted in FedEx absorbing approximately USD $420,000 annually in unrecoverable VAT payments to the government, as the company is unable to invoice customers correctly. To comply with the regulation and recover these costs, the system must: Update VAT logic to apply only to outbound documents Modify the local system to identify and map shipment types in the XML (documents vs. packages) This update is not only a regulatory compliance requirement, but also a financial efficiency opportunity, with a potential recovery of $420K per year. Reclassifying the project from an “Enabler” to an “Efficiency” initiative is appropriate given the measurable financial benefit. 01/22/2026 LE: Need to place this initivate on hold given that we cannot support it at this moment due to limited resources. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: LAC_CRI/DO/PAN Exonerate VAT Non-Account Hold(ROD) |  | 114220 | Business w/ Tech Initiative | SGA - Finance | SG&A | Consuelo A. Polonio | On Track | FedEx is currently unable to issue VAT-exempt invoices to non-account holders (ROD customers), despite regulatory provisions in Costa Rica, Dominican Republic, and Panama that allow VAT exemptions for customers located in Free Trade Zones or operating under specific tax regimes. This limitation is due to: System constraints that prevent VAT exemption logic from being applied to ROD transactions. Lack of integration between customer eligibility data and billing systems. Operational policies that may not support exemption validation for non-account holders. As a result: Overpaying VAT Customers are raising complaints due to being incorrectly charged VAT. FedEx is at a competitive disadvantage, with pricing up to 13–18% higher than competitors who apply exemptions correctly. There is a compliance risk, as the company may be remitting taxes that should not be collected under local law. This situation requires urgent review and resolution to align with regulatory requirements, improve customer satisfaction, and protect FedEx’s competitive position in these markets. 10/13/2025 Cancelled the initiative as per cancellation request submitted through PDSM #INC032618451 by Alison Cooper. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Daily Health Check Report Automation |  | 114223 | Business w/ Tech Initiative | SGA - Finance | SG&A | Nick Stuart | On Track | 3/15/2026 (dfw) asked IO to update LBC to correct format 7/16 - working on lean buisness case in prep for pi event | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Project Genesis - Oracle FCF - FY to CY |  | 127973 | Business w/ Tech Initiative | SGA - Finance | SG&A | Marcus A. Rapp, Jay Earnest, Christian Lemon | On Track | 4/7/26 - Executing solutioning 2/27/26 - Executing solutioning, completed SIT2 and ramping up UAT 1/28/26 - Executing solutioning 12/29/25 - Executing solutioning 11/5/25 - Executing solutioning 10/17/25 - Executing solutioning 10/9/25 - JHE - updated financials tab with new costing information recieved for the D&AI portfolio from Kendal Greene and for the Platforms portfolio from Zahra Taqi. Additionally, deleted association to GDX solution from the Initiative's Epic as instructed by Yogesh Chintamwar. 10/1/25 - Pending Finance, Domain and SVP Domain approval 9/24/25 - Received senior executive level approval for move to L3 9/12/25 - Submitted for portfolio PEL Greenlight requests 9/2/25 - Awaiting completion of architecture review processes and associated costing from IT to submit for portfolio greenlight 7/21/25 - Initiative has completed inital Architecture Assessment needed for L2 approvals. QA performed initial review and confirmed Initiatives are ready for submission. 6/9/2025 - added Christian Lemon as IO for back-up. Will be entering LBC information in the coming days as well. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-01 | 2026-09-15
Business w/ Tech Initiative: Project Sundance - Calendar Year Change |  | 127976 | Business w/ Tech Initiative | SGA - Finance | SG&A | Jay Earnest, Christian Lemon, Marcus A. Rapp | On Track | 4/8/26 - JHE - input Actuals for D&T costs for March '26. Actuals match forecast per guidance from IT costing leads. 3/23/26 - JHE - updated Money Step milestone to 1/1/2027. Two key milestone dates exist for the Initiative: 6/1/2026 and 1/1/2027, which are tied to the start of TY26 and CY27, respectively. Many applications must see modifications made prior to 6/1 go-live of TY26, but others will need modification in TY26 up to CY27 start. As the project has progressed, 1/1/2027 is thought to better represent the Money Step date/implementation complete date. 3/5/26 - JHE - input Actuals for D&T costs to match forecast as per prior guidance from IT costing leads. 2/9/26 - JHE - inputting Actuals for D&T costs to match forecast as per prior guidance from IT costing leads. 12/1/25 - JHE - worked with Mark Engstrom to have a high-level L2 architecture document created for the Initiative's D&T needs. That document has been uploaded to the Initiative's architecture common repository folder. 11/12/25 - JHE - entered Actuals for IT costs for October and September where applicable. Per guidance from D&T Finance representatives, Forecast amounts were transferred to Actuals line items as the process for IT cost Actuals is still a WIP. 10/14/25 - JHE - entered costing information for Platforms portfolio and uploaded supporting document provided by Zahra Taqi to the Initiative's content page. Additionally, input the costing from Commercial as provided by Jenny Mooring and uploaded supporting document. 10/9/25 - JHE - entered costing information for the D&AI portfolio supplied by Kendal Greene as well as uploaded associated documentation to the Initiative's content page. Costing has also been uploaded for Enterprise Services and Supply Chain Operations. Additionally, selecting "WIP" as Enterprise KPI as an entry is required in order to save the page, and no option applicable to this Initiative is available. 9/17/25 - Initiative team has been partnering with EA and the various impacted portfolios to align on and execute an approach to satisfy L2 architecture/IT requirements. Aim to continue this push and pursue a move to L3 such that IT teams can engage with this board directive. 7/21/25 - Initiative has completed inital Architecture Assessment needed for L2 approvals. QA performed initial review and confirmed Initiatives are ready for submission. 6/9/2025 - added Christian Lemon as IO for back-up. Will be entering LBC information in the coming days as well. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-12 | 2026-12-31
Business w/ Tech Initiative: PCRS - Enterprise Costing Integration |  | 127979 | Business w/ Tech Initiative | SGA - Finance | SG&A | Daniel Pelichek | On Track | 03/11/2026 - Putting initiative on hold due to EIW deprecation strategy change. Initiative may be needed in the future, depending upon which tech stack will be adopted enterprise-wide as well as where the Enterprise Costing final output will reside. These two factors are yet to be determined, therefore, no additional work was performed in the meantime. 01/30/2026 - Updated Actuals and Forecasts as well as Milestones. Pending confirmation of status of Environment setup milestone. 08/19/2025 - Following up on this: 1. Updated T-shirt size to M, from L, as per John Gilbert. Architectural document was also updated in the repository 2. Updated Baseline to show $4.5 million, as per Kendra Yarbrough and Joseph Nowell's guidances. Met with JJ Garcia today as well 3. Not developing this initiative will put initiative 8407 in jeopardy, since PCRS will not be able to support eMBP any longer. Impact not quantifiable due to possible overlapping. 08/08/2025 - Joint Architectural meeting was held between Commercial and Enterprise Services to validate the requirements for this initiative. Ryan Grover update the document in Sharepoint. 08/04/2025 - Responding to feedback requested: 1. As stated before, John Gilbert completed the Architectural document attached to Sharepoint. PCRS has a dedicated IT team under Loveena Goel 2. All Planview fields were filled as per the feedback from the different SMEs, namely Jay Earnest, JJ Garcia and Joseph Nowell. Therefore, discussions with Domain Finance and Domain PMO have taken place. 08/01/2025 - Met with Joseph Nowell for further refinement on Financials. 07/30/2025 - Received email with comments from JJ Garcia: "please add to your status rationale QA review complete and approved" 07/30/2025 - Addressed feedback. Met with Jay Earnest. Comments to the feedback below: 1. Financial assumptions are aligned with Domain Finance. In particular to baseline and target value as well as measure & unit have been reviewed and approved by Domain Finance. 2. Approach to calculate both one-time and net recurring benefit was aligned with Domain Finance. There is indeed a two component benefit (OUTDATED) 3. John Gilbert created the Architectural document uploaded to the Sharepoint site. 07/09/2025 - Added architectural documentation as well as business case. Roughly 65% of the FedEx revenue, which is repriced every year, would be at risk if this integration is not addressed | G: L3 | On Hold | L3 | 2026-01-01 | 2026-12-31
Business w/ Tech Initiative: GCS IFT - Adv S&P Policy Enabled by Tools & Tech |  | 127984 | Business w/ Tech Initiative | SGA - Finance | SG&A | Lucy Dolgy | On Track | 28th July Split the initiative into 4 requests. 0011815EMR IFT - Adv S&P Policy Enabled by Tools & Tech 0011808 EMR IFT Purchasing Gateway 0011813 EMR IFT Supplier Portal 0011811 EMR IFT CLM Please accept cancellation and we can progress through L gates quikcly as individuals - thank you 24th July. Requesting approval to split policy and tools into 4. Currently with MD's and Nike. Policy: August release closed for updates. This was a release with no tech changes so requested 2 points alterations: 1. addition of contract ownership (to be enhanced when we have CLM) 2. reduced threshold for souring directed contracting Now working to November release which will include tech changes only if purchasing gateway is live: 1. further reduce thresholds for sourcing direction 2. eliminate or reduce convenience purchase 3. reduce PO / invoice thresholds Tools: Purchasing Gateway: Data and tec aligning on contracting and implementation partner, the being presented by StP team to leadership for action to proceed by the 1st August CLM: RFP responses received and being scored by team 25th July - next steps to be presented to leadership 1st August Supplier & Invoice Portal: RFP response to be received by end of day 24th July and final scoring to take place 25th July. - next steps to be presented to leadership 1st August 16th July 2025 - Will be splitting this initiative into 4 and submitting as dependent initiatives 11th July 2025 - Waiting to hear feedback from Architecture review. Also planning to split this initiative into 4. Policy as main initiative then 3 tech initiatives all dependent on policy. This will be discussed at GPO on Tuesday 15th. 3rd July 2025 - Awaiting Architecture review meeting, now booked for the 11th July to enable submission to L2 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Pathlock for HRPAY access |  | 130471 | Business w/ Tech Initiative | SGA - Finance | SG&A | Sita Achanta, Mark Scott | On Track | 12/11/25 updated Milestones to reflect MTP date moved due to Peak 11/11/25 Updated Actuals for September and October 10/17/25 Purchase contract has been signed by VP. 10/10/25 Purchase contract was approved in Encore. Contract has been signed by the vendor and is pending FedEx VP signature. Once this is received we will receive and begin applying the software. 9/19/25 Received approval from PEL on 9/15 to move to L3 9/12/25 QA review with JJ & Sara. Updated financials & entered milestones. Waiting on Greenlight 8/19/25 - Addressed feedback and selected "Yes" for platforms impact. Resubmitting to SL2. Review is complete. We are ready to acquire product. | I: L4 | Active | L4 | 2025-10-15 | 2026-01-09
Business w/ Tech Initiative: The Ecuador ATA 023 Operation |  | 162355 | Business w/ Tech Initiative | SGA - Finance | SG&A | Jose Armando Mejia | On Track |  | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: EBS - Disbursements TH Cost Reduction |  | 165794 | Business Only Initiative | SGA - Finance | SG&A | Christian Lemon, Angela Edwards | On Track | **10/22** - Targeting L2 submission for the week of 10/19 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-02 | 2025-11-27
Business Only Initiative: FY26 City of Memphis, TN Property Taxes |  | 166035 | Business Only Initiative | SGA - Finance | SG&A | Hannah Brown, Pamela Lindsley | On Track | 2/3/2026-ready for L4 1/19/2026- Ready for l3 approval 12/23/2025: Submitting to L3 12/01/2025: Added the supporting documentation. Sent to Financial Analyst for review and resubmitted to L2. 11/04/2025: Completing required L1 entries, need input from Domain Finance on Enterprise KPI selection. Following will look to submit to L2. | K: L5 | Active | L5 | 2025-08-29 | 2025-08-29
Business Only Initiative: Tax: Canadian GST/HST Recovery |  | 166038 | Business Only Initiative | SGA - Finance | SG&A | Andrew Watkins, Hannah Brown | On Track | 4.14.26 Contract executed with 3rd party provider and work started. 1.6.26 Woking to complete 3rd party contract for tax recovery. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LAC-BR- Brazil Tax Reform - Alphanumeric CNPJ |  | 166045 | Business w/ Tech Initiative | SGA - Finance | SG&A | Maiara Gomes De Sousa Ferreira | On Track | We received the materials with information on which systems will need to adjust the alphanumeric CNPJ fields from the Deloitte consultancy. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: GTreasury RemainCo |  | 166110 | Business w/ Tech Initiative | SGA - Finance | SG&A | Kiley M. Kremser | On Track | On Track to SL2. Way late | G: L3 | Active | TEMP L3 - Enter L3 | 2026-06-01 | 2026-12-31
Business w/ Tech Initiative: LAC_CRI VAT 2% Public Universities |  | 167523 | Business w/ Tech Initiative | SGA - Finance | SG&A | Alison Cooper, Consuelo A. Polonio | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Europe Tax Team Alignment |  | 167539 | Business Only Initiative | SGA - Finance | SG&A | Michel Maenen, Jamie Pourciaux | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Oracle EBS interface data to Cash management tool |  | 177320 | Business w/ Tech Initiative | SGA - Finance | SG&A | Girish Yadav, Olivier De Waele | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Int'l Ship To Collect - Purple VAT Recovery Report |  | 103132 | Business w/ Tech Initiative | SGA - Finance | SG&A | Chandra Sekhar Vempada | On Track | 11/20/25 - Submitted VAT BDR execution support contract for WO 1 jurisdictions to FedEx for review | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: LACBR JDE–Decom and Historical Data Migration |  | 180102 | Business Only Initiative | SGA - Finance | SG&A | Sandra Parras, Barbara De Almeida Souza de Az | On Track | 3/31/2026: Demand Type changed to Lifecycle management To Answer ESPM Team Qs: This initiative has been changed to Lifecycle management as the request is to decomission the application and create a solution for employees to access in the future the application data. The work will be completed by the local LAC IT team US Stories have been created for decomission and data retention to comply with record retention under Records Management guidelines. They will be loaded in Agility v1 once this request reaches L3 Baseline changed to FY25; there are no savings in this PV request for this application decommission Baseline and Target Values are -0- at this time. The rationale to complete this application decommission is to take down this system as soon as possible as NOVITA has been implemented in Brazil Money Step Clarification completed. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Eliminate 50% of FP&A backfill open positions |  | 180118 | Business Only Initiative | SGA - Finance | SG&A | Adam Thomas, Licci S. Borsini, Joseph Nowell | On Track | 12/30: Developing the Lean Business Case in collaboration with Finance and submitted for Level 2 review. | E: L2 | Active | L2 Feedback Requested | 2026-02-02 | 2026-05-29
Business Only Initiative: QMCSO Surcharge | 91709 | 6707 | Business Only Initiative | SGA - HR | SG&A | Logan Pittman, Brandon Waits | On Track | 1/20/26 Initiative has 9 months of actuals entered. 11/6/25 Updated Oct actuals and FY27 and FY28 Forecast 9/8/25 Updated financials to reflect actuals. Applied surcharge numbers are still significantly lower than expected due to high population turnover rate. While the total QMCSO volume is similar to what we've experienced in previous years (1100-1600 per month), a higher than expected % of those sent are related to individuals that are no longer with the company as of the time of processing and can not be assessed the surcharge. In FY26, only ~9% of those QMCSOs that have been sent to FedEx are eligible for the surcharge. The original estimate was around 40-50% that would be eligible. The forecasts have been updated to reflect new estimates. 8/13/25 Updated financials to reflect actuals. Applied surcharge numbers are still significantly lower than expected due to high population turnover rate. While the total QMCSO volume is similar to what we've experienced in previous years (1100-1600 per month), a higher than expected % of those sent are related to individuals that are no longer with the company as of the time of processing and can not be assessed the surcharge. In FY26, only ~9% of those QMCSOs that have been sent to FedEx are eligible for the surcharge. The original estimate was around 40-50% that would be eligible. The forecasts have been updated to reflect new estimates. 7/11/2025 Updated financials to reflect actuals. Applied surcharge numbers are still significantly lower than expected. Team is working to understand why the % of applied surcharges to total number of QMCSOs is remaining lower than originally expected. 5/16/25 Updated actuals through April. Applied surcharge numbers are still signifcantly lower than expected due to the continued high volume of remaining QMCSO timestamped prior to 2025. * There was a significant amount of QMCSO runout from 2024 that the processing team is still working to complete. * QMCSOs timestamped prior to 1/1/25 are not applied the surcharge * As the QMCSO team works through the 2025 QMCSOs, we expect the number of surcharges to significantly increase over the next few months, reflecting the forecasted amounts. 4/21/25 Updated actuals through March. Applied surcharge numbers are signifcantly lower than expected due to the high volume of remaining QMCSO timestamped prior to 1/1/25. * There was a significant amount of QMCSO runout from 2024 that the processing team is still working to complete. * QMCSOs timestamped prior to 1/1/25 are not applied the surcharge * As the QMCSO team works through the 2025 QMCSOs, we expect the number of surcharges to significantly increase over the next few months, reflecting the forecasted amounts. 4/1/25 Updated FY26-FY28 Forcasts at the guidance of Enterprise Transformation Finance. FY26 totals now reflects the incremental value above FY25 savings and will be lower than originally reported.. 3/7/25 First surcharges hit on the latest payroll files. Expect early counts to report in Mid-March. Initial counts will be lower than expected until the new team finishes all the runnout 2024 post-marked QMCSO. 3/4/25 First QMCSO surcharges are showing up on payroll this week. Moved to L4. Expect to have reporting later this month to start reporting. 2/21/25 Based on what was agreed to in the BSB. The processing team is only applying QMCSO surcharge to QMCSO requests postmarked 2025. The team that took over this task was still finishing up QMCSO forms postmarked 2024. They have just recently got to the 2025 forms and have started applying the surcharge. March reporting should include January and some Feb numbers. 2/14/24 The processing team is still wrapping up completing the QMCSOs post-marked 2024. We expect to start seeing the surcharge applied on paychecks later this month and reporting for January to be available some time in March. Reporting will eventually catch-up to a 1 month lag as the new team catches | K: L5 | Active | L5 Feedback Requested | 2024-05-01 | 2025-01-24
Business Only Initiative: Reduce Health Reimbursement Account (HRA) and HSA | 91716 | 6708 | Business Only Initiative | SGA - HR | SG&A | Logan Pittman, Brandon Waits | On Track | 4/1/25 Updated FY26-Fy28 Forcasts at the guidance of Enterprise Transformation finance. FY26 totals now reflects the incremental value above FY25 savings and will be lower than originally reported. 3/7/25 No updates and there are no longer any costs associated since program was eliminated for CY25. 1/20/25 Submitted for L4. No evidence, other than AE communications and 2024 calendar year earned credits provided, to show as this program no longer exists for 2025 and so there are no longer costs associted with the earned credits. 1/14/25 Entered into 2025 plan year. No additional work to be done. Savings to be relaized over 2025 plan year. 1/7/25 Entered into 2025 plan year. No additional work to be done. Savings to be relaized over 2025 plan year. 12/30/24 On track. No additional work to be done. Savings to be relaized over 2025 plan year. 12/2/24 On track. No additional work to be done. Savings to be relaized over 2025 plan year. 11/25/24 On track. No additional work to be done. Savings to be relaized over 2025 plan year. 11/18/24 On track. No additional work to be done. Savings to be relaized over 2025 plan year. 11/11/24 Change communications included in 2025 ABE comms and moving forward for 1/1/25. | K: L5 | Completed | L5 | 2024-07-01 | 2025-01-02
Business Only Initiative: Recharge: Tuition Assistance Plan | 64802 | 7385 | Business Only Initiative | SGA - HR | SG&A | Tess Sutton, Michelle Ward |  | 06.25.25 Cancel due to initiative duplication. No longer needed. Implementation of process delayed to January 1, 2025 due to negative impact to employees | E: L2 | Cancelled | L2 | 2023-11-01 | 2025-01-21
Business Only Initiative: Talent acquisition/recruitment advertisement vendo | 19564 | 8249 | Business Only Initiative | SGA - HR | SG&A | Adam Schumacher | On Track | 3.3.25 financials have been restated and updated from TO finance. SVP finance approval has occured, sitting with Domain Sponsor for approval. 2.17.25 Patty Yardas provided updated financial numbers and have been adjusted in Planview. Moving to L4 today. 2.5.25 Finance is reviewing updated FY spend numbers to adjust future baselines and allow to move to L4. Follow up meeting Monday morning with finance to discuss status. 1.27.25 Met today to review with Finance and HR leadership. Finance is currently reviewing if any adjustments to FY baselines needed moving forward and then will be able to progress to L4. 1.20.25 On hold pending feedback from leadership review. Actuals will be recieved from vendors tomorrow and entered accordingly. 1.13.25 Waiting on clarification from TO finance around L3 to L4 feedback. Reached out again as of today. Leadership review of initiative requested and presented last week. On hold as it is being reviewed at higher levels. 1.6.25 Recruitment Marketing savings continue due to Shaker consolidation, continued adoption of harmonized processes and more favorable market conditions/needs for hiring. Working to get clarification on feedback requested so that updates can be made accordingly and moved to L4. 12.16.24 Actuals are slated to be recieved this week and will be entered. Waiting on clarification from feedback request to move to L4. 12.9.24 As discussed, November actuals will not be able to be updated for 12.11 as we do not receive actual spend updates from vendors and media until mid-month based on media billing cadence. 12.2.24 Recruitment Marketing savings continue due to Shaker consolidation, continued adoption of harmonized processes and more favorable market conditions/needs for hiring 11.25.24 Recruitment Marketing savings continue due to Shaker consolidation, continued adoption of harmonized processes and more favorable market conditions/needs for hiring 10.30.24 Recruitment Marketing savings continue due to Shaker consolidation, continued adoption of harmonized processes and more favorable market conditions/needs for hiring Updated cost savings to $18.28M using the FY23 base line. The original cost savings calculated from the FY22 baseline was ~$60M, but HR put extensive measures in place to maximize the spend and reduce expenses. We are ready for L3 approval. | K: L5 | Completed | L5 | 2023-02-16 | 2024-09-30
Business Only Initiative: Legacy FXE HR Vendor Spend Reduction | 87469 | 9177 | Business Only Initiative | SGA - HR | SG&A | Kelly Wade, Frank Olson, Anne Hemp, William B. McAlister | On Track | 6.6.25 * Updated May actuals. 5.14.25 * Confirmed actuals for April for May 16 due date. 4.18.25 * Confirmed actuals for FY25 * March for April 21 due date is confirmed. * submitted into l5. 4.9.25 * Double-checked milestones completed. * Money step confirmed and provided. * Added in Actual Exit Rate * Submitted into L4. 4.2.25 * Double checked financials for re-baselining to FY28. Confirmed. * Goal to submit to L4 once in L3 - goal is this month. 3.28.25 * Added forecast out to FY28. 3.21.25 * Awaiting Finance Domain approval/feedback into L3. * As this is a completed initiative, we do not have any updates at this time. * Once in L3, we will quickly submit actuals and move to L4. 3.14.25 * Aligned with Finance on cost savinings document. * Uploaded documentation of savings. * Added milestones and moneystep date. * Reconfiured the financial plan to align with the recurring benefits. * Changed KPIs to unit of contracts ended. * Submitted to L3. Corrected L1 Net Recurring Benefits $3.36M, annualized)-P&L/Hard and L1 Net Recurring Benefits ($3.36M, annualized)-Soft financials are accurate, sending back for SL2 approval. ESCC Case MKENNGA9 created to make adjustment made to L1 NRB. Need to be changed from 3,260,000 to 3,362,600. This is for the Legacy FXE HR Vendor Spend Reduction initiative. PDSM case opened to make correction: INC029028503 PDSM case closed / correction made. Added initiative owners to assist with PLANVIEW NOTE: Initiative is completed - we are just trying to get it entered into PLANVIEW. | K: L5 | Completed | L5 | 2022-12-01 | 2024-12-31
Business w/ Tech Initiative: Implement Paradox across enterprise to streamline | 19565 | 9434 | Business w/ Tech Initiative | SGA - HR | SG&A | Khristopher D. Tunstall, Claudia Versey | On Track | 1/15/2026: We are aligning Paradox with the new initiative of re-implementing Workday recruiting through project Odyssey. The decision was made to transition the Application Tracking System (ATS) for Non-High Volume roles and continue High Volume roles with Paradox. Launch is scheduled for September 1, 2026. 5/23 Rebaseline to FY25 4/16/2025: We are continuing to work through planning of Paradox implementation for the Regions outside of the US/Canada. alignment with our Hire to Retire processes, we are synchronizing the completion of the Talent Acquisition processes with another Strategic Initiative - Recharge Phase 3. This initiative is scheduled to launch in August 2026. Until then, we will not be able to fully complete the financial step or the overall implementation. 2/19/2025: Modified money step and implementation for International rollout of Paradox ATS. We have made modifications to the financial step and the overall implementation timeline. Although the project has successfully launched for US Domestic, the team is currently focused on fortifying the underlying infrastructure. To fully realize the financial step, we need to extend the launch to all Operating Companies (OpCos). However, the roadmap for this expansion has yet to be finalized. Additionally, in alignment with our Hire to Retire processes, we are synchronizing the completion of the Talent Acquisition processes with another Strategic Initiative - Recharge Phase 3. This initiative is scheduled to launch in August 2026. Until then, we will not be able to fully complete the financial step or the overall implementation. 1/23/2025: Currently the risk to the L4 Date is the completion of the internal roadmap for implmenting Paradox. Currently we are hardening the application for US and Canada. There is not an ETA when the international is to be published. Due to Project Recharge, the hiring processes have be harmonized globally to 5 key personas and we are moving forward with a single implementation for all OpCos in the US and Canada for June 2024. Researching if the FXE UK and Australia team can be included in June otherwise those areas and the rest of International will be a fast follow implementation in 2024. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-02-16 | 2026-08-31
Business Only Initiative: Spousal surcharge assessment | 19568 | 9435 | Business Only Initiative | SGA - HR | SG&A | Logan Pittman, Brandon Waits | On Track | 5.18.25 Completed over a year ago. No changes. Will enter financials through FY25. No financials will be entered after May 2025. 4.22.25 Completed over a year ago. No changes. Will enter financials through FY25. No financials will be entered after May 2025. 3.7.25 Completed over a year ago. No changes. Will enter financials through FY25. 2/5/25 Completed over a year ago. No changes 1/28/25 Completed over a year ago. No changes 1/20/25 Completed over a year ago. No changes 1/14/25 Completed over a year ago. No changes 1/7/25 Completed over a year ago. No changes 12/30/24 Completed over a year ago. No changes 12/23/24 Completed over a year ago. No changes 12/16/24 Completed over a year ago. No changes 12/10/24 Completed over a year ago. No changes 12/2/24 Completed over a year ago. No changes 11.25.24 Completed over a year ago. No changes 11.18.24 Completed over a year ago. No changes 11.11.24 Completed over a year ago. No updates. | K: L5 | Completed | L5 | 2022-09-01 | 2023-10-31
Business Only Initiative: Closing of health centers | 19569 | 9436 | Business Only Initiative | SGA - HR | SG&A | Logan Pittman, Brandon Waits | On Track | 2/5/25 Completed over a year ago. No changes 1/28/25 Completed over a year ago. No changes 1/20/25 Completed over a year ago. No changes 1/14/25 Completed over a year ago. No changes 1/7/25 Completed over a year ago. No changes 12/30/24 Completed in 2023. No changes. 12/23/24 Completed in 2023. No changes. 12/16/24 Completed in 2023. No changes. 12/10/24 Completed in 2023. No changes. 12/2/24 Completed in 2023. No changes. 11/25/24 Completed and still closed. No changes. 11/18/24 Still closed. No changes. 11/11/24 Completed over a year ago. No updates. The difference between the actual monthly savings and forecasted is due to what would have been an increase in annual contracted rates for CY24. Annual costs were set to rise to $11M annually in CY24 due to increases in expenses related to medical labor, supplies and admin fees. | K: L5 | Completed | L5 | 2022-07-01 | 2023-07-31
Business Only Initiative: Disability Income Replacement Reduction | 19570 | 9438 | Business Only Initiative | SGA - HR | SG&A | Logan Pittman, Brandon Waits | On Track | 5/18 Entered April 2025 actuals against 2023 baseline. Will continue to enter financials until end of fiscal year. Initiative has been in place over 12 months. 4/18/25 Entered March 2025 actuals against 2023 baseline. Will continue to enter financials until end of fiscal year. Initiative has been in place over 12 months. 2/21/25 Entered Jan 2025 financials against 2023 baseline. Feb 2025 savings will come in mid March. 1/20/25 Submitted for L5 1/15/25 Updated Dec Financials 1/14/27 Implemented 1/1/24. No changes. Last month of reporting savings. 1/7/27 Implemented 1/1/24. No changes. Last month of reporting savings. 12/30/24 Implemented 1/1/24. No changes. 12/23/24 Implemented 1/1/24. No changes. 12/10/24 Implemented 1/1/24. No changes. 12/2/24 Implemented 1/1/24. No changes. 11/25/24 Implemented 1/1/24. No changes 11.18.24 Implemented 1/1/24. No changes 11.11.24 Implemented 1/1/24. No changes 7.11.24 There was $1.823M in total June 2024 savings, but unable to include while initiative is stuck in L5 approval. 4.18.24 Update * The Jan-March actual impacts have been updated to reflect the monthly actuals vs the 2023 monthly actuals + 3% Wage inflation, instead of the previously used avg monthly baseline. * The updated actuals show a total savings of $1.9M over the first 3 months. * The April forecast was updated to reflect a ramp down of the prior 2023 disability payouts. * As a reminder, FedEx Enterprise Health Care cannot control who goes on disability and when they go on disability. The structure to control costs is in place, but actual claims can fluctuate month to month based on many variables. 3.24 Update STD/LTD Drive Project (Original Annual Savings Estimate: $24M) •Based on actual 2024 STD/LTD claims spend in January and February compared to the projected monthly, FedEx has seen an increase in claims spend ($818k) over the first two months. •A flat or upward trend was expected in the first three months as there is still a runout of the 2023 disability claims that were at the higher payout percentage. This is expected to trend downward as new claims assume the lower payout percentages. •The projected monthly claims is based on average over the entire calendar year. Monthly STD/LTD claims amounts are typically higher in the beginning of the calendar year due to a larger employee population during peak and higher rates of disease spread and accidents in the winter months that cause an increase in disability claims. | K: L5 | Completed | L5 | 2023-03-29 | 2024-01-01
Business Only Initiative: Part-time employee benefits eligibility | 19743 | 9443 | Business Only Initiative | SGA - HR | SG&A | Logan Pittman, Brandon Waits | On Track | 5.18.25 Forecasts updated through Feb 2025 due to 3 month claims lag. Will finish out through May reporting and will be done with this initiative. 4.1.25 Updated FY26-Fy28 Forcasts at the guidance of Enterprise Transformation finance. FY26 forecasts were updated to reflect actuals realized in 2024. $0 actuals were put in place for FY27 and FY28. 3.7.25 Financial numbers to be updated through Dec 2024 by 3.10. Claims numbers always lag 3 months. 2.14.25 Updated numbers through Nov 2024. 2/5/25 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 1/28/25 Entered most recent claims savings prior to 1/20. PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 1/20/25 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 1/14/25 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 1/7/25 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 12/23/24 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 12/23/24 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 12/16/24 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. Sept 2024 were added last week. 12/10/24 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 12/2/24 PT Savings still ongoing.Reminder, claims numbers always lag 3 months. 11/25/24 PT Savings still ongoing.Updated numbers through August. Reminder, claims numbers always lag 3 months. 11/18/24 PT Savings still ongoing.Updated numbers through August. Reminder, claims numbers always lag 3 months. 11/11/24 PT Savings still ongoing. Discussions with Finance this week about modifications to hours. **PT Savings (Original Annual Savings Estimate: $112M)** •Based on the first 3 months, the PT Drive initiative has resulted in an aggregate savings of $2.3M. •This is significantly lower than the original projection due to 3 factors: 1) A higher percentage of eligible employees enrolled in medical benefits for 2024, 2) An increase in PT minimum worked hours to meet the 12 hours/week threshold, and 3) Savings estimate is based on projected average, not actual. **Higher Percentage of Enrollment** •The medically enrolled percentage of eligible employees increased by 8.4 percentage points YoY due to the introduction of new no/low contribution medical plan options. •6,500 PT employees that were eligible and had previously waived in 2023 enrolled in medical benefits for 2024. **Increase in Hours** •To reach the projected DRIVE savings goal, FedEx had to shed ~16,600 enrolled PT employees from the FedEx plan. •Following the 2024 AE measurement, a lower than expected number of employees (~11,700 of enrolled and not enrolled PT employees) were calculated as ineligible to enroll in benefits due to an increase in hours worked to retain benefits. •Given that the threshold was so low (12 hours) compared to originally proposed (20 hours), employees were able to easily add enough hours to retain benefits eligibility. •**This is a positive for FedEx, given that there are now fewer PT employees in the workforce an those remaining had higher averaged worked hours, decreasing FedEx’s total overhead employee expenses.** **Savings Calculation is conservative and will need to be restated retroactively** •While the original estimate looked at individual claims data in certain hour ranges, the below only factors in average PT claims costs. •The total savings per individual in the lower hours population tended to be substantially higher than the average claims cost of a PT employee because some were solely working limited hours to receive needed health benefits. •A similar calculation can be done, but would need to be completed after the full year of 2024 claims have been submitted for this population. •Network 2.0 staffing will have significant impact on this workforce depending upon headcount, hours available, | K: L5 | Completed | L5 | 2023-03-29 | 2024-12-31
Business Only Initiative: SAS Migration - Workforce Planning |  | 86616 | Business Only Initiative | SGA - HR | SG&A | Matthew Hensler | On Track | Initiative no longer active in Planview | C: L1 | Cancelled | L1
Business Only Initiative: MySchedule - Blue Yonder Contract Review |  | 88453 | Business Only Initiative | SGA - HR | SG&A | James Addington | On Track | 3/17/26-Actuals and forecast updated to align with new contract terms. 1/16/26: Actuals updated 9/4/25: Actuals were provided for next 3 months. 7/14/25: Added Forecast as placeholder until we are able to connect with IT to provide us actuals 7/11/25 Actuals cannot be sent by the newly updated expected by date on such short notice. Will try to see if we can get it sooner in the future. Will provide once received. 5/2/25 On track 4/4/25 On track 3/13/25 On track. 3/6/25- On track. Actuals do not get sent to FedEx until around the middle of the month up until the 20th. Actuals will not be inputted by the 10th. Updating IO | I: L4 | Active | L4 Feedback Requested | 2024-07-01 | 2026-08-05
Business w/ Tech Initiative: FedEx ID to 8-Digit |  | 89644 | Business w/ Tech Initiative | SGA - HR | SG&A | Bill Stanek, Lee Frye | Some Issues | 22.Apr.26 •641 impacted applications have not started testing •7 applications indicating development in progress •21 indicating testing in progress •182 applications that have not responded to the question of FedEx ID impact 8.Apr.26 * 66% of impacted apps are ready. * Testing has not started for 32% of impacted apps. 30.Mar.26 * PM met with portfolio leads 14.Mar to discuss remaining apps. Will meet again this week. * 63% of impacted apps are ready. * Testing is in progress for 1% of impacted apps. * Testing has not started for 36.3% of impacted apps. * 240 application owners have not responded to emails. Might not be able to reduce this number any further. 3.Mar.26 * 59.2% of impacted apps are ready. * Testing is in progress for 1.5% of impacted apps. * Testing has not started for 36.3% of impacted apps. * 240 application owners have not responded to emails. 6.Jan.26 * 36.5% of impacted apps are ready or have begun testing as of Jan 6. * Testing is in progress for 2.0% of impacted apps. * Testing has not started for 61.0% of impacted apps. * 360 application owners have not responded to impact survey. * April 2026 expected 7-digit depletion date. 12.Dec.25 * 30.7% of impacted apps are ready or have begun testing as of Dec 9. * Testing is in progress for 1.7% of impacted apps. * Testing has not started for 67.7% of impacted apps. * 381 application owners have not responded to impact survey. * No concerns in SCO, PF, DAI for meeting January deadline. 5.Dec.25 * Increased cost estimate to allow for new capability to provide alternative ID generation mechanism to delay the transition June 1. This will provide time for key applications to be upgraded without ID collisions or business disruption. * Advanced money step milestone to June 1 to account for expanded work. * Platforms portfolio reports no impact from 8-Digit ID * SCO has no concerns to meet Jan 14 date. * Commercial: Sales and retail report no or low impact. RMIC has one app making code changes. * Enterprise Services has low confidence in making Jan 14 date due to low response. Will be escalating. * DAI has tested and is ready for January. 2.Dec.25 * 25.9% of impacted apps are ready or have begun testing. * Testing is in progress for 1.5% of impacted apps. * Testing has not started for 72.2% of impacted apps. * 381 application owners have not responded to impact survey. 1.Dec.25 * ARB approval for new capability, 1.1 Adjust FedEx ID Incrementor to Support 8 Digit Effort. Incremental 2TPIs for ES has been costed. Will request costing for incremental 1 TPI for SCO. 20.Nov.25 * 15.9% of impacted apps are ready or have begun testing. * SCO: fewer than 25 EAIs still pending survey response. All impacted applications have assigned sprints * Unknown whether work is planned in Platforms and Commercial, have not received updates. * ARB review sched 21.Nov for proposal to mitigate ID consumption by reusing ID numbers no longer in any system. 14.Nov.25 * Issue developing from accelerated pace of ID consumption since August may cause 8D rollover sooner than expected. This will be a problem for FXF and badging related applications that are near end of life. Architecture has developed a mitigation plan to reuse ID numbers no longer in any system. * No updated survey numbers to report. * SCO: fewer than 50 EAIs still pending survey response. * DAI: no concerns forJan 14 update. * Commercial: No update * Platforms: no update 7.Nov .25 * 8.1% of impacted apps are ready or have begun testing. Survey was re-sent and we expect the number to improve. * Discussions and analyses continue on reusing legacy Ground contractor IDs to avoid FXF development before the FXF workday instance is ready on Apr 22. * Risk for FXF of out of range numbers before April 22 continues. 1.Nov .25 * 6.5% of impacted apps are ready or have begun testing. Team suspects that many applications are ready, but have not submitted their results to the completion survey. Survey will be re- | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-11 | 2026-10-12
Business w/ Tech Initiative: Remote Worker Functionality |  | 106037 | Business w/ Tech Initiative | SGA - HR | SG&A | Laura DeKruger | On Track | 9/22/2025: Moved to Project Odyssey as an epic. Initiate project to establish enterprise remote worker functionality. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Employee Verification Letter - Phase 2 |  | 108664 | Business w/ Tech Initiative | SGA - HR | SG&A | Jun Wei Tan | On Track | PV request to cancel item. Re-raise the ticket if required | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Case automated reminder email & due date |  | 108670 | Business w/ Tech Initiative | SGA - HR | SG&A | Jun Wei Tan | On Track | PV team request to cancel. Re-raise ticket if required. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: HR svc Record Producer Update - Give Appreciation |  | 108674 | Business w/ Tech Initiative | SGA - HR | SG&A | Jun Wei Tan | On Track | As aligned with PV team to close the ticket and create a new ticket if required. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Purple Gateway HRSD Operational Support |  | 108679 | Business w/ Tech Initiative | SGA - HR | SG&A | Jun Wei Tan | On Track | PV team request to cancel. Re-raise ticket if required. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Replace IMAGE GUI for SIDA and STA |  | 141999 | Business w/ Tech Initiative | SGA - HR | SG&A | Brandon L. Lake, Ilazabeth Obi | On Track | 2.18.26 Met with Architect team for working session on IMAGE. GUI. Planview description to clarify scope includes backend logic, not just UI, and moving capabilities from SailPoint to ServiceNow. Service now has competing priorties with enterprise badging. 2.11.2026 SNOW advised enterprise badging team during discussion IMAGE will remain operation into 2027. New IMAGE GUI projected for December 2026 or early 2027. Due constraints with SNOW team and competing objectives. 1.12.26- Updated planview team on the depndency of Enterprise badgeing and service now 12.3. 25 – Met with Data and AI, Service now, Jim Finch for IMAGE SIDA and STA reporting from IMAGE planview to be parsed off from the 10.24.25 discussion. challenges & risks were discussed. •Delays with Workday Learning integration. •Uncertainty around Waveset and retirement of SailPoint. •ServiceNow API availability for CDAS integration. •Potential changes to connection points that could break data flows. •Need to finish data-source identification and mapping 11.6.25 – met with Service now team the team to perform work . Expected timeline Sept 2026 for IMAGE GUI 11.5.25- Triage meeting with Data and AI Drive 10.30.25- Discussion with Deloitte to assist with development 10.28-25 – Met with Data and AI team on 10.28.25 to discuss all future reporting the SIDA and STA to reside in LIP. Obtained contacts and set follow up meeting on Dec 3rd, 2025 10.24.25 – initial meeting with LIP team to placing the report portion (SIDA/STA) enterprise wide of IMAGE in on the LIP platform 10.14.25- Details for SIDA and STA business requirements with Diagram We reviewed the project timeline on 10.24.25 for: Implementation cost Timeline And potential incurred cost What platform would perform the work 10.1.25 Met with Joseph Nowell and George Oawald from Finance 9.23.25 * Added description for SIDA and STA * Q and A review with JJ.Garcia and manager 9.16.25 Met with sourcing Zachary Boles 9.19.25 * Added Financials after meeting with Finance * Added all ability statements * Updated Drive, Domain, and Cross function category * Need to review with managment and support personnel before submitting for L2 8.26.25 Added all documents from intial Triage 7.30.25 Met with EA architect | E: L2 | Active | L2 | 2025-11-06 | 2026-12-30
Business w/ Tech Initiative: OM&F Transition to ServiceNow (Purple Gateway) |  | 153136 | Business w/ Tech Initiative | SGA - HR | SG&A | Heather Dornan, Elizabeth Rosa | On Track | Business case completed, PPM (1232863 request ID) completed. This should be cancelled. | E: L2 | Cancelled | L2 | 2025-09-05 | 2026-04-30
Business Only Initiative: EMR-Awards and recognition program |  | 153781 | Business Only Initiative | SGA - HR | SG&A | Eduardo Sciortino, Laura Bullion, STEFANIA MARCHISIO | On Track | HR has confirmed they currently lack the resources to support a full RFP process due to other priorities. The new initiative will be done during late 2026. | C: L1 | Cancelled | L1
Business Only Initiative: Service awards program |  | 163634 | Business Only Initiative | SGA - HR | SG&A | Eduardo Sciortino, Laura Bullion | On Track | 03/23/26 We signed a second contract amendment with MTM that will deliver additional savings. 03/03/26 We are close to signing a second contract amendment with MTM that will deliver additional savings. Our plan is to execute a new contract incorporating these commercial updates as soon as possible; therefore, the supplier implemented the changes effective December 2025. Starting from November 1st, a new contract with MTM became active, including a negotiated 1% discount on all products, which already generates savings. The contract is being reviewed by MTM, once confirmed will be signed. 02/13/26 We are close to signing a second contract amendment with MTM that will deliver additional savings. Our plan is to execute a new contract incorporating these commercial updates as soon as possible; therefore, the supplier implemented the changes effective December 2025. Starting from November 1st, a new contract with MTM became active, including a negotiated 1% discount on all products, which already generates savings. 12/11/25: The Encore process has started (1254360). Note about the spend and potential savings: in L1 the spend and the potential savings were comprehensive of Freight. When preparing Financials in L2, Finance suggested to remove the Freight, leading to a lower amount of annual spend ($4.5M) and annual savings projected ($226K). | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2026-04-14 | 2026-04-14
Business w/ Tech Initiative: SIDA Transition from TSC/HID to Telos |  | 168982 | Business w/ Tech Initiative | SGA - HR | SG&A | Ilazabeth Obi, Femi M. Ajayi, Brandon L. Lake, Raymond F. Kienle | On Track | 1.12.26 Awaiting ServiceNow availability to review and give feedback. Due to cost savings, will switch vendors for SIDA to Telos. Meeting set to meet with Telos to discuss if they can build GUI for FedEx to replace Crossmatch (fingerprinting software). Otherwise ServiceNow or a thrid party vendor will need to build. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: US Screening services |  | 187789 | Business Only Initiative | SGA - HR | SG&A | Eduardo Sciortino | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: ECRM Outside Legal Optimization | 69962 | 7069 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho, David Billions | On Track | 04.14.25- Actuals udpated for March. 03.11.25 - Actuals updated, reports received from vendors today. Savings increased on WC spend but decreased for liability. Liability spend increased due to large case settlement and final billing from defense counsel. 01/27/2025 - Actuals updated, reports provided by 15th of every month. Will look to move this initiative to L5 by first week of February. 11/18/24 - Actuals updated through 10/31/24. Savings decreased due to WC and Liability spend increasing. The WC spend continues to exceed target due to the utilization of non-panel firms. The WC team plans to pull all matters and move litigation handling to panel firms. The liabilty spend increased due to 3 large payments ($2.5M) made to McGuire Woods to satisfy the FY22-FY24 open claims tied to alternative fee arrangement (AFA). | K: L5 | Completed | L5 | 2023-07-03 | 2024-06-28
Business Only Initiative: ECRM Preservation of Evidence, Legal Holds & Compl | 73172 | 7070 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho, David Billions | Some Issues | 11/10/2025 - Requesting to cancel as this initiative has been in place since 2023 and has already been initially baselined, rebaselined x2. 07/21/2025 - New contract for Insights going through legal review. 06/23/2025 - Moving to L3 today. Removed soft savings. Added KPIs to financials to track claims that have alleged spoliation. Contract for OSV's is currently moving through contract system Encore. Will be reviewed by Legal in next week and finalized by 6/30. Training for OSV's has been conducted over the last 2 weeks training them with the paralegals on preserviation of evidence for lawsuits. 03/31/25-FY26-FY28 Re-valued to FY25. 1/9/25 - Inititive is going to proceed utilizing OSV's on the ELS team. David Billions is working with paralegal team to build process flows for OSV team. Will work to move to L3 status by end of next week. 11/18/24 - Intiative currently on hold due to need to increase staffing utilizing FTEs or OSVs. FTEs will most likely not be an option due to staffing freeze. | E: L2 | Cancelled | L2 Feedback Requested | 2024-04-16 | 2025-06-11
Business w/ Tech Initiative: Global Targeting Center Risk Model Enrichment | 90447 | 7288 | Business w/ Tech Initiative | SGA - Legal | SG&A | Justin Williams, Daniel Kemp, Lee Skelton | On Track | Need engineering alignment with Dataworks and RDE to support production workload. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Liability Claims - Fraud Initiative | 92508 | 7322 | Business Only Initiative | SGA - Legal | SG&A | David Kadosh, Jean Givner | On Track | 9/26/25 - This initiative was submitted for L5 earlier this week. We will continue to track the numbers accordingly for the next several months. 9/12/25 - Numbers for FY26 Q1 have been recorded and entered. So far, we are seeing an uptick in the SIU-driven savings delta for FY26. Through Q1 we're showing a SIU-driven savings delta of 23%, which is up 18% from all of FY25. We've noticed a savings of $619,779 in FY26 Q1 compared to savings of $641,428 in all FY25. SIU referrals are up about 100% YOY from FY25 Q1 and consistent with referrals from FY25 Q4. We are currently in L4 and our plan is to progress into L5 in the very near future. We are reviewing our KPI numbers before submitting for L5. Once we proceed to L5 we will continue to track our numbers, but potentially look to put this initiative to bed as we are looking to create a new fraud initiative and playbook to continue to capture and expand on savings nationwide. This new initiative will incorporate and build upon the elements in the NY Fraud Initiative. 7/25/25 - The results for June were lower than normal and for FY26, we are evaluating whether the saving percentages should be tied to the fiscal year or to a rolling period. FY25 numbers will be locked in and FY26 numbers may be volatile as th savings percentage is only calculated on one month's results (which is why the month is lower for June 2026). Additionally, there may be some consolidation with the NY Fraud initiative or a new initiative to address fraud across the board. 6/19/2025 - May 2025 results received. Referrals are still up. For May, the amount "saved" ws $76,423.97. 5/23/25 - In FY24, FedEx paid 41,963 liability claims (6366 BI and 35,597 PD) for a total payout of $1,136,164,788. This initiative is focusing on cost avoidance. Through April 2025, the savings was $878k which is below plan. 5/12/25 - Received the results from April and note the volume of referrals has increased month over month, as have the savings. The financials are up to date and the supports have been attached. Total Reserves for FY25 (associated with SIU related claims) through April 2025 amounts to $8,035,301. Savings are being calculated off of the reserves. 4/28/25 - updated Primary IO due to departure of Dawn Boland from FX. Reminder...Savings is calculated by comparing the difference (delta) in payout on claims with and without SIU involvement. The delta is to be re-calculated quarterly. A new calculation should be done in June for new FY. The initial results showed 4% savings in FY24 and 13% savings in FY25. Therefore, the thought is “if we did nothing else, we would continue to have 4% savings. However, since we re-educated GB in red flags and encouraged increased usage of SIU, our savings went to 13%. Therefore, our delta savings factor is 9%.” We have not met the forecasted savings yet. I anticipate that there is a lag between increased referrals and savings since the files do not close the same month of referrals often and savings are not recognized until the file closes. However, this may need additional review if the savings do not improve. Referrals are definitely up. The sampling for savings was capped at $250k, I believe. This should avoid double dipping in savings with Jerrod’s project. However, may miss including some of the mid-sized fraud claims. 4.22.25 Actuals for March are entered. Result was below forecast again. Preparing project data to be transferred upon my transition. 4/11/25 Rebaselined to FY25. 4/7/25 I was out of the office last week. While out, Patrick approved this to L4, but requested some updates to projections. I've requested a meeting with Kendra to be sure I'm inputting this accurately. Actuals for March are entered. The referral volume continues to increase, which is promising (and expected). The savings are not tracking with the projections. Again, this can be due to lag between referrals and results. (A file referred to SIU today | K: L5 | Completed | L5 | 2024-10-29 | 2025-04-18
Business Only Initiative: State Self-Insurance Consolidation | 93065 | 7608 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho, Michelle Pitts | On Track | 02/16/26 - Actuals updated; Credit received from Sedgwick for additional $28K in savings. 01/29/26 - Report received from vendor 01/19/26. Actuals updated. 01/06/25 - Awaiting reports from vendor. Actuals will be updated prior to due date of Jan 13th. 12/8/25: No update from last week. 11/30/25: November actuals added. We are still waiting on a quarterly true-up from Sedgwick that should include a refund of approximately $33K for Regina Webster. Phase 2 of program is complete. 11/24/25: No update from 11/12/25. 11/12/25: October financials added. The TPA has updated invoicing rates for OSVs assigned to Self-Insurance. Regina Webster has been removed from the invoice, while Tish received a nominal increase. Michelle and Sonya are now fully dedicated to Self-Insurance, so their pay will be accounted for starting this month. As onboarding progresses, Tish will transition off the program, resulting in an additional monthly savings of $9,811.83. We are still awaiting Sedgwick’s quarterly true-up, which should include a refund of approximately $33,000 for Regina Webster for July through September, when we were billed despite her being off our service. 11/10/25: We received updated invoicing from Sedgwick and that will be reflected starting with October actuals. We have not received a true-up from Sedgwick to date so the expected recoup of OSV fees has not occured. 10/27/25: No update from 10/10/25. We are currenlty waiting on updating invoicing from Sedgwick with an anticipated timeline of later this week. 10/10/25: September actuals updated. Anticipate seeing an increase in savings with October actuals due to the bill corrections by Sedgwick some of which will be offset by two new hires that are working on SI program. We anticipate a one-time lump sum increase either in October or November due to the reimbursement of OSV fees that we were charged for after OSV terminated. 9/29/25: No update from 9/12/25. 9/12/25: Submitted to L4 the week of 8/11/25. Still waiting on whether Jerome has accepted the additional information he requested regarding my submission to L4 the week of 8/11/25. August actuals entered. Two new team members onboarded 9/2 and are in training to replace OSV on state self-insurance. 8/29/25: Submitted to L4 the week of 8/11/25. Still waiting on whether Jerome has accepted the additional information he requested regarding my submission to L4 the week of 8/11/25. No additional updates. 8/25/25: Submitted to L4 the week of 8/11/25. Jerome had requested additional information and that was submitted on 8/15. Still waiting for approval on request to move to L4 or request for more information. No additional updates. 8/11/25: Will have enough actuals to submit to L4 after July financials posted. Will touch base with financial stakeholders to ensure all check-list items are addressed. I will also send an email to Jerome Miller with an outline prior to submitting to L4. 8/4/25: No update from 7/21/25. 7/21/25: No update from 7/11/25 other than Sedgwick stated the true-up did not create a credit for the OSV costs as it only was applicable through 3/31. The new OSV rate was not reflective until April and therefore, we won't see a credit until the next true-up in October. 7/11/25: Actuals have been updated. Sedgwick will be issuing a credit in July as part of the invoice true-up, and we expect to see additional OSV-related savings reflected in that adjustment. R&I is undergoing staffing changes related to self-insurance team, which will impact financials in the coming weeks. One OSV ended service as of July 2nd, and we currently have an open R&I III position that will serve as a replacement. These staffing adjustments are expected to generate further cost savings in the near term. 7/725: No update from last week. 6/23/25: No update from last week. 6/16/25: Sedgwick did not break out financials on the June invoice received in May but stated they would in on next invoice received | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2024-08-06 | 2025-04-30
Business Only Initiative: Nurse Case Management Savings | 84802 | 7609 | Business Only Initiative | SGA - Legal | SG&A | Nancy Chiesa, Julianne Camacho | On Track | 5/26/25 - Financials will be added for May around 6/21. Otherwise, expect no activity on this initiative. 5/5/25- financials for April will be added before May 21. They are generally available around th 17th of each month 4/28/25- financials for April will be added before May 21. They are generally available around th 17th of each month 4/21/25- financials for April will be added before May 21. They are generally available around th 17th of each month 4/7/25- financials for March are in. 3/31/25 - financials were added for Feb. Until the March financials are available mid April there will be no additional updates 3/25/25 - financials were added for Feb. Until the March financials are available mid April there will be no additional updates 3/17/25 - financials were added for Feb. No further activity to occur until the March financials are added in April when they are available 3/10/25 - Actuals for Feb will be updated by 3/17. 3/3/25 - Actuals for Feb will be updated by 3/17. 2/25/25 - No changes since last update. Actuals for January have been entered. No other activity is anticipated. 2/17/25 - No changes since last update. Actuals for January have been entered. No other activity is anticipated. 2/10/25 - No changes since last update. Actuals will be entered monthly. No other activity is anticipated. 2/3/35 - No changes since last update. Actuals will be entered monthly. No other activity is anticipated. Update as of 11/4/24: Financials will be updated for October by 11/19/24. At that time, the KPI's will be divided out in to categories which will not change the overall savings, just show them broken down. The initiative will then be advanced to L4 for continued monitoring of savings. As of 11/11 : Financials will be updated for October by 11/19/24. At that time, the KPI's will be divided out in to categories which will not change the overall savings, just show them broken down. The initiative will then be advanced to L4 for continued monitoring of savings. The financials did not transfer from WAVE. We have the data but I have been unable to post in Planview due to technical issues. A ticket has been put in for assistance. The initiative is tracking favorably and on track - I just can't get the financials until we get the information moved over from WAVE and Planview issues resolved. 12/2/24 - actuals are in planview now. will continue to track monthly performance and advance to L4. 12/9/24 - data is now tracking correctly. There is nothing left to do with this initiative but track the monthy savings from TCM utilization. This initiative is dependent on claim volume - if there are less claims for nurses to work on, the savings will decline, and visa versa. As of 12/16: continuing to track results - now that we have enough history once approved to L4 we can move on to L5. This initiative is dependent on claim volume and types of claims nurses engage in. More frequency / severity will see more savings. Less frequency/less complex claims will see a reduction. The initiative is trending downward in savings which means less frequency and severity in our claims which is a good thing. 12/30/24 - no change, we will continue to monitor the monthly savings report. The cost can't accurately be forecasted because they align with the frequency and severity. More claims or more severe claims will have more nurse engagement thus costing more and visa versa. 1/6/25 - no change - will enter actuals by 1/20. 1/13/25 Will Move to L5 given we now have a years worth of data and are only tracking savings. The spreadsheet to show savings is attached and will be updated with the December savings. 1/20/25 - No changes - update numbers monthly, await approval to L5. 1/27/25 - no change since last week's note. | K: L5 | Completed | L5 | 2024-02-01 | 2024-09-17
Business Only Initiative: Settlement Champions | 96447 | 7702 | Business Only Initiative | SGA - Legal | SG&A | Ed Kinslow | On Track | 4/13/26 - Updating to L5 1/29/26 - Money step evidence and LBC entered as documents. Also entered financials that were prepared by Finance. Submitting again to L4 10/27/25 - Team West CCA/Settlemente Chanmnptions have completed staging. Savings will be realized in October and will be reflected when we updated financials in November. 10/17/25 - Team West CCA/Settlemente Chanmnptions have completed staging. Savings will be realized in October and will be reflected when we updated financials in November. 10/10/25- Completion of staging by Team West CCA/Settlement Champions is now set to be completed by EOB today. Savings will be realized in October and will be reflected when we updated financials in November. 10/3/25 - Completion of staging by Team West CCA/Settlement Champions is now set to be completed by EOB 10/10/25. Savings will be realized in October and will be reflected when we updated financials in November. 9/26/25 - CCA/Settlement Champions for Team West are wrapping up staging which will be completed by the end of September. Financials will be updated with September results once received. 9/12/25 - CCA/Settlement Champions for Team West are wrapping up staging which will be completed by the end of September. Financials will be updated with September results once received. 8/18/25 - CCA/Settlement Champions for the Team West that started in June should be done staging claims by the end of the month, we should start realizing savings in September. Call scheduled with finance on 8/21 to discuss how we will report savings. Initiative should be moving into L4 by the end of the calendar year. 7/11/25 - Financials are quarterly and will be available after the First Fiscal Quarter. 6/16/25 - Financial updated last week. We added two more CCA's/Settlement Champions that began 6/15/25 and they will begin their work on reducing 12+ month closings in August. These will be added to the initiative and it will be transferred to Lisa Transue as the IO. 5/19/25 - FINANCIALS WILL BE QUARTERLY. FINANCE SAID THERE ARE NO CHANGES TO BE MADE AND WILL BE INPUT IN JUNE FOR MAY. 5/7/25 - Financials will be quarterly. They will be available after May and to be input for May. 4/16/25 - The financials will not only be available quarterly and will not be available until 4/30/25. Financials will be updated prior to 5/15/25 and money step will begin at that point. 4/14/25 - Updated to L3 and waiting for approval. 3/3/25 - Now in L2, but questions on getting to L3 from finance. Working with Kami Griggs to get those addressed and the green light for L3. Settlement champions are in full swing and working. 1/27/25 - Meeting with Kami Griggs and Kendra Yarbrough on Baseline and data for savings was completed on 1/23/25. Data was sent to them to update Planview to get to L2. 1/20/25 - Still unable to work through Financial questions so Reid and I are working with Kendra Yarbrough and Kami Griggs to have a call to update. 1/13/25 - Moved to L2, but kicked back with financial questions. Working on answering thase questions to update to re-submit to L2. Call with Sedgwick to finalize Savings expected for the anticipated start of savings on 2/1/25. | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2025-03-03 | 2025-12-01
Business Only Initiative: Improve Subrogation Results - Workers' Compensatio | 88344 | 7703 | Business Only Initiative | SGA - Legal | SG&A | Gerald Hogue, Nancy Chiesa | On Track | Update Friday, Jue 6, 2025 Have entered the actuals for the month of May. For the month of May the incurred was $2,756,159.01 and the subrogation team brought in 15.49% or $426,793.63. From an expense standpoint we are positive for $14,192.42. Prior to the new team the 17% cost would have been $72,554.92 compared to our new fix cost of $58,362.50. Our returns continue to be higher than expected as for May our forecast (average for FY24) was $1,597,111.85 and actual recovery was $2,756,159.01. Update Friday, May 30, 2025 Initiative was accepted in L5 There are no updates at this time until we received the subrogation results for May. Once we receive the May results same will be posted in the financial section of Planview. Update Friday May 16, 2025 Initiative was submitted to L5 on May 12, 2025 No other update at this time. Will continue to input actual results on a monthly basis when received. Update 2 on Monday May 12, 2025 Initiative has been submitted to L5 Update Monday May 12, 2025 Actuals have been input into the system. During the month of April the Rate of Recovery was 28.84%. Recovery before expenses was $694,073.63. After expenses the recovery was $636,711.13. If you compare to prior recovery of 17% our recovery was higher by $59,800.02. Update Monday May 5, 2025 The subrogatoin report from Sedgwick has been recceived. Working on the results for April and should have the actuals in the system by the end of this week. Update Friday April 25, 2025 This was approved to move to L4. The next actuals will be input next month when they arrive. Other than the acceptance to L4 there is no other update until next month. Update Monday April 21, 2025 There is no update at this time. The actuals have already been entered into Planview and this has been submitted to L4. Each month we will continue to enter the actuals and move to L5 at the appropriate time. Update Friday 4/11/2025 On Thursday 4/10/2025 I submitted the initiative to L4. Last week the financials where updated for the month of March which was the 3rd month of actuals Money step was updated about 2 weeks ago Update Wednesday 4/2/2025 Have received the updated the March Acutals into the system. We had actuals at 23% for the month of March. This is the 3rd month of actuals and we should be able to move this to L-4 Update 3/28/2025 Have updated the exit rate Update Monday March 24, 2025 No change at this time. The actuals have been placed in the system from February. We anticipate receiving March actuals next week. Once same is received will reach out to determine if we can go to L4. Also in Planview we had previously input our exit rate the the 27% rate of recovery target. We have reached out to Kendra Yarbrough to determine if we need to go out farther with exit rate. Update Monday March 17, 2025 Last week the financials were input into the system. There are no updates at this time until we receive the financial information on the subrogation recovery in March. We are still in stage L3 at this time. Once we get the actuals for March we may need to adjust the forecast depending on the results. Once we finalize the forecast we should be able to move this to stage L4. I will have a meeting with Kendra to discuss. Update Monday March 10, 2025 The financials have been input into the financial screen. The new subrogation team had an actual rate of recovery of 31.01% with our forecast being 12%. If we have another succussful month with higher results in March we will consider re-forecasting our rate of recovery. Update Monday March 3, 2024 Have received the February numbers and it looks like we have a good month of recovery. Will need to update the financials in the system. Update Monday Feb, 24, 2025 There are no updates for this week. Was moved to L3 and we have input the first actuals form January into the system. Once we have the second month of actuals we will take a look at the forecast and see if we need to update same. | K: L5 | Completed | L5 | 2024-09-04 | 2024-12-02
Business Only Initiative: Bottom 20 Facilities Review | 88352 | 7704 | Business Only Initiative | SGA - Legal | SG&A | Ed Kinslow, Nancy Chiesa | On Track | 1/16/26 STATUS UPDATE: REMAINS ON HOLD. Plan is to remove Bottom 20 and integrate/relocate to the Medcor intake pilot initiative. 1/6/25 STATUS UPDATE: REMAINS ON HOLD. 1/1/26 STATUS UPDATE: REMAINS ON HOLD. 12/18/25 STATUS UPDATE: REMAINS ON HOLD. 12/4/25 STATUS UPDATE: REMAINS ON HOLD. 11/24/25 STATUS UPDATE: NO CHANGE. ON HOLD. 11/14/25 STATUS UPDATE: NO CHANGE. ON HOLD. 11/7/25 STATUS UPDATE: NO CHANGE. ON HOLD. 10/31/25 STATUS UPDATE: NO CHANGE. 10/24/25 STATUS UPDATE: NO CHANGE. CONTINUES ON HOLD. 10/13/25 STATUS UPDATE: NO CHANGE. CONTINUES ON HOLD. 09/30/2025 STATUS UPDATE: ON HOLD 09/23/2025 STATUS UPDATE: This initiative will be suspended pending the Medcor Intake pilot and to get through Peak. We will revisit how this will look thereafter based on the pilot and Network 2.0 optimization. 09/12/2025 STATUS UPDATE: No new updates at this time. 09/08/2025 STATUS UPDATE: Medcor Intake Pilot continues to progress, launch scheduled for OCT 1. QAT teams will present to Steering Committee 09/12/2025. 09/02/2025 STATUS UPDATE: Actuals entered. 08/25/2025 STATUS UPDATE: QATs will be presenting to the Steering Committee on 09/12/2025. Medcor Intake Pilot continues to progress, anticipated launch OCT 1 2025. 08/14/2025 STATUS UPDATE: Acutals for Bottom 20 Initiaitve from QATs will be entered at the beginning of Sept for the 6-month tracking period of FEB-AUG 2025. 08/05/2025 STATUS UPDATE: The intake pilot is in the planning process; the stations for the pilot have been identified. The processes have been presented to the Compliance and Safety departments. The takeaways from the meetings are in progress and the launch of the pilot has been tentatively moved to OCT 1 as a result. Anticipated progression to L4 is January 2026. 08/02/2025 STATUS UPDATE: No changes. 07/24/2025 STATUS UPDATE: No changes. 07/15/2025 STATUS UPDATE: No changes. 07/07/2025 STATUS UPDATE: Medcor Intake Pilot forecasted financials have been input and pilot is tentatively scheduled to begin 08/01/2025. 06/27/2025 STATUS UPDATE: In the process of determining the baseline for the Medcor Intake pilot to add to financials. Will set forecast for lag time reduction. 06/23/2025 STATUS UPDATE: No change. 06/13/2025 STATUS UPDATE: No changes. 06/09/2025 STATUS UPDATE: Continuing to measure QAT results, no changes currently 05/30/2025 STATUS UPDATE: No change. 05/23/2025 STATUS UPDATE: No change. 05/16/2025 STATUS UPDATE: No Change, EOY data will be available at the end of MAY, numbers will be updated at that time. Currently the QATs are making great progress on the determined root cause. 05/12/2025 STATUS UPDATE: No change. 05/02/2025 STATUS UPDATE: No change. 04/25/2025 STATUS UPDATE: No change 04/18/2025 STATUS UPDATE: No change 04/11/2025 STATUS UPDATE: Progress continues in individual QATs and charters being added to DQC 04/04/2025 STATUS UPDATE: Approved for L3; continuing QATs and tracking progress at bi-weekly meetings. 03/31/2025 STATUS UPDATE: Completed finance re-baselining exercise. 03/28/2025 STATUS UPDATE: Approved for L3 03/21/2025 STATUS UPDATE: Financials entered and Submitted to L3!!!! 03/14/2025 STATUS UPDATE: Financials have been submitted for review and will be input into Planview once approved to move to L3, milestones have been added and updated. Progression into L3 is expected for FY25. 02/28/2025 STATUS UPDATE: no change 02/21/2025 STATUS UPDATE: Financials are being reviewed and will be input upon approval. 02/14/2025 STATUS UPDATE: Financials are ready to be input into Planview, a meeting with Kami Griggs is set for Monday, 02/17/2025 to discuss and move forward; 12/02/2024 - STATUS UPDATE: Brainstorming QATs and charters for each are complete. QAT meetings will resume after peak and determine root causes to encourage positive results moving forward. 12/9/24 - No change since last week. Meetings to re | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-02-11 | 2025-09-01
Business Only Initiative: AMEA Legal Project Forward Phase 2 | 81221 | 8210 | Business Only Initiative | SGA - Legal | SG&A | Yukiko Masuda, Doreen Tan | On Track | 04/21/2026 No update | K: L5 | Active | L5 Feedback Requested | 2024-07-22 | 2025-05-30
Business Only Initiative: Liability Settlement Days Initiative | 92506 | 8244 | Business Only Initiative | SGA - Legal | SG&A | James Filous, Gloria Krotec | On Track | 6/6/25- FY25 Total Reserve Salvage is $8,385,220. No other change in status 5/30/25- May reserve salvage totaled $2,567,006 5/23/25 No change in status 5/16/25 No change is status 5/9/25 No change in status 5/2/25 No change in status 4/24/25 No change is status 4/18/25 No change in status from the last update. 4/11/25- L5 approved. No other change in status. 4/4/25- Submitted to L5. Settlement days events are being finalized for April and May 2025. 3/31/25 Re-baseline exercise completed. In L4 stage. No discrepancies between actuals and forecast. Settlement days events are being finalized for April and May 2025. 3/24/25- In L4 stage. No discrepancies between actuals and forecast. Settlement days events are being finalized for April and May 2025. 3/17/25- In L4 stage. No discrepancies between actuals and forecast. Settlement days events are being finalized for April and May 2025. 3/7/25- In L4 stage. No discrepancies between actuals and forecast. No February actuals to enter, no settlement days for the month. Upcoming settlement days are being finalized. 2/28/25 In L4 stage. No discrepancies between actuals and forecast. 2/17/25 Initiative waiting for L4 approval. No actuals for January as there were no scheduled settlement days for the month. Upcoming settlement days are being planned 2/10/25- Three months of acutuals have been verified. Submitting the intitaitive for L4 appoval. 2/3/25- December actuals have been entered. Need 3 months of acutuals to move to L4. Settlement Days – Liability Claims (DRIVE 92505) (Filous) - The Liability Claims team conducts informal settlement conferences with plaintiff attorneys and their clients to attempt claims resolutions. This Drive initiative is a collaborative effort designed to reduce claims costs, reduce cycle time, improve our closing ratio, and lower our average incurred by providing opportunities for both sides to resolve a significant number of claims in a one- or two-day session, avoiding the posturing of more traditional mediations. Through a series of process and tracking enhancements, savings are determined by calculating indemnity and expense reserve salvage on a case-by-case basis. The initiative kicked off on November 1, 2024, and has produced positive results thus far. To date, there have been 16 settlement day events held producing a total savings of $4,052,554. The Settlement Day Drive team continues to meet regularly to refine the process and to develop ways to bolster the program. Next steps include retraining the liability claims team, panel counsel, and Gallagher Bassett on the benefits and positive impact Settlement Days has on our key performance indicators. | K: L5 | Completed | L5 | 2024-11-06 | 2024-12-31
Business Only Initiative: Share Smartly | 15997 | 8260 | Business Only Initiative | SGA - Legal | SG&A | Christy Conrad, Alexis Serio | On Track | 6-16-25: Lifecycle Status updated as "Completed." 6-6-25: On track. No update. 5-31-25: On track. No update. 5-27-25: On track. No update. 5-16-25: On track, entered April 2025 actuals. 5-12-25: On track. No update. 5-5-25: On track. No update. 4-25-25: On track. No update. 4-18-25: On track, entered March 2025 actuals. 4-11-25: On track. No update. 4-7-25: No update. 3-28-25: L5 submission approved. Revalue for baseline and exit rate FY26-FY28 complete. 3-27-25: FY26-FY28 revalued. Submitted to L5. :) 3-21-25: We are awaiting review of KPI information by Finance so we can update and finalize. At that time, we will submit to L5. 3-14-25: We provided February Actuals by 3/10. We are awaiting review of KPI information by Finance so we can update and finalize. At that time, we will submit to L5. 3-7-25: The primary IO reviewed the KPIs based on the initiative's shift in focus to certain programs and we provided that information to Finance for review. Once the KPI numbers are updated, we will submit to L5. 2-28-25: KPI review and verification by the primary IO is underway. Once those numbers are verified and/or updated, we will submit to L5. 2-21-25: We updated forecast through 2027. The initiative's focus shifted to certain programs and those will be the focus going forward. KPI verification is underway by the primary IO. Once KPIs are verified, we will submit to L5. 2-14-25: IOs reviewing Finance's recommended actuals and forecast for the Share Smartly initiative. No changes made to the KPIs as they require a review by the primary IO. Per Finance, must overwrite Planview with the correct numbers. Will complete prior to COB 2/17. 2-10-25: IOs and Finance are doing a KPR review for baseline hours and costs due to an initiative update/changes. 2-3-2025: IOs and Finance are doing a KPI review for baseline hours and costs due to an initiative updates/changes. 1-27-25: Finance review of recent changes from April 2024 to December 2024 regarding NRB and forecast NRB for FY25. 1-20-25: Edited information from April 2024 to December 2024 regarding NRB and Benefit Actuals minus Cost Actuals. 1-13-25: Editing information regarding NRB and Benefit Actuals minus Cost Actuals. 1-6-25: 2024 staff changes require a review of reported cost/savings for (Jun-Nov) and forecast projections going forward. 12-30-24: Reviewing staff changes for both reported cost/savings (Jun-Nov) and forecast projections going forwrad. 12-23-24: Reviewing staff changes for both reported cost/savings (Jun-Nov) and forecast projections going forward. 12-16-24: Reviewing staff changes for both reported cost/savings (Jun-Nov) and forecast projections going forward. 12-9-24: Changes in staffing require a review of both cost/savings for November actuals, and forecast projections going forward. 12-2-24: On track 11-25-24: On track 11-18-24: October 2024 actuals entered. No update, on track 11-11-24: On track 4-3-23: sent back to L2 stage, after being approved for L3 and submitted for L4, in order to break out savings further by operating company 4-17-23: approved back to L3 and resubmitting for L4 Implementation Cost tracking complete | K: L5 | Completed | L5 | 2023-02-15 | 2024-04-01
Business Only Initiative: On Site Nurse Triage | 88544 | 8268 | Business Only Initiative | SGA - Legal | SG&A | Ed Kinslow | On Track | 4/13/26 - Updating to L5 12/3/25 - Discussed with George Oswald and the checklist for L4 is up to date and completed properly. Money step mareked completed since March when we started the project in March. We have been realizing savings and are now 9 months in for savings. The contract was in place in March. The money step was thought to be when we were saving at full savings for over 6 months. Adding the ontract for the March start date to the initiative. Link to money step evidence: https://fedex.pvcloud.com/planview/ContentManagement/readdoc.aspx?dsn=fdxprod&id=16746 9/29/25 - Utilization is moving in the right direction and self care is moving in the right direction. 8/18/25 - Updated financials/savings last week. Still working on Utilization and lag for MEMH. Moving forward with Indianapolis, Woodbridge and Atlanta. Contract through Encore and now with Business Transactions. Meeting wtih Indianapolis this week to work to schedule a visit to the location to meet with Sr. Leadership to explain the program and benefits along with looking for a location for the Nurses to be placed. 6/16/25 - Financial updated last week. We are working to add Indianapolis, Atlanta and Woodbridge. They will be entered into Encore and the addendums to the contract/work orders will be reviewed by BTG attorney and we will hopefully be able to launch Indianapolis in August. 5/12/25 - Working now to add 3 locations. Looking at Indianapolis, Atlanta and Woodbridge. Possible start date for one location beginning 7/1/25. 4/14/25 - Recently submitted to L3 and approved. Once we have 3 months of results, will work for submission to L4. Target date 7/22/25. Results to date are at 89% self-care. 3/12/25 -Now in L2 and questions for update to L3. Kami Griggs and I will be working to get it updated to L3. On-Site nurses started 3/3/25 in Rialto and MEMH. 3/3/25 - Now in L2 and questions for update to L3. Kami Griggs and I will be working to get it updated to L3. On-Site nurses started 3/3/25 in Rialto and MEMH. 1/27/25 - Meeting with Kami Griggs and Kendra Yarbrough on Baseline and data for savings was completed on 1/23/25. Data was sent to them to update Planview to get to L2. Still working through Contract issues and another call with Medcor and Business Transactions attorney is scheduled for 1/30/25 for contract finalization. 1/20/25 - Still unable to work through Financial questions so Reid and I are working with Kendra Yarbrough and Kami Griggs to have a call to update. 1/13/25 -Still working through contract issues. Call with Medcor and Business Transactions attorney set for tomorrow on the appendix review. Moved to L2 but pushed back for questions on financials. Working on that to re-submit to L2. Memphis scope completed and Rialto scope also completed 1/8/25 with Medcor, Safety and Operations. Start date for clinics is now anticipated for 3/1/25. | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2024-08-30 | 2025-10-31
Business Only Initiative: Nurse Line and Injury Reporting | 585 | 8271 | Business Only Initiative | SGA - Legal | SG&A | Ed Kinslow | On Track | 6/16/25 - Financial updated last week. Now will be having discussions to combine both Nurse Line initiatives into one so we can start reporting on Surface, Network Operations and other opcos separately. 5/12/25 - Working fo get the initiative to L5. 4/21/25 - Now in L4. Will be progressing to L5 by 5/15/25. Emails with Utilization rates sent to all Regionsl VP's by MD Jim English with the goal of increasing Utilization which will drive savings. 4/14/25 - Reviewing for submission to L5 by 4/21/25. Continuing to work on increased utilization. Updated financials. 3/28/25 Completed re-baslline exercise for FY25 and updated to FY28 exit rate with Kimi Griggs. 3/12/25 - Still need financials/savings and continued follow up with data analyst to get the numbers. 3/3/25 - Continuing with plan to increase Utilizations. Dashboard now includes Legacy Express locations and that will help tremendously with utilization. 2/17/25 - Continuing with plan to increase Utilizations. MD Jim English will be on the next Safety Council call to present the utilization and benefits on 2/25/24 2/3/25 - Continue to work on higher utilization to get savings in line with previous months savings. See plan below: Nurse Line Utilization Action Plan: •Network wide Communication with Nurse Line LGL 134 and 135 Training links. oStatus: FLC has finished their completion of making trainings “One FedEx” and is now available and a communication is being drafted for releas by 2/3/25. oWith this communication, we will re-introduce the Digital Signage for NL. •Communication prepared for Airport FedEx locations that have AT’s. Communication will provide clarity on the use of NL vs. AT’s. This should follow a meeting with the VP’s responsible for those locations. •Meeting with Memphis Hub Safety scheduled for 12/3 to discuss Utilization. •Meeting with Memphis Hub Day Sort VP scheduled for 12/3. One topic of discussion will be Utilization. •Working to schedule a meeting with Safety and Operations for Surface, Office and Logistics on utilization and possible additional training needs. Opportunities: •Regular visibility of utilization for all locations. •Possible re-forecast due to decrease in claims for some opcos. •Regular communications with utilization numbers. | K: L5 | Completed | L5 | 2022-10-20 | 2023-05-31
Business Only Initiative: Liability Subrogation Initiative | 91568 | 8327 | Business Only Initiative | SGA - Legal | SG&A | Jean Givner | On Track | 6/3/25 - Received May 2025 results. Initial total is $665,863.80 which, by GB's account, puts the total for FY25 at the sum of $6,921,086. The FY goal was $6.9 mil! 5/23/25 - Initiative results are behind plan by $1,331,624 through April 2025. It is unlikely that this full amount will be received in May. . Projecting about a third of that deficit will be recovered, which should bring total for the FY to approximately $6mil. This would be an increase over FY24 results. 5/20/25 - Received April 2025 results, noting recoveries in the amount of $423,446.71. Total is just over $5.56 mil for the FY. Would need a very strong month of May recoveries to meet the goal for FY25. 5/12/25 - No change. Holding for report from vendor to document savings. 4/28/25 - No change. Holding for monthly update on savings for the month of April. Should be able to enter same by middle of May 2025. 4/11/25: No change other than initiative is now in L5 state gate. 4/4/25: We continue to work with FEC and GB to improve processes for recoveries. A communication has been prepared to distribute in the Source and shoud be posted during the week of 4/7/25. GB also had great results in March, $668,533 (gross) which brings us to $5,271,602 for the FY. Only need $1,628,398 over the next two months to meet the target we set. However, we are just shy of $430k from exceeding last year! 3/31/2025: Updated financials to show the $1.2 mil delta for actuals expected from FY24-FY25. Also rebaselined/projected out to May 2027. 2/28/25: Working with accounting and finance to determine the actual amount of monies received and coded as subrogation. 1/20/25: a. Updating the money step to earlier in the FY to match the date of the change to process (Nov 2024). Also note there is still a dependency on accounting to identify the amounts actually wired to FX as subro. Likewise, the coding for subro accounting is being changed for easier identification of claims and opportunities. This accounting and coding should be completed by end of Jan 2025. b. No decision made yet on the internal staffing opportunity from former Ground RAP team to ECRM. The MD of that unit believes a business case will be completed by March 2025. c. The initiative team also continues to work with GB on improving the process to obtain information from internal FX contacts (facility and global vehicles) to support their proof of damages needed to the responsible parties to collect money owed. The FX communications team is holding for approval from Safety to put out an article in the Source related to accident reporting, completion of FNOL, and cooperating with GB.. 2/4/2025 - Actuals for Nov 2024 and Dec 2024 have been entered. Still working on communication campaign to enlist the cooperation from internal stakeholders for requests for documentation needed by Gallagher Bassett. | K: L5 | Completed | L5 | 2024-09-18 | 2025-06-18
Business Only Initiative: Corporate secretarial work vendor change | 19323 | 8370 | Business Only Initiative | SGA - Legal | SG&A | Shogo Osaka | On Track |  | K: L5 | Completed | L5 | 2022-12-01 | 2024-01-01
Business Only Initiative: Optimise the orgnaisation | 19322 | 8392 | Business Only Initiative | SGA - Legal | SG&A | Yukiko Masuda | On Track | 06/06/2025 No update. It's been over 12 months since the initiative achieved L5. | K: L5 | Completed | L5 | 2023-03-08 | 2023-08-01
Business Only Initiative: Outside Counsel Optimization | 2972 | 8944 | Business Only Initiative | SGA - Legal | SG&A | Joseph Milcoff, DeVona Hopkins | On Track | 6/13/2025. Submitted to L5. Capturing savings from negotiated discounts. 6/6/2025. Submitted to L5. Capturing savings from negotiated discounts. 5/30/2025. Submitted to L5. Capturing savings from negotiated discounts. 5/23/2025. Submitted to L5. Capturing savings from negotiated discounts. 5/16/2025. Workstreams are negotiating and implementing additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. 5/9/2025. Workstreams are negotiating and implementing additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. 5/2/2025. Workstreams are negotiating and implementing additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. 4/25/2025. Workstreams are negotiating and implementing additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. 4/18/2025. Workstreams are negotiating and implementing additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. 4/11/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Continuing to negotiate additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. Submitted for L4. 4/4/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Continuing to negotiate additional new rates/alternative fee arrangements. Capturing early savings resulting from negotiated discounts. Submitted for L4. 3/28/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Assuming these steps are completed, new rates/alternative fee arrangements are negotiated, and the team working on outside counsel guidelines completes by EOFY, 3 months of mature benefits should be reached at end of FY26Q1, enabling submission for L4. Capturing early savings resulting from negotiated discounts. Updated NRB baseline/exit rate. 3/21/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Assuming these steps are completed, new rates/alternative fee arrangements are negotiated, and the team working on outside counsel guidelines completes by EOFY, 3 months of mature benefits should be reached at end of FY26Q1, enabling submission for L4. Capturing early savings resulting from negotiated discounts. 3/14/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Assuming these steps are completed, new rates/alternative fee arrangements are negotiated, and the team working on outside counsel guidelines completes by EOFY, 3 months of mature benefits should be reached at end of FY26Q1, enabling submission for L4. Capturing early savings resulting from negotiated discounts. 3/6/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Assuming these steps are completed, new rates/alternative fee arrangements are negotiated, and the team working on outside counsel guidelines completes by EOFY, 3 months of mature benefits should be reached at end of FY26Q1, enabling submission for L4. Capturing early savings resulting from negotiated discounts. 2/27/2025. Workstreams are continuing spend analysis, developing negotiation strategy, and attempting to align with Sourcing initiative. Assuming these steps are completed, new rates/alternative fee arrangements are negotiated, and the team working on outside counsel guidelines completes by EOFY, 3 months of mature benefits should be reached at end of FY26Q1, enabling submission for L4. Capturing early savings resulting from nego | K: L5 | Completed | L5 | 2023-01-16 | 2026-03-19
Business Only Initiative: Nurse Line Injury Triage | 30023 | 8981 | Business Only Initiative | SGA - Legal | SG&A | Ed Kinslow, Jim English | On Track | 4/13/26 - Financials updated. In line for submission to L5, but not moved for not meeting projections. Not sure this is correct and will revisit with Project Manager. 9/29/25 - Continuing to work on increased utilization so we can get our savings to the estimated amount and get this moved to L%. 8/25/25 - Initiative rejected for L5 since it is not meeting plan. Need to determine if this initiative should be combined with original NL or if it should be re-forecasted. 6/16/25 - Financial updated last week. Now will be having discussions to combine both Nurse Line initiatives into one so we can start reporting on Surface, Network Operations and other opcos separately. 5/12/25 - Working to have the initiative in L5 by 5/15/25. Continuing with increasing Utilization. 4/21/25 - Now in L4. Will be progressing to L5 by 5/15/25. Emails with Utilization rates sent to all Regionsl VP's by MD Jim English with the goal of increasing Utilization which will drive savings. 4/14/25 - Submitted to L4 and waiting for approval. Continuing to work on Utilization rate. Updated financials. 4/2/25 - Submitted to L4. 3/28/25 Completed re-baslline exercise for FY25 and updated to FY28 exit rate with Kimi Griggs. 3/12/25 - Still need financials/savings and continued follow up with data analyst to get the numbers. 3/3/25 - Continuing with plan to increase Utilizations. Dashboard now includes Legacy Express locations and that will help tremendously with utilization. Money step will need to be moved to reflect the change when we can expect the utilization to the proper consistent level. Working with finance to change. 2/17/25 - Continuing with plan to increase Utilizations. MD Jim English will be on the next Safety Council call to present the utilization and benefits on 2/25/24. 2/6/25 - Reviewed initiative for progression to L4. Understanding that L4 requires the initiative to be in the money step, this initiative is not yet at the money step. We need more consistent utilization to get us to that step and we are working on the action plan set forth in the previous updates to make that happen. Keys to the increase in utilization are: * Regular utilization results for all locations - Data team in ECRM is working to that goal * Communication to all with training links 2/3/5 - Continue to work work on increase of utilization. Negative savings a result of low utilization and data team is working to get Utilization rates for all locations to help field push utilization for savings to match projections. Communication to go to specific express locations with Athletic Trainers on Nurse Line utilization as the first line of contact when an injur occurs. Jim English is having calls with VP's and MD's of those locations to discuss the benefits of the Nurse Line first as the injury triage to be used. Nurse Line Utilization Action Plan: •Network wide Communication with Nurse Line LGL 134 and 135 Training links. Links are now available and the communication is being worked. oStatus: FLC has finished their completion of making trainings “One FedEx” and is now available and a communication is being drafted for releas by 2/12/25. oWith this communication, we will re-introduce the Digital Signage for NL. •Communication prepared for Airport FedEx locations that have AT’s. Communication will provide clarity on the use of NL vs. AT’s. This should follow a meeting with the VP’s responsible for those locations. •Meeting with Memphis Hub Safety scheduled for 12/3 to discuss Utilization. Completed •Meeting with Memphis Hub Day Sort VP scheduled for 12/3. One topic of discussion will be Utilization.Completed •Working to schedule a meeting with Safety and Operations for Surface, Office and Logistics on utilization and possible additional training needs. Opportunities: •Regular visibility of utilization for all locations. •Possible re-forecast due to decrease in claims for some opcos. •Regular communications with utilization num | K: L5 | Active | L5 Feedback Requested | 2023-05-24 | 2025-02-28
Business Only Initiative: ECRM Legal Bill Review | 81647 | 8982 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho, Jim English | On Track | 04.22.26 - Actuals updated today with received reports. 03.18.26 - Actuals updated today. 02/16/26 - Reports not received from vendor yet; Should receive by tomorrow 2/17. 01/19/25 - Actuals & KPI's updated for December. 01/06/25 - Actuals will be updated when month end reports are completed. Have requested from vendor to be received prior to due date of Jan 13th. 10/27/25 - Acutals & KPI's updated. Progressing through to L5 today. 10/10/25- Actuals updated through August. 08/12/25 - Actuals updated. will progress to L5 today. 07/14/25-Actuals updated, vendor reports received today. 05/12/25 - Actuals updated, vendor reports received this morning. Will progress to L5 once we have enough actuals post L4. 04/14/25 - Actuals for March updated 4.14.25. Initiative moved to L4. 03.31.25 - Re-Baseline Complete 03.11.25 - Actuals updated today. 02/26/25 - Actuals and milestones updated. 02/12/25 - Conf call with Finance. Update net benefits and added in expenses for legal bill review fees. Adjusted KPIs. Submitting to L3 today. 01/27/2025 - Updated financials per Finance request and KPIs. 1st report/scorecard received from outside vendor. 1/10/25 - Implementation of program is underway with all panel firms for Liability and WC. Will move this initiative into L3 by next week. 12/9/24 - Contract is finalized; implementation of program will begin 12/9/24. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-02-01 | 2025-06-30
Business Only Initiative: Save Fast and Spend Wisely | 15998 | 9255 | Business Only Initiative | SGA - Legal | SG&A | Joseph Milcoff, DeVona Hopkins | On Track | 4/24/2026. March actuals have been updated. Run rate of recurring benefits is roughly $840K per month; run rate of expenses is recurring negative impacts is roughly $550K per month; and net savings of $300K per month +/-. February and March recurring benefits and net savings exceed run rate due to replacement of one outside counsel from K&L Gates with Bill Whitman of the Commercial Litigation team at trial of the FedEx v. National Union matter. Manually added exit rate to financials; re-submitted to L5. 4/17/2026. March actuals have been updated. Run rate of recurring benefits is roughly $840K per month; run rate of expenses is recurring negative impacts is roughly $550K per month; and net savings of $300K per month +/-. February and March recurring benefits and net savings exceed run rate due to replacement of one outside counsel from K&L Gates with Bill Whitman of the Commercial Litigation team at trial of the FedEx v. National Union matter. Submitted to L5. 4/10/2026. March actuals have been updated. Run rate of recurring benefits is roughly $840K per month; run rate of expenses is recurring negative impacts is roughly $550K per month; and net savings of $300K per month +/-. February and March recurring benefits and net savings exceed run rate due to replacement of one outside counsel from K&L Gates with Bill Whitman of the Commercial Litigation team at trial of the FedEx v. National Union matter. 4/3/2026. Although net should remain relatively consistent, near term shifts in Benefits and Expense anticipated; after March Actuals are entered this initiative will be submitted for reevaluation for L5 approval. 3/20/2026. Although net should remain relatively consistent, near term shifts in Benefits and Expense anticipated; after March Actuals are entered this initiative will be submitted for reevaluation for L5 approval. 3/6/2026. Although net should remain relatively consistent, near term shifts in Benefits and Expense anticipated; after March Actuals are entered this initiative will be submitted for reevaluation for L5 approval. 3/2/2016. Outstanding offers have been accepted; all have commenced employment. Subject to backfill approvals and barring excessive volume, we are at steady state. We have submitted to L5, pending approval. 2/20/2026. Outstanding offers have been accepted. With the exception of one records management specialist, all have commenced employment. One SFSW FTE remains to be backfilled due to a promotion. We have submitted to L4, pending approval. 2/13/2026. Outstanding offers have been accepted. With the exception of one records management specialist, all have commenced employment. One SFSW FTE remains to be backfilled due to a promotion. We have submitted to L4, pending approval. 2/6/2026. Outstanding offers have been accepted. With the exception of one records management specialist, all have commenced employment. One SFSW FTE remains to be backfilled due to a promotion. We have submitted to L4, pending approval. 1/30/2026. We have extended offers to the Phase 2 records management specialist and the Phase 3 paralegal. The Phase 3 attorney accepted our offer and has a start date of 2/2/2026. We are transitioning national coordinating counsel for joint employment to the in house team. 1/23/2026. With the exception of one records management specialist that was subjected to the hiring pause and is now posted, Phase 2 positions have been filled. Remaining Phase 3 hires include one attorney and one paralegal. The attorney accepted our offer and has a start date of 2/2/2026. We are transitioning national coordinating counsel for joint employment to the in house team. We are in the interview and offer process for the unfilled positions. 1/19/2026. With the exception of one records management specialist that was subjected to the hiring pause and is now posted, Phase 2 positions have been filled. Remaining Phase 3 hires include one attorney and one paralegal. We are transitioning national coordina | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2023-01-17 | 2026-04-10
Business Only Initiative: Legal Research resources/subscriptions | 15999 | 9256 | Business Only Initiative | SGA - Legal | SG&A | Nadeana Cook, Justin Blashock | On Track | 2/9/26 - Bloomberg contract has been finalized; per previous direction, intiiative will be submitted to L5 after updating for Jan actuals. 2/2/26 - no update from last week; Bloomberg contract still in legal review 1/26/26 - no update from last week; Bloomberg contract still in legal review 1/21/26 - no update from last week; Bloomberg contract still in legal review 1/12/26 - no update from last week; Bloomberg contract still in legal review 1/5/26 - no update from last week; Bloomberg contract still in legal review 12/30/25 - no update from last week; Bloomberg contract still in legal review 12/22/25 - no update from last week 12/15/25 - no update from last week 12/8/25 - no update from last week 12/1/25 - Bloomberg contract is still in legal review; decision was made to keep open until that contract was finalized 11/24/25 - Bloomberg contract is still in legal review 11/17/25 - Bloomberg contract is still in legal review; will work with Legal Operations director to determine if we can proceed with moving this initiative to L5 despite the contract not being finalized 11/3/25 - October actuals have been added, but Bloomberg contract is still in legal review; will work with Legal Operations director to determine if we can proceed with moving this initiative to L5 despite the contract not being finalized 10/28/25 - to my knowledge, there have been ongoing negotiations with Bloomberg regarding the new contract, but nothing has been finalized yet. 10/20/25 - awaiting confirmation that Bloomberg contract has been finalized. 10/13/25 - will be confirming to see if Bloomberg contract has been finalized yet so this initiative can be moved to L5. 10/6/25 - per last week's update, this initiative will move to L5 after Bloomberg Law contract is finalized. 9/29/25 - September actuals have been added; however, renewal of the Bloomberg Law contract is pending, so amount and terms of agreement may change. My recommendation is to keep initiative in L4 until those details have been finalized. 9/23/25 - no updates from last week. 9/8/25 - updating August actuals; initiative will be marked for L5 after submitting Sept actuals next month. 9/3/25 - no updates from last week. 8/25/25 - no updates from last week. 8/18/25 - no update from last week. 8/11/25 - no update from last week. 8/5/25 - per discussion with Finance, initiative will be marked for L5 after updating actuals for 2 more months. 7/28/25 - no update from last week. 7/22/25 - Since there are other vendor contracts up for renewal in the coming weeks, this initiative will stay in L4, and we will continue to update actuals. 7/14/25 - LexisNexis contract has been executed; will confirm if initiative can be moved to L5 7/7/25 - Awaiting confirmation that LexisNexis contract has been executed. 6/23/25 - Awaiting confirmation that LexisNexis contract has been executed. 6/16/25 - LexisNexis contract is in final stage of legal review. Once completed, initiative should be able to move to L5. 6/10/25 - we continue to consolidate legal research subscription contracts that are coming up for renewal. Validating Phase 3 milestones for completion. Initiative will be progressing to L5 soon. 5/29/25 - we continue to consolidate legal research subscription contracts that are coming up for renewal. Phase 1 and Phase 2 milestones are complete. Phase 3 milstones are underway with the goal to complete by May 31, 2025. Initiative is at L4 progressing to L5 by end of the FY. 5/23/25 - we continue to consolidate legal research subscription contracts that are coming up for renewal. Phase 1 and Phase 2 milestones are complete. Phase 3 milstones are underway with the goal to complete by May 31, 2025. Initiative is at L4 progressing to L5 by end of the FY. 05.15.2025 - we continue to consolidate legal research subscription contracts that are coming up for renewal. Phase 1 and Phase 2 milestones are complete. Phase 3 milstones are underway with the goal to complete by May 3 | K: L5 | Active | L5 | 2023-03-01 | 2025-12-31
Business w/ Tech Initiative: Legal technologies for Legal | 16000 | 9257 | Business w/ Tech Initiative | SGA - Legal | SG&A | Rochandra Prewitt, Justin Blashock | On Track | 11/6/25 - Requesting that this initiative be cancelled because the Document Management and Global Deployment of Onit requests were approved for L1, and requests for the other pieces of this initiative will be entered into Planview in the coming weeks. 11/3/25 - The Document Management and Global Deployment of Onit requests have been created and are currently in triage. The request covering remote local collections will also be entered into Planview. There will be further discussion on the legal intake and court reporter technology pieces before entering Planview requests. Based on the direction from IT Leadership, this initiative will be cancelled. 10/28/25 -will begin moving forward with creating separate initiatives for each piece of this larger initiative this week. 10/20/25 - working with NetDocs on business case for document management business continuity initiative; ESPM to schedule a meeting with finance for further discussion on Onit international initiative. 10/13/25 - will move forward with document management business continuity initiative, awaiting information from NetDocs to help with business case. Meeting with ESPM team today to get feedback on LBC for Onit international initiative. 10/6/25 - with news of NetDocuments acquiring OpenText, the document management business continuity initiative will be placed on a brief hold until Legal can discuss next steps with NetDocuments. Plan is for the Onit business with tech initiative to be submitted by the end of the week. 9/29/25 - currently working on the documentation for Document Management business continuity initiative and LBC & financials for new Onit business with tech initiative. 9/23/25 - plan is to split this initiative into smaller pieces; we are looking into submitting the Document Management piece as a business continuity initiative and the Onit work as a separate business with tech initiative. Before submitting to Planview, we will share with Enterprise Services team to ensure we have sufficient information. 9/8/25 - meeting with ESPM to take place tomorrow to review stop work criteria and the initiative's progression, better understand what is causing the current hold, and explore how we can add more value to help move it forward. 9/3/25 - a meeting is scheduled with ESPM on 9/9 to review stop work criteria and the initiative's progression, better understand what is causing the current hold, and explore how we can add more value to help move it forward. 8/25/25 - no update from last week. 8/18/25 - will start looking into splitting these items into separate initiatives as a workaround 8/11/25 - no updates at this time; this initiative along with some other business with tech initiatives will be discussed with Gina to help move them forward 8/5/25 - updated request type to resubmit to L2. 7/28/25 - continue gathering financial information to update baseline and target values. 7/22/25 - continue gathering financial information for baseline and target values. 7/14/25 - waiting for quotes from vendors and FY25 court reporting expense and international legal fee spend. 7/7/25 - continue gathering updated quotes from vendors. 6/23/25 - continue gathering updated quotes from vendors. 6/16/25 - LBC has been updated and working to get updated financials before submitting to L2 6/9/25 - because this initiative has been identified as a work-stop, financials and LBC are being updated in preparation for the move back to L1 5/29/25 - received guidance from Finance and will continue to work with IT on L2 architecture documentation. 5/23/25 - meeting with Finance next week to discuss what financials need to be added/updated and working with IT on L2 architecture documentation. 5/19/25 - continue working with IT on LBC documents. 5/13/25 - continue working with IT on LBC documents. 5/6/25 - continue working with IT on LBC documents. 4/24/25 update - continue working with IT on LBC documents. 4/15/25 update - continue working with IT on LBC | C: L1 | Cancelled | L1 Feedback Requested | 2023-06-01 | 2026-05-29
Business w/ Tech Initiative: Automate SP Assessment Workflow | 16003 | 9260 | Business w/ Tech Initiative | SGA - Legal | SG&A | Barrett Mitchell | On Track | 11/18/24--Continuing to see monthly savings and inputting over past 6 months. Likely eligible for L5 advancement. given pace of savings. 12/2/24- Will update with November savings numbers when available. No further update. 12/10/24-November numbers updated, 12/15/24-No update 12/27/24--No update 1/6/25--December actuals entered/submitted for L5 status given over 3 months of recurrng benefits 1/22/25--no additonal update; deleted actuals per Mike Glass request 2/3/25--Inputted January Actuals 2/7/25--Actuals differ from forecast on monthly basis, but projected forecast should meet actuals on an annualized basis 2/17/25--no update 2/21/25- no update 3/3/25--updated actuals 3/17/25--no update 4/3/25--updated actuals 4/13/25--completed baseline/exit-rate assessment 4/21/25-no update 4/29/25-no update 5/8/25--April actuals updated 6/2/25--Update May actuals | K: L5 | Completed | L5 | 2023-02-14 | 2024-05-31
Business Only Initiative: Sales Contract Support | 17441 | 9349 | Business Only Initiative | SGA - Legal | SG&A | Gabriela J. Kuzmik, Leendert Creyf, Magda Drecko | Some Issues | 13.03.2026 - The initiative is decided to be put on Hold until some related projects start again and it can be re-baselined. 19.01.2026 - October actuals entered. Nothing new to report. FY26-FY28 values have been re-baselined. Few Milestones on hold. Reason : Before implementing new thresholds, more granular management data needs to be obtained to assess appropriate and tailored threshold levels and avoid scaling back Sales support unduly. L4 estimated date - update : 05/31/2027. After further discussions with ACE management, ACE completion is currently estimated end of FY27. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-08-28 | 2027-05-31
Business Only Initiative: Procurement contracts | 17442 | 9351 | Business Only Initiative | SGA - Legal | SG&A | Agata Gajdzik, Ingrid Van Hamme, Leendert Creyf | On Track | 06/06/2025 - In L5. No further updates. Exempt from re-evaluation. | K: L5 | Completed | L5 | 2022-02-01 | 2023-12-29
Business Only Initiative: WC Medical Outcome Improvements | 22257 | 9482 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho, Jill Newman | On Track | 6/6/25: There is no change to report this week. Our next update will be in mid-June when we expect to receive the financial data for May. 5/30/2025: There is no change to report this week. Our next update will be in mid-June when we expect to receive the financial data for May. 5/23/2025: There is no change to report this week. Our next update will be in mid-June when we expect to receive the financial data for May. 5/16/2025: For FY25 as of 4/30/25, the actual savings percentage for bill review with this vendor exceeded expectations, resulting in $35.7M in additional savings compared to $32.5M we expected. The KPI confirmed actual savings for FY25 as of 4/30/25 greatly exceeded expectations, totaling $311M against a forecast of $242M. 5/12/2025: There is no change to report at this time. Our next update will be later this week when we expect to receive the financial data for April. 5/2/2025: There is no change to report this week. Our next update will be in mid-May when we expect to receive the financial data for April. 4/25/2025: There is no chnage to report this week. Our next update will be in mid-May when we expect to receive the financial data for April. 4/18/2025: There is no change to report this week. Our next update will be in mid-May when we expect to receive the financial data for April. 4/11/2025: For FY25 as of 3/31/25, the actual savings percentage for bill review with this vendor exceeded expectations, resulting in $32.6M in additional savings compared to $29.5M we expected. The KPI confirmed actual savings for FY25 as of 3/31/25 greatly exceeded expectations, totaling $284M against a forecast of $220M. 4/4/2025: There is no change to report this week. Our next update will be in mid-april when we expect to receive the financial data for March. 3/28/25: There is no change to report this week. Our next update will be in mid-April when we expect to receive the financial data for March. 3/23/25: There is no change to report this week as data on this initiative is received mid-month each month We expect to receive March's financial data in mid-April and will not have any change to report until then. 3/14/25: For FY25 as of 2/28/25, the actual savings percentage for bill review with this vendor exceeded expectations, resulting in $29.5M in additional savings compared to the $26.5M we expected. The KPI confirmed actual savings for FY25 as of 2/28/25 greatly exceeded expectations, totaling $253M against a forecast of $198M. 3/7/25: We expect to receive February's financial data by Monday, 3/10/25, and plan to update Planview upon receipt. 2/28/25: There is no change to report this week, as data on this initiative is received mid-month each month. We expect to receive February's financial data in mid-March and will not have any change to report until then. 2/21/25: Data on this initiative is received mid-month each month, so we will not have any change to report until February's financial data is received in mid-March. 2/14/25: Actual additional cost savings for January 2025 were $2,995,000 against a forecast of $2,950,000. Actual additional cost savings for FYTD25 as of 1/31/25 were $25,525,000, which is $1,925,000 more than the forecasted amount of $23,600,000 for FYTD25. KPI confirmed actual savings for January 2025 totaled $27M against a forecast of $22M for the month. For FYTD25 as of 1/31/25, confirmed actual savings totaled $226M, which is $50M more than the forecast of $176M. 2/10/25: Data on this initiative is received mid-month each month, so we will not have any change to report until January's financial data is received in mid-February. 2/3/25: As noted last week, data on this initiative is received mid-month each month, so we will not have any change to report until January's financial data is received in mid-February. 1/27/25: Data on this initiative is received monthly around the middle of the month, so we will not have any c | K: L5 | Completed | L5 | 2023-01-02 | 2024-07-31
Business Only Initiative: FEC Litigation Efficiency Gains |  | 88644 | Business Only Initiative | SGA - Legal | SG&A | Joseph Milcoff, Jeana Littrell | On Track | 6/13/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 6/6/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 5/30/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 5/23/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 5/16/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 5/9/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 5/2/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 4/25/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 4/18/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 4/11/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 4/4/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. Updated NRB baseline/exit rate. 3/28/2025. Submitted for L5. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. Updated NRB baseline/exit rate pending coordination with Finance. 3/21/2025. Approved for L4. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 3/14/2025. Approved for L4. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 3/6/2025. Approved for L4. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 2/28/2025. Submitted to L4. 2/21/2025. Submitted to L4. 2/17/2025. Savings are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. On track for money step. 2/10/2025. Savings increased based on FY25 H2 actuals, are on track, and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 2/04/2025. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 1/27/2025. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 1/20/2025. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 1/13/2025. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 1/6/2025. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 12/30/2024. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 12/23/2024. Savings are on track and entered in financials. New matters are being diverted from outside law firms to in house litigation teams. 12/10/2024. Savings are on track a | K: L5 | Completed | L5 | 2024-06-03 | 2025-05-30
Business Only Initiative: ALSP Utilization |  | 88680 | Business Only Initiative | SGA - Legal | SG&A | Denielle Hansberry, Jeana Littrell | On Track | 3/31/26 UPDATE: 1. CAN CLOSE THIS OUT - APPROVAL RECEIVED. 3/23/26 UPDATE: 1. Transactions group meeting was postponed to give stakeholders time to gather information from additional questions list from vendor. Scheduled for 3/25. 2. RegOps OSHA Tracker awaiting movement through L1 processes. 3. LegalOpos update TBD. 3/16/26 UPDATE: 1. RegOps OSHA Tracker pulled into separate initiative - moving through L1 to get this going now. 2. Transactions groups are meeting with Integreon to formalize next steps for SOW - pilot project for MNDA and related low-risk agreements. Meeting scheduled for 3/19 - should be able to pull this out and move it through DRIVE shortly thereafter. 3. LegalOps working on solutions, but likely will shut this initiative down then start new initiative to push that forward. 3/9/26 UPDATE: 1. RegOps OSHA Tracker Initiative pulled out into separate initiative - in the L0 phase as of 3/6/26 2. All 3 ALSPs met our 3/6/26 deadline: Consilio officially cannot meet the savings we need for Transactions Group. Elevate is reviewing to see if they can meet the bar we set, and Integreon says they are willing to meet the bar we set (no more than $15K a month, hoping that the work will grow over time). Scheduling a meeting between Transactions teams stakeholders and Integreon ASAP to see if we can nail down a proposal to seek L3 approval for as quickly as possible. 3. Legal Ops - still investigating - hope to have understanding of selected initiative and decision on moving forward by end of March 4. LAC and CIC will continue evaluating options for ALSP support, but if they decide to move forward, will be under separate initiatives. 5. Goal is to close this initiative or officially move it forward by end of March, with conclusion of LegalOps decision. 2/23/26 UPDATE: 1. FXO and FXL have fully explored their options and chosen not to proceed with ALSPs at this time. 2. Consilio proposal for joint sales initiative being negotiated now. includes LegalOps resource, which needs more information from internal LegalOps team to proceed. 3. Sales Transactions also reviewing integreon and elevate prposals 4. RegOps negotiating with Elevate to consider OSHA tracker 5. LAC discussion with ALSP delayed, but being rescheduled 6. CIC considering further discussion, but likely won't proceed by 3/6/26 2/10/26 UPDATE: 1. Proposal from Consilio for Sales, Comm., and Tech Transactions, FXL, FXO, and Legal Ops being returned with counter proposal and questions within the week 2. Proposals for same group from Elevate and Integreon being reviewed 3. RegOps Counter to Elevate being evaluated with followup questions 4. FXO meeting with Consilio re: subpoena responses 5. LAC and CIC engaging Elevate in separate meetings to evaluate support 6. Unlikely AMEA's CoE (Shogo's team) will provide value over Consilio's support for litigation - that evaluation likely complete. 1/29/26 UPDATE: 1. Requested financials for selected pilot projects from legal Ops and FXO again on 1/28/26 2. Consilio joint resource proposal received and reviewed with Consilio team 1/26/26. Joint stakeholder review session scheduled fro 2/5/26 (joint proposal requires joint assessment/feedback/response). FOCUS of this proposal is human resources, not AI/automation 3. Elevate proposal to RegOps reviewed, M. Mattila leading response 4. Elevate proposal for contract support provided to transactions/FXL/FXO teams. Review forthcoming. 5. Elevate proposal for LegalOps provided, review by LegalOps ongoing. 6. Integreon - revised proposal to LegalOps provided 1/26/26, review by LegalOps ongoing. 1/19/26 UPDATE: 1. proposals from Elevate and Consilio anticipated by Tues/Wed, 1/20-1/21 this week 2. Financials from sales transactions received to finalize internal business case 3. Reg Ops WPS team met with Elevate last week to finalize open questions for OSHA tracker so proposal could be provided 1/12/26 UPDATE: 1. RegOps, LegalOps following up in meetings with Elev | E: L2 | Cancelled | L2
Business Only Initiative: Create Centralized Legal Operations Organization |  | 88683 | Business Only Initiative | SGA - Legal | SG&A | James A. Davis | On Track | Week of May 19 - Placing Initiative On Hold until get exec decision on legal ops redesign and implementation. Week of May 12 - Enterer May actuals. Awaiting final exec decision on legal ops redesign and implementation. Will review benefit of the initiative at that time and decide whether the anticipated savings will be recognized or if the initiative should be cancelled. Week of May 5 - No changes. Compiling April actuals. Week of Apri 28 - No changes. Week of April 21 - No changes. Week of April 14 - Added March Acutals. Still awaiting final decision from Legal exec team on legal ops redesign for full implementation. Has and will further affect actuals and timing of savings. Week of April 7 - No developments. Will add acutals w/o April 14. Week of March 31 - No developments. Week of March 24 - No new developments. Revalued FY 26 - 28 complete. Rebaseline complete. Week of March 17 - No new developments. Week of March 10 - No new developments. February actuals entered. Week of March 3 - No new developments from last week. Still working to confirm potential reduction in savings. Week of Feb 24 - We may have discepencies with forecast and actuals in coming months/quarters due to decision to retain IT resources assisting with certain LAN requirements. Will work with leadership to determine if this will occur and will alter plan/forecast as required. Otherwise on track. Week of Feb 10 - On track. No descrepencies between forecast and actuals to date. Week of Dec. 2 - Completed Triage and moved to L1. Meeting with team to gather information on work to date. Week of Dec. 9 - Completed L1 and submitted for L2 review. Finance has contacted. Will provide feedback to Finance inquiry Week of Dec. 16 - Received feedback request from L2 review. Will provide that information as soon as possible and re-submit for approval. Week of Dec. 23 - Updated Money Step Date as requested. SL3 approval request for Inititaive sent Tracy Brightman for approval on 12/20. Week of Dec. 30 - Initiative moved to L3. Will begin process of completing tasks associated with this level and monitoring progress toward goals. Weeek of Jan. 27 - On track. Entered acutals for Dec during week of Jan 20th. Week of Feb. 3 - On track. No developments. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-22 | 2025-07-25
Business Only Initiative: FEC Business Transactions Group Efficiency Gains |  | 90060 | Business Only Initiative | SGA - Legal | SG&A | James A. Davis | On Track | Week of June 2 - Moved to Completed status. Finalizing May actuals for entry next week. Week of May 26 - No New developments. Week of May 19 - No new developments. Week of May 12 - Entered April Actuals. Savings going forward could be negatively impacted by need to engage outside counsel to cover work performed by paralegal going on STD. Week of May 5 - On Track. Compiling April actuals. Week of April 28 - On Track. Week of April 21 - On Track. Week of April 14. On track. Actuals added. Week of April 7 - On track. Will add actuals w/o April 14. Week of March 31 - Baseline/exit review completed week of March 17. No new developments. Week of March 24 -- No new developments. Week of March 17 - Revalued for FY25. Week of March 10 - Approved for submission to L4. Actuals will be entered after 3/10. The applicable spend is all from the ONIT system and invoices for each month are not due until the 10th. Will analyze this week and enter actuals when all applicable invoices have been received. Week of March 3 - No new developments. Provided requested information relative to submitting initiative to L4. Week of Feb 24 - Moved to L3. Input Actuals for period June 1 2024 - Jan 31 2025. Actuals were lower than forecast due to work continuing from FY24 that will conclude. Will work to review forecast at end of Q3 to determine if adjustments should be made for Q4FY25 and beyond. Week of Feb 10 - Included KPIs and corrected record to show savings will be "hard benefits" vs. "soft benefits". Re-submitted for review. With OneFedEx re-alingment of the Legal Business Transacations Teams from across the enterprise on June 1, 2024, we began moving legacy FXG overflow work from outside resources (law firms) back in house. The consolidated resources allowed for the transition of that work. The work remains in house and, assuming staffing levels for inhouse counsel remains at current levels, we should be able to retain all of that work in house and not have a need to utilize outside resources. Week of Dec. 23 - On Track. In SL2. Week of Dec. 30 - No Change. In SL2, awaiting Domain Lead Approval. Week of January 20 - On Track. Provided L2 Feedback. Savings are accuring. Week of January 27 - Additional L2 Feedback requested. Need to determine if savings are hard or soft. Week of February 3 - No new developments. On track. | K: L5 | Completed | L5 | 2024-06-03 | 2024-07-19
Business w/ Tech Initiative: Legal Technology for Litigation Support |  | 90063 | Business w/ Tech Initiative | SGA - Legal | SG&A | Sheronda E. Nelson, Justin Blashock, Tyler Koziar | On Track | 4/21/26-We are working with IT to understand next steps to advance forward. 4/6/26-We are working with IT to understand next steps to advance forward. 3/31/26-We are working with IT to understand next steps to advance forward. 3/16/26-We are working with IT to understand next steps to advance forward. 3/9/26-We are working with IT to understand next steps to advance forward. 3/2/26-We are working with IT to understand next steps to advance forward. 2/23/26-We are working with IT to understand next steps to advance forward. 2/9/26-We are working with IT to understand next steps to advance forward. 1/26/26-We are working with IT to understand next steps to advance forward. 1/19/26-We are working with IT to understand next steps to advance forward. 1/13/26-We are working with IT to understand next steps to advance forward. 1/5/26-We are working with IT to understand next steps to advance forward. 12/29/25-We are working with IT to understand next steps to advance forward. 12/19/25-We are working with IT to understand next steps to advance forward. 12/1/25-We are working with IT to understand next steps to advance forward. 11/24/25-We are working with IT to understand next steps to advance forward. 11/18/25-We are working with IT to understand next steps to advance forward. 11/10/25-We are working with IT to understand next steps to advance forward. 11/4/25-We are working with IT to understand next steps to advance forward. 10/27/25-We are working with IT to understand next steps to advance forward. 10/20/25-We are working with IT to understand next steps to advance forward. 10/13/25-We are working with IT to understand next steps to advance forward. 10/9/25-We are working with IT to understand next steps to advance forward. 9/29/25-We are working with IT to understand next steps to advance forward. 9/22/25-We are working with IT to understand next steps to advance forward. 9/15/25-We are working with IT to understand next steps to advance forward. 9/9/25-We are working with IT to understand next steps to advance forward. 9/3/25-We are working with IT to understand next steps to advance forward. 8/25/25-Still working to have this initiative resubmitted to L2; waiting on one last piece of information. We have made some revisions to the LBC and we are working to confirm the integration cost estimate for the Relativity-Onit integration. Once we have the confirmation needed, we will resubmit to L2 with the revised LBC. 8/18/25-Still working to have this initiative resubmitted to L2. We have made some revisions to the LBC and we are working to confirm the integration cost estimate for the Relativity-Onit integration. Once we have the confirmation needed, we will resubmit to L2 with the revised LBC. 8/11/25-Still working to have this initiative resubmitted to L2. We have made some revisions to the LBC and we are working to confirm the integration cost estimate for the Relativity-Onit integration as well as the estimated annual cost savings. Once we have the confirmations needed, we will resubmit to L2 with the revised LBC. 8/4/25-Working to have this initiative resubmitted to L2. We have made some revisions to the LBC and we are working to confirm the integration cost estimate for the Relativity-Onit integration as well as the estimated annual cost savings. Once we have the confirmations needed, we will resubmit to L2 with the revised LBC. 7/28/25 -Still working to respond to finance comments from the L2 review. LBC revisions are in progress and we are working to confirm the integration cost estimate for the Relativity-Onit integration. 7/22/25 - Working to respond to finance comments from L2 review. 7/15/25 - IO transferred from Justin Blashock to Sheronda Nelson. Working to respond to finance comments from L2 review. 7/7/25 - working on LBC revisions, estimate on cost to build Relativity-Onit integration is in process with Onit - estimated completion date is 7/14/25. 6/24/25 - working on | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Expand iCertis for Legal |  | 90069 | Business w/ Tech Initiative | SGA - Legal | SG&A | Rochandra Prewitt, Justin Blashock | On Track | 7/22/25 - based on discussion with Legal IT and Legal leadership, this initiative will be placed on hold until the RFP for the enterprise CLM is completed. 7/14/25 - this work may be paused due to the enterprise CLM initiative being stood up; a meeting has been scheduled with Legal VP sponsors and Legal IT leadership for tomorrow to discuss further. 7/7/25 - IT continuing to work on architecture docs. 6/23/35 - Architecture review is being scheduled by PEO. 6/16/25 - initiative was approved for L2, currently working with IT on L2 architecture documentation needed 6/11/25 - currently being reviewed finance domain lead 6/4/25 - initiative has been submitted to L2. 5/29/25 - received necessary guidance from Finance and will be submitting to L2 by the end of the week or end of day Monday. 5/23/25 - meeting with Finance next week to review and revise Financial information based on feedback provided and submit to L2. 5/13/25 - working to submit for L1 review. 5/6/25 - continue working with IT on LBC documents. 4/24/25 update - continue working with IT on LBC documents. 4/15/25 update - continue working with IT on LBC documents. Follow-up meeting to occur this week. 4/7/25 update - continuing work on "Ability To" statements. 4/1/25 update - met with EA on 3/31 and reviewed "Ability To" statements. Working to add more detail as requested by IT. 3/24/25 update - received quote from vendor for implemntation work. Working on LBC and with Enterprise Architech on L1 items. 3/18/25 update - discussed scope/LBC with VPs last week. Working with Enterprise Architect on items needed for L1. 3/9/25 update - working with Enterprise Architect on items needed for L1. 2/27/25 update - met with IT last week. L1 items in process. Follow-up meeting set for early next week. 2/20/25 update - meeting with IT scheduled for F 2/21 to discuss L1 requirements 2/13/25 update - waiting for enterprise architect assignment, LBC in process 2/4/25 update - waiting for enterprise architect assignment, LBC in process 1/20/25 update - waiting for enterprise architect assignment, LBC in process 1/14/25 update - waiting for enterprise architect assignment, LBC in process 1/6/25 update - waiting for enterprise architect assignment, LBC in process 12/24/24 update - waiting for enterprise architect assignment, LBC in process 12/16/24 update - waiting for enterprise architect assignment, LBC in process 12/10/24 update - next steps: waiting for EA assignment, build out LBC | E: L2 | On Hold | L2
Business Only Initiative: Liability Medical Bill and Record Review |  | 90164 | Business Only Initiative | SGA - Legal | SG&A | Jean Givner | On Track | 6/9/25 - pushing to L5 as we have over 3 months of documented "savings". Savings are noted to be soft so they are not tracked on the financial tab. 6/4/2025 - GB advises that reserve salvage from September 2024 through 4/30/25 amounts to $3.4 mil in medical cost savings since scaling the volume of submissions. 134 claims with total demands $22.7M and total settlements $6.4M would have settled at $9.8M, or $3.4M more, if not for the 15 pt savings differential (72% vs 57%) captured by using the Enlyte tool, minus $16K cost of using tool ($125/avg x 134 claims) 5/12/25 - Through the month of April, GB has increased their referrals to Enlyte (210 our of 1564 claims). The average savings between demand and settlement was 83% or a 75% savings if measuring the median. There were an additional 19 closures from the March results, for a total of 58 closures in April. 5/6/25 - Updating Milestones: Training Analytics, Expansion and target variables will be outlined. Still in L4 stagegate and will continue to document the soft savings. Monthly reports should be received from GB by the 10th of the month to address the prior month's results. 4/28/25 - Soft savings, so finaniclas are not tracked outside of spreadsheets that will be tracked in the milestones. 4/11/25 - no change. Still on track. Initiative is now at SL4 4/4/25 - Milestone for training will be reached on 4/15/25 as we deliver a presentation to the internal ECRM team and our outside counsel. No updates on "savings" for the month of March yet. 3/31/25 - No rebaseline necessary as all Soft Benefits. Also removing KPIs. Will attach results via a monthly spreadsheet and continous update of notes. PV used for visibility as there are no downstream impacts to link to tech or epics. 3/26/2025 - Entered milestone and Money Step Dates 3/17/2025 - Meeting held with Finance on 3/12/25 and followed by an email from P. Duffy. As a result, providing additional information to support the NRB sum of $4.5 mil. Holding for L2 approval and will also need to forecast to FY28 once approved. 2/27/25 - Starting 3/3/25, all BI and MCU teams at GB will submit claims to Enlyte. Criteria to submit has been refined. Next steps are to rerun the numbers with demand caps and segmenting data by branches (BI vs. MCU) and the type of review (bill only or bill combined with record review). 2/25/25 - Updated the demand Description under Basic Information to reflect how the program works and expected calculation of "savings". Will push to L2 as a result. 2/22/25 - Decision made to move back to L1 to recalculate the path to savings based on the number of referrals and the costs for the referrals. Will use a variable of 12% savings on reserves for cases included in the review vs. those that are not in the program. 2/21/25 - GB has identified a differential for the delta related to demand vs. settlement amount on Enlyte vs. Non-Enlyte claims. Starting at 12% but can fluctuate as the population of claims that have settled and completed the Enlyte review is relatively small at this time. Expanding the program to project approx 50 demand packages per month average rolling 3 months. Baseline utilization will target all demands received with over $5k in medical bills. Level 1 submission will include all demands except for those noted in Level 2, which would include high severity/complex treatment, complex medical issues/injuries, surgeries, overnight hospitialization/inpatient stays and treatment for extended periods (e.g. >12 months). 2/17/25 - Determined that the bill review vendor (Enlyte) bulk bills GB for the entirety of the work put through the process. Level 1 pricing is $110 (for bill review/review of demand packages, and $520 (for nurse case review of medical records). The pilot is expanding and the charges for the services will be paid off the claim file. 2/3/25 - working with GB to clarify costs of the Enlyte vendor in response to Finance's inquiry. Upon receipt, should be able to get | K: L5 | Completed | L5 | 2024-09-03 | 2029-01-29
Business Only Initiative: Law Firm Invoice Review |  | 90448 | Business Only Initiative | SGA - Legal | SG&A | Rochandra Prewitt, Justin Blashock, Nadeana Cook, Sheronda E. Nelson | On Track | 2/16/26 - made the necessary changes requested by Finance and resubmitted to L3 2/13/26 - made the necessary changes requested by Finance and will resubmit to L3; I've opened a PDSM ticket to update the L1 NRB to the correct value 2/9/26 - initiative not approved by Finance; will look into their notes and make the necessary corrections. 1/26/26 - submitted PDSM ticket to update baseline value based on invoice data received from EU Finance so that the information in the LBC document and Planview will match; once updates have beem made, I will be able to resubmit to L3 1/21/26 - received EU finance contact and will reach out to them for assistance gathering invoice data. 1/12/26 - based on discussion with George, a comprehensive list of FY25 EU law firm invoices need to be included for audit purposes; I have reached out to George and Mary Alice about a contact in Finance that can assist with gathering this information. 12/22/25 - as discussed with George and Mary Alice on Friday, I have attached an updated LBC that includes the EU and US legal spend being tracked as part of this spend management program; will resubmit to L3. 12/8/25 - as discussed with George and Mary Alice, the LBC has been attached to the initiative and resubmitted for L3 approval. 12/4/25 - met with George and Mary Alice from Finance yesterday to confirm the consolidation of the law firm invoice review initiatives. 12/2/25 - per guidance from Finance, the Law Firm Invoice Review 2.0 initiative has been cancelled, and the baseline and target values and L1 NRB have been updated to include the 2.0 savings; awaiting approval from Finance domain lead 11/3/25 - waiting to receive FY25 outside counsel spend to ensure baseline and target value accuracy. 10/28/25 - waiting to receive amount of FY25 outside counsel spend. 10/20/25 - after further discussion, we are taking another look at financials to ensure accuracy before submission. 10/13/25 - it was determined that all savings would be considered hard savings and count towards Legal's Surge goals; resubmitting to L3 this week. 10/7/25 - the decision was made that soft savings would count towards Legal's Surge goals. Financials have been modified based on meeting with Deloitte, and initiative will be resubmitted to L3. 10/6/25 - awaiting feedback regarding soft savings counting towards Surge goals. 9/29/25 - Legal is meeting with Deloitte today to discuss and modify financials for this initiative to ensure the numbers are aligned with Finance's definition of hard and soft savings. After updating the financials, the initiative will be resubmitted to L3. 9/23/25 - based on meeting with Finance & Deloitte last week, Legal will meet separately to determine hard savings for this initiative, and current savings that are listed will be moved to soft savings. 8/25/25- no update from last week. 8/18/25 - received numbers from Deloitte and will reach out to Finance to ensure accurate information is added to financial plan 8/11/25 - awaiting numbers from Deloitte 8/5/25 - Deloitte is expected to provide savings from invoice reviews next week. 7/28/25 - no update/change since last week. 7/22/25 - no update/change since last week. 7/14/25 - no update/change since last week. 7/7/25 - no update/change since last week. 6/23/25 - no update/change since last week. 6/16/25 - no update/change since last week. 6/10/25 - no update/change since last week. 6/4/25 - no update/change since last week. 5/29/25 - no update/change since last week. 5/23/25 - no update since last week. 05.15.2025 - no update since last week. | G: L3 | Active | L3 | 2025-01-01 | 2026-05-29
Business Only Initiative: Optimize hiring location |  | 92628 | Business Only Initiative | SGA - Legal | SG&A | Shogo Osaka | On Track | cost saving is on track and KPI is at the scheduled level. no risk is identified for the coming months. Entered L5 on July 12, 2025. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-02-03 | 2025-04-15
Business Only Initiative: ECRM SP Collection/Preservation |  | 109647 | Business Only Initiative | SGA - Legal | SG&A | DeVona Hopkins, Julianne Camacho | On Track | Early stages of business case establishment. | E: L2 | On Hold | L2 Feedback Requested | 2025-04-01 | 2026-09-18
Business w/ Tech Initiative: Records Mgmt Process FEC Surface Physical Records |  | 110331 | Business w/ Tech Initiative | SGA - Legal | SG&A | Benjamin Ferron | On Track | 2/16/26: Drafting LBC | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: DraftPilot.AI for Legal |  | 114540 | Business w/ Tech Initiative | SGA - Legal | SG&A | Tyler Koziar | On Track | 20250822 - We will be engaging in a 90-day pilot.Results of the pilot will be incorporated into our go-forward plan.Initiative will be put on HOLD on Planview pending the results of the Pilot 20250811 - Succesfully created DraftPilot security group and completed ECCPRT request to have the DraftPilot add-in made available through the admin managed M365 apps in Microsoft Word. Confirmed that users within the security group were able to access DraftPilot add-in in Word. Working with DraftPilot to secure licenses for use of the application. 20250728 - Continuing to work the Legal management to escalate this request for review by the GenAI team 20250714 - Update for the last two weeks of work on this: 1. (ELS) advised me to contact InfoSec to see if an InfoSec FIRST was required for this. 2.InfoSec FIRST team responded with “this add-in may not require a FIRST request. I would recommend reaching out to the Enterprise Collaboration & Communication team (Cliff Gurlen). They manage Microsoft products and have their own review process for unblocking Microsoft apps and add-ins”. 3.Cliff Gurlen (IT Mgr., ECCT) advised me to reach out to Phil Gartrell (IT Mgr., Global Workspace Engineering) 4.Phil advises me to open a ticket with the Cyber Security team for guidance on having this Microsoft add-in enabled as “FedEx has not yet incorporated a formalized process to request, register, or gain approval for items such as plug in or extensions”. 5.Cyber Security team advises that we need to open a FIRST request and submit this to the GenAI Governance team. 6.I am now working on submitting a FIRST and GenAI review to try to move this forward. Time is a flat circle. 20250707 - Sent a follow-up to the Cyber Security team (INC031218380) requesting an update or next steps regarding the enablement of the DraftPilot Word add-in. 20250701 - Opened a request with IT cyber security team to determine how to allow Microsoft Word add-ins to be enabled or permitted through the Microsoft store. Hopefully a solution can be determined outside of Planview as we have made no progress with this initiative in the last 2 months and this system continues to be an exceptional waste of everyone's time. 20250611 - Waiting for guidance from Enterprise IT team supporting legal on how to answer "Biz with Tech" LBC questions as well as how to proceed with submitting InfoSec FIRST and GenAI reviews 20250605 - Working with Finance domain to complete the financial questions for the LBC and waiting for confirmation from Gerald Neal in Enterprise IT on how to proceed with the FIRST request for InfoSec evaluation. Hoping to have both of these items completed by the end of the week. | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: Hazardous Waste & OWS (Oil Water Separators) |  | 98291 | Business Only Initiative | SGA - Legal | SG&A | Natalie Owens, Rafael Rodriguez, Ryan Nelson, Damodar Naik | On Track | 11-10-25 - NRO In the process of putting project on hold. The project has been determined that the project is not currently appropriate for the Planview process. After speaking with Finance, it doesn’t appear that the project will be able to show values by the current deadlines. The project will continue outside of the Planview process as value may be found in consolidating waste vendor contracts between legacy Express and legacy Ground. This task and process will be aligned during the on-going policy alignment. In addition, outside of Planview, Environmental will continue to look for cost savings and work with procurement to decrease current vendor pricing. The project will continue to be evaluated and if appropriate will be activated in the future. 11-3-25 - NRO Continue to have meetings with Finance and Management teams to discuss project moving forward. Project may need to be placed on hold while additional data and next steps are evaluated. 10-27-25 - NRO Currently collecting the necessary information for the initiative including contracts, spend details, billing codes, and waste category data. Initiative is slow moving with little progress due to the complex nature of the information. Data is contained in multiple cost codes, billing platforms, and grandfathered in vendors amongst the opcos. Initial conversations with Finance is indicating that savings will likely not be found or recognized in FY26. At this time, it appears that savings will only be achieved via renegotiated contracted pricing. Significant work will be required to align the data into usable information to begin the vendor bidding process. Once the project is sent out for bid, costing negotiations will begin. At this time, discussion may be needed to place the project on hold until data collection is made. Team will continue to work through the challenges and attempt to continue with forward progress. 10-20-25 - NRO Scheduled a meeting with Finance to discuss current status of the project. Working with management team to collect background information regarding the various hazardous waste vendors that may be utilized by the legacy Express OpCo. Trying to identify all available contracts for Hazardous waste and Oil/Water separator vendors. 10-14-25 - NRO Project is holding steady. Update meeting planned with Finance for this week. Working with Environmental team and Procurement on finalizing scope of HDR project assistance plan. 10-6-25 - NRO Received updated scope of work from HDR. Will review with procurement team and discuss next steps with Management team. Finance meeting was just a check-in and review of the provided data. Preliminary spend information is between $15-$17-million. Initial thoughts on reducing spend include reviewing multiple vendor numbers for the same vendor and seeing if a contract can be consolidated to better rates. Also looking to reduce the number of vendors currently utilized by field operations. 9-29-25 - NRO Scheduled meeting with consultant HDR on 9-30-25 to discuss scope changes. Finance has scheduled a follow up discussion on project financials on 9-30-25. This information is needed need for the LBC. On Friday 9-26-25, Legacy Express team members reported to the IO that they did not have the authority to dictate who was managing the Hazardous Waste at the field locations. Therefore, there is a potential for additional smaller local vendors to be removing regulated and hazardous waste from field locations. At this time, an additional four vendors have been identified that will need to be consolidated/removed from managing hazardous waste at the end of the RFP process. 9-23-25 - NRO Still waiting updated scope of work. Have not received any updates from Finance. 9-16-25 - NRO Met with internal team to discuss HDR proposal. Sent feedback to HDR and awaiting new scope of work. 9-8-25 - NRO Waiting for MD comment on HDR proposal and update from Finance regarding preliminary financials. 9-2-25 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC-BR-3-BRECOxATM_Endors Elect Spitfire Operation |  | 153698 | Business Only Initiative | SGA - Legal | SG&A | Artur Seixas, Claudia D. Prado, Sandra Parras | On Track | Nov 21, 2025: Entered by Sandra Parras (EID 488838) -> Due to LAC Officer decision as of Oct 1, 2025 all BRECO related requests that are not regulatory are on HOLD until Jan 15, 2026. There will be a meeting mid Jan 2026 to determine the next steps for all BDE/BRECO related initiatives. This initiative should be moved to AMI Brazil DOM POD, Sandra is in process to enter a PDSM to move this initiative to that POD. OIC, VPS + ESPM cc FYI Dear BDE Core and Extended Team: With the recent announcement regarding Brazil Domestic Exit, it means the Brazil Domestic Enablement and Domestic Customer Integration (BDE) Project is canceled Some of you have asked me what should be done with the requests in Planview, Onspring and/or PPM as it relates to Brazil DOM or the other portfolios. Below please find a list of the Planview initiatives that should be canceled NLT Jan 31, 2026. A copy of this email should be attached to each initiative canceled. Job aid link: Setting Initiatives to On Hold-Cancel.pdf I want to thank you for all your efforts in the last few years with BDE and I hope we get to work together in the future Any questions please let me know Thanks Sandra | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Workman's Comp (WC) Severity |  | 161577 | Business Only Initiative | SGA - Legal | SG&A | Nancy Chiesa | On Track | 2/16/26: The QAT has moved into the Assess phase and new subteams have been identified. The team reduced the original 15 hypothesis to three areas of focus including a drill down into the 5 most costly States (CA, FL, PA, NJ and Illinois). Teams will be drilling into to data to determine where there is more frequency and higher costs. We anticipate to be in the build phase by early Fall and will start adding potential savings to overall numbers in this initiative by early 2027. There are several aspects of the costs that are uncontrollable such as inflation, more work hours (8M more hours is expected to equate to 10M more in claims costs), and IBNR from FY24 & FY25 that was reduced but may project upwards. There will not be much if any activity in this DRIVE initiative pending the QAT's progression and identification of controllable measures on the prevention and claims management side that can be quantified via tracking. 9/11/25 - We will be meeting with Oliver Wyman 9/19 to discuss their findings. After that discussion, we will internally discuss where to focus our efforts on reducing severity, and how to basline, quantify and track results. 9/22/25 UPDATE: We did meet with OW and discussed some of the observations including Express Courier trends. The dive into this will continue to and we are not yet at a point where we can fully assess the viability of a DRIVE initiative and/or baseline for same. UPDATE: 9/29/25 - We are continuing to receive data from Sedgwick and Enlyte. So far nothing glaring stands out that would point us in the direction of what the specific drivers of severity are. We believe there may be a nexus with location optimization that prompted job changes (lifting heavier boxes) but until we can get more data to clarify, we are not able to baseline or project savings. UPDATE 10/10/25: We are continuing to receive data from Enlyte on PT and PM trends. So far nothing glaring stands out that would point us in the direction of what the specific drivers of severity are, and nothing has been noted to rise to the level of having confidence with large savings. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Liability Settlement Scouts/GB Closure Program |  | 161580 | Business Only Initiative | SGA - Legal | SG&A | James Filous | On Track | 12/4/25- On hold due to GB resources being assigned to cross initiatives which will impact the consistency and maturity of the data for Settlement Scouts results. 11/21/25- No change is status 11/14/25- Securing baseline data and resubmitting to L2 11/7/25 Working with finance for L2 approval 11/3/25 Working with finance for L2 approval 10/24/25- No change in status 10/20/25- Working with finance for L2 approval 10/10/25- Waiting for finance to approve to L2 10/3/25- No change in status since the last update 9/26/25- No change is status. Working with business partners to provide supporting documentation for L2 9/22/25- No change in status. Submitted to L2. Working with business partners to provide requested supporting documentation 9/12/25- Submitted to L2. Working with business partners to provide requested supporting documentation. 9/4/25 Met with Gallagher Bassett to determine best method of capturing financial gains. Follow up meeting set for 9/12/25 | C: L1 | On Hold | L1 Feedback Requested | 2026-01-01 | 2026-01-01
Business Only Initiative: Rental Optimization |  | 161584 | Business Only Initiative | SGA - Legal | SG&A | James Filous | On Track | 4/24/26- March actuals entered in tracker. Variance in actuals vs forcast due in part to daily rate and underperforming cash out 4/17/26- No change, Gatering data for L5 submission 4/10/26- No change. Working towards L5 4/3/26- L4 approved. Working towards L5 3/27/26- Awaiting approval to L4 3/18/26- Submitted to L4. Awaiting a response 3/12/26- Feb 2026 actuals entered. 3/6/26 No change in status. Anticipating Feb actuals in early March 2/27/26 No change in status. Anticipating Feb actuals in early March 2/23/26 No change in status. Anticipating Feb actuals in early March 2/13/26 No change in status. Anticipating Feb actuals in early March 2/6/26 No change in status, waiting for actuals to move to L4 1/29/26 No change in status, waiting for actuals to move to L4 1/23/26 No change in status, waiting for actuals to move to L4 1/16/26 No change in status 1/6/26- No change in status 12/19/25- In L3, no change in status 12/12/25- No change in status 12/5/25- Approved to L3 11/21/25- No change is status 11/14/25 Submitted for L3 approval 11/7/25 Securing baseline from GB/positioning for L3 11/3/25- No change is status 10/24/25- Added financial tracker. Positioning for submission to L3 10/20/25- No change in status 10/10/25- Approved to L2 stage 10/3/25- No change is staus since the last update 9/26/25- GB has revised their projections. Baseline is now $4m, target value is now 1,770,976. Projected savings is now $2,229,024. Supporting documentation entered in content. 9/22/25- No change in status. Submitted to L2. Working with business partners to provide requested supporting documentation 9/12/25-Submitted to L2. Working with business partners to provide requested supporting documentation. 9/4/25- Meeting with Gallagher Bassett on 9/5/25 to determine best method of capturing/reporting financial results | I: L4 | Active | L4 | 2025-10-01 | 2026-04-29
Business Only Initiative: Enlyte 2.0 |  | 161730 | Business Only Initiative | SGA - Legal | SG&A | Jean Givner | On Track | 2/27/26 - Still hodling for actuals from the vendor to document the tracking to forecast. Soft savings at this point until actuals realized and documented. 2/16/2026 - Referrals increased to 744 (an increase of 60 referrals since Dec 2025). Avg demands (capped at $1mil) is $3,606,618 and avg settlements are $1,644,081. The forecast for FY26 is now $24,366,000.. Actuals are being requested in order to determine if this can be hard savings vs. soft savings. If the former, we will continue efforts to move to the next L Gate. 1/16/2026 - Proposed soft savings are outlined to be approximately $12mil. Same depends on the valuation of damages and demands presented on the liability claims. There is no specific formula to further predict savings. 10/27/2025 - No change. Still proposed as soft savings that will not hit the P&L. Have a meeting (10/30/25) with Gallagehr Bassett to optimize the tracking of savings. 10/17/25 - no change. Still pending L2 Approval. Working to document the net recurring benefits. See Attachment. 10/10/25 - still pending L2 approval as a need to add documentation that supports the $1.6M benefit calculation for the Lean Business Case, has been requested. Update provided with notation that the additional referrals to Enlyte will offer additional savings off of the settlement evaluations. The volume of closed claims since June 2026 where Enlyte was engaged is currently 310. The monthly volume increase from June to Sept is 22% and that is expected to increase each month. Accordingly, the savings will follow with this increase. 10/3/25 - Updated Net recuring benefits to reflect $1.6mil which is the differnce between baseline of $3.4mil and projected savings of $5mil. Savings are calculated by taking the difference between the average demand (capped t $1mil) and the average settlement, for all demands that are submitted to the vendor (Enlyte) for review. Also added the most recent metrics chart to outline savings through 9/12/25. Will push strategy for L2 approval at this time. 09/05/25 - Project start with baseline of FY25 results at $3.4 mil. Project is expected to provide a savings on indemnity up to $5mil based on enhancements to the claim management process, as well as additional volume of demand packages sent to the vendor (Enlyte). | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Bond Management |  | 161734 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho, Michelle Pitts | On Track | 02/16/26 - Bond UAT has begun with evaluation of all bonds and potential for cancellation or renewal. Team is also moving entire bond managment process into Riskonnect for tracking/management. 12/8/25: UAT for bond management has not kickedoff yet because of delays in another unrelated process. 11/30/25: UAT for bond management has not kickedoff yet because of delays in another unrelated process. 11/24/25: No update from last meeting. 11/12/25: UAT is estimated to kick-off in November still; however, the estimated go-live date is not until 6/1/26. 11/10/25: No update from last meeting. 10/27/25: No additional update since 10/10/25. 10/10/25: UAT to move bond management into RK did not commence on 10/1 as anticipated due to prioritization of other projects. Evaluation of bonds will start late October or early November. 9/29/25: Progressed to L2. Currently working through L2 checklist and should have completed within next 2 days. 9/12/25: LBC submitted for review. Money Step has been defined. UAT to move Bond Management into RK begins 10/1. Evaluation of bonds will commence in October-November timeframe. | E: L2 | Active | L2
Business Only Initiative: On-Site Nurse Triage 2.0 |  | 161740 | Business Only Initiative | SGA - Legal | SG&A | Ed Kinslow | On Track | 4/13/26 - Ready to move to L2. Meeting scheduled with Project Team for next steps for 4/14/26. 9/29/25 - Contract is finalized and just waiting for the signatures. We are starting the Nurses on-site at the Indy Hub starting on 10/20/25. Atlanta Hub is scheduled to b eopened in November and Woodbridge in January. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Bottom 20-Liability |  | 161745 | Business Only Initiative | SGA - Legal | SG&A | Joede McCullough, Crystal C. Snook | On Track | 4/24/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. Safety analytics team being engaged as well. 4/17/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. Safety analytics team being engaged as well. 4/10/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. Safety analytics team being engaged as well. 4/3/26 - Data correction efforts underway. Evaluation ongoing. Initative remains on hold. 3/27/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. 3/20/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. 3/13/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. 3/6/26 - Data accuracy fixes continue to be evaluated. Initative remains on hold. 2/19/26 - Issue identified with data accuracy. Fixes being evaluated. Do not expect any FY26 value due to delays. We are putting the initative on hold and will look to reactive next fiscal year or sooner if possible. 2/13/26 - Continued collaboration with build team to address questions/concerns. Meetings with some stateholders have been executed, more in the planning phase. 2/6/26 - Team calibration meetings set with ECRM. Meetings with stakeholders are being planned. 1/30/26 - LIFT software/platform functional and live. Access provided to team and introducted concepts. ECRM meetings with stakeholders are being planned. 1/23/26 - Meeting set for 1/28/26 intro of software to liability team. Discussions ongoing re: available data and understanding. 1/16/26 - Meeting set for 1/28/26 intro of software to liability team. Working with DSP team to ensure data integrity/make any fine adjustments necessary. Confirming how often data will be refreshed for tracking purposes, etc. Ongoing network adjustments (facility closures/opens/etc.) may be a challange. 1/9/26 - LIFT software, access, and process being forumulated and revised. Super user testing underway. 12/19/25 - LIFT software, access, and process being forumulated. 12/12/25 - Revised planned start and completion dates. LIFT software, access, and process being forumulated. 12/5/25 - LIFT software, access, and process being forumulated. 11/26/25 - Submitted to L3, pending review 11/21/25 - Submitted to L3, pending review 11/14/25 - Submitted to L3, pending review. 11/4/25 - This is a soft savings initiative. Please review the document titled "Bottom20 Business Case Template-v1 PlanView" for the financial structure and information. Thank you. 10/31/25 - Submitted to L3, pending review. 10/24/25 - Developing financal tracking abilities. Working with RM team. 10/17/25 - Moved into L2. Working with GB/RK data analytics team to source tracking data. Will begin working on L2 checklist. 10/10/25 - Completed LBC and submitted for L2 approval. 10/3/25 - Completed LBC and submitted for L2 approval. 9/29/25 - Completed LBC and submitted for L2 approval. 9/19/25 - Met with RM team to determine tracking abilities and suggested targets. Usuful reports identified. Contiuing to develop LBC. 9/10/25 - Continuing to develop financial rationale and baselines. Current known information has been updated. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2026-06-01 | 2026-06-30
Business Only Initiative: LC AI Initiative |  | 161752 | Business Only Initiative | SGA - Legal | SG&A | David Kadosh, Benjamin H. Arnold | On Track | 2/19/26 - This initiative is temporarily being placed on hold. The pilot program has been completed and we are now rolling out LegalMation nationwide across all panel counsel. There is a slow ramp up period as we are introducing LegalMation to each firm while gathering documents and building data. Very little to no savings will be realized in the current fiscal year, hence the reason for this temporary hold. We hope to begin to realize some financial savings in June or July of 2026, but that is contingent upon the speed and success of the rollout and subject to change. 10/10/25 - This initiative remains on track. FedEx just sent the final draft of the MSA to LM for approval. Outside counsel firms are meeting with LM next week in order to "soft launch" the 6-week Pilot period. This represents significant process towards the ultimate rollout when actual savings will be achievable at the scale contemplated by this Initiative. 9/19/25 - This initiative is on track. ECRM is currently in the process of gathering data, finalizing the Master Services Agreement, and we anticipate that the LegalMation Pilot will commence in approximately 60 days. Once the Pilot ends and the program rolls out, we anticipate net savings for a full calendar year between approximately $300k--$1M. For FY'26, that number will be truncated given the point in the fiscal year when the program will roll out across the country. We cannot report actuals at this time because the program has not formally begun. We will run a 45 day Pilot prior to rolling the program out nationwide across our entire outside defense counsel panel. | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: ECRM Virtual Defense Counsel Evaluation (DCE) |  | 161756 | Business Only Initiative | SGA - Legal | SG&A | Julianne Camacho | On Track | 09/08/2025 - New initiative approved by triage group on Friday, 9/5/25. Working to progress to L2 by end of week. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Law Firm Invoice Review 2.0 |  | 165690 | Business Only Initiative | SGA - Legal | SG&A | Rochandra Prewitt, Ravirajaganesh P, Rebecca Weaver, Rick Harball | On Track | 11/6/25 - after discussing with Finance, we are requesting that this initiative be cancelled because the effort will be tracked under the original law firm invoice review initiative (90448). 11/3/25 - LBC completed; submitting to L2 10/28/25 - LBC in progress; awaiting private matter spend for baseline value. 10/20/25 - LBC in progress. 10/13/25 - LBC still in progress. 10/6/25 - working on LBC | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: Onit Expansion for Legal |  | 168950 | Business w/ Tech Initiative | SGA - Legal | SG&A | Tyler Koziar, Nadeana Cook, Renee Allen, Sheronda E. Nelson | On Track | 4/21/26 - Nadeana and Monique to discuss budget info and determine how best to move forward with L2 financial projections for single initiative 4/2/26 - Renamed initiative to "Onit Expansion for Legal" to begin merging previous initiatives- Global Deployment of Onit (168950, in L2) and Onit 2.0/"Legal Technology for Litigation Support" (90063, in L1). Tyler to export financial projections from both initiatives to determine how best to combine them in the new Onit Expansion for Legal. 3/25/26 - Continuing discussion with Legal management regarding merging "Onit 2.0" and "Global Deployment of Onit" into a single initiative... 3/19/26 - Legal Ops and ELS management discussing moving "Onit 2.0" and "Global Deployment of Onit" forward as a single initiative. Teams will work with management to make a determination in this space. 3/12/26 - -Submitted to "Greenlight" step in Planview on 3/10/2026 -Per Megan Wolff from Enterprise Portfolio Management, this intiative will require L2 Architecture before it can be moved to the next step... -Gerald Neal from ELS to check the status of Tech Eval before to begin work on L2 architecture and establish timeframe (original go-live estimated for 9/1) -Current prioritization rank of 214 (vs DMS at 22) 3/10/26 - 3/10/26 - Transitioned IO from Ro to Tyler. Established weekly meetings (beginning this afternoon) with Legal and IT stakeholders to get status updates and guidance on pending action items. ***Tyler replaces Ro as IO*** 2/16/26 - PPM proposal is currently in screening proposal status; once proposal is approved, the project number will be added in Planview and submitted to SL3 2/13/26 - PPM proposal is currently in screening proposal status; once proposal is approved, the project number will be added in Planview and submitted to SL3 2/9/26 - awaiting business owner approval of PPM request 2/2/26 - currently working on PPM proposal after receiving required access on Friday 1/26/26 - currently filling out L2 checklist items; once completed, I will submit to L3. 12/22/25 - L1 Architecture Alignment has been completed; currently working on Finance's business case template as part of LBC and will submit to L2 once completed. 12/15/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM. 12/8/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM. 12/1/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM. 11/24/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM. 11/17/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM. On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: New Document Management System for Legal |  | 168954 | Business w/ Tech Initiative | SGA - Legal | SG&A | Tyler Koziar, Renee Allen | On Track | 4/21/26 - ELS continues work on L2 architectural documents... Received updated L2 costing spreadsheet from Finance to upload to initiative. 4/9/26 - ELS continues work on L2 architectural documents. ESPM also asked ELS/Legal Ops to submit a detailed L2 costing spreadsheet -entirely separate from Planview and all financial data already entered within- which we did. 4/2/26 - ESPM acknowledged "large disconnect" with Planview in IOs not having access to view status of L2 initiatives submitted to L3 and lack of any visibility for IOs to see or confirm required L2 architectural documents. Gerald from ELS is working on L2 architectural documents to send to ESPM who will then let me (the IO) know once this is completed before I can submit this to the next step because this is beyond Planview's capability. 3/25/26 - Submitted from L2 to L3 but was rejected and sent back by Enterprise Portfolio team without clear explanation of why or next steps. Repeated emails to ESPM contacts have yielded no clear instruction on why this initiative is not moving forward. Gerald from ELS to reach out to his ESPM contacts to try and get clarification on how to move this initiative forward in spite of Planview's many shortcomings as a project management system. 3/19/26 - Updated "One Time Soft Benefit" to $0. We will be reaching out to NetDocuments for help answering the two remaining L2 questions regarding "Time to Value" and "Incremental Funding Requirement" in an upcoming meeting. 3/12/26 -ELS submitted 'Tech Eval' for NetDocuments last Thursday, 3/5/2026 -Planview initiative in "Enter L2" status -Tyler to capture remaining financial and prioritization fields from L2 form and send to Justin/Monique/Nadeana for review before submitting to next step -Current prioritization rank of 22 3/10/26 - Transitioned IO from Ro to Tyler. Established weekly meetings (beginning this afternoon) with Legal and IT stakeholders to get status updates and guidance on pending action items. **Tyler replaces Ro as IO** 2/16/26 - made updates requested by Finance and resubmitted to L2; soft savings estimate was reconfirmed with Legal Ops leadership 2/13/26 - made updates requested by Finance and will resubmit to L2; soft savings estimate was reconfirmed with Legal Ops leadership 2/10/26 - awaiting domain lead approval. 1/21/26 - updating Planview to match data in LBC and resubmitting to L2. 12/22/25 - Updating LBC spreadsheet to include proposals from DMS and implementation vendors per feedback from Finance; working with Legal leadership and ELS to determine whether it's best to wait until FY26 is used as the baseline to move further in process due to the possibility of work not starting until start of FY27. 12/15/25 - Working with IT to get details regarding servers that eDocs uses to determine potential savings and gathering other financial information 12/9/25 - L1 Architecture Alignment has been completed; will submit after gathering financial information 12/8/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM; also in the process of gathering information regarding potential savings 12/1/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM; also in the process of gathering information regarding potential savings 11/24/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and provides documentation to EPM; also in the process of gathering information regarding potential savings 11/17/25 - Awaiting notification from EPM that initiative has gone through L1 Architecture Alignment where the architect pulls the initiative in based on priority/capacity and | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Milana - Compulaw Replacement |  | 169238 | Business w/ Tech Initiative | SGA - Legal | SG&A | Renee Allen | On Track | * 11/20/25 - On hold - Milana currently looks to be more of a local enhancement rather than a business with tech initiative and work will continue. * On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LEGAL EIW/EDW Query Tool |  | 169242 | Business w/ Tech Initiative | SGA - Legal | SG&A | Renee Allen | Some Issues | * 3/27/26 - Teradata is no longer be retired, so we will need to evaluate additional options for unifying the necessary data the teams require under a consolidated data warehouse * 3/5/26 - Met internally with Charles to discuss any additional options since he currently works on the queries manually and may have additional knowledge on the additional owners of the data being used * 3/3/26 - Met internally with Jim to discuss options since he works on a similiar project * 2/16/26 - Abdul requested a document of work flow processes and the processes document was submitted * 2/12/26 - Met with George in finance to discuss project needs and options * 2/2/26 - Met with Skrikant and Abdul to discuss project but not the owner of the project to answer the LBC questions. He also stated Teradata is no longer being retired * 01/21/26 - Sent another follow up email to VP asking for a point of contact in Dataworks to assist with the LBC * 01/05/26 - Sent another follow up email to VP asking for a point of contact in Dataworks to assist with the LBC * 12/12/25 - Working with finance on the LBC and trying to find a contact * 11/20/25 - Sent an email to the Dataworks VP requesting a contact to assist with the LBC in L1 * On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Implement New Alert Line Software |  | 170387 | Business w/ Tech Initiative | SGA - Legal | SG&A | James Brucker, Keith R. Thomas, Kathy Werner | On Track | 4/20/26 - Received Greenlight approval on 4/14/26. Waiting for Finance Domain Lead approval for L3. 4/14/26 - Final costing clarificaiton received from all areas. Submitted for greenlight, attending EGC on 4/14 4/6/26 - Targeting EGC meeting on 4/14. Awaiting final clarification on if costing is needed for Platforms (review only impact) before submiting to L3. 3/31/26 - All L2 costing finalized, targeting EGC 4/7. Epic 0116835 received exception to move to L3 to begin work with LegIT team. 3/24/26 - Targeting 4/7/26 to receive final costing and present at EGC. In parallel attempting to go through exception process to move single Epic forward (#0116835) that already has complete costing. 3/23/26 - Awaiting L2 costing from SCO, DAI, and Platforms portfolios before submitting to L3 3/18/26 - Reviewed latest financials with Finance and added attachments with latest business case and RFP details. Awaiting L2 costing from SCO, DAI, and Platforms portfolios before submitting to L3 3/16/26 - Updated financials and sent updated LBC costing sheet to finance. Direction from finance to hold off submitting to L3 until they can provide further direction, which they do not anticipate doing until 3/18/26. 3/6/26 - ARB review meeting occurred 3/6/26, received tentative approval. Awaiting final approval. Next steps to finalize L2 costing before Greenlight. 3/2/26 - Architecture review board meeting scheduled for 3/6/26. After architecture documents are approved and IT sizing estimates are finalized, we will be in position to submit to L3. 2/23/26 - High level architecture documents complete, in process of finalizing impacts of impacted areas ahead of ARB meeting week of 3/2/26. 2/16/26 - DA&I architect has been assigned, high level architectural decisions for impacted portfolios tentatively agreed upon, plan to finalize L2 architecture documents by 2/20/26 2/10/26 - Continuing to work to L2 architecture, D&AI portfolio cannot assign architect prior to March, however planning to meet with SME of impacted area to accelerate discussion. 2/3/26 - Continuing to work to L2 architecture, goal to complete by 2/6 1/27/25 - Entered initial financials as part of L2 costing. Architecture work is underway, anticipate completion by 2/6/26 *Further update - after consulting with Finance and EPM, zeroed out financials until all costs and benefits are available. 1/19/25 - Approved to L2. In process of working through L2 checklist and IT lead is working on architecture documentation. 1/12/25 - Entered updated based on guidance from finance and resubmitted to SL2. 1/5/26 - Submitted to L2, awaiting domain finance lead review. *updated baseline to FY25 and resubmitted based on feedback from Finance. 12/29/25 - L1 QA review complete, submitted to L2, awaiting EPM review. 12/23/25 - L1 architecture review complete, waiting for domain expert QA review before submitting to L2 12/17/25 - Architecture assessment is underway. Kick-off meeting with stakeholders scheduled for 12/19/25. 12/8/25 - Kick-off meeting with stakeholders scheduled for 12/19/25. (scheduled by M. Wolff) 12/1/25 - Completed LBC, awaiting architect assignment (Enterprise Ranking of #9 in L1) 11/25/25 - Received approval to move to L1 as a business continuity initiative. LBC in progress, plan to finalize by end of this week. | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2026-03-18 | 2026-10-30
Business Only Initiative: ALSP Utilization - Alcohol Reporting Project |  | 170529 | Business Only Initiative | SGA - Legal | SG&A | Denielle Hansberry, Anthony Spalvieri | On Track | 4/20/26 UPDATE: No significant update. Transition on schedule, no issues. 4/13/26 UPDATE: No significant update. Transition on schedule, no issues. 4/6/26 UPDATE: 1. 1st month with Integreon completing all reports (except 2 to permanently stay with internal team) begins today (March Reports). All elements on track. 2. Audit of teams work will begin mid-month 3. Actuals updated through March for new vendor (Integreon) and through February for old vendor (Buchanan Ingersoll). Will update old vendor for March when invoice received. 3/31/26 UPDATE: 1. Transition on track. 2. Actuals waiting for old vendor. 3/23/26 UPDATE: 1. Integreon has successfully submitted, timely, all reports except 3, which states are blocking their access due to non-U.S. VPNs. They did this after review by B.I. support staff as part of on-time transition plan. 2. Deni Hansberry has engaged 3 states blocking access to obtain acknowledgement of U.S-VPN to try to resolve the submission block for future months 3. Anticipate timely full transition for March Reports (early April) with minimal inquiries to former support staff (i.e., on-time money step). Automation steps to proceed thereafter. 4. Actuals for new vendor, Integreon, up to date. Awaiting February invoice from old vendor, Buchanan Ingersoll. 3/16/26 UPDATE: 1. Actuals for January have been added. As soon as actuals for February are submitted, I will update in Panview. 2. Remainder of transition plan is on target. 3/9/26 UPDATE: 1. Integreon is preparing first-pass of ALL alcohol reports for February reporting period now. Current team will conduct per-report review to provide necessary feedback and support, but assuming this goes well, we are at the money step, where we start realizing savings because we are phasing out Buchanan Ingersoll. To date, transition is going well and anticipate timely alignment with Planview forecasted milestones. 2. automation efforts being mapped by Integreon as we speak - next steps for build of automation likely to come in next few months. 2/23/26 UPDATE: 1. ACTUALS NOT YET AVAILABLE - monitoring invoice submissions and will update when available 2. Training and Transition ongoing - anticipate Integreon completing all reports, with BI review/approval, for February reports, moving to money step as planned. 3. Automation to begin after that. 2/10/26 UPDATE: 1. ACTUALS NOT YET AVAILABLE - neither current vendor (Buchanan Ingersoll) nor ALSP (Integreon) have submitted invoices for January 2026 work, when Integreon work began. 2. Training and Transition ongoing. Current BI team is training Integreon team (shadowing current support) and will take over report creation for February reports in early March. Assuming this goes well, BI support will dwindle in March, then likely conclude in April or May. 1/29/26 UPDATE: 1. Resources onboarded 2. training begun (numerous training files completed, team feedback provided, transition timeline created and agreed upon, team assignments for shadow reporting during February reporting period for January reports set up) 3. Integreon will shadow current resources for January reports, beginning when reports become avaialble, Feb. 4, 2026. 1/19/26 UPDATE: 1. Meeting 1/21/26 with officially onboarded Integreon personnel to initiate transition plan and validation training 1/12/26 UPDATE: 1. Approvals for onboarding and W365 access are ongoing - temporary passwords should occur 1/12/26, with true access being provided thereafter. 2. Team met with Integreon team - their review of desk procedure is complete and they have begun practicing reporting processes. They will send samples. 1/5/26 UPDATE: Awaiting approvals of onboarding Integreon employees to facilitate transition. 12/23/25 UPDATE: 1. Matriculated to L3 2. ONIT and BillingPoint onboarding of Integreon complete 3. Onboarding for 4 OSVs - meeting with T. Koziar re: process on Monday 12/29/25 12/8/25 UPDATE: 1. Waiting on approval from Jerome Miller to move forward. Message g | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2026-04-23 | 2026-08-26
Business Only Initiative: ALSP Utilization - OSHA Tracker |  | 189312 | Business Only Initiative | SGA - Legal | SG&A | Denielle Hansberry | On Track | 4/24/26 UPDATE: Send for L3 4/20/26 UPDATE: Pending finance review of input information before submitting for L3. On Track | E: L2 | Active | L2 Feedback Requested | 2026-04-01 | 2026-08-31
Business Only Initiative: Uniform Modernization Phase 1 - Pants & Polos |  | 103229 | Business Only Initiative | SGA - Procurement | SG&A | Pooja Patel | On Track | Requesting to cancel this initiative for now, as discussions around costing are still pending. The first round of sample reviews is scheduled for 11/10, followed by design iterations. We’re targeting the second round of samples by late December or early January, after which costing discussions will continue with both incumbent and new suppliers. Initiative will continue to be worked on and IO will re-enter it in planview once we have final and approved uniform design and costing. Decision was supported by Tricia Frese and Zak Quereshi on 11/5. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Onboard TitanCloud |  | 103639 | Business w/ Tech Initiative | SGA - Procurement | SG&A | Anthony Calvino, Kor'an Sharif, Natalie Clark | On Track | Working toward implementation. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Monthly Fuel Close Automation |  | 103642 | Business w/ Tech Initiative | SGA - Procurement | SG&A | Anthony Calvino, Kor'an Sharif, Natalie Clark | On Track | Natalie Clark spoke with Ben and Megan Silva and they said that this request should have been initially submitted as Local Demand. This Monthly Fuel Close work was previously approved by GPEL prior to Planview being implemented, was solutioned by Architects, features and stories created, and worked on by the Development team. It was de-prioritized due to DRIVE and no hard savings to be had with this project. We have gotten the green light from IT and Business management teams to start working on this EPIC again. It does not affect other trains and is completely Local initiative". | C: L1 | Cancelled | L1 Feedback Requested | 2023-08-16 | 2027-01-20
Business Only Initiative: Packaging – Launch custom packaging program |  | 103924 | Business Only Initiative | SGA - Procurement | SG&A | Pooja Patel | On Track | At this stage, the project cannot move forward as certain foundational elements require further research and cross-functional alignment. While initial discussions have provided helpful context, there are still pending research regarding pricing structure, fullfilment process, etc. that need to be fully defined. Before proceeding, it will be important to: * Conduct additional research to validate assumptions, clarify requirements and their dependencies. * Assess potential technology capabilities required to support order fulfillment and the billing process. This will allow the business team to make more informed decisions and reduce the risk of rework or misalignment later in the process. Once the additional analysis and collaboration are completed, the project can move forward with greater clarity and confidence. | C: L1 | Cancelled | L1
Business Only Initiative: EMR CFT - Pro Services Increase SUM |  | 126554 | Business Only Initiative | SGA - Procurement | SG&A | Jonathon Golden | Attention Needed | Cancellation requested for this placeholder initiative. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Packaging - Supply Reconciliation Rollout (LAC) | 31805 | 6812 | Business w/ Tech Initiative | SGA - Procurement | SG&A | Stefano Baratella, Lauri Bates | On Track | September 2025: got confirmation by Finance that it is possible to account volume + initiative effect; total decrease vs FY25 (on a monthly basis) is calculated without considering a 8,5% saving obtained thanks to a different initiative about unit price reduction - the impact of this specific initiative is them only the volume + initiative effect on LAC supplies cost Oct 3rd: submitted for L5 after 4 months of actuals above target (with volume + initiative effect as described above) Re-baselined to FY25 on 03/31/25 23rd May 25: L4 stage reached, monitoring impacts Submitted for L4: see evidence attached (email by IT confirming algorithm is live and an example of a Panama case) - wiating to have SharePoint link to upload archtiectural documentation 30th May 25: algorithm is live in LAC and cases are being generated, Lauri Bates confirmed they solved the Mexico phone line issue, so we should be ready to move to L4; I asked Kyle Adams (IT Dept) an evidence to be attached to PlanView to support L4 submission 5 May 25: Sales communication has been sent this week, initiative looks on track on a general perspective 24 Apr 25: UAT tests planned 18 Apr 25: Communication to Slaes sent 11 Apr 25: Sales communication prepared by Comms team in Miami - go live date NOT postopned, go live confirmed on May 17th 04 Apr 25: Communication for Sales ready and reviewed by Comm Dept - go live date postponed to mid July as communicated by IT, L4 date to be moved 28 Mar 25: shared communication draft with Marketing, who reviewd it and is ready to distribute it 21 Mar 25: shared communications drafts with Lauri, she will review the internal communication (for her team) and investigate what could be a good communication channel for LAC Sales; also a LAC colleague has been involved to find a good contact in LAC Sales 17 Mar 25: Comms draft shared, to be fine tuned and distributed 14 Feb 25: new draft of comms for Sales and Team shared with Lauri Bates, wiating for her feedback 13 Feb 25: IT confirmed implementation costs - entered in actuals; confimred also plan is on time (expcted release date in May) | K: L5 | Active | TEMP L5 - Enter L5 | 2024-05-20 | 2025-06-16
Business Only Initiative: Insurance Brokerage Renegotiation | 37355 | 6925 | Business Only Initiative | SGA - Procurement | SG&A | Chad Jackson, Janie Pruitt | On Track | 4/30/25 Broker contracts have been executed. No changes in financials from 3/26/25. 3/26/25 Entered actuals. Also, rebaseline complete. Agreed price. Negotiate contracts. 2/6/25. Working on L3 approvals, but on track for L4 by end of March | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-12 | 2025-04-01
Business Only Initiative: Packaging - Ranpak Eliminate Transport Costs | 38234 | 7075 | Business Only Initiative | SGA - Procurement | SG&A | Callie Hinojosa, Ronnie Guerra | On Track |  | K: L5 | Completed | L5 | 2023-11-14 | 2023-11-30
Business w/ Tech Initiative: Surface bulk fueling – Cross OpCo fueling with FXG | 48908 | 7179 | Business w/ Tech Initiative | SGA - Procurement | SG&A | Lee McCutcheon, Joe Carlson | On Track | As long as Retail locations continue to offer Cost/Plus zero pricing, this initiative will primarily be an efficiency gain. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-09-02 | 2024-10-31
Business Only Initiative: Surface Fuel - DEF Purchasing Processes Across OpC | 54661 | 7208 | Business Only Initiative | SGA - Procurement | SG&A | Steven R. Wozniak, Jacob Triplett, Karra Seskey | On Track | N/A | K: L5 | Completed | L5 | 2023-11-20 | 2024-03-29
Business Only Initiative: Consolidate RFP Maintenance service for multiple l | 96027 | 7412 | Business Only Initiative | SGA - Procurement | SG&A | Hettie Van Gemert, Luigi Mastromonaco | On Track | Re-Baselinedto FY25 on 05/23/25 | I: L4 | Active | L4 Feedback Requested | 2024-08-15 | 2025-05-29
Business Only Initiative: OSC Spend Reduction - ADR FXO Ecommerce Developmen | 88720 | 7433 | Business Only Initiative | SGA - Procurement | SG&A | Tricia Frese, Greg Paulus | On Track |  | K: L5 | Completed | L5 | 2024-08-01 | 2024-08-01
Business w/ Tech Initiative: Packaging - Launch Reusable Packaging (US) | 80402 | 7647 | Business w/ Tech Initiative | SGA - Procurement | SG&A | Tyler Kenney, Kyle McCarter | On Track | *D&AI team reviewing for greenlighting but prevented by SCO backlog. Once both green lights are approved, timeline for AI model implemntation can be determined and architecture started. *Determined intial issues with current TAD reporting dashboard. Problems being addressed while also planning for changes once AI model is implemented. *Recieved Legal's first iteration of contract renewal with Returnity including amendments like outright purchase revenue share, packaging types besides boxes, and AI logo changes. *Submitted request for updating dot com packages to direct customers to RPP resources, specifically on the sustainable packaging pge. | E: L2 | Active | L2 | 2024-11-12 | 2026-03-02
Business Only Initiative: Packaging - Iconex Facestock Switch Avery (US) | 80282 | 7651 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Ronnie Guerra | On Track | Project is completed as there is no longer any Iconex product remaining to purchase for the transition. Iconex is no longer our supplier. All savings from RFP captured in Thermal Label Market Event. | K: L5 | Completed | L5 | 2024-04-26 | 2024-06-05
Business Only Initiative: Packaging - RR Donnelley Price Reduction (US) | 80579 | 7654 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Ronnie Guerra | On Track | No Remaining updates to be made the project is completed. All savings have transitioned to Thermal Label Market Event Entry. | K: L5 | Completed | L5 | 2024-06-04 | 2024-06-04
Business Only Initiative: Packaging - Pak Competitive Event (US) | 82042 | 7677 | Business Only Initiative | SGA - Procurement | SG&A | Pankaj Kumar Singh, Anchit Mahajan | On Track | May'25 Actuals updated. Forecast and exit rate are updated. Updated forecast and re-baselined to FY25 on 5/21/2025 and change the Baseline year to FY25. Alos, PAC WW $212k Check captured in April'25 Actuals. | K: L5 | Completed | L5 | 2024-09-23 | 2025-03-28
Business Only Initiative: Network 2.0 Surface Sort Bid Bundling | 88552 | 7746 | Business Only Initiative | SGA - Procurement | SG&A | Steve Muchko, Philip Simonetti | On Track | Re-baselined to FY25 on 05/23/25” | K: L5 | Active | L5 Feedback Requested | 2024-06-03 | 2024-10-11
Business Only Initiative: Uniforms - Specification Optimization - SKU Ration | 3096 | 7897 | Business Only Initiative | SGA - Procurement | SG&A | Elison Sabat, Stefano Baratella, Callie Hinojosa | On Track | Initiative is moving forward. Communication has gone out to OpCos informing them of the change. Currently working on depleting inventory and ramping up savings. Rebaseline to FY25 on 5/6/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-04 | 2026-06-12
Business Only Initiative: Ops Supplies - Commercial - First Aid and Safety a | 34529 | 7898 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Elison Sabat, Callie Hinojosa | On Track | Rebaselined to FY25 on 05/05/2025. Aug 12th: saving are regularly recorded, we are working on supplier to furtherly improve the figures (e.g. through a new SKU rationalization round) | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-17 | 2026-08-28
Business Only Initiative: Uniforms - Competitive Event FY25 | 80385 | 7899 | Business Only Initiative | SGA - Procurement | SG&A | Elison Sabat, Stefano Baratella, Callie Hinojosa | On Track | The savings is estimated at 27% due to pricing provided by chosen vendor. (L1 key assumptions and money step were not able to be updated in L2.) **Addessing Questions from L3 Submission: ** 1.What is the baseline spend and from what year? The baseline spend is $33,685,013 in FY24. This information is taken from accounting data and shown on the tab ‘Spend from AP’ in the most recent business case attached. 2.How are we estimating 27% savings when you then say 5/6/7% reductions? a.There are 2 parts to the savings for this initiative. The savings from the RFP will recognize a 27% reduction, but these reduction will start in January 2026 when the new contract with incumbent is active. In the interim, the incumbent is offering CY25 savings of 5/6/7% on specific SKUs to help FedEx to realize more near term savings. I understand this is not typically where the savings differ so greatly, but there is a ramp up period for the incumbent to be able to hit the full RFP savings (27%), so in the interim they provided us with smaller savings for CY25. This was disucssed with the FP&A contact and is in alignment. 3.Also, the NRB should be the FY25 exit rate of savings which right now is $364M. However, I don’t see the calculated/estimated. Please provide detail. a.In talking with the FP&A lead for this category, she noted that the exit rate that should be included for FY25 should be the May 2025 savings X12. This is how I came to include $1.0M as the exit rate (84,07412). There will be a significant step change to savings benefit in FY26. This has also been reviewed and disucssed with FP&A team and they are in alignment. 1/16 - FY25 exit rate updated to $363K due to the seasonality of this initiative. Step change to savings will be addressed at a later date. Rebaseline to FY25 on 5/6/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-10-28 | 2026-04-03
Business Only Initiative: Corporate finance advisory: Demand reduction | 32392 | 7902 | Business Only Initiative | SGA - Procurement | SG&A | Jonathon Golden, Arun Sengupta | On Track | 6/17/24 - Approved into L5 on 6/17/24. Stage L4, tracking actuals as they come in monthly. | K: L5 | Completed | L5 | 2023-05-31 | 2023-09-01
Business Only Initiative: FY24 Pro Fees Budget Reduction One-Time | 32404 | 7903 | Business Only Initiative | SGA - Procurement | SG&A | Brad Bush, Stephanie Skordeles | On Track | 6/17/24 JBB - Approved into L5. This is a one-time FY24 initiative only, so no further work will be done. 6/17/24 JBB - Initiative is pending approval from JWD and CFR to close out. 6/12/24 JBB - May actuals have been entered for Impacts and KPIs. This is an FY24 one-time reduction initiative that will now close out through L4 and L5. With the exception of a known and approved adjustment made for FXG PF spend related to Neil Lanasa agreeing to record the Enterprise Planning spend at FXG, the initiative met Plan savings. 6/10/24 JBB - No changes in status. This initiative will close out and go to L4/L5 as scheduled in the next week, once May actuals are submitted by 6/14 deadline. 6/3/24 JBB - No changes in status. This initiative will close out and go to L4/L5 as scheduled in the next week. 5/28/24 JBB - No changes in status. 5/20/24 JBB - No changes in status. Apr actuals have been entered. 5/13/24 JBB - No changes in status. No issues expected with April actuals by 5/20. 5/6/24 JBB - No changes in status. 4/29/24 JBB - No changes in status. 4/22/24 JBB - FXE Sep-Feb actuals removed from capture per leadership. No other changes in status. 4/16/24 JBB - No change in status. 4/9/24 JBB - Initiative and all milestones/impacts are on track. FY24 FXE impact estimate methodology was changed to exclude Audit and Legal Fees, leaving pure Pro Fees as the measure, approved by Leslie Benners. Mar actuals show a large favorable variance to forecast, as Mar forecast was locked prior to the methodology change. Sep-May FXE impact currently estimated at 34M. 4/1/24 JBB - Initiative and all milestones/impacts are on track. FY24 FXE impact estimate was refreshed after the 3/28 Forecast update, and savings for the initiative took a 6.6M hit due to a one-time charge in March related to a legal settlement that is not non-GAAP eligible. 3/25/24 JBB - Initiative and all milestones/impacts are on track. FY24 FXE impact estimate will be refreshed after Thu 3/28 Forecast Update. 3/18/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 3/11/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. All Feb actuals have been loaded except for FXG, which are expected prior to the 3/15 deadline. 3/4/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 2/26/24 JBB - FXE KPI was moved to Impact to capture savings. All others are tracking, no issues. 2/19/24 JBB - FXG Feb-May FY24 impact now reflects unplanned PF spend that Neil Lanasa has agreed to absorb on behalf of the enterprise. There is also consideration being given to capturing savings achieved from KPIs at FXE and FXF as impacts. No other issues, and all actuals have been loaded for Jan. 2/12/24 JBB - FXG Feb-May FY24 impact is under review for how to handle unplanned spend that Neil Lanasa has agreed to absorb on behalf of the enterprise. There is also consideration being given to capturing savings achieved from KPIs at FXE and FXF as impacts. No other issues. 2/5/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 1/29/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 1/22/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 1/16/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. Dec actuals have been entered. 1/8/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 1/2/24 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 12/26/23 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 12/18/23 JBB - Initiative and all milestones/KPIs are on track. No anticipated issues with Nov actuals. 9/5/23 JBB - Initiative and all milestones/impacts are on track. No updates or concerns. 9/11/23 JBB - Initiative and all milestones are on track. No u | K: L5 | Completed | L5 | 2023-07-07 | 2024-06-14
Business Only Initiative: Tax Services: Commercial & Demand | 32402 | 7904 | Business Only Initiative | SGA - Procurement | SG&A | Misty Arinder, Stephanie Skordeles | On Track | 5/6/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up. No impact to FY24 estimated impacts. Stephanie Skordeles assigned as IO, Brad Bush to be backup IO going forward. 4/29/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB again in April. No impact to FY24 estimated impacts. 4/22/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB again in April. No impact to FY24 estimated impacts. 4/16/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB again in April. No impact to FY24 estimated impacts. 4/9/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB again in April. No impact to FY24 estimated impacts. 4/1/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB again in April. No impact to FY24 estimated impacts. 3/25/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB again in April. No impact to FY24 estimated impacts. 3/18/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB in March. No impact to FY24 estimated impacts. 3/11/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB in March. No impact to FY24 estimated impacts. Feb actuals have been loaded. 3/4/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB in March. No impact to FY24 estimated impacts. 2/26/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB in March. No impact to FY24 estimated impacts. Actuals for Jan have been loaded. Milestones and L4 date were pushed out to 4/30 to allow Tax time to find alternate savings sources. 2/19/24 JBB - Discussions on and review of FY25 amounts continue, Misty has agreed to follow up with TEN and JBB in March. No impact to FY24 estimated impacts. Actuals for Jan have been loaded. 2/12/24 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts. 2/5/24 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts. 1/29/24 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts. 1/22/24 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts, and December actuals were loaded. 1/16/24 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts, and December actuals are being tabulated. 1/8/24 JBB - Discussions on and review of FY25 amounts continue, including a question from Business Owner Misty Arinder regarding moving this init to the Enterprise Excellence domain...to be addressed on 1/9/24 working group call. No impact to FY24 estimated impacts, and December actuals are being tabulated. 1/2/24 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts, and no actuals to record until December. 12/26/23 JBB - Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts, and no actuals to record until December. 12/18/23 JBB - Moved out due dates of milestones 34238 and 34240. Discussions on and review of FY25 amounts continue. No impact to FY24 estimated impacts, and no actuals to record until December. 12/11/23 JBB - Moved out due dates of milestones 34238 and 34240 by another week to allow time for discussion with MO Misty Arinder and McK team. Discussions on FY25 amounts continue. No impact to FY24 estimated impacts. 8/18/23 JBB - moved completion date of 34235/34236 milestones to 8/26, will follow up with milestone owner Misty Arinder ahead of that date to determine status. No | K: L5 | Completed | L5 | 2023-07-20 | 2024-09-25
Business Only Initiative: Packaging - Eliminate Paper Airway Bills | 334 | 7971 | Business Only Initiative | SGA - Procurement | SG&A | Lauri Bates, Katie McAuliff | Some Issues | 05/06/25 – Re-baselined to FY254/10/25- March actuals entered 3/14/25- Meeting scheduled Wednesday to finalize presentation to Sales looking for their full committment on FARM restrictions 3/7/25- Awaiting data to enter actuals for February 2/28/25- Movement with FARM restrictions and potential dotcom update. Followup next week 2/14/25- January actuals entered 2/7/25 - Awaiting actuals from finance to update actuals 1/31/25- Sales advisory borad meeting scheduled for 2/3-looking for support from sales to utilize FARM to restrict orders 1/27/25- December valued entered-additional meetings scheduled this week to gain sales support 1/10/25 meeting scheduled next week to meet with new Marketing manager to support supplyweb messaging 12/27/24-Meeting scheduled in January to meet with Sales and get their approval of our approach to use FARM to restrict airbill ordering 12/13/24 November actuals entered. Running behind plan due to roadblocks restricing more accounts types. Working on FARM restrictions being added, but continue to research option for customers to self help if denied airbills. 12/6/24 continued discussing option of FARM update vs waiting for approval from Sales and IT to remove completly off dotcom. Meeting scheduled for 12/10/24 | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-17 | 2023-09-29
Business Only Initiative: Packaging - White to Kraft Boxes (US) | 335 | 7982 | Business Only Initiative | SGA - Procurement | SG&A | Lauri Bates, Katie McAuliff | On Track | 4/10/25- March actuals entered 3/14/25- Nothing to report 3/7/25- Actuals entered. tracking close to plan 2/28/25- Awaiting actuals and will update by 3/10/25 2/14/25- Actuals entered. tracking close to plan 2/7/25-Awaiting values from finance to update actuals 1/31/25- Nothing new to report 1/27/25- December values entered-running as close to plan as we can based off the volume of boxes being ordered being up 5% 1/10/25- December values will be entered by 1/20/25 12/27/24- Initiative is running close to plan-nothing to report 12/13/24- November actuals entered 12/06/24-initiative is running close to plan, though volume has seen a modest increase which has reduced the savings by a small margin. | K: L5 | Completed | L5 | 2022-11-15 | 2023-09-29
Business Only Initiative: Caster Deck Redesign RFP | 59756 | 7988 | Business Only Initiative | SGA - Procurement | SG&A | Hettie Van Gemert, Steve Muchko | On Track | Signature page of the caster deck contract with supplier Wit Con is attached | I: L4 | Active | L4 Feedback Requested | 2023-10-27 | 2024-10-16
Business Only Initiative: Packaging - Thermal Labels - Demand - eliminate tw | 31806 | 7993 | Business Only Initiative | SGA - Procurement | SG&A | Lauri Bates, Katie McAuliff | On Track | 4/10/25- March actuals entered 3/14/25- Reporting Actuals with follow up question due to extraordinary savings last month. Awaiting response 3/7/25- Awaiting March actual to enter by 3/10/25 2/28/25- Awaiting March actuals to enter by 3/10/25 2/14/25- Awaiting actuals from finance to enter for January 2/7/25- Awaiting actuals from finance to enter 1/31/25- Nothing new to report 1/27/25- Valued entered, running ahead of plan 1/10/25-December values to be entered by 1/20/25 12/27/24-Solid month in November on savings to plan, nothing to report. 12/13/24 November actuals entered 12/6/24 Nothing new to report. Continue to monitor usage and reduce orders to 1 per piece. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-07-21 | 2024-01-01
Business Only Initiative: Packaging - Temp-Assure .com & Retail Price Match | 72092 | 8016 | Business Only Initiative | SGA - Procurement | SG&A | Katie McAuliff, Tricia Frese, Lauren Kantor | On Track | 1.14.25 - December actuals entered - above plan. October actuals entered 11.12 - above plan. | K: L5 | Completed | L5 | 2024-07-26 | 2024-08-08
Business Only Initiative: Interim Diesel Fuel Supplier to FXF at Dallas/Fort | 43253 | 8077 | Business Only Initiative | SGA - Procurement | SG&A | Anthony Calvino, Todd Dressler | On Track | N/A | K: L5 | Completed | L5 | 2023-09-18 | 2025-02-14
Business Only Initiative: Rack buy optimization - Negotiate/optimize local r | 48910 | 8078 | Business Only Initiative | SGA - Procurement | SG&A | Anthony Calvino, Todd Dressler | On Track | 3/11/2026: Worked to reduce rates at several racks, but project savings took a large hit with FXF divesting. We are no longer able to pool gallons for additional savings and FEC doesn't do enough volume to demand savings in most markets. *5/30/2024: Marathon Petroleum contract attached...fully executed with reduced rates driven by this initiative. Additional supplier contracts on in progress. Information and some history needed from OPIS to determine potential savings. Currently awaiting the delivery of an OPIS report. Will schedule additional phases for one month after the report is released to gather data and project savings. 11-13-2023 * Platts and OPIS reference prices are now being calculated daily for some major markets. * Tracking will continue until a differential by market by supply by volume can be determined accurately. * Daily Price Report is updated each day under Attachments. | K: L5 | Active | L5 | 2023-11-01 | 2024-05-31
Business Only Initiative: Packaging - Non Revenue Shipping - Lowest Cost Shi | 70283 | 8112 | Business Only Initiative | SGA - Procurement | SG&A | Jason Morgan, Tricia Frese | On Track |  | K: L5 | Completed | L5 | 2024-03-01 | 2024-06-28
Business Only Initiative: Uniforms - Specification Optimization - Uniform De | 31787 | 8113 | Business Only Initiative | SGA - Procurement | SG&A | Lauren Kantor, Tricia Frese |  | Uniforms went to RFP and captured additional savings without changing uniform design. This initiative should be cancelled. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-07-26 | 2024-11-14
Business Only Initiative: Packaging - Modification of Box Flap | 73627 | 8117 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Evan Edwards, Tricia Frese | On Track | Implementation with both suppliers is completed. Full ramp up will be completed by mid June as old boxes will be out of inventory. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-08 | 2025-05-30
Business Only Initiative: MRO & Supplies - Specification Optimization - SKU | 31794 | 8217 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes, Zakaria Qureshi | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2023-08-21 | 2023-10-31
Business Only Initiative: MRO & Supplies: Legacy MRO - Commercial - Vendor C | 31973 | 8218 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes, Zakaria Qureshi | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2023-08-14 | 2023-10-30
Business Only Initiative: MRO - Commercial - Legacy MRO competitive event | 34528 | 8219 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes, Zakaria Qureshi | On Track | Old initiative that was never used that was imported from the old WAVE tool. 10/7 | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: Ops Supplies - Staples Signing Bonus Check | 91677 | 8220 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes, Zakaria Qureshi | On Track |  | K: L5 | Completed | L5 | 2024-02-01 | 2024-08-23
Business Only Initiative: Packaging - Purple API (Europe) | 31855 | 8223 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Zakaria Qureshi | On Track | FY26 rebaseline activity completed on March 31st 2025 Forecast still active since impacts are mad of volumes rejections on a monthly basis | K: L5 | Completed | L5 | 2023-04-03 | 2024-05-31
Business Only Initiative: Packaging - Reduce Pouch SKUs (International) | 32774 | 8224 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Zakaria Qureshi | On Track | FY26 rebaseline activity completed on March 31st 2025 values are not incremental to FY25, therefore forecast has been set to zero according to instructions | K: L5 | Completed | L5 | 2023-06-01 | 2023-12-11
Business Only Initiative: Packaging - Vendor Consolidation of Thermal Labels | 34887 | 8225 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Zakaria Qureshi, Ketan Panchal | On Track | 20th Oct: received confirmation of go live of last prices - completed last milestone, submitted for L5 Re-baselined to FY25 on 03/31/25 TNT Labels have been already implemented (same item, same supplier, new - reduced - pricing); new prices are already in place since December 11th (see attached email), savings (even if partial) from December 2025already entered 11th Jul 25: all albels approved; checking witn Veritiv ETA for prce change in the catalogues 23rd May 25: tests completed, waiting for official feedback by Packaging Lab 30th May 25: software for testing available again for Packaging Lab; T.Wood expects tests to be completed within next week 5 May 25: new samples for the SKU’s still to be approved have been received, now have to be tested but Packaging Lab does not have yet the software available 18 Apr 25: new samples arrived - now to be analyzed by Packaging Lab 21 Mar 25: new samples will be provided by Paragon – ETA for shipping 7th April 17 Mar 25: Samples feedback to be shared - contact between manufactuer and Pkg Lab expected 21 Feb 26 new samples have reached Packaging Lab on 13th Feb, Tom said he estimates to complete the tests in 2 weeks 14 Feb 25: new samples tracking number 771881666740 - delivered on 13th Feb, Packaging Lab can now start testing them 06 Feb 25 new samples for FedEx labels shipped to Packaging Lab for new tests | K: L5 | Active | TEMP L5 - Enter L5 | 2023-09-01 | 2025-10-29
Business Only Initiative: Packaging - Boxes RFP event (International) | 34889 | 8228 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Zakaria Qureshi, Ketan Panchal | On Track | Oct 10th: submitted for L4 since new prices for Kg Boxes have been implemented in FCF catalogue (see attached confirmation by Veritiv) Re-baselined to FY25 on 03/31/25 - including new Veritiv uplift Aug 12th: Kg Boxes have been fully apporved and we are monitoring withb Veritiv the exact date when new procing can be implemented in catalogues (need to deplete existing stocks first); that wil be L4 date - currently mid September still looks feasible | K: L5 | Active | L5 | 2023-08-01 | 2025-11-28
Business Only Initiative: Packaging - Large to Small Pouches (International) | 46278 | 8229 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Zakaria Qureshi, Ketan Panchal | On Track | Re-baselined to FY25 on 03/31/25 27th May 25: L5 stage reached 24th May 25:Submitted for L5 - impacts are stable, new pouches (smaller and cheaper) are now the only ones available in the EU catalogues, so no alternative option is possible for requesters New item (small pouch - cheaper) available in FCF catalogue and some PO's already received Old items 155143 and 155144 eliminated from FCF catalogues See attachments (Money Step Evidence files) showing FCF - L4 stage reached | K: L5 | Completed | L5 | 2023-09-01 | 2025-04-01
Business Only Initiative: Packaging - RFP on KG Boxes (APAC) | 64022 | 8230 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Zakaria Qureshi, Jason Ng | On Track | FY26 rebaseline activity completed on March 31st 2025 values are not incremental to FY25, therefore forecast has been set to zero according to instructions | K: L5 | Completed | L5 | 2023-05-15 | 2024-04-30
Business Only Initiative: HR outsourcing, analytics, benefits and comp consu | 32394 | 8354 | Business Only Initiative | SGA - Procurement | SG&A | Rob Farr | On Track | Approved to L4; Tracking savings | K: L5 | Completed | L5 | 2023-07-12 | 2023-09-15
Business Only Initiative: P Card FEI | 2166 | 8401 | Business Only Initiative | SGA - Procurement | SG&A | Hayley Nebesniak |  | On hold pending re baselining, assessment of investment case, approval and negotiation with Deloitte of new contract | E: L2 | On Hold | L2 | 2023-01-05 | 2025-05-30
Business Only Initiative: Europe Procurement Insights Dashboard Cancellation | 32598 | 8402 | Business Only Initiative | SGA - Procurement | SG&A | Lucy Dolgy | On Track |  | K: L5 | Completed | L5 | 2023-07-03 | 2023-08-01
Business Only Initiative: FY23 Mobile Fuel RFP | 3027 | 8404 | Business Only Initiative | SGA - Procurement | SG&A | Amber Bonacci, Aditi Khanna | On Track | N/A | K: L5 | Completed | L5 | 2022-07-01 | 2022-12-30
Business Only Initiative: Packaging - Box Competitive Event (US) | 34525 | 8405 | Business Only Initiative | SGA - Procurement | SG&A | Jason Morgan | On Track | - Consistent realization of monthly savings from intiative | K: L5 | Completed | L5 | 2023-09-01 | 2024-01-12
Business Only Initiative: FY23 Retail Fuel Partner Discounts | 3028 | 8415 | Business Only Initiative | SGA - Procurement | SG&A | Amber Bonacci, Aditi Khanna | On Track | N/A | K: L5 | Completed | L5 | 2022-11-22 | 2023-08-04
Business Only Initiative: FY23 Bulk Fuel Initiative | 3025 | 8426 | Business Only Initiative | SGA - Procurement | SG&A | Joe Carlson, Aditi Khanna | On Track | N/A | K: L5 | Completed | L5 | 2023-02-06 | 2023-10-31
Business Only Initiative: Surface Bulk Fuel truck negotiations - Negotiate f | 48911 | 8427 | Business Only Initiative | SGA - Procurement | SG&A | Lee McCutcheon | On Track | N/A | K: L5 | Completed | L5 | 2023-11-08 | 2024-05-31
Business Only Initiative: Surface strategy - Identify best practices across | 40653 | 8449 | Business Only Initiative | SGA - Procurement | SG&A | Anthony Calvino, Aditi Khanna | On Track | 5/14/2021: Primary driver for Money Step (derived from initiative 8449) was determined to move in a different direction as we were unable to pinpoint savings with any accuracy. Updated money step to 1/31 to add milestones for future org design, eliminating the need for an additional initiative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-12-15 | 2025-05-30
Business Only Initiative: Deloitte Consulting FY25 Rate Reduction |  | 86891 | Business Only Initiative | SGA - Procurement | SG&A | Ameera Venkataraman, Rajat Srivastava | On Track | Negotiations have already been completed and reduction in monthly invoices have started. | K: L5 | Completed | L5 | 2024-11-29 | 2025-05-30
Business Only Initiative: PwC Consulting FY25 Rate Reduction |  | 86927 | Business Only Initiative | SGA - Procurement | SG&A | Ameera Venkataraman, Rajat Srivastava | On Track | The negotiations have already ben completed. | K: L5 | Completed | L5 | 2024-11-19 | 2025-05-30
Business Only Initiative: Oliver Wyman Consulting FY25 Rate Reduction |  | 86930 | Business Only Initiative | SGA - Procurement | SG&A | Ameera Venkataraman, Rajat Srivastava | On Track | Rate reductions have already been negotiated for remaining billing for FY 25. | K: L5 | Completed | L5 | 2024-11-29 | 2025-05-30
Business Only Initiative: Uniforms - Demand - Periodic Uniform Allowance |  | 87004 | Business Only Initiative | SGA - Procurement | SG&A | Elison Sabat | On Track | This initiative has been re-entered as a business with tech initiative, led by the business owner (Pooja Patel). New intiative is 0014945. | C: L1 | Cancelled | L1
Business Only Initiative: Ops Supplies - Legacy FXG Cargo Netting |  | 87328 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | This initiative to be cancelled, and compiled into PV#133516 to result in capturing more savings $. 10/7 | C: L1 | Cancelled | L1
Business Only Initiative: Ops Supplies - Legacy FXE Hub Air Filter Optimize |  | 87331 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | Project was complete, but did not result in savings above $100k annually. | C: L1 | Cancelled | L1
Business Only Initiative: Core Copy Paper Program |  | 88168 | Business Only Initiative | SGA - Procurement | SG&A | Callie Hinojosa, Zakaria Qureshi | On Track | N/A | I: L4 | Active | TEMP L4 - Enter L4 | 2024-12-18 | 2025-07-02
Business Only Initiative: EMR Plastic Pallets Tender SRN |  | 88760 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Thomas Dietsch | On Track | Difference of actual versus forecast savings should be due to the summer period. Forecast savings are calculated as average over a year. Contracts are signed. Cabka contract approved and requested to obtain signatures. Alpac contract still requires 4 approvals and are followed up. The contracts are close to being fully approved and L4 dates moved to September. Savings are being calculated from June onwards. | I: L4 | Active | L4 Feedback Requested | 2025-01-06 | 2025-09-01
Business Only Initiative: EMR Wooden pallets France |  | 88763 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Thomas Dietsch | Some Issues | All suppliers increased rates before contracts could be signed and will have to revalidate rates. That will put this initiative at risk. | G: L3 | Cancelled | L3 | 2025-01-06 | 2026-01-15
Business Only Initiative: MRO - Maintenance, Repair, Operational Consumable | 2156 | 8899 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes, Jason Morgan | On Track | Both contracts executed. Implementation began 4/10/13. | K: L5 | Completed | L5 | 2022-11-29 | 2023-04-14
Business Only Initiative: Travel Policy Change - Reduce First/Business Class | 2888 | 8934 | Business Only Initiative | SGA - Procurement | SG&A | Daniel Provence, Laura Bullion | On Track | No issues to report | K: L5 | Completed | L5 | 2023-01-09 | 2023-02-17
Business Only Initiative: Data entry outsourcing: Demand reduction | 32410 | 8935 | Business Only Initiative | SGA - Procurement | SG&A | Alex Thomas, Bradley Nieman | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2023-11-01
Business Only Initiative: General Consulting Commercial Opportunities (Rate | 2977 | 8946 | Business Only Initiative | SGA - Procurement | SG&A | Rajat Srivastava, Heather Sprague |  | Rate cards obrtained from key vendors to be used for negotiations with vendors, and this initiative doesn't have any $$ impact. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-01-16 | 2025-03-20
Business Only Initiative: Sort Equipment Bid and Rationalization | 3002 | 8955 | Business Only Initiative | SGA - Procurement | SG&A | Steve Muchko, Jessica Farny | On Track | Working to rationalize actual addressable spend. Assuming 80% will be addressable based off supplier data received from Insight dashboard. | K: L5 | Completed | L5 | 2023-06-12 | 2024-01-31
Business Only Initiative: Packaging - Thermal labels - Hot Melt Adhesive & S | 31797 | 8971 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Anchit Mahajan | On Track | The project is completed. No Addtional Savings will be entered. all savings has been transitioned to the Thermal Labels Market Event Entry. | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-01
Business Only Initiative: Packaging - Thermal Label Competitive Event (US) | 34527 | 8972 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Anchit Mahajan | On Track | The attached L4 evidence analysis matched the updated fiancials. This is the new NRB is $14.95M and the FY25 OI is ~$7M which does also match both the evidence and the fiancials sheet. | K: L5 | Completed | L5 | 2024-09-09 | 2025-04-18
Business Only Initiative: Packaging - Ops Labels Competitive Event (US) | 82041 | 8973 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Anchit Mahajan | On Track | The attached L4 evidence analysis matched the updated fiancials. This is the new NRB is $9.8M and the FY25 OI is ~$6.6M which does also match both the evidence and the fiancials sheet. | K: L5 | Active | L5 Feedback Requested | 2024-09-09 | 2025-04-25
Business Only Initiative: Tail Spend Reduction through Rapid Repricing |  | 89750 | Business Only Initiative | SGA - Procurement | SG&A | Harkaran Malhotra, Rajat Srivastava | On Track | Pilot phase has started; exact savings opportunities will be determined based on the results of pilot | K: L5 | Active | L5 Feedback Requested | 2024-12-24 | 2024-12-24
Business Only Initiative: Packaging - Commerical Print Competitive Event | 89771 | 8976 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Anchit Mahajan | On Track | Pricing is in effect. Please see attacehd savings model with notes on tracking methedology. The total savings has dropped as volume decline for the category as a whole has dropped. Less volume through the network equates to less labels applied. Contract awaiting FedEx signature, Exec to return on Tuesday from OOO and will be completed. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-02-03 | 2025-05-20
Business Only Initiative: EMR – Packaging – Envelope Competitive Event | 82040 | 8978 | Business Only Initiative | SGA - Procurement | SG&A | Pankaj Kumar Singh, Anchit Mahajan | On Track | March'26 Actuals updated. Feb'26 Savings updated. Jan'26 savings captured and also included the refund check ($43K) from Veritiv. Dec'25 savings captured in Financials. Nov'25 - Savings fell short of the forecast because volume dropped due to the supplier’s production issues, but they are ramping up now. Sep'25 - Savings dropped because of a volume decline due to equipment breakdown at the supplier in the begining of the month. August'25 - partial savings achieved, 100% transition to GPI SKUs by late Sep'25. After aligning with TO Finance, FY26+ forecast updated including the incremental value. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-26 | 2025-08-01
Business Only Initiative: Forklift Global Spend Aggregation and Standardizat | 3078 | 8980 | Business Only Initiative | SGA - Procurement | SG&A | Laurin Murk, Kyle Mitchell | On Track | 20230119 - KMM - Updated milestones and impacts to reflect that FXF does not plan to purchase forklifts in FY24. Plan updated to potentially impact FY25 purchases. | K: L5 | Completed | L5 | 2023-01-02 | 2024-06-28
Business Only Initiative: Packaging - RFP on plastic supplies | 3093 | 8987 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella, Jason Ng | On Track | FY26 rebaseline activity completed on March 31st 2025 values are not incremental to FY25, therefore forecast has been set to zero according to instructions | K: L5 | Completed | L5 | 2022-07-01 | 2023-11-30
Business Only Initiative: Office & Janitorial Supplies - SKU Rationalization | 3094 | 8988 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes, Jason Morgan | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2023-07-05 | 2023-09-29
Business Only Initiative: Uniforms - Demand - Rationalize Roles Offered Unif | 3097 | 8990 | Business Only Initiative | SGA - Procurement | SG&A | Jason Morgan |  | I talked to Jim Davis in legal, who has been talking to Jeff Robertson in labor relations. They relayed significant concerns that the uniform projects will have on team member morale and, as a result, an impact on the remain independent strategy for FedEx as a whole. It is the recommendation of Legal that we place all uniform initiatives that impact team members on hold until the spring to allow for workforce tensions to relax, and for the newly formed HR and Legal structures to establish a revised policy and strategy. Given this stance, we’re going to cancel tomorrow’s meeting, along with the uniform allocation initiative. That will impact DRIVE savings, but it’s for the right business reason. We’ll alert the DRIVE TO and reflect the changes going forward. Thanks to all of you for working with us, and we’ll revisit this in 6+ months. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-06-01 | 2025-07-24
Business Only Initiative: Packaging - Master Carton Optimization | 3100 | 8991 | Business Only Initiative | SGA - Procurement | SG&A | Anchit Mahajan, Mark West | On Track | Submitting this project to L5 following the guidlines provided by the TO office below and also attached as additional document. "Baseline will change to FY25 actuals (Jun-Feb) + Forecast (Mar-May); however, as a reminder, there is no “baseline” account for financials, only KPIs. That said, there is a drop down on the strategy view where you can select the baseline year for your initiative. When we “reforecast” FY26-28 values, we will be deleting the forecast for those years, as there are no remaining benefits over the new FY25 baseline." | K: L5 | Completed | L5 | 2023-06-01 | 2023-10-31
Business Only Initiative: Packaging - White to Kraft Envelopes (Global) | 3101 | 8993 | Business Only Initiative | SGA - Procurement | SG&A | Jason Morgan, Justin Troy | On Track |  | K: L5 | Completed | L5 | 2023-01-18 | 2023-05-31
Business Only Initiative: Preferred Hotel Policy | 3120 | 8995 | Business Only Initiative | SGA - Procurement | SG&A | Daniel Provence, Laura Bullion | On Track | Initiative is currently on track | K: L5 | Completed | L5 | 2023-04-12 | 2023-07-14
Business Only Initiative: Screening Services - FY22 Initiative, Negotiation | 4353 | 9024 | Business Only Initiative | SGA - Procurement | SG&A | Rajat Srivastava, Toni Williams, Heather Sprague | On Track | Updating IO | K: L5 | Completed | L5 | 2022-12-01 | 2022-12-01
Business Only Initiative: Packaging - Elimination of Cleaning Cards | 7310 | 9065 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Jason Morgan | On Track | no update as this is active and realizing savings. | K: L5 | Completed | L5 | 2022-12-01 | 2023-03-31
Business Only Initiative: FY24 Retail Fuel Discounts | 46326 | 9194 | Business Only Initiative | SGA - Procurement | SG&A | Amber Bonacci, Lee McCutcheon | On Track | N/A | K: L5 | Completed | L5 | 2023-11-27 | 2024-04-01
Business Only Initiative: Surface Bulk Fuel - Standardize Bulk Purchasing Ac | 51554 | 9202 | Business Only Initiative | SGA - Procurement | SG&A | Candace Lovell, Anthony Calvino | On Track | L2 Business case is being reviewed. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-25 | 2025-03-14
Business Only Initiative: Mobile Vendor Analysis & Consolidation | 70589 | 9203 | Business Only Initiative | SGA - Procurement | SG&A | Diona Hines, Anthony Calvino | On Track | 5/14/2025: After extensive analysis and work, it was determined that accurate savings could not be calculated for this initiative. We are instead pivoting, with leadership approval, to an RFP to consolidate locations under enterprise vendors. 11/15/2024-RFQ Phase 1 submitted and complete 10/15/2024 -Survey complete | C: L1 | Cancelled | L1 Feedback Requested | 2024-09-05 | 2024-09-13
Business Only Initiative: Surface retail fuel - Optimize WEX under one FedEx | 53674 | 9205 | Business Only Initiative | SGA - Procurement | SG&A | Lee McCutcheon, Anthony Calvino | On Track | N/A | K: L5 | Active | TEMP L5 - Enter L5 | 2024-01-02 | 2025-07-21
Business Only Initiative: Reduction of Retail Fuel Purchases-- Driving Bette | 53673 | 9208 | Business Only Initiative | SGA - Procurement | SG&A | Paul Harp, Anthony Calvino | On Track | N/A | K: L5 | Completed | L5 | 2023-11-13 | 2024-01-31
Business Only Initiative: Surface bulk fuel - Bulk supply improvements - Con | 61428 | 9209 | Business Only Initiative | SGA - Procurement | SG&A | Paul Harp, Anthony Calvino | Some Issues | Permit and equipment delays continues to hinder this project. The contractor expects to have permits in hand by October 15th as well as a solid project plan to completion. Hopeful that can be in early to mid December. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-14 | 2026-05-29
Business Only Initiative: Risk management advisory: Demand reduction | 32409 | 9214 | Business Only Initiative | SGA - Procurement | SG&A | Amber Glenn, Matthew Stratton | On Track | 10/23: I received confirmation of no Q1 spend with Marsh. Documentation has been attached on the "attachments" tab. No further action is necessary until the end of Q2. 12/6: I received confirmation of no Q2 spend with Marsh. Documentation has been attached on the "attachments" tab. No further action is necessary until the end of Q3. | K: L5 | Completed | L5 | 2023-07-06 | 2024-07-08
Business Only Initiative: Keyrus data analytics insourcing/vendor change | 32393 | 9217 | Business Only Initiative | SGA - Procurement | SG&A | Rob Farr, Matthew Stratton | On Track | Not doing WTW RFP given alignment with business owner on doing RFP on 2026 after the transformation and simplification for all healthcare plans has been executed. | K: L5 | Completed | L5 | 2023-07-28 | 2025-01-31
Business Only Initiative: Dim & Weight Equipment Sourcing Annual Rebate |  | 92182 | Business Only Initiative | SGA - Procurement | SG&A | Luigi Mastromonaco | On Track | Contract signed, benefits will be measured based on spenf of FY25 and will be tangible in FY26 | K: L5 | Active | L5 | 2025-06-09 | 2026-01-27
Business Only Initiative: Packaging - Plastics - Commercial - Incumbent rene | 30720 | 9327 | Business Only Initiative | SGA - Procurement | SG&A | Anchit Mahajan, Jason Morgan | On Track | Surpassed forecast for last 3 months. Submitting for L5. | K: L5 | Completed | L5 | 2023-06-20 | 2023-11-08
Business Only Initiative: MRO & Supplies - Commercial - Optimized sourcing o | 32484 | 9330 | Business Only Initiative | SGA - Procurement | SG&A | Callie Hinojosa, Jason Morgan | On Track | Continuing to enter in actuals. January 2025 will be a full year of tracking. Should be able to submit to L6 by then. | K: L5 | Completed | L5 | 2023-11-01 | 2023-11-30
Business Only Initiative: Packaging-Polyair Reduce Shipping Cost (US) | 38233 | 9332 | Business Only Initiative | SGA - Procurement | SG&A | Callie Hinojosa, Jason Morgan | On Track | On track | K: L5 | Completed | L5 | 2024-06-26 | 2024-08-09
Business Only Initiative: Uniforms - Demand - Periodic Uniform Allowance | 31784 | 9336 | Business Only Initiative | SGA - Procurement | SG&A | Jason Morgan |  | I talked to Jim Davis in legal, who has been talking to Jeff Robertson in labor relations. They relayed significant concerns that the uniform projects will have on team member morale and, as a result, an impact on the remain independent strategy for FedEx as a whole. It is the recommendation of Legal that we place all uniform initiatives that impact team members on hold until the spring to allow for workforce tensions to relax, and for the newly formed HR and Legal structures to establish a revised policy and strategy. Given this stance, we’re going to cancel tomorrow’s meeting, along with the uniform allocation initiative. That will impact DRIVE savings, but it’s for the right business reason. We’ll alert the DRIVE TO and reflect the changes going forward. Thanks to all of you for working with us, and we’ll revisit this in 6+ months. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-07-25 | 2024-11-21
Business Only Initiative: EMR - Ops Supplies - MRO Catalog Optimization |  | 93405 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | Waiting on PDSM ticket # INC031689306 to move to L3 | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Data entry outsourcing: Commercial | 32405 | 9453 | Business Only Initiative | SGA - Procurement | SG&A | Rajat Srivastava, Heather Sprague | On Track | 7/254/2025:Rebaselined to FY25, no incremental value to FY26 and beyond. Updated Financials accordingly. Action plan required to create RFI and identify potential replacement vendors before timeline can be confirmed. Not a risk to forecast as savings are not anticipated until FY25. | K: L5 | Completed | L5 | 2023-07-07 | 2024-08-30
Business Only Initiative: Implement spend control governance process | 32407 | 9454 | Business Only Initiative | SGA - Procurement | SG&A | Rajat Srivastava, Heather Sprague | On Track | 9/18: This week the pilot plan will be finalized. Still on track to launch the pilot in October. The pilot plan will be presented to senior leadership on 9/21. 9/25: This week I will provide an updated presentation, with feedback received last week, to Leslie so that it can be shared with the Finance Clearinghouse. We will also confirm the appropriate thresholds for committee review. An analysis of contract volume to assist in this decision was provided to McK last week. 10/2: Spend threshold analysis was completed last week. The updated presentation was provided to Leslie to share with her peers. This week I will schedule another working session to further develop the pilot plan. 10/9: Met with core team to discuss next steps. This week, I will work on a communication to share with leadership at Corp. 10/16: Continuing to work on finalizing the pilot. Communication will go out to Corp O&Ds this week or next week. 10/23: Communication was prepared and sent to management for distribution. SOPs for SCT members will be provided early this week. Everything is on track to launch the pilot on 11/1. 10/30: Further discussions are needed at the CVP-level prior to moving forward with the pilot. A meeting is scheduled to be conducted on 11/8. We will move forward in alignment with that discussion. 11/6: Further discussions are needed at the CVP-level prior to moving forward with the pilot. A meeting is scheduled to be conducted on 11/8. We will move forward in alignment with that discussion. 11/13: Leadership decided not to pilot the SCT and instead roll out enterprise-wide. All milestones related to the pilot have been cancelled. An analysis will be performed this week to determine the scope for the new process. 11/20: An analysis is being prepared to determine the scope for the new process. 11/27: Scoping analysis will be provided to Finance leadership by the end of this week. 12/4: Scoping presentation was updated based on feedback provided. A meeting with Finance leadership will be conducted this week. 12/11: Finalizing the submission process this week 12/18: KPI for November was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The full launch is scheduled for Jan. 2024 1/3: Communication for the new process is being drafted by the Comms team;. The SCT Core Team will meet this week to discuss details regarding the launch. 1/8: The SCT core team is waiting on the communication to go out to VPs communicating the new process. 1/19: KPI for December was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The process is ready for launch pending a communication to officers. 2/9: L4 date was pushed out two weeks to allow time to develop a sharepoint site for requestors 2/16: KPI for January was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The process is launching enterprise-wide on March 15, 2024 3/15: KPI for February was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The process is launching enterprise-wide on March 15, 2024 4/8: KPI for March was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The process was launched enterprise-wide on March 15, 2024 5/17: KPI for April was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The process was launched enterprise-wide on March 15, 2024 6/11: KPI for May was zero. The KPI was initially for requests submitted via the pilot. It has since been determined that the pilot will not be completed. The process was launched enterprise-wide on March 15, 2024 7/15: KPI for June was zero. The KPI was ini | K: L5 | Completed | L5 | 2023-07-19 | 2024-10-01
Business Only Initiative: Revise policy and guidelines | 32411 | 9455 | Business Only Initiative | SGA - Procurement | SG&A | Rajat Srivastava, Heather Sprague | On Track |  | K: L5 | Completed | L5 | 2023-07-03 | 2024-05-31
Business Only Initiative: Packaging - Operational print - Contract Re-negoti | 31796 | 9550 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Jason Morgan | On Track | project has completed its cycle, All savings will be transitioned to commerical print market event entry. | K: L5 | Completed | L5 | 2023-07-18 | 2023-11-01
Business Only Initiative: Sort MRO Optimization |  | 98332 | Business Only Initiative | SGA - Procurement | SG&A | Brian Pleslusky | On Track | Rebaselined to FY25 on 05/27/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-31 | 2025-01-31
Business Only Initiative: EMR - 2025 FXF OKC Renewable Natural Gas (RNG) |  | 141860 | Business Only Initiative | SGA - Procurement | SG&A | Paul Harp, Ajay Mahankali, LeRoy Marshall | On Track | . | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: EMR - 2025 Diesel Exhaust Fluid (DEF) |  | 141864 | Business Only Initiative | SGA - Procurement | SG&A | Ajay Mahankali, LeRoy Marshall | On Track | . | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: Modular Conveyor for Manual BTS Projects |  | 141867 | Business Only Initiative | SGA - Procurement | SG&A | Jordan Engle | On Track | Direction from Surface Finance and leadership is to not move forward with entering CAPEX related savings in Planview. Depreciation savings schedule was never established for this initiative and the guidance is to cancel. | C: L1 | Cancelled | L1
Business Only Initiative: Supplies - Cintas lens wipes renegotiation |  | 169868 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella | On Track | 12/29/25: submitted for L4, attached excerpt of billing report by Supplier showing new price (5 USD is in place) as evidence 12/11/25: resubmitted for L3 with requested corrections (added FY28 Exit Rate and added dates for the implementation milestones already completed) Dec 10th: submitted for L3 - added milestones and double checked financials (split by OpCo as already agreed with FP&A) Nov 24th: added Financials as in attached xls and resubmitted for L2 - see also email by FP&A - Aysha Mooghul Nov 21st: updated attached Business Case with different split by BU as per Jennifer Liu suggestion (see attached email too) | I: L4 | Active | L4 | 2025-06-02 | 2026-01-20
Business Only Initiative: EcoVadis and Hoovers - Vendor Reduction |  | 170656 | Business Only Initiative | SGA - Procurement | SG&A | Carlos Stringfellow | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: EMR - Ops Supplies - MRO Pricing Reductions |  | 104783 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | . | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: EMR - Packaging - MEISA Supply Chain Change |  | 132123 | Business Only Initiative | SGA - Procurement | SG&A | Jason Ng, Anchit Mahajan | On Track | 24/02/26: Provided FCF Order details as a proof of money step. 12/08/25: OpCo P&L updated as per the feedback. | I: L4 | Active | L4 | 2025-06-02 | 2026-03-16
Business Only Initiative: EMR - Packaging - FXG Warehouse Packaging Items |  | 132144 | Business Only Initiative | SGA - Procurement | SG&A | Mark West, Anchit Mahajan | On Track | After a deeper review, we’ve determined that this initiative is not aligned with our core packaging focus as initially suspected. Instead, it more closely fits within MRO category as it’s mainly operational items. We will be sharing the details with the appropriate team who is better positioned to lead next steps (if any). | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Sourced Spend Conversion |  | 133058 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | Move to On Hold due to needing more information from Engineering team around the criticality and necessity for OEM parts vs off the shelf items. More information needed from LBC. More information needed around Engineering Change Request Forms | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: EMR - Travel - Airfare Cost Reduction |  | 133481 | Business Only Initiative | SGA - Procurement | SG&A | Patrick McEntire, Nicholas Bidinger, Laura Bullion, Daniel Provence | On Track | Project is to be cancelled, direct by Nike Oyerinde, due to low benefit for high level of work required. | E: L2 | Cancelled | L2 Feedback Requested | 2026-03-27 | 2026-08-05
Business Only Initiative: EMR - Rental Car RFP |  | 133487 | Business Only Initiative | SGA - Procurement | SG&A | Patrick McEntire, Nicholas Bidinger, Laura Bullion | On Track | On Track | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2026-02-02 | 2026-04-30
Business Only Initiative: EMR - Ops Supplies Non Contracted Supplier Cons |  | 133516 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | .Working with internal controls to figure SOP around purchasing and how to combat non-compliant spending, need to revisit with FY25 Spend Data. New Planview Initiative to come | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR - Pro Services - EU Print Invoice RFP |  | 133767 | Business Only Initiative | SGA - Procurement | SG&A | Sreekumar Ramadas, Jonathon Golden | On Track | . | I: L4 | Active | L4 | 2025-06-02
Business Only Initiative: EMR - Pro Services - RRD Print Invoices |  | 133771 | Business Only Initiative | SGA - Procurement | SG&A | Jonathon Golden | On Track | Initiative will not be ready for L2 by requested 10/10 deadline; as such, cancellation of existing initiative and will be re-established in conjunction with the business team when closer to L2 readiness. | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Pro Services - FY26 Rapid Repricing |  | 133774 | Business Only Initiative | SGA - Procurement | SG&A | Sreekumar Ramadas, Jonathon Golden | On Track | . | I: L4 | Active | L4 | 2025-06-02 | 2026-02-23
Business Only Initiative: EMR - Pro Services - In-House Consulting Team |  | 133778 | Business Only Initiative | SGA - Procurement | SG&A | Jonathon Golden | On Track | Given enterprise hiring decisions, this initiative as planned is no longer viable; as such, initiative will be retooled to a FY26 consulting target reduction and resubmitted when ready to communicate. | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Pro Services - Commercial Media Spend |  | 133781 | Business Only Initiative | SGA - Procurement | SG&A | Drew Ray | On Track | N/A. | C: L1 | Cancelled | L1
Business Only Initiative: EMR - US Screening services |  | 136580 | Business Only Initiative | SGA - Procurement | SG&A | STEFANIA MARCHISIO, Laura Bullion | On Track | This project is delayed due to the audit and peak period to January 2026. it will be re submitted in the new year after re alignment with involved functions (HR and US Safety) | E: L2 | Cancelled | L2
Business Only Initiative: EMR Global Payment Cards |  | 136583 | Business Only Initiative | SGA - Procurement | SG&A | Paul Barker, Laura Bullion | On Track | RFI is in process and no problems currently | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2026-01-01 | 2027-04-30
Business Only Initiative: EMR Travel & T&E Savings |  | 142641 | Business Only Initiative | SGA - Procurement | SG&A | Cynthia J. Meade, Laura Bullion, Ta'mia H. Jeffrey | On Track | Following Finance's review of the identified travel savings, they concluded that there were no incremental savings versus FY25 and recommended cancelling the EMR Travel & T&E Savings initiative. | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Pro Services - FY26 Consulting Reduction |  | 165991 | Business Only Initiative | SGA - Procurement | SG&A | Jonathon Golden, Ameera Venkataraman | On Track | As communicated to Scott Higgins, VP FP&A: Main reasons being the lack of consistent year-over-year baseline for actual scope and the requirement to obtain SVP level buy in across multiple portfolios. The $100M target included $150M+ in McKinsey spend, that was designed to support enterprise transformation. While these costs no longer reflect current run rate, they have partly shifted to internal S&W to insource that work. Excluding spend with McKinsey, the SCT has approved $118M of FY26 consulting spend since its launch in April 2025, which represents 24% reduction from the $155M consulting spend compared to FY25 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: EMR - Packaging - Pre-Print to FXO |  | 166029 | Business w/ Tech Initiative | SGA - Procurement | SG&A | Pankaj Kumar Singh | On Track | This initiative was expected to deliver savings by moving pre-printed AWBs in-house. However, Carbonless paper used for AWBs is no longer available. Suppliers are testing new materials which may change pricing and require new printer and IT work. Due to these new variables, the project will not deliver savings this fiscal year. Recommending cancellation for now. | C: L1 | Cancelled | L1
Business Only Initiative: Lyreco Benefit Recovery mechanism |  | 171063 | Business Only Initiative | SGA - Procurement | SG&A | Stefano Baratella | On Track | Feb 3rd: submitted for L4 - invoice to supplier has been posted (see FCF screenshot attached) Jan 20th: resubmitted for L3 after feedback requested by Eryn Walter (details beow): - Same value is populated for the One-time Benefits (Latest Estimate) and L2 One-time Benefit ($)-Soft fields --> it was a mistake (sorry, I did not see "soft"), now Soft benefits are 0 - Does the Completed milestone have dates that can be added? --> Dates have been added Jan 20th: submitted for L3 (completed financials and milestones tabs) Jan 2nd: re-submitted for L2 after clarifications by FP&A (no recurring benefits, only one off - see email by Joseph Nowell attached) Dec 15th: submitted for L2 after OK by Beth Edger (QA Expert) - attached email | I: L4 | Active | L4 | 2025-11-03 | 2026-02-16
Business Only Initiative: MEX ops supplies savings strat by reducing rates |  | 185602 | Business Only Initiative | SGA - Procurement | SG&A | Blanca Martinez | On Track | On Track | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2026-06-01 | 2026-06-01
Business Only Initiative: WEX Fuel Card Contract Extension |  | 186142 | Business Only Initiative | SGA - Procurement | SG&A | LeRoy Marshall | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: FXG Dock Supplies Revamp |  | 188508 | Business Only Initiative | SGA - Procurement | SG&A | Ryan Estes | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: MEISA - Physical Security Guarding & Professional | 70176 | 7211 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion, Vivek Ahlawat | On Track | 2025/05/30: Actuals and savings pending for May month after OAC is confirmed to be available following month end. 2025/05/14: Actuals and Savings reported in Planview for April month. On track. 2025/05/09: Requested Actuals from our MEISA contact, and numbers pending receipt. 2025/05/01: Committed savings are on track. 2025/04/18: Committed savings are on track. 2025/04/11: Committed savings are on track. 2025/04/04: Committed savings are on track. 2025/03/28: FY26 through FY28 revalued. 2025/03/28: Committed savings are on track. 2025/03/23: Committed savings are on track. 2025/03/17: Committed savings are on track. 2025/03/06: Committed savings are on track. 2025/02/14: Committed savings are on track. 2024/12/13: Committed savings are on track. 2024/12/02: Committed savings are on track. 2024/11/26: Committed savings are on track. 2024/09/16: Initiative approved at L5. Following local FP&A approval (Nathan Ng) of the savings trend in MEISA for this initiative, attached is the evidence for this to be approved at L5. | K: L5 | Completed | L5 | 2022-10-03 | 2024-06-28
Business Only Initiative: Remote Monitoring Solutions (Perimeter and Gates) | 58791 | 7269 | Business Only Initiative | SGA - Security | SG&A | Mary Jo Hill, Robert Reetz, Rodney Powell | On Track | 7/10/25: This initiative is still On Hold. FXF will make a final determination on whether to move forward with Birdseye by 5/31/26. 6/13/25: FedEx met with Birdseye to notify them we will be pausing the expansion of the program until the Freight spinoff has been completed. FXF will make a final determination on whether to move forward with Birdseye by 5/31/26. This initiative has been placed On Hold. 5/30/25: This initiative is under additional review based on the upcoming Freight spinoff. 5/16/25: This initiative is under additional review based on the upcoming Freight spinoff. 5/2/25: The MSA is still being finalized with Legal. 4/25/25: The MSA is still being finalized with Legal. Sourcing will identify who will sign on behalf of FXF. 4/11/25: The MSA is still being finalized with Legal. Sourcing will identify who will sign on behalf of FXF. 4/4/25: The MSA is still being finalized with Legal. Sourcing will identify who will sign on behalf of FXF. 3/28/25: The MSA is still being finalized with Legal. This initiative has been rebaselined to reflect FY25, and the forecast for FY26-FY28 has been updated. The forecast is based on the assumption the MSA will be fully executed by 5/31/25. 3/21/25: Birdseye agreed to a $10M liability cap with no cost pass through to FedEx. They submitted an updated draft of the MSA with their edits for FedEx Legal to review. Legal is finalizing. 3/14/25: Birdseye agreed to a $10M liability cap with no cost pass through to FedEx. They submitted an updated draft of the MSA with their edits for FedEx Legal to review. Legal is finalizing. 3/7/25: Birdseye agreed to a $10M liability cap with no cost pass through to FedEx. They submitted an updated draft of the MSA with their edits for FedEx Legal to review. Legal is finalizing. 2/28/25: Birdseye agreed to a $10M liability cap with no cost pass through to FedEx. They submitted an updated draft of the MSA with their edits for FedEx Legal to review. A call is scheduled on March 5th, to discuss a deployment/installation strategy. 2/21/25: FedEx and Birdseye Legal teams are still negotiating. Birdseye advised they will need to raise the hourly rate for service, to help absorb additional costs they will have if they agree to the limitation of liability proposed by FedEx. The increased hourly rate dips into the anticipated savings and also reduces the 12 locations with savings down to only eight, if there is still a 3% annual increase. Security met with Risk Management to discuss bottom dollar and the target amount for limitation of liability. Procurement is continuing negotiations with Birdseye. 2/14/25: FedEx and Birdseye Legal teams are still negotiating. Birdseye advised they will need to raise the hourly rate for service, to help absorb additional costs they will have if they agree to the limitation of liability proposed by FedEx. The increased hourly rate dips into the anticipated savings and also reduces the 12 locations with savings down to only eight, if there is still a 3% annual increase. Security met with Risk Management to discuss bottom dollar and the target amount for limitation of liability. Procurement is continuing negotiations with Birdseye. 2/10/25: FedEx and Birdseye Legal teams are still negotiating. Birdseye advised they will need to raise the hourly rate for service, to help absorb additional costs they will have if they agree to the limitation of liability proposed by FedEx. The increased hourly rate dips into the anticipated savings and also reduces the 12 locations with savings down to only eight, if there is still a 3% annual increase. The call scheduled for last Wednesday, to discuss a deployment stategy, was put on hold and the Security team is going to meet with Risk Management tomorrow, February 11th. 2/3/25: FedEx and Birdseye Legal teams are still negotiating limitation of liability. Based on the last call, it appears we are close to an agreement. A call is scheduled | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-10-31 | 2025-08-14
Business Only Initiative: US contract security guard reductions | 61507 | 7299 | Business Only Initiative | SGA - Security | SG&A | Lori Parks, Erin Owen | On Track | 6/10/25: May actuals have been entered. Favorable by ~$256k. 5/12/25: April actuals have been entered. Favorable by ~$178k. 4/8/25: March actuals have been entered. Favorable by ~$130k. Guard invoices for the last week of March have not been fully processed and logged. Estimated amounts. Location CARN/110: Hours were reduced in September 2024 to 304 hpw at this location for standard Officer coverage. A decision was made/approved in late February 2025 to increase the standard Officer hours at this location to 392 hpw (an increase of 88 hpw). There were 88 hpw being charged to the repairs/maintenance category (which is a different GL account) for the entire FY25 to-date which have now been converted to standard/permanent. 3/28/25: Re-baselined based on FY25 actuals. 3/7/25: February actuals have been entered. Favorable by $115k. Guard invoices for last week in February have not been fully processed and logged. Estimated amounts. 2/11/25: January actuals have been entered. 1/14/25: December actuals entered were approx. $68k less than forecasted. The forecast spread the annualized savings evenly over 12 months. Actual hours and expenses were slightly higher due to added coverage for peak, remote lots added, holiday bill rates and 2 PA, NY, NJ 5% bill back fees for the EWR Ramp incurred in December (normally there is only 1), resulting in an additional/unplanned ~$20k. 12/11/24: When forecast was prepared the annualized savings was spread evenly over 12 months. Actuals are greater than forecasted for November due to the Thanksgiving holiday and holiday rates being applied to hours work for the holiday. 12/9/24: Nothing significant to report. Still waiting on guard invoice data to enter Novemeber actuals. 12/2/24: Nothing significant to report. 11/25/24: Nothing significant to report. 11/18/24: The savings for October were slightly higher due to 5 billing weeks in the month. Projected forecast reviewed and accurate based on current data. 8/14/24: Holiday (July 4) included in this month's impacts-Guard vendors are paid a higher bill rate for that day. Additionally, July had 5 billing weeks. Lastly, effective June 2024, the increased FY25 bill rate took effect (approximately 3-4% increase). 7/5/24: Removed the LAX Hanger location from the impacts calculation (~$49,504 recurring monthly benefit). The LAX Hanger is empty and there are no longer employees reporting. LAWA is currently conducting environmental studies. The hanger will eventually be demolished but there is not a timeline for completion. IThe savings will be captured under a future initiative, if appropriate. By removing LAX Hanger from this initiative's impact, the initiative is now ready for L4 submission. 6/19/24: The impacts for May were slightly less (recurring benefit) due to one additional billing week as well as holiday rates due to the Memorial Day holiday. 4/17/24: Per WR - Erice Muneno the guards will not be removed from LAX Hanger until the end of May. There are currently no employees at the location and the guards staff has been reduced to the minimum. The hanger is currently being demolished. The savings associated with this for WR Express has been reforecasted to not impact until FY25/June. 3/25/24: Some sites in the ER were removed from initiative. Some of the hours being reduced were related to WPV, repairs, construction coverage which were not in the baseline. There were also a couple of initiatives that the savings was captured under a different initiative (#5640). There still may be additional WR Express locations added to this initiative. Also, removed the one time cost since the BJD has not yet been drafted and/or approved. 3/5/24: Per John Walsh: Hartford/061 was included in the original analysis. Since this is a major HUB, it was decided to not reduce guards at this time. | K: L5 | Completed | L5 | 2023-11-01 | 2024-12-31
Business w/ Tech Initiative: Transition LiveSafe to Everbridge | 96133 | 7368 | Business w/ Tech Initiative | SGA - Security | SG&A | Virginia S. Geater, Hugh Hatley, Erin Owen | On Track | VSG - 3/9/26 - No change; awaiting 3 months of maximum savings; will move to L5 in June 2026 VSG - 2/9/26 - No change; awaiting 3 months of maximum savings; will move to L5 in June 2026 VSG - 1/29/26 - Per feedback received after submitting to L5, the project will be resubmitted to L5 when the project has met 3 months of the maximum savings (March - May 2026) VSG - 1/12/26 - No change; submitted to L5 VSG - 12/8/25 - No change; moving to L5 VSG - 11/10/25 - No change; awaiting 3 months of mature actuals before move to L5 (November 25) VSG - 10/3/25 - No change; awaiting 3 months of mature actuals before move to L5 (November 25) VSG - 9/12/25 - No change; awaiting 3 months of mature actuals before move to L5 (November 25) VSG - 8/12/25 - No change; project is complete VSG - 8/4/25 - As requested to move from L3 to L4, the Source article from 7/17/25 was uploaded in the Content tab. VSG - 7/17/25 - Workday launch occurred 7/14/25; Mobility push to FedEx owned devices occurred 7/16/25; Communication via the Source occurred 7/17/25. This project is considered complete. VSG - 7/10/25 - Workday MTP is scheduled for 7/14/25 and Mobility MTP is scheduled for 7/15/25. Communications in the Source is scheduled for 7/15/25. VSG - 6/25/25 - Workday testing has been successful; team will continue to test for next 2 weeks and complete MTP paperwork with new expected launch date of 7/15/25. Mobility testing is in progress to auto-push app to corporate devices. VSG - 5/29/25 - Workday integration is being tested; Based on outcome of testing, new launch date is set for 6/16/25. VSG - 5/15/25 - Testing conducted week of 5/13/25; Training is on schedule to be conducted 5/21 VSG - 4/29/25 - FIRST has been approved; Workday Integration team working with Everbridge to establish API connection; MVP of new app funcationality has been completed and ready for testing. Training currently scheduled for 5/21. VSG - 4/16/25 - Pending integration development with HRT, which requires the FIRST to be complete prior to development; FIRST has been approved by 5 of 6 approvers. VSG - 3/28/25 - Progressing with ES HRT ART to develop the integration with Workday; next meeting scheduled 4/1/25 VSG - 3/17/25 - Received approval to move to L3 on 3/7; contract approved and executed 3/12/25. Status moved to "On Track". VSG - 3/7/25 - Finance approval received 3/6; now awaiting Tracy Brightman approval to move to L3. The Encore contract process cannot continue until the project moves to L3. VSG - 3/5/25 - PEL greenlight received 2/18; awaiting Finance review/approval to move to L3; as project is 3 months behind (original expected start date was 12/2/24), changed Health Status to "Some Issues" VSG - 2/6/25 - Greenlight received from SCO on 1/30/25; awaiting PEL mtg with ES on 2/18 for greenlight VSG - 11/26 - Waiting Architectural Review Contract has been submitted to EnCore for review | I: L4 | Active | L4 Feedback Requested | 2024-09-02 | 2025-07-17
Business Only Initiative: Aviation: Dual use MSA Screening | 91789 | 7587 | Business Only Initiative | SGA - Security | SG&A | Sarah Washington, Hugh Hatley, Tamara J. Hudson | On Track | 6/4/25 Confirmed actuals for May 2025, 101,604 savings. Continuing to monitor. 5/13/25 Removed FY26 exit rates and added data for FY27 and FY28. 5/2/25 Updated April Actuals, Rebaselined to FY25, updated FY25 & 26 exit rates. Initiative will be closed out prior to FY28. 4/30/25 Continuing to monitor. Recurring benefits updated to 1,219,248 annually 4/8/25 Confirmed actuals for March 2025, 101,604 savings 4/4/25 Continued monitoring 3/13/25 Entered L5. Currently monitoring 3/13/25 Approval for L5 submitted. 3/7/25 Actuals verified for February ending the 3 month reviewal/monitoring phase. Savings slightly lower due to short month. Requesting consideration to move project to L5. 2/27/25 Monitoring actuals. Will submit to L5 once the actuals are reviewed from February invoices. 02/06/25 Monitoring actuals over the next 1 month with a target date of March 2, 2025 to submit to L5 01/31/25 Monitoring actuals over the next 1.5 months with a target date of March 2, 2025 to submit to L5 01/21/25 Monitoring actuals over the next 1.5 months with a target date of March 2, 2025 to submit to L5 01/14/25 On Track. December, 2024 projections confirmed as Actual, increasing monthly savings of $101,604. Will continue to monitor for L5 March 2, submission. 12/13/24 On Track...continuing to monitor 12/5/2024Monitoring actuals over the next 3 months with a target date of March 2, 2025 to submit to L5 12/2/2024L4 Approval received 11/26/2024Submitted for L4 approval 11/26/2024MSA Dual Role Contract and AU Termination Letters complete. Full dual role model for use moving from 7 locations to 29 locations effective 11/30/24 11/25/2024L3 approval obtained. Submission to L4 (money step validation will be submitted 11/26/24 11/14/2024Dual Role Initiative is at Stage Gate 3. Appears to be waiting on additional approvals 11/7/2024KPI’s of cost reduction and reduction of vendor numbers (Phase 1: $117/hr down to $93/hr and reduction of vendors from 16 to 6..6 rather than 8 due to the Network 2.0 closure site in Herndon, VA-BCBA). Our work order and expectations are in the final stages for execution to MSA. Savings rationalized earlier this month for savings. 11/1/2024October savings ~$34K (7 locations dual role and 1 closure). Our work order and expectations are in the final stages for execution to MSA. 10/29/2024SOW and expectations submitted and in review for contract amendment with MSA. 10/14/2024Upon Planview integration, this initiative will be updated to include the remaining 22 locations for overall projected savings of ~1.1M annually 10/7/2024MSA has agreed conversion of the remaining 22 US locations can begin Jan. 1, 2025. Legal and Procurement are engaged and starting the Termination Notice process for Allied-Universal, effective 12/31/24 at 2359 hrs. 10/1/2023Pilot implemented at ORDR using MSA to complete all cargo screening functions without support of the second contractor Allied - Universal (MSA did not request a bill rate increase for the pilot) 10/1/2024Allied-Universal termination effective date. FY25 projected savings ~$323K. 7 locations (6 to single contractor dual role and 1 termination of all cargo screening due to Network 2.0 at Herndon, VA) 9/25/2024MSA contacted to provide timeline of taking over 22 additional locations throughout the US resulting in an additonal ~ $809K in OSC reduction in cost. Advised by MSA 60-90 days is required due to completing additional training for added responsibilities. (22 additional targeted locations at ~$3,066 savings/location = ~$67,452 / month ….~$809,424 annually, total OSC annual cost reduction for all locations projected at ~$1.1M ) 9/25/2024Submitted for L2 approval. Resubmission was necessary and all approvals completed for L2 9/18/2024"Business case submitted for review prior to L2 submission. Overview: Single OSC-Dual role model concept August 2023 ORDR Pilot (Single OSC-Dual role) October 2023 Concept Validation October 2023 – September 2 | K: L5 | Completed | L5 | 2024-06-03 | 2024-10-31
Business Only Initiative: Amarok invoicing | 92617 | 7636 | Business Only Initiative | SGA - Security | SG&A | Lori Rankin, Robert Reetz, Chris Connors | On Track | 03/04/25 - On track. Savings were realized with payment of June 2024 invoice. In L4 04/22/25 - On track, In L5, rebaselined 5/7/25 - On track, April savings updated | K: L5 | Completed | L5 | 2024-07-22 | 2024-07-22
Business Only Initiative: Alarm Monitoring Insource from JCI to GSOC | 92621 | 7637 | Business Only Initiative | SGA - Security | SG&A | Lori Rankin, Jason Campbell, Jennifer Skertich | On Track | 9/19/24 - Business case in process. Working with IT and GSOC to determine if cellular link can be removed and alarms put onto Fedex Network. Additional savings would be removal of cellular cost as well as the backup POTS line currently being used at the legacy Ground sites. In L1 11/24/24 - On track. Pilot currently underway with IT to evaulate process for moving alarms on to Network. In L3 1/10/25 - On track. Pilot currently underway with IT to evaulate process for moving alarms on to Network. In L3 1/17/25 - On track. Pilot currently underway with IT to evaulate process for moving alarms on to Network. In L3 3/04/25 - On track. IT Pilot complete. Starting process with IT to move alarms to the FedEx Network. IT has additional wiring to complete before we can move them. SVP approval received on IT work, forwarded to IT. In L3 5/8/25 - On track. Pilot site complete - successfully moved NPIT alarm to GSOC. IT is on schedule to complete all wiring. Milestones updated to reflect GSOC avaiablity to complete moving alarms. 5/30/25 - On track. Held pilot post mortem with GSOC. Working thru panel replacement options with JCI due to the age of the panels and the connectivity to GSOC. 6/18/25 - Due to some alarm panels being at end of life, we are waiting for FY26 Surface funds to be approved to move forward. 7/14/25 - On track 8/1/25 - On track 8/8/25 - On track. 1% complete and moved to GSOC 8/22/25 - On track. 1% complete and moved to GSOC 8/29/25 - On track. 1% complete and moved to GSOC 10/17/25 - On track. 1% complete and moved to GSOC. IT is approximately 90% complete with their work. 11/11/25 - On track. IT completed moving alarms to network on 604 sites. 45 remain. GST work is slow as we work to move the alarms to the GSOC. 4 alarms were transitioned last week. 12/8/25 - On track. IT has 9 sites left to complete. Will be in January due to Peak IT freeze. Milestone date updated. GST has 2% completed and moved to the GSOC 2/10/26 - On Track IT completed on time. GST completed 7 additional sites last week. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-02-03 | 2026-12-31
Business w/ Tech Initiative: Global Guard RFP | 3732 | 9018 | Business w/ Tech Initiative | SGA - Security | SG&A | Christopher M. Winans, Charissa McNatt, Quincy McGlown, Ryan Nelson | On Track | 07/22/25 - CW - This is a duplicate of an existing initiative 87999 – EMR Security Bid Event. Initiative 87999 has updated forecasts and rationale. Chris Winans have requested that this Initiative be cancelled. (PDSM Ticket#INC031490804) | G: L3 | Cancelled | L3 Data Migration - TEMP | 2025-01-01 | 2026-10-12
Business Only Initiative: Reduce guard cost in parking areas | 5640 | 9054 | Business Only Initiative | SGA - Security | SG&A | Steven Ward, Lori Parks | On Track | 6/4/25: May actuals entered. Favorable by ~$100k. Guard invoices for last couple weeks in May have not been fully processed and logged. Estimated amounts. 5/12/25: April actuals entered. Favorable by ~$17k. 4/8/25: March actuals entered. Favorable by ~$16k. Guard invoices for the last week of March have not been fully processed and logged. Estimated amounts. 3/28/25: Re-baselined based on FY25 actuals. 3/7/25: February actuals entered. Unfavorable by ~$3.5k. Guard invoices for last week in February have not been fully processed and logged. Estimated amounts. 2/10/25: January actuals entered. 1/15/25: Increased forecast to account for increased savings for 316/East Atlanta. Savings has been moved over from Phoenix. 1/14/25: Initiative approved by Patrick Duffy for L5. 1/13/25: December actuals entered. Slightly under forecast due to holiday rates & changes in hours due to peak coverage. 1/6/25: Working on December financial impacts. Once December actuals are entered the inititiave will be reviewed for L5 submission. 12/9/24: November impacts entered. Nothing significant to report. 12/2/24: Nothing significant to report. 11/25/24: Advanced to L4. **11/19/24**: The value of the initiative changed due to the following sites being removed from the scope. Below is an itemization of the locations and a brief explanation as to why they were removed. 1. COGA 319 - The site said there are no guards currently being used for the parking lots and that the lease is ending in April 2025. 2. QFLR 3928 – Site was told DRIVE requirements to eliminate guards at start of project. Once the RAD units were installed the site was unable to eliminate the guards. 3. NCAN 447 – The airport did not allow RAD units on property due to the solar panels. Units have been removed. 4. QEBK 3112 – Access control and CCTV were installed, and guards were then eliminated. No need for RAD units. 5. BURB 918 – No guards being used in the employee parking lot. 6. ANAH 928 - No guards being used in the employee parking lot. 7. NASH 371 - The guard spend is less that RAD costs. 8. STAT 304 – Site already cancelled guards at remote lot across the street. 9. SNFD 347 – Site couldn’t cancel guards because they check the ID of vehicles as they enter the remote lot. 10. QBTH 3117 – Legal concerns about installing RAD in a shared parking lot with other tenants. 11. QNHW 3913 – Site only had one guard onsite. They had other duties inside the building besides the parking lot. 12. WSNC 299 – Site couldn’t cancel guards because they open and close the gates. 13. NYNY 100 - Site couldn’t cancel guards because they open and close the gates. 14. MARI 305 - No guards being used in the employee parking lot. 15. MEMP 381 - Site was told DRIVE requirements to eliminate guards at start of project. Once the RAD units were installed the site was unable to eliminate the guards. 16. NMEM 399 - MEMP 381 - Site was told DRIVE requirements to eliminate guards at start of project. Once the RAD units were installed the site was unable to eliminate the guards due to crime. 17. LERS 378 – The guard reduction taken was related to a gate construction project and therefore cannot be applied to the savings for this initiative. 18. ESAC 957 – Unable to validate guard savings from baseline v. actuals after the equipment was installed. 19. SACR 958 – Unable to validate guard savings from baseline v. actuals after the equipment was installed. 20. ATLA 303 – Only partial guard reduction taken. **11/12/2024** Once October actuals are entered the initiative will be submitted for L4. Effective 6/2024 (FY25): Hourly bill rate increases went into effect with the Contract Security Vendors (~3% increase). This will impact the recurring benefit. 4/2/2024 Devices being deployed next week 04/01-04/05: 5 RIO 360s SACR 958 8200 Elder Creek Road Sacramento, CA 95824 4 ROSAs ESAC 8371 Rovana Circle Sacramento, CA 95828 4 RIO 360s MEMP 381 555 Compress D | K: L5 | Completed | L5 | 2022-11-28 | 2025-04-30
Business Only Initiative: Facility Security FXF Guard Costs Reduction | 16012 | 9261 | Business Only Initiative | SGA - Security | SG&A | Mary Jo Hill, Lori Parks | On Track | 6/4/25: May actuals entered and are unfavorable by approx. $133k. Guard tracker items were entered documenting temporary hours added at 4 locations due to repair/maintenance issues, 1 location for a construction project and multiple locations needing coverage due to the Memorial Day holiday. 5/6/25: April actuals entered and are unfavorable by approx. 46k. Guard tracker items were entered documenting temporary hours added at 3 locations due to contruction and/or repairs at locations. 4/8/25: March actuals entered and are unfavorable by approx. $113k. Lowered forecast for remainder of Q4. 3/26/25: Zeroed out FY26-FY28 values since initiative will meet the L5 tracking requirements for FY26. 3/7/25: February actuals entered and are unfavorable by approx. $91k. There were 7 temporary posts added in February: 2 were added due to cut fences, 2 were added due to a broken gates and 3 were for firewatch until GSOC is able to begin monitoring the Fremont, IN location. Lowered forecast for Q4. Note: In early FY23 FXF noticed a substantial increase in guard spend compared to FY22. Swift action was taken to eliminate guarding at 20 service centers in Q3/Q4 of FY23. FY23 is the baseline for this initiative. A more detailed description of this is added to "content" labeled "9261 Financial impact variance explanation". 2/10/25: January impacts entered. January savings were less than forecasted. January consisted of 5 billing weeks compared to the baseline for FY23 January which had 4 billing weeks. Additional negative impacts to the financials for January include coverage due to multiple facilities being closed for the holiday and holiday bill rates applied. There were unplanned guards added to a few facilities due to repair/maintenance issues, one new facility opened (which is not in the baseline) and one location required WPV coverage to be added temporarily. NRB is trending closer to 6.1M for FY25. 1/13/25: December impacts entered. December savings were less than forecasted. Hours were increased during December due to facility being closed during holidays and holiday bill rate applied to that additional coverage. NRB is trending towards 6.4M 12/9/24: November impacts entered. December forecast has been lowered slightly due to increased guard hours for peak/holiday coverage. Still anticipated to achieve annual NRB. 12/2/24: Nothing significant to report. 11/25/24: Nothing significant to report. 11/12/24: As indicated in the original rationale entered, the savings per year was averaged over a 12-month period with the anticipation that some month the actuals could fluctuate over or under the monthly forecast. FY25 October actuals are coming in less than forecasted due to 2 factors: 5 billing weeks in the month of October and historical trends indicate an increase in criminal activity and/or WPV during the fall months, necessitating additional guard services at increased hourly rate, resulting in increased guard spend. Based on trending, we expect November to be very close to the $540k forecasted. When calculating the DRIVE Initiative guard service reduction figures, our FedEx Freight Security planning team was deliberately conservative with our estimates to allow for unforeseen variances in guard costs. Our saving forecasts were averaged over the twelve months of FY24, and we anticipated that some months could result in better savings than other months. The variances we anticipated include adding guards (including costly armed guard coverage) in response to unforeseen workplace violence incidents, guard coverage for unanticipated construction projects and, vendor invoicing lag times. During the DRIVE Initiative planning phase, we partnered with FedEx Freight Finance who agreed with this approach to ensure we accomplished our goals and that we were not over committing. | K: L5 | Completed | L5 | 2023-02-01 | 2023-09-29
Business Only Initiative: LAC: Brazil Security Initiative | 17505 | 9357 | Business Only Initiative | SGA - Security | SG&A | Erin Owen, Natasha Oliveira | On Track | 4/18/2025 No change 3/21/25 No change 03/11/2025 Deploy Technology at VCP Ramp Tomorrow, they will receive the ATS vendor in VCP, who will perform a series of tests at the checkpoints to create the report to send to ANAC along with the other documentation. 03/10/2025 - No change. 3/4/25 No change. 02/19/2025 Deploy Technology at VCP Ramp The status remains the same, but with a small update. This week, the supplier will learn about the technology, with the aim of presenting us with a proposal to submit the cabins to efficiency tests. After this stage, the report required by ANAC will be issued. 02/17/2025 Issue at Cuiaba location caused increased expense and slight unfavorability 02/05/2025 The Checkpoints are currently operating on a test basis, as previously authorized by ANAC. They are operating very well and without problems. We are gathering the necessary documentation (technical report, SOP, manufacturer's manual, among others) to request the official letter requesting ANAC's approval to operate without the need for security agents at the Checkpoints. has context menu 01/20/2025 Deploy Technology at VCP Ramp The technology is functioning well, and it is believed that the project is in its final stages. A service provider will be hired to conduct a series of tests on the cabins and generate a technical report on their functionality. Once this process is completed, the project will be ready to be submitted for approval by ANAC. 12/11/24 Deploy Technology at VCP Ramp GPS contract has been fully signed. Although we have red-flagged GPS over the past months that hiring AVSEC-certified agents for a twelve-hour shifts with equivalent salaries of an AVSEC-certified agent in the market working for 6 hours, they could not complete the full SOC scope with a total of 6 agents. With that in mind we will need a contract addendum excluding the SOC services as for the short term we will start with Orbital's headcount already certified and working in our facility. GPS ongoing training with Orbital agents since Sep 23rd up to Oct 2nd. Technology and people are done. There are three cabins and one is in the testing phase so that we can release the three cabins for operation. Completion set for January. 12/2/24 Deploy Technology at VCP Ramp GPS contract has been fully signed. Although we have red-flagged GPS over the past months that hiring AVSEC-certified agents for a twelve-hour shifts with equivalent salaries of an AVSEC-certified agent in the market working for 6 hours, they could not complete the full SOC scope with a total of 6 agents. With that in mind we will need a contract addendum excluding the SOC services as for the short term we will start with Orbital's headcount already certified and working in our facility. GPS ongoing training with Orbital agents since Sep 23rd up to Oct 2nd. Expected go live is now Oct 7th. Technology and people are done. There are three cabins and one is in the testing phase so that we can release the three cabins for operation. These 30 days will be used for the testing phase. I will extend the date on the wave for completion in 30 days. In this way, the project completion date is November 30th in Planview. 11/25/24 Deploy Technology at VCP Ramp GPS contract has been fully signed. Although we have red-flagged GPS over the past months that hiring AVSEC-certified agents for a twelve-hour shifts with equivalent salaries of an AVSEC-certified agent in the market working for 6 hours, they could not complete the full SOC scope with a total of 6 agents. With that in mind we will need a contract addendum excluding the SOC services as for the short term we will start with Orbital's headcount already certified and working in our facility. GPS ongoing training with Orbital agents since Sep 23rd up to Oct 2nd. Expected go live is now Oct 7th. Technology and people are done. There are three cabins and one is in the testing phase so that we can release the three cabins for operat | K: L5 | Completed | L5 | 2023-03-01 | 2025-01-31
Business Only Initiative: Mexico Security Initiative | 17601 | 9362 | Business Only Initiative | SGA - Security | SG&A | Erin Owen, Natasha Oliveira | On Track | 4/18/25 No change L5 3/21/25 No change L5 3/4/25 No change: Mexico at L5 2/17/25 No change; Mexico at L5 1/20/25 No change, Mexico is at L5 12/11 No change, Mexico is at L5 12/2 No change, Mexico is at L5 | K: L5 | Completed | L5 | 2023-03-01 | 2024-05-31
Business Only Initiative: Equipment Maintenance Optimisation | 20244 | 9447 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion | On Track | 24.03.2025: Rebaselined 26-28 Initiative will be closed at June. 03.12.2024: No change 26.11.2024: L5 since May 2024 - we continue to track savings and currently savings remain consistent. Attachment includes FY22 baseline values from Oracle Analytics Cloud (OAC). | K: L5 | Completed | L5 | 2022-10-03 | 2024-02-29
Business Only Initiative: OSC Physical Security Guarding Optimisation | 20247 | 9449 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion | On Track | 24.03.2025: Rebaselined 26-28 Initiative will be closed out in June. 03.12.2024: No change 26.11.2024: L5 since July 2024 - we continue to track savings and currently savings remain consistent. The team were required to add further content to the attachments including FY22 base values before this could be progressed to next stage approvals. This has now been validated by FP&A Europe. | K: L5 | Completed | L5 | 2022-10-03 | 2024-04-30
Business Only Initiative: OSC Security Screening Optimisation | 20249 | 9450 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion | On Track | 24.03.2025: Rebaselined 26-28. Initiative will be closed out in June. 03.12.2024: No change 26.11.2024: L5 since May 2024 - we continue to track savings and currently savings remain consistent. The team were required to add further content to the attachments including FY22 base values before this could be progressed to next stage approvals. The file now includes the additional content. | K: L5 | Completed | L5 | 2022-10-03 | 2023-09-29
Business Only Initiative: Physical Security Guarding Optimization | 21426 | 9477 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion, Simon Patterson | On Track | 2025/05/30: Actuals and savings pending for May month after OAC is confirmed to be available following month end. 2025/05/09: Actuals and savings included in Planview for April month as provided by FP&A APAC. 2025/05/01: Our annual FY25 savings for this initiative are predicted to end the year at circa $3.9m, against our comitted savings of $3.1m, so an overall improvement expected to be circa $0.8m. 2025/04/18: Our annual FY25 savings for this initiative are predicted to end the year at circa $3.9m, against our comitted savings of $3.1m, so an overall improvement expected to be circa $0.8m. 2025/04/11: Further to the below. The team in APAC has provided the actuals for guarding in the new locations / new services during FY25 as these costs should not have been included in DRIVE, so we have now acted to remove these from the financials, thereby increasing our savings in FY25. 2025/04/04: Vendors in scope for this initiative have been incorporated into guarding in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. The team in APAC is currently looking to obtain the actuals for guarding in the new locations / new services so we can act to remove these from the financials, thereby increasing our savings. 2025/03/28: Vendors in scope for this initiative have been incorporated into guarding in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. The team in APAC is currently looking to obtain the actuals for guarding in the new locations / new services so we can act to remove these from the financials, thereby increasing our savings. 2025/03/23: Vendors in scope for this initiative have been incorporated into guarding in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. 2025/03/17: Vendors in scope for this initiative have been incorporated into guarding in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. 2025/03/06: Analysis of savings versus baseline values has now been conducted centrally and at a regional level. FP&A in APac has reviewed the numbers and a re-forecast has been conducted in view of the impact of increased tariffs and other local operational developments increasing costs for the vendors in scope for this initiative. 2025/02/14: Analysis of savings versus baseline values has now been conducted centrally and at a regional level. FP&A in APac is now reviewing the numbers so that we can accurately re-forecast in view of the impact of increased tariffs applied to vendors in sco | K: L5 | Completed | L5 | 2023-01-31 | 2023-12-29
Business Only Initiative: Security Screening Optimization | 21431 | 9478 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion, Simon Patterson | On Track | 2025/05/30: Actuals and savings pending for May month after OAC is confirmed to be available following month end. 2025/05/09: Actuals and savings included in Planview for April month as provided by FP&A APAC. 2025/05/01: This initiative has been impacted by regulatory and inflationery tariff increases for the vendors in scope. Our predicted annualized savings for FY25 were $1.5 million; we expect to end FY25 with savings of circa $700k, so $800k less than originally predicted due to these tariff increases. 2025/04/18: This initiative has been impacted by regulatory and inflationery tariff increases for the vendors in scope. Our predicted annualized savings for FY25 were $1.5 million; we expect to end FY25 with savings of circa $700k, so $800k less than originally predicted due to these tariff increases. 2025/04/11: Further to the below, the team in APAC has provided the actuals for screening in the new locations / new services during FY25 as these costs should not have been included in DRIVE. We have now removed these from the financials, thereby increasing our savings for FY25. 2025/04/04: Vendors in scope for this initiative have been incorporated into screening in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. The team in APAC is currently looking to obtain the actuals for screening in the new locations / new services so we can act to remove these from the financials, thereby increasing our savings. 2025/03/28: Vendors in scope for this initiative have been incorporated into screening in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. The team in APAC is currently looking to obtain the actuals for screening in the new locations / new services so we can act to remove these from the financials, thereby increasing our savings. 2025/03/23: Vendors in scope for this initiative have been incorporated into screening in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. 2025/03/17: Vendors in scope for this initiative have been incorporated into screening in completely new locations/ or current locations requiring new services to meet operational changes and this is why our savings numbers have been reduced from what was predicted against these vendors in APAC when measured against our FY22 baseline values. We believe we should remove the 'actuals' associated with these new locations and added services to meet operational demands which will then mean our predicted savings would be on track. 2025/03/06: Analysis of savings versus baseline values has now been conducted centrally and at a regional level. FP&A in APac has reviewed the numbers and a re-forecast has been conducted in view of the impact of increased tariffs and other local operational developments increasing costs for the vendors in scope for this initiative. 2025/02/14: Analysis of savings versus baseline | K: L5 | Completed | L5 | 2023-02-13 | 2024-02-29
Business Only Initiative: APac - Equipment Maintenance Optimization | 25548 | 9538 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Dianne Bellion, Simon Patterson | On Track | 2025/05/30: Actuals and savings pending for May month after OAC is confirmed to be available following month end. 2025/05/09: L5 approval gained 2025/05/02. April Actuals and Savings have been added to Planview. 2025/05/02: Based on L5 evidence, Finance Domain Lead approved for this initiative to be progressed to L5. 2025/05/01: Following approval from local FP&A Analyst for APAC to progress this initiative to L5, now written to Finance Domain Lead to gain email approval before progressing this to L5 in Planview. 2025/04/18: Written to local FP&A Analyst for APAC, providing evidence to support progress to L5 for this initiative. 2025/04/11: Actuals and savings continuing to be tracked and reported monthly. Once March numbers are recorded, L5 will be progressed for approval in April - 3 months following L4 approval gained in January 2025. 2025/04/04: Actuals and savings continuing to be tracked and reported monthly. L5 is now being progressed for approval in April - 3 months following L4 approval gained in January 2025. 2025/03/27: FY26 through FY28 revalued. 2025/03/23: Actuals and savings continuing to be tracked and reported monthly. L5 will be progressed for approval in April - 3 months following L4 approval gained in January 2025. 2025/03/17: Actuals and savings continuing to be tracked and reported monthly. L5 will be progressed for approval in April - 3 months following L4 approval gained in January 2025. 2025/03/06: Actuals and savings continuing to be tracked and reported monthly. L5 will be progressed for approval in April - 3 months following L4 approval gained in January 2025. 2025/02/14: Actuals and savings continuing to be tracked and reported monthly. L5 will be progressed for approval in April - 3 months following L4 approval gained in January 2025. 2025/01/15: L4 approval gained. Now working to achieve L5. Actuals and savings continuing to be tracked and reported monthly. 2025/01/03: Final milestone - Money Step - completed. Now progressed to L4 to gain approval. 2024/12/13: Final Milestone - Money Step - is due to be completed by end of January 2025. In progress. 2024/12/05: Milestones now completed that were due December month. Final Milestone - Money Step - is due to be completed by end of January 2025. 2024/12/02: Milestones due at the end of December are on track for completion. Committed savings are on track 2024/11/26: Milestones due at the end of December are on track for completion. Committed savings are on track. The milestones including Money Step and KPIs have now been added to this initiative. The money step is also described on the Business Case tab as per Jane's advice. | K: L5 | Completed | L5 | 2023-01-02 | 2025-01-31
Business w/ Tech Initiative: FUSUS Core NVR Initiative | 94741 | 8729 | Business w/ Tech Initiative | SGA - Security | SG&A | Robert Walker, Maurice Morgan | On Track | Update as of 11/12/24: Impact Assessment Specification Required from Enterprise Architecture to complete LBC. Enterprise Architect currently not assigned. Potential delay on progression to L2. Timeline TBD. Update as of 11/25/24: FUSUS Core NVR Initiative (ID 8729) is currently #134 out of 180 initiatives slated in L1 that would need to undergo Alignment & Rationalization for EA resource. No timeline for assignment. Update as of 12/2/2024: FUSUS Core NVR Initiative (ID 8729) is currently #134 out of 180 initiatives slated in L1 that would need to undergo Alignment & Rationalization for EA resource. No timeline for assignment. Update as of 12/9/2024: Financial analysis for LBC estimated to be completed this week. This project still requires EA for alignment & rationalization. R. Reetz is engaging EA group for options to adjust priority ranking for initiative. Update as of 3/18/2025: Platforms approval for SL2. Impact assessment provided to IO. LBC Submitted. Pending review for SL2. Update as of 3/28/2025: L2 submission sent back by finance to explore additional savings. Analysis expected to be complete by 3/31. Will resubmit at that time. Update as of 3/31/2025: Analysis received from finance. Updated LBC and Financials to reflect analysis. Resubmitted for L2 on 3/31. Update as of 4/09/2025: Flowing through SL2 Approvals Update as of 1/22/2026: Initiative remains in L2 pending PEL review from Platforms portfolio. D&T costs are being validated and finalized. Once validated will update project financials. Timeline on completion TBD as ownership of these costs and next steps are not clear from Platforms Portfolio. PPM #1840271 | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2025-05-01 | 2028-01-27
Business Only Initiative: EMR - FY26 USCAN Contract Guard Optimization |  | 87999 | Business Only Initiative | SGA - Security | SG&A | Christopher M. Winans, Quincy McGlown, Ryan Nelson, Hugh Hatley, Lori Parks | On Track | 1/5/26 - Per MH removed $15M from NRB 07/16/25 - Updated to reflect NRB of $15M ($+10M EMR) 07/02/25 - Updating to include EMR title and ESI tag. Working with TO finance to update FY26 value. 03/24/25 - Status quo 03/18/25 - Status quo 03/06/25 - Bid event launched in Coupa on 03/06/25. Suppliers will have until 03/11/25 to load the MNDA, PNL, and Supplier Information sheet in Coupa before accessing the bid sheet. Round 1 will close out on 04/04/25. 02/05/25 to YTD - Holding recurring weekly meetings with Intl. and North American groups. Finalizing RFP scope/baseline, business requirements, and setting up bid in Coupa 01/29/25 - Held Kick-off meeting with Security MDs and SRMs 01/14/25 - Routing proposal to Security VPs for approval by 01/17/25 with a target kick-off meeting within the week of 01/21/25 - 01/24/25 01/08/25 - RFP proposal and template have been created. Reviewing draft with leadership by 01/10/25 | I: L4 | Active | L4 | 2025-01-06 | 2026-12-23
Business Only Initiative: Dangerous Zip Codes Surcharge |  | 88695 | Business Only Initiative | SGA - Security | SG&A | Christopher M. Winans, Charissa McNatt, Quincy McGlown, Ryan Nelson | On Track | 11/14/25 - Rebaslined initative at the guidance of Finance, reducing savings 08/08/25 - Gathering money step evidence. Submitting to L4 on 08/15. 06/11/25 - No surcharge to be applied. Tracking actuals for armed services that have been eliminated YTD. 03/27/25 - Status quo. 03/24/25 - Status quo. 03/18/25 - Aligning with Finance on 03/25/25 to prep for L3 submission by the end of the month. Revenue team still reviewing package pickup data. 03/05/25 - Revenue team has identified that high risk package routes with armed guard escorts see an average profit loss of 37%. Teams are gathering package pickup data to understand the bigger picture and ultimately decide wheter a surcharge for armed guard services is feasible. Business team identifying high-value package routes and reviewing charges vs. costs | K: L5 | Active | TEMP L5 - Enter L5 | 2025-05-01 | 2025-10-23
Business Only Initiative: Integrator RFP Service Organizational Change |  | 90856 | Business Only Initiative | SGA - Security | SG&A | Marlon D. Jones, Chris Connors | On Track | On Track 01/17/25 Having discussiions with VP of finance on the FedEx Express calculated savings 01/24/25 02/04/25 Moved to L2. 02/14/25 No update 02/21/25 No update 02/28/25 meeting with finance on 02/28 to finalize finacial plan 03/07/25 financial plan finalized. Working on finalizing milestones and risks. 03/14/25 No update. SL3 date is TBD due to pending decision from executive leadership on Freight ServiceChannel strategy. 03/21/25 No Update 03/28/25 Updated FY28 Exit Rate 04/04/25 No update. SL3 date is TBD due to pending decision from executive leadership on Freight ServiceChannel strategy. 04/11/25 No update. 04/18/25 No update. 04/25/25 No update. Waiting on ServiceChannel (SC) contract execution timing. SC execution time will inform the savings start time for this initiative 05/02/25 No update 05/09/25 No update 05/16/25 No update 05/23/25 No update 05/30/25 No update 06/06/25 no update 06/13/25 no update 06/20/25 no update 06/27/25 ready to submit to L3, but I need the baseline value changed. I submitted a ticket to change the baseline value. 07/07/25 submitted to SL3 07/11/25 pushed back to L2. Reason: be more descriptive in the money step. I will submit a ticket to revise the money step description. 07/25/25 Submitted to SL3 07/31/25 no update 08/08/25 no update 08/28/25 no update 09/02/25 SL3 submission was not approved. I added more KPIs based on feedback. Resubmitted to SL3. 09/25/25 meeting with finance to discuss KPIs and financials. 10/03/25 No update 10/10/25 entered L3. Acutuals updated 11/07/25 Actuals updated 11/14/25 No update 12/02/25 Nov 2025 actuals added 12/12/25 No update 01/07/26 No update 01/16/26 No update 02/06/2026 No update 02/12/2026 actuals updated but only 20% of workorders have been invoiced so I do not have an accurate picture of the average cost of repairs (I don't know the cost of repairs for 80% of workorders). The triage benefit calucation is impacted by this. 02/20/26 no update 02/27/26 - submitted to L4 03/06/26 - no update 03.13.26 - no update 04.02.26 - updated actuals 04.17.26 no update | I: L4 | Active | L4 | 2025-02-18 | 2026-05-15
Business w/ Tech Initiative: 92350-ENT Badging and Physical Access Release 3.0 |  | 92350 | Business w/ Tech Initiative | SGA - Security | SG&A | William Lamar, Andy Beavers, Jay Boyles, Rodney Powell, Bill Stanek | On Track | 4/10/26 - in L2; No Change; Architectural solutioning and SIDA Capabilities and Requirements are being finalized; workshop for 3.0 for June has been approved and is being planned and scheduled. 3/12/26 - in L2; Architectural solutioning and SIDA Capabilities and Requirements are being finalized; workshop for 3.0 for June has been approved and will be scheduled in the coming weeks. 2/27/26 - in L2; Architectural solutioning and SIDA Capabilities and Requirements are being reviewed; will be scheduling a workshop for 3.0 in the June time frame, date to be determined. 2/11/26 - in L2; Architectural solutioning and reviewing SIDA Capabilities and Requirements; continue to coordinate with project Odyssey 2/2/26 - in L2; Architectural solutioning with impacted portfolios continues with SIDA requirements; continue to coordinate with project Odyssey 1/13/26 - in L2; Architectural solutioning with impacted portfolios continues with SIDA requirements; continue to coordinate with project Odyssey 12/31/25 - in L2; Architectural Solutioning continues progress working with impacted portfolios as we work through the SIDA requirements and capabilities; In coordination with Odyssey as it is a dependency for this release 12/5/25 - in L2; Architectural Solutioning continues progress working with impacted portfolios as we work through the SIDA requirements and capabilities; In coordination with Odyssey as it is a dependency for this release 11/11/2025 - in L2; Architectural Solutioning continues progress working with impacted portfolios as we work through the SIDA requirements and capabilities 10/31/25 - in L2; Architectural Solutioning continues progress working with impacted portfolios 10/22/25 - in L2; Architectural Solutioning in progress 10/10/25 - in L2; Epics and Capability statements have been completed; Workshop on Oct 7-9 was completed and conceptual solutioning has begun 10/3/25 - in L2; Epics and Capability statements have been completed; Workshop for Release 3.0 is being finalized. 9/26/25 - in L2; Epics and Capability Statements are being refined; Workshop for Release 3.0 has been scheduled for 10/7-9 (Hybrid meeting locations plannded at MEM (WTC 50) and PGH as well as virtual 9/11/25 - in L2; Epics and Capability Statements are being refined; Workshop for Release 3.0 has been scheduled for 10/7-9 (Hybrid meeting locations plannded at MEM (WTC 50) and PGH as well as virtual 8/15/25 -in L2 Subsequent Releases of 7641; Building architural solution documents and engaging with the impacted portfolios; Looking to submit to SL3 by 10/31/2025 7/21/25 - Subsequent Releases of 7641; Building architural solution documents and engaging with the impacted portfolios; Looking to submit to SL3 by 10/31/2025 7/8/25 - in L2; Subsequent Releases of 7641; Building architural solution documents and engaging with the impacted portfolios; Looking to submit to SL3 by 8/15/2025 6/18/25 - In L2; Subsequent Releases of 7641; Continue to build out the capabilities and engaging with the other impacted portfolios as well as functional areas; Looking to move to L3 by 8/15/2025 6/4/25 - In L2; Subsequent Releases of 7641; Continue to build out the capabilities and engaging with the other impacted portfolios as well as functional areas; Looking to move to L3 by 7/15/2025 5/29/25 - In L2; Subsequent Releases of 7641; Continue to build out the capabilities and engaging with the other impacted portfolios as well as functional areas; Looking to move to L3 by 7/15/2025 5/21/25 - In L2; Subsequent Release of 7641; Continue to build out the capabilities and engaging with the other impacted portfolios as well as functional areas; Looking to move to L3 by 7/15/2025 5/16/25 - In L2; Subsequent Releases of 7641; Remain on Track; Continue to build out the capabilities and engaging with the other impacted portfolios, and functional areas 5/9/25 - In L2; Subsequent Releases of 7641; Remain on Track; Continue to build out the capabilities and engaging with the | E: L2 | Active | L2 | 2026-09-01 | 2026-11-23
Business w/ Tech Initiative: 92356- ENT Badging and Physical Access Release 2.0 |  | 92356 | Business w/ Tech Initiative | SGA - Security | SG&A | William Lamar, Andy Beavers, Jay Boyles, Rodney Powell | Some Issues | 4/20/26 - in L3: IT needed to add a new service contract with RightCrowd to provide a needed Test Environment which is a Outside Service Contract paid annually at $57,280 for April and paid out in May. Was added into planview in order that finance could get it entered into Encore this did not exceed the allowable amount of the overall budget. 4/10/26 - in L3: Business and IT conducted a Capabilities review for refinement 4/8; Solutioning, development continues, and some integrations with CDAS has begun. The balance is being solutioned and will be scheduling a ARB review 3/12/26 - in L3; Solutioning, development continues, and some integrations with CDAS has begun. The balance is being solutioned and will be scheduling a ARB review. 2/27/26 - in L3; Solutioning and some development has begun 90% of the Capabilities have been approved in the ARB, the balance is being solutioned and will be scheduling a ARB review in the coming weeks. 2/11/26 - in L3; Solutioning and ARB was rescheduled for Feb. 13 2/2/26- in L3; Solutioning is wrapping up and preparing for ARB review scheduled for Feb. 6 1/13/26 - in L3; Solutioning continues to complete ARB reviews scheduled Jan 16; Project plans are continuing to be built out based on the solutions for Ship Broker 12/31/25 - in L3; Solutioning continues to complete ARB reviews scheduled in Jan; Project plans are being built out based on the solutions for Ship Broker 12/12/25 - in L3; Architecture for Shipmanager and CDAS are wrapping up, ARB held on 12/9 and approved for L2/L3 for 2.0; Impacted Portfolios are working to buildout their project tasks with the goal to finalize the overall project plan by Fri. 12/5/25 - in L3;Architecture for Shipmanager and CDAS are wrapping up, ARB scheduled for 12/9 for 2.0; Impacted Portfolios are working to buildout their project tasks with the goal to finalize the overall project plan by Fri. 12/12 11/11 - in L3; L3 Architecture for Shipmanager is underway; Impacted Portfolios met to review the CDAS and SNOW requirements for integrations this week. 10/31/25 - in L3; L3 Architecture for Shipmanager is underway; Impacted Portfolios are busy assigning teams and inputting allocations to Epics, once completed will push the Epics into L3 EPM Review/Approval 10/22/25 - In L3; Adjusted the budget to align with the L3 approval; L3 Architecture has been completed; Pushing the EPICS into L3 pending EPM Review/Approval 10/10/25 - In L3 as of 10/7/25; Budget pushed out 1 month; I tried to move the Solutioning to "In Progress" but the ESE was not available, so when I get back from Vacation I will start that task 10/7 - moved to L3; Workshop this week Oct. 7-9 that includes Solutioning for Ship Manager, pending is the estimate and schedule 10/3 - in SL3 Final Financial Review expected approval any day. Have notified the PEO and the Approver of the pending status. Also pending is the ShipManager solution, estimate and schedule. 9/25/25 - in SL3 Final Financial Review expected approval any day. Also pending is the ShipManager solution, estimate and schedule. 9/11/25 - in SL3, pending Financial Review; Also pending is the ShipManager estimate and schedule from our Vendor Partner; Completed the QA review with JJ Garcia; Worked with Commercial on the need to complete the initiative by end of March, 2026 due to other key initiatives that are dependencies. 8/27/25 - in L2, Completed the Commerical PEL review and awaiting a Greenlight decision from the committee; Once we receive the Greenlight will be submitting this intiative to SL3; Still pending is the costing of ShipManager which is in progress; This will most likely be received after the project is moved to L3 and will require us to put in a change request in to add the ShipManager costing and adjust the schedule based on when we recieve it and the expected completion dates 8/15/25 - in L2, Subsequent Release of 7641; 2.0 L2 Architectue just identified the need for ShipManager integrat | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-16 | 2026-10-30
Business Only Initiative: Mexico Initiative - Insourcing |  | 98338 | Business Only Initiative | SGA - Security | SG&A | Natasha Oliveira, Erin Owen | On Track |  | E: L2 | Active | L2 | 2026-04-30 | 2026-04-30
Business w/ Tech Initiative: Ent Sec Info Mgt Sys eSIMS Access to Customer EFS |  | 98567 | Business w/ Tech Initiative | SGA - Security | SG&A | Suzanne Moore | On Track | 1/16/2026 - suzanne moore/437423 - cancellation requested, plan to merge the work into our ongoing Planview initiative for EIW retirement, since this work is related to those changes. This approach will help streamline efforts and avoid duplication. 12/12/2025 - suzanne moore/437423 - no update. 10/10/2025 - suzanne moore/437423 - costing document completed, L2 architecture documents in progress. 9/11/2025 - suzanne moore/437423 - sl2 finance domain lead approved. Pending SL2 Domain Lead Approval. 8/19/2025 - suzanne moore/437423 - changed back to original request type of Efficiency instead of enabler, since we have a different planview specifically created as an enabler for EIW to access customer data in EIW for batch processing needs. 7/31/2025 - suzanne moore/437423 - changed request type to enabler as this is required to support the EIW retirement initiative. will add the planview dependency once EIW retirement parent is in L2. 7/25/2025 - suzanne moore/437423 - architectural assessment completed, submitted to L2, feedback request for finance info in progress. 6/20/2025 - suzanne moore/437423 - architect assigned, architectural assessment in progress. 6/1/2025 - suzanne moore/437423 - pending enterprise architecture priorization. 5/16/2025 - suzanne moore/437423 - architecture in progress 4/26/2025 - suzanne moore/437423 - working on architecture review. 4/18/2025 - suzanne moore/437423 - L1 business case in progress. 4/11/2025 - suzanne moore/437423 - L1 LBC in progress. 4/4/2025 - suzanne moore/437423 - no status updates. 3/24/2025 - suzanne moore/437423 - no re-baseline needed since financials not yet updated. 3/21/2025 - suzanne moore/437423 - no updates for this week. Added new IO | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: Security Requested Intercept |  | 98572 | Business w/ Tech Initiative | SGA - Security | SG&A | Virginia S. Geater, Suzanne Moore | On Track | 3/11/2026 - suzanne moore/437423 - still pending enterprise architecture engagement. however, connors to help us with escalation. 12/12/2025 - suzanne moore/437423 - no update. 11/4/2025 - suzanne moore/437423 - pending enterprise architecture engagement 10/10/2025 - suzanne moore/437423 - pending enterprise architecture engagement 9/11/2025 - suzanne moore/437423 - pending enterprise architecture engagement 9/3/2025 - suzanne moore/437423 - pending enterprise architecture engagement 8/19/2025 - suzanne moore/437423 - pending architecture prioritization 7/31/2025 - suzanne moore/437423 - pending architecture prioritization 7/25/2025 - suzanne moore/437423 - business case in progress. 6/20/2025 - suzanne moore/437423 - business case in progress. 6/1/2025 - suzanne moore/437423 - business case in progress. 5/16/2025 - suzanne moore/437423 - business case in progress. 4/26/2025 - suzanne moore/437423 - continued work on l1 business case and financials 4/18/2025 - suzanne moore/437423 - L1 business case in progress. 4/11/2025 - suzanne moore/437423 - no status updates. 4/4/2025 - suzanne moore/437423 - no status updates. 3/24/2025 - suzanne moore/437423 - no re-baseline needed since financials not yet updated. 3/21/2025 - suzanne moore/437423 - no updates for this week. Added new IO | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC: CCA-US Initiative - Insourcing |  | 106591 | Business Only Initiative | SGA - Security | SG&A | Natasha Oliveira | On Track | 4/02/25 - No change. | E: L2 | Active | L2 Feedback Requested | 2026-06-30 | 2026-06-30
Business w/ Tech Initiative: Rapiscan - Bi-Directional X-Ray Screening |  | 106693 | Business w/ Tech Initiative | SGA - Security | SG&A | Christopher M. Winans, Hugh Hatley | On Track | 05/08/25 - Currently negotiating an MSA with Rapiscan to purchase their equipment / move the ScanOS AI technology out of the Pilot stage. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR CFT - Security Increase SUM |  | 126681 | Business Only Initiative | SGA - Security | SG&A | Hugh Hatley | On Track | This initiative was created in support of Enterprise Margin Recovery and was considered a placeholder. | C: L1 | Cancelled | L1
Business Only Initiative: Brazil Insourcing |  | 141796 | Business Only Initiative | SGA - Security | SG&A | Natasha Oliveira | On Track | The project will no longer take place in Brazil due to a decision by the Offices. | C: L1 | Cancelled | L1
Business Only Initiative: Securitime - Contract Security Guard Management |  | 141809 | Business Only Initiative | SGA - Security | SG&A | Christopher M. Winans, Hugh Hatley, Lori Parks | On Track | 09/30/25 - Updating to a expense only initiative per the guidance of TO Finance; savings to be captured under #87999. Please do not reference L1 NRB and corresponding notes due to this new guidance. 07/16/25 - Preparing a negotiation strategy / completing FIRST and tech eval for TSM approval | I: L4 | Active | L4 | 2026-03-27 | 2026-06-01
Business Only Initiative: OT Cost Offset by Increasing Uniformed FTEs |  | 165863 | Business Only Initiative | SGA - Security | SG&A | Jorian Williams | On Track | 12/2025 Awaiting approval from Senior Executive Leadership to hire requisite FTEs that will enable realization of projected cost savings. Pursuant to approval there will be a short recruitment window 1-1.5 months and 1 additional month for training before savings will be realized. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: EMR-Reduce GST Expenses for RAD |  | 165866 | Business Only Initiative | SGA - Security | SG&A | Marlon D. Jones, Jason Campbell, Maurice Morgan | On Track | 12.05.25 On track 03.06.26 actuals updated 03.13.26 no update 04.02.26 no update 04.17.26 no update | I: L4 | Active | L4 | 2026-01-15 | 2026-04-30
Business Only Initiative: EMR-Re-evaluating gate agents at QARH |  | 165873 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne | On Track | 07.01.2026: After further review this initiative has been idenitifed as a shift of costs rather than company wide savings and advise provided to cancel. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: EMR-Contract Guard Reduction in APAC |  | 165879 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne, Colin Troughton | On Track | Dec 12, 2025: Initiative in progress | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: EMR-Capital spend on security equipment proj. APAC |  | 165884 | Business Only Initiative | SGA - Security | SG&A | Kelly Aherne | On Track | Dec 17, 2025: Initiative on track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Canada EDDHT Dual Role RFP |  | 188135 | Business Only Initiative | SGA - Security | SG&A | Christopher M. Winans | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: 7641- ENT Badging and Physical Access Security 1.0 | 78735 | 7641 | Business w/ Tech Initiative | SGA - Security | SG&A | William Lamar, Andy Beavers, Jay Boyles, Rodney Powell | Some Issues | 4/23/26 - In L3; Pleased to announce the decision to fully expand from soft launch ePIAM Release 1.0 on Tuesday, April 28, 2026. We are expanding the solution with four identified defects. Stakeholders met on each of the defects and have agreed on their severity and mitigation. 4/10/26 - in L3: Team has moved to Production with a Soft Launch on 3/24 (Masked to the Users until defects are resolved). Team continues to work through defects and projects to Go Live ~4/17 3/12/26 - in L3; Team has moved from Pre-Production UAT testing and moving to Production with on 3/14 with a Soft Launch on 3/24 2/27/26 - in L3; Team has moved from IT Shake out to Pre-Production UAT testing and is actively testing and working to resolve the issues found . 2/11/26 - in L3; Team is working to resolve three issues found during IT Shakeout once completed will reinitiate UAT for pre-production 2/2/26 - in L3: Moved to staging environment and IT is conducting their shake out testing and expected to be release to begin UAT 2/3/2026 1/13/26 - in L3; UAT is underway and as issues are identified are being resolved 12/31/25 - in L3; Vendors are finalizing the implementation and preparing for UAT 12/12/25 - in L3; Vendors continue work to move the environment to staging; printer coupler issues resolved; UAT has been delayed until these have been resolved; day by day update 12/5/2025 - in L3; Vendors are working to move the environment to staging and working through printer coupler issues; adjust badge templates; UAT has been delayed until these have been resolved; day by day update 11/11/2025 - In L3; Vendors API Integrations are being tested and will continue until ready for UAT mid - late November; Go/No-Go Decision Target remains 12/12/25 10/31/25 - In L3; Vendors continue to test the API Integrations; Demo's have begun and will continue until ready for UAT mid - late November; Go/No-Go Decision Target remains 12/12/25 10/22/25 - in L3; Vendors continue to test the API Integrations; Go/No-Go Decision Target remains 12/12/25 10/10/25 - in L3; Actuals loaded; Continue to work with the vendors on two way communication with the API integrations; Vendors testing internally and once APIs are completed will begin full testing; Go/No-Go Decision 12/12/25 10/3/25 - - in L3; APIs are nearing completion; Integrations are nearing completion; Communication, Testing, Training and Deployment Strategy is being prepared; Vendors are in the process of integration development and working toward a Go/No-Go Decision of 12/12/25 9/26/25 - in L3; APIs are being build; Integrations are being established; Communication, Testing, Training and Deployment Strategy is being prepared; Vendors are in the process of integration development and working toward a Go/No-Go Decision of 12/12/25 9/11/25 - in L3; Completed PI4 Planning; Loaded actuals; Communication, Testing, Training and Deployment Strategy is being prepared; Vendors are in the process of integration development and working toward a Go/No-Go Decision of 12/12/25 8/27/25 - In L3; Preparing for PI4 Planning; Communication, Testing, Training and Deployment Strategy is being prepared; Vendors are in the process of integration development and working toward a Go/No-Go Decision of 12/12/25 8/13/25 - in L3; Completed PI4 Planning; Loaded actuals; Communication, Testing, Training and Deployment Strategy is being prepared; Vendors are in the process of integration development and working toward a Go/No-Go Decision of 12/12/25 8/5/25 - In L3; Preparing for PI4 Planning; Communication, Testing, Training and Deployment Strategy is being prepared; Vendors are in the process of integration development and working toward a Go/No-Go Decision of 12/12/25 7/30/25 - in L3; Timeline based on Vendor completion of Functional Requirements Review and project plan rationalization. Go Live Decision set for 12/12/25 7/21/25 - in L3; Adjusting timeline based on Vendor completion of Functional Requirements Review | G: L3 | Active | TEMP L3 - Enter L3 | 2024-09-03 | 2026-08-13
Business w/ Tech Initiative: New Invoice & Payment Fees (US & CA) |  | 114432 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Trinidad M. Soldano, Devvrat Kumar, Angie Houston, Jill Dunagan | On Track | **Weekly accomplishments - 4/23/2026** 3/16 - Addition of Canada to the Paper Invoice Fee scope 3/23 - Received additional feedback from Finance Domain Lead 3/24 - Incorporate the feedback received and reviewed readniess for resubmission with Financial Analyst (Christopher Bouzaher) 3/25 - Submitted for Finance Domain Lead review 4/2 - No updates - awaiting for Finance Domain Lead approval 4/9 - The project Target Load Date has been updated to TBD due to portfolio prioritization and capacity constraints. 4/16 - Final review meeting with Finance Domain Lead scheduled for 4/23 - Met with Finance Domain Lead and agreed to provide additional details on benefits reduction. | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2026-04-29 | 2027-02-26
Business Only Initiative: Zuora Collections Process for FedEx Surround |  | 114436 | Business Only Initiative | SGA - Ship to Collect | SG&A | Andrew Pellegrino | On Track | 4/23/2026 - Putting on-hold to keep from triggering reports. 6/17/2025 - Provided the requested feedback for the L1 business Case. 6/3/2025 - FedEx Surround (Montioring and Intervition) Products are currently availble for US, Hong Kong, and Singapore customers. | E: L2 | On Hold | L2 Feedback Requested
Business w/ Tech Initiative: EMR OTC - Paper Invoicing Fee EU, CA, and LAC |  | 126301 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Adela Nazarova, Angie Houston | On Track | 0/16/2026: EU region cannot participate in this initiative due to other critical projects. The removal was approved by Mike Callender. That region represented over 98% of the benefit. LAC benefit is less than $5k per year, but that region has a dependency on the LDP that is slowing the project down. Therefore, the scope of this initiative is being reduced to just the Canada region. As a result, the total benefit will go from $7.66M down to just $0.14M. Since Canada is going to utilize the US solution, it has been decided to move the Canada piece to Planview 114432. This Initiative is being cancelled. 12/18/2025: The initiative is still in the “L2 - Initiative Assessment & Decomposition Phase” a.The L2 work has not been completed by the Portfolio Operations Demand team. b.This initiative is still in the “Backlog” status. 11/10/2025: QA Team (Beth Hedger and Sara Proctor) reviewed all L2 updates and recommended promoting this initiative to Next Step). 10/16/2025: Shifted Cost Estimate Start Quarter from Q1 2026 to Q3 2026 to align with Milestones map. Change has been approved by Jaeyoon Lee <jaeyoon.lee@fedex.com> 8/8/2025: Per Jerome Miller, presenting Baseline and Target Values in terms of Count of Paper Invoices. 8/6/2025: Incorporated feedback from Jerome Miller in Finance. Also, adjusted down the volume of paper invoices in the EU based on the clarification from that region. 7/30/2025: This initiative has been reviewed and approved for submission by the QA team. 07/15/2025: It has been determined that AMEA region does not have paper invoices. And there is a separate Planview request for the US region. Hence, this request is limited to EU, CA, and LAC. | E: L2 | Cancelled | L2 Feedback Requested | 2025-09-16 | 2026-06-30
Business w/ Tech Initiative: EMR OTC - EU SR&A: Improving Billing Accuracy |  | 126684 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Matteo Fiorini | On Track | Initiative is replaced by JP - JP - Invoice Accuracy / Strategy Sequence ID 113351 | C: L1 | Cancelled | L1
Business w/ Tech Initiative: EMR OTC - Global Late Fee Phase I Regional Pilot |  | 130972 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Helena D. Oliveira, Mario Souffrain | On Track | 01/15/2026 - Commerical PRT backlog ranking for init changed to 14, still awaiting commercial feedback from PRT review to move forward. 01/07/2026 - No change to init priortization on Commercial PRT backlog list. Init project team is waiting on key information from PRT review to move forward. 12/03/2025 - Init moved up to 17 in Commercial PRT backlog list, project team reviewing other pre requisites and actioning dependencies. 11/11/2025 - Init moved down to 18 in Commercial PRT backlog list, created shell of milestone plan, KPI and financials tab 10/30/2025 - Init added to Commercial PRT backlog list with 11 ranking for commercial assessment on 10/22/2025, no change in status. PPM created by IO PPM Project number - 1829754. 10/16/2025 - Init to be reviewed in upcoming CPEL meeting on 10/22/2025. PPM to be created by Revenue Principal (Courtney Gonzalez) for Biz w/tech initiatives, follow up done. 10/09/2025 - CCH Greenlight received, L2LBC review and verbal signoff received from Planview and EBS Finance (George Oswald, Brian Keeney & Joseph Nowell) 10/06/2025 - Commercial L2 Triage meeting scheduled for 10/06/2025 and CCH domain review and approval planned for 10/10/2025 09/29/2025 - Preliminary review call conducted with Karen McConnico CCH PMO to discuss draft CCH questions tab, Brief demand description and CCH next steps. 09/18/2025 - Pushed to L2, sent initiative summary to Jerome 09/16/2025 - Initiative supporting architecture documentation link has been updated and Biz w/ Tech Additional Info has been filled based on documentation Finalizing L1 cost calculations for Finance review 09/04/2025 Consolidated LBC details have been updated in the L1 step 08/27/25 New direction has been received from leadership that the previously separate Initiatives to introduce late fees to Mexico, Puerto Rico, Canada, UK, and China be consolidated into a single Initiative. This Initiative (Strategy ID: 130972) was chosen as the Initiative to consolidate into. As such, the Initiative Name and Brief Demand description have been updated to reflect the consolidated scope of the Initiative. Consolidation of LBCs is also underway. 08/11/25 as directed by Mike Callendar and Leslie Benners, the initiative will focus specifically on Mexico. Title and demand description were updated and possible later expansion to the region will be addressed separately. | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: EMR OTC- Expand Late Fees from NA to Canada region |  | 130977 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Joseph Puthukkeril | On Track | Update 09/25: - 09/02/25 **New direction has been received from leadership** that the previously separate Initiatives to introduce late fees to Mexico, Puerto Rico, Canada, UK, and China be **consolidated into a single Initiative**. This Initiative will be consolidated into Strategy ID: 130972. As such, this **initiative is being placed on hold** until further notice. A consolidated LBC is being worked on. Update 08/25: - Email sent to Jerome Miller on 19 Aug - Initiative submitted to L2 on 19 Aug - QA review completed by Amanda Vela on 11 Aug - Biz w/ Tech Additional Info fields have been updated based on L1 Architecture alignment document on 07 Aug - L1 architecture alignment step has been completed on 05 Aug Update 07/25: - LBC details entered based on preliminary assumptions and estimations. - L1 related supports attached in planview - Canada Late fees is goverened by Criminal interest rate, Late fees calculation is based on our limited expertise. **Expertise in calculating APR/EAR is required for Late Fee % assessment to ensure compliance with criminal interest rate** | D: SL2 | On Hold | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: EMR OTC – Expand Late Fees from NA to China |  | 141849 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Kee-Siang Tan, Graham Lowe | On Track | 11-Aug-25 – as directed by Mike Callendar and Leslie Benners, the initiative will focus only on China. Title and demand description were updated to reflect the change and possible later expansion to the region will be addressed separately. 26-Aug-25 – leadership has determined that the global late fees Initiatives should be consolidated and continue under one Initiative. Going forward, the Initiatives will be consolidated under Strategy Sequence ID: 130972. Setting this Initiative to On Hold for the time being. Once path forward has fully stabilized, this Initiative will either be cancelled or brought back to active status | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: EMR OTC- Expand Late Fees from NA to UK |  | 141855 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Graham Lowe | On Track | 26-Aug-25 – leadership has determined that the global late fees Initiatives should be consolidated and continue under one Initiative. Going forward, the Initiatives will be consolidated under Strategy Sequence ID: 130972. Setting this Initiative to On Hold for the time being. Once path forward has fully stabilized, this Initiative will either be cancelled or brought back to active status. 08/08/25 – as directed by Mike Callendar and Leslie Benners, the initiative will focus specifically on the UK. Title and demand description were updated and possible later expansion to the region will be addressed separately. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: D&S Contract Reduction | 78787 | 6737 | Business Only Initiative | SGA - Ship to Collect | SG&A | Carlos Lopez, Eddie Utset, Kurt Kedroe | Some Issues | * saving is delay due to money step pending to get. It is missing to hire the new 3rd party collection agency in order to reduce the number of accounts that the BPO is handling (this is needed to realize savings). SEP24 *MAR3/2025 Pospone 1 month the money step action considering that the portafolio is not reducing. we will need to have an internal strategy to verify deeply. We already have part of the savings but its pending another portion, ALl steps are completed but we are not showing the decrease of the portafolio. Plan is to verify the information to confirm if there is something pending to purge or send to the 3rd party vendor. MAR14/25. In the next 30 days we will work in a process to reduce the number of accounts that the BPO works in order to get the savings. MAR26/25 Initiative is now baselined to FY25 APR16/25. pending to implement the oracle strategies process for less than 5K. money step were pospone to MAY30. MAY12.2025. pending to implement the oracle strategies process for less than 5K. money step were pospone to JUL15. AUG13/25. Money step is schedule for SEP15. Delay due to Oracle strategy project SEP18/25. Iniciative will be submit for L4 in OCT5. OCT7. All activities were done. SEP invoice refelect the savings. Good to move to L4 NOV6. Include new money step doucmnetation in order to resubmit to L4. | K: L5 | Active | L5 | 2024-04-01 | 2025-09-15
Business Only Initiative: Duty and Tax Error Correction Releasing EBS Americ | 78785 | 6734 | Business Only Initiative | SGA - Ship to Collect | SG&A | Eddie Utset, Carlos Lopez, Kurt Kedroe | Attention Needed | call schedule for the next week focus on determine final amounts. * update the transaction VOL date from SEP to OCT due to CIDV project that impact the initial schedule. * update the Automation structure plan from SEP to OCT due to CIDV project that impact the initial schedule. * Update the work automation milestone considering that the automation plan is taking more time considering thta we need an additional information from MEM. * * Update the work automation and vol milestone considering that the automation plan is taking more time considering thta we need an additional information from MEM . * 8jan25. date were reeschedule due to dificulties for onbatining the raw data. * MAR3/2025 Estructure the automation plan is taking more time due to aligment with DMI (MX and India) * MAR14/25. During our initial verification, it was determined that AI technology needs to be implemented in order to achieve the estimated savings. We are currently in contact with the team at MEM to gain access to the platform that enables AI developments. This access is required to confirm the development timelines. * MAR26/25 Initiative is now baselined to FY25 * MAR31/25. Update the structura automation plan finish date considering that we need to include in the plan the IA technology. * APR22/25. Pending to confirm with GENAI if we can use IA technology. * JUL1/25. Automation plan complete. Begin the automation development * OCT7. Automation is having some issues and we extend the target date to DEC25. * MAR26. after additional verifications we are adjusting the scope of the project and the financial impact. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2026-07-31
Business Only Initiative: Finance - Reduce Fees Paid to US Bank | 1038 | 8804 | Business Only Initiative | SGA - Ship to Collect | SG&A | Kathryn Quigley, Angie Houston | On Track | 03.12.2026 - moving Money Step date out to reflect contract completion date of 5/29/2026. Money step is tied to the signing of FXF Contract with US Bank; however, all savings for this initiative have been realized and intiative was at full run rate prior to FY25. 01.22.2026 - Per legal, we 'very close' on completion of FEC contract with US Bank which will be mirrored to create separate MSA/SOW for FXF Separation. Moving date out another 30 days to allow for contract completion. 11.25.2025 - Contacted contract work owner and confirmed completion ETA of 12/31/2025. Updated money step completion date to 1/9/2026. Money step is tied to contract execution. Though the initiative has not reached L4, it has achieved full run rate due to US Bank proactively reducing fees prior to contract completion. 08.13.2025 - Due to announcement of FXF Separation, the US Bank contract will move forward to include FEC and Custom Critical. A separate contract will be submitted for FXF. The process for this separate contract can be started prior to the June 2026 separation date using the same teamplate as the FEC contract. If completed, it can then transition over the new FXF Entity in June 2026. Work with legal continues on the FEC/Custom Critical contract. Initiative can be moved into L4 once the contract is finalized. 07.18.2025 - June 2025 Actuals Entered. Contract negotiations continue. 06.11.2025 - May 2025 Actuals Entered. No update on contract status at this time. 05.22.2025 - May 2025 - We are still waiting for legal to finalize the contract with US Bank - we are close to reaching an agreement on the final wording and anticipate completion within 90 days. The fees were actually reduced to the new rate in Sept 2023, so we are already seeing savings, but did not feel that it was appropriate to move into L4 without the final contract signed. 05.13.2025 - April 2025 Actuals entered. Contract completion pending on legal. 04.07.2025 - March 2025 Actuals entered. Continuing to wait for legal on contract completion. 3.21.2025 - Confirmed rebaseline to FY25. 3.7.2025 - Initiative remains on track; however, legal has now advised that in light of the FXF Separation announcement, we should not proceed with efforts to gain approval on a consolidated contract, but should instead move forward with separate invoices for Parcel vs. Freight. Angie Houston and team continue to work with legal to get this accomplished. Money step pushed out another 4 months to allow for contract completion with FedEx Legal and US Bank. We started seeing benefits from this project in Sept 2023 as US Bank started reducing rates for FXF disputes. We have not marked money step complete (though achieving benefits) - as overall contract has been consolidated for the one FedEx move. Prior we had multiple US bank contracts. Angie/Herb are working with Legal to finalize the consolidated one new contract. Once that is complete, project can complete to L5 (contract nearly complete). | G: L3 | Active | TEMP L3 - Enter L3 | 2022-11-01 | 2026-05-29
Business Only Initiative: Freight Surcharge Extraction | 4746 | 8276 | Business Only Initiative | SGA - Ship to Collect | SG&A | Kevin Johnson | On Track | 9/12/25: moved to L5. Updated financials through FY28 based on future forecast of $860k per month. 4/22/25: met with planview finance team and determined the actual impact needed to be changed to -92,613. Further evaluating FY25 baseline and proper entries for FY26 forecast.. 3/31/25: rebaselining. Seting remaining FY25 mnths to -125,000 and FY26-FY28 to -175,000 monthly. 3/12/25: Shipping volumes continue to remain down. Additionally, keying accuracy has improved since November resulting in less OCR captures added as corrections. OCR accuracy is being reviewed to request development improvements. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-28 | 2024-10-31
Business w/ Tech Initiative: Implement ability to send EFT Payments for Refunds |  | 92143 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Jill Dunagan, Angie Houston | On Track | 4/16/26 - updated money step date to 1/15/27 to align with New Paper Invoice & Payment Fees #114432 money step and due to init is backlogged waiting on D&T sizing. money step is subject to change based on D&T architecture and timelines. moved up to #3 in PRT backlog. 4/3/26 update: Booster reviewed for # 92143 / Implement ability to send EFT Payments for Refunds in the SG&A Domain •Approved to be boosted to account for the $27M enabled benefits. •Priority will update this morning on the dashboard. •PDSM ticket for ESI tag submitted; the ESI is now showing in Planview for both initiatives. •Emilee James’ team (@Michael Sibley) to check with the impacted portfolios to see the feasibility of resourcing based on new priority and provide an update 3/30/26 - submitted PDSM ticket to change to Primary Type of Value Customer Experience - Problem Resolution Primary Type of Value Impact High 3/26/26 - emails exchanged this week regarding changing ESI to Customer Experiece (2nd attempt, original occurred in 8/25) and request for a boost in PRT 3/16/26 - updated 'external spend category' to change from 'Ops Supplies & Print' to 'Professional Fees' based on request to do so from Beth Hedger via Procurement leadership email on 3/6 3/5/26 - no addtional updates since 3/2/26 3/2/26 - moving down consistently on all ranking lists, including PRT backlog. VPs Andrew Hosea and Aashish Gahlaut have connected and discussed this project falling behind even as the enabled project moves forward due to PRT backlog priority declining. On 2/27, MD Chris Gibney stated "Based on their priorities and current roadmap, neither is expected to have work started on them for about 12 months. Invoice and Payment Fees was targeting TY26, and current there are no resources available to get it done before CY27. I will reach out to CPEL to boost EFT Refunds so they can both be worked together in CY27" 2/12/26 - no change 2/5/26 - no change 1/29/26 - no changes. still waiting for priorty. might need to submit a ticket to have 'feedback requested' removed/reset as it seems stuck there and i'm not sure of the impact this is having. linked project we are an enabler for has NOT moved into L3 yet, as previously reported. 1/15/26 - no changes. still waiting for priorty. linked project we are an enabler for has moved to L3 1/2/26 - no changes. still waiting for priority 12/16/25 - no changes; still waiting to be prioritized. linked project is still in L2 but was scheduled for CPEL meeting this week.awaiting their ranking. 10/24/25 - New Paper Invoice & Payment Fees owner confirmed this project's NRB has been included in their NRB. I removed NRB from this project and marked this project as an Enabler. 10/21/25 - adding Angie Houston as secondary IO so that she can add this project's NRB to her project and I can mark this project as an enabler to her project 10/16/25 - directors approved on 10/8 to make this project an enabler for New Paper Invoice & Payment Fees - Planview #114432. two teams working together on next steps to move NRB into other project and then remove from this project and to mark this project as enabler once that is complete. 9/11/25 - in PRT backlong; 23 in commercial backlog; 147 in Enterprise backlog 8/25/25 - currently 19 on commercial portfolio backlog. communicating with Customer Experience ESI team about changing ESI in planview. 7/29/25 - met with Finance contacts about adding soft benefits and were not able to quantify any additional benefits. 5/23/25-financial forecasting data, KPIs, and milestones entered. Awaiting IT owner approval on related PPM and next steps when called up from PRT backlog 5/7/25 - attended CPEL meeting 5/5/25 -in L2. Meeting scheduled with finance to get guidance on entering finance and KPI numbers. CPEL meeting scheduled for 5/7/25 4/14/25 - attended L2 Commercial Triage Mtg - determined project needed to go to PRT; currently in PRT backlog 3/6/25-uploaded summary slides for architecture review. David Walker moved proj | E: L2 | Active | L2 Feedback Requested | 2025-05-07 | 2027-01-14
Business w/ Tech Initiative: Implement CAN FBO EFT (Electronic Fund Transfer) a | 89646 | 7715 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Nick Stuart, Aaron Cichocki | On Track | 11/19/24 -- entering lean buisness case working towards L2 10/8/25 -- Cancelling due to amount of time since intial project was conceived | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: International Airway Bill Data Extraction | 4747 | 8047 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Eric Duncan, Terry Becton | On Track | Genesis data entry contract was ended on March 15 with Atos/Syntel. Milestone 16516 is complete. The milestone dates are pushed back due to delays in the delivery of the IT solution. Hogher bisnuess value items are being complete ahead of the effort. it should alos the be noted the volume that drove the business benefit has dropped significantly. March 18, 2025, the remaining work for this initiative will be canceled. The development efforts have been continuously postponed due to higher priority work for the core development team. Additionally, this effort was targeting volume processed via the Genesis data entry application. Genesis volume has dropped significantly in the time since the origin initiative was created. The ongoing drop in Genesis volume reduces the ultimate benefits of the request. April 2, 2025, Fy25 rebaselining completed. Closed money step milestone. Obtaining applicable evidence and submit to L4 once uploaded. Inserted placehold link for architectural document. Initiative is legacy from WAVE and IT work was commpleted prior to migration to Planview. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-01-11 | 2025-06-27
Business Only Initiative: LTL Invoicing Accuracy & Customer Experience Proce | 85831 | 9191 | Business Only Initiative | SGA - Ship to Collect | SG&A | Clark Collins, Eric Boyle | On Track | 9/23/2025: Domain lead request that this initiative be canceled due to the FXF transition. Aligned with FXF leadership to confirm that 9191 should be canceled. NOTE: This initiative is a $0 iniitative to revenue/cost. Benefit is measured via KPI related to Customer Experience. KPI measures reduction of invoice adjustments due to inaccurate invoicing. Work completed in FY24. Initiative entered retroactive upon request from leadership. 3/6/25: $40M incremental SR&A reduction goal met 2 months ahead of schedule due to increase invoice accuracy success. 12/30: $42Mil incremental SR&A reduction YTD vs. FY24 through Nov FY24. L4 approved. Manual improvements achieved $40Mil Feb 2025 goal in Dec 2024. 12/16: $42Mil incremental SR&A reduction YTD vs. FY24. L3 approved. Manual improvements achieved $40Mil Feb 2025 goal in Dec 2024. 12/9: $42Mil incremental SR&A reduction YTD vs. FY24. L3 approved. Manual improvements achieved $40Mil Feb 2025 goal in Dec 2024. 12/2: $33Mil incremental SR&A reduction YTD vs. FY24. L3 approved. Manual improvements on track to hit $40Mil goal by Feb 2025. 11/18: $33Mil incremental SR&A reduction YTD vs. FY24 through October. L2 approved. Submitted to L3. Manual Improvements on track to hit $40Mil goal by Feb 2025. 11/11: $33Mil incremental SR&A reduction YTD vs. FY24 through October. L2 approved. L3 by Nov 7th. Manual Improvements on track to hit $40Mil goal by Feb 2025. 11/5: $25Mil incremental SR&A reduction YTD vs. FY24. L2 approved. L3 by Nov 7th. Manual Improvements on track to hit $40Mil goal by Feb 2025. | I: L4 | Cancelled | L4 | 2023-06-01 | 2024-05-31
Business w/ Tech Initiative: New 1st Party Fraud CAS17 Reason Code |  | 87207 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Andrew Pellegrino | On Track | 10/08/2025 - Putting this int on-hold until further notice. Low priority relative to competing intiatives. 02/21/2025 - Resubmitting for L2 approval. Enterprise Architect, David Walker, reviewed for the Fraud Cash Code initiative and provided the CPEL slide review (attached). The Enterprise Excellence domain system's recommended ranking for this initiative is currently 252. 02/14/2025 - Despite strong support from both the VP and SVP levels, the initiative has been pending for an extended period (approximately 3.5 years). This initiative is crucial for protecting FedEx from fraud. We kindly request your guidance on the specific actions or support required from executive leadership to expedite the prioritization and implementation of this critical initiative. Current system recommended ranking in L1 is 266. 11/21/2024 - US Collections has been waiting on this request since 2022. Right now, the Collections team uses a “work around” process until CAS17 is fully functional and creates the true control we need in this area. | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: Servientrega Contract services in Costa Rica Elimi | 81195 | 6738 | Business Only Initiative | SGA - Ship to Collect | SG&A | Carlos Lopez, Eddie Utset | On Track | Status 11nov24. Contract already finish since 15OCT2024. money step is complete and attempting move to L4. MAR14/25. Contract already stop since OCT2024. just waiting for L5 mar28/25rebaseline to fY25 has been completed. | K: L5 | Completed | L5 | 2025-10-15 | 2025-10-15
Business Only Initiative: Strengthen Total Cost of Payment Acceptance (TCPA) | 2681 | 8775 | Business Only Initiative | SGA - Ship to Collect | SG&A | Angie Houston, Christian Lemon | On Track | 9/4/2025 - Submitting to L5. Initiative reached full run-rate, prior to FY25 Re-Baselining. Exceeded benefits forecast. Process doesn't require benefits entry in FY26 following initiave reaching full run-rate. 4/21/2025 - Benefits are coming in higher than originally estimated, customer compliance with TCPA is doing very well and coming in above original forecast, expecting to come in around $10.3M for FY25. We took a conservative approach with the original estimate as these benefits are based on customers' choice of payment method, which we never try to influence, and customer revenue will fluctuate. 3/31/2025 - Re-Baseline for FY25 has been completed. 3/10/2025 - Benefits are coming in higher than originally estimated, customer compliance with TCPA is doing very well and coming in above original forecast, expecting to come in around $10M for FY25. We took a conservative approach with the original estimate as these benefits are based on customers' choice of payment method, which we never try to influence. 2/14/2025 - Benefit actuals entered for Jan 2025. Actuals had been fluctuating and have now stabilized following resolution of unknown data capture issues. Monthly actuals are decreasing, coming in under the previous forecast. Research is showing that this is due to lower customer revenue related to customers who have become compliant. Update 6/12/2024. Results following the stabilization period of FY23 H1 + December (due to Peak) have produced more favorable results than forecasted: Jan $0.624M, Feb $0.546M, Mar $0.751M and May $0.69M. Monthly performance will vary based on actual revenue for related customers, therefore, a decline or increase vs. the $0.6M monthly goal at full implementation will be experienced, such as January (Peak impact,), Also, benefits can be exceed goal when revenue is greater than FY22 revenue which used to calculate the baseline. Benefits are ahead of the delivery schedule expected to ramp up over a 12 month period. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-01 | 2023-12-29
Business w/ Tech Initiative: LAC BR BridgeOps - EBS/TMS Transition Program |  | 153785 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Tarcio Cora, Carlos Lopez, EVELLYN OLIVEIRA | On Track | 2026.01.13 – Conceptual architecture has been completed and Planview milestones have been updated (Money Step and Technology/System milestone). Risk has been captured in Planview. Resubmitting to PEO for SCO portfolio greenlight review. 10/10/2025 - Scope updated to include data migration and retention requirements as part of the EBS/TMS decommissioning program. BridgeOps now covers both process and data continuity, ensuring migration of historical and operational datasets to IBIS (reporting layer) and Serlefin (Bridge) (operational layer). This update aligns the project with legal, fiscal, and audit compliance standards required for system retirement. 09/30/2025 - Status Rationale – Initiative Name (BridgeOps / EBS/TMS Transition Program, Seq. ID: 153785) Current Status: Most L2 activities have been completed successfully: All required Planview L2 activities Lean Business Case finalized Technology milestones updated with timelines and risks At least one Epic with start/end dates Approved PPM number included Level of effort for impacted ARTs selected Pending Items: SCO cost/impact information: fiscal semester dates, TPIs/team composition, non-ART IT spend, impacted Solution Trains and ARTs Submission of D&T Finance Costing Request form and addition of resulting values to the Planview Financials tab Next Steps / Support Needed: Awaiting guidance from SCO to gather remaining impact information. D&T Finance support required to complete cost submission. Notes: An email has been sent to April Zhou requesting confirmation on the Lean Business Case and guidance on the remaining L2 items to proceed toward L3 approval. Gen0/Gen1 applications do not apply to this initiative. Overall: L2 is largely complete; pending items require input from SCO and D&T Finance to finalize and enable L3 submission. Status Rationale – 09/16/2025 On 09/15/2025, we held a meeting with the Architecture team to review the initiative. During this session, key architecture considerations were raised and discussed. The team confirmed that the overall structure of the project is aligned and progressing as expected. However, the Architecture team indicated that they need to conduct additional internal reviews on certain specific points before providing their final confirmation. As Initiative Owners, we are currently awaiting their feedback in order to proceed with the transition to Phase L3. 08/18/2025 - The initiative has completed the L1 Architecture Alignment. The documentation is available in the Enterprise Architecture Repository and the folder link has been added to Planview. Impacted Portfolios and T-Shirt Size were updated according to the L1 assessment. Lean Business Case has been completed and all applicable requirements in the Stage-Gate Checklist have been addressed. The initiative is now ready for submission to SL2. 08/05/25 - Uploaded the documents received from Serlefin's IT team to the EA SharePoint folder. These are being considered as the architecture documentation for the project. 08/01/25 - Initial L1 completed. Solution confirmed with vendor (Serlefin) and key assumptions documented. 08/03/25 - The target value of 79.17M has been corrected in alignment with Finance guidelines. The revenue figures were provided and validated by the Finance team, considering that the system retirement was initiated while FY25 was still ongoing. The architectural documentation is pending. I am currently awaiting contact from the EPM to proceed with the creation of the official Impact Assessment, as required. The documentation will be submitted once finalized and verified for consistency with Planview records. Additionally, this initiative is currently ranked #7 in the Enterprise Priority Dashboard and #3 within the Domain ranking according to the latest Power BI report. | G: L3 | Active | L3 | 2025-10-06 | 2026-12-31
Business w/ Tech Initiative: MEISA Tax eInvoicing initiatives |  | 154440 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | ANJALI S. DEO, Nikhil Goenka, Ewa Bronowicz | Attention Needed | 11/11/25- The PV ID is now in L3. Waiting for IT to prioritize the initiative for NIG & MWI Nigeria & Malawi have deadline of Nov'25 & Dec'25 respectively, however, this request is still not under L3. This needs to be fastracked as CREDO IT picks up the initiatives only when it is in L3 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2027-06-30
Business Only Initiative: Billing Change Fee in APAC |  | 93994 | Business Only Initiative | SGA - Ship to Collect | SG&A | Hirohisa Ando, Raja Nelavae, Tian-Meng Goh | On Track | This iintiative for Billing Change Fee (BCF) was migrated from Ground Ops POD to Finance POD BCF was implemented in selective APAC countries on Jan 6th 2025 and has contributed USD170K in 12 months (Feb'25 - Jan'26) Cancellation as Planview should not capture an implemented project. | E: L2 | Cancelled | L2 | 2025-01-06 | 2025-01-06
Business w/ Tech Initiative: PEACE Vietnam - Update 2C2P to M-Pay End Point |  | 168979 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Choy-Li Kelly Leong | On Track | On Hold | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Credit Note CSV File Format for Invoicing Solution |  | 171127 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Matthew Hudson | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: APAC e-Invoice (TH & FJ) |  | 171131 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Hye-Rim Lee | On Track | [12/29] We need to get approval ASAP for IT development. | G: L3 | Active | L3 | 2026-02-23 | 2026-12-08
Business w/ Tech Initiative: FedEx Billing Network - Change of Vendor |  | 171137 | Business w/ Tech Initiative | SGA - Ship to Collect | SG&A | Matthew Hudson | On Track | On Track | E: L2 | Active | L2
Business Only Initiative: LAC: ASC and Guatemala (CCA): Reduce Dex93 (unable | 23393 | 8790 | Business Only Initiative | SE - International | Service | Radames Callado, Alejandra Bastardo | On Track | Analysis of D93 usage in ASC & GT has been completed at this point. following items or Milestones are to Schedule with OPS Management on Rollout of acceptable usage. Will be completed in NLT 2nd Week of July | I: L4 | Cancellation Request | L4 | 2023-04-03 | 2023-10-31
Business Only Initiative: LAC - Focus on reducing OB PPWK related failures | 16055 | 9262 | Business Only Initiative | SE - International | Service | Gabriela Fernandez, Norma Suarez | On Track | This initiative is now being closed for two main reasons: first, it was requested; and second, the objective was successfully met, a 50% reduction in paperwork-related cage failures was achieved, resulting in a 1 PP improvement in DCC service levels across LAC. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-01-02 | 2024-03-29
Business Only Initiative: Global Hub Scanning Playbook |  | 91963 | Business Only Initiative | SE - International | Service | Elizabeth-Lynn Doiron | On Track | Playbook is completed in PDF and web version. Launch communication has been deployed. 7 subsequent focus item communiqués are on track for weekly deployment over the next seven weeks. There are no costs outside of FTE time used. Sharepoint site is developed and launched as global standard of what will be used by all hubs. Awaiting data from Finance with regards to providing a cost of quality model to illustrate that reduced variation in global scan inputs will improve customer experience and quality of data outputs, elements will be used to build business with tech. This initiative will be completed the week of May 6 when the final weekly communication goes out. Forthcoming initiatives to align with global standards will be costed as business with tech initiatives. This project is completed 05/22/2025 | E: L2 | Cancelled | L2 Feedback Requested
Business Only Initiative: Holistic Service - Incorporates Financial Impact o | 8265 | 7843 | Business Only Initiative | SE - Surface | Service | Andrea Mazzarella, Shawn Votino | On Track | 9/15/2025 - PDSM Request #INC032228182 submitted by Shyam Mohan requesting the cancellation of this initiative. 8/5/2023 - Initiative is on track | I: L4 | Cancelled | L4 | 2022-09-01 | 2023-06-30
Business w/ Tech Initiative: Improve Smalls Service by Implementing Standardize | 8253 | 8160 | Business w/ Tech Initiative | SE - Surface | Service | Mattew Stevenson, Dan Jacobs | On Track | The work has been completed for the Smalls Best Practices development and launch. | I: L4 | Cancelled | L4 | 2023-01-04 | 2024-10-31
Business Only Initiative: Improve Divert Rates in MEMH matrix | 10342 | 8213 | Business Only Initiative | SE - Surface | Service | Andy Messick, Zachary Rhodes, Darrell Jessup, Shane Floyd | On Track | Initiative is on-track. Quality Action Time has been established and is being lead by Noah Wilson in Operations, Planning, and Engineering. Assess, Build, Launch and Evaluate phases have been completed and/or underway. Waste walks have been completed and findings have been reviewed and communicated with stakeholders. Training packets have been created and reviewed with key operations personnel and are being implemented. AS line performance dashboards have been created to assist the team in identifying key areas to focus resources. 10/04 Weekly KPI: - Day Divert Rate Avg (September 27 - September 3): 90.46% - Night Divert Rate Avg (September 27 - September 3): 92.7% Milestones - Old radiation detectors on AS lines are being removed and productivity lights are being installed. - Premium pay has been approved for matrix hourly employees to help with employee retention. - Side scanners are currently being installed on AS lines in the matrix and 10 lines are targeted to be completed prior to peak. - Nightside is continuing to increase in divert rate with increased focus on methods and standards. | I: L4 | Cancelled | L4 | 2022-01-03 | 2024-09-12
Business w/ Tech Initiative: Reduction of Origin Wrong Day Lates (WDLs) - Focus | 10422 | 8888 | Business w/ Tech Initiative | SE - Surface | Service | John Defelice, Dan Jacobs | On Track | 6/25/25: Old initiative that has run its course. The Service Domain is reorganizing, both initiative owner and backup are in different roles and have been instructed by Pod lead to close out. 9/5/2024: OWDL reduction tool has been fully rolled-up to US operations. John Defelice and John Gallop V conducted three training sessions for Legacy Express SRMs. Tool has been communicated through monthly DRIVE communication, Focus on the Four messaging, RVP meeting, and Surface Service Council. RVPs have helped push adoption of the tool and IT has tracked tool usage. July averaged 30 unique users and ~200 views/day. The last week of August saw 71 unique users with 511 average daily views. KPIs will continue to be tracked for 12 months. Tool usage should reduce Origin Wrong Day Lates and improve MBG. DRIVE communication is below. This was communicated in various forums. What is it:The Origin Wrong Day Late Scan Compliance Report (Keyword “OWDL”) is a new legacy Express tool that can help reduce controllable money back guarantee (MBG) failures by quickly assessing opportunities at the package level. Benefit(s):The real-time reporting can be refreshed multiple times during outbound sorts to compare all pickup volume to outbound scan records. Packages with missing scans can be identified, located, and then possibly make outgoing flight or trailers cuts, thus reducing potential failures. How we’re measuring success:Success will be measured by reducing origin wrong day lates and monitoring average daily users. Timing:Enhancements to this tool rolled out in mid-June. Training for legacy Express managers was conducted, but additional trainings may be needed to push tool adoption. Actions to take:Legacy Express SRMs should use keyword “OWDL” to access the tool. At that point, if access is still needed, request Image role azure_dwx_atlaslabs_pbi_wdl_prod_view. Once access is gained, instruct ops managers to utilize the tool, especially on outbound sorts as critical cut times near. 8/5/2023 - Approved resolution of latency issues. Cost will reside with this initiative. | I: L4 | Cancelled | L4 | 2022-09-01 | 2024-08-28
Business Only Initiative: Final Mile Delivery Improvement | 38605 | 8891 | Business Only Initiative | SE - Surface | Service | Rick Harball, Dan Jacobs, Sean Cahalan | On Track | 10/9/2024 This initiative was stood up about a year ago but saw little progress. Initiative was moved back to L1 and redefined with Rick Harball as lead. Three sub-teams that are meeting weekly to drive Ground delivery failures, Express RDLs, and Network 2.0 PO service. Project is well structured, but identifying the number of focus locations to graduate still needs to be hashed out with team leads. Pushing through to L2 prior to the Planview move. 6/19/2025. With the changes in structure and reporting for the Service Assurance team to Service Excellence it changes the structure of the Service initiatives in the drive domain and our role in these initiatives. This team structure really is more of a QAT for service improvement with the field organization. Requesting to put this on hold until the new reporting structure and FY26 plans get finalized. 6/25/2025. Request is to cancel this initiative in Planview. This is a QAT initiative and not a Drive initiative. This has been local focus and Station specific action plans to improve delivery performance. While improved performance could help attract new customers and retain existing customers there is no accurate way to measure the cost savings or to quantify retention. This is best handled in the QAT arena. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Scan Integrity - Improving Scan Compliance Through | 8262 | 9073 | Business w/ Tech Initiative | SE - Surface | Service | Kamal Zerrad, Chris Rooney | On Track | 8/7/2023 - Preparing live demo of Phase 2 Hub tool for SCORE meeting this week. Also looking into possible retirement of HPR (legacy tool). | E: L2 | Active | L2 & CCH | 2022-10-03 | 2024-10-24
Business Only Initiative: Bulk Delivery Failure Reporting | 8266 | 9080 | Business Only Initiative | SE - Surface | Service | Loreto Vigiletti, James Woodard | On Track | 8/9/23: Monthly monitoring of avg daily failure counts. Will reach out to operations team to increase awareness of KPI targets and need for focus on improvement. 6/23/25: Report is being used to improve monitoring of bulk delivery failures and continues to be sent out daily. Failures have been reduced and report will continue providing visiblity to failures and detial information to address issues. | I: L4 | Cancelled | L4 | 2022-12-01 | 2023-07-28
Business Only Initiative: Improve Tuesday performance |  | 143633 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Jake Dorris, Lance W. Spradling | On Track | 10/8 Advancing to L3 7/31 changing primary | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-25 | 2026-03-06
Business Only Initiative: Verify Accuracy of Planning Assumptions |  | 143636 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Timothy Orris | On Track | Start of initiative | E: L2 | Active | L2
Business Only Initiative: Reduce Wrong Day Late (WDL) at N2.0 Locations |  | 143639 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Brian J. Curry, Sigfrido Pineda | On Track | 07/31 - Entering L1 LBC 07/24 - Preparing for L2 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-01 | 2026-01-22
Business Only Initiative: Improve PM Outbound Performance |  | 143643 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Jake Dorris, Michael D'Ambrosio | On Track | 10/27: On Track 10/10: Money Step Evidence added and Money Step completed. Ready to submit to L4. 10/10: Milestones updated. MPC preparation communication sent this week. 10/1: Reviewing milestone completion process. Change to enabler and readying for L2. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-09-15 | 2025-11-04
Business Only Initiative: Improve Visibility to Plan vs. Actual FRO Sequence |  | 143646 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Chelsea M. DeSalve, Randy Kelley | On Track | 3/30 - Began entering KPIs for February, still waiting on service KPIs from service team for January and February months (asked multiple times). SPOTlight initiative was assigned an architect and are beginning work in L2. In the process of determing the next steps for internal report, even after SPOTlight report goes into production. DataWorks needs to consume new data topic that was created to consume missing data elements on internal report - FLM Manifest (Randy Kelley is helping lead this conversation) 2/12 - Entered some January KPI information into PV, still waiting on the service data for the remaining KPIs (MBG & PO RDLs). Will discuss future outlook of initiative with team in our next meeting on 2/17, and will get an update on the progress of the SPOTlight initiative. 1/22 - SPOTlight report initiative has been moved to enterprise priority 52, meaning it may get assigned an architecture review soon. One of the three missing data elements for the internal report (Manifest Planned Arrival Time) is in progress. 1/5 - Met with Jennifer Weaver and Sarah Mertz to discuss plans moving forward with this initiative since it is no longer included in DRIVE. Still planning to track milestones and KPIs in PV. Will be updating the November KPIs and discussing any potential valulable alternatives with the internal report moving forward since we are still waiting on the SPOTlight report to gain momentum. 12/10 - Met with FLM Manifest team. Meeting resulted in the action item of updating the current FLM Manifest topic with some of the needed elements for the internal report (Manifest Arrival Time and Manifest Planned Sequence), and creating a new topic for the summary data needed. 11/3 - The SPOTlight initiative is not getting bumped up far enough for an architect assignment, so that report will not begin production anytime soon (as far as I know). I believe they hopped to 150, but only top 50 get architects. In the meantime, this roadblock is going to be brought up on the next TO (11/12), explaining we can't continue to move forward until 153749 does, even though we have a 0.24% PO Improvement tied to this initiative. I am waiting to hear back from Kevin Dexter - he was meeting with Brad to see if there is anything left for us to do/try before bringing this up on the TO. Also - I should be receiving October KPI data from Rahul this week and will enter that into PV. 10/24 - The SPOTlight inititave (153749) had a meeting yesterday to try and bump the prioritization up from 209 to 150 or better. It is my understanding that they will defintely get to 150, but have a follow up call on 10/28 to see if it can move even further up the line. Regarding 146346, we are on a stand still until we can get a date of production for the SPOTlight report. Hopefully we have a better idea following the meeting on 10/28. 10/20 - Determined the static list of N2.0, CSSP stations that we will focus on for our KPIs. Kevin Patch provided me with September data for our KPI baselines for PO MBG% and PO RDLs. I am waiting on Rahul for data regarding the PO Planned but Unsuccessful KPI and some sizing data to redo the calculation for the static list (prior we did it for all N2.0 stations). I am meeting with SPOTlight team tomorrow to chat about report timeline. 10/14 - Rahul requested numeric station number for pulling KPI data, so we are currently sourcing that. Once I receive a finalized list from Ana, Rahul will be able to provide me the data needed to finalize our KPIs for the static list of N2.0 stations Randy and I decided upon. Besides that, we are waiting on an estimated deployment date for the SPOTlight report since we were told we cannot go into L3 until we have that. I am meeting with the IO from the SPOTlight initiative and a few others 10/17 to hopefully get a timeline. 10/8 - The only KPI left to calculate a baseline for is PO MBG% and Ana is helping me with that. We need to decide if we are going to stick with a static set of N2.0 st | E: L2 | Active | L2 | 2025-07-15 | 2026-05-04
Business Only Initiative: SWARM PO Focus Markets- Legacy Express |  | 143748 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Lori A. Hughes, Sarah Mertz, Barry Mobley | On Track | Week ending 11.7.25 *PO MBG service level for week ending 11.7.25 for the WAVE 3 markets was 95.4%, 3 of 7 markets above target. * In October 2025 there were multiple signficant events that impacted PO MBG service level, including power outages in MEMH the week of 10.10.25 and 10.17.25 and multiple crew related delays for week ending 10.3.25 and 10.31.25. These extensive delays prevent destination locations from delivering on time service and become recovery contingency operations. Week ending 10.17.25 * Overnight service impacted by sort delays with SPSS at MEMH power outage during Thursday night sort, excessive rollover * Grand Rapids (GRR) market presented at Surface Service Council for PO MBG performance Week ending 10.3.25 * Cincinnati (CVG) market presented at Surface Service Council for PO MBG performance September 2025 * All WAVE 3 markets completed the PO Focus market program and exercises in September 2025. The markets created action plans for identified root causes and continue to work their plans to reduce PO service failures. Week ending August 29, 2025- * Market Leads completed analysis for Right Day Lates using station inbound scan/arrival times. Identified % of controllable failures for improvement. Week ending August 15, 2025 * Addition to weekly Wednesday meeting, added "office hours" call beginning August 15th. to support leads with their service analysis. Week ending August 8, 2025 *Norfolk (ORF) market presented at Surface Service Council for PO MBG performance Facilitating weekly meetings with FOCUS Market leads to review Priority Overnight Money Back Guarantee service peformance and corrective action plans. Project and individual market scorecards are distributed weekly with previous four week performance for identified service KPI metrics to track improvement. The scorecards and weekly summary are distributed to Surface and Network leadership teams weekly. Identified 6 new markets to join project beginning week ending July 25, 2025. Weekly meetings are held each Wednesday with market leads and action plans are documented. Project introduction call completed week of July 18 with initial location service survey due July 25, 2025. | H: SL4 | Active | SL4 Domain Lead Approval | 2025-06-23 | 2025-11-07
Business Only Initiative: Align courier staffing to engineering plans |  | 153114 | Business Only Initiative | SE - Domestic Priority Parcel | Service | Shea Winston, Thomas Beaudoin, Javier Martinez | On Track | 10/10/2025 - Changing Primary IO 10/9/2025 Final updates made to L2. 7/31/2025 Updates made to L2. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-15 | 2026-03-31
Business Only Initiative: IPF Flow Change S-URSA to X-URSA Friday Pickups |  | 143114 | Business Only Initiative | SE - Int'l Freight | Service | David J. Palmiotto | On Track | Changes to URSA to be implemented with the next earliest possible operating month (SEP25) | I: L4 | Active | TEMP L4 - Enter L4 | 2025-08-01
Business Only Initiative: Rationalize Transit Days by Day of Week |  | 143118 | Business Only Initiative | SE - Int'l Freight | Service | Elizabeth Amalfitano, Scott K. Wilson | On Track | LBC Submission for progression to L2 | E: L2 | Active | TEMP L2 & CCH - Feedback Requested - Enter L2 | 2025-08-11 | 2025-11-03
Business Only Initiative: Rationalize Lift Bump Priority and IPF Transit |  | 152861 | Business Only Initiative | SE - Int'l Freight | Service | Elizabeth Amalfitano, Scott K. Wilson | On Track | LBC for submission to L2 | E: L2 | Active | L2 & CCH - Feedback Requested | 2025-08-11 | 2025-11-14
Business Only Initiative: Decongest Orange / Purple network by shifting IEF |  | 152919 | Business Only Initiative | SE - Int'l Freight | Service | Stefan Gant, Ethan Schek | On Track | Currently launching | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-04 | 2027-09-30
Business Only Initiative: Swarm Enablement Structure |  | 153486 | Business Only Initiative | SE - Int'l Freight | Service | Charles O. Baggett, Anjum Sultana | On Track | 11/5/25: Continuing to monitor and support the other Swarm initiatives. There are four Europe initiatives, one LAC, one MEISA, one US, and one APAC. 10/3/25: This initiative entered L4 on 9/25. Charlie is meeting with the IOs of the enabled initiatives to review the Swarm Playbook and discuss next steps. 9/24/25: Charlie updated the milestone and KPI sections in Planview. All regional Swarm team have the playbook and are equipped to begin multi-dimensional analysis of their lanes and to identify actions to reduce lane-level service failures. 9/19/25: The first version of the Swarm Program Playbook was finished and sent to all regional Swarm teams, Initiative Owners, and regional Managing Directors. 09/02/2025: Met with ESPM and Finance teams to review this initiative before submitting to L3. Submitted to L3 today. 08/29/2025: Added a KPI of # of regions graduated. Submission to L3 is postponed until next week. 08/28/25: Charlie revised milestones based on feedback. Planning to submit for L3 on 8/29. 08/27/25: Waiting to submit to L3 until we gain more clarity on how these types of initiatives will be handled in Planview. SWARM initiatives are not linear. In the meantime, I added this initiative as a dependency to my enabling initiative: SE - MEISA SWARM OB (155320). 08/19/25: Initiative was sent back due to insufficient information about the 'Money Step." Charlie refined the money step description and re-submitted. 08/18/25: Slight delay as Charlie Baggett was waiting for IO access to submit L1 information. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-08-15 | 2025-10-17
Business Only Initiative: SE - ASOB SWARM LANES |  | 153490 | Business Only Initiative | SE - Int'l Freight | Service | Komal K., Yiu-Fai Tsang, Charles O. Baggett, Jimmy Zhang | On Track | 11/6/25: Komal K will be another IO for this initiative. I requested Planview access for Komal. 11/5/25: Thank you for the update on 10/24. Since the Int'l Freight Pod call is outside of your normal working hours, please continue to leave regular updates in this section so that I can speak to your progress or challenges on the pod calls. Thank you. Charlie Baggett. 10/24/2025: Requested for US marketing team to review the IPF EOD TT change on 10/23. next steps for SG is to implement skywalker starting Nov and reduce the Bulkout. JP is discussing with PCC team for clearance related issues. 10/8/2025: We met today to review the playbook and discuss next steps. This will stay in L3 until money step is achieved. 9/16/25: Jimmy or Yiu-Fai will need to update the "Brief Deman Description" section to include the selected focus lanes for this sprint. Proposed team structure—grouped by product and outbound region— targets high-impact lanes with potential to improve NSL by 0.1%-0.4% | G: L3 | Active | L3 Feedback Requested | 2025-08-08 | 2026-01-29
Business Only Initiative: SE - USOB SWARM LANES |  | 155186 | Business Only Initiative | SE - Int'l Freight | Service | Kelley Mathewson, Charles O. Baggett | On Track | 10/10/25: Added a date of 1/30/26 to the money step and added a money step description. Re-submitted to L3. 10/9/25: Added a description to each milestone and edited the "Brief Deman Description" section to only include DE, SG, and NL lanes (USOB, IPF). Average FY25 NSL for the three lanes is 54%. Cumulative target NSL is 59%. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-29
Business Only Initiative: SE-MEISA SWARM OB |  | 155320 | Business Only Initiative | SE - Int'l Freight | Service | Bernice Sridhar, Charles O. Baggett, Jarnail Singh | On Track | 09/24/25: List of top customers causing improper paperwork identified. Sales and Ops team aligning with these customers on the complete paperwork requirements. 09/24/25: Aligning with MEISA network teams to assess future demand and capacity for US freight and look alternatives to procure more capacity. 08/14/25: We had our initial kickoff with the MEISA swarm team today. Next steps are to continue with analysis and identify initial actions. Based on the data from service excellence team, top 2 challenges identified as missing paperwork and bulk out | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-30
Business Only Initiative: SE-EUOB SWARM Lanes |  | 155323 | Business Only Initiative | SE - Int'l Freight | Service | Ricky Hill, Louise Billings, Charles O. Baggett | On Track | 11/5/25: Since the Int'l Freight Pod call is outside of your working hours, please use this section to provide a brief weekly update regarding your progress and any challenges you're facing. 13/08/2025 - L2 completed and ready for review | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-29
Business Only Initiative: IPBSO and ODC Process or Logic Refine/Align |  | 159279 | Business Only Initiative | SE - Int'l Freight | Service | Elizabeth-Lynn Doiron, Elizabeth Amalfitano | Some Issues | 10/08: Reviewing L2 readiness 10/27: Reviewing viability of business only demand. Given the number of risks, surcharge trigger and impact to non customs delayed volumes MBG post clearance, team is reviewing for potential alternative business with tech solutions 12/18: Initiative placed into hold until further notice, given Service Domain removal from Planview | E: L2 | Cancelled | L2 & CCH
Business Only Initiative: Improve customer engagement with Apple |  | 160858 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Joysse Guilarte | On Track | Cancelled due to sizing | C: L1 | Cancelled | L1
Business Only Initiative: Reduce customer not in failure |  | 160863 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Joysse Guilarte, Elizabeth Davila | On Track | 04/21/2026 updates Mar * DEX08 FR at 0.38%, 0.03 Pp better than February and 0.02 Pp better than goal for March at 0.40% * NSL IB US-MX (Parcel) Mar at 73.2%, 8.5 Pp better than February and 3.0 Pp better than goal for March at 70.2% 03/13/2026 updates Feb * DEX08 FR at 0.35%, 0.07 Pp better than January and 0.09 Pp better than goal for February at 0.44% * NSL IB US-MX (Parcel) Feb at 64.8%, 2.2 Pp worse than January and 5.26 Pp worse than goal for February at 70.06% 03/03/2026 updates Jan * DEX08 FR at 0.42%, 0.01 Pp better than December and 0.05 Pp better than goal for January at 0.47% * NSL IB US-MX (Parcel) Dec at 67.0%, 1.9 Pp better than December and 3.03 Pp worse than goal for January at 70.03% 01/21/2026; KPIS updates Dec * DEX08 FR at 0.43%, 0.22 Pp worse than November and 0.07 Pp better than goal for December at 0.5% * NSL IB US-MX (Parcel) NOV at 65.1%, 6.9 Pp worse than November and 4.9 Pp worse than goal for December at 70% 12/12/2025; KPIS updates Nov * DEX08 FR at 0.21%, 0.26 Pp better than October and 0.29 Pp better than goal for Novembre at 0.5% * NSL IB US-MX (Parcel) NOV at 72%, 3 Pp worse than October and 2 Pp better than goal for November at 70% 11/11/2025: KPIs updates Oct * DEX08 FR at 0.47%, 0.01 Pp better than September and 0.03 Pp better than goal for October at 0.5% * NSL IB US-MX (Parcel) OCT at 75%, 0.7 Pp better that September and 5 Pp better than goal for October at 70% 10/20/2025: Update - Focusing on top 20 offender stations with highest failure rates, and scan compliance best practices adherence. 10/10/2025: Updated - Milestones status. KPIs performance start to be upload on Nov 2025 with the Oct 2025 results. 09/10/2025: Updating information to L1 LBC | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-25 | 2026-07-01
Business Only Initiative: Improve customer engagement with Augusta |  | 160866 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Joysse Guilarte, Armando Garcia | On Track | Cacekation due to sizing | C: L1 | Cancelled | L1
Business Only Initiative: Prepare for CA Holidays |  | 161354 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Jack Brown | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Reduce bad - address failures |  | 161358 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Joysse Guilarte, Elizabeth Davila | On Track | 04/21/2026: KPI updates Mar * DEX03 FR at 0.86%, 0.15 Pp worse than February and 0.21 Pp worse than goal for March at 0.65% * NSL IB US-MX (Parcel) Mar at 73.2%, 8.5 Pp better than February and 3.0 Pp better than goal for March at 70.2% 03/13/2026: KPIs updates Feb * DEX03 FR at 0.71%, 0.11 Pp better than January and 0.1 Pp better than goal for February at 0.7% * NSL IB US-MX (Parcel) Feb at 64.8%, 5.0 Pp better than January and 5.3Pp worse than goal for February at 70.1% 03/03/2026: KPIs updates Jan * DEX03 FR at 0.82%, 0.12 Pp worse than December and 0.07 Pp worse than goal for November at 0.8% * NSL IB US-MX (Parcel) Jan at 67.0%, 1.9 Pp better than December and 3.5Pp worse than goal for January at 70.05% 12/21/2026: KPIs updates Dec * DEX03 FR at 0.70%, 0.23 Pp better than November and 0.1 Pp better than goal for November at 0.8% * NSL IB US-MX (Parcel) Dec at 65.1%, 7 Pp worse than November and 4.9 Pp worse than goal for December at 70% 12/12/2025: KPIs updates Nov * DEX03 FR at 0.93%, 0.19 Pp worse than October and 0.13 Pp worse than goal for November at 0.8% * NSL IB US-MX (Parcel) Nov at 72%, 3 Pp worse than October and 2 Pp better than goal for Novembrer at 70% 11/11/2025: KPIs updates Oct * DEX03 FR at 0.74%, 0.24 Pp better than September and 0.06 Pp better than goal for October at 0.8% * NSL IB US-MX (Parcel) OCT at 75%, 0.7 Pp better that September and 5 Pp better than goal for October at 70% 10/20/2025: Update - Working currently along with WAM to focus on Apple failures reductions as the major contributor. 10/10/2025: Updated - Milestones status. KPIs performance start to be upload on Nov 2025 with the Oct 2025 results 09/10/2025: updating L1 LBC | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-25 | 2026-06-23
Business Only Initiative: Reduce Courier Churn at MTY |  | 161865 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Joysse Guilarte | On Track | It is a minimal opportunity | C: L1 | Cancelled | L1
Business Only Initiative: Review transits in insecure areas |  | 161874 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Joysse Guilarte | On Track | Cancellation due to sizing | C: L1 | Cancelled | L1
Business Only Initiative: Reduce lowest performing CA stations |  | 161881 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Jack Brown | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Swarm MX - US |  | 163695 | Business Only Initiative | SE - Northern and Sourthern Border | Service | Elizabeth Davila, Charles O. Baggett | On Track | 10/8/25: Added a description to the money step and re-submitted to SL3. 09/23/2025: Update to SL2 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-30
Business w/ Tech Initiative: Accurate transit time reflection by adding in-tran | 54370 | 8999 | Business w/ Tech Initiative | SE - Europe | Service | Svetlana Belinskaya, Andrei Hidigan | On Track | . | E: L2 | Cancelled | L2 | 2024-05-07 | 2024-05-14
Business Only Initiative: [EU] Swarm Sprint #3 |  | 141591 | Business Only Initiative | SE - Europe | Service | Sooraj Ravikumar, Charles O. Baggett | On Track | 10/3/25: Charlie reviewed the Swarm Playbook with the IO (Sooraj) and reviewed some of the Swarm resources. The next milestones are conduct multi-dimensional analysis (Service, Efficiency, Movement) to identify root causes and identify initial batch of actions to improve service performance. 07/14 - Analysis started for GB-JP, highest impact lane 07/04 - Key lanes identified | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-30
Business Only Initiative: [EU] SWARM - EU to APAC Deferred Parcel |  | 141595 | Business Only Initiative | SE - Europe | Service | Sooraj Ravikumar, Charles O. Baggett | On Track | 10/3/25: Charlie reviewed the Swarm Playbook with the IO (Sooraj) and reviewed some of the Swarm resources. The next milestones are conduct multi-dimensional analysis (Service, Efficiency, Movement) to identify root causes and identify initial batch of actions to improve service performance. 07/14 - Intra-EU network mapping complete 07/04 - Intra-APAC network mapping complete | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-30
Business Only Initiative: EU POD - EU SWARM |  | 141598 | Business Only Initiative | SE - Europe | Service | Louise Billings, Thomas Hartshorn, Charles O. Baggett | On Track | 07/14 Entering :LBC 07/04 - LBC in progress and on track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-16 | 2026-01-29
Business Only Initiative: EU POD - Deferred flow plan validation |  | 141601 | Business Only Initiative | SE - Europe | Service | Louise Billings, Thomas Hartshorn | On Track | 07/14 Entering LBC 07/04 - LBC for L1 in progress | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-25 | 2025-11-14
Business Only Initiative: Service EU Consistent Transit Times |  | 141604 | Business Only Initiative | SE - Europe | Service | Elisabeth Vullings, Thomas Hartshorn | On Track | 8/6 changing primiary owner | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: EU Service - CLH/Clearance on Entry |  | 141607 | Business w/ Tech Initiative | SE - Europe | Service | Thomas Hartshorn | On Track | Already in flight as part of Tricolour and the implementation will be tracked vai that POD | C: L1 | Cancelled | L1
Business Only Initiative: EU Service - US Gateway Handover |  | 141610 | Business Only Initiative | SE - Europe | Service | Thomas Hartshorn | On Track | Not required as validation confirmed routing was correct. | C: L1 | Cancelled | L1
Business Only Initiative: [EU] Swarm Sprint #2 |  | 141614 | Business Only Initiative | SE - Europe | Service | Timothy Nevill, Thomas Hartshorn, Stephanie Schneider | On Track | Assigned new Primary owner 7/16/25 entering L1 LBC 9/19/25 On Hold per SWARM guidelines. Inititive will start when sprint #1 is complete. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-07-08 | 2026-01-23
Business Only Initiative: EU Service - E9 Special |  | 141620 | Business Only Initiative | SE - Europe | Service | Louise Billings, Thomas Hartshorn | On Track | 07/16 - Preparing LBC for L2 Assigning new primary IO | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-01 | 2026-02-02
Business w/ Tech Initiative: Holiday in Transit - Transit Time Calculations |  | 141624 | Business w/ Tech Initiative | SE - Europe | Service | Thomas Hartshorn | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Service EU - Peak Management |  | 141628 | Business Only Initiative | SE - Europe | Service | Fernando Manuel Soares Costa, Elisabeth Vullings | On Track | We are already taking part of the regular Integrated Network Peak Planning calls and are sharing feedback to have a better peak planning for this year. We are within the timelines of the planning and have already shared some insights with our management group. We already had discussions with the relevant commerical teams participating in the INPP reviews. Insights were shared and reviewed. And the teams are already preparing for this year's peak. Work is underway to support operations with daily insights to ensure that prioritization is done in a timely manner | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-01 | 2025-11-14
Business w/ Tech Initiative: Critical Close Model Improvement | 32735 | 6932 | Business w/ Tech Initiative | SE - Tech | Service | Zachary Ambrisco, Connor Soboslay | On Track | Initiative has been greenlit by Dataworks. Waiting for Dataworks to update greenlight status in WAVE. Will confirm updated costs with Dataworks next week. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-08-01 | 2026-06-26
Business w/ Tech Initiative: Establish Single Source of Truth for Ops Driven CE | 33482 | 6970 | Business w/ Tech Initiative | SE - Tech | Service | Daniel Stolick, Barry Mobley, McKenzie Worden | On Track | 4/17/2026 1 Enhancement left to cover to be prepared for them all being ready for development. We have started on MVP3 because there are more Enhancements arising from discussions and items user want to have done. It is going to take time to see how DataWorks is going to move things to Atlas and how. There is a push to go from Azure to GCP, but there are many items yet to be resolved. We are able to continue in the Development space, but cannot move them into Production without going through DataWorks and they are not prepared to start to move things over until they determine how they will move forward. Still working on AI we determined the Users and now working on Personas There are many stages we have to complete to get through the AI work, and officially start testing. 4/10/2026 * There are 2 Enhacements left to review to see if they are covered or require adjustments. * We had to create MVP3 because there were other asks that are out of Scope for MVP2, so we are now capturing them. * There is also the capability to start to organize the data that is going to be added and who owns adding it. * The data requests are going to be organized and put in buckets for Data Works and our team. * We hace worked through the details of the Enhancements and how they are extremely picky, because some are mergeing data from Ground to Express * The AI is moving along trying to determine the users, what they will do, and how they will do it * The scope must be clear on AI in order for it to be accurate and defined, so it does not cost a fortune or grow out of control in its usabilitly. 4/3/2026 * There are 3 Enhancements to still review with the team to get clarity. * I meet with Sarah M on hers on April 6th to get clarification and get in the que for building. * All other Enhancements are being put in groupings for easier ability to build them in groupings. * Also must go through all the "data" enhancements to get then into buckets for building either with our team or Data Works. * The goal is to get started on something smaller so as a team we can get started to see if the developer has access and capability to get the started and be successful. * The team in UAT will be vital to do full UAT testing starting soon. * Also this will require test cases to be created for the Enhancements that are being fulfilled. * Once we fully complete the Requirements then they will be added fully to the Project Plan with dates 3/27/2026 * MVP Enhancement are being cleaned up and there are only a few left to discuss with the team * There are going to be new additional data points and screens * Have to get Amanda to get back end access to EDR and Legacy Reports, neither one have happened yet.. * The goal is to go through all of the Enhancements and have them organized in sections for Dev * Also the ones that are new data points those need to be marked and organized for Data Works so when they pull in the data we can give it all to them at once. * Opened up EDR AI testing this week and starting to capture those items and formally testing more * Also added an Enhancements document to capture anything that also needs to be adjusted in EDR AI 3/20/2026 * Continued work on EDR MVP2 Enhancements. * Amanda is still trying to get access to the data bases that are required for her to do the work necessary for MVP2 * Grouping of requirements continues so Amanda will have an easier time trying to do the work. * There are 6 Enhancements left to put into groupings. * Also adding in Overnight as a measure has taken up ample time to figure out how the measures are done but also what screens it will be added upon. * There are several full screen that will require discussion and the data behind it to see if it is already in EDR. * AI work is continuing and the scope of work. * The users expectations are great so we are trying to put some scope around it and what the expectations are. * Some examples if they want to ask questions, have AI make decisi | G: L3 | Active | L3 Feedback Requested | 2024-03-05 | 2025-11-28
Business Only Initiative: Delivery Experience Alignment and Measurement | 16201 | 7776 | Business Only Initiative | SE - Tech | Service | Madeline Virden, Sarah Mayfield | On Track | Week of 5/8: L4 checklist under review. 4/27: FXE STRYDE launch complete. 100% of FXE key stakeholders provided dashboard access. 4/21: FXE STRYDE launch calls continued on 4/18 & 4/19. FXE now at 75% completion. 4/14: FXE STRYDE launch calls held 4/11 & 4/12. FXE rollout now at 50% completion. 4/4: FXE STRYDE launch calls being held 4/4 & 4/5. Will continue with next 3 regions through the end of April. 3/30: Milestones on track. Maintaining 3/31 official start date for FXE - kickoff demo calls to begin week of 4/3 3/22: 100% of FXG STRYDE rollout is confirmed as of 3/16. FXE STRYDE dashboard continues to be in development and maintaining 3/31 start date. 3/14: Global Customer Insights Team, owner of RYDE survey and STRYDE Phase 2 Tool, confirmed new target start date for FXE STRYDE Dashboard rollout will begin 3/31 instead of tentative 3/22 date. End date for FXE Rollout is still end of April. 100% of FXG STRYDE Rollout should be reached by 3/16. Milestones have been updated accordingly. 3/7: L3 approved, milestones on track, FXE launch slightly delayed - more info to be provided in meeting with FXE legal taking place late 3/7 3/2: Awaiting L3 approval, on track with milestones 2/24: On track with milestones 1/23: Met with Finance team 1/23 for guidance on business case metrics. Met with CE team for tracking # assessment on survey response indicating a 1-3 star rating & claim correlation. Relayed tracking # level to their team on 1/25. Targeting to receive assessment back from CE team by end of next week. | K: L5 | Completed | L5 | 2023-01-02 | 2024-05-31
Business w/ Tech Initiative: Customer Data Exchange - Ground Enablement | 8278 | 7778 | Business w/ Tech Initiative | SE - Tech | Service | Megan Aurin, McKenzie Worden, Alexander King | On Track | 5/27: Milestones on track with RFID Pilot 2/23: Milestones on track 3/14: Milestones on track going into EPV workshop 3/15-3/16 4/19/2023: Continuing to work through the TCH and Technology New Demand Intake Processes – 7 Portfolios identified. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-02-01 | 2026-08-31
Business w/ Tech Initiative: Enterprise Service Data | 8280 | 7779 | Business w/ Tech Initiative | SE - Tech | Service | McKenzie Worden, Usman Alavi | On Track | 2026-02-25: UAT for CEM completed Friday (2/20). All issues/fixes/CRs are being documented by the business. 2026-01-28: UAT for MVP 2.1 (initial commit) underway. Contract has been extended (waiting on final signatures) which will extend some members through end of Feb. Money step pushed back ~1 week, then contractors to stay on for stabilization. A FTE will be available after for any issues. CEM is under development. 2026-01-07: mvp1 prod dataset is available. updating 1x per day because of performance issue. testing performance fixes, then CAB. mvp2.1 (initial commit) releasing version with bug fixes to stage for final QA testing and to have data ready. started with CEM initial DE tasks. timeline is tight. some contractors wrapping up at the end of the month and others mid-feb (small group). CEM devel. work at risk. team to update after discussing mitigation ideas. 2025-12-03: ISS data issue fixed, data reload was initiated. Prod performance issue scheduled update takes more time on PROD than on STAGE. Team is investigating issue. 2025-11-28: historical load done, incremental load in progress. ISS data issue still causing problems. ISS team is reloading it. MVP2 No issues ~95% devel completed. We have CAB to create endpoint in Atlas. Team has started CEM work. 2025-11-21: MVP1 UAT on STAGE completed. Prod code release is completed, historical load in process -- estimated completion ~ 5 days. ISS data issue with updates. ISS team informed and waiting on CAB to fix. MVP2 devel ~ 90% complete. 2025-11-13: UAT underway. Still planning for 11/14 MTP and additional testing will be done on prod throughout Nov + when other initiatives begin connecting to/using SSOT. 2025-10-29: MVP1: Stage fixes done, testing in progress. Need to do historical load, but very slow (doing it in two stages). Mid-Nov release planned. Hoping for small dataset available for UAT on stage. MVP2.1: Devel in progress. No delays expected, but reprocessing of data is very time consuming, so any fixes, etc. require a lot of time. 2025-10-23: MVP1: Stage bug fixing and historical load optimization is in progress. 3 of 4 done, 1 in progress; MVP2: dev for Fusion source is in progress 2025-10-15: MVP1 on track. Still working on optimizations. But risk to timeline identified for MVP2 because sep fusion is not keeping all data for full fiscal year, it purges >3 months. Developers met with Usman and Jim about alternative options. Performing analysis to ensure new data source recommendation is sufficient. 2025-10-08: MVP1 -- stage release for transformation logic is planned this week; optimizations for historical load are in progress, more fixes are needed; dq checks implemented. MVP2 -- 1/3 branches of transformations are completed and being tested on stage, need optimizations. 2025-10-03: No significant progress this week for MVP1. Optimization for 2 most problematic steps is in progress -- the team is experimenting on data to find the proper approach, it takes time because of the data volume. Remaining part (i.e., 95% of data transformations) is completed in DEV. Last transformation is in progress of development in DEV. Currently still on track for MVP1 release, but full stage release postponed 1.5 weeks because optimizations are taking longer than expected due to the size of the data. MVP 2 (1/2 -- initial commit): 2/5 development tasks are completed, 1 in progress. Optimizations are required. 2025-09-25: Optimization of 2 most problematic steps are in progress. Source DQ checks are completed. Remaining part (95% of transformations) is completed in DEV, preparing next STAGE release. MVP2: 1/5 development tasks are completed (for initial commit only). 2025-09-17: First increment (60% part of transformations) deployed to STAGE. E2E integration is in progress. SEP historical data is too slow, so working on optimization to speed this up. Remaining part (90% part of transformations) is completed in DEV. Have begun (small amount of) work on MVP2 (initial co | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-18 | 2026-02-16
Business w/ Tech Initiative: Network 2.0/Multi Network Service Reporting Tools | 71988 | 7780 | Business w/ Tech Initiative | SE - Tech | Service | Ben Barber, McKenzie Worden | On Track | 8/18/2025 - On Hold while we figure out where this work will go (N2.0 scorecard moved to Local Enhancement init under Anne Amato). | E: L2 | On Hold | L2 & CCH | 2024-04-01 | 2025-04-03
Business w/ Tech Initiative: Enterprise Internal Tracking | 30668 | 7781 | Business w/ Tech Initiative | SE - Tech | Service | Christian Piroli, Sarah Mertz, McKenzie Worden | On Track | Targeting Pre-Peak 2026 for Epic 1. | E: L2 | Active | L2 Feedback Requested | 2026-05-08 | 2027-08-31
Business w/ Tech Initiative: Customer Experience Metric MVP | 17571 | 7784 | Business w/ Tech Initiative | SE - Tech | Service | Usman Alavi, McKenzie Worden | On Track | This work is covered under Enterprise Service Data (7779), so putting this on hold while confirming all requirements are included in ESD scope. Note: Dataset & logic have been developed in the backend. Logic simply needs to moved to production/Atlas. | E: L2 | On Hold | L2 & CCH | 2024-10-11 | 2026-04-30
Business w/ Tech Initiative: First Overnight product service improvement | 8775 | 7844 | Business w/ Tech Initiative | SE - Tech | Service | Tunc Kulur, Shawn Votino | On Track | 1/3/2024: Team call: agreed to continue FO Focus market calls. The calls will continue to be focused on MEM IB Load Quality and MEM IB Chase compliance, more specifically PU>4 hours before departure first flight. | K: L5 | Completed | L5 | 2022-12-07 | 2023-08-04
Business Only Initiative: Minisort / Load Plans | 8263 | 8171 | Business Only Initiative | SE - Tech | Service | Brian Ellis, James Joy | On Track | 08/30/2023 - Mini-sort continues to show excellent improvement. The reports are being sent to hub management nightly which is helping drive improvements through accountability. | K: L5 | Completed | L5 | 2022-11-17 | 2023-05-30
Business Only Initiative: ENABLER Network Tools and Knowledge | 12455 | 8182 | Business Only Initiative | SE - Tech | Service | Nicole Behanna, Dan Jacobs | On Track | Intitiative was held open for another group but is no longer needed. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-03-03 | 2025-05-01
Business Only Initiative: Smalls Centralization | 537 | 8193 | Business Only Initiative | SE - Tech | Service | John Brunt, Dan Jacobs | On Track | 12/16/23 - Average daily volume has exceeded original threshold of 90K for project completion. In weeks ending 12/2 and 12/9, Smalls Centralization packages averaged 117K/day. Three months of realized benefit at full phase. Program is fully sustainable, as smalls best practices and strategy have been modified to encompass Smalls Centralization logic and parameters established for adding/removing destinations from the program. As smalls volume grows, Field engineering will continue to increase the percentage of smalls destinations being consolidated. Additional opportunities are inherent to standard smalls planning logic and will continue indefinitely after overwatch has ended. As evidence of this fact, there has been minimal involvement by the initiative team since September, and the program has not diminished, but rather has grown in that time. The initiative is being submitted for L5 review. 11/17/23 - Liaised with Hub and Outbound Engineering Support to develop collaborative guidelines for Smalls Centralization and traditional bypass bags so there is no directional conflict and augments maximum potential of Smalls Centralization. The guidelines are as follows: 1) No bypass is suggested from stations to non-service required hubs and transfer points. 2) Origin stations should build destination station bags only if sufficient density exists. Guideline is 40 packages minimum ADV for building overnight or mainline hot station direct bypass bags. In mainline cold lanes, origin stations should only build destination station bags if ADV reaches 100+ packages/day. 3) Origin hubs should build destination stations if average daily volume exceeds 100/day. In cases where eligible destinations outnumber usable smalls bins, actual service trends and lane slack should be used for selection of destination stations. 9/16/23 - Phase three (August 2023) increased the total SC volume again by 21K ADV. This increases total ADV for Smalls Centralization lanes to 64K/day, which comprises 3.3% of all O-D pairs and 5.2% of all smalls volume. Although the potential lane reports can be generated and distributed centrally, local engineering knowledge is required to vet the individual destination feasibility. There is still one market with significant potential opportunity (CHIN/RLTO) and one market with an automated smalls sorter that has been deemed unusable by local operations (ATLA/MARI). The CHIN/RLTO market should be submitted by WE 9-30. We are maintaining 90K as the optimal possible Smalls Centralization ADV. Our realistic target for full implementation is 85% of the theoretical 90K, or 76.5K. We are currently at 64K, or 84% attainment. 7/13/23 - Evaluated impact of Phase 2 rollout. Took multiple weeks in June/July and compared to pre-rollout in early May. To ensure overall smalls increases in OTS% were not incorrectly attributed to SC, I pulled total smalls OTS% performance for comparison. SC lanes, with the addition of phase 2 lanes, improved from 90.98% to 93.41%. Phase 2 lanes were the driver of this improvement. Overall smalls OTS% only improved by 0.95% (96.09% to 97.04%). So over the same time frame, SC improved 2.43% in OTS performance, or 2.56 times the performance of all smalls (90.98% to 93.41%). 6/30/23 - Project basically completed 6/15/23 - Phase 2 O-D pairs uploaded into the Lane Service Dashboard 4/17/23 - Full update Smalls Centralization Dashboard Active on 4/2/23 • Smalls Centralization segregation functionality active in Lane Service Dashboard maintained by the Service Assurance group. • Created and distributed training material and job aids to all regional engineering support. • Reviewed functionality and process on two Network Planning calls and during an NRD staff meeting. • The approved Smalls Centralization plan will be exclusively updated by Dan Jacobs and/or myself. Current Smalls Centralization Flow Plan Compliance completed on 4/ | K: L5 | Completed | L5 | 2022-02-01 | 2023-07-21
Business Only Initiative: FXG 2-Day Service Improvement - Root Cause and Cor | 25592 | 8890 | Business Only Initiative | SE - Tech | Service | Rick Harball, Dan Jacobs | On Track | 4/2/2025 - Weekly team meetings are in pace and continuing. Have a sub team lead and sub team leding a weekly call for the West Division and now have same for the East division. We have had 4 additional lanes graduate for the weekly reporting call in March and are now at 60 graduated lanes since team call started. We are focusing as well on the changes in Sunday eligible service and the hold to fill dispatch rule changes to see what impact it has on the service results. 11/25/2024 - Copy of notes sent reviewing the team initiative, success, and details on KPI's measured. The goal of the 2 Day service team is to improve the companies On-Time service results in the 2 Day service product. The team looked at daily service failures and impact and found that Monday package pick up was the largest day of the week and as well had the largest number of failures from an On Time service measurement as well as a raw package impact. The team then identified the top impact Origin District to Destination District service lanes from a On Time service percentage and raw package failure count from Monday pick up. The team also identified the top 3 Automated Stations in each region that had the largest impact to On Time Service and raw failures in 2 Day service. The team holds weekly calls with these impact Stations to review results, and improvements as well as review the Action plans that they have identified as gaps to improve service results. Once a District-to-District Lane or Station has achieved the current company service goal for 3 of 5 running weeks they are graduated from the call and the next largest impact lane or Station will replace them on the calls and responses. The money step goal of the team was to have 50 of these top impact lanes graduate and achieve the service goal. The team also has put together a list of Best Practices that we gathered from the action plans of the team and what improved the results. These practices are posted and shared with the field and are part of the process teams use when they first join the call to help their local process and results. So far, we have had 55 District to District and Station outbound top impact lanes graduate by achieving the company service goal, and we have a Best Practices document for the field to use to continue to drive improved results, these are attached to the plan in the Associated Request tab. Details on each KPI. KPI-1. Total Ground On-Time Service results and goal for the month. KPI-2. Total company 2 Day service results and goal for the month. KPI-3. Measurement of 2 Day team holding active weekly meetings with the field teams and 2 Day team lead focus meetings. KPI-4. Number of District-to-District Impact lanes and top Outbound impact that have achieved the company On-Time 2 Day service goal for 3 of 5 running weeks. KPI-5. Best Practices. This is that the formal Best Practices document has been shared and posted and with ( how many ) of the 49 Districts in the Surface Operations network. KPI-6. 2 Day partials compared to all partials. Increased cost was a concern of the team, and we did not want to incur additional cost to the company by having the field operations move additional partial loads against dispatch rules to improve service results. We are tracking the number of partial trailers dispatched in the 2 Day lanes against the total number of partials dispatched company wide to measure that we are not increasing costs to improve service. 10/29/24 - Successful move from Wave format to Plan view. Team is continuimg the weekly calls and follow up with the field teams on their action plans. We have graduated 1 more lane since the last update and are at 52 graduated lanes currently. 10/7/2024 - The team has hit the initial milestone goal of 50 lanes graduating to the approved level of service. We actually hit 51 graduated lanes with the data from last Monday. Based on this milestone achievement and the team having completed, posted, and shared | K: L5 | Completed | L5 | 2023-03-27 | 2024-10-31
Business Only Initiative: Last Mile Optimization Service Level Improvement | 19141 | 8892 | Business Only Initiative | SE - Tech | Service | Ryan Day, Dan Jacobs | On Track | **March 2024 Update** In January 2023, this project was established with the original intent to match service levels for Ground delivered LMO volume and Express deferred product offerings. Over the course of the last 13 months, LMO MBG service levels have risen from 94.4% to 97.4%. LMO NSL has risen from 91.0% to 95.9%. Express deferred service has hovered steadily around 98.6% with NSL around 96.6%. In recent months, the Ground Pod has re-defined goals to match Express deferred NSL to LMO MBG NSL. There are nuances (documented below) with MBG service level measurement differences and we believe NSL is a better metric to measure success. Ground NSL sits .7 percentage points below Express deferred NSL. The gap has been as small as .3 percentage points in October 2023. However, LMO NSL has been sustained above 95.5% each week during February. Outside of holidays and NSD events, the consistency of these metrics is at an all time high. All milestones have been completed in Wave. Service results are consistent, but action plans are still being developed to improve processes. (Action plan slide attached) This project will be moved to L5, but the goal of matching NSL levels is still a priority. **Nuances of Express deferred MBG compared to Ground delivered LMO MBG:** 1.Most LMO volume is attempted at least one day early, so even if the customer is not available, it still delivers on the second attempt on time / as an NSL success. More detail on why this is happening below. 2.The percentage of signature-required volume in LMO is lower than in the general E2 and XS population that FXE delivers, so fewer LMO packages are likely to have “customer not in” scans. We aren’t sure why this is the case (did we select geographies with lower signature requirements for LMO?), but it’s a fact. 3.There appear to be status codes, such as weekend code 11s applied by QA, that are not mapped correctly to FXE scans. The result is that some volume is not getting “excused” status in MBG as it should be. Regarding early attempts/deliveries: FXE delivers about 30% of the XS and E2 volume at least one day early, while FXG delivers over 50% of the same products from LMO at least one day early (with respect to the FXE commit). John also quantified that about 70% of FXG status code LMO volume still being delivered on-time. Day-of-week analysis shows that this is mostly happening on or around weekends. Putting these facts together, we hypothesize that FXG is setting commits on LMO packages at the point of handoff without knowledge of the FXE commit date. Because FXG treats weekends as potential delivery days and FXE does not, many of the FXG commits are earlier than FXE commits on the same package. For example, an LMO package where the FXG commit is on Saturday vs. the FXE commit on Monday. FXG is attempting the volume on the FXG commit day (Saturday) and either successfully delivering early or, if the business is closed, they are putting a status code on the package and delivering it on Monday, which is still on time for the FXE commit. This scenario also explains why we would see a lot of code 11s on weekends for FXE LMO volume, and thus it is important if the code 11 is sometimes not being mapped. We have not rigorously quantified the effects of these three things, but I believe the main driver is early delivery / attempt, followed by fewer signature-required shipments (we recently quantified resi ASR shipments have a 15 – 20% “customer not in” rate), followed by some scan mappings failing. All that very plausibly leads to a situation where NSL is at parity but MBG has a small persistent gap. **November 2023 Update** LMO NSL delivered by Ground and Express deferred NSL are within a quarter point. We will use the next three months to ensure service levels remain sustained. Per domain lead and initiative owner, sustained levels have been met and initiative should remain on-schedule and moved to L4. 1ST COLUMN - WEEK ENDING DATE 2ND COLUMN - DDI NS | K: L5 | Completed | L5 | 2023-01-02 | 2023-11-17
Business Only Initiative: Total On-Time PM Sorts (TOPS) - Improve On-time St | 6830 | 9059 | Business Only Initiative | SE - Tech | Service | Jason Lish, Sandeep Dhaliwal | On Track | 2024-04-03 March KPI Results: TOPS Reporting is currently under repair due to the changes in Management hierarchy and District Realignment. Reporting for March KPI's is currently unavailable. | K: L5 | Completed | L5 | 2022-11-09 | 2023-06-01
Business Only Initiative: Field Ops Analysts Service Training and Education | 8254 | 9069 | Business Only Initiative | SE - Tech | Service | Dan Jacobs, John Miklos | On Track | 11/17 - Work that has occurred since L4 - This documentation has also been uploaded as an attachment in Wave: In late October, the Service Assurance team led a Service Education campaign. The purpose was to inform and educate FXG operations of peak-centric service topics as well as key dashboards and how to use them. Two live demonstration meetings were held where each member of Service Assurance presented on a specific topic for 7-10 minutes. The two calls were attended by 225 field management members – DMDs, MDs, Metro Territory Managers, Linehaul Senior Managers, Field Ops Analysts, and Engineering Specialists. The topics covered included – Proper weather entries, proper LPSAP usage, accurate SRI entries, Lane Service Dashboard, Service Recap Dashboard, LMO Racer Tool, Daily Service Insights Dashboard, and Code 85 dashboard. In order to ensure all field management teams grasp these topics, the Service Assurance team recorded live voice-over videos of the demonstrations and uploaded to the Service Education site. Service education topics have also been included as highlights in weekly Focus on the Four communication. The Service Education site will continue to be the central location for educational topics. Below is a table that shows site usage statistics by week ending date. An increase of users was seen in August, after the initial communication was sent, as well as in early November after the Service Education campaign was conducted. First number indicates average unique viewers per day. Second number indicates average # of site visits per day. All milestones have been completed and site users have increased steadily over the past three months, which is why this initiative is being submitted to L5. Jul125287 Aug133357 Sep139352 Oct138389 Nov145400 8/31 - Submitting initiative to L4. Here is the work that has been completed. This has also been added as an attachment in Wave: Service Reporting •Daily Service Insights PowerBI Dashboard has been completed. oThe Daily Insights Dashboard User Guide has been uploaded to Wave. oOn 8/21, the dashboard was communicated to all management levels – FOAs, DMs, DMD, VPs oThis team also made changes to the Lane Service Dashboard to include smalls centralization, mainline hot flag, display economy volume. •This dashboard has not yet been widely adopted, but we will continue to push the usage during the Evaluate stage of this project Service Education When this project was established in February, we originally set out to create an onboarding service document for FOAs upon hire. However, after the Service Education sub-team was created, we found it more beneficial to update the Service Education/Playbook site the Service Assurance team owns. Benefits: •More interactive service education instead of a PDF •Easy to add and maintain topics. •University assistance for video education would not be required. “Micro Learning” sessions were created on the Education site. On 8/28, the following communication was sent out to all management levels: The Service Playbook located on the Service Education SharePoint site has recently been updated to include additional service topics. This work was completed as part of the Service Education and Reporting Drive initiative. The intent of this communication is to raise awareness so that the site can be used as an onboarding tool for new employees and those wishing to expand their service knowledge. This site will be a continual work in progress, so please direct questions on playbook subject matter to your region’s service mailbox. Please send ideas for additional topics or new content to Naomy Ibarra. The Service Playbook content can be broken into three sections: Service Basics Service Basics – Full circle of service, hub sorts, helpful definitions, root cause, and facilities overview Service Goals – FY24 priority metrics and KPIs FAQs – Various service questions and answers that the Service Assurance team often receives | K: L5 | Completed | L5 | 2023-02-27 | 2023-12-29
Business Only Initiative: Service Measurement Back End Systems Accuracy | 8255 | 9071 | Business Only Initiative | SE - Tech | Service | Dan Jacobs, John Miklos | On Track | 11/7 - Work that has been completed to reach L5 status -LPSAP permanent entries have been checked monthly to ensure start times prior to the outbound sort (5PM) are not entered. If entered a note is sent to the field and the entry is removed. -LPSAP permanent entry requirements were reviewed with 225 field management members during Service Education campaign. -Weekend advantage site remains updated to reflect new shipper enrollments. -Tier 1 and tier 2 accounts that were not enrolled in weekend advantage were submitted to customer support teams. Feedback was given and <10 accounts were added. -CLS job aid has been updated and training with the Service Assurance team has occurred during weekly calls. Extensive training is still an area of opportunity. -LPSAP decision tree was highlighted again during Service Education campaign in October. 225 field management members joined. -Hub area scheduled service matrix was updated with ATLA/MARI to DALL/FTWO/HOUS identified as mainline hot. -LPSAP user roles have been audited. o250 names have been added to the User role. These are people that only have tier1, Admin, or Approval roles and wouldn’t be able to add LPSAPs. oRemove Tier1 and Admin access to eliminate confusion. Users will still have the ability to enter LPSAPs. oResolver access – There are 529 individuals not in IT or Service Assurance that were audited. oA list is being sent to Managing Directors pre-peak, asking them to select users that should still have approval rights in LPSAP. Eliminating non-MD approval roles should help reduce the number of LPSAPs that are entered and not thoroughly reviewed. 8/31 - Money step was been completed. Bulleted list of the work that has occurred during this project. This is also uploaded to Wave as an attachment. Work that has been completed to reach L4 Status: Weekend Advantage https://myfedex.sharepoint.com/teams/gdGDOPR/MondayRes/SitePages/home_2019.aspx •Weekend advantage site has been updated: oChanged language to make weekend advantage clearer for sales oDeleted non-relevant or outdate information. Updated links oUpload weekend advantage footprints by hub on 8-18 oSetup a weekend advantage auditing process. Information sent to hub and district managers on 8/30 to verify footprints and look for additional opportunities. New stations will be added to weekend advantage week ending 9/15. oTier 1 and tier 2 accounts that were not enrolled in weekend advantage have been submitted to customer support team for further investigation. oCLS job aid has been updated and training will occur during the L5/evaluate stage of this project prior to peak. oPresented pros/cons of removing weekend enrollment to leadership, however the operational changes outweighed the administrative benefit. Decision to not move forward with removing weekend enrollment was made in early August. •LPSAP auditing process has been established: oIn early March, all permanent LPSAPs with zero origin stations were deleted. Also during this auditing process, we removed all permanent LPSAPs with a start time prior to 4:30PM. oThe service assurance team setup a weekly query to capture all of the LPSAP entries that were made the previous week. During the months of June and July, messages were sent to the field asking for proof of documentation when uploading a permanent LPSAP. This audit resulted in a 50% compliance rate. oIT was made aware of the failed LPSAP compliance audit. To decrease non-complaint LPSAPs, the Service Assurance team requested a modification to the LPSAP user interface. Once the IT work is prioritized, documentation for permanent LPSAPs will be required. Sales, shipper, or DM approval for permanent LPSAPs will be a required upload field in the LPSAP UI. oIT was also contacted to change the LPSAP UI to limit the number of early LPSAP entries. A start time prior to 6PM will no longer be allowed once the IT work is prioritized. oOn 8/31 another round of LPSAP audit occurred. FOAs we | K: L5 | Completed | L5 | 2023-02-01 | 2023-11-30
Business w/ Tech Initiative: USGO AM Sort Alignments to System Form | 8264 | 9077 | Business w/ Tech Initiative | SE - Tech | Service | Sandeep Dhaliwal, Richard Wooten | On Track | 12/4 Week - Focus is on the new AM Sort Dashboard FTE Reduction POD. This project will be part of that team's discussions. | K: L5 | Completed | L5 | 2022-11-23 | 2023-05-31
Business Only Initiative: FXE Freight Service Improvement | 8267 | 9082 | Business Only Initiative | SE - Tech | Service | Tom Barry, Forrest Smothers | On Track | 8/30/24 SERVICE/WDL •MEMH Freight Canopy influenceable WDLs continued a downward trend over the last two months oThere was a slight adjustment to last week’s average daily WDL figure, but it is still well below June and July averages •There have been some issues with late flights this week so numbers may increase over recent weeks •H22 (Hub Overlooked) WDLs have gone from 104 ADV in June to 39 ADV in August, representing a 63% decrease •Overall US Domestic Freight Service Levels (MBG & NSL) are higher FY25 to date compared to FY24 oBoth MBG & NSL were above 90% for the week ending August 23 •Forrest shared a chart showing Domestic Freight MBG service performance over the last 10 years oFY20 was the highest overall year with a total MBG service level of 96.6% and F1 MBG service level of 94.9% •Aircraft freight palletization rates out of MEMH remained above 70% for two consecutive weeks! BZ 8/21/24 - SERVICE/WDL •MEMH Freight Canopy influenceable WDLs have continued to maintain positive momentum for six consecutive weeks •There has been a clear trend since early July in reduced WDLs attributed to MEMH •A similar positive trend is observable in overall US Domestic freight service levels which are heavily influenced by MEMH performance •MEMH improvements are the result of the convergence of multiple factors including Ops focus and execution, Freight Canopy decongestion, and increased palletization of freight •The aircraft freight palletization rate for MEMH increased for the fourth consecutive week to finish at 70%! That’s a 15 percentage point improvement from mid-July’s figure (55%). BZ! FREIGHT CANOPY LAYOUT •Results of the recent modeling and simulation suggested that major changes to the canopy layout and workflow would likely provide marginal, if any, benefits •The modeling exercise did provide guidance on smaller potential areas of optimization, such as zone balancing, which are being evaluated and incrementally applied •The largest recent modification to the layout was moving the Canada and Mexico outbounds closer together to expediate canine inspections. Early indications are that this is having a positive impact. oProcess to apply stickers to freight to verify canine check is in development oOther international buildup positions are being evaluated for location change that would result in similar efficiency improvements •The opening of the Swinnea facility has also had a positive effect in decongesting the IPFS area •The preferred future state of Freight Canopy operations would be the elimination of the “short drop” and moving only one piece at a time •The modeling indicated that elimination of the short drop is achievable, but may require slightly more forklifts and operators would need to be upskilled FORKLIFTS & EQUIPMENT •MEMH Freight Canopy forklift availability has hovered in the high 60% range for the past several weeks •GSE has been investigating root causes of newly out of service forklifts for the past several weeks and providing feedback to MEMH Ops management on instances of operator-caused incidents •Many recent forklift issues are related to empty/missing fuel tanks and operators running over debris, both of which are usually preventable oACTION ITEM: MEMH Ops management, please review the GSE root cause analysis and share preventive measures with your teams •The replacement of thin forklift blades with thicker blades to help reduce damages was raised oPer a discussion from several weeks ago with GSE, an Engineering analysis is needed to justify the replacement of all forklift blades oOP&E is not familiar with the analysis that is required and whether that would fall within their purview oACTION ITEM: Suman to connect with Mike King and Russell to help clarify requirements GENERAL •Andy Grantham reviewed results of the MEMH Heavyweight Misflow report for 8/21 o188 wooden skids were misflows the previous night; 29 skids were domestic US oA single flight (FRA-MEM Flight #000 | K: L5 | Completed | L5 | 2022-11-30 | 2024-01-05
Business w/ Tech Initiative: Enterprise Disruption Reporting | 8274 | 9083 | Business w/ Tech Initiative | SE - Tech | Service | Elizabeth A. Bergin, Kerri Lindsey, Shyam Mohan, McKenzie Worden, Theresa D. Wilkins | On Track | Information from WAVE application: 6/14/23, Milestone 9933 is late. Awaiting TCH and portfolios to greenlight. 6/8/23, Milestone 9933 is late. Awaiting TCH and portfolios to greenlight. 5/31/23, Milestone 9933 is late. Awaiting TCH and portfolios to greenlight. 5/24/23, Milestone 9933 is late. Awaiting TCH and portfolios to greenlight. 5/10/23, Milestone 9933 is late. Awaiting TCH and portfolios to greenlight. 5/3/23, Milestones 9933 is late. Awaiting TCH and portfolios to greenlight. 4/26/23, All milestones are on track. 4/19/23, All milestones are on track. 4/12/23, All milestones are on track. 4/5/23, All milestones are on track. 3/28/23, All milestones are on track. 3/22/23, All milestones are on track. 3/15/23, All milestones are on track. 3/8/23, All milestones are on track. 3/2/23, All milestones are on track. 2/22/23, All milestones are on track. | G: L3 | Active | L3 | 2023-03-15 | 2026-11-30
Business w/ Tech Initiative: Last Mile Optimization (LMO) Visibility for Root C | 8279 | 9087 | Business w/ Tech Initiative | SE - Tech | Service | Mario Magparangalan, James Woodard | On Track | February 24, 2023. All milestones are on track. March 15, 2023 - - All milestones are on track. - Working RACER dashboard completed March 12. March 19, 2023 - - User Acceptance Training & Testing completed March 10 and March 13. - LMO Origin logic enhanced with addition of location specific handoff time FXE to FXG. March 22, 2023 - - User enhancements and recommendations centralized under LMO Core for consolidation and prioritization. LMO Core will coordinate with Dataworks on updates to LMO Racer. March 27 - - Milestones for Completion of compliance report for leadership and job aid/instructions/e-acknowledge delayed to March 31, 2023. Recent enhancements to LMO Racer still to be implemented and will be updated in instruction/job aid and has affected compliance report. April 3, 2023 - Milestone for Risk Compliance Reporting for review and follow-up by leadership delayed due to delay in second level of UAT. Start date and completion date adjusted accordingly. Training is scheduled for April 10 April 10, 2023 - Delay launch of Risk Mitigation Strategy to April 16 due to LMO Racer Training scheduled from April 11 - 14. - Delay development of Build Risk Compliance Reporting to April 16 due to LMO Racer Training scheduled from April 11-14. May 22, 2023 - LMO Racer completed on time (May 7) and in use. - Eight (8) training sessions completed for FXE and FXG o# of individuals trained: 2047 (FXG: 1847, FXE: 200) o# of locations represented: All FXG Districts, All FXE DDI and LMO Markets. Additionally the following staff support organizations participated: FXG – Ops Analysts, Change Management Office (CMO), Engineers. FXE: Operations, Planning & Engineering (OPE), Global Services & Quality Assurance (GSQA). - Effective April 27 LMO Service Daily Service Update communicated daily to stakeholders (SVP, VP, MD, Senior Managers, OPE for both FXE and FXG). - Initiated review meetings with DDI and LMO focus markets to identify root cause of service failures, establish corrective action and implement plans. June 1, 2023 Continue enhancements to LMO Racer. - Added visibility to outbound shipments on May 31. June 12, 2023 SSP locations added to LMO RACER for inbound and outbound shipments. July 17, 2023 Initiated enhancements to SSP locations in LMO RACER (SSP Failure Insights). Will use MSP as test market. July 27 2023 November 27, 2023 Re-deployed SSP Failure Insights to LMO RACER on November 15. Improvements achieved with assignment of failures were as follows: - Correct failure category - 93% - Correct failure location - 89% - Correct failure cause - 89% April 10, 2024 LMO Racer renamed to Multi-Network Racer (MNR) in February 2024 Enhancements completed for MNR: - E-SSP failure insight added for April 2024 - Tri-Color failure insight added for April 2024 Overview/Training on enhancements conducted on March 8 with NOSS team (Network 2.0 Operations Service & Support), (22 participants) Overview/Training on enhancements conducted March 25 and 26 with FXG Field Operations Analysts and Engineering Specialists (382 participants) | K: L5 | Completed | L5 | 2022-11-16 | 2023-05-12
Business w/ Tech Initiative: Enterprise Commit Engine |  | 91523 | Business w/ Tech Initiative | SE - Tech | Service | Kerri Lindsey, Sarah Mertz, McKenzie Worden, Shyam Mohan | On Track | 12/23/2024 - Completing LBC | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Enterprise Service Engine |  | 91538 | Business w/ Tech Initiative | SE - Tech | Service | Kerri Lindsey, Sarah Mertz, McKenzie Worden, Shyam Mohan, Alexander King, Theresa D. Wilkins | On Track | 12/23/24: Completing LBC | E: L2 | Active | L2
Business Only Initiative: Self-Service Reporting |  | 91544 | Business Only Initiative | SE - Tech | Service | Daniel Stolick, Kerri Lindsey, Sarah Mertz, Sean Cahalan | On Track | 4/20/2026 * Tera report is still requiring back end data to be set up in order to run the report. * This week Office Hours starts with Wave 1 and Wave 2 reports being served up to the Field * Wave 3 and Wave 4 reports should have been moved to Production for us to test them * The IMAGE roles should have been created and will be shared with the Field Team * The Sharepoint site must be updated with connection to reports. * Also must have all training documents and information on the site for the users. * The first week of training will be basic information and accessing reports. * The following training will be much more detailed hitting items like Power Automate which will take several weeks of training 4/13/2026 * Geo report was completely tested and finalized. * Tera data still requires being built in order to complete the report * We have 6 reports that need tested and another 16 that require full UAT testing * Wave 1 and 2 reports were moved to Production, but they still require testing in Production * After they have been fully tested they will then be moved into Sharepoint for usage * The training document for the field to use the reports is in progress and must be done by end of week. * It fell behind and the reports in Production fell behind based on people being out of office * We will then move Wave 3 and 4 to test next week to move into Production * Model 1 has adjustments that require being done and still requires full testing. * The idea is finalizing the model full testing in order for it to be prepared for May usability * We agreed that SSOT model should be built and Jim is handling it. * The goal is to have Field go into reports next week after training and start that in the Office Hours 4/6/2026 * Tera data report is waiting on Leo to complete the back end * Geo reports are completed and now awaiting full testing to be done and fully finished * There is one other reports from SS that has to be cleaned up that should be done this week * We are moving Wave 1 and Wave 2 reports into Production to be ready for the field to start using. * The goal is to be done fully testing those reports this week and move those into production and Kristin to add those to the Sharepoint site * We still have to get the IMAGE request to be fulfilled and done to access the reports. * The Office Hours is set up but no Field people have been invited because we have just moved the reports to Production to be tested. * Model #1 is being completed by Leo this week * We are asking all Power Users to fill out the BO validation for the Testing to match against the model. * Model #1 should be completed by end of week and the validation will start on it next Monday 3/30/2026 * Geo reports seem they are finalized and are in final testing to see if they are complete. * The team is still waiting on Tera data to complete that report in Shipper Solutions * There is an Active Network report that must be checked for errors. * Model 1 is to go into testing this week for final clean up * The strategy is to roll out Model 1 to Service team along with other models in starting of May * At the starting of June Model 1 will roll out to the field * The Field will be required to go through training prior to being given access to the model * There will be Office Hours to cover reports and Models * The Service Team will be testing 10 reports in Production this week and rolling those out to the Field next week * That week we will test more reports for Wave 2 and roll those out to the Field * The Project Plan is now in full effect and we are following it to move through the project. * 3/23/2026 * Geo reports should be completed, there is additional testing required to complete them and finalize. * Tera reports requires the back end data to be built and for the connection to be made to the data. No time given when this will be done. * Continuing to build reports there are some large ones that are being made right now slowing progress. * The 7 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-03 | 2026-02-27
Business w/ Tech Initiative: Service Reports Updates Interface |  | 92362 | Business w/ Tech Initiative | SE - Tech | Service | Sarah Mertz | On Track | Planned DW production start date: 3/10/2025 Planned DW MVP1 date: 9/10/2025 Planned DW L4 date: 12/31/2025 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Enterprise Failure Analysis |  | 92364 | Business w/ Tech Initiative | SE - Tech | Service | McKenzie Worden | On Track | 20206-01-28: feature doc and target state design in progress. non prod infra and ADO pipelines done. may need additional datasets because SSOT may not contain everything they need. may use svm. 2026-01-07: team has been onboarded and current state analysis and non prod infra setup in progress. 1/17 - updating business case | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2026-08-03
Business w/ Tech Initiative: Enterprise Service Exceptions |  | 92367 | Business w/ Tech Initiative | SE - Tech | Service | Kerri Lindsey, Sarah Mertz, McKenzie Worden, Shyam Mohan | On Track | 1/14/25: Completing LBC | E: L2 | Active | L2
Business w/ Tech Initiative: Network Performance Metric MVP |  | 92370 | Business w/ Tech Initiative | SE - Tech | Service | Usman Alavi, McKenzie Worden | On Track | TBD | E: L2 | Active | L2 & CCH
Business Only Initiative: Sort Down to Launch (D2L) | 15910 | 9251 | Business Only Initiative | SE - Tech | Service | Brian Ellis, Mike Stambaugh | On Track | 08/30/2023 - The Memphis Hub night sort launch and field arrivals continue to show vast performance improvements over our baseline. For the first time in 24 weeks, the average flight in time beat the average flight out time. | K: L5 | Completed | L5 | 2023-01-02 | 2023-05-11
Business Only Initiative: International Service Dashboard |  | 92643 | Business Only Initiative | SE - Tech | Service | Jean Bachman, McKenzie Worden | On Track | 02/27: Development of views and required metrics is ongoing and will be prepared fr when Dataworks can assign to be worked | E: L2 | Active | L2
Business w/ Tech Initiative: Customer Data Exchange Express Enablement |  | 93314 | Business w/ Tech Initiative | SE - Tech | Service | Megan Aurin, McKenzie Worden, Alexander King | On Track | 1/23/24 - added to L1 | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Enterprise Network Monitor | 18010 | 9378 | Business w/ Tech Initiative | SE - Tech | Service | Usman Alavi, McKenzie Worden, Barry Mobley, Christian Piroli | On Track | 2026-04-22: Working on Upcoming Enhancements (UTP), Filter corrections, Executive enhancements, Tracking ID Filters. 2025-06-30: Discussed priorities for peak, nice to have functionalities which can be deferred beyond MVP1. Identified how we can eliminate need for the SVM table. 2025-06-16: on track 2025-06-09: on track | G: L3 | Active | TEMP L3 - Enter L3 | 2023-03-01 | 2026-08-31
Business Only Initiative: International Freight Root Causing |  | 143630 | Business Only Initiative | SE - Tech | Service | McKenzie Worden | On Track | 11-13-2025: No major updates on dwell. Xianbin moving teams so need to figure out who will take over route compliance. 10-28-2025: IMWP not seeming like a reliable source for route to determine route compliance. Xianbin/George to update next week 10-23-2025: On track. Devel still underway. Dwell ~ 90% done, just finalizing consolidating locations. 10-10-2025: On track. Devel still underway. ~80% complete with dwell. 09-17-2025: Learned that DW team is working on similar metrics. Set a meeting for 9/20 to align with them and determine any overlap to ensure no duplicated work between the two efforts. 07-17-2025: filling out LBC | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-15 | 2026-02-27
Business w/ Tech Initiative: DREAMS Report |  | 111229 | Business w/ Tech Initiative | SE - Tech | Service | Jackie Kerscher, McKenzie Worden | On Track | On track | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: LAC: Enabler: Improve LAC scan compliance and adop | 23394 | 8289 | Business w/ Tech Initiative | SE - Tech | Service | Flavio Castro | On Track | Scan Compliance Reporting Tool (PowerBI) has some functionality and can be used by locations in a limited mode. Tool still needs to be updated with additional features and filters. New training sessions need to be conducted throughout LAC. As of today 10/24/2023 this DRIVE Initiative is on plan for implementation in the dates included in the Milestones section. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-05-16 | 2025-12-19
Business w/ Tech Initiative: Flightwatch |  | 163764 | Business w/ Tech Initiative | SE - Tech | Service | Elizabeth A. Bergin, McKenzie Worden | On Track | 2/13/26: Updated LBC to include the capability of identifying eligible disruptable flights and automatically creating Service Disruption Requests in Planview Work ID 0104620. 12/08/25: Added soft benefits commentary to demand description, $12.9M value to appropriate financial field and backup spreadsheet to contents folder 11/19/2025 uploaded supporting documentation 11/05/2025: updated LBC 10/21/2025: updated LBC | E: L2 | Active | L2
Business w/ Tech Initiative: LAC-BR-BRECO-BDE: Enable freight service (F3) |  | 127965 | Business w/ Tech Initiative | AMI - Brazil | Americas International | Alzira Baptista Borges, Natasha Barbosa Xavier, Tatiana Farias | On Track | Jan 20th 2026 - canceled as per Sandra Parras' Instructions From Sandra Parras OIC, VPS + ESPM cc FYI Dear BDE Core and Extended Team: With the recent announcement regarding Brazil Domestic Exit, it means the Brazil Domestic Enablement and Domestic Customer Integration (BDE) Project is canceled Some of you have asked me what should be done with the requests in Planview, Onspring and/or PPM as it relates to Brazil DOM or the other portfolios. Below please find a list of the Planview initiatives that should be canceled NLT Jan 31, 2026. A copy of this email should be attached to each initiative canceled. Job aid link: Setting Initiatives to On Hold-Cancel.pdf I want to thank you for all your efforts in the last few years with BDE and I hope we get to work together in the future Any questions please let me know Thanks Sandra Initiatives to be canceled in Planview by Initiative Owner Rationale: BDE project canceled as of Jan 5, 2026 Initiatives where a PDSM should be entered to cancel the request: Enter a PDSM under Enterprise Tools/Planview to cancel request, email to send to Lisa Rolfe with PDSM # entered Rationale: BDE project canceled as of Jan 5, 2026 Sandra Parras Manager, Program Management Office¦ LAC Marketing¦(786) 473-3605 -------------------------------------- 26 Nov 25 - Per BDE PMO Sandra Parras (488838) , this project is on hold until mid Jan 2026. Next steps to be confirmed after that 24 Oct 25 - Waiting for Finance local team feedback about LBC approval 17 Oct 25 - Waiting for Finance local team feedback about LBC approval 09 Oct 25 - Waiting for Finance local team feedback about LBC approval 03 Oct - 25 Waiting for Finance local team feedback about LBC approval 26 - Sep - 25 Waiting for Finance local team feedback about LBC approval 19 - Sep - 25 Waiting for Finance local team feedback about LBC approval 12 - Sept - 25 Waiting for Finance local team feedback about LBC approval 05 - Sept - 25 Waiting for Finance feedback abou LBC approval 29 - Aug- 25 - Waiting Finance feedback abou LBC approval 22 - Aug - 25 - Waiting Finance feedback about LBC approval 15 - Aug - 25 - Pending LBC approval by finance. LBC sent fo Brazil finance (Fred) in Aug 13th and waiting for feedback. Updated LBC on June'24th | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: Canada Post Cartage Agent Harmonization for NW2.0 |  | 88263 | Business w/ Tech Initiative | AMI - Canada Efficiency | Americas International | Shikha Sood, Daniella M. Dias | On Track | The viability of the initiative is in question - hence the hold | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Canada Efficiency Pod-Cartage-ADS & 2 Day Review |  | 157824 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Michael Fenton | On Track | This is no longer active as it is part of the Canada Cartage Elimination-Cartage Elim Model & Pursuit (157827). | C: L1 | Cancelled | L1 | 2025-10-30 | 2025-10-30
Business Only Initiative: AMI-CEP-Cartage-Elimination |  | 157827 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Michael Fenton, David M. McRonald, Dona Manalaysay | On Track | 03/05/26 - Approved Cartage will be splitting off onto its own initiative in order to move this initiative along to L3. Values have been split and new NRB of $23.9 entered into the financal card to move initiative to L3. Reviewed with Domain finance Rob Farr. Submitting for approval. 2/26/26-Unapproved cartage monthly data to Sohum for insourcing cost calculation; YEGR unapproved cartage removed with last day on 2/20; approved cartage model completed and 2 training sessions provided to CANA ES and 2 more to come. 11/20/26-2/3/2026-The team continues to communicate and drive down unapproved cartage at a district level. The new cartage elimination model has been finished and we are now moving ahead with 3 different projects within it. 11/13/25-Pivoting for package volume data for this via ODA Tracker and Code 28 report-we are going to use October data. Sohum Patel from Finance is then going to find the cost per package. 11/12/25 - Meeting between IO and the group that created the Added Capacity Agreement Contracting: Obboarding Guide for Federal Express Canada Corporation. CDA forge scanner data to be monitored weekly for growth as more stations work to get using the LG-036. 10/30/25 - DOA presented their VRS training material to IO and Lead. QPS & FOA are to be provide training WE 11/8. 10/16/25 - Working on the milestone of VRS Process Training with ED FOA to train all QPS in Canada and the QPS then train their respective stations 10/3/25 - Working to address the gap in volume. 9/23/2025 - Starting 9/25/2025 the unapproved cartage report will be sent out; the new Cartage Model is progressing and we have reviewed the first example. 9/18/2025 - Continuing to refine business case, by validating cost per package actuals. 9/11/2025 PC Database made accurate. Unapproved cartage elimination communication 9/15/2025. | G: L3 | Active | L3 | 2025-06-02 | 2028-05-31
Business Only Initiative: Canada Efficiency Pod-Unapproved Cartage |  | 157830 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Michael Fenton | On Track | This initiative is no longer active as it is part of the Canada Cartage Efficiency-Cartage Elim Model & Pursuit (157827). | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Canada STA Manifest Delivery Itinerary Addition |  | 161716 | Business w/ Tech Initiative | AMI - Canada Efficiency | Americas International | Gunter Loh, David M. McRonald, Gwynne Riggen | On Track | ****Add to top 26-Feb-2026: Still in Enter L2, no news. 15-Dec-2025: Enter L2. No updates from Architecture. 28-Nov-2025: submit to L2 (Boo-yah!). Checked T-Shirt = M. 25-Nov-2025: Waiting on req#161761 to clear SL2 before submitting. 13-Nov-2025: Waiting on Req#161761 to clear SL2 before submitting. 07-Nov-2025: Waiting on Req#161761 to clear SL2 before submitting. 31-October-2025: Appended new Enabler information as requested PV Req#161761 AMI-CEP-On-Road-Execution.Follow.up 20-Oct-2025: Updated submission based on POD feedback (David McRonald) -- Base FY25, Required by__, and new link for Architecture doc. 14-Oct-2025: Waiting on L1 Architecture review Note: Unable to link EADD - FRO C1.2 PV#0105121 in the Dependencies tab. | E: L2 | Active | L2
Business Only Initiative: AMI-CEP-Linehaul-Legacy Express Drop/Red |  | 161719 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Manlio Staropoli, David M. McRonald | On Track | **03/31** - Re-entered milestones that had been deleted. Moved Vacouver-Nanaimo task to the "Route Rationalization" initiative. Added task for YYZR-YSBA route elimination. **03/10** - Confirmed actuals for Feb. updated. YQG-DTW run will be eliminated this coming Monday 03/15 YYZ-YQG run is still being run by Exflex and is planned to be replaced by a TSP by the end of next week.. YYZ-YMX, one route was live in February and two more were eliminated last week with the last one coming soon - no firm date yet. **02/25** - YQG-DTW - both drivers have now been hired, meeting with GTS to finalize clearance process for transition to loose-load (from ULD). Expected launch April6 YYZ-YQG-WIND planned launch March 9 **02/12** - 1 Exflex to Monreal is in progress. One more still to be elimnated. Windsor Airtime on-track for end of month implemenatation. YQG-DTW still delayed due to driver hiring process. Targeting change will happen in March. **11/26/26** - One driver has been hired for the YQGA-DTWR run. Ops/HR having some difficulties hiring a second driver (required for backup and contingency) due to low wage and part-time shift. HR considering adding a cross-border premium to the driver's wage to attract more applicants. **10/10/25** - Reviewed with Finance and moved to L2. Vehicles moved to YQG in preparation for the elimination of DTWR cartage agent. Hiring in progress - on track to begin operations by Nov 30. **09/25/25** Discussions in progress with field engineering and Ops to expedite implementation of YYZR-YUT/YUL/YMX lane reduction. Aiming to move April 2026 implementation date to January 2026. **09.15.25** Hiring process started for YQGA-DTWR lane vendor replacement. **09/08/25** Currently completing L1 financials to move into L2 | G: L3 | Active | TEMP L3 - Enter L3 | 2026-05-29 | 2026-05-29
Business Only Initiative: AMI-CEP-Linehaul-Rail |  | 161722 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Sahil Guleria, Richard Davidson, David M. McRonald | On Track | 4/7/2026- Financials for March 2026 updated 3/28/2026- Rail Usage 100% to the projected maximum. 3/21/2026- Rail Usage 100% to the projected maximum. 3/14/2026- Financials for February 2026 updated. 3/7/2026- Rail Usage 100% to the projected maximum. 2/28/2026- Rail Usage increased to 91% of the projected maximum. 2/21/2026- Rail Usage remained at 82% of the projected maximum. 2/14/2026- The Rail usage was at 91% of the projected maximum. 2/7/2026 - Financials for January 2026 Updated and the Rail usage remained at about 91% of the projected maximum. 1/10/26 - CN rail usage back on plan 1/6/26 - Updated Financials for December 2026 12/6/25 - Decrease Rail usage due to weather and delayed service. 12/02 - L1 business case was in CAD. Converted to $1.3m USD at L2. 9/22 - Implmented 5 of 6 lanes, Toronto to Moncton is the last lane to implement due to material handling in the TORO, material handling will be in place 09/26 9/15- Implemented two lanes from Montreal (1 Halifax, 1 Moncton), safety concerns on loading containers on the hub outbound doors, Halifax failed on time service. | I: L4 | Active | L4 | 2025-09-12 | 2025-11-27
Business Only Initiative: AMI-CEP-Linehaul-Route.Rationalization |  | 161725 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Manlio Staropoli, David M. McRonald, Sahil Guleria, Richard Davidson | On Track | **03/31** - Re-entered milestones that had been deleted. Moved Vancouver-Nanaimo vendor replacement task from "Express Drop Red" into "Route Rationalization" initiative **03/10** - Updated Confirmed actuals for Feb. Kitek clear approved. Awaiting installation. Kirkland lake set for Mar. 30th launch **02/12** - Kirkland Lake change. Sales has asked for more time to communcate with customers. Date changed to Apr. 1, 2026. Atlantic Canada - Quite received for Kitek unts. CLEAR is required for equipment approval. Date changed to June 1st. to proved time for clear process. **9/22** - working on L2 submission by end of week **9./15** - no update to report | G: L3 | Active | TEMP L3 - Enter L3 | 2026-06-01 | 2027-06-01
Business Only Initiative: AMI-CEP-Sorts-Execution |  | 161728 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Karan Johal, Matthew Labutte, Matthew Molnar, Arthur Keating, David M. McRonald, Sean Pound | On Track | 9.23.2025 On track for L2 submission, meeting with VP Jeff Tallman tomorrow for approval/review. 10.10.2025 Putting Planview on hold, as the sort execution intiative is being combined with the sort planning intiative to create the Sort Planning and Execution Intiative. 04/0982026 - Cancelling old initiative as clean up when moving Canada Efficiency from Americas International to N2.0 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: AMI-CEP-On-Road-Service.Rationalization |  | 161749 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Nidia I. Ceron | On Track | Moved under parent initiative AMI-CEP-On-Road-Execution.Follow.Up. | C: L1 | Cancelled | L1
Business Only Initiative: AMI-CEP-Admin-Overtime.Reduction |  | 161755 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Leanna E. Smallbrook, David M. McRonald, Luiz H. Gottsfritz | On Track | 01/12/2026 - Status placed to ON-HOLD pending Admin model updates for Canada 09/16/2025 - Sizing is complete. Preparing L2 submission. 12/01/2025 - Sizing changed based on L1 business case to NRB of $2.5 M For Admin OT Avg month OT = 5142 hrs / 50% reduction = 2570/hrs (annual reduced hours = 30,850) Avg Admn pay = $25.50 x 1.5 = 38.26 (OT Pay) x 30850 = $1,180,206 CAD Exchange rate 1.35967 = $868,009 USD Fringe 26.4% = $1,096,839 USD For Ops Leads OT Avg month OT = 4910 hrs / 50% reduction = 2,455/hrs (annual reduced hours = 29, 459) Avg Ops Leads pay = $34.52 x 1.5 = 51.78 (OT Pay) x 29459 = $1,525,387.02 CAD Exchange rate 1.35967 = $1,121,881 USD Fringe 26.4% = $1,417,6385.46 USD Total Opportunity = $2,514,477.44 USD | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: AMI-CEP-On-Road-Execution.Follow.up |  | 161761 | Business w/ Tech Initiative | AMI - Canada Efficiency | Americas International | Nidia I. Ceron, David M. McRonald, Tennyson A. Vaughn | On Track | 03/23/26 - Working on simplified stop count sheet dashboard and process to implement at a few pilot locations. 03/02/26 - Reviewing financials for FY26 to capture savings related to this fiscal year as a separate initiatiave with no tech requirements. 02/12/26 - Working on a simplified version of stop count sheets, data requirements, calculations and output. 01/22/26 - Reviewing the timeline by district to complete WA sph goals for medium/large stations. Continuing weekly reports for the 2 main KPIs. 01/15/26 - Completing FY27 and FY28 KPIs to enter in planview. 01/07/26 - Finalizing review of FY27 and FY28 calculations with Finance. 12/18/25 - Reviewed actual savings with Finance and updated planview. Working on FY27 and FY28 calculations. 11/03/25 - Finalized savings allocation by FY and included supervisory savings based on actual turnover data. 10/27/25 - Reviewing savings allocation per FY with Executive team. 09/22//25 - Finalizing calculations to include leadership wages savings ahead of L2 submission. 09/15/25 - Refining calculations ahead of L2 submission 09/08/25 - Reviewing sizing before L2 submission. | E: L2 | Active | L2
Business w/ Tech Initiative: AMI-CEP-On-Road-Sort.Execution |  | 161764 | Business w/ Tech Initiative | AMI - Canada Efficiency | Americas International | Tennyson A. Vaughn, David M. McRonald, Nidia I. Ceron | On Track | Reviwing sizing before L2 submission | E: L2 | Active | L2
Business w/ Tech Initiative: AMI-CEP-On-Road-Route.Planning |  | 161767 | Business w/ Tech Initiative | AMI - Canada Efficiency | Americas International | Nidia I. Ceron, David M. McRonald, Tennyson A. Vaughn | On Track | 03/23/26 - Working on simplified stop count sheet dashboard and process to implement at a few pilot locations. 03/02/26 - Reviewing financials for FY26 to capture savings related to this fiscal year as a separate initiatiave with no tech requirements. 02/12/26 - Working on a simplified version of stop count sheets, data requirements, calculations and output. 01/22/26 - Reviewing the timeline by district to complete WA sph goals for medium/large stations. Continuing weekly reports for the 2 main KPIs. 01/15/26 - Completing FY27 and FY28 KPIs to enter in planview. 01/07/26 - Finalizing review of FY27 and FY28 calculations with Finance. 12/18/25 - Reviewed actuals with Finance up to Nov25. Finalizing FY27 and FY28 calculations. 12/04/2025 - NRB removed as this is an emable initiative. 03/Nov/25 - Finalized savings allocation by FY and included supervisory savings based on actual turnover data. 27/Oct/25 - reviewing the savings allocation per year with VPs. 22/Sep/25 - finalizing calculations to include leadership wages savings ahead of L2 submission. 15/Sep/25 - refining calculations ahead of L2 submission. 08/Sep/25 - reviewing sizing of the parent initiative for L2 submission. | E: L2 | Active | L2
Business w/ Tech Initiative: AMI-CEP-Admin-Courier.Performance |  | 161770 | Business w/ Tech Initiative | AMI - Canada Efficiency | Americas International | David M. McRonald, Luiz H. Gottsfritz, Aissa Mae P. Villanueva-Taruc | On Track | 09-16-2025 Review with IT, changing status from business with tech to Local Demand. 11-10-2025 Sending another savings review to be evaluated by the DMDs. Admin Model has been updated and informations for a few locations are in StaOps. HRs not allocated and Vehicle maintenance hours are a target for savings as well | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: AMI-CEP-CTP Transition Expense Reduction |  | 185056 | Business Only Initiative | AMI - Canada Efficiency | Americas International | David M. McRonald | On Track | 04/10/2026 -Mar. actuals entered onto Finance card. 03/11/2023 - Initiatve approved to L4. Feb. actuals entered onto Finance card 03/04/2026 - Money step validation uploaded. Submitting to L4 02/24/2026 - Pending TO Finance approval to L3 02/13/2026 - L2 Financials, KPIs and Milestones entered into Planview. Ready for QA review prior to L2 Submissin. | I: L4 | Active | L4 | 2025-06-02 | 2026-05-29
Business Only Initiative: AMI-CEP-On-Road-Performance |  | 191178 | Business Only Initiative | AMI - Canada Efficiency | Americas International | Nidia I. Ceron, David M. McRonald | On Track | ***04/14*** Financial card updated, KPI's added, Money step entered. L2 Financial support file uploaded. | F: SL3 | Active | SL3 SVP Finance Approval | 2026-06-19 | 2026-06-19
Business w/ Tech Initiative: Canada Domestic Ground Hazmat |  | 160144 | Business w/ Tech Initiative | AMI - Canada Revenue | Americas International | Tejas Shah | Some Issues | **10/22/2025** . Initiative status moved to ON HOLD status due to resource constrain. . IO Resource Gap as Meiry Pratas has accepted a role within FedEx (US FXF Marketing) . Awaiting Leadership update on Resouce Gap. **10/3/2025** . Finance and Marketing MDs review meeting on 2/10 . Approved for SL2 submission . Updated Portfolio field. As per Joe Nassar and Lee Anne Pontis, **Enterprise Services HR**T is not impacted at this time. As the initiative progresses into the execution stage, FLC team can be engaged. If any training development or University needs, a Purpe Gateway ticket to require support can be submitted. **9/22/2025** , L1 Template complete for AMI Pod discussion. . Request reviewed by Business Architecture team; initiative considered as Large from Tech side perspective as several backend system and applications are impacted. . Review complete with Finance POD lead. . Follow up with Sales about business pipeline - in progress. ETA 9/23 | E: L2 | On Hold | L2 & CCH
Business Only Initiative: AMI-CA REV- eComm Conversion |  | 162593 | Business Only Initiative | AMI - Canada Revenue | Americas International | Elton J. D'Souza | On Track | 9/16/2025 - Completed initial L1 sizing and drafted Light Business Case with updated $42M opportunity from ~7 lost B2C customers. Next step is to validate assumptions with Finance (cost-to-serve model) and build recapture timeline/pipeline. 10/8/2025 - Finance is still working through individual OI projection calculations (variables being considered - cost savings from wave 1 densification on top of $1.38 cost to serve reduction from efficiency pod and GRI's for each of the 7 accounts) 10/22/2025 - Finance is close to completion on providing updated OI projections, waiting on projected costs for outer years, expected completion early part of next week | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: AMI-CA REV- Residential Delivery Density |  | 162596 | Business Only Initiative | AMI - Canada Revenue | Americas International | Kunal Garg | On Track | On hold until we hear back from ops to identify areas with opportunities | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: AMI-CA REV- Win Back sales plan |  | 162599 | Business Only Initiative | AMI - Canada Revenue | Americas International | Kunal Garg | On Track | 2/172026: Canada VP Bryan Lima's approval to cancel the initiative as not transformational but tactical | E: L2 | Cancelled | L2 Feedback Requested
Business Only Initiative: AMI-CA REV- Reprice Bottom 20% |  | 163259 | Business Only Initiative | AMI - Canada Revenue | Americas International | Jasdeep Grewal | On Track | 4/16/2026 - In accordance with TO efforts to refocus on Strategic Programs, the AMI PMO and ESPM teams recommend that initiative #163259 -Reprice Bottom 20% be cancelled in Planview. Cancellation means that this work will no longer be tracked in Planview and will become a BAU effort. Please review the reasons for cancellation. Reasons in support of cancellation: •Significant reduction in value (<$200K in revenue) •No impact to FY26 (value expected FY27/28) •No IT development required (business-only effort) •Does not impact overall CX (impact is on an account-by-account basis) •Not transformational (regular good practice) •Does not align well to 1 of the 7 strategic programs (Purple Chips) Approved by Manjit Virdee. 3/13/2026 - 6 accounts finalized under reprice initiative. 1 account is not shipping with FedEx. Next steps is to follow up with removing any pricing on account no longer shipping. 3/6/2026 - call set up to review accounts with MD on 3/10/2026 2/27/2026 - analysis complete. Compiling a summary of the accounts to review with Manjit Virdee. 2/20/2026 - Analysis on track. 2/13/2026 - Analysis on track and progressing well. 2/6/2026 - progressing well and on track with detailed account review to determine profitability. Target completion 3rd week of Feb. 1/30/2026 - progressing on track with each account analysis to determine actual proftiability of account. 1/23/2026 - analysis in progress 1/16/2026 - 16 accounts are now being reviewed in detail including detail cost assessment and assessment of full book of business by product, type of business and volume distribution/metrics. 1/9/2026 - conversed with Finance and Manjit on the financial cards and the approach. Direction is to do deep dive on shortlisted accounts to determine accounts that are to be actioned for repricing. Initiating review of accounts with team. Estimate a few weeks to complete. 1/5/2026 - met with Jason on financial card updates before holiday. To connect with Finance this week on the line items fo rthe forecast and finalized the financial cards for next week's update 12/15/2025 - Will schedule meeting by EOW on financial card updates (Jason to schedule). Line items require finance input. Targeting deep dive in January. Need clarity on Jan 18th deadline for L4 (Jason validating with ESPM). 12/10/2025 - Finance lead approved initiative. L3 Updates in progress for adding milestones and updating risks. 12/1/2025 - Entered L3 gate 11/25/2025 - SL3 Finance review completed with Rob Farr. Updated business case as per Finance feedback. Customer list reviewed with Sales leadership. 11/21/2025 - QA readiness check for SL3 submission with QA expert. Performed SL2 and SL3 readiness check and confirmed actions closed based on EPM feedback. Approved to submit to L3 11/19/2025 - SL3 submission with feedback requested. 11/19/2025 - CCH review with Karen McConnico - Confirmed no impact to the Commercial value prop during CCH triage with CCH lead. 11/14/2025 Submission of L2 11/11/2025 Process of completing business case for L3 10/24/2025 Completing L2 phase this week. 10/03/2025 Finance and Marketing review completed with Rob Farr and Manjit Virdee. Completed L2 submission. | G: L3 | Cancelled | TEMP L3 - Enter L3
Business Only Initiative: AMI-CA GAF Growth |  | 163265 | Business Only Initiative | AMI - Canada Revenue | Americas International | Tejas Shah | Some Issues | 10/29/2025 . Initiative status moved to L2 and to ON HOLD status due to resource constrain. . IO Resource Gap as Meiry Pratas has accepted a role within FedEx (US FXF Marketing) . Awaiting Leadership update on Resouce Gap. ***10/10/2025*** . A PDSM ticket has been opened to modify the demand type as Business Only . Attached supporting documents {Business rational and assessment; L1 Template Finance review) ***10/08/2025*** . Received feedback from P&E about Technology impact. As per P&E (Elvin Tai), the efforts for this initiative don't require IT development work. . Working on updating the initiative as "Business Only' in PV. . Finance review prior to SL2 submission scheduled to 8/10 . PV SL2 submission target date 10/10 ***09/26/2025*** . L1 Template for FInance disussion completed. . Domain/Pod status update meeting with Product Marketing MD on 9/23 . On going fine tunning with Finance lead in preparation for Finance Commercial leads review. . Next steps: 1. GAF Growth financial review on 9/29 2. Architecture Triage team review - week of Sep 29 | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business Only Initiative: AMI-CA REV- SAM Growth Strategy |  | 163930 | Business Only Initiative | AMI - Canada Revenue | Americas International | Mary Markoulis | On Track | In accordance with TO efforts to refocus on Strategic Programs, the AMI PMO and ESPM teams recommend that this initiatives be cancelled in Planview | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: VIS Global FDM Phase 1 | 15397 | 9228 | Business w/ Tech Initiative | AMI - Canada Revenue | Americas International | Gabriela Martucci Salles, Joe Pascal | On Track | ***Newest Updates*** **Week of 01/19/26** - We did a first meet up with the FDMi architect and we still have follow up questions. A new meeting has been schedule for Monday, next week. **Week of 01/12/26** - The internal alignment between the Canada marketing team and the FDM team on the soltuion has been made. - Both teams will be meeting with an FDMi architect next week to review the proposed solution. -- 12/22/23: L3 Status delayed until features in ART and validated. This will not delay work, but L3 and L4 may appear very close to Money Step as we are local only and work may appear in Sprints as ART can accomodate. Placing anticipated L3 dates to end of March with the knowledge that the ART will take on work but may not know final development date immediately. Working on L2 Financial Justification. Targeting the extended deadline of Feb 3. Week of 8/1 /24 - Updated FY25 Clear, L3 and L4 Dates and KPI's - Working on the PI for review of features to support rollout Week of 8/6/24 - Reviewed new Flow with Architects and documented additional features in - SMS Call, Migration and Enrollment Flow with 2 PINS - Initiated FIRST Process, need IT resource Week of 8/19/24 - Finalized Technical Flow and starting on FIGMA Designs, estimate approvals 8/27 - PI Planning session scheduled for 8/28 - Launch for US will occurred prior to peak - Launch for CA will occur after Peak to allow for more testing - Migration efforts have stopped as the complexity of integrating with Receipt Central will be high in effort and not prioritized Week of 8/26 - Finalized acceptance Criteria - Groomed user Stories - Held PI Planning Session - Pre Peak will develop and launch Page 1.3.4.,7 for US - Post Peak will develop and launch enrollment flow Page 1-7 add/edit; goal for team will work on eliminating from flow Pin #2 for more streamlined experience to include Canada Week of 9/5 Gained alignment to postpone until post peak: Project ID #15397- FDM Expansion to Canada, will be delayed to post-peak. The L4 will be changed to 02/03/25 (estimate). The reasons for the delay include: •The timing to go through due diligence to select the new vendor selection from InfoSec, would not provide time to develop the solution prior to peak. •Another big concern was the minimal time it would allow for testing; the regional team would not have sufficient time to test and ensure the customer experience would not be adversely impacted. •Concern that due to above, there was no appetite for introducing this risk during peak, with the already ongoing issues related to Network 2.0 and the lost customers, in Canada. Week of 9/12 Development continues on the Pre Peak Flow for FDM, this will only impact US - enrollment flow will change where users are required to supply mobile number prior to validation - since we were delayed, development was able to provide solution for 1 PIN only, a better experience overall - this will assist in retiring Postcard Flow in US only, as any user who does not supply a mobile number will not be able to enroll and a postcard will not be sent Planning continues on the Post Peak Flow for FDM, this will impact US and CA - The PIN will be moved up to Step 2 - Twilio, the current address validation vendor, owes team documentation to create API, and we will begin the FIRST process once this is received - IT resource was provided to begin First once documentation is reviewed - Postcard CA flow, dev team wanted to confirm customer identifier on postcard not needed, PM worked with Infosec and CST team and confirmed customer identifier printed on the postcard is not needed, as the CST team can pull up enrolments via FCL to research any potential bad actors. Week of 9/19 Planning of PI05 for Post Peak Flow continues, technical flows complete, FIGMA design in progress - Twilio reviewed documentation and API with team - Dev team and PM will begin First Process - Waiting on Canadian Postcard SVS vendor to provide documentation, expected | G: L3 | On Hold | L3 Data Migration - TEMP | 2026-08-03 | 2026-11-30
Business w/ Tech Initiative: CA Domestic Commit: Additional Transit Days |  | 88267 | Business w/ Tech Initiative | AMI - Canada Revenue | Americas International | Daniella M. Dias | On Track | 02/03/26 - Dec and January actuals entered. Note - actuals/forecast/baseline will be entered as a %. The quarterly/annual numbers will appear incorrect as it is a sum of the %. Emailed Yolanda Cutler (testing team for SCO) to understand if they will be able to support testing for the initiative. 1/21/26 - Received domain finance approval to update value/request type. Resubmitting to SL3 1/16/26 - Bill Hopp in TO finance provided guidance and recommendation for changing primary value/request type. Waiting for domain finance approval 1/05/26 - Met with EPSM team and Finance domain (Elizabeth Lee and Sohum) to discuss labeling of Request Type for the initiative. Concerns that Growth and Efficiency labeling will require display of monetary business value once the changes go into production. This initiative improves service levels however forecasted that there is no impactful monetary gains/avoidances based on baseline data (i.e. MBG). Next steps: Elizabeth to reach out to Bill Hopp (TO finance) to understand if x increase in service level = $ and to understand how previous service level initiatives were tagged as for Request Type. 3/6/25 - Received finance sign off by Brianna Sonson and Jennifer Beatty 3/10/25 - Received architectural analysis by Kyle Edmonds | G: L3 | Active | L3 | 2026-06-01 | 2026-09-29
Business w/ Tech Initiative: AMI-CA NB- Distribution Solution Enhancement |  | 163268 | Business w/ Tech Initiative | AMI - Northern Border | Americas International | Rod Polako, Nitin Menon | On Track | 3/4 - Submitted to L2. L2 finance review scheduled for 3/5/2026. LAC has responded regarding suitability of project MOSAIC upon review of business/legal requirements and intial feedback is that the requirments are out of scope. Current LBC to remain as-is while further work continues with LAC. 2/17 - Met with Finance (Trent Rumble) to discuss and change the Primary Type of Value to Revenue Growth based on the presence of hard benefits in the current business case. 2/25 - Provided LAC with business requirements and process information in order to determine if project MOSAIC will meet the visibility needs of this initiative. Awaiting response from the team. Pulled updated iSell data to determine impact to model if MOSAIC is suitable. 2/11 - Connected with LAC regarding their initiative and confirmed that they are scoping Canada in their effort. Additional work in progress to validate CA's requirements within that project. Updating this request to reduce scope and effort in light of this development in progress. 1/28 - Request underwent architecture review. Current estimated size is "Large". Have reached out to LAC team regarding their visibility project to determine if this request can be partially handled via that separate project. Awaiting reponse. 1/16 - Updated Demand Description to remove the request for LTL expansion as it is out of scope. 12/18 - Updated Ability to statments as requested by David Walker. 12/16 - No updates at this time. 12/12 - Updated the Primary PEO for Commercial, Data & AI, Platform and SCO as requested by the team to help progress the request. 12/10 - No updates at this time. 12/5 - Scope of request may need to be revisited wrt visibility due to global solution being pursued (upon connecting with LAC team). IT architect assignment/prioritization being pursued with Roger Cooley. With agreement that current estimate of "small" t-shirt size is currently appropriate, the lower bound of the business value has gained confidence and is less likely to reduce the overall value of the project. 11/26 - Met with US team regarding visibilty component. Outcome of that meeting suggests that there may be a reduction in this request. Further investigation in progress. Still awaiting IT review for cost estimation. 11/21 - Awaiting IT review for cost estimation. 11/14 - Awaiting IT review for cost estimation. 11/7 - Updated NRB from zero to $2.4MM after discussion with CA Leadership and opened PDSM ticket to update information in L0. 10/31 - Further adjustments to financial model completed as directed by Finance. Still awaiting assessment by IT. Business case review with CA team scheduled for next week. 10/17 - Finalized financial model/business case with Finance. Awaiting meeting with IT for technical review and model updating. Changed Primary IO ownership. 09/26 - Met with business leads to review scope and initiative. Substantial rewrite of demand description completed. 09/19 - Assigned a secondary IO to work through LBC for L2. | E: L2 | Active | L2 - Enter Value Prop
Business Only Initiative: AMI-CA NB- Bulk Trucking (US-CA) |  | 163262 | Business Only Initiative | AMI - Northern Border | Americas International | Jose Carlos Dos Santos Jr., Jason Shatz | On Track | 10/03 - Initial financial reviews to complete business case; - Cost validattion with Linehaul engineering | G: L3 | Active | TEMP L3 - Enter L3 | 2026-06-30 | 2026-06-30
Business w/ Tech Initiative: LAC SB Digital: Commercialization of fdx platform |  | 163651 | Business w/ Tech Initiative | AMI - Southern Border | Americas International | Penelope Fisher | On Track | This effort is no longer in flight. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC SB: Southern Border - SB Distribution Offering |  | 89850 | Business Only Initiative | AMI - Southern Border | Americas International | Raul Cardenas, Kevin Johnson, Benjamin Fernandez, Sandra Parras | On Track | 4/17/26 - To be canceled - initative will be reviewed and incorporated to a new initiative as per Southern Border Ideation Session result on April 2, 2026 1/15/26 - Init on hold until March 1 2026 - due to IO (USI Mktg) resrouce reassignment - Higher Priority initiatives focus and SB Goals restatement after FXF spinoff direction 11/13/2025 - submitted to L3. Received feedback to complete financials section and milestones. Following job aid: Learn how to add and edit the Financial section at L2 stage for completion. 9/26/2025 - pending change from business with tech to business. Updated L2 fields. Meeting with Sales next week to discuss collateral needs and timelines for inputs to milestones section. 12/20 - work begun 6/6/2025 - Finance business case approved by domain lead and LAC FIN | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: LAC SB: Southern Border - Control Tower |  | 93265 | Business w/ Tech Initiative | AMI - Southern Border | Americas International | Arthur Nolte, Tammy Castine | Attention Needed | 2/12/26 Init to be cancelled, as efforts will be transitioned to Global Supply Chain Orchestration (Mossaic - PV ID: 179799) under Commercial Domain. Approvals obtained from AMI Domain VP/SVP and Global Supply Chain Orchestration teams for cancelation and transition to new domain. **2-10-26** Per Pedro in LAC, this project should be show as inactive based on a new intiative planned to provide Control Tower type of Automation through vendor support. Commercial Team unable to provide resources to support. **February 2026 Update** There has been **zero** information provided on the automation development to help move this project forward. The first file I have on this project is dated February 2024. **Two years and no significant movement** 1. Supply Chain Orchestration (SCO) team. No update from LAC team. 2. DataWorks Experimental Team (Hunter Douglas Pilot no updates) 3. Planview Commercial Team (have received no communidations from the Commercial team.) FXL LAC Control Tower is eager to engage with automation initiatives once 1-3 above are aligned with a clear path forward. **January 2026 Update** There has been **zero** information provided on the automation development to help move this project forward. The first file I have on this project is dated February 2024. **Two years and no significant movement** on automation, no automation timeline, no resources and no automation project plan. **There are three Control Tower type initiatives underway:** 1. Supply Chain Orchestration (SCO) team (still under definition) 2. DataWorks Experimental Team (Hunter Douglas Pilot no updates) 3. Planview Commercial Team (here in Planview) At this time, the development of automation with a defined plan that includes a clear path forward, with defined resources and a timeline is has not been provided. LAC Marketing continues supporting Control Tower efforts with the Supply Chain Orchestration (SCO) team. The SCO team is still under definition and path forward is also yet to be defined. No update provided. Commercial Team/Planview. No change in August, September, October, November, or December. LAC Control Tower is show as an active initiative in Planview but not moving forward in Planview pending the assignment of a Business Architect by the Commercial Team (required) and no timeline has been provided. **It is also unclear whether or how the Commercial Team and the SCO team might interact or align.** LAC Control Tower Proof of Concept is complete. FXL LAC Control Tower initiative will continue to manually support customers on-boarded during the POC. FXL LAC Control Tower is eager to engage with automation initiatives once aligned with a clear path forward. Revenue at risk - Project is in containment. All finance figures (revenue/costs/timing) in Planview related to the FXL LAC Control Tower are no longer valid because of the delay in automation development and implementation. **12-22-25 Calendar Year 2025 Planview Update)** There are **three** Control Tower type initiatives underway: **Supply Chain Orchestration** (SCO) team (still under definition) **DataWorks Experimental Team** (Hunter Douglas Pilot no updates) **Planview Commercial Team** (here in Planview) At this time, the development of automation with a defined plan that includes a clear path forward, with defined resources and a timeline is unclear. As reported in the last update, FXL has been advised that LAC Marketing continues supporting Control Tower efforts with the Supply Chain Orchestration (SCO) team. The SCO team is still under definition and path forward is also yet to be defined. **Commercial Team/Planview**. No change in August, September, October, November, or December. LAC Control Tower is show as an active initiative in Planview but **not moving forward** in Planview pending the assignment of a Business Architect by the Commercial Team (required) and no timeline has been provided. It is also unclear whether or how the Commercia | E: L2 | Cancelled | L2 Feedback Requested | 2025-03-03 | 2025-10-01
Business Only Initiative: LAC SB: Southern Border - Brick & Mortar | 70795 | 7769 | Business Only Initiative | AMI - Southern Border | Americas International | Amy Besserud, Sandra Parras, Jason Evers, Benjamin Fernandez | On Track | 3/25/26: Jan actuals updated 2/12/26: Dec actuals updated, Nov actuals updated as well - change in FXG and FXF numbers as finance provided updated correct info. 1/22/26 : Nov 2025 actuals updated. December actuals will not be available until Feb 2026 [BF] 11/11/25: QA Expert review not possible as AMI does not have a QA domain expert. However, reviewed intiative milestones, KPIs, and financials with Brett Buckhold, Maria Sarli, and Sergio Ramirez in lieu of domain expert - they approved submission to L3 11/5/25: Per guidance from Rakesh Shalia, initiative to remain as Business Only, NOT enabler as recommended. Milestones to be added that indicate sales as responsible for delivering the revenue, and commericial as responsible for providing and working forecast into business plan so additional capacity can be justified. 10/28: Initiative submitted to L3, but sent back for review on milestones and financials. Meeting this week to discuss potentially updating initiative to enabler. 10/21: Updated financials actuals - per guidance from PMO, since capacity project not scheduled to open until 10/31 we can't recognize any revenue even though it was advised there was capacity available to grow in all SBD markets- capacity project needed to support peak only growth and will be available on time 10/7: All on track for JBKA pre-peak startup. Local operations team is managing startup and customer plan (what will be worked in JBKA). Operational startup for 11/3 9/18: Initiative has been updated to business only. Awaiting submission to L3 until we can use actuals for June/July/August financials (will not accept forecasted financials for prior months) 9/4: PDSM request to business only still pending. JBKA on track for 10/31 startup. 8/27: Per guidance received, will be submitting PDSM to update to Business Only (not business with tech) 8/22: Capacity being added to JBKA facility in So. CA to support capacity constraints in OTAY. 7/16/25: Removed verbiage from brief demand status about the t-shirt size and FY25 exit rate per the request from the finance team (Jennifer Liu and Megan Lightford) 7/9/25: No changes to status Capacity add on track for FY26 | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-11-28 | 2025-11-28
Business Only Initiative: LAC SB Air MX-US OB Protect our base | 70791 | 7045 | Business Only Initiative | AMI - Southern Border | Americas International | Cynthia Evelyn Ortega | On Track | 10/23: In alignment with Pod Lead and Pod PMO, cancelling initiative to be replaced with a more actionable initiative to achieve the revenue goals.10/2: As per PMO, changed to initiative name to align with Domain naming convention. 6/26/2025: L3 submission in progress | E: L2 | Cancelled | L2B - Feedback Requested | 2024-07-22 | 2025-04-08
Business Only Initiative: LAC SB Air MX-EU OB Growth | 70792 | 7047 | Business Only Initiative | AMI - Southern Border | Americas International | Cynthia Evelyn Ortega | On Track | 10/23: In alignment with Pod Lead and Pod PMO, cancelling initiative to be replaced with a more actionable initiative to achieve the revenue goals. 10/2: As per PMO, changed to initiative name to align with Domain naming convention. 6/26/2025: L3 submission in progress | E: L2 | Cancelled | L2B - Feedback Requested | 2024-07-22 | 2025-03-31
Business Only Initiative: LAC SB Air MX-APAC OB Growth | 70781 | 7043 | Business Only Initiative | AMI - Southern Border | Americas International | Cynthia Evelyn Ortega | On Track | 10/23: In alignment with Pod Lead and Pod PMO, cancelling initiative to be replaced with a more actionable initiative to achieve the revenue goals. 10/2: As per PMO, changed initiative to LAC naming convention 6/26/2025: L3 submission in progress | E: L2 | Cancelled | L2B - Feedback Requested | 2024-07-22 | 2025-03-31
Business Only Initiative: LAC SB: Southern Border Savings |  | 166560 | Business Only Initiative | AMI - Southern Border | Americas International | Jose Alberto Aceves, Victor Manuel Guadalupe Guerre | On Track | Presentation of scenarios with Tier One Stakeholders | I: L4 | Active | L4 | 2025-07-28 | 2027-04-29
Business w/ Tech Initiative: LAC SB: Bid boards |  | 166601 | Business w/ Tech Initiative | AMI - Southern Border | Americas International | Jose Ignacio Gonzalez | On Track | 04/22/2026 •The information required to proceed to L2 has not yet been submitted, as the Finance Director requested the inclusion of yield metrics (per package for IP, and per pound for IPF and IEF). The assigned Finance team member is currently working on this requirement. •Meanwhile, the Commercial team remains actively engaged with clients, negotiating terms, conditions, and pricing in order to secure requests and continue participating in bid board opportunities. 04/16/2026 •The business case was presented to the Finance Directors to seek approval to move to L2. However, additional data was requested. The finance lead assigned to the project is currently working on it, and the information is expected to be ready next week. Summary per customer: •Forvia – Parcel Business: Forvia is evaluating FedEx as a potential provider for its Parcel business. IP Business Model: IP shipments would be managed via direct invitation to the Easy4Pro platform, without a formal contract. Business Mix: Easy4Pro volume is estimated at 70% Ground and 30% Air (Imports, Exports, Charters). •ZF – Approval of a lower rate is pending to secure the business; follow up is ongoing with local and European pricing stakeholders. •Sulzer – Two quotations have been issued to date. •Valeo – Awaiting customer confirmation on account currency (USD vs. MXN). •ZKW – Pending notification to initiate quotation activities. •Brose – Next steps will be defined following the upcoming customer call. •ThyssenKrupp – NDA for Mexican entities is pending FDX Legal signature. Contract has been shared with the customer for execution. Implementation follow up meeting in Germany is scheduled. 04/08/2026 •The 90-day credit terms requested by Valeo for the 10 new accounts have been approved, allowing FedEx to be included in the BB proposals. We are currently awaiting customer confirmation on whether invoicing will be issued in Mexican Pesos (MXN) or U.S. Dollars (USD). •A follow-up call with the client (Forvia) is scheduled for Monday, the 14th, to continue negotiations on the contractual clauses where proposed changes were not accepted. 04/01/2026 •After FedEx Legal reviewed the contract proposed by the client, Forvia, the agreement was returned with several observations. Forvia subsequently responded rejecting a number of the proposed changes. As a result, a call was held with the client on March 31, attended by Forvia’s Procurement representative. The following are the key topics discussed during that meeting: •The discussion was limited to Procurement, with no participation from Legal or Risk, leaving several topics pending, including Code of Conduct alignment, liability exposure, and contractual clauses related to first and last mile execution, all of which require further internal and cross functional review. •Open commercial and risk considerations remain, including uncertainty around liability coverage (USD 1M vs. USD 20M) and a client request for a 5% rebate, both of which require internal assessment and approval before proceeding. •A follow‑up call will be scheduled with the client once they confirm that all pending items have been reviewed internally. 03/25/2026 •The business case (BC) has been approved by the Sales team and will be presented to the Finance Managing Director during the first week of April. •Two working sessions were held to begin mapping the process for claims exceeding the current maximum limit of liability (USD 50,000). The agreed process will be formally documented in the SOP. •It was agreed with Sales leadership to request the creation of a dedicated flag in the iSell system to identify customer opportunities related to Bid Boards, enabling analysis of both won and lost opportunities. •The case was escalated to the VP of Credit & Collections to request approval for 10 accounts for the Valeo customer under 90 day credit terms. A final decision is expected in the coming days. 03/13/2026 •The project’s P | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC SB: Intl VP parity with key competitors |  | 166607 | Business Only Initiative | AMI - Southern Border | Americas International | Susana Caro del Castillo, Laura Carpenter | On Track | 01/26/2026 Cancellation requested as value proposition is a business as usual activity 12/17/2025 A) Marketing research of International Value Proposition is ongoing. Results will be ready in March 2026. B) The estimations of value of opportunity for Outbound MX-EU & MX-APAC has been reviewed and approved by MD Marketing Michel Capuano C) Comments and recommendations from Product Development for implementation plan & analysis. Next steps: To confirm if Inbound EU to MX and APAC to MX should be considered as part of this initiative. 12/10/2025 A) Marketing research of International Value Proposition is ongoing. Results will be ready in March 2026. B) The estimations of value of opportunity for Outbound MX-EU & MX-APAC has been reviewed and approved by MD Marketing Michel Capuano C) Comments and recommendations from Product Development for implementation plan & analysis. Next steps: To confirm if Inbound EU to MX and APAC to MX should be considered as part of this initiative. 12/03/2025 A) Marketing research of International Value Proposition is ongoing. B) The value of opportunity for Outbound MX-EU & MX-APAC has been estimated based on Pajiva 2024 Air Exporters data and is under MD Marketing review.Next steps: Alignment with Product Development for planning and socialization with VP LAC Marketing Rakesh Shalia. 11/27/2025 A) Marketing research of International Value Proposition is ongoing. B) The value of opportunity for Outbound MX-EU & MX-APAC will be estimated based on Pajiva 2024 Air Exporters data. Next steps: 1. Validation with SMPA of Exporters segments to be included into estimation. 2. Alignment with Product Development for planning and socialization with VP LAC Marketing Rakesh Shalia. 11/19/2025 The net benefit of the initiative will be determined once the marketing research is completed at the end of January 2026 and the P&E feasibility analysis is done 1.P&E is pending to assign a resource to analyze feasibility for improving transit times of the 26 lanes OB MX-EU & MX-APAC where FedEx is slower than competitors 2. Finance has provided FY25 & FY26 YTD report with revenue, volume and yields from OB MX-EU & MX-APAC 2.1 Finance P&L is dependent of the P&E analysis and costs as well as the results of marketing research. 3.Improvements for International Value Proposition initiative will be implemented in phases: 3.1 Improvements of transit times per group of lanes where P&E determines feasibility to improve 3.2 Plan & Development of actions required to gain market share in Parcel & Freight 3.2.1 Commit Transit times to Improve NSL to gather the goal of 80.6% •YTD MX-EU NSL 52.73% •YTD MX-APAC NSL 71.67% 3.3Close gaps in Products portfolio offer and coverage 3.4 Competitive rates 3.5 Enhance available tools and each point of contact with Customers for improving Customer Experience 3.6 Improve & commit Cut off times 3.7Improve & commit Pick up times 3.8Retail locations experience and availability 11/12/2025 Finance is validating the numbers to determine the net benefit from this initiative.The net benefit estimated by Marketing is $2.4M by FY28 if we would improve 1 day of transit in the 26 lanes MX-EU and MX-APAC where FedEx is slower than main competitors DHL & UPS.Budget under SMPA team to start the Marketing research of International Value Proposition for Outbound MX-EU & MX-APAC Top destinations, is pending to be confirmed 11/05/2025 SMPA Team ran the Service Improvement Model designed by MEM for 1 day of improvement to the 26 lanes into this initiative (OB MX-EU & MX-APAC). This model determines that if we improve 1 day of transit, we can get an incremental annual revenue of $2.7M with 13.3K total incremental volume. Finance is working on the financial exercise updating costs and ensuring that revenue baseline from FY25 is accurate to determine the net benefit from this initiative. Budget under SMPA team to start the Marketing research of International Value Proposition for Out | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC SB: GAF & IPF commercial missions |  | 166610 | Business Only Initiative | AMI - Southern Border | Americas International | Anayatzin Acosta, Jorge Ivan Galina | On Track | 10/30: The Commercial Mission has begun, we have been able to visit 13 customers accross 4 countries, they represent 3.9M lbs and $11.3M in revenue annually, we are half way of the trip and there are 14 more customers remaining with a potential business of 6.2M lbs. and $13.3M in revenue annually 11/05: •Up until 11/05, 9 more customers have been visited, representing 2.97M lbs. and $6.4M annually. 5 more customers are left to visit, representing 3.2M lbs. and $6.69M annually. This Commercial Mission is about to end in two more days. •A meeting with Financial team took place on 11/05 to review the first version of the P&L, this document will be updated to include an adjustment on the potential volume and revenue for the following commercial missions •Potential volume and revenue for the Commercial Mission to Asia is being worked so it can be included in the financial report 11/12: * Commercial Mission to Europe has concluded, 27 customers were visited, they represent a potential volume of 10M lbs. and $24.6M USD in revenue annually * LBC report was reviewed with John Frey and Josie Ortega and is now ready to be presented to Ben Alexander and Mariana Rios, tentatively next week depending on their agendas * A meeting with the team who travelled to Europe will be scheduled to review the results of the mission 11/19 * Meetings with each of the Sales teams have been taking place to follow up on the opportunities from the trip * Waiting for Ben Alexander and Mariana Rios to confirm their availability to present LBC report 11/26 * Meeting with the Commercial Mission team to start working on the Executive Summary including the aftermath of the trip and the following steps for each account * Meeting with Ben Alexander to present the project, Jorge Galina to review how to make it more robust for DRIVE 12/04 *Potential volume and revenue for the Commercial Mission to Asia is being worked with sales so it can be included in the financial report *A meeting with Financial team took place on 11/05 to review the first version of the P&L, this document will be updated to include an adjustment on the potential volume and revenue for the following commercial missions, next update next week. *Continue advancing the commercial mission into Europe. Face-to-face meetings are being held with customers in Mexico to align efforts and identify round-trip opportunities. 12/09 *Potential volume and revenue for the Commercial Mission to Asia is being worked with sales so it can be included in the financial report *A meeting with Financial team took place on 11/05 to review the first version of the P&L, this document will be updated to include an adjustment on the potential volume and revenue for the following commercial missions, next update next week. *Continue advancing the commercial mission into Europe. Face-to-face meetings are being held with customers in Mexico to align efforts and identify round-trip opportunities. 12/16 *Potential volume and revenue for the Commercial Mission to Asia is being worked with sales so it can be included in the financial report *Continue advancing the commercial mission into Europe. Face-to-face meetings are being held with customers in Mexico to align efforts and identify round-trip opportunities. *A follow-up call was held with the Finance team to calculate the revenue for the upcoming commercial missions. It was determined that, for FY27 three business trips will be conducted resulting in 9M USD and after FY28 4 CM 2 to Europe, 2 to Asia increasing to 12M USD per year 12/23 *Potential volume and revenue for the Commercial Mission to Asia is being worked with sales so it can be included in the financial report *Continue advancing the commercial mission into Europe. Face-to-face meetings are being held with customers in Mexico to align efforts and identify round-trip opportunities. *A follow-up call was held with the Finance team to calculate the revenue for the upcoming commercial missions. It | E: L2 | Active | L2
Business Only Initiative: LAC MEX Target High-Yield Categories |  | 160453 | Business Only Initiative | AMI - Mexico | Americas International | Laura Carpenter | On Track | 13/02: Transitioned from Monica Segura to Lau Carpenter (handover explanation) 07/01: Reassigned initiative owners: Lau Carpenter 10/29 Regarding the requested information and clarifications (L2 submission): In L1, I entered L1 Net Recurring Benefits ($, annualized) – P&L/Hard USD 246,760, which by mistake corresponds only to the month of May (it was not annualized) and reflects Operating Income. However, this was an error — the amount should have been annualized. By mistake, in L2 I had also entered the monthly amount instead of the annualized figure and in Revenue. This has now been corrected and also it was a mistake that I register manually a soft benefit that wgould go in zero. Additionally, I updated one of the costs to One-Time, which is the correct classification. Included the description of the money step milestone. 10/27 Updated L2 information (financials, milestones and risks) 09/24 Updated Financial information with operating income confirmed by finance (Kevin Cyriaque & John Frey). For FY28 the operating income is $285,241 USD, and the net recurring benefits were calculated with May 2028 operating income $20.563 by 12 months = $247,759.51 USD . The money step is once executed start having incremental ADV in weight range 10-15kg. Money Step: updated as requested. Once executed, it will start generating incremental ADV in the 10–15 kg weight range within the Golden Triangle 08/28 - LBC submitted in planview (L1) | G: L3 | Active | TEMP L3 - Enter L3 | 2026-06-30 | 2026-06-30
Business Only Initiative: LAC MEX Dom Value Proposition Main Competitors |  | 160608 | Business Only Initiative | AMI - Mexico | Americas International | Alejandra Gabriela Torres, Laura Carpenter | On Track | 01/26/2026 As per LAC Marketing alignment, Value Proposition is a business as usual process, which will continue as every year 07/01: Reassigned initiative owners: Lau Carpenter and Gaby Torres 12/03: Added milestones with dates and descriptions. Added KPIs that are a requirement for all initiatives and should be listed in the Financial Plan. This is an enabler, no Revenue associated, for both KPI added baselina and forecast as requiested, but data goes in zeros. The KPIs should be more associated with Value Proposition: Coverage, Transit Times, Price, NSL, Ctu.off times but this options are not available on planview. 10/20: The two initiatives that this enabler supports—LAC MEX Enhance Existing Undeveloped Products and LAC MEX Target High-Yield Categories—are now in L2. As this was the final requirement pending, I am proceeding with the submission today. 09/18: Changed based on feedback received: 1. Updated Dependencies from “Dependent of” to “Required by” and included both Domestic initiatives: LAC MEX Enhance Existing Undeveloped Products and LAC MEX Target High-Yield Categories. 2. Both initiatives are marked as Business only, the same approach being considered for this enabler. 3. Updated the Value type to Financial – Revenue Growth (Customer Acquisition), consistent with the initiatives (previously set as Financial – Revenue Protection). 09/17: This is an ENABLER, no value will be associated. Discusses and confirmed with Ben Alexander (finance domain lead) in call 9/17. Finance domain lead approves move to L2. Commnents: the enabler consists on revising our domestic value proposition to ensure competitiveness in the Golden Triangle. By doing this, it will support the rest of Mexico Domestic initiatives' targets. 08/28 - submission of LBC on planview | G: L3 | Cancelled | TEMP L3 - Enter L3
Business w/ Tech Initiative: LAC MEX Alternative Pricing Models Redesign |  | 160619 | Business w/ Tech Initiative | AMI - Mexico | Americas International | Stefania Contursi | On Track | Pending CPEL Meeting - Next Meeting Jan 14th | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: LAC MEX Revenue Management: Volume Discounts |  | 160630 | Business Only Initiative | AMI - Mexico | Americas International | Stefania Contursi | Attention Needed | 04/16/2026 - After further evaluation, we have decided to cancel this initiative as it is no longer aligned with the overall objective currently being pursued. The initiative carries a high risk of volume loss driven by potential price increases, and the current volume performance in Mexico is significantly lower than at the time the initiative was originally considered and designed. Given the current market and performance context, our priority at this stage is to maintain and protect the existing base, rather than pursue actions that could further pressure volume. | G: L3 | Cancelled | TEMP L3 - Enter L3
Business Only Initiative: LAC MEX Optimize Retail Network |  | 160639 | Business Only Initiative | AMI - Mexico | Americas International | Miriam Reyes, Monica Daniela Gomez | On Track | 04/24/2026 Trasnsfers of the 5 Owned to RSV are on progress. Properties team is contacting landlords to communicate change of tender for RSV and they will inform landlords response to complete the change. HR and Ops have coordinated the potential open positions for the employees of the Owned locations to be transfered to RSV. 03/26/2026 Transfers of the 5 Owned to RSV are late than expected plan but are now on track to be completed NLT April. 03/05/26 Transfers of the 5 Owned to RSV are on risk to be completed. Meeting with HR & Ops Retail next 03/09 02/26/2026 Available actuals from December and January on Financials tab. The 5 Owned to be transferred to RSV was recently approved by Mayra Payan to move forward on 24/02. Their savings are expected to be reflected at the end of April. 02/19/2026 Actuals from the 4 closures will start to be reflected on the January report to be informed by the end of February. Regarding the 5 Owned transfers to RSV all of them are on risk to be completed because Mayra Payan has concerns about the financial model used including variable costs of cost x package. We are waiting for other actions proposed by Mayra instead of the transfers to RSV. 02/11/2026 The 4 closures are completed CZAK, PPEL, VERJ & MTTB. The 5 Transfers of Owned to RSV are on going being 4 (TGZB, TGZF, TGZE and VERP). They should be executed NLT March. ACAC is still pending. Waiting for MD Ops Retail Mayra Payan' approval to proceed with transfers. Savings from the 4 closures will be reflected on the January report available at the end of February. 01/29/2026 3 of the 4 closures are completed CZAK, PPEL & VERJ. MTTB is still pending and should be executed NLT 02/28. Transfers of the 5 Owned to RSV are ON RISK because MD Ops Mayra Payan is retracting for continuing with transfers. Savings from closures will be reflected on January expenses report. A new meeting with Michel Capuano and Mayra Payan for next steps regarding transfers that would impact to the savings from this initiative. 01/23/2026 On track. Savings from 2 of the 4 closures (Owned) will be reflected on January expenses report. Meeting with MD Ops Mayra Payan will be held on next 01/28 to get her approval for completing the transfers of the 4 of the 5 Owned in plan. ACAC is still pending to finding an interested RSV to take it. 01/14/2026 Two of the four closures were executed on 12/13/2025: CZAK & PPEL. The remaining 2 MTTB & VERJ are on process to be closed and will be completed by 01/31/2026. Transfers of Owned to RSV to be completed by 02/09/2026: Financial statements of 4 Owned TGZF, TGZB, TGZE and VERJ have been shared with the interested RSV. Review with Properties of these 4 contracts to prepare transfers to RSV. ACAC is still pending to obtain an interested RSV. Monthly savings from these closures and transfers in FY26 plan $46k: Jan $30k, Feb $38k, Mar $46k 12/18/2025 Milestone 165607 Transfer 5 Owned to RSV is now on track. Financial statements have been shared with the interested RSV to take the owned retail locations and we are in the process to proceed with transfers. Additionally, the milestone 165610 Closure 4 Owned retail locations are 50% of progress: 2 of the 4 closures are already executed (CZAK & PPEL are already closed; MTTB & VERJ will be closed NLT 01/31/26. 12/12/2025 Milestone 165607 Transfer 5 Owned to RSV response expected by December 31st 2025, will update for any delays January 5th 2026 12/10/2025 On track 12/02/2025 On track 11/27/2025 On track 11/19/2025 On track 11/12/2025 Plan for closures and transfer to RSV will start on December and is estimated to be completed in January. Savings once locations are closed and transfered to RSV will be reflected since January 2026. The locations to be closed have changed versus the originally locations selected. They will be 4: CZAK, MMTB, PPEL and VERJ. This selection allows to keep better savings into the initiative beacuse only one of them have pending depreciation (writte off) | G: L3 | Active | TEMP L3 - Enter L3 | 2026-04-30 | 2026-04-30
Business Only Initiative: LAC MEX Air Line Haul Optimization |  | 160650 | Business Only Initiative | AMI - Mexico | Americas International | Jose Alonso Ramos | On Track | 4/14/2026 March 2026 actuals submitted 3/27/2026 February 2026 actuals submited 2/10/2026 Actuals and money step updated up to Jan 2026 1/21/2026 Actuals up to Dec 2025, the money step excel document has a line with the actual air expense in the "MoneyStep" sheet 1/14/2026 Actuals for Dec on progress 12/30/2025 Actual for savings and CPP confirmed 10/28/2025 CCH meeting was held and CCH template have been sent 10/23/2025 CCH template on process 10/14/2025 L2-L3 template uploaded on content 10/02/2025 Presentation with Ben A. 09/22 Pending for L2 submission IMPLEMENTATION DATE 10/01 | I: L4 | Active | L4 | 2025-09-01 | 2026-01-30
Business Only Initiative: LAC MEX Ground Linehaul Optimization |  | 160654 | Business Only Initiative | AMI - Mexico | Americas International | Jose Alonso Ramos | On Track | 4/14/2026 March 2026 actuals submited 3/27/2026 February 2026 actuals submited 2/10/2026 Actuals and money step updated up to Jan 2026 1/21/2026 Actuals up to Dec 2025 uploaded, money step document has a line with actual ground expense in the "MoneyStep" Sheet. 1/14/2026 Actuals confirmation on progress 11/07/2025 Financial plan updated (PT impact) 10/23/2025 Information for L2 uploaded and submitted 10/14/2025 L2-L3 template uploaded on content 10/01/2025 Presentation of L2-L3 template with Ben A. | I: L4 | Active | L4 | 2025-06-02 | 2025-12-22
Business Only Initiative: LAC MEX Courier Inhouse |  | 160661 | Business Only Initiative | AMI - Mexico | Americas International | Maria Jose Magana | On Track | 09/22 Additional research required due lack of Customers interest on FedEx proposal. Project to be putted on hold for future date to be confirmed 08/28 1st Pricing escenario done and use for L1 stimation impact. | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval
Business Only Initiative: LAC MEX Facility & Vehicle Rentals optimization |  | 160668 | Business Only Initiative | AMI - Mexico | Americas International | Jesus Esparza | On Track | 03/09/26: Milestones were added again, actuals from feb were updated 03/02/26: Milestones were deleted from the initiative, support was requested via ePDSM 02/23/26: Additional team members were added for CYWA & PPEA migration 02/16/26: Preparation for CYWA & PPEA migration in execution 02/09/26: Actuals updated 02/04/26: Working with Finance to update actuals for the project 01/27/26: CYWA & PPEA closure process in excecution, operation redistribution phase 01/14/26: Project in approval process for L3 (SL3) 12/30/25: Corrections made for SL3 submission 12/14/25: Changes for normalized Baseline were shared with FInance Leads 10/17/25: Full Business Case data in progress 10/02/25: Corrections requested were made in Planview 09/29/25: Submitting to next step (SL2) | I: L4 | Active | L4 | 2026-05-01 | 2027-06-30
Business Only Initiative: LAC MEX Enhance Existing Undeveloped Products Ret. |  | 160672 | Business Only Initiative | AMI - Mexico | Americas International | Alejandra Gabriela Torres | On Track | 13/01: Transitioned from Monica Segura to Gaby Torres (handover explanation) 07/01: Reassigned initiative owners: Gaby Torres L1 LBC Submitted Aug 28 2025 | G: L3 | Active | TEMP L3 - Enter L3 | 2026-05-29 | 2026-05-29
Business w/ Tech Initiative: LAC MEX Global P&D Ecosystem | 80200 | 9022 | Business w/ Tech Initiative | AMI - Mexico | Americas International | Catherine M. Gies, Miriam Paulina Martinez | On Track | * **01/07/26**: PPM proposal approved; PPM Project ID 1836846 created. Pending Architect assignment to begin solutioning discussions and updated timeline for regional launches from Corp team. * **01/06/26**: PPM proposal submited and pending IT Lead approval. Pending Architect assignment to begin solutioning discussions.March POC launch posteponed (new timeline TBD by Corp Team) due to FR Dev fixes. * **12/29/25**: Still pending Architect assignment to begin solutioning discussions. Dev costs (if any) need to be included in business case before proceeding to L3. Catherine working on submission of PPM. * **12/16/25**: Need Architect assignment to begin solutioning discussions. Requires dev costs (if any) to be included in business case before proceeding to L3. * **12/8/25**: Moved into L2 Status * **11/10/25**: Determined should remain as Business w/Tech. John Turner updated L1 Assessment on Nov 6th. Finance Lead was assigned by Ben and NPV analysis is in progress to avoid further delays. * **10/24/25**: Discussion with SIV team identified a separate local enhancement to PV 0105030 - IVVI / SIV would be created. AGC PV discussion to take place next week. Will likely need to keep 9022 as business with tech due to COD/FTC solution needed for all MX launch. Meeting next week with EU will determine if solution is only needed by MX or if other countries will need this as well, and if so, whether it remains in MX PV Request (9022) or if a separate global initiative will be required. * **10/20/25**: Added Initiative Folder Link for Ops Model Architectural Artifacts, updated impacted portfolios based on L1 architectural review, and modified T-shirt size in Planview request. Ryan provided L1 Architectural review document on 10/16. * **10/14/25**: Jhon Turner confirmed that Initiative 9022 should be able to leverage the architecure outcome from 7406 (global request), similar to other regional requests (7627 for EU and 9524/9525 for APAC) as there is no architectural work needed for 9022. *** General:** MX Launch is planned alongside regional launches in EU, APAC, MEISA for GP&DE. Architectural development prioritized for FR MTP in October while regional work targeted for completion in Jan 2026 prior to March 2026 POC launch for regions. | E: L2 | Active | L2 | 2025-06-02 | 2026-12-04
Business Only Initiative: LAC MEX Staffing Efficiency |  | 163717 | Business Only Initiative | AMI - Mexico | Americas International | Jose Alonso Ramos, Jesus Esparza | On Track | 4/20/2026 March 2026 actuals submited 3/27/2026 Actuals submited up to february 2026 01/14/26 Reviewing full business case in order to move to SL3 (New efficiencies added) 10/27/25 Pending to find how to track automatically benefits from Dim& Weight machines 10/02/25 Initiative reviewed with Ben Alexander. REady to SL2 | G: L3 | Active | L3 | 2025-06-02 | 2027-06-04
Business Only Initiative: LAC MEX Road Linehaul Savings |  | 141579 | Business Only Initiative | AMI - Mexico | Americas International | Araceli Pulido, Jose Alberto Aceves, Victor Manuel Guadalupe Guerre | On Track | 04/22/26 Additional stakeholder criteria are currently under development to be incorporated into the evaluation process; therefore, this initiative remains ongoing. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-01 | 2027-04-16
Business Only Initiative: LAC MEX PUD Savings |  | 141583 | Business Only Initiative | AMI - Mexico | Americas International | Constanza Jara, Victor Manuel Guadalupe Guerre, Angelica Mendoza, Rubi Berenice Rodriguez | On Track | NUXA - TLCA: Presentation of scenarios with Tier one Stakeholders MMCA, MTYA, SLWA: RFQ2 was initiated this week MLMA, UPNA & NCGA: Evaluation 3 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-31 | 2026-07-31
Business Only Initiative: LAC MEX DIM Weight Machines FY26 |  | 130226 | Business Only Initiative | AMI - Mexico | Americas International | Silvia L. Gonzalez Alonso, Christopher Bernat | On Track | 4/13 - Updated Financials/KPI Actuals for Mar'26. Missing depreciation Actuals, dependent on Finance resources. 3/17 - Feedback received from INC033567375: "KPI lines are from financials and they only sum up. They don't calculate based on the aggregation type (average vs. sum). This has been already communicated to finance stakeholders. Any aggregation needed for KPIs needs to happen outside Planview." 3/12 - Updated Financials/KPI Actuals for JFeb'26. Missing depreciation Actuals, dependent on Finance resources. 3/2 - TIJR DW machine MTP completed on 2/28 2/25 - TIJR installation started on 2/20. MTP planned for 2/27 2/11 - Updated Financials/KPI Actuals for Jan'26. Missing depreciation Actuals, dependent on Finance resources. 1/29 - LOMA machine completed MTP 1/28 - 2 GDLA machines and 2 CUAH machines completed MTP. 1/21 - Updated Financials/KPI Actuals for YTD. Missing depreciation Actuals, dependent on Finance resources. LOMA machine installation and commissioning completed on 1/13. MTP pending due to data trasnmission issues to back-end systems. GDLA 2 machines installations completed on 1/19. Pending commissioning, delayed due to conveyor mechanical issues. CUAH 1st machine installation and commissioning completed on 1/20. Pending acceptance testing and MTP. CUAH 2nd machine installation started 1/19 1/19 - Initiative approved to move to L3 12/30 - In accordance with TO Finance Guidance made changes to financials: removed line for Capital and added depreciation schedule instead, as depreciation affects OI and capital is tracked outside of Planview. Opened PDSM ticket (INC033567375) to report bug in Financials tab, KPI aggregation method not working for average, returning sum instead. 12/29 - Feedback addressed: updated financials, added KPI actuals line and did QA review with ESPM team in lieu of a QA Domain Expert. 12/18 - Init changed to Business Only with PDSM ticket INC033461350. Change reviewed and approved by Mark Kowalczyk from EPM team. 12/10 - MMCA machine moved to production 12/8 - Attended Commercial L2 Triage meeting. Decided to remove impact to Commercial Portfolio. Update done in Planview. 11/11 - Submitted to L3 for approvals. Finance approval received on L2 Business Case 11/6 - Submitted L2 Business Case for approval from POD Financial lead 10/8 - Updated engineering design for first subset of machines received from vendor, pending delivery schedule 10/6 - Updated inititive name as per PMO 7/23 - MTYA machine moved to production | G: L3 | Active | L3 | 2025-07-23 | 2026-07-03
Business w/ Tech Initiative: LAC MEX Vendor invoice validator App Replacement |  | 166147 | Business w/ Tech Initiative | AMI - Mexico | Americas International | Jorge Ivan Jaramillo | On Track | In Progress | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: LAC MEX Limit or Eliminate PUPs for Dom Vol <10pcs |  | 168737 | Business Only Initiative | AMI - Mexico | Americas International | Susana Caro del Castillo | On Track | 07/01: On Hold | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: LAC MEX Employee payment of Insurance deductibles |  | 168740 | Business Only Initiative | AMI - Mexico | Americas International | Carlos Humberto Herran, Rodrigo Ojeda | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC Mex Reducing PUD to 1/week in Extended Areas |  | 168743 | Business Only Initiative | AMI - Mexico | Americas International | Susana Caro del Castillo | On Track | 07/01: On Hold | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Outsource Retail Network through RSV and Alliances |  | 168774 | Business Only Initiative | AMI - Mexico | Americas International | Jose Ignacio Gonzalez | On Track | The initiative was not approved to move forward due to the financial results identified in the analysis (L1), which indicated that the expected returns did not meet the required thresholds. Pod Lead is in agreement as discussed with MKT MD and Mgr/IO 11/10/2025 | C: L1 | Cancelled | L1
Business Only Initiative: LAC MEX REPSE Ops Implementation |  | 171104 | Business Only Initiative | AMI - Mexico | Americas International | Judith Almanza | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC MEX New Courier Job Family |  | 171108 | Business Only Initiative | AMI - Mexico | Americas International | Judith Almanza | On Track | The initiative will be on hold until FY27 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: LAC MEX Dim Weight CUAH Dual Head Enhancement |  | 179970 | Business Only Initiative | AMI - Mexico | Americas International | Silvia L. Gonzalez Alonso, Kyle R. Gilbert | On Track | 4/13 - Updated Financials/KPI Actuals for Mar'26. Missing depreciation Actuals, dependent on Finance resources. 3/12 - Updated Financials/KPI Actuals for Feb'26. Missing depreciation Actuals, dependent on Finance resources. Approved in L4 3/9 - Completed L# checklist and submitted to L4. Financial Actuals updated retroactively for the period since installation was complete. Milestones and money step marked as Complete. Money Step evidence uploaded. 3/9 - Initiative approved to move to L3. 3/3 - QA review complete. Changes made based on feedback: Money step description added and date changed to allow for PV approval timeline. Init submitted to L3 2/25 - Initiative ready for L3. Requested "Domain QA Expert" review as last step. Planned participation in dedicated hours on 3/3 2/12 - Initiative approved for L2 2/11 - Business Case reviewed with Finance Domain leads, approved to move to L2 and L3 12/30 - Initiative On Track. Working on LBC | I: L4 | Active | L4 | 2025-11-10 | 2026-03-13
Business w/ Tech Initiative: TS-VL4-NETWORK-EdgeOptimization-LAC |  | 188514 | Business w/ Tech Initiative | AMI - Mexico | Americas International | Jessica Kraus | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: [WIN] [COMM] CISCO LAC - Additional Business |  | 188522 | Business w/ Tech Initiative | AMI - Mexico | Americas International | Lisa Stockton | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Introduce New Revenue Streamlines for Retail |  | 193319 | Business Only Initiative | AMI - Mexico | Americas International | Sandra Mitzi Torres | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: (Intra-AS) Downgauging Intra-Asia flights to addre | 32306 | 6712 | Business Only Initiative | APAC - Air | APAC | Julian Man, Breckin Cheung | On Track | Schedule change completed for 11th Oct implementation. Operations alignment completed. Ready for launch. | K: L5 | Completed | L5 | 2023-08-07 | 2023-10-11
Business Only Initiative: (Intra-AS) Southeast Asia (SEA) to KIX connection | 32302 | 6904 | Business Only Initiative | APAC - Air | APAC | Paul Sousa, Hilary Tse | On Track | The SEA to KIX connection removal case is ready to move to L5 in WAVE as we have already had 3 full months of consistent run rate. | K: L5 | Completed | L5 | 2023-06-01 | 2023-08-01
Business Only Initiative: (Inter-Con) Supplementary AS-EU capacity via SPAC | 32304 | 6905 | Business Only Initiative | APAC - Air | APAC | Stella Shen, Cindy Chee | On Track | 1. In Nov’23 overall we under-perform by 42% (-156klb) due QR HAN-DOH NW'23/24 schedule changes. Later departing flight ex-HAN is unable to connect to required DOH-CDG; unable to recover on same lane due TT 2. Impact is partially mitigated by incrementally flexing up CAN-CRK/BKK-CDG/FRA QR lanes but limited by PT capacity availability on FX/CAN-CRK/BKK 3. Another contributing factor is the take down of origin CRK-DOH-CDG lane, where CRK origin IE/IEF is unable to fill minimal 1x AKE/day; volume is sent to CANH for consolidation to achieve cost efficiency 4. Overall net impact is -42% and expected to persists through NW'23/24 season till Mar'24. | K: L5 | Completed | L5 | 2023-08-01 | 2023-11-30
Business w/ Tech Initiative: (Both) Demand and Capacity Planning and Management | 32312 | 6907 | Business w/ Tech Initiative | APAC - Air | APAC | Tarun Madan, Alex Siu, Mishtu Sharma, Kai-Yong Tan, Fawzi Cheikh Bessaih, Aiman Khan | On Track | Decision pending at Dataworks for PFS (Preferred future state solution) ODS and DW are currently working on interim solution since Jan 2024. There has been a delay in delivery and as per the last MBR discussion with Andrea, the requirement for interim solution has now changed to add more regions (FrontDoor and Intra-Asia) | I: L4 | Active | TEMP L4 - Enter L4 | 2024-01-01 | 2026-08-28
Business Only Initiative: (Intra-AS) D2 SIN-SYD takedown | 32688 | 6931 | Business Only Initiative | APAC - Air | APAC | Paul Sousa, Hilary Tse | On Track | Further update to CLH assumptions, the P&L is revised and the valuation (benefits) changed from $7.1M to $6.4M. Reverting to L2 to revise the impact # per McKinsey's guidance. | K: L5 | Completed | L5 | 2023-08-08 | 2023-09-12
Business Only Initiative: (Intra-Asia) Comm Linehaul RFQ | 34458 | 6992 | Business Only Initiative | APAC - Air | APAC | Philip Tan, Kai-Yong Tan | On Track | Updated with projected deliverable with summed attachment and change update on value to U$9.5 million. | K: L5 | Completed | L5 | 2023-09-01 | 2024-04-30
Business w/ Tech Initiative: (Both) Dynamic, in-day D&C management (LIBRA) | 38250 | 7077 | Business w/ Tech Initiative | APAC - Air | APAC | Alex Siu, Mishtu Sharma | On Track | The initiative is a migration project from LIBRA tool in dataiku to OIP platform. The MTP happened on june 21, 2024 and the tool is now in production and is used by RMCC that helps the team take daily decisions on shorter term demand and capacity planning. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-02-01 | 2024-06-14
Business Only Initiative: (Intra-AS) D5 SIN-KIX connection removal | 39954 | 7098 | Business Only Initiative | APAC - Air | APAC | Paul Sousa, Hilary Tse | On Track |  | K: L5 | Completed | L5 | 2023-09-05 | 2023-10-20
Business Only Initiative: CLH Utilization Improvement - TPAC | 89083 | 7292 | Business Only Initiative | APAC - Air | APAC | Takeshi Ishikawa, Yee Yong Tan, Kai-Yong Tan | On Track | Pass the initative ownership to PNM per management direction. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-02-26 | 2025-03-31
Business Only Initiative: XMN New Jet City | 71897 | 7500 | Business Only Initiative | APAC - Air | APAC | Hai-Ming Zhang, Fei Faye Ning, Shao Wei Cui, Sally Lam | On Track | XMN flight improves TPAC IP HV for XMN city by 1 day TT and 1 day TT improvement for Quanzhou IP HV traffic Total 3-years XMN contribution at $84M on best case scenario and $67M for worst case driven by total subsidy income of $18M - $35M and DOC saving of $6M despite CLH buy protection in FY26-27 of $27M | I: L4 | Active | L4 Feedback Requested | 2024-02-09 | 2024-11-01
Business Only Initiative: TAO New Jet City | 71899 | 7501 | Business Only Initiative | APAC - Air | APAC | Shao Wei Cui, Sally Lam, Fei Faye Ning | On Track | The TAO flight was successfully fully launched on Oct 28th. The flights have increased from 1x to 5x per week. This achievement not only reinforces FedEx’s commitment to expanding into key markets,but also positions us with a market-leading value proposition in the TAO-TPAC market. | K: L5 | Completed | L5 | 2024-02-09 | 2025-09-15
Business Only Initiative: (Intra-AS) PVG-KIX daytime flight | 85634 | 7569 | Business Only Initiative | APAC - Air | APAC | Hilary Tse, Paul Sousa | Some Issues | Pending China customs approval on CAN-PVG transshipments to launch this new daytime flight. China team is following up and attempting for trial run in Summer'25 if possible. | E: L2 | Cancelled | L2 | 2024-08-01 | 2024-10-22
Business Only Initiative: [Intra-AS] Overfly CRK on D2 SYD-CRK-CAN upon Poco | 90937 | 7570 | Business Only Initiative | APAC - Air | APAC | Hilary Tse, Eun-Suk Ahn | On Track | Launched together with Pocono flight in Nov'24 Baseline has been updated for FY25 | K: L5 | Completed | L5 | 2024-07-22 | 2024-10-28
Business Only Initiative: [ASPIRE] Pocono-Lite (CAN-CGK-SIN-BKK-CAN and CAN- | 73543 | 7579 | Business Only Initiative | APAC - Air | APAC | Hilary Tse, Paul Sousa | On Track | The Growth Initiatives #73536 [ASPIRE] Grow CGK Inbound and #73538 [ASPIRE] Grow JHB Inbound already moved to L2. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-01 | 2024-10-29
Business Only Initiative: [ASPIRE] Re-flow JHB Inbound vol through SIN inste | 73548 | 7582 | Business Only Initiative | APAC - Air | APAC | Hilary Tse, Paul Sousa | On Track | The Growth Initiative #73538 [ASPIRE] Grow JHB Inbound is already approved to move to L3. This is an enablement initiative to support JHB growth. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-18 | 2024-10-29
Business Only Initiative: [ASPIRE] KUL pure split build up by selected origi | 73554 | 7586 | Business Only Initiative | APAC - Air | APAC | Hilary Tse, Paul Sousa | On Track | This is an air network enablement initiative to support #73540 [ASPIRE] Grow Greater KUL Inbound, which is already moved to L2. | K: L5 | Completed | L5 | 2024-06-03 | 2024-07-05
Business Only Initiative: [S&P] China_CTUA domestic commercial linehaul tend | 5844 | 7799 | Business Only Initiative | APAC - Air | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track | The money step is completed, ready to start tracking the KPIs and the generated savings. Proofs of execution has been uploaded in the attachment section however the KPI and the Impact lag behind because of delay in getting the relevant data for calculation. | K: L5 | Completed | L5 | 2022-12-01 | 2022-12-01
Business Only Initiative: TSN-PEK-CAN Domestic Charter Flight | 88432 | 8187 | Business Only Initiative | APAC - Air | APAC | Shao Wei Cui, Yan Pan, Fei Faye Ning | On Track | As of October 25, we have achieved the service levels outlined in the business case, with call-in cutoffs set at 16:00 for PEK and 15:30 for TSN. Additionally, as of November 11, the GQTTI has been updated, expanding inbound sameday service coverage to 88% of PEK zip codes (covering 96% of IB volume) and 60% of TSN zip codes (covering 60% of IB volume). Currently, the flight has been officially launched on the 5th of July, 5X per week from D1 to D5, and it is operating normally on a daily basis. | K: L5 | Completed | L5 | 2024-06-03 | 2024-12-31
Business w/ Tech Initiative: [CLONED FROM #38250/New 80703] Short-Term Interven | 80703 | 8267 | Business w/ Tech Initiative | APAC - Air | APAC | Alex Siu | On Track | Envisioning to start after AirPlan completion. Effort to focus on adoption of already developed D&C tool suites and alignment with global D&C than to move forward with more development. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-07-22 | 2024-09-02
Business Only Initiative: (Intra-AS) HKG-BKK & HKG-ICN TNT CLH termination-c | 35764 | 8373 | Business Only Initiative | APAC - Air | APAC | Takeshi Ishikawa | On Track |  | K: L5 | Completed | L5 | 2023-06-12 | 2023-10-06
Business w/ Tech Initiative: ARROW - Air Routing Regional Operation Workstation | 92869 | 8809 | Business w/ Tech Initiative | APAC - Air | APAC | Shawn Bernhard, Kai-Yong Tan, Alon David Honig | On Track | Update 30 Sep '25: * Done: AMS uld type * WIP: To make capacity across shipment origin visible and editable on the same page Update 10 Sep '25: * Done: Remarks popup box & change audit log * Done: Adjust app to allow for inclusion of CT & FXL teams * WIP: AMS uld type Update 14 Jul '25: * Done: Loose lane * On hold: 777 LE. Pending exec approval * WIP: Remarks popup box and audit logs Update 18 Jun '25: * Both PowerApps and PowerBI have been migrated to the new environments. * Shawn: Working on user migration * Developers: Working on Loose lane handling and 777 load equivalents Update 10 Jun '25: * PowerApps to be migrated on 13 Jun to new dev/test/prod environments Update 27 May '25: * Migration by end-June might be delayed due to incorrect system configuration * In the meantime, to work on small features (to maintain overall timeline) | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-01 | 2026-12-31
Business Only Initiative: [Intra-AS] 2x KIX-PVG-KIX Cancellation | 77067 | 9407 | Business Only Initiative | APAC - Air | APAC | Paul Sousa, Adi Putra | On Track | Downgauge is implemented. | K: L5 | Completed | L5 | 2024-06-11 | 2024-07-05
Business Only Initiative: [Intra-Asia] CRK loop downgauge from B777 to B767 | 88480 | 9418 | Business Only Initiative | APAC - Air | APAC | Adi Putra, Paul Sousa | On Track | Downgauge has been reflected on PHX schedule for May'25. Hull will be used for F4 Upgauge. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-03-14 | 2026-03-12
Business w/ Tech Initiative: APAC Data Hub Migration |  | 85741 | Business w/ Tech Initiative | APAC - Air | APAC | Rajesh Mohan, Vaibhav Gupta, Alon David Honig | On Track | Project has completed L0 sufficently quickly. LSSI provided us with the credentials to access FIPs | I: L4 | Active | L4 | 2024-07-22 | 2026-02-27
Business Only Initiative: CLH Utilization improvement - FD |  | 89540 | Business Only Initiative | APAC - Air | APAC | Colin Ta, Stella Shen, Cindy Chee, Kai-Yong Tan | On Track | Lane level review is ongling, and actions/Milestone has being taken respectively to drive the utilization improvement | I: L4 | Active | TEMP L4 - Enter L4 | 2024-10-01 | 2024-10-15
Business Only Initiative: Master Yoda Phase 1 |  | 89543 | Business Only Initiative | APAC - Air | APAC | Hilary Tse, Paul Sousa | On Track | Master Yoda received officers' approval for Module 1 & 2 to launch by Apr'25. Baseline updated to FY25 [08Apr'25] | K: L5 | Active | L5 | 2025-02-28 | 2025-03-31
Business Only Initiative: Re-route US to APAC (SIN,BKK) via KE IA network |  | 90311 | Business Only Initiative | APAC - Air | APAC | Sisi Jin, Paul Sousa | On Track | Conducted trial run | E: L2 | Cancelled | L2 Feedback Requested
Business Only Initiative: CLH RFQ Intra Asia |  | 90317 | Business Only Initiative | APAC - Air | APAC | Yuen-Ting Chan, Takeshi Ishikawa, Sisi Jin | On Track | Green | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-01 | 2025-08-01
Business Only Initiative: Tactical Local CLH Capacity Procurement |  | 92631 | Business Only Initiative | APAC - Air | APAC | Chi-On Andy Yeung | On Track | TLC initiative for mass market is integrated into D&C planning and management process (Strategy Seq ID. 6907). Per Finance, most of individual customer demand can be covered by BP allocation, the target of revenue generation under TLC initiative cannot be projected. | C: L1 | Cancelled | L1
Business Only Initiative: QDM for Intra Asia redesign and NSL improvement |  | 105956 | Business Only Initiative | APAC - Air | APAC | Yiu-Fai Tsang, Jimmy Zhang | On Track | Refining opportunity statement and evaluating options | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval | 2025-09-03 | 2025-12-31
Business Only Initiative: O4 Upgauge 777 |  | 106982 | Business Only Initiative | APAC - Air | APAC | Adi Putra | On Track | Implemented by Feb'25 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-12-19 | 2025-02-03
Business Only Initiative: CLH Utilization Improvement - IA |  | 106985 | Business Only Initiative | APAC - Air | APAC | Eun-Suk Ahn, Sisi Jin | On Track | 1. Calculated CLH cost avoidance based on BP25 as the baseline and considered that PNM has improved CLH IA LF from 85% to 88%. 2. The cost saving only projected from 88% to 90% FY26 target. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-02 | 2026-05-29
Business Only Initiative: Cargo Nets - Local procurement in APAC |  | 107001 | Business Only Initiative | APAC - Air | APAC | Jeromy Lai | On Track | Change already implemented since FY25 Q4. Budget for FY26 already submitted through PPMS. | K: L5 | Active | L5 | 2024-08-08 | 2024-12-31
Business Only Initiative: PEK-CAN domestic charter flight-Leg change |  | 144057 | Business Only Initiative | APAC - Air | APAC | Fei Faye Ning, Shao Wei Cui | On Track | current is L1, as PEK-CAN charter flight is suspended now, so we will change ths status to on hold, will back to active when the flight is recovered. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Launch of D1 HAN-CAN OB flights |  | 160226 | Business Only Initiative | APAC - Air | APAC | Paulo Galgo, Hilary Tse, Darren Han | On Track | on track | K: L5 | Active | L5 | 2025-08-19 | 2025-09-01
Business Only Initiative: HKG-TPE-KIX Reroute to HKG-KIX |  | 165171 | Business Only Initiative | APAC - Air | APAC | Sally Lam | On Track | Revise schedule is updated | K: L5 | Active | L5 | 2025-09-15
Business Only Initiative: Air Cargo Market Intelligence |  | 191993 | Business Only Initiative | APAC - Air | APAC | Julian Man | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: New Domestic book In and storage surcharge | 33066 | 6848 | Business Only Initiative | APAC - AU Domestic | APAC | Benjamin Dean, Con Gallanos | On Track | 19 Mar 2025 - Economic conditions remain challenging with pressure on retail consumer spend dampening demand for book in shipments. | K: L5 | Completed | L5 | 2023-06-12 | 2024-04-12
Business w/ Tech Initiative: PIE Review | 56581 | 6851 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Elliot Berry, Con Gallanos | On Track | 6/11 - 4 Stations live on the new PIE scheme, results and feedback from week 1 are positive. 16/4/25 - Reviewed post pilot results with MDs and seeing good benefits of the new PIE scheme. All metro stations to be rolled out by mid May and 4 Regional stations to be completed by end May. Finalising revised financials and go live dates for L3 submission. 1/5/25 - Scope singed off my Ops MD. Financials and rebaseline being finalised and will be sumbitted to L3 by 9/1/25. 16/7/25 - Request to cancel as this initiative has been stuck in L2 - Feedback requested for months. We've been on calls with numerous teams and raised several IT tickets, but no one can move it back to a stage where we can correctly update the baseline and financials. Please cancel and we will reraise the initiative from scratch. Thank you | E: L2 | Cancelled | L2 Feedback Requested | 2024-08-21 | 2025-11-07
Business Only Initiative: Direct Serve Contractors (DSC) 2.0 | 69081 | 6853 | Business Only Initiative | APAC - AU Domestic | APAC | Elliot Berry, Con Gallanos | On Track | 27/5/25 - Financials: Initiative Rebaselined to FY'25 - Strategy View: Baseline Fiscal Yr of Intiative changed to FY'25, however the Baseline Value is hardcoded and cannot be changed. 1/5/25 - Now progressed to L3. Recruitment and rollout continue. Strong productivity results over the past 2 weeks. Exceeded April recruitment target. 11/6/25 - 89 DSC's onboarded, on track with target and on track with SPH and productivity targets. 24/9/25 - Cancelling this initiative and raised PV Request.0013782 as business with Tech to enable CDAS as a replacement. 2/4/26 - Initiative reactivated as closed PV 168571 as we were unable to get CDAS in AU within a reasonable timeframe. Will continue to tracks costs and savings for DSCs under this initiative. | G: L3 | Active | L3 | 2024-01-10 | 2026-06-26
Business Only Initiative: Dispatch/DRP Supervisor reduction | 78460 | 6855 | Business Only Initiative | APAC - AU Domestic | APAC | Elliot Berry, Con Gallanos | On Track | 16/4/24: Entered into WAVE 6/11 - Details submitted and approved. 17/12/25 - Benefit realised, no further updates | K: L5 | Active | TEMP L5 - Enter L5 | 2024-01-01 | 2025-05-30
Business Only Initiative: Courier AM On Dock time reduction | 78637 | 6857 | Business Only Initiative | APAC - AU Domestic | APAC | Elliot Berry, Con Gallanos | On Track | 27/5/25 - Financials: Initiative Rebaselined to FY'25 - Strategy View: Baseline Fiscal Yr of Intiative changed to FY'25, however the Baseline Value is hardcoded and cannot be changed. 6/11 - Initative progressing well, hitting weekly financial targets and slightly off the KPI, but a significant improvement on basline. 17/12/25 - On track and hitting targets. BAU now. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-08 | 2024-10-18
Business w/ Tech Initiative: Fiji Direct Serve Conversion | 32976 | 6945 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Stephen Williams, Koey Cheng, Laurentius Adi-Kurniawan | On Track | Project launched and ready for L4 submission Due to unavailablity of actual financials, the forecasted numbers have been removed. L4 submission to be made without Actual financials, as aligned with Planview SME (Krishnaprasad Ramachandran) | G: L3 | Active | TEMP L3 - Enter L3 | 2023-03-01 | 2026-04-30
Business Only Initiative: Non Ops Saving- Mascot office optimization | 33093 | 6955 | Business Only Initiative | APAC - AU Domestic | APAC | Benjamin Dean, Jessycha Jessycha | On Track | 10/29 - Update IO name | K: L5 | Completed | L5 | 2023-09-13 | 2023-11-30
Business Only Initiative: Rate escalation without revenue loss - Risk mitiga | 33095 | 6958 | Business Only Initiative | APAC - AU Domestic | APAC | Chontelle Bright, Matt Daniels | On Track | Field Sales team nationally working through 1555 customers who received Book-In & Storage to identify any down trade / lost business due to new surcharge. | K: L5 | Completed | L5 | 2023-07-03 | 2024-05-31
Business Only Initiative: Rate escalation without revenue loss - Rate mitiga | 33096 | 6960 | Business Only Initiative | APAC - AU Domestic | APAC | Chontelle Bright, Matt Daniels | On Track | Weekly standup call commenced 17th Aug with sales management to understand any customer rate escalations. | K: L5 | Completed | L5 | 2023-07-03 | 2024-05-31
Business Only Initiative: Rate escalation without revenue loss - Risk mitiga | 33234 | 6962 | Business Only Initiative | APAC - AU Domestic | APAC | Chontelle Bright, Matt Daniels | On Track | Weekly standup call commenced 17th Aug with sales management to understand any customer rate escalations. | K: L5 | Completed | L5 | 2023-07-03 | 2024-05-31
Business Only Initiative: Rate escalation without revenue loss - Manual nati | 33235 | 6964 | Business Only Initiative | APAC - AU Domestic | APAC | Chontelle Bright, Matt Daniels | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-31
Business Only Initiative: Vehicle Reverse Sensor retrofit | 76341 | 6993 | Business Only Initiative | APAC - AU Domestic | APAC | Brent Francis, Max Maim, Angela P. Campbell | On Track | 15/09/2025 - Have realigned costs with a 1.52 converson rate rather than the 1.43 that has been input. - Everything else is done with the correct conversion rate of 1.52 18/08/2025 - Installation of Sensor Kit into Vehilces is now at 100% completion as of Today. - 699 of 699 Installed. - Awaiting conformation to Push to L4 15/08/2025 - Installation of Sensor Kit into Vehilces is currently at 99.86% - 698 of 699 Installed - 1 Unit remaining -Perth airport 12T roller bed truck (1ICS700) - Now booked for Monday 18th August. 15/08/2025 - Have re-aligned Instalation Completion Date (Initiatives Milestone)to 1st September to align with Vendor delays as we close out the remaining 7 installations across Newcastle (6) & Perth (1). 14/08/2025 - Have re-aligned Money Step to line up with changed expected instalation compeltion of 30th August (Vendor Delays have impacted Install Time). L4 now the 1st September 2025. - Will progress for L4 pending review and approval. 11/08/2025 - Installation of Sensor Kit into Vehilces is currently at 98.86% (as at8th August '25) - 691 of 699 Installed - 2 depots remaining (Perth x 1 & Newcastle x 9). -Perth airport 12T roller bed truck (1ICS700) was booked for last Monday (final unit) but unable to released due to accident damage on the other airport roller bed truck (1SGB631). - Re-booking date TBA. Newcastle auto electrician (NAE) experiencing tradesperson shortage (2 electricians resigned) - Remaining 7x vehicles completion ‘mid-August'. - Will Progress to L4 to keep initiative moving forward. 05/08/2025 - Have re-aligned Money Step to line up with expected instalation compeltion of 15th August (Vendor Delays have impacted Install Time). L4 now the 18th August 2025. 04/08/2025 - Installation of Sensor Kit into Vehilces is currently at 98.14% (as at 31st July '25) - 686 of 699 Installed - 3 depots remaining (Perth x 1, Canberra x 3 & Newcastle x 9). - Perth airport 12T roller bed truck (1ICS700) booked for Monday 4th Aug – final unit. •Newcastle auto electrician (NAE) experiencing tradesperson shortage (2 electricians resigned), the Remaining 7 vehicles completion scoped by mid-August. •Canberra – 3 vehicles remaining which are scheduled for completion across the weekend. 30/07/2025 - Have re-forcast Installation Completion Date by another two weeks (15th August) as we finalise the remaining 20 Installs - 3 depots remaining (Perth x1, Canberra x 7 & Newcastle x 12) - Some issues with Vendor and Vehicle availability without hindering operations (especially regional). 25/07/2025 - Installation of Sensor Kit into Vehilces is currently at 97.14% (as at 25th July '25) - 679 of 699 Installed - 3 depots remaining (Perth x1, Canberra x 7 & Newcastle x 12) 21/07/2025 - Installation of Sensor Kit into Vehilces is currently at 96.57% (as at 18th July '25) - 675 of 699 Installed - 3 depots remaining (Perth x1, Canberra x 10 & Newcastle x 13) - Redbank is now completed! 15/07/2025 - Installation of Sensor Kit into Vehilces is currently at 96.13% (as at 4th July '25) - 671 of 698 Installed - 4 depots remaining (Redbank x2, Perth x2, Canberra x 10 & Newcastle x 13) 10/07/2025 - Have modified Instalation Completion Date (Initiatives Milestone) from 11th July to 31st July to align with Vendor delays as we close out the remaining 5% across Newcastle and Canberra. 07/07/2025 - Installation of Sensor Kit into Vehilces is currently at 94.13% (as at 4th July '25) - 657 of 698 Installed. - An additional 3 sensors are being fitted in Redbank - 4 Depots to close out. 27/06/2025 - Installation of Sensor Kit into Vehilces is currently at 93.24% (as at 27th June '25) - 648 of 696 Installed. - Gold Coast now 100% pushing 8 Depots to completion - 4 Depots to close out. 23/06/2025 - Installation of Sensor Kit into Vehilces is currently at 91.38% (as at 20th June '25) - 636 of 696 Installed. - Adelaide now 100% pushing 7 Depots to completion - 5 Depots to close out. 10/06/2025 - Have amended the Instalation Completi | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2024-03-01 | 2025-08-29
Business Only Initiative: Manage the growth and structure of Intermediary ac | 35023 | 7001 | Business Only Initiative | APAC - AU Domestic | APAC | Chontelle Bright, Matt Daniels | On Track | Working on regaining ShippIt SRG business that was lost last year >US$800k | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-31
Business Only Initiative: Removal of some 2nd Run Shuttles for SW2 and RSE | 55956 | 7120 | Business Only Initiative | APAC - AU Domestic | APAC | Dean Bright, David B Williams | On Track | Initiative now in place effective January 10th, 2024 (Wednesday) 12/2/2024 - Waiting on L3 approval so I can enter January's results 8/4/2024 - L3 approved, January and February numbers have been entered, waiting for temp labour report from finance for week 44 to finalize March's numbers 5/12/2024 - Missed Novemebr target by approx $11k (still overall the project is ahead of target). This was purely due to increased temp labour / Outside Hire required to deliver excess volumes during peak period. | K: L5 | Completed | L5 | 2023-10-23 | 2024-05-21
Business Only Initiative: FY25 General rate increase revenue capture | 89761 | 7144 | Business Only Initiative | APAC - AU Domestic | APAC | Joyitesh Deo, Chontelle Bright | On Track | Completed | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2024-07-08 | 2025-05-30
Business Only Initiative: Domestic- Manual handling surcharge- additional re | 56400 | 7219 | Business Only Initiative | APAC - AU Domestic | APAC | Joyitesh Deo, Monika Eades | On Track | Money step is already realised with this project as it already launched. Need CLH approval to report the money step to this project. | K: L5 | Completed | L5 | 2023-09-18 | 2024-03-01
Business w/ Tech Initiative: Remote surcharge- distance based pricing | 56420 | 7220 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Joyitesh Deo, Mark Bredin | On Track | 14/08/2025 Surcharge Launched 06/30/2025 UAT testing of Revenue DB modification for remotes. 06/17/2025 CMS Prod released 28th May Developments commenced on invoicing, on line rate card and Databases. 04/28/2025: UAT testing loop progressing. 04/14/2025: UAT Testing on CMS work progressing. - UAT near completion by commercial team - UAT in progress by Billing team 03/25/2025 IT CMS devlopment work commenced. 11/11/2024 IT Commercial and Back office meeting re remote tiering Set up Epic for remotes in Agility 11/04/2024 Competitor Distance based charges investigated. 10/28/2024: P&E Post Code Suburbs Tiered remote groups analysed by Weight bands: Under 10kg, Under 30Kg, over 68Kg. 84% under 30Kg. 12% over 68Kg. PC Suburbs by Regional, Rural & over 70Km analysed by Weekly con count compated to existing remote flag - none over 100. 44% remotes 50 - 100 weekly con 30-50 45%, 20-30 46%, 10-20 65%, 5-10 63%, 1-5 69%, 0-1 70%. 9/08/2024: Cross Functional Team selected, PECs Document Presented with requirement for completion of Functional requirement statements to be completed by Tue 13th Aug. Methodology to classify Remote Tiers established, Grouping of Post Code Suburbs into Tiers being worked on for discussion with P&E. | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2024-07-01 | 2025-08-07
Business w/ Tech Initiative: Win Back B2B and B2C >30kg shipments | 75350 | 7313 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Heath C. Elliott, Eddie Johnson | Some Issues | **Cancellation Request 29-01-2026** From the Business Owner and MD of Sales Monika Eades. "Path file feasibility inconsistent with data requirement to accurately determine a residential address. Commercially we have adopted a residential waiver under surcharges for light weight as BAU in domestic, heavy weight shipments is captured under the pallet initiative" **05/26 FY25 Baseline applied **04/16** PAF quality during testing was Poor to say the least. Ops and IT met with Intechand Aust Post to discuss the results. Austpost said they have an updated PAF file in May and Intech comitted to update thier Grammer file. Scott B will perform another round of testing the PAF quality and then the business will decide if the quality is good enough to deploy to prod for billing. If not then a decison on the initiativeitself may have to be made. **11/13** Complete - The 1st phase is a simple flag in the API payload allowing our customers to flag the collection and/or delivery address as residential so that the return quote includes any relevant residential surcharges. Completed and released, customers are being provided the updated API specifications. (note some prefer to wait for phase 2) In Progress long term - 2nd phase is to allow customers to provide the full collection/delivery address, the address will be cleansed and if understood it is validated against Australia Post's Postal Address File (PAF) then classified as residential or not. This phase is due for delivery end of March 2025 and at this stage is still green. In Progress now - incoming Dot Net code ongoing Next Steps next - checking for address overrides in FMS. Our operational system FMS holds certain addresses where operations and sales agree that the detail in PAF is not correct. Risks - Minor - The PAF trail by operations (the first real implementation phase for PAF) is behind schedule. This should not impact as PAF in UAT is working and it will be released in production well before our API is deployed to prod. Minor - The migration from our current OSVs to Accenture during the final weeks may impact delivery. Most of the development is being handled by an in-house developer. Move to L2 to progress IT development (TCH) **03/06** Update to Zach Meekins - Mgr IT Strategic Program Management Office [PMO] Project is now Phase 1 Tech completed, Phase 2 tech completed not deployed. 7313 relies on the PAF (Postal Address File) which determines if delivery address is residential or commercial. This PAF work was completed through the PAF Core enablement initiative, which was completed prior to DRIVE. PAF relies heavily on Australian Post’s data to determine if an address is residential or commercial. During testing of the 7313 initiative, it was identified that PAF (Postal Address File) has less than 50% accuracy. Due to low PAF accuracy the 7313 initiative cannot be activated as there is a high potential FedEx would be unnecessary charging some customers residential fees. Meeting set for 6March to understand what measures will be taken by the vendor, and potentially Australian Post, to increase the residential v commercial address accuracy. This may take months to remediate. Due to potential delay, business leadership (Peter Langley, VP Ops Australia) discussing looking at creating an internal solution to determine which address is residential v commercial to expedite this. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-09-09 | 2026-03-02
Business Only Initiative: Matraville - Removing Day 7 Sort Operations | 96926 | 7329 | Business Only Initiative | APAC - AU Domestic | APAC | Dean Bright, Con Gallanos | On Track | •All employee consultation sessions were completed last week •Over Friday 8th November to Sunday 10th November, the Matraville leadership team issued formal letters to all impacted employees giving them seven (7) days’ notice of their new roster •The new roster begins next Monday 18th November •The first Sunday that we will be not operating the sort will be Sunday 24th November •During the week commencing 25th November, the team will work with Navin to pull the STATS to see if anything did not get sorted or moved and to gauge any service impact. The NSL will not be available until 2 weeks after Update 25/11/2024 1.All managers on site along with 3 supervisors. Paul Tipping (Regional LHL) also joined us to ensure no issues on the trucking side which was a great help 2.The planned manning was 80 in LSO and 18 in the Bond. The actual was 80 in LSO and 17 in the Bond 3.Both FedEx flights (FX6013 and FX0077) arrived on time, and we already had the FX6013 from Friday staged for sorting 4.All commercial flights received and processed except the SQ211 which is arriving too late (please see my other email to APAC on this) 5.The plan volume was 31,887 add we actually handled 32,733 packages 6.All Linehaul departed on time 7.3 units of Non Con rolled over due to time and no space on the Road Linehaul units 8.The Pre Clearance rate was only 88% (impacted Bond) Update 5/12/2024 Plan is in place and we have completed 2 x weekends of no Sunday sort. We are still working through the financial benefit for Novemeber. All is on track | K: L5 | Completed | L5 | 2024-09-30 | 2025-02-28
Business w/ Tech Initiative: AU domestic transformation due to ProIV retirement | 96745 | 7748 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Eddie Johnson, Prashant Menon, Alex Vasilevski, Vicky Shih | On Track | **Week beginning 02/03/2026** Conceptual Architecture meeting continue...Extended Warranty, Visibility, Charge Codes, Collaborative Shipping Final planning 2nd Memphis Workshop **Week beginning 23/02/2026** Conceptual Architecture meeting continue...SWMY, Grren to Purple Billing, Intro to Test Team beginning to discuss testing process, Visibility Planning 2nd Memphis Workshop **Week beginning 16/02/2026** Chinese New Year lower number of meeting, Conceptual Architecture meeting continue...Pickup Epic Planning 2nd Memphis Workshop **Week beginning 09/02/2026** Conceptual Architecture meeting continue...ShipNow and Paperless Shipping (eReturns), Shipping and Quote, Special Services, Shipment Flow & Label Generation, SWMY, Order Supplies, **Week beginning 0202/2026** Conceptional Architecture meetings continue,. Shipping Quote, Pickup, PASGO, SWMY SPS Domestic Alignemtn ongoing Digitial Migration Cross Functional Workshop Key decisions made during the workshop include: * Adopting a phased, batched customer migration approach rather than a "big-bang" simultaneous migration * Further defining customer personas with tailored migration strategies and communication approaches * Aligning product transition communication with the overall migration timeline (Jan 2027) * Critical dependencies centre on January 2027 system readiness for EAN (Enterprise Account Number), MAGIC (online platform) with Domestic Shipping, and AU domestic systems to support the migration commencement in Feb/Mar 2027. * Domestic SpS to be included in the customer migration planning * Four disctinct Personas developed - Power Users / API Customers / Relationship Led // Digital SMall business **Week begining 19/01/2026** Refinement of Digital ATs with CT and Digital Marketing, Pickup ATs, FedEx Dotcom with EU and US. SPS product and direction meetings with AU Operations VP and senior leaders. Sessions with local development teams to understand the requirements and asks for them. To get some work started this PI. A series of pre-workshop meetings on Migration being held prior to the in-person workshops first week of Feb. **Week begining 12/01/2026** More daily calls working through ATs. Product, Dispatch, Revenue Accounting, Case/CE, Pickup. FedEx DotCom with EU and US. Sessions with local development teams to understand the requirements and asks for them. **Week begining 5/01/2026** Series of daily calls to work through the Ability To statements so that teams understand what is required of them. Shipping and Pricing, Operational Lens, Invoicing, Magic Load Times, FedEx DotCom & Pickup SCO Greenlight required details and high level estimates of costs for the expanded scope. Details below: Expected FY Half Start: **FY26 H1** Expected FY Half End: **FY28H1** Level of Effort for all SCO ARTs impacted (select one): XS (1 team, .25-.75 PIs) S (1-4 teams, .75-1 PIs) M (4-6 teams, 1-2 PIs) L (6-8 teams, 2-3 PIs) **XL (8-9 teams, 3-4 PIs) it is essentially 3 of these** If more information is known such as specific # of TPIs or known ART team makeup (internal vs. external resources), please provide to better inform L2 costing, but not required if unknown: The high level TPI estimate is 36 PIs these will run in parallel Non-Labor IT expenses/IT Labor not part of ART teams (if known): Unknown List of ARTs Impacted (if known): **SCO IA AUS NZ Consolidated ART (ANZ-ART) SCO TN ELRS ART SCO P&D Run and close ART SCO Solution Train impacted: P&D, IA, Transport Network** **Weeks 9/12/25 - 19/12/25** Series of in person workshops in Memphis with representatives from all of the impacted ARTs (except Magic) were held to further understand and breakdown the asks of the initiative. SPARX is the repository for architectural artifacts. The group broke the initiative into eight Epics 1. Product 2. Shipping & Quote 3. Invoicing and Settlement 4. Pickup 5.Visibility 6. MAGIC Load Times 7. FedEx DotCom Applications 8. Case and Customer Support Sparx Lin | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2027-05-04
Business Only Initiative: Non Ops saving - Fleet | 32939 | 8033 | Business Only Initiative | APAC - AU Domestic | APAC | Christopher Pierce, Jeroen De Boer | Some Issues | Tracking deliveries each month ongoing, deliveries will flow through into 2025 due ot supply issues with the Auto Mezz trucks 15 units impacted. Deliveries will take place over the course of the year with final deliveries expected by approximately October. 29/04/2025 - No deliveries made in April, estimate a total of 4 to come through next month. 21/05/2025 - 2 Vehicles are almost finished being built next delivery looking to be roughly End of June/Early July. 27/05/2025 - No new updates 03/06/2025 - No new updates still tracking for 2 deliveries end June early July. 11/06/2025 - No new updates still tracking for 2 deliveries end June early July. 08/07/2025 - 2 vehicles to be delivered by End of July 30/07/2025 - 2 Vehicles delivered 30/07/2025 13 remaining. 01/09/2025 - 3 Vehicles to be delivered Mid September 7/10/2025 - 9 vehicles remaining deliveries due to be finalised by end of November. 31/10/2025 - Request to move money step to 'completed' | I: L4 | Active | TEMP L4 - Enter L4 | 2023-05-22 | 2025-10-28
Business w/ Tech Initiative: Improve Station Labour Productivity | 32970 | 8297 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Kel Kent | On Track | 09/15 - Weekly VALET Reports consolidation. PnE updates to major solutions. 09/09 - Cadence call with US VALET team on IT componets for next step reporting. Follow up on VALET connect issue. 09/02 - Work with PnE and IT on next steps. Cadence call with US VALET and Forecasting. 08/18 - Finalise V Reports presentation for OPS Leaders. Continued review of VALET OPS PnE, IT Template and cadance. 08/12 - Review requirements template for IT, OPS PnE. Check data quality of report in Production. 08/05 - Followup call on Gross pkgs and Reports. Update of PERA and SRRA with SME, Endineer. 07/30 - MDs Snr Managers OPS Workshop summary material. VALET SME follow up cadence from workshop. Develop V Reports material for OPS. 07/23 - Create and deliver VALET presentation for MDs Snr Managers OPS Workshop. Further progress work for Reports. 07/14 - IT to source US VALET requirements templates to progress next component. PnE to review. PnE SME work on adjustment tasks to support KPI Dash reqirements. 07/07 - Progress testing and confirm upload. Provide Report confirmation to IT. 06/ 30 - Test draft Report and provide feedback to IT, some delay due to VALET issues.Requires action to date format and review upload format. Share upload knowledge with additional SMEs. 06/23 - Test draft VALET Report both in VALET and data build. Esculate issues with IT and PnE OPS to resolve. 06/ 17 - Initial IT Test Report completed awaiting next steps. 06/04 - Build OPA / table to support IT requirement. IT to run test Report with included changes. 05/29 - Test IT current work and solution. Critique ODA rules for report. 05/21 - Work with IT to progress VALET Report. Quarterly cadence call with US. Follow up cadence call with SMEs on refining additional Tasks. 05/13 - Planview financial updates. 05/ 07 - Review and feedback on finanacials. 04/ 29 - Confirm revised baselines and update PV. Review and feedback additional IT questions. 04/22 - IT User Story clarifications. Review and adjust baselines to support FPnA request. 04/15 - SYD Basin Engineers status call and updates.IT PV L4 followup. 04/07- Engineers status call and updates. NZ Cadence calls. 04/01 - NZ Cadence calls. 03/25 - NZ Cadence calls. Prestige call presentation. 03/19- Cadence calls NZ.Forecast review and updates. 03/12 - NZ Cadence calls.Local support. 03/05 - Weekly cadence call with NZ. SME Leads cadence call with progress updates and go forward. 02/26 - Follow up cadence calls with NZ Stations post Go Live. Monthly updates including Prestige. 02/10 - Go Lives in NZ full week travel plus 3 days onsite fo Go Live in AKLA and covering WLGA and CHCA remotey with Train the Trainer SMEs. 02/03 - Progress PnE formulated Forecast using US methods. Communicate to SMEs new updated Forecast. NZ cadences to prep for Go Live. 01/30 - Commence refinining Planned vs Actual Reporting. Communicate interim Forecast for FEB, MAR 2025. 01/22 - Travel booked for NZ Go Lives. NZ Cadence calls. QLD Regional South cadence cals. 01/15 - NZ bi weekly pre-requisite calls and prep. Travel requests for NZ mid Feb. QLD Regional cadence move oustanding solutions to production and support. 01/08 - Re convene weely Cadence calls with NZ in preperation for Feb Go Live. Run through initial soltions with NZ team and bridge any gaps.Follow up call scheduled for QLD Regional support and Initiatives. 12/18 - AKLA, CHCA, WGLA pre - requistites. NZ Admin shheets, belt configuration and flow rates for builds. Go Live NZ Travel approvals. 12/10 - Update presentations, continue builds for NZ, support Engineers with new builds. 12/05 - Follow up QLD and VIC Regionals on Initiatives. Progress and provide templates to NZ, cadence call. Advance builds for AKLA, CHCA and WLGA. 11/25 - Work with AU IT on local solution and update SCORED template. Progress NZ VALET pre- requisite supported by PnE SMEs. Followup Regionals with outstanding Initiatives. 11/20 - Money Step completed 11/19 - Progress NZ VALET setup, multiple Cadence calls | K: L5 | Completed | L5 | 2024-08-09 | 2024-11-18
Business Only Initiative: AU Excessive Annual Leave Management | 58315 | 8417 | Business Only Initiative | APAC - AU Domestic | APAC | Renae N. Bullock, Carol Ng | Some Issues | 11/02/2026 - EAL through December and January reduced due to leave booked by employees as well as planned shut down of functional areas over the festive season. EAL accruals per timeline breakdown sit as; 8-12 weeks = 78% of EAL 12-16 weeks = 15% of EAL 16+ weeks = 7% Managers and their relevant HR support to focus on the 38 employees with 16+ weeks of EAL and further reduce the liability across 8-12 weeks. 8/12/2025 - Increase in EAL due to reduction of leave accessed through November as we move through peak period. Managers encouraged to ensure M&P staff take leave during December and January especially functions falling within required shutdown period. Ops Managers encouraged to have frontline teams forward book leave for January post peak period to further reduce EAL balances within the function. 10/07/225 - Small reduction in Excessive leave for June with high valumes of M&P staff accessing leave. Further focus needs to take place through Operations to bring the balances lower. Leave reports have been provided to MD's to ensure discussions take place with employees of EAL balances, to encourage leave. 10/06/2025 - Excessive leave was not reduced through May, further focus needed on sites with significant EAL to reduce, EAL needs to be accessed and not just cashed out. MD's to work through reports provided on 6/06/2025 to further push for leave of emnployees. 28/05/2025 - Financials - Initiative rebaselined to FY25. Strategy View: Baseline fiscal year to FY25 9/05/2025 - Updated analysis sent to MD's to further review excessive leave. Reminder of upcoming Public holidays to encourage further staff leave. 04/14/2025 Excessive leave levels not rediucing as required throughout the business. Further follow up and requests put forward to relevant MD's to encourage more leave through April and May to reduce the excessive leave levels. Baseline updated post holidays in Dec/ Jan. Submitting for L3 Approval. Per Elaine Moraes Queiroz request this was cancelled PDSM Ticket# INC033878461. Planview #8417 initiative to be cancelled - Rationale: BDE project canceled as of Jan 5, 2026 | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2023-11-01 | 2025-05-30
Business w/ Tech Initiative: EMR OTC- New surcharge- late domestic invoice fee | 63568 | 8428 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Gavin Zhai, Patrick Fan | On Track | After further disucssion with SAP team, the current SAP interests feature is not feasible for AU LPF needs. Several meeting conducted among AU IT and SAP team on discussing the feasible solution. There are 3 options proposed. IT team need to work on details steps to understand whether any system enhancement/development required. especcailly, talk about the file interface between SAP and CMS. AU IT team will show similar surcharge existing in CMS system for SAP team as a reference to understand how that data post into SAP. SAP team will come back a roughtly timeline of the rediness on supporting AU LPF, if SAP system needs a delvelopment. 7/28: work with Supply Chain SCO team on clariying the impact to the Supply Chain SCO. the requested information had updated in PV accordingly. PECS document access grant is under processing. Base on the understanding, this initiative will not involve IT support from Supply Chain SCO. it is under ANZ-ART, no impact to Enterprise SCO. wait for the Supply Chain SCO response. 8/12: Had meeting with SCO IT Finance team on 11th Aug. SCO IT Finance team asked to update the estimated $605K cost into PV as a default cost forecast which could impact SCO portfolio. Had explained during the meeting, there is no cost from the involved 2 IT teams (EU SAP & the Independent ART:SCO - IA - APAC AUS-NZ Consolidated ART) and no any cost impact to SCO portfolio. There is a PEL meeting schedule on 14th Aug to present the AU LPF to SCO leadership team for greenlight approval. 8/19: We had aligned with EU SAP team and the independent ANZ – ART team with a new timeline of the system side development. IT teams are ready to go with the system development, only wait for the Planview request can be moved into L3. 9/16:CMS and SAP unit testing partially completed, we are waiting for the SAP sample output file for the rest system functionality testing. 10/1:CMS changes implemented successfully -(CHG0959183) 11/3: Online Rate Card impremetation complete and finalized the LPF exemption customer acct list with Sales, Commercial & BP team on 29th Oct. SAP IT testing completed without any issue and sign-off on 30th Oct. 11/17: SAP team confirmed the change had moved into production (not enable) on 10th Nov. Completed business UAT end-to-end testing on 14th Nov. Business UAT completed on 17th Nov. 11/24: Communicate with external/Internal stakeholders for the AU Dom. LPF implementation on 20th Nov. 12/8: Live AU Dom LPF 2 weeks later after communication done on 07th Dec. 12/22: Leveraging live data by testing for LPF. 01/13: The first week LPF invoice successfully upload into live system. 01/20: Second week LPF invoice successfully upload into live system. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-03-01 | 2026-04-29
Business Only Initiative: Courier productivity savings- Telematics Install | 33082 | 8493 | Business Only Initiative | APAC - AU Domestic | APAC | Adam Marsden, Cameron Agars | On Track |  | K: L5 | Completed | L5 | 2023-09-01 | 2024-02-16
Business Only Initiative: Courier productivity savings- Telematics vehicle i | 33084 | 8504 | Business Only Initiative | APAC - AU Domestic | APAC | Adam Marsden, Cameron Agars | On Track |  | K: L5 | Completed | L5 | 2023-10-30 | 2023-10-30
Business Only Initiative: Courier productivity savings- Telematics vehicle u | 33092 | 8560 | Business Only Initiative | APAC - AU Domestic | APAC | Elliot Berry, Adam Marsden, Benjamin Dean, Con Gallanos | On Track | 17/12/25 - 113 vehicles sold YTD. Further vehicle utilisation review underway to identify further opportunities. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-06-01 | 2024-06-25
Business Only Initiative: Introduce a Bulk Fleet "Drop & Run" process at Mel | 57208 | 8571 | Business Only Initiative | APAC - AU Domestic | APAC | Andrew Eastick, Benjamin Dean, Brent Francis | On Track | Ready for L5 | K: L5 | Completed | L5 | 2023-11-01 | 2024-07-31
Business Only Initiative: AU Insourcing/Outsourcing - VIC/TAS Regional | 77675 | 8582 | Business Only Initiative | APAC - AU Domestic | APAC | Andrew Eastick, Benjamin Dean | On Track | Entered into WAVE, initiative has been delivered and money step already achieved in FY24. Moving through L gates as quickly as possible. | K: L5 | Completed | L5 | 2023-10-02 | 2024-05-28
Business w/ Tech Initiative: EasySend Underdeclared Consignments | 57251 | 9020 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Leeanne Michelle Pellow, Andrew Symington | On Track | 12/11/24 October financials updated $104,000 underdeclared, accross 714 shipments. Identified training activity will take place after Go Live date, this will not impact the Go Live or project deliverables. 9/12/23 Program management reviewed and approved to include in next PI in Jan 2024 | K: L5 | Completed | L5 | 2023-11-15 | 2024-05-28
Business w/ Tech Initiative: Pallet Hire Reduction | 78459 | 9146 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Elliot Berry, Con Gallanos, Andrew Symington | On Track | 5/2/26 - LEO scanner changes delayed due to Accenture issues. Pallet webpage on track for deployment on 22/2. LEO will be a few weeks after. Will have minimal/no impact on financial savings. 2025-10-15 - IT development work continuing, UAT underway. 2025-10-07 - IT development work continuing, UAT underway. 2025-10-01 - IT development work continuing. 2025-09-23 - IT development work continuing. 2025-09-16 - IT development work continuing (UAT commence PI CY04.01, APK release prepared for AU LEO UAT environment, UAT for web module underway) 2025-09-09 - IT development work continuing. 2025-08-26 - IT development work continuing. . 2025-08-19 - IT development work continuing. 2025-08-12 - IT development work continuing. 2025-07-22 - IT development work ongoing. UAT to commence soon. 17/12/25 - Webpage and scanner UAT complete. Pending deployment in Feb after IT change freeze 2025-07-16 - Website development progressing well, UAT to commence in a few weeks. LEO APK development complete and ready for UAT to commence. 2025-07-08 - IT development continuing. End-to-End testing underway. Next steps - complete UAT once End-to-End testing is complete. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-28 | 2026-05-25
Business w/ Tech Initiative: Courier productivity savings - Dynamic Route Plann | 33077 | 9361 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Andrew Eastick, Koey Cheng | On Track | 2025.02.12 Initiative been tracking on target for the past 3 months 2023.08.16 Discussed with IT team project has commenced before WAVE and all Technology is finalized, so the initiatives has been identify not required additional IT resources | K: L5 | Completed | L5 | 2023-08-07 | 2024-06-28
Business Only Initiative: Reduction of VFTE enabled by DIMS process improvem | 32852 | 9364 | Business Only Initiative | APAC - AU Domestic | APAC | Peter Gutsche, Koey Cheng | On Track | 2024-02-07 *EP2 - Request has been submitted to create a PDSM incident report for Infosec to look into the issue. *BS7 - Tunnel issue has been resolved and back online. VFTE savings confirmed with Map and will be reflected in the next update. 2024-02-05: Update tracking to include MAP benefits which were identified last week. 2024-02-05 *EP2 - Tunnel 1 bottom unit got replaced, and software has been updated to updated version and firmware. Toyota Forklift 79 is with Toyota oil leak has been repaired, pending Mettler to replace the IPC (forklift PC) within this week. Trellix/anti-virus software making the PC becoming slow. Mettler software team is looking for a solution/alternative. *BS7 - Pending for spare part to arrive 2024.01.31 EP2 - One forklift down due to oil leak and issue with the IPC (forklift PC) which will be replace and configured after the oil leak issue is repaired as it is a safety hazard. BS7 - Equipment has been shipped, ETA arrival end of this week, once arrived we can commence the repair. 2024.01.29 PER - LFT certified, forklift task completed, and software is updated, system is live and ready to use. EP2 - One forklift down due to oil leak and issue with the IPC (forklift PC) which will be replace and configured after the oil leak issue is repaired as it is a safety hazard. BS7 - Equipment has been shipped, ETA arrival end of this week, once arrived we can commence the repair. 2024.01.24 RSE - Drive Through has been commissioned successfully last Wed and system is online. PER - Tunnel #1 was down due to connectivity but it has been resolved today. EP2 - Static PDIM unit removed last weekend from station floor which will allow more space to accommodate for Drive Through activity. BS7 - Equipment has been shipped, ETA arrival end of this week, once arrived we can commence the repair. 2024.01.18 Peter Gutsche to work with Andrew Eastick to understand cost savings for the MAP team 2024.01.15 actual are under forecast as per challenges we have in the relative station: BS7 – 2nd Tunnel in the process of getting repaired as the unit was damaged during operation. PER – 2nd Tunnel to go live Mon 15th Jan RSE – Additional forklift calibration process for the forklift capacity at depot, pending with vendors, schedule date TBC EP2 – Scheduled removal of the previous static PDIM unit this weekend 19-21st Jan, to allow more space to accommodate for Drive Through activity. 2024.01.12 RSE installation update - pending for LFT confirmation scheduled for next week SW2, MEL and PER tunnel are not picking up correct read on the dimension during trial phase. EP2 is encountering data transmission issue. RSE, pending for LFT 1800mm Tyne Working closely with the vendor, and escalation has been raised to the vendor's system support team based in Norway. | K: L5 | Completed | L5 | 2023-06-01 | 2024-02-23
Business Only Initiative: Improving DIMS compliance to 91% (Reduce revenue l | 32851 | 9365 | Business Only Initiative | APAC - AU Domestic | APAC | Sean M’Gee, Koey Cheng | On Track | 2024-02-07 *EP2 - Request has been submitted to create a PDSM incident report for Infosec to look into the issue. *BS7 - Tunnel issue has been resolved and back online. 2024-02-05 *EP2 - Tunnel 1 bottom unit got replaced, and software has been updated to updated version and firmware. Toyota Forklift 79 is with Toyota oil leak has been repaired, pending Mettler to replace the IPC (forklift PC) within this week. Trellix/anti-virus software making the PC becoming slow. Mettler software team is looking for a solution/alternative. *BS7 - Pending for spare part to arrive 2024.01.31 EP2 - One forklift down due to oil leak and issue with the IPC (forklift PC) which will be replace and configured after the oil leak issue is repaired as it is a safety hazard. BS7 - Equipment has been shipped, ETA arrival end of this week, once arrived we can commence the repair. 2024.01.29 PER - LFT certified, forklift task completed, and software is updated, system is live and ready to use. EP2 - One forklift down due to oil leak and issue with the IPC (forklift PC) which will be replace and configured after the oil leak issue is repaired as it is a safety hazard. BS7 - Equipment has been shipped, ETA arrival end of this week, once arrived we can commence the repair. 2024.01.24 RSE - Drive Through has been commissioned successfully last Wed and system is online. PER - Tunnel #1 was down due to connectivity but it has been resolved today. EP2 - Static PDIM unit removed last weekend from station floor which will allow more space to accommodate for Drive Through activity. BS7 - Equipment has been shipped, ETA arrival end of this week, once arrived we can commence the repair. 2024.01.15 actual are under forecast as per challenges we have in the relative station: BS7 – 2nd Tunnel in the process of getting repaired as the unit was damaged during operation. PER – 2nd Tunnel to go live Mon 22nd Jan RSE – Additional forklift calibration process for the forklift capacity at depot, pending with vendors, schedule date TBC EP2 – Scheduled removal of the previous static PDIM unit this weekend 19-21st Jan, to allow more space to accommodate for Drive Through activity. 2024.01.12 RSE installation update - pending for LFT confirmation scheduled for next week SW2, MEL and PER tunnel are not picking up correct read on the dimension during trial phase. EP2 is encountering data transmission issue. RSE, pending for LFT 1800mm tyne Working closely with the vendor, and escalation has been raised to the vendor's system support team based in Norway Pending equipment delivery and commencement of installation for MELA and MBWA end of Aug 2023.08.16 Discussed with IT team project has commenced before WAVE and all Technology is finalized, so the initiatives have been identify not required additional IT resources. | K: L5 | Completed | L5 | 2023-06-01 | 2024-02-23
Business w/ Tech Initiative: AU LEO App - Surcharge enablement | 33073 | 9367 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Sean M’Gee, Koey Cheng | On Track | Project on track for automated system ready for Feb release, but actual have started being tracked as CMS team are charging customer with a manual method 2024.02.14 Started tracking actual with CMS applying the manual way to charge customer for the Tail-lift service. | K: L5 | Completed | L5 | 2023-07-03 | 2024-02-14
Business Only Initiative: AU LEO App - Split delivery reduction | 33075 | 9369 | Business Only Initiative | APAC - AU Domestic | APAC | Sean M’Gee, Koey Cheng | On Track |  | K: L5 | Completed | L5 | 2023-06-30 | 2023-10-25
Business Only Initiative: Linehaul utilization 2.0 | 77899 | 9371 | Business Only Initiative | APAC - AU Domestic | APAC | Thomas Finlay, Koey Cheng | On Track | 2025.01.17 - Initiatives has been tracking over target for 3 months after reaching L4. Overall we are still above target at USD $3.382m to date with USD $629k above the annual target. To support AU Surface Linehaul, we are envisioning a prescriptive tool that provides a forecast and recommend an optimized network. | K: L5 | Completed | L5 | 2024-04-29 | 2024-10-04
Business Only Initiative: Fuel RFP Australia (retail and bulk fuel) | 56908 | 9474 | Business Only Initiative | APAC - AU Domestic | APAC | Chaka Conway, Aditi Khanna | On Track | 01-12-24 Submission for L3 | K: L5 | Active | TEMP L5 - Enter L5 | 2023-07-17 | 2024-11-19
Business Only Initiative: EE2.0 - AU Superannuation Contribution Holiday |  | 90944 | Business Only Initiative | APAC - AU Domestic | APAC | Carol Ng, Yee Yong Tan | On Track | **June 11** Actuarial report and MEM Accounting input available. Actual benefits in cashflow is updated for period from Jan - May 2025. **May 28** - Pending advice from MEM Accounting and actuarial report from Trustee to provide updates for actual benefits. - it is estimated that reports will be avilable in end June. **May 16 - ** * Implementation of contribution holiday by payroll is on track; * Current monthly entries on planview reflects the best estimates available and is expected to receive advices to updates; * On-going meeting with AU Trustee and FedEx Accounting to get clarity on accounting treatment of such benefits; * Preliminary US GAPP Report is available, where APAC Accounting team will review with MEM Accounting team and advicedetails around actuals benefits for cashflow and P&L. On track - implementation plan aligned, ready for January 2025 being effective date. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-22 | 2025-06-30
Business w/ Tech Initiative: Contractor Safety Management System - Avetta |  | 93337 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Max Maim, Angela P. Campbell | On Track | QDM Complete, Funds budgeted with Operations, Infosec/First approved, Tech Spend approved, tech Eval approved, EnCore Approved. **Require Planview to engage OKTA team to assist with 2-Factor Authorisation. with the IMAGE Team (Purple ID) ** Unsure which portfolio is impacted. **System Architecture has been added as an attachment. This was also submitted as part of the FIRST review and approval.** 9/4: The LBC - Demand shaping documents have been uploaded. Business processes and Ability To Statements. 17/4: Federation Mtg 19/04 - Architecture alignment step complete and approved. Architechture link added to Planview, T-Shirt size and impacted portfolios updated. 27/5 - Service ticket raised last week. No further progress. Initiative not progressing, Planview system issue. 5/6 - System issue fixed and moved to next step. 17/6 - PEO pushed back to L2. EA requirements. 10/9 - New Local Enhancement Initiative raised as it meets the required criteria. | E: L2 | On Hold | L2
Business w/ Tech Initiative: ERQA Robotic Depalletizer |  | 98686 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Koey Cheng, Michiel Butterbrod, Dean Daniel | Attention Needed | 2025.09.23 Discussion with APAC and local IT team. Confirming that we will raise this as a Local Enhancement demand type today in Planview as the Tech support required does not require any architectural development as it is only vendor connectivity and it will only impact single portfolio (Supply Chain Operation Portfolio). 2025.09.16 Reach out to triage team to confirm if we should proceed the initiative with Biz with tech and Local enhancement, as currently based on the business case and expected saving the priority are low for IT resources 2025.09.09 POC with vendor at overseas site are scheduled at the end of September, and working with IT on the Business with Tech requirement for L2 submission 2025.09.02 Pending respond from Triage team to confirm the Demand type for the initiative 2025.08.19 Working through the Triage team feedback respond for SL2 submission 2025.08.08 Submitted for SL2 review 2025.07.29Fedex onsite testing on site at AWL test centre confirmed for late September. Test parcel confirmed and being delivered 2025.07.22 Planning for the POC of the Robotic's test plan and criteria with Vendor, to finalise the spend requirement for the LBC 2025.07.15 Ongoing discussion on the Robotic's test plan and criteria with Vendor, to finalise the spend requirement for the LBC 2025.06.24 Weekly cadence call to discuss POC test plan and criteria with vendor and relevant parties 2025.06.17 Ongoing discussion on the Robotic's test plan and criteria with Vendor, to finalise the spend requirement for the LBC 2025.05.27 Discussion on the Robotic's test plan and criteria with Vendor 2025.05.12 Onboarding vendor into FCF to proceed with PO raising 2025.05.05 Ongoing contract and pricing discussion with vendor 2025.04.28 Going through contract and pricing discussion with vendor 2025.04.14 Working with Finance on business case approval, re-initiaited vendor engagement for the purchase agreement discussion 2025.03.25 APAC P&E team requested the hold on vendor engagement so they can further review the Business case and the financial benefits for this project 2025.03.14 working with vendor for the purchase agreement 2025.02 CLEAR request submitted and pending for Finance review and approval | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: AU Domestic Claims |  | 104308 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Andrew Symington, Leeanne Michelle Pellow | On Track | 2025-12-02 - cancellation request. Laberg is retired. AU team will continue to use sharepoint tool until global solution (Project CENTAUR) is deployed. Additional AU project not required - will roll up into Project CENTAUR. 2025-09-03 - Placed on hold as discussed on AU pod domestic stand up until sytem solution is defined. 2025-08-26 - contacts and process information received for BOT option, following up with BOT team 2025-08-19 - following up with Jens Klemm regarding RBA BOT processes and contacts 2025-08-12 - meeting with EU team (Jens Klemm), reviewing CED + RPA Bot options 2025-08-08 - meeting complete with US team (Kevin Lipe, Project Centuar), to do - follow up with G Machado re orange EU solution 2025-07-22 - Reached out to US IT solutions team to discuss application options. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: AU Card Surcharge |  | 104624 | Business Only Initiative | APAC - AU Domestic | APAC | Pui-Yue Ruby Lui | On Track | 03/17 Notified CG BPO for change 03/21 Create and emails sent (for extrnal target list) on iMarket 03/21 Introduction of Card Surcharge Made by TNT Express Customers in Australia + FAQs sent to internal customers 3/24 - 3/28 continue transactions test 4/9 1st DD file with surcharge will be transacted. Monitoring in progress. 4/9 - 4/30 The total transaction USD 5.77M with scucharge recoving USD 84K 5/9 Sales provided the list of account # for the 5 customers under temp exceptions of CC surcharges waivers. 5/19 US$23K CC surcharges approved from the MDs to refund to these 5 customers. 5/28 Sales requrest additional 2 weeks exemption support for CC fees for the identified customers. (approved by RO MD) 6/12 removed customer ATS from exceptions, will proceed with us charging CC fees 6/13 Mgmt has approved 30-day payment term and without SD for cust MUVE 6/19 Sales requested to add another 2customers for exceptions and processing for review 8/22 Recop CCF (USD) 45K in Jul 2025 (only 1 group of customer excepted with MD approval and all temp wavier support removed) 8/29 the following are the list of accounts for CCF wavier approved by MD ACCOUNT NAMETNT AC ABCO PRODUCTS PTY LTD -NSW30005085 ABCO PRODUCTS - QLD30022013 ABCO PRODUCTS - VIC30022012 ABCO PRODUCTS - WA21834256 ABCO PRODUCTS - SA50000012 ABCO INTERNATIONAL50003718 ABCO PRODUCTS - BULK ACCOUNT50009237 | I: L4 | Active | L4 | 2024-10-23 | 2027-12-31
Business w/ Tech Initiative: Standardizing Australia AR Operations with Oracle |  | 106178 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Patrick Fan, Gavin Zhai | On Track | 08/29/25 As the Planview initiative is going to be discussed and worked on during the upcoming transformation workshop, hence update as On Hold. 07/14/25 Learn from EU SAP team, there is a SAP decommissioning imitative for TNT business which expect AU would become part of the central project. Will update once we have clearer plans share from EU SAP team. 0707/25 Clarify with EU SAP team on the maintance fee per annum if all the regions/country had moved from SAP into Oracle, Only AU TNT left. 06/30/25 Received Stop Work criteria feedback from EPM, seeking for any insight/recommendation can be shared from EBS strategy team. 06/23/25 Complete LBC case. 06/17/25 Approach to US EBS team and BPO team on SAP and Oracle license cost mapping for LBC. 06/09/25 Completed Biz w/ Tech Additional Info section of LBC. Approach to STC SMEs on receiving estimate the benefit or cost-saving to complete the Financial and Implementation section of LBC. 06/02/25 Setup meeting with IT team and FP&A assistant on the Lean Business case creation. 05/27/25 Check with SAP team and FP&A assistant on the Lean Business case. 05/21/25 Seek for IT assistant on the Lean Business case. 05/07/25 Working on the Lean Business case. 04/28/25 Create the Lean Business case. 04/14/25 Approach EBS RMIC (Revenue Management, Invoicing & Collection) team to understand the next step. 03/21/25 Go through Triage review and submit to L1 in Planview. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: AU Domestic Product Harmonization and Rebranding |  | 109744 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Jenny He | On Track | 9/11 - Updated the Primary type value to 'Brand Enhancement' - Non-Quantifiable. - Updated the money step - Action points: Update 'Request Type' to ' Enabler' and add its dependencies - Add 'myTNT replacement PV#7748' as a dependency since we want FedEx product names to be displayed on the new FedEx Domestic Online Booking tool 5/26 - Estimated FY25 revenue impact size is $705M 3/26 - Updates: - Target to complete by Oct'26 - Estimated FY24 revenue impact size is $748M - Estimated revenue dilution is $125k | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: AU NT Alice Spring Depot Transition |  | 110198 | Business Only Initiative | APAC - AU Domestic | APAC | Pritesh Gandhi | On Track | FedEx Depot already closed and Supplier has started service in the Region for FedEx. Estimated savings is less than USD 100K. | D: SL2 | Cancelled | SL2 Finance Domain Lead Approval
Business w/ Tech Initiative: AU LH Optimization |  | 126781 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Thomas Finlay, Koushik Das, Lorida Bejleri, Vaibhav Gupta, Koey Cheng | On Track | Everything is in progress as part of the project plan | E: L2 | Active | L2 Feedback Requested | 2026-03-09 | 2026-12-31
Business w/ Tech Initiative: AU - SpS Hubs API Local Courier |  | 89969 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Nathan L. Henley, Frank Sun | On Track | 25/03/26 Requested to push forecast based on delayed start. No change in figures however Planview runs only until May28 original figures include an additional 6 months of rev (approx $700K difference. 25/03/26 A number of planning activities have been undertaken in the past month, Accenture team requested Feb and Approved March, however a Clear number is now being requested. PI PLanning for the next period has been undertaken, however until team is stood up, limited resourcing is available beyond ensuring plans are in place for Accenture team, and that the external vendor is aware of what work is required on their side. Continue to be requested to update financials despite not starting. 4/02/26 EPIC has moved to L3, still an issue in planview showing "Enter L3" while it appears we are in L3. IT has begun reviewing architecture and resource planning in preperation for a build process to start end of March during the next PI. MVP est. AUG 2026 to be confirmed. Forecasts will be updated when resouces committed and build begins. 27/1 INC033852800 created as there is an issue moving the Epic from L2 to L3 which is creating an Agility linking issue stopping the PMO team from linking into Planview. note: Unable to update forecast/actuals until we have a build start date/resource allocation). 22/1 met with SPS stakeholders and IT PMT to confirm build priorities for API and IT PM lead has requested resources. Likely fill work applied between now and March next PI not until April. 16/01 multiple days pf PI planning this week - Hubs API requested for more attention during last day as pioririty for team is AU transformation. 12/01/ L3 approved 30/12/25 2026 19/12 Have chased multiple avenues to push this to L3 as awaiting finance approval, escalated through local finance heirachy 26/11 advised that associated Solutionl required to be added to epic - IT has now added this. Firmed with requested can be resubmitted to L3. 24/11 Still uncertain around KPI - baseline remains 0 as this is new revenue, however have changed the Revenue from $ value to % (note that only whole numbers appears; however does equal 100 in the total). Resubmitted to L3. 17/11 advised to monitor power BI but that KPI was still not correctly entered - have sought clarification. Power BI mentions L3 - Planview says L2 14/11 no response rcvd as such both IO and EO have updated based on understanding - resubmit to L3. nlte - archietecture docs uploaded into the Planview "content" file location within the initiative. 11/11 Reuqested to update multiple items: L2 Architecture/EO to complete Epic/Add tech milestone tag for SCO - IO to add KPIs forecast/baseline - Clarification sought 11/11 however have updated 4/11 New Demand Prescopal Review Meeting attended and presentaed ast 2am for pre approval - Greenlight revieved offline - requested to update planview and submit to L3. 30/10 GEN0/01 Approval meeting attended during US Office hours for approval 20/10 both SCO Lead and Architecture enablement has reached out to prep for 30/10 presentation to review committee lookint to close any gaps/clarify any questions. Meeting set for 21/10 with project stakeholders. 16/10 finalised form for GEN 0/1 specifivs as requested and updated SCO presentation with details also. Advised SCO PMMA of completion. 8/10 SCO team advised need to provide GEN1/GEN1 details 7/10 Chased SCO team again for approval to submit to L3 29/09 SCO team again requested details provided on the 1/09. This email chain has been resent to them - awaiting approval to submit to L3 27/09 SCO Finance confirmed all correct in Planview as per requests 26/09 Updated the SCO rates to a different line on the Financials as requested. Awaiting green light. 22/09 Alex V from IT walked me through the potential line issues from the SCO finance update that was inputted. Have updated, loaded attachment and asked for feedback as we had not recieved any updates. 16/09 Have updated financials with SCO values as requested and responded as | G: L3 | Active | TEMP L3 - Enter L3 | 2026-04-01 | 2026-11-11
Business Only Initiative: AU Trailer Maintenance |  | 161048 | Business Only Initiative | APAC - AU Domestic | APAC | Ngoc Mai Bui, Kyle Mitchell | On Track | The local fleet team has a parallel and active Planview initiative to insource the maintenance of the trailers with an estimated savings value of $600K, currently in L1. Initiative number and title…#164437-AU Trailer Service In-Sourcing. | E: L2 | Cancelled | L2 - Enter Value Prop
Business Only Initiative: AU - Vehicle Tyre Retreading |  | 163081 | Business Only Initiative | APAC - AU Domestic | APAC | Christopher Pierce | On Track | Supplier has commenced supporting the initiative by the due date of 10.01.2025. Tyre retreading is being monitored alongside new tyre replacments. Benefits are very complex to calculate on a monthly basis, will be more visible at an annual level when reconciled against number of overall tyre replacements. Tyre replacements require long-term monitoring to allow for the tyres to wear our and then move to the next stage of the re-treading cycle, up to 3 events. | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: AU - Forklift Utilisation |  | 163084 | Business Only Initiative | APAC - AU Domestic | APAC | Christopher Pierce | On Track | Work has commenced reviewing overall forklift utilisation nationally. 3/3/26 - Baseline is FY26, benefits expected to commence from FY27. | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: AU - Trailer Service In-Sourcing |  | 164437 | Business Only Initiative | APAC - AU Domestic | APAC | Christopher Pierce | On Track | Hiring requests have been submitted into MOIRAI | E: L2 | Active | L2 - Enter Value Prop
Business Only Initiative: APAC: ANZ Structural Cost Savings ACCS |  | 166674 | Business Only Initiative | APAC - AU Domestic | APAC | Binh Tran, Laurentius Adi-Kurniawan, Koey Cheng | On Track | Sanitising Numbers | I: L4 | Active | L4 | 2026-02-02 | 2026-06-30
Business Only Initiative: APAC: ANZ Structural Cost Savings - Offshore |  | 166684 | Business Only Initiative | APAC - AU Domestic | APAC | Binh Tran, Laurentius Adi-Kurniawan, Koey Cheng | On Track | Tasks to be offshored have been identified. | G: L3 | Active | L3 | 2026-05-04 | 2029-02-16
Business Only Initiative: Vehicle Reverse Sensor Retrofit 2.0_Phase 2 |  | 168435 | Business Only Initiative | APAC - AU Domestic | APAC | Angela P. Campbell, Max Maim | On Track | On Track | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2027-05-28 | 2027-05-28
Business w/ Tech Initiative: CDAS for AU Domestic Business (DSCs) |  | 168571 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Angela P. Campbell, Elliot Berry, Con Gallanos | On Track | 19/12 - reviewed with Megan and we were advised AU architects can provide documentation at this stage and CDAS team have also provided the estimate for T-shirt size during their evaluation of the initiative. 26/3 - not required at this time due to ongoing delays. 1/4/26 - Pursuing an external solution. | E: L2 | Cancelled | L2
Business Only Initiative: Regional WA Agent Conversion |  | 169898 | Business Only Initiative | APAC - AU Domestic | APAC | Motass Chiekelard, Con Gallanos | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: QLD Cluster Agent Savings |  | 170076 | Business Only Initiative | APAC - AU Domestic | APAC | Andrew W. Martland, Con Gallanos | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: AU- Bond Shelf Automation with Robotics Geek+ |  | 170420 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Laurentius Adi-Kurniawan, Ali O. Hekimoglu, Koey Cheng | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: AU - Fuel Tax Credit Process Review |  | 170596 | Business Only Initiative | APAC - AU Domestic | APAC | Christopher Pierce, Jeroen De Boer | On Track | On Track | E: L2 | Active | L2 - Enter Value Prop
Business Only Initiative: AU - Vic/Tas Regional Depot Pool Drivers |  | 170681 | Business Only Initiative | APAC - AU Domestic | APAC | Michael Cooper, Andrew Eastick | On Track | On Track | G: L3 | Active | L3 | 2026-09-01
Business w/ Tech Initiative: AU Hospital Runs |  | 170686 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Luisa F. Rodriguez, Roland Gienau | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: AU - Air LHL Qantas Freight Contract Extension |  | 177998 | Business Only Initiative | APAC - AU Domestic | APAC | Thomas Finlay, Koey Cheng | On Track | In principal agreement with Qantas. Finalising drafting of contract extention, | G: L3 | Active | L3 | 2025-11-28 | 2026-05-01
Business w/ Tech Initiative: AU-AMS Unloading in Matraville Induction |  | 184512 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Ali O. Hekimoglu, Laurentius Adi-Kurniawan | On Track | Options are not beyond the expected price range | C: L1 | On Hold | L1
Business w/ Tech Initiative: AU Data Infrastructure Modernization-Data Lake |  | 191323 | Business w/ Tech Initiative | APAC - AU Domestic | APAC | Laurentius Adi-Kurniawan, Roberto Mattos | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: [EC] EGER - Alibaba Global including IA | 71757 | 6794 | Business Only Initiative | APAC - Commercial | APAC | Augustine Lung, John Kang | On Track | Alibaba VN-WW project is postponed indefinitely due to poor ROI. Will check again the progress in their new FY (start in Apr 2025.) | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-06-20 | 2025-06-30
Business Only Initiative: [EC] EGER - JD.com Global including IA | 71759 | 6796 | Business Only Initiative | APAC - Commercial | APAC | George Hong, Augustine Lung, Xalas Hui | On Track | 04/28/2025 going good 2025.09.20 - Advised by Finance Pod Coach (Yan Cai) FY25 Ramp up completed | E: L2 | On Hold | L2
Business Only Initiative: [EC] EGER - eBay China OB | 73380 | 6797 | Business Only Initiative | APAC - Commercial | APAC | George Hong, Augustine Lung, Yan-Hui Luna Huang | On Track | eBay's CN OB project has been postponed due to their system development resources have been prioritized to be used on other projects , there is no specific timeline when they will activate, we will keep close monitoring on the progress and will reactivate the inititative once receiving confirmed update from eBay. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-05-20 | 2026-05-28
Business Only Initiative: [FD] FD Deferred Network Solutions (Westbound) | 45239 | 6943 | Business Only Initiative | APAC - Commercial | APAC | Chloe Chuang, Hundred Mo | On Track | Both solutions have been launched. No further action. | K: L5 | Completed | L5 | 2024-08-21 | 2024-10-21
Business Only Initiative: [IMPT] TPAC-APAC Import growth | 92781 | 6997 | Business Only Initiative | APAC - Commercial | APAC | Brian Chen, Harry Cheng | On Track | Pricing program was released on Nov 19th by Marketing team | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-15 | 2024-11-29
Business Only Initiative: [FD] Rationalize FICP value props and convert F1R | 38452 | 7087 | Business Only Initiative | APAC - Commercial | APAC | Hundred Mo, Dorothy Lee | On Track | conducted Sales webinar in week of 17 Jun, blasted eDM to target customers executed and real end-to-end shipment testing to ensure all operational | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-01-02 | 2024-07-01
Business w/ Tech Initiative: [EC] APAC Fulfillment: White-label solution powere | 69457 | 7440 | Business w/ Tech Initiative | APAC - Commercial | APAC | Mark Baeck, Jane Jian | On Track |  | G: L3 | Active | TEMP L3 - Enter L3 | 2023-10-02 | 2026-05-29
Business Only Initiative: [EC] APAC Alliances and Compatibles | 69565 | 7441 | Business Only Initiative | APAC - Commercial | APAC | Mark Baeck, Jane Jian | On Track | 05/28/2025 - FY25 Baseline Applied | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-04-29 | 2025-08-29
Business Only Initiative: [EC] M15-APAC Fulfillment: Customer acquisition | 70234 | 7442 | Business Only Initiative | APAC - Commercial | APAC | Mark Baeck, Jane Jian | On Track | Corp Load of new Fastbill codes moved to FY26. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-05-06 | 2027-08-19
Business Only Initiative: [EC] SAM - Intra-Asia CN OB: AU B2B2C and B2C | 69627 | 7443 | Business Only Initiative | APAC - Commercial | APAC | Ian Zhang, Kate Jian | On Track | [Aug] - FY25 Baseline Applied | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-17 | 2026-11-27
Business Only Initiative: [EC] SAM - Intra-Asia CN OB: JP B2B2C | 69629 | 7444 | Business Only Initiative | APAC - Commercial | APAC | Ian Zhang, Linda Chen | On Track | [May] - FY25 Baseline Applied | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-01 | 2026-05-29
Business Only Initiative: [EC] SAM - Intra-Asia CN OB: SEA B2B2C and B2C | 69631 | 7445 | Business Only Initiative | APAC - Commercial | APAC | Ian Zhang, Linda Chen | On Track | [May] - FY25 Baseline Applied. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-08-01 | 2026-11-27
Business Only Initiative: [EC] SAM - SEA into AU eCommerce - Phase 1 | 69623 | 7455 | Business Only Initiative | APAC - Commercial | APAC | Helen Price, Ricky Kwok | On Track | “[Date] - FY25 Baseline Applied” | E: L2 | On Hold | L2 | 2024-07-12 | 2024-11-29
Business Only Initiative: [EC] SAM – NPAC (HK, KR, JP) to Intra-Asia EC | 69625 | 7457 | Business Only Initiative | APAC - Commercial | APAC | Masahiro Kiyosawa, Mihoko Takagi | On Track | On track 5/28/2025 - FY25 Baseline Applied | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-01 | 2026-05-29
Business Only Initiative: [EC] EGER - SHEIN AU | 71760 | 7499 | Business Only Initiative | APAC - Commercial | APAC | Milanda Qi, Augustine Lung | On Track | 05/28/2025 - FY25 Baseline Applied | K: L5 | On Hold | TEMP L5 - Enter L5 | 2023-12-01 | 2026-06-12
Business Only Initiative: [EC] SAM - B2C development AU>NZ | 76664 | 7589 | Business Only Initiative | APAC - Commercial | APAC | Matt Daniels, Ricky Kwok | On Track | On Track | G: L3 | On Hold | L3 Feedback Requested | 2024-05-01 | 2025-04-30
Business w/ Tech Initiative: [EC] EGER – SHEIN ZA | 85514 | 7692 | Business w/ Tech Initiative | APAC - Commercial | APAC | Milanda Qi, Gloria Yuan, Augustine Lung | On Track | 05/28/2025 - FY25 Baseline Applied | K: L5 | Active | L5 | 2024-05-01 | 2025-05-01
Business Only Initiative: [EC] EGER - K-culture B2C | 69617 | 7856 | Business Only Initiative | APAC - Commercial | APAC | Sian Lee, Jung-Won June Choi | On Track | FY25 Baseline Applied | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-07-01 | 2025-08-07
Business Only Initiative: [COMM] DS - SHEIN T2 pricing for peak | 89544 | 8091 | Business Only Initiative | APAC - Commercial | APAC | Alex Siu, Tony Jin | On Track | Pricing is implemented and capacity is planned - however Sales team feedback customer volume is soft and does not require the capacity which would trigger the Tier 2 Pricing in November. Originally planned Tier 3 pricing is expected to continue occur Dec 1 to Dec 7 - Volume from Dec 1 has been above the base level of 270T, volume above 270T will be charged Tier 3 rates. Update on Jan 15 - Actual volume shipped Dec 1 to Dec 7 exceed allocation, total 297.7T will be billed with Tier 3 pricing of 1.5/lb additional, which is USD984k ex fuel and USD1.54M with DFS | I: L4 | Active | L4 Feedback Requested | 2024-09-02 | 2024-11-15
Business Only Initiative: [EC] SAM – Intra-Asia via intermediary reselling | 70110 | 8181 | Business Only Initiative | APAC - Commercial | APAC | Rebecca Lim, Xiaoxi Liu | On Track | . | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-15 | 2025-12-30
Business Only Initiative: [FD] RPI AMEA-EU SOP/KPI | 43277 | 8209 | Business Only Initiative | APAC - Commercial | APAC | Rachel Lui, Harry Cheng | On Track | Implementation started on Mar19 (L4) , KPI will be monitored closely to ensure success. | K: L5 | Completed | L5 | 2023-09-01 | 2024-02-23
Business Only Initiative: [FD] Greater Bay Area Industry Vertical - Lithium | 39219 | 9475 | Business Only Initiative | APAC - Commercial | APAC | Ben Yuen, Harry Cheng, Anthony Leung | On Track | As new LB risk scoring framework will be launched, performance (lbs, revenue) of newly approved GBA LB shipper with shell company in HK will be monitored. For existing customer, we will also increase share of wallet via identifying and addressing the needs from existing large customers. | I: L4 | On Hold | TEMP L4 - Enter L4 | 2023-09-18 | 2024-08-30
Business Only Initiative: [COMM] RQ - Pre-Approved program repricing CN | 89548 | 9509 | Business Only Initiative | APAC - Commercial | APAC | Anita Yu, Gloria Yuan | On Track | . | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-24 | 2024-07-19
Business Only Initiative: [COMM] RQ - Pre-Approved program repricing JP/HK/K | 89549 | 9511 | Business Only Initiative | APAC - Commercial | APAC | Anita Yu, Gloria Yuan | On Track | . | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-06-17 | 2024-09-13
Business Only Initiative: [COMM] DS - APAC Payer EG/ER DS waiver reversals | 89546 | 9513 | Business Only Initiative | APAC - Commercial | APAC | Mimi Yiu, Gloria Yuan, Augustine Lung | On Track | APAC CM monitors and owns the DS process | K: L5 | Completed | L5 | 2024-07-01 | 2024-12-23
Business Only Initiative: [COMM] RQ - APAC payer Strategic Pricing repricing | 89547 | 9514 | Business Only Initiative | APAC - Commercial | APAC | Gloria Yuan, Catherine Chen | On Track | GOOD | H: SL4 | On Hold | SL4 Finance Domain Lead Approval | 2025-05-30 | 2025-05-30
Business Only Initiative: [COMM] DS - Demand surcharge above BP | 89545 | 9516 | Business Only Initiative | APAC - Commercial | APAC | Mimi Yiu, Gloria Yuan | On Track |  | K: L5 | Completed | L5 | 2024-08-05 | 2024-09-16
Business w/ Tech Initiative: Local Apps Modification for MAGIC CDL Removal |  | 157485 | Business w/ Tech Initiative | APAC - Commercial | APAC | Xiao-Ou Roman He, Launa Morris, Yu-Jing Huang | On Track | Work can be carried out without DRIVE after discussion with development teams and DRIVE leads. Put it on hold to be safe. | E: L2 | On Hold | L2 & CCH | 2025-10-08 | 2026-06-29
Business w/ Tech Initiative: NienMade AU Domestic API Integration and IPD JP&NZ |  | 159126 | Business w/ Tech Initiative | APAC - Commercial | APAC | Xalas Hui, Jesper B. Pauig, May-Lee Mary Leong | On Track | We want to re-classify this as Local Enhancement to speed up the development process. | C: L1 | Cancelled | L1
Business Only Initiative: KTOP (KR-TW-KR) initiative |  | 159129 | Business Only Initiative | APAC - Commercial | APAC | Jae-Wook Woo | On Track | Launched on July 1, 2025 | I: L4 | Active | L4 | 2025-06-02 | 2026-03-02
Business w/ Tech Initiative: Microsoft - Repair and Return v2.0 |  | 144046 | Business w/ Tech Initiative | APAC - Commercial | APAC | Wing Kin Chow, Lisa Stockton, Richard Holloway | On Track | On Track | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-08-20 | 2026-04-30
Business w/ Tech Initiative: Lonza - New Customer SG for SPOTS - URGENT Req. |  | 153824 | Business w/ Tech Initiative | APAC - Commercial | APAC | Wing Kin Chow, Xalas Hui, Lisa Stockton | On Track | On Track | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2025-09-01 | 2026-03-23
Business Only Initiative: [ASPIRE][ID] Grow CGK inbound | 73536 | 7573 | Business Only Initiative | APAC - Commercial | APAC | Riva Sjarif, Boonthida Ratanavilaikul | On Track | on track 10/29 Flight launched (money step) Interim solution implemented for enbler they are still work in progress 25/5/27 FY25 Baseline Applied | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-01 | 2025-11-03
Business Only Initiative: [ASPIRE][MY] Grow JHB Inbound | 73538 | 7575 | Business Only Initiative | APAC - Commercial | APAC | Nur Fadhlin Binti Ahmad Fauzee, Boonthida Ratanavilaikul | On Track | 28/05/2025 - FY25 Baseline Applied on track 10/29 Flight launched (money step) Interim solution implemented for enabler they are work in progress | K: L5 | Active | TEMP L5 - Enter L5 | 2024-07-17 | 2024-12-31
Business Only Initiative: [ASPIRE][MY] Grow Greater KUL Inbound | 73540 | 7577 | Business Only Initiative | APAC - Commercial | APAC | Nur Fadhlin Binti Ahmad Fauzee, Boonthida Ratanavilaikul | On Track | 28/05/2025 - FY25 Baseline Applied | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-24 | 2024-07-02
Business Only Initiative: [ASPIRE][MY] Grow PEN Inbound & KUL MY Outbound | 73539 | 7697 | Business Only Initiative | APAC - Commercial | APAC | Nur Fadhlin Binti Ahmad Fauzee, Adi Putra, Hilary Tse, Montree Lorlertsakul, Boonthida Ratanavilaikul | On Track | in progress | K: L5 | Active | L5 | 2024-11-22 | 2025-10-27
Business Only Initiative: [DeepSEA][MY] Grow Target Customer Taiyo Yuden in | 87854 | 6679 | Business Only Initiative | APAC - Commercial | APAC | Edwin-John Tong, Boonthida Ratanavilaikul | On Track | On hold - 8/19 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [FLEX][MY] Inventory Logistics Solutions for MedTe | 87860 | 6681 | Business Only Initiative | APAC - Commercial | APAC | Lynna Lee, Boonthida Ratanavilaikul | On Track | On hold - 8/19 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Acer - Customer Requirement |  | 157479 | Business w/ Tech Initiative | APAC - Commercial | APAC | Lisa Stockton, Richard Holloway, Wing Kin Chow, Mark N. Hoffmann | On Track | Work being completed using LE Planview requests instead | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Lexmark - Customer Requirements |  | 157482 | Business w/ Tech Initiative | APAC - Commercial | APAC | Lisa Stockton, Richard Holloway, Wing Kin Chow, Mark N. Hoffmann | On Track | Work being completed using LE Planview Request | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: [NPACSEA TA] In-source M&P Hiring Model | 95118 | 7403 | Business Only Initiative | APAC - Commercial | APAC | Jeff Cheah, Friendy Fong | On Track | Denise informed to onhold first. Alignment needed with Central US for Global HR Strategy. Target to complete in next 2 weeks. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [DeepSEA][SG] Jurong Innovation District | 87865 | 8288 | Business Only Initiative | APAC - Commercial | APAC | Bryan Tan | On Track | Placed on hold as JID is still in a nascent stage. The team will continue to monitor JID's development and reinstate when it is ready. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [DeepSEA][ID] DPS ¦ unlocking e-commerce potential | 87846 | 7667 | Business Only Initiative | APAC - Commercial | APAC | Ramadhani Tiswar, Mellyana | On Track | 9/16 - placed on hold | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [FLEX][VN] Grow North Vietnam revenue to TPAC by u | 87864 | 9408 | Business Only Initiative | APAC - Commercial | APAC | Anh Do, Bao Nguyen | On Track | There is currently no CLH available in the market that will give positive P&L. PNM is working on a business case shipping from ICN to TPAC with KE and if the business case provides positive P&L, the volume from North VN could leverage on this option. This will be visit again upon the approval of the KE business case. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-08-13 | 2024-11-13
Business Only Initiative: [S2][MY] Grow Perishables Industry incl. Halal |  | 89931 | Business Only Initiative | APAC - Commercial | APAC | Angeline Tham | On Track | Reasons why drop Perishable and Halal: 1)Need to conduct cleansing of the ULD 2)Unable to mix with non-Halal products. 3)Dedicated truck to deliver Halal Products 4)Once the ULD / Truck carry Non-Halal products, we will need to conduct cleansing again. Will be replace with eCommerce | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][VN] Grow SGN Freight |  | 89939 | Business Only Initiative | APAC - Commercial | APAC | Bao Nguyen, Mellyana | On Track | [04/08/2025] - FY25 Baseline Applied | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][VN] Grow Freight |  | 89943 | Business Only Initiative | APAC - Commercial | APAC | Bao Nguyen, Mellyana | On Track | [04/08/2025] - FY25 Baseline Applied [09/22/2025] - VN Sales IO suggest removing from Drive as it was stuck due to the low pricing ask | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][VN] Penetrate OB Perishables |  | 89947 | Business Only Initiative | APAC - Commercial | APAC | Bao Nguyen, Mellyana | On Track | [04/08/2025] - FY25 Baseline Applied | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][ID] Grow OB for Fashion & Retail |  | 89963 | Business Only Initiative | APAC - Commercial | APAC | Al Faris Tarieq Alwyni, Mellyana | On Track | [04/10/2025] - FY25 Baseline Applied | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][ID] Round Trip Cracking Cigarette Opportunity |  | 89983 | Business Only Initiative | APAC - Commercial | APAC | Mellyana, Wilujeng Dewi Ariyant | On Track | [04/09/2025] - FY25 Baseline Applied | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2 Enabler][ID] Hunter Sales Scheme 2.0 |  | 90320 | Business Only Initiative | APAC - Commercial | APAC | Mellyana, Al Faris Tarieq Alwyni | On Track | No one apply, go with external hire - Hunter SS Initiative as growth initiative | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: [S2][PH] Grow OB Perishable |  | 90380 | Business Only Initiative | APAC - Commercial | APAC | Cattleya Ann R. Corpuz, Anna-Marie Liwag-Inawat, Mellyana | On Track | [04/07/2025] - FY25 Baseline Applied | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][SG] Pull Model to Grow SG IB from CN |  | 91341 | Business Only Initiative | APAC - Commercial | APAC | Mellyana | On Track | The accounts nominated for the Pull Model for those accounts are not ideal (e.g., not big enough revenue potential, or do no require any support on Drive) | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][TH] Pull Model to Grow TH IB from CN |  | 91344 | Business Only Initiative | APAC - Commercial | APAC | Ontheera Komutrat | On Track | We are waiting for their suppliers address and contact person so that will work push-pull with CN Sales, FXE & FXL team which expected after April 20th (long holiday after Songkran). | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][MY] Pull Model to Grow MY IB from CN |  | 91347 | Business Only Initiative | APAC - Commercial | APAC | Angeline Tham | On Track | On Hold Project as per Melly's message | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][ID] Pull Model to Grow ID IB from CN |  | 91350 | Business Only Initiative | APAC - Commercial | APAC | Mellyana | On Track | The accounts nominated for the Pull Model for those accounts are not ideal (e.g., not big enough revenue potential, or do no require any support on Drive) | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][MY] Penetrate DG RT to CN |  | 91504 | Business Only Initiative | APAC - Commercial | APAC | Edelquin Basanes, Angeline Tham, Mellyana | On Track | [04/10/2025] - FY25 Baseline Applied | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: [S2][SG] E-Commerce |  | 92075 | Business Only Initiative | APAC - Commercial | APAC | Lin-Shan Alvin Koh, Mellyana | On Track | [04/08/2025] - FY25 Baseline Applied | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S2][SG] Technology |  | 93096 | Business Only Initiative | APAC - Commercial | APAC | Mellyana, Lin-Shan Alvin Koh | On Track | [03/31/2025] - FY25 Baseline Applied | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: [FLEX][TH] Grow Freight Business across Thailand | 87852 | 6926 | Business Only Initiative | APAC - Commercial | APAC | Waranya (Pu) Rattanakantong, Chatwadee Chantaweekun | On Track | Pending for freight pricing approval | E: L2 | On Hold | L2 | 2024-08-01 | 2025-02-28
Business Only Initiative: [S2][ID] Live Fish | 87857 | 7664 | Business Only Initiative | APAC - Commercial | APAC | Dimas Widiwantono, Mellyana | On Track | On-hold waiting consignee's broker details from shipper to unlock the live fish clearance capabilities at Los Angeles and Chicago | E: L2 | On Hold | L2 & CCH | 2024-07-31 | 2024-09-06
Business Only Initiative: [DeepSEA][KH] Grow Cambodia OB to APAC by improvin | 87863 | 9405 | Business Only Initiative | APAC - Commercial | APAC | Anh Do, Bao Nguyen | On Track | on hold - 9/4 | E: L2 | On Hold | L2 | 2024-08-13 | 2024-11-19
Business Only Initiative: {S2}{TH} Grow Inbound |  | 89934 | Business Only Initiative | APAC - Commercial | APAC | Ontheera Komutrat, Mellyana | On Track | [03/31/2025] - FY25 Baseline Applied [09/22/2025] - Initiative put on hold as it is no longer required. FD3 IMPT has been successfully launched and IA IMPT is now under BAU discussion | E: L2 | On Hold | L2
Business Only Initiative: {S2}{TH} Grow eCommerce |  | 89404 | Business Only Initiative | APAC - Commercial | APAC | Ontheera Komutrat, Mellyana | On Track | [03/31/2025] - FY25 Baseline Applied | E: L2 | On Hold | L2 | 2024-12-02 | 2025-02-12
Business Only Initiative: [S2]{ID} Industrial |  | 89703 | Business Only Initiative | APAC - Commercial | APAC | Mellyana, Al Faris Tarieq Alwyni | On Track | [04/15/2025] - FY25 Baseline Applied | E: L2 | On Hold | L2 Feedback Requested | 2024-09-02 | 2026-06-18
Business Only Initiative: [S2 Enabler] SEA Leads Generation |  | 91338 | Business Only Initiative | APAC - Commercial | APAC | Chin-Chai Keh, Mellyana, Zoe Fan, Vivien Seah | On Track | [04/04/2025] - FY25 Baseline Applied | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business Only Initiative: [FLEX][PH] GROW INTRA-ASIA AND TPAC FREIGHT | 87848 | 7321 | Business Only Initiative | APAC - Commercial | APAC | Jenieryll-Jomarie Mangalindan, Edelquin Basanes | On Track | [05/28/2025] - FY25 Baseline Applied | G: L3 | On Hold | L3 Feedback Requested | 2024-07-01 | 2026-05-29
Business Only Initiative: [DeepSEA][TH] EEC - To gain fair market share TH | 87847 | 7736 | Business Only Initiative | APAC - Commercial | APAC | Adisak Phungprasertying, Mellyana, Phasphitak Charoenphitak | On Track | [04/04/2025] - FY25 Baseline Applied | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-06-03 | 2026-03-06
Business Only Initiative: [DeepSEA][PH] Grow Cebu | 89468 | 7751 | Business Only Initiative | APAC - Commercial | APAC | Ma. Cristina Ignacio, Renato Lising | On Track | [05/28/2025] - FY25 Baseline Applied | G: L3 | On Hold | L3 Feedback Requested | 2024-08-01 | 2025-05-05
Business Only Initiative: [DeepSEA][ID] SRG RT | 87856 | 7663 | Business Only Initiative | APAC - Commercial | APAC | Al Faris Tarieq Alwyni, Mellyana | On Track | On track | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-08-01 | 2026-05-29
Business Only Initiative: [S2][ID] Hunter SS 2.0 External Hire |  | 89960 | Business Only Initiative | APAC - Commercial | APAC | Al Faris Tarieq Alwyni, Mellyana | On Track | [04/17/2025] - FY25 Baseline Applied | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-01-20 | 2025-11-03
Business Only Initiative: [DeepSEA][TH] CNX : Opportunity to Grow in the Nor | 87849 | 6912 | Business Only Initiative | APAC - Commercial | APAC | Chalengpot Ratsom, Waranya (Pu) Rattanakantong, Adisak Phungprasertying | On Track | 05/29/2025: FY25 Baseline Applied. | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-08-28 | 2025-04-25
Business Only Initiative: [DeepSEA][ID] BTH OB | 87853 | 7666 | Business Only Initiative | APAC - Commercial | APAC | Mardyah Sofian, Mellyana | On Track | Ready for L3 | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-08-01 | 2026-05-29
Business Only Initiative: [ASPIRE][VN] Grow revenue for SGN-IA/EU with 1D Tr | 32770 | 8232 | Business Only Initiative | APAC - Commercial | APAC | Lan D. Tran, SANG TRAN, Darren Han, Zoe Fan | On Track | Adjustment in monthly forecasts (Dec 2023 to Oct 2026) were made with reference to Nov 2023 actual and projected Dec 23 sales pipeline to better estimate actual market conditions where we had seen intensified competition following the flight launch. Competitors had been able to offer alternative air capacity at low prices that we had not be able to match due to the constrained air network capacity out of CAN Hub. Monthly forecasts will be refreshed moving forward when more data is available. | K: L5 | Active | L5 | 2023-08-01 | 2023-11-30
Business Only Initiative: [DeepSEA][PH] Grow SLR revenue TPAC and Intra-Asia | 87855 | 8438 | Business Only Initiative | APAC - Commercial | APAC | Ranny Chua | On Track | [05/28/2025] - FY25 Baseline Applied | I: L4 | On Hold | TEMP L4 - Enter L4 | 2024-06-04 | 2024-12-31
Business Only Initiative: [DeepSEA][TH] AYU : Saturate Unexplored Areas in A | 87850 | 9506 | Business Only Initiative | APAC - Commercial | APAC | Bigg Klinsupa, Giant Talawong | On Track | 05/28/2025 : FY25 Baseline Applied. | K: L5 | Active | L5 | 2024-08-16 | 2026-06-30
Business Only Initiative: [DeepSEA][MY] Sales Effectiveness for Seremban and | 87851 | 7709 | Business Only Initiative | APAC - Commercial | APAC | Nastain Mohd Razak, Nerissa Lee | On Track | New Sales AE has been onboarded and on the job for 8 months. Revenue showing beating goals monthly. | J: SL5 | On Hold | SL5 Finance Domain Lead Approval | 2024-10-18 | 2025-02-28
Business Only Initiative: [S2][PH] Grow IA IB for all vertical. |  | 90199 | Business Only Initiative | APAC - Commercial | APAC | Anna-Marie Liwag-Inawat, Mellyana, Cattleya Ann R. Corpuz | On Track | [05/28/2025] - FY25 Baseline Applied | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-02 | 2025-12-01
Business w/ Tech Initiative: CISCO - Customer Requirements |  | 161260 | Business w/ Tech Initiative | APAC - Commercial | APAC | Lisa Stockton, Richard Holloway, Kenneth McMahon, Wing Kin Chow, Xalas Hui, Mark N. Hoffmann | On Track | Work being completed using LE Planview Request | E: L2 | On Hold | L2 Feedback Requested
Business Only Initiative: [COMM] - FY26 Demand Surcharge P1 Upside |  | 163476 | Business Only Initiative | APAC - Commercial | APAC | Anita Yu, Mimi Yiu | On Track | On Track. Oct 03, 2025 : Added KPI of weight. Baseline, Actual, Forecast. Baseline is 0 beconz this is revenue upside on top of BP. | K: L5 | Active | L5 | 2025-08-20 | 2025-12-22
Business Only Initiative: APAC-EEU Growth Opportunity |  | 163485 | Business Only Initiative | APAC - Commercial | APAC | Ben Yuen | On Track | . | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: [COMM] Front Door APAC-EU |  | 164999 | Business Only Initiative | APAC - Commercial | APAC | Xalas Hui | On Track | 2025.11.10 Feedback to SVP Finance Note: No additional capacity / investment is requested beyond what is already planned in BP26. The Front Door initiative is planned to create a balanced lane growth portfolio in Asia Pacific to enable long-term revenue goals in line with Mission15. The long-term target margin is at double digit; short term is at 1% as we invest in this lane that is bigger than TPAC. On Track 2025.10.23 - * Reviewed with APAC Finance Pod Coach * Financials updated with revised BP exchange rate * One time pricing program * No Exit rate defined | K: L5 | Active | L5 | 2025-06-16 | 2025-10-30
Business Only Initiative: [COMM] TPAC Rebound |  | 165168 | Business Only Initiative | APAC - Commercial | APAC | Xalas Hui, Brian Chen, Ontheera Komutrat, Shine Peng | On Track | 2025.11.07 Feedback to SL3 SVP Finance The initiative is planned to revitalize the APAC to TPAC lanes revenue, tracking in DRIVE (Planview) to ensure milestones completion and projected revenue deliver per timeline. 2025.10.29 - One Time benefits reviewed with Finance Pod Coach Milestones with description are added | K: L5 | Active | L5 | 2025-06-02 | 2025-12-01
Business w/ Tech Initiative: Test - New Flow Business w Tech |  | 166959 | Business w/ Tech Initiative | APAC - Commercial | APAC |  | On Track | Cancellation request placed throgh INC033615299 by Darrien Han to remove initiative from APAC Commerical POD | C: L1 | Cancelled | L1
Business w/ Tech Initiative: APAC Online Latency & Reliability |  | 186310 | Business w/ Tech Initiative | APAC - Commercial | APAC | Kai-Bon Derrick Chan, Cathy Tee | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: M15 APAC Tier 2-4 City Penetration TH-EEC |  | 188432 | Business Only Initiative | APAC - Commercial | APAC | Waranya (Pu) Rattanakantong, Phasphitak Charoenphitak | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: M15-CN Tier 2-4 City Penetration (CZXA/WUXA/WNZA) |  | 188030 | Business Only Initiative | APAC - Commercial | APAC | Heng Hyman Zhang, Qi-Feng Huang | On Track | On Track | D: SL2 | Active | SL2 Domain Lead Approval
Business Only Initiative: SLR, Philippines |  | 188985 | Business Only Initiative | APAC - Commercial | APAC | Ranny Chua, Rico-Oscarito L. Medina | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: M15 CN Tier 2-4City Penetration (ChengduChongqing) |  | 188989 | Business Only Initiative | APAC - Commercial | APAC | Xia Betty Shui | On Track | On Track | D: SL2 | Active | SL2 Domain Lead Approval
Business Only Initiative: M15 - APAC Tier 2-4 City Penetration: TH-AYU |  | 189000 | Business Only Initiative | APAC - Commercial | APAC | Chirattaya Pituckanotai | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: M15-CN Tier2-4 city penetration (CGO/SIA/DLC/SHE) |  | 189003 | Business Only Initiative | APAC - Commercial | APAC | Yang-Lin Chai | On Track | On Track | D: SL2 | Active | SL2 Domain Lead Approval
Business Only Initiative: M15-CN Tier 2-4 City Penetration--DGM, SZV,HGH,FUO |  | 189011 | Business Only Initiative | APAC - Commercial | APAC | Ben Ye, Zheng Jed Peng | On Track | On Track | D: SL2 | Active | SL2 Domain Lead Approval
Business Only Initiative: M15-Scale Premium Air Freight for Lithium Battery |  | 190309 | Business Only Initiative | APAC - Commercial | APAC | Shu-Nga Cheung | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: FedEx TH as Authorized WHT Agent |  | 190722 | Business w/ Tech Initiative | APAC - Commercial | APAC | Jovelyn R. Senon | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: M15 Tier 2-4 CN Establish a New Partnership Model |  | 191131 | Business Only Initiative | APAC - Commercial | APAC | Zhi-Chu Roger Zhang | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: [M15] APAC E-commerce Platform Algorithm |  | 191134 | Business w/ Tech Initiative | APAC - Commercial | APAC | Cash Shen | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Cross-Border Cost Efficiency Last-Mile Partnership |  | 191241 | Business Only Initiative | APAC - Commercial | APAC | Yun Roger Xiao, Xiao-Yan Xu | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: M15 [VIB] - F&R Luxury DTD Solution & Return |  | 191244 | Business Only Initiative | APAC - Commercial | APAC | Abhinandan Pathak | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: M15 - AI/DC Mission Center |  | 191247 | Business Only Initiative | APAC - Commercial | APAC | Abhinandan Pathak, Paul Sousa | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Maximize Outcome from EC SaaS Companies & Alliance |  | 191250 | Business w/ Tech Initiative | APAC - Commercial | APAC | Gloria Yuan | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: SEA - Optimize in-country transit network with bet | 43482 | 6793 | Business Only Initiative | APAC - Ground | APAC | Mardyah Sofian, Budha Sari Widyaningrum | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-31
Business Only Initiative: (Core 2) - Ops Support Structure optimization | 73870 | 6891 | Business Only Initiative | APAC - Ground | APAC | Cecile Xi, Jimmy Zhang | On Track | completed initial analysis on saving opportunities in Jan, and obtained SVP's and VP's blessing in early Feb. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-02-01 | 2025-02-28
Business Only Initiative: CNS - Station Fedex practices | 43490 | 6930 | Business Only Initiative | APAC - Ground | APAC | Bo Hou, Fanny Yang, Yee Yong Tan | On Track | Green | K: L5 | Completed | L5 | 2023-11-21 | 2024-01-31
Business Only Initiative: CNS – Ops Contract Renegotiation | 58520 | 6944 | Business Only Initiative | APAC - Ground | APAC | Chloe Ye, KK Yan | On Track | Over 3.73M total value current CNS operation contracts spending in FY23, target to save about 6% during FY25. Total 7 contracts are selected at current stage for pilot after PE and FP&A's further review, given each contract saving percentage is different, we expected potential annual saving is 0.23M. | K: L5 | Completed | L5 | 2023-10-02 | 2024-02-29
Business Only Initiative: Customer Supply Management | 34055 | 6988 | Business Only Initiative | APAC - Ground | APAC | Ben Ye, Phoebe Huang | On Track | Sep 5 Reviewed the potential savings with Finance Emi-san, Tracy and Ben. Corrected the savings to US$1.8M instead of US$2.1M (included some MEISA markets). | K: L5 | Completed | L5 | 2023-10-02 | 2024-08-30
Business Only Initiative: CNN - Gateway Fedex practices | 43493 | 7026 | Business Only Initiative | APAC - Ground | APAC | Bryan Wei, Yong-Sheng Wu | On Track | Apr.9,2025 Rebaseline is no need due to YOY increamental is less than USD250K (USD41.9k decreamental FY26 VS FY25) | K: L5 | Completed | L5 | 2023-10-27 | 2024-01-01
Business Only Initiative: Station Operations Reports Optimization (SORO) | 37321 | 7064 | Business Only Initiative | APAC - Ground | APAC | Walter Shui, Rachel Chee | On Track | Green | K: L5 | Active | TEMP L5 - Enter L5 | 2023-09-14 | 2025-03-28
Business Only Initiative: Office consolidation opportunity in KR | 43476 | 7141 | Business Only Initiative | APAC - Ground | APAC | Jeroen De Boer, Jeong-Mi Seo | On Track |  | K: L5 | Completed | L5 | 2023-07-17 | 2024-01-31
Business Only Initiative: CN - Optimize in-country transit network with bett | 43480 | 7142 | Business Only Initiative | APAC - Ground | APAC | Shao Wei Cui, Mavis Yuan | On Track | the high level saving estimation is completed, we reviewed the draft study with Finance team twice this week, the net incurring benefit is updated from $1.4M to $1.1M, because we changed the exchange rate and removed CLH renegotiation out of scope. the review with Philip will be held next Monday or next Wednesday, depending on the FP&A's schedule. Per alignment between FedEx Finance and McKinsey, project team use the average spending of FY23 as base to calculate the potential benefits of this initiative. | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-31
Business Only Initiative: NPAC - Centralize operational contract mgmt | 43483 | 7143 | Business Only Initiative | APAC - Ground | APAC | Hitoshi Nasu, Kenji Shimizu | On Track |  | K: L5 | Completed | L5 | 2023-07-03 | 2024-03-01
Business Only Initiative: NPAC - In/outsourcing opportunity | 43500 | 7146 | Business Only Initiative | APAC - Ground | APAC | Mike Hung, Jimmy Wong | On Track | All initiatives launched | K: L5 | Completed | L5 | 2023-11-27 | 2024-07-31
Business Only Initiative: (Non Core) Ops Support Structure Optimization | 73183 | 7150 | Business Only Initiative | APAC - Ground | APAC | Abby Ang, Elaine Chua | On Track | Abby will take over as the IO | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-01 | 2025-02-28
Business Only Initiative: Singapore Changi Business Park Office relocation | 46481 | 7166 | Business Only Initiative | APAC - Ground | APAC | Jeroen De Boer, Jonathan Lee | On Track |  | K: L5 | Completed | L5 | 2023-10-27 | 2024-05-31
Business Only Initiative: CNN – Ops Contract Renegotiation | 58181 | 7243 | Business Only Initiative | APAC - Ground | APAC | Yang-Lin Chai, Janice Zhang | On Track |  | K: L5 | Completed | L5 | 2023-10-09 | 2024-01-31
Business Only Initiative: [P4] PH OT | 85896 | 7293 | Business Only Initiative | APAC - Ground | APAC | Donna Manibo, Jenieryll-Jomarie Mangalindan | On Track | GREEN | K: L5 | Completed | L5 | 2024-08-01 | 2024-08-15
Business w/ Tech Initiative: Vietnam Direct Serve Conversion - Corporate Load | 65767 | 7300 | Business w/ Tech Initiative | APAC - Ground | APAC | Ee-Hui Tan, Bao Nguyen | On Track |  | K: L5 | Active | L5 | 2023-11-01 | 2026-03-02
Business Only Initiative: Reinforcing SOP Compliance on Non-Stackable Shipme | 90401 | 7326 | Business Only Initiative | APAC - Ground | APAC | Kevin Zhang, Jimmy Zhang | On Track | Actionable Items before moving into L1 1. A revised NSS SOP that includes instructions that if we apply the NSS scan that NOTHING CAN BE STACKED ON TOP OF THE NSS pallet but we can stack the NSS pallet on another non NSS pallet if deemed safe 2. Source of measuring mechanism 3. the "assumptions" to get to $347K from current in terms of %NSS improving to 10.9% in scan 4.A process to have Ops take pictures of NSS scanned pallets and upload to accessible SharePoint site (this should be part of the SOP Terry's team releases. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-15 | 2025-04-01
Business Only Initiative: JP SV Program | 95901 | 7388 | Business Only Initiative | APAC - Ground | APAC | Kenji Shimizu, Kei Alan Kubota, Hitoshi Nasu | On Track | . | K: L5 | Completed | L5 | 2022-04-01 | 2024-05-31
Business Only Initiative: Intra-Asia IE Transit differentiation | 91862 | 7426 | Business Only Initiative | APAC - Ground | APAC | Paul Cheung, Glendy Ip | On Track | on going | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-16 | 2025-02-19
Business Only Initiative: (Core) Ops Support Structure optimization | 72101 | 7508 | Business Only Initiative | APAC - Ground | APAC | Walter Shui, Rachel Chee, Jimmy Zhang | On Track | 1. we have completed initial study on saving opportunities in Jan, and obtained SVPs' and VP's endorsement in early Feb. 2. For NPAC, due to time constraints, we haven’t yet completed the study, so we used weighted average saving percentage of SEA to simulate the number just to provide a sense of value size. | K: L5 | Completed | L5 | 2024-01-01 | 2025-03-31
Business Only Initiative: [P4] KR OT | 85898 | 7566 | Business Only Initiative | APAC - Ground | APAC | Jin-Kyung Kim, Jae-Wook Woo | On Track |  | K: L5 | Completed | L5 | 2024-08-15 | 2024-08-15
Business Only Initiative: [P4] HK Vendor Savings | 85778 | 7593 | Business Only Initiative | APAC - Ground | APAC | Steven Ying, James Chan | On Track | On Track | K: L5 | Completed | L5 | 2024-06-03 | 2024-08-23
Business Only Initiative: CN - Optimize in-country transit network with bett | 74361 | 7618 | Business Only Initiative | APAC - Ground | APAC | Shao Wei Cui, Mavis Yuan | On Track |  | K: L5 | Completed | L5 | 2024-04-01 | 2024-05-31
Business Only Initiative: PUD 2.0 - Garuda Project | 79700 | 7644 | Business Only Initiative | APAC - Ground | APAC | Ayu Restini, Rendy Rano Satria | On Track | 2,308,000 | K: L5 | Completed | L5 | 2024-05-16 | 2024-11-29
Business Only Initiative: [P4] HK OT | 85897 | 7674 | Business Only Initiative | APAC - Ground | APAC | Leo Cheung, Michael Koo | On Track |  | K: L5 | Completed | L5 | 2024-07-24 | 2024-08-15
Business Only Initiative: [S&P] China_CANIP commercial linehaul | 55476 | 7793 | Business Only Initiative | APAC - Ground | APAC | Lei Xie, Sebastien Charpentier | On Track |  | K: L5 | Completed | L5 | 2023-07-03 | 2024-02-01
Business Only Initiative: [S&P] North China - Beijing PUD project | 73194 | 7795 | Business Only Initiative | APAC - Ground | APAC | Tan Li, Sebastien Charpentier | On Track | The bidding phase has been completed. Savings has been identified, and verified by local FP&A. | K: L5 | Completed | L5 | 2023-09-01 | 2024-05-01
Business Only Initiative: [S&P] China PVGIP (Shanghai Gateway) Shuttles 2023 | 29941 | 7796 | Business Only Initiative | APAC - Ground | APAC | Yao-yao Huang, Sebastien Charpentier | On Track | The bidding phase has been completed. Savings has been identified, and verified by local FP&A. | K: L5 | Completed | L5 | 2023-05-12 | 2023-09-29
Business Only Initiative: [S&P] South China Cross-Border Trucking Service | 5303 | 7797 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track | The money step is completed, ready to start tracking the KPIs and the generated savings. Proofs of execution has been uploaded in the attachment section however the KPI and the Impact lag behind because of delay in getting the relevant data for calculation. | K: L5 | Completed | L5 | 2022-12-30 | 2022-12-30
Business Only Initiative: [S&P] South China Shuttles Project 2022 | 5842 | 7798 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track | The money step is completed, ready to start tracking the KPIs and the generated savings. Proofs of execution has been uploaded in the attachment section however the KPI and the Impact lag behind because of delay in getting the relevant data for calculation. | K: L5 | Completed | L5 | 2022-10-03 | 2022-10-03
Business Only Initiative: [S&P] PEKIP (Beijing Gateway) Shuttle project 2022 | 5845 | 7800 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track | The money step is completed, ready to start tracking the KPIs and the generated savings. Proofs of execution has been uploaded in the attachment section however the KPI and the Impact lag behind because of delay in getting the relevant data for calculation. | K: L5 | Completed | L5 | 2022-10-03 | 2022-10-03
Business Only Initiative: [S&P] WUHA (Wuhan) Shuttle Service | 5846 | 7801 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track | The money step is completed, ready to start tracking the KPIs and the generated savings. Proofs of execution has been uploaded in the attachment section however the KPI and the Impact lag behind because of delay in getting the relevant data for calculation. | K: L5 | Completed | L5 | 2022-12-30 | 2022-12-30
Business Only Initiative: [S&P] Customs Bonded Trucking Services in South Ch | 61856 | 7802 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2024-01-01
Business Only Initiative: [S&P] China Cross Border Trucking Services (Phase | 68579 | 7803 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track |  | K: L5 | Completed | L5 | 2023-10-02 | 2024-03-01
Business Only Initiative: [S&P] China - Bundled PUD Savings Reported into Wa | 79764 | 7804 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track |  | K: L5 | Completed | L5 | 2023-06-01 | 2025-05-30
Business Only Initiative: [S&P]Hong Kong Cross Border ULD Trucking Services | 95107 | 7806 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Sebastien Charpentier | On Track | Rebaseline to reflect benefits in FY26 and beyond. | K: L5 | Completed | L5 | 2024-08-15 | 2025-02-28
Business Only Initiative: ETD Process Standardization (Discontinue GENESIS S | 32650 | 8054 | Business Only Initiative | APAC - Ground | APAC | Yannie Kwok, Terry Fu | On Track |  | K: L5 | Completed | L5 | 2023-07-10 | 2024-06-28
Business Only Initiative: Reinforce REX83 scan for Bad Address shipments | 32651 | 8055 | Business Only Initiative | APAC - Ground | APAC | Yannie Kwok, Terry Fu | On Track |  | K: L5 | Completed | L5 | 2023-08-01 | 2023-10-31
Business Only Initiative: SEA - Operational Contract Renegotiation and Conso | 58704 | 8140 | Business Only Initiative | APAC - Ground | APAC | Vijendran Paripanapan, Kheng-Tek Lee | On Track | to be complete in May 2025 | K: L5 | Active | L5 | 2023-05-01 | 2025-06-02
Business Only Initiative: CN PEK Office Consolidation | 68456 | 8167 | Business Only Initiative | APAC - Ground | APAC | Jeroen De Boer, Wei-Jian Lin | On Track | green | K: L5 | Active | TEMP L5 - Enter L5 | 2023-11-14 | 2025-01-31
Business w/ Tech Initiative: AirMax---RMCC demand control | 74889 | 8183 | Business w/ Tech Initiative | APAC - Ground | APAC | Karl Zhang, Xu Jun | On Track | In good track | K: L5 | Completed | L5 | 2024-05-06 | 2024-11-15
Business Only Initiative: Enforce eco-driving and introduce auto start/stop | 43470 | 8184 | Business Only Initiative | APAC - Ground | APAC | Bryan Wei, Xue Ling | On Track | Apr.09, 2025 Re-baseline is no need, due to YOY incremental saving is less than USD250k (FY26 VS FY25: USD19k incremenal ) | K: L5 | Completed | L5 | 2023-08-01 | 2024-05-31
Business Only Initiative: Improve origin DIM capture rate | 32649 | 8190 | Business Only Initiative | APAC - Ground | APAC | Yannie Kwok, Terry Fu | On Track | Jul 16 MY team advised that the delivery of the machine will be delayed to end of Aug. So, the completion milestone is now revised to end of Sep. Apr 9 Updated actual impact based on the new methodology from Mck (use actual volume) Feb 6 The completion date of Milestone #67192 (JP) has been revised to Sep end due to long DWC purchasing lead time. Feb 1 1. Recurring Negative Impact for machine maintenance cost has been added. 2. The completion date of Milestone #38249 has been revised to March 17 due to some delay in US Jan 9 Updated Dec actual revenue impact Dec 15 1. Update "Forecast" of Recurring benefit from Dec 2023 to May 2027 2. Three new milestones regarding the additional dimming machines for CN, MY and JP have been added. Dec 12 Update Nov actual revenue upcharge. Dec 11 1. CLEAR for additional machine was submitted for CN, JP and MY. 2. PPMS was also created for the capital request for CN, JP and MY. Nov 16 Update actual benefits based on the method from Finance and Mck. Nov 2 The new machine in NRT was up and running on Nov 2. Oct 18 As advised by Mck, the final conclusion on how to track the actual performance can only be confirmed by end of Oct. For now, the actual upcharge was updated based on traditional methodology. Oct 16 Finance team is still working on the actual tracking methodology. Once finalized, actual revenue data will be updated for Jun to Sep. Oct 9 We are working with Finance to get project ID for CLEAR preparation for the 3 funded machines. Oct 5 Reviewed the following proposed methodology for actual revenue tracking with Emi-san and Pauline: Act vol*act rex82%* Act upcharge – base vol*base rex82%*base upcharge (baseline in FY23) Will update WAVE after Emi-san review it with Philip. Oct 3 The methodology on tracking the actual revenue upcharge was reviewed among Emi-san, Tony and Lannie. We all agreed on the approach. For details, please see the attachment. Sep 29 Updated actual revenue upcharge for Jun-Aug. Sep 26 Jane Amaba commented on initiative "Improve origin DIM capture rate": "FCH approved 9/19" Initiative #32649 "Improve origin DIM capture rate" has reached the required number of approvals. The Initiative was moved from state "Submitted for L3 approval" to state "L3 (Actions planned)". Sep 13 Finance SVP in the US has reached out to Philip and asked him to fund 3 dimming machines to support the initiative. Sep 12 Jane Amaba updated that this initiative was discussed on Sep 12 at the Finance Clearinghouse (FCH) meeting. Approval is pending confirmation if this is in the current FY24 financial forecast. Michelle Miller was following up on that. Update on Sep 6: With the new machine in TW up and running from Sep 1, the end to end DIM capture rate for packages from TW has increased from 71% to around 80%. This has enabled us to collect around US$1.7M/year. Update on Aug 30, 2023: 1. The new machine in TPEIP is planned to go live on Sep 1, 2023. 2. The new machine in NRT will start installation from Sep 13, 2023. It is expected to go live on Oct 15, 2023. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-07-17 | 2025-03-31
Business w/ Tech Initiative: Reduce PUX43 no package unproductive stops | 32652 | 8191 | Business w/ Tech Initiative | APAC - Ground | APAC | Terry Fu, Kathleen Tiu, Yannie Kwok | On Track | Aug 2 Updated from the AUT team in the US that the relevant IT team is still working on the issue (not able to send a positive notification to customers). So, the implementation of the 4 POC markets will be postponed to Aug 19. Jul 29 There was an issue with the end-to-end system tests in which the positive notifications did not work as expected in the test environment. The team needs time to verify the issue. With this, the completion date for the following 2 milestones were revised with 1 more week. Milestone #76578 Milestone #76567 Jul 16 The ENS team has MTP for the 4 POC markets on Jul 13. May 29, 2024 Created PPM and submitted for L3. May 21, 2024 Rebase the impact/values with FY24 YTD April data. Please refer to the attachments for details. May 10, 2024 Discussion among Marketing (Russell Fleming) and Enterprise Notification Service (ENS) team (Shankar Ramasamy) occurred last week. To avoid introducing new risks to the high priority visibility commercial items that have commitments at the executive level, including the top two priorities for the Peak timeframe, it was decided to support this imitative as per below plan: - 4 POC markets with English Notifications - ENS team will complete and MTP on Jul 13; - The rest markets with notifications in local languages - ENS team will complete and MTP on Sep 21. Feb 19, 2024 Meeting with Duncan Reid and Christian Piquet to discuss: The topics we wanted to cover are: 1) Your rollout plan for this initiative. 2) The required systems to be in place for the Automated Pickup tool. 3) The customer setup required for a customer to use the Automated Pickup Tool. 4) The language requirements for each market in your rollout plan. 5) Next steps to evaluate each market and confirm the customer base that will be able to be setup with the Automated Pickup Tool. Feb 9, 2024 Review with Sriram Krishnasamy and Tony Kreager on Feb 9, 2024. Jan 4, 2024 A meeting with the business owner of automated pickup and the business architect is scheduled on Jan 11. The intend of the meeting is to discuss the true AMEA needs for Automated Pickup for value and then proceed with an action item list of what teams need to perform research to get a scope for an MVP. Dec 7, 2023 Met with the Ex-PEL team again on Dec 7 and our initiative was approved to next step. •APPROVED to move to from Funnel to Ready for Assessment – Position 6 Dec 1 We shared our initiative in the Ex-PEL meeting. They all agreed that this is a good initiative and the potential cost savings are solid. They guessed the major challenge will be the customer notification in local language. So, Brian Marflak suggested we started with English markets and gradually replicate to other markets. They requested us to prioritize the markets (different local language) based on the size of the prize. We sent the data on Dec 1. Nov 21 We received invitation from Pam Coile to attend the Express Portfolio meeting on Nov 30/Dec 1 to present our request to the committee. Nov 16 Revised L3 timeline to Jan 31, 2024 based on the feedback from the TCH team as advised by Brian Marflak on Nov 11. Nov 8 Update from Brian Marflak on Nov 11: We won’t be able to start PRT until January. Unfortunately, we have been inundated with URGENT demand that we have been trying to balance. We had to rush Canada Transition Project, Possession without PUP/PUX and just recently have to expedite Max Whitetail. Currently this effort (iD3675 - AMEA Automated Pickup (DRIVE #32652)) resides in the No Status column of the Kanban with no WJSF determined. Below is a screenshot of our current schedule with the current backlog highlighted. We anticipate MAX White Tail PFS will be expedited to the top of our backlog as indicated. With everything we have in hand today, it is estimated that PRT could start the assessment of this effort no earlier that Jan 2024 without having to consider trade-offs. Nov 2 Brian Marflak updated Jimmy that our request actually involves | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-27 | 2026-05-04
Business Only Initiative: Improve origin weight capture rate | 35866 | 8192 | Business Only Initiative | APAC - Ground | APAC | Terry Fu, Yannie Kwok | On Track | Mar 25 Updated the actual impact using the actual volume and upcharge/package as per Finance and Mkc (Ryan). Submitted for L5 today. Dec 21 Submitted for L4. Dec 20 The last milestone completed on Dec 18. Dec 12 Updated Nov actual revenue upcharge. Dec 1 The last milestone for the MTP for the last local machine in CN (CANA) is delayed to Jan end and therefore, L4 date is revised to Jan 31. Nov 16 Updated Oct actual benefits based on the actual tracking method from Finance and Mck Oct 16 Submitted for L3. Oct 11 Updated milestones and updated it in WAVE. Will submit for L3 today if no further question from Finance. Oct 9 Reviewed the KPIs and milestones with Caroline. Caroline will arrange a meeting for IO to review the KPI and milestone with Philip before L3 submission. Oct 3 Impact, KPI and milestone were added for L3 submission. Caroline from China Fin team is on holiday this week. Will review the above with her (on Oct 9) before L3 submission. Sep 20 Revised the scope to exclude volume from SHEIN (accounts for around 45% of China total outbound) as per advice from Finance. It is because the pricing and billing terms and conditions for SHEIN are special and unique. The revenue impact dropped to US$2.6M from US$15M. Sep 6, 2023 Due to potential machine limitation, the target was adjusted to 85% instead of 90%. The impact changed from US$21M to US$15M. Aug 31, 2023 The estimated impact was reviewed with Caroline and Emi-san from Finance team Aug 30, 2023 The estimated impact was reviewed with Mimi and Simon from commercial team | K: L5 | Completed | L5 | 2023-08-22 | 2024-01-31
Business Only Initiative: Implementation of VALET in APAC | 72850 | 8194 | Business Only Initiative | APAC - Ground | APAC | Terry Fu, Yannie Kwok, Rick Yu | On Track | 04/20/2026 - All milestones completed. On track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2026-05-29
Business Only Initiative: Review of Policies and Procedures Impacting Operat | 43504 | 8199 | Business Only Initiative | APAC - Ground | APAC | Jeremy Goldstrich, Yee Yong Tan | On Track | Initiative put on hold after more groundwork is done with the following findings: 1.The volume of cash PUPs across APAC is small. 2.JP, KR, HK, SG, ID have no ROD. Markets like TW, PH, MY and TH have significant cash ROD activities on road, but there are already ongoing clearance initiatives aim to reduce cash handling in TW and SEA. 3.We are already imposing a handling fee for D&T ROD in most APAC countries. Imposing a cash surcharge on cash ROD can be deemed as double charging the customers. 4. Savings not significant even if all cash handling activities are eliminated (see table below). ![](inline-attachments/43504/image/1f08e642-42c0-4881-8bbf-d78b15be9b17-image.png) ![](inline-attachments/43504/image/08c00e68-c3a5-4066-aa91-cb5e58ac6096-image.png) | E: L2 | On Hold | L2
Business Only Initiative: ID - HQ Office Optimization | 68651 | 8201 | Business Only Initiative | APAC - Ground | APAC | Jeroen De Boer, Yin-Yen Kwan | On Track |  | K: L5 | Completed | L5 | 2024-01-01 | 2024-02-29
Business Only Initiative: [S&P] South Zhejiang PUD Project 2024 | 94471 | 8203 | Business Only Initiative | APAC - Ground | APAC | Yao-yao Huang, Yong-Meng Cui | On Track | Initiative On Track | K: L5 | Completed | L5 | 2024-08-09 | 2025-01-01
Business Only Initiative: [S&P] Shanghai Transportation Project 2024 | 96498 | 8205 | Business Only Initiative | APAC - Ground | APAC | Yao-yao Huang, Yong-Meng Cui | On Track | Initiative On Track | K: L5 | Completed | L5 | 2024-07-22 | 2025-01-01
Business Only Initiative: [OSC Savings] [GW/Hub] NRT WEC Ground Handling | 91547 | 8207 | Business Only Initiative | APAC - Ground | APAC | Shinsuke Tanaka, Yoshitaka Ito | On Track | A bid is required to change from Outsource to Insource. The bidding process is currently underway, but I will place the POD status as On Hold, as it will be difficult to determine the amount of the savings until then, as quotes from vendors are expected around November. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [S&P] Security - Singapore SCC renewal | 29817 | 8222 | Business Only Initiative | APAC - Ground | APAC | Stefano Baratella, Zakaria Qureshi | On Track | FY26 rebaseline activity completed on March 31st 2025 values are not incremental to FY25, therefore forecast has been set to zero according to instructions | K: L5 | Completed | L5 | 2023-01-27 | 2023-06-30
Business Only Initiative: CNN - In/outsourcing opportunity | 43497 | 8234 | Business Only Initiative | APAC - Ground | APAC | Dong Hou, Zorran Fu | On Track | Opportunities have been defined; project team was formed to work on detailed analysis in respect regions. the initial valuation was done after team meeting, it's not verified by FIN yet but submitted to WAVE as required. | K: L5 | Completed | L5 | 2023-11-30 | 2024-01-04
Business Only Initiative: VCIS - Direct Ops | 34067 | 8252 | Business Only Initiative | APAC - Ground | APAC | Pantene Pang, Jeslin Supardi, Yee Yong Tan | On Track | Cost Impacts validated by Finance (Emi Suzuki & Sho Yoshida) and all agreed to use actual HR Workday cost (salary, fringe & OT) numbers. Also since Courier-Leads, Motorbike & Foot Courier do have distinct routes, their headcounts and costs have been included as well. Using TH pilot variable compensation in FY22H1 and FY23H1, actual productivity gained was 6%-8%, which was based on either actual variable payout via individual performance (pilot group) or PPP payout (control group), whichever is higher. Hence, potential to have higher productivity. Initial assumption of 10% productivity increase for On-Road Frontline employees challenged by Financial Analyst. Revised productivity increase assumption to 6% instead. Value reduced from $6M to $4.8M. Call has been scheduled with HK & KR Ops MDs and Senior Mgrs on Aug 30 to seek their buy-in and agreement to pilot HK & KR first. Will submit to L2 for approval after seeking KT's approval. | I: L4 | Active | L4 | 2023-11-08 | 2026-04-01
Business Only Initiative: [P4] SG OT | 85894 | 8287 | Business Only Initiative | APAC - Ground | APAC | Bryan Tan | On Track |  | K: L5 | Completed | L5 | 2024-08-15 | 2024-08-15
Business Only Initiative: SEA - Station Fedex practices | 43491 | 8305 | Business Only Initiative | APAC - Ground | APAC | Kawit Rojanavasee | On Track |  | K: L5 | Completed | L5 | 2023-12-06 | 2024-03-29
Business Only Initiative: [P4] TH OT | 85893 | 8307 | Business Only Initiative | APAC - Ground | APAC | Kawit Rojanavasee | On Track | OT reduction actions launched and achieve per planned in past 4 months. | K: L5 | Completed | L5 | 2024-08-15 | 2024-08-15
Business Only Initiative: TW SV Program | 93627 | 8342 | Business Only Initiative | APAC - Ground | APAC | Michael Chu, Yee Yong Tan | On Track | On track for value generated by this initiative | K: L5 | Completed | L5 | 2023-10-02 | 2023-11-30
Business Only Initiative: [P4] MY OT | 85895 | 8389 | Business Only Initiative | APAC - Ground | APAC | Whai Teik Teoh | On Track |  | K: L5 | Completed | L5 | 2024-08-06 | 2024-08-15
Business Only Initiative: KR SV program | 96222 | 8390 | Business Only Initiative | APAC - Ground | APAC | Won-Dae Choi | On Track | 05/27 | K: L5 | Completed | L5 | 2023-11-01 | 2024-05-31
Business Only Initiative: Eliminate the manual DIM and Weight process | 34066 | 8792 | Business Only Initiative | APAC - Ground | APAC | Paul Cheung, Alex Chan | On Track | review the initiative with FA, sharing the logic and method for the saving calculation | I: L4 | Active | L4 | 2023-09-21 | 2026-02-27
Business Only Initiative: CNN GOLF - Station Optimization | 43489 | 8922 | Business Only Initiative | APAC - Ground | APAC | An Tian, Michael Zhang | On Track | Money step completed, stable savings | K: L5 | Completed | L5 | 2024-01-01 | 2024-08-01
Business Only Initiative: [OSC Savings] [GW/Hub] KIX SPJ Ground Handling | 91543 | 9304 | Business Only Initiative | APAC - Ground | APAC | Asataro Fukuhara, Katsutoshi Ueda | On Track | - | K: L5 | Completed | L5 | 2024-10-10 | 2024-10-10
Business Only Initiative: [OSC Savings] [GW/Hub] KIX CKTS Ground Handling | 91544 | 9306 | Business Only Initiative | APAC - Ground | APAC | Asataro Fukuhara, Katsutoshi Ueda | On Track | - | K: L5 | Completed | L5 | 2024-10-10 | 2024-10-10
Business Only Initiative: [OSC Savings] [GW/Hub] KIX SPJ Pushback | 91546 | 9309 | Business Only Initiative | APAC - Ground | APAC | Asataro Fukuhara, Katsutoshi Ueda | On Track | - | K: L5 | Completed | L5 | 2024-10-10 | 2024-10-10
Business Only Initiative: NPAC - Station Fedex practices | 43492 | 9375 | Business Only Initiative | APAC - Ground | APAC | Jack Wu, Avery Tsai | On Track | There are some of improving our in-station operation methods and idea come out form JP ?KR ?HK and TW as below, In FY24. 1. For time card paperless 2. Creation specifications for e-VIR 3. e-Route Book 4. e-Daily Route Assignment 5. e-OSA ED3.0 Trace handling | K: L5 | Completed | L5 | 2023-12-15 | 2025-05-30
Business Only Initiative: SEA - In/outsourcing opportunity | 43499 | 9388 | Business Only Initiative | APAC - Ground | APAC | Ayu Restini | On Track | The values and impact has been uploaded in WAVE. All of the districts (ID and MY) has submitted their detailed calculations and assumptions to FA. These were submitted for review by EMI and Philip prior to L2 submission. | E: L2 | On Hold | L2 | 2024-07-22 | 2024-09-06
Business Only Initiative: [S&P] PVGIP sortation maintenance service RFP | 31300 | 9519 | Business Only Initiative | APAC - Ground | APAC | Luigi Mastromonaco, Gergana Kacheva | On Track |  | K: L5 | Completed | L5 | 2023-10-30 | 2023-10-30
Business w/ Tech Initiative: Optimize Stops Sequencing to improve OnRoad Effici | 32628 | 9524 | Business w/ Tech Initiative | APAC - Ground | APAC | Bill Roque, Kenneth Leung, Shuo Sun | On Track | on track | I: L4 | Active | L4 | 2023-10-13 | 2025-07-18
Business w/ Tech Initiative: Optimize On-Road Route Plan to improve OnRoad Effi | 32634 | 9525 | Business w/ Tech Initiative | APAC - Ground | APAC | Bill Roque, Kenneth Leung, Shuo Sun | On Track | On track | I: L4 | Active | L4 | 2023-10-23 | 2026-01-30
Business Only Initiative: China FY25 - Lease Renewal Strategy |  | 86766 | Business Only Initiative | APAC - Ground | APAC | Wei-Jian Lin, Jeroen De Boer, Mei-Ling Minnie Situ | On Track | CN FY25 Lease renewals on track as per normal BAU, no delays expected. | K: L5 | Active | L5 | 2025-01-01 | 2025-05-30
Business Only Initiative: EE – CN EC center consolidation FY25 saving |  | 89253 | Business Only Initiative | APAC - Ground | APAC | Fei Faye Ning, Shao Wei Cui | On Track | aligned with ops MDs on the approachs of achieving saving in FY25 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-12-19 | 2025-11-28
Business Only Initiative: [S&P] CN North Jiangsu & Anhui PUD Tender FY25 |  | 90314 | Business Only Initiative | APAC - Ground | APAC | Jing-Yi Olivia Zeng, Yong-Meng Cui | On Track | Green | K: L5 | Completed | L5 | 2024-08-27 | 2025-04-15
Business Only Initiative: Tender of Ground Handling Shanghai China |  | 91693 | Business Only Initiative | APAC - Ground | APAC | Wai-Yee Asley | On Track | SCT already approved. The new contract will be effective on 15 Mar 2025. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-09-02 | 2025-04-15
Business Only Initiative: [S&P] China SpS Clinical transportation |  | 105763 | Business Only Initiative | APAC - Ground | APAC | Lei Xie, Yong-Meng Cui | On Track | Will calculated actual savings based on vendor's monthly billing statement which verified and provided by Ops. | K: L5 | Active | L5 Feedback Requested | 2025-01-01 | 2025-05-15
Business Only Initiative: [S&P] Redesign of Supply Chain ULD Cover |  | 109253 | Business Only Initiative | APAC - Ground | APAC | Jason Ng | On Track | 04/24: The project was implemented starting from 01 March 2025. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-09-16 | 2025-03-03
Business w/ Tech Initiative: Surgical Demand Control |  | 127954 | Business w/ Tech Initiative | APAC - Ground | APAC | Matthew Au | On Track | Duplicate | C: L1 | Cancelled | L1
Business Only Initiative: [GW/Hub] PVGIP Facility/Sort MX Contract & Consuma | 91539 | 7564 | Business Only Initiative | APAC - Ground | APAC | Ricky Ying, Henry Wang | On Track | n.a | K: L5 | Completed | L5 | 2024-04-01 | 2024-10-04
Business Only Initiative: Ramp & Warehouse Optimization Phase 1 (KIX & NRT- | 73398 | 7565 | Business Only Initiative | APAC - Ground | APAC | Jose Ignacio Ibarguen, Yee Yong Tan, Katsutoshi Ueda | On Track | We request the cancellation of this initiative at KIX due to significant operational constraints. The current staffing model at KIX relies heavily on outsourced vendor personnel, with contracts structured around parcel movement. Incorporating the time management tool would require reopening these contracts to include testing provisions, which is not recommended. Given these limitations, both the local Operations VP and the APAC P&E VP have endorsed relocating the POC from KIX to TPE. The TPE location operates under a predominantly FedEx staffed structure, providing greater control over individual activities and facilitating tool implementation. A new PV initiative will be submitted to reflect the tool’s testing at TPE. Despite the challenges encountered at KIX, we have confirmed that the tool demonstrates strong potential to support our preferred future state (PFS) by enhancing Gateway and Ramp resource management. Currently, APAC lacks dedicated resource management solutions to effectively manage staffing at gateways and ramps, and this tool presents a promising option to address that gap. | G: L3 | Cancelled | L3 | 2024-04-15 | 2025-12-10
Business Only Initiative: [OSC Savings] [GW/Hub] PVGIP Self-Handling | 91541 | 7826 | Business Only Initiative | APAC - Ground | APAC | Wen-Ming Michael Li, Shan-Shan Dong | On Track | On Track | K: L5 | Completed | L5 | 2022-09-01 | 2024-06-14
Business Only Initiative: APAC [GW/Hub] SZXIP Employee shuttle bus | 91542 | 8231 | Business Only Initiative | APAC - Ground | APAC | Xiao-Gang Yang, Zhi-Ping Wang | On Track | 1. The cost save is on track by monthly and beat the plan 2. No additional save in FY26 (11Apr2025) | K: L5 | Completed | L5 | 2024-05-13 | 2024-07-31
Business Only Initiative: [OSC Savings] [GW/Hub] PVGIP Temp contract | 91537 | 8324 | Business Only Initiative | APAC - Ground | APAC | Karl Zhang | On Track | The savings is in good track as plan. | K: L5 | Completed | L5 | 2024-02-20 | 2024-10-31
Business Only Initiative: [OSC Savings] [GW/Hub] PVGIP Employee shuttle bus | 91538 | 8325 | Business Only Initiative | APAC - Ground | APAC | Karl Zhang | On Track | The savings is in good track as plan | K: L5 | Completed | L5 | 2023-10-10 | 2023-12-29
Business Only Initiative: [OSC Savings] [GW/Hub] CANH Temp contract | 91540 | 6986 | Business Only Initiative | APAC - Ground | APAC | Ryan Zhou, Christina Gan | On Track |  | K: L5 | Completed | L5 | 2024-03-01 | 2024-10-16
Business Only Initiative: CN SZX/DAT CCO Saving |  | 131600 | Business Only Initiative | APAC - Ground | APAC | Xiao-Gang Yang, Kathleen Tiu, Hong-Yan Karen Duan | On Track | FP&A and Sales reveiw the yield performance of DATIP Customers on 06/18/2025 | K: L5 | Active | L5 | 2025-06-09 | 2025-07-25
Business w/ Tech Initiative: China Linehaul Optimization |  | 139894 | Business w/ Tech Initiative | APAC - Ground | APAC | Shao Wei Cui, Mavis Yuan, Fei Faye Ning | On Track | L1 | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Tender Surface Transportation South China |  | 141502 | Business Only Initiative | APAC - Ground | APAC | Jing-Yi Olivia Zeng, Yong-Meng Cui | On Track | This initiative has been identified and planned by The finalized FY26 Strategic Sourcing category plan for Surface Transportation, every step is on track. | K: L5 | Active | L5 | 2025-09-01 | 2025-10-01
Business Only Initiative: EMR- Tenders Surface Transportation Networks China |  | 141505 | Business Only Initiative | APAC - Ground | APAC | Yong-Meng Cui, Yao-yao Huang | On Track | According to the finalized Strategic Sourcing category plan FY26 for Surface Transportation, every key step is on track. | K: L5 | Active | L5 | 2025-09-01 | 2025-10-01
Business Only Initiative: EMR-Tender Surface Transportation Domestic CLH |  | 141508 | Business Only Initiative | APAC - Ground | APAC | Lei Xie, Yong-Meng Cui | On Track | FY26 Strategic Category plan for Surface Transportation has identified the multipe tenders already, the plan is in place. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-09-01 | 2025-12-02
Business Only Initiative: EMR-Tenders Intra-city & ODA/OPA China |  | 141511 | Business Only Initiative | APAC - Ground | APAC | Jing-Yi Olivia Zeng, Yong-Meng Cui | On Track | The progress is on track. | K: L5 | Active | TEMP L5 - Enter L5 | 2026-03-02 | 2026-03-02
Business w/ Tech Initiative: JP Grow Chubu IB OB |  | 153827 | Business w/ Tech Initiative | APAC - Ground | APAC | Teruaki Yamashita | Some Issues | Since the change in DRIVE thresholds, this measure will be handle as a local project. | C: L1 | Cancelled | L1
Business Only Initiative: China FY26 - Lease Renewal Strategy |  | 155223 | Business Only Initiative | APAC - Ground | APAC | Wei-Jian Lin, Mei-Ling Minnie Situ | On Track | Rental saving comes from each lease renewal result, can be tracked by monthly | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2026-05-01
Business Only Initiative: CN NCW CCO SAVING |  | 156585 | Business Only Initiative | APAC - Ground | APAC | Yang-Lin Chai | On Track | Renegotiation has been completed, is monitoring results. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-06-02 | 2025-08-01
Business Only Initiative: CN PVG GW Saving |  | 156590 | Business Only Initiative | APAC - Ground | APAC | Karl Zhang, Kathleen Tiu, Ricky Ying | On Track | On track | K: L5 | Active | L5 | 2025-03-03 | 2025-10-27
Business Only Initiative: CN CAN GW Saving |  | 156593 | Business Only Initiative | APAC - Ground | APAC | Di Wu, Pinky Jiang | On Track | Added 2nd IO | K: L5 | Active | L5 | 2025-06-16 | 2025-09-01
Business Only Initiative: CN CAN/XMN/CTU CCO Saving |  | 156596 | Business Only Initiative | APAC - Ground | APAC | Jun Cheng, Pinky Jiang | On Track | 2/9/2026 : SHEIN volume decrease in Jan lead to less saving from SBZ on-site handling fee and clearance fee. 11/10/2025: update the target saving again due to project OWN implementation. One of action items will not generate saving after Oct as operation scenario has changed. The related saving will reflected in project OWN result. And two action items new added into this initiative. 10/17/2025: update the target saving after align with Fin and GTS, part of saving will shift to a GTS PV related to iClear. 9/30/2025: all action items has achieved to money step. added 2nd IO | K: L5 | Active | L5 | 2025-05-21 | 2025-09-30
Business Only Initiative: CN GSH PUD Saving |  | 156599 | Business Only Initiative | APAC - Ground | APAC | Bin Qin | On Track | on track | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-02 | 2026-01-01
Business Only Initiative: CN MSD PUD Saving |  | 156603 | Business Only Initiative | APAC - Ground | APAC | Li-Wei Emma Wang, Pinky Jiang | On Track | adding 2nd IO | K: L5 | Active | L5 | 2025-04-01 | 2025-12-01
Business Only Initiative: CN PEKIP GW Saving |  | 156606 | Business Only Initiative | APAC - Ground | APAC | Yong-Sheng Wu | On Track | Contract signed with vendor and the contract started from Aug.1,2025 | K: L5 | Active | L5 | 2025-06-30 | 2025-08-01
Business Only Initiative: CN PRD PUD Saving |  | 156609 | Business Only Initiative | APAC - Ground | APAC | Chao-Huang Kevin Lian | On Track | On track | I: L4 | Active | L4 | 2025-06-02 | 2026-06-30
Business Only Initiative: CN YRD PUD Saving |  | 156656 | Business Only Initiative | APAC - Ground | APAC | Zheng Jed Peng, Zorran Fu | On Track | Re-negotiation has been completed, now is monitoring results. | I: L4 | Active | L4 | 2025-06-02 | 2026-03-02
Business Only Initiative: CN GSH CCO Saving |  | 156659 | Business Only Initiative | APAC - Ground | APAC | Bin Qin | On Track | On Track | K: L5 | Active | L5 | 2025-05-30 | 2025-10-31
Business Only Initiative: CN DSH PUD savings |  | 156662 | Business Only Initiative | APAC - Ground | APAC | Lin Eagle Zhou | On Track | on track | I: L4 | Active | L4 | 2025-08-01 | 2026-05-29
Business Only Initiative: CN PVG CCO Saving |  | 156665 | Business Only Initiative | APAC - Ground | APAC | Wen-Jie Jack Li | On Track | On track | I: L4 | Active | L4 | 2025-09-01 | 2025-12-30
Business w/ Tech Initiative: APAC Ops Performance Mgt Digitization |  | 157700 | Business w/ Tech Initiative | APAC - Ground | APAC | Kathleen Tiu, Hendy Leong | On Track | Requested by Kathleen Tiu | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR - Tender of Ground Handling Beijing China |  | 154874 | Business Only Initiative | APAC - Ground | APAC | Wai-Yee Asley | On Track | The contract with selected vendor BGS is mutually signed and started on 1 Jul 2025. The actual invoice copy will be obtained from supplier to calculate actual saving in each month and actual saving will be inputted in Planview. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-28 | 2025-07-01
Business Only Initiative: CN Network Fit |  | 162659 | Business Only Initiative | APAC - Ground | APAC | Sunny Zheng, Mavis Yuan, Shao Wei Cui | On Track | L1 | K: L5 | Active | L5 | 2024-09-02 | 2025-10-31
Business Only Initiative: APAC: Structural Cost Savings in Japan Gateway Ops |  | 163093 | Business Only Initiative | APAC - Ground | APAC | Kengo Taguchi, Terry Cheung | On Track | April, 20th, 2026: Upated for March transaction: - ATFC completed additional 23 VFTE training, onboarding for operation from April (productivty 50% - JP Temp reduction is aligned with plan 50K USD/month - However, JP FTE S&W plan is negative because of 10HC reduction but no cost change due to SI 4.1% increase and 11 HC promotion in Oct 2025 - Going forward, SI incremental factors will be captured separately in order to understand pure saving. Mar-26¦ Plan ¦ Actual ¦ Plan vs Actual Gap ¦ Remarks JP S&W (incl OTFTE) saving38,000(28,253)(66,253)No SI 4% and 11 promotion cost, not dialed in. ATFC S&W cost16,90318,548(1,645) JP OSC to coversion saving64,83367,0222,189 JP CCO Temp saving25,40052,01126,611 NACCS IDA saving6,0006,000 JP Temp coverted cost49,32852,819(3,491) Total68,00225,413-32,316 Feb-26¦ Plan¦ Actual¦ Plan vs Actual Gap ¦ Remarks JP S&W (incl OTFTE) saving38,000(17,678)(55,678)No SI 4% and 11 promotion cost, not dialed in. ATFC S&W cost16,90312,5914,312 JP OSC to coversion saving64,83367,0222,189 JP CCO Temp saving25,40032,0116,611 NACCS IDA saving6,0006,000 JP Temp coverted cost49,32853,258(3,930) Total68,00221,506-46,496 Jan-26Plan ¦Actual ¦Plan vs Actual Gap ¦Remarks JP S&W (incl OTFTE) saving38,000(26,663)(64,663)No SI 4% and 11 promotion cost, not dialed in. ATFC S&W cost16,903100,312(83,409)Due to performance bonus month JP OSC to coversion saving64,83367,0222,189 JP CCO Temp saving25,40039,50814,108 NACCS IDA saving6,0006,000 JP Temp coverted cost49,32854,921(5,593) Total68,002-69,366-137,368 Jan27th, 2026: Upated for Dec transaction: - ATFC completed hiring additional 23 VFTE for additional 10-15% JP entry build off-shoring. (17k USD/month) - ATFC purchased Note PC for 23 agents. (ontime cost 36K USD) - JP completed OSC to Temp conversion transition. Counted one time cost 35K USD for new temp training Nov1st, 2025: Updated KPI LineNote as "USD(% cost reduction will be monitored by $ divided by baseline $)" Oct31st, 2025: Submitted for SL2 as... - All necessary information are updated based on the EPM (Eryn Walter) feedback, - The APAC domain PMO (Krishnaprasad Ramachandran) was completed for SL2 submission. Sept28th, 2025: Answer to the question from SL2 EPM Notes: Can you please elaborate on the action being taken to achieve value? 1. Systems-Tools-SOP Review with OT control We are re-engineering SOPs and leveraging local tools to eliminate inefficiencies and improve process flow: - Entry build rework process: Licensed brokers to directly amend errors and record a memo for later review, instead of sending items back into the queue for rework. This reduces duplicated work. - Customer profile database: Perform housekeeping to remove non-active profiles older than 3 years, reducing system clutter and improving lookup speed. - Shipment auto-classification: Review and optimize existing rules to increase the share of automatically categorized shipments, streamlining workflow and reducing shipment variation. - Entry build local tool: Enhance usability of the HS lookup tool to boost entry build productivity. - We are implementing a digital productivity management approach: Use MS-Power Apps (PC based) to capture daily employee activity and track productivity across all workforce types (FTEs, vendors, OSC). - Conduct monthly productivity reviews with PE (GTS) and Ops leadership to identify the root cause of OT gaps and set improvement actions. - Reallocate work to ensure optimal use of Operational FTEs (OTFTEs). 2. Labor Cost Optimization We are expanding lower-cost labor deployment to reduce Japan-based vendor dependency: - Leverage the ATFC (Philippines clearance center) for additional volume handling. - Utilize the foreign worker program to supplement operations at a lower cost base. 3. Operating expense review Identify recurring operating expenses (monthly fee, printing, equipment rental/contract) co | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-03 | 2027-01-29
Business Only Initiative: JP PUD Cost Saving |  | 163097 | Business Only Initiative | APAC - Ground | APAC | Kenji Shimizu, Hitoshi Nasu | On Track | Add Milestone and Financial Forecast Add Key Assumption Add Estimated Baseline Value, Target Value Add IO. We've filled in the required fields for now. The cost reduction figures may be subject to change. | I: L4 | Active | L4 | 2025-01-01 | 2025-06-02
Business Only Initiative: [CN - OWN] CN Station In-sourcing |  | 163101 | Business Only Initiative | APAC - Ground | APAC | An Tian, Fei Faye Ning, Shao Wei Cui, Francis Kong | On Track | On Track | I: L4 | Active | TEMP L4 - Enter L4 | 2025-08-01 | 2025-12-01
Business Only Initiative: [CN - Threshold] CN Data-Entry Vendor Optimization |  | 163104 | Business Only Initiative | APAC - Ground | APAC | Li-Xia Eva Yang, Chunyong Zhang | On Track | 9/29 On track | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2025-06-20 | 2025-12-31
Business Only Initiative: KR Gateway Cost Saving |  | 163253 | Business Only Initiative | APAC - Ground | APAC | Hoon-Joong Lee | On Track | Actual saving realized | K: L5 | Active | L5 | 2025-03-03 | 2025-06-02
Business Only Initiative: JP Gateway Cost Savings |  | 163256 | Business Only Initiative | APAC - Ground | APAC | Katsutoshi Ueda, Yoshitaka Ito, Shinsuke Tanaka, Hidenori Mayuzumi, Asataro Fukuhara | On Track | Planning is on-going | I: L4 | Active | L4 | 2024-07-22 | 2025-07-31
Business Only Initiative: KR Inbound A1 Scope Revisit |  | 163491 | Business Only Initiative | APAC - Ground | APAC | Sun-Pil Rho | On Track | 10/01/25 [Completed Actions] •Transitioned 2,789 postal code areas from Next Day Delivery to Same Day Delivery via GGX, as part of the Service Expansion plan in December 2022. •Conducted delivery frequency analysis over 30 months of shipment data. •Identified 1,266 postal code areas as low-potential or cost-inefficient. •After two rounds of review with the Sales team: oDecided to discontinue Same Day Delivery via A1 Service in 667 postal code areas. oExcluded 599 postal code areas from the initial discontinuation list. [Ongoing Actions] •Currently in discussion with the Sales team regarding the remaining 559 postal code areas. •Evaluating which of these areas may also be eligible for service discontinuation based on delivery efficiency and cost-effectiveness. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-10-27 | 2025-12-01
Business Only Initiative: China Vehicle Replacement Saving |  | 163494 | Business Only Initiative | APAC - Ground | APAC | Zhao-Rong Zhang | On Track | on track | G: L3 | Active | TEMP L3 - Enter L3 | 2026-03-02 | 2026-06-30
Business Only Initiative: TH Outsource |  | 165942 | Business Only Initiative | APAC - Ground | APAC | Kawit Rojanavasee | On Track | All key milestones including money step completed | I: L4 | Active | TEMP L4 - Enter L4 | 2025-05-01 | 2025-11-28
Business Only Initiative: TW PUD Cost Savings |  | 165945 | Business Only Initiative | APAC - Ground | APAC | Chien-Wen Shih, Paul Sousa | On Track | Estimaing L1 LBC// The value for TW PUD initiative is too small to move forward, hence we can put on HOLD now and re-use it for some other initiative idea later. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: APAC Truck Management APP |  | 165948 | Business Only Initiative | APAC - Ground | APAC | Rick Yu | On Track | 2/10 - Cancelling request is made. The development of the App is on good track. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Optimize NRT Sat Operation / ATA mix termination |  | 166569 | Business Only Initiative | APAC - Ground | APAC | Masahiro Anzai, Rumi Ikeda | On Track | On track | G: L3 | Active | L3 | 2025-12-01 | 2026-07-07
Business Only Initiative: TW - Optimize Shuttle OPTG Model |  | 166968 | Business Only Initiative | APAC - Ground | APAC | Chien-Wen Shih, Kathleen Tiu | On Track | On Track | G: L3 | Active | L3 | 2026-03-02 | 2026-11-11
Business Only Initiative: TW - Adopt New B2C Model |  | 167002 | Business Only Initiative | APAC - Ground | APAC | In-Woo Ha, Kathleen Tiu | On Track | Scope to be expanded to APAC-wide, and explore RESI customer self-PUP options such as lockers, retail box or convenience store. | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business Only Initiative: JP Shuttle Utilization Improvement |  | 167032 | Business Only Initiative | APAC - Ground | APAC | Tomoya Kimura, Rumi Ikeda | On Track | Consolidate with 167043 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: JP Shuttle Dashboard for Consolidation |  | 167043 | Business Only Initiative | APAC - Ground | APAC | Rumi Ikeda, Tomoya Kimura | On Track | after the analysis and study of the savings value, total valuse for this initiative is quite small (US$4k yr) We will monitor it outside Planview. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: JP Shuttle Coloading Opportunity and SSX Reduction |  | 167046 | Business Only Initiative | APAC - Ground | APAC | Tomoya Kimura, Rumi Ikeda | On Track | This initiative to be cancelled as all change required is out of FedEx control, only minimum saving is estimated after initial study and vendor has concern with the proposal. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Expansion of SRO to MY and TH |  | 167052 | Business Only Initiative | APAC - Ground | APAC | Bill Roque, Kenneth Leung, Shuo Sun | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: HK - Close HKGC WSC |  | 167570 | Business Only Initiative | APAC - Ground | APAC | Jimmy Wong | On Track | On Track | I: L4 | Active | L4 | 2025-03-31 | 2025-07-31
Business Only Initiative: HK - Insourcing |  | 167575 | Business Only Initiative | APAC - Ground | APAC | Jimmy Wong | On Track | On Track | I: L4 | Active | L4 | 2025-08-15 | 2026-03-31
Business Only Initiative: HK - OT Saving |  | 167578 | Business Only Initiative | APAC - Ground | APAC | Jimmy Wong | On Track | On Track | I: L4 | Active | L4 | 2025-08-29 | 2026-02-27
Business Only Initiative: SG Operations OT Reduction |  | 167581 | Business Only Initiative | APAC - Ground | APAC | John Patrick De Leon, Kathleen Tiu | On Track | On Track | I: L4 | Active | L4 | 2025-12-01 | 2026-03-06
Business Only Initiative: JP - Ramp Insourcing for NRT Ops |  | 167584 | Business Only Initiative | APAC - Ground | APAC | Hideo Nakakuki, Kathleen Tiu | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: TYOPC/NRT Ops Efficiency Improvement |  | 167587 | Business Only Initiative | APAC - Ground | APAC | Masahiro Anzai, Kathleen Tiu | On Track | .12/19/2025 - Initiative pivot to capture ATA operational cost reduction and due to low value, is merged with PV# 166569 - 'Optimize NRT Sat Operation / ATA mix termination'. This initiative to be put On-hold in the interim. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: SG-Station Process Redesign following attrition |  | 167590 | Business Only Initiative | APAC - Ground | APAC | Brian Neo | On Track | On Track | I: L4 | Active | L4 | 2025-12-16 | 2026-01-07
Business Only Initiative: JP NGOA Satellite Station |  | 167593 | Business Only Initiative | APAC - Ground | APAC | Kenji Shimizu | On Track | On Track | G: L3 | Active | L3 | 2025-06-02 | 2026-05-29
Business Only Initiative: KR Surge - Courier Service Optimization |  | 167596 | Business Only Initiative | APAC - Ground | APAC | Won-Dae Choi | On Track | On Track | G: L3 | Active | L3 | 2025-11-03 | 2026-04-30
Business Only Initiative: KR Surge - Supplies Optimization |  | 167599 | Business Only Initiative | APAC - Ground | APAC | In-Woo Ha | On Track | per the item lead (Sung-Jin Lee), the purchase cost of supplies from the local vender is actually higher. | C: L1 | Cancelled | L1
Business Only Initiative: KR Surge - ICN Gateway Resource Cost Optimization |  | 168104 | Business Only Initiative | APAC - Ground | APAC | In-Woo Ha, JY Kim | On Track | project was targeting for May'26 implementation at first, however due to summer slot complication, was decided to postpone for winter impelmentation. (Sijia, APAC network) | E: L2 | Active | L2
Business Only Initiative: KR Surge - ICN Gateway Resource Cost Optimization |  | 168105 | Business Only Initiative | APAC - Ground | APAC | In-Woo Ha | On Track | duplicated with KR Surge - ICN Gateway Resource Cost Optimization (Strategy Sequence ID 168104) | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Project Beyond (Phase II) cancelled |  | 168234 | Business w/ Tech Initiative | APAC - Ground | APAC | Vivien Zhang | On Track | duplicate with 168236, delete 168234 | C: L1 | Cancelled | L1
Business Only Initiative: TW Gateway Cost Restructuring |  | 177925 | Business Only Initiative | APAC - Ground | APAC | Yuan-Ming Dustin Wang, Terry Cheung | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: VN Restructure Cities - Biz with Tech |  | 184944 | Business w/ Tech Initiative | APAC - Ground | APAC | Hoang Anh Truong, Darren Han, Yoshitaka Ito, Ee-Hui Tan | Attention Needed | (2026.03.27) Complete L1 architecture review. (2026.03.26) EPC approved for the Business Continuity designation. (2026.03.13) Escalation needed to expedite IT development works to comply VN regulations. | E: L2 | Active | L2
Business Only Initiative: Transition Plan: TW-PH Offshoring Implementation |  | 186109 | Business Only Initiative | APAC - Ground | APAC | Chien-Hung Chen, Hing-Lung Henry Hau, Rubio V. Laroya Jr. | On Track | 2026/3/20 by Aaron GTS and TW CCO mgmt have aligned and confirmed the Business Case proposal this week, and will proceed with obtaining MD approval next week 2026/3/26 by Aaron TW CCO prefers to hold the session during the week of 3/30 to obtain OPS MD approval | C: L1 | Active | L1
Business Only Initiative: Transition Plan: KR-PH Offshoring Implementation |  | 186518 | Business Only Initiative | APAC - Ground | APAC | Dong-Sik Woo | On Track | On Track 2026/02/27 Dong-sik Woo: I would like to request the cancellation of PV# 186518, as KR team will not be proceeding with this project futher. The decision has already been aligned with and communciated to KR Clearance Operations management team. | C: L1 | Cancelled | L1
Business Only Initiative: Turbo Process |  | 187851 | Business Only Initiative | APAC - Ground | APAC | Yi Phoebe Zhang, Chunyong Zhang | On Track | On Track | E: L2 | Active | L2 | 2026-02-17 | 2026-05-29
Business Only Initiative: ID Gateway Cost Saving |  | 187854 | Business Only Initiative | APAC - Ground | APAC | Shandy Yudha Nugraha, Mellyana | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: SG Gateway Cost Savings |  | 188034 | Business Only Initiative | APAC - Ground | APAC | Mellyana, Walter Shui | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2025-12-29 | 2026-02-27
Business Only Initiative: KR Data-Entry Optimization |  | 189694 | Business Only Initiative | APAC - Ground | APAC | Hoon-Joong Lee | On Track | On Track | D: SL2 | Active | SL2 Finance Domain Lead Approval
Business Only Initiative: KR Vendor PUD & Shuttle Cost Savings |  | 190295 | Business Only Initiative | APAC - Ground | APAC | Sung-Jin Mike Kang | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: China 3 Major Gateways Re-bidding Project |  | 193012 | Business Only Initiative | APAC - Ground | APAC | Shen Ray Lu | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Fleet Right sizing | 354 | 6894 | Business Only Initiative | EU - Air | Europe | Zander F. Bekker | On Track | Submitted to L5. Proof of savings in attachment. | K: L5 | Completed | L5 | 2022-09-01 | 2023-01-30
Business Only Initiative: BHX site closure, transfer of ramp to EMA, courier | 32186 | 6898 | Business Only Initiative | EU - Air | Europe | Michael Wallis, Christopher Lund | Some Issues | Delayed until 9th May, contractor delays in installing equipment in EMA | K: L5 | Active | L5 Feedback Requested | 2023-06-01 | 2025-06-23
Business Only Initiative: Downgrade EDI from B737 to ATR and extend CGN B737 | 359 | 7005 | Business Only Initiative | EU - Air | Europe | Zander F. Bekker, Hessel Jensma, Sebastien Barbieux | On Track | Confidence in delivering value on time: High (already implemented on May 29th) Confidence in delivering the full value: High initiative submitted to L4 with L4 Test done and proof of Money Step attached | K: L5 | Completed | L5 | 2023-03-01 | 2023-05-30
Business Only Initiative: Optimize Aircraft MTOW and adjust capacity to dema | 367 | 7116 | Business Only Initiative | EU - Air | Europe | Federico Bey Marin, Carlos Carvajal | On Track | The analysis for required fleet is available one year ago. The operator response very slow. Master change quote has been requested end of April/May To Boeing. They normally have 90 days to reply. Operator refuses to check with alternate DOA at this moment as this would not improve timeline. Operator refuses to check other DOA for this MTOW changes until reponse from Boeing is received. Milestones timelines to be defined once FedEx has visibility on DOA paperwork timeline for completion. Money step milestone delayed to 3rd NOV 2024, forecast adjusted. Update by 31st OCT 2024: Monesystep milestone delayed to 15th Nov 2024, forecast adjusted. Rational: The operator needs clarificaction from authorities on how to manage the MTOW config changes for the fleet. 08 NOV 24: The operator delays the implementation to unknown date. This has been escalated in FedEx. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-10 | 2024-11-25
Business Only Initiative: Overfly HEL OB | 2489 | 7227 | Business Only Initiative | EU - Air | Europe | Zander F. Bekker | On Track | update 30/1/2023 LK: HEL and TKU are ready for today's launch of the new setup, there are standby trucks ready as backup solution in case of issues during first days of operation. On time departure is crucial in order to have the connectivity work. DH1 will be used in HEL for clearance. issues expected if too many DGs arrive after the 1st truck departure, if too many pallets arrive from the stations that are connecting among the last ones. Performance will be monitored during the first 2 weeks to determinate if there are any regular impacts. 17-7-2023: initiative submitted to L5 for approval. Attached Jan23 schedule showing HEL-CDG flights and Feb23 schedule showing no HEL-CDG flights; as well proof of ramp handling reduction as well as trucks cancellations and additional as per business case. | K: L5 | Completed | L5 | 2022-11-01 | 2023-01-30
Business w/ Tech Initiative: Optimum Flight Dispatch- Machine Learning | 82747 | 7338 | Business w/ Tech Initiative | EU - Air | Europe | Federico Bey Marin, Carlos Carvajal | On Track |  | K: L5 | Active | TEMP L5 - Enter L5 | 2024-05-13 | 2024-08-20
Business w/ Tech Initiative: Optimum Flight Dispatch: Data transfer to air oper | 95048 | 7449 | Business w/ Tech Initiative | EU - Air | Europe | Federico Bey Marin, Carlos Carvajal | On Track | 18/DEC/2024 IT to asses and prioritize the implementation of the data storage/transmision improvement. Architectural documentation to be provided. 29/SEP/2025 Dataworks Start Date----- 13/FEB/2025 Dataworks Finish Date | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: WS2 - Build ULD Move Model to enable CDG efficienc | 79837 | 7454 | Business w/ Tech Initiative | EU - Air | Europe | Carolina Assis De Souza, Christopher Kay, Heni Najjar, Ladislau-Emeric Kabat | Some Issues | 20260312: 20260312: Backlog for 1,5 months for prioritization. 20251113: Re-activating initiative based in Demand Shapping Guide: https://myfedex.sharepoint.com/sites/EPM/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FEPM%2FShared%20Documents%2FDRIVE%20Operating%20Model%20%28Op%20Model%29%2FGuides%2C%20Job%20Aids%2C%20%26%20FAQs%2FPDF%5FProcess%20Guide%2FProcess%20Guide%20%2D%20Demand%20Shaping%20Guidance%2Epdf&parent=%2Fsites%2FEPM%2FShared%20Documents%2FDRIVE%20Operating%20Model%20%28Op%20Model%29%2FGuides%2C%20Job%20Aids%2C%20%26%20FAQs%2FPDF%5FProcess%20Guide&p=true&ga=1 20250501: New drive process - merging enabler initiative into new one | E: L2 | Active | L2 | 2023-07-03 | 2026-05-29
Business Only Initiative: CDG EMPHASYS Project | 86209 | 7562 | Business Only Initiative | EU - Air | Europe | Karim El Beilk, Heni Najjar | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2024-03-04 | 2025-06-02
Business Only Initiative: Reduce the amount of empty ULD movements in Europe | 80433 | 7606 | Business Only Initiative | EU - Air | Europe | Marvic Guerra Araya, Megane Lecamus, Younes El Alaoui El Mdaghri | On Track | New IO appointed | K: L5 | Active | TEMP L5 - Enter L5 | 2025-03-19 | 2025-05-16
Business Only Initiative: Network incompatibility IMR caster deck | 82385 | 8128 | Business Only Initiative | EU - Air | Europe | Alberto Garavaglia, Ivan Feldzer, Donnia Westlake | On Track | Scope changed again. No real opportunities/financial benefits have been identified at this stage, agreement is to cancel the initiative | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Capacity/Route Review in West Atlantic | 364 | 8254 | Business Only Initiative | EU - Air | Europe | Brigitte Rulli | On Track | As of 5th Dec-22 1 aircraft from WA have been phase out leading to savings on Leasing costs - the total BH have changed so leading to additional BH (less savings on this initiative but more impact on leasing costs - fleet costs). As of April-May 2023 another a/c from WA should be phased out . Total costs savings expected for FY23 1426 K$ | K: L5 | Completed | L5 | 2022-05-02 | 2022-12-16
Business Only Initiative: Air hub optimization | 90469 | 8372 | Business Only Initiative | EU - Air | Europe | Sofie van Porten, Michael Nilles | On Track | Active | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-14 | 2026-02-20
Business Only Initiative: Fuel Savings - Cost Index, APU start, Single engin | 365 | 8395 | Business Only Initiative | EU - Air | Europe | Federico Bey Marin | On Track | Confidence in delivering value on time: 100% Confidence in delivering the full value: 100% Workstreams 1.Delay APU start departure and arrival (-10 STD +5 STA). ASLB Action (24 OCT 2022): Fuel Savings to be updated with APU running times- Operation running without issues. Only implemented in CDG for the moment. ASLB Action: Implement this fuel saving procedure on all stations. ASLB Action (21 NOV 2022): to provide an implementation date after peak. FedEx Action (05 DEC 2022): Sending request for changing APU start up time aiming implementation from first JAN next year and savings to be reviewed. Escalated: Note with feedback from meeting will be provided in the evening by today. APU start STD -10 at departure to be implemented by 23rd JAN 2023. APU at arrival procedures to be reviewed and aiming to still reduce more the APU utilization while not starting the APU at arrival. FedEx Action (12 JAN 2022) :to share the existing phraseology and procedures and ensuring ramp personnel readiness in order to agree an implementation date. SRA to be developed. Monitoring Phase. APU reliability monitored and no decrease shown. FedEx following up on handling/ground ops procedures enabling not starting the APU at arrival both in CDG and other local ops. ASL asks not to further implement APU reduction policies because this could impact the On Time Performance. FedEx indicates that appropriate on time performance is in its interest and asks, once greenlight for implementation (FedEx still under evaluation),to implement properly defined trial to measure the APU reliability and on time performance impact. After reviewing the results we could discuss the way forward. •ASLB Implemented •ASLF Implemented •ASLI Implemented 2.Single Engine Taxi –For taxi In (only NG for the moment) -I21 to I24 not allowed CDG. Potentially limitation as a precautionary would be for gates I81 to I84 at CDG (The airport hasn’t published any restriction for these gates other than for I81 and I82). Checking list of airports where single engine can be operated. ASLB Action (24 OCT 2022): Fuel Savings to be updated and providing FedEx with implementation date. To be implemented by JUL 2023. List with the airports where this can be implemented will be provided by week 53 2022. ASL B action ASL B Action (12 JAN 2022) List of airports to be shared. •ASLB Implemented •ASLF Implemented •ASLI Implemented 3.OFP Actual payload vs maximum – Aim for new year implementation after peak.- Outbound stations provide payload already in advance. Dispatch optimization could be implemented by today. Payload data availability is a problem for CDG and LGG airports. FedEx Action (07 NOV 2022): Check if CDG and LGG could share payload with operator 2-3 hours in advance to the flight. That would enable manual/optimizing the OFP/dispatches. If negative we have to go to automatic OFP with reference payloads (this reference payload to be reviewed periodically as per forecast). FedEx meets with IT to develop a tool for predicting potential onboard payload. Outbound stations dispatch already to be optimized by early January. Outstations to agree on sharing the payload 3 hours in advance to the flight. FedEx Action (05 DEC 2022): Select several stations for trial period early Jan. Outstation management approached for ensuring this data is shared 3 hours in advance. No reliable predictive payload 3 hours in advance by today. ASL request payload info to be sent to opsaslb@aslairlines.com, dispatchaslb@aslairlines.com- FedEx proposes POC and shares list of routes and payloads for dispatch and planning purposes. ASL to come back with an POC starting date by tomorrow. ASL will be ready to perform day by day customization in MAY. POC running well on all sectors. New method for determining reference payload. •ASLB Implemented •ASLF Implemented •ASLI Implemented 4.Cost Index -Aiming for Cost Index 10 to be reviewed in the future. ASLB Action (24 OCT 2022): Fuel Savings to be upd | K: L5 | Completed | L5 | 2022-07-15 | 2023-07-31
Business Only Initiative: Maintenance package tender (Int) | 3082 | 8983 | Business Only Initiative | EU - Air | Europe | Luigi Mastromonaco, Gergana Kacheva | On Track |  | K: L5 | Completed | L5 | 2022-01-03 | 2024-08-30
Business Only Initiative: Teesside (MME) Ramp Opening | 21124 | 9472 | Business Only Initiative | EU - Air | Europe | Christopher Lund, Michael Wallis | On Track | Import operations commenced on 07 January 2025 as per revised plan. MME ramp is now fully operational with 4 x nbound and 4 x outbound flights per week. 22 November 2024 - money step date further postponed to 07 January 2025 due to ongoing technical difficulties with the CCII ASN. ALthough MTP testing scheduled for 23 November, precautionary business decision not to implement MME phase 2 (imports) until after peak. 20 NOvember 2024 - money step date postponed to 03 December 24 due to technical issues associated with the CCII Anti-Smuggling Net (GTS issue). Training needed on how to set up a PPM project required for L3 – This is scheduled for next week. Now submitted for L2 approval. Once agreed I can then work on the L3 requirements as discussed with SA. PPM complete, now awaiting TCH approval before proceeding to L3. | K: L5 | Completed | L5 | 2023-10-09 | 2025-01-07
Business Only Initiative: RFP - Dejammer project | 31681 | 9520 | Business Only Initiative | EU - Air | Europe | Jessica Farny, Gergana Kacheva | On Track |  | K: L5 | Completed | L5 | 2023-02-01 | 2024-03-01
Business Only Initiative: E67 |  | 98263 | Business Only Initiative | EU - Air | Europe | Miguel Fernandes, Steve Johnson | On Track | On track | K: L5 | Active | TEMP L5 - Enter L5 | 2025-03-03 | 2025-06-02
Business Only Initiative: Air Ramp SLA I-EU Network |  | 160137 | Business Only Initiative | EU - Air | Europe | Rui Paula, Hessel Jensma | On Track | Due to project prioritization, the initiative was placed on hold | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: CGN Sort Window Adjustment |  | 165939 | Business Only Initiative | EU - Air | Europe | Sofie van Porten, Michael Nilles | On Track | 2025/10/24: working on LBC | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2025-12-05 | 2025-12-05
Business w/ Tech Initiative: PPE Consumption Reduction - Vending Machines |  | 166021 | Business w/ Tech Initiative | EU - Air | Europe | Marcos Arromba, Megane Lecamus | Some Issues | 2026/03/18 - Pushing again to have Architect assigned to Process flow, Data diagram, and Network diagram. The FIRST was moved to "production" on 20/01/2026. 2026/03/11 - Clarifying about LE scope. 2026/03/03 - Feedback from InfoSec to Gesmatik - "We need IT mapping for the Process flow, Data diagram, and Network diagram". Confirmed that we can set up a POC with badge + no FCF connection and later updgrade the solution. 2026/02/25 - Reviewing strategy for current approach with Pod Coach (Carolina) + PMO IT (Ram). Setting a parallel LE as POC for CDG without operators integration - login with badge - and no FCF connection. Again, on a discussion if it's a BO, anf after that we need the FIRST approval for this to move after gets prioritized in L2. 2026/02/18 - After call with Dexxis, InfoSec checked the software puts at risk our network. Request to have IT support to have viable soluton. Requesting feedback 2026/02/11 - Clarifying on a concern raised by InfoSec about TeamViewer compliance, arranging a call with the vendor - Dexxis. 2026/02/06 - Changed the Annualized Value Range as advised by ESPM through a PDSM ticket. Requested for another vendor software analysis - Gesmatik - from InfoSec. 2026/01/26 - Limited resources to start working on the initiative from EPM. "Enterprise Services Portfolio cannot support the execution of this initiative at this time, we will need to place it on hold until resources become available. In the meantime, please work with your ESPM lead to increase the Enterprise Ranking through Booster." | E: L2 | Active | L2 | 2025-09-01 | 2026-02-27
Business Only Initiative: Europe Feeder Ramp Policies and Procedures |  | 166024 | Business Only Initiative | EU - Air | Europe | Zebensui Montenegro Rodriguez, Marcos Arromba | On Track | 11/04 - Three aeronautical engineers have been approved to implement this initiative. Hiring and onboarding process will start. 12/01 Three aeronautical engineers positions are posted in external and internal HR websites. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-12-15 | 2027-06-30
Business Only Initiative: Optimize Aircraft Handline Set Up & Quality in EU |  | 189684 | Business Only Initiative | EU - Air | Europe | Dita Ancevska | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Enable all CDOs for ASR/DSR on shipper demand |  | 130402 | Business w/ Tech Initiative | EU - B2C | Europe | Akanksha Padhi, Helen O'Doherty | On Track | Oct 3 : Cancelling due to feasibility issues. Aug 5 : KPIs to be tracked in 130405. Financial plan completed. June 18th 2025 In L1, business case being worked on. | E: L2 | Cancelled | Portfolio Greenlight
Business w/ Tech Initiative: Merchant Delivery Management |  | 130405 | Business w/ Tech Initiative | EU - B2C | Europe | Akanksha Padhi, Helen O'Doherty | On Track | Apr 13, 2026 Work yet to start, latest plan below Development & Testing complete Start 22-Apr-26 End 30-Jun-26 Staging Start 1-Jul-26 End 8-Jul-26 Go/No-Go QA Validation Start 9-Jul-26 End 17-Jul-26 PO Validation Start 17-Jul-26 End 24-Jul-26 MTP Readiness Start 24-Jul-26 End 30-Jul-26 UAT TBD Go Live TBD Submitted a D&T Finance request for an updated Forecasr. Feb 17, 2026 Testing in progress, dev completion expected late March. Testing milestone moved to March. No impact on delivery date or money step. June 18th 2025 In L1, business case being worked on. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-03 | 2026-11-30
Business w/ Tech Initiative: EU dropoff dev & rollout + eligibility check |  | 130408 | Business w/ Tech Initiative | EU - B2C | Europe | Farah Ahmed, Debora Magalhaes, Wilhelmina Zuckerman | On Track | 01/27/2026: CCH greenlight received. CPEL completed; waiting for PRT prioritization | E: L2 | Active | L2 Feedback Requested | 2026-01-01 | 2026-03-31
Business w/ Tech Initiative: EU retail indirect injection drop off |  | 132336 | Business w/ Tech Initiative | EU - B2C | Europe | Farah Ahmed, Debora Magalhaes, Wilhelmina Zuckerman | On Track | On hold due to value vs t-shirt sizing. Next steps tbd | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: WS11 - I-EU B2C: Global Direct-to-Retail | 69824 | 8174 | Business w/ Tech Initiative | EU - B2C | Europe | Wilhelmina Zuckerman, Debora Magalhaes, Stan Aalbers, William Bouwman, Akanksha Padhi, Paul Wicks, Rocio Vargas, Guillaume Blondel, Farah Ahmed, Harald Beets | On Track | 14 April 2026: (updates in bold) • FXRS: Two defects opened. FXRS team working with UVSDK team. No ETA yet. ○ Defect 306003: Expected Error messages not getting returned for HAL Shipments. ○ Defect 308056: HAL shipment failing with error "Hold at Location country must match Recipient country." even HAL country same as recipient country. • GSM: Testing completed. Release to take place by June 2026. • CAFE: All released planned to be completed by end of April. • DHAL file has been validated; deployed to PROD. • Country deployment defect as LU was not showing HAL available. Under investigation; awaiting clarification from LSSI team. * Country rollout underway for FR; 3 stations active; **ES rollout underway**; NL under discussion 7 April 2026: (updates in bold) • FXRS: Two defects opened. FXRS team working with UVSDK team. No ETA yet. ○ Defect 306003: Expected Error messages not getting returned for HAL Shipments. ○ Defect 308056: HAL shipment failing with error "Hold at Location country must match Recipient country." even HAL country same as recipient country. • GSM: Testing completed. Release to take place by June 2026. • CAFE: All released planned to be completed by end of April. • DHAL file has been validated; deployed to PROD. • Country deployment defect as LU was not showing HAL available. Under investigation; awaiting clarification from LSSI team. * **Country rollout underway for FR; 3 stations active. ES planned for completion mid-May; NL under discussion** 31 March 2026: (updates in bold) • FXRS: Two defects opened. FXRS team working with UVSDK team. No ETA yet. ○ Defect 306003: Expected Error messages not getting returned for HAL Shipments. ○ Defect 308056: HAL shipment failing with error "Hold at Location country must match Recipient country." even HAL country same as recipient country. • GSM: Testing completed. Release to take place by June 2026. • CAFE: All released planned to be completed by end of April. • DHAL file has been validated; **deployed to PROD**. • Country deployment defect as LU was not showing HAL available. Under investigation; awaiting clarification from LSSI team. Country deployment plans under discussion with the country leads from FR, NL, ES. 24 March 2026: (updates in bold) • FXRS: Two defects opened. FXRS team working with UVSDK team. No ETA yet. ○ Defect 306003: Expected Error messages not getting returned for HAL Shipments. ○ Defect 308056: HAL shipment failing with error "Hold at Location country must match Recipient country." even HAL country same as recipient country. • GSM: Testing completed. **Release to take place by June 2026.** • CAFE: All released planned to be completed by end of April. • **DHAL file has been validated. Release on March 28th** • Country deployment defect as LU was not showing HAL available. Under investigation; awaiting clarification from LSSI team. Country deployment plans under discussion with the country leads from FR, NL, ES. 17 March 2026: • FXRS: Two defects opened. FXRS team working with UVSDK team. No ETA yet. ○ Defect 306003: Expected Error messages not getting returned for HAL Shipments. ○ Defect 308056: HAL shipment failing with error "Hold at Location country must match Recipient country." even HAL country same as recipient country. • GSM: Testing completed. Waiting for release. • CAFE: CAFE4003 prod release is planned this week (4003). All released planned to be completed by end of April. • DHAL file has been validated. Waiting for confirmation of release date. • Country deployment defect as LU was not showing HAL available. Under investigation; awaiting clarification from LSSI team. Country deployment plans under discussion with the country leads from FR, NL, ES. 10 March 2026: * Missed requirement identified for DHAL. Developement completed and pending validation from the team. * Some defects open for CAFÉ & GSM. For CAFE. Team is working on it to gte it fixed. Testing is also taking place. Re | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2027-12-31
Business Only Initiative: I-EU B2C: COMMERCIAL |  | 98689 | Business Only Initiative | EU - B2C | Europe | Guillaume Blondel, William Bouwman | On Track | Moved from the Commercial POD into the B2C POD. All milestones completed and reached maturity. Actuals tracking principles different in commercial POD than B2C POD so cancellation would avoid possible conflicts with new developments from the B2C POD | K: L5 | Cancelled | L5 | 2024-05-01 | 2025-05-30
Business w/ Tech Initiative: EU Retail Location Management Transformation |  | 132401 | Business w/ Tech Initiative | EU - B2C | Europe | Wilhelmina Zuckerman, Harald Beets, Debora Magalhaes, Farah Ahmed | On Track | On track | E: L2 | Active | L2 - Enter Value Prop
Business w/ Tech Initiative: RTH development and rollout in Europe |  | 143329 | Business w/ Tech Initiative | EU - B2C | Europe | Harald Beets, Farah Ahmed, Debora Magalhaes, Wilhelmina Zuckerman | On Track | Partner assessment in countries in scope is in progress, preparing integration details, details and timelines tbd | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Development & rollout Direct to Retail - Lockers |  | 152790 | Business w/ Tech Initiative | EU - B2C | Europe | Farah Ahmed, Debora Magalhaes, Harald Beets, Wilhelmina Zuckerman | On Track | Going through steps to submit to L2 | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Retail & returns reporting & monitoring tool |  | 152793 | Business w/ Tech Initiative | EU - B2C | Europe | Eiske Jensma, Debora Magalhaes, Farah Ahmed, Harald Beets, Stan Aalbers, Wilhelmina Zuckerman | On Track | 15/12: Waiting for dependencies to move forward into L3. On track and working to submit to L2 | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: GPS Proof of Delivery for EU Inbound Shipments |  | 143243 | Business w/ Tech Initiative | EU - B2C | Europe | Akanksha Padhi, Helen O'Doherty | On Track | March 16 2026 : Launch for all countries (minus NL/DE/DK) planned for 3rd week of May. Remaining countries will be rolled out in August post ATLAS related work is complete in late July. Feb 17, 2026 : new request for data flow of EU GPS captured on LEO to be stopped from flowing into ATLAS. Portfolios impacted - D&AI + SCO. Aligned with both, no, cost/value impact. Ability to statement to be added for SCO once finalized. No impact on delivery or money step. past : Awaiting LR approval, Privacy notice. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2034-06-30
Business w/ Tech Initiative: Residential Shipment Identification Enablement |  | 165761 | Business w/ Tech Initiative | EU - B2C | Europe | Claudia Arntz, Pedro Constantino | On Track | 6/2/2026 Claudia Arntz: LBC agreed with Finance and ready to submit to L2 26/2/2026 Claudai Arntz: Initiative has moved into L2, but at the moment it is not ranking high on the backlog based on the current prioritization. However this is required to support the InPost work, which makes its timing more critical than the current ranking reflects. Sponsor requested to tag this as a strategic priority and raise it with the EPSM team. | E: L2 | Active | L2 & CCH
Business Only Initiative: FICP- Intra-EU Transit Improvement GB,NL->DE |  | 166566 | Business Only Initiative | EU - B2C | Europe | Dipankar Debroy, Jeroen Lamers | On Track | 11/18- New IO added | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Map View on the Morning of Delivery |  | 180565 | Business w/ Tech Initiative | EU - B2C | Europe | Nikola da Costa, Akanksha Padhi | On Track | **12 of January 2026** - FIRST WIP - LR WIP **19 of January 2026** - FIRST submitted - LR Submitted - Business case and Ability to Statement WIP - DPIA data privacy impact assessment PRA/PIQ WIP 5 of march 2026 QA check with Transformation specialist, after this ok good to submit to L2. 30. of April 2026 - Approved, moved to L2 27 of March 2026 - Call with Commercial Architecs, L2 Triange - **Work Council: Countries approved**: (Austria, Switzerlang, Czech Republic, Denmark, Estonia, Spain, Hungary, Ireland, Lithuania, Luxembourd, Latvia, Portugal, Sweden, Slovakia, Slovenia, Turkey, United Kingdom) Countries WIP ( Belgium, Germany Netherlands) | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: EU Retail - Indirect Injection - HAL |  | 189937 | Business w/ Tech Initiative | EU - B2C | Europe | Farah Ahmed | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Implement Integrated Facilities Management (APEX P | 1317 | 7239 | Business Only Initiative | EU - Business Support | Europe | Guido Bollekens, Arjan van der Nat | On Track | 11072024 huge leakage due to variable costs. We are investigating what is happening and how to mitigate going forward 06052024 Due to resources constraints we have leakage of value. The resources where incorporated in the business case but BCE approval has not been approved in numerous occasions. For one we lack the resources to support on service quality but also to protect us from value leakage. Status moved to leadership attention BCE's approved by Vinay and uploaded to sharepoint 30042024 Due to resources constraints we have leakage of value. The resources where incorporated in the business case but BCE approval has not been approved in numerous occasions. For one we lack the resources to support on service quality but also to protect us from value leakage. Status moved to leadership attention 29042024 Money step evidence uploaded as attachment #9 and #10 Ready for L4 after FPA questionnaire upload 22042024 Ready for L4 15042024 Advised by POD team to cancel milestone 9109 as it is a duplication of 9108 (money step) and to set status of 9108 to complete since scope is fully implemented Initiative is ready to move to L4 once validated by FP&A 27-03-2024 Scope fully implemented 12-02 Increased focus on performance issues in France. Get well plan established as well weekly alignment calls with OPS senior managers and monthly alignment on MD level to track improvement. 23012024 Poland cleaning will need to be descoped. We currently use a vendor that has the status of sheltered workplace and entitles us of receiving a tax reduction of around 450K€ yearly. If we would transfer this scope towards Apleona we would loose this benefit. This was not known at the time the BC was created, and this impact or benefit was also not calculated or included into the BC. Impact of implementing IFM cleaning would have been 574K€, deducting the tax reduction leaves a negative impact of 124k€ We currently feel comfortable to hit our savings target and would not ask for adjustment of budgetted impact 16012024 Change milestone #9801 because of delay in Poland. Money step should the mast step. approved by Simon and Denise on mail Potential issue in Poland with Lanua. FedEx receives tax reduction because of the incumbent supplier for cleaning is a sheltered work place. We are investigating to mitigate 01122023 Late milestones due to delay of go live Poland 14112023 Late milestone mitigated no delay in implementation. Overreporting due to delayed invoicing variable spend due to lack of resources 09102023 Milestone #9105 still late (Provider is late with establishing their Baltic branches) but feedback from provider is we will still be able to sign work orders before ultimate deadline. Extra support is working on controlling the variable spend this week 27092023 Milestone #9105 late but mitigation in place to sign work orders before end of October. Currently no delay foreseen in hitting plan. Some issues status explanation, - control on variable spend and reporting: mitigation is to hire extra support externally until internal open position is filled. Additional costs fit within budget of business case, no negative impact on wave impacts - operational issues under control in UK: mitigation action to replace account director to have a stronger leadership and improved command and control - Open positions not et filled in the team due to lack of suitable candidates 07092023 Confidence in delivering value in time (high) Confidence in delivering full value (Medium) 04/09/2023: After intensive readiness deep dives we have found that due to high workload and limited resources focusing on wave 1 stabilization we are not ready for go live Romania and Poland at November 1st. Romania needs to be postponed 1 month to December 1st and Poland March 1st 2024. December 1st is not possible due to the bigger portfolio in Poland, peak and holiday season brings us to March 1st. Impact will be reflected in the forecast. Milestone #9105 is delayed due to | K: L5 | Completed | L5 | 2022-07-01 | 2024-09-12
Business Only Initiative: Phase 1 - Real Estate Office Footprint | 1309 | 7864 | Business Only Initiative | EU - Business Support | Europe | Maaike Thoben-Dijkgraaf, Sonia Colleoni | On Track | **Update 24-12-2024: all evidence per milestone delivered to Finance. 3 months of delivering value, hence moving to L5. ** Update 30-09-2024: all evidence per milestone delivered to Finance (Chris/Michael). Moving to L4 again. Update 24-09-2024: Money step realized by delivery Frankfurt / Gravenbruch and Lyon 5th floor. Update 07-09-2023: Confidence in delivering value on time = High Confidence in delivering full value = Medium (because of the amount of projects involved in this Initiative) FedEx has approximately 85 office facilities in 32 European countries. The main office locations per country larger than 1,500 sqm have been reviewed. Per office facility, the number of desks, number of FTE allocated to that facility (current and projected) and vacancy are (to be) verified. Pending LR consultation outcome on implementation of the Flexible Working policy, 13 office locations have been identified as priorities that will be suitable for either physical transformation to accommodate collaborative workspace and/or reduction of the office facilities footprint and/or (re)negotiating a better lease. Based on WorkDay data and based on the employees who are eligible for hybrid or remote work, there is a significant potential to reduce space. This will require capital investments to accommodate relocation an/or changes to the space. | K: L5 | Completed | L5 | 2022-01-03 | 2024-10-01
Business Only Initiative: Company Cars EU | 2165 | 8904 | Business Only Initiative | EU - Business Support | Europe | Paul Barker, Laura Bullion | On Track | New proposed way of obtaining the savinjgs via a TCO model which includes lower vehicle costs, mileage tracking to reduce cars in mileage entitlement pool, reducing mileage leases to 120,000 km over 60 months rather than 150,000 km - saving lease costs & through mileage tracking of drivers, ensure leases are reduced if drivers do not hit mileage leased commitment | K: L5 | Completed | L5 | 2022-10-20 | 2023-03-28
Business Only Initiative: Consolidate operational small equipment (Int) | 3020 | 8966 | Business Only Initiative | EU - Business Support | Europe | Yasmine Wenger, Jessica Farny | On Track |  | K: L5 | Completed | L5 | 2022-09-01 | 2024-10-01
Business Only Initiative: Implement customer functionality to book freight p | 4761 | 9038 | Business Only Initiative | EU - Business Support | Europe | Vincent Lafeber, Rocio Vargas | On Track | We have now 3 months of consecutive results surpassing our ambition. Evidence for L5 gate attaced. We can move to L5 now. *Confidence delivering value on time: HIGH, Digital development in progress. Concerns about customer experience when automatically dealing with local anomalies *Confidence delivering full value : HIGH IT sizing conversations no longer needed, no further IT development requirement after successful production tests for EU markets. could move up the time table for QP enablement. FedEx.com/MAGIC will deliver in 2 phases August Phase 1 requesting a pick up when creating a freight shipment and December Phase 2 Stand alone freight pick up experience. Operational alignment on standard pick up process presented to Dispatch teams in all EU markets - blue print definition approved by Brian DeCair and now enabled soft launch (on QP). Moved up the QP freight pick up timeline as we can go faster now with soft launch. Split the benefit & KPIs as per June 2023 to differentiate between Sales (65%) and CS (35%) impact as per finance request. | K: L5 | Completed | L5 | 2022-11-17 | 2024-05-31
Business w/ Tech Initiative: EU Datamart Migration and associated Data products | 87876 | 6991 | Business w/ Tech Initiative | EU - Commercial | Europe | Sofia Cloe, Dipankar Debroy, Christopher Boden, Mariana Marques | On Track | On track, no late milestones | G: L3 | Active | TEMP L3 - Enter L3 | 2024-09-27 | 2028-07-10
Business Only Initiative: [ERN growth] - Quote Platform REF | 51224 | 7196 | Business Only Initiative | EU - Commercial | Europe | Rocio Vargas, Marion Meester, Perrine Jourde, Paul Wicks, Burcu Sezer, Nicolas Ferrer | On Track | Money step completed. Moving to L4. | I: L4 | Completed | L4 | 2023-12-01 | 2025-05-29
Business w/ Tech Initiative: WS #11 Enablement of IED on Intra-European single | 64586 | 7380 | Business w/ Tech Initiative | EU - Commercial | Europe | Beatriz Figueiredo, Sonika Tiwari, Pip Fanning, Lizzy Houska, Nicholas Forward, Paul Wicks, Rocio Vargas | Some Issues | Status as of 13th May 25: Currently tracking Medium confidence to achieve 1st Oct money step Key issues: * No test lead assigned - require resolution. Has already been escalated - expect confirmation by 16th May * Issues with test accounts in L3 - not enabled for CPP. Following up with IT and Pricing Business side progresses on track - need to secure GTM resources for communication planning **June 17th 2025 - Medium Confidence** **IT Update**: * Development pending in Clearance ART and SORT is facing some L3 testing issues * We cannot move confidence to high until we have E2E testing dates locked it * Solution Architect documents are up to date * Test lead assigned **Business Update:** * Routing setup in progress. * Minor risk has been highlighted for Pricing are being looked at and are on track. **Oct 2nd 2025 - Medium Confidence** IT * MTP for SABRE under discussion, ETA 15th Oct Business * JOMA needs new prices before they can sign, API in progress * Future Electronics has not responded this week Pricing still not signed. API discussion underway **Nov 13th 2025 -** IT side: •MTP for Non-SPOC happened on 27th Oct. Business side: Future Electronics will be ready with packs on belt in last week of Nov. CT is working with them on API config. JOMA SPORT - Do not want to start before first week of Jan. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-23 | 2026-06-01
Business w/ Tech Initiative: WS #11 Create SPOC location in NL for Intra-EU Eco | 67260 | 7411 | Business w/ Tech Initiative | EU - Commercial | Europe | Beatriz Figueiredo, Sonika Tiwari, Pip Fanning, Nicholas Forward, Paul Wicks | Some Issues | **Status as of 13th May 25:** Currently tracking Medium confidence to achieve 1st Oct money step Key issues: * No test lead assigned - require resolution. Has already been escalated - expect confirmation by 16th May * Issues with test accounts in L3 - not enabled for CPP. Following up with IT and Pricing Business side progresses on track - need to secure GTM resources for communication planning **June 17th 2025 - Medium Confidence** **IT Update**: * Development pending in Clearance ART and SORT is facing some L3 testing issues * We cannot move confidence to high until we have E2E testing dates locked it * Solution Architect documents are up to date * Test lead assigned **Business Update:** * Routing setup in progress. * Minor risk has been highlighted for Pricing are being looked at and are on track. **Oct 2nd 2025 - Medium Confidence** IT * FAPI tests are in progress. * MTP for SABRE under discussion, ETA 15th Oct Business: * Waiting for MOO to sign the pricing contract * Future Sound signed it already, API call this week. * Urban Bar will start post peak **Nov 13th 2025 -** IT side: •MTP for SPOC (System - Gemini) is scheduled for Nov 24th * Provided E2E is completed by 18th Nov. (Requested MD approval for this push back) •E2E Testing is blocked. * ROCS fix was deployed, IT will test again for final check * Gemini issue is being tested again. Fix already works. Business side: Future Sound is working with our CT team on API config. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-23 | 2026-05-01
Business Only Initiative: [ERN Growth] - Intra EU Economy Parcel Umbrella Ca | 71130 | 7436 | Business Only Initiative | EU - Commercial | Europe | Hanh Phan, Burcu Sezer, Henrik Heizmann, Paul Wicks, Rocio Vargas, Sigrid Smits, Francisca Ferreira | On Track | move to L5 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-19 | 2024-06-28
Business w/ Tech Initiative: I/EU Increase Revenue by Improving Onboarding Flow | 69604 | 7451 | Business w/ Tech Initiative | EU - Commercial | Europe | Sergio Borges, Rainer Mielhahn, Joe Goode | On Track | Ressourcing decision made and ensured | G: L3 | On Hold | TEMP L3 - Enter L3 | 2026-12-28 | 2026-12-28
Business Only Initiative: Improve FICP ES-US Transit Time from 4 to 3 days c | 70247 | 7475 | Business Only Initiative | EU - Commercial | Europe | Burcu Sezer, Rocio Vargas, Pascal van der Giessen, Dipankar Debroy | Attention Needed | 4th June 2025 Ready to proceed to L4 ---------- Earlier staus: Email sent out to coach and PMO starting from 24th Jan and awaiting next steps / how to proceed: Hi Rocio and Rudi, Following our discussion earlier this week on the FICP ES-US 3-day TT Commit Initiative (#70247) we want to propose the following next steps and require your input: The L4 Money Step for March may need to be postponed as the scope of the initiative has now changed to ES-US 3-day TT improvement for limited lanes - selected location ID's and via Original Banded Commit. We could keep the money step for March ’25 but change the scope of the initiative to: FICP Original Banded Commit TT ES-US, 3-day for 50% volumes and open scope for expansion in future with P2P CLH. First phase is currently being implemented: 2 Location ID's - MADA & ROZA - will be launched 3rd Feb and will account for ~50% of the volume. Phase 2 - further expansion of Location ID’s will need to be confirmed with our US colleagues. In the last communications it was mentioned that a next expansion of location ID’s may be possible in May. Phase 2 expansion is expected to add cost and may fly on PT. We need to be sure that we are doing profitable business rather than adding more costs just to bring down TT. There is concern on PT availability and it is more rational to keep 100% CLH (50% 3-day, 50% 4-day), but move to PtP CLH for lower cost to serve. Regarding the base case scenario, we could consider changing some assumptions. Below is a high-level assumption and may change as we progress with the 3-day catchment expansion: - Our base should be when ES-US was via CDG on PT with 4-day TT. - Phase 1 is then moving ES-US on CLH via PHL-MEM route with 4-day TT. This should be considered 100% non PtP volume. - A subset to this scenario, a partial money step is to give ROZA & MADA 3-day TT, approx. 50% of the FICP volumes – going live in Feb’25 - A phase 2 or PFS will be, 1) 80% volume with 3-day TT (50% on CLH, 30% on PT) 2) 20% volume with 4-day TT (all on CLH as they cannot meet cut-offs for 3-day TT) In terms of financial impact, we will need to calculate profitability before adding any cost which will automatically translate to a volume target for Sales. Once we finalized the scope, we must re-forecast the financial impact. The following info will be required: Latest forecast for incremental volume for FY25, FY26, FY27 by month - YPP (incl. & excl. DFS), AWPP (lbs), Pack per shipment - Operational set-up and corresponding volume @Rocio and @Rudi we will require confirmation and advice on what actions to take next also in Planview. For now, it is good to realize that we are launching 2 Location ID’s on 3rd Feb accounting for ~50% volume. ---------- Earlier status: Original timeline was to change the Country-to-Country Transit Time from 4 to 3 days for the FICP product in March’25, copying the already active NL/BE/DE/FR/IT/GB transit approach into US. With ongoing P&E end-to-end analysis, we were notified that in current situation we will not be able to quote the full origin of Spain for a 3-day, though only a selection of Location ID’s. As a solution, we have been advised to use Origin Banded Commit initiative for FICP which was moved to production in April’24. Banded Commit enables international products to quote different transit times based upon O/D catchment areas. This solution would make it possible to subtract a day at origin Location ID level, solving our issue. Unless EU P&E manages to set up a full country 3-day connection into US, we are dependent on the Origin Banded Commit solution before we can move into the Money Step. P&E to provide full overview which Location ID’s will get a 3-day transit vs current 4-day transit into US. Green light received to include Madrid area Location ID’s for the FICP Banded Commit ES-US POC targeting Feb’25: Origin: ES MADA ROZA Destination: All of US | G: L3 | Completed | L3 Data Migration - TEMP | 2024-07-29 | 2025-05-26
Business Only Initiative: Creating a customer focused SAM segment | 75487 | 7623 | Business Only Initiative | EU - Commercial | Europe | Peter Pellegrini, Burcu Sezer, Paul Wicks, Rocio Vargas | Attention Needed | The research phase is complete, and since we’re no longer tracking KPIs into FY26 or capturing financial value, continuing further doesn’t appear necessary. While the alternative would be to move to L4 and then L5, that would require completing the Money Step (GTS Rollout & Go-live), which is currently on hold. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-01-19 | 2025-02-21
Business Only Initiative: Enabling IC [Trans-Atlantic] Express Freight and E | 78041 | 7639 | Business Only Initiative | EU - Commercial | Europe | Adam Wisniowski, Burcu Sezer, Rocio Vargas, Nicolas Ferrer, Paul Wicks, Santosh Nair | On Track | IPF transit time improvements on plan. Some risk linked to the revenue goal driven by external factors. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-06 | 2026-05-04
Business w/ Tech Initiative: WS11: Grow I-EU ERN - New rate card initiative | 84178 | 7717 | Business w/ Tech Initiative | EU - Commercial | Europe | Bhavesh Thacker, Robert Anghel, Paul Wicks, Rocio Vargas | On Track | w.b. 05/08/24: Working on the proposal & recommendation for a workshop which will fully scope out and plan the solution needed to create and implement the new zoning set up and list rates. Considering key pre-requisites for: stakeholders, data, organisation, resource & support to ensure the workshop is as productive as possible. w.b. 02/09/24: Workshop delivered successfully, key outputs, •Scope agreed: Acquisition & Incremental business, 10 initial markets & field, EN, EG/ER customer focus. •Zoning: New zoning standards & mapping agreed, we will require circa 35 zones to achieve the desired granularity •Rates: New list rate logic & methodology agreed and list rates created for 4 markets. w.b. 09/09/24: Sales feedback sessions held with freight sales, IT & DE field sales teams - all are in support of this initiative and can see how it will add value. First call held with Memphis team to discuss implementation options, initial feedback is that our core and additional requirements can largely be met. Memphis team to feedback on timelines and follow up questions. w.b. 30/10/24: Approach agreed with Memphis team, we will target the Nov MTP and use the dynamic geography functionality, this will allow the fastest speed to market and earliest realisation of benefits. Next steps: •Confirm and set up postcode splits for UK/DE/FR/IT in eRD •Finalise strategy for special programs •Set up special programs •Engage sales playbook process for G2S w.b. 24/02/25: Feb CSR resolved the missing BE imports defect but the defect on minimums is still outstanding •Need to understand whether the minimums defect will be resolved in the Mar CSR, this is not confirmed •resource needed to configure and deploy the special programs is still outstanding, request has gone to the COE •Analysis of costs and price creation due to be complete this week and is on track w.b. 10/03/25: •Minimums defect: fix has been deployed in L5 and now ePRS Business team is testing it •Resource for configure & deploy of special programs is still outstanding: COE is now engaged, inital call had, and they are investigating what support they can offer. Also call booked with 3 internal stakeholders to get an understanding of what re-prioritisation is need to try deliver this work in house, or what training can be offered to COE to help them deliver this requirement quickly. •Price positioning analysis and strategy creation complete for 9 out of the 10 markets, PL is remaining and due to be complete by 12th March. w.b. 17/03/25 •Mar CSR release due 21st March, confirmation received it will resolve the open defect on minimums. •Resource for configure and deploy: oAga and EU prices will load the 'shell' special programs for all markets and download the loading templates after March CSR, oJohn and team will populate the loading templates with discounts per market oResource for testing end to end and UAT is still outstanding, this will need to be supported by ePRS SME's most likely the current configure & deploy team or central ePRS. w.b. 24/03/25: •Minimums defect has now been resolved with Mar CSR release - fully tested and working correctly •Resource for configure and deploy: oAga & EU Prices teams have started work to create the 'shells' for the bands for all 10 markets. - this work is due to be complete by 28 Mar oAs market 'shells' become ready, the download templates will be sent to John T's team for discount population, John's team will populate the discounts and re-upload the templates into ePRS and then along with Aga test the bands are working as expected. The timeframe for this is unknow at the moment until 1 upload is complete, this is process for all 10 markets is expected to take 2-4 weeks. oGiven the delay due to the unforeseen ePRS defect on minimums and the re-shuffling of resource to load and test the bands the current forecast for pricing to go live is end of April which first revenue realisation in June, forecast is updated to reflect this | I: L4 | Active | L4 | 2024-08-05 | 2026-01-26
Business Only Initiative: EU-APAC EB Deferred Initiative | 84176 | 7720 | Business Only Initiative | EU - Commercial | Europe | Armaan Ghai, Nicolas Ferrer | On Track | New initiatves on FD launched, as a result no CLH P2P action required. | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: [ERN Growth] I-EU - Optimize pricing strategy & ta | 51230 | 7809 | Business Only Initiative | EU - Commercial | Europe | Hanh Phan, Sergio D'Angelo | On Track | July update: since March, the win ratio has increased in a stable (parcels ~ 26% and freight ~ 30%). KPIs were updated for May-July (data status 27th July) We have moved several milestones. Now await for Jan isell data to start to measure all programs in terms of activities on country view and how they support RE as well mapping with win ratio data. We are on track in milestones, ECH template today got updated with MKT ops support for GTM in some activities related to online marketing segment, the support has been agreed and secured by stakeholders, so no change/review required. | I: L4 | Completed | L4 | 2023-08-01 | 2024-11-19
Business Only Initiative: [ERN growth] I-EU - Increase Parcel revenue by 10% | 51238 | 8235 | Business Only Initiative | EU - Commercial | Europe | Sigrid Smits, Muhammed Abubakar Anwar, Zvonimir Trosic | On Track | . | I: L4 | Completed | L4 | 2024-02-05 | 2024-06-28
Business Only Initiative: [ERN Growth] I-EU - Accelerate customer onboarding | 51233 | 8300 | Business Only Initiative | EU - Commercial | Europe | Dimitrios Dimitriadis | On Track | The Project Management Tool and Dedicated Contact Details of LOC were already implemented, and it is now only a matter of monitoring the progress on a monthly basis. | I: L4 | Completed | L4 | 2023-10-26 | 2024-10-04
Business Only Initiative: [ERN Growth] Push freight-only sales to new and ex | 51216 | 8385 | Business Only Initiative | EU - Commercial | Europe | Vanessa Brooks | On Track | Lead in EU Feb focussed on FedEx Deferred Freight and how we bring this education to sales. Review service after previous feedback from the listening circle on freight post end of sort windows. New dashboard created in iSell for portfolios to view service across customers proactively. Calendar year 2025 Smarter Sprints scheduled Feb 13th / April 9th / June 17th / Oct 16th. Deep dive on country mix of parcels and freight to see how we can target education by country. Working with Phil Wildsmith to incorporate mapping of education and timelines based on ORG changes and segments / leadership to support changes. Sprint last 13th Feb generated 599 opportunities 43m revenue in pipeline, April Sprint generated 424 opportunities 24.8m. Work in flight to support Freight dedicated team also through the below activities:- * Build cross-product education for both groups. P&S to include Air and Ocean * Include: Pricing, ePRS, iSell (may still be on two different versions for the time being) * Series of webinars, maybe 1 a week for May into June (small bitesize) * There needs to be some Leadership Education, 3 or 4 PAX (Coach2Grow, iCoach) * There will be some changes to some EG/ER accounts, may be coming into direct alignment with Phils team * Include Supply Chain Mapping & Questions * Need to include Incoterms (look at Ocean & Air) * Get targeted Freight Lanes from Ops (White Tail) – Where to target (Routing, plane sizes for freight dims) * Still some work to clarify around Comp & Bens | I: L4 | Completed | L4 | 2023-12-20 | 2024-06-28
Business Only Initiative: EU - increase QP Revenue through commercial push a | 68907 | 9001 | Business Only Initiative | EU - Commercial | Europe | Sigrid Smits, Rocio Vargas, Paul Wicks, Burcu Sezer, Jefnie Merdyanto | On Track | * Promoting Intra-Europe Freight : Growing with brokers/LSPs was discussed with pricing. They won't go beyond parcel by road tier 1 rates for LSPs. Quote platform already live - generate incremental REF revenue via internal & external promotion campaigns. Set up in place, Paid Search campaigns to be launched in June. | G: L3 | Completed | L3 Data Migration - TEMP | 2024-04-15 | 2025-10-31
Business Only Initiative: Grow EU to AU/NZ | 18354 | 9406 | Business Only Initiative | EU - Commercial | Europe | Burcu Sezer, Rocio Vargas, Alexis Bruylants, Nicolas Ferrer, Paul Wicks | On Track | Initiative submitted to L2. Pending approval | K: L5 | Active | TEMP L5 - Enter L5 | 2023-12-01 | 2024-06-28
Business Only Initiative: Demand surcharge (international) |  | 87137 | Business Only Initiative | EU - Commercial | Europe | Adam Wisniowski, Nicolas Ferrer, Paul Wicks, Rocio Vargas, Robert Anghel | On Track | Move to L5. Currently lower value than expected experienced due to lower capture ratio, forecasted gap vs target. FY26 milestones cancelled - to be moved as new initiative. Ready to move to L4. | K: L5 | Completed | L5 | 2024-05-06 | 2025-09-12
Business Only Initiative: Disbursement Fee minimum charge increase |  | 93869 | Business Only Initiative | EU - Commercial | Europe | Robert Anghel | On Track | 02 December 2025: Updated Description of the Money Step in Milestones and Risks. 28 November 2025: Ready to submit to L3 to track the actuals from the Minimum Disbursement Fee increase. Implemented in Jan 2025 already. 17 April 2025: Changed L1 baseline to FY25. Cannot edit L2 financials as Initiative is in review stage with Data and AI. Will change it after I can edit L2 financials. 18 Feb 25: Updated SL1 details and moved to "Ready to SL2" 14 Mar 25: submitted to SL2. Please be aware this initiative is already in production. There is no IT work needed, and no other impacted portfolios. Work was done already, I just need to move it to L3 to start reporting additional revenue. 17 Mar 25: Redefined the Abillity to statements. As impacted portfolios, the Commercial Portfolio is selected at the end of the request. Also, Business Process and/or Operational Impact field was also updated. I am waiting for the Initiative Supporting Architectural Documentation link (EPM to contact me). | I: L4 | Active | L4 | 2024-11-01 | 2025-01-01
Business w/ Tech Initiative: FIF (FedEx International First) enablement in ePRS |  | 96406 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel, Yu Meng | On Track | 23 March 2026: Provided answers via Teams to Thomas Wittmann's questions and submitted again for L3 approval. 12 Feb 2026: correct PPM no: 858860. 22 Jan 2026: submitted to L3. Also, need to mention here that the solution agreed does not enable FiF in eMBP. 15 Sep. Moved to Portfolio greenlight in L2. We have discussions on email with David Skipper, Ram Gutta and Priti Bhatt to find an alternative solution. We need to move to SL3 in order to IT to start working on it. 10 Apriul 2025: submitting to L2 | G: L3 | Active | L3 | 2026-01-21 | 2027-12-30
Business w/ Tech Initiative: Transit Time Data Enablement |  | 85939 | Business w/ Tech Initiative | EU - Commercial | Europe | Sigrid Smits, Adam Wisniowski, Hanh Phan, Francisca Ferreira | Some Issues | 5th Dec'25: Replacing this EU init with the Global GQTTI rethink effort VBA: visualizing TT. Planview number #161877 Redid the demand description and value statement to better position the efficiency gain in speed to market as well as reduction in effort to create a cross functional capability view that can be enhaned with competitor data in the next stage. Next step is | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Alex & Gross (A&G) Insourcing Initiative |  | 155220 | Business Only Initiative | EU - Commercial | Europe | Diana Zeller, Sandrine Buisson | On Track | 12/11/2025 Submitted to L3. Incremental volume added as a result of improved activation result expected from this inhousing initiative. While it was submitted as a cost saving initiative only for L2. 08/12/2025 ROI existing. Working on documents to be ready for upload. 18/02/2026 Hiring approvals obtained. Termination letter out to vendor and hiring process started. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-12-09 | 2026-06-12
Business w/ Tech Initiative: BMW - Customized Tracking Webhook |  | 163927 | Business w/ Tech Initiative | EU - Commercial | Europe | Jamie Dean, Tommaso Barbieri | On Track | 2026-03-31: Working with Sales to obtain an update from BMW on timelines, and with other parties (US Commercialization & Visibility Team) as to whether the Planview initiative is now required) 2026-02-02: Initiative is ready to be submitted to L2 2026-01-27: Financials updated for L1BC, just final review before submitting to L2 2025-12-15: Still waiting on the details from Pricing to support the financials. 2025-11-05: Working with Finance and Sales to obtain the margins and breakdown of av. Weight per pack, and av pieces per shipments per product | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: AI to Automatically Create Courtesy Net Rates |  | 167057 | Business w/ Tech Initiative | EU - Commercial | Europe | Konstantinos Eleftheriadis, Silvia Berbotto, Margherita Piersanti | On Track | 2 Feb 2026. Ready for L2 submission. Initiative includes Domestic (PROUD) and International (ePRS) - future potential separation of Domestic-International between pods in L3. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AI Improved Domestic RQM |  | 167063 | Business w/ Tech Initiative | EU - Commercial | Europe | Silvia Berbotto, Margherita Piersanti, Konstantinos Eleftheriadis | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AI Chatbox — Sales Companion |  | 167068 | Business w/ Tech Initiative | EU - Commercial | Europe | Silvia Berbotto, Margherita Piersanti, Konstantinos Eleftheriadis | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: [WIN] Iris Galerie Poland EC-Ship Integration |  | 167451 | Business w/ Tech Initiative | EU - Commercial | Europe | Jesper B. Pauig | On Track | A Local Enhancement has been created for this project and the development has been completed. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: IEDR (Import Entry Document Retriever) |  | 169419 | Business w/ Tech Initiative | EU - Commercial | Europe | Francesca De Giovanni | On Track | On Track 03 Feb 2026: Conducted CCH Greenlight triage with the CCH Lead in Memphis (Karen McConnico). Added details to Brief Demand Description to outline the current state, impacted countries, and an explanation on the Finland proof of concept (PoC). Note: I will be on holiday until 20 Feb and will resume L2 activities upon my return | E: L2 | Active | Portfolio Greenlight | 2025-09-02 | 2025-09-02
Business w/ Tech Initiative: Revenue Quality Management (RQM) tool |  | 170091 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Deploy agents at key hubs with cameras |  | 170095 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Tightening auditing system with technology |  | 170098 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Digitize pricing agreements to automate profiling |  | 170101 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Manually analyze data of small customer groups |  | 170104 | Business Only Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Set up process & tool to enable mass pricing updat |  | 170108 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Enable ePRS with field to capture greater |  | 170111 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Create central data lake to integrate commercial p |  | 170897 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Introduce dynamic customer profile checks |  | 170900 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Build automated communication tool/process to mass |  | 177023 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel | On Track | 15 Dec 2025: updated Demand Description. On Track | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Turkey Full Transit Time Review & Improvement |  | 180632 | Business w/ Tech Initiative | EU - Commercial | Europe | Yunus Emre Kayaalp | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Improve Turkey's E-Commerce Value Proposition |  | 183793 | Business w/ Tech Initiative | EU - Commercial | Europe | Maria Andrianakou | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Romanian Inbound Fee |  | 183812 | Business w/ Tech Initiative | EU - Commercial | Europe | Robert Anghel, Bartosz Iwaniec | On Track | On Track | C: L1 | On Hold | L1
Business w/ Tech Initiative: Convert Faroe Islands and Greenland to DR Ctry |  | 192120 | Business w/ Tech Initiative | EU - Commercial | Europe | Nuno Miguel Salgueiro | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Improve revenue quality via introduction of new Pa | 30744 | 6781 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Mayla Giraudo, Monica Soncin | On Track | Confidence in delivering value on time is high. Confidence in delivering the full value is high. I monitored the data from January to August and I confirm: confidence in delivering value on time is high and confidence in delivering the full value is high. | K: L5 | Completed | L5 | 2022-09-01 | 2024-12-31
Business Only Initiative: Improve revenue quality via introduction of Automa | 30772 | 6785 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Mayla Giraudo, Monica Soncin | On Track | Confidence in delivering value on time is high. Confidence in delivering the full value is high. I monitored the data from January to August and I confirm: confidence in delivering value on time is high and confidence in delivering the full value is high. | K: L5 | Completed | L5 | 2022-09-01 | 2024-12-31
Business Only Initiative: Improve revenue quality via compliance surcharge I | 30778 | 6787 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Mayla Giraudo, Monica Soncin | On Track | Confidence in delivering value on time is high. Confidence in delivering the full value is medium/high July 2024 In July 2024 we worked on re forecast of this initiative #30778: the old annual target was $m 3.04 the new annual forecast is $m1.31. We have to reforecast because part of the customers in scope on this initiative are also in scope in another new initiative #81504, hance now no double counting. | K: L5 | Completed | L5 | 2022-09-01 | 2025-01-01
Business Only Initiative: CWC - WS7 - Increase Dim weight capture CWC EU | 82400 | 6908 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Olaf Wozniak, Cesar Guzman | On Track | W44/2024: -> Offers for Łódź hub and Poznań station received. Technical review ongoing. Orders to be placed in W45. -> Offer for Chorzów pending -> List of stations in scope of this initiative under review. Once finalized, site preparations/solution design will start. -> German stations in scope already contracted and planned for execution. First site will be upgraded in Feburary 2025. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2027-03-30
Business Only Initiative: CWC - WS7 - IT Increase CWC & legal for trade(LFT) | 82404 | 6909 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Olaf Wozniak, Cesar Guzman | On Track | Project scope finalized | I: L4 | Active | L4 | 2024-06-03 | 2026-03-31
Business Only Initiative: Roll-out manual AHS-P and Non-Stackable scanning i | 87791 | 6910 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Prajwal Bhat, Cesar Guzman | On Track | 13-12-2024 - Surcharge scanning process now launched at all target air and road hubs. Gathering money-step evidence and submitting initiative to L4 17-03-2025 - Evidence gathered to submit initiative to L5 | K: L5 | Completed | L5 | 2024-08-05 | 2024-12-02
Business w/ Tech Initiative: Enable SNS on FDX [iTrack #3876] | 55837 | 7217 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Eduard van der Lande, Prajwal Bhat | On Track | Confidence on delivering on time: high Confidence on delivering full value: n/a 2024-02-19: status changed back to on track following successful testing. | K: L5 | Completed | L5 | 2023-07-31 | 2024-02-20
Business Only Initiative: Increase AHS scanning compliance (TNT Intl, FDX In | 385 | 7250 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Prajwal Bhat, John Macdonald | On Track | Update 07062024 Europe Highlights CWC – stable performance but below target (86.2%) for May -France best in class performer -DE issues with high volume stations (manpower shortages) under review -E Europe call with high volume stations managers to drive improvement, i.e. WAW, BUH NSS-P – Improving but below target (1.41%) for May – best performance to date!! -BNLX follow up on 3 keys stations produced positive gain -FR plans to roll out DH2 scanners in May/June- improvement expected. -SE Europe exceeding target - NS – Steady on target (2.32%)¬– best performance to date!! -Best Europe result in 2024 !!.. again !! -BNLX, FR, CHAT, E Europe beating target Actions -DE focus on key station improvement required with PE team on manpower shortage issues -Italy senior mgmt review to share improvement actions -Iberia senior mgmt review to share improvement actions -EE facility mgmt call on top 8 stations planned Update 24052024 Europe Highlights CWC – stable performance but below target (86.1%) -France best in class performer -Iberia back on target -DE has significant technical issues. -E Europe VP support obtained to drive performance to target NSS-P – Improving but below target (1.23%) -BNLX follow up on 3 keys stations for improvement underway -FR plans to roll out DH2 scanners in May/June- improvement expected. -SE Europe exceeding target - NS – Steady on target (2.13%) -Best Europe result in 2024 !! -BNLX, FR, CHAT, E Europe beating target Actions -Formal response for DE to reforecast pending with CWC Pod steer-co -DE focus on key station improvement required -Italy VP call required to review performance -Iberia VP call required to review performance Update 17052024 Europe Highlights CWC – stable performance but below target (86.8%) -France best in class performer -Iberia back on target NSS-P – Stable but below target (1.1%) -Nordics exceeding target) -FR plans to roll out DH2 scanners in May/June- improvement expected. -SE Europe exceeding target NS – Steady on target (1.96%) -BNLX, FR, CHAT, E Europe beating target Actions -DE to share process improvement targets for CWC Pod forecast under review -DE focus on key station improvement required -Italy VP call required to review performance -E Europe VP call set up for May 23 to review next steps with deep dive with key stations Update 10052024 Europe Highlights CWC – stable performance but below target (86.7) -BNLX back on target (senior mgmt focus) -Iberia back on target -4% increase in Nordics NSS-P – Stable but below target (1.18) -BNLX back on target (senior mgmt focus) -FR plans to roll out DH2 scanners in May/June- improvement expected. -SE Europe deep dive with high volume countries performed. Improvement expected NS – Data issue means delay on the report for recent week -SE Europe deep dive with high volume countries performed. Improvement expected Highlights: CWC – stable performance SEE hit CWC target BNLX + DE improving NS and NSS-P Actions: NS report not working – ticket open VP calls required with EE and SEE to improve performance Highlights: 19042024 Stable results in CWC and NS. NSS-P results now under urgent review. DE best NS and NSS-P results to date Stefan Dreis meeting held to agree DE improvement focus BNLX senior mgmt team focusing on NS and NSS-P Actions: EE Ground Ops VP to attend meeting to discuss how best to support CWC Pod results. Awareness session aimed at champions on how to best escalate plant & equipment issues. SEE MD call to review issues in Greece, Slovenia and Bulgaria Update 11042024 - Piece level surcharging on FDX to go live on 15-Apr, expect positive impact. Previous IT issue on #32257 (FDX Non-stackable) appears resolved, and back on track. Also, positive benefits due to Enabler Initiative #55837 SNS on FDX is visible on #32257. Update 25032024 - Submitted for L4 approval. DE - Low scanning compliance at many facilities, ma | K: L5 | Completed | L5 | 2022-11-21 | 2024-08-30
Business Only Initiative: Increase TNT International CWC performance complia | 377 | 7261 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Olaf Wozniak, Cesar Guzman | On Track | Update 08072024 Europe Highlights CWC: stable performance but below target (84,6%) for June NSS-P: another month of improvement, still below target (1,30%) NS: Performance dropped to 2,18%, remains above target Issues with equipment in PT, IT and DE impacted CWC results Actions: Change of approach to communication with Champions. Instead of weekly meeting for all Champions, individual sessions will be arranged we each Champion in order to bring more focus on regions. There will be 1 monthly call with all Champions to discuss overall EU results. Italy - communication to station management to focus on CWC (especially NS and NSS-P performance) EE - focus on CWC results, Champions to present an improvement plan Update 07062024 Europe Highlights CWC – stable performance but below target (86.2%) for May France best in class performer DE issues with high volume stations (manpower shortages) under review E Europe call with high volume stations managers to drive improvement, i.e. WAW, BUH NSS-P – Improving but below target (1.41%) for May – best performance to date!! BNLX follow up on 3 keys stations produced positive gain FR plans to roll out DH2 scanners in May/June- improvement expected. SE Europe exceeding target NS – Steady on target (2.32%)¬– best performance to date!! Best Europe result in 2024 !!.. again !! BNLX, FR, CHAT, E Europe beating target Actions DE focus on key station improvement required with PE team on manpower shortage issues Italy senior mgmt review to share improvement actions Iberia senior mgmt review to share improvement actions EE facility mgmt call on top 8 stations planned Update 24052024 Europe Highlights CWC – stable performance but below target (86.1%) France best in class performer Iberia back on target DE has significant technical issues. E Europe VP support obtained to drive performance to target NSS-P – Improving but below target (1.23%) BNLX follow up on 3 keys stations for improvement underway FR plans to roll out DH2 scanners in May/June- improvement expected. SE Europe exceeding target NS – Steady on target (2.13%) Best Europe result in 2024 !! BNLX, FR, CHAT, E Europe beating target Actions Formal response for DE to reforecast pending with CWC Pod steer-co DE focus on key station improvement required Italy VP call required to review performance Iberia VP call required to review performance Update 17052024 Europe Highlights CWC – stable performance but below target (86.8%) France best in class performer Iberia back on target NSS-P – Stable but below target (1.1%) Nordics exceeding target) FR plans to roll out DH2 scanners in May/June- improvement expected. SE Europe exceeding target NS – Steady on target (1.96%) BNLX, FR, CHAT, E Europe beating target Actions DE to share process improvement targets for CWC Pod forecast under review DE focus on key station improvement required Italy VP call required to review performance E Europe VP call set up for May 23 to review next steps with deep dive with key stations Update 10052024 Europe Highlights CWC – stable performance but below target (86.7) BNLX back on target (senior mgmt focus) Iberia back on target 4% increase in Nordics NSS-P – Stable but below target (1.18) BNLX back on target (senior mgmt focus) FR plans to roll out DH2 scanners in May/June- improvement expected. SE Europe deep dive with high volume countries performed. Improvement expected NS – Data issue means delay on the report for recent week SE Europe deep dive with high volume countries performed. Improvement expected Highlights 03052024 CWC – stable performance SEE hit CWC target BNLX + DE improving NS and NSS-P Actions: NS report not working – ticket open VP calls required with EE and SEE to improve performance Highlights 24042024 Highlights: CWC – Europe stable performance NSS – P – Europe performance has improved- DE and BNLX thank you NS - stable Actions: EE VP meeting to drive focus on PL, CZ, HU, RO SEE VP meeting to drive focus on GR, BG, UK mgmt team | K: L5 | Completed | L5 | 2022-11-21 | 2025-06-30
Business w/ Tech Initiative: Ensure Automatic captured non stackable status (SN | 70576 | 7481 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Pilar Gomez Martinez, Prajwal Bhat | On Track | 2024-11-11: Checks carried out on data transmissions of non statckable for FedEx internationa, TNT international and TNT Italy domestic. LSRE2 sees data comming from UDS and is able to pass it to HCH. HCH sees the data comming from LSRE2 and is able to pass it to other systesm: SEP, Common Systems and Filiali respectively/ 2024-11-5: LSRE 2 implemented in TO1 and monitoring of transmission starts 2034-10-31: Monitoring starts only to find out that Torino has two UDS and the one where the devices are connected work under code TO1. Request to enable LSRE2 in Torino submited 2024-10-24: LSRE2 implemented in XIKA 2024-09-30: Prepare work for rollout of LSRE2 in pilot site Torino (XIKA). REQ5913674 raised to enable transmittion of status to LSRE2 2024-09-24: New risk/dependency spotted for the initiative to move to money step: This initiative requires that pilot site is already using LSRE2.0 (no sites except DWCH are in this situation). Implementing LSRE2 has other dependencies, specially for clearance locations, that are not in place.. Proposed pilot site is a clearance location so it is a no-go. New proposed pilot site is XIKA (Torino) 2024-09-23: RITM6434842 raised in PDSM to enable pilot site IMRH for transmissions to LSRE2 with date 21st October. 2024-09-23: Agree on steps for rollout of LSRE2 in pilot site (IMRH-Novara). This is a mandatory steep to be able to also consume the automated non-stackable statues with LSRE 2 2024-9-18: MTP date in between 16th and 29th October (PI4.4). IT will confirm exact date later on, but pilot site preparations can now be scheduled. 20-24-11_ Confirmed E2E test and sign off 2024-07-14: Raise Surface request 2024-07-05 - waiting confirmation of when work identified and accepted during SCI review with surface Portfolio will be injected into US ARTs so we can align this with EU Sort ART 2024-06-28 - Awaiting answer from US Surface Review Board 2024-06-13 SCI presented to Surface Review Board. SCI awaiting now Management approval. 2024-04-29: In review with ECH, call on Tuesday this week involving also the Product Managers 2024-04-22: With ECH, meeting planned for Tuesday 23rd April to confirm planning and resources. 2024-04-08: Kick-off with solution architect (Derrulex Djoukwai) planned for tomorrow 15:00 – 16:00. Asking Bishruta to join. (this stage is expected to take 3wks). 2024-04-01: Pushed to L2, request received to review risks from Simon Alexander. 2024-03-25: Raised for approval for L2 upon request solution architect coordination. 2024-03-11: Demand was initiated and Portfolio accepted. Solution architect to be made available: "Thierry volunteered as Solution Architect for initiative and can start as of end of march (after his vacation). "Filip de Moor asking if we can get all L1 and L2 approvals completed." Once those are in we can engage on TCH assessment which can be reused for the solutioning work (SCI)" | K: L5 | Completed | L5 | 2024-06-03 | 2024-11-15
Business Only Initiative: CWC - WS7 - Increase surcharge capture AHS shipm. | 82401 | 7686 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Cesar Guzman, Olaf Wozniak | On Track | 11/05 - 3 of 40 NCOY machines to be installed this week, coming 37 will be installed before mid Dec. NCOY DWS XL dry run to be MTP this week in BCN (ES). | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2026-10-30
Business w/ Tech Initiative: CWC - WS7 - AHS - Packaging. Increase capture | 82402 | 7687 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Cesar Guzman, Olaf Wozniak | On Track | 11/05 - Platform technical solutions deployment by FedEx IT confirmed on Jan25 Vendor (Vitronic) offer review for the latest set of specs on going Solutons contracting to be comleted on coming week. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-31 | 2026-10-29
Business Only Initiative: CWC - WS7 - NS/SNS - Increase capture | 82403 | 7688 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Cesar Guzman, Olaf Wozniak | On Track | On track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2027-03-29
Business w/ Tech Initiative: WS7 - Optimize AHS surcharges through GRI / CPR cl | 82405 | 7689 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Robert Anghel, Karen Wunderlich | On Track | 26 May 2025: updated L1 baseline to FY25 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-17 | 2027-06-01
Business w/ Tech Initiative: WS7 - Introduce Unauthorized surcharge | 82406 | 7690 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Robert Anghel, Karen Wunderlich | On Track | 26 May 2025: updated L1 baseline to FY25 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-17 | 2027-06-01
Business Only Initiative: WS7 - Increase AHS Weight surcharge base price | 82418 | 7691 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Robert Anghel, Karen Wunderlich | On Track | 26 May 2025: updated L1 baseline to FY25 | I: L4 | Active | L4 | 2024-06-10 | 2027-06-01
Business w/ Tech Initiative: CWC - 84180 - Align UDS DWC devices to HCH naming | 84180 | 7718 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Michael I. Spragg, Pilar Gomez Martinez, Prajwal Bhat | Some Issues | 2025-11-28: Confirmation needed if this issue will affect all countries or only UK and if it is possible to feed the AHS from eOPS where there is information on piece level. 2025-11-26: While analyzing problems with UK barcode a new issue has been raised. TSS new interface only handles data to Common Systems on consignment level. This is ok for iinvoiceing purposes. It will however impact the additional handling surcharge (AHS) process for TNT. This process inspects the PIECE weight & dims in Common Systems. If any piece meets the AHS policy thresholds it will trigger a AHS status code to be added to the consignment (in Track & Trace) which in turn is picked up by Global Link Rating which then ADDs a surcharge (subject to any special rate exemptions), thus charging the customer higher revenue. This could lead to disputes if challenged and definetely to a loose of revenuew due to not having AHS surched applied. 2025-11-25: Confimred that TNT Germany domestic barcode data is now being consumed by Common System. Work in progress for UK domestic 2025-11-24: Confirmed that TNT international barcode idata s now being consumed by Common Systems. Issues remain for Germany domestc and UK Domestic 2025-11-18-Issue with CS test envoronment spotted and third E2E test restared . At this point there will not be time to MTP (if E2E succssfull) before freeze. Pilots sites and development dependency on rollout of TSS new interface. Planview milestones updated 2025-09-22: New E2E scheduled. It is still unknown if MTP and pilots can be done before peak period 2025-08-5: Updated SCI 2025-07-15:Meeting with IT to agree on way forward to fix found issues during E2E test. Agreement to include an additional development to integrate in LSRE2 the Location Translation service with Buffer HCH Bridge. Next sep is to update SCI to add a new feature for LSRE2 2025-06-23: Ongoing fix on the IBIS side. Currently waiting for some proxy changes 2025-06-13: After meeting with all IT teams, to analyse flow of data, the issue is spotted in the IBIS L3 environment. Some work is being done to fix the issue so E2E can be restarted 2025-05-30: E2D data generated from UDS for TNT shipments is not being consume properly by Common Systems. Althought there is communication, weight and dimensions are not passed. This is a showstopper to MTP as the data should be in Common Systems before it is sent to T&T so the billing system can use it. For FedEx shipments data is in SEP. As it is unknown at the time of this updte when the issue will be solved, milestones dates have been rescheduled. 2025-05-26: E2E data from UDS to LSRE to HCH to SEP is working although a cosmetic issue spotted. Awaiting final confirmation that information arrives from HCH to T&T and Filiali 2025-05-15: E2E test restarted 2025-05-07: Confirmation from E2E test team that testing will be done from 15 to 26 May. Milestones updated accordingly 2025-05-04: HCH confirmation that code has now finalized and E2E test can restart 2025-03-26: Meeting with HCH for calrification of the situation and commitement to carry out the additional development that reqiores to be included in one of the next PI and prioritized. It is still not known end date to recomence E2E testing 2025-03-20: E2E spotted issue with HCH not consuming the LSRE2 messages. Change is required in HCH. Earlies PI it can take the work is PI 02 starts 4 -3 - 2025 and ends 6-11-2025 (Phyllis Bruns). Some changes are required in Planview. 1.The DRIVE initiative requires an update to include the Revenue Quality POD. 2.2.The DRIVE must be resubmitted for approval within the Sort Domain process. Unclear how to proceed and how to go about it. Milestones dates to be recalculated for a new E2E to start after PI02 ends. 2025-02-28: Delay in E2E completion. 2025-02-26: Confirmation that Chile UDSs are out of scope. Also APAC UDSs 2025-02-05: Confirmation from UDS test teams on availability for E2E test 2025-02-05: Confirmation from France that | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-14 | 2027-03-31
Business Only Initiative: Improve surcharges compliance | 11168 | 8058 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Geraldine Rolandez, Thomas Murena | On Track | Confidence in delivering value on time: High Confidence in delivering the full value: High The confidence levels are High (75-100% confident/likelihood), Medium (50-75% confident/likelihood) and Low (less than 50% confident/likelihood). | K: L5 | Completed | L5 | 2023-09-01 | 2025-01-31
Business w/ Tech Initiative: FedEx AHS (Pride surcharge Capabilities) | 11126 | 8106 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Ryan O'Boyle, Trent Turner | On Track | “Confidence in delivering value on time: [Med]” “Confidence in delivering the full value: [High]” June 29th - Awaiting conf of CL of Epic 3C in mid August. Planning impact analysis requirement should we get the green light. Config of equipment, SOP and training. rollout approval. Next call planned w/c July 3rd. June 9th - No update to risks. Again shared the core risk issues with Maggie and Emma. June 1st - No update to risks but advised discussing with Maarten. May 25th - No update from Maarten R. Raised concerns again and with UK Management board. Rob P asked for 1 slider to outline the core risks. May 18th - Awaiting solution for equipment to ensure hubs conducts REX83H scans and can be configured + adoption of 1 scan code for all triggers or build of new. Require follow up with Maarten. May 9th - Awaiting confirmation of origin scan capture reason if weight & dims included. Confirmed equipment insufficient to capture DI customers. Meeting planned with Maarten, Darren and Kieron for 12th May. May 4th - main areas of discussion and perceived ‘risks’ with associating actions: Assessment of station activity required to confirm whether SOP for manually applied scans is being adhered to with scans only manually applied based on packaging, rather than being applied based on packaging, dimensions and weight as per TNT. (Action: Suban/Kieron) DL confirmed that hubs are not applying any manual scans due to lack of equipment required to perform the task (LEO) DL estimated that 50 would be required. (Action: Ryan to escalate) Automated capture of REX 82 and REX 83 scans occurs in hubs (for abuser charge capture) however whether this will ultimately result in the AHS surcharge being applied when the AHS thresholds are exceeded, has not been confirmed. Exposure is limited here as by the nature of AHS there should be limited amounts going across the machines. All of the above suggests significant gaps in any impact analysis performed using data currently captured, with 2 meaning revenue leakage at point of launch for D2H customers as AHS will not be applied. Week 15 - Confirmed with martin solution in scanning sop to be provided in two weeks. Arranging session with ground ops and P&E to validate current REX83H scanning to support customer impact analysis. Ryan to set meeting in week 16. Week 14 - No Update week 13 risk remains outstanding - call with Maarten to discuss 3 scan code solution and OS. Need review for pricing codes and links to US Corp load with approach not yet defined Week 13 - new risk identified in that current scanning and code set up is for packaging only and not dims and weight triggers with a manual scan code. Under investigation with Robert Higgins and Maarten Rae. Additionally creates a risk in conducting customer impact analysis which could be understated as not inclusive of the 2 additional triggers. Week 12 - Initial Analysis started, raised queries to P&E regarding projected revenue and data captured. Call to be set up to discuss Monday 3rd April including next steps, current compliance and deeper dive analysis. $370k dilution due to corp load for 2 weeks. Approval from Wouter R to amend money step / impact value. Week 11 - US IT Expect 3 week delay go live Jan 20th ($554k dilution over 3 week period), Require approval to adjust money step. Week 10 - No further update. Due to begin assessment of shipment level data week 11 Week 9 - Awaiting feedback on potential risk of delay of item level charging. Received latest shipment level impact to start to assess weekly levels post Anchor launch. Week 8 - Item level billing now a potential delay concern. Escalating via RP to CG and oneslider created to support awareness of risk of forgone revenues and impact to migration. Week 7 - P&E have provided scanning data at shipment level for review starting in week 8, awaiting feedback from escalation regarding overall status and confirmed Board update for march 15th ref P | K: L5 | Completed | L5 | 2022-12-19 | 2025-09-19
Business Only Initiative: Improve Domestics CWC and Pallet Stations performa | 11117 | 9108 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Simone Teofilo, Nicola Quero | On Track | Confidence in delivering value on time: medium Confidence in delivering the full value: high | K: L5 | Completed | L5 | 2022-12-01 | 2023-09-29
Business Only Initiative: TNT AHS Surcharge Price Increase - Standard Tariff | 11125 | 9111 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Ryan O'Boyle, Arta Baltina | On Track | “Confidence in delivering value on time: [High]” “Confidence in delivering the full value: [Med]” Reforecast completed with lower than expected results vs target - please see below rationale for as to why this is the case - this highlights the change in base TNT business with YOY decline and shows relative operational compliance stable across both time periods, with evidence to show action has been undertaken in response to performance dropping below expected levels Current base business no longer reflective as we see overall decline vs the Initial analysis based on 2022 volumes/customers/performance -Average Revenue per day (exc fuel & surcharges) -11% in 2023 vs 2022 -13% drop YOY (2022 yearly average vs 2023) in trading standard tariff customers per week -Average 1.4% drop in ST customers month on month For context – in Jan 2022 7248 trading ST customers on average each week, by September 2023 this reduces to 5486 ( 24% total reduction) With regards to declining business 1.For the total base business the average Items per month in 2022 was ~469k vs ~390k equating to a 17% overall reduction 2. A) For the AHS manually scanned by the ops teams in stations and hubs, average Items per month in 2022 was ~42k vs ~37k equating to a 12% overall reduction in total B) The average scan percentage increased from 8.9% in 2022 to 9.5% in 2023 with October 2023 being 9.7% With regards to compliance – activities have been undertaken in recent months to ensure that scanning levels improve and more accurately reflect the business The example of this would be the below timeline a)In 2022, May, June and July scan percentage sat at 9.4%, 9.6% and 9.6% respectively b)Between August 2022 and Jan 2023, scan percentages dropped to between 8.3% to 8.9% c)From Feb 2023 to date, scan percentages have increased to between 9.4% and 9.8% following intervention both by commercial, operations and P&E This would suggest that the proportion of AHS in the overall business is similar to that of last year, therefore there would be a limited scope for any further June 9th - Review of KPIs shows yoy drop in total ST customers and scans. Total customer links to churn and no new business in TNT and requires a deeper assessment. Paks scans down 9.5k for Apri//May yoy possibly due to scanning compliance issues identified with the hubs. Awaiting new league tables and performance tracking of AHS May 18th - Base AHS continues to be reviewed due to a 20% drop over 2 weeks mainly driven by Marston Gate. DL believe overstated in previous weeks and back to accurate/normal however only represents 50% of the downturn. Call pending May 23rd with stakeholders. Base AHS under review as revenue value declining, items numbers showed significant drop (20%) in week 18 - Requirement for monitoring through call to be set up No further updates due to initiative launched - confirmation of L5 Money Banked to be provided when applicable - Any events that may directly impact this initiative will be added as / if / when they occur. Week 15 - No Update Week 14 - First week live early estimation $28k based on 4 day week. Written to Kieron & Ray regarding league table and reporting. Week 13 - no update Week 12 - IT ticket raised for Price loading to be actioned Wednesday (MS), Confirmation of change on TNT.com to made Monday 3rd April. Rating Team actioned 46 Customer waivers Week 11 - No Update Week 10 - Customer communications sent out as per below. 46 customers shared with rating team to move ahs to £10.95 from default. Approval gained to reduce revenue impact. Week 9 - Confirmed 46 customers removed from £2 increase in April. Solution likely to adjust to a Personalised Tariff. Internal comms issued to Sales with customer letter copy provided (March 7th). External comms confirmed to be sent on March 10th to be received Monday 13th March. David Green to review the reactive customer group (196 customers) at parent account level to ensure a close Sal | K: L5 | Completed | L5 | 2023-02-09 | 2023-04-28
Business Only Initiative: TNT AHS weight trigger change | 11127 | 9113 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Ryan O'Boyle, Arta Baltina | On Track | “Confidence in delivering value on time: (High]” “Confidence in delivering the full value: [High]” July 5th - No further update June 15th - Arta concluded analysis and preparing to present recommendation and impacts to leadership in LRMC or WTR w/c 19th June June 9th - Arta commenced customer impact with an expectation to review output by end of June + recommendation. May 26th - Received data of 31kg - 45kg. Week 15/16 - Initial discussions started with Dilip & Malcolm to request data from P&E for 31kg-45kg items as not currently captured for extended time period (TBD), Raised IT ticket for CapGemini to run revenue simulation. Raised importance regarding operational SOPs that will need to be changed due to current issues surrounding FDX AHS scanning - Data to be validated to understand if revenue is being captured correctly for TNT items. Week 12 - Socialised change in all sales webinar with commencement date Week 11 - No Update Weeks 10 - No Update Week 9 - No update Week 8 - Reconfirmed IT requirements with IT and proceeding to greenlit Week 7 - No Update Week 6 - No Update Conducted first session with IT and Marketing to evaluate system changes required and comms strategy. Early indications are this requires limited IT work. | K: L5 | Completed | L5 | 2023-04-24 | 2023-10-20
Business w/ Tech Initiative: TNT Cube data customer declared | 11128 | 9114 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Ryan O'Boyle, Arta Baltina | On Track | “Confidence in delivering value on time: [High]” “Confidence in delivering the full value: [High]” July 5th - Call held with Ground Ops and Hubs to outline support required with 142 customers - details shared on Monday 3rd for these customers to be checked - awaiting feedback. Details to be shared with Sales this week to allow simultaneous review with Ops. Reporting tracking issue to be resolved with full report available in 3-4 weeks but 'interim' solution to be provided weekly commencing 12 July. June 29th - Gone live June 19th. Removed 142 customers requiring validation via Ops checks and Sales to re-educate and adjust if necessary then place back into compliance. Delays to customer actions require urgent attention. Additionally encountered issues with tracking upside performance which has required a new ticket to produce this solution w/c 3rd July. June 9th - Analysis on capgem data to provide histogram of customer impact vs customer size vs % impact to enable isolation of top customer requiring mitigation. To be presented w/c June 13th June 1st - Concluded session with Malc. Some outstanding queries but did confirm there is a max calculation that negates for large possibly incorrect entered dims. Histogram to be completed on actual data this week. May26th - Data received today. Still awaiting answers to queries in logic of theory logic vs reality. Week 16 - Awaiting confirmation of Data availability from CapGemini for extended time period, First two server tests result in lower than theoretical analysis. Theory vs actual to be analyzed to understand capture and any comments/concerns to be raised in week 17. Week 15 - confirmed with PSP GTS approach only pending UAT impact validation to be presented at next PSP May 24th. Ongoing question regarding business rules charging if checked vs greatest available. Awaiting confirmation on reduction from 31kgs to 0 in configuration. Initial findings for system results shared, 2 week sample requested by 15th May. Commercial assumptions to be provided 22nd May. Week 14 - Finalize proposal and recommendation for review at RMC & PSP regarding action plan highlighting exposure risk. Discussion pending with marketing team regarding requirements for potential GTS/GTM. Requirement for system validation of theoretical customer impact analysis. Week 13 - No Update Week 12 - Waiver program, GTS & GTM milestones added, Additional value added from AHS FedEx dilution #11126. Preparation for RQM discussion 12th April. . Week 11 - Detailed customer analysis completed to be shared 12th April with RQM deep dive. Confirmation additional milestones to be added including customer & GTS comms and the creation and approval for waiver matrix. Week 10 - Adjustment made to total impact due to delayed start by months. Customer impacts using refined assumptions ongoing to improve accuracy to inform key decision making such as requirement for additional milestones relating to comms, waiver matrix & planning etc. Week 9 - IT design and estimate received and approved with development started this week. 12-16 week expected. Awaiting approval of delayed moneystep foregoing $190k (3 months delay). Reforcasted from July to May inclusive of higher impact to ensure full commitment of total initiatives. Require to add new milestones once delay approved to cover GTS, GTM and changes to IT build and testing. Customer impact to commence week 10 Week 8 - Delay confirmed 12 -16 weeks. Likely launch postponed to July 1st. Deeper level analysis underway planned to review in 2 weeks based on high than expected impacts. Week 7 - Update from ICS pending, initial impact analysis raises concerns regarding overall impact requiring active comms and phased beyond initial April Week 6 - Launch date at risk due to CapGemini Coding issues. Analysis undertaken to understand scope of applying charges and being checked for validation and shared at RMC. We | K: L5 | Completed | L5 | 2023-01-30 | 2023-07-28
Business Only Initiative: FR Domestic revenue: Increase revenue quality (yie | 11167 | 9147 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Gregory Jimenez, Geraldine Rolandez, Cesar Guzman, Damir Babic, Thomas Murena | On Track | 2024-11-25: first station equipped with 2 machines, will be fully operational by he end of this week. next step with Mktg to survey data and enable invoicing from these machines (Jan 25) Initiative is on going with supplier meetings and first cost estimation received this week. Following last week CAPEX alignment meeting at EU level, we are requested to reduce investment by $4.2M. This means do not continue anymore this project and stop all discussions with suppliers. We need clear guidance on next steps before submitting CLEAR and entering negotiations with suppliers. As a reminder, this CWC initiative represents a capital need of approx. $4.9M for get approx. and we estimate $3.1M of additional revenue per year. ROI is very good, less than 2 years. 2023-03-23: last update on Capex confirms that this initiative has been deprioritized by Memphis. It has been submitted again regarding the good ROI expected but if agreed it will be taken in charge by Maarten Rae's team under another initiative around CWC in Europe. 2023-04-06: initiative put on hold. no news on CAPEX, not possible to move forward at this stage, next steps being CLEAR submission before RFQ to suppliers. 2023-04-21: Initiative is now under CWC POD but still on hold. some points to be discussed with Maarten R. as we are ready to go compared to other ones in CWC POD | K: L5 | Active | TEMP L5 - Enter L5 | 2024-02-05 | 2026-10-30
Business Only Initiative: TNT AHS Surcharge Price - Personalised Tariffs | 12015 | 9157 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Ryan O'Boyle, Arta Baltina | On Track | “Confidence in delivering value on time: [High]” “Confidence in delivering the full value: [High]” Week 9 - No update Week - 8 No update Week 6 - No Update Currently on track however limited milestones or preparation required at this stage. | K: L5 | Completed | L5 | 2023-09-04 | 2024-01-15
Business Only Initiative: UK Dom Fuel recalibration | 59554 | 9272 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Ryan O'Boyle, Arta Baltina | On Track | “Confidence in delivering value on time: (High]” “Confidence in delivering the full value: [High]” | K: L5 | Completed | L5 | 2023-11-06 | 2025-04-18
Business w/ Tech Initiative: DWC for non COY shipments when sorted using totes |  | 89532 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Pilar Gomez Martinez | On Track | Initiative in initial states of solution research and data capture for business case creation. Additional research and feedback from vendors required | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: AHS-P (Straps) - Introduction of charge in Europe |  | 93239 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Nicholas D. Ward | On Track | Remains on track for July roll-out traget | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Ops Tech Mobile - Lifecycle Replacement Europe | 83027 | 7700 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Damir Babic, Ferry Spaan | On Track | # Update 2024-12-12 *2024-12-12 Update Diebold received POs for: ** iROADS: 326 scanners ** Honeywell 8680i: 175 scanners ** Honeywell CT47: 482 scanners Total YTD: 983 In Financials Actuals: 983-122 (Nov) = 861 items # Update 2024-12-05 * Entities have started to place orders at our vendors. * Operational reports: https://myfedex.sharepoint.com/teams/CPEEquipment/SitePages/Reporting-Tools.aspx#lifecycle-progress-reports * Update from Finance on November: * 100008618 – Lifecycle program scanning equipment FY25 * Approved capital = $6.6m * Spend to Nov FY25 = $25k for capital * The POs (commitments) have already been submitted worth for November: € 2.540.586 # Update 2024-11-29 * Purchasing process has started, the first PO updates will be reported next week * All solutions have now been enabled for transition * In discussion whether end of service contracts and price reductions should also be included in the PlanView. # Update 2024-11-08 * Procurement escalation resolved. Critical work is completed. Communication sent out to Field P&E for instructions to start replacing through repair and/or full renewal https://myfedex.sharepoint.com/teams/CPEEquipment/SitePages/Lifecycle-Replacement-Europe.aspx Monitoring to start on Purchase Orders (Procurement reports) * Workorders to vendors for commitment to purchasing outstanding with Damir Babic (follow up with Damir on 11/11/2024). # Update 2024-11-06 1. Procurement escalation wrt FCF Catalogue being a blocker to start consuming budget: Hi Ferry I met with Accenture and the team this morning and they have highlighted where the issues occurred in the latest updates. It was a result of removing and adding line items out of sync. Ralph is working to resolve this together with Accenture as a priority. Accenture have agreed they will waive their 2-3 day SLA and prioritise their efforts to ensure we get the updates completed asap. I have a follow up call with Accenture on Friday to get a progress update. Kind regards Heather Radics ¦ Manager - IT S&P ¦ Sourcing and Procurement ¦ +44 7917580803 ¦ Express House, Holly Lane Industrial Estate, Atherstone, Warwickshire CV9 2RY ¦ fedex.com 2. iROADS In agreement with US Team, we will continue deployment of iROADS accross the other countries. ¬ # Update 2024-11-01 1. Procurement escalation to Accenture (1st Nov, to be followed up 5th Nov) * Example: scanners worth over €2,800 with vendor Diebold are now in the catalogue as €4 with another vendor. 2. Avalanche retired 31st October. ** * This leaves 40,000 devices in Europe unmanaged. Replacement was part of this Drive initiative, but is not happening due to afore mentioned 4. iROADS * The US solution owner is concerned on iROADS with Avery Dennison 6059+ (Android 12) for production deployment. Reason: battery drainage within 2-3 hours; upgrade issues; unknown sponteanous reboots during use. * Avery Dennison is in the process of swapping the already received equipment for Europe: (UK: 212; EU: 400) * AMSA and Poland remain testing. Poland will extend the usage of iROADS. Note that Poland does not use printing functionality * Phasar * Software is not ready to use with ringscanner 8680i. Scheduled for January '2025 8. Pscan * Honeywell 8680i available for swapping during repair 10. Telnet based solutions * Ready for swapping during repair. Procurement to release the catalogue (see above mentioned issue) 10. Workorders * There are 6 workorders in the Encore Request queue. These are bouncing back by Procurement contracting teams and delaying the delivery of equipment. Vendors do no longer trust FedEx on their commitments, hence the workorders for delivery. # Update 31 October 2024 due to Accenture, we keep on having issues with ordering items through FCF Catalogue. At this moment, Procurement is (again) chasing Accenture teams to properly update all items that Operations will need to order. This is still a big blocker. As a consequence, our vendors have become a | G: L3 | Completed | L3 Data Migration - TEMP | 2024-06-03 | 2025-05-30
Business Only Initiative: OTP MHS and sorter | 91010 | 7707 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Dimitrios-Agamemnon Christodou, Kostas Adamopolous, Nebojsa Vasiljevic | On Track | Project is progressing well with no delays foreseen. No payments done yet to the MHS vendor still we are progressing - payments planned for later - july. Delivery of the MHS is anticipated for Sep- Oct 2025 - way ahead of schedule. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-12-02 | 2026-05-29
Business Only Initiative: BUD MHS and sorter | 91011 | 7708 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Dimitrios-Agamemnon Christodou, Kostas Adamopolous, Nebojsa Vasiljevic | On Track | The project is idle for too long! Once t he project is live again we will file another request in Planview. | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: Stansted Mx Insourcing |  | 89063 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Paul Spoor, Maria sim | On Track | Week 36 - Aug actuals added. Due to low headcount and ongoing recruting the actuals are slightly hire than plan (2k) this is driven by overtime to cover missing staff. Recruitment on going Week 29 - TUPE complete, all transfer complete and technicians are now on Fedex payroll. Moving to L4 Week 29 - Onboarding comlpete, 1 candidate decided not to transfer which leaves another vacancy which has to be backfilled. Transfer date still set for 17th July as per plan Week 28 all consultations completed and onbolarding process in progress. TUPE finalised with contracts beng returned Week 27 - 2nd consulations completed and final terms shared. Expected VI final feedback in wk 28 Week 24 - Individual consultations under way, TUPE detials all shared and being discussed. 2nd round of consultations expected in week 27 Week 22 - Individual consultations to begin, schedule being reviewed on 30/05. Job requisition (admin) has been raised fo rmanager position and is going through apporvals. Week 20 - Milestone for TUPE process extended to match the money step. HR advised that the process will be ongoing until contract sign as technicians can pull out at anytime without consequence. This is adminstritve and will not affect the planned execution date. NO RISK Week 19 - All Q&As closed following collective consulation. Individual consultations are being planned Week 15 - So far 2x roles will not TUPE across to Fedex, adverts have been submitted to advertise these positions. The RC for all 8 roles has been apprved and ready to be utilised should other team memebers not decide to transfer over. Milestone for begin recruitment has been completed Week 14 - All ELI information received Week 12 - FAQ sent out to all roles in scope with details on TUPE process as part of EL1 process Week 11 - Requisition now raised in workday, RC749525. Wk10 - Vanderlande team informed of contract end and potential TUPE to Fedex. Process started to get approval for 8x requistitons in Workday for the technician roles and the BCE approval process has started for the fixed manager position. WK07 - HR appointed Rachel Alison to assist in TUPE transfer. Vanderlande arranging a site visit on 25th February to discuss changes Wk04 - Finaince checklist complete submitted to L2 Wk 04 - Business case adjusted at request of Finance to reflect exchange rate of 0.79$ to the £. All text in initiative also alterted to match new saving calculation Wk 03 - Milestones added as well as vanderlande contract, Wk 02 - Added Risks to Planview, I need guidence from finannce and POD lead to move in to L2 - All fields seem to have been filled in Current status is in line with business case timeline (Attached) | I: L4 | Active | TEMP L4 - Enter L4 | 2024-11-25 | 2025-07-17
Business w/ Tech Initiative: STAT60 and STAT56 auto-posted by UDS |  | 91951 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Jesus Marin | On Track | 07/08: Since the technical solution to implement this initiative is already under scope of LSRE2.0, this strategy to be put On Hold as agreed with Pranshu Saxena. Until the PFS arrives in 2026, alternative options are being investigated because now it is possible to apply STAT60 and STAT56 with UDS. There is a gap with the correct Clearance LOC ID being posted. 06/27. LSRE2.0 is as explained by Eduard Van Der Lande the tech solution for this request. This is planned to be in production no sooner than January 2026 05/20. There have been changes in the Scan mapping from TNT to Fedex that could cover the gap for STAT 60/56. To be investigated. TNT/FedEx Scan Mapping. 05/06. Financials revision is pending with Rob Davidson. A call with him to be scheduled for this or next week before submission to L2. 03/25 L1 feedback request . Strategy has been updated. 03/18: Received L1 Architecture Alignment Complete report. 02/24: Contacting IT Sort & Ramp Systems Intl Dev for support on the Biz w/ Tech Additional Info 02/18. Meeting with David Egan regarding Biz w/ Tech Additional Info. David recommended to have a call with Emily Woestenenk to get the right prioritization from IT to execute the solution. 02/11. Meeting with Rob Davidson. TBD how to calculate the net recurring benefits, taking into account the initiative is improving the Operational Efficiency of all the clearance locations. David Egan has been contacted to work on the Biz w/ Tech Additional Info. 02/04. Meeting with FP&A planned for 02/07 to review the Financial inputs for L1 LBC. 01/28. No answer from Finance department has been received, so I proceed to start completing the Financial items on my own, and wait for the feedback after submission. 01/20 Completing the LBC - Financial. Finance department has been contacted to start preparing the LBC | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: G&A - Reduction ticket process in Encore |  | 97699 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Sonia Colleoni | On Track | We do see potential for savings but the new contract with JCP for the ticketing has been just renewed in US for additional 3 years and the current calculated savings are very limited. Hence to be kept on hold while the team is working on this further refinements | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FRA GTH Sorter Re-design |  | 97702 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Kurt Riisberg, Matias Montero-Paschold | Some Issues | 4 Dec 2025 have been directed to investigate alternative option of a combined location at FRA vs. the separate FRA GTH & FRA Gateway. Will have more info. mid-January on how to proceed. Currently under evaluation on how to move forward as this is an enabler of a project that has gone to L3. Net recurring benefits are set to zero in order to add assistant IO. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: G&A - Reduce cleaning audits. |  | 94047 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Gianna Abello, Sonia Colleoni, Christian Johannes Visschedijk, Lynn Simpson | On Track | The audit will be completely removed | K: L5 | Active | TEMP L5 - Enter L5 | 2025-01-20
Business Only Initiative: G&A - Reduce office cleaning |  | 94050 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Gianna Abello, Guido Bollekens, Sonia Colleoni | On Track | On track. It includes also the windows cleaning reduced from twice to once a year | K: L5 | Active | L5 | 2025-01-20 | 2025-10-31
Business Only Initiative: G&A - Reduce landscaping at non customer areas |  | 94053 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Gianna Abello, Sonia Colleoni, Christian Johannes Visschedijk, Lynn Simpson | On Track | On track | K: L5 | Active | TEMP L5 - Enter L5 | 2025-01-20 | 2025-04-10
Business w/ Tech Initiative: WS7 - Introduce Unauthorized surcharge (phase 2) |  | 103180 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Robert Anghel, Karen Wunderlich, LJ Bowman | On Track | 30 March 2026: Initiative became redundant. LJ Bowman confirmed there is no further need for this initiative and that it will not produce the initial estimated impact. \27 Jan 2026. There's a similar initiative 104047, which needs to be cancelled since this initiative covers it. 26 August: Added Sales Execution and Billing & Collection (i.e. Revenue Operations) as additional function being impacted (as Unauthorized pictures need to be accessable in case of customer queries) 19 May: Edited L2 net recurring benefits and impacted regions. 14 March: adding required fields for L2 where available, awaiting Chris Gibney input where to get IT architect name from as it seems L2 requirement but no clarity on where to select from 18 March: adjusted Ability-To statements to required format. Changed business dates from 260 to 250 in revenue estimate calculation (change from annual $5.4M to $5.25M. | E: L2 | Cancelled | L2 Feedback Requested
Business Only Initiative: AMS GTH Expansion |  | 103183 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Larrisa Singh | On Track | Business Requirements to be redefined with possible colocation, therefore placed on hold. Expecting to resume Feb 2026. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: IMRH Hybrid maintenance team |  | 103186 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Samuel Jeremiah Adeleke | On Track | New vendor maintenance contract in place since June 2025. FDX inhouse maintenance team 100% in place since first week of September 2025. | K: L5 | Active | L5 | 2025-03-10 | 2025-11-03
Business Only Initiative: EXTRA OSC Vehicle Maintenance Insourcing (UK) | 89791 | 7615 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Craig Munro, Gary Carciente | Attention Needed | 06/02/2026: On tack to move to L4. Money Step evidence will be uploaded asap. ready to move to L4 **I have reviewed this initiative and it should not be moved to L4, please hold - Craig Munro** **Following review - confirmed FY26 cost reduction not met. Proposed Action Plan: Correct FY25 – Update FY25 Cost reduction to $0 & update health Status (Pending Approval) Implement Net Headcount Tracking - accurate staffing data to better support cost-saving goals. Enhanced Contract Mgmt - Renegotiate terms with high-spend vendors to mitigate rising costs and enforce stronger performance standards. Maintenance optimization – Fast-track the analysis to determine the most cost-effective mix of in-house and outsource. Update & Relaunch Initiative - Re-initiate the project focused on optimizing mx operations to deliver cost reduction and efficiency gains. Reforecast cost savings For TY26 vs baseline of FY26 (Pending Approval) Update Money step from 14/11/25 to 14/11/26, 12-month extension. (Pending Approval) Craig Munro** | H: SL4 | On Hold | SL4 Domain Lead Approval | 2024-05-03 | 2025-11-14
Business Only Initiative: Reduce FLT/PPT Scheduled Maintenance in Europe |  | 89060 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Craig Munro, Helen Moralee, Kevin Graindorge | Some Issues | We are progressing with local changes to frequency where possible, however due to being a small team with a high volume of assets per team member, we need the support of GV to initiate the changes in GV Max (Global Maintenance System) to avoid extra admin, realised the reductio in admin costs and ensure system reflects reality from a planning and compliance perspective. On hold due to : 1. Forklift tender ongoing, new forklifts with reduced PM frequency requirements expected before end of TY26/early FY27 2. Telematics deployment - ongoing, provides clear uitilisation data allowing PM reduction 3.global fixed PM schedule. Currently working to deploy country specific frequencies based on: > H&S Policy (internal) > Manufacturer guidelines > country regulations > hours of use | E: L2 | On Hold | L2 Feedback Requested
Business Only Initiative: PM reduction at PUD Vans in mainland Europe |  | 87028 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Michael Rudolph | On Track | In discussions with Global Vehicle Engineering MEM about advantages and disadvantages of this regulation. MR 10.01.2025: GV recommends to go for smart PM instead of PM reduction. This is easier to implement. No further action planned on this initiative at the moment. MR 14.01.2025: As implementation of Smart PM will take min. 12 month we will skip every 2. PM for the time being. This will result in a Service intervall of 8 month instead of 12. OEM recomendation is 12 month or 40.000km. MR 17.02.2025: Numbers slightly changed. Assets in scope: 2300 NOT 3400 PM Hard savings: €880.900 NOT €1.302.200 Admin savings:€46.000 NOT €100.000 Total savings:€926.900 NOT €1.402.200 | K: L5 | Active | L5 | 2025-02-03 | 2025-05-26
Business Only Initiative: POC CGN - Smalls Reusable Bags |  | 105753 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Pilar Gomez Martinez | On Track | Awaiting decision on how to plan the initiatives for deployment | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Insourcing GSE maintenance at STN (partially) |  | 105757 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Craig Munro, David Kemeni, Yves Grandmaire, Gary Carciente | On Track | Supervisor appointed and will officially commence 1st June 2025, technician recruitment ongoing. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-17 | 2026-07-31
Business Only Initiative: EXTRA OSC Maintenance CDG | 89224 | 9265 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Cecile Jourdan, Paul Spoor, Arjan van der Nat | On Track | Week 33 - Taken off hold, actuals added for June and July - including a correction for the period when it was held. .Placed on hold after VP and SVP approval due fact that all associated I/Os are currently out of office. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-12 | 2025-04-01
Business Only Initiative: ServiceChannel EU Implementation |  | 92684 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Satu Schroderus, Guido Bollekens, Paul Spoor, Vaibhav Srivastava | On Track | 09/04/2025 Resubmitting for L2 review following ESI, Annualised benefit and Request type confirmation 02/04: Switched request tyrp from Enabler to Efficiency after discussion with Arjan van der Nat and Quincy McGlown - resubmitted for review 01/29: Implementation plan is being finalized. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-31 | 2027-06-01
Business Only Initiative: OSV to insource |  | 112930 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Sonia Colleoni | On Track | Ad hoc insourcing initiatives and this is not anymore needed | E: L2 | Cancelled | L2 | 2024-07-22 | 2025-11-28
Business Only Initiative: Insourcing GSE Mx at CGN and FRA (partially) |  | 113357 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Yves Grandmaire, Craig Munro, David Kemeni | On Track | On track as project about to commence. | E: L2 | Active | L2 Feedback Requested | 2025-09-01 | 2026-06-29
Business w/ Tech Initiative: External Sharing/Distribution of PIP Images |  | 126003 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Nicholas D. Ward, LJ Bowman | On Track | Submitting to L2 -Update 29/09 - Adding LJ to Owners -Update 02/10 - FP&A Input - Change baseline year to FY25, change baseline value to $36M, change target value to $3M (to keep it consistent for financials in L3) -Update 06/10 - Selecting "Ready for SL2" box following FP&A sign-off -Update 09/10 - Changed benefit type from Hard to Soft after understanding hard can be 0 if required -Update 10/10 - Changing L0 Annual Benefit from Unknown to actual value -Update 14/10 - Changing Finance Domain Lead to Nigel Belfield | E: L2 | Active | TEMP L2 - Enter Value Prop
Business Only Initiative: EU-QARHUB-Insourcing Residential MX (Hybrid) |  | 126006 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Marcos Bartoloni | On Track | 06/17: Initiative pending Life cycle Steps completion to be launched. Benefits are explained, and follows FedEx strategies to impulse insourcing model (in combination with Hybrid model). 06/03/2026: For the Flexible work roles (Technicians & Technician Sr), all job requisitions have been launched in WORKDAY and currently pending for hierarchical approval upstream. For the MOIRAI approval process regarding the Non-Flex work roles (Control room Specialist & Maintenance Specialist), approvals have been given up until Miguel Cortes, and is currently laying on the Regional Council approval. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-12-01 | 2026-09-30
Business w/ Tech Initiative: Shannon Property Project |  | 92050 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Kevin C. Cullen, Ben Radford | On Track | On hold as project now proceeding as local enhancement. This initiative will be deleted once local enhancement progresses to L3. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: HQ closing date on Friday |  | 93550 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Sonia Colleoni | On Track | The current HQ in AMS because of the hybrid way of working it does have a very low occupancy rate particularly on Friday. Some analysis has been carried out by the team and the result is that the office has an occupancy peak particularly between Tuesday-Thursday with the lowest occupancy rate on Friday. Today the office is open until late and this initiative will allow to close the office on Friday from 7pm until Monday morning to cut costs | K: L5 | Completed | L5 | 2025-03-03 | 2025-03-10
Business Only Initiative: WS3 - infrastructure- Improvement dock door reliab | 82253 | 9264 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Paul Spoor, Arjan van der Nat | On Track | Week 16 - Germany financials based on average of previous weeks due to data not being received in tome by supplier - correction will be made in next month submission to ensure quarterly balance is correct Stansted UK was due to finish this week, but incorrect rails have been delivered, date now moved out to Mid March, this still ensure completion prior to scheduled project end date Due to delays in CEU VP and SVP permission granted to move Money Step to 30th April 2026. Note that benefits are already being delivered but last installation is pushing dates out Week 37 - Actuals completed for Aug. Month savings not acheived however quarterly forecast has been meet due to strong July Week 35 - Altered end date for training, this will be deliiivered as doors are installed. Milestone now reflects this Week 29 - Only 7x POs remaing across EU - Installations began in week 28 and being rolled out across EU. .CBRE and Apleona confimred that all wil be done by deadline of 29thJan. Week 28 - Final quotes are in for CDG with PO being raised. Wk 27 - Training documentation written up by Aploena which will be applicable for all sites. Week 23 - All POS released for UK and Installation plan received fro all regions except CDG and SSE, date has been extended to 30/06. PO's (not all) have been released for CEU and Nordics. Project on track with no risk Week 22 - Installation plans taking longer than expected, dates moved back to 23rd June. No impact to money step as we are ahead of schedule with small installations in progress Week 19 - Landlord permissions confirmed for SSEU region. and underway in DE and UK not applicable Week 18 - Written confirmation obtained from both CBRE and Apleona confimring that labour resource and Materials are available to complate all installations prior the money step deadline date of 30th Jan 2026 Week 13 - BENELUX taken out of plan with milestones cancelled, no opportunities were identified for asset improvement during the Program Scope/Material resourse phase Week 12 - Pricing issues resolved with CBRE and full alignment in SEU. Baselines and KPIs recalculated based on FY25 actuals prior to 31/03 deadline following review with finance. Week 10 - Meetings held with CBRE and Apleona. Based on scope defined, materials and labour are being reviewed to confirm installation plan. These actions have been moved to in porgress on the milestone tracker. These calls were 1 week late but will not affect the money step deadline. Week 10 - Scope now confimred in each region, with provisional costs submitted for assets within the scope. Costs are undergoing further review before. Apleona/CBRE assigning a PMO for each region to support delivery. Week 6 - ENCORE submission now fully apprved, funds ready to be used. Week 3 - Project still not financially approved in ENCORE Week 51 - All forecasts and Milestones adjusted in Planview and ENCORE. ENCORE approval submitted and going through the process to secure funding. Week 49 - Given that funds have yet to be approved I have been given approval by Elaina Invernizzi and Floor Hommen to move all milestones back by 3months to absorb the delay. The financial forecast will also be adjusted Scope of works ongoing and on track to meet the Milestone deadline, however financial approval has still not been receioved from CFO Committiee, if this hasnt been receioved by week 49 dates will need to be reviewed. Week 48 - CFO have given approval for the CLEAR to move forward, however i still need to obtain Corp approval through ENCORE - I have started this process. The initiativce needs to be altered due to the 4 month delay getting approvals. I will discuss wioth POD lead and Sponsor and will need to move all milestones and capital forecasts to mirror the delays getting financial approvals. - Money step will move too. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-11-29 | 2026-12-31
Business Only Initiative: Visual Sort Assist in Wiesbaden |  | 140202 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Georgiana Constantin, Juergen Kogure, Georgel - Victor Vijulie | On Track | 01st Oct: Info updated for L3 re-submission, in line with recommended actions. 07th July: Cost savings will consists in 2 FTEs reduction. Savings will be flagged after Go live. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-03 | 2026-08-31
Business w/ Tech Initiative: EUR-MHE CCTV Standard and DE Hubs Implementation |  | 143237 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Joern Kaulfuss, Daniel Kujat | On Track | 07/25: Adding of hard and soft benefits of initiative | E: L2 | On Hold | L2 Feedback Requested | 2026-05-29 | 2026-05-29
Business Only Initiative: EUR-CGNHU Homecoming - Insourcing Residential Mx |  | 105743 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Andreas Hastedt, Daniel Kujat, Joern Kaulfuss | On Track | Decision could not be reached in shortterm. To not risk operational continuity the contract with vendor was extended another year until Q2 2027. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-05-01 | 2026-07-09
Business Only Initiative: Insourcing GSE maintenance at CDG (partially) |  | 105760 | Business Only Initiative | EU - Infrastructure & Revenue Engineering | Europe | Craig Munro, David Kemeni | On Track | WC approval required to implement supervsior positions, presentation to WC will take place in the coming weeks. | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: INNOV_RFID Technology Implementation |  | 188793 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Anass BOUYARMANE, Cesar Guzman | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: INNOV_Autonomous Mobile Robots (AMRs) |  | 189847 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Andrea Massimo De Angelis | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: ZWS - New Sorter (Obsolescence Capital Request) |  | 189927 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Benjamin Dorn | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: INNOV_Automated iRoad Print Label Application (PA) |  | 189930 | Business w/ Tech Initiative | EU - Infrastructure & Revenue Engineering | Europe | Alexis Prichinenko | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: WS3 Network efficiency (STW 2.0) | 82132 | 7297 | Business Only Initiative | EU - ERN | Europe | Frank Wouters, Jan Maarten Braaksma | On Track | 21/11/2024 Initiative put on hold. | C: L1 | Completed | L1 Data Migration - TEMP
Business w/ Tech Initiative: ROCS2.0 Reporting Data to dAtlas | 69526 | 7393 | Business w/ Tech Initiative | EU - ERN | Europe | Rene Vedder, Marit Heidemann | On Track | ***Week16 - 10th April L3 ROCS Operate 2.0 and CDAS go live on April 13th. Production workspace requested to be able to provide completed reports to Ops ROCS Plan ingestion completed and approved ***Week13 - 20th March L3 RNCO-epic seemed still to be in L2 - moved now to L3! Plan -tests are now giving the results as expected ....... ***Week12 - 13th March L3 Phase Plan - plan data is now available Request to start setting up the connection between ROCS and MFBA raised ***Week11 - 6th March L3 Phase Plan - plan data not yet available ***Week10 - 27th Feb L3 Phase Plan - expected to have data this week CDAS - testing ready - some issues ***Week9 - 27th Feb L3 Phase Milestones adjusted •Nonprod storage issue - global problem still only temp fix - awaiting action infowys Data PLAN2.0 will be available coming week CDAS - all data provided UAT to be started ***Week8 - 20th Feb L3 Phase Actual Financials updated with planned ones as actuals are not available Workspace - RNCO will get own workspae Accenture Support - should start from ERN go live - now in financials put on Oct '26 PLAN data still pending as it was not planned CDAS data can be tested - RNCO team requested Historical data should at least be 7 months retained (under investigation) ***Week7 - 13th Feb Still L2 Phase - submitted for L3 in Planview! Finance review pending Actual Financials to be updated Workspace question still pending Accenture Support - should start from ERN go live PLAN data still need to be loaded before team can start working ***Week6 - 6th Feb Still L2 Phase - but submitted for L3 in Planview! Tom Seipp has given the approval Meeting with Ben was there to propose a different approach for the epic, Instead of support of Accenture - the reports should 'be build' by AI. This meeting was the reason the green lighting was postponed Global Nonprod storage issue - temp fii implemented - dashboard work has been resumed. - Long term solution is under investigation Progress in reports - some can be reviewed now. For PLAN reports - no progress becuase the data seems to be to limited - while it even could be tested with production data - but data needs to be enabled for publishing towards Dataworks for test and production Historical data - some agreement are made between biz and dataworks - solution became clear KT sessions for RNCO ongoing - but awaiting now additional courses which need to be done by RNCO teammembers first, but good progress: first report was created/published ***Week5 - 30th Jan Still L2 Phase Meeting with Ben scheduled for Feb 3rd to get IT Green light. No change to planning. KT in progress with RNCO. A global non-prod storage issue (due to firewall changes) is blocking report publication; rollback may be needed. This is not impacting now, but might become and issue when it takes longer. Discussion ongoing on ROCS historical data. ***Week4 - 23th Jan Still L2 Phase Still in L2 Phase requested IT to get approval of Ben Komada as the timeline was provided third week of December. The request for support from Accenture for RNCO should be done at the moment ROCS2.0 is live and adjustments are needed. EIW depreciation has been cancelled - initially the EIW-depreciation was planned for May 2026 - and should have meant that ROCS2.0-reporting and ROCS2.0 should have been live before May2026 for all networks. ***Week 3 - 16th Jan Still L2 Phase * PLAN2.0 data is available and can be consumed in dataworks - discussed when the data can go live - reports still to be created * Go LIve ROCS2.0 + CDAS end of March - > * Historical data is under discussion - can be loaded with the existing files instead of EIW * ROLLS data: Idea is to replace the current static file used for reporting ROLLS data. * KT sessions started with RNCO team * * To be checked - IW depreciation has been cancelled according Vincent Romeo - or is it postponed again ***Week 51 - Week 2 2026 - 9th Jan Still in L2 phase •DA and DE are currently focused on cl | G: L3 | Active | L3 | 2024-09-16 | 2027-04-01
Business Only Initiative: WS5 Productivity improvement commitment | 90918 | 7397 | Business Only Initiative | EU - ERN | Europe | Mark Timmermans, Floor Hommen |  | Target has been agreed for FY26 but no tangible plan identified on how to achieve this - initiative value is loaded in wave to support total value commitment calculation but more detail to this initiative will be added in H2 FY25 | C: L1 | Completed | L1 Data Migration - TEMP
Business Only Initiative: WS3 Netherlands infrastructure design - Consolidat | 81689 | 7401 | Business Only Initiative | EU - ERN | Europe | Stefan Van den Berg, Frank Wouters | On Track | Apr-9 2026: update actuals of Mar-May as there is no change in savings for the coming months, As of June no financial updates anymore required. Mar-12 2026: update actuals of Feb Feb-12 2026: update actuals of Jan Jan-12 2026: update actuals of Dec Nov-12 2025: update actuals of Oct Oct-7 2025: update actuals of Sept Sep-15 2025: added confirmation letter landlord of the lease end as money step evidence Sep-12 2025: Expected L5 date is June 2026 Sep-08 2025: update actuals of August Sep-03 2025: Initiative is ready to submit to L4 - Check FP&A in progress Aug-11 2025: update actuals of July and forecast for Aug, Sept and Oct July-7 2025: update actuals of June June-12 2025: update actuals of May Jan-20 2025: Update financial actuals and kpi Dec | K: L5 | Active | L5 | 2024-05-01 | 2025-09-01
Business w/ Tech Initiative: WS 2 EU Linehaul Driver App MVP | 77037 | 7634 | Business w/ Tech Initiative | EU - ERN | Europe | Michele van Zutphen | Attention Needed | 29/04/25: Initiative put on hold because of ROCS 2.0 NA (North America). They also need a mobile solution in ROCS 2.0 and a Workstream is set up to define the requirements for a mobile app for LH Drivers that covers both NA and EU needs. Discussed by Filip de Moor in new TCH process; request done to EU LH ART for resource availability or resources required to progress it. Currently no resources or budget available within EU LH ART to progress this initiative. According to Michael Strong (Mgr IT in EU LH ART): in FY25 it is not prioritized so work will not start in FY25. This means that in case budget and resources cannot be made available, most likely, the development of this version of the application (and next initiatives that will be raised for version 2 of the driver app and the initiative for the required e-FTI platform - to provide all legal documents for a movement digitally) will not be ready by the end of 2026 - as legislation in EU is changing and all EU countries will allow usage of digital paperwork, we will not be ready on-time to immediately grasp the benefits of providing digital paperwork (=quicklane at the border, less time spent on briefing and debriefing of drivers and printing required paperwork, continuously running costs for damages to our fleet that are not caused by our own drivers). Addressed by Michele van Zutphen that the budget required is the case for all other bunker initiatives Spoken with Pierre: WS 2 EU Linehaul Driver App MVP - Need to check the details but today in the afternoon I will send requests to McKinsey to get ECH approval for critical EU bunker initiatives which are still in the queue. So if it is not fixed today #77037 will need to wait for further investigation by Management Board if trade off discussion is needed 12/16/25 Initiative cancellation request received via PDSM ticket # INC033430506. | E: L2 | Cancelled | L2 | 2024-07-31 | 2028-05-31
Business w/ Tech Initiative: WS 2 - Load content sequence and priority summary | 82280 | 7635 | Business w/ Tech Initiative | EU - ERN | Europe | Rene Vedder, Marit Heidemann, Martijn Koker | On Track | As ROCS will also be implemented in North America (NA) and in NA they have a similar requirement. This work will be included in the larger requirement for ROCS deployment is the US. This initiavtive is still something business wants, but does not have the priority to move forward now. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2024-07-04 | 2024-07-19
Business Only Initiative: Operation Holistic | 34075 | 7867 | Business Only Initiative | EU - ERN | Europe | Emilia Greco, Sooraj Ravikumar | On Track | Confidence in delivering value on time: Medium Confidence in delivering the full value: N/A. Scope of this initiative is to undertand how business process is moving across data systems. | K: L5 | Completed | L5 | 2023-08-08 | 2024-03-08
Business Only Initiative: WS3 Loose load lanes road network | 82300 | 7892 | Business Only Initiative | EU - ERN | Europe | Stefan Van den Berg, Alizee Cogez | On Track | Mar-12th 2026: Update actuals of Feb Feb-12th 2026: Update actuals of Jan Jan-12th 2026: Update actuals of Dec Nov-12th: Update actuals of Oct Oct-7th: Update actuals of Sept APR25: Approval process for BJD and Capital Committee took too much time. Started April 10 and ready May 13. Next steps is submit L3 and CLEAR which also expected to require some weeks. The BJD is based on a CLEAR approval target date mid of May. The BJD approval timeline took over a month (April 10th till May 13th). This moves everything with 1 month, thus Clear approval (mid of June) and delivery of the installation one month later which impacts the expected savings in the BJD. MARCH25 : scope frozen with reduced scope validated FEB25 : scope has been reduced to accelerate the L2 validation of a number of locations that we are ready to proceed with FEB25 : capital needed has been updated according to quotations received by Sort Tech & Properties, total estimated capital needed went from 5.6M€ to 7.5M€ JAN25 : bypass savings estimations reviewed, 50% capture rate applied to the expected flex down, total estimated savings currently around 1M€/year DEC25 : to break DNG loose unload bottleneck, a new injection line needs to be built, total estimated capital needed went from 4.1M€ to 5.6M€ NOV24 : Change of approach decided, new scope defined | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-11 | 2026-10-30
Business Only Initiative: WS3 LGG Loose Unload | 87273 | 7895 | Business Only Initiative | EU - ERN | Europe | Stefan Van den Berg, Alizee Cogez | On Track | Apr-12th 2026:Update actuals of Feb Feb-12th 2026:Update actuals of Jan Jan-12 2026: update actuals of Dec Nov-11 2025: update actuals of Oct Oct-7 2025: update actuals of Sept 10 Sept: Initiative is ready to go to L4, the linehaul savings started per Sept 9th. Expected L5 date is Sept 1st 2026 08 Sept: updated actual financials August 04/18: LLG LL expected to be delivered end of May/early June. contingency flexbelt not ready yet due to H&S requirements 11/12 : CLEAR submited, project is back on track. 11/06 : Quotation received by Sort Tech Design with a different price, different equipment, to be validated with Ops and P&E LGG (lead time 10 days because of some holidays), and discrepancy to be noted with the business case based on first quotation 10/21 : CLEAR process delayed by a ban on the supplier (FMH) which provides the equipment we plan to acquire. Need to renew quotations with Sort Tech Design with a different equipment from a different supplier, and validate it with Operations | I: L4 | Active | TEMP L4 - Enter L4 | 2024-10-02 | 2025-09-12
Business Only Initiative: Remove cages as a loading device for trailers, fro | 1070 | 8172 | Business Only Initiative | EU - ERN | Europe | Fernando Lopez, Wietse Feenstra | On Track | CONFIDENCE ACHIEVEMENT ON TIME: LOW (Will stick to plan&revise every exception, savings are coming but not at speed planned) CONFIDENCE VALUE IN FULL ACHIEVEMENT : CONFIDENT (Though some Initiatives will be in need of investment ) October 7th Updated results for September 2024 Week 34 Data for August updated in wave Transformation works in MV9 are going well as expected, and will be finished in two weeks times (closer to end of September). Nevertheless MV9 has been increasing the use of pallets. Week 33 v2 Initiative has been approved to pass to L5 by POD Lead and POD Finance During week 34 will work out the process of transforming, sign out and next step Week 33 Month of July has been updated in Wave. Works will start in MV9 during week 34, and will take place for 6 weeks. DE still uses repositioning costs and there is no response on my requests when MD is not involved. SE had a repositioning truck last week reported Weeks 30 to 31 Results are behaving steadily : Germany keeps on using trucks to reposition cages under ERN cost, rather than under Country (DE is repositioning cages to Customers exporting) or Air Ops (DE is repositioning cages into Airports for loading purposes). In one hand, the cost is the same BUT not placed where it belongs... on the other, this initiative is a transformation of the way we work. This is been followed by every country except Germany MV9 keeps the plan and we expect by the end of August, to replace all points of building cages into points of building pallets. Weeks 24 to 29 Best results and lowest repositioning costs since we started, WoW. Only Germany is still using cages for processes related to Air. Still don't understand why this practice has not stopped. Will revise with POD lead on HO Return Week 23 Very good series on results for May with highest saving in repositioning and lowest use of trailers (by eliminating long distance repositioning. Great focus from the team and keeps accelerating. Though we needed to delay project for 5 months (delays on floor marking in MV9) the net savings achieved since started goes up to $1.7M. Based on the net recurring benefits of $M1,02 in the first 12 months , we achieved $M1,13 Week 22 Due to several constrains along the way in France during L4 process (Unions approvals, CLEAR, engineering and re-engineering, etc) our touchstone MV9 Hub, will only have the floor marking and lay out by the end of July. (9 weeks of delay) I have no choice other than requesting delaying L5 step (latest milestone 67770) for the second week of August (week 33) This will allow MV9 to finish works, and at least have a week and start seeing ROI. At the same time we could closed milestone whilst updating July results on wave. Request has been accepted by DRIVE Finance (Nigel Belfield) and ERN POD Lead (Mark Timmermans) Weeks 19-20 Positive trend is confirmed with savings on repositioning. (€ 572,2K YoY) Nordics need to consolidate latest actions and impact of FR on Hubs/countries around will be mitigated once floor marking is done in MV9 (Mid June 2024) Final milestone (#67770) is late and needs to be revised. Week 18 April updated in Wave. Nordics results confirms working in the right direction. MV9 feed-back on expected dead-line remains (beginning of FY25) By this Thursday on next POD Stand-up meeting, the decision needs to be taken on delaying final MS. Week 17 Final Milestone #67770, has due date May 1st. Serious doubts we can achieve ir on time. Nordics : *Estimated dead line 23/05/2024* (67% of reposition cost left) confirms stop using cage with exception of DG) Great news. Moving our cages stored and cages to be scrapped with take 2/3 weeks to see cost reduction MV9 : *Estimated dead line 31/05/2024* Impact repositioning cost effect on Hubs surrounding Minor saving expected; NL , DE, BE Week 15 Nordics (SE,NO,DK,FI) is in the final push to remove cages as loading device. Pending on how NO, DK, FI can manage. MV9 Working on the plan for floor marking before end | K: L5 | Completed | L5 | 2022-11-21 | 2024-08-12
Business w/ Tech Initiative: Introduce Sort Time Windows | 370 | 8908 | Business w/ Tech Initiative | EU - ERN | Europe | Ben van Camp, Robert Higgins | On Track | Update 2-10: Workshop planned for 11-Oct with Road and Hub P&E to identify any remaining key blockers. Adjustments can be made to the model at that point and then we can move forward with GOPS and Field P&E validation. Update 11-9: Confidence in delivering value on time: Medium Confidence in delivering the full value: High Update 4-9: Continued impact of domestic volume into the model Push to finalize labor impact by middle of September for LR handover Update: Staffing plans have been created for the majority of the RTHs. Data is being compiled to update our business case and ensure there is no revenue leakage by pushing the money step to May '24 Presented new timeline to NS Steerco on 28-7. New timeline will start ramp up in Feb 24 with completion in May 24. Delay is caused by other competing initiatives creating a resource constraint on P&E. Revenue leakage is not expected, current staffing plan milestone is being conducted to verify potential savings. | K: L5 | Active | L5 | 2022-11-08 | 2025-03-31
Business w/ Tech Initiative: Magnus 2.0 | 371 | 8919 | Business w/ Tech Initiative | EU - ERN | Europe | Stefan Breuer, Anabell Cordero Rovelo, Jan Maarten Braaksma | On Track | 03/13/2026 following actions completed to prep for L5 submission: * impact & KPI forecast updated based on current runrate and future outlook (Sponsor approval received in week 11) 04/06/2024: moved back on track 1.) dependency milestones added to reflect money step Milestones from ALPHA and Segregate P/F. These are expected to drive value for load factor improvements, which are tracked combined under Magnus 2.0 as of FY25 2.) #369 added as enabler for Magnus 2.0 3.) L5 date rescheduled - aligning with money step/dependency MS date from #369 4.) Forecast updated as of FY25, as per the agreed approach to combine Load factor impact tracking of Alpha, Segregate P/F and Magnus with no change to overall FC for ERN POD 03/05/2024 L5 progression is at risk due to consolidation of Load factor impact from several initiatives within the ERN POD (ALPHA, P/F & MAGNUS). Discussions to finalize recommendation for future solution and next steps scheduled for upcoming week. 10/11/2023 reason for status change to some issues: Risk for completing Milestone for MVP1 sign-off (Milestone #38896) As where we stand today, the risk is very high, that not all items that we consider to be crucial for value delivery which is expected from the MVP version will be closed on time by this Friday. Hence Initiative status changed to “some issues”. Tomorrow end of day, we will have more clarity on the exact number of items left over and estimated time for resolution, based on which we will determine the way forward for the Milestone. 09/18/2023: Engaged with Key users identified for MVP1 Testing Phase 3; Onsite Workshop Planning for Key user group 09/04/2023: Milestone Planning for MVP1 UAT and sign-off added to accommodate for Data validation and key user acceptance testing and feedback loop to gather development topics for ROAD 2 MR1 08/22/2023: Confidence in delivering value on time: Medium Confidence in delivering the full value: High 08/15/2023: Testing for Data quality for MVP1 is not completed. Main topics: 1.) Data inconsistency identified for historic ROCS movement data, issue has been isolated to come from data transfer to dAtlas, to be verified and resolved (similar issue as flagged for ROAD1) 2.) apart from the above, testing is continued for other areas of MVP1, current state is that testing for approx 75% of the first (out of 4 layers) completed, iterative process for resolution ongoing. In general testing takes longer than expected due to high complexity and since no minimal testing before MVP1 handover, testing efforts higher than planned. 31/07/23: MVP1 dashboard was delivered on 28/07 for testing. Following week testing will be taking place for feedback to Dataworks and to confirm complition of Minimum viable product 19/07/23: Back on track to deliver an MVP1 solution by July 31. For MVP 1, DW will manually upload the load factor and forecast dynamic tables to build the new ROAD 2 dashboard. Later on, for MVP2 (still to be added to a timeline) the ingestion of these dynamic tables will be done automatically. 16/06/23: re-gained confidence in DW product management to deliver MVP, however visibility/transparency concern not fully resolved, hence status moved to some issues 24/05/23: Leadership support is needed, because of the concerns in regards to lack of visibility/transparency on the product development from Data Works and lack of confidence that the MVP is going to be delivered in time to generate expected value revised Milestone planning from DW means a delay of Delivery of Magnus 2.0 product vs initial planning which puts activation of money step and impact calculation at risk 03/09/23: Alignment of Milestones DW vs WAVE pending final confirmation of revised DW timelines, which is to be confirmed before we can have the status moved back on track | K: L5 | Active | L5 | 2022-11-11 | 2025-06-30
Business w/ Tech Initiative: Segregate Freight and Parcels | 369 | 8930 | Business w/ Tech Initiative | EU - ERN | Europe | Gaurav Jain, Ben van Camp | On Track | Update 20-12: Initiative is completed. Last milestone was linked to STW (Sort Time Windows) which is now handed over to operations. IT work was completed in Mar '23, seeking a link to add to planview to show completion (no sharepoint found at this point). Freight-Parcel reporting is a part of Magnus 2.0. Money step evidence is the completion of STW control tower governance, which was completed 31-10. Road network change stabalization was considered completed. Update 11-9: Confidence in delivering value on time: Medium Confidence in delivering the full value: Medium Update 9-4: Continued work on first roll-out of option code in November Led by Road P&E, lanes where orange is faster than purple will be slowed down Need to align on specific lanes to assess hub impact and prepare sort rules in uDS Update 31-7: Major changes related to the rollout of the new option code won't take place until the new year. This will follow the marketing communication go-to market strategy for multiple initiatives (STW, Tri-Color, One World, etc.) POC lanes have been identified (VIE <-> IMR), awaiting OK from marketing. Update 8-5: IT solution should be in place by end of week. Alignment with Magnus 2.0 and LH team on tracking taking place this week Update 1-5: Estimated IT solution delayed by ~ 2 weeks. All change requests have been created and being followed up on by the proper teams. No long term issues identified, simply the fixes that are needed to address isssues unrelated to the HWT option code. Update 24-4: An issue was identified with NSL21 which the new HWT option is linked. NSL21 is for road but was being assigned to air in the NL causing packages to show routing to an air hub. This wasn't just for HWT shipments but only noticed once the option code was added last week. Error was with PHI (parcel handling instructions) and not in the label. Estimated packs impacted were estimated at 500-600. Rollback of some of the system changes that had taken place over the past weeks was executed on Friday. Now NSL21 is linked to road but to reactivate the roll-backed systems will take 2-3 weeks. Successful IT system deployment that have taken place in the past 2 weeks: •ExpressLabel •Collection Booking service •ExpressConnect Pricing •ExpressConnect Shipping •EDI Services – micro service Upcoming deployment for the remaining 3 EAIs •MyTNT2 : 17th April •CCD: 20th April •ITIH : 24th April | K: L5 | Completed | L5 | 2022-11-02 | 2024-12-20
Business w/ Tech Initiative: ALPHA - Advanced Load Planning and Hub Application | 372 | 8941 | Business w/ Tech Initiative | EU - ERN | Europe | Gaurav Jain, Ben van Camp | On Track | 03/06/2024 - L-Gate progression has been updated with new milestones and L4 dates based on agreement with all parties. 03/05/2024 - L-Gate progression for ALPHA to L4 is at risk due to the consolidation of load factor reporting between the initiatives within the ERN POD. Discussions to continue next week to finalize recomendation for next steps. Great work from Dataworks/IMAGE teams last week to get the access issues to ALPHA resolved. We have now given access to 1700+ users as of last week. Thank you to the entire teams for their efforts to solve this issue. 31/10/2024 - Delaying milestone by one week due to some last minute technical issues that need to be corrected, new date will be 08/11/2024, approved by POD LEAD and milestone date updated. Confidence in delivering value on time: Medium Confidence in delivering the full value: Medium | K: L5 | Completed | L5 | 2022-11-21 | 2024-11-08
Business Only Initiative: LH - Competitive tender - Italy Dom & Intl | 2981 | 8948 | Business Only Initiative | EU - ERN | Europe | Patrick L'Allemand, Lukasz Milewicz | On Track |  | K: L5 | Completed | L5 | 2022-06-15 | 2024-01-02
Business Only Initiative: LH - Competitive tender - Northern and Central Eur | 2983 | 8950 | Business Only Initiative | EU - ERN | Europe | Carl Bridgman, Lukasz Milewicz | On Track |  | K: L5 | Completed | L5 | 2023-01-10 | 2024-04-01
Business Only Initiative: Magnus 1.0 | 376 | 8952 | Business Only Initiative | EU - ERN | Europe | Stefan Breuer, Anabell Cordero Rovelo | On Track | 09/29/2029: All actions completed to move to L4, submitted to POD Finance for L4 checklist test. Monthly Impact & KPI actuals will continuously submitted by IO, using the Magnus Scorecards for Financials, ROLLS for Load Factor & FP&A monthly volume and cost report for Unit cost 09/04/2023: Objective setting and Prioritization of business value for ROLLS MR4 completed 08/22/2023 Confidence in delivering value on time: High Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2022-10-03 | 2023-10-31
Business Only Initiative: LH - Competitive tender - France | 2984 | 8953 | Business Only Initiative | EU - ERN | Europe | Thomas Dietsch, Kris Tammel | On Track | uodate as requested by FP&A | K: L5 | Completed | L5 | 2023-09-01 | 2024-09-19
Business w/ Tech Initiative: Decrease empty trailers from volume imbalanced cou | 378 | 8963 | Business w/ Tech Initiative | EU - ERN | Europe | Marija Jelic, Marisa Martin | On Track | Confidence in delivering value on time: High Confidence in delivering the full value: High - Cost calculation is adjusted. Cost per km for On-Ways using subco (masterplan) is frozen as at the moment LOCs are not doing much with Tour switching. If they do start again , we will revise the cost. Cost is very volatile in this group (as it is really small) and many external factors (not related to this project) can trigger it. - Actual Impact (Benefit) of March 2024 has been adjusted (increased benefit) because we were underestimating benefit value for the whole year because in Baseline calculation 2 months of already achieving value is taken into account. - Forecast for months April and May 2024 are adjusted to reflect year on year value (decreased benefit). Actuals will also be adjusted once available. - Final yearly value is almost the same , it was only phasing that we wanted to correct for. - KPIs are not adjusted for the phasing but actuals values are being reported. - Benefit and Cost Forecast for FY25 is also adjusted to reflect same phasing methodology. - March 2024 Impact was adjusted to recover benefit ( so higher value is reported than actually is) that was not included in reporting as project started in April 2023 and we used full year FY 23 values for Baseline. - April and May 2024 Impact were corrected for the more correct year on year monthly view (so lower value is reported than actually is). - August results are low, that is probably because of implementation of STW. Total kms actually dropped a bit in August abut empty kms grew. It will take some time for LOC to re-optimize new schedules and get rid of empties where possible. Hub to hub schedules changed completely and some station to hub had to follow as well, so change for LOC s was very big. IN next 2 months we will actually see full impact of STW as FR will go live end of September and UDE operations will be completely closed by end of September. Then some months after that I expect that LOCs will be able to optimize better their schedules. | K: L5 | Completed | L5 | 2022-10-03 | 2023-11-30
Business Only Initiative: Fuel card rebate discounts (Int - EU) | 3026 | 8967 | Business Only Initiative | EU - ERN | Europe | Chaka Conway, Amber Bonacci | On Track | On Track | K: L5 | Completed | L5 | 2022-12-02 | 2024-06-19
Business Only Initiative: Improve Load Quality | 379 | 8974 | Business Only Initiative | EU - ERN | Europe | Stefan Breuer, Anabell Cordero Rovelo | On Track | EBWEBWEBW: please see attachment #7 for detailed description how monthly impact is computed (aligned with POD Finance) 09/22/2023: Milestones for OPS Trainer certification and scheduling of LQ Training modules completed, in line with the communication of the Handler program launch 09/04/2023: With having actions to fill OPS Trainer positions and to launch load quality training modules initiated and keeping track of progress, Initiative is moved back on track 08/22/2023: Confidence in delivering value on time: Low Confidence in delivering the full value: High 08/15/2023: With 2 certification sessions held last week, now 45% of total required Trainer FTE's certified. Recruitment completed for 65% of required FTE's. Recruitment process for following countries delayed due to either works council or candidate not confirmed within the first interview wave: 1.) France (4 open positions. No successful candidates, more interviews running), 2.) Germany (works council negotiation ongoing), 3.) Italy (2/6 OT are not identified yet, recruitment ongoing). 07/08: Overall number of OPS Trainer identified, increased to 83%. Number of trainers certified remained unchanged. 2 Certification sessions setup to activate in Poland and France this week. As of today 12 out of 54 regions across Europe ready to execute trainings as of the week of August 14th. 28/07: Weekly status adjusted to "Some issues" as the identification and certification of trainers will be delayed. There is a plan from L&D to do certification for identified trainers in different waves but we still havent reached the planned numbers. As of today 79% of trainers have been identified, and 28% certified. 13/07: Adjusted the forecast as agreed; July 2023 now shows as zero and transferred that value to be delivered June 2026 per the delayed milestones timelines (AC). 16/06: with rescheduling L4 date, to be managed by revised milestone planning for OPS Trainer concept towards new L4 date, Initiative is back on track 25/05: Initiative status changed to some issues due to a delay expected in the implementation of the OPS Trainer model as key enabler for Loading Quality Training delivery 31/03: Loading Quality Guidelines finalized, covering all required elements to support good loading practices. Guidelines handed over to L&D to be incorporated in Training modules/curriculum. Milestone 22150 completed and Initiative moved back on track 21/03: Loading Quality Guideline Draft document presented from methods & standards team, which contains a reference to achieve higher Load factors, however fundamental elements defined from Business owner missing, which need to be worked on, hence Milestone 22150 remains open 03/09: currently the milestone for the creation of Loading Guidelines is at risk, which has implications for the achievement of the following milestones. The reason for this is that there is a lack of clarity within the organization as to which area is responsible for creating the Loading Guidelines to achieve maximum utilization of LH units. continued work with L&D on Training elements | K: L5 | Completed | L5 | 2022-11-01 | 2024-04-24
Business w/ Tech Initiative: WS1 1C UK Domestics into MAGNUS - 1 | 82283 | 8985 | Business w/ Tech Initiative | EU - ERN | Europe | Gaurav Jain, Jan Maarten Braaksma | Attention Needed | 31/10/2024 - IT work still being done and has not finished therefore Milestone 4 is still open and delayed. 11/11/2024 - Milestone 3 is still being actioned by the ground teams in the UK, but will take longer than the planned end date 11/11/2024 - Milestone 4 is still being actioined and the IT teams are working on the solution to enable the data flow. 22/11/2024 - Milestone 3 is still being actioned by the ground teams in the UK, but will take longer than the planned end date 22/11/2024 - Milestone 4 is still being actioned, waiting to hear who the IT owner is for this and what the current status of the milestone is. 05/12/2024 - Milestone 3 continues to be actioned, but with the planned rollout of DH2 scanners in the UK to all stations by the end of FY25, then we need to consider changing this milestone as that is the realy end state solution for volume to transfer to LVT/MAGNUS, current milestone is temporary solution as there was not initial view on when DH2 would be rolled out 05/12/2024 - Milestone 4 is still being actioned, but still no word on the owner of this from a Tech side and what the current status for resolution to this is 05/12/2024 - Overall with the delay in the ability to not start the tender process till February 2025 and it being a 6 month long process, then overall we need to look at adjusting the date for this to September 2025 to align with this change as the value can not be realized until a full new schedule is implemented. 29/09/2025 - Milestone 3 is still being actioned by the ground teams in the UK, but will take longer than the planned end date, no new date available 29/09/2025 - Milestone 4 is still being actioned, IT work is not completed and it has been raised as a concern as no one is specifically assigned and the work has not been completed. The issue is with Joram on how to address the issue of data not flowing into the system correctly for MAGNUS to work correctly 29/09/2025 - Money Step mileston shows as in progress as the new GBD schedule is going live today, that is despite the IT piece not being completed. The initiative will realize monetary value, but the IT piece has not been completed. The optimisation was done manually which does not achieve the objective of it being within the framework of MAGNUS to be actioned on a daily/weekly/monthly basis. 20/04/2026 - All items remain on hold as no one person has been assigned to this project to address the underlying issues of why the data is not flowing into MAGNUS. This not only affects this particular initiative but also affects all data flow in all locations. If the underlying issue of the data flowing correctly is addressed it will solve many different data flow issues for the network as a whole. This requires one person to be assigned to manage thru the different groups to address all the different issues that cause this. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-03 | 2026-05-01
Business Only Initiative: Collapse WEX Network in Germany | 6588 | 9008 | Business Only Initiative | EU - ERN | Europe | Stefan Breuer, Anabell Cordero Rovelo | On Track | 01/15/2025: with all actions executed, Initiative is ready to move to L4 12/18/2024: cancelling the planned execution of weekend sort optimization in Hub HNJ due customer's Takko volumes requiring weekend sortation changing the situation to not feasible to implement. Corresponding milestone 26649/55863 is cancelled and forecast the updated to reflect the value leakage of -0.36m$ (-0.15m$ impact for FY25). 12/06/2024: execution of weekend sort optimization in Hub HNJ will not be executed as per plan by Jan 1st 25. Reason for this is that additional volumes (8-14 Inbound Trailers on Saturdays) from Takko Direct injections are early sorted during the weekend, to prevent Hub Ops process and service disruptions, if these volumes were sorted Mondays only. This entirely changes the situation in terms of optimization opportunities. The execution is on hold which is also a risk to move to L4 as per plan. Plans will be re-assessed in week 50 and adjusted based on the outcome 06/04/2024: current state of execution progress of weekend sort optimization in Hub locations DFT & HNJ is behind plan with expected negative financial impact vs forecast for May and June 03/18/2024: assessment of mitigation options to limit delay of execution in Hubs due to current social unrest and strikes completed; DFT execution plan has to be adjusted to cater for 2 months postponement with an estimated value compensation through a change of ratio towards higher reduction on flex working hours (less impact on fixed contracts to mitigate LR related delay) - status change 'on track' 01/22/2024: we are experiencing a delay in local LR process to execute weekend sortation optimization in Hub HNJ, which is a risk for on-time execution of the business case element, hence status changed to some issues. The situation is currently assessed in order to see if mitigation is possible. 09/19/2023: Confidence in delivering value on time: Medium Confidence in delivering the full value: High | K: L5 | Active | L5 | 2023-09-25 | 2025-01-15
Business Only Initiative: LH - Competitive tender - Central Europe Wave 1 | 4431 | 9026 | Business Only Initiative | EU - ERN | Europe | Kris Tammel, Lukasz Milewicz | On Track |  | K: L5 | Completed | L5 | 2022-08-15 | 2023-12-19
Business Only Initiative: WS3 Purple Priority by Road | 82285 | 9275 | Business Only Initiative | EU - ERN | Europe | Jeroen Lamers, Michael Cusack | On Track | 27/08/2024- As approved, milestones and timelines have been adjusted; while keeping the forecasted L4 date. The milestones are now more granular and limit the scope to stations with DH2 deployment. Roll up will now be planned in 3 different phases ECH has also now been given green-light 13/06- Buisiness case and Baseline updated to verified values as per bellow: The are curently 463 IP purple pieces (OCT-NOV 2023 ave.) moving by air that have been identified as eligible to move by road, while mainiting express service. Rerouting these, would bring handling cost benefits at the air hub and gateways side but will bring additional handling cost on the road side. Considering 4.52 $/piece for an air hub, 1.54 $/piece for a gateway and 0.96 $/pieces for ground/road transit hub we determined a benefit of 145.567 $/year (value considering flex down % provided FP&A). 3/09/2024- Approved by Finance and POD coach , ready to submit to L3 18/11/2024- submitted actual KPIs and adjusted service performance forecast & baseline as agreed when submitting into L3. Values now reflect Sept and Oct MBG% for lanes in scope for DE-FR 04/02/2025- due to complexities on the PHX system set up roll out has been delayed and we are currently working on new timelines to ensure full project delivery 07/02/2025- A new delivery plan has been drafted and approved. Milestones, L-gate delivery dates and Risks have been adjusted accordingly 08/09/2025 - All objectives (i.e. implementing all lanes in scope) have been reached. That means that as of Monday 1st September, 1.371 (currently carrying +80% of all orange priority by road within the road network) haven been opened up for purple as well. Purple systems have been enabled, allowing purple priority shipments, parcels and freight to follow the same by-road routing instead of Air. Expected L5 step: as of January 2026. | K: L5 | Completed | L5 | 2024-06-17 | 2025-10-06
Business Only Initiative: Road Hubs Future State | 22998 | 9492 | Business Only Initiative | EU - ERN | Europe | Robert Higgins, Prajwal Bhat, Damjan Ivanovski, Lars Paeschke | Some Issues | 21/10/2025: L5 estimated date Jul 2026. 1 milestone to complete which does not impact money step: EDP Deployment Confidence in delivering on time: Medium Confidence in delivering value on time: High | K: L5 | Active | L5 Feedback Requested | 2023-06-01 | 2026-06-26
Business Only Initiative: LH - Competitive Tender Iberia | 65567 | 9500 | Business Only Initiative | EU - ERN | Europe | Kris Tammel, Lukasz Milewicz | On Track | Intiative is ready to be submitted for L5 as it has 3 months of mature realized benefit. | K: L5 | Completed | L5 - Restarted Initiative | 2024-06-24 | 2025-02-19
Business Only Initiative: International rebate for forklifts | 41848 | 9521 | Business Only Initiative | EU - ERN | Europe | Kyle Mitchell, Gergana Kacheva | On Track | chanding IO due to previous IO leaving FedEx | K: L5 | Completed | L5 | 2023-10-30 | 2024-01-15
Business w/ Tech Initiative: RO eTransport compliance - Data requirement |  | 90829 | Business w/ Tech Initiative | EU - ERN | Europe | Martijn Koker, Rene Vedder | On Track | Preparing for L2 gate; process, relevant data to be gathered and architecture drafted and undergoing checks. | E: L2 | Active | L2
Business Only Initiative: LH Extra and Adhoc Europe Wave 1 |  | 94279 | Business Only Initiative | EU - ERN | Europe | Kris Tammel, Lukasz Milewicz | On Track | Estimated L5 date is 15th of Jan, 26 | K: L5 | Active | L5 | 2024-11-01 | 2026-10-01
Business Only Initiative: WS3 LGG Loose Unload 2.0 |  | 96326 | Business Only Initiative | EU - ERN | Europe | Stefan Van den Berg, Alizee Cogez | On Track | Mar-12th 2026:Update actuals of Feb Feb-12th 2026:Update actuals of Jan Jan-12th 2026: Update actuals of Dec Nov-12th: Update actuals of Oct Oct-7th: Update actuals of Sept 08-Sept: Financials Aug updated. Implementation set on hold as there is an issue with the height of the first installed boom (initiative WS3 LG Loose Unload) 08/11: Financials are adjusted 07/04 : CLEAR approved 26/03 : checklist and feedback request check done - submitted to L3 05/03 : submitted to L2 11/02 : reached L1 stage | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-14 | 2026-04-30
Business Only Initiative: LH RBT Competitive Tender 2025 |  | 96331 | Business Only Initiative | EU - ERN | Europe | Lukasz Milewicz, Kris Tammel | On Track | 2026/02/23 - Initiative on track, there are no actions to be taken 27/04/2025 - (ref Money Step) •#25 Suppliers have been awarded out of RBT tender . The contracts with those suppliers were already extended in Dec 25 until Dec 27 because the contract includes the overall lanes so only RBT lanes are applicable with a single subcontractor. •As evidence of new prices kicking in from 1st April 24, attached are the CRF (Change Request Forms) for Jan de Riijk and Kuijpers which represent collectively 66 % of the total volume and 53% of the awarded total spend. Change Request Form is Fedex Template to change prices in FCF Ready to submit for L1 - 13/02/2025 Additional user added - Lukasz Mikiewicz - 12/02/2025 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-18 | 2025-06-27
Business Only Initiative: EMR - LH Italy Dom. & Int. Competitive Tender 2025 |  | 104305 | Business Only Initiative | EU - ERN | Europe | Kris Tammel, Lukasz Milewicz | On Track | Ready to be submitted to L5 - at least 3 months of mature benefits reported | K: L5 | Active | L5 | 2025-05-12 | 2026-09-28
Business Only Initiative: EMR - LH Competitive Tender-BLX+DE+Nordics+Baltics |  | 107099 | Business Only Initiative | EU - ERN | Europe | Min Lu, Kris Tammel | On Track | 14/04/2025 - Baseline and assumptions are validated by FP&A. Baseline was calucated on FCF actual price (FY25) - Master Plan (Volumes) dated 01/07/2025. Contracts have been signed and FCF pricings have been adjusted via CRFs according to tender results. It's ready to move to L4 dated 17/12/2025. New rates will be effective from 12/01/2026. Expected date of moving to L5 will be on 30/04/2026. | I: L4 | Active | L4 | 2025-08-11 | 2026-04-13
Business Only Initiative: EMR - LH UK Dom&Int Competitive Tender 2025 |  | 107102 | Business Only Initiative | EU - ERN | Europe | Lukasz Milewicz, Kris Tammel | On Track | 2026/02/23 - Initiative on track, there are no actions to be taken Business case is validated by FP&A and ready for submission 11/04/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-04-07 | 2026-01-20
Business Only Initiative: WS3 DNG Loose Load |  | 114423 | Business Only Initiative | EU - ERN | Europe | Stefan Van den Berg | On Track | Apr-9th 2026: Update actuals of Mar Mar-12th 2026: Update actuals of Feb Feb-12th 2026: Update actuals of Jan 26/09: Architectural Review in L1 took 8 weeks, risking the implementation not ready before peak freeze 2026 which results in extra delay 11/06 : reached L1 stage | E: L2 | Active | L2 | 2025-04-01 | 2027-07-30
Business Only Initiative: EMR - LH Germany Dom (Van/Airfeeder) Tender 2025 |  | 133115 | Business Only Initiative | EU - ERN | Europe | Min Lu, Kris Tammel | On Track | Baseline was calucated on FCF actual price (FY25) - Master Plan (Volumes) dated 29/04/2025. Contracts have been signed and FCF pricings have been adjusted via CRFs according to tender results. It's ready to move to L4 dated 05/09/2025. Expected date of moving to L5 will be on 19/12/2025 | K: L5 | Active | TEMP L5 - Enter L5 | 2025-05-16 | 2025-12-15
Business Only Initiative: EMR - LH Extra and Adhoc Wave 2 |  | 133128 | Business Only Initiative | EU - ERN | Europe | Kris Tammel, Lukasz Milewicz | On Track | Expected L5 date: 15th of May, 2026 | I: L4 | Active | L4 | 2025-08-18 | 2027-01-12
Business Only Initiative: GHFH Sorter Adjustment |  | 155232 | Business Only Initiative | EU - ERN | Europe | Juergen Kogure, Marc Schmitz | On Track | 07.08.2025 - Preparing L2 Move 01.09.2025 - Checklist and Feedback request with FP&A done, submission to L3 03.09.2025 - Added description to Money Step Milestone, re-submission to L3 08.10.2025 - BJD approved by all function. Project ID for CLEAR requested to Finance. Delay of Vendor award by 1 month to account for additional time needed for CLEAR. 06.11.2025 - CLEAR submitted for Approval. Updated version of the BJD uploaded to planview with new exchange rate. Impact of CLEAR delay on the overall timeline to be discussed with the vendor after CLEAR approval. 10.11.2025 CLEAR approved 08.12.2025 Vendor PO sent and kick-off with Vendor and internal stakeholders held. 12.01.2026 December Actuals updated, First Invoice received. On site meeting with Vendor planned for 01/2026. 28.01.2026 Project completion and Money Step Milestone postponed to 18th of May 2026. The delay was caused by the delayed submission of the CLEAR, Vendor material and resource availability and the easter holidays in April 2026. Milestone postponement aligned with ERN POD Lead. Final Rate to vendor also postponed to May 2026, since the payout is tied to completion of the project. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-25 | 2026-07-13
Business Only Initiative: Mega Trailers in Road Network Operations |  | 161063 | Business Only Initiative | EU - ERN | Europe | Wouter Kamp, Cosmin Coman | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: LZV project |  | 162585 | Business Only Initiative | EU - ERN | Europe | Wouter Kamp, Cosmin Coman | On Track | 13/11/2025 working on business case. | E: L2 | Active | L2 | 2025-06-02 | 2027-07-30
Business Only Initiative: SKGA Station Modification Project |  | 169602 | Business Only Initiative | EU - ERN | Europe | Dimitrios-Agamemnon Christodou | On Track | On Track | G: L3 | Active | L3 | 2026-01-01 | 2026-06-01
Business Only Initiative: EU Trailer Asset Management |  | 187860 | Business Only Initiative | EU - ERN | Europe | Stefan Breuer | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Reduce churn France | 27333 | 6709 | Business Only Initiative | EU - France | Europe | Cedric Frenkel, Sandrine Mauras, Arnaud Desmiers | Some Issues | 1.We've lost 4 months with Puzzle on 2 of the main subjects (mpup & On the Road Excellence) and we've got the Olympics coming up until September 9. 2.The onboarding POC shows that we need IT development. With Forward, IT support is not a given Therefore, we will ask to change de L4 date. | G: L3 | Completed | L3 Data Migration - TEMP | 2023-11-10 | 2024-07-31
Business w/ Tech Initiative: Ops Tech Mobile - Lifecycle Replacement France | 83029 | 7701 | Business w/ Tech Initiative | EU - France | Europe | Florence Altamura, Romain Bugand, Damir Babic, Vasile Catalin Turta | On Track | * Order placed in December following quotations received * FOPD : France placed order in December 2024 for € 6 141 584 * SORT : France placed order in December 2024 for € 480 844 * Invoices received, forecast CAPEX & OPEX updated * Deployment plan under validation * FOPD : Application on Android 13 delivered and tested. Pilot in April, then rollout will normally start on the 23rd of June till September - TBC * SORT : Application on Android 13 not yet delivered | C: L1 | Completed | L1 Feedback Requested | 2024-07-22 | 2025-10-02
Business Only Initiative: Get smaller PUD subcontractors by changing depende | 11481 | 8029 | Business Only Initiative | EU - France | Europe | Yves Ferrand, Sylvie Babel, Cedric Frenkel | On Track | Confidence in delivering value on time: HIGH Confidence in delivering the full value: HIGH Initiative on track, monitoring is performed on each opportunity of cost saving with smaller PUD subcontractors. The gap with the first objective is due to 1 - change of context in France : the will to stop contracts pro-actively to seek for smaller subcontractors was reviewed due to the legal context with some former subcontractors. The legal risk was too high to stop the contracts without a valid reason (change of customer, optimization...) 2- impact of PUZZLE : all the exFRD contracts cannot be taken into account as they are extended until PUZZLE deployment. There is no possible opportunity on these contracts 3 - Impact of TNT end of day initiative : the impact of this initiative is not taken into account for now as the starting date and impacts are not fully defined yet. We can expect a positive impact as some contracts will have to be reviewed and we will be able to look for smaller subcontractors then. | G: L3 | Completed | L3 Data Migration - TEMP | 2022-12-01 | 2025-06-12
Business Only Initiative: Implement Under Achiever process for all contract | 11166 | 8057 | Business Only Initiative | EU - France | Europe | Geraldine Rolandez, Thomas Murena | On Track | Actual KPIs will be filled in for Jan-Feb-March with the target as we will calculate the actual every Quarter => in April for Jan/Feb/march Analysis on going to finalize rules for the next wave of CPR/UA => will have to be finalized end of june Confidence in delivering value on time: [lHigh] Confidence in delivering the full value: [High] New rates activated in January 24 as planned Ready to submit : L4 submission planned A follow up will be done monthly | K: L5 | Completed | L5 | 2023-08-16 | 2025-01-08
Business Only Initiative: Optimize the station footprint (UROA Closure) | 11164 | 8406 | Business Only Initiative | EU - France | Europe | Benoit Lambert | On Track | The move of the operations staff and activities was completed successfully on March 1st as per plan. The refurbishments works are on-going | K: L5 | Completed | L5 | 2022-06-22 | 2023-06-02
Business Only Initiative: Reduce non-resources COST | 11156 | 9139 | Business Only Initiative | EU - France | Europe | Rémi Bidilié, Cedric Frenkel | On Track | 2024 July 8th : Preparation to move initiative to L5. Attachment #5 for proof of savings. As it is a saving initiative based on invoices received, yearly status is more accurate than monthly. Yearly FY24 vs FY23 saving is : 1.3m$. Confidence in delivering value on time: high Confidence in delivering the full value: high April 04th Update : We are having incremental cost which need to be offset from the general saving - Puzzle project : Modis : Incremental 100k€ for FY24 Orange : 50k€ for FY24 HubOne : 100k€ for FY24 Composite Network : 100k€ for FY24 All the above impacts the net spend with those providers negatively of 0.4M$ There is also double counting on Modis provider in FIT Europe Drive initiative of 200k€ yearly on FY24. This will be removed from this initiative, so forcast is going to be 200k€ lower. January 2024 29th : FY22 Baseline changed from 26 to 13m$ (half of the providers changed or no action possible). Total savings : FY23 vs FY22 = 989415 $ FY24 vs FY23 (projected) = 2m$ Ready to move to L4 status. List of providers for which spent was reduce or contract renegociated : DELL SAS : spent reduced HUB ONE : spent reduced ORANGE : Contract renegociated EVERIAL : spent reduced KYNDRYL FRANCE : spent controlled MODIS FRANCE : Contract reviewed, service and spent reduced. Attachment #3 : Excel file with cost YTD end of december 2023. Projection on FY24 (projected known cost over the full year) shows a reduction of 2.5m$ vs FY23. Final savings will be known at the end of FY24 and will land around 2m$ if we take into account late invoices and some contingency. Attachment #4 : Cost spreadsheet for "Orange" network cost before and after contract negociations. August 15th : Actuals have been update vs FY22 because rebaselining has not been uploaded in wave. with new conversion ratio (eur/dollar 0.91) which is why the actuals are below forecast. April 21 : No major updates. Still in line with objectives April 7: Received FP&A results. Results are still slightly above target. March 24 No major updates. Still in line with objectives March 2nd 2023 Invoiced actuals received from FP&A. Actuals are now updated in Wave impacts slightly above expectations. Feb 2023 Actuals reporting has been requested to FP&A but not received yet. Initiative is well on track but actuals will be updated against finance reporting once received. | K: L5 | Completed | L5 | 2023-01-16 | 2023-12-29
Business w/ Tech Initiative: Introduce new domestic service portfolio, rebalanc | 11160 | 9142 | Business w/ Tech Initiative | EU - France | Europe | Audrey Cheikoussen-Leble, Romain Cauquil, Cedric Frenkel | On Track | 1) Confidence in delivering value on time: [HIGH] 2) Confidence in delivering the full value: [HIGH] - Business case update has been shared and updated - Planning is on track allowing the Project to move forward - IT timelines are clear and product availability is Mid November vs a pre-sell period starting in September - some challenges currently being addressed - decision required to Prioritize EOD vs HC - It has been confirmed that WC information will be October 4th to present the reopening of the EOD product for Sales | G: L3 | Completed | L3 Data Migration - TEMP | 2023-01-09 | 2024-04-30
Business Only Initiative: Improve French overseas territories value prop | 11162 | 9143 | Business Only Initiative | EU - France | Europe | Cedric Frenkel, Samson Roland Ohouens, Farid Medjahed | On Track | 2023-10-16 Monitoring sept: •1879 parcel in September, + 1 pack PPD vs 2022 •NSL: 72% vs 69.5% in 2022 2023-08-24 Confidence in delivering value on time: Low Currrent result are below baseline since FY23, it might take some time to fill the gap. Confidence in delivering the full value: Medium As we are at an early stage, we will monitore closely the coming months to see if the impact is in line with the expected value. 2023-07-28 New pricing structure clear and in place (WREG, G1R, EMBP) Go to sales launched on july 21st (internal comms) Prospects leads loaded to Telesales (wave 1) Customers leads loaded to Sales Beginning of the selling period | I: L4 | Completed | L4 | 2023-02-07 | 2023-10-31
Business Only Initiative: New Business & Acquisition DOM B2B | 11175 | 9148 | Business Only Initiative | EU - France | Europe | Cedric Frenkel, Cyril Carli | On Track | Level of confidence to deliver full value on time : Medium Good result over the last few months and ahead of schedule for FY25 results New forecast implemented on Nov 19 with a slight drop in FY25 and a more important one in FY26 as France will be more focused on International business and will target to maintain current Domestic additional volumes more than keep growing as in original plan Nov 27, 2024 Initiative is checked by Finance and Coaches and is ready to move to L4 | I: L4 | Completed | L4 | 2022-12-05 | 2024-09-06
Business Only Initiative: Realize Puzzle initiative | 11487 | 9153 | Business Only Initiative | EU - France | Europe | Jasmine Khounnala, Benoit Lambert, Florence Altamura | On Track | - Confidence in delivering value on time: HIGH - Confidence in delivering the full value: HIGH FR Work Councils reelection will result in ending PZL consultation Sept. 28th instead of August 8th. Consequences are twofolds: - Go live date switching from beg of May to June 1st - One-off impact on MPLA lease up to 900k€ as we cannot terminate the lease on time and will restart for 3 years. This can be lower as we wait for Landlord's feedback to mitigate the impact (ongoing) Wave to be updated accordingly along with the ongoing rebaselining exercise | I: L4 | Cancelled | L4 | 2022-09-01 | 2024-10-31
Business Only Initiative: Optimize the station footprint (QFC closure) | 14163 | 9170 | Business Only Initiative | EU - France | Europe | Mariana Veras, Cedric Frenkel | On Track | QFC Building handover confirmed by the landlord (final report to be shared with FedEx) - Money Step Completed. MHE consctructor onsite last week (from Oct 13th to 17th 2025) to solve some punch list items and be able to sign the FAT soon. Ongoing works in the reception area. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-09-08 | 2025-10-01
Business Only Initiative: ACE execution | 29678 | 6753 | Business Only Initiative | EU - Integration Roadmap | Europe | Rogier van der Horst, Charlotte Brown | On Track | not needed for migration | C: L1 | Cancelled | L1 Data Migration - TEMP | 2023-11-13 | 2024-10-01
Business Only Initiative: Italy PUD stations integration | 31408 | 6798 | Business Only Initiative | EU - Integration Roadmap | Europe | Fabio Cavalleri, Giorgio Abrami | On Track | Completed | K: L5 | Completed | L5 | 2023-05-25 | 2024-07-01
Business w/ Tech Initiative: FedEx Print As You Go (PASGO) | 31919 | 6813 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Ines Moura, Matilde Quintas, Pip Fanning, Nicholas Forward, Ana Silva | On Track | Status 1st Oct 25; * FedEx API launch on track for 3rd Oct 25 * MAGIC/PFS to be added to a new Epic * L4 date to be moved to Sep 26 to account this change | G: L3 | Active | TEMP L3 - Enter L3 | 2023-10-23 | 2027-08-20
Business w/ Tech Initiative: Packing List Return Service iPFS | 61460 | 6902 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Celia Aguado Galarreta, Teresa Martinez | On Track | Submitted to L5 on 23/10 | K: L5 | Completed | L5 | 2022-01-03 | 2025-07-31
Business w/ Tech Initiative: Packing List Return Service PFS | 87556 | 6903 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Celia Aguado Galarreta, Teresa Martinez | On Track | 2026-03-24: * XPL developer support is required to: 1) deliver Purple PLR enhancements and 2) complete XPL microservice migration from GDOP to FedEx Azure. Current lack named XPL owners with code knowledge and GitHub access, following the original team's dissolution, and without this, ES Purple PLR cannot onboard high-volume customers - to avoid disruption to business in the process * Aligned with GDX US team on 23/03 and supported prioritizing a new work creation at Planview * 'COM - GDX - eIANS FedEx PLR Enhancements' (ID - Request: 0019262) new work created on 23/03 * Approved, already into L2 on 24/03 and moved to SL3 approvers to be included in the next PI _____ 2026-02-10: * FedEx announced on 09/02 a conditional agreement to take a 37% stake in InPost, indirectly impacting to PLR as last year InPost acquired Sending - Packing List Non-Network default Provider (NNP) * Requirement to migrate XPL webservices from GDOP Azure cluster, currently in use (fxi-001-eastus2-prod), to preferably an Azure cluster in the EU region (fxi-001-prod) w/John Duncan and Kranthi * WIP on enhancements / new features on XPL 2026-02-03: * Pilot was successfully completed and formally approved on 02/02 to proceed with customer onboarding * Next customers with strong migration potential: BIOMERIEUX (203667040) and/or PROMEGA (208320604) * Identified enhancements are being addressed with XPL team, with weekly governance starting next week * PLR EU Home article published on /02 highlighting the initiative * Reached ECM project leads and aligned with CLM team towards customer priorization 2026-01-15: * Kick off of Pilot FedEx PLR customer (KARL STORZ). PLR shipment done and correctly POD uploaded * Rescission of Cibernos contract on 31/01 to create savings * PLR as an enabler. Not setting migration timelines, but timeframes of service availability depending on the complexity 2025-12-23: * Pilot delayed due to external customer constraints (end-of-year inventory) until Jan 2025-11-18: * Internal announcement of the L4 strategic milestone achieved on 06/11 * First migration process completed by 17/11 to start shipping by Dec 01st * Training on XPL (+100 stakeholders) successfully completed among ES GOPS teams for FedEx PLR. All training assets are deployed. Survey showed +90% satisfaction on the training and solution among operational teams 2025-10-31: * MTP completed by 30/10 * Ops Senior Management and GOPS MD for Iberia gave greenlight on PL pilot by 31/10 * Submitting L4 2025-10-28: * MTP final date postponed from 27 to 28/10 on 22/10 by Idrees * PLR XPL Testing Ending on 23/10 * Production deployment completed on 28/10. Testing in Prod ongoing to be completed by 31/10 * Customer Pilot (mid Nov) on hold as per GOPS (Marise Rodriguez) blocker on 23/10. Excluded NNP areas and nationwide testing arguing operational constraints. Internal discussions along 23 and 24/10. MD (Rogier) intervencion by 27/10 and GOPS offering Malaga area as option to Pilot - insufficient * On 27/10, shared upper management communication and waiting for MD level recommendation on how to proceed as per the risk involved: 1) Momentum loss 2) Strategic imperative 3) Limited testing scope 4) Reduced flexibility 5) Readiness * F2F Karl Storz meeting on early Nov (on hold as per decision above) * Operational trainings set: live-demo of XPL + job aid (Nov 12-14, on hold too) * Ongoing Support Model definition (DPE) 2025-10-21: * MTP discussion on 14/10 and 16/10 as per delay on live-date w/ Idrees * Enhancement requirement discussion on 16/10 w/ Kranthi Gajula asking for commitment on Oct 31st readiness * UAT sign-off and validated the key fixes in the test environment on 24/10 * Proceeded with production deployment on 24/10 * MTP on 27/10 * GOPS alignment F2F meeting to detail internal training on 21/10 2025-10-14: * Still delayed as per issues/defects/ development work. Developed issue tracker w/ DPD-XPL teams to speed it up * Escalated the urgency to pri | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-01 | 2026-01-30
Business Only Initiative: Road Transit Time Integration Intra Europe C statu | 32603 | 6918 | Business Only Initiative | EU - Integration Roadmap | Europe | Jan Maarten Braaksma, Frank Wouters | On Track | 5/12/2024: satisfied with kpi. Ready for L5 submission “Confidence in delivering value on time: 100% “Confidence in delivering the full value: 0% (For C-status scope there will be for 99.4% of the orange shipment a transit time alignment between orange and purple, and for 0.6% the purple transit will be slower that orange, Italy purple bubble). Milestone #54785 LSSI update for last 0.8% will be done in same batch as LSSI update for Sort Time Window which will take place 2nd September 2024. With this the moneystep milestone has been rescheduled form 11/7/2024 to 2/9/2024. | K: L5 | Completed | L5 | 2023-06-01 | 2024-09-02
Business Only Initiative: Road Transit Time Integration intra Europe inbound | 32604 | 6919 | Business Only Initiative | EU - Integration Roadmap | Europe | Jan Maarten Braaksma, Frank Wouters | On Track | Ready for L5 submission. “Confidence in delivering value on time: 80% “Confidence in delivering the full value: 0% (for 97.7% of the orange Eco shipments ex GB to Europe it is expected that migrating to Purple will not have a slower transit time. For 2.3% of orange Eco shipments a downgrade is expected compared to current orange transit time) | K: L5 | Completed | L5 | 2023-06-01 | 2024-10-01
Business Only Initiative: Road Transit Time integration intra Europe outboun | 32605 | 6921 | Business Only Initiative | EU - Integration Roadmap | Europe | Stefan Van den Berg, Frank Wouters | On Track | 29-July-2025: Iniitiative is ready to be submitted to L5 27-May-2025: Adjusted 'Baseline Fiscal Year of Initiative' to FY25 iso FY24 14-Jan-2025: LSSI batch 3 went go live - Iniitiative is ready to be submitted to L4 7-Mar-2025: Milestones are updated | K: L5 | Completed | L5 | 2024-01-01 | 2025-01-06
Business Only Initiative: Road Transit Time integration intra Europe deferre | 32606 | 6922 | Business Only Initiative | EU - Integration Roadmap | Europe | Frank Wouters, Jan Maarten Braaksma | On Track | “Confidence in delivering value on time: 90% “Confidence in delivering the full value: 90% | K: L5 | Completed | L5 | 2023-08-01 | 2023-12-08
Business w/ Tech Initiative: ACE - Enable Proactive Monitoring & Intervention - | 64779 | 7066 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Graca Machado, Jessica Jaltem | On Track | 10/11/2025 - FP&A tests completed - Initiative ready to move to L4 - Initiative KPI changed due to the revamp of the customer relationship survey. FedEx is no longer measuring customer satisfaction. KPI is still obtained from the customer relationship survey, new version, and we are considering the Get Support problem incidence as a kpi. This is because the reports developed by this initative support the customer is getting the right information at the right time, decreasing the need to get further support from Customer Care. 06/11/2025 - Initiative to be moved to L4 on Monday, after the publication of the October KPI. 3/11/2025 - Trying to move the initiative to L4, EPIC was closed by Admin on Friday evening. 30/10/2025 - No change from last week. PDSM ticket still pending, no resolution yet. Escalaed to third level. 23/10/2025 - No change from last week. PDSM ticket still pending, no resolution yet. Escalation sent. 17/10/2025 - Still the same issues as the previous weeks. PDSM ticket has been closed with no resolution, reopened it and no resolution yet. 10/10/2025 - Still trying to move to L4, PDSM ticket is still under investigation 01/10/2025 - Trying to move to L4, there's an error when closing the EPIC, PDSM ticket raised 29/09/2025 - UAT succefully completed, report enhancements identified and logged for the next iteration - 5 customers onboarded, feedback to be collected for the next two weeks, to identify any potential enhancements - Initiative ready to move to L4 by Sept 30th 17/09/2025 - UAT is progressing successfully - Testing with an external customer to start this week - Three report enhancements to be worked for the next release - Still waiting for the approval to move the L4 date to Sept 30th 10/09/2025 - Good progress this week, UAT is now progressing at a fast pace - A new data architect was brought in and correction of issues is going well - Some data discrepancies still under investigation - Waiting for approval to move L4 date to Sept 30th. 01/09/2025 - Working sessions took place last week to analyse all the issues raised - Issues seem to have been corrected and the updated reports will restart to be produced this week for continued testing - In the Exception report, data from CEBS is not yet included, so report needs further developed - In the Pick Up report, not all data sources have been considered, further analysis is on going - L4 date needs to be moved back, waiting for confirmation from the development team regarding the timelines 11/08/2025 - First reports received, data is incorrect - Development team is assessing the issues - No timelines have been provided by when we can start receiving the reports with the correct data 03/07/2025 - Infosec has been approved, IT architecture as well - FIRST request approval still pending. - Testing has started, still with test data. It expected the IT development to be deployed into production this week so we can continue with data validation 12/06/2025 - no progress from last week. Same topics still pending 05/06/2025 - FIRST request approval still pending - Approval to delay L4 by two weeks requested to POD lead 30/05/2025 - FIRST request approval still pending - L4 date may need to be delayed by 2 weeks 23/05/2025 Development wise, we are on track to generate the reports. There are still a few fields that are pending. We’re still connecting with different people to get those details. The integration with DWNS to send the reports is also pending and the team is working on it. We have the CAB approval for the infrastructure set up in production and we’re working on the infrastructure set up, as this will be the first go live. We have also raised a FIRST request and it’s still pending the approval. This is a risk, in case the architecture approval gets delayed. 12/05/2025 - Development on-going, some delay in accessing required data fields - Demo booked for Thursday 15th May 24/04/2025 - Team in contact w | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-05 | 2025-10-17
Business w/ Tech Initiative: External Customer Reporting Project PFS | 71626 | 7358 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Prasantha Jagarapu, Graca Machado | On Track | ✅ Key Milestones Completed **Tool Launch (MVP 1.0):** The ECR tool was launched on 11th March 2025 to Sales users and Leadership. **Training & Communication:** User Guide, FAQ, and FLC Training Material have been developed. Sales communication was prepared in collaboration with the Sales Enablement team. **Customer Data Availability:** Reporting is now available for 1,441 global IDs previously receiving SAM Commercial and Benelux reports. 🔄 In Progress **MVP 2.0:** Targeted for 31st May 2025. **Key inclusions:** SPS, Customer References, and Bug Fixes. Scoping work to be completed by 31st March. **Support Structure & Customer List Editions:** Interim processes are in place. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-04-03 | 2025-03-31
Business w/ Tech Initiative: EUM - MPS Parcel/Freight Corporate | 68191 | 7418 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Farhana Z. Aadam, Celia Aguado Galarreta | On Track | Status as of 13th May 25: Initial feedback from architects confirms we cannot remove T-status lanes using existing policy grid (current version only features origin country, so OD pairs cannot be blocked). Several options under consideration - but no effort or timelines yet received. Also need to consider if scale of required development would result in technical debt - to be discussed further. 07/11/25 - remove floor weight for REF based on OD pairs (so already c and t status distinction) Allowing Cstat only gives the same business risk as TNT does not differ, as such we are fine to move forward allowing MPS PF in full on REF as a mvp and take the time in CY26 to constrain. they have decoupled this grid from IPF limited to FAPI- so no risks Architects will plan a review session with Chris Watts and all impacted teams on the documentation/plan in the next available slot. looking at 19/11 CPEL Grid testing still needs to happen. What unlocks L4: Bus Arch will update and finalize the PECS by next Tue 11/11 I can then update the planview Focus for this week: to confirm L3 commit date with the team Sentiment: I’m confident that we can still make the Jan deadline for the 1st phase (enabling MPS Parcel Freight on REF on FAPI) 14/11/25: Chris has setup the review for Monday 17th 3pm UK time - looking to get L3 date as soon as this is completed. Ive asked Samantha gomes to share some possible customers for Mixed Parcel Freight FedEx API testing. List of potential customers has been received, I will review these. 21/11/25: PRT complete and ready for L3 Rank - completed epic and checking with Pollyana before submission -For enterprise KPI ive added N/A as the option because #of customers as per sharepoint guidance isnt there. Alison will look into this for me as there isnt anything else in the KPI options that match what I need. updated the Planview Milestones dates, PPM#, KPIs, impacted portfolio information, and contacted the corrected parties to have the IT costing provided so the initiative can move to L3. 28/11: Initiative submitted to L3- awaiting greenlight & prioritisation. some questions from April around Platform costings / money step (ive replied/completed ) added Celia as secondary IO to cover me while im away in December. Handover completed on Thursday . Once in L3 next step is development discussions with the architects - I have contacted them to confirm their phasing of development with timelines. 23/12: I am back from vacation, handover back from Celia completed. Awaiting commercial greenlight for L3 submission (April) We are waiting for the CPEL target date so that commercial solutions can confirm their support for this initiative. Once all impacted portfolios are ready for the greenlight, we will submit for EGC approval. The next EGC is 6th Jan. C-stat confirmed - IPF / domestic is now included in scope REF is priority once testing is successful will move to domestic/IPF Follow up on UAT testing: Last Monday’s call with impacted Commercial teams: - •Policy Grid Updates work is minimal and can be completed over the next few weeks. the bigger piece of work is the E2E Testing. •All possible steps are being taken to have this E2E Tested in the next feasible testing cycle starting 11th Jan, and testing plans are being worked up. Test scenarios will be completed by next week and planning underway •E2E testing will inform whether we need Revenue certification. For this reason, there is currently no end date. when we move into E2E Testing will this become clear. •Next Touch Point is 23rd December and further updates on Test scenarios will be provided. 02/01: no new updates 06/01: to include below in the MPS PF implementation guidelines: •Customers need adjusted strategic net rates to avoid billing of 68kg/ piece min. I will pick this up with pricing Radoslaw Samborski •Rogier discussed with Steve May that we dont want to go to zero as a min bill weight – likely keep 10 or 15kg a piece. •Customers | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2024-06-18 | 2026-06-04
Business w/ Tech Initiative: Enable- G2D conversion Slovakia ( ACE enablement) | 72858 | 7528 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Piotr Buczkowski, Naime Balci | On Track | **April 22nd** Initaitve is ready for L5 submission. WREG was implemented in April 26'. **Dec.10th** *Go live took place on July 1st -major issues have been fixed. -credit cards will be deployed as of Oct. 25' CSR. -alignment took place on Sept.1st after EE MB decision to credit invoices with wrong disbursement fee -closing call took place -G2D SK as a project has been completed already -only submission for L5 is pending -the latter is connected with WREG milestone ( deployment date is pending confirmation) **Jan.5th** WREG implementation is only holidng us from L5 submission. Team confirfmed will come back to WREG implementatio after peak. Implementation date is still TBC, | K: L5 | Active | L5 | 2024-02-01 | 2026-03-31
Business Only Initiative: Customer Migration Execution-all segments | 73468 | 7568 | Business Only Initiative | EU - Integration Roadmap | Europe | Oxana Klinkert, Freke De Boer, Ijjou Bikhezar | On Track | On track | C: L1 | Active | TEMP L1 - Create L1 LBC | 2024-06-03 | 2025-05-22
Business Only Initiative: MPS Parcel/Freight Regional | 86488 | 7629 | Business Only Initiative | EU - Integration Roadmap | Europe | Pip Fanning, Nicholas Forward, Ana Silva, Matilde Quintas | On Track | Status 21st Nov 2025: * Initiative moved to L4 as of 31st March 2025 * Requirement was to deploy a solution that could be leveraged by the ACE migration team - this was achieved * The solution is not preferred, so deployment to customers is limited by design. It is therefore not possible to include specific revenue supported by the deployment (this solution is a "just in case the customer needs it", it is not being actively promoted) The L4 date was over 6 months ago and the original objectives have been achieved to support the ACE migration team. all milestones and KPI specific have been achieved. As such, we propose to close this initiative and move it to L5 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-07-08 | 2025-08-25
Business w/ Tech Initiative: Enable- G2D conversion Bulgaria and Cyprus (ACE en | 81415 | 7670 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Piotr Buczkowski, Naime Balci | On Track | ***Cyprus*** -go live took place on Sept. 1st -no major issues have been identified for CY G2D go live. -closing call will took place on Nov. 5th **Bulgaria ** **April 22nd** No major issues after conversion. FBO-some challenges with registration. ePRS-some challenges with eSign. QP-project is about to start. WREG-it looks like it was already immplemented. **April 13th** We have no major issues in BG. Below topics may need to be addressed on "closing call": (i) Archiving ownership in BG (ii) Tax storage data requirement For (ii) we are waiting for confirmation what current storge ruls are. Local legal requirement is 10 years. From CT issues we keep monitoring " -FBO log in -WREG -BG wrong invoices ( internal comms has been prepared and shared with custoemr facing teams) **April 8th** Go live took place on April 1st. There are several minor issues which we are fixing with local and central teams. **March 25** All on track for go live. Daily calls with US IT started on March 20th. Control Tower calls will start on April 1st. **March 3rd** We have a GO for BG G2D on April 1st! MTP calls will start 10 days prior go live date. Customers comms was launched on March 2nd. Credo confirmed readiness for April 1st go live. **Feb 12th ** It looks like the only mising confirmation is Credo development and testing. This will be confirfmed by Feb.18th to enable April 1st go live. Focus for this week: -go live date confirmation after Credo/RO "go" **Feb.5th** US IT confirmed MTP on April 1st. Credo IT readiness will be confirmed on team call on Feb.11th. Comms plas has already been updated with new MTP date. *Focus for this week:* GTS raised a new request which is connected: -with account creation for private individuals -collection of EGN ( personal ID number) Evaluation is ongoing if this is really necessary and/if it's G2D related topic. **Jan 30th** BG G2D go live has been moved to April. Main reason that local requriements have not been delivered and couldn't be tested. New go live will be most likely April 1st 26'. **Jan.26th** We have for G2D BG MTP on March 2nd : US IT- "GO" ( testing confidence is high) Region- "NO GO" as Credo IT developments are not ready to be tested Focus for this week: -GO/NO GO call with several MDs will take place on Jan.27th -decision is required as we need to start comms ( Feb.5th to ex.customers) **Jan.19th for Bulgaria** Readiness call took place today. Go/no go will be given on Jan.26th latest. Outocome of below testings is pending : (i) Credo for BG local requirements (ii) CVD for pending accounting defect. No other issues have been identified. Coming key steps are : - Jan.23rd testing completions - Jan.26th go decision - Feb.5th customer comms - March 2nd MTP | G: L3 | Active | TEMP L3 - Enter L3 | 2024-01-01 | 2026-06-01
Business w/ Tech Initiative: EUM - Express Domestics final countries | 86593 | 7710 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Freke De Boer, Giorgia Casadei, Sara Voye | Attention Needed | Apr 14: EE, LV, LT, SI have gone live surccesfully early April; GTM / GTS will be done at the end of April. For IE and BG the Oct CSR has been confirmed, | G: L3 | Active | L3 Feedback Requested | 2024-08-07 | 2027-01-29
Business w/ Tech Initiative: FDX UK Oversize/Exceed Dims - Manual Scan | 57680 | 8107 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Stuart Phillips, Trent Turner | Some Issues | OS launched in FedEx without scan requirement. This means the risk to TNT migration of not having OS no longer exists and so development no longer required. | E: L2 | Cancelled | L2 | 2023-12-01 | 2025-04-18
Business w/ Tech Initiative: Enable TNT TPP's / CSP's Customers Migration by en | 25224 | 8156 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Nikola da Costa, Guilaine Cicut, Guillaume Blondel, Ana Sofia Amorim | Some Issues | **Already delivered:** * The program, legal framework, technology and support to achieve migration readiness have been provided to TPPs in July 2024 free of charge. * All ACE-critical TPPs have been receiving official communications and invitations since May 2024. * Most ACE-critical TPPs have been assigned dedicated CT O2P leads for 1-to-1 support for the first year post program launch. Since this summer, 3P CT and Marketing are stepping up directly with the providers at risks. **Updated Nov 10 2025** * 46 ACE-critical TPPs enrolled for Integrator (signed program agreement, developing to APIs) from a total of 53 identified 3P. * 14 fully validated ACE-critical Integrator, already deploying to end-customers and we have an additional 4 providers in the progress of being validated. * We are working with TPPs to agree on development timelines. Our ask is end of CY25 but we are willing to accomodate if providers negociate with us. **RISK AND MITIGATION** * 17 third-party providers have been identified as "at risk" of meeting the May 31, 2025 technology readiness deadline. The list with revenue and customer associations was taken to EU Sales Leadership (during the Dan Vines Staff meeting on January 31) to assign local sponsorship for key providers identified for escalation. * Socialized the escalation framework for ACE-critical third-party providers at risk with the ACE leadership (during the February ACE VP Steerco), received approval to proceed with Steps 4 & 5 (Legal Letter and Cease & Desist with committee approval) for providers at risk. * It was agreed with the leadership that before we trigger Step 4, we would inform the Sales teams that we're intending to do that, so they can start reaching out to end customers using the impacted TPP solution and start talking about potential alternative integration options. * Communications and reminders sent to all identified 3rd parties regarding the May 2025 timeline * End-customers being leveraged to push their providers via an eKit designed for Sales – HighSpot records indicates only 14 downloads, so we do not believe this eKit is known/used much by sales. * In August 2025, 14 providers received the Legal letter giving them 14 days to registered onto the Integrator program if not done already, and 5 months to request validation – this proved to be effective as most providers contacted us back and we now have timelines with most of them. * One provider requested financial compensation to develop join the program and FedEx API, an FTIP (FedEx Technology Incentive Program) exception process is in progress since a few months. * The challenge is to strike the right balance between program objectives and supporting customers using non-compliant 3P onboarding, as we received clear direction from RMC that we cannot block business. **ASK:** Sales to agree on problematic provider ownership based on territorial & customer assignments and engage for business-type conversations to return providers back on track. Tech options for relusctant providers are under-investigation with cross-functional global team. **Updated Jan 8 2025** * Drive ownership transfer From Guillaine Cicut to Nikola da Costa **Updated Jan 12 2026 (Nikola da Costa) * 47 ACE-critical TPPs enrolled for Integrator (signed program agreement, developing to APIs) that represents **100% of TPP in scope**. ( Previusly 53 identified 3P. after following up directly with the providers 6 is out of scope) * 17 fully validated ACE-critical Integrator, already deploying to end-customers * We are working with TPPs to agree on development timelines. **Updated Feb 13 2026 (Nikola da Costa) * Provider COMSOL validated Fabruary 13 * 18/47 fully validated ACE-critical Integrator **Updated Feb 20 2026 (Nikola da Costa) * 18/47 fully validated ACE-critical Integrator * KPIs acutals updated * We are working with TPPs to agree on development timelines. Our ask is June 2026 as that is deadline for TNT migration (Note, extention process f | I: L4 | Active | L4 | 2023-12-01 | 2025-12-01
Business w/ Tech Initiative: Turkey Instant Invoicing | 79256 | 8431 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Nectarios Panagopoulos | On Track | 18/03/2025: No actions 03/12/2025: The "instant invoice" is in Production since July while country started to use it since October. The performance is excellent with 100% success ratio in November. Two months of mature benefits have been captured + 2 months being in production already and the success ratio has been monitored and the result is successful. Please see the following documents as evidence for the recurring benefits: 1. Outlook file "RE Instant Invoice_Monthly " = Monthly analysis of the success ratio of the initiative 2. Outlook file "Update from the Transformation Office" = email communication from the Transformation Office which clearly states that the instant invoice was a critical dependency for Turkey G2D, protecting $38 million and driving ACE G2D transition. 25/11/2025: The "instant invoice" is in Production since July while country started to use it since October. The performance is excellent with 100% success ratio in November. 10/11/2025: On Track, Instant Invoice is in Production since October. 07/10/2025: Local TR team started to use the instant invoice as of Oct 1st. No issues. 24/09/2025: Solution has been delivered (incl. new PDF layout for invoice as per the GTS request) and invoices are delivered on time at the provider (Pagero) the last 3 days. 14/07/2025: The development is loaded in Production 10/07/2025: The initiative has been approved and it is good to load for July' 25 CSR. Initiative on track. Global IT to deliver for July' 25 CSR. | K: L5 | Active | L5 Feedback Requested | 2024-09-02 | 2025-09-18
Business Only Initiative: Migrate TNT Marketing + ISR segment customers to F | 17812 | 9366 | Business Only Initiative | EU - Integration Roadmap | Europe | Oxana Klinkert, Piotr Glowka | On Track | Migrated so far in this fiscal: 6.75M$, primarily mkt and ISR customers Currently in flight – 7.2 M$ rev, 7k Customers DR8 batch planning in preparation (planned GTM in April, DE & IT are likely to start with Mkt mid March), active batch planning with Country PMOs will start 4th Dec Freight online pick-up in DR8 -still an open topic to close with DI - education through CE & Sales will be needed, but parity/disparity with MAGI is not fully defined Clearance POC CH – cannot be supported through ACE Classic and needs voluntary migration ACE Governance completed, functional governance still work in progress with some functions Work in progress: 1) Consolidation of functional and ACE roadmaps to improve customer experience after Q1 customer research. A number of impactful improvements for DR8 (mid March) on the way 2) ACE contingency process- to be finalized end of Nov 3) Risks mitigation plans- to be finalized and of Dez 4) ACE FY25 & FY26 Forecast – currently sales review today is the review with Giles 5) Functional readiness managed through milestones – target to finalize next two weeks | K: L5 | Completed | L5 | 2023-03-01 | 2024-05-31
Business Only Initiative: Migrate TNT field sales segment customers and 'sim | 17814 | 9368 | Business Only Initiative | EU - Integration Roadmap | Europe | Oxana Klinkert, Piotr Glowka | On Track | Migrated so far in this fiscal: 6.75M$, primarily mkt and ISR customers Currently in flight – 7.2 M$ rev, 7k Customers DR8 batch planning in preparation (planned GTM in April, DE & IT are likely to start with Mkt mid March), active batch planning with Country PMOs will start 4th Dec Freight online pick-up in DR8 -still an open topic to close with DI - education through CE & Sales will be needed, but parity/disparity with MAGI is not fully defined Clearance POC CH – cannot be supported through ACE Classic and needs voluntary migration ACE Governance completed, functional governance still work in progress with some functions Work in progress: Consolidation of functional and ACE roadmaps to improve customer experience after Q1 customer research. A number of impactful improvements for DR8 (mid March) on the way ACE contingency process- to be finalized end of Nov Risks mitigation plans- to be finalized and of Dez ACE FY25 & FY26 Forecast – currently sales review today is the review with Giles Functional readiness managed through milestones – target to finalize next two weeks | K: L5 | Completed | L5 | 2023-11-01 | 2024-05-31
Business Only Initiative: Migrate TNT EG ER and complex EN sales segments to | 17817 | 9370 | Business Only Initiative | EU - Integration Roadmap | Europe | Paul Maas, Oxana Klinkert | On Track | Kicked migration project with 180 customer which resulted into 234 projects Move to L4 by latest 28.06. Next steps: continue to relaunch new bacthes and kick off customer migration projects in FY25 | K: L5 | Completed | L5 | 2023-07-03 | 2024-05-31
Business w/ Tech Initiative: Enable a scalable FedEx DG road offering allowing | 17825 | 9372 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Ana Silva, Nicholas Forward | On Track | **16/02/2026** DH2 tests finalized. This represents 95% of the cap 16 delivery. Next steps in progress: Phasar and GSS tests will be completed during L4. In progress: Capability 16 showing Warehouse ADR points 1.Create UAT test scripts 2.Plan IT resource to setup onsite test environment 3.Conduct UAT with business representation and IT support in attendance 4.Create training materials/ instructions for end users 5.Deploy to all Stations/ Transit locations **12/01/2026** **Project Health** Status Rationale What unlocks L4 Operational confirmation that Purple shipments are visible and can be processed correctly by the impacted teams. Completion of post-peak readiness checks ahead of pilot execution. Focus for this week Confirm Purple pilot go / no-go following operational validation. Align end-to-end testing readiness, with testing confirmed to start after January 23rd. Update Planview to reflect confirmed timelines and remove any ambiguity. Maintain Orange end-to-end testing positioned after peak, aligned with IT availability. Sentiment Positive Testing availability has now been confirmed post-peak, removing a key timing uncertainty. The remaining activities are confirmation-based rather than development-driven, and timelines are stabilizing. **02/12/2025** PURPLE – Planview Update Project Health: On Track Status Rationale: What unlocks L4: •Confirmation from PLA and PTD to enable the ADR flow before pilot (Purple). Focus for this week: •Follow up with PLA/PTD on ADR filtering confirmation (blocking for ADR enablement). •Support alignment with Mike on PHASAR progress (in progress). •Prepare January pilot planning (location-based activation). Sentiment: Positive Purple development remains stable; ADR enablement is the only pending dependency. ORANGE – Planview Update Project Health: On Track Status Rationale: What unlocks L4: •Completion confirmation from Consolidation and GSS, plus testing commitment from E2E. Focus for this week: •Validate whether Consolidation is fully completed (status needs confirmation). •Track GSS progress (completion expected end of December). •Monitor PHASAR progress (in progress for Purple & Orange). •Acknowledge PSCAN (test-only, not started) and SPLITS (no PI5 commitment; revisit in PI1). •Prepare for E2E follow-up with Mike on 12/5. Sentiment: Confident Core components (CRES, Consolidation, GSS) progressing as planned; dependencies clearly mapped and under follow-up. **24.11.25** **IN PROGRESS** Orange Solution Development: Consolidation and GSS development are in progress and on track to be completed by the end of December. SPLITS cannot support due to other higher priority work. DG work will be re-evaluated in PI 1. E2E ETA for DH2 flow: PI 1 (January 2026) Purple Solution Remaining Development: PHASAR, GSS, SABRE PHASAR development is in progress. GSS development and scrum testing– Completed. Pending PHASAR development for Next Neighbor testing. SABRE development and scrum testing – Completed- Available in L3 for testing. Purple Pilot: The Business is in discussion with some potential locations for Purple Piloting after PEAK. **NEXT STEPS** Continue development for Orange Solution. Request E2E test support for the remaining items of DG Road. The Business team will pick a location for Purple piloting after PEAK Freeze is over. **RISK / AWARENESS** L4 DATE: 4/30/2026 Awareness: #1 REX83 Currently in production, WBDG provides the ability to update/removing selected DG handling codes. This was done as a part of the GPN OD Split and DG REX epics. LEO and eMassEntry are excluded from the scope. Next Step: WBDG to release one client updates before activating this capability in Prod. (After PEAK) ______________________________________________________________________________________ **"Status 11.11.25"** **Complete**:** **Purple Solution Deployment:** DH2 flow deployment is completed (Nov 3) and will be ena | G: L3 | Active | TEMP L3 - Enter L3 | 2023-02-01 | 2026-10-08
Business w/ Tech Initiative: Enable - G2D conversion for Turkey ( ACE enableme | 17828 | 9373 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Piotr Buczkowski, Philippe Schorp | On Track | **April 22nd** Initative is ready for L5 submission. Cash allocation backlog is as per below and value are decresing. Below the latest update for TR Backlog Progress Unapplied cash DateBacklog Value (USD)Backlog Items 29-Dec-258,964,35835,300 11-Feb-263,929,97220,499 27-Feb-262,232,85912,606 13-Apr-261,271,9046,937 Nov.10th -TR G2D go live took place on June 2nd -disbursement fee and ADT file has been moved to production -instant invocing has alrady been launched in October 25' -PDF for D/T has been fixed **Other topics:** - .com rates in TRY is a separate initiative and will be monitored by CT - value proposition will be managed separately - corproate credit cards may be delivered earliest after Jan.26' CSR -closing call took place on Nov.10th and we had no major issues Submission for L5 is pending. **Jan.5th** There are several issues which base business keeps solving. *Billing*: FedEx billing process is more automated comparing TNT billing process. We are facing instant invoice delays nowadays related global issues but Global IT team is managing the issues and we have benn kept in touch with them. There is no big issue. *Dispute:* Since 1 June, retain team have been managing majority of disputes. The backlog has been cleared, after re-organization at dispute team. They resolved more than 18,000 disputes in a short period and we are almost within 10 working days period to reply. This is very good progress. *Collection:* As retain team we have been receiving requests from customers, purple pulse and sales. The customers are reaching us and says that they can not receive any reply from TR-Collection team within 10 working days. They are asking retain team support. Retain team is giving full support alongside their daily workload as much as they can. They are checking payments at bank account and credit card statement. If reconciliation is needed, they work on it. Retain team ask Cash Allocation team to correct the posting. Retain team are also following delayed refund cases. *CashApp*: Since July 2025, the main issue is Cash Application. Some customers made payments to wrong bank accounts (it was expected but the transfer was not completed and accounts became "bad payer". Retain team wrote CashApp the transaction each time, it did not work as it was expected. TNT payments are hold at FedEx bank account and not posted to SAP yet. *Credit Card payments*, we faced two issues. One of them is the payments were not posted to customer accounts. When some of them were posted to FedEx AR, the net amount which bank paid FedEx (after deducting comm fee) was posted to customer account. We again raised the issue. CashApp said that it should be posted "net amount" to customer account and the difference will be write-off. This is also new for us new, it might create problem at customer side. The backlog at credit cards payments is about more than 8,000 payments as last 6 months volume. We do not know why Blackline (CapGemini system) does not allocate the payments as FIFO, that was agreed topic during G2D project. CashApp is insisting to get payment detail as invoice level now. This is not common customer behaviour to pay invoice level in Turkey. We need to work on this. They raised this request this week and they are talking about last 6 months volume. *Ancillary Revenue*: Process owner is GOPS. The request is to get bank statement with starting AWB number at explanation area. The customs brokers need to be informed about this topic by local team and team is aware. | K: L5 | Active | L5 | 2022-05-02 | 2025-11-28
Business w/ Tech Initiative: Enable Express Domestic standard product & pricing | 18161 | 9394 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Freke De Boer, Nicholas Forward | On Track | REady to submit | K: L5 | Active | L5 Feedback Requested | 2022-10-03 | 2024-12-31
Business Only Initiative: Enable TNT France Domestic Legacy - customized aut | 20996 | 9465 | Business Only Initiative | EU - Integration Roadmap | Europe | Harri Janakka, Samantha Gomes, Jan Denys | On Track | 27-05-2025 * The intiave last milestone was closed succesfully today in a mutual agreement with FR CT Managers Willian Jacquot and Laurent Saez. * The key project deliverables where reviewed with DI O2P team and FR local team already on 06th May 2025 and proven succesfully implemented. * The project - planned technical capabilities delivery and validation can be hereby confirmed complated succesfully. * Activities to improve the experience and migration results are taking a place outside this project scope. __________________________________________________________________________________ 27-05-2025 * Preparing to close up the initiave. Final eveluations on-going. __________________________________________________________________________________ 13-05-2025 * FR project review was held on Tue 6th May. All parties approved the positive outcome of build custmer data migraiton tooling, process and comms outcomes. * The customers data cleansing activities and process improvement activities will taken care outside of the iniative. * Prepearing to start the iniative closure. ________________________________________________________________________________ 06-05-2025 * Project team review taking a place today Thu 06-05-2024, with objective to review the project - Initiative outcome. _______________________________________________________________________________ 29-04-2025 * Due Eastern and 1s of May bank holidays the initiatiative evaluation meeting will take a place 6th May, impacting - delaying the final milestones closure. * The indicative feedback is postive, hence expecting initiative closing in time. ______________________________________________________________________________ 22-04-2025 * By Friday 25-04 the first customers will see the TNT account deactivation message in myTNT.fr, ,when the we'll start the last validations for the process / tooling build. ______________________________________________________________________________ 15-04-2025 * Progressing as per plan. ______________________________________________________________________________ 08-04-2025 * Progressing as per plan. ______________________________________________________________________________ 01-04-2025 *Progressing as per plan. ________________________________________________________________________________ 25-03-2025 * Progressing as per plan. * No major updates until 25th Apr, when online customer profile customers will have DD and FR team is trickering the required message to customer with DIO2P. ______________________________________________________________________________ 18-03-2025 * Up to date progressing well. * The next major batch going live is S80 in the begnning of April. ____________________________________________________________________________ 11-03-2025 * FR POC batch S77 execution on-going as per plan. DD dates in April (online) and in May (combined / deployed) ____________________________________________________________________________ 25-02-2025 * FR POC on-going. _____________________________________________________________________________ 18-02-2025 * Live customer validation moving on schedule ___________________________________________________________________________ 10-02-2025 * End to end testing on-going. * ACE MM Batch 76 and the first 4 customers migration process on-going. (Day 1 is Tue 11th Feb). ------------------------------------------------------------------------------------------------------------------------ 04-02-2025 * Testing on-going and the first custmers are going into migration process next week. * Looking approval & guidance to move on L4. * 2 testing milestone schedules changed by Rogier verbal approval. _____________________________________________________________________________ 28-01-2025 * Requesting change for 4 milestones in aligment to changed DI O2P team delivarables - readiness. _____________________________________________________________________________ 21-01-2025 * Due a lack of test environm | K: L5 | Completed | L5 | 2023-06-01 | 2025-05-29
Business w/ Tech Initiative: Enable TNT Legacy - customized automation shippers | 20998 | 9467 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Harri Janakka, Samantha Gomes, Jan Denys | On Track | 13-04-2026 * No change on project Status. FR TOP CT Customer pre-consultations started and the potential POC customers could be found in the next 4-8 weeks. _______________________________________________________________________________ 31-03-2026 * No change on project Status. Pending TNT Migration to progress to enable SALE POC. _______________________________________________________________________________ 17023-2026 * No Major Changes. Although the SALE POC is likely delayed further due delays in FR EDI Customer Migration. _______________________________________________________________________________ 24-02-2026 * Both MAGIC batch and Integrated shipping solutions customer base in a solid growth and improvements based on customer and CT input are taking a place. * SALE POC keeps bending pilot customers. Alignment to start pre-consultations with FR EDI customers will start and in by end April - May we can decide what we'll do with SALE offering. _______________________________________________________________________________ 10-02-2026 * No major changes. SALE - Offline labelling solution still pending the first POC customers. ¦ No POC customer on-boarding in sight in a short term. _______________________________________________________________________________ 27-01-2026 Evaluation progress update * No major changes. SALE - Offline labelling solution still pending the first POC customers. ¦ No POC customer on-boarding in sight in a short term. _______________________________________________________________________________ 13-01-2026 • MAGIC batch and standard integrated shipping achieved record results during the peak period. Customer activity rebounded to high levels in January following the Christmas and New Year break. • SALE solution proof of concept (POC) is pending confirmation of pilot customers. ______________________________________________________________________________ 16-12-2025 Evaluation progress update * MAGIC batch and integrated shipping customer base and volume growing constantly. * SALE - Offline labelling solution still pending the first POC customers. / Likely to go March - May prior the first TNT customer migration related cases appears with customers implementing SALE. ______________________________________________________________________________ 02-12-2025 Evaluation progress update * No major changes. SALE - Offline labelling solution still pending the first POC customers. ______________________________________________________________________________ 11-11-2025 Evaluation progress update * MAGIC Batch shipping - New all time records made both with # of customers using it as on #of Shipment created. * MAGIC Integrated shipping - Slow progress with scale up in EU. Further education and hands on workshop activities planning for EU CT on-going * SALE - Offline labelling solution still pending the first POC customers. ______________________________________________________________________________ 04-11-2025 Delivered capabilities evaluation - customers results summary. * MAGIC Batch shipping - Used in all regions. In EU 750+ active customes / >100K weekly shipments * MAGIC Integrated shipping - Slow scale up in EU 80+ active customers / >6K weekly shipments. Additional CT training planned to support growth. * SALE - Offline labelling solution still pending the first POC customers. TNT FR and IT Domestic migration start is expected to open the demand finally. ______________________________________________________________________________ 09-10-2025 * The iniative is ready to be moved on L4. * Finally, the EPIC's which Dataworks created and associated to Iniative themselves and asked to cancel are disconnected from the this iniative. * The email from Dataworks confirming the associated EPIC cancelation is attached in the content documents. * This iniative was extablished in WAVE and development work was conducted by Digital related to MAGIC development / and By IT related to Flag / SALE developm | I: L4 | Active | TEMP L4 - Enter L4 | 2023-01-02 | 2025-08-01
Business w/ Tech Initiative: ACE - Enable Proactive Monitoring & Intervention - | 21010 | 9469 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Graca Machado, Jessica Jaltem | On Track | 14/01/2025 Initiative ready to move to L5 October 2024 Initiative completed and interim reports delivered. | K: L5 | Completed | L5 | 2023-07-17 | 2024-08-07
Business w/ Tech Initiative: Postal enablement EE, LV, LT, IE, BG, CY, SI, UA | 27245 | 9491 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Freke De Boer, Monika Jelen | On Track | EE, LV, LT, SI went live on Sept 29, CY, BG and UA went live on Jan 5, for BG some minor issues will be fixed by Feb 2. The BG issue has been fixed as well as IE has gone live successfully. This means we can move this initiative into L4 | I: L4 | Active | L4 | 2024-08-07 | 2026-02-09
Business w/ Tech Initiative: FY24: P2O XLB removal for intra EU IE/F shipments | 24332 | 9517 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Hessel Jensma | On Track | January 29th: * 100% of the P2O labels have been removed as of mid October. Key metrics are all stable and within limits: 1) MBG%, 2) data exchange and 3) amount of volume FDX volume. | K: L5 | Completed | L5 | 2023-03-13 | 2024-02-29
Business w/ Tech Initiative: Enable- G2D migration Portugal ( ACE enablement) | 25581 | 9541 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Piotr Buczkowski, Philippe Schorp | On Track | **April 22nd** Project is ready for L5 submission. WREG was implemented in April 26. Direct Debit is being monitored separately by Rev.Operations - not "must have" for PT G2D. **Dec. 9th** -go live took place on May 1st -closing call took palce on July 31st and G2D PT as a project has been completed already -several open issues will be managed by PT local country leadership -only submission for L5 is pending -the latter is connected with: (i) WREG milestone ( deployment date is pending confirmation) (ii) SEPA/DIRECT DEBIT ( deployment date is pending confirmation)) **Jan.5th** Neithter Direct Debit nor WREG are implemented hence can't submit for L5. | K: L5 | Active | L5 | 2023-01-02 | 2026-03-31
Business w/ Tech Initiative: Enhancements DORA for Domestic Customer Migration |  | 97134 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Priti Bhatt, Robert Anghel | On Track | 31 Mar 2026 - work in progress for DORA features. We also resolved few issues in MIA with support of DORA team, MTP with fixes was carried out last Friday. The money step of this initiative will be expended as agreed and aligned with leadership. 24 Mar 2026 - On track - a MTP is being planned during the week of 6th April to address some performance related enhancements' and a couple of features related to segmentation and rerating. DORA IT team is also supporting to resolve the recent gaps and issues came up in MIA tool. This is to ensure MIA is fully stable again at the earliest. 2nd Mar 2026 - On track - no new update 23 Feb 2026 - On track - no new update 17 Feb 2026 - On Track - no major update, development work in progress 9 Feb 2026 - On Track - development work in progress 27th Jan 2026 - On Track - no major update, development work in progress 19th Jan 2026 - On Track - no major update, development work in progress 13th Jan 2026 - On Track - no new update 6th Jan 2026 - On track - no new update 16 Dec 2025 - On Track - no new update nor any issue to highlight 8th Dec 2025 - On Track - no new update nor anything to highlight for this week, development work is in progress. 1st Dec 2025 - On Track - development in progress, MTP being planned for early Jan26. 24 Nov 2025 - On Track - development work in progress. 17 Nov 2025 - On Track - MTP for feature like generration of discount load template was completed. Remaning features for Jan'26 MTP are in development. 24 Feb 2025: moving initiative to SL2 12 Mar 2025: submitted to SL2 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-01 | 2026-05-29
Business w/ Tech Initiative: Enhance MIA for Customer Migration (Intl & Dom) |  | 97139 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Priti Bhatt, Robert Anghel | On Track | 6th Jan 2026 - On track - ready for L4 16 Dec 2025 - on track for L4 8th Dec 2025 - On Track - work in progress, no new update, 1st Dec 2025 - On track for L4 24 Nov 2025 - Money Step date changed to 29th Dec'25. Financials updated. No major impact on deliverables. Date changed based on 2 month timeframe from system release date of IT vendor team. 17 Nov 2025 - On track for the features planned. 24 Mar 2025: Answering EPM question: Hello, thank you for supplying the approrpriate architecture documentation. However, can you please elaborate a bit further on the Money Step? This should be the overall strategy for realizing value from the initiative. - Money step field updated (provided additional information). Also, the $ 1.2B amount is a one-time SOFT benefit. Updated Estimated Annualized Value Range to Maximum >$35M since it considers both soft and hard benefits. 12 Mar 2025: submitted to SL2 24 Feb 2025: moving initiative to SL2 | I: L4 | Active | L4 | 2025-05-01 | 2025-12-29
Business w/ Tech Initiative: Enhancements for PRIDE to enable DomesticMigration |  | 97147 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Priti Bhatt, Robert Anghel | On Track | 13 Apr 2026 = On track - no new update 31 Mar 2026 - On track - no new update, remaining features are being developed 24 mar 2026 - On track - MTP was carried out last week. Features like Reassignment through UI and mass upload are in production now, along with few enahancements in the mass agt process. 2nd Mar 2026 - On track - no new update 23 Feb 2026 - On track - no new update 17 Feb 2026 - On track - UAT gonig on for the features planned for March MTP 9 Feb 2026 - On track - UAT began, MTP planned for March 2nd Feb 2026 - On track - UAT for 2 features starting tomorrow, MTP being planned for March. 27th Jan 2026 - On Track - no major update, development work in progress 19th Jan 2026 - On Track - no major update, development work in progress 6th Jan 2026 - On track - no new update 16 Dec 2025 - On Track - no new update nor any issue to highlight 8th Dec 2025 - On Track - no new update nor anything to highlight for this week, development work is in progress. 1st Dec 2025 - On Track - feature development is work in progress for Jan26 MTP 24 Nov 2025 - On Track - WIP for Jan'26 MTP 17 Nov 2025 - On Track - 3 key features have been rolled out in Production. Development on the for Jan'26 MTP is on track. 7 April. Inserted a dummy PPM number (as I am still waiting to get PPM proposal request access). April Zhou said we will need PPM number prior for L3. We have everything in place to move it to L2. Will submit as is and insert the correct PPm number once it will be requested. 25 Mar 2025: Updated T-Shirt size to Medium 24 Mar 2025: Updated T-Shirt size to XS 24 Mar 2025: Answering EPM questions: Hello, can you please elaborate further on the Money Step?This should be the overall strategy for realizing value from the initiative. - Done, inserted more details on the Money Step. Also, I have seen multiple initiatives come through that each have $1,200,000,000 listed as soft one-time benefits. Do all of these initiatives result in the same financial benefits? - Yes, the $ 1.2B is regarding all customers which are due to be migrated. As these 3 initiatives focus on different areas of customer experience when migrating we cannot split the $ 1.2B. We provide the same number, as a soft benefit. Discussed and agreed with Finance on the topic. $ 1.2B should be seen as a one-time SOFT benefit. Also updated Estimated Annualized Value Range to Maximum, >$35M, as this field considers both soft and hard benefit. 12 March 2025: submitted to SL2 20 Feb 2025: making progress to move initiative to SL2 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-01 | 2026-05-29
Business w/ Tech Initiative: Enable-G2D conversion Ukraine (ACE Enablement) |  | 108573 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Piotr Buczkowski | On Track | **April 22nd** Alignement with IT took place on April 21st. We will also need to schedule a call with local PWC-it's pending. Next steps regarding PDD preparatiomns are: *Step 1.* Internal alignment session to agree options & agree “Team recommendation/s”. This I will schedule when Revenue Operations confirm that has received all “answers” regarding “as is” set-up. *Step 2.* If need, e.g., if recommendation/s will be different vs FedEx standard we need to get and approval from impacted functions. This would mean we will present “Team recommendations” to a proper leadership forum. This is TBC when our recommendations are known. *Step 3*. Only after Step 2 we would know what needs to be requested to (i) US UT as PDD or (ii) regional Credo IT and what final impact on local business would be ( I mean “changes” vs today). **April 13th** We have received PWC feedabck #2, There may be a need to review business requirements with PWC directly. TBC. **March 25** After receiving PWC feedbck, G2D team has identified key below issues: 1. Usage of local 1C system. 2. AoA (invoice) distribution to customers via 3 local platforms (“Vchasno”, “Art Office”, “SOTA”) 3. Tax/VAT Invoice creation and register it in the Unified Register of Tax Invoices 4. “Instant Invoice” for transportation charges is required during the customs clearance to confirm the value of transportation services. 5.Act of Acceptance compliance: eSignature and eStamp G2D team will seek for guidance / decisions for each topic. **March 3rd** PDD will be filled in by mid March earliest. Key is to get PWC tax feedback. Initiative is on L2 and ranked as #48 in the PRT backlog at cpel. **Feb.13th** UA seems to be a complex conversion. We are waiting for PWC feedabck regrding key regulatory enablers. In parallel functions keep updating PDD. Triange for L2 will be on Feb.16th with US IT commercial teams. Focus for this week: -triage for L2 -team call -1C system follow up ** Jan.26th** WtW session took place. UA has several non standard requirements among which most important are: -Cyrillic alphabet & local language -Tax invoces as parallel to std.invoice -instant invoicing Focus for this week: -on Jan.29th we will complete WtW session and PDD update will start -L2 submission **** Jan. 15th**** WtW session will take place in week 4th ( 21st,22nd and 23rd of Jan. 26'). Epic owner from US Commercial has already been confirmed. PDD will be prepred by end of Feb.26' which will be reviewed with US IT Feb./March. Therefore L3 submission won't happen prior March 26' most likely. Focus for this week: WtW preparations Nov. 21th G2D work will re-start in November with below plan: -kick off Nov. 25' -WtW Jan.26' -PDD completion by end of Feb.26' -CSR slot TBC after PDD review March 26' -team participants have been confirmed LENC -regional decision is to keep current TNT LE name. -LENC will be executed when political situation changes for better. Dec.1st Kick off took palce on Nov.25th hence we started G2D UA officially in EU Region. *General sentiment* UA does not look as an easy conversion. The VAT accounting system in Ukraine is similar to the European model but has significant differences. To confirm the VAT amount, a tax invoice must be registered for each sale in the Unified Register of Tax Invoices. This is a separate document that must be recorded both in the accounting systems and on the Tax Portal. | E: L2 | Active | L2 & CCH | 2025-11-03 | 2026-11-30
Business Only Initiative: EUM - COD at Express DOM RO |  | 109602 | Business Only Initiative | EU - Integration Roadmap | Europe | Anna Radecka | On Track | N/A | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-29 | 2026-06-12
Business w/ Tech Initiative: STRATUS - MPS mixed P\F c- status restriction |  | 167882 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | SIMONA BERTELLO | On Track | On Track 12/15 - Cancellation request received via PDSM ticket #INC033390019 | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: EUM - Nordics Invoicing Requirement |  | 170274 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Zara J. Knight, Carolina Nutt | On Track | Awaiting Commercial Greenlight | E: L2 | Active | Portfolio Greenlight | 2026-03-31 | 2026-12-31
Business w/ Tech Initiative: EUM - Update Bundling Logic Cut Off Time |  | 168032 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Christopher Seem, Stuart Phillips | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: PRIDE Dev Features for Cust. Migration & Cust. Exp |  | 180482 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Narender S, Tanmay Korgaonkar | On Track | On Track | E: L2 | Active | L2 & CCH | 2026-05-01 | 2027-12-31
Business w/ Tech Initiative: EUM - PASGO PFS |  | 183750 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Ines Moura, Matilde Quintas | On Track | On Track | E: L2 | Active | L2 - Enter Value Prop | 2026-09-30 | 2026-09-30
Business w/ Tech Initiative: EUM - Enablement DG by Road Coverage in eSRG |  | 183780 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Ana Silva | On Track | On Track 16.02.26 •The topic was discussed in Friday’s L1 Architecture call, and the initial feedback was positive. •It is expected to move to L2, pending formal confirmation from the architecture team. | E: L2 | Active | L2
Business w/ Tech Initiative: Storage and Access to COD RO Payment Recipt |  | 185341 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Anna Radecka, Agnieszka Pallett | On Track | On Track | E: L2 | Active | L2 Feedback Requested | 2026-04-06 | 2026-07-30
Business w/ Tech Initiative: EUM - Flex API Configuration (MPS PF Corp) |  | 189697 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Farhana Z. Aadam, Giorgia Bendinelli, Jamie Dean | On Track | On Track 20/04: EA received the latest initiative backlog list on Tuesday, 4/14 – and 189697 is one of the 4 new L1 Assessments for EA to assign, and should be assigned to an architect on Monday, 4/20. Usually, it takes about a week for architects to complete the assessment. | C: L1 | Active | L1
Business w/ Tech Initiative: IED EU DG Enablement–Limited Quantities & Lith Bat |  | 189969 | Business w/ Tech Initiative | EU - Integration Roadmap | Europe | Ana Silva, Pip Fanning | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Reduce Churn Rate by improving Post Sales | 11120 | 7327 | Business w/ Tech Initiative | EU - Italy | Europe | Rodolfo La Faietta, Marco Figueira | On Track | Confidence in delivering value on time: Medium to High Confidence in delivering the full value: Medium to High, following the additional sub-initiatives added after the Ideation Sessions and the consequently expanding the initial scope | G: L3 | Completed | L3 Data Migration - TEMP | 2023-01-16 | 2025-05-30
Business w/ Tech Initiative: Vertical Markets development (HealthCare & Fashion | 11675 | 7339 | Business w/ Tech Initiative | EU - Italy | Europe | Simona Galano, Marco Figueira | On Track | Confidence in delivering value on time: Medium Confidence in delivering the full value: Medium Since some of the initiatives milestones were delayed we can have an impact in the value delivering Main drivers are the lower yield than plan and Service issues (not stable at 92%). 31/03/2025 - Rebaselined to FY25 update 16/4/24: Initiative submitted to L4 given completion of Money Step. L5 date set for 1/5/24. The initiative has now been re-forecasted to a total impact value of 3.4M$ of revenue for FY25 and 4.2M $ of revenue for FY26 lower than initial plan due to: 1.Lower yield due to small parcels, low weight, less premium volumes 2.Luxury & Health Care Customers still reluctants to come back (because lower service level compared to their expectation) 3.Constraints on Customers side (IT develop & additional costs – Customer internal organizations review – Customer supply chain changed? shipping internationally instead domestic) 4.Network performances not stabilized yet 5.ShipToCollect issues to be solutioned before approaching new business 6.Customers are looking for cost reduction due to geopolitical environment 7.Lower rates by competitors 8.Good and stable performances provided by competitors 9.Approach other markets (not only HC and Luxury) 10.Longer implementation period due to Customer complexity (mainly Enterprise Global or Regional Customers – sometimes going through RFQ) 11.Priority label project not yet implemented (not yet approved by MB) (it was the base of my initiative for HC Customers) Reforecast approved by Pod Lead, Sponsor and Domain Finance Lead. | I: L4 | Completed | L4 | 2023-01-09 | 2024-07-31
Business w/ Tech Initiative: SME Domestics sales focus - Field sales - replaced | 23275 | 7350 | Business w/ Tech Initiative | EU - Italy | Europe | Luca Nicolini, Marco Figueira | On Track | Confidence in delivering value on time: High Confidence in delivering the full value: Medium 31March2025 Initiative rebaselined to FY25 FY24 Value leakage in Sales initiatives has been acknowledge but not quantified. Main drivers are the lower yield than plan and Service issues (not stable at 92%). The team is reviewing results/plan and will perform reforecast by end of September/Beginning of October. Update April 1, 2024: the initiative has been replaced by #73298 as of June 1, 2024 and that future value has been set to zero. | K: L5 | Completed | L5 | 2023-01-02 | 2024-02-06
Business Only Initiative: New Business by leveraging Enterprise National Tea | 23305 | 7361 | Business Only Initiative | EU - Italy | Europe | Luca Nicolini, Marco Figueira | On Track | Confidence in delivering value on time: High – I don’t see an issue since we are already in L4 delivering value (not the full value). Confidence in delivering the full value: Medium 31March2025 Initiative rebaselined to FY25 FY24 Value leakage in Sales initiatives has been acknowledge but not quantified. Main drivers are the lower yield than plan and Service issues (not stable at 92%). The team is reviewing results/plan and will perform reforecast by end of September/Beginning of October. Update April 1, 2024: the initiative has been replaced by #73298 as of June 1, 2024 and that future value has been set to zero. | K: L5 | Completed | L5 | 2023-03-31 | 2023-12-15
Business Only Initiative: Domestic Sales Focus – Inside Sales - replaced by | 23282 | 7372 | Business Only Initiative | EU - Italy | Europe | Luis Aristegui, Marco Figueira | On Track | Confidence in delivering value on time: High - I don´t see any issue since we are already in L4 delivering value though not full value yet. Confidence in delivering the full value: Medium 31March2025 Initiative rebaselined to FY25 FY24 We have reached some of our KPI´s and new business is growing 22% vs. LY but still far from 50% ambitious growth that expect to reach in Q2. Growth at two digits, but need to confirm Q1 final data, expect to be around 13% while need to reach 22%. Service performance is not reaching the expectations and while NPS is improving and there is a churn reduction still needs to reach the expected levels so we can achieve our growth targets. I am still confidence we can do FY25 target. The initiative has been replaced by #73298 as of June 1, 2024 and that future value has been set to zero. | K: L5 | Completed | L5 | 2023-03-13 | 2023-05-31
Business w/ Tech Initiative: WS10 – ITALY ONE – Cross Sort Enablement | 86416 | 7391 | Business w/ Tech Initiative | EU - Italy | Europe | Fabio De Marino, Gianfrancesco Gramaglia, Luca Smeraldi | On Track | 11/12 - Completed implementation for all 21 sites 10/9 - activated 18 sites on 21. Overall plan on track: project end estimated for 31th Oct 9/25 - Activated 16 sites on 21. Overall plan on track: project end estimated for 15th Oct | I: L4 | Active | L4 | 2024-08-22 | 2026-01-23
Business w/ Tech Initiative: Governance & reporting | 11964 | 7394 | Business w/ Tech Initiative | EU - Italy | Europe | Guillermo Valdes, Marco Figueira | On Track | Confidence in delivering value on time: High Confidence in delivering the full value: High the initiative was an enabler to monitor progress , already closed long time ago. we had extra actions cancelled due to AS400 cancellation | K: L5 | Completed | L5 | 2022-12-12 | 2023-09-29
Business Only Initiative: Domestics IT Worldwide Sales incremental growth - | 23274 | 7405 | Business Only Initiative | EU - Italy | Europe | Joelle Wegener, Marco Figueira | On Track | 31March2025 Initiative rebaselined to FY25 This initiative has been replaced by #73298 as of June 1, 2024 and that future value has been set to zero. | K: L5 | Completed | L5 | 2023-03-06 | 2023-05-31
Business w/ Tech Initiative: Ops Tech Mobile - Lifecycle Replacement Italy | 83047 | 7414 | Business w/ Tech Initiative | EU - Italy | Europe | Giuseppe Casoli, Damir Babic, Gianfrancesco Gramaglia, Luca Smeraldi | Some Issues | # Update 2026-04-13 * Planview status: L3 status * SW requirement and development for MWI app defined but some issues/open points need to be solved * MWI SW development (Android based) completed * Purchase Order for Zebra TC77 completed and delivered to Peak Tech (3400 devices and annexes) * Capitals increase related to CLEAR 100009142 to face emerging Maintenance/IT costs finalized Next Setps: * Complete app update/Close open points identified during UATs * Finalize full implementation in next pilot stations with Gops involvement * Finalize the implementation of the massive deployment plan covering all FedEx stations, outsourced stations and delivery points # Update 2024-12-12 * Italy completed all POs for FOPD Italy scope Updated in Forecast for December 2024 * CAPEX * Italy completed all POs for FOPD Italy: € 3,498,801 * in CLEAR: €3,733,180 * OPEX * Vendor professional services PO is submitted: €150,015 * Vendor repair contract PO is submitted: €357,000 (PR: NL0000000071397) * In CLEAR: €3,808,0000 * Total: €4,005,816 * Conversion to USD:1.075269001033118 --> 4,307,329USD # Update 2024-12-05 * To support Italy on contingency plan, Israel is sending additional legacy equipment to Italy. Great collaboration of the community (Ido Shmueli) * Close to 95% of the expected Purchase Orders have been submitted. * Update from Finance 100009142 – Italy domestic scanning equipment * Approved capital = $4.8m * Spend to Nov FY25 = $0 * Operational reporting: https://myfedex.sharepoint.com/teams/CPEEquipment/SitePages/Reporting-Tools.aspx#lifecycle-progress-reports # Update 2024-11-29 * Over 50% of the required POs have been submitted. Amazing job from Giuseppe Casoli! * Spunte is too old to be used on new technology. Italy to consider to reprioritise moving over to DH2 ASAP # Update 2024-11-05 Below excerpt is from the regular update provided by Gianfrancesco Gramaglia. For the full overview of the Cross sort initiative, refer to their regular updates. Devices: o Clear approved o First hardware PO issued (89 required) Workorder INTL - Peak - Italy Domestics FOPD in progress to secure supply chain (vendors want commitment from FedEx) o MWI : developments not yet assigned to new supplier (Accenture) that hasn’t yet made the offer in terms of feasibility (cost /time) Ask to the Steerco o Support to have a supplier in charge of the MWI developments, with a clear commitment ( cost and time) o Contingency plan to be started (both for hardware purchase and software developments)- Giuseppe Casoli # Update 2024-10-03 * Velocity licenses activated. * ECH Greenlight received # Update 2024-09-17 # * Italy team to update for ECH greenlight (maintenance team to confirm resource allocation) --> Done. Awaiting update from ECH team to provide greenlight. # Update 2024-08-27 1. Awaiting PPM number (request in attachment) in order to submit for L3. # Update 2024-08-21 1. FODP Software: In progress with Italy team # Update 2024-08-12 Ferry: By accident set the status to L0 in stead of L2 approval. Please approve L1 again so we can submit for L2. Will be updated with the information from Luiigi/Giuseseppe. # Update 2024-07-25: * CLEAR is approved for Italy 1 FOPD: * Preference to go for Zebra TC77 equipment using the last final buy offer. This is risk free. Aligned and agreed with Fernando Manso and Giuseppe Casoli team. Order to be confirmed by 31st August, distribution between Oct-Dec to vendor. Vendor to deliver based on distribution plan. Distribution plan is complete. * If the final buy is approved, it leaves room for also including the racks and shelves. * Distribution planning started 2. SORT * MWW app (Spunte) is in final test phase. There is user experience feedback on whether or not to improve the screens using the capabilities of Velocity. This is currently under review * When the Velocity ENCORE approval request is completed, enabling Spunte can start on all DH2 devices in Italy. Test location to be | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-26 | 2026-06-30
Business Only Initiative: Increase revenue and volumes on 10 Express Domesti | 65934 | 7416 | Business Only Initiative | EU - Italy | Europe | Luca Nicolini, Marco Figueira | On Track | update 31March25 - REbaselined to FY25 update week 7: service issues are still affecting customers in a concentrated manner , e.g. Abraham Industries spa had 10 case of delays last week. If service is not reliable, customer trust and growth is lost. update week 6 : Jun revenue results above plan. Some issue detected on service on Eurofins Genoma customer (healthcare) with 10 shipments misrouted. Service recovery not possible. update week 4: nothing to highlight, still waiting to progress to L3 after having provided additional info required by Javier update week 3 : nothing to highlight, still waiting to progress to L3 after having provided additional info required by Javier update week 2 : on June 11, 10 express presentation has been shared with all sales update week 1 : mktg provided a draft of the reviewed 10 express customer facing presentation. It will be shared this week with all italian sales and stored in Mktg sharepoint. | G: L3 | Completed | L3 Data Migration - TEMP | 2024-04-02 | 2025-03-18
Business Only Initiative: Domestic Improvement (Yield) | 73298 | 7427 | Business Only Initiative | EU - Italy | Europe | Luca Nicolini, Marco Figueira | On Track | update 31March25 - REbaselined to FY25 update w7: nothing relevant to highlight; service level still below target (MBG 89,54%). update w6 : June revenue and volume results on new business are well above plan while Yield is below plan. As new business is monitored on "rolling 12 months" basis (as monthly average) still high is the impact of the lower yield new business on boarded in June23-Jan24. In Sept a review is planned with Pricing to evaluate and , in case of need, pricing on new acquisition will be further adjusted. **To remark that Service level on DOM is still far below the expections (from March to June stably below 90%) to attract high yielding business profiles.** update w5 : June KPI concerning Opportunity creation and Closed won have been updated. Both are above plan. update w4 : new calculated amount on Impacts and KPIs for dismissals have been provided by Pricing to avoid results overlap in reporting vs initiative #81504. MarcoF will update data in Wave update w3 : nothing to highlight update w2: KPIs forecast on dismissals elements have been updated according to the anticipated dismissal wave implementation. Update on related Forecast figures for Impact will be updated by Marco. update w1 : milestone 74238 and 74239 have been reviewed. related dismissal waves have been anticipated both to have effective date on Sep,1 (MB decision) | G: L3 | Completed | L3 Feedback Requested | 2024-02-20 | 2025-05-30
Business Only Initiative: Review TNT Domestic Fuel Surcharge IT | 81504 | 7673 | Business Only Initiative | EU - Italy | Europe | Mayla Giraudo, Monica Soncin | On Track | May2024: We have detected a potential duplication with #30778 Improve revenue quality via compliance surcharge IT DOM , as they are including revenue generated by Fuel surcharge in Domestic-we will clarify with SImon and Damir June 2024: we find not duplicity so we progress with the initiative , potential reforecasting in CWC pod due to lower compliance at higher fuel surcharge August 2024 : we have to reforecast #30778 because part of the customers in scope on this initiative are also in scope in another new initiative #81504, hance now no double counting. November 2024 +1.0% increase of % Fuel Index Reforecast : 4.84Mio +1.00% is the increase of % Fuel Index applied from November 1st, but we have to consider that not all customers pay Fuel Index. Some customers have the Fuel waver implemented so in this case the impact will be lower than +3.78%. | K: L5 | Completed | L5 | 2024-05-03 | 2025-03-26
Business Only Initiative: Handling insourcing | 11119 | 9109 | Business Only Initiative | EU - Italy | Europe | Luca Smeraldi, Arnoud Appels | On Track | “Confidence in delivering value on time: --> High (75-100% confident/likelihood), “Confidence in delivering the full value: --> Medium (50-75% confident/likelihood) | K: L5 | Completed | L5 | 2022-10-03 | 2024-07-01
Business Only Initiative: One Italy - Commercial Approach (Volume & Yield) |  | 90683 | Business Only Initiative | EU - Italy | Europe | Marco Figueira, Luca Nicolini | On Track | After review by Finance and Europe Transformation Office, it was decided to cancel the initiative since the volume reduction / savings will be capture in BP moving forward. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Italy Web Infrastructure Migration (TNT) |  | 105989 | Business w/ Tech Initiative | EU - Italy | Europe | SIMONA BERTELLO, Tommaso Barbieri | On Track | **Update September 2025** - Due the missing Disaster Recoverry infrastructure, it has been necessary to migrate to Azure Cloud platform. We are already working with Cloud Platform Team under Anthony Morgan to prepare the new web infrastucture. **Update May 2025** - Disaster recovery platform not defined yet and the targeted for production is not complited. The Initiative started from January 2025 and we expected to deliver value within 18 months. | E: L2 | Active | L2
Business w/ Tech Initiative: WS10 – One Italy – NNP Enablement | 88219 | 9036 | Business w/ Tech Initiative | EU - Italy | Europe | Alfonso Maria Pentangelo, Fabio Cavalleri | Some Issues | 03/21/2024 Poste has shared the quotation that was validated on FedEx side, we are going to set the technological and legal stream with Poste. The iniative is bus with tech in L2 but we have not yet an it architect assigned 11/26/2024 missing quotation by NNP provider (targeted now within December the 6th); corporate solution identified for international (FOPD team will be part of technical discussion with NNP provider), Poste would like to start the discussion after proposal acceptance so we've postponed the technical kick-off call; missing technical solution for data exchange of orange domestic shipments (IT to follow up) | G: L3 | Active | TEMP L3 - Enter L3 | 2024-09-02 | 2026-09-25
Business w/ Tech Initiative: DH2 to cons TNT Italy dom shipments |  | 140008 | Business w/ Tech Initiative | EU - Italy | Europe | Gianfrancesco Gramaglia, Giuseppe Casoli | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Prontopacco delivery enablement |  | 143240 | Business w/ Tech Initiative | EU - Italy | Europe | Alfonso Maria Pentangelo, Marco Figueira, Guillermo Valdes | On Track | Progressing with IT on next steps and guidance for development | E: L2 | Active | L2
Business w/ Tech Initiative: Italy: Enable D1 (FedEx First) for HAL |  | 165625 | Business w/ Tech Initiative | EU - Italy | Europe | Debora Magalhaes | On Track | This initiative was wrongly entered. I have already created another one which will replace this one. | C: L1 | Cancelled | L1
Business Only Initiative: LTL POD - Launch FDF product Intra-Europe |  | 162494 | Business Only Initiative | EU - LTL | Europe | Jefnie Merdyanto | On Track | Updating the financial business case for FDF | E: L2 | Active | L2 Feedback Requested | 2025-09-29 | 2026-01-02
Business w/ Tech Initiative: LTL POD: Develop flexible pricing model |  | 162497 | Business w/ Tech Initiative | EU - LTL | Europe | Arjan Pikee | On Track | 2025 12 17 Now discussion the financials | E: L2 | Active | L2 & CCH
Business Only Initiative: LTL Optimizing Station and HUB operations |  | 163488 | Business Only Initiative | EU - LTL | Europe | Reza van der Meer | On Track | 12/12/2-2025: With the enabler of the development of the staging and rollout plan (initiative) being rolled out towards the POC locations we are able to test the assumptions that we can increase loadfactor on the trucks from Italy and UK into the Benelux. FR and DE without adding cost. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: LTL Develop & Rollout Refined Staging Process |  | 164137 | Business Only Initiative | EU - LTL | Europe | Reza van der Meer | On Track | 2711/2025: On the moment the identification process and all steps have been finalized and signed off by the stream. That is also the case for the scanning procedure that was developed for the staging process within POC. Communication for the ERN Road network community has been developed and that is also the case for the needed job aids for the local team in the UK and IT that will start with the POC process as of January 2026. For local management their is also a job aid developed and from central a communication memo will be send out to all relevant stakeholders to inform them on the general backgrounds and start date of the POC. Last but not least a Q&A has been made to be added to communication both in general as the local teams involved with POC to answer possible questions. 12/12/2025: Final alignment on all documents for staging, scanning, identification and communication has taken place and all documents have been shared and aligned with both the IT as UK team (as POC start locations) No issues came out of those sessions and both locations also have signed off on the procedures and with that to start up the preparations for the POC start as of 1/1/2026. All final documents have also been shared with Ops and POD leadership and to take onboard any feedback. No remarks or feedback was received. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LTL Digital - Delivery by Appointment |  | 164143 | Business w/ Tech Initiative | EU - LTL | Europe | Pedro Casal, Jefnie Merdyanto | On Track | January 22nd 2026 Spoke with transformation specialist. Waiting for Entreprise Architect to be assigned and asked for the help of IT PMO. January 7th 2026 In L1, in agreement with FP&A, value is up to Medium ($ 10Million) | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: LTL Digital - GPS Tracking |  | 164148 | Business w/ Tech Initiative | EU - LTL | Europe | Francisca Ferreira, Jefnie Merdyanto | On Track | 23/01/2025 Wanting for an Enterprise Architectural to define T-Shirt Sizing. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: [ERN Growth] Intra EU Economy Freight umbrella cas | 66201 | 7399 | Business Only Initiative | EU - LTL | Europe | Hanh Phan, Burcu Sezer, Henrik Heizmann, Paul Wicks, Rocio Vargas, Sigrid Smits | On Track | move to L5 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-19 | 2024-06-28
Business Only Initiative: LTL POD – 18. A Dedicated Problem Resolution Team |  | 169902 | Business Only Initiative | EU - LTL | Europe | Rodolfo La Faietta | On Track | 10/09/2025: Road Freight Premiere Care (RFPC) desk definition 10/21/2025: CE Dashboard finalized to track resolution speed, customer feedback, and satisfaction 10/27/2025: Got pre-approval from CE Function for resources manning model 12/02/2025: completion of Future state problem resolution customer journey map 12/3/2025: finalized financial plan with FP&A and started the QA check with Transformation Specialist. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: LTL - Improved Pickup Data and Visibility |  | 186680 | Business w/ Tech Initiative | EU - LTL | Europe | Michaela Maravas | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: JP - Pricing: Expiring Pricing EG/ER, IS and Marke | 28208 | 6726 | Business Only Initiative | EU - NPS | Europe | Agnieszka Bernacka, Paul O'Donohue | On Track | Placed on hold whilst all breakpoints and cross overs are reviewed with a view to cancelling the initiative as it's covered elsewhere. | K: L5 | Completed | L5 | 2023-09-01 | 2024-02-15
Business w/ Tech Initiative: SU - Single Point Of Access Enhancement | 67236 | 6740 | Business w/ Tech Initiative | EU - NPS | Europe | Arthur Tops, Gaelle le Joncour | On Track | 2026-02-18: Initiative in L5. January Measure FY26 vs. baseline FY24Q3 shows Hero score improvement: Billing: +19%; Customer Technology: +19%, Clearance: +10%. We have improved to 77 from baseline 58 for Billing enquiries, to 80 from 61 for CT and to 82 from 72 for Clearance. Current performance with small fluctuation month over month. Build in progress of a granular Service Journey report based upon intent per contact channel aligned with DSM and COPC logic showing OSAT and Hero scores, and aligning with new Issue resolution measure. Review of hand over in CI team for further SPOA progress reporting in NPS Pod. 2026-01-28 initiative in L5 Planned closure Feb 2026. SPOA Reporting Follow up - Gaelle: Discuss with Philip at the O&D meeting to clarify his expectations regarding SPOA/FCR reporting and who should be involved/leading these efforts. •Kelly and Ruben: Raise the topic of SPOA/FCR measurement and any related work with Cansu during the 28 Jan call to understand if she is working on something specific. •Kelly: Bring up the topic of SPOA/FCR measurement and clarify expectations with Philip during the 29 Jan call. 2026-01-21: Initiative in L5. December Measure FY26 vs. baseline FY24Q3 shows Hero score improvement: Billing: +20%; Customer Technology: +10%, Clearance: +11%. We have improved to 78 from baseline 58 for Billing enquiries, to 71 from 61 for CT and to 83 from 72 for Clearance. Current performance with small fluctuation month over month. Build in progress of a granular Service Journey report based upon intent per contact channel aligned with DSM and COPC logic showing OSAT and Hero scores, and aligning with new Issue resolution measure. Review of hand over in CI team for further SPOA progress reporting in NPS Pod. 2025-12-17: Initiative in L5. November Measure FY26 vs. baseline FY24Q3 shows Hero score improvement: Billing: +18%; Customer Technology: +16%, Clearance: +12%. We have improved to 76 from baseline 58 for Billing enquiries, to 71 from 61 for CT and to 84 from 72 for Clearance. Current performance with small fluctuation month over month. Build granular Service journey report based upon intent per contact channel aligned with DSM and COPC logic showing OSAT and Hero scores. 2025-11-19: Initiative in L5. October Measure FY26 vs. baseline FY24Q3 shows OSAT/Hero score improvement: Billing: +23%; Customer Technology: +11%, Clearance: +10%. We have improved to 80 from baseline 58 for Billing enquiries, to 72 from 61 for CT and to 82 from 72 for Clearance. Current performance is stable with small fluctuation month over month. 2025-11-05: Initiative in L5. Cancelled Epic due to system bug on EPM Review. The EPIC work is completed and closed out, CQL Tick-box is tested and delivered in production March 2025. So this Planview work item #0109516 is also administrationally finalized; cancelleation as per advise of EPM Review contacts and aligned with Kara Terrel Coston/Shelby Stockbridge of DRIVE gorvernance. 2025-10-29: Submitted from L4 to L5 after 3 months data and deployment. Evidence uploaded to Planview. Alignment call on submission held with Nicola Thorn. Step approved by Dylan Davies. Call held with Stef Evens to address EPM Review for Epic #0109516 - Appears to be hold due to bug related to transfer of initiative from Wave 67236 SU - Single Point Of Access Enhancement to Planview. Allocations missing. 2025-10-22: September Measure FY26 September vs. baseline FY24Q3 shows OSAT/Hero score improvement: Billing: +21%; Customer Technology: +9%, Clearance: +11%. We have improved to 79 from baseline 58 for Billing enquiries, to 70 from 61 for CT and to 83 from 72 for Clearance. So the trend stays positive although with some fluctuations for CT & Clearance. No further actions required. 2025-10-08: Measure FY26 August vs. baseline FY24Q3 shows OSAT/Hero score improvement: Billing: +21%; Customer Technology: +19%, Clearance: +7%. We have improved to 79 from baseline 58 for Billing enquiries, to 80 from 61 f | K: L5 | Active | TEMP L5 - Enter L5 | 2024-02-01 | 2025-05-30
Business Only Initiative: JP - Account Creation and Minimum Customer Data St | 28761 | 6741 | Business Only Initiative | EU - NPS | Europe | James Pipe, Ravi Van Roy | On Track | 10/03/26 - The project has now reached and exceeded the KPI target as of this month due to a number of ongoing actions. 15/08/25 - The project is ready to move to L5. The KPI used to monitor the progress of the initiative will not meet its expected target of an increase of 50% due to the total number of accounts being created having reduced significantly. The KPI is based on a percentage of total, and therefore does not reflect the progress made. Attached is an Excel document, which shows the current KPI, baseline and target. If the same figures are expressed as a reduction in the number of incorrect accounts rather than an increase on the number of correct accounts, it is clear the progress is on target. The number of "incorrect" accounts has been reduced from a monthly average of 10,500 to 5,350 - a reduction of around 50% In addition to the initial KPI. the usage of dummy VAT numbers on business accounts has been reduced from around 30% to 20%. The usage of dummy phone numbers on business accounts has been reduced from around 25% to less than 5%. The elements to the KPI - VAT number and phone number completion as well as email address completion will be separately monitored in the second phase of the project - J2P Master Data Goverance - MDG - 98318 where we expect to see further improvements. 01/08/25 - The project milestones from this phase are now completed. All ongoing work items have been moved across to the next phase of this project - J2P Master Data Goverance - MDG - 98318. A leadership decision was made to transfer account creation activities from Cap Gemini and into WNS in order to align the standards and controls and improve the quality standards, based on the guidance from Internal Audits and the stalled progress and KPI results due to the lack of compliance by the BPO to the MDS standards. The majority of this transition was completed in May 2025, allowing the J2P team to concentrate on bedding in the processes, identifying and filling process gaps and improving the minimum data standards. The next phase will concentrate on transforming the processes to streamline and simplify them, and in turn produce Sales facing materials and guidelines. The other main priority for the team is working towards the governance framework that has now been given a sponsor. The implementation of this framework is being worked on concurrently with the items identified for the next phase of the project. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-05-01 | 2024-12-27
Business w/ Tech Initiative: SU - Issue resolution -Technical support (CMOD) | 67936 | 6742 | Business w/ Tech Initiative | EU - NPS | Europe | Ammar Jazzar, Marcus von Pein, David Potter | On Track | 3/31/2025 Updated: Money step will not be met as we have stopped the roll out of the survey to allow further redesing globally for CEBS , our plan is to peform further implmentation for the rest of EU countries to use the survey targeting July . One more note that the survey might be stopped in CEBS and Moved to another project waiting on confrimation from Eylem (GS1) waiting to understand further on the impact 9/3/2025 The final survey batch for wave 3 is going to be on 20th Sep which will allow us to move this one to L4 and also be ready to close and complete this intiative CMOD Email notification & post case survey launch 26 Oct: * UK + IE: already had email notification launched, now have post case survey added in the Resolve notification mail * FR, IT, DE, ES, BE, NL: email notification incl. post case survey launched * Support calls set up with the countries - some issues identified but no show stoppers - defects raised as needed - knowledge gaps closed via FAQs 04/22/2025 Money Step pushed to end Sep 2025 further work will be picked up as of 27/April as I/O is out of Office 9/3/2025 - The last wave of the survey as part of the last milestone will be completed on the 20th of Sep which will allow us to close this intiative and move it to L4 Based on the inputs from Philip we can now move this to L4 as already enabled for EU | I: L4 | Active | TEMP L4 - Enter L4 | 2024-02-05 | 2026-03-06
Business Only Initiative: Invoice Data Feed (mapping of all relevant invoici | 28878 | 6747 | Business Only Initiative | EU - NPS | Europe | Ioannis Zafeiropoulos, Diogenes De Leon | On Track | Continuous refinement of our mapping - Ongoing Support on getting all data for our KPIs (total nr of invoices, enquiries and credit notes/rebills) - Completed Evaluation of requirements of STC - Ongoing (ETA end of this week) | K: L5 | Completed | L5 | 2023-04-24 | 2023-07-03
Business Only Initiative: JP - Sales/Pricing: CHT moves governance | 38279 | 7078 | Business Only Initiative | EU - NPS | Europe | Rosalinda Novak, Maria Grodecki | On Track | For the last months we have been monitoring KPIs and checking if any adjustment needed. From this workstream perspective we have reached the objevtive and further steps will be taken by Invoice Accuracy Project in regards to CHT in EU. **New updates** Inc CoE DDC/Marketing support: error rate improved to 4% in March. Training: Sales training on CHT is progressing—E&E initiated a change to the onboarding training flow, and there’s also a request to extend this into overall CHT training. Hierarchy clean-ups: moving toward regular hierarchy clean-ups (WWS & ENs)—Vijay agreed to set up a call to align and confirm next steps. **Very brief KPI summary** Corrected moves: improved from 5% (FY25) to 4% (FY26). DDC/Mkt wrong moves: strong improvement, down from 37% (Oct) to 4% (Mar). Incorrect submitters: majority still driven by Sales, with overall volumes lower in FY26 vs FY25. Apollo cases: remain low overall, with a small uptick in FY26 H1. As the project owner I would like to pass now to L5. _________________________________________________________________________________________________________________________________________________ 07.01.2026 As we enter the fourth month of Level 4 (L4), we are observing a very positive trend in error rates during our audit of the INCoE tasks. December closed with a notable improvement: only a 13% error rate and zero incorrect decisions recorded. Our current focus is on enhancing task quality. This includes correcting broken hierarchies when a move originates from one, and ensuring that all moves include the necessary supporting information — particularly the "Proof Link", which is sometimes missing. If this positive trend continues through the first half of January, we plan to begin preparations for Level 5 (L5). In parallel, Apollo is also showing promising results (zero cases captured). However, we understand that this is due to INCoE terminating tasks impacted by pricing changes and adjusting pricing options accordingly. As a result, tasks are not appearing in Apollo — either because they retain a pricing configuration or have been terminated, with the new pricing option negatively affecting EU pricing. We are currently working on defining a process better aligned with the EU context, adapting the existing best practice that has proven successful in the US. ___________________________________________________________________________________________________________________________________________ 10.12.2025 After 3 Months in L4 we have accomplished the following Milestones: All DRIVE initiative milestones implemented FY24 Q3: US concluded testing phase; EU audits implemented FY24 Q4: Direct move support started; EU team defined FY25 Q1: US scoped additional segments; feedback from WWS FY25 Q2: Go-live with EU support team; automation prep FY26 Q2: Full implementation of DDC/CHT checks by INCoE Audits are in place Apollo is tracked on monthly basis Support model transition completed: US → EU --> INCoE Implemented (upgrade for IT NA accounts) FY26 Q2 - What we still need: The error rate from the INCoE is still high. We keep monitoring, sharing best practices and we decided to audit weekly one of the DDC/Marketing accounts (Implemented or rejected moves) so we can understand better what is still missing and how we can support better. Current error rate trend: Sep 26% - Oct 37% - Nov 22% Objective now is to move to L5 at the end of January. ____________________________________________________________________________________________________________________________________________________ 11.11.2025 Keep tracking KPIs and auditing INCoE tasks now for all DDC + Marketing account. Plann completly implemented. Error rate high (Sep 26% – Oct 37%). November TBC _____________________________________________________________________________________________________________________________________________________ 10.10.2025 This week, we had a call with the IN CoE team to review the SOP and asses | I: L4 | Active | TEMP L4 - Enter L4 | 2023-10-02 | 2025-09-08
Business Only Initiative: JP - Pricing: Apollo upgraded functionality | 38281 | 7079 | Business Only Initiative | EU - NPS | Europe | Agnieszka Bernacka, Paul O'Donohue | On Track |  | K: L5 | Completed | L5 | 2023-08-21 | 2024-02-23
Business w/ Tech Initiative: JP - Pricing: FedEx credit calculations | 38292 | 7081 | Business w/ Tech Initiative | EU - NPS | Europe | Kelly Gibb, Graca Machado | On Track | 08/04/2025 July KPIs added BAU Process is running, No support need and no major updates Approval received to submit to L5 07/31/2025 Check for L5 move 07/30/2025 BAU Process is running, No support need and no major updates June KPI added - 4 days, slight increase due to 1 CQL taking more than 30 days to be approved - however, still within target. Request to coaches for L5 submission. 07/02/2025 BAU Process is running, No support need and no major updates KPI for June to be added/ 06/25/2025 BAU Process is running, No support need and no major updates KPI for May added 05/20/2025 BAU Process is running, No support need and no major updates KPIs for April added - 2 days which is the lowest ever since the launch. 04/29/2025 BAU Process is running, no updates/support needed. KPIs added, slight increase due to multiple incidents impacting BAU disputes, however still within plan. 04/23/2025 BAU Process is running, no updates/support needed. KPIs for march will be added this week, behind track on publishing due to absence. 04/09/2025 BAU process is running, no updates support needed. 04/02/2025 * BAU process is running, no updates support needed. 03/26/2025 * BAU process is running, no updates support needed. 03/18/2025 * BAU process is running, no updates support needed. * February KPIs added and on target. 03/04/2025 * BAU process is running, no updates/support needed/ 02/24/2025 * BAU Process is running, no updates/support needed * January KPIs completed and on track. * 02/04/2025 * BAU process is running - no updates/support needed * January KPIs to be planned and updated * 01/29/2025 * BAU Process is running - no updates/support needed * 01/20/2025 * Actual KPI for December added and on targert - average 6.15 days, one anomoly in sample (63 days) due to complexity of case and more than 100k AWBs impacted. * BAU Process is running - no update/support needed. 01/16/2025 * No updates - BAU process is running * KPIs to be loaded before deadline 20.1.2025 01/08/2025 * Moved to L4 * 01/06/2025 * evidence added for L4 readiness and submission. Awaiting feedback from FP&A * Awaiting feedback from coach for L4 submission. * KPI samples to be selected for December results. 12/27/2024 * Awaiting update on DE works council - this will be moved to BAU follow up due to length of time to get approval,new process will be followed without the use of RDA - minimal impact to process. * Evidence to be added for L4 readiness and submission. 12/17/2024 * Agreed with Maria Grodecki - no further roll out of RDA required in Sales organisation with the exception of Germany WWS after W/C approval - further people to be trained in Sales co-ordinator team but does not impact project or timeslines as process is already live. * Awaiting update on DE works council * StC fully onboarded with new process, continue to monitor progress and educate if errors arise. 12/03/2024 * Process continues to be followed * Support requested via Graca Machado for DE works council approval, awaiting feedback from Daniel Seemann (MD CE) who is following up with LR contacts in country. * October and November KPIs to be added this week. 11/19/2024 - * Process continues to be implemented and followed * Tool enhancement live - will work with Matteo Fiorini (Sales Co-ordinator) on manual calculation requests to ensure tool meets requirements * Continue to push for Germany works council approval * October results to be published. 02/10/23 update: oS2C investigating defect and time lines for Fixing – Escalated to Ellen & Mike oWorkshop planned for Nov oEnd November Recommendation 09/10/23 update: Open elements in wave submission completed and moved to L1 for approval. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-07-31 | 2025-01-02
Business Only Initiative: JP - Account cleanup | 68277 | 7420 | Business Only Initiative | EU - NPS | Europe | Matthew Hudson, Rebecca Whitehead | On Track | 5/3 The clean is complete and ready for submisison to Level 6 | K: L5 | Completed | L5 | 2024-02-05 | 2025-05-30
Business Only Initiative: SR - MPUP Safety Net | 67926 | 7438 | Business Only Initiative | EU - NPS | Europe | Marco Notenboom, Christina O'Connor, Jose Maria Fernandez | Some Issues | 13Jan, projecht on hold until 1st week of Feb. 11/4: Escalate PDSM request to delay L4 date once approved, as it has been overdue. Monitoring 11/4: Safety report is down since 19 of Sept, on 3rd of Nov seems to be up and running but tested by Spain CC team and detect some invalid date. Architects reviewing so we cannot proceed with countries phase 1 go live. 11/4: GSP updates, walkthrough session done with Janet Chamdal, no issues to implement CMOD dispatch case. For nextday safetynet support she will select one country to test. 09/29: GSP countries introduction of Safetynet Next day with Janet Chamdal. Monitoring how the can implement due to their set up. Following call set up for 15th of October 09/29: identified Phase 2 countries with low DILO coverage. Meeting for this date with GOPS stakeholders to review how we can improve this discipline to enable Safetynet for Phase2 countries (29/09/2025) 09/12: information analyzed and shared to Sponsor for further guidance. L4 delay potentially identified due to different DILO coverage rate within EU countries. 09/10 : asked to architec team to download a table by country to identifiy DILO level per country as information is not in the backstate of the tool. 09/4 & 09/09: Meeting with Mette Larsen to fine tune some concerns related to CCD system duplicity with Safetynet. Agree to put on hold walktrough session as not all countries have a mature DILO process. 09/02/2025: BPM webinar completed. Initiative presented to all EU countries. 08/29/2025: Checklist meeting with Coach and FP&A stakeholder to prepare initiative to move to L4 wk35: BPM presentation sent to CE and heads up to all country CE leads for Safetynet support comms during BPM on the 2nd of Sept. Countries Walkthrough session during wks 37&38 scheduled. wk34: initiative update sent to all CE MDs wk33: end users testing solution 08/19/2025: Meeting with Sharon Bustin to review SOP handling exception to include Safetynet and system enhacement for Nextday. wk32: solution prepared for production wks31&32: UAT for data validation completed 07/15/2025: IO back ups until 11th of August (Almudena Manso and David Diges). On wk 32 UAT expected to be done for Spain with the new enhancement. 07/09/2025: P&E informs that the release of the new version of the booking page with Safety Net KPI has been postponed to August 4. A new data source must be realised and will delay Safetynet feature. We are still on plan to 2nd of Sept launch during BPM but alert P&E any other delay will impact the initiative lauch in EU. 07/07/2026: The new booking information is expected to be released this weekend in Station Insight tools. So UAT would run during wks 28&29 potentially. 06/16/2025: Initiative and timelines updated to CE MDs for information.Leads validation. 06/13/2025: Timelines agreed with CE P&E to lauch to EU countries during BPM on September (2nd of Sept). Brenda approved L4/money step to September, so Plan view updated accordingly. 06/10/2025: Architects confirm minor enhancement for Safetynet will be ready for UAT during the first week of July. 06/02/2025: Agree with Sotyanka Filipova to use BPM and CE Stand ups as communication channel for EU countries 05/28/2025: New architect contact due to changes in the organization with previous (Leena Lewis). New name assigned Anshuman Prabhakar. Meeting scheduled for 06/05 to understand requirements. 05/29/2025: Catch up call with Paul Pugal to clarifiy UK next day support. 05/29/2025: Meeting scheduled with Stoyanka Filipova to agree on best approach to launch Safetynet next day to EU countries. 05/20/2025: Request detail sent to Leena Domun to discuss about minor enhacement identified in Station Insights. 05/14/2025: Identified opportunity in Station insights tool to create a "buttom" to automatically downaload info for Safetynet next day. This enhacement will reduce manual workload in GOPS and avoid daily downloads from PDM. Sharing detail with Leena Domun (Project manager BI&Data Arquite | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-04-03 | 2026-01-29
Business w/ Tech Initiative: WS2 - SR – Pickup Capabilities Information Accurac | 82231 | 7450 | Business w/ Tech Initiative | EU - NPS | Europe | Markus Scholz, Jose Maria Fernandez | Some Issues | LBC finally updated - ready for L2 12-12-24 Call with Brenda McWilliams-Piatek on Friday 13th to validate initiative and seek for support. Initiative has overlaps with Front Door and PuD-PFS. Need clarification on how to proceed further or possible move under one of the other initiatives. 01-15-2025 still support needed - no architectural documentation. Technical enhancements partially already made - some adjustments are "wip" by Magic team. Seeking for feedeback about the MTP dates from Digital team "Tanja de Boer". without answer yet. 08-19-25 cancelation requested as topic has been integrated into a central P&E activity (Mark Timmermans/Thomas Hartshorn) | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: SR- MPUP Station management | 67930 | 7461 | Business w/ Tech Initiative | EU - NPS | Europe | Guillermo Valdes, Jose Maria Fernandez | On Track | **Jun 9th** Working on L5 move and checklist Good trend on last week PUP Effectivenes, target 96% April : 96% May : 95.5% last week 202523 : 95.9% , recovering trend and almost on target for June **May 28th** MPUP improvement plans will continue as BAU under central FPE Service Plan – starting next week all districts will build their plans again DILO has been deployed and teams engaged , 3 months with several webinars and best practice meetings Performance has reached the target in Effectiveness : 96% during March and recovering in May after some data issues in the dashboard, but I see a good trend again in recent weeks We will sunset NPS POD PUP Dashboard and all booking performance will be in 360 navigator Insights- Bookings , an EU table league will be deployed and successful pick up will be a key priority metric ASK TO MOVE TO L5 ** May 27th** We had last meeting with Country leads on May 27th , we shared last results , trends an update per country We have review the dashboard strategy and DILO sharepoint We have priotitized performance per country and a clear ASK to countries below 96% target Countries are preparing action pLans to Central P&E ( Thomas Harston) to be rpesented next week June 5th We will update in attachments , and monitor - support suring next month MIlestones are completed and project close as it will be running as BAU in Service Forum CountryTotal Request VolumeActive VolumePUP Effectiveness %Missed Scanned %Missed Scanned VolumeNot Scanned %Not Scanned volume GB500,242401,42598.1%1.0%39130.9%3,749 DE318,835256,37997.0%1.8%45881.2%3,022 IT140,411111,33394.9%1.9%20723.3%3,647 PL136,552127,04885.6%2.5%322011.8%15,032 ES126,89799,58796.8%2.5%24720.7%710 NL114,04275,69397.6%1.4%10231.1%828 FR81,28068,86880.6%6.5%445312.9%8,898 BE62,89348,13797.9%1.3%6280.8%382 PT61,64047,14496.7%2.1%9811.2%589 CH55,56540,07398.6%0.5%2020.9%348 RO49,03136,34997.7%1.9%7030.4%151 SE43,59334,95797.0%1.7%6101.3%447 TR39,63230,24593.4%1.3%3905.3%1,607 CZ34,68730,42697.2%1.9%5900.9%268 HU32,98224,49097.5%1.5%3641.0%244 AT26,93422,50697.7%1.4%3190.9%195 DK24,53219,81096.9%2.5%4910.7%129 GR24,00319,04994.8%1.6%3083.6%684 FI17,76615,46492.4%2.0%3065.6%866 LT16,73213,85199.1%0.7%990.2%31 IE16,27012,67698.5%0.8%1070.6%80 IL14,19811,11496.6%2.4%2700.9%104 SK11,9259,69899.1%0.5%480.4%42 BG11,2578,68498.1%1.0%870.9%82 NO7,9076,95189.4%1.1%749.5%662 LV7,7756,46498.9%0.9%610.2%13 SI6,9695,66995.5%3.8%2150.7%41 EE6,1194,66999.3%0.4%200.2%11 LU5,3993,19399.3%0.4%130.3%8 CY3,9303,12095.5%2.2%702.2%70 MT2,9842,01196.0%0.0%04.0%81 HR52052098.7%0.0%01.3%7 AM49236098.1%0.0%01.9%7 RS37232693.6%5.2%171.2%4 MD34023499.6%0.0%00.4%1 UA29123597.9%0.9%21.3%3 GE228113100.0%0.0%00.0%0 AZ14482100.0%0.0%00.0%0 IS1341290.0%0.0%0100.0%129 BA554586.7%13.3%60.0%0 MK433844.7%2.6%152.6%20 GI22220.0%0.0%0100.0%22 AL201963.2%15.8%321.1%4 ME151573.3%26.7%40.0%0 PS330.0%0.0%0100.0%3 Total2,005,6611,599,22495.5%1.8%287302.7%43,221 ** May 23th** Working with countries in action plans and best practice sharing continued trend of improvement last 2 weeks twe are recovering data quality , we arealso impacted by holidays and eastren in term of volume PUP Effectivenes, target 96% April : 96% May : 95.5% last week : 95.9% , recovering trend ** April 23th** Working with countries in action plans and best practice sharing continued trend of improvement last 2 weeks the data uploaded to Datawarehouse is not complete , we are asking FAMIS team in US to review and correct, will follow up ** April 15th** Working with countries in action plans and best practice sharing Continued trend of improvement in PUP Effectivenes, target 96% 2 | K: L5 | Completed | L5 | 2024-04-08 | 2025-05-30
Business Only Initiative: SR - MPUP Closing the gaps | 67929 | 7472 | Business Only Initiative | EU - NPS | Europe | Marco Notenboom, Jose Maria Fernandez, Emily Woestenenk | On Track | 2025 - 03 - Dec: Initiative will remain in L4 for additional 3 month to work on getting the penetration rate to the expected levels 2025 - 21 - July: L4 check 2025 - 08 - July: * Data ready for sales * more than 100% increase in collaborative shipping volume 2025 - 30 - June: defect # 41627 resolved. 2025 - 24 - June: Postive: o184% increase in the number of importers using Collaborative Shipping, compared to one month prior to launch. o32% increase in the number of shipments created, compared to one month prior to launch. o27% increase in the number of successful pickups, compared to one month prior to launch. o Additional resources have been assigned to digital team to clear up the remaining development itemsent items Issue: Defect 41627, Worldwide 600+ booking attempts per day get error message and are unable to be shared. Extra: We now have data related to high volume RPI customers – ask, how do we approach sales ? 2025 - 17 - June: The 50% pilot has been impachted by defecht 41627 resulting in 600+ shipment per day not able to be shared, Digtal team is implanting a soleetion today (17th off june) GTM camphighn legal and Markting aproved we are still waiting on 1005 share to go live to proceed video from AMEA is ready - meeting planned for roll out EU 2025- 20 - May: 50% of online RPI will activate across EU as test for moving the share button as the default option GTM email campaign willl only start once we go 100% live, however we are progress in getting article ready in local languages in order to save time once we do go 100% Next CE stand up pack will have article about collaborative shipping 2025 - 05 - May: GTM, is still with the legal review they had some questions, I keep you posted as soon as the copy is approved. Next step Smartlink for translation 2025- 24 -april: The main development item moving the share bottom to be the default option is potentially getting delayed again to end of May ( this will be the 5th time it get delayed) 2025-15 -April: new development team stared, possible delay as there re-prioritizing the development items for collaborative shipping. G2M on track 2025-April: L4 moved to 30th of April due to Digtal delay 2025-April: Email campaign/news leather to existing customers stared - update April 7 : First draft: Latest Friday 11 April EOD Second/Final version : Thursday 17 April Brand and legal review: 17 April - 24 April | K: L5 | Active | L5 | 2024-04-10 | 2025-11-25
Business Only Initiative: WS8 - International churn reduction (EU CX Bunker | 83118 | 7624 | Business Only Initiative | EU - NPS | Europe | Philipp Muenchenberg, Marco Russo | On Track | Collaborated with Marketing, FP&A and NPS stakeholders on updating & clarifying content for the L3 submission. Agreed to split Sales Corrupted Selling Time from the value related to reduced churn. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-01 | 2028-01-31
Business w/ Tech Initiative: WS8 - GS4 – CED Data Visibility, Intent Classific | 82156 | 7655 | Business w/ Tech Initiative | EU - NPS | Europe | Simon Plunkett, Mal Graham | On Track | 25/11/2025 * Moved to L4 18/11/2025 * Initiative passed QA and approved to move to L4 11/11/2025 * Continue to finalise requirements to move to L4 as per timelines * Closure of EPIC last remaining step, awaiting confirmation 21/10/2025 * Continue to finalise requirements to move to L4 as per timelines 14/10/2025 * Meeting held to progress move to L4 as per timelines (31st October) * Actions to finalise L4 move to be taken this week to then pass to Finance review * Development will move to BAU after L4 07/10/2025 * BPM webinar and EU launch (7th Oct) * Continued development of additonal case types (in additon to original scope) and preparation for PI5 * Investigations in improving Intent alignment acorss channels (esp. Voice) 30/09/2025 * Continue preparations for EU launch (BPM webinar prep, training) * Investigations in improving Intent alignment acorss channels (esp. Voice) 23/09/2025 * Continue preparations for EU launch (BPM webinar prep, training) 16/09/2025 * Mandatory Chat intent update tested and sucessfully moved to production 12th Sept 09/09/2025 * System update scheduled for 15th Sept for Chat intent to be mandatory * Intents and Touchpoints shared on CE High Performance Steerco 01/09/2025 * Rollout continues for BRIDGE. Alignment required with Sharons team on communication for EU. Call scheduled this week to agree approach 26/08/2025 * EU Bridge go live is planned w/c 3rd September * All other regions went live this week * Training added to rep schedules throughout the next 4 weeks - 1 hr 15/08/2025 * EU Rollout for Bridge agreed with WTF for September 29/07/2025 * Einstein to be used to build Phraseology Framework in Pi04 with Agentforce explored for future capabilities * Rollout plan under review - Awaiting on EU WFM confirmation 22/07/2025 * Touchpoints communicated in Weekly Standup 19/07 * Bridge defects fixes successful * Rollout plan for Bridge to be finalised * Contact creation flow for bridge to be improved based on user feedback * Phaseology currently under exploration - Einstein and Agent Force capabilities being explored 14/07/2025 * Touchpoint Comms to be included in this weeks Standup pack * Defects identified through BRIDGE Pilot due to be released into Production this week - 17th July * BRIDGE Rollout - US lead working with WFM in the markets to create rollout plan - Estimated End of August delivered to all reps. 08/07/2025 * Pilot complete, feedback in process of being reviewed * Design change possibly needed to avoid additonal handling time * Continued alignment with Marketing on GPS project. 01/07/2025 * Pilot ongoing, feedback submission open until 7th July * FSH Intents UAT signed off * Go to market discussions started with CE L&D/BPM 24/06/2025 * Pilot will begin this week with 380 reps across US,APAC & EU. Self learning followed by immediate use of new functionality. Support channels set up between regions and Mal. * GPS discussions ongoing. 17/06/2025 * Move to production successful, ready for (Global) pilot w/c/ 23rd June * Training materials in process of being finalised (1-2 hours self learning for POC) * Discussions on non-US GPS information started 10/06/2025 * Bridge Phase 1 UAT complete. Move to production this week in readiness for pilot w/c 23rd June 13/05/2025 * Touchpoints (human assisted) and Bridge Phase 1 moving to UAT by 14th May 7/04/2025 - 14/04/2025 - 21/04/2025 - 29/04/2025 * Work in progress by the scrum teams - regular demos provided to share progress 31/03/2025 * Work in progress by the scrum teams * Human-assisted transactions screens tested by CC Reps who provided positive feedback. * Monthly governance call with MDs took place 24/03/2025 * PI event took place last week: 2 scrum teams of CED ART assigned to execute GS4. * VEGA will focus on Human-assisted transactions and BRIDGE, with the goal to deliver those in the June timeframe. * MACGYVER will focus on Intent classifications, with the goal to deliver Email, Webform & Chat in the June ti | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-02 | 2025-10-31
Business Only Initiative: WS8 - GS5 – Improve internal handling and visibil | 82157 | 7680 | Business Only Initiative | EU - NPS | Europe | Sharon Bustin, Pavla Burghout Votapkova | On Track | SB: 10/9 All on track nothing to add SB: 3/9 All on track nothing to add SB: 13/8 All on track nothing to add SB: 27/9 nothing to add all on track. SB: 25/6/25 nothing to add all on track SB: 16/6/25 nothing to add SB: 11/6/25 Nothing to add SB: 4/6/25 - nothing to add. SB: 28/5 We are going to close off our milestones and we will join the new initiative that is being set up. No support needed. SB: 21/5 We met with Samantha and Robert and Marco to discuss next steps for the CT initaive. We are pending the initiatve be finalised in Planview and then understanding the timelines, currently this is still not clear. Marco has requested the critical milestones and timelines, so that we can get a better view. SB: 29/4 Further discussions with Samantha Gomes and Robert Crooks took place last week, they have advised that the plan view request is in progress, but we dont have an Initiative number yet. They aim to have this in PI3 June/July and deliver in August, dependant on resources though. I have offered support to help identify critical milestones, Laura will remain in the project. We have asked for IO name so that we can invite them to join the NPS POD. SB: 29/4 No risks/support needed. SB: 23/4 No risks/support needed. SB: 15/4 - CT team have decided to stand up a new Planview Initative for the move to CED. We will keep our refinement milestone open to keep touchpoints open as per Philipp. Expected delivery date is approx Sept 2025. SB: 9/1/24 - Milestone 98618 - After discussions with Samatha Gomes ( IT Manager) and Robert Crooks, the development of features needed by the CT Support Team will not happen this side of FY25 due to other higher priorities. The suggestion is that we either extend the milestone to accomodate the new timelines or we cancel this milestone off from our intiative an they start a new DRIVE initiative, both of which will only be scoped in PI3. This needs to be discussed with Brenda. Philipp is happy to extend the milestone in our initiative to support them. I have asked for confirmation of whether there are cost impacts, previously we were lead to believe that there were no development costs as such, that it was only support needed to move to CED, however, it seems that there are discussions around features which will need to be costed. I am waiting for further feedback from Samantha/Rob. SB: 26/3 Milestone 98618 - The project manager Asha Jutta has been OOO periodically and we have not had any definitive updates. We have spoken to Rob Crooks in IT to see if he can advise the status of the development. He has advised that - due to the 1 source priority the development for CT moving to CED - had not been planned into a PI yet and was supposed to be planned for the up coming PI, however, CT Support Team have not provided their final list of requirements so that the IT could plan the features in CED. We have spoken to Samatha Gomes(IT Manager) and she has allocated another person in her team to pick this up whilst Asha is OOO, however, the development will not be ready in May to achieve the milestone date. This "milestone" for CE - is to update our SOP, however, as we are not able to do this, due to the delays with the CT Support initiative, we will have to do the CT SOP update as part of BAU, so i propose that we close this "cancel" this milestone for the purposes of our CE initiative. This was listed as a "Refinement" and does not impact the Money Step which has already been completed. SB: 18/3 Milestone 98618- the project manager for this activity being led by CT has been off ill, for quite some time. We have spoken to the manger of the team to get an update on the current situation. We understand that the technical development on the CT side is still ongoing and we are pending completion date. Once we get a view of what has been included into the design, we can start to update the SOP. At the moment, we do not have clarity on the timelines and for this reason the "timeline" of end May could | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-21 | 2025-05-30
Business w/ Tech Initiative: WS8 - GS6 – Knowledge Management 2.0 – System Enh | 82158 | 7681 | Business w/ Tech Initiative | EU - NPS | Europe | Sharon Bustin, Rebecca Wilson | On Track | SB: 10/9/25 on track nothing to add SB: 3/9/25 on track nothing to add SB: 13/8 all on track , nothing to add SB: 25/6 all on track. Nothing to add SB: 4/6/25 working to submit to L4 SB: 28/5 All milestones are now complete. Working towards submitting to L4. SB: 21/5 The last 3 milestones are on track, no risks/support needed. SB: 7/5 Milestone 85007 - Go live new governance was completed on 6/7. We have 3 milestones left 84994 - which is related to the onboarding of the FTE, we are in Week 6 now. Onboarding is planned to be completed by end of may. 85006 - all delieverables to be completed by end of may. 85008 New content to be available by end of May. No support/risks. SB: 29/4 Onboarding continues of new FTE. SOP is now finalized and we are sharing it with UK and PL. for COPC readiness. No risks/support needed. SB: 23/4 Onboarding continues. No risks/support needed. SB: 15/4 Milestone 84994 TE onboarding continues. All other activities are on track. No risks/support needed. Governance SOP has been finalised and has been shared with COPC. COPC Interview completed today 15th April - pending feedback. But do not expect any negative feedback based on the evening review. SB: 9/4/25. Milestone 84994 FTE onboarding is in progress. No risks / support needed. SB 26/3/25 Milestone 84995 - is complete. We are currently focussed on the Onboarding of New FTE milestone which is due to be completed at end of May. No risks/support needed. SB: 18/3/25: Milestone 85009 -complete. Milestone 84995 SOP finalisation is due end of month and ontime for completion. Reporting: we are focussing on sorting out reporting, as we still have some issues with the ability to filter on country properly, which is impacting our ability to report accurately, however the impact is minimal and will be resolved and then we can backdate the reports. No risks / support needed. SB: 10/3/25: Milestone 85009 - lessons learned session taking place today. (Milestone is due this week and ontime for completion) Milestone 84995 SOP finalisation is due end of month and ontime for completion. Reporting: we are focussing on sorting out reporting, as we still have some issues with the ability to filter on country properly, which is impacting our ability to report accurately, however the impact is minimal and will be resolved and then we can backdate the reports. No risks / support needed. SB: 3/3/25: Milestone 84988 - stress tests completed for SOP governance. Milestone 85009 - lessons learned is due next week and ontime for completion. Milestone 84995 SOP finalisation is due end of month and ontime for completion. No risks / support needed. **SB: 26/2/25: Focus this week:** Milestone 85008: SOP content creation continues but focus is on reviewing feedback received so that we can reply and update to demonstrate practise of Ontime Update metric. Focus is also on Content Accuracy. Milestone 84987, 84988 - governance creation continues in readiness for COPC by end of March. Ontime Metric and Content Accuracy metrics - work is being done to evidence how we determine these metrics. We have agreed with the UK the move of their International articles to the central database and we are supporting this work at the moment. The UK will continue to own their domestic articles for COPC Audit in Apiil. Milestone 84994: 2 FTE have been hired, contracts signed. Start date is 1st April. **SB: 17/2/25: Focus this week:** Milestone 85008: SOP content creation continues but focus is on reviewing feedback received so that we can reply and update to demonstrate practise of Ontime Update metric. Focus is also on Content Accuracy. Milestone 84987, 84988 - governance creation continues in readiness for COPC by end of March. Ontime Metric and Content Accuracy metrics - work is being done to evidence how we determine these metrics. We are also discussing with the UK the potential move of their 149 articles to the FedEx Intl database for the purposes of the Audit. Milestone | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-24 | 2025-09-05
Business w/ Tech Initiative: WS8 - T1 – Conclusive info about shipment status | 82227 | 7682 | Business w/ Tech Initiative | EU - NPS | Europe | Hugo Gil C. Neves, Rupesh Agrawal | On Track | 23/09/2025 Held a meeting with Gary and the two EPIC owners (Sonam and Ndaya) to review and work toward finalizing the EPICs required for moving to L4; still pending finalization 29/08/2025 Scott Harkins accepted the proposal to close the initiative and move the final features to the Digital Deflection Initiative. I’m at the stage of moving to L4, but I’m waiting for Sonam Sharma and Nadya Kledzik to close the Epics under their responsibility. 22/07/2025 I’ve asked Martje and Brenda to postpone the "money step" milestone to early September and am currently awaiting their response. The STAT44 milestone has been confirmed as released. The milestone “Limit the number of duplicated scans” is scheduled for release on 25/07/2025. I will update the due date in Planview accordingly. The meeting with the US team to address the T1 milestones will be rescheduled to ensure the availability of key stakeholders 16/07/2025 After Martje spoke with Austin, he asked his team to schedule a meeting to explore how our request could be folded into a broader workstream. We will be having a meeting with the US Team do adress this on July 22nd 08/07/2025 Update about the potential issues related to two milestones: 1.**“Regional customization of tracking verbiage”, “Differentiation between international and domestic messages”.** As mentioned in the previous NPS Pod there is a new initiative called the Problem Resolution DRIVE Initiative (aka digital deflection), which includes a component focused on tracking flexibility. This will allow for regional customization of tracking verbiage and differentiate between international and domestic messages. Waiting for the following information from the visibility team = Exact name of the initiative, Initiative Owner, State of the Initiative in Drive, under the scope of any program and name of the program. Update about the potential issues related to one milestone: 2.“**Visual representation on the package travel itinerary**”. As mentioned in the previous NPS Pod both legal teams from the US and EU denied the idea. I reached out to Bernhard Hofer but they have no trace of legal involvement in this specific project. They have to look at this again from scratch. I reached out to Rupesh to ask the US legal Team to identify the EU counterpart involved in this process in the past. 23/06/2025 After last week’s discussion with Rupesh, I identified potential issues related to three milestones: regional customization of tracking verbiage, differentiation between international and domestic messages, and the visual representation on the package travel itinerary. I expect to gather more details and have a clearer status after the Visibility Regional Call next Thursday. 06/06/2025 According to Rupesh: "Based on the latest update from the SEP team, the STAT44 changes are now targeted for release on July 12, which keeps us on track to meet the L4 milestone." 03/06/2025 According to the last update from the US Team (Geeta Prakash Tahiliani) the focus is to move STAT44 and other initiatives into production approximately one to two weeks before the July CSR (scheduled for July 12th), provided that they have testing support. 27/05/2025 Currently the US Team are still looking for the UAT´s after 5/31. Still working to get the next release date 23/05/2025: STAT44 Feature UAT´s are scheduled for May 31st. Waiting for the confirmation of the release date May 20: Important heads-up regarding STAT44, our biggest feature. There’s a risk of a delay in the planned schedule finish date. Rupesh mentioned that the team is facing technical challenges that may push the UAT phase to the last week of May. Consequently, the release date will be prioritized accordingly. Money step as been updated accordingly. May 15: Planview updated with new timelines and corrected moneystep. Hugo is no the primary IO and Rupesh (global visibility team) is the back up. April 23: first meeting with Hugo (new IO) to introduce tra | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-19 | 2025-11-28
Business Only Initiative: WS8 - T5 – EDD Enablement | 82230 | 8867 | Business Only Initiative | EU - NPS | Europe | Akanksha Padhi, Bikram Virk | On Track | Ma 25 : next roll out of 400 lanes in May will bring 98% coverage to EU inbound volume Nov 12 : with the new roll out, we have achieved 84% coverage for EU IB lanes. Remaining 16% are dependent on the fix needed to provide the ability to launch more lanes in one go. US is looking into this. Sep 23 : same as last update. Sep 09 : Delay in complete roll out - Dataworks team unable to push all remaining lanes into production. They have been now provided a list of lanes prioritized according to volume and they will confirm how many of those cam be pushed to production pre-peak. Aug 20 : working on finalizing list of lanes to launch in September Aug 4 : Suppression logic in place - no new notifications to be riggered to the recipients if EDD has confidence less than 80%. Working towards finalizing the next lanes for roll out. June 4 : Next roll out planned in July around release of the notification suppression fix. May 5 : 17 intl lanes rolled out on Apr 28th. Now we have GDPP EDD coverage for 70% of EU IB volume. Next roll out planned in July around release of the notification suppression fix. April 15 : Planned launch date for teh 17 international lanes is confirmed to be April 30. April 4 : 17 international lanes planned for launch in April. These will increase EDD coverage of EU IB by 4% March 20 2015 : same as March 11 update + call planned for March 27 to share recommendations on next steps with management. March 11 2025 : we launched 10 international lanes in O-D pairs and are seeing an increasing in EDD change rate and call volume. We are currently assessing this with the global team and Global is also working at assessing the impact of Customs Clearance on EDD for international lanes. The above assessment will help develop recommendations for further roll out of international lanes. RESOLVED (update from March 11) - Nov 12 2024 : 1. we launched 130 lanes on Oct 30th and are monitoring metrics, will update management in the last week of Nov on the results so far. 2. previous plan was to launch all DOM/Intra EU lanes post POC. This is not feasible as some lanes have EDD accuracy of 20%. Lanes with >60% accuracy have been identified and are being priortitzed for a tentative Jan launch (depands on SEP load and global needs to confirm timelines) - this will also be discussed in the above update. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-05 | 2026-04-24
Business w/ Tech Initiative: SU - Improve dispute handling by streamlining proc | 4763 | 9039 | Business w/ Tech Initiative | EU - NPS | Europe | Wouter Geysens, Gaelle le Joncour | On Track | reviewing dates deliverables and L3 will be submitted (review done with Nuria and Emily) | K: L5 | Completed | L5 | 2023-05-01 | 2024-09-30
Business Only Initiative: WS8 - GS7 – Case & Contact Propensity Reporting o | 82159 | 9093 | Business Only Initiative | EU - NPS | Europe | Tomas Drasar, Marcin Kuzma | On Track | w37 Action plans defined accross all regions w33 •SEEU – Exploration sessions took place, focus on customers SOLMAZ, ARAS CARGO and SOUOZ from TR for investigation of route causes. Next update call 06/08/2025 with Petya and TR SMEs - FOXWAY from EE handled in GR to be deepdived – Next update call 08/08/2025 with Petya and GR SMEs •FR/NORDICS -Exploration sessions with Andrea took place. Sophie Chevallier Kretsch assigned to the project, returning to office 18/08/2025. Plan is to explore first France and then move to SE. Fragkiskos to support with opportunity identification until nominee returns to office. •DACHPL -Exploration sessions with Michael Hobbs took place. Initial focus in DE customers – rest countries to be further investigated. Next update call 06/08/2025 •UKIE -Mark Hill nominated – to be back at the office 11/08/2025, Fragkiskos to explore opportunities in preparation for intro call. •CLM – Farfetch •Report already in use to support improvement initiative for contact reduction. Update call planned 08/08/2025 •Report Development : Combined POF with CASE and AWB data details provided according to feedback to enable further opportunities w18 Issue with call reporting, working on fix w17 Finalizing Dashboard, adding chat and email w15: 1) Dashboard - email / chat ... working on including the data 2) Findings - CLM onboarding - agreed with CLM team (Lutz) to work on plans to introduce the tool to the CLM team in next weeks, plan is to use it for QBR s to have specific duiscussions if needed - LSP - main group of offenders, waiting for feedback from Will on next steps - Waste Cases (cases resolved too fast) - new initiative kicked off with GTS P&E - Customer in focus - Cettire, main action around service change cases / why FDMI not used ? w14: 1) Dashboard - email / chat ... we have the data, testing it, on Wed meeting to understand when we can include 2) Findings - CLM onboarding - waiting for feedback from Will, but in paralel discussion with CLM team (Lutz) - LSP - main group of offenders, waiting for feedback from Will on next steps - Waste Cases (cases resolved too fast) - waiting for feedback from Mark Ruddock (send reminder last week) - Customer in focus - Cettire, main action around service change cases / why FDMI not used ? w12: 1) Dashboard - email/chat ... update expected this week - FSH dashboard created NEXT STEP: Update the dashboard with emails and chat 2) Findings - short time resolution - waiting update from Mark Ruddock NEXT STEPs: - Will be following on FSH usage - Preparing customer upadtes w10: - Cases with fast resolution identified and sunmmary shared with IR steerco - Waiting for feedback on email and chat CE Datalake reporting possibility inclusion in next PI planning (promised to be available second half March) - Preparing Feb snapshot of the progresswith top propensity customers | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-01 | 2026-04-08
Business w/ Tech Initiative: WS8 - GS2 - Digital Issue Resolution Improvements | 82153 | 9104 | Business w/ Tech Initiative | EU - NPS | Europe | Eylem Zagli, Mark Wareham | On Track | **16 December 2025** Having noticed a drop in Issue Resolution in the VVA, joint investigation with PolyAI is being completed. While it’s too complex to attribute the change to a single root cause, the decline in Resolution appears to be driven by the following factors: •A 5% increase (since September) in shipments scanned with a “Delivery Exception” •An increase in shipments scanned with “Delivery Updated”, alongside a 1.5-day increase in the delta between the original Committed Date and the Estimated Delivery Date, indicating a rise in missed deliveries •A significant decrease in Resolution for Delivered shipments in the UK Overall, this suggests the decrease in Resolution is predominantly driven by operational issues. This week already, 30% of unresolved EU FedEx calls are associated with shipments that have an open case — 10% higher than two weeks ago. Continued monitoring of the behaviour will take place. Looking across the other regions, APAC and LAC are also having similar reductions on the PolyAI environment, in addition the US Nuance IVR environment is also experiencing a reduction and they are tracking a rise in repeat callers completing the survey each time they track a shipment. **18 November 2025** * Initiative is now in L4! * KPIs will be monitored for the next 3 months, before closing the initiative completely. * Lessons Learned will be conducted to be documented and shared back with the organization. **11th November 2025** * Pushing the initiative to L4 today **04th November 2025** * Completing final preparations for Money Step. **28th October 2025** * Final Implementation Milestone was completed on the 21st October with the completion of the Tracking Enhancement activity. * Preparation towards L4 Step continued. **21st October 2025** * VVA Tracking Enhancements completion was due to be completed by PolyAI on the 17th October, however there was a delay in this being released from PolyAI QA. A revised date of the 20th October was confirmed by PolyAI, but due to the disruption caused to PolyAI through the Amazon Web Services outage the push to production has now been planned for the 21st October. **14th October 2025** * VVA Tracking Enhancements completion remains on track and awaiting PolyAI confirmation of when the configuration will be ready for test and push to production prior to the 17th October **07th October 2025** * VVA Tracking Enhancements completion remains on track and awaiting PolyAI confirmation of when the configuration will be ready for test and push to production prior to the 17th October. **25th September 2025** * VVA Tracking Enhancements completion of the improvements will be in the next PolyAI Sprint, completing on the 17th October, confirmed in the PolyAI Demand Sprint meeting held on the 24th September. The dealy was caused due to increased engineering time needed and therefore the improvements have had to be split across Sprints. The L4 date has been changed to the 31st October to accomodate implementation activity. **23rd September 2025** * As reported last week, Tracking Enhancement improvements on status DL+DY(A52) was released on the 19th September * Further Tracking Enhancements planned to be delivered by the 6th October and are in the current delivery Sprint. * As the next Sprint will be after the Money Step date, the proposal is that the Money Step date is amended to incorporate the release and this will be requested in the NPS POD call on the 24th September. **17th September 2025** * Sep 19th Release is on track with no issues, which will deliver the Tracking status enhancements for 2 most problematic status codes/events. * As per Polyai's recent updates, the 2nd sprint of Tracking Enhancements updates will be delivered by October 3rd and there is risk to complete it by 30th September which is our Money Step. * Besides, not 100% of the tracking status code exceptions will be covered yet by the end of the 2ns sprint. However 30% of the most frquently occur | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-15 | 2026-03-06
Business Only Initiative: Implement key STC KPIs | 28303 | 9105 | Business Only Initiative | EU - NPS | Europe | Simon Plunkett, Anita Loureiro Mato | On Track | Confidence in delivering value on time are High | K: L5 | Completed | L5 | 2023-04-03 | 2023-09-15
Business Only Initiative: WS8 - GS3 - Minimum Quality Mgmt Framework | 82155 | 9133 | Business Only Initiative | EU - NPS | Europe | Marco Russo, Andrea Mohrhardt, Jodi Gough | Some Issues | **12th September 25** Training STC & GTS: •12 Minimum Quality training (Best practice) sessions by CE (Jodi & myself) are completed since August. •5 training videos and top tips were shared by CE on 21st August—currently zero views recorded. •2x COPC external trainings for full COPC framework - (not only Quality) 8 people from STC, 20 from GTS are booked in for end Sept/early Oct. 2025 Testing/POC practical Transactional monitoring STC: •Postponed to start preparing for it (building VOC criteria & Scorecards etc.) earliest January 2026. GTS: •CE and GTS partnered, VOC criteria to build the Scorecard is completed. •Voice Scorecard, Email Scorecard and MS Form (to insert monitoring results by GTS) is all ready. •Terri redirected the scope to test the quality process with one team on the Voice channel only, pausing all other work. •With the “Voice only” decision from GTS testing depends now on Five9 go-live and call recording, expected in October. •Alternative options (pending Terri’s approval): test on Email channel or resume Programme-level development. •CE (Richard) is ready and available to create a reporting visual as soon GTS has done any transactional monitoring. Quality System (create an EU version from existing US EPS Quality system) to retire MS Forms approach •Weekly alignment sessions ongoing with US EPS team since appr. 2 month, good progress. •Next challenge: securing approval for 1 additional FTE in the US (via Planview approval process to L3). VP Updates: •Presentation deck for Brenda and Mark, next call is beginning of October, is nearly ready. •Calls with Ellen and Brenda are paused **1st April 25** Introduction call with COPC & GTS happened. 12th May week for Baseline TBC (because of MD´s are asked to keep agenda empty for this week) Other weeks challenging because of Holiday. For STC: still giving time to Ellen to organize a call (as suggested by Philipp) For Operations: taken out from this initiative but not approach itself (to be integrated in FIRE potentially) Quality System: no updates since last call with US | E: L2 | On Hold | L2 | 2024-07-01 | 2026-06-09
Business Only Initiative: Customer communication: Friction-free, connected b | 28444 | 9254 | Business Only Initiative | EU - NPS | Europe | Ji Mariano, Ariane Gwinner |  | “Confidence in delivering value on time: Medium - 50-75% confident/likelihood” “Confidence in delivering the full value: Medium - 50-75% confident/likelihood" - Ongoing analysis of fedex.com and tnt.com audit results, ongoing conversations with parallel teams to close gaps and reduce overlaps (FBO, payment on .com, DCC) - Ongoing audit of offline materials - working session with new vendor - Ongoing customer journey mapping on support part | E: L2 | Completed | L2 | 2023-04-03 | 2025-02-28
Business w/ Tech Initiative: Single Point of Access (SPOA) for billing enquirie | 27749 | 9359 | Business w/ Tech Initiative | EU - NPS | Europe | Arthur Tops, Augusto Costa | On Track | Despite Slovenia, Bulgaria & Greece were included in original scope. Through the project implementation and new activity measurement capability we have realized there is no business need to implement the current SPOA scope for billing enquiries in these markets. France: 13 December 2023 Completed training for International implementation as per SPOA scope from Business Case. 13 Dec 2023 Agreed completion of additional domestic training (outside UK scope) and move this to completion first week January 2024 for Domestic | K: L5 | Completed | L5 | 2023-03-23 | 2023-12-22
Business w/ Tech Initiative: CEBS Work Queue simplification |  | 93866 | Business w/ Tech Initiative | EU - NPS | Europe | Ammar Jazzar, David Potter, Marcus von Pein, Tania Mencarelli | On Track | Ammar will become primary lead soon and David P will be the back up. DP: Received feedback from Finance to move to L2. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-02-03 | 2026-05-29
Business Only Initiative: J2P Master Data Governance - MDG |  | 98318 | Business Only Initiative | EU - NPS | Europe | James Pipe | On Track | 21/04/26 - Ready to move to L3 once dependencies have been added. 06/04/26 - Proceeding with updating Planview with all milestones and dependencies. Formalisation of MDG will be included as a milestone. 10/03/26 - Still awaiting feedback on the formalisation of the MDG team. In the meantime, all KPIs have now met and exceeded target. 06/01/25 - Still awaiting direct feedback on whether the governance team is to be formalised. OTC priorities my influence this direction. 09/12/25 - Initiative is on track. Planning review is scheduled for later today and a meeting with Clearance is planned for tomorrow to get clarity on the latest plans. 01/12/25 - Initiative is on track. Planning is ongoing. Clearance plans for Gemini have changed, so awaiting further clarity. Working on presentation of progress and next steps for EBS townhall in December which is taking priority. 25/11/25 - Initiative is on track, awaiting meeting with leadership to review plans 18/11/25 - Initiative is on track. Milestone planning is ongoing 11/11/25 - Initiative is on track. Planning is being reviewed with leadership before updating Planview. 04/11/25 - Initiative is on track. Progress and planning is being documented for wider socialisation. 28/10/25 - Initiative successfully in L2. Detailed milestone planning is underway. 14/10/25 - Initiative submitted to L2 07/10/25 - Meeting held. Awaiting update from POD Coach before pushing to L2. 23/09/25 - Planview final review before meeting with FP&A 16/09/25 - Meeting held and aspirational targets agreed. Planview is being updated with the final details in preparation to meet with FP&A. 09/09/25 - Follow up meeting scheduled with Leadership to discuss KPIs 02/09/25 - Meeting scheduled this week with leadership to present phase 1 progress and agree KPI targets 26/08/25 - Awaiting an audience with leadership to present results from previous phase and agree KPI targets. 05/08/25 - Dashboard data is still being revised and confirmed, but are now in place. Team holidays are now preventing a discussion on KPI targets, which need to be in place before discussions with FP&A. 28/07/25 - Reviewing the data and dashboard to ensure accuracy. Once confirmed, I will set up a meeting with FP&A. 22/07/25 - Data is available for the KPIs. A meeting will be set up with FPA to confirm move to L2. 08/07/25 - KPI dashboard is expected at the end of this week barring further complications. If not delivered, the data will be available so we can progress with the initiative and move to L2. 01/07/25 - Still awaiting telephone number KPI data to be completed by the US team. A meeting today was held - still a work in progress, to be delivered ASAP. 24/06/25 - 2/3 KPIs are ready. Waiting on telephone number completion data to be confirmed before meeting with FP&A. 17/06/25 - KPI dashboard has been refined and is planned to be ready at the end of this week. Next step will be to meet with FP&A. 10/06/25 - Priorities have kept us from finalising KPI dashboard data. Once done, we will review the data with FP&A. 27/05/25 - Finalising KPI dashboard data in preparation for reviewing the data with FP&A. 20/05/25 - Still awaiting KPI data and dashboard queries to be amended and tested before reviewing with FP&A and progressing with L2. Dashboards are 80% ready. 13/05/25 - Still awaiting KPI data and dashboard queries to be amended and tested before reviewing with FP&A and progressing with L2. 06/05/25 - Still awaiting KPI data and dashboard queries to be amended and tested before reviewing with FP&A and progressing with L2. 29/04/25 - Waiting on KPI Dashboard to be updated, run and tested before reviewing with FP&A and submitting to L2. 22/04/25 - Working with the US Governance team to set up KPI reporting and following up on final steps before moving to L2. 15/04/25 - Working on KPI clarification and further planning before moving to L2. 08/04/25 - Clarity on where the Clearance piece has been gained - it will remain a dependency on the project. Ad | E: L2 | Active | L2 | 2025-01-06 | 2026-12-31
Business Only Initiative: EU Payment Options (EFT) - Cash Application |  | 103117 | Business Only Initiative | EU - NPS | Europe | Carla Rocha, Hugo Gil C. Neves, Riccardo Sbabo | On Track | 2025/11/25 - CPEL Outcome: ranked #37 in the PRT backlog 2025/11/11 - Commercial L2 Triage Meeting 2025/10/16 - Official on L2 Stage 2025/08/19 – On Track All blockers resolved. - Financial contact confirmed: E.R. Pirabhu Raaj. Business case submitted with FY25 data (March 2024 sample), assumed valid as payment methods have not changed in the past 12 months. - IT contact confirmed: Kavitha Krishnaswamy. Weekly meetings initiated to align with the new Global Payment Portal scope. - EA alignment in progress. Assigned to L1 Architects as confirmed by Ryan Grover. Delivery is expected by the end of this week 2025/08/13 – Some Issues EA alignment pending. Request escalated to Ryan Grover; meeting to be scheduled. 2025/07/30 - Attention Needed - Definition of Financial Main Contact - E.R.Pirabhu Raaj, and working on update the Business Case to FY25 data (actual based on a sample fromMarch 24) - Waiting on confirmation from IT to have Kavitha Krishnaswamy as main Contact, and feedback on the scope and timeline of the new Global Payment Portal | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: JP - Invoice Accuracy |  | 113351 | Business w/ Tech Initiative | EU - NPS | Europe | Matteo Fiorini, Trudie Shepherd | Some Issues | 2026‑04‑14 – The initiative has been moved from Attention Needed to Some Issues. This reflects the fact that the interim dashboard now covers the key areas required to drive root‑cause monitoring and corrective actions from an Invoice Accuracy perspective. The Some Issues status is driven by a subset of initiatives progressing more slowly than expected. These areas, including Expiring Pricing, are now standing topics in the Invoice Accuracy weekly alignments and, if not resolved, will be escalated for discussion at the CESC planned for May 27. 20260320_2 pricing POCs launched out of four. Business with Tech still in backlog 20260311_pricing POCs expected to be launched next week. Billing POC is running. Ops ones also not progressing as expected due to: - Takko POC (new rating logic) requires the approval of the newly appointed SVP - PIP POC: difficult to collect information on picture usege by CapGemini's dispute team - DIM POC (new DIM dispute resolution process): kick off postponed to start new process already with CE rather than CapGemini 20260210_initiative still in backlog. Initiatives are growing in terms of reach/expected impact: 7 new POCs being launched in Feb - 3 POC's related to the strategic pricing process - 3 POC's related to Ops disputes - 1 POC related to hold billing capabilities 20260114_booster was not approved and initiative still in the backlog. Short update due during CESC Jan 20 and a long one on Feb 24 to provide overview of progresses and support need for the initiative 20251212_While we are still waiting for an architect to be assigned to JP 113351 EU Invoice Accuracy, we are moving forward with a local enhancement on our current single-source-of-truth dashboard (CAB dashboard). In parallel, thanks to a PowerBI prototype, we are already testing some of the enhancements that we want to get via the business-with-tech initiative. The feedback from the stakeholders that have seen it confirms that this will represent a significant step forward in our capacity to identify and tackle root causes collaboratively across functions. With Invoicing being highlighted by relationship surveys as the ‘most serious’ EU issue for 3 months in a row, it’s clear that a push to accelerate this initiative is justified. Closer connection with O2C mega process is already initiated and further opportunities will be discussed at the next CESC meeting (Dec16) 20251202_Still waiting for an architect to be assigned. Toby Hay has been involved in IA to ensure linkage with O2C mega process. 2-day workshop organized to map IA-related processes and prepare the O2C workshop on customer onboarding. 20251118_Currently waiting for an architect to be assigned. Review planned with SVP beginning of Dec to review if booster needed * Data and Analytics workstream, previously only progressing via manual sampling and analysis, can now also count on a static PowerBI Dashboard, that works as a prototype of the long term dashboard that we want to obtain through the business with Tech. Local request created for short term enhancement of CAB: 0008680 * Pillar Leads have been appointed for Pricing Ecosystem, Data Capture, Operations, Top Customers. Action plan of each focus area have been defined and top customer reviews ongoing | E: L2 | Active | L2
Business w/ Tech Initiative: GEN AI Automation webform to case |  | 131245 | Business w/ Tech Initiative | EU - NPS | Europe | Jens Klemm | On Track | oppportunities newly evaluated Dataworks concept approval Gen AI Inquiry - #GENAI398 Gen AI Core Submission #0045 - TRACE – Tracking & Response Agentic Cognitive Engine FIRST ID: 7950 | E: L2 | Active | L2 | 2026-07-01 | 2026-12-31
Business w/ Tech Initiative: Global Invoice Presentment Delivery (GIPD) |  | 155418 | Business w/ Tech Initiative | EU - NPS | Europe | Andrew Pellegrino, Guru Diraviam | On Track | 6-March-2026: Submitting to L3 today. Reviewed Baseline value, target value, and NRB (Hard) with EU Fiancne (Holger). Request will go to Rachel, then Dlyan, them EU Domain lead for approvals into L3. Emily W. to assist with PV approvals. 27-Feb-2026: GIPD moved from Commercial Domain to Europe Domain. Now working with EU domain finance to prep the initiaitve financials for L3. 16-Jan-2026: Submitted the GIPD initiative to L3 in Planview twice, most recently on 15-Jan-2026. However, it has been returned to L2 both times. Below are the Commercial Portfolio Greenlight comments explaining why it was not approved for L2: 11/18/25: PRT backlog #33 — Once the L2 architecture assessment is completed, then submit the greenlight request. 1/15/26: PRT backlog #29 — Once the L2 architecture assessment is completed, then submit the greenlight request. 19-Dec-2025: We are identifying which Planview initiatives depend on the development of the GIPD initiative and incorporating their associated benefits into the GIPD business case to help increase its priority. 22-Sept-2025: Upon full launch on 31-Dec-2028, the init would generate $3.8M annual savings from IT and business areas. Incremental IT Savings: $2,449,159 Incremental EU Savings: $519,400 Incremental APAC Savings: $556,920 Incremental MEISA Savings: $254,072. 10-Sept-2025: Working with EBS regional partners, IT, and Finance, on L1 LBC. | G: L3 | Active | L3 | 2026-03-02 | 2028-12-29
Business w/ Tech Initiative: GLIDE - Phase 1 |  | 114428 | Business w/ Tech Initiative | EU - NPS | Europe | Guru Diraviam, Rebecca Whitehead | On Track | 26/2/2026 - Greece - Technical requirements discussion ongoing. France workshop planned in India for Mar 9-13. Poland credits moved to production on Orange and Purple. Next week - Continue technical dsicussions and finalize the requirements for Greece. Prepare for France workshop. 13/2/2026 - Poland - Went live 9 Feb, currently tracking the rejections and errors as post go-live support. Completed the declaration to greece authorities for getting extension to implement e-invoicing in Greece. Next week - Move Poland credit notes to production once the bug is fixed from Pagero, start workin on technical requirements for Greece 29/01/2026 - Updated the forecasted financials, identified that we need one additional scrum team for implementation and 6 EBS and 3 Tax resources which were not part of initial estimate. We also have a yealy contract with vendor which was not included in the original estimate as the original estimate IT estimated two scrum teams for FDX International and Domesitc but did not include TNT systems, Craft and domestic in the estimate which requires additional scrum team. We need this costing until Dec 2030, but planview does allow only until May 2029. 19/01/2026 - BE went live beginning of Jan 2026, no major issues so far. IT went live Jan 5 and no issues and process seems to be stable now. Next week plan - Focus on BE post go-live process and ensure no setbacks and errors are handled properly. Poland go-live at risk, due to limited IT resources but to be decided on delay later this week or early next week. Greece not prioritized for current PI which is critical risk. 22/12/2025 - Belgium Orange and Purple signed off for move to production Jan 2, 2026. Italy move to production agreed and planned for Jan 5, 2026. Next week plan - GLIDE Belgium go-live Complete all minor testing for Italy to be ready for move to production | G: L3 | Active | TEMP L3 - Enter L3 | 2025-12-31 | 2030-12-31
Business Only Initiative: Enable ARTH for Poland FedEx Domestic shipments | 60728 | 7296 | Business Only Initiative | EU - Poland | Europe | Anna Radecka, Robert Sopela | On Track | Relase data change for Spt 29 (one week later) as the IT release is planned for this date. As a consequence money step start date moved one week ahead. | K: L5 | Completed | L5 | 2024-01-22 | 2024-09-26
Business w/ Tech Initiative: COD at Express Domestic PL | 86600 | 7527 | Business w/ Tech Initiative | EU - Poland | Europe | Anna Radecka, Abhijit Ovalekar | On Track | 2.04.26 - ad hoc functionality on production; COD silution on production; production final test in progress; awaiting ZPD solution | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-01 | 2026-05-28
Business w/ Tech Initiative: Launch of Dangerous Goods value prop in FedEx Dome | 16959 | 7538 | Business w/ Tech Initiative | EU - Poland | Europe | Anna Pawlak, Agata Kaim | On Track | Reasons for cancellation ask: Changes in Commercial Policy and Project Scope. The project's original scope, centered on FedEx legacy operations, has shifted to focus on Express Domestic. This change has notably reduced potential revenue opportunities, particularly due to pricing policies that exempt current customers from Dangerous Goods (DG) shipment fees for one year post-migration. Lack of Cash on Delivery (COD) in Express Domestic. The absence of COD options within Express Domestic limits growth opportunities. COD is a crucial feature for customers, particularly for enabling DG shipments. This limitation further complicates migrating existing customers to the new system, making successful transition unfeasible. Resource constraints post EBO implementation. The recent implementation of the EBO system has significant influence on our resources. As a result, the team is prioritizing verification and other high-impact tasks, leaving limited capacity to continue with this project effectively. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-02-13 | 2026-01-26
Business Only Initiative: DG by Air | 64707 | 7549 | Business Only Initiative | EU - Poland | Europe | Anton Pelykh, Agata Kaim | On Track | The project have 2 phases: Phase 1 launch in November in Lodz (2 stations) and Gdansk - done. Phase 2 is planned for is planned for April 2025 for Rzeszow, Katowice and Poznan (x2), Chorzów. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-10-02 | 2025-04-04
Business Only Initiative: Uplift of fuel curve | 17034 | 7561 | Business Only Initiative | EU - Poland | Europe | Maciej Jedlikowski, Agata Kaim | On Track | Confidence in delivering value on time: high Confidence in delivering the full value: high | K: L5 | Completed | L5 | 2022-07-21 | 2023-03-31
Business Only Initiative: Start of Customer Profitability Review (CPR) | 17036 | 7572 | Business Only Initiative | EU - Poland | Europe | Maciej Jedlikowski, Agata Kaim | On Track | CPR is, and to be BAU process, agreed at PL DRIVE, at customer level, to avoid any unnecessary churn. Initiative to replace with BAU CPR process. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-05-01 | 2025-08-01
Business Only Initiative: Increasing surcharge compliance | 17222 | 7583 | Business Only Initiative | EU - Poland | Europe | Maciej Jedlikowski, Agata Kaim | On Track | Moved and combined with 17034 Confidence in delivering value on time: high Confidence in delivering the full value: high | G: L3 | Active | TEMP L3 - Enter L3 | 2023-04-03 | 2026-08-07
Business Only Initiative: Boosting FedEx Domestic GRI | 17223 | 7594 | Business Only Initiative | EU - Poland | Europe | Maciej Jedlikowski, Agata Kaim | On Track | Confidence in delivering value on time: high Confidence in delivering the full value: high | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-01 | 2025-03-31
Business Only Initiative: Domestic fuel curve change | 64711 | 7605 | Business Only Initiative | EU - Poland | Europe | Maciej Jedlikowski, Agata Kaim | On Track | Confidence in delivering value on time: high Confidence in delivering the full value: high | K: L5 | Completed | L5 | 2023-11-28 | 2023-12-01
Business Only Initiative: HUB Ext. (Wypedy VRDH) and open for LL capability | 89577 | 8357 | Business Only Initiative | EU - Poland | Europe | Robert Sopela, Tomasz Glowniak | Some Issues | [23.04.2026] Still On Hold [10.04.2026] Project is currently on Hold due to lack of full approval. Business case updated and sent again to upper managment level to be revewiwing. Awaiting for decision about capital readiness for full project scope and conitnuation of further works. [03.09.2025] Project is Now at RISK. CLEAR is in SVP FInance already since 03rd of Aug'25 what is pushing high pressure on the 1st part of the Project which is Maintenance activity planned for first two weeks of Jan'26. Without approval we can't go with that maintenance as well as we are delay with delivery date for the whole project. [05.06.2025] All required details delivered into the Initiative. Corrected Finance, added KPI's as well as Milstones and Monay Step. Added all required positions and re-checked all details on the process. [02.04.2025] Wypędy Extension is a key player in the Future PL Ground network setup. As Wypędy are well communicated and is planned to be in the next 12 months sort locations for all International Movements and connecting them to Domestic Network, investment into LL capability is a key point in future Growth and grwoth capability. [16.12.2024] Call with Properties - Jaime Silva. Agreed steps for delivering BJD costs and benefits by the end of Jan'5 | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-06-02 | 2027-05-31
Business Only Initiative: Pila NEW Station (BTS) - HSE & Volumes Driven | 92677 | 8359 | Business Only Initiative | EU - Poland | Europe | Tomasz Glowniak, Robert Sopela | On Track | Sharing updates [29.01.2026] Due to long inactive caused by lack of resources, situation has changed. Project will be continueas as a Local Enhancement - wrok ID 0115540. New resoures are assigned, Busienss Case is ready and will be submitted. PPM is almost ready (IT approval in progress). | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Re-launch time definite services in FedEx Domestic | 16970 | 8803 | Business Only Initiative | EU - Poland | Europe | Anna Pawlak, Agata Kaim | On Track | Reasons for cancellation ask: Operational Readiness Concerns. Our current operational infrastructure is not fully prepared to handle the anticipated increase in Premium shipments. Proceeding with the promotion under these conditions could compromise service quality and customer satisfaction. Unfavorable Timing - Upcoming Peak Period. The impending Peak period presents additional strain on our logistics and delivery networks. Introducing or promoting Premium services during this high-demand phase poses a significant risk to both standard and Premium service levels, potentially leading to operational inefficiencies and reputational risk. Limited demand for Premium services in Poland. With raising cost customers are switching due lower cost services. Exception is Healthcare but that requires a separate attention. Resource constraints post EBO implementation. The recent implementation of the EBO system has significant influence on our resources. As a result, the team is prioritizing verification and other high-impact tasks, leaving limited capacity to continue with this project effectively. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-03-02 | 2026-03-09
Business Only Initiative: Freight - boost volumes mix on B2B with high-yield | 17143 | 9328 | Business Only Initiative | EU - Poland | Europe | Rafal Dziura, Lukasz Igielski | On Track | As we observe a dynamic increase in international freight, the available capacity for domestic freight has become limited. We have agreed to maintain strict control over purely domestic pallet volumes to stay within the limits defined by the network and GOPS. On average, we aim to transport 2.3–2.5K domestic pallets per day, which enables us to optimize the network and reduce delivery costs for freight and heavy-weight shipments. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-02-27 | 2023-05-15
Business Only Initiative: Resellers - leverage flexibility in efficient capa | 17145 | 9331 | Business Only Initiative | EU - Poland | Europe | Rafal Dziura, Lukasz Igielski | On Track | Confidence in delivering value on time adjusted by the MB decision: 100% (combination of SME and resellers volumes) Despite the fact that the numbers are below the initial plan, this is on track according to the management board decision. This initiative has been redefined due to high pressure on cost from the resellers and negative impact on the P&L. The expected missing volumes moved to the SME Boost initiative and the resellers volumes outlook is stable organic growth with at the stable yield. Expected volumes is around 4K-5K per day on average to optimize first and last mile network and cost. Following the recent management board decision, we have approved a shift in volume allocation between the initiatives — in favor of SME Boost over Resellers. Our analysis showed that reducing prices for resellers, while expected to increase volumes, does not support overall profitability. This is mainly due to the customer profile, which lacks multiple-shipment potential. In contrast, we see significantly stronger revenue generation through FS (Field Sales) and IS (Inside Sales) channels. Consequently, we have adjusted the forecasts for the upcoming quarters to reflect this strategic shift. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-02-27 | 2023-05-31
Business Only Initiative: New & Incremental Business by leveraging Enterpris | 17149 | 9333 | Business Only Initiative | EU - Poland | Europe | Rafal Dziura, Piotr Pogonowski | On Track | Confidence in delivering value on time: 100% Confidence in delivering the full value: 100% The ongoing customer segmentation process continues to influence the volume allocation across different initiatives. Recently, we promoted several customers who were part of collaboration programs, which has contributed positively to our results. As a result, both volumes and revenue in the Enterprise National segment have stabilized at a level above the initial plan. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-02-06 | 2023-05-15
Business Only Initiative: Domestics PL WWS Incremental Growth | 17154 | 9334 | Business Only Initiative | EU - Poland | Europe | Peter McVey, Rafal Dziura | On Track | As we reach capacity in domestic, the WWS focus remians on international products. Current strategy is to maintain existing volumes and future migration of the orange volumes to the purple network. We agreed and aim to keep c.a. stable per day | K: L5 | Active | TEMP L5 - Enter L5 | 2023-02-27 | 2023-11-30
Business Only Initiative: SME - Boost Sales Productivity & Effectiveness | 17184 | 9335 | Business Only Initiative | EU - Poland | Europe | Rafal Dziura, Lukasz Igielski | On Track | Confidence in delivering value on time: HIGH Confidence in delivering the full value: HIGH Following the management board decision, we have approved a shift in volume allocation between the initiatives — in favor of SME Boost over Resellers. Our analysis showed that reducing prices for resellers, while expected to increase volumes, does not support overall profitability. This is mainly due to the resellers profile, which lacks multiple-shipment potential. In contrast, we see significantly stronger revenue generation through FS (Field Sales) and IS (Inside Sales) channels. Consequently, we have adjusted the forecasts for the upcoming quarters to reflect this strategic shift. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-01-02 | 2023-11-30
Business w/ Tech Initiative: PL domestic LH PFS set up review | 17332 | 9343 | Business w/ Tech Initiative | EU - Poland | Europe | Robert Sopela, Mariusz Mik, Anna Przybylska | On Track | Unable to appoint ERN and ERN P&E representative to own this initiative. Ask submitted. Waiting long for any response. Unable also to cross check if this initiative is already contained in other DRIVE PODs. [06.03.2023] Status for the initiative - MD's onboarded. Team agreed. First work team meting scheduled. [16.04.2023] First SteerCo with MD & VP Level conducted. Agreed next SteerCo deck layout and approach. [05.05.2023] Moday 8th of May'23 - review Temporary Costs for LH for FY24 - required to estimate costs required to keep PUD Interim integration (Station consolidation) until PFS LH Network will be designed. RN Team working on the final LH Schedule. All Assumptions finalized before due time. Ongoing work on the first delt model. [12.06.2023] Final approach for re-modelling agreed. First value and costing delivered. Ongoing detailed finetuning from RN P&E side. [15.10.2023] LH DRIVE Initiative is going to be reviewed and updated with New circumstances. Leadership is informed, as last SteerCo (Functional MD & VP's) get full view on the project status. No yet fully established risk on Money Step date, but RN P&E Team get ask to review potential options for mitigation. [22.10.2023] Ongoing work from Road Network on the DELTA model (NEW). Expected to be delivered end of Oct'23. Go/No Go decision is postpone to next SteerCo November 9th if modelling will be finalized. **[23.10.2024]** DHv2-CSK interface which is enabler for running fully integrated scanning activity for all type of labels is not yet ready. Earliest Sprint we can get this development started is plan for first part of Nov'24. If finalized to end of Nov'24 we can start test and have onsite scanning PoC as of Feb'25. Based on that we can't count on that solution as of Feb'25 where we are going to launch iPFS stage with all Stations integrated and LH Setup launched in iterim mode. We are working on contingency plan with usage of iMag old system scanning devices. LH Setup for Feb'25 recieved today - 23.10.2024 - what is late to submit L3 end of Oct'24. We need 3-4 weeks to make LH Setup review and recaluclate FTEs impact. Expected to have 2-3 weeks delay in L3 submission, but it would not impact Launch date (June'25) and interim step for Feb'25. **[07.11.2024]** DHv2-CSK interface development finally get started. We expected to get its first draft of solution available early December'24 for tests. We expect to have Dec'24 time for testing and Jan'25 as potential fine tunning. Moveing to Production MTP expected March'25. That will be a time we can start planning full LH volumes mix in June'25 as per original plan. Secondly - final Feb'25 schedule agreed with last Station in Szczecin what is giving us more flexibility to run full PUD Integration in Feb'25 as per plan. Now ready to collect costs and savings to preapre material for Finance. **[30.11.2024]** Project progressing well with LH setup for Feb'25. Plan is agreed and confirmed. From PUD #402 perspective also going well. Team finalized most of the PUD Setups and finalizing it with running as of Feb'25. HUBs are ready for Feb'25. FOr June'25 we do not have yet LH Setup and expect it will be available next week. From DHv2 interface twith CSK - as of week commencing 02nd of Dec'24 we are going to start tests. **[26.01.2025]** All Required implementation activity are in place - final week required to properly launch Integration activities. All 6 Stations going to be integrated as of Feb'25 - #402 is going to be finalized. LH Setup in place. HUB's reporting readiness. PUD Integration almost finalized. DHv2 first view in L3 environment. [11.02.2025] After 19th SteerCo meeting there is a Go for launch L3 with 0,44 m$ Savings expected from the LH savings in PL. [21.03.2025] Work on first line to be redundant started. As of this week RN P&E and LOC as well as Field & HUB P&E start working on the integration activity. [05.06.2025] All Financials corrected and included NEW lines as well as Actuals are updated | I: L4 | Active | L4 | 2023-03-06 | 2026-03-31
Business Only Initiative: EUR_PL-Katowice-Infrastructure-Ramp |  | 90962 | Business Only Initiative | EU - Poland | Europe | Tomasz Glowniak, Robert Sopela | Some Issues | [23.04.2026] Initiative on L2. Required to complete additional documentation related to CCH Commercial Clearing House and Value Prop impact. Task in progress. Awaiting approval for BJD. Last minute information is - we lost opportunity to rent any space at the airport area. Waiting for Properties team confirmation. [10.04.2026] No other informations from the LL side causing we are still pushing all formal works to finalize this project. Currently sumitted to L2 level. Business Case, especially financial part (benefits) are currently fine tuned. Aim is to finalize this during next 2 weeks and submitt to L3 to start CLEAR processing. [27.03.2026] The project timeline shift by one year due to capital constraints has significantly deteriorated our position with the landlord (LL) and materially increased the risk of losing the current location. Over recent weeks, the LL has clearly communicated limited willingness to wait for our revised timeline. Parallel discussions have already been initiated with alternative tenants, most notably DHL, who has proposed a long-term land lease model with self-funded facility development. This option is highly attractive for the LL, as it eliminates the need for capital investment on their side while securing long-term tenancy. As a result, the LL is now actively evaluating alternative use of the site, and our position as the smallest tenant further weakens our negotiating leverage. The previous assumption of a potential short-term extension is no longer reliable. The delay in decision-making effectively creates a scenario where: * we risk losing the current footprint without a secured alternative, * we may face operational disruption in Southern Poland, * and we lose strategic positioning in a high-growth region. Given current dynamics, the overall status of the project has shifted to high risk, with a real and increasing probability of displacement if no immediate mitigation or acceleration actions are taken. Required next steps / considerations: * Reassessment of project timing and funding prioritization * Exploration of interim solutions to secure continuity * Immediate re-engagement with LL to reassess positioning and potential short-term safeguards In summary, the situation has escalated from a capacity-driven investment case to a time-sensitive risk mitigation scenario with potential business continuity impact. [17.03.2026] Still waiting for decision from Katowice Airport authorities. We were informed that Katowice Airport has own project General plan for Airport where they considering modernisation or even total rebuilding whole property infrastructure. They are veryfing their data, forecasts as well as data from all current cargo companies. Some feedback from Airport authorities is expected till Friday, 20th of Mar [29.01.2026] After long inactivity caused by lask of resources and changes of decisions made by Airport authority, works on this project were restored. MHS team is veryfng technical specufication for sortung system. Business case is awaiting final infrmations (costs, plot shape) to be finalized. Ongoing NJD Review [31.03.2025] NRB updated within L1 process with LH and PUD estimation only for FY26-FY28. Revenue only. | E: L2 | Active | L2 & CCH
Business Only Initiative: LT/Kaunas New BTS Facility for Ramp/HUB/Station at |  | 91485 | Business Only Initiative | EU - Poland | Europe | Bernard F. Gutkowski, Robert Sopela | On Track | [31.03.2025] NRB updated within L1 process with LH and PUD estimation only for FY26-FY28. [02.02.2026] Due to lack of resources and prioritization of another project, land plot requirements were finalized later and currently the search for a suitable landplot is conducted by Real Estate deparment. Once landplot will be available, confirmaiton of the building shape can be done;. It allows to estimate costs (rent, MHS design and cost etc.) [23.02.2026] There is a search for land plot. It should ended until beginning of March 2026. Once landplot is available, it is possible start further processes (selsection of landplot, fitting the building, desining MHS, cost estimation, creation BJD etc.). [16.03.2026] Pending the answer from the Real Estate team concerning the land and lease data. [10.04.2026] Real Estate team prologed process due to new offers coming. In order to speed up process estimation of MHS costs has been done (to be verified after confirming land plot and final building shape). [24.04.2026] After discussion with PM and Real Estate, final shape of the building and a sorter are confirmed. Collection of benefits (staffing, incremental revenue, changes in LH network( are under investigation. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Suwalki (ZWKA) New BTS Facility |  | 103486 | Business Only Initiative | EU - Poland | Europe | Robert Sopela, Tomasz Glowniak | On Track | [31.03.2025] NRB updated within L1 process with LH and PUD estimation only for FY26-FY28. Baseline is FY25 for PUD (March multiplied to May and April) with 3% of savings. LH is based on the One movement cancelation with 200km both ways and 4,9 PLN per km. Added Rent for both locations with 65k$ [04.02.2026] We need to go with Local Enhancement. NEW Work Request will be submitted by Tomasz Glowniak. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Szczecin NEW Station (BTS) - Integration&Capacity |  | 103491 | Business w/ Tech Initiative | EU - Poland | Europe | Tomasz Glowniak, Robert Sopela | On Track | [23.04.2026] PL OPS Team choose final landlord's offer and now all tasks related to new location planning started. Bussines case will be build for this case as well as all design activities for building, plot, processes, equipment. [10.04.2026]. Monday, the 13th April PL local management will decide about final location and costs, to establish direction of future works. Most of data needed for Business case are already collected. Depeneding on decisions updated Busienss Case will be submitted asap to L2. [19.03.2026] Arrangements with OPS team regarding the station setup, finalizing detaild related to shape, number of gates, etc. for layouts presented by Landlords. Technical Requirements for sorting equipment need to be corrected base on MHS team feedback. When finalized next step will be uploading Business Justification Document and go further with otehr activities. [29.01.2026] After long inactivity caused by lask of resources works on this project were restored. Busienss case documents are during finalisation. Technical Requirements for sorting equipment were shared to respective team. Curently Properties team is looking for the best plot for new facility. [31.03.2025] NRB updated within L1 process with LH and PUD estimation only for FY26-FY28. Baseline is FY25 for PUD (March multiplied to May and April) with 3% of savings. LH is based on the One movement cancelation with 50km both ways and 4,9 PLN per km. Added Rent for both locations with 230k$ | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Lomza NEW Station (BTS) - HSE & Volumes Driven |  | 103494 | Business Only Initiative | EU - Poland | Europe | Robert Sopela, Tomasz Glowniak | On Track | [31.03.2025] NRB updated within L1 process with LH and PUD estimation only for FY26-FY28. Baseline is FY25 for PUD (March multiplied to May and April) with 3% of savings. LH is based on the One movement cancelation with 130km both ways and 4,9 PLN per km. [04.02.2026] We are going with Local Enhancement. Request ID 7986 | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Picture POD for PL Integrated Network |  | 142173 | Business w/ Tech Initiative | EU - Poland | Europe | Agata Skrok | On Track | •Picture POD => availability of resources remains as a main challenge on Field P&E side now. Due to this, further works on this project have been initially re-scheduled for Q3’2026 (July) | E: L2 | On Hold | L2 Feedback Requested
Business w/ Tech Initiative: LV/RIXA New Facility for Station with HUB & Ramp a |  | 91219 | Business w/ Tech Initiative | EU - Poland | Europe | Robert Sopela, Bernard F. Gutkowski | On Track | [27.03.2025] Project got positive approval from Finance with less than 3Y ROI and is now ongoing Functional Approval before CLEAR Submission. [27.04.2025] After review with FInance Revenue is kept as Soft Benefit. Proper email shared with FP&A Manager. [21.10.2025] Hi Eryn, as requested I made a corrections. | E: L2 | Active | L2 & CCH | 2025-05-26 | 2027-04-01
Business Only Initiative: PL - KTW ramp import staffing change |  | 152796 | Business Only Initiative | EU - Poland | Europe | Anna Przybylska | On Track | Per Tomasz Glowniak requested this Initiative be cancelled. - INC034096889 | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: Fraktal->CIS Communication Demand Request |  | 157688 | Business w/ Tech Initiative | EU - Poland | Europe | Wioleta Jakubowska, Robert Sopela, Tomasz Glowniak | On Track | 28.08.2025 on track 10.04.2026 requried IT Architure Documentation - need support from IT to build document , So far one for EPM team didn't provide any documentation 17.04 2026 upate owners add Tomasz Glowniak & Robert Sopeła, send PDSM request INC034534827 to change Estimated Annualized Value Range from 1. - Unknown to 2. LOW =< $1M 22.04.2026 INC034534827 - completed | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: AT - B2C operational setup (ENABLER) | 27953 | 6722 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Dipankar Debroy, Celina Knoepfle | On Track | **29-Apr-2025** * Handover taking place as defined in the initial scope. Initiative milestones completed, and ready to move to L4 **27-Feb-2025** * Ready for launch on 3rd of March **03-Dec-2024** * Missing CCH approval, requiring follow up with IO of #69824 to understand the concern | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-03 | 2025-03-17
Business Only Initiative: ATHA Direct loading, Bonded Warehouse and MHS inst | 89632 | 7386 | Business Only Initiative | EU - PUD | Europe | Dimitrios-Agamemnon Christodou, Kostas Adamopolous, Eser Sezek, Robin Hummel | On Track | 2025-11-20 Update: Milestone Achieved: The installation of the MHS system is finished and the Ops team operate the sorter for both Import and Export operations. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-10-07 | 2026-05-29
Business w/ Tech Initiative: 03 - Increase Route Productivity - Monitoring Impr | 386 | 7616 | Business w/ Tech Initiative | EU - PUD | Europe | Patrick Tediek, Robin Hummel | On Track | Initiative Confidence Level: - - Value Achieved = 100% - Value achieved on time = 80% - Execution of initiative on time = 100% Status: 06-Nov-2025: Forecast adjustment for FY27/28 to remove FR as per agreement to move the savings to the Domestic initiative. Status 17-Jul-23: - - A gap between the Wave targets and actuals driven by the need to finalize the approach to measuring the productivity increase and translating into financials. Expected to have ready for Jul-23 reporting, and updating of the Jun-23 actuals 22 December 2023 - agreed with Simon to move the milestone #7173 end date due to dashboard functionality being developed. 25/04/2024 #386 - UK POC has kicked off to test the latest dashboard functionality - productivity improvements 30/04/2023 #386 - significant cleanup of the settlement code usage in the UK. This will enable focus on improvement of productivity. 02/05/2024 #386 - new dashboard functionality tested in POC stations UK 10/05/2024 #386 POC testing UK. 17/05/2024 #386 POC testing UK. 24/05/2024 #386 POC dashboard testing UK. 31/05/2024 #386 POC dashboard testing UK. 21 June 2024 - LTP dashboards have been launched and webinars executed. 28June 2024: Initiative updated with documentation after L4 rejection. The money step has been reached: In combination of initiative #389 rounds are being optimized. The baseline productivity was 29 and today the average productivity is: 44.12, see screenshot productivity overview in the attachments for the month of June 2024. A monitoring dashboard has been developed to measure the rounds and areas on a stop rate, the dashboard will reflect the contract productivity vs actual productivity and display achievements and enable managers to take action in optimizing their rounds and areas to ensure they are optimal, referencing the capture rate achieved. See attachment dashboard sample 1 and 2 of screenshot samples of the dashboard. A sample of ARCgis which has been used has been added. 11 July 2024 - to update the impacts for June, I will temporarily pull back the initiative to update it and put it back to L4 15 July 2024 - Forecast has been updated. 31 July 2024 - CDAS avg stops round has been added. This shows the stops per round avg as per CDAS data. The FY22 baseline data is referenced. 1 August 2024 - annualized FC updated with May 2025 figures. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-14 | 2024-06-14
Business w/ Tech Initiative: 06 - EU PUD Route Optimization - Integrated countr | 387 | 7627 | Business w/ Tech Initiative | EU - PUD | Europe | Tobias van der Linden, Salvatore Nijmeijer, Alexander Braun | Some Issues | Confidence in delivering value on time: Low Confidence in delivering the full value: High **2026-01-02** Regarding MFR, no major news for this week. 2025-12-19 **Complete**: Regarding MFR, no major news for this week. **In progress**: Regarding MFR, validation of several RDM and RDNA related issues/enhancements in progress. **Next steps**: Regarding MFR, continue research on defects/issues and create tangible actions. Release of MFR dashboard. Enhancing communication approach on FAQs, knowledge articles, as well as strengthen communication in cases of outages etc. towards stakeholders in the stations. 2025-12-12 **Complete**: Regarding MFR, an outage occured which was triggered by the vendor RouteSmart, as of 12/15 it seems to be fixed and MFR is back up running **In progress**: Regarding MFR, validation of several RDM and RDNA related issues/enhancements in progress. **Next steps**: Regarding MFR, continue research on defects/issues and create tangible actions. Release of MFR dashboard. Finalize RDNA MTP. Enhancing communication approach on FAQs, knowledge articles, as well as strengthen communication in cases of outages etc. towards stakeholders in the stations. 2025-12-05 **Complete**: Regarding MFR, 2 fixes linked completed and loaded which are linked with what appeared to be a timezone issues regarding ETAs, as well as loading time for completed scans. **In progress**: Regarding MFR, validation of several RDM and RDNA related issues in progress. RDNA MTP in progress and expected to be finished during CW50. **Next steps**: Regarding MFR, continue research on defects/issues and create tangible actions. Release of MFR dashboard. Finalize RDNA MTP. Enhancing communication approach on FAQs and knowledge articles. 2025-11-28 **Complete**: Regarding MFR, mo major news this week, teams continue focusing on development work. **In progress**: Regarding MFR, validation of several RDM and RDNA related issues in progress. Finalization of dashboard for sharing with a wider stakeholder audience / users. **Next steps**: Regarding MFR, continue research on defects/issues and create tangible actions. Release of MFR dashboard. Enhancing communication approach on FAQs and knowledge articles. | G: L3 | Active | TEMP L3 - Enter L3 | 2022-10-03 | 2027-03-31
Business w/ Tech Initiative: 04 - Optimize in-station processes | 388 | 7638 | Business w/ Tech Initiative | EU - PUD | Europe | David Diener, Gery Hermans, John Macdonald | On Track | Call with FR Team to update on phase 2 relaunch PPM number created for FAMIS deployment: 707760 obtained Dec 3rd, 2024. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-10-21 | 2025-05-30
Business w/ Tech Initiative: 03 - Increase Route Productivity - PUD Planning To | 389 | 7649 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Jack Halliwell, Mireia Ferrer Sancho, Celina Knoepfle | On Track | Initiative Confidence Level: - - Value Achieved = 100% - Value achieved on time = 80% - Execution of initiative on time = 100% Status Updates: - 05-Nov-2025: Forecast adjusted for FY27 onwards removing France savings as agreed - 12-Sep-2025: No updates - 03-Sep-2025: No updates - 25-Apr-2024: Current total route cuts in EU at 572 daily routes (Mar-24 actuals) & completion of 61% of total stations (Mar-24 actuals) - 02-May-2024: Agreement with team to schedule PUD1 rollout to small SME team and conduct further testing. Alignment with DW required to get estimation on effort for addl. features - based on this outcome decision to be made on continuation of MVP2 - 08-May-2024: No update - 16-May-2024: Wave actuals updated for #389, with $1.15m saving in April - 23-May-2024: Moving of money-step to end of FY25 at 31-May 2025. Reason for the move is due to aligning with the implementation plan created by the regions in April 2023 | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-04 | 2025-08-29
Business w/ Tech Initiative: 06 - Domestic PUD Route Optimization - PL IT FR | 407 | 7660 | Business w/ Tech Initiative | EU - PUD | Europe | Alexander Braun, Tobias van der Linden | Attention Needed | Confidence in delivering value on time: Medium Confidence in delivering the full value: Medium **2025-11-05** Forecast adjustment for FY26 and FY27/28. FY26 linked to latest outlook, 27/28 includes removal of FR as per agreement to move the savings to the Domestic POD. **2025-09-19** Money step/L4 date changed to 31 Oct. 2025-08-25 Planned L4 date not feasible due to delays, alignment with leadership to take place 8/26. 2025-05-23 No update, awaiting further feedback on deployment and value capture from local team. 2025-05-09 No update, awaiting further feedback on deployment and value capture from local team. 2025-05-02 **Complete**: - **In progress**: PL solution assessment in operational environment. **Next steps**: Assess and action recent finding on pick-up constraints which trigger algorithm issues. **Risk/awareness**: Recent findings might have an impact on value delivery / timelines for PL. 2025-04-11 **Complete**: Financials updated for FY25 and FY26 **In progress**: PL solution assessment in operational environment. **Next steps**: Assess and action recent finding on pick-up constraints which trigger algorithm issues. **Risk/awareness**: Recent findings might have an impact on value delivery / timelines for PL. 2025-04-04 **Complete**: Remaining FR milestones cancelled due to the establishment of a new initiative specifically for FR. **In progress**: PL solution assessment in operational environment. **Next steps**: Assess and action recent finding on pick-up constraints which trigger algorithm issues. **Risk/awareness**: Recent findings might have an impact on value delivery / timelines for PL. 2025-03-21 No particular update, FR is expected to be an initiative on its own, #407 remaining with focus just on PL. 2025-03-14 No update, awaiting leadership directions. 2025-03-07 FR was prioritized for FRO which might conclude in a dedicated initiative and dis-continuation within #407. Details are still being clarified with leadership. 2025-02-28 No update, awaiting leadership directions 2025-02-21 No update, awaiting leadership directions 2025-02-14 No update, awaiting leadership directions 2025-02-07 **In progress**: Review of new FR timelines still in progress and linked to overall FR discussions. #407 implications will depend on the overall FR discussion. Feedback on FR POC activities which were planned/conducted in January indicates critial gaps and issues, specifically the dependency on uDS and the recent development seem not have provided the capabilities which are required for the local solution. **Next steps**: Assessment of impact of above described situation. **Risk/awareness**: Timelines for a potential MFR approach for FR DOM were based on a timely decision approach as potential developer recruitment and team shaping requires time, waiting for decision making might impact initial timeline indication negatively. Having operations getting used with local RO solution prior transition to central tools appears questionable with issues and gaps such as the uDS dependency. 2025-01-31 No update | I: L4 | Active | L4 | 2022-12-01 | 2025-12-01
Business w/ Tech Initiative: 01 - Implement payment governance structure for AD | 390 | 7672 | Business w/ Tech Initiative | EU - PUD | Europe | Patrick Tediek, Robin Hummel | On Track | 06/11/2025: Forecast adjustment for FY27/28 to remove FR as per agreement to move the savings to the Domestic initiative. 02/05/2023 #386 - significant cleanup of the settlement code usage in the UK. 10/05/2024: Results of the cleanup display the spend challenges with employed drivers 17/05/2024: Results of the cleanup display the spend challenges with employed drivers - looking into delayed inputs of adhoc 24/05/2024: - looking into delayed inputs of adhoc 31/05/2024: - assessing delayed inputs of adhoc and what can be done to make managers more aware. 27June2024: Status moving the initiative to L4. The money step has been reached. We have implemented a governance policy (See attachment LTP Exceptional Pay policy) to CDAS countries. Different settlement codes have been defined and implemented see previous attachment and UK example (UK LTP AD HOC CDAS Settlement). An LTP dashboard has been developed to display and provide analyses on different management levels, from high level to detail on ADHOC spend. When we started the initiative, the ADHOC spend was very high level and lacked any detail. We can now see what the ADHOC is, where is the spend for etc. This is very useful to managers to steer. A dashboard has been rolled out with many webinars and initiatives to peal the cost layers in the countries to help to reduce the cost. See attachment LTP Dashboad VPs & MD's PPT webinar info. Over 350 resources joined the webinars. Different country sessions have been organized to take the users through the data. The ratio ADHOC (ratio taken full LTP spend) has been reduced from 12% to 6%. Attachment 9 displays the ADHOC reduction. Only KPI used in WAVE due to bad data is the amount of monthly adhoc spend data. Document with #390 additional evidence displays the ADHOC development during FY24, displaying the level of spend but also the ADHOC ratio development versus total PUD spend. 15 Juyl 2024 - Forecast and impact have been updated with June. 1 August 2024 - annualized Forecast updated with May 2025 figures. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-23 | 2024-06-28
Business Only Initiative: 01 - Change of non productivity based compensation | 393 | 7683 | Business Only Initiative | EU - PUD | Europe | Patrick Tediek, Robin Hummel | On Track | Status 17-Jul-23: - - A gap between the Wave targets and actuals driven by the need to finalize the approach to measuring the productivity increase and translating into financials. Expected to have ready for Jul-23 reporting, and updating of the Jun-23 actuals Status 19 July. * higher spend on non productivity payments due to countries switched from productivity based payments to fixed payments during FY23 due to market and volume changes. Status 20 September 2023 the KPI's require recalibrating as due to the new processes of capturing data in CDAS, the data has changed significantly and require further analyses to assess the definitions have been used correctly. For this the KPI's have been set to baseline. This will be updated. 22 December 2023 Agreed with Simon to move the end date of milestone 7999 to end of March due to functionality development. 25/04/2024 #393 - UK POC has kicked off to test the latest dashboard functionality - rate-card performance in round and areas. a change for milestone 70497 will be sumbited due to a delay in the Spotfire platform update to Remars. 02/05/2024 #393 - work on rate-card projection for PUD Bunker 10/05/2024: #393 - bunker work. 17/05/2024: #393 - bunker work. 24/05/2024: #393 - bunker work and testing dashboard. 31/05/2024: #393 - bunker work and testing dashboard. 30 June 2024 Initiative moving to L4. Guidance has been provided to the station in Europe. A process to stipulate which rate-card setting to be used - see HTP rate-card decision matrix. New functionality in the LTP dashboard has been developed to show Non Productivity Based Payments, this functionality displays the types of expense in a station, country and region. This to drive managers to take care of their non productivity based spend. see screenshot NPBP 1 Rate-card status and performance based on contracted rates and actual stops are monitored. see screenshot area performance dashboard 1. Through the dashboard the capture rate performance of rate-cards can be monitored, the functionality shows the capture rate on additional stops but also providing details on the ratio of stops in rate 2 - see screen shot capture rate performance. The dashboards shows also stop trends supporting the station managers in their stop spend assessment. See screenshot stop trends. Webinars were launched with all management levels within GOPS. Webinars with FP&A, FP&E and S&P will follow to provide visibility at different functions to support our cost analyses of the LTP subcontractors. Screenshots added to display a change in station from non productivity base to productivity base compensation and change of rate-card to have a capture rate for additional volume. 11 July 24 - Pulled back to L3 to make update to Impact and KPI's for June 2024 and pushed back to L4. 15 July 24 - Pulled back to L3 to make a forecast update as per request and added additional evidence. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-12-19 | 2024-06-28
Business w/ Tech Initiative: DK - B2C Operational Set-up (ENABLER) | 90114 | 7684 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Dipankar Debroy, Celina Knoepfle | On Track | **Latest Update - 19-May-2025** * First handover started this week * Goal to submit initiative to L4 by end of the week **Old:** * IT developments move to production * Testing ongoing * IT Developments on track * Transit Time extension is still awaiting approval from Marketing | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-22 | 2025-03-17
Business w/ Tech Initiative: Capability to switch on and off FDMI - EU LMO | 91619 | 7685 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Dipankar Debroy, Celina Knoepfle | On Track | IT developments completed & ready for L4 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-04 | 2025-03-17
Business Only Initiative: 05 - EU Station Consolidation | 402 | 7694 | Business Only Initiative | EU - PUD | Europe | Guillermo Valdes, Robin Hummel | On Track | EU Station consolidation - CONFIDENTIAL -Value Achieved: 90% -Value achieved on time: 90% -Execution of initiative on time: 90% Along EU there are several options to reduce station foot print and simplify operations merging station process or closing them with low or limited service impact NL: Close FDX location : Close FDX location : Leya and move volume towards Elst and Zwolle - clear split on GOPS cost and other functions DE: Merge 4 former LNP stations (QWUA, ZNVA, ZNSA, QKZA) + 2 more with low service impact (Giessen , Ulm ) + 4 FDX Courier station (MHGA, FRFA, MGLA, HGLA) UK: Closure proposal of 2 Express sites – EPC Glasgow ( ONHOLD) and EPC Enfield ( delayed to April23 ) and 1 domestic location – FedEx Beckton SEU: IT: Bari and Venezia closure ( Executed) ES: Merge of Barcelona ( On Hold) and Valencia (Cancelled - no capital) PL : 14 stations plan - BYDGOSZCZ and Kielce in FY23 , the rest 12 during FY24-25 - to be clarified with Country after capital allocation FR: 1 stations - POXA Original plan 33 stations - Actual Plan Jun23 : 28 - Cancelations 5 Executed : 14 Original Run rate annual FY26: $17M , related to GOPS: $10.64M and other functions $6.41M FX23 Update Mar23: Run rate annual FY25: $13.11M , related to GOPS: $6.69M and other functions $6.42M FX23 Update Jul23: Run rate annual FY25: $11.3M , FX24 - rebase lined Update Aug23: Delayed planned station MHGA in DE , For MHGA, earliest go-live is 02.10. For FRFA, earliest go-live is 18.09. Both will be reported in Nov23 but implemented mid Oct23 Update Oct 23: reported Fr POXA merge - first month reported Update Nov23: 3 new stations reported for DE Update Dec23: Original plan 33 stations - Actual Plan Dec23 : 4 - Cancelations No Capital 7 - Cancelations On Hold 4 - Executed : 18 Update Jan24: updated values and phase 3 of NL LEYA to ENSA - Original plan 33 stations - Actual Plan Dec23 : 3( 2 Fy24 1 Fy25) - Cancelations No Capital 9 - Cancelations On Hold 3 - Executed : 18 Update Mar24: updated values and DE MHGA - Original plan 33 stations - Actual Plan : 2( 1 Fy24 1 Fy25) Delayed FY26 :3- Cancelations No Capital 6 - Cancelations On Hold 3 - Executed : 19 Update 29-April-24: monitoring values and KPIS for monthly report next week Update May24: Original plan 33 stations - Actual Plan : ( 1 Fy25: Opole – Rzeszów – moving 2F1R as of June’24) - Delayed FY26 :3- Cancelations No Capital 6 - Cancelations On Hold 3 - Executed : 20 UpdateNov24: no more stations to merge under 402 - Poland pendind ones willbe consolidated in POD DOm Poland -We will move iniatiaive to L5 Actuals updated and Forecast updated Finally approved to L5 19 Nov 2024 | K: L5 | Completed | L5 | 2022-10-03 | 2024-05-31
Business w/ Tech Initiative: WS2 - Eliminate requirement for couriers to captur | 82597 | 7695 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Marco Coelho, Tobias van der Linden, Pedro A. Castro | Some Issues | **24/06/2024** - Ongoing submission and reviews for L2 approval. **03/07/2024** - Ongoing corrections for L2 submission and milestone / KPI creation and TCH document creation. Have also added some notes in the TCH document, a risk and notes in the milestone, related to the ability to measure success of REX dim/weigh capture exclusively on freight. **08/07/2024** - Change in working days from 230 to 250 **05/09/2024** - Submitted for L3 approval **06/09/2024** - Altered Impact 91703 to zero values, as entered in error by external user and not related to this DRIVE program. **25/09/2024** - Asked for KPI #86282 to be removed. As not an accurate kpi, given customer migration of Freight is not in scope of this program. **30/09/2024** Meeting with FP&A related to L3 submission and additional KPI's KPI - Percentage of freight is no longer being captured based on the countries which opt out. KPI - Percentage of freight shipments that still have information entered into the Leo device KPI - How many countries have opted out of capturing dim/weight **07/10/2024** - Still working with revenue to validate any revenue risks **21/10/2024** - First view in planview of work and trying to assess soft and non quantifiable benefits. **23/10/2024** - No soft benefits added, as these are already captured in the Hard benefits values. Following earlier KPI creation in Wave, estimated baseline values added. **21/11/2024** - Revenue sign off achieved for this work, given it does not negatively impact revenue if this was taken away. (Leo Capture of Dim/Weights) **13/11/2024** - Work now on the backlog for the SCO Architecture Decomposition. It looks like it is #26 on the Enterprise Priority list. Once Architecture is able to pick this work up they will be in touch. **22/04/2026** - Ready for L3 submission, with all financials included. | F: SL3 | Active | SL3 Domain Lead Approval | 2024-07-03 | 2026-10-02
Business Only Initiative: Productivity improvement commitment (incl. EU KPI | 90917 | 7758 | Business Only Initiative | EU - PUD | Europe | Robin Hummel, Jack Halliwell, Celina Knoepfle | On Track | **2025-11-06** Forecast adjustment for FY27/28 to remove FR as per agreement to move the savings to the Domestic initiative. **2025-09-24** * In-Station productivity targets have been increased for October-2025 by 2% **2025-09-24** * L4 Date updated from 30-May-2026 to **26-Feb-2027** to reflect the delayed implementation of FRO * Reduction of the FY27 forecast of $0.9m. No FY26 impact expected **2025-09-18** * Rebaselining of the KPI Targets for DE/IT/FR/PL completed. * Request made to change FRO milestones **2025-09-12** Rebaselining of the KPI Targets for DE/IT/FR/PL conducted. Other countries got the opportunity to rebaseline, however not mandatory. Feedback expected until end of this week **2025-09-03** Small changes being made in the productivity baseline figures for the in-station KPIs. Countries have until 11-Sep to make potential adaptations if needed **2025-08-27** Dependency set to initiative 6696, as this initiative supports in delivering a KPI dashboard to support the productivity improvement **2025-02-28** Implementation of optimization checklist slightly delayed by 2-weeks with plan to complete launch until mid march | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-18 | 2027-02-26
Business Only Initiative: Enforce in-station operations reviews | 94088 | 7763 | Business Only Initiative | EU - PUD | Europe | David Diener, Robin Hummel, John Macdonald, Sebastien Chamblanc, URSULA MARKS | On Track | 12092025 no updates reviewed options to accelerate value, | G: L3 | Active | TEMP L3 - Enter L3 | 2024-09-02 | 2026-12-18
Business w/ Tech Initiative: 03 - Increase Route Productivity (Direct Served ar | 394 | 7792 | Business w/ Tech Initiative | EU - PUD | Europe | David Diener, Sebastien Chamblanc | On Track | Document and financial review before L4 submission | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-14 | 2024-11-29
Business w/ Tech Initiative: Reduce LTP duplicate stops through launch of Debri | 80425 | 7865 | Business w/ Tech Initiative | EU - PUD | Europe | Marco Coelho, Tobias van der Linden, Robin Hummel, Pedro A. Castro | Some Issues | We are on track right now. We are currently prioritizing initiatives for next 3 - 6 months. 25/03/25 * We are in POC stage and Rollout stage in all EU. * UK Rollout might go into May due to easter week. But no financial impact expected. 14/05/2025 * Milestone ending updated because development and rollout is delayed * Email is sent accordingly * Waiting for SMEs to deliver new rollout plan 18/06/2026 **Country Pilots**:Pilots to run in all countries will for Debrief - our of scope countries Poland, France, Italy, Cyprus, Russia, Turkey and Israel. **Enhancement analysis and development** - work in progress. Do not impact go live planned. **Updated rollout plan:** * week of 22nd June - SMEs training live on community calls * Training sessions for station managers and debriefers (Provided by SMEs): 30 june till 14 july 30/06/2026 * 1 training session performed last week fot the SMEs with the last features * next 4 weeks rollout plan ongoing * spain adn portugal will roll out in 2 phases - 1 phase until end of july, second phase in September * Germany will sill perform some testing for a few month until full rollout * Full Rollout: due 29 july 04/07/2025 * manager access to debrief is now availeble * Country pilots considered closed since all major markets have already runned successful testing - excluding out of scope countries 18/08/2025 - Milestones updated GO live of the tool in all countires updated to 31-Sep-25 due to new legal approval need and lack of personal to start using the tool - MD aproved. 23/10/2025 * UK roll out ongoing in 15 locations * Eastern Europe roll out on going * waiting on roll out plan from SME in Spain, Switzerland, Norway, Sweden. 28/10/2025 * implementation postponed due to delay in some locations. * We have live stations in 70% of the coutries in scope, but still missing Germany, Sapin and most of UK that represent close to 50% of scanning locations. 04/11/2025 Forecast adjustment for FY26 and FY27/28. FY26 linked to latest outlook, 27/28 includes removal of FR as per agreement to move the savings to the Domestic POD 2025-11-21 - AT, DK and NO completed the roll-out this week; - IE roll-out to be completed until the end of the next week; - NL roll-out to be completed until the end of the next week, completing BENELUX; - UK Domestic: aligning the mismatch CDAS/LSSI. 23 Stations to be roll-out until the end of the month. - Several stations in stand-by until the end of the peak; - PT, ES on-hold until Jan'26 - DE Work Council decision, for now, is a NO GO for Debrief Tool in Germany. Also, POC Stations must be disabled until the end of the Month; Despite that it's not up to us (decision was made due to an outdated template by the WC end) we should redefine strategy/approach to overcome the situation. 2025-11-28 - DE, Meeting with Markus Scholz about the Works Council decision postponed due to sick leave; - IE, some stations postoned implementation due to staff holidays and/or need for further training. Implementation to be completed until the EoY; - LT, Roll-out expected for this (past) week. Waiting for updates; - NL, New Access Managers should be fully implemented. Remaining station should also been enabled this week. Waiting for updates; - UK, Roll-out of the 23 Stations that are already working with Debrief Tool slightly delayed but ongoing; 2025-12-12 - FI, Roll-out completed - LT, Roll-out completed - IE, only 1 Station to go **All roll-outs suspended until the end of Peak Freeze** **2026-02-05 **- UK showing great progess. 60% rolled out. Reamining locations planned to roll out until end of February. - no major updates on rest of locations - **Spain and Portugal are issue cause of lack of plan for local implemantation;** 2026-03-13 UK in last phase of rollout - 93% live, remaining to go live next days Spain/Portugal - 3 locations being tested without connection to CDAS to get next steps approval Germany - Working Council keeps blocking it Switzerland - on going training | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-01 | 2026-03-02
Business w/ Tech Initiative: WS1 - 1A Improve address correction by automation | 82581 | 7866 | Business w/ Tech Initiative | EU - PUD | Europe | Marco Coelho, Tobias van der Linden, Robin Hummel, Pedro A. Castro | On Track | We are waiting for Dataworks team to suggest us the AI Tool. We got a greenlight earlier, but now more re-validations are required from their side. We have sent them the raw data to finalise their decision. We hope to get an answer asap. Key Contact is - Kevin White. 11th December 2024 - We are still waiting for Dataworks to finish their analysis of the tools 25th Feb 2025 Waiting for Dataworks for contract signing with Loqate 25th Mar 2025 Contract is signed, development has started. We are on track 15th May 2025 Development is completed. One feature called Suggestions is rolled out in EU. Another feature rollout is in progress. This feature is Auto-correction. 25th June New Date to finish all testing updated to 11th July 1st September We will use the automatic address correction report figures from August to calculate savings and work on the money step to close this initiative this month once the savings are calculated. 2025-09-19 Achieved 44% of manual address corrections. With the AI learing curve we believe 50% will be achieble over the next few months. 2025-09-26 L4 stage - request submited | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2025-08-29
Business w/ Tech Initiative: EMR – WS6 – Develop & implement CSP PFS | 82613 | 8085 | Business w/ Tech Initiative | EU - PUD | Europe | Patrick Tediek, Robin Hummel | Some Issues | The roadmap for Spotlight and MEDALS is still pending and has been escalated. Interaction with the Dataworks team is taking place. Further information has been shared with IT. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2027-05-31
Business w/ Tech Initiative: Freight identifier (HWT) for TNT domestic shipment | 96668 | 8239 | Business w/ Tech Initiative | EU - PUD | Europe | Dominik Meschede, Amir Wahba | On Track | Agreed to put initiative on hold as IT estimation on the work needed to get a separate HWT identifier for the TNT domestic volume (T-Shirt size: M) seems too high for a limited no. of shipments which will more and more decrease with ongoing customer migration. | D: SL2 | On Hold | SL2 Domain Lead Approval
Business Only Initiative: WS3 - DE: Add 2 boom conv. HAM sorter (loose load) | 82611 | 8240 | Business Only Initiative | EU - PUD | Europe | Deniz Akbasolglu, Dominik Meschede | Some Issues | 24Oct2025 - no approval from GOPS . TBD with GOPS MD 01SEP2025 - Adjusted Milestone Date for CLEAR approval from 22AUG to 19SEP as approved 20JUN2025 - Change of scope, milestones and financials to reflect extension of ZVRA/HAM sorter only 13APR2025 - Set Milestone 2 end date 30MAY and 4a start date 30MAY 07APR2025 - non HAM Milestones cancelled due to scope change 06Jan2025 - Milestones updated in PV 30DEC2024 - Change request of Milestones Dates approved by Patrick Super 06DEC2024 - Update BC necessary; requested reschedule Milestone CLEAR Approval and RFP due to new Supplier 27June2024: alignments and final Checks done -> ready to move to L3 04July2024: ---- | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-09-02 | 2026-08-10
Business w/ Tech Initiative: WS6 - Acquire LTP cost data for EU non-integrated | 81043 | 8441 | Business w/ Tech Initiative | EU - PUD | Europe | Steve Miller, Mireia Ferrer Sancho | On Track | ** 20/2/26 - new plan received from dev team. Resources confirmed, New milestone dates entered into PV. Status returned to 'green' on track ** 27/1/26 - still no plan available or confirmation of resources ***13/1/26 - marked as some issues due to lack of plan from D&T team to complete next phase of work (linked to confirmation of resources). We have been able to extend the money step for the project but am still waiting for a project plan to confirm delivery of next phase (integrated dashboard) **10/12/25** 3 domestic countries delivered into dashboard. planning underway for next phase. money step extention approval received **6/10/25** FR UAT will start on 6th Oct as planned. PL load issies hopefully resolved - will make a formal announcement of release this week if we get 5 clear runs of the load process IT data now available for testing **29/9/25** PL now live although we are still having some problems with the data load process preventing us from an official launch. DW are still working in a resolution FR is on track for UAT and go live in Oct IT now moved (with agreement ) to Nov UAT and go live - milestones adjusted accordingly **15/9/25 ** PL UAT now conditionally signed off (on time) so expecting to have first version of dashboard live by 19th Sept. FR UAT will run as planned in Oct, but learnings from the PL UAT mean the IT UAT will be delayed until November release - mainly due to availability of knowledgeable resources to run the UAT and assess impacts of observations. We feel it will be better to run a quality focussed UAT for each country seperately to guarantee a better quality product overall. No impact on money step | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2026-07-30
Business Only Initiative: DE - B2C operational setup | 1047 | 8805 | Business Only Initiative | EU - PUD | Europe | Robin Hummel, Hanns Hubertus | On Track | Status Update: - - 02-May-2024: LSSI changes went live successfully, allowing for turning off of DEX17 solution for intra. EU FICP volume into DE. Assessment ongoing on request to increase SHEIN volume into DE from 3.5t to 20t per day - 08-May-2024: DEX17 removed successfully on 06-May. SHEIN assessment ongoing however challenging to meet SLA with proposed flight movements from APAC. New customer Farfetch started shipping ~1-1.5k APPD to DE on FICP (and partially IP) - 16-May-2024: April actuals added with $174k savings and continuous growth in volume | I: L4 | Completed | L4 | 2022-12-12 | 2023-04-28
Business w/ Tech Initiative: WS2 - Automate the application of pickup scans and | 2768 | 8861 | Business w/ Tech Initiative | EU - PUD | Europe | Giancarlo Pinto, Marco Sclep | On Track | Initiative #2768 being progressed from L0 to L1 after IO and back-up IO have reviewed and updated the Overview and Impact tabs. | E: L2 | On Hold | L2 | 2024-07-22 | 2025-11-28
Business Only Initiative: Discipline Pick Up execution - DICE- Reduce negati | 2321 | 8909 | Business Only Initiative | EU - PUD | Europe | Guillermo Valdes, Robin Hummel | On Track | -Value Achieved: 100% -Value achieved on time: 100% -Execution of initiative on time: 100% Issue identified in UK and PT in Fy23 : they have changed CDAS and they do not pay this negative stops : 915k$ potential value leakage - risk updated Feb23 launched in Europe New forecast due to new data in cdas ( less countries paying PUX43) $1,5m + $0.8m ( Fr Domestic) / Total $2.3m - Old New Forecast Aug23: increased due to Nordics countries stop paying negative stops in DK NO FI - pending SE Total: ~$2.55m Investigating potential impact and actions on PUX40 ( Duplicated collections) - POC in August23 with logic changed in MyTNT2 Working initiative as BAU Investigating potential extra savings in Italy in Domestic system Good progress month by month exceeding plan Dec 4th: increased forecast for F24 and Fy25 based on last 4 months trend Feb 5th: Good trend again below 5% after peak Mar 13th: increased forecast for F24 and Fy25 based on last 1 month trend Planning to move to L4 - pending - Final OK from Esha and Simon 2024-04 trends update Monthly trend: ![](inline-attachments/2321/image/3bc1f8f4-684a-49d0-8831-6fe51340679e-image.png) Good progress week by week exceeding plan ![](inline-attachments/2321/image/85aff37a-f63d-40a8-94b3-91e52daa27ce-image.png) | K: L5 | Completed | L5 | 2022-11-21 | 2024-03-29
Business Only Initiative: Preferred vehicle leasing suppliers (Int) | 3141 | 8997 | Business Only Initiative | EU - PUD | Europe | Naser Amer, Kyle Mitchell | On Track | on Track | I: L4 | Completed | L4 | 2022-12-01 | 2024-05-31
Business Only Initiative: Dataworks & other IT related cost tracker | 4883 | 9042 | Business Only Initiative | EU - PUD | Europe | Steve Miller, Arjan van den Broeck | On Track | awaiting approval to move to L4 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-07-31 | 2025-03-31
Business Only Initiative: Dedicated PUD - The Netherlands | 5341 | 9050 | Business Only Initiative | EU - PUD | Europe | Sebastien Charpentier, Claudio Modonese | On Track | The money step is completed, ready to start tracking the KPIs and the generated savings. Proofs of execution has been uploaded in the attachment section however the KPI and the Impact lag behind because of delay in getting the relevant data for calculation. | K: L5 | Completed | L5 | 2022-10-03 | 2022-10-03
Business w/ Tech Initiative: DE_§73 Specifications for packages with increased | 94736 | 9231 | Business w/ Tech Initiative | EU - PUD | Europe | Benjamin Dorn, Robin Hummel, Celina Knoepfle, Amir Wahba | Some Issues | 2025-10-24: In Progress: Work is aligned with JCLS (PCC - Purple Common Core) ART PI5, Sprint 1. Development is scheduled across two sprints, with completion targeted by November 4, 2025. Next steps: Test plan development Solution realization and go-live planned for January 2026 Risk/Awareness: Enterprise prioritization of 160, Commercial Portfolio prioritization of 83 and Domain prioritization of 34, puts resource assignment during execution at risk for a regulatory change. Request did not arrive to the offline systems in time to make the Spring 2026 General Release. Manual work around stickers will continue to be used for shipments originating from the offline systems until coding can be completed in the subsequent general release. Transition challenges arising from changes in previous vendors/resources (Syntel/WIPRO), impacting technical capacity. Current vendor, Accenture, experiencing difficulties with resource fulfillment and required domain expertise. 2025-11-05: In Progress: Work is aligned with JCLS (PCC - Purple Common Core) ART PI5, Sprint 1. Development is in process, with completion targeted by November 18, 2025. Next steps: Test plan development Targeting Dec 1-18 for Testing Solution realization and go-live planned for January 2026 Risk/Awareness: Enterprise prioritization of 160, Commercial Portfolio prioritization of 83 and Domain prioritization of 34, puts resource assignment during execution at risk for a regulatory change. Request did not arrive to the offline systems in time to make the Spring 2026 General Release. Manual work around stickers will continue to be used for shipments originating from the offline systems until coding can be completed in the subsequent general release. --> 12-18months after Target Date (Jan27-Jun27) Transition challenges arising from changes in previous vendors/resources (Syntel/WIPRO), impacting technical capacity. Current vendor, Accenture, experiencing difficulties with resource fulfillment and required domain expertise. 11-11-2025: Complete: - Conceptual architecture has been finalized. - Initiative approvals secured; currently progressed to Level 3 stage. - IT PM/EO/QA Lead identification completed. - Offline applications plan to accommodate the weight icons in their Spring 2026 release. In Progress: - Development is in process, with completion targeted by November 18, 2025. - Test documentation ready for review and targeting review next week when IO is available. Next steps: - Testing targeting Dec 1-18 - Solution realization and go-live planned for January 2026 for online applications - Applications to provide their deployment dates Risk/Awareness: L4 Date: 30 Jan 2026 - Enterprise prioritization of 160, Commercial Portfolio prioritization of 83 and Domain prioritization of 34, puts resource assignment during execution at risk for a regulatory change. - Transition challenges arising from changes in previous vendors/resources (Syntel/WIPRO), impacting technical capacity. - Current vendor, Accenture, experiencing difficulties with resource fulfillment and required domain expertise. 11-26-2025: Completed: Conceptual architecture has been finalized. Initiative approvals secured; currently progressed to Level 3 stage. IT PM/EO/QA Lead identification completed. Offline applications plan to accommodate the weight icons in their Spring 2026 release. Test documentation reviewed. In Progress: Development is in process, with completion targeted by November 18, 2025. Test execution targeting Nov 21 to begin. Next steps: Solution realization and go-live planned for January 2026 for online applications Applications to provide their deployment dates Risk; Enterprise prioritization of 160, Commercial Portfolio prioritization of 83 and Domain prioritization of 34, puts resource assignment during execution at risk for a regulatory change. Transition challenges arising from changes in previous vendors/resources (Syntel/WIPRO), impacting technical capacity. Current | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2026-06-30
Business w/ Tech Initiative: EDI Checker Replacement | 96388 | 9233 | Business w/ Tech Initiative | EU - PUD | Europe | Benjamin Dorn, Celina Knoepfle, Amir Wahba | On Track | green | E: L2 | Cancelled | L2 & CCH
Business w/ Tech Initiative: EU - B2C Operational Set-up (ENABLER) | 16222 | 9268 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Mike Ruckert, Celina Knoepfle | On Track | Initiative Confidence Level: - - Value Achieved = N/A - IT Enablement initiative - Value achieved on time = N/A - IT Enablement initiative - Execution of initiative on time = 100% Status Update: - - 25-Apr-2024: LSSI developments to go live with May-24 URSA (29-April) - 02-May-2024: Successful go-live of the LSSI changes. Development working as expected leading to DEX17 to be turned off by 06-May-2024 - 08-May-2024: DEX17 solution for FICP into DE has been turned off successfully. All milestones closed - 16-May-2024: No update | K: L5 | Active | TEMP L5 - Enter L5 | 2023-04-17 | 2024-08-02
Business w/ Tech Initiative: IE - B2C operational setup (ENABLER) | 24310 | 9515 | Business w/ Tech Initiative | EU - PUD | Europe | Robin Hummel, Kieron Everitt, Celina Knoepfle | On Track | Updates 03-Apr-2025 - - IT developments completed and volume handed over Updates 12-Aug-2024 - - Initiative changed to enabler initiative linked to #69824 - All value removed from the initiative Updates 22-Jul-2024 - **Leadership Attention** - Planned move to production of Ireland LMO solution cancelled due to the global IT production load freeze. Currently undetermined timeline until when the load can take place **Previous update** Final IT developments expected to be ready for move to production by end of July. Small production testing required to validate the operational solution prior to actual handover of FICP volume to AnPost | K: L5 | Active | TEMP L5 - Enter L5 | 2023-09-04 | 2025-03-17
Business w/ Tech Initiative: Integration of SIV prior to FRO international |  | 87142 | Business w/ Tech Initiative | EU - PUD | Europe | Tobias van der Linden | On Track | Initiative put on Hold. Legacy corporate technology are in containment and priority on Corporate developments go to the future GPDE Globalization. Considering GPDE is expected to be launched by Q1-CY26, the value for this initiative becomes less significant due to the reduced value capture period. SIV is already on the plan to be integrated with the future state GPDE technology. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: Volupia-move solution to OIP & station deployment |  | 90346 | Business w/ Tech Initiative | EU - PUD | Europe | Mireia Ferrer Sancho, Robin Hummel | Some Issues | - DW working on the local enhancement to feed the Volupia station model with non-integrated shipment domestics data from EU360 - DW requested to create a new initiative to request their support for: •Data consumption from EU360 (volumes that we get from SEP today) •Country model decommissioning for stations - The team has identified that some local engineers misinterpret the outcome of the forecast; this is a concern. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-12-09 | 2026-09-30
Business Only Initiative: Camberley - J4 |  | 93872 | Business Only Initiative | EU - PUD | Europe | Miguel Fernandes, Ben Radford | On Track | All on track | K: L5 | Completed | L5 | 2024-10-15 | 2025-02-14
Business w/ Tech Initiative: PUD3&4 Improvement |  | 103193 | Business w/ Tech Initiative | EU - PUD | Europe | Sebastien Chamblanc, David Diener, John Macdonald | On Track | 27.08.2025 Money step : They will be already money step in FY26 with some of the features already developed and launched. Exit Rate will happen as soon as all features completed in FY27. On-track - Has to be assigned to Lukasz Bagdanski and Piotr Sobon 23.04: This is not a new product to be developed, it’s just improvements to the current version with no major architectural changes. Before we’ll go ahead with development it will be confirmed with Robert Sims, upon his approval we’ll start all necessary work. Hence, there’s no need for this to be in queue for Enterprise Architect. | G: L3 | Active | L3 | 2025-09-01 | 2026-09-04
Business w/ Tech Initiative: EDP EU Requirements |  | 107304 | Business w/ Tech Initiative | EU - PUD | Europe | Marcos Gonzalez, John Macdonald, David Diener, Jonas Broughman, Maria sim | Some Issues | 2025-11-15 L1 Architecture alignment Approved on Nov 14th 2025. GO from Finance and Domain QA to move to L2. 2025-12-04 L2 inputs in progress. PPM Proposal submitted 1834590 - EDP EU Requirements 2025-12-10 L2 inputs in progress. PPM Project 1835156 has been created from Proposal 1834590 - EDP EU Requirements. The Proposal is now Closed (Approved). 2026-01-22 Initiative scope updated: Platform migration works moved to another inititive. Platform Portfolio not impacted anymore. Initiative remains as T-shirt size M. 2026-02-27 Initiative still in L2. Kept low in the Enterprise ranking. IO raised Boost justification to submit to be considered. 2026-04-02 Opoened a case INC034441397 to move initiative to Local Enhancement. | E: L2 | Active | L2
Business w/ Tech Initiative: Courier ADR Points |  | 132398 | Business w/ Tech Initiative | EU - PUD | Europe | Timothy P. Hartless | Attention Needed | Initiative is only moving down the ranking with no visibility or estimate on when this will move to L3. Waiting for assignment of an Enterprise Architect and submission of a decomposition document before this initiative can be submitted for L3 approval. | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: Reporting capabilities for EU Debrief application |  | 169333 | Business w/ Tech Initiative | EU - PUD | Europe | Marco Coelho, Pedro A. Castro | On Track |  | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Make Debrief & MFR Compatible with GPDE |  | 187857 | Business w/ Tech Initiative | EU - PUD | Europe | Richard Soubies | On Track | Cancelling this demand since other solutions not involving dependencies with other ARTs have been identified. This demand is no longer needed | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Volupia European Forecast Enhancements |  | 191326 | Business w/ Tech Initiative | EU - PUD | Europe | Alejandro Arruebo | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: WS5 - Operational Analytics (KPIs) | 82614 | 6696 | Business w/ Tech Initiative | EU - Sort | Europe | Anshuman Prabhakar, Maria sim, Lars Paeschke, Adrian Bondar, John Macdonald, Robin Hummel | On Track | Release 1.1: * Early Feb - 360 Nav Platform will be made available to 4.5K+ OPS and P&E users * WS7: Working on CWC view with Event Dates to determine daily perfroamce of locations * Station Insights: Booking page is developed * UAT is in progress * Priority Metrics development for 4 ESP PMs in progress. To be launched in next reelase. * Team performed limited performance test on the platform. More investigations in progress to scale up performance testing. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-15 | 2026-05-29
Business w/ Tech Initiative: WS1 - [1C - Project Zenith ] Execute Sort with Cur | 82588 | 6782 | Business w/ Tech Initiative | EU - Sort | Europe | Kapil Gogia, Thomas Mackenzie | Some Issues | Updated: Apr 13 2026 SUCCESSES * Second SME session held last week and was very well received. This ill be followed by 1 more in the coming week * Five (5) User Session trainings invites have been sent * Most defects are fixed or close to being fixed - SFP Dashboard issue still being resolved by the L3 support team * Performance issues resolved both in On Cloud and On Prem but testing in On Prem still due IN PROGRESS / NEXT STEPS * SME training plan in place. Target roll-out all Europe - May 31 * SME Sessions (3): April 13, 2026 Purpose: SFP knowledge sharing with the SMEs and getting feedback on what training content they would like to have and basis that feedback, refine our module training sessions MILESTONE TARGETS * On Cloud Rollout - In progress * Full Rollout - Target May 31 2026 RISKS * Testing/Analytics Lead pulled out of EU SFP leaving big gap from Analytics point of view LEADERSHIP ASKS | G: L3 | Active | L3 Feedback Requested | 2024-05-06 | 2026-09-04
Business w/ Tech Initiative: WS1 - [1C - Project Zenith ] Comprehensive E2E Net | 82590 | 6786 | Business w/ Tech Initiative | EU - Sort | Europe | Giancarlo Pinto, Oliver When | Some Issues | 28 Nov 2025 SUCCESSES - Nothing to report IN PROGRESS / NEXT STEPS - EPIC 2 ARB - Agreement on initiative has been reach, Two initiative one with Epic 1 &2 and two Epics for 3 & 4, value estimation split analisys on going - Initiative temporarely on hold due to internal Initiatives/Programmes reorganization MILESTONE TARGETS - NA RISKS - Confirmation received about EU usecase not prioritized for PI4 to start development, LEADERSHIP ASKS - Nothing to report | E: L2 | Active | L2 | 2024-08-08 | 2027-05-31
Business w/ Tech Initiative: WS1 - [1C - Project Zenith ] Interim SFP | 82587 | 6788 | Business w/ Tech Initiative | EU - Sort | Europe | Jessica Ferrari, Thomas Mackenzie | On Track | L4 status is currently in progress. Ongoing activities include: 1-Reviewing the SFP platform in collaboration with the data work team. 2-Implementing SPF for countries included in Phase 1 of the rollout. L5 expected date March 2026 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03 | 2026-01-29
Business w/ Tech Initiative: WS1 - [1A] Exploit Shipment data opportunities wit | 82579 | 7395 | Business w/ Tech Initiative | EU - Sort | Europe | Christian Johannes Visschedijk, Ramon Kok, Fedor Lenting | Attention Needed | We can't move the intitative to L4 because its success is no longer measurable. After the initiative went live in October 2024, we observed positive results for 3 months, with shipment duplicates reduced by 80%. Unfortunately, since January 2024, the duplicate rates have returned to their previous high levels. These TSS duplicates issues are not related to our initiative but are due to other changes in TSS, data flow disruptions, the rollout of different scanning devices, team transitions, and other technical problems. As a result, we can no longer accurately measure the initiative’s success, and it appears destined to remain in L3 indefinitely. Due to ongoing problems with TSS—not just duplicates, but other unintended effects—an in-depth analysis was conducted, leading to a comprehensive understanding of the issues. A new initiative has been launched to address them: Local Enhancement ID 0107419 – TNT Shipment Services Development, currently in L2, and targeted for completion before the peak period. This new initiative is Work ID 0107419, please see PlanView Initiative 0107419. Hence this initiative will be set to completed. | G: L3 | Cancelled | L3 Feedback Requested | 2024-05-15 | 2025-10-17
Business w/ Tech Initiative: WS1 - [1A] Improve sort flow process efficiency fo | 82580 | 7415 | Business w/ Tech Initiative | EU - Sort | Europe | Maria sim, Gianna Abello | On Track | 20 Feb 25 - Requested L5 checklist from FP&A All milestones complete and initiative trending positely against plan. Estimated move to L5 would be end February 2025 as per guidance that 3 months would need to be available | K: L5 | Completed | L5 | 2024-07-22 | 2024-11-08
Business Only Initiative: Target Service improvement upon realisation of all | 83687 | 7417 | Business Only Initiative | EU - Sort | Europe | Elisabeth Vullings, Maria sim, Gianna Abello, Thomas Hartshorn | On Track | 9 Oct 25 - Rebaselining exercise complete to align with Global NSL Targets, removing $6.3M & $11.1M from the FY28 NRB. .28 Nov 24 - Service monitoring postively for October and all enabling initiatives that have gone live are trending very positvely, , therefore, returned to On Track but will continue to monitor Some of the enabling initiativs are trending behind schedule eg 82584, 82582 investigation required on the impact for the value realisation | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2026-06-01
Business w/ Tech Initiative: WS2 - Consolidate sortation, routing, label printi | 82598 | 7437 | Business w/ Tech Initiative | EU - Sort | Europe | Guiomar Sanz Redrado, Traian Sinescu | On Track | CW 40 - Maria Sim update the money step to 17th October as agreed on the Sort POD Sponsor call with Miguel and Joram. This allows for the solution to go live and IO to return from holiday to review the business case status CW 31 - Follow up on open items pending for TCH review / L3, awaiting domain architecture assessment. Call held with HR Learning to clarify HR and L&D needs. CW 32 - Portfolio EU and US added by TCH / CW 33 - Added Ressource Template / CW 38 - Received TCH Greenlight / CW 39 - Stakeholders review session held CW 40/41 - SCI review. discussions on non-acceptable NFR and options to reduce CW 42/44 - Discussions ongoing to adjust SIP posting logic to requirments from the central / QPI teams, only point missing to complete SCI CW 45 - Agreement not to autopost SIP, discussions on repeated SIP logic. Issues securing printer rolls for testing printer escalated CW 48 - SCI completed and ready for approval, but approval session delayed to 5 th Dec due to Thanksgiving holiday CW 50 - SCI presented to surface review on 5.12. Awaiting approval / Attempting to get hold of FRO-size labels for testing better visibility of intercept. In contact with US Ground team to get a test label CW 51 - SCI to be considered approved following Chand Shaik & Brandon Slone (Manager Architecture Review Board) recommendation on 18.12 as few approvals pendings and no rejections so far // Initiaitive presented to Sort Solution Leadership Council on 17.12 and approved with questions on PFS and architectural decisions to limit future work. // Label roll from Ground on way to HOF to test new label size and increase intercept visibility CW2 - Agreement no Supply Chain demand is required due to approval from Sort Solution Leadership. Features and Capabilities entered in Agility. New labels formats receied and layout test in progerss. CW4 - Updated milestones after feedback from developers. Contacted Markus Scholz for potential pilot in AGEA. CW5 - Initiatied analysis of iroads locations, DH2 rollout and printer needs. CW6/8 - Presented initiative to DH2 user community to positive feeedback. Development continuing, with confirmation of menu design and configuraiton UI CW10 - Discussion on CLEAR creation for the Honeywell printers. Preparation on configuration files for ITD to link UDS and IROADs and to configure postings CW12 - Developmet 90% ready but blocked due to iroads team support not being prioritized. Procurement of new printers and budget source still tbd, delaying actual usage of solution in operations (POC printers have been secured) / CW13 - Still no feedback from iroads team. Milestones to be updated/delay. CW14 - Development delayed to end 27May (end next PI, as per development team) due to missing iroads information and both solution and application architect having left the company. Not possible to absorb delay by reducing testing window, so main milestone is affected. CW16 - Printer selection confirmed by US Ops Tech & Innovation team. Discussed MVP1 of labels without iroads information to unlock value until iroads team can be involved. CW17 - IT confirmed no Iroads ressources available until 5.May, causing project to be delayed. CLEAR approval ongoing but FY25 budget expenditure unlikely. CW18 - CLEAR for printers approved. Preliminary feedback from developments team of MVP1 (without iroads info) planned to be completed 20.May CW31 - Updated milestones. POC penciled for September due to vacations and iroads/lsre mto CW43 - After discussion with FP&A and POD Coaches on23.10, financials agreed to not be adjusted. CLEAR 100012353 for printers (that can be used by FRO/PUD POD) considered BAU. Avoidance of replacements are covered in parent initiative 83027. Development costs were entered following previous guidelines. Target move to L5: March2026 CW46 - Approval for FR obtained from WC as per info from Emilie Geoffray on 12.Nov | K: L5 | Active | L5 | 2024-07-15 | 2025-11-11
Business Only Initiative: WS1 - [1A] Paperwork Improvements - reduce #Airway | 82585 | 7650 | Business Only Initiative | EU - Sort | Europe | Marielle Sitskoorn, Sue Bird, Samantha Gomes | On Track | **11Aug25** - "Expect to move initiative to L5 as of 1 June 2026 after 12 months from go live" - Forecast used for July actuals (agreed by Maria S with Rob D and Olga G) due to vacation of source data SME - to be updated upon SME's return and data provided. **08Aug25** We are working on moving this to L4 w/c 11Aug, required review with PUD and FP&A. In addition we are updating KPIs and obtaining Jul25 Actuals. **04Aug25** - call Robin Hummel and Maria Sim and need to adjust forecast and apply Jun/Jul2025 numbers for "actuals". **24Jul25** SVP Approval to move moneystep and L4 to Aug25 ******21Mar25** - Policy Grid "go-live" date pushed to 17/18May25 by US Policy Grid owners (Bret P and Mark C) **06Mar25** Still working towrads Go live on 19th April: - approval required to go live without T-status indicator in Policy Grid - minimise risk for customers with intra-EU T-status shipment - Work on internal- en external communication **27Feb25** US advises to go for 19thApril implementation date - this means one month delay of current money step date - due to high amount of changes for current month no fallback option to roll back when unexpected issue occur with T-status shipments. Aprroval required for Go Live, despite the fact that no segregation is possible bewteen T-status vs V-status shipments. Small risk for Intra-EU T-status shipments. **20Feb25** on average there are 1400 Intra-EU customs controlled shipments per month from non-ETD accounts. Still invetisgating data - some large accounts can be moved to ETD, quite a few shipments from internal FedEx (non rev) accounts and some false T1 shipments. But there will always be a risk that for a few T1 shipments no AWB will be printed. **14Feb25** Small risk - unfortunately there is no capability to distinct C-status from T-status with priniting the amoun of AWBs. This would mean that for Intra-EU T-status shipments no AWB copies will be printed. This is a small risk, because there are probably just a few of these type of shipments, and probably most of these customers are on ETD. But the volume still need to be analyzed. Do we progress Y/N? **09Jan25** On schedule - socializing planned changes with P&E/ Ops/ Clearance mgrs. Working on internal and external communication. **19Dec24** - On schedule - working on internal/ external communication with Marketing. Draft Purple Track message is ready. **04Dec24** - Verifying with Stn Admin IO for cross-over. Working on Communication plan for Jan24 **26Nov24** - Target date update from Mark Coyne to Samantha G and Team email 26Nov24"...can [not] guarantee a February 10th ...think it is realistic...new grid ...likely be moved ...on a Saturday,.. 8th or 15th[Feb]. ... one big dependency... spoke with the TradeTools release manager yesterday ... team is planning on MTPing the functionality that would allow us to make these changes without IT on January 4th [2025]. If that MTP is successful it should leave us more than enough time to implement this change by February 7/15. If that MTP is delayed for any reason then we still might be able to do it in that time frame, but it would be at risk." **19Nov24** - Confirmation from Legal (OUE) that Digital will update upon AWB creation to see referenced to EU T&Cs. Awaiting conf at country Legal Counsel from COE **01Nov24** - Awaiting Legal approval following checks with Digital, Local Legal Counsels and verification of local language options on-line account opening. Will request configuration change with US IT (Brett Perry/ Mark Coyne) for next slot. On track for L3 submission, no late milestones | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-27 | 2025-08-08
Business w/ Tech Initiative: WS1 - [1B] Shipment CDM - First iteration for Sort | 82586 | 7693 | Business w/ Tech Initiative | EU - Sort | Europe | Ramon Kok, Fedor Lenting, Dave van Wingerde | Some Issues | **2025 SEP 30** - 5 Shipment Art related capabilites still in **“on-hold”** status. On-hold until after peak this year. - Not for capability 1.5 (consume by Sort), that capability is active - We continue our efforts towards Shipment PFS via the new shipment tech foundations. This work may be rebranded as part of these tech foundations. - **Capability 1.5 will be planned after delivery of SSDC2.0 – Dataflow to Sort (targeted at CY26-1 - CY26-2)** **29 Dec 2025** New Sort versions of SSDC will not work on SEP data anymore. So, this initiative actually no longer works as it is built off data flows that we will no longer being using in UDS Sort. CDM was meant as an enabler, no value will be added and was built on SEP data flow. Approval for cancellation requested **Rationale for cancellation:** *Reason* •During the bunker the concept of common data model was created, however, since then we have evolved past the first concept into a new different way of approaching the Common Data Model. This is owned by the Global teams in the US •This initiative actually no longer works as it is built off data flows that we will no longer being using in UDS Sort (not known at the time that we started this initiative) *Impact* •There is no financial impact to the POD •Enabler initiative only | G: L3 | Cancelled | SL4 Finance Domain Lead Approval | 2024-08-09 | 2027-01-15
Business w/ Tech Initiative: WS7 - Reduce Manual Handling Efforts in Stations | 82682 | 7705 | Business w/ Tech Initiative | EU - Sort | Europe | John Macdonald, Adrian Bondar, David Diener | On Track | Update 05112025- As agreed in recent steer-co this intiative can be cancelled. The SMLs bagging will report progress % compliance to PUD and Sort HFS as an enabler. Update 20122024 30/60/90 Plan - see Milestone Chart Success stories and learning RTM Station BotG completed. All necessary controls in place to produce stable performance to target on SML bagging, i.e. SOP, WI, KPIs etc Floor space, IT Apps and Ops consumables now in place and used Results – RTM bagging 80% of SMLs to QAR, LGG and CDG Open issue - the 360 Dashboard was not available to support BotG (Legacy report used). Awaiting update on UAT plans for early 2025. - FP + A target for RPC (aligned with Drive Pods, i.e. 388, HFS etc.) for 2025 not shared or published. Update pending - FP + A governance approach to monthly Actual (USD) into Planview not agreed. Update pending Action plan for upcoming weeks 360 Dashboard team advise that necessary changes will be in place by mid-January to allow UAT to occur [#82614]. Follow up with FP+ A on RPC targets for 2025 Follow up with FP + A on how monthly governance meetings will work to translate the lead KPI % SML bagged ex origin into USD Actuals for Planview ** Attention needed. Obtain and send SVP message to target audience to engage with Sort Pod (bless kick off Jan - March campaign with full support (ownership) and resources allocated Ensure 360 Dashboard passes UAT and is ready for Jan-Mar 2025 campaign. 360 Dashboard team must produce a user guide to prep UAT scripts and to allow the Sort Pod to produce Playbook (critical path) Ensure FP+A agree way forward with 388 and HFS on target setting and reporting for stations. To ensure campaign reporting (Actual USD) and Planview Actual updates (critical path) Risks 360 Dashboard is under pressure to make mid-January deadline the level of engagement in January with Champions and front line facility mgmt will be diluted with no Dashboard available to track compliance and results. Update 06122024** 30/60/90 Plan - see Milestone Chart **Success stories and learning** RTM Station BotG in week 3. DH2 scanning now put in place. SMLs bagging now live to QAR, LGG and CDG Dedicated SML sort area set up in RTM floor Drivers now segrgating SMLs KPI Dashboard [#82614] regular meetings to UAT approve the tool.** **Action plan for upcoming weeks** Continue KPI Dashboard daily meetings to approve UAT [#82614]. Enter into week 4 of BotG. Validate process controls (SOP / WI) and Mechanisms (Scanners, floor space, bag racks, bags, tags and emplyee comeptence) Escalate urgency of FP + A target for 2025 RPCC. This to allow campaign reporting on process compliance (% SML bagged) and USD Actuals for Planview Produce SMLs bagged Playbook and perform train the trainer on CWC Champions ** **Attention needed.** Obtain and send SVP message to target audience to engage with Sort Pod (bless kick off Jan - March campaign with full support (ownership) and resouces allocated Ensure 360 Dashboard passes UAT and is ready for Jan-Mar 2025 campaign. 360 Dashboard team must produce a user guide to prep UAT scripts and to allow the Sort Pod to produce Playbook (critical path) Ensure FP+A agree way forward with 388 and HFS on taregt setting and reporting for stations. To ensure campiagn reporting and Planview Actual updates (critical path) Update 04102024 30/60/90 Plan - see Milestone Chart Success stories and learning L3 approved. KPI Dashboard [#82614] daily meetings to fine tune the approach. New milestone [Ronald Bout] about allowing NC shipments into totes to be conveyed and sorted onto the parcel sorters. QAR personnel are enthusiastic about using NCs to Totes so that there is momentum. Action plan for upcoming weeks Continue KPI Dashboard daily meetings to fine tune the approach [#82614]. QAR Pilot Convey NCs in totes. Align with Sort Technology to create reports that can capture the data for totes processing NCs. Attention needed Obtain and send SVP message to target audien | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-06-03 | 2025-06-30
Business w/ Tech Initiative: WS1 - [1A] 82582 Sort-Unitize C status on barcode | 82582 | 8095 | Business w/ Tech Initiative | EU - Sort | Europe | Marine Lampaert, Traian Sinescu | Attention Needed | **March 23rd: ** - SCO - capability 6: MTP delayed to May26. No impact on value but Money step needs to be moved to end of May26. - Commercial: GSM MTP scheduled for March 26 (remaining 10% of the value). Status to be confirmed by the commercial teams. **Dec 8th:** Approval received to move the Money step to April26. Timelines have been updated in PV. **Nov 26th:** Rollout ongoing - value achieved around 90% - Commercial: GSM MTP pending and delayed to Mar26 (vs Dec25). Affecting around 10% of the value. As a consequence Money step needs to be moved to Apr26 (vs Feb26). - SCO - capability 6: development ongoing / No impact on the value **Sep 8th:** Rollout ongoing - value achieved around 88% - Commercial: pending for Cafe and GSM only. - uDS: rollout completed Money step changed from Dec 2025 to Feb 2026 due to an additional capability added. This capability does not impact the value. New capability (capability 6): Rationalize the way systems are defining which territories are part of EU. Today the definition is maintained in 4 different systems (Trade tools, ISDC, Visa prime, MSO) leading to inefficiencies and discrepancies between systems (C/T information in the barcode could be different from the C/T information in the data). In addition, the definition coming from Trade tools and used in the barcode is more accurate than the one from ISDC, Visa prime and MSO as using postal codes vs Visa location codes. It was therefore decided to add a capability so that ISDC, Visa Prime and MSO could leverage the definition from Trade tools. **Aug 1st:** Rollout ongoing, no issues identified in production and starting to see the benefits. - Commercial: pending for Cafe and GSM only. - UVSDK service: done - uDS: rollout completed at 98% **Jun 6th:** Move to prod started - Since Jun 2nd labels for EU free-circulation contain the CLR handling code (phased rollout on commercial side therefore CLR is present on around 82% of the FDX EU free-circulation) - UVSDK service will be loaded on the uDS on Jun 16th - New uDS version rollout will start on Jun 17th (that's when we will start seeing some value for the FDX packages) **May 15th:** Go given for the following: - Trade tool to produce the trade affiliation file on May 17th - USVDK to load their code changes to PROD on 5/17/25 and use the trade affiliation file from Trade tools for building of the JUN25 PROD URSA file to be effective in Production on 6/2/25 - UVSDK service to load their code change adding the free-circulation flag - Summer 2025 - uDS to load 4.3 When sorting on barcode set the Custom controlled status depending on the free-circulation flag received from UVSDK service & 4.6 Modify the sort/unitization parameters to add FDX C-stat and FDX T-stat - Summer 2025 *Note: uDS rollout cannot start before the full release testing is completed (including changes not related to this EPIC)* **May 2nd:** Decouple testing is planned May 5th / May 6th. We then expect both fixes for defects #33157 and #43120 to be deployed to L3. This leaves just a few working days to complete testing before the Go/no-go on May 13th. We are therefore at risk for this milestone. This could have an impact on the money step. **April 25th:** L3 testing is blocked due to the two below defects: - #33157: CLR is getting removed when performing a PUP with LEO/Pscan. Fix will be done by UVSDK team and will be ready on May 5th. - #43120: FDX domestics should be identified from the form ID and not using the goods-classification-code received from UVSDK. Fix planned for end of April. Testing will resume once these fix are delivered. Still targeting May 13th for the Go/No go **April 11th:** L3 testing ongoing. 5 defects opened (tracked in valueedge octane). Update on the 2 most critical ones that could impact the MTP: - #33157: CLR is getting removed when performing a PUP with LEO. Fix will be done by UVSDK team and should be fixed end of April. - #43120: FDX domestics should be identified from the | G: L3 | Active | TEMP L3 - Enter L3 | 2024-05-01 | 2026-03-31
Business w/ Tech Initiative: WS1 - [1A] 82583 More granularity for intercepts | 82583 | 8096 | Business w/ Tech Initiative | EU - Sort | Europe | Marine Lampaert, Traian Sinescu | On Track | 12th August 2025 - This initiative is on hold pending the outcome of 97130 - Data flow to sort solution. Once 97130 we will review this initiative again to determine the best solution **April 11th:** Solution architect has been assigned. When available design of the solution will start **Feb14th:** Status changed to ontrack as it was agreed to put this initiative on hold. **Jan 30th:** Initiative is put on hold for 1 month to focus on the dataflow to sort. **Jan 13th:** we actually have a bigger issue than just the manual removal of intercepts with DH2 as solution design of 82584 will not over the needs of this initiative. This will most likely require developments in uDS, DH2 and CIS. Raj will follow-up and prepare the solution design and/or implementation plan. **Jan 7th:** An issue was discovered regarding the manual removal of intercepts with DH2. Indeed DH2 is calling an API to retrieve the configuration of intercepts that are allowed to be removed manually. This configuration is stored in CIS and contains the uDS category (CUO, CUE...) on top of the handling code. As we plan to change the uDS category of some handling codes this process will be impacted. In addition during the transition period the same handling code could be mapped to 2 uDS category (the old one CUO and the new one CUP for example). 2 options are being discussed: Update the config file to add the new category on top of the old one or make changes in DH application to ignore the uDS category coming from CIS file. Follow-up call organized on Jan 13th. **Dec 31st:** Communication is being prepared for the change that will happen on January 14th (adding the new sort modifiers in uDS - preparation step). **Dec 12th;** As a preparation step, new sort modifiers will be introduced in uDS on Tuesday 14th January but won't be used as no handling codes would be mapped to them. **Dec 3rd:** On the deployment options it was decided to select the one with the dependency on #82584. There is therefore now a herd dependency on #82584 and any delay on that initiative would delay this one. **Nov 15th:** Initiative put back on track as timeline for 82584 (delivery in March 2025) is compatible with our April 25 target. Therefore even if we keep the dependency we can make the date. Still there is a risk of delay if #82584 is delayed. **Nov 7th:** Initiative was rebaselined. Money step is now Apr25. The discussion on the deployment and whether or not "dependency with #82584 can be removed" as not yet happened and this is putting at risk the timelines. **Oct 31st:** In terms of deployment we have a dependency with #82584. If this initiative is delayed then there will be an impact on the money step. The solution architect will investigate if this dependency can be removed. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-05-01 | 2025-07-15
Business w/ Tech Initiative: WS7 - Increase Smalls and Conveyable Handling (Air | 82681 | 8799 | Business w/ Tech Initiative | EU - Sort | Europe | Adrian Bondar, John Macdonald, Robert Higgins | On Track | Update 31012025 Nav 360 Dashboard UAT continues. Cross check figures shown by Nav 360 against legacy OPDA Dashboard to ensure accuracy and consistency of reporting. Alignment with the 388 Initiative [PUD Pod] to assess overlapping. Meeting scheduled for next week. Purple Track communication over the main areas of focus to be presented next week. # Status update and next steps to be shared with the VPs next week. Update 20122024 30/60/90 Plan - see Milestone Chart Success stories and learning RTM Station BotG completed. All necessary controls in place to produce stable performance to target on SML bagging, i.e. SOP, WI, KPIs etc Floor space, IT Apps and Ops consumables now in place and used Results – RTM bagging 80% of SMLs to QAR, LGG and CDG Open issue -the 360 Dashboard was not available to support BotG (Legacy report used). Awaiting update on UAT plans for early 2025. -FP + A target for RPC (aligned with Drive Pods, i.e. 388, HFS etc.) for 2025 not shared or published. Update pending -FP + A governance approach to monthly Actual (USD) into Planview not agreed. Update pending Action plan for upcoming weeks 360 Dashboard team advise that necessary changes will be in place by mid-January to allow UAT to occur [#82614]. Follow up with FP+ A on RPC targets for 2025 Follow up with FP + A on how monthly governance meetings will work to translate the lead KPI % SML bagged ex origin into USD Actuals for Planview ** Attention needed. Obtain and send SVP message to target audience to engage with Sort Pod (bless kick off Jan - March campaign with full support (ownership) and resources allocated Ensure 360 Dashboard passes UAT and is ready for Jan-Mar 2025 campaign. 360 Dashboard team must produce a user guide to prep UAT scripts and to allow the Sort Pod to produce Playbook (critical path) Ensure FP+A agree way forward with 388 and HFS on target setting and reporting for stations. To ensure campaign reporting (Actual USD) and Planview Actual updates (critical path) Risks - 360 Dashboard is under pressure to make mid-January deadline - the level of engagement in January with Champions and front line facility mgmt will be diluted with no Dashboard available to track compliance and results. **Update 05122024** 30/60/90 Plan - see Milestone Chart **Success stories and learning** RTM Station BotG in week 3. DH2 scanning now put in place. SMLs bagging now live to QAR, LGG and CDG Dedicated SML sort area set up in RTM floor Drivers now segrgating SMLs KPI Dashboard [#82614] regular meetings to UAT approve the tool.** **Action plan for upcoming weeks** Continue KPI Dashboard daily meetings to approve UAT [#82614]. Enter into week 4 of BotG. Validate process controls (SOP / WI) and Mechanisms (Scanners, floor space, bag racks, bags, tags and emplyee comeptence) Escalate urgency of FP + A target for 2025 RPCC. This to allow campaign reporting on process compliance (% SML bagged) and USD Actuals for Planview Produce SMLs bagged Playbook and perform train the trainer on CWC Champions ** **Attention needed.** Obtain and send SVP message to target audience to engage with Sort Pod (bless kick off Jan - March campaign with full support (ownership) and resouces allocated Ensure 360 Dashboard passes UAT and is ready for Jan-Mar 2025 campaign. 360 Dashboard team must produce a user guide to prep UAT scripts and to allow the Sort Pod to produce Playbook (critical path) Ensure FP+A agree way forward with 388 and HFS on taregt setting and reporting for stations. To ensure campiagn reporting and Planview Actual updates (critical path) Update 04102024 30/60/90 Plan - see Milestone Chart Success stories and learning L3 approved. KPI Dashboard [#82614] daily meetings to fine tune the approach. New milestone [Ronald Bout] about allowing NC shipments into totes to be conveyed and sorted onto the parcel sorters. QAR personnel are enthusiastic about using NCs to Totes so that there is momentum. Action plan for upcoming weeks Continue KPI | I: L4 | Active | L4 | 2024-07-22 | 2026-04-02
Business w/ Tech Initiative: WS1 - [1C - Zenith] Plan versus Actual Analytics |  | 85930 | Business w/ Tech Initiative | EU - Sort | Europe | Xavier Bellsola Olba, Tim Veenstra | On Track | CANCELLATION Plan vs Actual as an Initiative now have parts integrated into RouteGuard and input was given into EU E2E EPIC 2. The following components have been included into RouteGuard using legacy (intra-Eu region) IM/IR information providing a view of scheduled routing vs actual routing. There separate views and KPIs for -Does the planned Origin match the actual Origin? -Does the latest IM routing contain any/only (P)lanned legs -> Incomplete Route -Is the latest IM routing equal to the earliest IM routing? -Is the Routeguard string (Radar route) equal to earliest IM routing? -Does the planned Destination match the actual Destination? Interim SFP dashboards were not incorporated, but we are being provided via DataWorks and the iSFP team is reviewing those. EU E2E EPIC 2 has been fed with requirements too. Please cancel the initiative as it has been completed SUCCESSES • Actual scan data accuracy improvement • Data in production in OIP (no access anymore) IN PROGRESS / NEXT STEPS In progress: • Getting resources to develop PowerBI dashboard • User stories and requirements shared with DW Next Steps • Onboard EU stakeholders to enhance data accuracy MILESTONE TARGETS • Data visualization available for stakeholders ASAP RISKS • No resources available might become a roadblock for further progress • No possibility to progress to L2 until data architecture docs are available LEADERSHIP ASKS • None | C: L1 | Cancelled | L1 Feedback Requested | 2024-06-03 | 2025-07-10
Business Only Initiative: P2O shipment data exchange - Reduction |  | 86769 | Business Only Initiative | EU - Sort | Europe | Timothy P. Hartless, Natascha Schlangen, Sabrina Sicard, Maria sim | On Track | * 2026.02.05 All flows deactivated as per the plan. WNS, DXC and RPA deactivation complete. Completed the steps as per the L3 Checklist and will review with TO and Finance prior to submitting for approval to move to L4 * 6 Aug 10 Survey response comming back for Deferred Intra EU, assessing and getting in contact with requestors. Volume not yet going down yet due to 1) routing set up errors with Zenith. 2) IM/IR back scenario's utilezed following old design. Flow is being stopped. When we stopped the P2O data flow in ITIH, we have discovered that IM/IR started generating P2O shipments that were previously generated under the stopped scenario. Investigations are ongoing to stop this process together with the US team. Code change ws needed. Awaiting move to production this week. * 28 July Survey send out to Road Organisation for completion on the 15th of AUG. * 28 July Shipment volume was expected to go down with 50% and only went down with 25%. P2O data correction is not following this trend. No reduction seen in June statistics. *15 July requested Jorams attention and approved or L2. *SL2 Approved by Javier pending Joram - 14 July* *POC scenario 26 - 22 April * Switch of Express Meisa to America's, 10.05%. (part of step 1) Comms to be send out to LGG 14th of April. *Submitted Ini to L2 8 APRIL* Awaiting EPM to be assigned and provide the documentation to be added. *FPA meeting 20 MAR* Awaiting to attach the FPA checklist to submit to L2. Added change plan to the initiative. *Project Team Meeting 11 MARCH* Created project tracker for Assess phase. *Project Team Meeting 19 FEB* Initial analyses done by Bart on file provided by Mattijs on most occuring data codes. 6 categories identified to deep dive further on: 1 MWW 2 Clearance 3 MWI 4 HLC 5 Quantum 6 ED *Project Kick off call on 7 FEB* Set up weekly cadence meeting SMEs identified Next steps; 1. Analyse DATA from Mattijs to identidy where MWW are still in used 2. Create a Ops Survey to understand where and Why the P2O data exchange are still required 3. Create Lean Business Case (LBC) | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-03 | 2026-04-30
Business w/ Tech Initiative: AVsec regulatory requirements |  | 89399 | Business w/ Tech Initiative | EU - Sort | Europe | Marielle Sitskoorn, Sue Bird, Karine Balle, Colin Troughton, Traian Sinescu | On Track | 20251218 - Updated money step to end of Jan 26 to allow for alignment with marketing on the EBR definition. Approved by Joram and Miguel in Sponsorm Meeting (Maria Sim) 20250718 - Caught at SL3 - Checking on issues 20250715 - requested via ePDSM to adjust the MoneyStep for this initiative into: ' all FedEx EAN accounts have an EBR status (Y/N) assigned in the EAN database' Current MoneyStep has been copied to initiative 2 - #132985 20250321 - Moved to SCO Home Portfolio: IO - Darma Taimuty PISA - David Lawrie PM - Zack Sherman BA - Holly Hardman 20250313 - Following CPEL (12Mar25) and follow-up call with David Walker (PMO), Arun S and Shahab S it was established that the initiative/ strategy is not assigned to the correct Home Portfolio (currently it sits in the Commercial). Commercial advise that the EBR/ non-EBR flag is simple and the complexity sits in either/ both SCO (Pam Coile (call 17Feb25)/ Mahati Koduri) or Platform (EFS? - Angela Curtis). We have spoken to Christian Piquet and he recommends we escalate to Leadership. This needs a similar solution to ITAR or CN Restricted Parties or re-purpose the Security TS flag. In addition Jim Bailey has raised to Leendert Creyf and Frank Jary (13Mar25) and will raise on call with Terry Harris and Richard Smith (13Mar25). 2025/03/06 - Submitted to L2; awaiting approval. Invited for CPEL on 3/12. In the meantime request made fo (* taskforce resources (Ops/Field P&E) to work on: 1. planview initiative and the required capabilities 2. business continuity plan in case we dont the capabilities in time 2025/02/28 - Awaiting approval L2 checklist. Invited for CPEL on 3/12. 2025/02/21 - Discussion with SCO Team, 18Feb25. Creating MVP and high level timeline. 2025/01/15 - under review to amalgamate 3 initiatives to 1 initiative (cancelled #1137 (commercial) and #478 (courier devices) Underway 2026/03/05 On 6th Oct '26 CAM has completed processing EBR updates on 51M+ records, This means that all EAN accounts in CAM have now an EBR Y/N flag. This information is then provided to Atlas. Data A&I has provided a dashboard from which Europe P&E can download the non-EBR accounts. This information then can be used for manual upload in Sort. A local enhancement has been opened to upgrade the EBR logic. | I: L4 | Active | L4 | 2025-06-24 | 2026-01-30
Business w/ Tech Initiative: Dataflow to Sort |  | 97130 | Business w/ Tech Initiative | EU - Sort | Europe | Christian Johannes Visschedijk, Maria sim, Marine Lampaert | Some Issues | ** Adjust money-step in March 2026(!) 06/02/2026 -> New risk added. The new Data Flow will most likely increase the issue of not having the data in regards to US domestics ending-up in EU. Capability 1 ongoing. Solution Architect work should be done by next week. 27/01/2026 -> New risk added. Availability of Solution Architect. Due to intitiatives with higher priority. Some mititgating actions have been taken (i.e. EU Sort Design Meeting). However this will only mitigate the EU application side of the design, not the US. Timelines are in the process of being updated. Once finalized, request will be made to update Money Step. 19/01/2026 -> ARB went well. Few questions to be answered by Solution Architect. Ricky to set up calls with ART's to check if anything missing. SA on another porject till end of month. 15/12/2025 -> Timelines will be updated once we receive feedback from the ARTs on when their development can be completed (Solution Archtiect should be able to get that this week and it will be added into the solution document). We can expect a delay in the deployment of capabilities 1, 2 and 3. 25/11/2025 -> Milestone "Capability 1 - Solution Design" at risk. 06/10/2025 -> based on feedback EPM - Added impacted portfolio's in Milestones & Risks - Added comment to money step - Updated Arch document link from a file to Arch folder. - Check done with transformation specialist before submitting 22/09 Initiative Update. During the first SCO PEL the impact of Gen0/Gen1 was discussed. It was determined additional allignment was needed as changing Gen0/Gen1 systerms is not prefered. A discussion was had on Gen3 application. However, this was not an option. A shift was made to Gen2, as this ensures a more futureproof solution. This meant readjusting to SEFS - EFS. Impacting Platform portfolio and requiring additional development from the Sort Portfolio. This also lead to increased cost. 8/8 - Still in L2 - challenges to move to L3. ARB step completed and Gen 2 feed was agreed. Need to add the Platform portfolio in PV --> PDSM opened to move back one step so this can be done Waiting on updating costs for SCO & Platform. Value to be agreed upon. 17/06 Pre-Pel attended. Minor changes to deck. Ready to get pulled in. 12/06 Finance inputted. First milestones created PPM confirmed and added. 11/04 - Introduction with Solution Architect. PDSM Ticket opened for adding risks/milestones. Awaiting L2 Documentation to be completed. Once done, costing and Greenlighting can be done. 25/03 - Updated link to Arch Document 25/03 - Submitted to SL2. 14/03 - Issues with determining the correct KPI and what exactly success looks like needed for the Finance Checklist. 06/03 - Arch documents linked. Dependencies added. Financial checklist to be completed before submission. 21/02 - L1 LBC Completed. To do: Arch. documents and adding dependencies for submission to L2. 14/02 - Weekly meetings in place. Raj Mohan to describe the current state: all dataflows to Sort both uDS & HubStack as well as the dataflows from sort like SSDC 1.0 feed into LSRE. Raj moving to Linehaul at the end of the PI, replacement plan not yet finalized. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-30 | 2026-12-25
Business Only Initiative: Eu Overgoods transition to NAVI4/ RECOVER |  | 106092 | Business Only Initiative | EU - Sort | Europe | Neil Ferguson, Sue Bird | On Track | 20250321 - Moved from L0 to SL1 - Pete T (VP) taking to Miguel C (SVP) Monday, 24Mar24 as project in flight, adding to Planview and L of ABLE process. Value tbc | E: L2 | Active | L2 | 2025-09-12 | 2026-05-29
Business w/ Tech Initiative: Zenith-GNP & Europe – Solver capabilities |  | 110052 | Business w/ Tech Initiative | EU - Sort | Europe | Zander F. Bekker | On Track | Initiative to be cancelled and scope of work to be included the global DCM initiative. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: AvSec Phase 2 - EBR at shipment level + sort dec |  | 132985 | Business w/ Tech Initiative | EU - Sort | Europe | Marielle Sitskoorn, Karine Balle, Sue Bird | On Track | **30Jul2025 **- L1 to L2 approval rec'd FP&A **30JUN25 - Project went through triage; LBC to be completed. | E: L2 | Active | L2 | 2026-01-29 | 2027-06-30
Business w/ Tech Initiative: ZEUS (Zenith European Solutions) |  | 161060 | Business w/ Tech Initiative | EU - Sort | Europe | Jeroen Lamers, Michael Cusack | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: uDS/DH2 Enhancements for MPS Consolidation |  | 169832 | Business w/ Tech Initiative | EU - Sort | Europe | Marc Schmitz | On Track | Duplicate Initiatives created by system - 169834 remains for progression | C: L1 | Cancelled | L1
Business w/ Tech Initiative: uDS/DH2 Enhancements for MPS Consolidation |  | 169834 | Business w/ Tech Initiative | EU - Sort | Europe | Marc Schmitz, Juergen Kogure, Tom Desmet | On Track | On Track | E: L2 | Active | L2
Business Only Initiative: Road, Air Network & Ground operation-GSE | 46457 | 7031 | Business Only Initiative | EU - Sustainability | Europe | David Kemeni, Craig Munro | Some Issues | Week 8 Gathering all cost information and modelling expected capital requirements to replace all non sustainable GSE by 2024 and as per the Road Map. Week 9: Cost impact submitted for review - total capital required to replace all existing GSE with a sustainable alternative by 2040. Week 12: Presented L3 progress and overview to sponsor last week. currently exploring all opportunities to improve accuracy and improve timeline. currently on track or May. Week 13: Continuing to explore all opportunities to improve accuracy and improve timeline. currently on track or May. Week 14: Continuing to explore all opportunities to improve accuracy and improve timeline. currently on track or May. Week 15: Annual Leave - no progress Week 16: Travelling - no progress Week 17: Travelling - no progress Week 18: on track for L3 Week 19: Travelling - no progress Week 20: on track for L3 Week 21: Travelling - no progress Week 22: L3 submitted. Week 20: on track for L3 Week 21: Travelling - no progress Week 22: L3 submitted. Week 31: BOFA finance lease contract for the UK is in Encore and on track for signature by 31st August (as per milestones) Week 32/33: Annual Leave Week 34 - 41 collation of updated actual requirement from operations FY25 Close: 13 diesel or LPG units removed from the UK vs a target of 33. Progress impacted by lease renewal process being on hold (strategy change from operating lease to finance lease) 13 removals achieved by reallocating units purchased via the FY23 BOD. These units were no longer required for the project they were purchased for in Italy. (capital cost $857K). | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2026-07-24
Business Only Initiative: Road Network-Alternative fuels - strategy | 46459 | 7156 | Business Only Initiative | EU - Sustainability | Europe | Marcos Arromba, Megane Lecamus | Some Issues | Jan/26 - Dec/25 - Nov/25 - Oct/25 - Sept/25 - Aug/25 - IO changed from Jesse Hupkens to Marcos Arromba Aug/25 - FR roll out in FR started delayed May/25 - FY26 target, from 4.924 M Litre to 10,7 M Litre Sept/24 - UK roll out of HVO goes as planned. Nov/23 - NL bunkertank placement at QAR has been deemed unfeasable at the current stage of operations location setup. New Rates with Shell are in place but new contract is still being reviewed by Legal. This will allow QAR to continue on HVO with all own truck. The new rates saves 150-170K annually compared to previous HVO rates. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-05 | 2026-08-28
Business w/ Tech Initiative: Road Network-Alternative fuels - strategy - contra | 46461 | 7158 | Business w/ Tech Initiative | EU - Sustainability | Europe | Marcos Arromba, Jesse Hupkens | On Track | 18/02/2026 - Request to set status "On Hold" by PM - Marit Heidemann. Expected restart April-2026 Pilot in DE was successful. Learnings captured for future development in ROCS 2.0. Pilot workload is not scalable and requires the development in ROCS2.0 to be completed. ROCS2.0 development and roll out has seen delays, therefore development is pushed to Early 2026 CY. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-05-01 | 2026-05-29
Business Only Initiative: Ground Operations-EV deployment - LTP Phase 1 FY20 | 46462 | 7159 | Business Only Initiative | EU - Sustainability | Europe | Patrick Tediek, James Dahringer | On Track | Currently aligning about the future of this initiative, pending company strategy for FY2026 | G: L3 | Active | L3 Feedback Requested | 2024-04-12 | 2026-06-01
Business Only Initiative: Ground Operations-EV deployment - Own fleet | 46463 | 7162 | Business Only Initiative | EU - Sustainability | Europe | Louise Whitehouse, Michael Rudolph | Some Issues | 06.11.2024 Order of the 208 eVans delayed 10.12.2024: 198 eVans ordered first week of december 2024. Order for Denmark (10eVans) is still pending. 10.01.2025: 10 eVans for Denmark ordered 19.12.2024. For all Vans no derlivery date yet. 30.01.2025 no update. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-04-02 | 2025-11-28
Business Only Initiative: Enablers-Sustainability revenue impact assessment | 46469 | 7165 | Business Only Initiative | EU - Sustainability | Europe | Stijn Meeus, Perrine Jourde | On Track |  | K: L5 | Completed | L5 | 2024-01-01 | 2024-06-25
Business Only Initiative: Facilities - Building emission reduction - FY25 | 46467 | 8969 | Business Only Initiative | EU - Sustainability | Europe | Alexander Boogerd, Jonathan Pierret | On Track | 17/07/24: reopening and submitting ECH since IFM suppliers were confirmed to be covered via BAU Updated data based on staffing and budget available | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-03
Business Only Initiative: Facilities - Offgrid Electricity supply strategy - | 46466 | 8970 | Business Only Initiative | EU - Sustainability | Europe | Livia Ferreri, Jonathan Pierret, Eliana Invernizzi | On Track | on track | G: L3 | Active | TEMP L3 - Enter L3 | 2023-11-01 | 2028-02-29
Business Only Initiative: Implementation of Energy Management System in Euro | 46465 | 9267 | Business Only Initiative | EU - Sustainability | Europe | Agustin Oterino, Arjan van der Nat, Linda Bissoli | On Track | Weekly status put on hold due to resourcing constraints. We will require resources to be able to support this initiative as current assigned resources are overloaded and need to focus on stabilizing for example IFM (which is part of keeping the lights on and is DRIVE initiative as well). Resource issues have been addressed numerous times but so far without desired success. We continue to work low profile on this initiatives but without confirmed timelines and assumed accountabilities which are a prerequisite to be able to move to L3 and is dependent on resource allocation and confirmation. Weekly status changed to some issues as we have worked on a plan in order to be able to support this initiative going forward. Issues are still related to resource challenges but are we are making progress on the required automation for which we are asking for turn key options whereby selected supplier will do project management, installation and execution and thus reducing the burden on the internal organization. This is subject to final SVP decision making on the proposal when presented next week. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-03 | 2026-12-25
Business Only Initiative: Sourcing & Procurement - co2 emission reduction re | 64774 | 9544 | Business Only Initiative | EU - Sustainability | Europe | Justin Troy |  | Changing status for cancellation request per alignmet with "Europe ¦ Planning & Engineering – Properties & Real-Estate" team | E: L2 | Cancelled | L2
Business Only Initiative: Utilities - Optimization Pilot Italy |  | 96215 | Business Only Initiative | EU - Sustainability | Europe | Mike Ruckert, Marco Figueira | On Track | Duplication of efforts as cost savings on both Gas and Electricity are already captured in existing initiatives in the Sustainability POD | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Channel Islands Integration | 70147 | 7097 | Business w/ Tech Initiative | EU - UK | Europe | Kieron Everitt, James Newby | On Track | January 5th 2026 IT work completed and released to production. Tested as complete. Ready to move to L4. November 18th 2025 Testing completed successfully in L3 to be able to release to production on January 3rd 2026. Approval granted to push L4 date to January as cost / savings are already beeing seen since June 2025 financials and are not impacted by this date change. October 16th 2025 Development work completed, but awaiting fix of issue rasied in testing around L3 / L6 environments. (issue in L3 impacts Northern Ireland as well which is fine in Production) July 10th 2025 KPI based on Ground Ops anual spend reduction. Jersey and Guernsey full spend based on FY25 spend. July 7th 2025 SCO PEL approval obtained for SCO Greenlight. Portfolio costing confirmed and added Milestones to reflect ETD requirements updated. Epics added. Initial confirmation of starting work in next PI, with delivery expected for November 2025 URSA file upload. June 3rd 2025 Commercial Portfolio not impacted. SCO Portfolio identified as sole impacted. Requesting SCO green light to keep project moving and in line with SCO requirement to be in L3 before starting work. Still waiting for confirmation of when development / configuration will be prioritised, start, and as such be delivered. Latest update from business is that Channel Islands is not currently compliant regarding customs. This solution will help with that compliance. | I: L4 | Active | L4 | 2024-04-08 | 2026-01-30
Business Only Initiative: Domestic - UK Enterprise National Team | 11137 | 7986 | Business Only Initiative | EU - UK | Europe | Greg Evans, Ben Radford, Steve Brown | On Track | L4 approval now gained. Continue to push creation stats to feed output - pipeline value key Confidence in delivering value on time: High (based on recent reforecast) Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2022-12-14 | 2024-05-29
Business Only Initiative: TNT & FedEx Domestic Fuel step up | 11129 | 7994 | Business Only Initiative | EU - UK | Europe | Ryan O'Boyle, Stuart Phillips | On Track | “Confidence in delivering value on time: [High]” “Confidence in delivering the full value: [High]” July 5th - submitted for L5 May 18th - Re-entered March results into April as requested. Still outstanding ability to adjust KPI and impact targets. No further updates due to initiative launched - confirmation of L5 Money Banked to be provided when applicable - Any events that may directly impact this initiative will be added as / if / when they occur. Week 11 - Additional 200k vs target Week 9 - Feb results to be updated in week 10 Fuel data provided to upload Jan actuals & KPI figures Attachement 4 shows evidence of Money Step being completed with screenshots of both tnt.com & Fedex.com with recalibration completed and matching + loading in universe, confirmation from IT of the fuel message change on invoices and a test consignment showing the fuel calculated as expected | K: L5 | Completed | L5 | 2022-11-07 | 2022-11-07
Business Only Initiative: UK Domestic Customer Yield Management & Profitabil | 89242 | 7995 | Business Only Initiative | EU - UK | Europe | Ryan O'Boyle, Stuart Phillips, Trent Turner | On Track | Data gaps on tooling and availablity. Ongoing resource issues due to Ace prioritisation. Discussing potential back up plans and mitigation wc 20th January follow up. | E: L2 | Active | L2 & CCH | 2024-01-15 | 2026-09-03
Business w/ Tech Initiative: Reduce churn FedEx | 11135 | 9116 | Business w/ Tech Initiative | EU - UK | Europe | Paul Pugal, Ben Radford | On Track | I remain confident that we will continue to achieve the overall target of remaining at zero for this year. We saw a slight downturn last month but have recovered this month and covered the loss so still ahead of plan moving into August. I feel we need to continue the positive momentum this calendar year as it would expected churn will increase the month following Pride and GRI implementation in January 2024. Confidence in delivering value on time : Medium Confidence in delivering the full value : Medium | K: L5 | Completed | L5 | 2022-12-01 | 2023-12-29
Business Only Initiative: Domestics UK WWS Incremental Growth | 11138 | 9121 | Business Only Initiative | EU - UK | Europe | Peter McVey, Joelle Wegener | On Track | Confidence in delivering value on time: High Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2023-01-03 | 2023-03-01
Business Only Initiative: SME Domestics sales focus | 11139 | 9123 | Business Only Initiative | EU - UK | Europe | Steve Brown, Greg Evans | On Track | Confidence in delivering value on time: High Confidence in delivering the full value: High Confidence level on current SME drive goal is 100% on achievement however we have agreed to take a percentage of the economy drive initiative so confidence level may have to be adjust once this has been confirmed | K: L5 | Completed | L5 | 2022-12-12 | 2023-05-19
Business Only Initiative: Belfast - Optimise Operations | 11141 | 9125 | Business Only Initiative | EU - UK | Europe | Ben Radford, Joseph O'Neil | On Track | Project will now be delay due to potential TUPE issue, we are working through legal implications with Steve Adnam (UK legal). We anticipate 60 days notice will be issued on 31st January, therefore the new start date will be 2nd May. Confidence in delivering value on time High Confidence in delivering the full value High Full year cost saving needs to be adjusted to $750k. Working with vendor ref value of redundancy compensation | K: L5 | Completed | L5 | 2022-12-12 | 2023-05-31
Business w/ Tech Initiative: Governance and reporting | 11142 | 9127 | Business w/ Tech Initiative | EU - UK | Europe | Tim Robb, Ben Radford | On Track | Confidence in delivering value on time: Medium Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2022-12-07 | 2024-05-31
Business w/ Tech Initiative: "FedEx Now" Guest Shipping Platform | 11144 | 9129 | Business w/ Tech Initiative | EU - UK | Europe | Nicholas Wilyman, Rupi Banwait | On Track | Taking initiative back to L3 in order to: - Add additional impact; International revenue and vendor cost (Approved by Karen on 13/2/24) Once impacts are added and reforecasted initiative will be submitted back in L4 | I: L4 | Completed | L4 | 2023-01-03 | 2023-11-08
Business Only Initiative: Increase Domestic traffic to Online Account Regist | 11145 | 9132 | Business Only Initiative | EU - UK | Europe | Georgina Green, Des Gallagher | On Track | Confidence in delivering value on time: High - 100% Confidence in delivering the full value: High - 100% The actual revenue and volume numbers for December are now available, so the Impacts and KPIs have been updated. The December numbers are not complete, this is because the data will still not be fully available for another few weeks - this is a well known issue across the business. To mitigate the risk of missing revenue, we will add the revenue to future months as and when it becomes available - This has been agreed with Gemma Biggs, Javier Ribes Sampedro, and Leila Chavant. The project owner will ensure that the YTD revenue is tracked as accurately as possible as we continue to track the performance of this project. The money step is complete and the first month of revenue has been recorded for December 2022. This is the rationale for progressing this project to L4 stage. - see attachment 4 titled 'WREG_FY23_REV_To_COB_Dec22.xlsx' for the current revenue and volumes achieved in December 2022. - See attachment 5 for evidence of the money step | K: L5 | Completed | L5 | 2022-11-25 | 2023-03-08
Business w/ Tech Initiative: Deploy online broker strategy to open valves | 11146 | 9134 | Business w/ Tech Initiative | EU - UK | Europe | Stephen Taylor, Ben Radford, Ines Miroto | On Track | "Confidence in delivering value on time: HIGH" "Confidence in delivering the full value: HIGH" **W/C 7th April 2026** Negotiating with Packlink for launch during during Q1 FY26. (Finally!) CCL new promotion commencing Q1 FY26 Vinted case (Pan-European) being refined with Set Menu Direct To Retail solution to be solved for future enablement / scale International volumes by association ramping nicely, especially FICP - not captured within Drive Initiative SOW evaluation for 0-2kg PUDO where our competitors have taken share - opportunity to use as valve | K: L5 | Completed | L5 | 2023-01-03 | 2024-05-31
Business w/ Tech Initiative: Cross-sell Domestic products to International cust | 11148 | 9136 | Business w/ Tech Initiative | EU - UK | Europe | Georgina Green, Des Gallagher | On Track | Confidence in delivering value on time: High- 100% Confidence in delivering the full value: High- 100% L4 status based on: pricing loaded, CPP enabled, customers comms complete as of 30th May 2023. Project is currently tracking ahead of schedule. | I: L4 | Completed | L4 Feedback Requested | 2022-12-05 | 2023-06-30
Business w/ Tech Initiative: Increase share of UK domestic e-commerce market | 11153 | 9138 | Business w/ Tech Initiative | EU - UK | Europe | Craig Smith, Gary Carciente, Ben Radford | On Track | 29th October - Moving to money step given PPOD is now on track and regular monthly financial reporting undeway. ARTH and DTR were initially delaying money step but now moved out to seperate European e com POD Money step moved out to October due to delays around DTR rollout and PPOD not fully activated Moved to some issues as still waiting on ARTH, DTR and PPOD Money Step pushed from the 30th June to the 30th September, now 31st March. This request is due to the delays in the rollout of Direct to Retail (#19013) and Auto Direct to Hold (#19014) as it appears initial target dates will not be achieved. Have moved weekly status to some issues given we are late on ARTH milestone. Was due end of Feb, now looking at full roll out of ARTH end of July 2024. DTR still planned to be ready for end of May following testing. Established baseline numbers for reporting as original baseline incorporated all UK sales segments - Initiative now targets UK E com team contributions to ensure focus and accurate none duplicated reporting. Original target remains in place however risk identified in original ramp up goals. Vacant positions also impacting output. Rules of engagement / collaboration are now agreed and cascaded - should support improved collaboration, but potentially dials down the numbers/opportunities available to dedicated e commerce teams. Need to discuss and assess full impact of this with Sales MDs as e com opportunity pool shrinks vs mainstream sales increasing with new e com classification at 70%. Update received on replacement positions, these are now signed off and recruitment underway. Also now had approval on external recruitment as and when needed. Confidence in delivering Value on time: Low Confidence in delivering the full value: Medium | K: L5 | Active | TEMP L5 - Enter L5 | 2023-01-02 | 2025-10-31
Business Only Initiative: SFS Restructure | 69278 | 9466 | Business Only Initiative | EU - UK | Europe | Ben Radford, David Gardiner | On Track | Confidence in delivering Value on time: High Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2024-01-04 | 2024-04-30
Business Only Initiative: Management Layers & Supervisory | 68779 | 9468 | Business Only Initiative | EU - UK | Europe | Ben Radford, Raymond Masterson | On Track | Still on track and awaiting FP&A approval to move to L5 Confidence in delivering Value on time: High Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2024-01-12 | 2024-05-31
Business Only Initiative: Integrate International Ops in London | 68780 | 9470 | Business Only Initiative | EU - UK | Europe | Ben Radford, Steve Johnson | On Track | Confidence in delivering Value on time: High Confidence in delivering the full value: High | K: L5 | Completed | L5 | 2024-01-11 | 2026-02-27
Business Only Initiative: UK Health & Safety PPE & Medical Supplies |  | 93418 | Business Only Initiative | EU - UK | Europe | Ketan Panchal | On Track |  | C: L1 | Completed | L1
Business w/ Tech Initiative: UK Sameday - Removal of Local ACI Solution |  | 157696 | Business w/ Tech Initiative | EU - UK | Europe | David Gardiner, Lisa Stockton, Richard Holloway | On Track | 30/09/2025 - On track | E: L2 | Active | L2 - Enter Value Prop
Business Only Initiative: [IN][SG&A] India - D&T bad debt reduction | 34893 | 7000 | Business Only Initiative | MEISA - India | MEISA | Tushar Raibagi, Dimple Khilwani | On Track | Initiative on track with milestone implementation in progress - Consignee credit review process being finalized and agreed with stakeholders - Issues related to cash application delay identified, working teams established for process streamlining - Gaps in Sun Impex billling identified and currenty working with the team to streamline the process - US related dependencies for fraud action items being discussed and hilight to the respective team - Impact of actions taken to reduce bad debt to be realized 6 months after the execution of money step | K: L5 | Completed | L5 | 2023-06-06 | 2024-05-31
Business Only Initiative: [IN] [Air Operations] FALCON: Re-design India/MEA | 36291 | 7051 | Business Only Initiative | MEISA - India | MEISA | Mustafa Assaf, Mohammed Wazif Ziavudheen | On Track | This case is linked to the FALCON DRIVE project #497 in the International Air Network POD L4 evidance submitted and approved by FP&A | K: L5 | Completed | L5 | 2024-03-13 | 2024-12-31
Business Only Initiative: [IN] [OB]Grow SAM E-commerce with Convenient Expor | 36428 | 7055 | Business Only Initiative | MEISA - India | MEISA | Ravinder Kumar Panthri, Vinay Gopalan, Navin Vijan | On Track | Cancelation request initiated considering this initiative is being re-aligned to new initiative Grow SAM B2C in FY26 and is going to be tracked seperately | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-06-01 | 2025-05-30
Business Only Initiative: [IN] [IB] Grow India paid Imports revenue with key | 36443 | 7056 | Business Only Initiative | MEISA - India | MEISA | Rishabh Seth, Vinay Gopalan, Ravinder Kumar Panthri | On Track | Cancellation request placed considering IN PAID imports from all lanes is being tracked seperately under new initiative in FY26 | K: L5 | Cancelled | L5 | 2023-06-01 | 2025-02-28
Business Only Initiative: [IN] [RT] Grow Aerospace & Industrial revenue with | 36458 | 7058 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Hemant Pimplikar, Vinay Gopalan, Krishnaprasad Ramachandran | On Track | Moved to L5 as initiative has given mature benefits above plan in 5 months since Jun'24. (fulfills the qualifying condition of 3 months of mature benefits) | K: L5 | Completed | L5 | 2023-06-01 | 2024-12-31
Business Only Initiative: [IN] [OB] Grow SAM with Cluster Strategy | 36468 | 7059 | Business Only Initiative | MEISA - India | MEISA | Ravinder Kumar Panthri, Sachin Shukla, Vinay Gopalan, Shweta Amin - Bharadwaj | On Track | Cancelation request initiated considering this initiative is being re-aligned to new initiative SAM B2B with clusters in FY26 and is going to be tracked seperately | I: L4 | Cancelled | L4 | 2023-06-01 | 2025-02-28
Business Only Initiative: [IN] [OB] Grow SAM with new business and base grow | 36472 | 7060 | Business Only Initiative | MEISA - India | MEISA | Ravinder Kumar Panthri, Sachin Shukla, Sharath Shetty, Vinay Gopalan, Shweta Amin - Bharadwaj | On Track | Cancelation request initiated considering this initiative is being re-aligned to new initiative SAM B2B in FY26 and is going to be tracked seperately | I: L4 | Cancelled | L4 | 2023-06-01 | 2025-02-28
Business Only Initiative: [IN] [FOSS (FedEx One Stop Shop)] - Digital platfo | 37318 | 7063 | Business Only Initiative | MEISA - India | MEISA | Klaudia Palgan, Nitin Shetty, Akshay Kumar | On Track | On track | K: L5 | Active | L5 | 2024-04-01 | 2025-09-26
Business Only Initiative: [IN] [RT] Grow Healthcare vertical with identifie | 37438 | 7068 | Business Only Initiative | MEISA - India | MEISA | Mritunjoy Tripathy, Hemant Pimplikar, Vinay Gopalan | On Track | 1. FCF and IPF shipments for Cipla and Zydus on track 2. Alkem movement had stabilized but now lost due to space constrain from our side , we are now working to regain 3.Philips outbound movement stable for next quarter 4.On Track, L4 evidence approved by FP&A team Moved to L5 as initiative has given mature benefits above plan in 5 months since Jun'24. (fulfills the qualifying condition of 3 months of mature benefits) | K: L5 | Completed | L5 | 2023-11-01 | 2024-12-31
Business Only Initiative: [IN] [OB] Grow IRFS with differentiated network of | 38179 | 7073 | Business Only Initiative | MEISA - India | MEISA | Ravinder Kumar Panthri, Sachin Shukla, Vinay Gopalan | On Track | on track | K: L5 | Completed | L5 | 2023-10-02 | 2024-07-31
Business Only Initiative: [IN] [Cost] Split capability at origin for Economy | 40749 | 7109 | Business Only Initiative | MEISA - India | MEISA | Kunal Trivedi, Vinay Gopalan, Monish Nandi | On Track | All Milestones are completed | K: L5 | Completed | L5 | 2024-02-01 | 2025-04-15
Business w/ Tech Initiative: [IN][OB] 5% Yield improvement on spot shipments | 81104 | 7183 | Business w/ Tech Initiative | MEISA - India | MEISA | Vikas Bharadiya, Vinay Gopalan, Aftab Sara | On Track | on track | G: L3 | Active | L3 Feedback Requested | 2024-06-26 | 2026-03-16
Business Only Initiative: [IN][E2E] Supply Chain solution - Engineering and | 73760 | 7192 | Business Only Initiative | MEISA - India | MEISA | Deepa Pandey, Hemant Pimplikar | On Track | Demand on hold as Fedex-L&T legal team is not ready to sign each other's contract . L&T requirements is, they want to do shipments with us as case to case basis and whenever they will float an inquiries, we can mention our terms. Business expected to start from FY27 onwards. | E: L2 | On Hold | L2 | 2024-07-23 | 2025-05-30
Business Only Initiative: [IN] [IB] Grow Offshore paid Inbound revenue for A | 51205 | 7193 | Business Only Initiative | MEISA - India | MEISA | Sachin Shukla, Hemant Pimplikar, Sara Hariga, Rishabh Seth, Vinay Gopalan | On Track | Cancellation request raised considering this initiative has a higher dwell time and not pursued in FY26 | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-07-18 | 2025-04-30
Business Only Initiative: [IN][RT][Enabler] Drive Delhivery service level im | 57253 | 7197 | Business Only Initiative | MEISA - India | MEISA | Deepak HR, Suvendu Choudhury | On Track | all milestones are completed and actions in place to improve service. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-17 | 2025-03-31
Business Only Initiative: [IN] [IB] Grow Offshore paid Inbound revenue for U | 59500 | 7286 | Business Only Initiative | MEISA - India | MEISA | Rishabh Seth, Hemant Pimplikar, Sachin Shukla, Vinay Gopalan | On Track | Cancellation request raised considering this initiative has a higher dwell time and not pursued in FY26 | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-06-03 | 2025-04-30
Business Only Initiative: [IN][E2E] Supply Chain solution – Tata AutoComp (T | 69237 | 7340 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Krishnaprasad Ramachandran, Hemant Pimplikar, Vinay Gopalan | On Track | Cancelation request placed considering FXL is the major revenue contributor in this initiative and going ahead FXL revenues will be tracked as KPIs. | I: L4 | Cancelled | L4 | 2024-07-29 | 2025-03-31
Business Only Initiative: [IN][E2E] Supply Chain solution - Air India (Tata | 69238 | 7342 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Krishnaprasad Ramachandran, Hemant Pimplikar, Vinay Gopalan | On Track | Cancellation request placed since the major revenue contribution is from FXL and FXL revenues are being tracked seperately | K: L5 | Cancelled | L5 | 2024-08-12 | 2025-03-31
Business Only Initiative: [IN][E2E] Supply Chain solution - Chemicals – Reli | 69239 | 7344 | Business Only Initiative | MEISA - India | MEISA | Hemant Pimplikar, M Thenappan | On Track | Canecellation Request is raised considering teh business is alerady onboarded & tracking it under the Industrial vertical | E: L2 | Cancelled | L2 & CCH | 2024-07-22 | 2024-09-13
Business Only Initiative: [IN][E2E] Supply Chain solution - Consumer goods / | 69240 | 7345 | Business Only Initiative | MEISA - India | MEISA | Hemant Pimplikar, M Thenappan | On Track | Cancellation Request raised since we have alredy onboarded Relaince & currently tracked under Industrial Vertical | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: [IN][E2E] Supply Chain solution – Tata Services (U | 88474 | 7346 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Hemant Pimplikar, Vinay Gopalan | On Track | Tracking Tata Intitative through Indvidual Intitatives in Plan view | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: [IN][E2E] Tata motors - Passenger Vehicle | 97900 | 7347 | Business Only Initiative | MEISA - India | MEISA | Hemant Pimplikar, M Thenappan, Vinay Gopalan | On Track | Cancellation request placed considering this intiative has major componenet of FXL Revenue & this will tracked as KPI under the Grow Aerospace & Industrial Intiative | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: [IN][E2E] Supply Chain Solution Tata Steel | 98013 | 7348 | Business Only Initiative | MEISA - India | MEISA | Hemant Pimplikar, M Thenappan, Vinay Gopalan | On Track | Cancellation request placed considering this intiative has major componenet of FXL Revenue & this will tracked as KPI under the Grow Aerospace & Industrial Intiative | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: [IN] [E2E] Supply chain solution - TITAN | 96112 | 7351 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Krishnaprasad Ramachandran, Hemant Pimplikar, Vinay Gopalan | On Track | Cancelation request placed considering FXL is the major revenue contributor in this initiative and going ahead FXL revenues will be tracked as KPIs | I: L4 | Cancelled | L4 | 2024-10-07 | 2025-05-30
Business Only Initiative: [IN][E2E] Supply Chain Solution - TASL(TATA ADVANC | 97181 | 7353 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Krishnaprasad Ramachandran, Hemant Pimplikar, Vinay Gopalan | On Track | Cancelation request placed considering FXL is the major revenue contributor in this initiative and going ahead FXL revenues will be tracked as KPIs. | I: L4 | Cancelled | L4 | 2024-10-07 | 2025-05-30
Business Only Initiative: [IN][E2E] Supply Chain Solution TATA MOTORS CV | 97293 | 7354 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Krishnaprasad Ramachandran, Hemant Pimplikar, Prafulla Ghatole, Vinay Gopalan | On Track | Cancelation request placed considering FXL is the major revenue contributor in this initiative and going ahead FXL revenues will be tracked as KPIs. | G: L3 | Cancelled | L3 | 2024-10-07 | 2025-09-30
Business Only Initiative: [in] [E2E] Supply chain solution - Tata electronic | 96111 | 7355 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Krishnaprasad Ramachandran, Hemant Pimplikar, Vinay Gopalan | On Track | Cancelation request placed considering FXL is the major revenue contributor in this initiative and going ahead FXL revenues will be tracked as KPIs. | G: L3 | Cancelled | L3 | 2024-10-07 | 2025-06-02
Business Only Initiative: [IN] [Enabler] Sales competency assessment | 64468 | 7377 | Business Only Initiative | MEISA - India | MEISA | Anindya Dasgupta, Huafreed Nasarwanji, Harshal Bhand | On Track | 13Jun25: Made Anindya the IO as Harshal has moved into a new role. As on date; 28th July, this project is currently on hold following directives from Hua. 20th Nov: Hua has approved to cancel is initiative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-03-01 | 2025-11-28
Business Only Initiative: MEISA CLH Optimization | 72257 | 7511 | Business Only Initiative | MEISA - India | MEISA | Prateek Nath, Mohammed Sanis | On Track | ~$3m annualized savings from MEISA Intercontinental lanes. Savings to be captured based on Rate negotiations, sourcing additional CLH partners | K: L5 | Completed | L5 | 2024-06-03 | 2025-04-30
Business Only Initiative: MEISA Fuel Surcharge Increase | 89596 | 7571 | Business Only Initiative | MEISA - India | MEISA | Hiren Sagalia, Pradeep Mistry | On Track | The initiave fulfills the qualifying conditions of 3 month of mature benefits from Oct 24 to Dec 24 | K: L5 | Completed | L5 | 2024-05-16 | 2025-01-31
Business Only Initiative: [MEISA] Reinstatement of Demand Surcharge | 93205 | 7574 | Business Only Initiative | MEISA - India | MEISA | Hiren Sagalia, Pradeep Mistry | On Track | The initiative fulfills the qualifying condition of 3 months of mature benefits from Oct to Dec 2024. Also, the overall DS revenue between Sept to Dec 2024 is $11.21 Mn which is greater than the targetted revenue of $9.34Mn from demand surcharge initiative | K: L5 | Completed | L5 | 2024-07-09 | 2024-09-20
Business Only Initiative: [MEISA] [Enabler] RPI Collaborative shipping Tool | 79237 | 7642 | Business Only Initiative | MEISA - India | MEISA | Rahul Shirke, Vinay Gopalan | On Track | All milestones are completed. | K: L5 | Completed | L5 | 2024-07-01 | 2025-04-30
Business w/ Tech Initiative: [Enabler] MEISA - Simplifying WREG Account Opening | 79684 | 7643 | Business w/ Tech Initiative | MEISA - India | MEISA | Rahul Shirke, Vinay Gopalan, Klaudia Palgan, Sachin Shukla | On Track | All milestones including money step completed. | K: L5 | Active | L5 | 2024-06-17 | 2026-02-27
Business Only Initiative: [IN][Air Operations] Project M2 – Orange flight | 90074 | 7698 | Business Only Initiative | MEISA - India | MEISA | Aparna Sreedevi, Sara Hariga, Mustafa Assaf, Mohammed Wazif Ziavudheen, Richard Ramirez | On Track | M2 Flight launched in Nov'24 and all mielstones have been compeleted | K: L5 | Completed | L5 | 2024-05-01 | 2025-03-31
Business Only Initiative: [IN] CE Quality Assurance Framework | 82857 | 7699 | Business Only Initiative | MEISA - India | MEISA | Om Singh, Patrick Peter Makwana | On Track | as part of CE reimagine | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-09-02 | 2026-05-29
Business w/ Tech Initiative: [MEISA] [Enabler] TCH initiative for STC Revenue E | 92839 | 7743 | Business w/ Tech Initiative | MEISA - India | MEISA | Yash Chaturvedi, Percy Saher | On Track | There is a separate plan view created for each of these in replacement from the combined one. Approved by Marketing MD - Arthi for cancellation here. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2024-07-01 | 2025-03-13
Business Only Initiative: [IN] [IB] Grow SAM Offshore paid Inbound revenue f | 59504 | 7768 | Business Only Initiative | MEISA - India | MEISA | Hemant Pimplikar, Sachin Shukla, Vinay Gopalan | On Track | Cancellation request raised considering this was for last year and all off shore paid initiatives are being aligned to tricolor domain | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: [IN] [Enabler] Improve outbound CLH utilization & | 57254 | 7996 | Business Only Initiative | MEISA - India | MEISA | Sunil K P, Sudhir Rana, Krishnaprasad Ramachandran | On Track | On track, monithly monitoring action in place to improve utilization. | I: L4 | Active | L4 Feedback Requested | 2023-12-01 | 2025-03-31
Business Only Initiative: [IN] [Enabler] Improve billing, Cash Application a | 57252 | 8197 | Business Only Initiative | MEISA - India | MEISA | Yash Chaturvedi, Priya Shenoy | On Track | All milestones completed | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-01 | 2025-03-31
Business w/ Tech Initiative: [MEISA] [Enabler] TCH initiative for STC Enablers | 86818 | 8198 | Business w/ Tech Initiative | MEISA - India | MEISA | Priya Shenoy, Yash Chaturvedi | On Track | There is a separate plan view created for each of these in replacement from the combined one. Approved by Marketing MD - Arthi for cancellation here. | E: L2 | Cancelled | L2 | 2024-07-01 | 2024-12-17
Business Only Initiative: [IN] [RT] Drive incremental revenue by implementin | 35868 | 8250 | Business Only Initiative | MEISA - India | MEISA | Neeraj Bhutada, Santosh Karveershettar | On Track | The initiative has given mature benefit above plan from Oct'24 to Dec'24. | K: L5 | Completed | L5 | 2023-08-01 | 2024-07-02
Business w/ Tech Initiative: [MEISA] [Enabler] Configuration of ATLANTIS for ME | 94473 | 8272 | Business w/ Tech Initiative | MEISA - India | MEISA | Vinay Gopalan | On Track | Request for cancellation raised considering this has been implemented and already in use | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: [IN] [RT] Grow Hi-tech vertical with identified o | 37439 | 8421 | Business Only Initiative | MEISA - India | MEISA | Srinivasa Rao Kodavatiganti, Vinay Gopalan, Krishnaprasad Ramachandran, Hemant Pimplikar | On Track | - Commercial Line Haul, Ongoing weekly status of connection APAC to BLR in South & AMD in West - Implants : plan underway to secure 3-4 more Implants to grow offshore business - Drop Ship: 2 projects are on course - FOSS : FedEx one stop solution. FXL services are billed to Express Account. Awaiting Import - Investment Pricing : monitoring Phase I & II | K: L5 | Completed | L5 | 2023-06-01 | 2024-10-31
Business Only Initiative: [IN] [RT] Grow Automotive, Fashion & Retail vertic | 37440 | 8422 | Business Only Initiative | MEISA - India | MEISA | Tathagata Ghosh, Hemant Pimplikar, Vinay Gopalan | On Track | On Track, L4 evidence approved by FP&A team | K: L5 | Completed | L5 | 2023-12-01 | 2024-12-31
Business Only Initiative: [IN] Grow revenues - ICL | 83385 | 8423 | Business Only Initiative | MEISA - India | MEISA | Waseem Irfan, Krishnaprasad Ramachandran, E S Sudharsan, Vinay Gopalan | On Track | Initiative placed for cancelation considering ICL is being tracked outside of Planview in FY26 | I: L4 | Cancelled | L4 | 2024-03-01 | 2025-03-31
Business Only Initiative: [IN][Cost] Optimise Gateway Operation model to red | 36261 | 8443 | Business Only Initiative | MEISA - India | MEISA | Subodh Randive | On Track |  | K: L5 | Completed | L5 | 2024-01-16 | 2024-04-15
Business Only Initiative: [IN] [Enabler] Sales incentive re-imagined | 58242 | 8965 | Business Only Initiative | MEISA - India | MEISA | Vinay Gopalan | On Track | Cancelation request being initiated considering this is already implemented and no activity in 100 days and not pursued in FY26 | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-01-30 | 2025-02-28
Business Only Initiative: [IN] [Enabler] Sales Capability Development | 64467 | 9088 | Business Only Initiative | MEISA - India | MEISA | Anindya Dasgupta, Harshal Bhand | On Track | We have modules for all the Key commercial initiative - IN Imports (IN & Offshore paid), Freight (Express & FXL), eCommerce, Vertical specific (Healthcare) and Pricing (Selling profitably and responsibly) 13Jun25: Changing the IO to Anindya as Harshal has moved into a new role. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-01 | 2025-06-19
Business Only Initiative: PCC + implementation in India | 89834 | 9095 | Business Only Initiative | MEISA - India | MEISA | Vikeeth Kottari, Sharath Shetty, Anita Bhardwaj | On Track | No KPIs defined for the project | E: L2 | Cancelled | TEMP L2 - Enter Value Prop
Business Only Initiative: [IN][FDX] - End - to -End Order orchestration plat | 37415 | 9110 | Business Only Initiative | MEISA - India | MEISA | Kranthi Chennamsetty, Aman Saraswat | On Track | Further development on the fdx platform tailored to MEISA Roadmap, have a take a different direction, with changes in the global fdx priorities. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-03-01 | 2026-04-30
Business Only Initiative: [IN] [SG&A] Reduce % of Bad Debt to Revenue | 36434 | 9404 | Business Only Initiative | MEISA - India | MEISA | Priya Shenoy, Balamurugan Periyallangan | On Track | Initiatives are on track and no challenge identified 5th Sept - Obtained FP&A confirmation to move the initiative to L5 and moved | K: L5 | Completed | L5 | 2023-06-01 | 2024-05-31
Business Only Initiative: [IN][E2E] FXL Growth - Nomination business |  | 88072 | Business Only Initiative | MEISA - India | MEISA | Prithvi Rautela | On Track | Decision taken to cancel as the control lies largely at the destination side and driving this for results from the origin will not be very efficient and ownership will be difficult to assign. | E: L2 | Cancelled | L2
Business Only Initiative: MEISA - Pune rental reduction |  | 91042 | Business Only Initiative | MEISA - India | MEISA | Vikeeth Kottari, Sharath Shetty, Anita Bhardwaj | On Track | Initiative has been reinitiated | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: [IN][E2E] Supply Chain Reliance Lifescience |  | 91047 | Business Only Initiative | MEISA - India | MEISA | Mritunjoy Tripathy, Krishnaprasad Ramachandran, Hemant Pimplikar | On Track | We started trial shipments but since most of the lanes are toward non regulated markets like countries in the continent of Africa , Latin America , etc we dont have the value propostion and desired price point to compete with freight forwrders and niche service operatores . | E: L2 | Cancelled | L2 - Enter Value Prop
Business Only Initiative: [IN] [E2E] [FXL] WW AERO & INDUSTRIAL (Excl Tata) |  | 91638 | Business Only Initiative | MEISA - India | MEISA | Prafulla Ghatole, M Thenappan, Hemant Pimplikar, Vinay Gopalan | On Track | Cancellation request raised considering this will be tracked as KPI under the core EGER Aero initiative | G: L3 | Cancelled | L3 | 2025-03-20 | 2025-07-30
Business Only Initiative: [IN][E2E] FXL Growth - India Paid (SAM ) |  | 92992 | Business Only Initiative | MEISA - India | MEISA | E S Sudharsan, Vinay Gopalan | On Track | Cancelation request placed since this is FXL initiative and FXL revenues are being tracked seperately | C: L1 | Cancelled | L1
Business w/ Tech Initiative: QP API enablement |  | 92995 | Business w/ Tech Initiative | MEISA - India | MEISA | Klaudia Palgan | On Track | QP API access for third-party integration is being addressed under the under Global Spot Modernization initataive (Commercial Domain) - this initataive is cancelled to avoid duplication. | C: L1 | Cancelled | L1
Business Only Initiative: [IN] Cost Optimization for Customs Clearance |  | 96416 | Business Only Initiative | MEISA - India | MEISA | Pankaj Jadhav, Vinay Gopalan, Shrikant Nikam | On Track | Initiative put for cancellation considering FP&A feedback that rate negotiations with vendors are part of BAU and not transformational | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: [IN] [FXL] [E2E] Grow Hitech |  | 103617 | Business Only Initiative | MEISA - India | MEISA | Jayanta A. Baruah, Vinay Gopalan, Krishnaprasad Ramachandran, Srinivasa Rao Kodavatiganti | On Track | Being cancelled, this will be tracked as a KPI under the main EGER Hitech initiative | G: L3 | Cancelled | L3 | 2025-05-01 | 2025-10-31
Business Only Initiative: [IN} [FXL] [E2E] Grow Automotive |  | 103624 | Business Only Initiative | MEISA - India | MEISA | Mahesh Gopinath, Vinay Gopalan, Krishnaprasad Ramachandran, Tathagata Ghosh | On Track | Cancellation request is hereby placed considering it will tracked as a KPI under the core initiative of EGER grow Auto | G: L3 | Cancelled | L3 | 2025-05-05 | 2025-11-12
Business Only Initiative: [IN] [FXL] [E2E] Grow Healthcare |  | 109573 | Business Only Initiative | MEISA - India | MEISA | Ameya A. Morye, Vinay Gopalan, Mritunjoy Tripathy | On Track | Cancellation request raised considering the initiative will be tracked as a KPI under the core EGER Healthcare initiative | E: L2 | Cancelled | L2 - Enter Value Prop | 2025-06-03 | 2025-12-15
Business w/ Tech Initiative: Develop REX repost tool for MEISA |  | 127945 | Business w/ Tech Initiative | MEISA - India | MEISA | Pramod Nair | On Track | 06/11 : L1 - Received recommendations from Senior Agile Coach ¦ Software Engineering Practices – Supply Chain Operations to proceed with our work outside of Planview since the Legacy ARTs used by us were not onboarded in Planview. SCO team will work to bring in process for our ARTs in next few weeks. We had 1 demand already rejected. We shall now be requesting cancellation of remaining 2 demands. | C: L1 | Cancelled | L1
Business Only Initiative: MEISA CLH Optimization FY26 |  | 144789 | Business Only Initiative | MEISA - India | MEISA | Abhimanyu Nandi, Prateek Nath, Krishnaprasad Ramachandran, Vinay Gopalan | On Track | On-track ; Money Step Evidance updated and progress to L4. | I: L4 | Active | L4 | 2025-06-02 | 2026-05-29
Business Only Initiative: MEISA CLH Optimization FY26 |  | 152201 | Business Only Initiative | MEISA - India | MEISA | Prateek Nath | On Track | Lisa Rolfe requested that this Initiative be cancelled due to it being a duplicate (PDSM Ticket#INC031570966) | C: L1 | Cancelled | L1
Business Only Initiative: [IN][OB] Grow Freight FY26 |  | 156549 | Business Only Initiative | MEISA - India | MEISA | Neeraj Bhutada, Vinay Gopalan, Santosh Karveershettar, Krishnaprasad Ramachandran | On Track | The initiative is on track. | I: L4 | Active | L4 | 2025-06-02 | 2026-02-02
Business Only Initiative: [IN][OB] Grow SAM MM Business FY26 |  | 156552 | Business Only Initiative | MEISA - India | MEISA | Igor Collaco, Vinay Gopalan, Krishnaprasad Ramachandran | On Track | Initiative is on Track to move to next stage | I: L4 | Active | L4 | 2025-06-02 | 2026-01-15
Business Only Initiative: {IN}{RT}Grow EGER Healthcare FY26 |  | 156555 | Business Only Initiative | MEISA - India | MEISA | Mritunjoy Tripathy, Vinay Gopalan, Hemant Pimplikar, Krishnaprasad Ramachandran | On Track | The initative milestones are completed and ready for L4 | I: L4 | Active | L4 | 2025-06-02 | 2026-02-27
Business Only Initiative: [IN][RT]Grow EGER Auto FY26 |  | 156558 | Business Only Initiative | MEISA - India | MEISA | Tathagata Ghosh, Vinay Gopalan, Hemant Pimplikar, Krishnaprasad Ramachandran | On Track | Innitiaves On track to move to next stage | I: L4 | Active | L4 | 2025-08-01 | 2026-03-05
Business Only Initiative: Project Pascima (FX CAN-BOM Connectivity) |  | 160148 | Business Only Initiative | MEISA - India | MEISA | Richard Ramirez, Mohammed Wazif Ziavudheen | On Track | Case is discontinued, benefits combined with alternative Case SINDBAD | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: [MEISA] Grow new business with "ProspeX"(Lead gen) |  | 160151 | Business Only Initiative | MEISA - India | MEISA | Sachin Shukla, Vinay Gopalan, Rahul Shirke | On Track | Cancellation request put considering this is to be tracked as KPI under the SAM initiatives. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: [IN] [IB] Grow India Paid Imports - FY26 |  | 161706 | Business Only Initiative | MEISA - India | MEISA | SUHAIL MAHAJAN, Vinay Gopalan, Ravinder Kumar Panthri, Krishnaprasad Ramachandran | On Track | Imports is being focused upon considering tariff scenario with initiative on track | I: L4 | Active | L4 | 2025-11-14 | 2026-05-29
Business Only Initiative: [IN][OB] Grow SAM B2B + B2C FY26 |  | 161710 | Business Only Initiative | MEISA - India | MEISA | SUHAIL MAHAJAN, Vinay Gopalan, Ravinder Kumar Panthri, Krishnaprasad Ramachandran | On Track | SAM B2B and B2C initiative is on track | I: L4 | Active | L4 | 2025-06-09 | 2026-03-31
Business Only Initiative: [IN][OB] Grow SAM B2B including Clusters- FY26 |  | 161713 | Business Only Initiative | MEISA - India | MEISA | SUHAIL MAHAJAN, Vinay Gopalan, Ravinder Kumar Panthri | On Track | Cancellation request raised considering we have combined B2B and B2C into a single B2B+B2C initiative based on FP&A recommendation on tracking overall SAM which gives a more accurate picture | G: L3 | Cancelled | L3 | 2025-06-02 | 2026-04-14
Business Only Initiative: [IN][RT] Grow EGER Hi-tech FY26 |  | 162663 | Business Only Initiative | MEISA - India | MEISA | Srinivasa Rao Kodavatiganti, Vinay Gopalan, Hemant Pimplikar, Krishnaprasad Ramachandran | On Track | The intiative is on track Money step evidence submitted Push to L4 | I: L4 | Active | L4 | 2025-08-01 | 2026-02-27
Business Only Initiative: [IN] [RT] TIME CRITICAL SOLUTION FY26 |  | 164337 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Vinay Gopalan, Hemant Pimplikar, Rahul Kitson | On Track | Solutioning is completed for India | E: L2 | Active | L2
Business Only Initiative: [IN] [RT] Grow Aerospace - Industrial FY26 |  | 164340 | Business Only Initiative | MEISA - India | MEISA | M Thenappan, Vinay Gopalan, Hemant Pimplikar, Krishnaprasad Ramachandran | On Track | Intiative is on Track, Money step evidence updated & progressed to L4 | I: L4 | Active | L4 | 2025-06-16 | 2026-02-16
Business Only Initiative: [IN][RT] Develop Healthcare capabilities for IN |  | 166572 | Business Only Initiative | MEISA - India | MEISA | Mritunjoy Tripathy, Vinay Gopalan, Hemant Pimplikar | On Track | On Track | E: L2 | Active | L2
Business Only Initiative: Test BizOnly_IO Splash_cpropst |  | 180702 | Business Only Initiative | MEISA - India | MEISA | Cynthia Propst | On Track | On Track | G: L3 | Cancelled | L3
Business Only Initiative: Direct On Air India - Optimizing Domestic Line-hau |  | 190292 | Business Only Initiative | MEISA - India | MEISA | Zachary Dsouza | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: [MEA] [AE] UAE PLACI – Pre-Load Advance Cargo Info | 77407 | 6710 | Business Only Initiative | MEISA - MEA | MEISA | Lucrezia Lecchi, Brandon Yu | On Track |  | K: L5 | Completed | L5 | 2024-04-05 | 2025-03-31
Business Only Initiative: [ZA] SARN expansion (Vendor operation) | 94480 | 7016 | Business Only Initiative | MEISA - MEA | MEISA | Dewald Hattingh, Clinton Steyn | On Track | 12/11/24 - Vendor onboarding completed. Credit application currently under legal review. 1 additional RISK loaded due to seasonal demand as advised by the vendor. 10/21/24 - The vendor has been loaded on the FedEx system. The vendor credit application is being completed, and once completed, the full rate card will be received and shared with the pricing team to be worked on. 12/10/24 - Vendor has provided rate card and service capabilities. Services shared with the sales team to review. The pricing team requested customer profiling to be completed by the commercial team to ensure correct pricing model creation. Utilization for OB lanes continues to improve currently on 18% IB lanes still under 10%. 17/01/25 - Sales has completed the customer profiling step for the utilization piece, while the expansion profiling is underway. Pricing is currently reviewing submissions by sales for utilization price point. Utilization in December for OB increased to 25% while inbound decreased to 1%. Round trip utilization for December was at 13%. 29/01/25 - SL3 submission completed. Sales has received the SARN utilization-specific pricing. Marketing is currently working on leave-behinds for Sales to make use of as well as the go-to-market packs. In terms of utilization, sales has met with some customers regarding the initiative, and initial feedback from customers indicates interest in the offering pending validation of exact capabilities. 26/02/25 - **SARN utilization** - reduced slightly in the month of January; this was due to low volumes across the SSA market, and KPIs were updated. The sales team has confirmed that they are closing new business using the new rate card prepared for SARN utilization specifically. FedEx South Africa has registered its road bond with the Namibia border, enabling the movement of "in-transit" goods from Namibia through South Africa. **SARN expansion**— Feedback was received from the sales on the customer profiling. The market does not work on rate cards in its current state. Follow the meeting held with the pricing team, requesting that the cost structure be used to develop the new price point pending feedback. 14/03/25 - **SARN Utilization** Go to market plan has been shared with the Sales teams to make use of the new SARN rates prepared. OB Utilization for Feb '25 at 16% while IB is at 3%. **SARN expansion** New rate card for SARN expansion delayed due to some additional information requested by the pricing team. 24/04/25 - **SARN Utilization** Good traction noted on the OB utilization in MAR increasing to 24% overall, IB utilization remains low with 4%. **SARN expansion** Pricing team provided feedback regarding new rate cards and further investigation required from FP&A. The vendor will however be onboarded by SPS to activate and test services. 6/5/25 - **SARN Utilization** Good traction continued on the OB utilization in APR increasing to 26% overall, IB utilization remains steady but low with 4%. **SARN expansion** FP&A has provided feedback on the costing exercise to pricing, feedback now pending from the pricing team regarding new rate card. Expansion rate card milestone has been delayed. 06/06/25 - **SARN Utilization** Although weight increased MOM by 2500+ kg, the utilization reduced to 24% due to additional capacity required and frequency to Namibia being increased. IB weight increased by 600 kg, but due to additional capacity created, utilization remained at 4%. **SARN expansion** contract addendum with SPS still pending for vendor testing. 27/06/25 - **SARN Utilization** Forecast updated until end FY28, full impact expected FY27Q1. With incremental ramp up starting towards end FY26Q1. Transit time adjustments being reviewed for SARN serviced destination.**SARN expansion** SPS confirmed that the movement through ConCargo will be possible with SPS supporting in quoting and billing customers. Marketing to start work on the Go to market plans. All milestones updated. 11/07/25 - **SARN Ut | I: L4 | Active | TEMP L4 - Enter L4 | 2024-08-01 | 2025-10-31
Business Only Initiative: [ZA] [RT] Overtime optimization | 36275 | 7018 | Business Only Initiative | MEISA - MEA | MEISA | Rashil Madaree, Clinton Steyn | On Track |  | K: L5 | Completed | L5 | 2023-06-12 | 2024-03-29
Business Only Initiative: [AE, SA] [RT] Grow OB IRFS by leveraging MERN netw | 36277 | 7035 | Business Only Initiative | MEISA - MEA | MEISA | Khurram Azfar, Jithin Acharya, Klaudia Palgan | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead, the direction is to proceed with the cancellation of this initiative (in FY26 MERN LTL impact incl. DG will be tracked under Business with tech, growth initataive #7621) | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-08-01 | 2025-08-29
Business Only Initiative: [SA, ZA] [RT] Penetrate and grow revenue from EG/E | 36279 | 7037 | Business Only Initiative | MEISA - MEA | MEISA | Rahul Kitson, Klaudia Palgan, Yogesh Jadhav | On Track | on track | K: L5 | Completed | L5 | 2023-10-09 | 2025-05-30
Business Only Initiative: [ZA] [OB] Penetrate Wine vertical in South Africa | 36280 | 7040 | Business Only Initiative | MEISA - MEA | MEISA | Kate Berrington, Megan Smith | On Track | Initiative will be cancelled in FY26. Initially this initiative was onboarded without the proper research being done in the ZA Wine market, with majority of these customers choosing sea-freight solutions. The team have attempted to win sample business as express business, however the nature of sample business in this sector is not consistent, impacting the ability to achieve the associated ramp-up targets. Cancellation approved by Pod Lead. | G: L3 | Cancelled | SL4 Finance Domain Lead Approval | 2023-09-01 | 2025-07-31
Business Only Initiative: [SA][OB][IB] Leverage govt tie ups to grow busines | 36283 | 7044 | Business Only Initiative | MEISA - MEA | MEISA | Rashid Aqel, Nitin Shetty, Joseph Johnson, Klaudia Palgan | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead on June 25th 2025, the direction is to proceed with the cancellation of this initiative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-12-01 | 2025-06-30
Business Only Initiative: [AE, SA] [RT] Penetrate Oil & Gas segment in UAE a | 36284 | 7046 | Business Only Initiative | MEISA - MEA | MEISA | Joseph Johnson, Nitin Shetty, Klaudia Palgan | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Leadership on August 6th, the direction is to proceed with the cancellation of this initiative | I: L4 | Cancelled | L4 | 2023-09-01 | 2025-03-26
Business Only Initiative: [AE, SA] [OB] Penetrate SAM through launch of clus | 36286 | 7048 | Business Only Initiative | MEISA - MEA | MEISA | Shella Marie Chavez Razon, Klaudia Palgan, Sami Jaraman, Trupti Vasani | On Track | On Track | K: L5 | Completed | L5 | 2023-09-25 | 2024-07-18
Business Only Initiative: [MEA] [SG&A] Reduce % of Bad Debt to Revenue | 37428 | 7067 | Business Only Initiative | MEISA - MEA | MEISA | Priya Shenoy, David Grobler | On Track | On track: 2 milestone dates have been extended, however these would not impact the money step date. | K: L5 | Completed | L5 | 2023-10-02 | 2024-10-25
Business w/ Tech Initiative: [ZA][IB] Grow imports business via adapting immedi | 40756 | 7110 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Tamaryn Hamilton, Megan Smith, Gary Hamilton | On Track | **Initiative to be cancelled in Planview.** Rejected at L4 progression due to development work not being successfully completed. This development will be re-scoped into a new APAC led initiative. Consolidated with other MAGIC development requirements for better prioritization. | G: L3 | Cancelled | L3 Feedback Requested | 2023-10-02 | 2026-04-30
Business Only Initiative: LH - Competitive Tender MERN (Middle East Road Net | 70158 | 7194 | Business Only Initiative | MEISA - MEA | MEISA | Min Lu, Afsana Parvin | On Track | 10/08/2024: Initiative submitted for L3 without fuel | K: L5 | Active | TEMP L5 - Enter L5 | 2024-05-21 | 2025-04-21
Business w/ Tech Initiative: [AE, SA] MERN LTL Revenue Growth incl. DG launch | 86937 | 7621 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Jithin Acharya, Krishnaprasad Ramachandran, Klaudia Palgan, Khurram Azfar, Nitin Shetty | On Track | Oct 21st: Daniel Knopfmacher advised original “test only” & “light touch approach” is no longer valid. full Solution Architecture review is required due to SCO impacts; 11/07/2025 Current Status •Both Marketing and Global Pricing acknowledged business criticality. •Initiative remains in Drive process (CPEL/PRT backlog), Current enterprise prioritization ranking: 267. •High complexity and low NRB ($0.6M) limit prioritization; current prioritization ranking logic favors higher-value initiatives. | E: L2 | Active | L2 & CCH | 2024-12-02 | 2027-04-13
Business Only Initiative: [MEA] [Air Operations] Africa Network | 68575 | 7696 | Business Only Initiative | MEISA - MEA | MEISA | Mustafa Assaf, Megan Smith, Mohammed Wazif Ziavudheen | On Track | 2026.01 - Reinstated due to landing rights being obtained for JNB and NBO 3x rotation. Effective Jan 15, 2026 through to Jun 2026. | I: L4 | Active | L4 | 2024-11-21 | 2026-01-30
Business Only Initiative: [SA] [ENABLER] WREG - Automated Invoice Account Cr | 83609 | 7706 | Business Only Initiative | MEISA - MEA | MEISA | Rahul Shirke, Sachin Shukla | On Track | On track | K: L5 | Active | L5 | 2024-09-02 | 2025-01-17
Business Only Initiative: [MEA] CE Quality Assurance Framework | 84839 | 7723 | Business Only Initiative | MEISA - MEA | MEISA | Om Singh, Patrick Peter Makwana | On Track | Will be consolidated as part of the CE Reimagine initiative | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-09-02 | 2026-05-29
Business Only Initiative: [AE] [SA] Grow revenue by leveraging ecosystem pla | 86748 | 7726 | Business Only Initiative | MEISA - MEA | MEISA | Nigel Karlos Desouza, Klaudia Palgan | On Track | In line with the DRIVE ME FY26 initiative structure aligned with Domain leadership, the direction is to cancel initiative #7726 (L2). | E: L2 | Cancelled | L2 & CCH | 2024-08-12 | 2025-11-28
Business Only Initiative: [AE] [OB] SAM Growth (Base, Clusters) | 86014 | 7728 | Business Only Initiative | MEISA - MEA | MEISA | Shella Marie Chavez Razon, Klaudia Palgan, Trupti Vasani, Yogesh Jadhav, Nitin Shetty | On Track | on track | K: L5 | Active | L5 | 2024-06-26
Business Only Initiative: AE SA ZA IB offshore paid from USA | 94199 | 7753 | Business Only Initiative | MEISA - MEA | MEISA | Sammy Bousaba, Rahul Kitson, Klaudia Palgan | On Track | Apr 10, 2026 - Initiative is cancelled as part of the clean up activity in prepartaion for TY26 Sept 23, 2025 – Status updated to ‘On Hold’, pending Domain leadership guidance on whether the IB offshore paid impact should be positioned under MEISA or another domain. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: MA - Introduction of BSA paid by GSP | 85558 | 7807 | Business Only Initiative | MEISA - MEA | MEISA | Sebastien Staelen, Zaid Khammash, Klaudia Palgan | On Track | The BSA was sucessfully extended in April 2025 - effectively delviery more value than initially planned | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-26 | 2024-09-05
Business Only Initiative: [AE] [RT] Building operational capabilities to pen | 36278 | 7998 | Business Only Initiative | MEISA - MEA | MEISA | Andres Klein, Sukhvinder Singh, Yogesh Jadhav, Klaudia Palgan | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead on June 25th 2025, the direction is to proceed with the cancellation of this initiative. | I: L4 | Cancelled | L4 | 2023-11-01 | 2024-07-31
Business Only Initiative: [AE] [RT] Pilot One Stop Shop solution UAE | 36301 | 8006 | Business Only Initiative | MEISA - MEA | MEISA | Osama Farooqui, Susan Varghese, Yogesh Jadhav, Klaudia Palgan | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead on June 25th 2025, the direction is to proceed with the cancellation of this initiative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-11-01 | 2025-08-29
Business Only Initiative: [SA][RT] Improve Operational capabilities in Saudi | 36309 | 8119 | Business Only Initiative | MEISA - MEA | MEISA | Sahar Al fatayri, Klaudia Palgan, Trupti Vasani, Yogesh Jadhav | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead on June 25th 2025, the direction is to proceed with the cancellation of this initiative. *** JED HV clearance was interrupted because heavy rains on Dec 11 JED HV clearance resumed on Dec 19 and no service issues have been reported since then. Sales efforts continue to onboard more clients. Provisional Dec 2023 actuals were entered based on the observed overall country YoY growth - The manifest table doesn’t include high value indication, hence we don’t yet have visibility on actual performance. we will rerun the data once AMEA marketing database for DEC is available. | I: L4 | Cancelled | L4 | 2023-08-29 | 2025-04-30
Business Only Initiative: [MEA]: Improve/Protect the OB GSP Paid yields for | 79206 | 8141 | Business Only Initiative | MEISA - MEA | MEISA | Pradeep Mistry, Vincent Bardet | On Track | Money step completed | K: L5 | Completed | L5 | 2024-03-20 | 2025-07-31
Business Only Initiative: [MA] [RT] Commercial Growth | 94197 | 8142 | Business Only Initiative | MEISA - MEA | MEISA | Seif Eldick, Sammy Bousaba, Klaudia Palgan, Harshal Bhand, Nitin Shetty | On Track | Jun 11, 2025: Had a triage session with CCH lead, Karen McConnico and confirmed there is no commercial value prop impact based on the revised scope of the initiative. Have removed FIC and Retail scope. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-01-02 | 2026-04-30
Business Only Initiative: [AMEA] [MEA] [Enabler] Improve billing, Cash Appli | 36306 | 8196 | Business Only Initiative | MEISA - MEA | MEISA | Yash Chaturvedi, Priya Shenoy | On Track | Actual KPIs considering the controllable and non-controllable impacts added in revised summary. Business impact on invoice accuracy due to bulk clean-ups, Issue resolution impact due to peoplesoft craft issues and 0365 issue impacting cash-apps performance along with global projects. Agreed with Finance lead to consider controllable & non-controllable to proceed with L5. **Key Service KPIs** * Invoice Accuracy: Nov. 1.1%, Dec. 1.9%, Jan, 2.25% (Goal 2.5%) * Issue Resolution: Nov. 87.3%, Dec. 86.3%, Jan, 88.6% (Goal 85%) * Cash-app TAT 72hrs: Nov. 89%, Dec. 91%, Jan, 89% (Goal 90%) * Unapplied %: Nov. 4.1%, Dec. 3.9%, Jan, 4.3% (Goal 2.5%) | K: L5 | Active | L5 | 2023-11-06 | 2025-06-30
Business Only Initiative: Review and optimize the rates in GSP contract | 79180 | 8214 | Business Only Initiative | MEISA - MEA | MEISA | Sebastien Staelen, Zaid Khammash | On Track | new gsp contract template has been developed and being shared by legal on august 15 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-07-22 | 2025-08-15
Business Only Initiative: [QA]: Optimize PUD costs paid to GSP for ecommerce | 96421 | 8216 | Business Only Initiative | MEISA - MEA | MEISA | Sebastien Staelen, Zaid Khammash | On Track | On-track | K: L5 | Completed | L5 | 2024-08-01 | 2025-02-12
Business Only Initiative: [ZA] GROW COLD CHAIN | 94483 | 8269 | Business Only Initiative | MEISA - MEA | MEISA | Mritunjoy Tripathy, Megan Smith | On Track | 2026.01.05 - Healthcare and Cold Chain initiatives in South Africa are very closely linked, and in most cases, the same customers utilize both solutions under the same account number. This overlap makes it challenging to accurately split revenue between the two initiatives and determine which portion belongs to Healthcare versus Cold Chain. To simplify tracking and ensure clarity, we have combined these two initiatives under one consolidated revenue target in initiative #94353 / #8444 with the cold chain specific scope being added. 22/01 - Added Megan Smith as back-up IO | I: L4 | Active | TEMP L4 - Enter L4 | 2024-11-26 | 2026-01-16
Business Only Initiative: [MEISA] Grow the military/defense business segment | 98571 | 8273 | Business Only Initiative | MEISA - MEA | MEISA | Andres Klein, Klaudia Palgan, Nitin Shetty | On Track | Moving from L1 to L2. Defense opportunities remain active for pursuit across MEISA. This sales initiative is in pursuit to grow this segment for FedEx and is aligned with the Defense FedEx sales teams from different regions. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-17 | 2026-04-30
Business Only Initiative: [ZA] SAM Growth | 94474 | 8298 | Business Only Initiative | MEISA - MEA | MEISA | Kate Berrington, Megan Smith, Sarah Padayachee | On Track | 11/11 Needed to assign a back up IO to the intiative. | K: L5 | Active | L5 | 2024-10-01 | 2025-08-29
Business Only Initiative: [ZA] SSA GSP IPF/IEF Service expansion | 94485 | 8311 | Business Only Initiative | MEISA - MEA | MEISA | Eloise Trollip | On Track | 2026.03.27 - For DR Congo IPF Expansion the GSP finally has a contract in place with ET which is wide bodied aircraft and can handle IPF but we want to first run a trial with IP shipments post ME Airspace closure contingency. We have also just about finalized on all of the ancillary charge queries etc for provision into the contract so once the trial mentioned above is done and the contract amendment is complete we can submit the GQTTI. IPF activation for 1 first wave country already complete and pipeline & linehaul review for second first wave country under review | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-30 | 2026-05-29
Business Only Initiative: [ZA] SSA GSP Dry Ice / DG activation Africa | 94487 | 8312 | Business Only Initiative | MEISA - MEA | MEISA | Eloise Trollip | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-31 | 2025-09-30
Business Only Initiative: [ZA] ZA - SSA GSP PTP | 94488 | 8313 | Business Only Initiative | MEISA - MEA | MEISA | Eloise Trollip, Megan Smith | On Track | Some new wave 1 PTP already in the process of being implemented. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-03-28 | 2025-05-30
Business Only Initiative: [ZA/SSA] Grow Industrial Vertical | 94355 | 8314 | Business Only Initiative | MEISA - MEA | MEISA | Gary Hamilton, Megan Smith | On Track | 2025-05 Added Megan Smith as back up IO | I: L4 | Active | L4 | 2024-10-02 | 2026-03-31
Business Only Initiative: [SA] [OB] SAM Growth (Base, Clusters, EC) | 86013 | 8364 | Business Only Initiative | MEISA - MEA | MEISA | Sahar Al fatayri, Klaudia Palgan, Nitin Shetty, Yogesh Jadhav | On Track | On track | I: L4 | Active | L4 | 2025-05-30
Business Only Initiative: [ZA] Onboarding vendor (cool dollies/thermal blank | 94486 | 8387 | Business Only Initiative | MEISA - MEA | MEISA | Megan Smith, Wayne Petersen | On Track | 2026.04.14 - Oximio contract is going through the Encore approval process. Currently pending MD Operations’ approval. Target start date is May 1, 2026. 2026.04.13 - Vendor fully onboarded and contract finalization underway. Tracking of KPIs to begin once vendor is being utilized. 2026.03.13 - IO amended to Megan Smith due to Wayne Peterson leaving the organization. Contracts all approved in ENCORE | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-27 | 2025-09-30
Business Only Initiative: [ZA / SSA] Grow Automotive Vertical | 95180 | 8429 | Business Only Initiative | MEISA - MEA | MEISA | Gary Hamilton, Megan Smith | On Track | 2025-05 Added Megan Smith as back up IO | I: L4 | Active | L4 | 2024-09-02 | 2026-03-31
Business Only Initiative: [ZA]Healthcare Growth (Pharmaceuticals and Medical | 94353 | 8444 | Business Only Initiative | MEISA - MEA | MEISA | Tamaryn Hamilton, Megan Smith | On Track | Added Megan Smith as back up IO | K: L5 | Active | L5 | 2024-10-04 | 2026-03-31
Business Only Initiative: [AE] Grow OB IRFS by leveraging MERN network - FTL | 38902 | 8615 | Business Only Initiative | MEISA - MEA | MEISA | Rahul Kitson, Klaudia Palgan, Mritunjoy Tripathy, Nitin Shetty, Akshay Khosla | On Track | on track | I: L4 | Active | L4 | 2023-10-02 | 2026-03-31
Business Only Initiative: Deactivation of IE/IEF from CN Origin into GSP Mar | 79219 | 8682 | Business Only Initiative | MEISA - MEA | MEISA | Sammy Bousaba, Klaudia Palgan, Harshal Bhand | On Track | progressing | K: L5 | Active | TEMP L5 - Enter L5 | 2024-08-30 | 2024-08-30
Business Only Initiative: [ZA] [RT] Reactive lost TNT customers in South Afr | 36292 | 8870 | Business Only Initiative | MEISA - MEA | MEISA | Kate Berrington, Amanda Scott, Megan Smith | On Track | Initiative will be cancelled in FY26. After reviewing the data for the TNT customers, IO and team ran a blitz to attempt to win these customers back (approx. 90 customers). However, it was found that all of the TNT customers have been contacted and informed of their active FedEx accounts, leaving no action to ‘Win-back’. Cancellation approved by Pod Lead. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-09-15 | 2025-07-31
Business Only Initiative: [MEA] [RT] Transit Time improvements across AE, SA | 36287 | 9003 | Business Only Initiative | MEISA - MEA | MEISA | Lucrezia Lecchi, Andreia Frutuoso | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead on June 25th 2025, the direction is to proceed with the cancellation of this initiative. | I: L4 | Cancelled | L4 | 2023-10-02 | 2024-12-20
Business Only Initiative: [MEA] [Enabler] Sales Capability Development | 88190 | 9089 | Business Only Initiative | MEISA - MEA | MEISA | Anindya Dasgupta, Harshal Bhand | On Track | on track | K: L5 | Completed | L5 | 2024-08-01 | 2025-02-28
Business Only Initiative: [MEA] [Enabler] Sales competency assessment | 88638 | 9090 | Business Only Initiative | MEISA - MEA | MEISA | Anindya Dasgupta, Harshal Bhand | On Track | 13Jun25: Changing the IO to Anindya as Harshal has moved into a new role. As on date; 28th July, this is on hold as per direction from Hua. 20th Nov: Hua has approved to cancel this initative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-03-01 | 2027-03-31
Business Only Initiative: [AE] [OB] Penetrate e-Commerce segment in UAE | 36276 | 9345 | Business Only Initiative | MEISA - MEA | MEISA | Andres Klein, Klaudia Palgan | On Track | on track | K: L5 | Completed | L5 | 2023-06-01 | 2024-12-31
Business Only Initiative: [MENA]] Grow EG ER focused verticals with E2E | 86344 | 9347 | Business Only Initiative | MEISA - MEA | MEISA | Mohammed Shamim Shaikh, Klaudia Palgan, Yogesh Jadhav, Rahul Kitson | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Lead on June 25th 2025, the direction is to proceed with the cancellation of this initiative. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-08-01 | 2025-07-14
Business Only Initiative: [SA] [OB] Grow e-Commerce segment in Saudi Arabia | 40606 | 9348 | Business Only Initiative | MEISA - MEA | MEISA | Sahar Al fatayri, Klaudia Palgan, Mohamed Ali | On Track | As per the FY26 DRIVE ME initiative structure aligned with the Domain Leadership on August 6th, the direction is to proceed with the cancellation of this initiative (e-commerce will be in scope of a new SAM-focused initataive) | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-12-01 | 2025-10-01
Business Only Initiative: [AE] [SA] [ZA] [IB] Grow inbound offshore paid bus | 50605 | 9350 | Business Only Initiative | MEISA - MEA | MEISA | Sammy Bousaba, Klaudia Palgan | On Track | Apr 10, 2026 - Initiative is cancelled as part of the clean up activity in prepartaion for TY26 Aug 18, 2025 – Status updated to ‘On Hold’, pending Domain leadership guidance on whether the IB offshore paid impact should be positioned under MEISA or another domain. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: MEISA Bad Debt POD - 1% to Rev. | 88774 | 9402 | Business Only Initiative | MEISA - MEA | MEISA | David Grobler, Balamurugan Periyallangan | On Track |  | K: L5 | Completed | L5 | 2024-08-15 | 2025-04-25
Business Only Initiative: [AE] Freight PUD Network redesign in UAE |  | 88079 | Business Only Initiative | MEISA - MEA | MEISA | Djafer Tadjine, Hussain Khanbhaiwala, Sukhvinder Singh, Parag Kaul | On Track | On track | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2025-08-15 | 2026-04-30
Business Only Initiative: Salesforce license optimization |  | 91329 | Business Only Initiative | MEISA - MEA | MEISA | Patrick Peter Makwana | On Track | planview approval process ongoing | K: L5 | Completed | L5 | 2024-10-01 | 2024-11-29
Business Only Initiative: MEISA telephony expenses reduction |  | 91332 | Business Only Initiative | MEISA - MEA | MEISA | Adhir A. Varma, Patrick Peter Makwana | On Track | Risk: Due to ongoing situation, the 100% savings realisation will start from 9th May. Also customers could take time to transition to new number | I: L4 | Active | L4 | 2025-01-31 | 2026-03-02
Business Only Initiative: EE2.0 - MEISA savings due to deferred projects |  | 91635 | Business Only Initiative | MEISA - MEA | MEISA | Avinash Rupani, Klaudia Palgan, Sumit K. Neogi | On Track | No expenses thus far. | K: L5 | Completed | L5 | 2024-08-01 | 2025-02-28
Business Only Initiative: [ZA] Launch partner Life Science Center-IMP Depot |  | 96421 | Business Only Initiative | MEISA - MEA | MEISA | Megan Smith | On Track | Initiative will be included as a core milestone under the Global Clinical Trials initiative (IO: Michael Ely). Due to this, this initiative will be cancelled in MEA Pod. Local work: vendor onboarding is completed. | E: L2 | Cancelled | L2 & CCH - Feedback Requested | 2025-08-15 | 2025-11-28
Business Only Initiative: [ZA] Reduction of bank charges in South Africa |  | 96425 | Business Only Initiative | MEISA - MEA | MEISA | Lata Puraswani, Megan Smith | On Track | Negotiation completed with Standard Bank to lower the charges. Revised contract is under review with legal team. 03/05 - Added Megan as back up IO | K: L5 | Active | TEMP L5 - Enter L5 | 2025-08-05 | 2025-09-30
Business Only Initiative: [GSP] Optimize costs for IB BS / OB BCN shipments |  | 99514 | Business Only Initiative | MEISA - MEA | MEISA | Sebastien Staelen | On Track | as recommended by Klaudia and agreed with Zaid, we are closing this initiative due to low impact. the enabler will remain active. | C: L1 | Cancelled | L1
Business Only Initiative: [SSA/KE] Launch of 3x NBO Freighter |  | 99517 | Business Only Initiative | MEISA - MEA | MEISA | Ruth Kabogo, Megan Smith, Consolata M. Nzomo | On Track | Initiative to be cancelled, new request to be added in FY27 if the need arises again. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: [SA] Address standardization to optimize last mile |  | 103863 | Business Only Initiative | MEISA - MEA | MEISA | Mohammad Faisal Al Ho, Akshay Kumar, Klaudia Palgan, Palanivel Guruswamy | On Track | Started. IB Revenue is ~$90m, if 10% of addresses are incorrect, this equates ~$9m Revenue that is impacted. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-07-15 | 2025-09-01
Business w/ Tech Initiative: Split EMEA Oracle AR Extracts into EU & MEISA |  | 113052 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Yien-Tiang Eve Yong, Umesh Naidu | On Track | This should be a local enhancement instead of Business with tech | C: L1 | Cancelled | L1
Business Only Initiative: GSP SAM Clusters |  | 113056 | Business Only Initiative | MEISA - MEA | MEISA | Harshal Bhand | On Track | Cancelling this initiative as we are working on a larger GSP initiative. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: MODERNIZING CIAM PAYMENT |  | 130554 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Lukesh Chhandwani | On Track | This development is needed across AMEA hence have raised a new PV at AMEA level hence this PV raised for MEISA needs to be cancelled. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [SSA/SZ] Swaziland Country Name Change |  | 130557 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Vanessa Goncalves Lume, Megan Smith, Bianca Theresa McGee | On Track | 2026.04.13 - pending L2 Architecture review. Currently in the L2 Backlog with a priority rank of #284 with impacts to all 5 portfolios and currently sized as an XL. **At this point, there is no concern with the delay as the Eswatini authorities have stated that there will be no fines or penalties associated to companies that do not have the name changed.** Added Bianca McGee as IO, as Vanessa Lume is on Maternity leave. The request is being redirected to MEISA / MEISA-MEA Pod in Air & International Domain. Please note that this initiative is BwT (Business with Tech) and therefore requires IT involvement and prioritization. As per IT guidance, all work requiring tech involvement needs to be entered on Planview for action, as no work is being prioritized by IT, without a PV number. PPM Proposal 1834898 - Approved by Business Owner | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: [SA] Implementation of National Address |  | 130738 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Mohammad Faisal Al Ho, Klaudia Palgan | On Track | The deadline from the TGA (Transport General Authoritiy) in Saudi Arabia for all courier companies to comply to national address requirement is 01 Jan 2026. | E: L2 | Active | L2 | 2025-12-24 | 2025-12-31
Business Only Initiative: [MEISA] - Project SAVE 2.0 Roll out |  | 141544 | Business Only Initiative | MEISA - MEA | MEISA | Nayanthara Anup (Nayan), Klaudia Palgan | On Track | [Nov 26] The roll out of Project SAVE to MEISA involved, training sessions, setting up accesses for all MEISA CC owners, correcting the EDM structure as well as CC Ownership along with FP&A, change management programs, and tracking the progress using weekly score cards. Above had been already completed and currently we are tracking savings across MEISA. Also, the users are now able to view the entries on their CC on a real time basis and correct any wrong entry prior to the month end enabling clean month end closure. | I: L4 | Active | L4 | 2025-06-02 | 2026-04-14
Business Only Initiative: [MEA] [RT] [Commercial/Sales] [Enabler] Adapt dyna | 36274 | 8433 | Business Only Initiative | MEISA - MEA | MEISA | Pradeep Mistry | On Track |  | K: L5 | Completed | L5 | 2023-10-30 | 2024-04-30
Business Only Initiative: GSP Commercial Growth |  | 152785 | Business Only Initiative | MEISA - MEA | MEISA | Harshal Bhand, Klaudia Palgan, Sammy Bousaba | On Track | Jan 7, 2026 - Cancelling as alligned with Sammy Bousaba due to recent developments. | C: L1 | Cancelled | L1
Business Only Initiative: [ZA/SSA] Grow Fashion / FMCG |  | 153535 | Business Only Initiative | MEISA - MEA | MEISA | Gary Hamilton, Megan Smith | On Track | Created L1 business case and submitted accordingly | I: L4 | Active | TEMP L4 - Enter L4 | 2025-11-28 | 2025-11-28
Business Only Initiative: [SA] EN segment growth in Saudi Arabia |  | 153830 | Business Only Initiative | MEISA - MEA | MEISA | Akshay Khosla, Klaudia Palgan, Tarek Adel, Nitin Shetty | On Track | Nov 28, 2025 - extending Money step end date as the pricing program is still WIP, actual pricing requirements specific to customers and lanes are being reviewed with the RMT, including competition market benchmarks vs VMs, and what can be approved by specific lane / customers | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-01 | 2026-05-29
Business Only Initiative: [AE] EN segment growth in UAE |  | 153833 | Business Only Initiative | MEISA - MEA | MEISA | Akshay Khosla, Klaudia Palgan, Nitin Shetty | On Track | Nov 28, 2025 - extending Money step end date as the pricing program is still WIP, actual pricing requirements specific to customers and lanes are being reviewed with the RMT, including competition market benchmarks vs VMs, and what can be approved by specific lane / customers | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-15 | 2026-04-30
Business Only Initiative: [AE] Middleman segment growth in UAE |  | 153836 | Business Only Initiative | MEISA - MEA | MEISA | Viral Narendra Mehta, Nitin Shetty, Klaudia Palgan | On Track | CE Backend team is working on the M&I solution and needs more time to allocate resources and launch this in UAE . | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-30 | 2026-05-28
Business Only Initiative: [SA] [OB} Middleman Segment Growth in Saudi Arabia |  | 157302 | Business Only Initiative | MEISA - MEA | MEISA | Joseph Johnson, Klaudia Palgan, Nitin Shetty | On Track | On track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-29 | 2026-04-30
Business Only Initiative: {SA} Retail Expansion Strategy |  | 160155 | Business Only Initiative | MEISA - MEA | MEISA | Jithin Acharya | On Track | based on the updated initiative structure retail segment is included in other growth initiatives - SA – SAM (Base + Clusters + Ecom + Retail). | C: L1 | Cancelled | L1
Business Only Initiative: {AE} Retail Expansion Strategy |  | 160158 | Business Only Initiative | MEISA - MEA | MEISA | Jithin Acharya | On Track | based on the updated initiative structure retail segment is included in other growth initiatives - AE – SAM B2C (Ecom + Retail) | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [ZA] Magic Development (TAX ID field pop-up msg.) |  | 160223 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Wayne Petersen, Megan Smith | On Track | As this request was changed to a pop-up message and not a mandatory field, there would not be any quantifiable savings amount to justify tech development. Due to this, the initiative will be cancelled and not continued in Planview. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: [AE] [IB] Grow SAM Imports (Country Paid) - UAE |  | 161053 | Business Only Initiative | MEISA - MEA | MEISA | Vincent Bardet, Klaudia Palgan, Sammy Bousaba, Nitin Shetty | On Track | on track | K: L5 | Active | L5 | 2025-10-01 | 2026-04-02
Business Only Initiative: [AE] [OB] SAM Segment - Grow E-Commerce |  | 161057 | Business Only Initiative | MEISA - MEA | MEISA | Vincent Bardet, Klaudia Palgan, Sammy Bousaba, Nitin Shetty | On Track | on track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-22
Business Only Initiative: [SA] [IB] Grow SAM Imports (country-paid) |  | 162392 | Business Only Initiative | MEISA - MEA | MEISA | Tarek Adel, Klaudia Palgan, Rashid Aqel, Nitin Shetty | On Track | On track | I: L4 | Active | L4 | 2025-09-29 | 2026-04-30
Business Only Initiative: [AE]EGER: Grow Offshore Paid Inbound Revenue |  | 162396 | Business Only Initiative | MEISA - MEA | MEISA | Rahul Kitson, Klaudia Palgan, Mritunjoy Tripathy, Nitin Shetty | On Track | on track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-09-30 | 2026-04-30
Business Only Initiative: [SA]EGER-Grow Buyer Rev with Focus on Key Vertical |  | 162400 | Business Only Initiative | MEISA - MEA | MEISA | Rahul Kitson, Klaudia Palgan, Mritunjoy Tripathy, Nitin Shetty | On Track | on track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-01 | 2026-04-30
Business Only Initiative: [AE]EGER:Grow Buyer Rev with Focus on Key Vertical |  | 162404 | Business Only Initiative | MEISA - MEA | MEISA | Rahul Kitson, Klaudia Palgan, Mritunjoy Tripathy, Nitin Shetty | On Track | on track | I: L4 | Active | L4 | 2025-10-01
Business Only Initiative: [SA]EGER-Grow offshore paid inbound revenue |  | 162407 | Business Only Initiative | MEISA - MEA | MEISA | Hemant Pimplikar, Klaudia Palgan | On Track | 23/9 - as per guidance from WW Sales MD due to minimal YOY revenue growth | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: [ZA/SSA] SARN Utilization Growth |  | 162544 | Business Only Initiative | MEISA - MEA | MEISA | Jansen Van Vuuren, Megan Smith | On Track | *Added Megan Smith as back-up IO. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-09-30 | 2025-11-28
Business Only Initiative: [AE] Project SAVE-UAE Sponsorship Policy Benefit |  | 163720 | Business Only Initiative | MEISA - MEA | MEISA | Nayanthara Anup (Nayan), Klaudia Palgan | On Track | On track | K: L5 | Active | L5 | 2025-11-28
Business w/ Tech Initiative: [SA] Biometric Attendance System Implementation |  | 168292 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Mohammad Faisal Al Ho, Klaudia Palgan | On Track | Currently FedEx Saudi Arabia does not have any automated solution to capture working hours for 200+ employees across the kingdom. This puts a huge risk on ops team in errors in recording due to manual system and it does not give any visibility to the Operations management on effectively monitoring working hours and improvement of efficiencies | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: {MEA} Develop Healthcare Capabilities in AE & SA |  | 177357 | Business Only Initiative | MEISA - MEA | MEISA | Mritunjoy Tripathy, Hemant Pimplikar | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: GSP CEBS Data Sharing |  | 188790 | Business w/ Tech Initiative | MEISA - MEA | MEISA | Janet Chamdal | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Smalls Bags Broken Open | 538 | 6673 | Business Only Initiative | FXG D - DPS | Dock | Erin Doyle, Phil Eskew | On Track | Initiative was moved to the Dock domain. 2023-02-01: Initiative was moved back to L3 in order to see measurable improvements on KPIs leading up to moving to L4. Money step will change to milestone 7386 in order to track performance of KPIs before making the move to L4. Milestone 7362 will be moved to Change Management step. | K: L5 | Completed | L5 | 2022-11-04 | 2023-03-31
Business Only Initiative: Smalls Reusable Bags | 539 | 6684 | Business Only Initiative | FXG D - DPS | Dock | Alejandro Avila, Allison Graf | On Track | 2/10/23: N/A 2/3/23: N/A 1/27/23: N/A | K: L5 | Completed | L5 | 2022-11-02 | 2024-06-04
Business w/ Tech Initiative: [Enabler] Dock Data Modernization | 68511 | 7145 | Business w/ Tech Initiative | FXG D - DPS | Dock | Michael Frieden, David Ojeda | On Track | Initiative is currently on schedule. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-01 | 2028-09-12
Business w/ Tech Initiative: Compass - Surface Expansion | 68538 | 7429 | Business w/ Tech Initiative | FXG D - DPS | Dock | Juan Leoni, Michael Frieden | On Track | 5/19 - Ticket created to move from L2 to L1. Rescope was approved by Jim Moore, moving initiative from enabler to value | E: L2 | Active | L2 | 2026-01-01 | 2027-06-25
Business w/ Tech Initiative: Dock Management Tool Enhancements | 23314 | 8440 | Business w/ Tech Initiative | FXG D - DPS | Dock | Stephen McGeever, Erin Wise | On Track | Everything is on track. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-04-03 | 2026-02-27
Business w/ Tech Initiative: Tracking Reusable Smalls Bags | 2824 | 8929 | Business w/ Tech Initiative | FXG D - DPS | Dock | Alejandro Avila, Allison Graf | On Track | WE 7.29 -steven leicher reached out for cost analysis for forever label to use for containerization project WE6.24 -no updates WE 6.17 -no updates WE 6.10 -No updates -FY24 RB order should begin arriving 8.22 -Waiting to see what the FY24 orders and balancing training does to compliance WE 5.27 -In limbo stage waiting to see what balancing model and extra bags does to compliance -This will make the case for allocating additional funds to buying more RB until RFID is available -Still updating the PPT to be ready once team wants to present WE 5.20 -updating PPT to reflect below options -allocating funds to additional bags: waiting to see what the most recent order (400k bags) and the balancing model does to compliance would support this option -revisit forever barcode -also adding labor costs for each of the tracking options WE 5.13 -No update -Meeting 5.12 to talk through path forward WE 5.6 - really struggling with seeing clear path forward. -do we revisit forever barcode with dual barcode having a lot of concerns -with concerns of dual barcode and other option being >$10m is forever barcode really that big of an ask? -do we wait and see what the additional 400k bags do to compliance along with balancing model training -do we just go with dual barcode in the short term even though there are a lot of concerns -setting up call later this week/early next week with Jake, david o, david o, megan, mike, sarah to discuss path forward WE 4.22 -Tech research team presented their suggestion -smalls team discussing how we want to proceed -Word that RFID could be started as soon as Q1- if this is true (shorter timeline) do we bulk up on bags until RFID is implemented- would be cheapest option without infrastructure cost -Creating final PPT to present to DRIVE leadership WE 4.15 -Tech research and Dev team provided updated estimate for RFID: $10.8m with $232k recurring - still waiting on final xls/ppt from zebra -Tech research and dev team to provide their suggestion on next weeks touch base WE 4.8 - No major updates - Still waiting on RFID costs from Tech research and Dev -~$7m estimation currently - once costs are finalized we will put together PPT with our recommendation to present to DRIVE leadership WE 4.1 - IT provided internal IT costs for BLE and RFID and an updated IT cost for Dual Barcode -Dual barcode was $2.485m now $1.6675m - BLE and RFID $0.8875m -Timeline for IT work 40-50 weeks -Tech dev team working with zebra to get a quote for RFID: should have by Friday -Douglas King said that even if we decide as a company to go the RFID route it will be 2-4 years before the network is able to read RFID (we would not have to pay for infrastructure) -Network will be BLE readable by June -Looking into short term/long term solution WE 3.25 - Fist Jagadeesh IT architect call 3.23 - WIRO team invited to call to talk through why they believe that bags would need to travel through scan tunnel for dual barcode to work - Finding out from SA team plans to have entire network set up to be able to read BLE - Tech dev team setting up RFID scan tunnel test with ZEBRA - after test tech dev team to put together quote with ZEBRA to determining cost estimate -A lot of movement outside of this initiative for RFID at FDX. Leadership meeting at Zebra headquarters to discuss how we can use RFID (Next week) - Need to see outcome of that- if FDX is going to move to RFID and put readers in building this decision is obvious WE 3.18 -Testing RFID at ECLE with zebra/tech research team -Proved that RFID would scan through bags on stands, through bags stored in gaylords, scan through full bags -Meeting with Lisa Perez and architects to determine IT pricing for BLE and RFID options -Jagadeesh to lead the IT architects to find "t-shirt" IT cost for RFID and BLE- 2 week target date WE 3/11 -Met with Lisa Perez (TCH): decision to move back to L2- is this happening? -Gives more time to make dec | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-07-22 | 2026-03-25
Business w/ Tech Initiative: 2D barcode sortation | 21276 | 9473 | Business w/ Tech Initiative | FXG D - DPS | Dock | Deepak Chandran, Erin Wise | On Track | Change in Milestone "Rollout phase 2" | K: L5 | Active | TEMP L5 - Enter L5 | 2022-10-04 | 2025-06-27
Business w/ Tech Initiative: Real-Time Ops Manager (ROM) | 517 | 9518 | Business w/ Tech Initiative | FXG D - DPS | Dock | Joseph Sasala, Heather Mullins, Sarah Bauer | On Track | 1.What has specifically been identified as a risk/impediment/blocker - 1.2 delays to photoeye and TLS ingestion 2.What other related projects and/or initiatives are impacted by this issue? - N/A 3.What affect does this issue have on delivery times for this initiative? - slight delay to rollout for automated hub and OB operations 4.What is being done to resolve the issue? - adjusted the timeline and rollout plan, working with impacted ARTs to try to align development work 5.Does this needed to be escalated to move past the impediment? - No | I: L4 | Active | TEMP L4 - Enter L4 | 2022-05-11 | 2026-05-29
Business w/ Tech Initiative: Metrics - Compass | 524 | 9529 | Business w/ Tech Initiative | FXG D - DPS | Dock | Juan Leoni, Michael Frieden | On Track |  | G: L3 | Active | TEMP L3 - Enter L3 | 2022-10-03 | 2026-09-04
Business w/ Tech Initiative: [Enabler] Employee Productivity Awareness | 520 | 9551 | Business w/ Tech Initiative | FXG D - DPS | Dock | Samantha Nagle, David Ojeda | On Track | All milestones complete. Pilot results were presented to the station for final feedback. L4 presentation and submission scheduled for 11/25. | K: L5 | Completed | L5 | 2024-04-22 | 2024-11-15
Business w/ Tech Initiative: Employee Productivity Awareness [Full] |  | 96205 | Business w/ Tech Initiative | FXG D - DPS | Dock | Samantha Nagle | On Track | 09/18 - The current cost savings estimate for the initiative is greatly outwieghed by the estimated hardware costs to make it functional. We will be placing this initiative on hold until we can find another effort that can share costs and/or add value. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Daily Priority Metrics |  | 96218 | Business w/ Tech Initiative | FXG D - DPS | Dock | Ronald Thies | On Track | We need some Ground data. We have continue with building an Express version of the report since we have the data for that. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: [Enabler] Robotic Trailer Unloading Project-Step 3 |  | 96226 | Business w/ Tech Initiative | FXG D - DPS | Dock | William Brandt | On Track | Project is moving forward towards a targeted goal of a September CY25 deployment. Timeline is tight, but on track so far. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: (Enabler) Robotic Trailer Loading Project |  | 96229 | Business w/ Tech Initiative | FXG D - DPS | Dock | Amanda G. Noe | On Track | 03/31 LBC is complete | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: QRTL (Queuing Robotic Trailer Loader) Development |  | 98297 | Business w/ Tech Initiative | FXG D - DPS | Dock | John Barron | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Compass - AI Navigator |  | 141638 | Business w/ Tech Initiative | FXG D - DPS | Dock | Michael Frieden, Juan Leoni, Abiola Abraham | On Track | Created LBC - 07/25 | E: L2 | Active | L2 | 2026-01-01 | 2027-02-26
Business w/ Tech Initiative: Print & Apply at Overhead Sorters |  | 189750 | Business w/ Tech Initiative | FXG D - DPS | Dock | Daniel Bonnett, Ely Roselius, Tyler Howcroft | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Package Handler (PH) Overtime (OVT) Reduction | 30589 | 6777 | Business Only Initiative | FXG D - Execution | Dock | Mark Centofanti, David Henderson, Gail Kouch | On Track | Week ending 6/17/2023: • Building L2 and L3 launch plan. • Finalized KPI and cost metrics. • Prepping for L2/L3 pitch. Deji Aina and Jake Hunter gave financial approval to move forward. Dry run presentation went well and finalized presentation for 6/19 pitch based on recommendations. Week ending 6/24/2023: • L2/L3 pitch completed (Approved). • Updated FY25 impacts and FY24 ramp up plan. • Submitted for L2 approval. • CMO plan template to be submitted. (Completed) • Milestone 314444: Initiate review meeting scheduled with A. Herne, Legal on 6/22/2023. (Completed) • Legal Touchpoint Meeting (Completed) Approval received from A. Herne 6/22/2023. • Submitted for L3 approval. • KPI%: 1.43% for w/e 6/17/2023 down from 1.89% for w/e 6/10/2023 Week ending 7/1/2023: • Update dashboard to include an "about" tab (overview of dashboard) • Draft PH Hours Dashboard job aid. • Draft manager and director email. • Draft communication to launch dashboard. • Meet with Pilot location SRM (B. Jackson) for project update • KPI%: 1.26% for w/e 6/24/2023 down from 1.43% for w/e 6/17/2023 Week ending 7/8/2023: • Route PH Hours Dashboard job aid, email, and launch communication for approvals. • KPI%: 1.28% for w/e 7/1/2023 up from 1.26% for w/e 6/24/2023 Week ending 7/15/2023: • Approval received for draft communication, job aid, and email. • Workfront ticket 1207585 opened for dashboard launch communication. • Meet with Deji Aina regarding status of initiative's cost savings calculator. (Completed - monthly cost savings will be forwarded by D. Henderson/G. Kouche for Deji to review) • KPI%: .80% for w/e 7/8/2023 down from 1.28% for w/e 7/1/2023 Week ending 7/22/2023: • Job aid forwarded to pilot location and D. Henderson for final review/approval. • Link to dashboard and job aid posted to the field reporting site. • KPI%: 1.84% for w/e 7/15/2023 up from .80% for w/e 7/8/2023 • Spoke with manager at pilot location who felt increase is related to expected UPS strike and hours pattern may continue depending on strike outcome. Week ending 7/29/2023: • Created dashboard communication to be included with Focus on the Four's People section • Presented dashboard information to My Schedule team during their weekly staff meeting • Dashboard launch communication published in The Daily Ground 7/27/2023 • KPI%: 2.0% for w/e 7/22/2023 up from 1.84% for w/e 7/8/2023 Week ending 8/5/2023: • Dashboard officially launched 8/1/2023 • Slide presentation developed for RVP meeting • Communication/talking points created for My Schedule/BY staff meeting • Thurs, 8/3/2023 - Email sent to 338 SRM's showing PH's with potential OVT hours. • KPI%: 1.69% for w/e 7/29/2023 down from 2.0% for w/e 7/22/2023 Week ending 8/12/2023: • Presented dashboard on RVP joint staff meeting (8/7/2023) • Tues, 8/8/2023 - Email sent to Directors and SRM's with employees showing worked hours over 40 (actual) • Milestone #31353 (launch automated email process) completed. • Thurs, 8/10/2023 - Email sent to 336 SRM's showing PH's with potential OVT hours. • KPI%: 1.56% for w/e 8/5/2023 down from 1.69% for w/e 7/29/2023 Week ending 8/19/2023: • Completed Control Environment information • KPI%: 1.43% for w/e 8/12/2023 down from 1.56% for w/e 8/5/2023 Week ending 8/26/2023: • KPI%: 1.44% for w/e 8/19/2023 up from 1.43% for w/e 8/12/2023 Week ending 9/2/2023: • Create PH Hours Dashboard slide for FY24 Peak Planning Meeting (Meeting in Sept.) • KPI%: 1.42% for w/e 8/26/2023 down from 1.44% for w/e 8/19/2023 Week ending 9/9/2023: • Completed DRIVE playbook template. • 9/5/2023: Present the PH Hours dashboard during an HR call with Delaware Valley as a tool to be leveraged by their locations. • August Financials: Drive Pro | K: L5 | Completed | L5 | 2023-06-15 | 2023-12-01
Business Only Initiative: EPDI Exemptions | 31469 | 6800 | Business Only Initiative | FXG D - Execution | Dock | Scott Wallis, Carol Eskew | On Track | 6/3/2025 - Financials updated for May MVA 5/6/2025 - Financials updated for April MVA 4/8/2025 - Financials updated for March MVA 3/4/2025 - Financials updated for February MVA 2/11/2025 - Financials updated for January MVA 1/10/2025 - Financials updated for December MVA 12/6/2024 - Financials updaetd for November MVA 11/18/2024 - Financials updated for October MVA. 10/29/2024 - ready to update impacts and KPIs for October next week. 10/7/2024 - CIE Review - Additional Identified Impact Accounts removed from EPDI Exemption Program (94275) was scheduled to be completed on 10/4. Will likely be completed by middle of this week (10/9/24). Should be minimal impact to other remaining milestones. 10/4/2024- updated impacts and KPIs for Sept. Reviewed with Deji on 10/4. 9/4/2024 - updated impacts and KPIs for Aug. Reviewing with Deji on 9/6. 8/6/2024 - updated impacts and KPIs for July. Reviewing with Deji on 8/9. 7/10/2024 - updated impacts and KPIs for June. Reviewing with Deji on 7/12. 6/5/2024 - updated impacts and KPIs for May. Reviewing with Deji on 6/7. 5/8/2024 - completed milestone 38874, 40619, 40625, 40623 and 40628. Money step also completed as well. Updated April Impact and KPIs. Reviewing with finance on 5/14. 4/5/2024 - Updated impacts and KPIs for March. Reviewing with Deji on 4/5. 3/8/2024 - Reviewed with Deji. 03/06/24 - Updated impacts and KPI for February. Still need to review results with Deji on 3/7/24. 02/28/24 - Low impact milestone set to complete. Also updated forecast for KPI (target revenue/package % difference) from Feb - June. Will update remaining months this Spring. 12/21/23 - I updated the forecast for target revenue/package %. Will review with Deji in the new year. 12/20/23 - Confirm clean up for low impact accounts (near completion). 1 high impact account and 2 medium impact accounts to be removed immediately. Another high impact and medium impact accounts to be removed 1/15/24. We are a few days ahead of schedule for the high impact accounts, while we are a week or so behind with medium accounts. Expect to make up ground next year. Also projected out the KPI for target revenue/package % through the end of next fiscal year. However, this has not been reviewed with Deji, and won't be until next year. Question - should I update Wave with my data, and then review with Deji, and if there is not an issue, go ahead and report on it? Else wait until next month? 11/29/23 - Low impact account removal - have now reached all 97. However, when CIE verifying removal of those accounts, some clean up left to do. Feedback provided to pricing so execution can be improved. Targeting removal by next week. CIE analysis milestones high/medium accounts - on track. Pricing milestone for work with sales - on track, but there is a learning curve, as we've seen with the removal of low impact accounts. Meeting scheduled on 12/4 with sales about Priority Tire - our first high impact account that is going through this process - coming out of meeting, goal is to know the expectation for what may be gained in revenue, and what may be given back to the account as part of a waiver. Provided updated calculator to Deji for KPI - revenue/package gain. He is reviewing. May not be ready in time to project for November (due by 11/30). Not concerned about this because we are still only seeing revenue from low impact accounts removed so far, and won't begin tracking for high impact accounts until next year. 11/22/23 - For low impact account removal, we are now at 84 of 97. It was noted that 8 of the remaining belong to one pricing analyst. Pricing is following up with that analyst for an update. We are also planning to reconcile our internal CIE count of removed accounts vs. Pricing's list of removed accounts to ensure alignment. 11/21/23 - Continue to remain on track with the progress CIE Medium and CIE High Impact review milestones. Will have an update on the progress on the low | K: L5 | Completed | L5 | 2023-09-05 | 2025-03-14
Business Only Initiative: [Enabler] OB/OTP Productivity Improvement | 33929 | 6982 | Business Only Initiative | FXG D - Execution | Dock | Daniel P. Kramer, Erin Doyle | On Track | Progressing as expected | I: L4 | Active | TEMP L4 - Enter L4 | 2023-08-07 | 2025-03-14
Business Only Initiative: [Enabler] Inbound Productivity Improvement | 33930 | 6985 | Business Only Initiative | FXG D - Execution | Dock | Heather Ferlaino, Jayme Gawel, Erin Doyle | On Track | Week Ending 3/2/2024 * Above Target for 6 months out of 9 months * February is projecting to be above goal by 8.58% Week Ending 7/29/2023 * Business case baseline and target has been entered. Baseline date range was FY23. Consolidated TLH is of the stations currently on the two reports for FY24 Q1. | K: L5 | Completed | L5 | 2023-08-22 | 2024-03-15
Business Only Initiative: Non-Exempt (NE), Non-PH Overtime (OVT) Reduction | 58947 | 7195 | Business Only Initiative | FXG D - Execution | Dock | Mark Centofanti, David Henderson, Gail Kouch | On Track | Week ending 11/4/2023: • Begin working with Ian Payner to establish impacted employee group for OVT review and reduction. • Switch ownership of initiative to David Henderson Week ending 11/11/2023: • Develop financials for L2/L3 review • WAVE Updates for L2 review • Meet with Deji Aina and Tatiana Nuss for financial review (11/7/2023) • Email B. Jackson, SRM, regarding new dashboard pilot program • Compete CMO template for L2/L3 review for C. Mora • Meet for dry run of L2/L3 pitch (11/9/2023) • L2/L3 meeting (11/10/2023), initiative approved. Week ending 11/18/2023: • Dashboard created and under review • Slides created for People Council meeting (11/27/2023) • Meeting scheduled with pilot location (11/17/2023) Week ending 11/25/2023: • Meet and fine-tune the NE dashboard • Separated OPM and OPA designation based on field feedback • Begin drafting dashboard job aid Week ending 12/02/2023: • Updated financials based on separating OPM's and OPA's into two separate buckets. • Presented dashboard at People Council meeting (11/27/2023) • Continue drafting job aids • KPI: 5.32% for week ending 11/25/2023 down from 6.24% week ending 11/18/2023 Week ending 12/09/2023: • Presented dashboard at SRM meeting (12/04/2023) • Draft Daily Ground communication. • Continue drafting job aids • Create a slide presentation for a Peak Ramp Down meeting for D. Dorn. (Completed) • KPI: 16.89% for week ending 12/02/2023 up from 5.32% week ending 11/25/2023 Week ending 12/16/2023: • Job aids completed, sent for management review/approval. • Once approved, will be shared with pilot location contact for review/feedback. • Created launch communication (Milestone 61589) sent for management review/approval. • Once approved will be shared with Communications group. • FLDA will also pilot the dashboard, link provided to District HRM. • Dashboard updated to display part-time/full-time standard hours. • New dashboard links provided to pilot location contact. • Dashboard information presented during HR Manager meeting (12/11/2023). • KPI: 14.52% for week ending 12/09/2023 down from 16.89% for week ending 12/02/2023 Week ending 12/23/2023: • Dashboard information shared with the Maintenance Team (Patrick Snyder, MD and Travis Clark, Ops Analyst) • Very positive feedback received specifically regarding the ability to access more current OVT data instead of a two-week lag in receiving the information. The MD forwarded the dashboard link to their Ops Analyst, and we have been working through their questions on the dashboard data - no dashboard changes to be made. • Launch communication sent to Communications group for review. (Document finalized and ready for legal review) • Job aid reviewed and approved by pilot location manager • Draft email for automated email process. (Completed 12.22.2023) • Dashboard scheduled to complete by 5AM ET (no longer manually refreshed). • KPI: 11.04% for week ending 12/16/2023 down from 14.52% for week ending 12/09/2023. Week ending 12/30/2023: • Dashboard information shared with the Maintenance Team (Patrick Snyder, MD and Travis Clark, Ops Analyst) • FLDA/pilot district: Sent follow-up sent to District HRM on 12/20 and 12/26 to verify if link shared with District locations. • Launch communication: Communications forwarded to Legal for review/approval. • Job aid reviewed and approved by pilot location manager • KPI: 8.45% for week ending 12/23/2023 down from 11.04% for week ending 12/16/2023 Week ending 1/6/2024: • Ticket opened to move dashboard from DEV environment to QA (Testing) environment (RITM5616642/REQ5137969) (Completed 1/2/2024) • Ticket opened to move dashboard from QA environment to Production environment (RITM5616649/REQ5137976) (Completed 1/2/2024) • Dashboard moved to production and sched | K: L5 | Completed | L5 | 2023-11-06 | 2025-03-28
Business w/ Tech Initiative: NC Scan and Label Barcode | 33771 | 7311 | Business w/ Tech Initiative | FXG D - Execution | Dock | Tyler Howcroft, Ely Roselius, Haochen Zhang, Joe Melichar | On Track | completed QA review with Sarah Bauer on 2/12 | G: L3 | Active | L3 | 2025-11-12 | 2026-07-07
Business Only Initiative: Re-Label Reduction | 86975 | 7730 | Business Only Initiative | FXG D - Execution | Dock | Chris Gallant, Gregory Mayfield | On Track | Updating milestones | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-25 | 2025-04-03
Business Only Initiative: Post Peak PH Ramp Down FY23 | 14125 | 8102 | Business Only Initiative | FXG D - Execution | Dock | Brett Blackwell, Tray Glover | On Track |  | K: L5 | Completed | L5 | 2022-12-01 | 2023-02-28
Business Only Initiative: [Enabler] Hub Productivity Improvement | 33931 | 8103 | Business Only Initiative | FXG D - Execution | Dock | Barry Williams, Tray Glover, Erin Doyle | On Track | 1/21/2025 -Added Back-up IO. | K: L5 | Completed | L5 | 2023-08-22 | 2024-06-14
Business Only Initiative: [ENABLER] CUBEs Improvement | 68604 | 8105 | Business Only Initiative | FXG D - Execution | Dock | Tim Tam, Tray Glover | On Track | Setting up new Cubes Calculations that will affect Focus Lanes. Set to go live 8/1. - 7/12 New L4 Date set. - 7/12 Calculating new lanes for Q4 - 2/29 Communicate with Field with new lanes and take feedback - 3/1 Feedback Form comms sent to Daily Ground - 2/9 Feedback Form structure decided. (Engineering will own the form) - 2/9 Advanced to L3 - 2/9 Submitted for L3 - 2/8 Advanced to L2 - 2/7 Submitted for L2 Approval - 2/6 Correction from McKinsey Completed - 2/5 Submitted correction to McKinsey - 2/2 L1 to L2 meeting held - 2/2 Updated Milestones to ABLE format. -1/31 Business Case Completed. -1/31 KPIs Completed -1/31 Transitioning to initiative "Cubes 65" as a stand alone project instead of this enabler. | I: L4 | Cancelled | L4 | 2023-11-01 | 2024-10-25
Business Only Initiative: Sortation Certification | 1475 | 8108 | Business Only Initiative | FXG D - Execution | Dock | Barry Williams, Trey Curtain | On Track | Week Ending 7/29/2023 L5 date was changed to October 28th 2023. Actual impact has not met target for the past two month. Required to met target for 3 months running. Week Ending Week 5/13/2023 All certification checklists are due on 5/10/2023. We will have final April results by 5/11/2023. Daily Ground article request will be submitted on 5/11/2023. Results will be entered into Wave on 5/15/2023. Ending 4/29/2023 Hub March results dropped due to large weather impacts, additional NC added to the network (spring peak), and increase to productivity goals. Some hubs consolidated ECON operations into the hub operation which also had an impact to certification results. Hub team provided the bottom 3 hubs to focus on improving TLH to be mentioned during leadership calls. Next steps to transition from L4 to L5 is to focus on the Hub certification rate and find ways to improve monthly metric results. We are going to send Hub certification best practices and ways to improve metrics to the field so they now how to dig into low performing metrics. The Hub team is also going to start posting preliminary results mid-way through the month. This will help hub managers know where they stand and what metrics they need to focus on for the last half of each month. Week Ending 4/22/2023 March Daily Ground was posted on 4/19/2023. March Results: IB: 82.7% OB: 67.1% Hub: 20.0% Company: 73.6% Week Ending 4/15/2023 Updated Hub Certification KPI forecast to hit 70% certified in FY24 July. Impacts were also updated. March results will be final this week. Week Ending 4/8/2023 Continued field certification support Week Ending 4/1/2023 Money step verbiage was updated to align better with savings calculation. Week Ending 3/11/2023 Heather sent out email to all engineering specialists asking for them to review the preliminary file to make sure everything was showing accurately. We got some feedback and was able to update the file before finalizing the results. Results will be final on 3/13/2023. Week Ending 2/25/2023 Added a new milestone where IO will send an email to the Engineering Specialists a week prior to checklists due dates asking them to double check that the file has all stations that are actively opened. This should help with feedback after certification is file. Completed Risk Assessment milestone. The final email to Engineering Specialists and DMs and the Daily Ground article are directing field employees to view the file. Week Ending 2/18/2023 Milestone "Risk Assessment" is completed. The communication is directing more people to the report. Certification rates has also improved since starting communication. This is due to more people being aware of the report and where it is located. Week Ending 2/4/2023 Milestone "Risk Assessment" will be late. IO would like to record January views after communication goes out, otherwise risk assessment would be Peak views only. Canceled milestone 3517. A call with the field would be more beneficial if there was a change in the process. Week Ending 1/28/2023 Mark Grebinoski presented at the Efficiency Council December Certification results. Plan to continue presenting results at least to the end of this FY. We will reevaluate for FY24 if we need to continue presenting the final results. Week Ending 1/20/2023 Results will be presented to either the efficiency or people council in February with January's results. We did not want the first presentation to be a peak month. Milestone #4322 was moved back a month, that change does not affect L4 date. Results were emailed out be Heather Ferlaino. December Daily Ground article was sent out on 1/19/2023. Change of Management milestones were entered. December impact and KPIs were entered. November impact was entered (Nov. KPIs are locked) | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-14 | 2025-09-15
Business Only Initiative: NC Dim Compliance | 31934 | 8109 | Business Only Initiative | FXG D - Execution | Dock | Samuel Ogunbo, Trey Curtain | On Track |  | K: L5 | Completed | L5 | 2023-08-21 | 2024-01-19
Business Only Initiative: [Enabler] Rehandle Reduction | 93597 | 8110 | Business Only Initiative | FXG D - Execution | Dock | Terence Burke, Samir Qattea | On Track | Green. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-09-03 | 2026-05-29
Business Only Initiative: TLH Reconciliation | 68786 | 8233 | Business Only Initiative | FXG D - Execution | Dock | Julia Buchen, Zoe Hinkle | On Track | With the new MIPR process being tied back to the company’s P&L, we no longer need to account for TLH reconciliation within the Domain. | I: L4 | Cancelled | L4 | 2025-05-29 | 2025-05-29
Business Only Initiative: Hubs Sort Elimination |  | 85911 | Business Only Initiative | FXG D - Execution | Dock | Brett Blackwell, Tray Glover | On Track | Initiative no longer needed, hubs have been tasked to create capacity through new sorts and increased sort lengths | I: L4 | Cancelled | L4 | 2025-01-13 | 2025-06-26
Business Only Initiative: [Enabler] Execution Task Force |  | 89423 | Business Only Initiative | FXG D - Execution | Dock | Sarah Bauer, Katelyn Maravola, Karen Easley, Kassandra M. Harden | On Track | On Track | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-20 | 2025-10-31
Business Only Initiative: [Enabler] Field Leadership Focus (Pilot):SouthEast |  | 89426 | Business Only Initiative | FXG D - Execution | Dock | Mary Braud, Sarah Bauer | On Track | After review on the Domain Standup Call on October 30, 2025, it was agreed to cancel this initiative. | E: L2 | Cancelled | L2 | 2025-02-03 | 2025-06-02
Business Only Initiative: [Enabler] FY25 TLH Performance |  | 92129 | Business Only Initiative | FXG D - Execution | Dock | Erin Doyle, Daniel P. Kramer | On Track | 4.2% increase of goals has been implemented and communicated for all dock operations. Pilot programs have launched, and current engineering and management teams are in evaluation stage for each pilot district. Cancellation Request: Scope of initiative has changed to ensuring TLH attainment in FY26. | E: L2 | Cancelled | L2 | 2024-12-18 | 2025-05-30
Business Only Initiative: EMR - Supplies Catalog Restrictions |  | 139977 | Business Only Initiative | FXG D - Execution | Dock | Patrick Snyder | On Track | Sourcing and Procurement to work with Finance on accepting cost avoidance as savings to track for Enterprise Margin Recovery TO Finance stated cost avoidance, does not meet Planview requirements. | D: SL2 | Rejected | Reject Initiative
Business Only Initiative: EMR - Service Channel Work Order Approval |  | 139980 | Business Only Initiative | FXG D - Execution | Dock | Patrick Snyder | On Track | Sourcing and Procurement to work with Finance on accepting cost avoidance as savings to track for Enterprise Margin Recovery TO Finance determined cost avoidance, does not qualify for Planview. | D: SL2 | Rejected | Reject Initiative | 2025-01-13 | 2025-02-24
Business Only Initiative: EMR - HODES Projects |  | 141399 | Business Only Initiative | FXG D - Execution | Dock | Larry Schamus | On Track | Cancel request sent via PDSM ticket INC032604476. | C: L1 | Cancelled | L1
Business Only Initiative: EMR - Preventative Maintenance Reduction |  | 143742 | Business Only Initiative | FXG D - Execution | Dock | Patrick Snyder | On Track | Sourcing and Procurement to work with Finance on accepting cost avoidance as savings to track for Enterprise Margin Recovery TO Finance determined cost avoidance, does not qualify to use Planview. | C: L1 | Cancelled | L1
Business Only Initiative: EMR Powered RTLs |  | 144759 | Business Only Initiative | FXG D - Execution | Dock | Christian T. Lewis | On Track | Collecting information | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Change Default Audit Status to 'Live' |  | 163055 | Business w/ Tech Initiative | FXG D - Execution | Dock | Scott Wallis, Kristi Vaughn | On Track | 9/29/2025 - Completed QA Review with Sarah Bauer 9/18/2025 - Progressing through approval process | E: L2 | Active | L2
Business Only Initiative: Cubes 65 |  | 165736 | Business Only Initiative | FXG D - Execution | Dock | Tim Tam, Clint Damman | On Track | Completed QA review with Sarah Bauer 10/9/25 Completed L3 QA review with Sarah Bauer on 2/25/26 | G: L3 | Active | L3 | 2026-01-01 | 2027-04-01
Business Only Initiative: Operational Readiness Checklists |  | 165750 | Business Only Initiative | FXG D - Execution | Dock | Justine Peters | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Operations Standard Accountability |  | 165868 | Business Only Initiative | FXG D - Execution | Dock | Tim Seaman, Sarah Bauer | On Track | On track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Operations Supervisors Training Organization |  | 165872 | Business Only Initiative | FXG D - Execution | Dock | Christa Abouswid, Sarah Bauer, Brett Blackwell | On Track | Being cancelled due to overlap with the University and other ongoing projects. | C: L1 | Cancelled | L1
Business Only Initiative: Sort Manager Training |  | 165746 | Business Only Initiative | FXG D - Execution | Dock | Daniel Ewert Snyder | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC | 2025-10-06 | 2026-02-11
Business Only Initiative: [Enabler] Peer to Peer Training |  | 89826 | Business Only Initiative | FXG D - Execution | Dock | Daniel Ewert Snyder, Joseph Sasala | On Track | Planning under way for training classes. Building upon exisiting DM training formula. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-15 | 2025-09-01
Business w/ Tech Initiative: Service Change (Intercept) Automation /Change Orde | 83504 | 6832 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Darma Taimuty, Carol Woodard | On Track | Awaiting SCO PEL date. (Need to obtain SCO Greenlight and EGC greenlight.) | E: L2 | Active | L2 Feedback Requested | 2025-01-17 | 2027-10-01
Business w/ Tech Initiative: Collect Error Automation | 10628 | 7880 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | John Ropelewski, Staci Mattson | On Track | Meeting of this initiative for L2/L3 slated for Thursday 12/8/22. From the 12/8 meeting asked to obtain some additional financial information and collect trends. Information will be reviewed on 12/15. Leadership asked for additional research regarding the feasibility of eliminating this service offering. Meetings slated with Marketing for this information. | C: L1 | Active | TEMP L1 - Create L1 LBC | 2023-01-02 | 2025-04-16
Business w/ Tech Initiative: Rating Transportation Charge for Packages Tendered | 2948 | 7882 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Brad Kauffman, Eric Rowland | On Track |  | K: L5 | Completed | L5 | 2022-12-13 | 2023-08-31
Business Only Initiative: FT PH < 30 hours Turnover impact | 1020 | 8800 | Business Only Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Matthew Hensler, Jennifer McKay | On Track | 1.21.25 Update: Initiative is in L5 status. Primary IO is being updatedf rom Jennifer McKay to Matt Hensler moving forward. | K: L5 | Completed | L5 | 2022-12-01 | 2024-09-13
Business Only Initiative: Operations Manager (OPM) Hours Alignment and Overs | 1759 | 8887 | Business Only Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Brian Schroeder, Ian Payner | On Track | 3/12/24 - Volume in February dropped around 10M handled packages per week over Oct/Nov. This is off a baseline of around 170M handled weekly packages. OPM hours did decrease, however the hours did not decrease enough to meet the savings target. 12/14/23 - November performance exceeded goals for the impacts and KPI. ($3.5M actual vs 2.1M forecast, 457 actual on 454 forecast pkgs/hr). 12/7/23 - The initiative was approved for L4. 11/30/23 - Reviewed the L4 checklist with the dock domain and submitted for approval to move to L4. 11/23/23 - Started review the L4 checklist. 11/16/23 - The OPM initiative hit both the financial goal and KPI for October. Plan to go to L4 on 11/30. 11/9/23 - New goals were posted for the impacted facilities. Plan to go to L4 review on 11/30. 11/2/23 - New goals were distributed to the CMO for review with impacted facilities. 10/26/23 - FAQ's were provided to the CMO to assist in adoption of the initiative. The team has addressed the issue with how volume is reported, so now we will review the goals and identify any situations where FY23 Q4 was not a proper representation of the goal for FY24. 10/19/23 - Overall September performance came in positive to plan. 10/12/23 - Monthly results are due next week by 10/17. Team is still evaluating the way volume is reported and how that impacts goaling. 10/5/23 - Still evaluating the options for goal alignment and how volume is reported. Several stations have unique situations where is reported differently then where hours are reported, so productivity calculations do not match goal and performance. 9/28/23 - The monthly reporting has been updated and the report was distributed to field leadership highlighting August performance. The team is still evaluating if any facilities had different operating plans in Q4 of FY23 versus FY24 and may need their goals updated. 9/21/23 - The team is working to update reporting for Phase 2. The updates include ranking facilities within a district or providing a goal attainment percentage and showing the appropriate goal for each month since March for each facility. 9/7/23 - Phase 2 is rolled out and all questions have been answered. Once August data is available, the team will re-run the analysis to address the field questions for operations that operated understaffed in 4th qtr FY23. 8/31/23 - Phase 2 has been fully released to field operations. The primary question from the field has been asking how goals were developed with concerns about facilities that were understaffed in the 4th qtr of FY23. The team continues to address these questions and potentially look at options for adjusting the goals if necessary (however financial commitments must be maintained). 8/24/23 - The DMD/MTM/DM communication was distributed last week. The SRM communication will be distributed within the next couple of days. We have adjusted the format of the goal spreadsheet to make it easier for field ops to understand. 8/17/23 - The phase 2 communication is in final review and will be distributed by the end of the week to DMD's and MTM's. 8/10/23 - The first draft of the Phase 2 communication has been developed and will be distributed to DMD's by the end of next week. Target a Senior Manager communication by 8/23. 8/3/23 - Continue working towards Phase 2 release. 7/27/23 - The final proposal for phase 2 will be reviewed on 7/31 with the RVP's. Once alignment is reached, the communication plan can be started and the information can be rolled out to the field. | K: L5 | Completed | L5 | 2022-11-07 | 2023-11-30
Business Only Initiative: Operations Admin (OPA) Hours Alignment and Oversig | 1867 | 8889 | Business Only Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Staci Mattson, Ian Payner | On Track | 1/27 - all information calls with identified stations have been scheduled. 2/9 - held initiative information calls with Phase 1 identified stations and provided materials for them to use as they start to identify opportunities and develop action plans. 2/23 - communication went out this week to Phase 1 SRMs as a reminder to enter their a/p. TRACS showing approx 1/3 action plans entered so far. 3/3 - communication sent out on reporting tool is now available on field reporting. email follow-up on action plans not yet entered in TRACS. Communication sent out to SRMs that did not have action plans entered as of 2/27 & 3/3. 93% of action plans have been entered. 3/23 - communication on the final 5 stations needing a/p. KPI updates were entered along with Feb. actuals have been entered. Changed over the main KPI to Target facilities only. Feb stats - volume was down 15.5% YoY, OPA hours were reduced by 12%, fell short of, the '12% reduction of hours for the target facilities was greater than the rest of the company with the hours reduction 9.6%. Feb was the rollout month, so official measurement starts in March. 3/30 email to RVP for 2 stations that do not have a/p in tracs. 4/12 Positive results from March stats - updated Impacts and KPI. 5/11 - communication sent out 2 weeks ago to RVP & DMD for March results, waiting on April results. People council presentation on 5/15. 5/18 - updated April results under KPIs and Impacts. Monthly email with April OPA results and reporting was sent to RVPs/DMDs/SRMTMs/DMs. 6/1 - waiting on May results. Request on T/O stats for Drive locations shows no direct correlation. Meeting next week to discuss Phase II facilities and goals. 6/8 - May's results were entered under KPIs and Impacts. Held the first meeting to discuss Phase II facilities and goals. 6/15 - May results were sent to the RVP & DMD. Work continues on phase 2 facilities. 6/22 - Met with Joey this week to cover the FY23 baseline changes and new targets. 6/26 - Met on 6/28 to continue the discussion around phase 2 facilities. 7/20 - Met on 7/14 to review phase 2 options, entered June results in WAVE, met on 7/19 to finalize the phase 2 plan for all stations and their goals. 7/27 - Phase 2 plan finalized and will be shared with the RVPs on 7/31, if no requested changes are given, it will be rolled out to the field. Communications to be developed for rollout. 8/3 - Meeting set up for 8/8 to work on the communication to the field regarding phase 2. 8/17 -July impacts and KPIs were entered in WAVE. positive results for the month of July. 8/24 - DMD communication was sent out for Phase 2. working on SRM communication with more details. posted tools and goals for the stations i n the field reporting DRIVE folder 8/31 - closed out the phase 2 communication milestone. addressing any questions from the field after last week's rollout. KPI's were updated for phase 2. 9/7 - updated a CMO DRIVE deck with Phase 2. Running data for QTR1 to compare to QTR 4 for Phase 2 to analyze where we may need to adjust some goals for stations. 9/14 - updated KPI and Impacts with August results which were above goal for both areas. 9/28 - monthly email to DMDs was sent out last week. KPIs - action plans are no longer required for the phase 2, so that is being zeroed out 10/19 - sept results KPI/Impacts were entered, positive results > targets. Action plans are not being tracked for Phase 2 - so that will be zero going forward. 11/2 - Amy attended a CMO call last week to answer any questions from the CMO team on their assistance with this initiative. FAQs were posted to the folder for field access. Goals were adjusted for 22 stations after analysis from finance on changes from Q4 to Q1 productivity in locations that were 15% lower in Q1 due to being understaffed in Q4 data that was initially used. 11/16 - entered oct results, Oct was a positive month. 11/28 - L4 checklist complete with money step attachments included 11/3 | K: L5 | Completed | L5 | 2022-12-06 | 2023-11-30
Business w/ Tech Initiative: Customer Service Case Automation (CSCA) | 3545 | 9016 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Jeremy Dolan, Eric Rowland, Ashley Semple | On Track | **Update 4/23** Rebaseline completed **Update 4/10** a. MVA for March updated b. Key KPI exceeded forecast c. CSCA Dashboard is rolled out to the field and being used for reporting **Update 3/14** a.Response rate reporting continues to rise each week to ~39% up from ~23% at the inception of reporting. b.Execution Task Force Calls continue to be held every Thursday with project team and bottom performing district representatives c.Ashley continuing to be onboarded to the project & created P&D forum slides to be published this month around enhancements to CSCA d.SMS alerts functionality being moved to production this weekend e.Jess is continuing her work on CSCA powerBI reporting/dashboard, we meet weekly on Thursdays f.Reforecast was presented and approved by Jim Moore g.Set up Office Hours calls in March to field questions from the field, have had 90+ acceptance emails h.Continuing to answer questions from the field, generally QPS’s via CSCA_Support@fedex.com email i.Partnering with SPS and legal to create a SPS-Facing deck that we will push operations to present to their AO/BCs **Update 3/7** **Going forward - ALL UPDATES TO CSCA INIT. ACTIVITY WILL BE POSTED HERE** -Execution task force meetings on going. -Feb and March MVA values reforecasted and approved -Feb MVA still under target -Weekly adoption %s continue to rise though, up to 38.6% **Update 2/13:** **Going forward - ALL UPDATES TO CSCA INIT. ACTIVITY WILL BE POSTED HERE** -Project Added to Execution task force, activities started -Execution task force focus group created with SME's and stakeholders -Backend planview issue is prohibiting the addition of execution task force milestones. Help Ticket raised, still no resolution -Ad-Hoc reporting expanded to MDs/DMs this week, previously was to all QPS's -Presenting at QPS monthly meeting 2/13 to drive adoption -Presenting at RVP meeting 2/24 to drive adoption -Modern reporting solution for CSCA is in flight -MygrounBiz landing page for CSCA instructional resources is in flight -CSCA Sharepoint site with instructional resources is and has been actively communicated -January MVA numbers are complete and entered -Additional communications around general CSCA information and CSCA enhancements being planned. **Update 12/27:** Still running ad-hoc response reporting weekly myself Demand feature requests are entered with CE Data & Analytics team to expand and restructure the dashboard they created to fit the business/operational needs data-wise App training videos: Desktop version: Done AO_BC Videos Posted to Case EBS sharepoint site, alerted QPS Eng Support team to distribute to select group of QPSs to utilize for now Mobile version: In Progress by Alexis Smith Demo Mode for CSCA - Being looked into by Case EBS IT/product management - could help station staff familiarize themselves with the app Will return to RVP meeting when adoption resources are completed Will schedule a post-peak retraining/refresher course that I'll lead and likely pull in operational folks to that have had success with the application **Update 12/8:** Savings entered for November MVA KPI's entered (all 3) for November MVA Cost information entered for November MVA CSCA responses vs CSCA eligible cases is still low (8%), but higher than October (6%). Videos and MGB centralized CSCA resouce location still in the works. **Update 11/13:** - Cost actuals entered - Savings entered using actuals & finance's calculation spreadsheet - Reviewed with Joseph Schuler (covering for Janet while on vacation). Provided statement explaining lower than expected adoption rate (below KPI's). - 2/3 KPI's entered (see below) **KPI's** **2/3 KPI's Entered** - (Manual vs automated case % for CSCA-eligible cases) - **Done** - Source CE IT: Manager - Shiva Samula - Average Case Resolution time % Month over Month - **Done** - Source: CE Data & Analytics "CHIPs" dashboard - Manager: Tessa Newell - Repeat callback reduction - There used | I: L4 | Active | TEMP L4 - Enter L4 | 2023-11-01 | 2025-06-05
Business w/ Tech Initiative: Electronic Supplemental ISP Data Collection Report | 3556 | 9017 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Daniel Badillo, Eric Rowland | On Track | 10/9/24 - September MVA updated. 8/13/24 - July impacts updated. 4/29/24 - April Impacts and KPIs have been reforcasted. 4/9/24 - RCC ART Milestone work has been started as of 4/1/24. 3/4/24 - Milestone "Non-tech Standard Operating Procedure Change" has its status marked as completed. 2/27/24 - Clerical and Supply Impacts were updated to reflect the new minutes used per P&D day handling the report. KPI was left as is. 11/30 - The project is moving to capture savings FY24 February through non-tech solution ahead of the electronic solution. 8/24 - The decision to side with Trimble or Dataworks has been made. We are going with a Trimble solution. 8/2 - The decision to use a Dataworks Solution or Trimble solution has been escalated to domain leadership. 7/26 - We have collected the requested data and can query for more when we need it. We are awaiting a decision on the path forward from leadership. Whether it's a Trimble solution, Dataworks solution or a combination of both. 7/5 - The parties necessary to gain the information we require have returned from vacation and we are awaiting their results. 6/29 - Team members needed to assist in gaining information regarding the scope and potential costs are out this week and we expect an answer next week. 6/21 - Information regarding State by State Odometer readings have been gained and we are awaiting additional information to satisfy the questions of Trimble. 6/14 - Status has not changed, are awaiting the data that is collected from these examples. 6/7 - Information was gathered regarding the process for collecting total odometer readings across state lines. This information was sufficient to move forward with our next step. Next step is to find examples of work areas that cross state lines to determine what fields and how the data looks once collected. 5/31 - Status has not changed, awaiting meetings with the proper teams. 5/24 - Meeting with the proper teams to answer the pending questions from TRIMBLE. Answers expected by end of week. 5/18 - Awaiting the response from the TRIMBLE team. Meeting will be set up in the coming week. Researching how the funding request would be handled. I don’t think we should lock this one into the bankable plan yet and get an update from Tracci on that discussion next week. | K: L5 | Completed | L5 | 2022-11-29 | 2026-08-19
Business Only Initiative: Outsourcing of In Transit Quality Assurance (ITQA) | 4982 | 9048 | Business Only Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Eric Rowland, Nicholas Ciarletta, Jacob T. Meyer | On Track | 3/12 Due to some enhancements to NCR label types in February, we had a dramatically reduced video code volume. Certain stations that had previously had high volumes of this specific package type had up to 5k fewer packages available for video coding this month resulting in savings coming in under plan. Additionally, with the tight margins we were expecting until we go down to one vendor, the costs for the month of February were higher than the benefits, resulting in a 5.2k net loss. Depending on March volume this may be something we will see again, however once we go down to a single vendor we will see positive savings return. 2/8 Updated Impacts and KPI's based on new forecast with lower volume and timeline for the switch to a single vendor. Further changes to vendor costs are expected to take place following the change to a single vendor. 1/23 Update to the L5 date to mid to late April to use March MVA 1/7 The first couple weeks of December trended with volume forecasts, however the second half dropped off and was well below expected volumes bringing our monthly volume and savings down below forecast. We are now looking at January volume numbers to see if we need to reforecast volume and savings based on current volume. The L5 date will also need to be pushed back to mid April so we are able to include March numbers, assuming we are able to hit the forecast over the next couple months. 12/7 There was a brief outage on 12/6 resulting in the vendors receiving no images for a couple hours. This had no impact on total packages submitted by the vendors and didn't require any station intervention. The vendors are continuing to monitor the situation but it appears to have been small downtime during a server reboot. 11/30 Cyber Monday volume was above the average but still within the capacity of both vendors, and vitally no outages occurred during this week. We continue to monitor the situation at a heightened level but it appears the impacts of peak volume have not had a major influence on vendor performance. 11/23 Unfortunately we have had to push the tech change back to post peak with a mid January date planned. Included with this will be more security enhancements as needed. Both vendors have been running smoothly, with no concerns about volume thus far. 11/16 The vendors have continued to video code just over 95% of all packages requiring data entry. There was a brief outage over the weekend, which had very little impact on the total volume handled by the vendors. Looking forward at peak volume, the image API can be a constraint as both vendors are currently using this API at its maximum capacity. If this capacity is increased, the vendors will be able to handle the peak volume, and will be able to perform video codes closer to a FIFO method, removing the need for stations to perform video codes on premium volume or any other packages that are worked early. 11/9 Meetings have been taking place to discuss implementing tech changes prior to peak, all parties are on board and ready to start the work as soon as the needed approvals are given. This work will give the vendors additional capacity for peak volume and help them cut into the 5% gap by working premium volume and other packages that station staff are currently working. 11/2 There was a brief outage over the weekend due to the role swap that took place upstream of us. There was relatively little impact on the vendors, as they were able to form a queue of packages ready to submit and reattempt all of them after the outage was fixed. We are making sure both vendors are added to a mailing list and will be informed when updates like this are taking place in the future so they are more prepared for a potential outage. 10/26 During the month of October, compliance numbers have had little change compared to September. This has largely been related to premium volume and other issues that there are currently no planned solutions for. Originally all Alaska and Hawaii stat | K: L5 | Completed | L5 | 2022-01-03 | 2023-11-22
Business Only Initiative: [ENABLER] Resolution for Inaccurate Task Codes | 17851 | 9376 | Business Only Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Cassandra Mott, Michael George | On Track |  | K: L5 | Completed | L5 | 2023-06-07 | 2024-04-30
Business w/ Tech Initiative: In-Station Consolidated Quality Assurance VB1 | 87369 | 9494 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Jeremy Dolan, Ashley Semple, Eric Rowland | On Track | **Update 10/23** •L4 Date o3/31/26 oCode is being deployed to production, but toggled on only to select pilot locations either 10/24 or 10/27 depending on when final approval from leadership is completed oFull rollout to Fedex surface pushed back to post-peak •Unable to deploy changes during peak black out period and concern over 1.) rushing the change pre-peak and 2.) measuring results for DRIVE during peak based on that change •Current Status oL4 date is 3/31/26 oSuggested by domain and approved 10/23 by domain leadership •Work completed in the last 2 weeks oTesting completed and demo’d oPresented update to domain leadership 10/23 oMVA reporting for changes already released related to Redirect to Hold •Work In Progress oCommunications distributed to selected pilot locations •Next Steps oDistribute communications via The Source and to QPS’s oIdentify Express channels to similarly communicate changes oTrain impacted pilot locations •Risks/Awareness oN/A, changes made to L4 date and approved. **Update 7/24** •What has been completed: oSolution Delivery documentation finalized and given to development team oSolution Delivery documentation accepted by development team, no issues o1 PI estimate for work to close out ISCQA VB1 #9494 from 7/18/25 (9/24/25 is 10 weeks/1 PI) oMet with Field Mgmt. and Clerical staffing pod project management and determined a new L4 date of 10/24 oPresented to Dock domain on 7/24 and were approved for both L4 date change and adjustment to financials associated with that change oLisa Payne’s org. reached out late 7/23 about pulling our architectural resources for the project •Architecture is complete, seems to be no impact because of the above but gathering more information •What is in progress (next 1-2 weeks) oDevelopment oDemos oUpdating planview with new L4 date & accompanying milestone dates •What are next steps (2+ weeks) oDevelopment oDemos oTesting oISCQA VB1 Pt1 KPI reporting in planview •Health (RAG) status of the entire initiative and the SCO portion of work oHealthy •Any leadership support needed oI would like to understand where/why the decision was made to pull architectural resources, regardless of whether it has an impact on the project or not. We were given no warning or heads up. If we were not able to get the solution delivery completed for 9494 last week we would be stopped in our tracks and left in limbo – again. Bad business practice and bad communication from the governing parties across the board. | I: L4 | Active | L4 | 2024-03-19 | 2026-03-31
Business w/ Tech Initiative: ISCQA #2 - VB2+ |  | 94029 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Jeremy Dolan, Ian Payner, Eric Rowland | On Track | **Update 10/28/25** - Direction given by EPC to proceed if capabilities in ISCQA VB2 have no impact or test only impact outside of SCO. - Proceeding with capabilities 1, 2 and their associated functionality and cost savings. Dropping DG&Haz capability due to reliance on commercial and platform impact > test only. - Platform confirmed test only impact, awaiting greenlight - Commercial confirmed test only impact, awaiting greenlight - On Schedule for SCOPEL 11/13/25 **Update 3/14** a.Presented and Approved for L2 b.Ticket submitted to resolve PV issue. VB2+ is in L2 officially. c.Decomp/Solutioning is “Paused” by Dan Knophmacher’s team until further notice as discussed before. **Update 3/7** -Presented to dock domain leadership to move from L1 to L2 -Awaiting necessary approvals -Initiative decomp and solutioning "paused" until resources are available for initiative to be picked back up. **Update 2/13** Decomp for ISCQA #2 VB+ is **paused** by PRT. Reason being - Architectural resources will be redistributed to work on higher ranking enterprise initiatives until told other wise. Instructions going forward from PRT: 1. Continue to move init. to L2 2. Complete Lean Business Case in PV 3. Answer outstanding questions for VB2+ from architects outside of paused working sessions 4. Prepare for if/when decomp resumes on init. ------------------------------------- VB2+ is included in this planview initiative and is actively undergoing decomp. | G: L3 | Active | L3 | 2024-11-01 | 2026-06-17
Business w/ Tech Initiative: Manual QA Closure Scan Elimination |  | 96381 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Jason O. Word | On Track | Status is green | E: L2 | Active | L2 | 2026-03-02 | 2026-12-21
Business w/ Tech Initiative: Service Change (Intercept) Automation VB2 |  | 139983 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Darma Taimuty, Carol Woodard | On Track | This is second value bundle of four. Foundational work is being completed in VB1. It is very important to move this forward to ensure work is completed as most cost savings is included in VB1. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Service Change (Intercept) Automation VB3 |  | 139987 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Darma Taimuty, Carol Woodard | On Track | Preparing to submit to L2. | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Service Change (Intercept) Automation VB4 |  | 139990 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Darma Taimuty | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Van Service Audit Modernization |  | 165812 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Brad Kauffman | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Wearable 3.5 Sortation Applications Modernization | 87338 | 8118 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Krzysztof Gawel, Tristan Possessky | On Track | Working to move the project into L3. Financials are incorrect as Planview only goes from 2022 to 2028. This project has financials that extend into FY30. Document from Finance is available upon request. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-05 | 2026-10-29
Business w/ Tech Initiative: [Enabler] Dock/QA/Garage Replacement Device | 87337 | 9540 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Krzysztof Gawel, Aaron Jones | On Track | Working to move to L3. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-08 | 2026-10-30
Business w/ Tech Initiative: Common CONs - Value Bundle 1 |  | 89829 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Erin Wise, Negar Solgi | On Track | On track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-14 | 2026-04-30
Business w/ Tech Initiative: LEO In Station App Retirement |  | 190299 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Jeremy Dolan, Eric Rowland | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Gen AI Address Research |  | 163050 | Business w/ Tech Initiative | FXG D - Field Mgmt & Clerical Staffing | Dock | Eric Rowland, Daniel Badillo | On Track | Working LBC | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Dock QAT Teams (Hub Process Improvement) | 58848 | 7273 | Business Only Initiative | FXG D - Planning | Dock | Tony Palmentera, Sarah Bauer | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2023-10-31 | 2025-08-21
Business w/ Tech Initiative: [Enabler] RFID - Vehicle Loading and Unloading | 91675 | 7280 | Business w/ Tech Initiative | FXG D - Planning | Dock | Daniel P. Kramer, Daniel Bonnett | On Track | The RFID Proof-of-Concept projects at ECLE, COVI, and AFWH are still in the process of being stood up. The installation process is complete at ECLE and RFID data is being captured and sent to Atlas. However, Dataworks is currently working to make the RFID data available to the Operations Workstream to allow for meaningful analysis. We are working with DataWorks to get a PowerBI dashboard to show information on the RFID scans. We would like the dashboard to capture the following: First and last read of RFID tag at specific load door, including date and time Load door number associated with each read RFID tag Total number of unique RFID tags read at a specific load door and the corresponding trailer number Total number of unique RFID tags at all load doors and all corresponding trailer numbers System should check for re-reads every 15 minutes System should alert if package does not belong in the load Justification for cancellation: No progress has been made besides updated time studies and cost analyses. This initiative is more of the future state of RFID (1-2 years from now). The resources for RFID are currently focused on the 7 projects selected to highlight what RFID can do, and this use case was not included in that portfolio. As information: Current analysis shows that the initiative will cost more money than it saves due to labor hours. It's more of a visibility tool than a cost savings initiative. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: [Enabler] RFID - Package Sortation and Movement | 91747 | 7281 | Business w/ Tech Initiative | FXG D - Planning | Dock | Tim Tam, Tray Glover | On Track | Higher priority RFID projects ahead of this one. Also, waiting for finalized "standard" RFID implementation for the network to know true capabilties vs pilot facilities that are much more heavily equipped. Unclear when the 7 other projects will conclude. | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: EMR OTC - RFID - Customer Pickup Solutions | 92649 | 7284 | Business w/ Tech Initiative | FXG D - Planning | Dock | Megan Aurin, Nathan Tonkinson | On Track | Added analysis for margin recovery 11/3/25. Completed SL2 QA review with Sarah Bauer on 5/28/25 | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: RFID - Package Loss and Recovery | 92664 | 7285 | Business w/ Tech Initiative | FXG D - Planning | Dock | Brittany L. Rowlett, Daniel Bonnett, Nathan Tonkinson | On Track | Initiative is on track and primary ownership is being transferred to Brittany Rowlett Completed SL2 QA Review with Sarah Bauer on 5/13 Completed QA Review with Sarah Bauer on 7/15 Data and AI DRIVE Triage meeting completed on 8/15 (Approval to add Rachel wood as PEO on 10/21). SCO Greenlight meeting completed on 9/26. This meeting is to review task needed for approval. Andrea Ards name has been added as the PEO. SLC was able to match a high value shipment with a material value of $94,498.05. This package was sent to the recipient, avoiding a potential claim. We do not know what the actual claim amount is, but the value of the shipment. Shipment was located while testing the ability to decode a RFID tag to get more researchable information. Customer Experience SOPS updated to prompt questions to the Shipper if an RFID tag was on the item or box. * Revisiting the proposal to ensure we are capturing the right audience. Meeting on 10/24 with other stakeholders. * Task- Complete business rules and process flow. Focus on priority shippers. | E: L2 | Active | TEMP L2 - Enter Value Prop | 2026-01-08 | 2026-08-19
Business w/ Tech Initiative: [Enabler] RFID - Core IT Development Work | 96465 | 7287 | Business w/ Tech Initiative | FXG D - Planning | Dock | Daniel Bonnett, Cody J. Rose, Sarah Bauer | On Track | Initiative is currently on track | I: L4 | Active | L4 | 2024-04-01 | 2027-06-16
Business Only Initiative: Dock QAT Teams II (IB Specialists) | 30845 | 7785 | Business Only Initiative | FXG D - Planning | Dock | Chris Newman, Sasha Sosebee | On Track | On track | K: L5 | Completed | L5 | 2023-05-01 | 2024-06-28
Business w/ Tech Initiative: Enhanced Engineering Demand Planning - VB1 | 514 | 8100 | Business w/ Tech Initiative | FXG D - Planning | Dock | Andrew Tenore, Brett Blackwell, Tray Glover, Daniel Ewert Snyder, Yancy Haggard | On Track | On Track | I: L4 | Active | TEMP L4 - Enter L4 | 2022-12-19 | 2027-08-20
Business w/ Tech Initiative: Enhanced Engineering Demand Planning - VB2 | 2146 | 8101 | Business w/ Tech Initiative | FXG D - Planning | Dock | Yancy Haggard, Brett Blackwell, Tray Glover, Amy Raduzycki , Andrew Tenore | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-01-01 | 2026-07-10
Business Only Initiative: Prime Optimization - Hub & OB | 511 | 8111 | Business Only Initiative | FXG D - Planning | Dock | Trey Curtain, Tray Glover | On Track | on track | K: L5 | Completed | L5 | 2022-01-04 | 2023-06-01
Business Only Initiative: Sorted but not delivered (commercial volume on wee | 11393 | 9149 | Business Only Initiative | FXG D - Planning | Dock | Heather Mullins, Mark Grebinoski | On Track |  | K: L5 | Completed | L5 | 2022-12-01 | 2024-07-31
Business w/ Tech Initiative: Network Operating Plan (NOP) Sort Plan - 2 week | 515 | 9429 | Business w/ Tech Initiative | FXG D - Planning | Dock | Junbo Wang, Kevin Patch | On Track | Milestone 4039 - Value Bundle 1.1 - Rollout/ Adoption will be late to start due to an issue discovered during UAT (User Acceptance Testing) testing. Anticipated delay is one week. No anticipated impact to other milestones, field users, or dependencies for other initiatives. Failures in the process were identified, documented and resolved within 24 hours. | K: L5 | Completed | L5 | 2022-05-11 | 2025-06-09
Business w/ Tech Initiative: Network Operating Plan (NOP) Sort Plan - Peak&3mo | 11084 | 9440 | Business w/ Tech Initiative | FXG D - Planning | Dock | Junbo Wang, Kevin Patch | On Track | Currently, all the technology related tasks for NOP 1.4 has been completed. The 3 month projection is posted in the NOP Sort Volume Projection Dashboard, all relveant stakeholders has been comunicated. The NOP Peak model is ready to use for Peak FY26. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-11-06 | 2025-10-02
Business Only Initiative: Smalls Scan Performance | 513 | 9452 | Business Only Initiative | FXG D - Planning | Dock | Phil Eskew, Mike Lininger | On Track | 02/26. Uploaded OB Sort Quality Review (OB SQR) Analysis. Analysis provided a comparison of results across 3 Districts (October vs January). 03/01. Early Clock-in Results integrated into Small Scorecard Engaged bottom performers on Early Clock-in Metric/STD Attainment. Bottom performers contacted: 03/16-03/17. ELOU-400; ALTA-303; EBAL-209; BLDR-806; AUST-311, ROBB-086; 925-WRLT; 293-SPAR; 762-NFTW; CAMD-081; EALN-316; ALBA-122 03/21-03/23. CHAR-282; RKIS-612; TACO-994; NPIT-150 03/27 SCRA-185 04/04 LNXA-641, ATLA-303 04/12 753-DALL | K: L5 | Completed | L5 | 2022-01-03 | 2024-08-09
Business Only Initiative: Dock QAT Teams (IB Specialists) | 521 | 9463 | Business Only Initiative | FXG D - Planning | Dock | Mark Grebinoski, Chris Newman | On Track | Initiative is on track 3/31 - March stations visited being provided to Deji for the monthly tracker to be calculated. 4/12 - Impacts and KPI actuals updated with March results | K: L5 | Completed | L5 | 2022-01-03 | 2023-03-31
Business w/ Tech Initiative: Databricks Workspace- Surfacing Eng Support |  | 98829 | Business w/ Tech Initiative | FXG D - Planning | Dock | Phil Eskew | On Track | While waiting for creation of new workspace, team continues to pursue securing required data tables in Atlas (waiting on fulfillment of data ingestion request that was submitted in October, 2024) as well as familiarize with future tools available in similar VDAP environment | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: RFID Bulk Delivery Manifest (BDM) |  | 110602 | Business w/ Tech Initiative | FXG D - Planning | Dock | John Ropelewski, Staci Mattson | On Track | June 4-DOCK POD mtg. June 6-Meeting regarding KPIs for BDM June 9-Meeting with OPS tech-new RFID engineer -Status update provided to PM June12-RFID meeting-deep drive with Marketing -Data collections from POC management regarding BDMs sent to PMs and Marketing June 16-Status update provided to PM June 18-RFID meeting-anchor use case for full implementation -DOCK POD meeting June 23-Status update provided to PM June 24-PDSM open to change initiative to Customer Experience ESI -Meeting continuation of anchor use case for full implementation June 25-Meeting with OPS Tech regarding RFID printer and wearable technology June 26-RFID meeting, financials relook with Finance June 27-NPIT RFID equipment testing for preload June 30-Meeting regarding customer who might benefit from RFID July 2-Meeting with Enterprise Architect -DOCK POD meeting July 8-Meeting with Enterprise Strategic Program Management regarding initiative Service impact July 9-Status update provided to PM July 11-Meeting with Ops tech team to discuss next steps for RFID BDM July 15-Review of Planview dock POD information as EA review completed for Friday SL2 meeting -Completed QA Review with Sarah -Email from the Enterprise Architecture group confirming L1 Architecture Alignment Completion July 16-DOCK POD Mtg. July 17th-Re-review of Planview information for SL2 meeting for Friday Future-July 18th-SL2 meeting with Zoe Hinkle and Jim Moore for approval to L2 status | E: L2 | Active | L2 & CCH
Business w/ Tech Initiative: [Enabler] RFID & FedEx Label Automation |  | 142115 | Business w/ Tech Initiative | FXG D - Planning | Dock | Daniel Bonnett | On Track | Completed SL2 QA Review with Sarah Bauer on 12/15/2025 | E: L2 | Active | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: RFID Analytics |  | 153532 | Business w/ Tech Initiative | FXG D - Planning | Dock | Nathan Tonkinson, John Ropelewski | On Track | Mitigation plan in place with manual runs of VDAP that will work indefinitely | E: L2 | Active | L2 | 2026-03-23 | 2026-04-29
Business w/ Tech Initiative: Hiring App / Web Tool | 508 | 6672 | Business w/ Tech Initiative | FXG D - Staffing | Dock | Beth Bowman, Christy Begley | On Track | Per the guidance provided in the Dock meeting today, I updated the following milestone dates to reflect the pilot extension: Pilot End Date (from 05/18 to 06/07) Policy & Procedure Publish (from 05/18 to 06/07) Company Wide Rollout (from start date 05/18 to 06/07) As of May 31, 2024 we have received 1,960,543 applications, hired 328,217 package handlers in 14 days on average across the network. To help reduce over sourcing the team was prepared to implement Paradox's Candidate Volume Optimizer tool that would help monitor applications in the job and unpost the position to reduce over sourcing. During our pilot phase with ~20 locations, we did realize reduction in over sourcing of applicants. | K: L5 | Completed | L5 | 2022-11-01 | 2024-10-31
Business Only Initiative: Ops Supervisor HC Attrition | 83004 | 7164 | Business Only Initiative | FXG D - Staffing | Dock | Jacob Humble, Dawn Perry | On Track |  | K: L5 | Completed | L5 | 2024-01-23 | 2025-01-31
Business Only Initiative: P&D Manager and Ops Coordinator attrition | 97246 | 7592 | Business Only Initiative | FXG D - Staffing | Dock | Joseph Schuler, Jacob Humble | On Track | 2/27 - reforecast February FY25 | K: L5 | Completed | L5 | 2024-11-20 | 2024-11-20
Business w/ Tech Initiative: [ENABLER] PH Training Compliance | 2032 | 8893 | Business w/ Tech Initiative | FXG D - Staffing | Dock | Lee Anne Pontis, Amy Spence | On Track |  | K: L5 | Completed | L5 | 2022-04-11 | 2023-10-16
Business w/ Tech Initiative: FXG: New Hire Administration Automation | 3479 | 9013 | Business w/ Tech Initiative | FXG D - Staffing | Dock | Lauren Boehme, Lee Frye | On Track |  | K: L5 | Completed | L5 | 2023-03-29 | 2024-03-22
Business Only Initiative: [Enabler] Ops Supervisor Scheduling Oversight | 83006 | 9386 | Business Only Initiative | FXG D - Staffing | Dock | Clinton Dodds, Megan Le | On Track | 2/10/2025: •Switching to an enabler initiative – Presenting to Jim on 2/20 oFindings from this initiative will help create business case for technology development •7 additional facilities were identified for the pilot. Communications will begin this week oLooking to include in Feb 27th autoschedule 2/4/25 * Analyzing OVT to determine additional facilities to POC * Review Friday on direction of Strategy (cont. as POC or enabler) * Tracking KPIs for current POC facilities 1/28/25 * Ironed out the understanding and planning for the current initiative and its goals. * Team will meet tomorrow to present additional facility options and justification in order to expand the proof of concept to gain additional data. * KPIs will be tracked in order to provide justification toward the follow-up initiative where we work toward a potential launch - if this initiative is successful. 1/14/2025 * First schedule for 4 facility POC launched on Thursday 1/9 for this upcoming Sunday 1/19 * hiccup mgrs able to edit themselves/peers. BY has resolved * Finalized KPI (SC, usage, non sort hours, non sch hours) * Lead/ Specialist in Dallas to support rollout | K: L5 | Active | TEMP L5 - Enter L5 | 2025-01-09 | 2025-05-05
Business w/ Tech Initiative: Hire Ahead (Algorithmic Sourcing Tool) | 507 | 9451 | Business w/ Tech Initiative | FXG D - Staffing | Dock | Melissa Hopkins, Beth Bowman | On Track | Approved by dock domain to cancel 12/11/25 * IT issues began causeing issues with model runs starting in August 2025, has not been a successful model run since Nov 6th 2025 * Consistant low adoption with the Hire Ahead tool since Launch despite numerous communications and training * Odyssey (Recharge phase 3) will cause the HA tool to break fully due to job and location architecture changes * Exploring partnership with Enterprise People Anayltics team on absorbing HA capabilities into the new WFM tool Dependancies have significant potential to impact timeline for development * Surface ART (Timekeeping/P&P) to create 2 Gateways for APIs * Datawoks Hire Ahead > Gateway > Paradox * Paradox > Gateway > ERMA Dataworks is dependant on the establishment of the gateway to finalize development work to stay on track * as of 11/21/24 Waiting on PDX to expose elements in the API for consumption * Timekeeping/P&P ART is waiting on passing dev work to teams until these are exposed ***Approval to remove the API work from scope obtained | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-06-01 | 2026-01-30
Business Only Initiative: [Enabler} VTO - Package Handler Voluntary Time Off |  | 87793 | Business Only Initiative | FXG D - Staffing | Dock | Andrew McConkey, Amy Raduzycki , Dawn Perry | On Track | Started to put together a plan for re-educating field, training written, trainers, signed up, sessions created. FAQ created | K: L5 | Active | TEMP L5 - Enter L5 | 2024-10-15 | 2026-03-18
Business Only Initiative: Redistribution of Excessive FEC Non-Exempt OT |  | 104460 | Business Only Initiative | FXG D - Staffing | Dock | Mark Centofanti, David Henderson | On Track | Completed SL3 QA review with Sarah Bauer 5/8/2025. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-02 | 2026-04-24
Business w/ Tech Initiative: [ENABLER] Enhanced Engineered Demand Planning - N2 | 57663 | 6911 | Business w/ Tech Initiative | FXG D - Staffing | Dock | Zach Schneider, Chad Verbeek | On Track | Initiative is actively rolling out as of April FY25 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-02-01 | 2025-10-31
Business Only Initiative: GV Surface Tech Mobile Device Repl/Upgrade |  | 103539 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Joseph H. Vu, Diego Guadalupe | On Track | Deplyment of replacement devices >90% completed development of SOP and training in progress | G: L3 | Active | TEMP L3 - Enter L3 | 2025-02-17 | 2026-05-29
Business Only Initiative: GV Surface Tech Performance Scorecards Assessment |  | 103543 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Diego Guadalupe | On Track | On L3 started launch process Math with calculations to savings and analysis is attached to support docs Excel spreadsheet. Are they not visible? Otherwise where should these be loaded? Do you want us to send an email with the attachments or a call. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-11 | 2027-05-28
Business Only Initiative: GV Surface Field Maintenance Admin Supp Assessment |  | 103547 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Randy M. Steinhorst, Diego Guadalupe | On Track | Initiated assessment | G: L3 | Active | TEMP L3 - Enter L3 | 2026-03-31 | 2026-12-25
Business Only Initiative: Eliminate Low Value Maintenance |  | 105887 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Kelly Kull, Jacob Hanson, Keith Anderson | On Track | Initial calculations and review with McKinsay and finance. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-04-17 | 2025-04-17
Business Only Initiative: Strengthen Vendor Maintenance Controls |  | 105891 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Jacob Hanson, Keith Anderson, Kelly Kull | On Track | Strengthening vendor oversight and controls to reduce labor hours based on FY23 actual labor hours. Implementing key metrics to measure vendor performance, additional contractual controls, and standard business review processes to recognize positive maintenance vendor pefromance and correct poor vendor performance. | I: L4 | Active | L4 | 2025-03-03 | 2026-04-17
Business Only Initiative: GV Surface Parts Inventory Min/Max Automation |  | 108341 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe | On Track | Loading information | E: L2 | Active | TEMP L2 - Enter Portfolio Greenlight | 2025-08-04 | 2027-08-06
Business Only Initiative: GV Surface Warranty Process Review |  | 109290 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe, James Morris | On Track | Working details | G: L3 | Active | L3 Feedback Requested | 2025-06-02 | 2028-05-31
Business Only Initiative: GV Surface GV Max Adding Service Items Automation |  | 109293 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe | On Track | Working details | G: L3 | Active | L3 Feedback Requested | 2025-06-02 | 2028-05-31
Business Only Initiative: GV Surface Improve Special Orders Parts Process |  | 109297 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe, James Morris, Kyle Mitchell | On Track | Working details | G: L3 | Active | L3 Feedback Requested | 2025-06-02 | 2028-05-31
Business Only Initiative: GV Surface Int'l Mobile Device Dep Assessment |  | 109302 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | James Morris, Diego Guadalupe, Paco Esmeralda III | On Track | On November 5, 2025, David Kemeni, District Fleet Manager for CDG, submitted to Global Vehicles WHQ the 2 iPad models CDG is considering and asked whether to use a data plan or Wi-Fi. I responded that either model iPad would work and the U.S. and Canada Technicians are using Wi-Fi with their iPads. On September 23, 2025, CDG repsonded with the following: Currently working at sourcing 3 samples through IT teams Then will set up the trial, assessment (ABLE) if ok , will set up a business case for our MD/VP get it implemented in CDG in parallel will also include recommendations for EU (LGG, STN, CGN, FR) On September 4, 2025, GV-WHQ met with David Kemeni from CDG to share the process of creating a buisness justification document for funding, process of acquiring the devices, and the process of adding the devices to the Airwatch console. Verizon (USA) confirmed devices must be purchased locally and activations must be completed at the Technician level using LDAP. We are currently awaiting feedback from CDG | E: L2 | Active | L2
Business Only Initiative: GV Surface PM E-Forms |  | 109305 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe, James Morris | On Track | Working details | I: L4 | Active | TEMP L4 - Enter L4 | 2025-10-06 | 2027-06-29
Business Only Initiative: GV Surface GV Max Activate MSPL Vehs/GSE |  | 109308 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Diego Guadalupe, Janice Jones | On Track | Working the details | G: L3 | Active | TEMP L3 - Enter L3 | 2025-11-03 | 2027-05-28
Business Only Initiative: GV Surface GV MAX API Configuration Deployment |  | 109311 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe | On Track | Working the details | G: L3 | Active | TEMP L3 - Enter L3 | 2026-01-01 | 2028-05-31
Business Only Initiative: GV Surface GSE PM Frequency Rev for Cargo Trac + |  | 109314 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Diego Guadalupe, Janice Jones | On Track | Working the details Completed Plan and Financials | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-11 | 2027-05-27
Business w/ Tech Initiative: GV Surface eVIR & GV Max Interface |  | 109317 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe | On Track | Loading data | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: Rental Trailer Platform | 83257 | 7202 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Curt Hinchee, Denise hanchulak, Joseph Galioto | On Track | Previously submitted, Pod was moved. Initiative has be delayed awaiting new Pod assignment. | E: L2 | Active | L2 & CCH | 2023-11-01 | 2026-08-25
Business w/ Tech Initiative: Outside maintenance - Specification optimization - | 55131 | 7274 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Russell Smith, Diego Guadalupe | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Global Asset System for the Enterprise |  | 152887 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Joseph Galioto | On Track | On schedule | E: L2 | Active | L2
Business Only Initiative: Global Vehicles (GV) Telematics |  | 157299 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Christelle Laot | On Track | "2026-04-06 - Geotab came onsite at the MEMH to view GSE equipment." "2026-03-25 - The GV core team completed Uptake training session". "2026-03-20 - Added 2 PUD stations in Atlanta with 20 PUD vehicles for the US POC" "2026-03-09 - Expanded the scope of the Planview initiative, in particular to include GSE and EU" "2026-03-05 - Uptake project kickoff " "2026-02-19 - Completed/closed FIRST #7955 for Uptake" "2026-02-02 - The Geotab daily report with fault codes sent to NQAA technicians is only including vehicle source from now on. The GV core team continues to collect facts on how Geotab fault codes compare to DTC tools, using NQAA feedback". "2026-01-28 - GV confirmed the large T-shirt size opportunity for the business case at the fleet domain synch call using POC data and actual FedEx financials. GV quantified the two following use case opportunities: fuel consumption caused by idling time + driver behavior expenses caused by fuel/fluid/filter levels" "2026-01-23 - The GV core team completed Intangles training sessions" "2026-01-16 - Intangles devices are fully installed in Canada for POC at 5 PUD stations, with a total of 48 PUD vehicles of two manufacturers and models" "2025-12-29: Visit at NQAA to show technicians the Geotab website application. Spot check on odometer values, GPS locations, and vehicle dashboard warning lights". "12/16 - The framework is being developed for the business case assessment." "12/12 - The GV core team starts assessing data integrity from the Geotab POC" "12/11 - The GV core team completed Geotab training sessions" "11/25 - Geotab devices are fully installed in the US for POC at 10 PUD stations, with a total of 99 PUD vehicles of various manufacturers and models" "11/24 - Completed/closed FIRST #7957 for Intangles" "11/21 - Completed SaaS and hardware evaluation agreement for Intangles for the POC in Canada" "11/11 - Plans are made to continue Geotab installations at other POC locations in the US. The total of devices is expected to be around 100 for the POC with Geotab in the US. The POC is planned for 6 months" "11/10 - Project kickoff took place at the WHQ with Geotab" "11/10 - Geotab provided acccess to their website to view telematics data associated with FedEx vehicles. Data transmission is working well" "11/09- Geotab devices installed on 10 PUD vehicles at NQAA station in Memphis" "10/20 - Completed SaaS and hardware evaluation agreement for Geotab" "10/09 - Completed/closed FIRST #7694 for Geotab" "09/09 - Discussions with FedEx IT support stakeholders led to the conclusion that the current "business with tech" initiative should be reclassified as "business only" while in L1 Planview (no IT support needed for the POC) "08/26 - Met with supplier Geotab. POC will be free" "08/25 - Met with supplier Intangles, since selected by UPS. POC will be free, but has to take place in Canada" "08/15 - Pricing is still TBD" "2025-08-14 - GV is still in discussions with Geotab for the hardware and Uptake for the software" "2025-08-13 - GV defended the project successfullly in front of the triage team" | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: GV Surface Application Fields Automation2 |  | 160255 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Paco Esmeralda III, Diego Guadalupe | On Track | In progress | E: L2 | Active | L2 Feedback Requested | 2025-10-15 | 2027-07-12
Business w/ Tech Initiative: Modernize P&D SP-Owned Permanent Vehicle Processes |  | 93967 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | David Jackel, Joseph Galioto, Matthew D. Capo | On Track | 2/5 Initial request. | E: L2 | Active | L2
Business w/ Tech Initiative: LH Self-Service |  | 93522 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Matthew D. Capo, David Jackel, Joseph Galioto | On Track | Still on track - Ginger Ambrose should be the IO. | E: L2 | Active | L2 & CCH
Business Only Initiative: Insourcing Maintenance in Canada |  | 166695 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Kai-Mei Lam | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Ground Support Equipment with SenseAware |  | 168768 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Randy M. Steinhorst | On Track | 11/12/2025 - completed L1 LBC 11/12/2025 - submitted requested info regarding change to FY25. Baseline and target values based off October 2025. 3/2/2026 - initiative cancelled as it overlaps with broader scoped initiative | E: L2 | Cancelled | L2
Business Only Initiative: FEC Courier Retail Fuel Optimization |  | 177091 | Business Only Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Anthony Calvino | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FEC P&D Rentals |  | 183742 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Curt Hinchee, Denise hanchulak | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Surface Rentals |  | 191258 | Business w/ Tech Initiative | Fleet - Maintenance | Surface Fleet and Support Equipment | Curt Hinchee | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Right Size Rental Fleet | 75471 | 8852 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Brian Marflak | On Track | Changing IOs due to job duties change | K: L5 | Completed | L5 - Restarted Initiative | 2024-05-20 | 2025-04-03
Business w/ Tech Initiative: Reduce MOR by shifting demand (GSE) |  | 104444 | Business w/ Tech Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Karl W. Lindsley, Richard Wooten | On Track | Re-submitted as 'GSE/Heavy Truck Asset Usage Tracking' to clarify and better define scope. | C: L1 | Cancelled | L1
Business Only Initiative: Idle GSE Retirements in GV Max |  | 104448 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Karl W. Lindsley, Richard Wooten | On Track | Following the GSE Asset Review initiative a very low number of assets was identified for retirement with very low savings. After review with Alejandro Alvarez and Nick Wright it was recommended that this initiative be canceled. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Rebalance owned fleet underutilized assets |  | 104451 | Business w/ Tech Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Natalie N. Farr, Tim Paterra, Kathleen C. Pruss | On Track | 01.05.26 - The SCO and the D&AI financials have been added to the financials 12.23.25 - Financials updated for L2 11.05.25 - Updated NRB rate in financials. Meeting with EA team on weekly basis to to align on key objectives, clarify expectations, and set the foundation for successful execution Currently assessing vehicle rebalancing opportunities | G: L3 | Active | L3 | 2025-04-01 | 2027-09-30
Business w/ Tech Initiative: Reduce buffer through forecasting vehicle demand |  | 104454 | Business w/ Tech Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Kathleen C. Pruss, Richard Wooten | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: Reduce Legacy FXG Planned Trailer rentals for FY26 |  | 107799 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Fnu Shikha, Prasham Jain | On Track | 4/15 - T-shirt sizing and calculation logic for cost savings derived 12/17 - We achieved 10.16% dormancy on target of 10%. However we were overplanned to 18.5M to the actuals in Peak as approx 17M. If we calculate dormancy on the actuals then we did really well as 9.34% dormancy. 12/19 - This is a one time savings for Peak. We recorded our lowest dormancy and now we can return the Rentals. | K: L5 | Completed | L5 | 2025-04-01 | 2026-01-02
Business Only Initiative: Reduce Legacy Ground's 33 Foot Trailers |  | 110064 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Fnu Shikha, Prasham Jain | On Track | Have done the initital analysis and are trying to look at a potential buyer/ vendor where these assets can be disposed or sold. 207 trailers are sold and we have received money for them from the vendors. -- 12/09 233 trailers disposed so far and its looks to be on track. -- 12/16 241 trailers disposed. --12/29 249 disposed --1/7 250 disposed -2/13 267 disposed -3/30 331 disposed -4/20 350 disposed | K: L5 | Active | L5 | 2025-04-01 | 2025-10-01
Business Only Initiative: US Ops Vehicle Rental Reductions | 338 | 8863 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Thomas Woodburn, Ronaldo Caparaz | On Track | This initiatve was REPLACED with the Vehicle Right Sizing Initiative back in March 2024. There has been no work/actuals since March 2024 with this initiatve as it's a duplicate and was replaced. Please cancel this initiative. Thank you, Tom Woodburn Instructed to re-activate the initiative until FY26. Any actuals should come from the Vehicle Right Sizing initiative that replaced this initiative last year in March 2024. | K: L5 | Completed | L5 | 2022-10-18 | 2023-06-01
Business w/ Tech Initiative: Utilization KPI Dashboard |  | 130698 | Business w/ Tech Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Tim Paterra | On Track | 12.02.25 - Project being removed as an enabler from Rebalance owned fleet to excelerate it in the IT ranking. Initiaitve being cancelled due to low value and challenged getting IT resources at the moment. 09.16.25 - Moved to enabler 06.25.25 - Filling out L1 Lean business case | E: L2 | Cancelled | L2
Business Only Initiative: Canada Vehicle Purchase to Reduce Rentals |  | 130986 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Michael Fenton, Robert J. Howe | On Track | 2/24/2026-Purhcase vehicle communication of delivery to Canada has been requested to improve and a plan is in place to provide this; vehicles from the 1123 are to start arrving this summer. 2/5/26-Purchased vehicles are to start arriving now for 15+ year old assets. Assests earmarked to replace rentals are to start arriving this summer. New owner | G: L3 | Active | TEMP L3 - Enter L3 | 2025-06-16 | 2026-08-31
Business Only Initiative: Canada Right Size Rental Fleet |  | 130990 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Michael Fenton, Robert J. Howe | On Track | 2/24/26-Region at goal and moving to March goals per district; long term rentals data is being analyzed still 2/5/26-The team has finished tracking Long Term rental leases and Hoecker's team is analyzing the data, so we can take a wholistic approach to returning them as a region. There is the continued effort to drive down rentals to district goals on a weekly basis, with the KPI of driving down 100 less rentals per month to get to baseline. New IO | G: L3 | Active | TEMP L3 - Enter L3 | 2026-10-29 | 2026-10-29
Business w/ Tech Initiative: Innovation - Internet of Things (IoT) for GSE equi |  | 153556 | Business w/ Tech Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Georgiana Constantin, Craig Munro | On Track | 19/03/2026: Initiative to be cancelled as it was common agreed between EU and US (VP level) to merge efforts into one main initiative (#157299) and avoid duplication. 10/06: All costs are estimated, as there is no historical info that can help with the calculation rationale. | E: L2 | Cancelled | L2
Business Only Initiative: Reduce underutilized ST Trucks and Tractors |  | 153933 | Business Only Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Teresa G. Childress | On Track | Oct 23, 2025. Money step complete. Tracking actuals. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-04-11 | 2025-05-09
Business w/ Tech Initiative: GSE/Heavy Truck Asset Usage Tracking |  | 163700 | Business w/ Tech Initiative | Fleet - Utilization | Surface Fleet and Support Equipment | Karl W. Lindsley, Richard Wooten | On Track | 03/03/26 - Placed on hold because Finance cannot determine a useful baseline and there is a long term likelihood of the usage data coming from telematics (which is getting tech resources vs this initiative). 10/27 - Submitted supporting financial documentation, awaiting architects to be assigned. 10/06 - Working on L1 documentation. | C: L1 | On Hold | L1 Feedback Requested
Business Only Initiative: Global Tire RFP |  | 99483 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon | On Track | Assess phase 10/8/25 | E: L2 | Active | L2
Business Only Initiative: RFP remaining 30% of sites for FXG repair facility | 98744 | 7107 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Rahul Bajaj, Kyle Mitchell, Jacob Hanson | On Track | Supplier Awards and Contracting Compelete. Actuals to be recorded starting Feb 2025. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-10-25 | 2025-01-30
Business Only Initiative: RE01 - RFQ for Switchers Rentals | 98751 | 7135 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Nishant Saun, Robin Lyon, David Jackel | On Track | Ideation outcome, postponed/cancelled until further notice | E: L2 | Cancelled | L2
Business Only Initiative: PT01 - Negotiate with OEMs for additional discount | 98748 | 9165 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed, Josh Thorn, Kyle Mitchell | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-01 | 2026-05-14
Business Only Initiative: GM06 - RFP mobile service vendors | 98747 | 7425 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Josh Thorn, Keith Anderson, Kyle Mitchell, Rahul Bajaj | On Track | On track 01/31 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-02 | 2025-12-12
Business Only Initiative: VP07 - RFQ for FY26 Switcher | 98741 | 7134 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon, David Jackel, Rahul Bajaj | On Track | All units have been delivered and savings has been entered | K: L5 | Active | L5 | 2025-03-03 | 2025-08-08
Business Only Initiative: GM03 - Compare repair facility labor rates and par | 98745 | 9422 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Josh Thorn, Brian Gage, Keith Anderson, Kyle Mitchell, Rahul Bajaj | On Track | On track - updated target value to focus on FEC only (removed FXF) | E: L2 | Active | L2
Business Only Initiative: VP06 - RFQ for FY26 Trailers & Dollies | 98740 | 7423 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Josh Thorn, Kyle Mitchell, Keith Anderson, Rahul Bajaj, Ryan Skender | On Track | On Track | K: L5 | Active | TEMP L5 - Enter L5 | 2025-06-10 | 2025-06-18
Business Only Initiative: VP08 - RFQ for FY26 ICE Vehicles | 98742 | 9151 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Kyle Mitchell, Rahul Bajaj, Amanda Sewell | On Track | Initiaitve divided into multiple initiaives depneding on vehicle type - this placeholder initiative is no longer needed | C: L1 | Cancelled | L1 Data Migration - TEMP
Business Only Initiative: GSE Tire Strategy, Pricing and Negotiations | 98761 | 9175 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon, Kyle Mitchell | On Track | Aligned with manager, Kyle Mitchell, to cancel this initiative. We will explore incorporating this effort into a larger global tire initiative. | E: L2 | Cancelled | L2
Business Only Initiative: PT03 - RFP parts for trailing & forklifts (non-pow | 98750 | 7752 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed, Josh Thorn, Kyle Mitchell, Rahul Bajaj | On Track | 02/12/2025 - Meet w/ Business Team w/ initial RFP Recommendation. Took feedback, and rebuidling recommendation. For FXE, due less than desirable RFP savings outcome, going to go back out to suppliers to input bids. - Going to create negotiation meetings w/ FXF and FXG suppliers | K: L5 | Active | L5 | 2024-10-30 | 2026-02-18
Business Only Initiative: N2.0 Large Walk-Ins Supplier Negotiations |  | 99467 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Rahul Bajaj, Kyle Mitchell | On Track | All negotiations have been completed. Executed LOI (Letter of Intent) with suppliers. New PO's have been issued to the suppliers with the updated specs and aligned with Finance on the savings model. Received approval from Finance that the project is good to move to L4, as the money step is now complete. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-01 | 2025-05-07
Business Only Initiative: RFQ for FY26 Tractors |  | 99473 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon, Kyle Mitchell, Ryan Skender | On Track | 07/14/25: submitting for L4 | K: L5 | Active | L5 | 2025-06-27 | 2025-06-27
Business Only Initiative: FXF FY26 Forklift RFQ |  | 104708 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon, Grace Ige | On Track | Initiative progressing as units continue to be delivered | K: L5 | Active | L5 | 2025-02-10 | 2025-09-05
Business Only Initiative: EU - PUD Vehicle Specification Review with GV |  | 105853 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Rahul Bajaj, Kyle Mitchell | On Track | The specifications have been approved by leadership. New PO's have been issued to the suppliers with the updated specs and aligned with Finance on the savings model. Received approval from Finance that the project is good to move to L4, as the money step is now complete. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-01 | 2025-05-26
Business Only Initiative: PUD Rental Category Optimization |  | 106009 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Nishant Saun, Laurin Murk, Kyle Mitchell | On Track | On track | I: L4 | Active | L4 | 2026-02-02 | 2026-02-02
Business Only Initiative: Purchasing Leased MAN Trucks for NL & LUX |  | 106618 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Naser Amer | On Track | We executed the purchase contracts and transferred the ownership of the purchased trucks to FedEx in the Netherlands and Luxembourg. | K: L5 | Active | TEMP L5 - Enter L5 | 2025-12-31 | 2025-12-31
Business Only Initiative: Launch RFP for Accident Repair Services and Glass |  | 108653 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Ryan Skender, Kyle Mitchell, Josh Thorn, Rahul Bajaj | On Track | 10/6: Assessment and data collection under way | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2026-05-01 | 2026-05-01
Business Only Initiative: RFQ for FY26 intermodal containers |  | 108656 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Josh Thorn, Kyle Mitchell, Rahul Bajaj | On Track | On Track | K: L5 | Active | L5 | 2025-09-23 | 2025-11-14
Business Only Initiative: FY26 Chassis RFQ |  | 108660 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Grace Ige, Robin Lyon, Rahul Bajaj | On Track | FXF not moving forward with Chassis purchases in FY26 | E: L2 | Cancelled | L2 - Enter Value Prop
Business Only Initiative: Trailer Rental Market Event |  | 109673 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Nishant Saun, Laurin Murk | On Track | Ideation outcome, postponed/cancelled until further notice | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: CAN Tractor Rent to Lease Conversion |  | 109676 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Kyle Mitchell, Rahul Bajaj | On Track | Next step is coordination with Legal on Lease agreement | I: L4 | Active | L4 | 2026-03-09 | 2026-03-09
Business Only Initiative: Assess savings for Isuzu alternative parts |  | 109681 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Yunus Saiyed, Kyle Mitchell, Rahul Bajaj | On Track | Updated pricing with supplier, facilitate cost savings. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-05-01 | 2026-09-30
Business Only Initiative: Achieve Savings from aftermarket/pvt. label parts |  | 109687 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Yunus Saiyed, Kyle Mitchell | On Track | Savings estimate allinged with finance. Baseline calculated per FY25 Spend, Saving target estimated from the baseline | I: L4 | Active | L4 | 2025-10-06 | 2026-01-02
Business Only Initiative: Parts Distribution- Non-Rev Shipping vs. Dealer |  | 109691 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Yunus Saiyed | On Track | Ideation outcome, postponed/cancelled until further notice | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Vehicle Lease Strategy for EU (PUD Vans) |  | 110006 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Naser Amer, Kyle Mitchell | On Track | RFP planned to launch early May2026 as business requirements are being defined. | E: L2 | Active | L2
Business Only Initiative: EMR – Int'l Registration Plan (IRP) FEC licensing |  | 110009 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Ryan Skender, Grace Ige, Rahul Bajaj | On Track | After internal assessment opportunity, it was determined we could not proceed with this project. | C: L1 | Cancelled | L1
Business Only Initiative: FEC vehicle branding / decals |  | 110012 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Ryan Skender, Grace Ige, Rahul Bajaj | On Track | Ideation outcome, postponed/cancelled until further notice | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: FEC Fleet Management Assessment |  | 110015 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Ryan Skender, Grace Ige, Rahul Bajaj | On Track | We are in the process of identifying and assessing the appropriate data for this project. We are under contract until 2027 so are on track from a timing perspective. | E: L2 | Active | L2
Business Only Initiative: RFP for Powered GSE Purchase – FY26 Capital |  | 110147 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed, Kyle Mitchell | On Track | Baseline, saving target estimation aligned with finance. | I: L4 | Active | L4 | 2025-06-03 | 2026-04-09
Business Only Initiative: GSE Refurbishment – market event |  | 110150 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed | On Track | Cancelled for further evaluation | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Specification Review for GSE |  | 110153 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed | On Track | Cancelled for further evaluation | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Contracted maintenance services management – Holma |  | 108650 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Josh Thorn, Kyle Mitchell | On Track | Assessment | E: L2 | Active | L2
Business Only Initiative: Vehicle Rent to Lease - US | 35896 | 6693 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Lindsey Taylor, Bradley Arnell | On Track | On Track | K: L5 | Active | TEMP L5 - Enter L5 | 2023-09-15 | 2025-09-30
Business Only Initiative: Vehicle & equipment parts - Commercial - Enhance G | 55140 | 7210 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed, Diego Guadalupe, Rahul Bajaj, Janice Jones, Josh Thorn | On Track | All calalogues updated in system with new pricing. | K: L5 | Active | L5 | 2022-12-01 | 2025-06-02
Business Only Initiative: Vehicle & equipment parts - Specification optimiza | 55142 | 7212 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed, Diego Guadalupe, Rahul Bajaj, Josh Thorn | On Track | Supplier catalog updated. Moneystep marked complete. Capturing savings on monthly basis. | K: L5 | Active | L5 | 2024-04-01 | 2025-07-03
Business Only Initiative: Ground Support Equipment (GSE) Parts Global Spend | 3080 | 8403 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Yunus Saiyed, Josh Thorn, Kyle Mitchell, Rahul Bajaj | On Track | Suppliers catalog was updated in the system at the beginning of Jan, ready to begin tracking a full month 02/01/2025 | I: L4 | Active | TEMP L4 - Enter L4 | 2023-10-30 | 2025-01-31
Business Only Initiative: Light/Medium Duty Vehicle Rentals | 2155 | 8898 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Kyle Mitchell | On Track |  | I: L4 | Active | TEMP L4 - Enter L4 | 2022-12-01 | 2023-06-01
Business Only Initiative: Light_Medium Duty Vehicle Upfitters | 3145 | 8998 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Kyle Mitchell, Amanda Sewell | On Track | Completed | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-01 | 2024-07-30
Business Only Initiative: Tires - Transition to Lowest Unit Cost Provider | 3150 | 9002 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon, Kyle Mitchell | On Track | initiative is complete - PDSM ticket submitted on 2/19 to move back to completed status | K: L5 | Completed | L5 | 2023-03-01 | 2023-08-01
Business Only Initiative: Roadside, On-Site and Prev. Maintenance RFP | 59485 | 9171 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Rahul Bajaj, Kyle Mitchell | On Track | On Track - Tracking Savings | I: L4 | Active | TEMP L4 - Enter L4 | 2024-01-17 | 2024-06-10
Business Only Initiative: GV Walk-in Specs Rev USA/CA W700 to W1200 |  | 93519 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Rahul Bajaj, Diego Guadalupe, Kyle Mitchell | On Track | The specifications have been approved by leadership. New PO's have been issued to the suppliers with the updated specs and aligned with Finance on the savings model. Received approval from Finance that the project is good to move to L4, as the money step is now complete. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-01-01 | 2025-05-09
Business Only Initiative: EMR – Straight Truck RFP |  | 133026 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon | On Track | On track as of 10/03/2025 - working on sending POs | I: L4 | Active | TEMP L4 - Enter L4 | 2025-12-05 | 2025-12-05
Business Only Initiative: EMR – Original Equipment (OE) Tire Rebates |  | 133030 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Robin Lyon | On Track | On track 10/10/25 | I: L4 | Active | TEMP L4 - Enter L4 | 2025-06-02 | 2025-10-30
Business Only Initiative: FXF FY25 Trailer Purchase | 85478 | 7725 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Kyle Mitchell, Rahul Bajaj | On Track | Week of 08/05/24 - RFQ completed in Q4 FY24 - FY25 orders placed with suppliers and tracking delivery schedules and impacts February 2025 - all trailers part of initiative have been delivered to final destination | I: L4 | Active | L4 Feedback Requested | 2024-03-01 | 2025-03-14
Business Only Initiative: EMR - FY26 Intermodal Containers |  | 154739 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Josh Thorn, Kyle Mitchell, Rahul Bajaj | On Track | Active | K: L5 | Active | L5 | 2025-09-23 | 2025-11-14
Business Only Initiative: EMR: Tractor RFP for UK & EU |  | 154744 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Naser Amer, Kyle Mitchell | On Track | Following the execution of the framework agreements, purchase orders for all 397 tractor units in scope were issued to four suppliers—Daimler, MAN, DAF, and Volvo. Deliveries have already commenced from three suppliers for the UK and Netherlands. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-15 | 2026-06-02
Business Only Initiative: European Road Network (ERN) & UK Trailer RFP |  | 165126 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Naser Amer, Kyle Mitchell | On Track | On track | E: L2 | Active | L2
Business Only Initiative: GSE Lease Strategy - EU |  | 167128 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Ngoc Mai Bui, Craig Munro, Kyle Mitchell | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: Global Standardization of Bolt/ Plastic Seals |  | 167921 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Ketan Panchal, Chris Avitabile | On Track | On Track | E: L2 | Active | L2
Business Only Initiative: EMR Vehicle Wash Freq Reduction (EMEA & APAC) |  | 133510 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Damodar Naik | On Track | Shall go for RFQ in Coupa (EMEA & APAC) for Vehicle washing services after getting required details from FedEx Stakeholders and current suppliers. This will help us in two main opportunities 1. Vendor Consolidation & 2. Cost Optimization. Some vendors replied saying that they already done the frequency reduction recently. Only 4 out of 24 shortlisted high spend vendors responded for this initiative and the amount is small. | E: L2 | Cancelled | L2 Feedback Requested | 2025-10-02 | 2026-03-30
Business Only Initiative: EMR Vehicle Wash RFP for North America |  | 133513 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Damodar Naik, Christopher M. Winans | On Track | 05th Aug, 2025, updated the financial tab For the first time planning for North America RFP | G: L3 | Active | TEMP L3 - Enter L3 | 2025-10-02 | 2026-08-20
Business Only Initiative: EMR - US Mobile Fuel RFP |  | 163300 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Rolando Olmos | On Track | 09/18- RFP launched 9/8 to 20 suppliers. Bids due 9/29. | E: L2 | Active | L2 Feedback Requested | 2025-10-06 | 2029-01-31
Business Only Initiative: PT02 - Negotiate with OEMs for additional discount |  | 177085 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Yunus Saiyed | On Track | On Track | I: L4 | Active | L4 | 2025-11-03 | 2025-12-01
Business Only Initiative: N2.0 Parts Payment Term Benefit - TAG & DREAM |  | 188366 | Business Only Initiative | Fleet - Asset Strategy/Procurement | Surface Fleet and Support Equipment | Laurin Murk, Kyle Mitchell | On Track | On Track | I: L4 | Active | L4 | 2026-01-30 | 2026-01-30
Business w/ Tech Initiative: FAST: Enabler: Acceptable commodity alignment be | 74297 | 8003 | Business w/ Tech Initiative | FXF - Commercial | Freight | Tyler Tressler, Susan A. Patrone | On Track | Initiative on hold. Changes to the overall FedEx Freight Strategy no longer support a business case for this initiative. Without a strategy to involve FedEx Freight in 100% pickup and delivery of Express Freight, the value of enabling certain commodities at FedEx Freight no longer supports based on cost, complexity and employee affecting changes. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FAST: Enabler- FedEx Automation & Customer Experi | 74322 | 8002 | Business w/ Tech Initiative | FXF - Commercial | Freight | Lynette Gaillard, Susan A. Patrone | On Track | With the dissolution of the FAST POD, decision was made ton 10/11/2024 to place on hold at this time due to cost benefit. Moved to L1. Beginning L2 checklist. Meeting with Tricolor team to determine customer shipment creation gaps and align Express/Freight shipment creation order details for domestic and international. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-07-22 | 2024-09-03
Business Only Initiative: 2025 NMFC Changes |  | 93279 | Business Only Initiative | FXF - Commercial | Freight | Shelly D. Due | On Track | 03/18/2025 Over 2K NMFC items expected to move to 13-sub density scale in 2025. Currently developing communication and fedex.com content and assessing current online tools for customer use. Targeted email to sales in development but dependent on data lists from pricing/RQ. Reviewed draft Communication Plan with Core Team on 3/7/25. Included industry benchmarks and timeline Evaluating changes to online NMFC classification calculator and development of density calculator with proposed plan by 3/31/25 Sales classification lookup tool complete. Sales education and one pager targeted by 3/31/25 Currently, there are no financials tied to this initiative. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: [US] FedEx Freight in Enterprise Claims Desktop - | 15293 | 9199 | Business w/ Tech Initiative | FXF - Commercial | Freight | Drew Kelley, Shirley Turner | Some Issues | Leadership directive to place initiative on hold received by LTL Freight Pod on 02/17/25. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-06-06 | 2025-08-06
Business w/ Tech Initiative: FedEx Freight : Modernize fedex.com LTL shipping | 15292 | 9198 | Business w/ Tech Initiative | FXF - Commercial | Freight | Shea Anderson | Some Issues | UPDATE: currently on "hold" due to removal of resources. PRIOR UPDATE: Sr. Officer decision made on direction of the platform of LTL shipping on fedex.com on 02/22/2023: build/introduce LTL shipping solely in the Magic platform. Effort will depend on prioritization and funding per Anthony Norris and Scott Harkins; however, leadership stated to proceed to L3. PRIOR UPDATE: We moved L4 date to May 31, 2025 as the a result of extensive delay due to lack of development resources. Magic shipping for LTL received dedicated funding in Q4 FY24, for developers to begin Q1 FY25. We have experienced some delays in Q1 FY25, although not detrimental, in API. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-02-01 | 2025-05-28
Business w/ Tech Initiative: FXFD Personalized Notifications - per customer req | 85324 | 6809 | Business w/ Tech Initiative | FXF - Commercial | Freight | John Sullivan, Kelli Ostertag | Some Issues | 11/3/25: FXF IT deprioritized due to separation priorities; As FXF IT resources free up between now and post separation Marketing will continue to show these capabilities as a market diffentiator and need for large accounts like Sam's Club, Walmart, and Chewy 10/24/25:SEP25 Revenue at $1.2M - FY25 YTD Revenue $27.5M. IT resource cannot proceed with this work due to seperation. Pending POD leadership decision how to move forward in planview. 10/20/25: SEP25 Revenue at $1.2M - FY25 YTD Revenue $27.5M. IT resource cannot proceed with this work due to seperation. Pending POD leadership decision how to move forward in planview. 10/7/25:SEP25 Revenue at $1.2M - FY25 YTD Revenue $27.5M Mockups for Standard, Premium and Pickups completed. Brand and Legal approved. Work is on hold due to some impacted applications being a part of Wave #1 and Wave #2 regarding separation activities. Timeline NOT expected to be affected. Coding cannot take place within those applications at this time. : The team has about 3 weeks of coding left to perform. 9/29/25: AUG25 Revenue at $1M - FY25 YTD Revenue $27.5M Mockups for Standard, Premium and Pickups completed. Brand and Legal approved. Work is on hold due to some impacted applications being a part of Wave #1 and Wave #2 regarding separation activities. Timeline NOT expected to be affected. Coding cannot take place within those applications at this time. : The team has about 3 weeks of coding left to perform. 9/14/25:AUG25 Revenue at $1M - FY25 YTD Revenue $27.5M Mockups for Standard, Premium and Pickups completed. Brand and Legal approved. Work is on hold due to some impacted applications being a part of Wave #1 and Wave #2 regarding separation activities. Timeline NOT expected to be affected. Coding cannot take place within those applications at this time. : The team has about 3 weeks of coding left to perform. 9/5/25: this has been put on hold due to some impacted applications being a part of Wave #1 and Wave #2 regarding separation activities. Coding cannot take place within those applications at this time. : The team has about 3 weeks of coding left to perform. Timeline not expected to be affected. This work cannot proceed at this time due to the criticality it poses if not completed once started, and the looming impacts from Freight Separation. For the remaining development stories the team will be modifying the core business logic of how notifications work today, so once they begin this development they will not be able to stop until complete. The separation work is structured in waves- if the team identifies a gap in the separation schedule, pertaining to the impacted applications for this initiative, there may be an opportunity to perform this coding. 8/25/25: no new updates. On track 8/18/25: no new updates. On track 8/12/25: no new updates. On track 7/28/2025: IT is working solution that is expected to take 3 PI's to finish. We reested information regarding what resources needed to launch prepeak and IT team said it was not possible even with additional resouces. 7/22/2025: IT sent test shipments. Some time data was missing. Defect was found. IT determined it was code defect on their side needed to be updated. Timeline should not be impacted. 7/14/2025: IT sent test shipments. Some time data was missing. Defect was found. IT determined it was code defect on their side needed to be updated. Timeline should not be impacted. 7/8/2025: IT sent test shipments. Some time data was missing. Meeting with IT to discuss if error on IT side or Salesforce side. Next steps will be decided after meeting today. 6/23/25: IT team is adding resources to assist with effort to start this PI 6/25. Meeting to be scheduled with IT team and Salesforce support. Knowlege transfer bean 6/19/25 for IT additional resources. 6/10/25: Notification IT work may be delayed due to ​significant attrition within the team. Leadership is aware. 5/20/25: Commerical work was compl | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-06-12 | 2026-02-16
Business Only Initiative: [Southern Border] Grow FedEx Freight LTL Mexico | 69276 | 7999 | Business Only Initiative | FXF - Commercial | Freight | Heather Newberry, John Sullivan, Kelli Ostertag | On Track | 11/3/25 Initiative changed status to "On Hold" to revisit business case post-separation. Marketing will continue to commercialize existing D2D LTL offering and promote with LTL sellers and revisit business case closer to separation. 10/31/25 Completed review with finance lead Cecil Weddle and Pod Lead Carson Davidenko. Initiative will move to hold in Planview 10/24/25 Gained input from additional stakeholders for forecast/business case adjustments, IO adjusting and review with Finance wk of 10/27 Working with Carson Davidenko on L2/L3 checklist Feedback from Karen M.; expand out additional information in planview wk of 10/27; and will re-review 10/17/25 Gained input from finance for forecast/business case adjustments, IO adjusting and review again with Finance wk of 10/20 Working with Carson Davidenko on L2/L3 checklist Providing Karen McConnico a walk-through of initiative; scheduled for wk of 10/20 (objective to gain her guidance/decision on potential CCH requirements) 10/10/25 Finance Lead has shifted from James Schaffer to Cecil Weddle, walk-through scheduled for 10/10. Finance agreement and added information are needed to complete the financial sections of Planview​ Working with Kelli Ostertag/Susan Patrone of Planview health status and entries of L2/move to L3 checklist. ​ Providing Karen McConnico a walk-through of initiative; scheduled for 10/13 (objective to gain her guidance/decision on potential CCH requirements)​ | E: L2 | On Hold | L2 & CCH
Business Only Initiative: Freight Grocery Initiative | 65044 | 6808 | Business Only Initiative | FXF - Commercial | Freight | Oscar Zuluaga, John Sullivan | On Track | 10/15/2025 Domain leadership has discussed this initiative with senior executive leadership. A decision has been made to cancel this initiative in Planview With the change in the landscape of this initiative and priorities with Separation, cancelling this initiative will allow us to leverage this work at a later date and re-assess / evaluate the future potential value. 10/14/2025 The FXF Grocery initiative will no longer be a business case or a DRIVE initiative, per the direction of FXF leadership. It will, however, continue as pillar to grow weight per shipment 9/23/2025 Aug25 Revenue at $6.3M. [VS Plan: -$5M (-44.2%)], [YOY: -$500K (-$7.4%)]​ FY26 YTD Revenue at $20.5M: [VS Plan: -$6.8M (-25.4%), YOY: -488K (-2.4%)]​ Sales enablement aligning with RQ/Sales before setting up webinars and targeted communication to suppliers in FXF Sales to promote grocery this week ​ Freight Grocery initiative to be reviewed with Finance before proceeding to L4 9/16/2025 Aug25 Revenue at $6.3M. [VS Plan: -$5M (-44.2%)], [YOY: -$500K (-$7.4%)] FY26 YTD Revenue at $20.5M: [VS Plan: -$6.8M (-25.4%), YOY: -488K (-2.4%)] Sales enablement to send targeted communication to suppliers in FXF Sales to promote grocery this week Freight Grocery initiative presented to SURGE and greenlighted to submit to L4 in Planview, but requested to be reviewed with Finance 9/9/2025 Actuals for Aug25 Updated in Planview Completed Money step, documenting in planview and ready to move to L4 Sending targeted communication to FXF sellers of Grocery suppliers 8/25/25 Sales enablement sent out targeted communication to grocers./suppliers in FXF Sales to promote grocery Grocery initiative changed in Planview to Biz only 8/12/25-Jul25 Revenue at $7.1M, VS Plan: -$0.4M (-5.6%), YOY: -87K below (-1.2%), FY26 YTD Revenue at $13.8M: VS Plan: -$1.8M (-11.8%), YOY: 11.3K above (0.1%) FY26 YTD YOY Incremental Revenue of 0.205M from Customers that awarded FedEx the “Preferred Carrier Status: (Gordon Foods, McLane) FY26 YTD YOY Incremental Revenue of 1.1M from newly onboarded suppliers (Redstone, Worthy, CH Guenter) 7 new opportunities added to the pipeline (BJs, Farmers of America, Restaurant Depot, Reliance Vitamin, US Foods, Meijer, Colonel Jim Breading, ) with potential total revenue of $11.9M/year Change approved for Grocery initiative to "Biz only“ after removal of the Visibility Dashboard per DataWorks deprioritization 8/5/25 -Highspot updated with new Sales process to enter Grocery opportunities and communication on Sales Dispatch went out to FXF sellers SSO login for Lumper payment platform Relay completed and testing in FXF select locations successfully completed Requested change for Grocery initiative to "Biz only“ after removal of the Visibility Dashboard per DataWorks deprioritization 7/8/25- New Isell flag to track pipeline, engaged G2S support for FXF Sales awareness. Setup SSO login for lumper payment platform Relay 6/23/25- Customer Facibg leave behind published in Highspot. Aligning Top 30 Grocers with LTL Sales Team 5/16/25- G2M approval by MAC for Leave Behind, brand working on design this week. Meeting with RQ on 5/23 to align on pipeline and capability management approach for FY26​ 5/9/25- Completed contract for Lumper pyament system-Relay and established new pipeline management process 5/2/25 - Presented update to Mktg VP & actions to increases revenue, including focus on capabilities and fast tracking onbording 4/28/25 - Adjusted planview financial/kpis to reflect new OM of 14% from Finance and applied baseline of FY24 to FY25 only 4/21/25 - Customer facing leave behind assigned to G2M team 4/14/25 - Updated business case with FY25 baseline, gathered feedback from Top 30 accounts and identiefied stage in onboarding 4/7/25- Indentified "no service zones" and aligned with Grocery customers. Scheduled dsicovery calls with Sales AEs for Top 30 grocers 3/31/25 - FXF Direct team engaged Top 30 Grocers. Identified Top 100 grocers in indius | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-05-20 | 2025-12-31
Business w/ Tech Initiative: FedEx Freight Direct to/from US-CA, CA-US, and Dom | 15313 | 9206 | Business w/ Tech Initiative | FXF - Commercial | Freight | Saloni Lalan, Kelli Ostertag, Meiry R. Pratas | On Track | **9/30/2025: Sep Week 4 (9/21 - 9/27 - 5 b/d): Revenue 33K, Shipments 50 (15 Basic, 24 Basic by Appt)​ Sep Week 3 (9/14 - 9/20 - 4 b/d): Revenue 39K, Shipments 58 (8 Basic, 50 Basic by Appt)​ FY26 YTD performance: Revenue $782K, Shipments 1,698 **9/24/2025: •Sep Week 3 (9/14 - 9/20 - 4 b/d): Revenue 39K, Shipments 58 (8 Basic, 50 Basic by Appt) •Sep Week 2 (9/8 - 9/13 - 4 b/d): Revenue 24K, Shipments 50 (6 Basic, 42 Basic by Appt) FY26 YTD performance: Revenue $745K, Shipments 1,643 Transition IO responsibilities from Meiry Pratas to Saloni Lalan **9/9/2025: Sep Week 1 (9/2 - 9/5 - 4 b/d): Revenue 27K, Shipments 44 (4 Basic, 40 Basic by Appt) Aug Week 4 (8/25--8/29): Revenue $33K, Shipments 56 (10 Basic, 43 Basic by Appt. 2 Standard, 1 Premium) FY26 YTD performance: Revenue $675K, Shipments 1,540 * Working towards tranisitioning Initiative ownership to US FXF Marketing - Saloni Lalan **8/25/2025: Aug Week 3 (8/18--8/22): Revenue $48K, Shipments 57 (8 Basic, 45 Basic by Appt. 1 Standard, 1 Premium, 1 Basic Return) Aug Week 2 (8/11--8/15): Revenue $48K, Shipments 83 (10 Basic, 73 Basic by Appt) FY26 YTD performance: Revenue $656K, Shipments 1,525 **8/18/2025: Aug Week 2 (8/11--8/15): Revenue $48K, Shipments 83 (10 Basic, 73 Basic by Appt) Aug Week 1 (8/4--8/8): Revenue $30K, Shipments 71 (10 Basic, 58 Basic by Appt, 1 Standard, 1 Premium, 1 Basic Return) FY26 YTD performance: Revenue $560K, Shipments 1,385 **8/11/2025: Aug Week 1 (8/4--8/8): Revenue $30K, Shipments 71 (10 Basic, 58 Basic by Appt, 1 Standard, 1 Premium, 1 Basic Return) July Week 5 (7/28-8/1): Revenue $38K, Shipments 80 (14 Basic, 65 Basic by Appt, 1 Basic Return) FY26 YTD performance: Revenue $512K, Shipments 1,302 FXFD Lower British Columbia (LBC) Postal Codes: 30 Shipments and $16K in Revenue since launch 7/7 **8/5/2025: July Week 5 (7/28-8/1): Revenue $38K, Shipments 80 (14 Basic, 65 Basic by Appt, 1 Basic Return) July Week 4 (7/21-7/25): Revenue $42K, Shipments 90 (13 Basic, 77 Basic by Appt) FY26 YTD performance: Revenue $482K, Shipments 1,231 FXFD Lower British Columbia (LBC) Postal Codes: 29 shipments and $16K in Revenue since launch 7/7 **7/28/2025: July Week 4 (7/21-7/25): Revenue $42K, Shipments 90 (13 Basic, 77 Basic by Appt) July Week 3 (7/14-7/18): Revenue $54K, Shipments 105 (18 Basic, 87 Basic by Appt) FY26 YTD performance: Revenue $442K, Shipments 1,149 FXFD Lower British Colombia (LBC) Postal Codes: 25 shipments and $15K in Revenue since launch 7/7 **7/21/2025: July Week 3 (7/14-7/18): Revenue $54K, Shipments 105 (18 Basic, 87 Basic by Appt) July Week 2 (7/7-7/11): Revenue $53K, Shipments 133 (24 Basic, 108 Basic by Appt, 1 Standard) FY26 YTD performance: Revenue $399K, Shipments 1,053 FXFD Lower British Colombia (LBC) Postal Codes: 20 shipments and $11.7K in Revenue since launch 7/7 **7/15/2025: July Week 1 (7/7-7/11): Revenue $53K, Shipments 133 (24 Basic, 108 Basic by Appt, 1 Standard)​ July Week 1 (6/30-7/4): Revenue $47K, Shipments 131 (11 Basic, 120 Basic by Appt)​ FY26 YTD performance: Revenue $342K, Shipments 949 **7/2/2025: July Week 1 (6/30-7/4): Revenue $47K, Shipments 131 (11 Basic, 120 Basic by Appt) June Week 4 (6/23-6/27): Revenue $56K, Shipments 160 (15 Basic, 145 Basic by Appt) FY26 YTD performance: Revenue $287K, Shipments 819 FXFD launches in British Columbia - Lower British Colombia (LBC) Postal Codes (7/7) **7/2/2025: June Week 4 (6/23-6/27): Revenue $56K, Shipments 160 (15 Basic, 145 Basic by Appt) June Week 3 (6/16-6/20): Revenue $64K, Shipments 155 (21 Basic, 134 Basic by Appt) FY26 YTD performance: Revenue $250K, Shipments 697 **6/24/2025: June Week 3 (6/9-6/13): Revenue $64K, Shipments 155 (21 Basic, 134 Basic by Appt) June Week 2 (6/9-6/13): Revenue $78K, Shipments 224 (33 Basic, 190 Basic by Appt) FY26 YTD performance: Revenue $185K, Shipments 531. **6/16/2025: June Week 2 (6/9-6/13): Revenue $78K, Shipments 224 (33 Basic, 190 Basic by Appt) June | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2023-03-07 | 2025-01-20
Business w/ Tech Initiative: FedEx Freight Direct Mainstream | 15291 | 8001 | Business w/ Tech Initiative | FXF - Commercial | Freight | Libby Thelen, Susan A. Patrone, Chiedo Ugorji | On Track | 4.16.26 Due to Separation the decision has been made to cancel any additional FXFD Mainstreaming features on Cafe/FSM as this platform will no longer support FXF/FXFD once the TSA expires. 1.13.26 No issues. 12.12.25 Init on track, no issues with launch, actuals updated for Oct and Nov. 12.1.25 Init on track, no issues with launch, actuals are delayed as FXFD Dashboard is still down. 11.14.25 Init on track, no issues with launch, actuals are delayed. 11.7.25 No additional updates at this time. 10.24.25 Init on track, no issues with launch. FXFD mainstreaming is currently on track. Phase 1 (FXFD API) and Phase 2 (E2E Pricing) on track for April 23CSR Phase 3a - Phase 3 project split through CPEL. - Phase 3A -Ship Manager/Cafe Phase 3B - MAGS Phase 3a pending CPEL EPIC lead and start (targeting June 23) Engaged with Freight Finance and Forecasting for Business Case re calibration for Phase 3. All Phases entered through CPEL/FPEL/RMIC (Phase 2) only. 3.10.25 * Back to High confidence level for April '25 CSR as two capabilities are delayed. These delays will push the two specified capabilities to the July '25 CSR, however, this initiative's planned September '25 FSM/Cafe General Release will not be impacted by the delays.​ * Returning to CPEL on Wed 3/12 for July ’25 CSR approval for the delayed capabilities ​ * User stories being refined, functional testing continuing with 85% passed for L3C4 test scenarios 3.17.25 *Funcional testing continuing, medium and low outstanding defects are being addressed and will not impact project release. *Capability 1.0 - Rate Shop Feature deferred to Post April L3 Testing. Approved by CPEL on 3/12 as this will not impact September release. *Awareness: Dependency on Cascade 3.1 API Enabler (Ability for FSM to connect to FedEx API 1st party gateway). Phase 2 - FedEx Assisted Client Instance Authentication. Target Date post July ’25. 3.25.25 Testing continuing with high confidence, overall intitiative continuiing with high confidence. No other updates at this time. 3.28.25 Per JL/Finance completed updated financials with FY25 exit rate. 4.15.25 Dev work continuiing, majority of the work will be completed with April '25 CSR. Rate Shop Feature dev work and CALC Changes are targeted for Post-July '25. This will not impact September release. Awareness: Dependency on Cascade 3.1 API Enabler (Ability for FSM to connect to FedEx API 1st party gateway). Phase 2 - FedEx Assisted Client Instance Authentication. Target Date post July ’25. 4.22.25 No changes for this week. 4.29.25 April work complete. Rate Shop Feature dev work continuing along with CALC changes, targeted for Post-July '25. This will not impact September release. Awareness: Dependency on Cascade 3.1 API Enabler (Ability for FSM to connect to FedEx API 1st party gateway). Phase 2 - FedEx Assisted Client Instance Authentication. Target Date post July ’25. 5.7.25 (Phase 3A FSM - #15291) L3, Med-Low confidence level forSep '25 FSM General Release due to risk associated with Dependency on Cascade 3.1 API Enabler (Ability to connect to FedEx API). API enabler targeting July ’25 CSR, but it may not be completed in time. Mainstreaming team is currently working on an iterim solution to bring on revenue and volume by pivoting to Web Services since FXFD can be enabled in Web Services. This would be interim solution until the April '26 FSM General Release at which point the API Enabler would be complete and Mainstreaming init could launch. 5.20.25 (Phase 3A FSM - #15291) L3, Intiative is now split into two parts. High confidence level for Part 1: Sep 25 FSM General Release using Web Services to enable FXFD funtionality in FSM. Dev work/ testing underway targeting July 25 CSR. Med confidence level for Part 2: Apr 26 FSM General Release using APIs to enable added Rate Shop FXFD funtionality in FSM. This part 2 Mainstreaming API work is completed, but cannot be released until Dependency on AP | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2022-03-01
Business w/ Tech Initiative: Freight Inspection Tool FIT 2.0 | 26157 | 6683 | Business w/ Tech Initiative | FXF - Commercial | Freight | Robert Holstein, Juan Oscar Rodriguez | On Track | 04/18/2025 Updated Planview with the new KPI and updated revenue forecast for the FIT 2.0 reforecast. 04/09/2025 Working on reforecaste and rebaseline for FIT 2.0. Tentative date 04/17. ------------------------ Contract with the vendor ends December 31st and the application will be handed over to FXF IT. Current work includes adjustments to the Frequent Offenders logic that will result in more confident revenue producing shipments to the inspectors. Revenue corrections is ongoing to fix revenue numbers that were incorrect due to earlier bugs in the project. Validation of these numbers has taken time due to the number of corrections needed. Work is wrapping up with enhancements to the following: Shipment Page Starring Shipments Combing of Capacity Loads Offline Mode Admin Services | K: L5 | Completed | L5 | 2023-02-01 | 2025-05-29
Business Only Initiative: FXF100 Item 640 Rewording | 73463 | 7567 | Business Only Initiative | FXF - Commercial | Freight | Aaron Epperly | On Track | 6/2/2025 On track updating May financial date and recording this week. 5/13/2025 On track monitoring monthly revenue trends. 5/5/2025 On track entered April 2025 KPI and revenue totals. Continu to track revenue and record L5 data. 4/28/2025 On track monitoring monthly revenue trends. Will enter April revenue this week. 4/21/2025 On track monitoring monthly revenue trends. 4/14/2025 Completed March KPI and Financial updates last week. On track monitoring monthly revenue trends. 4/7/2025 Completed March revenue totals and updated planview financials and freight leadership. Project is on track and now in L5. 3/31/2025 Approved for L5 complted the movement in planview. This week will record March revenue. 3/24/2025 Prep completed for L5 surge session. On track monitoring revenue trends. 3/17/2025 On track monitoring monthly revenue trends. 3/10/25 On track monitoring monthly revenue trends. 3/3/2025 On track monitoring monthly revenue trends. 2/24/2025 On track monitoring monthly revenue trends. 2/17/2025 On track monitoring monthly revenue trends. 2/10/2025 On track monitoring monthly revenue trends. 2/3/2025 On track monitoring monthly revenue trends. 1/ 30/2025 On track monitoring monthly revenue trends. 1/23/2025 On track monitoring monthly revenue trends. 1/16/2025 On track monitoring monthly revenue trends. 1/9/2025 Recorded December revenue. Gatherered feedback on low trends for December from Freight Analysis team. Driven by high number of inspector vacations and time off combinded with low shipment volumes. 1/2/2025 On track monitoring monthly revenue trends. 12/27/2024 On track monitoring monthly revenue trends. 12/20/2024 On track monitoring monthly revenue trends. 12/13/2024 On track monitoring monthly revenue trends. 12/06/2024 Recored November revenue. Gatherered feedback on low trends for December from Freight Analysis team. Driven by high number of inspector vacations and time off combinded with low shipment volumes. 11/29/2024 On track monitoring monthly revenue trends. 11/22/2024 On track monitoring monthly revenue trends. 11/15/2024 On track monitoring monthly revenue trends. 11/8/2024 Recorded October revenue totals and updated status. 11/01/2024 On track monitoring monthly revenue trends | K: L5 | Completed | L5 | 2023-12-05 | 2024-05-31
Business Only Initiative: Control Room Temp. in Temp. Controlled Network | 82027 | 7408 | Business Only Initiative | FXF - Commercial | Freight | Kevin Malek, Kelli Ostertag, Matthew T. Hull | On Track | Week of 12/15/25 - Drafting a CRT agreement for new customer Eversana. They are interested in starting in Q1 2026. Week of 12/01/25 - Presented CRT solution for winter protect from freeze product for Sherwin Williams. Week of 11/17/25 - Customer Fresenisus Kabi is looking at expanding locations beginning of 2026. They plan to start discussing and identifying locations in December. Week of 11/10/25 - Initial customer Viatris is considering a pilot program with CRT. They will be reviewing the pricing that was provided to them after the 1st of the year. Week of 10/27/25 - Fresenius Kabi added new additional delivery location in Miami, FL. Week of 10/20/25 - Completed three weeks of pickup and delivery of CRT freight to the states of GA & FL for customer Fresenius Kabi. No service issues. Customer reviewing timeline to expand deliveries into additional states. Week of 10/13/25 - Memphis crossdock facility is now ready for the first CRT product shipments. Week of 10/06/25 - Completed first pick up and delivery of freight through the CRT network for customer Fresneius Kabi. Week of 09/29/25 - Customer Fresenius Kabi has delayed the start-up. Working to reestablish a new start date. Week of 9/22/25 - Completed pre-launch meeting with customer to ensure we are in alignment for Monday's launch requirements. Week of 09/15/25 - Customer has scheduled the first CRT shipments for Monday 9/29. Shipments will iinclude delivery locations to the states of GA and FL. Week of 09/08/25 - Customer Fresensius Kabi has targeted a new start date of 10/03. Week of 09/01/25 - Customer Fresenius Kabi has delayed the start-up. Sales meeting with them tomorrow, 9/04, to reestablish a new start date. Week of 08/04/25 - Customer Fresenius Kabi scheduled to start pickups on 8/22. Week of 7/28/25 - New trailers scheduled to be in place on 8/15. Week of 7/21/25 - Legal has completed the new Master Agreeement for CRT services. Week of 7/7/25 - Current crossdock provider in Atlanta has provided a move out date of December. We have narrowed down and are now negotiating the new Atlanta location between two companies. Week of 6/30/25 - Current TMF system has been set up for CRT and tested successfully. Rates have been loaded for 1st customer Fresenius Kabi. Week of 6/23/25 - Provided a draft CRT Master Agreement with suggested changes/updates for FCC Legal review. Provided additional pricing detail to Viatris (initial CRT customer opportunity) upon their request. Week of 6/16/25 - Pricing has been presented to all 3 initial customers. Scheduling a meeting with 1st CRT customer (Fresenius Kabi) to review implementation timeline and plan. Week of 6/9/25 - Secured 1st CRT customer, with potential of 2.2M annualized incremental revenue. Continue meeting with legal for Master Agreement - building off current TCN (2-8 degree) Master Agreement. Week of 6/2/25 - Meeting scheduled 6/9 to review and complete the CRT Master Agreement with Legal team. Forklifts have been delivered. Week of 5/26/25 - Completed purchase of three forklifts from FXF - one for each FCC managed crossdock location. Working with Legal on drafting CRT pricing contract addendum for current customer Fresenius Kabi. Week of 5/19/25 - Met with 2 of the 3 initial customers and revising pricing based on feedback. Legal has approved the addendums for Reno and Fort Worth. Memphis has signed their addendum and it's currently with legal Week of 5/12/25 - QA Review completed by Kelli Ostertag (approved). Note: CCH has been approved and have emails to confirm Week of 5/05/25 - Jason Campbell met with Bonnie Voldeng and Jamie Cox to align with Healthcare Marketing Team. The documentation / CCH information has been updated and resubmitting to CCH greenlight. Week of 4/28/25 - Working through CCH process, need greenlight soon. Week of 4/14/25 - preparing CCH for L3 Surge that is scheduled on Friday 4/25. Week of 3/17/25 - preparing for L2 surge on Thursday 3/27. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-20 | 2026-08-28
Business w/ Tech Initiative: Multi DIM - Handling Unit Movement (HUM) | 26276 | 8349 | Business w/ Tech Initiative | FXF - Commercial | Freight | Carson Davidenko, Andy Jensen, Kelli Ostertag | Some Issues | **Latest Updates:** 4/24: Discrepancies delivered. Only remaining milestone is Grouping. 4/17: Same update as last week. 4/10: Same update as last week. 3:27: Same update as last week. 3/20: Same update as last week. 3/13: Duplicate tracking functionality deployed. 3/6: Same update as last week. 2/27: Same update as last week. 2/20: Same update as last week. 2/13: This week we....just kidding.....same update as last week. 2/6: Same update as last week. 2/2: Same update as last week. 1/26: Multi-DIM deployed to production. 1/16: Same update as last week. 1/9: Same update as last week. 1/2: Same update as last week. 12/26: Same update as last week. 12/22: Same update as last week. 12/12: Same update as last week. 12/8: Same update as last week. 12/1: Same update as last week. 11/21: Same update as last week. 11/14: Same update as last week. 11/7: Same update as last week. 10/31: Same update as last week. 10/24: Multi-DIM functionality testing being done in L3. L3 environment is unstable and has significantly delayed testing. 10/15: KO - Money Step date updated to 6/1/26 due to we will not roll into hubs without auto capability functional. Auto functionality is currently being tested and solutioned in HRO but is yet to be stable, so not able to move forward until it is. Also working with finance on re-baselining to FY25. 10/10: Same update as last week. 10/3: Same update as last week. 9/26: Skeleton shipment void has been deployed to production. 9/19: Same update as last week. 9/12: Same update as last week. 9/5: Same update as last week. 9/2: Same update as last week. 8/22: Same update as last week. 8/15: Same update as last week. A new effort to avoid doing this work has been raised by the Commercial portfolio. 8/8: Same update as last week. 8/1: Same update as last week. 7/25: Same update as last week. 7/18: Same update as last week. 7/11: Duplicate tracking continues to be a high-risk milestone. Estimates put completion at May 2026 with assumptions FXF separation won't be an impact. 7/5: Same update as last week. 6/27: Same update as last week. 6/20: Same update as last week. 6/13: Same update as last week. 6/6: Same update as last week. 5/30: Same update as last week. 5/23: Same update as last week. 5/16: SCO architecture continues on duplicate tracking number. Skeleton shipment void work has started. HUM Pilot Planning is being marked done as a deployment strategy has been refined. 5/2: Commercial declined to work the duplicate tracking number service so SCO will own it. SCO architecture is reviewing now so it can get assigned to a team. Commercial will still need to make integration changes. SCO development work continues. 4/25: Same update as last week. 4/18: Same update as last week. Commercial did assign some solutions level arch to do the lower level design. Development will likely be split among SCO and Commercial. 4/11: Same update as last week. Duplicate tracking number continues to be stalled. 4/7: Commercial ownership discussions ongoing, escalated to VP level. All other work that has not been called out above is on track. 3/28: Commercial ownership discussions ongoing, expect to hear a decision no later than 4/2. 3/21: Commercial solutions architecture is nearing completion. Discussions from leadership about who will build/own the solution are needed. 3/7: HUM development continues, Milestone 30760 still at risk due to architecture and development resources 2/28: Milestone 30760 has an architect assigned, determining impact to commercial portfolio applications. 2/21: Milestone 30760 (duplicate tracking numbers) is blocked, awaiting Commercial activities. 11/15: Currently being actively developed by IT. We are progressing as planned. Development on track to enable HRO HUM Pilot (target Dec 2nd) 11/05: Currently being actively developed by IT. We are progressing as planned. Development on track to enable HRO HUM Pilot (target Dec 2nd) 10/29: Currently being actively developed by IT. We are progressing as planned. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-01 | 2026-06-01
Business w/ Tech Initiative: NMFC Update |  | 105850 | Business w/ Tech Initiative | FXF - Commercial | Freight | Kevin Kotil, Tomm Brennan | On Track | 12/18/2025: - Leadership approved to put this initative on hold to prioritize SPIN and other higher priority items. 12/15/2025: - Awaiting decisions around potentially putting the initiatvie on hold until after spin and other decisions are made surrounding NMFC. 12/5/2025: - ARB Approved - Working through L2 checklist to move towards L3. - Submitted PPM Proposal 12/1/2025: - Awaiting ARB approval 11/20/2025: - Presented to Architecture Review Board, awaiting response of approval - Working towards completion of L2 Checklist 1/14/2025: - Received approval in Conceptual Architecture Peer Review, moving on to Architecture Review Board meeting next week. 11/05/2025: - Peer review scheduled for next friday 11/14 11/03/2025: - Finishing impacted ART's and estimates, expected to be complete 11/5/2025. 10/30/2025: - Working on estimated timing of the epics as well impacted Arts. 10/22/2025: - Near completion of conceptual architecture. Josh has listed out each EPIC along with their specific capabilities in EaSparx - Working with Leo Yan to put together a high level information flow map of how the NMFC prediction model works so Josh can add it to the EaSparx Diagaram - After completion of conceptual architecture (possibly late next week) we assess the level of work and estimates on how long the build will take 10/15/2025: - Continuing to work with Enterprise Architecture on the Solutions Architecture. - Josh Lombardo, from Enterprise Architecture Team, expects to to have the bulk of Solution Architecture complete by 10/20 and we plan to review/discuss on our 10/20 Monday Touchpoint Call. 10/01/2025: - Starting Solutions Architecture 9/23/2025: - Completed Decompostion - Solutions Architecture is beginning 9/16/2025: - Provided additional information to Business Architecture for Epic Description - Complete Decomposition possibly by next week 9/26 9/12/2025: - Continuing to work through Decomposition 9/4/2025: - No new updates 8/27/2025: - Continuing Architectural Decomp (delays due to competeing priorities ie. SPIN) 8/20/2025: - No new updates 8/11/2025: - No new updates 8/5/2025: - Sent over non functional requirements doc to Business Architecture team - No additional updates, call to go over the current scope of work with Ryan Plumlee tomorrow 7/30/2025: - Completed non functional requirements document - Decomp halted due to SPIN efforts this week - will resume next week. 7/22/2025: - Assess and Decomp projected to be completed mid august. 7/17/2025: - Sankeerth Finalized NMFC dashboard and sent over to LaDona and Greg for feedback. - Leo working to complete the automation of the data pipline (automate the training data, NMFC base tables, and NMFC prediction data pipelines) 7/14/2025: - Sankeerth is working to connect the data from the machine learning model to synapse (expected completion End of Week) - Once complete he will complete the MVP dashboard (expected to be complete by end of week/early next week) 7/8/2025: - Continuation of Decomp with Biz Arch - Finalizing mock up of Power BI report to hand over to OR to publish once the data pipeline is set up - (Tenative - will know more on EOD 7/9) Data pipeline should be complete by EOW 7/1/2025: - Continuing Decomp - Continue to build out interim Dashboard while we work on longer term solution with Architecture Decomp 6/24/2025: - Beginning architecture decomp 6/25 - 6/16/2025: - Potential architecture engagement beginning 6/23. - Brainstorm solutions on how to best manage feedback for training/re-training the NMFC prediction model in the future, based on feedback from Freight Analysis team. 6/11/2025: - Updating the high level architecture document to be prepared when we have architecture team engaged 6/9/2025: - Reviewing NMFC's that have "Null" class codes - Provided a list to of top opportunity shippers that frequently give bad/no NMFC codes 6/2/2025: - Met with Business Architecture to provide futher details on the scope/objective of the initat | E: L2 | On Hold | L2 & CCH | 2025-11-18 | 2026-04-30
Business w/ Tech Initiative: Nitro Backhaul Markets |  | 108334 | Business w/ Tech Initiative | FXF - Commercial | Freight | James Wright, David Gedlinske, Shane Huff | On Track | WE 8/8/25 - Continuing to coordinate proof of concept with thrid party customers, detailing out truckload agreements, applixcable lanes and volumes, rates, etc. WE 7/25/25 - Initiative moved to Commercial Pod. Continuing to coordinate and negotiate with POC customers for agreement and POC lane selection. Business case pending rates, lanes, and volume assessment completion and TL agreement signed by all parties. WE 5/2/25 - Working through DRIVE processes, building business case and teding to administrative steps in Planview. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Nitro Optimization |  | 105698 | Business w/ Tech Initiative | FXF - Commercial | Freight | Shane Huff, David Gedlinske, Jon Warner | On Track | 7/2/2025 - Initiative will be placed "On Hold" due to separation "stop-work" and entanglement assessments. No ETA to pick this work back up and continue at this time. 5/29/25 - Aligned with Data & A Port via triage on 5/21. pending team assemblage and scheduling of architectural calls with ESPM. 5/13/25 Proposal and UPR submitted in PPM. Request #851875; UPR #9012963. QA reviewed by Staci Prewitt, approved. 5/5/25 L1 Architecture Alignment complete. Copied Initiatve folder link to the Planview Initiative Support Architectural Documentation. Updated Impacted portfolios to reflect the L1 Architecture Assessment document. 5/1/25 Business case completion pending Legal review. L1 Architecture pending completion of business case. 3/26/25 * FEC/FXF optimization logic work ongoing (output eta adjusted to 4/4-14/11) * "Leverage Commercial team to fill back haul and partial PUP capacity" goal removed from initiative. Will become separate initiative. 3/18/25 * Dwx making adjustments to FEC/FXF optimization logic for future lane identification (next output eta 3/28-4/4). * Dwx updating HH/BH logic to better identify BH opportunties that are associated with BH Rail lanes. | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business Only Initiative: Volume Service Min Qualifiers | 97256 | 7173 | Business Only Initiative | FXF - Commercial | Freight | Mark Gundry, Debbie Hensley | On Track | 3.3.25: Submitted to L5 2.25.25: Surged to L5 - Approved - pending confirmation of costing (contribution vs total rev) 2.20.25: Surge to L5 1.27.25: Monitoring and compiling information. L5 push slated for February 1.6.25: Min Drop shipments will now flow through LTL Select (IT change implemented) 12.16: Succesfully moved to L4 12.9: Prepared to surge to L4 9/12/24 - ~800 shipments secured during pilot stage 12.3: Working with marketing to adjust LTLSelect to consume the new min drop factors (expand customer access to min drops on this platform) - effective DEC end of month 11.22: Adjusted Rev/ADS/NRB numbers based on 5 week pilot. Submitted/approved for L3 11.15.24: Will submit to L3 - completed month long pilot 10.29.24 Completed the 2nd week of the expected month long pilot 10.21.24 Surging to L2 today 10.23.24 | K: L5 | Completed | L5 | 2024-10-15 | 2024-12-09
Business Only Initiative: FXF OCR Delivery Receipt Surcharge Extraction | 88837 | 8277 | Business Only Initiative | FXF - Commercial | Freight | Timothy P. McFarland, Brienne Parker, Kevin Johnson | On Track | **Update for Week Ending 6/13/25** * WE 6/13/25 Totals * $235,515.80 **Update for Week Ending 6/13/25** * WE 6/13/25 Totals * $134,874.97 * M-W, Th and Fri outstanding due to IT Update causing bots to fall behind. **Update for Week Ending 6/6/25** * L5 Approved * WE 6/6/25 Totals * $287,831.54 **Update for Week Ending 5/23/25** * SL5 Submitted * WE 5/2/25 Totals * $133,126.65 - 3 days of reporting **Update for Week Ending 5/9/25** * L4 gained * Delays caused by Bot failues/shut and continued IT updates disrupting the process. Continued investigation into continuity issues ongoing. **Update for Week Ending 5/2/25** * L4 Submission made 4/28/25 * WE 5/2/25 Totals * $108,638.96 - 2.5 days of reporting * Delays caused by Bot failues/shut and continued IT updates disrupting the process. **Update for Week Ending 4/25/25** * L4 Submission made 4/28/25 * WE 4/25/25 Totals * $172,946.17 - 3.5 days of reporting * Delays caused by Bot failues/shut downs over the weekend. **Update for Week Ending 4/18/25** *Waiting on L4 Approval Finances reworked, Awaiting Alex/Laurie approval * Total revenue recapture for W/E 4/18/25 - $156,916.80 * 4/5 days reported, Friday 4/18 not yet reported * **Update for Week Ending 4/11/25** * Gained L3 Approval * Surged for L4 * Working to update forcast to exclude testing work Field Compliance did Last year. * Total revenue recapture for W/E 4/11/25 - $204,112.08 **Update for Week Ending 4/4/25** * Awaiting L3 Approval * Answered Questions around expected value calculations for Alex, April, and Laurie. * Total revenue recapture for W/E 4/4/25 - $125,090.81 * Delays in acutals caused by database upgrades * M-W, TH-F Reporting yet to be received. **Update for Week Ending 3/28/25** * Awaiting L3 Approval * Total revenue recapture for W/E 3/28/25 - $104,982.87 * Delays in acutals caused by database upgrades * M-T, W-F Reporting yet to be received. **Update for Week Ending 3/21/25** * Simplified KPI stood Up * Submitted for L3 * Total revenue recapture for W/E 3/21/25 - $150,131.47 * M-Th, Friday Reporting yet to be received. **Update for Week Ending 3/14/25** * Still waiting to get feedback from Alex post surge. * Securing data for KPI * Possible simplification of KPI * Total revenue recapture for W/E 3/7/25 - $187,265.14 **Update for Week Ending 3/7/25** * L3 Surge session on 3/6/25 * Received and answered follow up questions from Alex 3/7/25 * Received Total population data from imaging going back to 3/17/25 and will receive moving forward * Total revenue recapture for W/E 3/7/25 - $183,631.45 **Update for Week Ending 2/28/25** * Moved initiative from Bisness w/ Tech to Buisness only * Further researched data needed and owners for KPI's * Still seeking total population numbers to better understand how many DR's/shipments are being processed daily * Total revenue recapture for W/E 2/28/25 - $189.399.40 **Update for Week Ending 2/21/25** * Moved initiative from Bisness w/ Tech to Buisness only * Stood up milestones and KPI's * Starting 2/26 we should start receiving the data needed from the UK team both historically and moving forward * Will allow us to compute KPI's and better understand the process as a whole * Total revenue recapture for W/E 2/21/25 - $184,817.75 **Update for Week Ending 2/14/25** Technical issues slowed progress week ending 2/14/25. •Database outage 2/8/25 •Okta requirement updates 2/11/25 •Internal Bot Issues 2/12/25 Above issues have been addressed, Bot files have been archived and will run this week, 3 runs have been completed as of the morning of 2/17/25, but not yet worked/validated. •Total of 538 accessorial keywords added in those 3 runs •EEV of 538 keywords is about $52K •Actuals to follow validation and working of raw results from Corrections Bot **Update for Week Ending 2/7/25** * First week of running process end to end. Launced 2/3/25 * First Day Data 44,951 shipments reviewed, result | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-08-30 | 2025-05-16
Business Only Initiative: Detention w/ Power (Item 500-1.3.A) | 86884 | 8435 | Business Only Initiative | FXF - Commercial | Freight | Rachel Combs, Kelli Ostertag | On Track | 10/10/2025: Regression testing completed, all fixes deployed and relaunching new dashboard on 10/10. 10/3/2025: Additional fixes deployed this week and testing is underway. Vendor and Ops began testing 10/1-10/2. Will perform full regression testing and look to relauch New Detention Dashboard on 10/13. 9/26/2025: Production fixes deployed and successful testing of performance issues. Will continue Regression testing through this week with plan to relaunch app week of 10/6. 9/22/2025: Currently experiencing issues with performance on the Vendor Dashboard. Expecting a fix to be deployed 9/23. This is delaying Detention revenue capture. 9/15/2025: Minor fixed deployed to correct address and chargeable time. Potential issue with data for reporting, and meeting scheduled with Systems Development to review data. 9/8/2025: Business Case updated with new Baseline Values, will present to Finance for approval on 9/9. App is in Production, some minor updates were pushed to Prod 9/8, and positive feedback from Ops. Pending new reporting to be distributed to Ops, Vendor reporting is complete. 9/2/2025: Re-evaluating the Baseline Values and seeking approval to make adjustments based on FY25 Detention data. App is in production and communication schedule to be sent to Ops this week. 8/25/2025: UAT complete. Making some minor updates for reporting, and scheduled to surge 8/28/2025. 8/19/2025: Vendor UAT is underway with completion target date of 8/21/2025. L4 target set for 9/5/25. 8/11/2025: UAT completed by Ops, Vendor still unable access dashboard for UAT. w365 access is prohibiting the access to the dashboard. Firewall request has been approved to go through MPLS connection and should be completed within 1-2 days. This will allow direct access to the dashboard without W365 acces. Requested that vendors have UAT completed by 8/15 pending access issue is resolved. 8/4/2025: UAT feedback was provided to Systems Developers and updates made. Vendor issue with W365 access preventing access to the dashboard. It was recommended to now pursue Firewall access until W365 issue resolved. 7/28/2025: UAT is underway and notification sent to Communications Team for scheduling the communicaitons to the field. Access requests are being processed for the Production Dashboard for vendor access. 7/21/2025: PurpleID integration and server build is complete. Vendor access through W365 was successful. Next steps are to perform UAT this week. 7/14/2025: Update on Prod Server Build: UI and SQL servers built and being set up. Server admin working to get proxy and all the other settings for SQL server. Drivers are installed, but additional work needed to be done on the SQL server before we can replicate the database over to the new PROD server. The UI server is nearly ready, but will need to deploy, get the new DNS set, SSL cert requested / installed, and PurpleID integration completed. 7/7/2025: Update from Systems Development that some progress is being made on server build. 6/30/2025: Prod server build still pending as a result of IT roadblocks. Critical step of decommissioning bad server has been completed. 6/23/2025: Prod Server build pending due to IT roadblocks. Will likely need MD engagement for escalation. 6/16/2025: Attempts to get servers pushed through to build phase continue. There have been some roadblocks and MD is engaged with IT to gain traction. 6/9/2025: No timeline for server build, but they have been fully approved. 6/2/2025: There are still discussions going on regarding the server builds, but no ETA yet. I inquired on hitting a target of late June and was told that it would be very tight as there are other steps once server build is complete. Regarding Vendor access: W365 requests submitted for a sample of ADEC supervisors. Once approved, testing will take place before submitting access for other ADEC users. 5/27/2025: IT challenges address | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-08-16 | 2025-09-05
Business Only Initiative: New Release Program |  | 87626 | Business Only Initiative | FXF - Commercial | Freight | Marcia L. Collins, Brienne Parker | On Track | 6/4/25: May 2025 actuals entered on Financials tab. 5/5/25: April 2025 actuals entered on Financials tab. 4/8/25: March 2025 actuals entered on Financials tab. 3/28/25: Approved to move to L5. Monthly actuals will continue to be added to the financials. 3/20/25: Approved to move to L4 during surge today. Also approved to move to L5 once L4 is complete. Continue adding actuals monthly. 3/14/25: Uploaded the money step documentation. Ready for L4 surge on 3/20/25. 3/7/25: Updated milestones per EPM feedback. Freight Finance has advised to only complete Financials through FY26 at this time. 3/7/25: Approved for L3 during surge review on 3/6/25. 3/3/25: Updates to the financials have been made. Ready for L3 surge. 2/21/25: Updated financials to remove forecast where actuals have been entered. Approved to move to L2. 2/14/25: Updated business case uploaded into Planview and financials have been updated. 2/11/25: Updated business case sent to Curtis Long and Alex Thomas on 2/5/25. 1/31/25: Updated business case review scheduled for 2/3/25. 1/27/25: Met today to review release figures through Dec 24. Leadership asking to add Jan 25 to data and further analysis. 1/20/25: Meeting today to discuss business case. 1/13/25: Business case excel file attached to Planview and submitted for L2 approval. 1/6/25: Business case draft in excel has been modified per feedback from Finance. Review with Laurie Oswalt on 1/7/25. 12/13: * Business case draft in excel has been created. Reviewing with Laurie Oswalt on 12/16/24. 12/6: * Communication sent to Operations RVPs and MDs on 11/13/24 to advise them of the enhanced process •Releases, rollouts and volume surges has been added to the Freight Growth section of the US Field Sales Highspot page •The enhanced release process was communicated to all Sales on the 12/6/24 edition of Sales Weekly •Next steps: create business case 12/2: Freight Release, rollout and volume surge link added to the LTL Growth page on the US Fields Sales homepage. 12/2: L1 Approved. Working on business case. Program featuring in Sales weekly on 12/5. | K: L5 | Completed | L5 | 2024-10-25 | 2025-01-22
Business Only Initiative: Shiplify (manual portion) | 64296 | 8294 | Business Only Initiative | FXF - Commercial | Freight | Kurtis DeDear | On Track | 12/6: Revenue down due to less working days, and a Shiplify shipment decrease of approximately 22% MOM overall ADS decrease of ~18%. 9/27: reforecast completed with approval from leadership. 9/20: Reforecast data analyzed and awaiting approval from leadership for new amount. 9/13: Analyzing data for potential reforecast, with potential adjustments included. WE 7/12 Revenue capture continuing, report generated, will have to be reworked to understand revenue decline May to June. Preliminarily looks like customer renegotiations happening. we 7/5 Continual revenue capture, will have report created to help determine where the decrease of revenue is coming from, May to June expected to soften cyclically, will be analyzing to see if customers are renegotiating contracts. 12/4 Impacts tab updated to reflect anticipated automation date to change over, the recurring benefit and cost have been pushed to 0 to reflect. first month of Shiplify is completed $ ~ 4.3M in November 45,350 shipments total processed. Contract signed 11/8 manual processing of these bills underway. November number estimated to 3.5M with late start of process, and holiday impending. Other figures have been updated to reflect the anticipated revenue numbers we've projected. | K: L5 | Completed | L5 | 2023-07-03 | 2023-11-10
Business Only Initiative: SPEAR | 83942 | 7711 | Business Only Initiative | FXF - Commercial | Freight | Sudheer Kelam, Nicole Long | On Track | 6/24/25: Entered May actuals and users are using new enhancements without any issues. 6/3/25: L4 surge completed 5/22/25: Attended Surge call on 5/22/25 seeking for L4 5/12/25: We are doing a time study to measure the improvment with new enhancements and preparing for L4 4/21/25: No updates 4/16/25: All the enhancements deployment is complete including documentation and education. 4/7/25: Phase 4 enhancements move to production is scheduled to occur on 4/10/2025. 3/31/25: Planning to deploy a few things on Apr 10 after successful testing. 3/10/25: Developing Phase 4 enhancements 3/4/25: No much updates this week 2/26/25: We released many enhancements to all the users on 2/19/25 successfully after careful testing and documentation. 2/4/25: We are testing a few enhancements and getting ready to go to Prod in 10 more days. Also, submitted a few invoices to pay the vendor. 1/27/25: Entered Actual $ last week and working on a few SPEAR enhancements testing this week. 1/20/25: Entered to L3. Working on Actual $$’s for Jun 2024 through Dec 2024 1/14/25: Prepare for L3 surge call. Met with Brie today to discuss this. 1/6/25: Entered KPI metrics and updated timeline. Preparing for Surge call. 12/10/24: Still working on L3 checklist 12/3/24: Latest enhancements and fixes under change request CHG0870725 have been implemented with no issues. Change request closed as of 12/3. 12/2/24: I (Sudheer) came back from parental leave and will start working on this initiative this week. 11/26/24: Backup IO on Rating Modernization has been updated to be Sudheer Kelam. 11/20/24: Change request CHG0870725 for latest enhancements and fixes in SPEAR tool has been moved to 'implement' status and should be complete as of 11/23. 11/18/24: Nicole Long added as a backup IO for Rating Modernization; added it as an 'Investment Dependency' in Planview. 11/18/24: Feedback request still pending; still waiting to be added as backup IO on Rating Modernization. Once added, will add that initiative to 'Investment Dependencies' in Planview. 11/11/24: Submitted change request CHG0870725 for latest enhancements and fixes in SPEAR tool on 11/6. As of 11/11, all IT, FEC leadership and change management approvals have been granted. Request is currently in 'scheduled' status, pending IT delivery. Nicole Long will meet with Brienne Parker this week to determine how to enter 'Investment Dependencies' into Planview. 9/26/24: 1. I will list the items included in each of milestones in respective description sectioin 2. Create education/communication milestones 3. Finish business case tab 4. Signed up for DRIVE - FLC classes part 1 and part 2 9/16/24: Still working on L2 checklist. 9/9/24: Working on L2 checklist. 9/2/24: "Phase 1 Enhancements" milestone completed successfully and we released to Production on 8/29/24 8/19/24: Worked on milestones 8/5/24: Completed Overview and Impacts tab 7/15/24: Still figuring out an efficient way to come up with "Net recurring benefits" number. I met with Debbie Hensley last week and planning to meet with some others this week to brainstorm. 7/8/24: Planning to complete "Overview" tab by end of tomorrow. I planning to meet with a few RQ team members to figure out revenue generation 6/13/24: on hold until more details are available. | K: L5 | Completed | L5 | 2024-06-03 | 2025-05-30
Business w/ Tech Initiative: Rating Modernization | 26156 | 8291 | Business w/ Tech Initiative | FXF - Commercial | Freight | Kurtis DeDear, Sudheer Kelam | On Track | 2-6 RM development on going. replacement for edd and dual debtor development work on going. 1-30 RM development on going. replacement for edd and dual debtor development work on going. Testing for edd phase 1 done and successful. 1-23 RM development on going. replacement for edd and dual debtor development work on going. Testing for edd and dual debtor starting: Rsplits causing issues for CA testing. 1-16 RM development on going. replacement for edd and dual debtor development work on going. Testing for edd and dual debtor starting 1-9 RM development on going. replacement for edd and dual debtor development work on going. 12-26 1-2 RM development on going. 26 S&P rates loaded should allow for no disruption of rating. 12-19 RM development on going. Some work within L2/L3 happening to enable multiple SP rates to be live, this product should move to PROD week of 12-26. Implementation of this allows the enablement of GRI rates for S&P. 12-12 RM development on going. Some work within L2/L3 happening to enable multiple SP rates to be live and work through kinks to ensure rating with newest rating engine works. 12-5 RM development on going. Decisions are being made for which customers will be allowed on an expanded pilot. Further development needed to allow a company wide launch. Rate files for 2026 SP have been completed and initial testing good in L3, GRI testing will be completed within other applications to ensure the rating system continues to work and rates are as expected. 11-28 RM development on going. Decisions are being made for which customers will be allowed on an expanded pilot. Further development needed to allow a company wide launch. Rate files for 2026 SP have been completed and initial testing good in L3 11-14 RM development on going. Decisions are being made for which customers will be allowed on an expanded pilot. Further development needed to allow a company wide launch. 11-7 RM development on going. Space and Pace in production continued monitoring for initial launch to ensure there aren't issues. Work being assessed for follow ups that didn't meet the initial launch. Further customer evaluations are happening to see who fits the profile and will allow for further revenue capture. Reviews on going for customers that will be brought on, limitations dependent on D83 splits and dual debtor work to be finished to broaden the launch much further. 10-31 RM development on going. Space and Pace in production continued monitoring for initial launch to ensure there aren't issues. Work being assessed for follow ups that didn't meet the initial launch. Further customer evaluations are happening to see who fits the profile and will allow for further revenue capture. 10-24 RM development on going. Space and Pace in production continued monitoring for initial launch to ensure there aren't issues. Work being assessed for follow ups that didn't meet the initial launch. Further customer evaluations are happening to see who fits the profile and will allow for further revenue capture. Decisions on retrieving pricing and fuel 10-17 RM development on going. Space and Pace in production continued monitoring for initial launch to ensure there aren't issues. Work being assessed for follow ups that didn't meet the initial launch. Further customer evaluations are happening to see who fits the profile and will allow for further revenue capture. 10-10 RM development on going. Space and Pace in production continued monitoring for initial launch to ensure there aren't issues. Work being assessed for follow ups that didn't meet the initial launch. Further customer evaluations are happening to see who fits the profile and will allow for further revenue capture. Successful first month of Revenue capture ~$48k 10-3 RM development on going. Space and Pace in production continued monitoring for initial launch to ensure there aren't issues. Work being assessed for follow ups that didn't meet the initial launch. Further | G: L3 | Active | TEMP L3 - Enter L3 | 2023-06-01 | 2027-04-26
Business w/ Tech Initiative: EDI Optimization |  | 88873 | Business w/ Tech Initiative | FXF - Commercial | Freight | Debbie Hensley | On Track | 8.19 Phase 1 of the project will focus on the seperation and will be tracked under Project Fairway. Phase 2 will be for FY26, the scope of the project has been updated to reflect work starting then. 8.11 Reviewed with Finance it was discussed that the first year of this initiative should be moved over to projec Fairway with the remaining work tracked in Planview after 5.31.26. 8.4 VRM has been completed by Cleo, Invoicing profile has been completed. Meeting held to review Cleo's Transactional Monitoring & Management Concierge. Meeting scheduled this week to review Customer Communications with Marketing, this will be the communication letting customers know that they will be receiving additional information about changes we will be requesting as we move forward with our EDI transformation 7.29 Connectivity testing has been completed succesfully. VRM has been submitted, pending feedback on approvals. 7.21 Sharing backend information and technical discussions are on-going with internal FX teams and with the vendor 7.15 Team has met, building out the freight side, stand up calls have been established and samples of OB 204 and IB 990 Maps have been sent to Cleo. Finishing the financials for the overall project. 6/30 Contract has been signed, Implementation plan to be complete in 10 months has been established, will be holding kick-off project meetings this week. 6.23 Vendor contracts have been submitted in Encore and are going through the approval process. Legal is involved and has started the redline process. 6.16 Legal and leadership reviewing proposal and info Sec review is being submitted. 6.9 Vendor proposal has been submitted, leadership is reviewing 6.2 Meeting with vendor scheduled this week to review proposal. 2nd venddor has been engaged and is requesting changes to the mnda. 4.28 Meeting held to review the Invoice Adjustment Process project plan, will have a demo on existing process next week Meeting with vendor & I/T, will be pulling together a system/process overview to discuss on our next call, reaching out to second vendor for engagement too. 4.14 Working on Invoice Adjustment Process, Anne is working with the leads to schedule next meeting. Meeting scheduled with I/T to discuss high-level architect view for meeting with potential solution provider. 4.7 Working through the requirements, due to vacations have seen a little delay. 3.24 Met with Solution Provider, discussed options for full and partial support. Pulling together some additional information for a second meeting to go into more specific support areas. 3.18 Meeting held with EDI Solutions Provider, another one scheduled for this week. Updating Planview for next steps. 3.10.25 Meeting being held this week for the EDI Invoice Adjustment Process Reached out to an EDI Solutions Provider to set up a meeting, MNDA has been sent, once their legal reviews and signs we will move forward with scheduling a meeting. 3.3.25 Ability to's will be sent this week for review. 2.24.25 Wrapping up the ability to's, prior to uploading to planview I will be reviewing with EDI contacts. 1.27.25 Proposal for implementing an EDI Invoice Adjustment process was shared with the Manager of Invoice Analysis. The plan was met with approvals to move to the next stage. Gathering additional requirements to put an implementation plan together. EDI Dashboard data/applications/tables were obtained and compliled. Scheduling a meeting for next steps for development 1/21/25 Researching alternatives for EDI Solutions Mapping EDI Data for the Dashboard Pulling EDI help information for updates and process improvements for Sales material Met with EDI inovicing for Invoice Adjustment Process, meeting with additional groups for plan review **1/13/25** Working on identifying application and data sources for EDI Dashboard, holding meeting with EDI invoicing to start mapping out EDI Invoice Adjustment Process. 1.6.25 - Moving foward with EDI Dashboard analysis, identifying the EDI | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Mexico Volume Services | 86886 | 7171 | Business w/ Tech Initiative | FXF - Commercial | Freight | Mark Gundry, Debbie Hensley | Attention Needed | 7/11/2025: Per Freight Domain Lead, initiative to be paused until further notice 6/18/25 - QA for SL2 performed by Kelli Ostertag - approved to surge on 6/19 6.18.25: Currently undergoing the QA Assesment and planning to surge to L2 asap 6.13.25: Initial Arch Review Complete 6.2.25: No updates 5.15.25: No updates to provide. Still awaiting prioritization, currently #225... 4.15.25: Submitted Lean Business Case required documents 4.7.25: Building out the Demand shaping section and ability to's for MX VS. Will complete this week 3.10.25: Reached out to Bizz arch 3.3 who stated concern with commercial request and said we may not get a good priority list for several more weeks. I will follow up 3/14 2.25.25: Still awaiting prioritization arch review 2.18.25: No new updates 2.3.25: 86886 is on the list of FXF inits currently being reviewed by FXF leadership to validate priority ranking 1.27.24: Domain arch rank 244; Filling out AB2/scenario documents 1.6.24: Domain Arch review still pending 12.18.24: Domain Arch placement 155/306 - strategy ID 7171 - assigned Medium benefit level w/ 4.45 benfit score 12.9.24: Awaiting priotitization for domain arch review 12.3.24: Awaiting priotitization for domain arch review 11.15.24: Obtained costing values for MX PD, dray and LH for Vols LF 11.11.24: Awaiting prioritization for domain arch review. Currently 30th on the list 10.29.24 - Picked up first two volume service Mexico shipments as a pilot 10.10.24: Surged to L2 10.6.24: requested support from FXF Costing to create cost factors required to rate VS shipments | E: L2 | On Hold | L2 | 2024-07-09 | 2025-06-03
Business Only Initiative: Dispute Resolution | 93385 | 9192 | Business Only Initiative | FXF - Commercial | Freight | Rudolph J. Pienaar, Eric Boyle | On Track | 9/23/2025: Domain lead request that this initiative be canceled due to the FXF transition. Aligned with FXF leadership to confirm that 9192 should be canceled. 7/3/2025: Per Freight Domain Lead, initiative to be paused until further notice. 3/10: 1. Customer Survey Post Dispute Resolution - Targeting full survey volume by March. Formalizing parcel expansion and the audit process through EBSHub. 2. Mapping Current Dispute Routing and Input Channels - Complete 3. Dispute Type Study - Computing KPIs and SLA history to operationalize monthly executive reporting beyond current CESC Dispute Turn-Around time metrics. Targeting Q4. 4. Develop Standarized Dispute Responses - Complete. 5. SR&A Root Cause Drill Down - Complete 6. Reweigh Support Pilot - Pilot identified continued need to require 2 pieces of documentation for Reweigh dispute analysis. Team is looking into alternative improvements." 3/3 - Preparing for L3 submission. 1. Customer Survey Post Dispute Resolution - Targeting full survey volume by March. Formalizing parcel expansion and the audit process through EBSHub. 2. Mapping Current Dispute Routing and Input Channels - Complete 3. Dispute Type Study - Computing KPIs and SLA history to operationalize monthly executive reporting beyond current CESC Dispute Turn-Around time metrics. Targeting Q4. 4. Develop Standarized Dispute Responses - Complete. 5. SR&A Root Cause Drill Down - Complete 6. Reweigh Support Pilot - Pilot identified continued need to require 2 pieces of documentation for Reweigh dispute analysis. Team is looking into alternative improvements." 12/30 - Preparing for L3 submission. 1. SR&A Root Cause Drill Down - Complete 2. Mapping Current Dispute Routing and Input Channels - Process implementation Complete. Working to identify and measure impact. 3. Dispute Type Study - High level analytics and 2 Rounds of sampling completed. Next steps to analyze findings into executive summary. 4. Develop Standarized Dispute Responses - Complete 5. Customer Survey Post Dispute Resolution - Refining SHOT Survey for FXF Post Dispute Resolution. Will submit to legal once finalized. Working iSell and Qualtrics to implement. 6. Reweigh Support Pilot - Pilot starting Jan FY25 to study impact on final resolution based on using only one form of documentation if customer does not initally provide required two documents. 12/16 - Preparing for L3 submission. 1. SR&A Root Cause Drill Down - Complete 2. Mapping Current Dispute Routing and Input Channels - Enhanced warm handoff procedures sent out to team leads 3. Dispute Type Study - Analyzing round two of sampling. 4. Develop Standarized Dispute Responses - Revised Standardized responses approved and sent out. 5. Customer Survey Post Dispute Resolution - Rough draft developed. iSell and Qualtrics alignment by 12/20. 12/9 - Preparing for L3 submission. 1. SR&A Root Cause Drill Down - Complete 2. Mapping Current Dispute Routing and Input Channels - Enhanced warm handoff procedures sent out to team leads 3. Dispute Type Study - Round two of sampling in progress. 4. Develop Standarized Dispute Responses - Revised Standardized responses approved and sent out. 5. Customer Survey Post Dispute Resolution - Rough draft of survey format in development.. 12/2 - Preparing for L3 submission. 1. SR&A Root Cause Drill Down - Complete 2. Mapping Current Dispute Routing and Input Channels - Engaged team leads and vendors in warm handoff procedure training and adoption. 3. Dispute Type Study - Initial round of sampling complete. Round 2 of sampling next. 4. Develop Standarized Dispute Responses - Standardized responses and additional info requests implemented across EBS team members and vendors. 5. Customer Survey Post Dispute Resolution - Project kick-off on 12/5. " 11/11 -Moved to L2 1. SR&A Root Cause Drill Down - Complete 2. Mapping Current Dispute Routing and Input Channels - Pilot in progress. Actively engaging agents and vendors for training and adoption. Ta | E: L2 | Cancelled | L2 | 2024-09-24 | 2025-05-01
Business w/ Tech Initiative: Detention w/o Power (Item 500-1.3.B) | 86885 | 8436 | Business w/ Tech Initiative | FXF - Commercial | Freight | Rachel Combs | Some Issues | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 6/16/2025: No updates, pending prioritization direction. 6/9/2025: No updates, pending prioritization direction. 5/20/2025: Recommendation received from BA & IT to review prioritization and potentially place on hold. Discussion with Curtis & Heather determined this should remain as an active initiative and be included in the domain review activities to determine if work remains or is removed. 5/12/2025: Pending guidance from Executive leadership on prioritization against Separation work. 5/5/2025: Discussion with Ryan Plumlee about prioritization and details of initiative. It was recommended to discuss with Heather Rorie on where priority falls. 4/28/2025: Awaiting next meeting with Marketing. 4/21/2025: Received customer data and putting presentation together for next meeting with Marketing. ¦4/14/2025: Held meeting with Bonnie V. Susan P, Mandy B. and went over inititiave. Decision to pull customer data and identify who top customers are before presenting to DJ Miller 4/7/2025: Submitted CCH review and awaiting date to be scheduled with DJ Miller for greenlight 3/31/2025: Updated Baseline amounts for FY25 and submitted CCH responses. 3/24/2025: Approved to move to L2, but received notification needing Value Prop. Will connect with Finance for direction 3/17/2025: Awaiting approval to surge to L2: Business case updated with appropriate NRB and Soft benefit. 3/10/2025: Awaiting direction on EA. Have updated to SCO portfolio, and updated forecast. 3/3/20025: EA review completed and advised to move to SCO Portfoltio, not Commercial. Awaiting direction from Finance before submitting to next step. 2/24/2025: Architecture review scheduled for today. 2/17/2025: Awating call schedule for Arch presentation 2/10/2025: Awaiting callback on Architecture review 2/3/2025: Submitted slides for Architecture Review. 1/27/2025: Making final edits to Architecture documenting business scenarios. 1/20/2025: Drafting business scenarios for Architecture review. 1/13/2025: Drafting scenarios to prep for Architecture discussion 1/6/2025: Pending architecture feedback and prioritization 12/20/2024: Pending architecture feedback and prioritization 12/13/2024: Pending architecture feedback and prioritization 12/6/2024: Pending architecture feedback and prioritization 11/29/2024: Pending architecture feedback and prioritization. 11/22/2024: Pending architecture feedback and prioritization. 11/12/2024: Updated Portfolio for Commercial. Pending Enterprise Architecture prioritization | E: L2 | On Hold | L2 & CCH | 2024-08-30 | 2024-12-18
Business w/ Tech Initiative: New Pricing System for FedEx Freight |  | 92197 | Business w/ Tech Initiative | FXF - Commercial | Freight | Sudheer Kelam, Michelle L. Rogers, David Gedlinske | On Track | 8/19/2025: Leadership reviewed and determined work is included within Project Fairway scope, initiative# 143551 Project Fairway - Commercial Separation Enablement. This initiative is no longer required. 7/30/25: Freight Business Architect Amy Dixon is expected to complete her work by the end of this week. She is currently finalizing the fuel capabilities and the list of non-functional requirements. 7/15/25: I'm still collaborating with Amy Dixon, Rick Egleston, and Mike Paradowski to finalize the changes needed in the FXF system due to the new pricing system being developed for FXF. 6/23/25: Completed Enterprise Arch review and waiting on Demand Costing process 6/3/25: Submitted PPM with Request #: 856734 5/22/25: Preparing for L3, we have architecture review this Friday 5/23 5/13/25: Pending enterprise architecture review and preparing for CCH review and L3 submission 4/30/25 QA Review completed by Kelli Ostertag, approved. Scheduled for L2 surge on 5/1/25. 4/29/25: Preparing for QA Review and L2 surge 4/21/25: Completed business case template and will discuss with Brie about next steps. 4/16/25: Building business case template and discused next steps with Brie on 4/15/25 4/7/25: Michelle Rogers and Gabe Beyl presented recommendations to separation office and ePRS IT team and waiting to receive their feedback. 3/31/25: Michelle and Gabe are presenting to spearation office on 4Apr2025 about our recommendations on New Pricing System 3/10/25: We are waiting for proposals from external vendors 3/4/25: No much updates this week 2/26/25: After evaluating multiple vendor off-the-shelf tools, Michelle and I submitted our recommendations to Heather for review. Still waiting on a proposal from 1 more vendor before we make a decision on our path forward: purchse or build. 2/4/25: Michelle and I are working to provide high level recommendations to VP Heather Rorie by mid of this month. We are also attending demos from multiple vendors to analyse what fits best for our need. 1/27/2025: Plannig to meet with Finance this week. Working with vendors Conga, Exusia and CoForge for MNDA and Demos etc. 1/20/2025: Working on business case template. Still exploring different tools and find out requirements. 1/14/2025: Waiting for enterprise architect team to reach to us. Sudheer is working on business case template and exploring different tools/options to do this project. 01/08/2025: Sudheer and Michelle attended Triage meeting today and our requested got approved by the team. We entered into L1 gate today. | E: L2 | Cancelled | L2 & CCH | 2025-06-02 | 2026-06-01
Business Only Initiative: 5,000 ADS |  | 87287 | Business Only Initiative | FXF - Commercial | Freight | Brienne Parker, Vickie R. Odom | On Track | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 3/31/25: No new update this week 3/24/25: No new update this week 3/17/25: No chnages from last week 3/10/25: Per Finance guideance, deleted Feb 2025 forecast as actuals won't be available until April 2025 3/3/25: No changes. Awaiting February 2025 results to enter into Planview. 2/24/25: No change from last week. 2/17/25; Received approval from Alex Thomas in Finace for reforecast and updated Financials tab 2/10/25: Reforecast complete and approved by Heather Rorie & Tyler Kidder. Awaiting feedback from Alex Thomas in Finance. 2/3/25: No changes from last week. 1/27/25: No change from last week. Officially in L3. Will start reporting actuals next month. 1/20/25: Officially in L3. Will start reporting actuals next month 1/13/25: Awaiting SVP Finance approval for L3 1/6/25: L2 approvals obtained. Need steps to finish L2 to move to L3. 12/16: Awaiting SVP Finance approval 12/9: Updated NRB per Alex Thomas' request. Awaiting Finance approval 12/2: Approved in L1. Surging for L2 on 12/2. 11/19: Beginning business case build. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-05-30 | 2025-05-30
Business Only Initiative: Top 200 Declining Accounts |  | 87620 | Business Only Initiative | FXF - Commercial | Freight | Brienne Parker, Christine Ruff | On Track | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 11/19: Beginning business case build. 12/2: Adding case details 12/9: Updated NRB 12/16: Moved to L3 02/05: Reforecast Top 200 numbers 03/07: No actuals for Feb reported yet 4/17: No actuals for March available yet | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-10-21 | 2025-05-30
Business Only Initiative: Capacity Load Accounts |  | 87623 | Business Only Initiative | FXF - Commercial | Freight | Brienne Parker, James Wright | On Track | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 3/7/25: Updated financials to remove February Forecast Revenue, Cost, & ADS and will add Actuals once RQ obtains February Costing Data. 1/13/25: Updated financials & KPI's through FY26; corrected Soft P&L to "0"; submitted for L3 review 12/11/24: Updated NRB to OI 12/2/24: Approved in L1. Surging for L2 on 12/2. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-05-30 | 2025-05-30
Business Only Initiative: Pricing |  | 88866 | Business Only Initiative | FXF - Commercial | Freight | Whitney Rupp | On Track | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 6/24 - Pending update on costing delay from pricing. 6/16 - KPIs received and updated. 6/9 - Requested ADS (KPIs) for pilot customers for May. Up-to-date costing is still pending. 6/4 - No new update. 5/12 - Requested ADS (KPIs) for State-to-State pilot customers for April. I have also requested an updated target date for Feb costing if available. 4/25 - Pending costing to enter actuals for Feb and March. 4/14 - March actuals added and money step marked as complete. 3/31 - New baselines established using FY25 data. 3/17 - No new updates. 3/10 - Financials added for Feb. 2/3 - 2/24 - No new updates. 1/27 - Currently in L3; no new updates. 1/20 - Surged and approved to move to L3. 1/13 - Remaining information provided to Alex, pending move to L2. Tentative plan to surge for L3 on Thursday, working to compile remaining financials. 12/23 - Pending updated business case with revenue per shipment added for Alex to review. 12/16 - Reviewed business case with Laurie Oswalt on 12/16. Continue compiling information in preparation for surge on 12/19. 12/9 - Preparing to Surge on 12/12. Establishing baseline meaasurements, expected benefits and goal Money Step Date. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-06-30 | 2025-06-30
Business Only Initiative: Billing and Invoicing |  | 88869 | Business Only Initiative | FXF - Commercial | Freight | Whitney Rupp | On Track | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 6/24 - No new update. 6/16 - ADS (KPIs) entered for May. 6/9 - Requested ADS (KPIs) for May Financials. 6/4 - No new update. 5/12 - Requested KPIs for April 2025 Financials. 4/25 - No new update. 4/14 - March actuals added. 3/31 - Manager hired/announced. Manager working to hire SPOC team. 3/17 - No new update. 3/10 - February financials entered. 2/24 - No new update. 2/17 - SPOC manager position posted. 2/10 - SPOC effort continues. 2/3 - Moved to L3. 1/27 - Pending decision from Finance on need for KPIs included. 1/20 - Surged and approved to move to L3. 1/13 - Preparing to surge to L3 on Thursday. Completed CCH review and compiling financials. 12/23 - Approved for move to L2. Working on next steps. 12/16 - Reviewed business case with Laurie Oswalt on 12/16. Continue compiling information in preparation for surge on 12/19. 12/9 - Preparing to Surge on 12/12. Establishing baseline meaasurements, expected benefits and goal Money Step Date. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-10-01 | 2025-10-01
Business Only Initiative: Shipping Engagement |  | 88870 | Business Only Initiative | FXF - Commercial | Freight | Debbie Hensley, Susan A. Patrone | On Track | 6/30/2025: Per Freight Domain Lead, initiative to be paused until further notice. 6.23 UAT is still ongoing 6.16 still working through UAT 6.2 UAT is ongoing, new users have been added to the group. 5.5 Testing has slowed due to some vacations, on track to complete by eom 4.28 Meeting held to discuss testing on EDI Dashboard, we are going to continue testing this week and schedule a call with the developer regarding observations. 4.21 The Sales handout has been published to HighSpot and is complete. 4.14 - Testing has started for the EDI Dashboard, meeting scheduled for next week to review, then we will open it up to additional business/Sales testers. Sales Handout - pending final edit review with Highspot and tentative date to publish. 4/7 - Sales Handout with edits sent back to Katie(HIghspot) - pending next steps from the team on approval and publishing. Meeting this week to review testing, access has been granted for user(s) 3/30 - working on final edits for Highspot/Sales handout. Starting testing of EDI Dashboard this week 3/24/2025 - Working on updating Business with Tech to Business only impact, or do we cancel the initiative/place on hold. 3/17/2025 Sales Handout - final edits being incorporated and will be sent to Sales Playbook for review. Clarification from Legal on what can be included regarding comparision to competitive charges. 3.10.25 EDI Dashboard is progressing, still on track for a demo on 3.20 Sales Handout - final edits being incorporated and will be sent to Sales Playbook for review. 3/3/2025 EDI Dashboard - next call scheduled for 3.20 to review the dashboard. Have confirmed with small user group that they will be able/willing to test it.**reminder, this is an internal dashboard NMFTA Standardized eBOL/Finalized this will be absorbed in the Run, Grow, Transform Freight work. No future updates for Shipping Engagement. Rate Transparancy - No further work under Shipping Engagement for this workstream at this time. Sales Handout - reviewing final edits recommended by Playbook including the "why's" of the industry wide surcharges. HR request to review draft with Will Washington. Targeting a draft back to the Sales Playbook team by early next week. 2.24.25 EDI Dashboard - next call scheduled for 3.20 to review the dashboard. Have confirmed with small user group that they will be able/willing to test it.**reminder, this is an internal dashboard NMFTA Standardized eBOL/Finalized this will be absorbed in the Run, Grow, Transform Freight work. No future updates for Shipping Engagement. Sales Handout - reviewing final edits recommended by Playbook including the "why's" of the industry wide surcharges. HR request to review draft with Will Washington. 2/17/2025 NMFTA Standardized eBOL/Finalized internal managment review week of 2/14. Findings to be shared with team within the next week. Per BCV this will be absorbed in the Run, Grow, Transform Freight work. EDI Dashboard data mappings along with test data to data columns has been sent to the developer. Next meeting scheduled for end of this week. 2/11/2025 EDI Dashboard - Still in development process. Target completion TBD. Root Cause analysis of declining Driver and Sales Reps scores. Markeing is reviewing RYDE research. Form QAT on Customer Servcice/Entry point for FedEx Freight. Owner TBD. NMFTA - finalizing presentation this week for internal review and next steps for sharing out. Sales Handout - reviewing final edits recommended by Playbook. Susan and Kelly Crow to review and target end of February to close out. 2/4/2025 No Updates 2/11 Rate Transparancy - Bonnie and Heather discussed, pending additional data review before moving forward to present as part of the Brie follow ups. 1/28/25 Rate Transparancy - A list of gaps for API rating have been identified and provided to RQ for validation if the rates are available in Freight Rating and/or FXFR (translation from the frontend to the backend systems). Pending result | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-11-01 | 2024-12-19
Business w/ Tech Initiative: Capacity Management Quoting Tool 2.0 | 26155 | 6680 | Business w/ Tech Initiative | FXF - Commercial | Freight | Jessie Kilgore, Debbie Hensley, Mark Gundry | On Track | 2.4.26 •Customized Solutions (CSQT) oExecuted a successful production release on Tuesday January 27th oiSPI team deployed their initial release to production on Monday January 26th oBilling integration dev/testing activities are in progress as we work closely with the iSPI and FDS teams (no current blockers) oRequirement clarification continues for delivered shipments and the operational visibility capabilities oDevelopment activities remain focused on MVP2 committed scope for the current PI •MultiModal (CMQT) oMigration of MMTL solution from Azure to the CMQT architecture is in-progress oAdditional changes to the quote sheet T&Cs are pending full approvals from business and legal 1.14.26 •Customized Solutions (CSQT) oNext production release planned for Tuesday January 13th oiSPI team planning to complete their integration efforts and deploy to production on January 26th oRequired billing integration activities are in progress as we work closely with the iSPI and FDS teams (no current blockers) oRequirement clarification in-progress for mass quotes, delivered shipments and external API oOther development/testing activities are focused on MVP2 Beta scope •MultiModal oMigration of MMTL solution from Azure to the CMQT architecture is in-progress - continue to support regression testing activities oAdditional changes to the quote sheet T&Cs are pending full approvals from business and legal 12.19.25 Customized Solutions (CSQT) oBilling team has re-engaged and planning to complete required activities by the end of January 2026 oAll MVP1 fast-follow items have been completed and are scheduled to be in the next production release oKey upcoming activities: UAT support, implementation of post-MVP1 functionality, and next steps for external API capability MultiModal oMigration of MMTL solution from Azure to the CMQT architecture is in-progress - expected to support regression testing during week of December 22nd oAdditional changes to the quote sheet T&Cs are pending full approvals from business and legal 12.3.25 The Dev team presented a proposed solution, but it introduces significant risks for our customers and places excessive responsibility on billers to validate quotes. The Business has requested identification and documentation of the gaps between the two proposed options and an assessment of whether a better solution can be developed. Additional meetings are scheduled and ongoing this week. 11.26.25 Met with development teams to see if we could move forward with the iSPI integration. Feedback is: "plan to get iSPI changes ready for L3 testing by mid-December. If there are no issues reported during testing, we will move the code to Prod by 01/17." 11.21.25 POC for iSPI alternate approach was completed, it did not provide the functionality that was needed. •We were able to successfully generate a Freight Bill by populating the ABOL (Automated Bill of Lading) and SHIPMENT tables. However, we could not persist a custom ETA date which is MANDATORY for Priority Plus guaranteed shipments. •The POC does introduce another potential approach to integrate with billing, however, this also would require ISPI development work to be done. 11.9.25 iSPI has notified us that they are unable to complete ingegration for CSQT until after separation. We have a meeting on 11.10.25 to review what work is pending and a timeline if work was to continue. This is a major requirement for the project and does prevent adoption of the CSQT work. 10.31.25 CSQT Currently in UAT, have had a delay in deploying to production, now expected to deploy 10.31.25. Once this is deployed, we will be able to close our two late milestones, as they are waiting for this functionality to move into prod. 10.24.25 CMQT * Next production release scheduled for Monday, Oct 27th to deploy CSQT 1.0 into production * CSQT is in UAT 10.17 **CMQT 2.0** * Next production release scheduled for Monday, Oct 20th to mitigate 2 RAP obserations AN | G: L3 | Active | TEMP L3 - Enter L3 | 2023-06-15 | 2026-12-22
Business Only Initiative: International Freight Bill Entry Enhancements | 86226 | 7598 | Business Only Initiative | FXF - Commercial | Freight | Jenn Mollric, Matt Cheyney | Some Issues | This initiative is dependent on Imaging Modernization - OCR and IBEX work (Systems Development, blocked by COLO move). We cannot provide a clear L4 date without clarity on OCR and IBEX. | G: L3 | On Hold | L3 Feedback Requested | 2026-01-16 | 2026-01-16
Business Only Initiative: FXFC Procurement |  | 93860 | Business Only Initiative | FXF - Commercial | Freight | Robyn Selk | On Track | ON hold due to seperation review of accounts. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: International Reweighs |  | 103905 | Business Only Initiative | FXF - Commercial | Freight | Shane Turner | On Track | W/E 5/24 - Currently working thru L2 checklist building milestones and assessing risks. W/E 5/31 - Currently working thru L2 checklists Control Environment items. | E: L2 | Cancelled | L2 | 2025-04-01 | 2026-05-01
Business w/ Tech Initiative: Project Fairway - Infrastructure Separation Enable |  | 143541 | Business w/ Tech Initiative | FXF - Separation | Freight | David Gedlinske, Cory Estes, Elizabeth Allen | On Track | WE 4/3/26 - Project Fairway continuing as planned, roadblocks and speedbumps mitigated as encountered. Weekly reporting compiled and disseminated to executive leadership for both FEC and FXF. WE 1/16/26 - Builds in progress. SIT and UAT conducted as planned. Risks and roadblocks are being mitigated as encountered, escalating as needed. WE 9/5/25 - initiative on track, in L3. EPM team testing data flow for epics from Agility to Planview. WE 8/15/25 - Platforms Triage completed on 8/15, pending resutls or further discussion. L1 arch documentation adjustment pending. WE 8/8/25 - Continued collaborative review of applicable EAIs. On Track at this time. UPR # 9013095. 7/22/25 - L1 arch assessment completed. Documentation uploaded to repository, PV updated accordingly. QA Review performed and approved by Kelli Ostertag for SL2. 7/17/25: CE - added David as IO and set all required criteria to 0 so I can save. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2029-05-11
Business w/ Tech Initiative: Project Fairway - Data & AI Separation Enablement |  | 143544 | Business w/ Tech Initiative | FXF - Separation | Freight | David Gedlinske, Cory Estes, Elizabeth Allen, Brandy Mears, Karen A. Lucarelli, Ramyasine Boominathan | On Track | WE 4/3/26 - Project Fairway continuing as planned, roadblocks and speedbumps mitigated as encountered. Weekly reporting compiled and disseminated to executive leadership for both FEC and FXF. WE 1/16/26 - Builds in progress. SIT and UAT conducted as planned. Risks and roadblocks are being mitigated as encountered, escalating as needed. WE 9/5/25 - initiative on track, in L3. EPM team testing data flow for epics from Agility to Planview. WE 8/15/25 - Data & AI Portfdolio triage complete on 8/13. WE 8/8/25 - Connected with Data & AI portfolio, L2 triage scheduled for 8/13 1400-1500. UPR # 90130936. Proposal # 1360130. 7/22/25 - L1 arch assessment completed. Documentation uploaded to repository, PV updated accordingly. QA Review performed and approved by Kelli Ostertag for SL2. 7/17/25: CE - added David as IO and set all required criteria to 0 so I can save. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-04 | 2026-07-20
Business w/ Tech Initiative: Project Fairway - Back Office Separation Enablemen |  | 143548 | Business w/ Tech Initiative | FXF - Separation | Freight | David Gedlinske, Cory Estes, Rachel Avery, Elizabeth Allen | On Track | WE 4/3/26 - Project Fairway continuing as planned, roadblocks and speedbumps mitigated as encountered. Weekly reporting compiled and disseminated to executive leadership for both FEC and FXF. WE 1/16/26 - Builds in progress. SIT and UAT conducted as planned. Risks and roadblocks are being mitigated as encountered, escalating as needed. WE 9/5/25 - initiative on track, in L3. EPM team testing data flow for epics from Agility to Planview. WE 8/15/25 - PPM Proposal aprpoved, PPM #1373824. WE 8/8/25 - Continued collaborative review of applicable EAIs. On Track at this time. UPR # 9013094. 7/22/25 - L1 arch assessment completed. Documentation uploaded to repository, PV updated accordingly. QA Review performed and approved by Kelli Ostertag for SL2. 7/17/25: CE - added David and Rachel as IO and zero'd all other required fields so I could save with new IO. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-04 | 2026-06-01
Business w/ Tech Initiative: Project Fairway - Commercial Separation Enablement |  | 143551 | Business w/ Tech Initiative | FXF - Separation | Freight | David Gedlinske, Cory Estes, Stefanie Larson, Elizabeth Allen | On Track | WE 4/3/26 - Project Fairway continuing as planned, roadblocks and speedbumps mitigated as encountered. Weekly reporting compiled and disseminated to executive leadership for both FEC and FXF. WE 1/16/26 - Builds in progress. SIT and UAT conducted as planned. Risks and roadblocks are being mitigated as encountered, escalating as needed. WE 12-12/2025 - Project Fairway continuing as planned. WE 9/5/25 - initiative on track, in L3. EPM team testing data flow for epics from Agility to Planview. WE 8/29/25 - presenting to CPEL on 8/27. Submitted for Portfolio greenlights, SL3. WE 8/15/25 - presented to Commercial Triage, they recommended a thorough PRT review and discussion, including all ARTs; awaiting schedule for PRT. WE 8/8/25 - Continued collaborative review of applicable EAIs. On Track at this time. UPR # 9013096. 7/22/25 - L1 arch assessment completed. Documentation uploaded to repository, PV updated accordingly. QA Review performed and approved by Kelli Ostertag for SL2. 7/17/25: CE - added David and Stefanie as IO and zero'd all other required fields so I could save with new IO. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-04 | 2028-01-03
Business w/ Tech Initiative: Project Fairway - Operations Separation Enablement |  | 143555 | Business w/ Tech Initiative | FXF - Separation | Freight | David Gedlinske, Brandy Mears, Cory Estes, Adren Hillenburg, Elizabeth Allen, Karen A. Lucarelli, Ramyasine Boominathan | On Track | WE 4/3/26 - Project Fairway continuing as planned, roadblocks and speedbumps mitigated as encountered. Weekly reporting compiled and disseminated to executive leadership for both FEC and FXF. WE 1/16/26 - Builds in progress. SIT and UAT conducted as planned. Risks and roadblocks are being mitigated as encountered, escalating as needed. WE 9/5/25 - initiative on track, in L3. EPM team testing data flow for epics from Agility to Planview. WE 8/15/25 - PPM proposal approved, PPM #1373825. WE 8/8/25 - Continued collaborative review of applicable EAIs. On Track at this time. UPR # 9013090. Proposal # 1361194. 7/22/25 - L1 arch assessment completed. Documentation uploaded to repository, PV updated accordingly. QA Review performed and approved by Kelli Ostertag for SL2. 7/17/25: CE - added David & Adren as IO and zero'd all other required fields so I could save with new IO. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-08-04 | 2026-08-18
Business Only Initiative: FXF- Freight Service Dashboard | 27915 | 6720 | Business Only Initiative | SE - FXF | Freight | Bill Guadagnini, Mark Madson | On Track | Report is published and on the FXF Reporting Hub we had 78 users in December and 148 in January. | K: L5 | Completed | L5 | 2023-08-01 | 2024-02-29
Business Only Initiative: FXF - Other Bucket | 27916 | 6721 | Business Only Initiative | SE - FXF | Freight | Gus Correa, Morgan Schultz | On Track | L4 surges 1/8 L3 surge as of 8/28, working through milestones. Education to Top Offenders has started. | K: L5 | Completed | L5 | 2023-07-26 | 2024-01-04
Business Only Initiative: FXF - Rail Carrier Service Reporting | 28375 | 6732 | Business Only Initiative | SE - FXF | Freight | Stan Bradford, Matthew Schaffer | On Track | Apr 26th. Money step completed. Reviewed L4 check list and will submit for L4. | K: L5 | Completed | L5 | 2023-07-18 | 2024-04-26
Business Only Initiative: FXF - SE - [Enabler] - Shift End Reporting (SRR) | 56699 | 6923 | Business Only Initiative | SE - FXF | Freight | Mark Williams, Mark Madson | On Track | 1-16-26 Inbound is fully executed and in production. No further development will be done at this time. Cancelling the initiative and when ready to look at other shifts - will enter New Initiative in FedEx Freight new platform. (Commercial Leadership: Carson Davidenko) 2026-01-12: Continue IB Shift Post launch feedback and daily usage reporting. 2026-01-05: Continue IB Shift Post launch feedback and daily usage reporting. 2025-12-29: Continue IB Shift Post launch feedback and daily usage reporting. 2025-12-22: Continue IB Shift Post launch feedback and daily usage reporting. 2025-12-15: Continue IB Shift Post launch feedback and daily usage reporting. 2025-12-08: Continue IB Shift Post launch feedback and daily usage reporting. Further development is on hold: SYSDEV is currently involved in the Spin-off related reporting migration process and unable to commit to timing on updates or additional shift development at this time. 2025-12-01: IB Shift Post launch feedback and daily usage reporting. Pending response from SYSDEV. 2025-11-24: IB Shift Post launch feedback and daily usage reporting. Pending response from SYSDEV. 2025-11-17: IB Shift Post launch feedback and daily usage reporting. Pending response from SYSDEV. Awaiting SYSDEV response to the 11/11/25 request for IB SRR Updates and to explore the opportunity for additional shift development. Follow ups sent 11/14 and 11/17. 2025-11-10: IB Shift Post launch feedback and daily usage reporting. 11/11/25 Request sent to SYSDEV for IB Updates and to explore the opportunity for additional shift development. 2025-11-03: IB Shift Post launch feedback and daily usage reporting. 2025-10-27: IB Shift Post launch feedback and daily usage reporting. 2025-10-20: IB Shift Post launch feedback and usage monitoring. 2025-10-13: IB Shift Post launch feedback and usage monitoring. 2025-10-06: Post launch feedback and usage monitoring. 2025-09-29: SRR now live in production environment for pre--launch testing , finalizing QRG, conducting SME - lauch team calls. 2025-09-22: SRR now live in production environment for pre--launch testing 2025-09-15: SRR now live in production environment for pre--launch testing 2025-09-08: SYSDEV to move to Production and User testing of the production version. 2025-09-01: Working with SYSDEV on timing for the completion of the name change updates to the UI to SRR - Shift Reconciliation Report. 2025-08-25: Working with SYSDEV on timing for the completion of the name change updates to the UI to SRR - Shift Reconciliation Report. 2025-08-18: Working with SYSDEV on timing for the completion of the name change updates to the UI to SRR - Shift Reconciliation Report. 2025-08-11: Review open items with SYSDEV to get IB into production, review all shift specs, change nae to SRR - Shift Reconciliation Report. 2025-08-05: Re-activated 2025-05-08: Placed On Hold pending SYSDEV resource allocation to complete the remaining shifts, IB Shift pilot to continue to build use case and OPS buy in on value for MBG/NSL improvement opportunty. 2025-05-05: Pilot Launch with SAV, ORL, TUP and WOR. Scheduling calls with ENJ and STL. 2025-04-28: Pilot calls with SAV, ORL, TUP and WOR. Scheduling calls with ENJ and STL. 2025-04-21: Finalize Planning and communications on the expanded Pilot to SAV, ORL, TUP and ENJ. 2025-04-14: Finalize Planning and communications on the expanded Pilot. 2025-04-07: Finalize Planning and communications on the expanded Pilot. 2025-03-31: Finalize Planning and communications on the expanded Pilot. 2025-03-24: Plan and communicate expanded Pilot. 2025-03-17: Complete comparison analysis to RACER results. 2/17/25 thru 2/28/25. Update QRG for expanded pilot. 2025-03-10: Complete comparison analysis to RACER results. 2/17/25 thru 2/28/25. Update QRG for expanded pilot. 2025-03-03: Complete comparison analysis to RACER results. 2/17/25 thr | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2023-12-04 | 2026-05-29
Business Only Initiative: FXF - Live Misload Report | 33759 | 6980 | Business Only Initiative | SE - FXF | Freight | Jeff Jacobs, Dawson Mills | On Track | Dev resources bandwidth allowed for early development of reporting tool. Looking to launch to Ops by 09OCT23. | K: L5 | Completed | L5 | 2023-08-21 | 2024-05-07
Business Only Initiative: FXF - Pick-up Service Reporting | 62373 | 7306 | Business Only Initiative | SE - FXF | Freight | Kathleen Crawford, Rene Lopez | On Track | Week 1/6: The Top Opportunity tab updates is still in backlog. Decemeber EOM table changes were completed per Bill Guadagnini's request as the team continues to experiment with pickup reason changes. Week 11/6: Continuing work on tickets, updates, and engage necessary parties. Week 10/21: Top opportunity view completed. Still working on outstanding tickets. Week 10/7: Continuing work on tickets and engaged Rob Nachand and Damon Dworak for additional assistance with the handheld events. Finalizing Top Opportunity view. Week 9/30: Tickets still being worked and reaching out to additional support on the handheld triggered events. Meetings scheduled to review additional enhancements. Week 9/23: Demos and education completed and working through outstanding tickets and additional view. Week 9/16: Demos and education ongoing. Week 9/9: Continue demos, follow up on tickets, and additional "top oppty" view. Week 9/2: Continue demo calls and working through open ticket items and updates. Week 8/26: FQS team started region/district demo's this week. Continue to work through open tickets for low impact report defects and working on enhancements from feedback shares in RVP & OSE calls. Week 8/19: Demo with Clint's team and RVPs. Working through pending updates and suggestion (add Route) with Nithish and Jamie. Week 8/12: Completed demo with FQS team, identified several issues during demo for Nithish to look into, following up with Nithish on outstanding items in meeting 8/14. Week 8/5: Gathering all feedback from pilot centers. Continue report validation. Week 7/29: Continued with daily check-in calls. Centers are in 2nd week of piloting report. Week 7/22: Continued with daily check-in calls. Centers have begun piloting report. Week 7/15: Daily status update calls. Meeting with ops this week to review report. Week 7/8: Next meeting scheduled for 7/10. Appear to still be on track. Week 7/1: Call scheduled with developers for 7/2. Reviewing updates to report and begin drafting communication for ops and pilot. Week 6/24: Development Team is working on making the necessary changes. Anticipate call for late this week or early next week on the updates. Week 6/17: Timeline will not change to provide visibility of pending dev work for prioritized completion - milestones will remain late and L4 date will go past due. Dev Team outlined remaining tasks and committed to complete within 4 weeks. Tentative readiness to start pilot on 7/15. Week 6/10: Working to finalize development to enable pilot. All changes were not completed prior to developer's scheduled vacation. Meeting with new developer on 6/13. Week 6/3: Developer is still incorporating all changes. Met with new developer and Nitish is bringing him up to speed. Week 5/27: Reviewing updates completed last week by Nitish and next meeting will occur this week. Plan to demo and review with operations within the next 1-2 weeks. Week 5/20: Reviewing updates completed last week by Nitish and scheduling next meeting. Hope to be able to demo and review with operations within the next 1-2 weeks. Week 5/13: Met with NIthish and Rene to review additional updates on 5/16. Week 5/6: Set up next meeting with Nithish to review report updates and met on 5/7. Nithish is unable to meet the remainder of the week so will circle back with updates made to the report with him early next week. Testing is still being done on the data provided in the report. Week 4/29: No change from last week's update. Follow up with Nithish to discuss new projected completion date and meet to discuss this week if needed. Week 4/22: Met with Nithish on 4/23 to review and discuss changes made to the report. Reason and Status split into 3 charts, added pickup performance metric, brought in modified request data. Pending : Drill through charts for modified requests, Pickup Reliability tab and Trends. Projected to complete by 4/26. Week 4/15: Follow up meeting is pushed to 4/23 due | K: L5 | Completed | L5 | 2024-01-23 | 2024-11-01
Business Only Initiative: FXFC CN Rail Mvmt Visibility | 71577 | 7331 | Business Only Initiative | SE - FXF | Freight | Robyn Selk, Eiren Good | On Track | Initiative has moved out the milestones to accommodate the rail strike in Canada. New dates have been applied for completion of L3 and L4. 02/10 completed L4 prep and submitting. 03/13/2025 100% moving on to L5 with surge on 03/20/2025 | K: L5 | Completed | L5 | 2022-01-03 | 2025-02-14
Business Only Initiative: FXF - Prioritize Opportunity Volume | 23670 | 8097 | Business Only Initiative | SE - FXF | Freight | Travis Williams, Jarrette Bishop | On Track | 12/04/2024 - submitting for L5 this week. 01/06/2025 - KPI Tracking only. Entered DEC actuals on 1/6/25 02/05/2025 - KPI Tracking only. Entered JAN actuals on 2/5/25 | K: L5 | Completed | L5 | 2023-08-03 | 2024-11-08
Business Only Initiative: FXF - Network Discipline | 29730 | 8099 | Business Only Initiative | SE - FXF | Freight | Travis Williams, Dawson Mills | On Track | 01/28/25 - progressed to L5 - monitoring and reporting monthly KPIs from the LMT Historical Report Team has advanced to L3, and is prepping for L4 11/06/2024- submitting for L4 this week | K: L5 | Completed | L5 | 2023-08-23 | 2024-11-08
Business Only Initiative: FXF - PUDE/Late Tender | 29731 | 8419 | Business Only Initiative | SE - FXF | Freight | Jacob Kirkpatrick | On Track | During testing, Operations systems/enterprise systems team discovered that when PUDE correction is requested through the corrections app, it works as it should. However if the corrections app is started through another application like shipment inquiry, road dispatch, etc the PUDE code will show that it has been applied, but it will not ultimately update the eta to include the extra day of service. This now requires 2 IT teams to work. There will be an update that is applied this weekend and should have working by Monday. Hoping that this update will in turn, positively impact some of the other issues we are having with PUDE code sticking to shipments as well as accurately displaying in SQI. 02/13 all education completed in each region, money step documentation uploaded to attachment tab. 03/11/2024 submitted for L5. | K: L5 | Completed | L5 | 2023-08-14 | 2024-02-27
Business Only Initiative: FXF - ETA & Planned movement Alignment | 28052 | 9379 | Business Only Initiative | SE - FXF | Freight | Daniel Mellis, Mark Milburn | On Track | 6/20 Drafted Demand Request document to send to IT to fix weekend logic issue in R&E maintenance. | K: L5 | Completed | L5 | 2023-08-08 | 2023-12-15
Business w/ Tech Initiative: FXF - RACER | 23669 | 9504 | Business w/ Tech Initiative | SE - FXF | Freight | Bill Guadagnini, Gus Correa | On Track | Rail DeRamp information is now showing on the test sight - the core team will test this week prior to moving to production. | K: L5 | Completed | L5 - Restarted Initiative | 2023-03-01 | 2025-05-15
Business w/ Tech Initiative: FXF - True Commit Date | 23673 | 9508 | Business w/ Tech Initiative | SE - FXF | Freight | Bill Guadagnini, Brienne Parker | Some Issues | Recommendation to place on hold approved by Alyssa Tokorcheck. Forward momentum dependent on work within #15982 Centralized Delivery Address Preferences planned for Feb 2025. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-05-31 | 2026-01-30
Business Only Initiative: FXF - Customer Experience Dashboard | 81059 | 6716 | Business Only Initiative | SE - FXF | Freight | Brent Longoria, Gus Correa | On Track | 9/30- leadership headlines, approval email, and district rollout completion have been uploaded. I'll work with Martha to do email surge for L4. CX Tools has been rolled out to all districts! we are keeping the teams site active for at least 3 weeks so our SME's have a central area for information and questions. 9/25- Dashboard is live on FXFR Reporting tools. Labeled "CX Tools" 9/24- Leadership Headlines comms went out, informing field leadership of the Customer Experience Dashboard. At least 6 districts have completed rollout. 9/17- testing purpleid starting today. We should have a new link after they are ready. Still some pending work on UI, but IT is confident these are minor. Adjusting IT work timeline to give them more time. We are still meeting weekly with SME’s for both the SRR an customer experience dashboard rollout. So far, all good.9 9/10- New link for CX UI. The link was a big reason we were seeing the site issues. We've got SME calls scheduled out now, 2 per week for updates and questions. Mark W. is travelling until tomorrow, so we are catching up today and tomorrow on their report and info for the SME's to be prepared for both rollouts. Currently, updating the metric display orders since the tab orders are complete. we will default to the Overview tab, so you get a good high level view of how we did. We found a couple defects in Billing accuracy and Confirmation Discrepancy, but so far we're looking solid! Pending actions are the move to prod for data, which will be done before rollout begins.For leadership comms, i'm working with Ryan Glover now ( Laura Melton is now covering a different area for separation). shooting for wednesday 9/24 for the leadership comms. 9/3- we are giving IT 2 of our rollout weeks to get a few changes made. we still believe we can rollout by the end of september. planview is updated. 8/27-Working with Mark Williams to see if we can combine the rollouts of SRR and the Customer Experience Dashboard. IT will be making some UI changes after 8/31, but we still think we can hit the 9/30 timeline. SME's have a team site setup, and we have them engaged and looking in the tool daily. Initial feedback is great. 8/20-we have basically all the SME's assigned. We are introducing them to the tool in the original message, but hosting 2 calls this week, to explain rollout schedule and methods. Continued UI testing with SME's feedback. On the IT side, we now have 3 sorts for "top opportunities" 1) failure counts- this will be used most often to identify customers that we can target based solely on failures instead of %. 2) Denominator- this will focus on largest customers 3) Value (Percentage) this will assist in focusing on our largest opportunities with small/midsize customers. CX UI has really heightened the visibility to 999 customers. This was eye-opening to see them all in one place. It was ultimately decided that the lift to look more closely at 999's would involve a major re-write on the backend, so we will look for outside reporting to improve this. We are still on track for rollout by the end of september. 8/12: We have names for most of the SME's. Prod server is fully connected and data goes back to beginning of FY25 (06/01/2024). requested the sort order changes and addition of "failure counts" as a sorting function. This will give us the ability to look at customers in 3 different ways 1) Failure Counts descending (most helpful) 2) Percent ascending ( typically shows small-midsized customers) 3) Denominator descending (largest customers) 8/6- Gathering District, FE, and FQS SME's to assist with the rollout currently planned to be completed by End of september. Hosting weekly calls to get SME's comfortable with the dashboard, even though UI changes are still happening. Production server for the backend data is ready, and Data is being loaded through this weekend. Data will be from 6/1/2024-onward. (FY25 to date). Hosting weekly calls | K: L5 | Completed | L5 | 2025-05-01 | 2025-09-30
Business w/ Tech Initiative: Enabler - FXF Handheld Life Cycle Management | 26237 | 6689 | Business w/ Tech Initiative | FXF - Dock | Freight | Brent Casey, Dennis Jamiot | On Track | 02/05 - Deployment is complete. Awaiting surge session. 01/20 - Google account fixes have been deployed. Additional production support is underway such as application level support. 01/06 - Omnisa (AirWatch) fix is being deployed to the MIWE Region today (01/06). 12/30 - PEAK/Freeze ongoing. No changes until 01/06. 12/16 - Omnisa (AirWatch) solution to switch devices from user based to device base has been deployed to Alpha & Beta locations. Pushes to the remaining devices in production will begin in waves starting 01/06 to MIWE, 01/08 to SOWE, 01/10 to SOEA, 01/13 to NOEA, 01/15 to NOWE, and 01/17 to Canada & Staging. 12/09 - Omnisa (AirWatch) has created a solution to remedy the Google account issues we are having that is impacting the keyboards on the devices. Omnisa has to update their database from user base to device based allowing more than ten accounts. Now that this has been completed the next step is to push an intent to the Honeywell devices from Omnisa. There is a limit of five hundred devices in a batch so waves of these updates will be needed. The first wave is to our alpha locations, HRO, SGF, CLE which was pushed on 12/03. 12/02/2024- MR05-CUE firmware deployed to Production over the weekend to provide a fix to the Wi-Fi heartbeat issues, VZW IMSI issues, and Cradle BT volume profile. 11/18/2024 - Last weekend of deployments completed. Follow-up installastions for tractors that were not at domiciled locations to follow. Motive v78.3 was pushed to full production on 11/16 to combat the nextstat excessive logging that was "bricking" the devices. | K: L5 | Completed | L5 | 2023-01-30 | 2025-05-09
Business w/ Tech Initiative: Enabler - Tracking Number Recycling | 26259 | 6692 | Business w/ Tech Initiative | FXF - Dock | Freight | Sandy Lindsey, Garrett Hammers | On Track | 01.20.26 - Work considered complete. Cancelling in Planview to prepare for Freight separation.**** 01.13.26 - Work in progress continues with BOTH FXF teams (AR & SEFS) - Delivery - Freight - FXF Solution. NOTE: FXF SEFS team was moved from Supply Chain Operations side to Delivery-Freight-FXF Solution on the Freight side. Work completed last week * FXF AR Team - None. * SEFS Team - B-2748362 - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Range Reclaim Fixes - Part 2 - Prepare for MTP Work in Progress * FXF AR Team –None. * SEFS Team - B-2748362 - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Range Reclaim Fixes - Part 2 - MTP targeted for 01.13.25. Next Steps * FXF AR Team – No additional development work for THIS team. * SEFS Team -None. Risks/Awareness * FXF AR Team – None. * SEFS Team - None. 01.06.26 - Work in progress continues with BOTH FXF teams (AR & SEFS) - Delivery - Freight - FXF Solution. NOTE: FXF SEFS team was moved from Supply Chain Operations side to Delivery-Freight-FXF Solution on the Freight side. **L4 updated to 01.30.26** Work completed last week * FXF AR Team - None. * SEFS Team - B-2748362 - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Range Reclaim Fixes - Part 2 - Moved to L3 12.19.25 - Business testing completed. Work in Progress * FXF AR Team – No additional development work for THIS team. * SEFS Team - None. Next Steps * FXF AR Team – No additional development work for THIS team. * SEFS Team -B-2748362 - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Range Reclaim Fixes - Part 2 - Aiming for MTP Jan 2026. Risks/Awareness * FXF AR Team – None. * SEFS Team - None. 12.30.25 - NO UPDATE REC'D FROM TEAM DUE TO HOLIDAY 12.23.25 - Work in progress continues with BOTH FXF teams (AR & SEFS) - Delivery - Freight - FXF Solution. NOTE: FXF SEFS team was moved from Supply Chain Operations side to Delivery-Freight-FXF Solution on the Freight side Work completed last week * FXF AR Team - None. * SEFS Team - B-2748362 - FXF-Ship-Scrum Lords - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Range Reclaim Fixes - Part 2 - Moved to L3 12.19.25 Work in Progress * FXF AR Team – No additional development work for THIS team. * SEFS Team - B-2748362 - FXF-Ship-Scrum Lords - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Range Reclaim Fixes - Part 2 - Business testing in progress in L3 Next Steps * FXF AR Team – No additional development work for THIS team. * SEFS Team -Update logic for ongoing purging: 1. Update Legacy Purge Engine with logic to send out PROCESS_FLOW¦PURGE Events on tracking numbers it finds on Purescale tables older than the retention period (still not sure if 7 years or 18 months yet) 2. Update Legacy Purge Engine to receive PROCESS_FLOW¦PURGE Events via JMS to delete identified tracking numbers from Purescale 3. Update 3537136 and 7502 to delete entries from tables when receiving a PROCESS_FLOW¦PURGE event Risks/Awareness * FXF AR Team – None. * SEFS Team - None. 12.16.25 - Work in progress continues with BOTH FXF teams (AR & SEFS) - Delivery - Freight - FXF Solution. NOTE: FXF SEFS team was moved from Supply Chain Operations side to Delivery-Freight-FXF Solution on the Freight side Work completed last week * FXF AR Team - None. * SEFS Team - Dec 11, 2025 - CHG0978867 - Recycle the catchup tracking numbers older than 10 years. B-2741292 FXF-Ship-Scrum Lords - Tracking Number Recycling - EAI 3537679 FDXF-SEFS-Range-Mgmt-App - Schedule Range Rebuild Work in Progress * FXF AR Team – No additional development work for THIS team. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2023-08-23 | 2026-01-30
Business w/ Tech Initiative: Imaging Systems Modernization - OCR | 26260 | 6694 | Business w/ Tech Initiative | FXF - Dock | Freight | Leslie Jensen, Garrett Hammers, Rachel Avery | On Track | 5.16.23: Assigned new IO. 5.12.23: On hold until further notice 03.02.2026- Requesting cancellation as Initiative is complete. There is features/improvements that are slated to MTP at a later date. This will be added to the initiative tracker in use at the time when the user-improvements are adopted. | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-05-01 | 2025-07-25
Business Only Initiative: Team Member Feedback Enablement | 96683 | 6749 | Business Only Initiative | FXF - Dock | Freight | Gloria Ballard, Garrett Hammers, Brienne Parker | On Track | L3 Surge Session 11/20 | K: L5 | Completed | L5 | 2024-11-07 | 2025-03-24
Business Only Initiative: Tech Assets Lifecyle Mgmt | 30064 | 6767 | Business Only Initiative | FXF - Dock | Freight | Shaun Bullock, Garrett Hammers | On Track | 4.25.25 Decisions being made prior to split. Waiting on conversations direction. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-01-02 | 2025-12-12
Business Only Initiative: TriColor-Heavyweight Injection Report Improvements | 80723 | 7131 | Business Only Initiative | FXF - Dock | Freight | David Gedlinske, Jason Shatz | On Track | WE 5/23/25 - Back end data sources have moved from EIW/EDW to VDAP/ATLAS, and modification to application will be needed to keep it functional. Call scheduled for 5/23 to discuss alternative architecture and approach we can leverage to get the modifications completed. WE 4/12/25 - report live for end user group. Preparing for L5, continuing to monitor end user feedback. | K: L5 | Completed | L5 | 2024-08-01 | 2025-04-30
Business w/ Tech Initiative: FXF Paperless Delivery Receipt and Photo Capture | 55716 | 7214 | Business w/ Tech Initiative | FXF - Dock | Freight | Brent Maddin, Garrett Hammers, Molly Thayn | Some Issues | On Hold until after Seperation 10-27-25:Development in progress for signature screen, coding in progress for 1.2, 1.3 (complete), 2.1, 2.2, 2.3, working to populate Paperless delivery screens with data and screen functionality 10-12-25 MTP Driver Collect, services coding complete VB1 10-03-25: EDM meeting Monday 09-29-25: Completed testing for some E2E tet casesservice coding somplete for VB1. still signifucant work on HH/GUI interface to complete 08-18-25: Testing UPDATE Identified solution for SEFS issue that is occurring during testing. Coding in progress. Will look to test code changes early next week in hopes for a MTP by 8/23 08-04-25: Testing still remains unstable in L3...Working thru Agility/Plainview Epics coming thru into Plainview 07-14-25: Still trying to work through Driver Collect for US and Deliver Stop testing in an unstable L3 environment 07-07-25:Driver Collect for US and Deliver Stop are code complete- trying to test in an unstable L3 environment. 06-09-25 eDR & Photo Capture - L3 Solution Internal pre-Review 06-02-25The team remains head down to complete coding and activities around the committed objectives for this PI. We are in great shape to report that all objectives will be successfully completed. 05-19-25 Meeting is to review the capabilities internally prior to presenting for ARB review: 05-05-25 Hardening PND and Purescale, Financial Review of savings 04-21-25 Actuals entered in plainview 04-14-25 Fincance meeting discussing cost savings 04-07-25 Architecture meetings 03-31-25" Added KPI's and weekly meetingds 03-24-25: eDR meetings 03-17-25: Kickoff automate Image reconciliation. 03-10-25:eDR C4.1.2 Scope Discussion - Core 03-03-25 Paperless Delivery Receipts Stakeholder Weekly Touchpoint 02-24-25 Weekly Touchoint 02--09-25 update in Planview for the Commercial ‘demand request 02-02-25-eDR Meetings 01-27-25- eDR Cabability Kick-off (1.3.10) 01-20-25- eDR decomp and driver collect/cod meetings 01-13-25- Driver Collect/COD meetings wrapped up, Kick off decomposition for Capability C2.1.5 (Driver) Capture Complete Shipment Return Information (Epic: Capture Delivery Event Info meeting) today 01-06-25- Driver Collect meetings/discussions this week 12-20-24- Steven Payne planning future work and needs...Delivery Date for eDR 11-25. 12-23-24- eDR meetungs 12-16-24 eDR meetings with Joshua Bolling 12-09-24 ART Handoff last week. Meetings upcming to discuss next steps. 12-02-24 eDR Capability - Solution Handoff to ART Deck meeting 12-02-24 11-25-24 eDR meetings continuing last week to gather info for eDR's. 11-18-24 eDR meetings with architects. 11-10-24 eDR story's for P1 scheudled Mon 11-11-24 and Meeting 11-12-24 for OS&D info on eDR's. 11-04-24 Clear request approved, waiting on resourcing for next steps. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-08-15 | 2026-11-30
Business Only Initiative: DriveWyze | 55717 | 7215 | Business Only Initiative | FXF - Dock | Freight | Mathew Crates, Garrett Hammers | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 09/23/25-Had meeting with Staci and Garrett, money step completed, reviewed L4 requirements. Benefits will need to be updated, will need to have a call with finance to determine next steps. 11/18/24 Drivewyze has acquired new proxy server service Thursday November 21st and we began configuration on Friday November 22nd . They expected to have it setup next week and planning to have things stood up for testing early December. 01/16/25 We have resolved the proxy issue and are now able to log into the application and have been able to complete some beta testing. Once completed we will be able to begin testing with a small group of drivers. 01/30/25 Drivewyze has been able to remove a screen that gave drivers the option to exit or run in background which was decided on by our group within FedEx to minimize risk of closing out of the application. Prod deployment for update is set for 02/01/25. Once this is deployed we should be able to set up pilot for testing the application. | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-01-29 | 2025-10-30
Business w/ Tech Initiative: Freight LTL/Direct Appt Application | 57268 | 7231 | Business w/ Tech Initiative | FXF - Dock | Freight | Kathryn Snyder, Garrett Hammers, Molly Thayn | On Track | On hold due to prioritization on resourcing. | E: L2 | On Hold | L2 & CCH | 2023-07-27 | 2025-10-31
Business Only Initiative: Enabler- FXF Freight Continuity | 58160 | 7242 | Business Only Initiative | FXF - Dock | Freight | Shane Turner, Nicole Brown | On Track | Week of 5/27 - MF exit postponed to 6/15. | K: L5 | Completed | L5 | 2023-12-04 | 2024-03-15
Business Only Initiative: Clerical Dashboard | 89629 | 7370 | Business Only Initiative | FXF - Dock | Freight | Donald Baker, Garrett Hammers | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. Milestones and financials complete, ready for L5 surge on 10/2/25 | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-11-01 | 2026-05-06
Business Only Initiative: HR Admin Critical Reporting Needs | 91403 | 7379 | Business Only Initiative | FXF - Dock | Freight | Valerie Cruz, Garrett Hammers | On Track | L3 Surge (11/20) | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-12-02 | 2026-12-31
Business Only Initiative: [Enabler] Shift Level Goaling - Dock BPH | 72917 | 7531 | Business Only Initiative | FXF - Dock | Freight | Tomm Brennan, Patrick Duane | On Track | Goals loaded. Project complete | K: L5 | Completed | L5 | 2024-06-26 | 2024-08-27
Business w/ Tech Initiative: CORE: Dock Communications and Total Dock View Inte | 96178 | 7721 | Business w/ Tech Initiative | FXF - Dock | Freight | Gary Moses, Nicole Brown | On Track | 7/3: Iniative is placed On hold as FXF prioritizes resources needed for separation 6/24/25: Business case was resubmitted for L2 approval in Planview. It was flagged in error by Finance and will be approved per Alex Thomas. Initiative has shifted down in prioirty to #52 per the EDP site. 6/16/25: Per Alex Thomas, "Jarod’s team is working with the IO to us to revisit the business case to tie the financials to what we would expect to see from a financial standpoint and tie in the KPIs we track for rating and efficiencies. I am waiting to hear back from Jarod on where they are in the process." 6/10/25: Initiative listed as prioirty #24 on the EDP site. 6/4/25 QA Review performed by Kelli Ostertag after meeting with Finance and adjustments made to Business Case. Approved to submit to SL2. 6/2/25: Lean Business Case revised with new NRB; benefits now declared hard. Ready to submit to L2 after QA Checklist assessment. 5/29/25: Revising LBC to include workflow steps with percentage of new workload vs. baseline to solidify savings. LBC will be reviewed with Sr. leadership and shared with Finance in efforts to move to L2. 5/21/25: Jarod and Alex met with Kari and she is recommending them to revisit the business case to tie the financials to what we would expect to see from a financial standpoint and tie in the KPIs we track for rating and efficiencies. They (Jarod and Alex) are discussing what that needs to look like. Timeline TBD. 5/19/25: Link for "Inititative Supporting Architecturual Document" updated to grant access to the submitted architecture documentation. Initiative is now prioirty #65 (backlog) on the EDP site. Still awaiting assessment & clarification of benefit structure (soft or hard) from Finance team. 5/15/25: During L2 surge, it was recommended that business case should be reviewed by Finance before moving forward to assure understanding on how benefits would be captured. Review scheduled for afternoon of 5/15. Initiative dropped to prioirty #262 (backlog) on the EDP site. 5/14/25: QA Review performed by Kelli Ostertag, approved. Scheduled to surge to SL2 on 5/15/25. 5/1: L1 Arch Assessment was completed on 4/30 where impacted portfolios, t-shirt sizing, and architecture outcomes responsibilty was determind. 4/30: Initiative remains as prioirty #82 (backlog) on the EDP site. 4/16: Initiative drops to prioirty #82 (backlog) on the EDP site. 4/10: Initiative drops to prioirty #81 (backlog) on the EDP site. 4/7: Initiative moves up as prioirty #80 (backlog) on the EDP site. 4/3: Initiative moves up as prioirty #82 (backlog) on the EDP site. 4/1: Initiative moves up as prioirty #93 (backlog) on the EDP site. 3/27: Initiative remains as prioirty #97 (backlog) on the EDP site. 3/17: Initiative remains as prioirty #97 on the EDP site. 3/5: Initiative moves up as priority #97 on the Enterprise Demand Priortization work site. 2/19: Initiative moves up as priority #100 on the Enterprise Demand Priortization work site. 2/11: Initiative moves up as priority #102 on the Enterprise Demand Priortization work site. 2/6: Initiative remains as priority #106 on the Enterprise Demand Priortization work site. 1/31: Initiative is currently listed as priority #106 on the Enterprise Demand Priortization work site. 1/28: Initiative is currently listed as priority #91 on the Enterprise Demand Priortization work site. 1/27: Initiative is currently listed as priority #222 on the Enterprise Demand Priortization work site. 1/21: Initiative is currently listed as priority #197 on the Enterprise Demand Priortization work site. 01/14/25: Initiative is currently listed as priority #181 on the Enterprise Demand Priortization work site. 01/07/25: Still awaiting response from EBA on next steps. Initiative is currently listed as priority #154 on the Enterprise Demand Priortization work site. 12/17/24: Still awaiting clearance to move to L2 with required enterprise architecture documentation. Current priority ra | E: L2 | On Hold | TEMP L2 - Enter Value Prop
Business w/ Tech Initiative: CORE: Optimize Freight Routing on Docks | 26268 | 7775 | Business w/ Tech Initiative | FXF - Dock | Freight | Kevin Kotil, Sara Bailey | On Track | 6/30/2025: - On Hold reasoning: Paused as Freight Prioritizes resources needed for separation. 6/24/2025: - Working on gathering all tools/reports outside of ACCOPS that Operations relies on 6/16/2025: - Madhuri Shared the inital pass at the enterprise architecture, working to finalize by the end of this week. - Ranked 8th in priority to get Solution Architecture engaged. 6/9/2025: - Working on summarizing all CORE work and outlining in a high level document 6/4/2025: - Outlined potential heirarchy of the routing factors. 5/28/2025: - Met with Madhuri 5/22 and went over Non Functional Requirements, and Archetectural Decision Roadmap. - Awaiting further engagement to start building out the solution architecture. - Working on building high level rules for the factors that go into the dock routing. 5/20/2025: - Triage Meeting with Data & AI on 5/21 05/08/2025: - No new updates - Completed PPM initial request, awaiting further action - Working on L2 checklist - Meeting next week with Enterprise architecture (Madhuri) to work through the solution architecture 5/07/2025: - Approved and moved into L2. - Architecture mapping will be worked on once Madhuri (Enterprise Architect) returns from vacation 5/12 5/06/2025: - No new updates - Awaiting Finance for approval to move to L2. Sent follow up message to finance team on 5/5. 4/29/2025: - Surged on 4/25, awaiting final approval from Alex to move to L2. 4/22/25: - QA review completed by Kelli O, approved. 4/17/2025: - Completed Nonfunctional requirements list with Biz Arch and Enterprise Architecture. - Waiting to recieve the Architecture documentation to upload in planview/sharepoint. 4/14/2025: - No new updates, continuing Decomp 4/8/2025: - Continuning decomp, walking through current systems with Enterprise Architects 4/3/2025: - No new updates. Continuing decomp, breaking out the work into epics. 3/25/2025: - Continuing to work with Business Architecture and detail out Epics - Detailed out the each of the routing factors, what they could potentially be used for. Will continue to add detail as requested 3/17/2025: - Breaking down the initiative into individual Epics - Prioritization/order in which epic/capability to work on first 3/12/2025: - Continuing Initial Decomp with Biz Arch. - Working to complie very high level documentation/mock up of future UI. 2/24/2025: - Setting up bi-weekly touchpoint call with Buisness Architecture to decomp out Core Optimize Freight Routing 02/13/2025: - Priority Ranking 101 - Still waiting to discuss with enterprise architecture 1/07/2025: - Dropped in priority to 155 12/17/2024: - Dropped in priority from 96 to 128. - Need to add the in shift staffing as milestones within initative. 12/09/2024: - Still awaiting the discussion with Enterprise Architecture. Currently ranked 96 on the priority list. 11/18/2024: - Waiting for Enterprise Architecture to contact us to walk through the current state/future state 10/24/24: - Finalized Detailed Documentation and sharing with the business architecture team. - Meeting with FE managers for feedback and additional input - Meeting with NE team to get their thoughts on the dock routing and what abilities should be included 10.24.24: Creating a detailed documentation of the value,ability to, current state/future state of all the "value bundles" associated to the optimized freight routing on Docks. 9.4.24: seeking TripleCrown business case to review value associated with like improvements. 8.20.24: attempting to identify savings associated with efficiency gained by solution. planning to keep as 1 initiative through architecture decomp, then will review need for additional wave cards. 8.13.24: reviewing previously drafted value associated with similar efforts. 8.5.24: Received greenlight on value-bundles. Will connect with Bus. Arch regarding alignment & next steps. 7.31.24: Meeting on Monday 8/5 w CORE Leadership team. Plan to have initiatives in draft outline w "ability to's" and some seque | E: L2 | On Hold | L2
Business Only Initiative: FXF - BO - [Enabler] - Geographic Map Reporting | 55765 | 7834 | Business Only Initiative | FXF - Dock | Freight | Mark Williams, Shaun Bullock | On Track | 2026-01-19: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 2026-01-12: Monitoring feedback. 2026-01-05: Monitoring feedback. 2025-12-29: Monitoring feedback. 2025-12-22: Monitoring feedback. 2025-12-15: Monitoring feedback. 2025-12-08: Monitoring feedback. 2025-12-01: Monitoring feedback. 2025-11-24: Monitoring feedback. 2025-11-17: Monitoring feedback. 2025-11-10: Monitoring feedback. 2025-11-03: Monitoring feedback. 2025-10-27: Monitoring feedback. 2025-10-20: Monitoring feedback. 2025-10-13: Monitoring feedback. 2025-10-06: Monitoring feedback. 2025-09-27: Reports in production environment for pre-launch testing. 2025-09-22: Reports in production environment for pre-launch testing. 2025-09-15: Reports in production environment for pre-launch testing. 2025-09-08: SYSDEV completing the INFOSEC / IMAGE / Purple ID authorities. 2025-09-01: SYSDEV completing the INFOSEC / IMAGE / Purple ID authorities. 2025-08-25: Testing complete. SYSDEV completing the INFOSEC / IMAGE / Purple ID authorities. 2025-08-18: Testing complete. SYSDEV completing the INFOSEC / IMAGE / Purple ID authorities. 2025-08-11: Testing complete. SYSDEV completing the INFOSEC / IMAGE / Purple ID authorities. 2025-08-04: Continue Testing ORCA. Work on completing the IMAGE / Purple ID authorities. 2025-07-28: Continue Testing ORCA. Work on completing the IMAGE / Purple ID authorities. 2025-07-21: Testing ORCA. Work on completing the IMAGE / Purple ID authorities. 2025-07-14: Continue ORCA development. Discuss adding Purple ID to ORCA for vendor update authorities. Finalize MAXIMO read capability. 2025-07-07: Continue ORCA development. Discuss adding Purple ID to ORCA for vendor update authorities. Finalize MAXIMO read capability. 2025-06-30: Continue ORCA development. Discuss adding Purple ID to ORCA for vendor update authorities. Finalize MAXIMO read capability. 2025-06-23: Continue ORCA development. Discuss adding Purple ID to ORCA for vendor update authorities. 2025-06-16: Continue ORCA development. Discuss adding Purple ID to ORCA for vendor update authorities. 2025-06-09: Continue ORCA and DOLPHIN testing. Juan to take over pending backend updates for ORCA when time permits. 2025-06-02: Continue ORCA and DOLPHIN testing. Juan to take over pending backend updates for ORCA when time permits. Reviewed ORCA feedback with the Transportation team. 2025-05-26: Continue ORCA and DOLPHIN testing. Determine next steps on XIRGO. 2025-05-19: Continue ORCA and DOLPHIN testing. Determine next steps on XIRGO. 2025-05-12: Continue ORCA and DOLPHIN testing. 2025-05-05: Continue ORCA and DOLPHIN testing. 2025-04-28: Continue ORCA and DOLPHIN testing. 2025-04-21: Continue ORCA and DOLPHIN testing. 2025-04-14: Begin ORCA testing. Continue DOPLHIN testing. 2025-04-07: Continue working with Transportation and Fleet Maint. to confirm end user data needs for ORCA. Continue initial DOPLHIN testing. 2025-03-31: Continue working with Transportation and Fleet Maint. to confirm end user data needs for ORCA. Continue initial DOPLHIN testing. 2025-03-24: Resolve weekend Spotfire conversion issues. Continue working with Transportation to confirm end user data needs for ORCA. Continue initial DOPLHIN testing. 2025-03-17: Continue working with Transportation to confirm end user data needs for ORCA. Continue initial DOPLHIN testing. 2025-03-10: Continue initial DOPLHIN testing. Continue working with Transportation to confirm end user data needs for ORCA. 2025-03-03: Continue initial DOPLHIN testing. Confirm end user data needs for ORCA. 2025-02-24: User Testing of first | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-06-17 | 2025-11-03
Business Only Initiative: [Enabler] Operational Handling Unit Metric | 55715 | 7881 | Business Only Initiative | FXF - Dock | Freight | Edgar Correa, Staci Prewitt | On Track | Waiting on the solution from HUM from the Groupings perspective, since that data is a critical show stopper for this initiative. | E: L2 | On Hold | L2
Business Only Initiative: [Enabler] Dock Bidding System | 45546 | 7883 | Business Only Initiative | FXF - Dock | Freight | Kelsey Grape, Staci Prewitt | On Track | 5/15- Tool has seen steady use for over 3 months, prepping to surge to L5 | K: L5 | Completed | L5 | 2024-01-22 | 2025-01-03
Business Only Initiative: Quality Starts with Me Campaign - Claims Reduction | 94131 | 7884 | Business Only Initiative | FXF - Dock | Freight | Daniel Mellis, Staci Prewitt, Brent Longoria | On Track | 3/27/2025 approved for L5 and will look at for reforecast due to exceeding forecast. 3/26/2025 L5 Surge 3/27/25. 12/17/24 L4 surge call 12/19/24. Money Step evidence uploaded to planview 12/6/24 L3 reached. solutions in action. will begin reporting actuals. 10/21/24 - IO working to update Planview with L2 info and seek L3. We are continuing to evaluate the Chem Spill data to represent the additional cost savings by avoiding Chem Spills with improved quality practices. As that is finalized we will add this to Planview. | K: L5 | Completed | L5 | 2024-06-03 | 2024-12-04
Business Only Initiative: Poly-Woven Airbags | 33233 | 7885 | Business Only Initiative | FXF - Dock | Freight | Kathleen Crawford, Staci Prewitt | On Track | 1/19: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 1/19: Continue to work with sav-a-bundle team as opportunities are identifed and provide education back to the field. 1/12: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 1/5: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 12/29: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 12/22: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 12/15: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 12/8: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 12/1: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 11/24: Continue to work with sav-a-bundle team as opportunities are identified and provide education back to the field. 11/17: Follow up messages regarding sav-a-bundle trip sent to SCMs and MDs. Updating FCF with the standard inflator including the hose which will allow Sigma to pull them in bulk and store at their warehouses and quicker delivery to operations. 11/10: The team met this past Thursday (11/6) to review findings from the trip to sav-a-bundle. Dusty provide a powerpoint and word document recapping the visit. Follow up messages will be sent to the SCMs and an overview to the MDs reviewing the findings and opportunities. 11/3: The team will review the trip to sav-a-bundle on Thursday and determine next steps for education, communication, and the recycling process. 10/27: Part of the team is meeting at sav-a-bundle this week. The recycling process is still being determined if it will be updated or not. 10/20: Bo and Amber are having further discussions to update the recycling process with the addition of the consolidation hubs and will update the team. A trip to sav-a-bundle at the end of the month is planned. 10/13 Week: Held meeting last week with the internal team (ops, sav-a-bundle) and reviewed the possible update to the recycling process with the addition of the consolidation hubs. Bo and Amber are having further disussions and will update the team. A trip to sav-a-bundle at the end of the month is planned. 10/6 Week: Bo sent comms to the field regarding the survey. Internal team call scheduled for 10/9 to discuss recycling and visit to sav-a-bundle. 9/29 Week: Bo will be sending out communication. 9/22 Week: Following up with Bo on the communication to the field. 9/15 Week: The two deflating tools were added to the FCF for ops to purchase. Bo will be sending out a message to ops regarding the survey feedback and deflate options. 9/8 Week: Overall very favorable survey feedback with the 257 responses we received. Pleased to see that 73% recognize that a poly woven airbag should be used 5+ times. The biggest call out was deflating airbags. We have a call on 9/12 for us to touch base as a group on how to address deflating airbags. 9/2 Week: We have had 158 survey responses, and Bo sent a reminder message to SCMs to complete by the deadline of 9/4. 8/25 Week: This week a survey was sent to SCM's to gain additional insight into the Poly-Woven Airbag DRIVE initiative. 8/18 Week: Bo and I are working on publishing a survey to go out to the field no later than 8/25. 8/11 Week: Bo provided feedback last week and Cory is coordinating with MDs on the recycling/reuse process. 8/4 | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-09-13 | 2025-04-28
Business w/ Tech Initiative: Recovery Operations Control System | 91338 | 7886 | Business w/ Tech Initiative | FXF - Dock | Freight | Frank King, Staci Prewitt | On Track | 7/1/2025 On hold per pause/continue dispostion 6/19/2025 Working with Jessie Melton on potential options to accomplish work. And couple the work with Freight separation. They now have the information documented within the Tech Separation plan that this will need rewrite/build. Timing to get started likely a few months. 5/8/2025 per message with Jennifer Choate, Ryan Plumee and Jessie Melton- This one completed business architecture and the hold up is that we could not find an IT team to own/pick up the work. In order to move forward, we need an IT team assigned. The work could be done to identify the IT team(s) that should own this, but no development could be planned until we have a path forward for tech separation and other high priority initiatives tied to Freight's preferred future state first. 5/5/2025 removed hold and back to active to ensure it remains on enterprise priority list. messaged Ryan Plumlee to ensure alignment on next steps. 5/01/2025 Placing on hold until more details regarding ownership are available. 4/28/2025Staci will contact Jennifer Choate to inquire, If there are items in Planview that can be completed when it can be taken off "on hold" it can help expedite progress. It is currently on hold pending details on the separation plan for IT support since this is a business system no IT team will accepted ownership at this time. Still waiting on some insight for tech needed. 4/17/25 This is recommended to go back to L1 due to some missing planview.Staci will work with Frank to get these items in Planview so when it can be taken off "on hold" it can help expedite progress. It is currently on hold pending details on the separation plan for IT support since this is a business system no IT team will accepted ownership at this time. 3/27/25 "some issues" noted due to lack of update and movement. | E: L2 | On Hold | L2
Business Only Initiative: [Enabler] Progressive Trailer Loading (PTL) | 82690 | 7887 | Business Only Initiative | FXF - Dock | Freight | Karl Olsheski, Staci Prewitt | On Track | 1/2/25 PTL launch still going well. Seeing improves across the company in Bills per Trailer and TCU %. 11/17/25 PTL has been launched to the company. Pre-shift for PTL went out on 11/14/25. 11/13/25 Confirmed launch of PTL to company. Official pre-shift with be released 11/14/25. Updated photos in QRG's and updated corp comms. Interest in PTL in many districts have been expressed since the TCU goal adjustment. SOWE, NOWE, SOEA and NOEA have start to apply tapeline to each forklift. Seeing positive results in SOWE regions with earlier rollouts. 10/30/25 Met with RVPs for approval to move forward with company launch. Recieved the approval. Call setup with FE managers to discuss rollout plan and launch date on 10/30/25. Will update planview once setting date. 10/9/25 Had meeting with MEM for PTL rollout and feedback. MEM would like to simplify the instructions and guidelines. MEM has seen TCU improves during the first week. Reworked the QRG to have instructions for one green line to deck shipments. Short instructions for shipments above and below the line. Reached out to L&D to update the infographic to adjust to the new QRG. Goal is to release PTL to the company during quality week 10/20. 10/2/2025 Continuing to work with MEM for PTL launch. Going to meet with MEM ops today to get feedback. 9/11/2025 Reached out to MEM SCM. They are planning to pilot after installing the tapeline. Going live with HUM which is delaying the rollout of PTL. 8/21/25 MEM selected as center to do the commuication campaign. Reached out to MEM with all documents and set to launch 8/25/25. Contacted FE in ME district to get local support. 8/14/25 Presented PTL to Trevor & Pat. Both agreed the project should move forward. Trevor requested for a roll out campaign in MEM or NEM. Reaching out to local FE in ME district to align a plan for the roll out. 8/7/25 Set meeting with Trevor, Pat, and Cory to review PTL documents for 8/11/25. If approved will move towards a meeting with RVPs then launch. 7/24/25 Updated infographic from L&D. Reviewed the QRG and infographic with FE's, mentors and ops. Positive feedback, need to make the size description a bit more detailed on infographic. Reached out to corp comms about setting a communication launch date. 7/3/25 Got first draft of infographic from L&D. Looks good so far. Sent back a few notes to simplify the documents and a few corrections. Reached out to corp coms to update the pre-shift launch document. 6/19/25 Charlie Baggett informed he has taken a new position with FEC. Contacted Eric and Ken for an infographic. They said I would have an update and waiting on their response. 6/12/25 Reached out to Charlie Baggett about infographic. They were have a meeting this week about it. Haven't recieved an update yet. Brent has modified the video from KCY. 6/5/25 Had meeting with Ken Cary, Eric Cocco, Charlie Baggett, Cory Herrman and Brent Longoria for follow up L&D meeting. Reviewed the updated QRG and got a lot feedback. L&D would like to create an infographic for PTL/TDL. Made updates to QRG and sent copies to everyone the call. Created ways to remember PTL/TDL messaging and added the data facts behind it. Got video from KCY on 6/4/25 and working with Brent to review video footage. 5/29/25 Working with Danny Drabek in KCY to get a video of TDL. 5/22/25 Call to review new QRG with Cory, Brent and Staci. Working with KCY to get a video example of PTL/TDL in action. Will be setting a meeting with L&D with the new QRG and ways to add this part of new hire training for freight handlers. 5/15/25 Shared rewrite of QRG with Brent. Positive feedback for simplifying the QRG. Adding new pictures with adjusted tapeline. 5/8/25 Created query to confirm different tapeline for forklifts. FY24 30"-70" range 56.34 % to deck, Under 30" 34.6 %, Over 70" 9.06 %. Reduced down QRG and instructions. Will be looking to get feedback on the QRG. 5/1/25 Met with L&D to review QRG and simplified version. Gave advi | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-07-02 | 2025-11-17
Business Only Initiative: Rack 'Em | 82691 | 7888 | Business Only Initiative | FXF - Dock | Freight | Nathan Kulikowski, Mark Parisher, Staci Prewitt | On Track | 6/5/2025 * Expansion options have been determined. * Creating a blueprint guide that will be given to each center on how to install and implement the effective use of racks in each center. * Working with granger rep on alternative parts that will substitue effectively and safely for the parts that are discontinued. * Will work will Granger on a bulk deal as well if we are going to order hundreds of thousands of dollars of equipment. | K: L5 | Completed | L5 | 2023-09-01 | 2025-02-07
Business Only Initiative: Rehandle Tool | 87091 | 7889 | Business Only Initiative | FXF - Dock | Freight | Daniel McKnought, Mark Parisher, Staci Prewitt, Deborah Harrison | On Track | 5/8 - April Actuals Entered 4/14 * Adjusting trap discipline code to fully automate reporting. | K: L5 | Completed | L5 | 2024-08-06 | 2024-12-27
Business w/ Tech Initiative: (Enabler)iSPI upgrade and enhancements | 26244 | 7896 | Business w/ Tech Initiative | FXF - Dock | Freight | Andrew Smith, Erin Reesman, Stefanie Larson | On Track | 7/28/25: The development team is actively working on four key items: 1. Filter Aliases which is done but waiting on MTP, 2. The capability to bill Y0 Recovery in iSPI is in the business testing phase and once confirmed will MTP, 3. The ability to convert a confirmed R0 to C0/D0 in iSPI in development. 4. Void Pros/Cancel Pros is in IT testing. 7/14/25: Team has continued testing Aliases search and will be complete with that work once Zip Code work is completed. Y0 enhancement is completed. Both enhancements are planned to MTP on 7/26. 6/25/25: Dev team moved the Ref Edits feature to prod on 6/14. 06/11/25: Dev team has begun testing Ref Edits is in UAT testing and all other iteams are still in Progress. 06/02/25: Dev team continues to work on the same stories as previous week. 05/27/25: The development team is actively working on four key items: 1. Filter Aliases, 2. Intra-Center Volume Shipments, 3. The capability to bill Y0 Recovery in iSPI, and 4. The ability to convert a confirmed R0 to C0/D0 in iSPI. Additionally, the reference edit enhancement is planned to be migrated to production (MTP) later this program increment once Kris has completed everything. Valentina continues to work on Angular upgrade. 05/14/25: Dev team continues to work on the 4 items: 1. Filter Aliases, 2. Intra-Center Volume shipments, 3. Ability to bill Y0 Recovery bill in iSPI, and 4. Ability to convert a confirmed R0 to C0/D0 in iSPI. We also will MTP the reference edit enhancement sometime this PI. 04/28/25: We begin the next PI on 04/30/25 and the developement team will begin working 4 additional items toward this project. 1. Filter Aliases, 2. Intra-Center Volume shipments, 3. Ability to bill Y0 Recovery bill in iSPI, and 4. Ability to convert a cofnirmed R0 to C0/D0 in iSPI. We also will MTP the reference edit enhancement sometime this PI. 04/12/25: Successful MTP today 04/12/25 for the 3 enhancments. Now working on planning the next items for the dev team to work on. Meetings scheduled this week for alignment. 04/09/25: MTP scheduled for 04/12/25 for 3 enhancements: 1. Intra-Canada functionality, 2. Arrival and departure times for non-confirmed shipments, and 3. Extreme length notification. I am currently developing educational documentation to support this effort. 03/31/25: MTP targeted for 03/29/25 has been moved to 04/12/25. 03/25/25: Three of the four enhancements are scheduled for deployment to production this weekend, March 29, 2025. The enhancements include: 1. Intra-Canada functionality, 2. Arrival and departure times for non-confirmed shipments, and 3. Extreme length notification. I am currently developing educational documentation to support this effort. 03/14/25: Inta-Canada Shipment defaulting to Prioirty is complete and will MTP on 03/29/25. Arrive and Depart times for non confirmed shipments is complete and will MTP on 03/29/25. Extreme Lenth error message when over 12 feet is entered is complete and in L3 for UAT testing. Reference Edit requirements for all shipments is half complete, the design of the entry and error message is complete. Next will be the message when user selects complete and they have not entered a ref edit. 03/10/25: B-2342977 is ready for UAT testing, this is the arrive and depart times story. Also the Ref Edit (B-2351612) story and DIMS(B-2342939) story both are behind actively worked this week. 02/28/25: B-2369745 is in Build (FBE GUI updates) B-2342977 is in Build (Modify the current process that is pulling data from drivers or default values and use data entere if there). B-2342946 is in UAT testing (Intra Canada shipment: if shipper and consingee country codes are Ca then deafult the shipment to priority) 02/21/25: Dev team working on B-2342946 Intra-Canada shipment and B-2351574 Intra-Canada Design Document. Also working B-2342974 Arrive and Depart Times GUI and B2342975 Arrive and Depart times values in boxes. B2369743 FBE GUI updates to angular. 02/09/25: The development team h | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-07-22 | 2027-05-18
Business Only Initiative: [Enabler] Trailer Fill: DIM | 26136 | 8086 | Business Only Initiative | FXF - Dock | Freight | Kevin Kotil, Tomm Brennan | On Track | N/A | K: L5 | Completed | L5 | 2023-06-13 | 2024-01-12
Business Only Initiative: FXF - BO - [Enabler] - Geofence Modernization (GFM | 26286 | 8087 | Business Only Initiative | FXF - Dock | Freight | Mark Williams, Tomm Brennan | On Track | 2025-09-29: Monitor compliance and feedback. 2025-09-22: Monitor compliance and feedback. 2025-09-15: Monitor compliance and feedback. 2025-09-08: Monitor compliance and feedback. 2025-09-01: Monitor compliance and feedback. 2025-08-25: Monitor compliance and feedback. 2025-08-18: Monitor compliance and feedback. 2025-08-11: Monitor compliance and feedback. 2025-08-04: Monitor compliance and feedback. Enter July actuals. 2025-07-28: Monitor compliance and feedback. 2025-07-21: Monitor compliance and feedback. 2025-07-14: Monitor compliance and feedback. 2025-07-07: Monitor compliance and feedback. 2025-06-30: Monitor compliance and feedback. 2025-06-23: L4 Approved. 2025-06-16: Discuss moving to L4 and review L4 requirements. 2025-06-09: Development/testing of procedure to read and write synapse table data from GeoApp to Driver Handheld. OR is actively working to finalize the DB2/pureScale table update process. & testing the soluiton. The process is in production now - on demand the application will write to the Prod EDEN tables. Right now, Dennis Jamiot is the only user authorized for that. 2025-06-02: Development/testing of procedure to read and write synapse table data from GeoApp to Driver Handheld. OR is actively working to finalize the DB2/pureScale table update process. & testing the soluiton. The process is in production now - on demand the application will write to the Prod EDEN tables. Right now, Dennis Jamiot is the only user authorized for that. 2025-05-26: Development/testing of procedure to read and write synapse table data from GeoApp to Driver Handheld. OR is actively working on / testing the soluiton. 2025-05-19: Development/testing of procedure to read and write synapse table data from GeoApp to Driver Handheld. OR is actively working on the soluiton. 2025-05-12: Pending step is for FXF OR to set up procedure to read and write synapse table data from GeoApp to Driver Handheld. OR ownership just moved to Jaime Outlaw, Timeline has not been established. 2025-05-05: Pending step is for FXF OR to set up procedure to read and write synapse table data from GeoApp to Driver Handheld. OR ownership just moved to Jaime Outlaw, Timeline has not been established. 2025-04-28: Pending step is for FXF OR to set up procedure to read and write synapse table data from GeoApp to Driver Handheld. OR ownership just moved to Jaime Outlaw, Timeline has not been established. 2025-04-21: Pending step is for FXF OR to set up procedure to read and write synapse table data from GeoApp to Driver Handheld. OR ownership just moved to Jaime Outlaw, Timeline has not been established. 2025-04-14: Pending step is for FXF OR to set up procedure to read and write synapse table data from GeoApp to Driver Handheld. OR ownership just moved to Jaime Outlaw, Timeline has not been established. 2025-04-07: Pending step is for FXF OR to set up procedure to read and write synapse table data from GeoApp to Driver Handheld. OR ownership just moved to Jaime Outlaw, Timeline has not been established. 2025-03-31: Pending step is for FXF IT to set up process to read and write synapse table data from GeoApp to Driver Handheld. IT ownership has been determnied, Jim Connolly / IT Director and Steve Rosamond / IT Manager. Completion Timeline has not been established. 2025-03-24: Pending step is for FXF IT to set up process to read and write synapse table data from GeoApp to Driver Handheld. IT ownership has been determnied, Jim Connolly / IT Director and Steve Rosamond / IT Manager. Completion Timline has not been established. 2025-03-17: Pending step is for FXF IT to set up process to read and write synapse table data from GeoApp to Driver Handheld. IT ownership has been determnied, Completion Timline has not been established. 2025-03-10: Pending step is for FXF IT to set up process to read and write synapse table data from GeoApp to Driver Handheld. IT ownership has been determnied, Completion Timline | K: L5 | Completed | L5 | 2024-01-29 | 2025-06-02
Business Only Initiative: Hostler Visibility Improvement | 96102 | 8237 | Business Only Initiative | FXF - Dock | Freight | Kenji Fincher, Brian Mellis | On Track | 7/10/25 - No additonal updates at this time, other than finalizing June actuals. | K: L5 | Completed | L5 | 2024-10-01 | 2024-12-02
Business Only Initiative: Enabler - FXF Account Clean Up | 48046 | 9046 | Business Only Initiative | FXF - Dock | Freight | Andrew Smith, Stefanie Larson, Garrett Hammers | On Track | Still on going 7/14: Michele Rogers is working with the Apollo team for access for the pricing data. Apollo Dev team will need to write the FXF data to Atlas. Apollo team is still determining a timeline. | K: L5 | Completed | L5 | 2023-11-02 | 2025-04-04
Business w/ Tech Initiative: Cabnit Retirement | 86939 | 9317 | Business w/ Tech Initiative | FXF - Dock | Freight | Ashley Campbell, Garrett Hammers, Jim McBee, Shaun Bullock, Belinda Veach | On Track | 4/25/25 Business UAT 100% Complete on 4/24. New app is live as of 4/25. Cabnit to fully retire/shutdown 4/27. We will terminate the sftp outbound in FedEx Net at 1145am CT on Sunday 4/27. We will have Dataworks dev team for 2 weeks after production deployment. 4/17/25: Production development underway. Test environment is stood up with files loaded. Business will begin UAT 4/18 and will work through 4/24. 4/11/25: UI development work is delayed due to data pipeline issues. UAT delayed until test environment ready. Engaged Dataworks team to get alignement on post-production support process. 4/4/25: : UI development work is delayed due to functionality issues - team is working through the weekend to resolve. UAT delayed start, new date TBD. SFTP mailbox in FedEx Net CABNITUAT_MB and folder DATA2CABNITUATPROCESSED created. 3/28/25: UI development work is on track; UAT expected to start 1st week of April. SFTP mailbox in FedEx Net CABNITUAT_MB and folder DATA2CABNITUATPROCESSED created. 3/21/25: UI development work is on track; UAT expected to start 1st week of April. Taylor Robinson & I are working with the EDI team to understand preferences for Cabnit data load, so the history will feed to the new App. 3/14/25: UI development for Dataworks Updates is in progress and on track. EDIHelp team engaged and awaiting our readiness on the SFTP updates 3/7/25: The FedexNet Report Testing for interim solution is complete. UI development for Dataworks Updates is in progress and on track, with some VPN-related Angular errors being resolved. EDIHelp team engaged and awaiting our readiness on the SFTP updates. 2/28/25: Ingestion framework is paused due to issue with position-based files. Call set up 3/4 to discuss what this means. UI demo held this week, and minimalist approach is user friendly and clean for Business partners. 2/21/25: Development work in progress & on track. The team is finalizing Redis configurations to support data storage and system performance, keeping Dataworks on track for their CloudOps infrastructure milestone. Making efforts to ensure that the Accenture resources are fully onboarded with the appropriate access. Team intends to have the UI mockup ready for review on February 21st. 2/14/25: FIRST Request Closed (EAI 3541200 XNET Reports in Azure). Contractors onboarded as of 2/7. Deep Dive with Dataworks scheduled 2/12; successfully introduced Cabnit system & answered technical questions. 2/7/25:Intake Form submitted to Data Ingestion team. Positive progress on OIP subscription build. FIRST for (EAI 3541200 XNET Reports in Azure) have two of the five InfoSec domains has been approved, but the others are still 'under review' 1/31/25:Work on non-production infrastructure has started. Intake form for Data ingestion team submitted and call to be scheduled to review solution context, Q&A before pipeline is established. 1/24/25: Greenlight to start work 1/24/25; added milestone and flipped to 'In Progress'. Taylor Robinson will be attending their DSU for alignment on a technical level. FIRST still in progress. No issues as Interim Work-Around testing continues til the end of February. 1/17/25: Dataworks given greenlight to start work. FIRST work continues for 3541200 XNET Reports in Azure) 1/13/25: Set up a weekly 15 minute reoccurring call with Dataworks/Taylor Robinson for progress updates. FIRST in progress for (EAI 3541200 XNET Reports in Azure). Screening and fast-track questions submitted. Domain questions completed but pending submission. New BCDR Plan required for Azure-based solution (receiving files via FedEx Net SFTP); Taylor Robinson is working on this 1/7/25: Dataworks estimated completion timeline is end of March. FIRST in progress (EAI 3541200 XNET Reports in Azure). Team is also working through creation of new BCDR. 12/6/24: Met with Ray on short term soultion since we do not know Dataworks timeline to complete. Updated Milestone to add short-term solutioning. Met with FedEx Net and setup m | K: L5 | Completed | L5 | 2024-04-04 | 2025-04-28
Business w/ Tech Initiative: Tricolor Feight Heavy Weight | 74314 | 9320 | Business w/ Tech Initiative | FXF - Dock | Freight | Michael Anderson, Ashley Campbell | On Track | 3-6-25: Putting work on hold for now due to seperation activities and need to evaluate how to handle these scenarios with the future setup. 2/24/25: Recommendation to pause work due to the separation of FXF. Meetings to be held on next steps soon. 2/11/25: Decomp for Dock confirmation started on 2/10. Reviewed key requirements for Dock Drops & SLC Possession Scans. 12/6/24: Trap Routes for FXHW Service Levels: Goal is to enable creation and maintenance of FXHW-specific trap routes that are protected from deletion by operations staff, leveraging functionality similar to current admin trap routes. Process & Ownership Clarifications: Admin trap routes require IT involvement for creation (led by Christopher Gardiner and Balasubramanium Muniswamy). There is a need to define ownership and processes for FXHW trap routes, distinguishing between DIRT3000 and DIRT3001 systems. Next Steps: Set up a meeting to confirm ownership and responsibilities, involving key stakeholders like Dustin Creamer (new owner of delivery planner) and relevant tech leads (e.g., Don Rogers) 11/8//24: Continuing working sessions with Architecture. The team debated the necessity of distinct NFRs for each epic versus a combined approach, similar to the previous value bundle. Decomposition is ongoing for Capability 2.2, which seeks to provide FXF planners, including City and Dock teams, visibility into incoming FXEHW shipment volumes with service types eligible for handoff to FXF 10/25/24: SIPOC diagram work for Heavyweight Keywords to trigger banners (like guaranteed keywords). Pulling together workstreams to start formulating milestones and potential target completion dates. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-08-22 | 2025-11-07
Business w/ Tech Initiative: Dock Layout Tool Mod. | 26134 | 9543 | Business w/ Tech Initiative | FXF - Dock | Freight | Kevin Kotil, Mark Aparicio, Mark Williams | On Track | 09/03/2025: - Re-education complete with each SME in each Region has been complete. - 17 of 26 Districts have completed at least 1 Class 1 or 2 SC. 07/23/2025: - Testing continues with no issues reported as of 07/23/2025 05/28/2025: --Back end code has been updated to accept 8-digit employee numbers and deployed to production in anticipation of 8 digit employee numbers starting 01/01/2026 5/22/2025: -All approved pending updates have been completed, prelimiarily successfully tested and move to production. -DLO Core testing team has been notified and futher testing and scrutenizing has been requested. 5/15/2025: - IB layout upload ability in test environment. Still testing 4/30/2025: - Deploying the following updates to test, and will look for PROD approval after testing/validation next week: - IB layout upload to test - Clear all button that moves all cards currently on the layout back the the left side of the screen. - Auto-populate the layout with the previously "implemented" layout for the specific shift. Currently if you previously implemented a layout for OB-HUB it would pre-populate for the OB or the HUB shift, but now it'll only pre-populate with the distinct matching shift. 4/15/2025: - Deployed latest updates to production, which includes the following features: - Autopopulating the layout with previously implemented layout - Removing necessity to put the cards on the layout prior to optimizing. created a feautre to auto dump to the layout - Next steps: work on import feature for IB layouts, remove seconds from cut time, change cubic feet to trailer count 4/9/2025: Working on changes to SQL, Java, and UI: - Ability to save the latest implemented layout and auto populate when going to a dock layout screen the next time the user requests data - Removing the necessity to place cards before optimizing - Cards are placed randomly when Optimize button is clicked - Updated the information that will be displayed in logs Changes in Terraform: - Adding a custom log search alert for DLO Java component that notifies the action group if an exception occurs The following changes have been pushed to test: - Ability to save the latest implemented layout and auto populate when going to a dock layout screen the next time the user requests data - Removing the necessity to place cards before optimizing - Cards are placed randomly when Optimize button is clicked 4/8/2025: - Released the latest updates to the tool and provided communications to the Feild Engineering Team 4/3/2025: - Push to prod awaiting Cab Approval. If approved plan to push tomorrow(4/4) - Prod push includes: - Sorting/filtering on the lanes tab - Displaying weight and cut time on exported layout 4/1/2025: - Testing currently underway in the test environment for the latest updtes to the lanes tab to include the sorting and filtering functionality. - Dataworks also deployed the ability to view the weight and cut time for the door on the exported "optimized layout", as well as the implemented layout. 3/26/2025: - Planning to deploy updates to production next week after testing. Which includes the following: - Display Break Bulk 1 AND the service lelvel code in the lanes tab - Adding the ability to sort and filter for the expanded colums within the lanes tab - Display the average daily weight and cut time in the exported PDF of the layout 3/20/2025: - Mark Aparicio is Engaged with Dataworks team and working to complete some backlog items as time permits with the developers schedule (first item to complete is filtering) 3/17/2025: - Released the latest changes to production on the compliance tab - Trevor, Jason, Cory to meet with DW leadership to discuss necessary steps to complete the remaining backlog items 3/12/2025: - Waiting for approval from ankit/raymond on approving the latest changes, both Ankit & Raymond are out of office - Mark Aparicio is engaged with developers to get backlog items prioritized. 03/06/2025: - Developers are working t | K: L5 | Completed | L5 | 2023-02-28 | 2024-11-01
Business Only Initiative: Rehandle Reduction | 26137 | 9547 | Business Only Initiative | FXF - Dock | Freight | Cory Estes, Jacob Maher | On Track | -On hold due to OR resource being on higher priority objectives. Will continue work once the OR resource frees up - Raymond will provide me an update on resource allocation on 8/30 | E: L2 | On Hold | L2 | 2023-06-14 | 2024-08-13
Business Only Initiative: Dock Execution Planning | 26138 | 9549 | Business Only Initiative | FXF - Dock | Freight | Edgar Correa, Kelsey Grape | On Track | Completed and banked $14,176,198 for FY 25. | K: L5 | Completed | L5 - Restarted Initiative | 2023-08-04 | 2024-12-27
Business Only Initiative: Punch to Scan/Scan to Punch |  | 80152 | Business Only Initiative | FXF - Dock | Freight | Daniel McKnought, Brent Longoria | On Track | 3/11- Made adjustment to actuals to exclude system outage on the 8th of Feb 2/20 - Continuing to see incremental improvements even through weather and backlog. 2/13- Trending towards 34 mins making incremental gains. Had many discussions with operators on details of the report it is getting solid attention. Financials entered. 1/30-Discussed Refresh Schedule for OPM data to prevent issues with data integrity. Now have the capability drill into all the punch scan events that make up ttl punch to scan 1//14 - Launched Weekly/ Monthly Progress tracking 1/7- Continuing to send email to highlight opportunities 12/19- surge call 12/9 - Updated email / excel format better fit operations needs 12/2 - Started Sending daily email to field with excel workbook 11/25- Sent initiation email to RVPs 11/18-surge call today @1500 11/13- starting on SL2 surge info to enter into Planview. 11/12- submitted for SL1 approval Surge call scheduled for 11/18 or 11/20 for L3. planning to surge beforee 11/22 cutoff. 11/05- spoke with Laurie to fill her in on LBC. Working on goals per center based on performance and opportunity for improvement. Surge call scheduled for 11/11 for L2 | K: L5 | Completed | L5 | 2024-11-18 | 2024-12-02
Business Only Initiative: DIM Preventive Maintenance |  | 87982 | Business Only Initiative | FXF - Dock | Freight | Garrett Hammers, Korey Ranson | On Track | 11/19: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. Reduce preventative maintenance schedule from twice a year to once a year | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-10-07 | 2025-01-31
Business Only Initiative: PT Freight Handler Reduction |  | 91969 | Business Only Initiative | FXF - Dock | Freight | Justin Schuller, Staci Prewitt, John Hewitt | On Track | 04/01/2025 - placed on hold while a comprehensive pilot is conducted. Data is needed to propery financials. Timing is estimated at least 6 months before data woudl be available to use. 03/27/25 - Still looking for finance approval to move to L2. No other update. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: 92261 - Modernized OS&D Processing System |  | 92261 | Business w/ Tech Initiative | FXF - Dock | Freight | Kirby Brooks, Amber Taylor, Garrett Hammers | On Track | On hold due to prioritization for resourcing. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: FXF Fraud Reduction |  | 97670 | Business Only Initiative | FXF - Dock | Freight | Samuel Nunez, Garrett Hammers | On Track | On hold due to prioritization on resourcing. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Mexico to US Transit (ML16 change) |  | 104465 | Business w/ Tech Initiative | FXF - Dock | Freight | Michael Anderson, Kelli Ostertag | On Track | 1-16-26: Placing On HOLD. Heavy lift as this touches ML16. 5/1: Surged and approved 4/29/25: QA Review performed by Kelli Ostertag, approved. Scheduled for Surge to L2 on 5/1 4/25: updated information that EPM was requesting feedback on. Scheduled for QA on 4/29/25 | E: L2 | On Hold | L2
Business w/ Tech Initiative: Driver Handheld and Modernized OSD Exception App |  | 106287 | Business w/ Tech Initiative | FXF - Dock | Freight | Kirby Brooks, Amber Taylor, Garrett Hammers | On Track | On hold due to prioritization for resourcing. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Field Engineering Measurements & Compliance |  | 106290 | Business Only Initiative | FXF - Dock | Freight | Jacob Maher, Daniel McKnought | On Track | 6/26- No Major update, slow rolling with STASH requirements 6/19- Hosted the call with Cory and Trevor. Currently we are in a space and pace as we wait for more of a prioritization list to come out. Continuing to slowly work with OR on STASH requirements and prepping for future state. 6/12- Had to reschedule the touch base call due to OoO to 6/16. Continuing to work with STASH devs in the mean time. 6/5- Talked with Jamie about getting STASH development underway. Wanting to confirm we've got our heads on straight and focusing on STASH is the right move. 5/26- Met with End Users of Stash to develop a list of requirements for a reimagination of the tool. Stash is looking to be one of the two corner stones of this initiative. The second being the dashboard to show our plan scores. 5/19- Meeting with end users and stash developers is scheduled for later next week. Developing a list to action items for it. Also developing LBC for final dashboard. 5/12- Met with Damon to go over stash tool usage at MEM. There isn't much usage there, but it warrented a second look. Follow up meeting scheduled 5/19. 5/5- Looking to meet with FE at MEM togo over the stash tool and do a thought experiment on how accurate it can be without changes. 4/28- Attended Stash call and are looking to field test the tool when time allows. Diving into PSP Metrics to start assigning plans to metrics. 4/21- Continuing to meet with FEs to discuss engineering plans and Stash call on friday 4/25 4/14- Stash review call has been pushed back again to next friday. We are meeting with FEs to understand the tools used to make engineering plans. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Enhanced trailer markings |  | 107853 | Business w/ Tech Initiative | FXF - Dock | Freight | Jack Johnson, Brett Adams | On Track | ON HOLD | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: CORE: LTC Modernization |  | 107893 | Business w/ Tech Initiative | FXF - Dock | Freight | Jacob Kirkpatrick, Mark Parisher, Shane Turner | On Track | 06/30: Project On Hold due to seperation reprioritization notice per Cory Herrman. 06/17: Completed call with finance & additional I/O to discuss combination of initiatives & financail step focus. Currently in holding pattern until finance finishes review of deck that Dustin prepared that focuses on a delivery exception ratio vs $$$ amount. 06/10: Received Architecture alignment confirmation that the L1 Architecture Alignment Step has been completed. Linking to to planview. Will follow steps to update impacted portfolios & T-Shirt size as well. 06/09: Completed call with finance to discuss combining with other core initiatives. 06/03/2025: Combining with other core initiatives to create Core Quality which will allow us to pool resources. 05/28: Worked through L2 requirements & LBC. In progress pending finance & pod lead review. 05/21: Uploaded supporting documents of LTC logic, linehaul notation, & LTC logic within shipments life cycle. Received & reviewing LBC from another innovation project to help guide how this project will determine/capture financials. Will be deciding on a primary KPI to focus on in the upcoming week. 05/13: Aquired Individual H/U decks from SGF pilot. Uploaded all decks associated with Individual H/U to shared TEAM site for Shane & myslef. Updated Brief Demand Description 05/02: Completed call with Dustin/Shane to go over initial steps of updating planview. Completed calls with Shane & myself discuccing current LTC logic & how (if unchanged) ) would impact current OSD exception entry if applied to multiple handing units. 04/25/25: Contacted project leads of individual handling unit to inform of our project and open comms for future collaboration. 04/25/25:Working on LBC, meeting with Lori in finace on 04/29/25. Working through L1 checklist. 4/14/24: Creating LBC and identifying relevant metrics. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: CORE: Network Decking |  | 107902 | Business w/ Tech Initiative | FXF - Dock | Freight | Kelsey Grape, Mark Parisher, Kevin Kotil | On Track | 6/26- Change to enabler for Load Quality Audit (UPR #: 9012987; PPM proposal #: 856518) | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: CORE: Load Quality Audit |  | 107909 | Business w/ Tech Initiative | FXF - Dock | Freight | Christen Daniels, Shane Turner | On Track | 6/30/25: Initiative placed on hold to prioritize resouces needed for FXF separation. 6/27/25: New measurements approved. Load Quality Audit initiative will track damage exceptions and use damage claims $$ for savings. Changed the lean business case and uploaded it to planview. Changed the details in planview. Ready to move forward. 6/25/25: Proposed a way to measure impacts separately for each CORE Quality initiative. Submitted to finance for review. 6/18/25: L2 pending review of other CORE quality initiatives, LTC Modernization and Network Decking. To determine best way to keep impact results separate. New methodology is being reviewed by finance. 6/10/25: L2 pending review of other CORE quality initiatives, LTC Modernization and Network Decking. To determine best way to keep impact results separate. 5/29/25: Waiting on finance domain lead approval to L2. The initiative is #83 in the Enterprise L2 Priority list. I/O Christen Daniels out of office 5/30/25 through 6/6/25. 5/27/2025: Reviewed financials with Jarod Vonderheide, Brad Nieman, Cody Snook, Trevor Bettley, Cory Herrman. Approved and agreed upon a 1.8% reduction in LTC goal, but impact assessment will begin in Q1FY27 and go through FY28 due to the claims cycle. Submitted for L2. 5/22/25: Surge attempted. Meet with Trevor Bettley and Alex Thomas to review financials again. 5/21/25: QA reviewed and approved by Staci Prewitt. 5/19/25: Financials approved by finance and pod lead. Impact has been updated in Planview. Next step is LBC QA. 5/14/25: Meeting scheduled for Monday 5/19/25 to review the new FY25 savings estimate. 5/7/25: Continue work on LBC. Approved by finance to use Claim Cost per OB/HUB LTC to measure impact. 5/5/25: Continuing work on LBC. Waiting for approval to use Claim Cost per OB/HUB LTC to measure impact. 5/1/25: Laurie O. will follow up with Alex - Claims Reduction is in L5 and might be over by the time LQA App is launched. 4/28/24: Continue working on LBC. Met with Finance this week to review savings estimates. There is concern that the method used to assess savings overlaps with the Claims Reduction initiative. Met with IOs from Claims Reduction this week to discuss. Work in progress to determine best way to measure savings without any overlap or double-dipping. | C: L1 | On Hold | L1 Feedback Requested
Business w/ Tech Initiative: FXF Mobile Dock Application |  | 107913 | Business w/ Tech Initiative | FXF - Dock | Freight | Aaron Griffin, Garrett Hammers, Korey Ranson | On Track | On hold due to prioritization on resourcing. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Facility Maintenance - Custodian Program |  | 110320 | Business Only Initiative | FXF - Dock | Freight | Tahza Eggleton, Richard C. Ainsworth | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 12/18/25- coordinating with final centers to cancel existing agreements as Custodians are hired. All potential centers have been contacted, with 30% identified as good candidates for in house. 66% of these have issued cancellations to their national providers. Finalized custodial hours report and developed savings calculator. | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2025-05-01 | 2025-09-30
Business Only Initiative: Hostling Hours Planning |  | 130632 | Business Only Initiative | FXF - Dock | Freight | Christen Daniels | On Track | 3/5/26: Hostling Hours Planning Tool Cancellation Request Rationale: Roadblocks: Data oUnable to automate and load new data into the planning tool each week. oUnable to automate the function of submitting a daily plan Used VBA in Excel desktop, but Excel Online does not support VBA. Tried replacing VBA with Office Script and Power Automate without success. oUnable to save the daily plan directly to a database schema. Results in manual data pull for planned vs. actual reporting Data Accuracy oUnable to join the data table that contains corrected hostler-shift data. This data table comes from a procedure that is also used for the Dock Planning tool. It buckets hours into the correct shift for reliable shift planning. 13% of hostling moves are performed while punched to an incorrect department or shift. Incorrect shift-data results in an unreliable plan, because we are using historical data to estimate move counts per shift User Experience •Excel desktop: oNot available to frontline supervisors oMultiple users saving/submitting plans at the same time generates lag and risk of data loss and file corruption (online source, not tested) •Excel online: oMultiple users saving/submitting plans at the same time generates lags and risk of data loss and file corruption (online source, not tested) Hostling Hours Planning Tool Recommendation: •Develop a web application that mimics Dock Planning tool, hosted in the same place as Dock Planning tool oHostling moves logic is already developed oHostling roster logic is already developed oHostling shift logic is already developed oWeb mockup is available for the development team 3/5/26: Will close/cancel this initiative in Planview. Will be re-opened by FXF as a Business with Tech initiative in WAVE. 2/23/26: Reviewed roadblocks with Ops Research. Roadblocks still remain. Next steps: Document the road blocks in more detail, review with pod stakeholders, determine next steps for initiative. 2/4/26: Excel tool has been moved to a Sharepoint site using Excel Online. This has created the following roadblocks: 1. Automating the "Submit Plan" button to save the daily plan somewhere for back-end reporting and analysis of tool ROI. 2. Automating the data load into the tool 3. Generating a report that measure plan vs. actual - without saving the plan somewhere, we cannot create a plan vs. actual report I reached out to Ops Research for assistance and got a couple of names of folks that might be able to help. I will reach out and update status afterward. 1/23/26: Improvement requirement work still in progress. 1/12/26: Improvement requirement work is in progress. 1/5/26: Pilot at KCY is complete. Improvement requirements documented. Begin work on improvement requirements 1/12/2026. Planview milestone dates have been updated. 12/17/25: Pilot at KCY is complete. Improvement requirements documented. Begin work on improvement requirements 1/12/2026. Planview milestone dates have been updated. 12/10/25: Pilot at KCY is complete. Improvement requirements documented. Begin work on improvement requirements 1/12/2026. Planview milestone dates have been updated.. 12/3/25: Pilot continues at KCY service center 11/20/25: Meetings on 11/20/25 and 11/21/25 to intro/demo the tool for pilot. 11/13/25: Ready to begin pilot/UAT. 11/05/25: On track, no roadblocks. 10/30/25: Working on Milestones 9 & 10. Milestone 11 is complete. Initiative is on track with no roadblocks. 10/23/25: Working on Milestone #9. Initiative is on track with no roadblocks. 10/15/25: Working on Milestone #8. Initiative is on track with no roadblocks. 10/8/25: Working on Milestone #8. Initiative is on track with no roadblocks. 9/25/25: Working to clear up late milestones. We are still on track and have no roadblocks. 9/17/25: L3 Approved. Continue work on milestones. No roadblocks. 9/11 | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2025-08-21 | 2026-02-13
Business Only Initiative: Play It as It Lies |  | 110003 | Business Only Initiative | FXF - Fleet | Freight | Jaclyn Natoli | On Track | 2025-08-07: Darren P. said we can cancel this and use the data collected during the assessment to support improved decision making in the future. 2025-08-05: Solidified strategy and data needed to support optimal decision making for end of life cycle. Asked leadership to assess if this needs to be a Planview project still because quanitifying savings/ baseline would require us to evaluate and size the value from making a different decision last year and the juice does not seem worth the squeeze. Suggestion- work smarter in the future and use the data collected to drive educated decisions (look at yard capacity/ value of yard space, market/ vendor trends, etc.). | C: L1 | Cancelled | L1
Business Only Initiative: FXF Out of Service |  | 110323 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | Exploring value drivers and objectives of initiative as well as level of effort 6/17/25 - QA Review completed by Marty mills, approved to surge to L2 | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Tractor Utilization Compliance | 88160 | 7124 | Business Only Initiative | FXF - Fleet | Freight | Jaclyn Natoli, Gary Moses | Some Issues | 2026-01-19: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 2026-01-12: we had to cancel the subscription service a month ago due to some quality concerns. Sent a comms to share the issues/ concerns with the users so they are not left in the dark. We are testing the fixes in the sandbox version of the report. If it passes UAT this week, all actuals can be entered into Planview and we can push to prod. Update on some of the action items/ next steps: - Dheeban has now developer access to the ADF /notebooks and has a high level overview of the project. - Bid snapshot skipped 12/4 run due to triggers set to inactive during ADF auto deployment. I copied the 12/3 snapshot to 12/4 to fix the report. It used the latest state of LH_CO_BID table to check compliance since snapshot was absent. The report should update shortly once ADF run finishes. - The QRG is now visible on the prod report. Notes for me: CPM_norm data from Equip Lifecycle Mgmt. tool is used to quantify savings tied to 'sweating our assets'. This report is owned by DataWorks and I am calling that out as a POTENTIAL RISK (using all caps for the full effect). ITEMS BELOW ARE COMPLETE BUT FXF NEEDS TO TAKE OVER EQUIP LIFECYLE BEFORE THE SPIN-OFF (in my opinion). I say this because a backend job failed for a few days before I noticed and was able to connect with Saeid to resolve said issue. That impacted the downstream data availability in the Synapse App Schema we setup for FXF to access and use data from the Euip Lifecycle Mgmt report. If I was not pulling data to support actuals for Power Pooling, I would not have noticed NULL values for a handful of units (the indicator that triggered me to align with Saeid to diagnose and resolve the issue). Please note- this job failed last Tuesdays so it will not impact the reported actuals for August. Future back-end changes post push to prod- Redirect input from Equip Lifecycle Mgmt Business Group Schema to App Schema in Synapse that Raymond is working with FXF IT to create for Prod level Equip Lifecycle Mgmt report. Reassess logic tied to DML14 policy changes (drivers on extra-board with a tractor due to a cancelled bid). | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-10-01 | 2025-12-16
Business Only Initiative: Fleet Maint Employee Productivity | 81508 | 8381 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | Report launched to the field on 10/21. In follow up/tracking stage of the report. | K: L5 | Completed | L5 | 2024-07-16 | 2024-11-04
Business Only Initiative: Eliminate Container Preventative Maintenance |  | 87644 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | Moving through milestone requirements | K: L5 | Completed | L5 | 2024-11-20 | 2024-12-09
Business w/ Tech Initiative: Paperless PM & Standardization | 84812 | 7084 | Business w/ Tech Initiative | FXF - Fleet | Freight | Tricia Mulanax, Daniel Hockman | On Track | Re-evaluating this initiative as a an electronic checklist within the tablet and currently assessing MAS (Maximo) capability for being able to meet the criteria before we proceed further to understand if tech is still needed or not. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-11-01 | 2025-08-27
Business Only Initiative: Imperial Supplies SKU reduction |  | 108405 | Business Only Initiative | FXF - Fleet | Freight | Charlie Baker | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 12/12/25 - INC033395192 - this PDSM request is to update back to L5 active. I mistakenly submitted L5 to complete. INC03339519 12/10/25 - L4 checklist requirements completed. 8/6/25 - Completed all milestones, uploaded money step evidence, approved to submit to L4 via email. 7/28/25 - QA review performed by Kelli Ostertag/approved to surge to L3. 4/16/25 - Worked through L1 requirements. Align with stakeholders and set up meeting for week of 4/21/25. 4/17/25 - Stakeholders not available to meet until week of 4/28, so I will have a meeting with Laurie Oswalt on 4/22 to go through financials. 4/22/25 - Had meeting with Laurie and Marty. Discussed pulling spend for wiperblades, gloves, sorbent supplie and any other categories to figure baseline. 1st meeting with stakeholders is on 5/1 @ 14:00. 5/1/25 - Had first stakeholder meeting today at 1400. Dylan was absent. The team discussed the initiative and first category of wiperblades. 5/8/25 - 2nd stakeholder meeting with Richard H, Jim Williams and Marty M. Discussed gloves, wiper blades, first aid supplies and manager approval processes. We also talked about ladder purchases, shelving and part bins. 5/6/25 - Had meeting with Laurie O and discussed business case and finacials. Laurie recomends that I change the wording in the description to be more specific to the categories I am targeting to save in instead of the whole Imperial catalog of $5.7M. 5/20/25 - Submitted PDSM ticket to update savings margin from 20% to 15%. INC030741501 & INC030741276 5/30 All PDSM tickets have been worked and updates made. 6/2/25 - PDSM ticket INC03091324 has been submitted to update Key Assumptions in PlanView. 6/3/25 - QA Review completed by Marty Mills, approved to surge to L2. 6/18/25 - Reached out to Finance for alignment. 7/14/25- PDSM Ticket INC031456139 update baseline/NRB | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2025-06-19 | 2025-08-06
Business Only Initiative: Freight LAWN Care | 83492 | 8393 | Business Only Initiative | FXF - Fleet | Freight | Jeff McNair, Aaron Laging | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. Send communication to finance for updated lawn care spend for FY24. Put together survey questions. Getting an idea from the field on the appetite for bringing lawn care in house. 8/12 - validating impact and nrb. Surging for L2 8/15 - finalize requirements for L3 9/5- gain survey information through 9/11. Working with Brian Baker on equipment specs. Looking at aligning with sourcing, safety, L&D, and legal in the near future. 9/12 - captured and bucketed data from our survey. We have 80 centers interested in transitioning to in house lawn care Working with Brian on equipment specs and equipment purchasing. They are reaching out to current vendors to see if they sell the type of equipment we need. Meeting with safety, l&d, and legal 9/13 to give them the scope of the project and get an idea what they need from the team to move forward. 9/19 identify stakeholder requirements. Align with milestones to account for those. This week's focus will be finalizing equipment specifications. 9/26 aligned with HR compensation to create job descriptions and standardization. Equipment- fleet maintenance finalizing equipment specifications. 10/31 - Equipment specifications have been finalized. Aligning with Safety on job hazardous analysis on equipment and tasks. 11/7 - Currently working with Marv to align with safety on the job hazardous analysis on equipment. Marv commited to have us a plan by next meeting on 11/14. After this we will circle back with L&D and legal to work on education and job description. 11/14 - Marv provided overall Safety and OSHA guidelines. Will schedule a meeting with Darren Plumlee to review next steps. 11/21 - Darren reviewing documentation from Marv and will follow up. 12/10 - Aligned with Safety, Legal and Sr. Leadership; decision made to forgo Phase 2. Safety and Legal to tie off with centers currently performing in-house lawn care. Week of 12/16 - Entered L4, there will be no actuals to report from December through February. Actuals will resume March 2025. 2/13 - Email communication sent to the field informing them of the decision NOT to pursue this initiative. 4/3 - Actuals entered for March; will continue to track until 12 month milestone is reached. 5/8 - April actuals entered 5/8. 5/16 - Next step to enter May actuals and determine close out date. 6/2 - May actuals entered. Ready for L5 Surge. Approved to move to L5 6/5. 7/7 - June actuals entered. 8/5 - July actuals entered. 9/2 - August actuals entered. 10/8 - September actuals entered. 11/10 - October actuals entered. 12/10 - November actuals entered. 1/6 - No actuals to report for December 2025. | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-08-15 | 2025-03-31
Business Only Initiative: Freight Dock Doors |  | 87550 | Business Only Initiative | FXF - Fleet | Freight | Landon Harris, Bryan D. Raver | On Track | * 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. * Week of 11/18: Seeking L2 and L3. * Week of 11/25: Successfully surged to L2 and L3. Confirmed list of phase 1 locations. Developed method for spend tracking. * Week of 12/5: Communicated project with Facility Maintenance, Safety, Security, and Operations (Bo Garl). Beginning a test pilot of 4 locations (TPA, LIT, DAL, NOG) to last one week. Gathering information on potential Corporate policy changes. Also gathering information and feedback from security. Unforseen tasks will most likely delay L4 date of 12/16. * Week of 12/9: Completed test pilot and gathered feedback. Scheduled meeting with Security * Week of 12/6: Held meeting with Security to discuss overall project, sent list of locations for review. * Week of 1/6/25: Following up with Security on overall project. Validating if changes need to be made to governing policy/procedure. * Week of 1/13/25: Met with Bo Garl to discuss communication plan. He suggested we touch base with Laura Melton in Communications. Met with Laura, discussed the project and will begin drafting the communication to be sent to the field. Still awaiting feedback from Security. * Week of 1/20/25: Confirmed security is good with the overall project and has no concerns. Working with Laura Melton to develop the communication plan. Advised by Travis Allgeier to hold off on sending out communication on 1/24/25 until he meets with Bo Garl and Jeff First. * Week of 1/27/25: Communication was sent in WPS on 1/24, received concern from email and competing DRIVE initiative. The team worked with Bo Garl to develop clarifying communication that would allow both DRIVE initiatives to run simultaneously. New communication and launch date with be 1/31. * Week of 2/5/25: Additional communication was sent to the field on 1/31 with the launch of the initiative. Team will begin monitoring dock door usage and spend to report savings. * Week of 2/10/25: Project has been launched for one week. Overall spend by location has been set to RVPs to discuss with SCMs to drive awareness. * Week of 2/17/25: No change on the project. Acutals will be pulled in March to determine first month savings. Communication will continue with and RVPs * Week of 3/3/25: Actuals were pulled. A savings of ~$78k was reported comparing actuals from Feb 2025 to actuals of Feb 2024. Spend will be updated and sent to RVPs * Week of 3/10/25: Updated actual spend was sent to RVPs * Week of 4/7/25: Updated actual spend in Planview and sent updated YTD spend to RVPs * Week of 4/14/25: Worked with Laura Melton to draft communication for the field on phase II locations beginning the dock door initiative. * Week of 4/21/25: Communication was fully approved and scheduled to be sent out in the weekly pre-shift email on Friday 4/25/25 * Week of 4/28/25: Communication for phase 2 sent to field. Actuals will be updated the first week of May. * Week of 5/5/25: Actuals for April received and plugged into Planview. All up actuals will be sent to RVPs for review. * Week of 5/12/25: Actuals were sent to RVPs for reference. * Week of 5/26/25: Continuing to monitor dock door maintenance * Week of 6/2/25: Received actuals. Updated Planview financials. Sent updated spend to RVPs * Week of 7/7/25: Received actuals. Updated Planview financials. Sent updated spend to RVPs * Week of 8/4/25: Recieved actuals for the month of July. Updated Planview financials. Sent updated spend to RVPs * Week of 9/1//25: Received actuals for the month of August. Updated Planview financials. Sent updated spend to RVPs * Week of 10/6/25: Received actuals for the month of September. Updated Planview financia | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-11-18 | 2025-01-31
Business Only Initiative: Fuel Island Maintenance cost reduction |  | 108398 | Business Only Initiative | FXF - Fleet | Freight | Brian H. Baker | On Track | 3/31 - The actions are complete to close out the initiative. 3/31 - Accelerated schedule rollout 76.37% complete. 2/24 - rollout schedule started. SC district active. 11/6/25 - QA review performed by Kelli O. for SL3 - APPROVED. 10/24 - INC032806531 created. 10/20 - rec'd initial finance approval. re-aligning business case. will require PDSM tickets 10/1 - we have the parts supplier solidified. procurement is verifying the contract side to ensure Ryder will hold current pricing w/o handling the labor. Now we have to figure out ordering process for the shops..... getting w CB. this week i hope to have the internal Labor.... tied to the 8 months of invoices. 9/26-rec’d the Catlow hanging hardware info 9/8 - still revising business case to align w financials 9/4 - rec'd 8 months of Ryder invoices from procurement. 8/11 - re-defined KPI to reflect rollout %. Updated business case. 8/6 - built milestones and KPI's. Aligning w/ finance. gaining concent from stakeholders. 7/24 - inputs set up in Maximo test for review. not Active yet, awaiting meeting w/ Heather and Tina to see how these will look in ACCOPS. meeting set for 2nd week of Aug. 7/8 - Maximo asset inputs discussions and alignment w/ SME's. 6/24 - finance meeting 6/17 - milestone alignment. 6/10/25 – QA Review completed by Marty Mills, approved to surge to L2. Surge has been scheduled for this Thursday, 6/12/25. 6/9 - Updated Business Case. INC030999407 Created to correct primary type of value and money step. 5/30 - Finance review -completed. placed PDSM ticket to correct the one-time benefit. 5/29 - INC030873862 Created to correct the previous ticket, worked incorrectly. 5/19 - updated demand description and placed PDSM ticket to update expected business outcome verbiage. 5/15 - aligned with finance. submitted PDSM ticket to correct basline value to 7M. 5/5 - CORE Team meeting. JH - getting parts pricing. 4/22 - discussion around if we need to assign FI's asset numbers/location specific and if we have the ability to do so within Maximo. AT/BB/GB/CF 4/19 - This is something that we can talk about. Currently, I do a lot of this myself. But I am not sure we would want 300+ people having access to these as you can very easily make them unusable with a few wrong clicks. Maybe a team of folks? Idk. There should be more investigating than simply unblocking a pump in a lot of cases which is one reason I would like Ryder not to have access to these. If they aren’t getting a pulser signal or if they are authorizing and not getting fuel, but Ryder just unblocks every time someone calls in, then we never know there’s a larger issue. This is something I want to make better and to improve the uptime of the island, not just unblock to complete a phone call. To support fuel, I currently manage •275 Card Readers at 219 bulk fuel locations •28 Servers •229 ATG’s ( VeederRoots) •EFS relationship (card provider) •Firewall rules with vendors and from our card readers to the Data Center •Spare parts (which I think we should expand on) There is a lot of technology outside of the dispensers. Then we have the compliance piece that Brenden manages. Fuel is a big animal. It’s not going to be as simple as removing Ryder and adding in 7-8 contracts. But in the end, this project should save us money and get us much better results. Thanks, Justin Hudson ¦ Sr. Procurement Specialist 4/18 -Would the remote into the card readers be something that we could have access to? Mainly for doing resets when card readers are not working. 4/18 -Has initial discussion been use the 8-10 vendors for managing everything direct from the respective locations or is the plan to have internal resources as a switchboard dispatching to the 8-10 vendors? 4/18 - Before I forget to bring it up later, we need to find out who monitors our Veeder Roots ( is that Ryder? ) for the islands today and see who else can if we make a change. Also, it would be very helpful for each locatio | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2025-06-24 | 2026-03-31
Business Only Initiative: Biodiesel Tax Savings | 48914 | 8437 | Business Only Initiative | FXF - Fleet | Freight | Joe Carlson, Aditi Khanna | On Track | 04.18.2025 Forecast zeroed out, as this project and it's savings moved to Seq ID 8077. The FXF Locations associated with this project is no longer being managed by 3rd party distributors. The savings are already being captured under #8077. To avoid double counting, the forecast has been removed, and no further savings will be reported under this iniatitive. This is not a loss in savings, as the savings are moving to another project. | K: L5 | Completed | L5 - Restarted Initiative | 2023-11-14 | 2024-08-16
Business Only Initiative: Tires - Specification optimization - Cross opCo lo | 55137 | 7209 | Business Only Initiative | FXF - Fleet | Freight | Robin Lyon, Joe Felan | On Track | 8/5/24 - submitted for L3 approval. Reduced pricing was implemented June 1, 2024. | K: L5 | Completed | L5 | 2023-09-26 | 2025-01-31
Business Only Initiative: Predictive Cruise Control |  | 87641 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. MPG improvements starting to shape up | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-11-29 | 2024-12-06
Business Only Initiative: Fleet Maint Vendor Dashboard | 81507 | 9423 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax, Brian Gage | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. Report has been modified and relaunched to the field and to transportation for use. Tracking benefits from reduced vendor use in the targeted areas. | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-10-15 | 2025-08-06
Business Only Initiative: [Enabler] Equipment Needs Model | 26141 | 9554 | Business Only Initiative | FXF - Fleet | Freight | Jacob Maher, Jaclyn Natoli | On Track | We have been asked to include FXC equipment information which may slow down some model progression and possibly delay timelines ingesting the new data. FEND launched 10/24, we will continue to gather feedback and integrate improvements as we include more and more models into the dashboard. Continuing to gather feedback and address potential issues within FEND. Final Model was added and rolled out 1/31/24 marking the official full scale launch. 2/26- Hostlers have been removed from this initiative 3/11- Moving our inventory source off of the daily equipment snapshot to directly tie into the maximo table, since that is what we are already using for the state of the fleet model as well as our manual validations. 3/18- Still looking to move the inventory sources. Our devs have been in and out of the office delaying time to complete 3/25- Changed inventory on Dolly model 4/1- Making maintenance changes and a few UI arrangement changes 4/8- Preparing for the 4/19 Needs usage for FEs 4/15- Preparing for the 4/19 Needs usage for FEs, Added Executive summary to FEND | K: L5 | Completed | L5 | 2023-04-10 | 2024-01-16
Business Only Initiative: [Enabler] Fleet Mtnc - People Service Profit | 26142 | 9556 | Business Only Initiative | FXF - Fleet | Freight | Gary Moses, Nicole Brown | On Track | 12/18: PSP Goaling discussion w/Matt concluded that a working / focus session is needed with Tomm Brennen, Ali and Tricia to iron out the recommended key measurement factors in each reporting area (Safety, Equipment and Performance drivers; generate a number and denominator). Hours (Actual vs. Expected by category) will likely be a predominate factor of measure along with equipment pool for equipment. Focus areas will be: 1) Uptime 2) OOS Hours 3) Dwell time per equipment and 4) Over / Under Hours (where the appropriate percentile is unknown - 60, 75 or 80 1/3/24: Tricia M. is working with Curt on making sure there is data alignment & accuracy from the PSP push report. Right now, it's not correct so until then she and Curt will be working the metrics 2 at time in the PSP weblink. No demo until then; still awaiting Curt's response on a timeline. 1/8: PSP landing page development touchpoint will resume on 1/11; will seek guidance from Curt on data validation and server access. Gary will look at communications / QRG from push report and assure it will be translated properly to landing. 1/15: PSP landing page still under development. Milestone for completion has been changed from Feb 1 to Feb 8 allowing additional time for validation. Curt has identified that a risk remains on timing of data releases to populate dashboard (Maximo DB2) and Synapse; need to assure timing is consistent. 1/18: Curt inquired about setting arbitrary acceptable range on landing page of +-3% as starting point until enough data if captured to move to new range. Company range is tighter. Spare pool O/U only goes back 3 weeks; no previous quarter or year data points available. 1/22: Re Goaling: Tomm Brennan advised that we should create checklist to establish approach for "next steps" once goaling calculations are complete 1/29: Team has requested demo and uploading of goals to landing page by Curt. Review and discussion with FM Leadership to follow on the accuracy & relationship of value (weight). Input will be need by stakeholders 2/5: Team will need to confirm with Tomm on how calculations should be directed to SD 2/9: Team discussed how goals will be populated into the PSP Landing Page. Curt provided a format to Tomm/Ali to begin adding the metric logic into so that he can upload to page. He stated that it would take him 1-2 days to complete uploads once data (goals) are received. Based on Curt's suggestion, team agreed to move forward with initially populating page goals and updating them once enough data is collected over time to determine acceptable targets. 2/13; Initial goals and range preferences have been provided by Ali in the preferred format suggested by Curt. Team inquire when goals will be populated in the dashboard; a scheduling for user demo & rollout plan will follow. 2/19: Demo of landing page for FM Leadership is scheduled for Friday February 23. Goal of demo is to assess overall content and layout and provide feedback prior to full production rollout by March 9. 3/8: Darren and FM leadership team will review OOS hours and O/U Spare Pool logic during the week of 3/11. For the O/U spare pool, there immediate concern if goal should be cascaded down to the local level; create a minimum and maximum allowance band versus a zero target goal. If so, Curt will need new O/U spare pool logic and ample time to execute changes prior to the March 20 production rollout deadline. Also, FM leadership is suggesting that the team investigate the ability of obtaining O/U unit updates by location (best time as a standard). The challenge is there are different start-up times by location so a standard update time must be established so metrics can update properly. 3/14: Systems Development team (Curt) has removed the OOS hours metric from the dashboard. His remaining task is to add the O/U spares logic (over = red, under = green). He will need until the middle of next week to make changes and update/test the server. Tric | K: L5 | Completed | L5 | 2023-06-13 | 2024-04-30
Business Only Initiative: [Enabler]FXF Advanced Clean Fleet Approach | 28507 | 8056 | Business Only Initiative | FXF - Fleet | Freight | Jacob Maher, Thomas Griffin | On Track | Continuing to record KPIs as the list of units have been registered. Working on the spin off initiative to get some reporting and IT systems to accompany this list. 3/18- No update, the units have all been registered. 3/25- No update, the units have all been registered. 4/1- No update, the units have all been registered. | K: L5 | Completed | L5 | 2023-10-19 | 2023-12-29
Business Only Initiative: Equipment Lifecycle mgmt | 26144 | 9559 | Business Only Initiative | FXF - Fleet | Freight | Jaclyn Natoli, Jacob Maher | On Track | 2025-06-24: Equip. Lifeycle Mgmt tasks and timelines from Saeid: Remove temp from CPM_normmodel 6/25/2025 Finalize normalized CPM table schema in Synapse7/2/2025 Productionizing the report7/31/2025 (Jaclyn to work with stakeholders to determine a home since it will not go on the FXF Reporting Hub) Entered in May actuals. To support CPM_norm needs for the Dispatch Complaice report- Interim- have data available for Nithish to use via Business Group Schema to enable Tractor Utilization Compliance initiative (Dispatch Compliance report) to meet L4/ $ step date of 5/31. Long-term goal- Push Equipment Lifecycle Management - TEST - Power BI was to push to Prod and create an App Schema in Synapse to expose Equip Lifecycle data. Weekly pulse-check to start next week. Cassandra's response/ the latest update on the Motive fixes: Odometer Jumps in Motive - MDB Enhancements have been finalized to reduce these moving forward, implementation ~Apr 28 Backfill ETA ~End of April Missing Drive Time/Mileage in Motive - MDB Long term is the same ~End of May to fix and backfill all historical data Short term Script has been created and going through approvals now to resolve all instances by end of week. (March '25 to current) Fuel consumption – MDB 27 tractors identified with issue –repairs are underway by FXF Techs - 14 now completed as of 4/3. Next update will be 4/11. 'Solution' notes- - No existing structure according to Barry (we are the first doing this) - IT said that we can experiment with calling the API that will be replacing PeopleNet in the future. Tested in dev and it worked so we expect it will work in Prod. - Goal is to move Equipment Lifecycle process to Prod and utilize Motive data from API. - Temperature is not available in Motive to support CPM_norm but we are testing the impact of removing it from the prediction model. Will compare with and without temperature. Other factors, such as odometer reading, speed, shipment weight and avg. elevation, are available. - Validate data accuracy of info coming from Motive (compare dispatch miles from dispatch tables to Motive miles) - Saeid will be combining data sources (Motive and PeopleNet) and will validate that there is no overlap or duplicate data for 52 week rolling average/ aggregated data displayed in the Equipment Lifecycle Mgmt report. 1) Pull 6 months of odometer and fuel readings using Motive API [1/8-1/17] Note- API was too slow so we are going to use the data bridge. As of 1/16, Saeid pulled all the data and saved in Azure DataBricks. 2) Validate Motive data using dispatch miles [1/20-1/21] Note- data validation began on 1/17. [1/17-1/20] 3) Combine Ppnet and Motive data to get all history of traveled miles and fuel consumption over 1 last year and update lifecycle dash [1/22-1/23] now [1/21-1/22] *DATA DID NOT PASS VALIDATION AND ALL SUBSEQUENT WORK IS DELAYED* 4) Validate CPM_norm without temp (temp not available in Motive) 5) Production level report and data not encompassed in steps 1-3. Productionizing will take approx. 2 weeks and is dependent on data validation and ease of pushing the jobs to Prod. Note- Nithish to use placeholder Synapse Prod table to mitigate delays to rollout Dispatch Compliance report and also support Saeid pushing to Prod as needed. Side note- after work mentioned above is complete, FXF needs to investigate storing data locally to minimize API traffic and cost. Follow-up with Jason H. on this ask as the data is centric to FXF (Jamie O. mentioned he will ask). | K: L5 | Completed | L5 | 2023-06-05 | 2024-04-30
Business Only Initiative: Facility Capacity Utilization Tooling | 26263 | 6697 | Business Only Initiative | FXF - Fleet | Freight | Landon Harris, Shane Turner | On Track | Week of 10/07: Continuing to use tool and roll out to internal users as needed. Week of 10/14: Continuing to use tool and roll out to internal users as needed. Week of 10/21: Continuing to use tool and roll out to internal users as needed. Made update to coding that pulled Hub Schedules on parking data Week of 10/28: Continuing to use tool and roll out to internal users as needed. Week of 11/04: Continuing to use tool and roll out to internal users as needed. Week of 11/11: Continuing to use tool and roll out to internal users as needed. Week of 11/18: Continuing to use tool and roll out to internal users as needed. Week of 11/25: Continuing to use tool and roll out to internal users as needed. Week of 12/2: Continuing to use tool and roll out to internal users as needed. Week of 12/9: Continuing to use tool and roll out to internal users as needed. Week of 12/16: Continuing to use tool and roll out to internal users as needed. Week of 1/6/25: Continuing to use tool and roll out to internal users as needed. Week of 1/13/25: Continuing to use tool and roll out to internal users as needed. Week of 1/20/25: Continuing to use tool and roll out to internal users as needed. Week of 1/27/25: Continuing to use tool and roll out to internal users as needed. Week of 1/3/25: Continuing to use tool and roll out to internal users as needed. Week of 1/10/25: Continuing to use tool and roll out to internal users as needed. Week of 1/17/25: Continuing to use tool and roll out to internal users as needed. Week of 1/31/25: Continuing to use tool and roll out to internal users as needed. Week of 2/7/25: Continuing to use tool and roll out to internal users as needed. Week of 2/14/25: Continuing to use tool and roll out to internal users as needed. Week of 2/21/25: Continuing to use tool and roll out to internal users as needed. Week of 2/28/25: Continuing to use tool and roll out to internal users as needed. Week of 3/7/25: Continuing to use tool and roll out to internal users as needed. Week of 3/14/25: Continuing to use tool and roll out to internal users as needed. Week of 3/21/25: Continuing to use tool and roll out to internal users as needed. Week of 3/28/25: Continuing to use tool and roll out to internal users as needed. Week of 4/4/25: Continuing to use tool and roll out to internal users as needed. Week of 4/11/25: Continuing to use tool and roll out to internal users as needed. Week of 4/18/25: Continuing to use tool and roll out to internal users as needed. Week of 4/25/25: Continuing to use tool and roll out to internal users as needed. Week of 5/2/25: Continuing to use tool and roll out to internal users as needed. Week of 5/9/25: Continuing to use tool and roll out to internal users as needed. Week of 5/16/25: Continuing to use tool and roll out to internal users as needed. Week of 5/30/25: Continuing to use tool and roll out to internal users as needed. | K: L5 | Completed | L5 | 2024-04-02 | 2024-09-09
Business Only Initiative: Fleet Mtnc - Staffing | 26140 | 9552 | Business Only Initiative | FXF - Fleet | Freight | Gary Moses, Nicole Brown | On Track | 1/3/24: Laurie O. stated that she is finishing up compiling the direct labor hours provided in Kronos (internal hours captured in ledger) of technicians along with validating invoice entries in Maximo of outside service vendors. There are known discrepancies in Maximo so those are errors are being resolved. Entries in Wave are due on January 19th. 1/10: During the FM Staffing Weekly Touchpoint, the team reviewed new logic provided by Finance on measuring the external hours shift YOY. The following changes are the result of not meeting the required shift from external to internal hours to achieve the $5.6M savings. Therefore, Fleet leadership recommended: 1) Find an additional approach to track costs and headcount by locations and aggregate internal vs. external cost to achieve 90 /10 split. •Focus on 90 / 10 internal to external cost ratio as the primary deliverable 2) Develop an effective way to provide visibility (dashboard/report) which can be used to at the center levels to drive changes to cost structures and/or headcount. •Monitor staffing to see if there is any correlation between headcount and external hours shifting internal These recommendations will focus on evaluating this initiative on the 90/10 spend mix instead of the 97.2/2.8 split in internal vs external hours. In addition to that we will be looking at activity at each shop to determine what changes are required at each level. McKinsey will provide direction on if we should revert back to L2 during the week. 1/18 Follow up: Ability to compare the internal hours for that location to those external invoices for a time period, every two weeks if possible. Objective is to understand what shops or non-shop locations with techs domiciled that drive the external labor being higher so we know where we either need to hire internally or force the work to internal vs. external. And then see how we drive that number over time. 1/25: Project Impacts, KPIs and Baselines were reviewed by team including McKinsey. Team decided to add internal / external expense as base KPI and adjust impacts and KPIs to include ramp up. Awaiting new methodology from Finance to capture internal / external expense at network cascaded down to the same measurement at shop level. 1/31: Finance worked through methodology in capturing shop expenses (internal / external) & staffing impacts at all levels. Their team meeting to go over data was held on Wednesday. They are now ready to review and walk team through the aspects of the model. 2/6: New financial impact approach presented to Sr. Management. Darren requested that a deeper dive is still needed to uncover what does being fully staffed look like in terms of internal / external expense mix, bottom up (location, district, region, network). Team has been tasked to find out if 90 / 10 ratio is the correct target expense mix. 2/19: Actual savings for January submitted in Impacts and KPIs tabs. Savings (avoidance) monthly projections/forecasts for remaining FY24 and throughout FY25 have been determined. 3/7: **Wave updates are complete. 2 KPIs removed and one added. Actuals and forecasts have been adjusted. -#31062: Maintenance Cost Per Mile - Removed -#33823: % of External Hours to Total Hours - Removed -#73826: Internal Spend - Added** 3/13: Takeaway from FM Weekly Staffing Update: **In FY25, a campaign to retro fit tractors with blind spot technology will be handled by vendors. Team will need to separate & track its impacts (costs, hours) from the internal/external spend we are tracking in the staffing initiative. We will list as risk to current project.** 5/1: Met with Finance partner (Laurie O.) to discuss approach to capture Bendix Blind Spotter technology expenses in FY25. A couple of items will need to be confirmed prior to planning. 1.Is this project considered capital or expense? Or a combination of both? If a combination of each, then what items will be expensed? 2.Is this campaign part of the F | K: L5 | Completed | L5 | 2023-07-11 | 2023-12-22
Business Only Initiative: Fleet Mtnc Workflow | 26143 | 9558 | Business Only Initiative | FXF - Fleet | Freight | Gary Moses, Kelsey Grape | On Track | 10/18: Analysis on shops that can accommodate the mechanic position have been identified & narrowed down to 3 shift hub locations (68). -Trailing equipment PM data has been added to the analysis to further evaluate mechanic position to cover work. Not all locations are complete with trailing workload evals as of 10/18 but anticipate finalizing by Friday 10/20. - COMPLETE 10/19 -Percentage of work that can be covered by a mechanic and its associated headcount will drive calculations in acquiring cost savings between technician and mechanic positions -Finance will review analysis prior to L2 submission scheduled for November 3rd -Team will continue to discuss approach on development of shift assignment tools that will dictate allocation of labor for both skill sets (technician vs mechanic) -Determine how many positions (mechanic) can be filled before the end of FY24; working session scheduled for 10/25 10/26: Finalized FY24 and FY25 headcounts for mechanic position fills as 44 and 47, respectively. Finance team partners will prepare a business case summary based on those headcounts. After review of the business case, the project will be on target for L2 submission on November 3rd. 11/9: Project successfully moved to L2 on 11/2. Team will conduct a brainstorming session on 11/16 aiming to leverage data from Maximo to structure and deploy resources (incorporation of Shop Utility Technician). Emphasis will be placed on building process flow & decision tree. Team will also begin working through L3 requirements. 11/16: Billy Fox and Bob Baumgardner presented the SIPOC and first iteration of the process flow during working session. More direction is needed from leadership on decision tree to standardized assignment of work to Shop Utility Technicians (SUTs) across shops. Automation portion of project should be placed into another initiative; current project will require manual assessments and assignments of work to SUTs. A discussion is scheduled for advisement on Monday November 20. 11/17: FM leadership provided direction on steps (milestone added) to standardize ork across the the shops. It was decided that the use of technology to optimize work is still undetermined and should be captured in another initiative. 11/20: Team decided to change milestone #64126 "Post SUT positions for all opportunity locations" type from "Implementation" to "Money Step". Milestone #29931 was shifted to new initiative for automation, #64244 "FM - Work Order Processing". Milestone #57654 was deleted. 11/22: Monthly benefits generated via Finance for 44 SUTs added for remainder of FY24 (Jan 2024 through May 2024). L3 surge scheduled for 11/29. 11/29: L3 Surge updates include 1. Completion of baseline KPIs 2. Addition of a Money Step milestone for hiring SUTs and 3. Revision of financials in Impacts section to reflect MOM aggregate labor savings as SUTs are added throughout FY24 and FY25. 11/30: Shop Utility Technician baseline is 3 (based on current headcount from the locations: CGT, DSM and OKC) 12/7: Per Joe Felan - "We're currently working on two milestones with 12/31 deadlines; both of which are being worked on by Tricia/Chris. I brought up the decision tree and Tricia stated (she was right) that milestone has been moved to the development initiative. Right now she's getting the work accomplishment codes for the SUT role for the QRG." 1/11/24: Hiring of SUTs continues throughout the network. No issues. 2/14/24; A net hiring of 6 SUTs is complete. No issues. 2/19: Actual savings for January submitted in Impacts and KPIs tabs. Wage savings for 6 SUTs onboarded in January was approximately $16,910. Initial projections were modified slightly due to the SUT rate increase; values were realigned with FT instead of PT wage rates. 2/19: January FY24 wage savings was updated by Finance to $13,939. The decrease in savings is driven by the increase in starting wage for SUT to align with Dock FT instead of Dock PT. 7/10/24 Submi | K: L5 | Completed | L5 | 2023-06-16 | 2024-05-31
Business Only Initiative: FM - Work Order Processing | 64244 | 7118 | Business Only Initiative | FXF - Fleet | Freight | Gary Moses, Kelsey Grape | On Track | 5/9: Creation of job plans continues where alignment on specified job reason codes is completed & variance report template development is underway. PMA scans will only take place on domiciled revenue-generating equipment per select location for data acquisition. 5/16: PMA Job plans are uploaded in Maximo; accuracy of plans has been verified per Billy Fox. Next step is to activate job plans to associate with job scans per work order. Use of reason code 11 for follow-ups in a work order (a.k.a. "child work order") will need to be added to pre-shift communique along with discontinuation of reason code 08 assignment for the same supplemental work. Data sets will soon occupy Maximo and variance report will begin once job plans activations and communiques are complete. Other: Extended milestone #69196 due date to June 22 from May 18 (Chris Weng). 5/23: Dolly PMs and PUP PMs - Joe Felan identified an issue in separating the PM flag intervals (Note: Dolly and PUP PMs have a 180-day service level interval; not assigned by asset number. There is only a 2-3 min difference in time to complete PMs). These two assets are currently attached to master job plans. There are a couple of options. Suggestions were made: 1) To create separate work accomplishment codes for both Dollies and PUPs.(?) A drop-down to select which type of equipment was being serviced would be required, however a learning curve risk would be added as operators would need to understand how to distinguish between both codes/equipment types. ---OR--- 2) To create a new master PM for Dollies and PUPs with 180-day intervals. Remove PMs from master job plans so that times can be accounted for uniquely. Result: Suggestion #2 received unanimous approval therefore work will begin to create master job plans in Maximo for both Dollies and PUPs. 6/18: A demo of the Maximo environment for job plan assignments was conducted by Billy Fox for selected team members. Test level job plans for 36K mileage PMAs are being entered in Maximo system. Chris is awaiting feedback from Joe on proceeding to condense PMAs for Road, City and Box trucks. Each unit's SRTs for 36K mile/180-day PMAs varies within minutes. 6/20: Discussions continue on how Dolly and PUP PM accomplishment codes (AD and AP) will be separated; by asset type and then by lead time? Possibility remains on changing lead times on certain assets PMs to better align with other equipment PM cycles. Some lead times are set at 30 days while others are at 20 days. Chris will schedule a call with a select audience of FM leaders to iron out direction. 6/25: Per Chris Weng - Fleet Maintenance leadership is conducting field testing on job plans and validating; ensuring solutions are attainable/sustainable. Spoke with leadership to align on major reason codes. 7/16: Category Team decided that this initiative focus will be related to employee productivity and will remain as an enabler. 7/18 From call: * Testing complete * Need to take gathered results and understand on how we should move forward * Focus project on concentrate on data and efficiencies in the shops * Stalled; need to engage IBM going forward on data solutioning on how to measure SRTs; to mass assign job plans without impacting PMs * Need consistent scanning * Need to focus on data consistencies, proper PM on work orders and follow up IBM: TBD on when they will provide direction Short term next steps: Evaluating any implementation of job plans based on testing results 7/23: Fleet Maintenance is evaluating data inconsistencies in scanning; errors due to assignment of PM reason/labor codes within job plans that is captured though work orders. Next step is to understand how to resolve scanning and assignment inconsistencies to help establish a future standard or baseline that will measure productivity and efficiency improvements. 9/24: Reason code training releases on hold due to Productivity Tool delay. Current | K: L5 | Completed | L5 | 2024-04-09 | 2024-10-31
Business Only Initiative: FM Error Invoice Queue | 42165 | 7136 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax, Joe Felan | On Track | Tool is launched to the field and they have received education. Currently 163 in queue with only 1 over 10 days old. No value for money banked to progress to the L5 stage. Feedback has been positive with much easier management by the administrative support rep as well as by the Parts Coordinators and FMMs. Additionally, work on the part of the Administrators as third parties to manage has been removed as the invoices are now handled directly between the centralized support rep and the field. | K: L5 | Completed | L5 | 2023-09-26 | 2024-01-12
Business Only Initiative: Fuel Optimization | 26145 | 8379 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | Fuel island maintenance and holidays have impacted plan performance | K: L5 | Completed | L5 | 2023-07-03 | 2023-11-30
Business Only Initiative: FXF + FXG + FXE Equip Specification Alignment | 28831 | 6746 | Business Only Initiative | FXF - Fleet | Freight | Tina Reding, Jacob Maher | On Track | 5-16-23 Kick-off meeting held and scope of project communicated 5-23-23 Call to discuss next steps. Plan is to break-up into teams in order to move project along 6-2-23 Teams assigned to spec categories 6-9-23 Hostler spec review 6-15-23 Continue hostler spec review 6-20-23 53' trailer review 6-26-23 conclude hostler spec review 6-28-23 Single axle road tractor review 6-29-23 Continue 53' trailer conversation 7-12-23 Single axle road tractor wrap-up 7-25-23 53' trailer wrap-up 8-4-23 straight truck (power) spec review 8-14-23 decision was made not to compare forklift specs as they are used in different capacities 8-24-23 Surge session for L2 9-7-23 28' Pup discussion 9-12-23 Continuation of 28' pup discussion 9-19-23 28' discussion 9-29-23 Continue 28' discussion 10-10-23 Complete 28' discussion and begin dolly overview 10-11-23 box spec overview for straight trucks 10-24-23 dolly spec review 11-1-23 liftgate trailer spec review | K: L5 | Completed | L5 | 2023-06-09 | 2023-11-30
Business Only Initiative: FY24 Zone 3 Fuel Winterization | 32222 | 6901 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax, Chris Weng | On Track | Finance to review value and advise on readiness for L3. We have decided to make this initiative specific to Zone 3 only. Initiative 46199 will address Zone 1 and 2 including the 4 site pilot testing as well as other low-risk sites for FY24 implementation and savings. | K: L5 | Completed | L5 | 2023-08-01 | 2024-03-01
Business Only Initiative: Integrate Custom Critical Equipment into FXF Maxim | 97064 | 7367 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax, Joe Felan | On Track | Only 30 PMs completed in January overall, 8 of which were performed by FXF | K: L5 | Completed | L5 | 2024-10-01 | 2025-01-31
Business Only Initiative: Non-Domiciled Equipment Plan | 32676 | 8380 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | Power BI report has been created but needs work to be usable by the field. Canceled the IT portion of this request and IT required milestones. Juice no longer worth the squeeze with the progress they have made through manual processes. | K: L5 | Completed | L5 | 2023-08-15 | 2024-04-19
Business Only Initiative: Reduce FXF Fuel Demand | 56458 | 7221 | Business Only Initiative | FXF - Fleet | Freight | Kevin Waldon, Ray Walsh | On Track | 1/29 - Requesting to surge to L5 | K: L5 | Completed | L5 | 2024-03-22 | 2025-01-31
Business Only Initiative: Reduce Trailing PM Frequency |  | 87647 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax | On Track | Doing some further investigating prior to making the changes on the PMs to ensure things stay in good repair. | K: L5 | Completed | L5 | 2024-11-20 | 2025-01-17
Business Only Initiative: Surface Bulk Fuel Zone 1 and 2 Winterization Initi | 46199 | 6975 | Business Only Initiative | FXF - Fleet | Freight | Tricia Mulanax, Chris Weng | On Track | Added cost of additization, lower overall volumes and suppliers continuing to supply #1 when not prescripted are factors resulting in no gains. | K: L5 | Completed | L5 | 2023-10-02 | 2025-04-01
Business Only Initiative: Trailing Equip Pool Mgmt | 28799 | 6743 | Business Only Initiative | FXF - Fleet | Freight | Jaclyn Natoli, Jacob Maher | On Track | 2025-05-13: entered April actuals and submitted to L5 (have 12months of actuals to prove value). | K: L5 | Completed | L5 | 2023-10-03 | 2024-06-21
Business Only Initiative: Vehicle parts supplier negotiation | 3146 | 9000 | Business Only Initiative | FXF - Fleet | Freight | Yunus Saiyed, Rahul Bajaj, Kyle Mitchell, Josh Thorn | On Track | Savings have been tracked for the whole FY25 | K: L5 | Completed | L5 | 2023-06-09 | 2024-07-01
Business w/ Tech Initiative: Asset Tracking RFI |  | 148193 | Business w/ Tech Initiative | FXF - Fleet | Freight | Korey Ranson | On Track | 2025-12-08: Reviewed RFP Scoring and Vendor Selection: Motive, Xirgo, Spireon, Philips Connect. Aliging with FM on installation timeline projected mid-Jan. Location KCY SC 2025-15-08: Held separate calls with each vendor to align on expectations and gather the detailed installation instructions, required documentation, and estimated timeframes needed to support Fleet Maintenance during the evaluation installs. The goal is to review these details and address any concerns ahead of the KCY vendor installations planned for the week of Jan 12. 2026-22-01: Placing on hold in planview when Fedex Freight creates technology demand flow , will make this active in Wave. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: [Enabler] Base/Variable Forecast | 26146 | 6674 | Business Only Initiative | FXF - LH | Freight | Raymond Igharas, Elena Chas | On Track | 10/7/2025 * Process completed back in May 2025. * Awaiting to move process from Dataworks's OIP platform to FXF Azure platform. 7/30 * OR team is running the forecasting process in Azure and SAS this week, after Finance published the GUESS forecast numbers last week. Both SAS and Azure are experiencing run-time/network issues today (Tuesday 7/30). Once these issues are resolved, the processes will complete. 7/16 * OR team has successfully tested the connection and modifying the Syanpse Prod tables from OIP. * Have populated on PROD table (CFD_DAILY_FINAL) with forecasts from 5/2024 to 12/2025. * PROD tables are ready for the Forecasting process to execute at the end of the month. Meanwhile, the team will populate the PROD tables with history now. 7/9 * Imran is working to create the internal datasets on Azure to be used for the monthly and daily Forecasting process on Azure. Targeting July 12 for completion. * Updates Forecasting App Synapse Schema in FXF, where the forecasts will be published and available for FXF internal customers * IMAGE role for access became available today. * Requests for the Forecasting team members have the new IMAGE role submitted today. It may take a day or two day for the system to implement the access to the table. * App Synapse Schema has been established last week. * Currently working with Dataworks to have a Service Principal to publish the forecasts from OIP to the Forecasting App schema in FXF environment. * Once accessible to OIP, the team needs to test the connection and write the forecasts out to the Forecasting tables in FXF environment. * Two milestones remaining. As of now, on track to complete by end of week. 6/25 * Project is on track. * Issues for for POC Dashboard pulling from forecast data from storage location has been resolved. POC Dashboard on-track. * The forecasting process for the monthly IB/OB/Hub and the daily OD has been moved, tested and validated on OIP. Imran will work on generating the output files for our FXF internal customers and the ongoing history datasets. * The forecasting process for the daily IB/OB/Hub is currently being tested and validated on OIP. We are expecting to complete this task by end of next week. * The work for forecasting Oversized shipments will be deferred until all other milestones for this project has been completed. * Imran has completed the code, but validation of this new process will take some time. * Since the output for this process is needed once a year and Vijoe can still use his current process, the delay of this work will not impact anything. * Work on this will resume after all the other tasks are done. * FIRST approved. * Data Modeling is completed. Waiting for IT to setup the Application Synapse tables to host Final Forecast. * Business Group Schema in Synapse has been setup, which is needed to share data between forecast process and reporting. 6/4 Update * Dashboard POC is underway * Incorporation of GUESS to ADW for IB, OB, and Hub is completed. * Currently, moving daily OD level forecasting to Dedicated Workspace in OIP, as well as incorporating GUESS. * FIRST for BV Forecasting * Needed to store Final Forecast in Application Synapse tables * Submitted last week and currently in SME review. * Work on moving Daily forecasting and reporting to Prod will start this week * Expecting approval for team members to access Synapse Business Group Schema in Synapse any day. * Schema needed to share data between forecast process and reporting. * IT's data modeling for Application Synapse tables to host Final Forecast expected to complete this week. 5/29 Update * Milestone for POC Dashboard on Monthly Forecast targeted for 6/15. * Work on incorporating GUESS updates on weight will complete by 6/3. * Request for FXF Synapse tables to hold Forecasts are being processed by IT. | K: L5 | Completed | L5 | 2023-06-01 | 2024-07-12
Business Only Initiative: (Enabler) Closeout Tool | 26233 | 6688 | Business Only Initiative | FXF - LH | Freight | Lauren Cole, Jeff Blythe | On Track | AM Closeout (Operations) - 11/14 SOWE and NOWE Roll-Out | K: L5 | Completed | L5 | 2023-08-08 | 2023-12-12
Business Only Initiative: Improved FXF Drayage Dashboard | 86452 | 6701 | Business Only Initiative | FXF - LH | Freight | Kinn Kinney | On Track | 4/7/2025 Working with Jason Honeycutt for resources. Have reached out to Operations Research to get an estimate of work needed, conservative estimate is 1-2 weeks. Discussion with Brandon to see if we need to reach out to Raymond for priortization. 3/24/2025 No update, awaiting responses for resources. 3/10/2025 No update, awaiting responses. System Development may be able to develop. Narrowed down metrics. Determining if we will get resources. 3/3/2025 Pursuing both paths to move forward with internal resources and DW Demand Shaping. Have trimmed the request for metrics down and turned over to Jason Honeycutt and team for review. Awaiting response. 2/24/2025 Further discussion with Jason Honeycut, Brandon Ali, and Cory Estes. Determined initiative will go back to DW and go through demand shaping process. Meeting scheduled with I/Os to review on 2/27. Week of 2/17/25 - meeting scheduled on 2/19 as follow with System Development - They can not support this effort at this time. Informed leadership. 1/13/2025 Moving from Data & AI to having developed by System Development. Meeting with Mgrs of System Development on 1/15. 1/6/2025 Now #155 (was #92) on L2 Enterprise Priority List. Pending architecture review. 12/9/2024 #130 on L2 Enteprise Priority List. Pending architecture review. Working with Lee Skelton as EPM has advised Data and AI should proceed, but we can not complete the L2 lifecycle step without EA and/or PPM # - which will trigger the portfolio greenlight step. Entered proposal (request # 722511) with the limited information we have. 12/2/2024 Have been given credentials, now just need to work through process of establishing a PPM. 11/18/2024 Working on obtaining PPM # and completing L2 lifecycle step so the portfolio greenlight step will be triggered. This is part of reimagination and per Lee S - will not need to go to triage. 11/12/2024 Reached out to Jennifer Choate for guidance on next steps. Referred to Lee Skelton for guidance, who has reached out to Emilee James questioning that the initiative never came through Reimagination Architecture Review to trigger intake. Asyet, no response from Emilee. 11/5/2024 Waiting for TCH process to begin envisioning sessions. 10/30/2024 Testing 10/7/2024 TCH toggle has been flipped, waiting on response from that group to begin envisioning sessions. Will continue to consider UI/UX to improve communication with TCH team once meetings begin. | E: L2 | On Hold | L2 | 2024-08-01 | 2025-02-28
Business w/ Tech Initiative: Drayage Optimization (Now) | 67026 | 6715 | Business w/ Tech Initiative | FXF - LH | Freight | Kinn Kinney | On Track | 4/7/2025 On track with DW Devlopment. Jim Mullady has confirmed that we will be able to continue using the cost/container metric as long as it is not below a service center level. API endpoint has been developed and is just waiting on data for testing. Past due with justification while Nitin was working on data ingestion. 3/24/2025 DW development on track, no update from Jamie Outlaw regarding cost/container metric. Have been asked to re baseline/forecast by 3/31, but ability to pull critical metric will influence financials. Needing decision from leadership for guidance. Work with DW continues, no update from Jamie Outlaw regarding cost/comtainer metric. 3/2/2025 DW development of staffing model continues on schedule. Met with Laurie Oswalt to discuss metric evaluation for cost/container. Preliminary decision made to use standard drayage labor rate by location instead of individual actual labor rates. More discussion needed with Compensation and leadership to finalize. 2/24/2025 Continued development from DW on the staffing model. Requested access for the synapse table to get list of FXF and FEC locations. Will request dispatch data if needed once moved to OIP environment. *CAUTION* Have been informed by Jim Mullady that actual individual labor rates will no longer be accessible when moving to UKG timeclocks. This information is used directly to determine the cost per container move and is the top level metric impacting our projections and expected savings. Working with finance to review options. 1/13/2025 Working with finance on re-forecasting now that we have new timeline on tech development. Finance has approved reforecast. 1/6/2025 Estimated development completion by DW provided on 1/7 -- development to be completed by 5/12/25. Reviewing timelines now for testing and implementation. Will review re-forecating based on this new timeline. 12/16/2024 Waiting on DW to provide milestones and timelines so that we can accurately reforecast projections. We have provided a QRG on the requested UI/UX to. 12/9/2024 Had multiple meetings with Business Architect and continue working through business case scenarios with refinement for UX. Next meeting scheduled for 12/10. 12/2/2024 Had first meeting with DW architect. Continue to work with Business Architect on PEL Decomp and establishing milestones and timeline from DW. 11/18/2024 "Dataworks blocker from PEL (Impact Assessment) has been mitigated. We now have resources from Dataworks assigned. Architect: Sadhasivam Jayabalaganesan Delivery Lead: Raj Kumar Kasi" 11/14/2024 Based on SCO PEL meeting, on hold for assignment of DW architechts. New architect assigned, responding to update request from Parker Fleming. 11/12/2024 Completed SCO PEL process. Scheduled for SCO PEL to get approval for Decomp 11/14/2024. 11/4/2024 Been working with the PRT process and business architects to determine full development need. Scheduled to go through SCO PEL on 11/7/2024. 8/7/2024 Teams are working on updating the baseline and target values for KPIs and Impacts. Have had multiple meetings with the Business Architect to discuss current and future state of the model and ability to statements. Would like to discuss an education campaign to assist in utilization of the current manual model and PSP metrics. We currently can't recognize utilization based on KPI metrics. Some are improving, others are moving in the opposite direction. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-01-15 | 2025-07-31
Business w/ Tech Initiative: Drayage Optimization Execution System | 67028 | 6913 | Business w/ Tech Initiative | FXF - LH | Freight | Jacob Maher, Charles Crowder | On Track | 6/25- Moved back into L2 and dropped the Enterprise part of the title. 5/5- Moved back to L1 to get on the Enterprise back log. Waiting on them to reach out to jump start the progress 1/13- Still waiting for the architecture process, no update 12/19- Waiting to filter through the architecture process. Once we get our turn for documentation, we will also get contacts to be used for the PPM process. 11/12- Gathering the resources to help get us the PPM number as well as the architectural diagramming. 11/5- Engaging with Tech to help determine research. 10/28- Gathering Demand shaping information and engaging with Tech to determine what needs to be researched. 10/9- Continuing conversations with leadership to develop the answer to build vs buy and what all we can go after. | E: L2 | On Hold | L2 | 2024-02-01 | 2024-09-18
Business Only Initiative: Chassis Strategy | 91022 | 6914 | Business Only Initiative | FXF - LH | Freight | Jim Clark, Charles Crowder | On Track | 2025-10-13 Same update as 10-06, FEC is supposed to be done with their migration analysis today or tomorrow. 2025-10-06 Waiting for FEC to approve DCLI's migration language before we move onto the final Exclusivity category. They report they should be completed by Monday or Tuesday. 2025-09-29 DCLI has forwarded us their proposed migration language along with supporting data. Next step is to share with FEC, should happen this week. 2025-09-21 After receiving the Finance analysis next step is to analyze and understand DCLI's proposed migration language. We are doing this in concert with FEC and it will likely take the rest of the week. 2025-09-15 On Track, no update 2025-09-08 On track, no update 2025-09-02 DCLI is jogging in place while they wait for me to counter-offer. I'm waiting for Finance's analysis, I spoke to Laurie Friday and she has turned in her data to Alex, Kari and probably April. Once I get that I will get with FEC to make sure they agree with my counter (~$9.75) and then I will set up a meeting with DCLI to deliver it. 2025-08-25 On track, waiting for the financial analysis on the $10.50 offer. 2025-08-18 Meeting with DCLI leadership today in Memphis and waiting for Finance to finish their analysis on the latest offer from DCLI. Hoping to be able to counter that offer by Friday. 08-11-2025 Waiting for the financial analysis to determine what our counter should be. In the meatime we are meeting with DCLI's senior leaders next week in Memphis. Once we establish and agree on a rate the next step will be arguing exclusivity. 08-04-2025 DCLI countered with $10.50 plus a few million dollars in incentives. Finance is analyzing and we'll come up with a counter. At this point it looks like all of the savings will come via a DCLI exclusive contract, both for FEC and FXF. 2025-07-28 Date for DCLI's proposal counter is now Weds 7/30 and as late as Fri 8/1, 2025-07-21 No change, on track 2025-07-14 No change, on track 2025-07-08 No change, on track 2025-06-30 Still waiting on counter from DCLI. Also finishing up on T&C's agreement with Trend. 2025-06-23 Met DCLI in HRO last week. We did drive our points home and the next step is for DCLI in the comings weeks to submit a counter proposal. 2025-06-16 DCLI will be in HRO 6/18 for agreement talks. We will know more following the meeting. 2025-06-09 No change, on track 2025-06-02 No change, on track 2025-05-27 DCLI is responding to the proposal I sent Friday. Meeting is set for this Friday 5/30. 2025-5-19 In Memphis today (5/19) meeting with our lawyers regarding the DCLI contract. We should have a draft to send them this week. Also finishing the Trend T&C's. 2025-05-12 Meeting with DCLI today to discuss chassis purchases and new agreement expectations. 2025-05-05 Trent chassis contract should be complete as the last round of redlines circulate. New proposed DCLI contracts for FEC and FXF have been drawn up and a meeting is set with them for 5/8. 2025-04-28 Met with Milestone in HRO last week to discuss their lease chassis pool and also finished up redlines on the T&C's contract with Trend Chassis. Legal is fashioning a counter-proposal for DCLI that excludes exclusivity and high rate escalators, should be ready to review with Neil next week. 2025-04-21 The NACPC contract to lease/purchase 130 chassis for the ATL market has been completed. Next steps is to work on delivery timelines etc... DCLI is on hold temporarily as we finish the railroad spinoff contracts. 2025-04-14 Still waiting for final word on from NACPC regarding the lease/purchase agreement. In the meantime we are working up a counter-proposal for DCLI including a. All-inclusive low rate per billable day. Relaxed exclusivity language which would allow us to purchase and/or lease chassis. Normal rate escalator. 2025-04-07 Still waiting for final word on the NACPC lease/purchase agreement. Sent a template T&C's to Trend and also talking with TRAC as we already have a T&C's contract with them 2025-03-31 NACPC is still | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: FXF CT Linehaul Rate Reduction and Mode Shift | 74675 | 6973 | Business Only Initiative | FXF - LH | Freight | Brad Troutt, Gannon Roberts | On Track | N/A | K: L5 | Completed | L5 | 2024-01-01 | 2024-10-31
Business Only Initiative: FXF CT Linehaul Bid | 80813 | 6974 | Business Only Initiative | FXF - LH | Freight | Jeff Scroggins, Gannon Roberts | On Track | 06/06/25 Actuals for May entered--mirrored Aprils numbers 05/15/25 Entered actuals for April @ $391,619 04/03/25 Entered actuals for March @ $291,224 Increase due to decrease in number of schedules canceled due to lack of volume 03/05/25 Entered February actuals of $168,864. This being much closer to re-forecasted of $170,000 02/10/25 Entered January actuals of $181,299. 01/29/25 Updated forecast to reflect closer to actuals. This due to changes in the network and not as many of the pt motor schedules running as planned. New monthly forecast $170,000. 01/09/25 Entered December Financials $158,374. Currently 9 of the original schedules have cancelled all together. Another 20 have changed carriers that are changing the overall savings total. 12/18/24 No changes to this initiative 12/05/24 Entered November Financials: $180,329. 11/14/24 Entered October Financials: $207,038 in total savings. Some adjustments to the original carriers due to service and carrier no longer able to support. Out of 50 original RFP bids 21 have changed 16 lanes changed due to service or carriers could not maintain 5 lanes cancelled by our Network Engineering Team 10/29/24 Waiting for October to finish. Will add actuals first week of November 10/03/24 Entered actuals for September. The variance in actuals versus forecasted is due to additional lanes (Total of 4) being permanently cancelled by Network Engineering. Additionally, there are 5 lanes that have been either taken away from carrier due to service or carrier cannot meet commitment and given the lane back. All of these compounded with schedules being cancelled due to lack of freight periodically or lack of equipment creates the variances. 09/12/24 Entered actuals. The variance in actuals versus forecast is due to 1 lane completely canceled from our network. This lane was one of the higher savings lanes. Variance also driven by schedules that were canceled due to different reasons such as "lack of driver", "lack of freight" etc. The savings from these cancelations were removed from the actuals. 09/05/24 Collecting actuals now. 08/01/24 No weekly updates. Remaining new pricing scheduled to go into effect next week. 07/23/24 Entered Milestones and KPIs for L3 approvals Currently in round 2 of the bidding process. Carriers were communicated with regarding the result of round 1 and are now reviewing and updating if they want to continue with the bid. Scenarios will be ran June 10th and FXF will review the results and start negotiating with the carriers. | K: L5 | Completed | L5 | 2024-05-10 | 2024-08-05
Business Only Initiative: FDXU Stacking | 68252 | 6984 | Business Only Initiative | FXF - LH | Freight | Erik Pinzon, Kyle Butrum, Justin R. Coggins | On Track | 3/13/25 Changing IOs - intiative on track. In L5 - tracking actuals - On Track 8-12-24 July actuals have been entered. Re-forecasted August moving forward. DCLI Rate changing is August ($11.28 per chassis per day to $12.97 per chassis per day). | K: L5 | Completed | L5 | 2022-11-01 | 2024-09-13
Business Only Initiative: Economy Oversight | 35230 | 7004 | Business Only Initiative | FXF - LH | Freight | Charles Crowder, Lauren Cole | On Track | 2024-11-04: progressing thru L5 approvals; Oct actuals being entered 2024-10-28: prep for L5 2024-10-07: seek L5 | K: L5 | Completed | L5 | 2023-10-23 | 2024-10-31
Business Only Initiative: Delay Pay | 36022 | 7022 | Business Only Initiative | FXF - LH | Freight | Shane Curtis, Kevin Kotil | On Track | N/A | K: L5 | Completed | L5 | 2023-11-06 | 2024-01-09
Business Only Initiative: Long Combination Vehicle (Short Term Win) | 38567 | 7093 | Business Only Initiative | FXF - LH | Freight | Lee Aronson, Greg Lange | On Track | L3 surge session. | K: L5 | Completed | L5 | 2023-12-05 | 2024-08-12
Business Only Initiative: Mode Shift Analysis Tool | 88168 | 7315 | Business Only Initiative | FXF - LH | Freight | Jacob Maher, Ehssan Hayik | On Track | 2/26/26- Per domain lead all work has been completed. Due to separation and leaving of planview we are closing it out. 7/09- Got two extra resources and we are getting them up to speed. Beginning work to separate the front end UI from Backend to rebuild them separately. 6/19/25 QA Review for SL3 completed by Kelli Ostertag – approved to Surge with Domain Leadership 6/11- Engaging with IT team to help them prep to create the environment for us, PI begins today and still no official timeline for when this work will be completed (still latest timeline is 8/19). UI and code edits are up next after helping IT team. 5/28- Passed through triage, we are slated to be worked on in PI03 which runs 6/11-8/19. Beginning UI conversations so we can be ready when the environment is created for us. 5/21- On the schedule for triage to set up the environment for 5/22. We have been told it is between 8 and 10 points. Which translates into 1 iterations, laymen's terms 5-10 days. 4/21- Waiting on the local enhancement to get the environment started for Hueon to start editing the code to fit in the environment. 4/14- Created Local enhancement to get the Azure Web Services process started. Getting the environment set up to drop our code into. Will keep track of that request within planview. Request ID: 0006662 4/7- Meeting with IT contacts on whats the process and best practices setting up Azure Web Services 3/31- Changed the initiative to buisness only and are ready to surge to L2. We are able to use the shared OR keyvault and have requested a secret in there. We will be setting up a call with IT team to get the app service process started. 3/24- Service principle has been requested and granted, Hueon has requested a secret to help us in setting up the keyvault. After the keyvault we just need to test the connection and figure out Jenkins 3/17 - Some of the steps were completed with the previous effort here. Requesting service principle, oboarding to FXF databricks, setting up keyvault and finally figuring out Jenkins 3/10 - Identified what pathway to travel down for server choice. Prepping the code of the tool to head down that path. Starting the process to get an azure subscription and revisiting the LBC to make sure it still applies. 8-31-2024 We are currently working on creating our business case and establishing what we will need to identify tech needs as well. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2025-07-07 | 2026-03-31
Business w/ Tech Initiative: Unified Equipment Pool (rail + dray) | 67029 | 7318 | Business w/ Tech Initiative | FXF - LH | Freight | Ehssan Hayik, Kevin Bair, Kinn Kinney | On Track | On Hold 7-1-25 On Hold 5-6-2025 We are working on updating the baseline for UEP and restructring the scope with the sole focus of FXF savings. 2-24-2025 Tech is planned to be delivered in September 2025. Will look to reforecast and adjust when value will be realized. Meeting with finance scheduled 2/25. 2-10-2025 We have a call scheduled with the ART team this week for capability 2 & 4 as well as working on getting actuals entered for Jan. and reforcastiong plans completed. 1-6-2025 Cantching up on late milestones and working with Dataworks to get a status update on when other milestones could be started. 1-20-24 Approved for Decomp and Decomp has begun. 11-11-24 We are working on updating our actuals for October. We arealso working with the PRT for our decomp stage. 11-4-24 We are finalizing the lane change and the amount of that lane change to best distinguish what we will need to reforecast our totals by. 10-29-24 We are looking into seeing if reforcasting will be needed. We are also identifying a possible lane change that would increase our net recuuring benifits by 4.5 million. 10-7-2024 We are planning to update all the impacts and KPIS for September. We have calls scheduled with the PRT and Data works teams as well. 9-30-2024 This week will be working on scheduled calls with the PRT team as well as discussions with our FEC contacts on peak plans and how that will effect the equipment pools. 9-23-2024 Still waiting for official L3 to be approved. Currently have planned calls with our PRT and data works team to complete the IT processes. Also plan to schedule a call with FXG to go over a few lane opportunities. 9-18-2024 Submitted for L3 approval. Gathering actuals to populate as soon as Initiative goes into L3. Next PRT working session for SCO is scheduled for 9/19. Envisioning session scheduled 9/19 with Dataworks. 9/9/2024 Currently still waiting for PPM # to submit for L3. We have a call schedule with the PRT team this week. Week of 09/02/2024 We are currently looking through more unified lane opportunities to better classify a market equipment pool and establish a network designed repo plan. Currently still waiting to be greenlit so we could submit for L3. .8/17/2024 We are working with finance to finalize our monthly profile and establishing our KPI's. We plan to surge to L3 on 8/20/2024 but will be following up with finance 8/19/2024 to ensure we are ready to take that next step. 8/10/2024 This week we met with the Data works team for a triage session on the needed tech. support. We completed an Initiative architecture survey and submitted for the intake meeting. Architecture team has followed up and scheduled a dispositioning exercise for Monday 8/12. We are also building out monthly profiles and establishing KPIs. 8/6/2024 Working with teams from Surface IT and Dataworks to try to fast track for TCH greenlight. Scheduled for PRT/PEO on 8/21. We also held brief meeting with the maintenance teams from both sides to continue to bridge the gap on equipment repair process. Reached out to Xirgo team to ensure there's a process behind receiving the Xirgo report weekly. 7-26-2024 TCH request has been sent as well as surface demand request. We should be completing our weekly XIRGO Milestone report as well as starting to get actuals for July next Friday. We had some great progress with the milestones that started as well. 7-20-2024 We have added milestones and currently building out our TCH demand request, Reviewed the milestones with the milestone owners and discussing what's next steps. Working on getting June Actuals for FXG as well. 6-29-2024 to 7-10-2024: We have created milestones and established working sessions on what the OCM process will be. We also have established an enterprise maintenance team to help work on our shop/red tag processes. 6-29-2024: this week we held one internal working session around establishing the milestones for the UEP initiative. Theis next week we will begin lay | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-03-01 | 2025-12-05
Business Only Initiative: Multiple Turn Analysis | 28553 | 8075 | Business Only Initiative | FXF - LH | Freight | Tyler Sanders, Timothy Johnson | On Track | 8/6 -- Preliminary July results show over 5,000 hours replaced. Waiting for Kronos edits to be settled this week and for hourly wage gap from finance. Final results will exceed monthly goal. | K: L5 | Completed | L5 | 2023-08-22 | 2024-08-30
Business Only Initiative: Pre-Approved Driver Alternate Routes | 35227 | 8098 | Business Only Initiative | FXF - LH | Freight | Travis Williams, Chris Wade | On Track | Eliminating non-standard routes will result in annual cost savings. This team is examining each leg used, and the frequency of use to estimate a total cost savings for the company. After comparing active construction routes with non-standard routes we have a clear picture of which routes can be eliminated. | K: L5 | Completed | L5 | 2023-10-30 | 2023-12-04
Business w/ Tech Initiative: ACF Reporting Dashboard and IT Flag | 66968 | 8170 | Business w/ Tech Initiative | FXF - LH | Freight | Jacob Maher, Weston White | On Track | 2/17- On track, false positive issue has been resolved 2/10- On Track, monitoring KPIs 2/3- On track, monitoring KPIs 1/19- Deployed with no issues, Money step completed. Surge scheduled for 1/29 1/13- Deployed 1/12, there were errors coming up and we pulled back the update. Looking to make some upgrades to prevent unnecessary errors and will look to redeploy ASAP. 1/6- Move to Production date has been moved back to 1/12 as this got slated with other updates that needed to be tested. No significant changes to our plans 11/9- No additional Update. 99.5 dispatch compliance 97% unit compliance. 11/12- No additional update. 99.7 dispatch compliance 96% unit compliance. 11/5- No additional update, it is currently planned to be moved to production with the gen refresh 10/28- Talks with the tech team on trying to get this solution pushed through separate from Gen Refresh. It is looking likely that it will just be slated with the Gen Refresh in January. 10/9- Dispatch compliance from 9/29-10/06 - 99.7% with 6 noncompliant dispatches. 1 new units hit the railyard for the first time taking us from 719 to 720. Development work is planned to complete in PI04 (prevent unregistered tractors to be dispatched to CA railyards in ACCOPS). Looking for MTP conversation. | K: L5 | Completed | L5 | 2024-01-30 | 2025-01-30
Business Only Initiative: Road Trailer Dispatch Sequencing | 96271 | 8248 | Business Only Initiative | FXF - LH | Freight | Allen Floyd, Mark Parisher, Nathan Kulikowski, Christen Daniels | On Track | 3/13/26 Cancelling this initiative in planview. This will be put on hold in Wave as we are focusing on other areas until the separation. 3/3/26 Patrick Mark working to get request elevated. Issue is getting it moved to L6. Needs to be here to be able to test before moving to Prod. Will reach back out to Mark today. Nothing else he can do at this time waiting to test. Dheeban Couple changes to the logic last week and it is working. Solution from the IT team slowed it down instead of sped it up. Talking to them about increasing the size of the compute. Exploring ways to make the tool/logic more cost efficient. Nathan Checking runs and Data last night and there were a lot of error runs last night. it deletes all the old data and then pulls in the new one. No data in the tool. Adding a pop up to let the user know. Last night found an issue with HLs. HRL built a CLT HL and the current logic. The HL was disregarded. Wanted to send out the green light with those waiting to use it. Having a higher fail rate. Dheeban will put the code back to previous so that the fail rates will be lower. At this point it looks like we are likely going to be late as we are finding some things that would delay the start. 2/25/26 Patrick: •Issue moving to the L6 queue. This has to move through L6 before it moves to prod or get through L3. Patrick is having issues finding what the issue is. After testing would move to a prod subscription. Dheeban: •Going well. Working with Nathan. Adding NWA and ATL to trailer sequencing. Can add in test a specific center or a whole district. Changes are now automatic. •No progress on combining into a single tab. Jamie: •Will have some cost with the Azure. It will be a pay as you go through them. Before all the cost was absorbed by FEC. Do not have a good ideal on what. oThis is the only option we have in running this application. oThe reason this one is different is that it has optimization code running behind the scenes that runs information and then optimizes the information that the spotfire is displaying. Most other reports does not have the complexity that this one has. Nathan: •Presented to FE group and they are getting this out to the local groups. •Issues with trailer history and a few others. •Nathan has been testing locally oATL, •Still collecting points of view of on the 1 tab for Trailer sequencing. 2/18/26 Meeting recap 12/18/26: •Update on Patrick being able to get new tables to L6 queue and moving to a prod subscription (last estimate was for 2/25/26 to prod subscription). oStill in progress, request submitted with JMS team. There’s enough info to pass along to Mohankumar, and Buddie Duggins to add the tables to L6. Patrick to get special access to test them in L6. After tables are in L6 and tested, then will elevate to a prod JMS subscription. ETA to complete is open-ended •Update on Dheeban moving back to Purescale for trailer pairing and running the program timely. Last meeting it was running for SOWE and PX district, is that still the same? oProgram runs every 15 minutes, average run time is just over 10 minutes, which is good right now. Pipeline is stable, hasn’t failed more than once or twice in a day, which is common. When loading for the network, load will be higher and will need to get with IT to help. IT assistance is common. Still running for SOWE and PX Tool is in prod and will start working with IT now to get the ball rolling on improving on optimizing run-time for the network load •Jaime and Dheeban will request IT assistance and let us know status within 1-2 days. Will reach out for additional support from higher-ups if needed. •Updates from Nathan on testing and ops feedback on the best things to show at the top of the screen. Updates on combining Trailer Sequence and Trailer Pairing into 1 tab. oWorked with Dheeban on verifying data, looked good on the live time loading piece | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-10-21 | 2026-03-27
Business w/ Tech Initiative: Enterprise Drayage | 4895 | 9045 | Business w/ Tech Initiative | FXF - LH | Freight | Erik Pinzon, Kyle Butrum | On Track | Week of 3/10/24 On track. For WE: 3/8/25 FXF handled 87.95% of FEC Drayage Dispatches and 76.77% of FEC Drayage Miles . Goal is 90% Dispatches / 80% Miles. Week of 3/3/25 On track, February actuals entered. Decrease in % handled by FXF month over month. Jan - FXF handled 87.44% of FXG drayage dispatches. Feb - FXF handled 86.96%. Week of 2-17-25 Corp Comms (Leadership Headlines goes out on 2/19 - announcing TRACK Web Application. Last milestone will be complete - and surging to L5 on 2/20. UP - API fix ging to Cab approval this week. Week of 2-10-25 submitted 340+ dispatcher access roles to prepare for rollout. Demo calls scheduled - part of the corp comms for people to register. (4 options). Canada (PT) added into TRACK for visibility. Week of 2-3-25 Dispatcher Role has been corrected/tested. TRACK Web Application rollout is the only remaining milestone "Rollout TRACK" - Preparing Corporate Comms to go out 2/19. (Pushed a week due to schedule conflicts). Education Calls planned for week of 2/24. Discontinue OLD TRACK planned for 3/30. L5 pushed for 3/30 - will look to get scheduled for surge. WE: 2-1-25 FXF handled 90.31% of FXG drayage dispatches / 79.43% of drayage miles. Week of 1/27/25 Received CAB approval for updates in TRACK Web application. FEDZ's update sent to PROD on 1/27/25. Still working through DISPATCHER Role - ticket with OKTA open. Aligning with Bo/Travis for comms and regional call rollout. MM Spec becoming SME's to handle rollout. New L5 date anticipated to be 2/28/25. Week of 1/20/25 New Rollout Plan established. Will move L5 date to 2/28/25. WEL 1/18/25 FXF handled 88.66% of FXG Drayage Dispatches and 78.67% of Drayage Miles. Week of 1-6-25 Update - WE: 1/4 - FXF handled 88.59% of FXG Drayage Dispatches. Complete month of December handled 83.96%. TRACK changed are moving to PROD this week. (includes stackable edits in TRACK Dispatch and carrier ID filter on TRACK Dock.) WE: 12/28 - Will be looking to establish new timeline for rollout of TRACK. 2 remaining milestones on this intiative related to TRACK. WE: 12/14 - FXF handled 84.22% of FXG Drayage Dispatches. WE: 11/30 FXF handled 89.47% of FXG Drayage Dispatches. PEAK is underway. Continue working with Dataworks on tweaks to TRACK Web Application. Multimodal Specialists are using application to become SME's and prepare for rollout in January. WE: 11/16 FXF handled 93.10% of FXG Drayage Dispatches. Week of 11/9/24 FXF handled 91.56% of FXG Drayage Dispatches. Week of 11/4/24 New plan for rollout determined. Milestones pertaining to testing and rollout have been pushed out. Now through Dec - Multimodal team becoming SME's in new app while developers are still fixing 3 areas. January - full rollout planned with corpo comms and regional calls planned. Week of 10-24-24 Developers are still trying to solve for Crosstowns and FXG Empties. Will need to test FEC loads when solution is implemented. Preparing for Rollout in parallel. Meetings scheduled 10/29 with Multimodal Managers for communication plan and timeline of rollout. Milestones at risk of being late again. Due dates have been adjusted several times (as well as the L5 date), when new plan on timing for readiness of rollout is determined - will review adjusting due dates again. Week of 10-7-24 Last TSP in SoCal has been transitioned. WE 10-5 FXF handled 89.34% of FXG Drayage Dispatches. September handled 89.53%. TRACK: Oppty with empties in FXG showing assigned to FXF. Developers are working on solution. Other data in TRACK is being tested and proving to be good. 9/5/24 Extended due dates on remaining Milestones for Testing and Rollout - which moves our L5 date. | K: L5 | Completed | L5 | 2022-01-03 | 2025-11-28
Business Only Initiative: Zuum | 26147 | 9181 | Business Only Initiative | FXF - LH | Freight | Gannon Roberts, Jaime Nuessner | On Track | Weekly Status - pre L4 surge meeting - Added comments to risk assessment due to weather in January 2023 compared to January 2023 - word document entered for evidence as an attachment displaying ADHOC numbers for January 2024 - screen shot of Zuum platform entered as attachment as evidence of go live. - updated forecast numbers through FY27. Weekly Status- - securing adhocs - working on minor adjustments Weekly Status - Going live today. Weekly Status - still working on build phase with Zuum team. - began carrier training yesterday 12/18 - began internal training today 12/19 Weekly Status - still working with Zuum on the build and customization of the load board, all seems to be on schedule. Weekly Status 11/7/2023 - submitted for L3 approval. - continue working with Zuum on the build phase. Weekly Status 10/31/2023 - completed tasks for L3 Surge - L3 surge scheduled for 10/31. Weekly Status 10/24/2023 - had a meeting with Pod team to prepare for L3 surge. - Working on a few updates for L3 surge - working with Zuum on build phase. Weekly Status 10/10/2023 - working on getting everything entered for L3 surge - working with Zuum on tickets and fielding questions as they come in. Weekly Status 10/3/2023 - scheduling calls to walk through tickets and examples pages of load board with Zuum. Weekly Status 9/26/2023 - Contract was signed by all parties on 9/21 - working through the steps with VAM to secure vendor # - fielding questions and working through tickets with Zuum during the build phase. Weekly Status 9/19/2023 - still working with legal to finalize the contract - FXG is having introductory process discussions with Zuum - fielding questions from zuum as they write tickets for customization Weekly Status 9/12/2023 - working with legal and Zuum to finalize the last few things needed for an executed contract. - Begin working on L2 tasks Weekly Status 9/5/2023 - Meeting for L2 surge and submitted for approval. - working with finance on how to measure savings. - meeting with legal teams to finalize contract. Action items were to copy and paste some verbage, Approval of liability for data breach, and order form and SOW approval by FXF legal and finance. Weekly Status 8/29/2023 -Zak, Jaime, and I had a L3 review call to discuss what was still needed in wave to push through L2 and L3 Gates. - after meeting I entered process/contingency milestone, and updated 2 or 3 others - Entered planned monthly recuring benefits - Entered KPI monthly baseline and targets. - Had a meeting with legal reps from FedEx and Zuum to walk through existing redlines. Projected that contract will be signed by the end of this week or next. - Worked with the Zuum team to ensure that final adjustments were made on the SOW. - Developed a draft of written policy and procedure for the new adhoc process and developed/documented a contingency plan if Zuum were to have issues for any period of time. These documents have been sent to our compliance specialist for review. Week Ending 8/26/2023 - No updates this week Week Ending 8/19/2023 - couple of last questions about SOW met and discussed about with Zuum team - legal and Zuum going through redlines on the contract and DPA. Meeting 8/22 to discuss final questions. Week Ending 8/12/2023 - had a meeting with Zuum team to finalize the SOW and cover questions about SLA. - Had a meeting with POD team to review content for Surge schedules Tuesday 8/15 - Finalized the 3PS milestone. - updated list of milestones dates, risks identified, and KPI's Week Ending 8/05/2023 - had another meeting with the Zuum team to work on the SOW specifics. - received word from Ground leadership that they would not be included in this initiative, we will move forward with Freight's numbers. - working with legal on the contracting process. - scheduled a surge prep meeting for Monday 8/7. Week Ending 7/29/2023 - had 3 meeting with the Zuum team to discuss and finalize SOW and specific adjustments needed made to the | K: L5 | Completed | L5 | 2023-02-14 | 2025-01-31
Business Only Initiative: Operations Expense Control | 87606 | 9186 | Business Only Initiative | FXF - LH | Freight | Matthew Otto, Jaime Nuessner | On Track | All work Completed. Executed Money Step end of December | K: L5 | Completed | L5 | 2024-08-21 | 2024-10-25
Business Only Initiative: (Enabler) Network Analytics | 26232 | 9187 | Business Only Initiative | FXF - LH | Freight | Stan Bradford, Jaime Nuessner | On Track | Apr 22nd. Evaluated 4 versions with new metrics related to speed and functionality and made a decision on which version would be loaded into PROD. That version was loaded into PROD and all is functioning as expected. Apr 16th. Data for Trailer Compliance placed into PROD. Work on dashboard functionality has begun. Experiencing slowness with the test version with these metrics added. Apr 8th. PROD request submitted last week but failed to load correctly. Was resubmitted on Apr 8th. Work to begin getting Trailer Compliance metrics into the dashboard set to begin on Apr 9th. Apr 2nd. Data validation for the Trailer compliance metrics has been completed and a PROD change request will be made this week to get the data pulled into the dashboard. Work to get visibility into the dashboard will be done next week. Expecting completion in about 2 weeks. March 19th. Work has begun on getting Trailer Compliance metrics in the dashboard. Currently investigating "unknown" shift dispatches in the Compliance report. March 13th. Had gateway issues last week that prevented new data from loading. That was resolved. Also had an issue on Mar 11th with new data not loading. That was resolved this morning. Other priorities have prevented work from begining on the final to metrics this week. Feb 26th: It has been discovered that Cancelled Bids cannot be entered into the dashboard because this metric does not have dispatch attributes like the other metrics withen the Power BI data table. By definition, this metric is related to dispatches that did not happen. Adding these would require doing an outer join on the cancelled bid data and significantly increasing the table size and slowing the dashboard. We are still exploring ways to include the Extra Bids metric as these are tied to dispatches however there are mis matches in the data that need to be resolved. The Trailer Departure and Arrival compliance Power BI is complete and these two metrics are ready to be added. Feb 12th: Jan 22nd. Elena has started work to get two metics (Cancelled Bids & Extra runs) into the dashboard. For the other two metrics (Trailer Departure and Arrival Compliance), Evan has finalized the Power BI for that report which will enable our dashboard to get data from it. The work for bringing those two into the dashboard will begin once the first two are complete. The Cancelled Bids and Extra runs Power Bi is ready to connect with the Network Analytics dashboard but won't have history past Nov 2024 until IT prioritizes loading the data. Trailer Compliance logic is finalized and the test Power BI is stood up. We will validate before moving to PROD. Jan 15th. Currently determining if data in the Trailer Compliance reports is accurate enough to move forward with setting up Power BI. For the Cancelled Bids/Extra runs, there has been no progress on request getting the data needed into the PureScale tables to produce the history **(REQ6134030)**. Jan 8th. OOR is now in the PROD version. For Cancelled bids/Extra runs, a work order form was submitted to get the needed history into the PureScale tables. For the Trailer Complaince, we continue to work to refine logic to capture arrival times for those traielr moving out of route. Dec 3rd. OOR was moved to PROD but bug in code was causing data to be too high. Code was updated in DEV and a new change to PROD request has been made. Cancelled bids was also moved to PROD with an issue identified. That will be corrected and a new change to PROD request submitted. Trailer dept/arriv compliance continues to develop logic and has reached out to IT for help with how to handle rail weekend arrivals. Nov 21st. Change request to move OOR data to PROD complete and will begin moving in historical data. This should be complete by Nov 22nd. If this goes well, daily jobs to append data in PROD will be set up on Nov 25th. This will place all current metrics in the Dashboard in the PROD environment. The change req | K: L5 | Completed | L5 | 2023-07-25 | 2025-03-31
Business Only Initiative: Connection Pruning | 75603 | 9377 | Business Only Initiative | FXF - LH | Freight | Andrew Fleming, Mark Milburn | On Track | N/A | K: L5 | Completed | L5 | 2024-01-02 | 2024-08-12
Business Only Initiative: Railroad Competitiveness | 72937 | 9424 | Business Only Initiative | FXF - LH | Freight | Gaurav Singh, Lee Willhite | On Track | The savings is on track, and the L5 surge meeting is scheduled on 02/13/2025 Week of 09/02/2024, The loads have been shifted from BNSF to the Union Pacific form June 2024 on the 2 lanes and the L4 surge call for the initiative is scheduled on 09/05/2024. | K: L5 | Completed | L5 | 2024-01-15 | 2024-09-30
Business Only Initiative: FXF - RECOVERY | 71065 | 7369 | Business Only Initiative | FXF - LH | Freight | Donald Baker, Matthew Otto | On Track | Our team is working with Tyler Austin (Systems Developer) to get the RECR information/data added to the POV/Transit Delay tool. From there, we will develop a tab within those reports to display both "live" RECR info along with historical data. The historical data section will be used for KPI's to measure successful RECR use in the operations. We are also engaging Learning & Development to assist in the new education rollout process, including a new QRG focusing on proper RECR use in the operations. With this education rollout, we will utilize 629 headhaul lanes to focus on RECR use and reduction of linehaul schedules on a daily basis at a minumum of 5% daily. 5/1/25 - Our team completed the Re-Forecast of RECR with Laurie Oswalt and are ready for the L4 surge call. 5/16/25 - Project was approved to L4 earlier this week. In reviewing checklist for L5, we have completed all steps and are ready to submit to L5. | K: L5 | Completed | L5 | 2024-02-19 | 2025-05-02
Business Only Initiative: Winter Bid Network Changes |  | 84618 | Business Only Initiative | FXF - LH | Freight | Lee Aronson, Andrew Fleming | On Track | Bid reductions associated with Connection Pruning and cubic utilization data will be implemented with the onset of the Winter Bid on 12-1-24. | K: L5 | Completed | L5 | 2024-12-02 | 2024-12-02
Business Only Initiative: Florida Rail Ramp Storage Fees |  | 87629 | Business Only Initiative | FXF - LH | Freight | Juanitta Gibbany, Jonathan Vineyard | On Track | Dependent on contract negotiations to add additional free day - No FY25 value will be realized until negations are completed. Negotiations are not expected to be completed in 2025 calendar year. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Reservation Cancellation for Rail Owned Assets |  | 87632 | Business Only Initiative | FXF - LH | Freight | Tamera Warren | On Track | Week of 4/2 - Begin Q4 with updated numbers Week of 3/26 - Getting with Carrier to reduce weekly number Week of 3/19 - Gathering feedback from stakeholders for Q4 review Week of 3/12 - Gathering feedback from stakeholders for Q4 review Week of 3/5 - Waiting for invoices to confirm actuals Week of 2/26 - Continuing plan, no further changes Week of 2/19 - Continuing plan, no further changes Week of 2/12 - January actuals entered, no further changes at this time Week of 2/5 - Full month of updated reservation counts begins Week of 1/29 - Preparing to surge to L4 Week of 1/20 - Scheduled for L4 surge on 1/29. Sent updated reservation totals to the rail carriers to eliminate unneeded guaranteed reservations. 49 Reservations/Week, 196/Month | I: L4 | Cancelled | L4 | 2024-12-05 | 2025-03-31
Business Only Initiative: Driver Motel Spend Reduction |  | 87939 | Business Only Initiative | FXF - LH | Freight | Stephanie Patton, Jeff Scroggins, Terry Crow | On Track | Contract and Vendor Risk Management finalization. | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-07-22
Business Only Initiative: Trip Mileage Compliance |  | 89832 | Business Only Initiative | FXF - LH | Freight | Matthew Fike, Lauren Cole | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. on 5/20/2025 QRG was created and added to PowerBi report. Report is ready to test, and has been pushed to the team for testing and any reviews that may be required. on 5/19/25 Follow up QA Review completed by Kelli Ostertag, approved to Surge for SL3 on 5/19 got a near final version of the report. Slowness was helped, added a "toll" flag to indicate any added miles as a result of using the toll roads. Also changing the title of the report to include delay pay and added miles. We are also starting to add to the current delay pay QRG to account for the added mile piece to this report. on 5/8 3rd version of report was received and more suggestions were made, report is right where we want it but the rate of refresh is really slow. We also want it to show driver domicile. on 5/5 after a few test runs had a newer test version of the report on 5/2 got a rough working version of added mileage that was incorporated into the current delay pay PowerBi report on 4/25 met with report development team to lay out idea for added mileage reporting on 4/18 went to surge and was approved to move to L2 on 4/15 Q&A reveiw approved by Kelli Ostertag on 5/24 met with development team to layout plan for added miles to be combined with the delay pay report, gave details of what we wanted to see in the report on 5/7 met with development team again to go over initial report, make edits as needed on 5/8 had a test version of the report, tested it with the team and requested some edits to be made to improve reporting. on 5/12 report was modified based off of feedback from initiative team members on 5/15 we added driver domocile to the report based off of additional feedback on 5/19 QRG was added to the report to help guide users throuigh the different reports on 5/22 report was edited to limit data to improve speed to download on 5/28 report went live in the reporting hub on 6/17 eraly departs was added to the report based off of feedback from the Sr ops advisor team on 6/24 driver domicile region was added at the request of the sr ops advisor team. on 6/26 inititive was pushed to L4 on 9/10 90 day assessment ended (6/1/2025-8/31/2025). For Q1 FY26 miles were reduced by 96100 on a goal of 21095. Initiatve will be pushed to L5. | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2025-04-25 | 2025-06-11
Business Only Initiative: VIA Optimization |  | 91596 | Business Only Initiative | FXF - LH | Freight | Nicole Brown | On Track | 1/19: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 1/14: No major updates (January Forecast: 3,416 miles ($9,057) / Actual: 3,382 miles ($8,028) 1/8: No major updates. * Updated December Financial actual. Exceeded Dec Forecast (December Forecast: 3,966 miles ($9,413)/Actual: 6,649 miles ($15,782) * January Forecast: 3,416 miles ($9,057) / Actual:1,836 ($4,358) 12/30: No major updates. Exceeded Dec Forecast (December Forecast: 3,966 miles ($9,413)/Actual: 6,649 miles ($15,782) 12/23: No major updates. Exceeded Dec Forecast (December Forecast: 3,966 miles ($9,413)/Actual: 5,844 miles ($13,871)) 12/16: No major updates. Exceeded Dec Forecast (December Forecast: 3,966 miles ($9,413)/Actual: 4,586 miles ($10,885)) 12/9: No major updates. (December Forecast: 3,966 miles ($9,413)/Actual: 2,312 miles ($5,488)) 12/2: No major updates. Exceeded Nov Forecast (November Forecast: 3,086 miles ($7,325)/Actual: 5,069 miles ($12,032)) 11/25: No major updates. Exceeded Nov Forecast (November Forecast: 3,086 miles ($7,325)/Actual: 4,770 miles ($11,322)) 11/19: No major updates. Exceeded Nov Forecast (November Forecast: 3,086 miles ($7,325)/Actual: 3,479 miles ($8,258)) 11/12: No major updates. Exceeded Oct Forecast (November Forecast: 3,086 miles ($7,325)/Actual: 2,080 miles ($4,937)) 11/4: No major updates. Exceeded Oct Forecast (October Forecast: 3,324 miles ($7,889)/Actual: 5,143 miles ($12,207)) 10/28: No major updates (October Forecast: 3,324 miles ($7,889)/Actual: 4,656 miles ($11,051)) 10/22: No major updates (October Forecast: 3,324 miles ($7,889)/Actual: 3,859 miles ($9,160)) 10/15: No major updates (October Forecast: 3,324 miles ($7,889)/Actual: 2,147 miles ($5,096)) 10/8: No major updates (October Forecast: 3,324 miles ($7,889)/Actual: 1,006 miles ($2,388)) 10/1: Achieved September forecast (Forecast: 2482 miles ($5,866)/Actual: 5854 miles ($13,895)) 9/24: On track to exceed September forecast (Forecast: 2482 miles ($5,866)/September MTD Actual: 4176 miles ($9,897)) 9/17: Completed L5 surge 9/10: Ready to surge to L5 on 9/11. Enhancements are complete 9/3: Central dispatch is reviewing enhancements. Preparing for L5 surge. (August Forecast: 1,959 miles ($4,650) /August Actual: 6,283 miles ($14,913) 8/27: Feedback enhancements testing to begin August 27; targeted to be completed by 9/5 Preparing for L5 surge. (Forecast: 1,959 miles ($4,650) /Actual 5,184 miles ($12,304)) 8/20: Tyler is working on feedback form 8/6. Will followup next week. Preparing for L5 surge. Month to Date miles savings: 16,805 (Forecast - 2,471 miles) 8/13: Tyler is reviewing feedback from 8/6. Preparing for L5 surge. Month to Date miles savings: 9,817 (Forecast - 2,471 miles) 8/6: Preparing for L5 surge. Achieved July forcasted milage savings (Forecast: 1,959 miles ($4,650) /Actual 32,201 miles ($76,432)). Received the following feedback on comments, NITRO lanes and VIa opp sent to planner after 2100 local time: • Update VIA comments time zone • Add a column that captures the time stamp of when the users was notified of BV opportunity • Remove VIA opportunities that are being sent to planner after 2100 local time • Once BV option is no longer applicable (IE, projection changed and no empties were available OR empties were utilized elsewhere) – recording of opportunity should not be sent to the history report • If BV notification is not sent to planner, recording of opportunity should not be sent to the history report as “NO REASON PROVIDED” as it does not appear planner was notified of opportunity. NITRO lanes were eliminated but we still see an example of these showing up still 7/30: Continuing t | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2025-04-01
Business Only Initiative: Zuum III |  | 93066 | Business Only Initiative | FXF - LH | Freight | Gannon Roberts | On Track | N/A | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Cube Based OB Projections |  | 92703 | Business w/ Tech Initiative | FXF - LH | Freight | Sara Bailey | On Track | 6/24/24 No Change 6/16/25 No change 6/10/25 Will keep initiative as is and not roll into larger PFS LH Awaiting prioritization and resourcing 6/4/25 Determined this is not local demand due to the fact that the cube data is not on the same platform as OB Projections and would cause latency in calling data from different platform Waiting on leadership decision on how to proceed with initiative as stand alone or absorb into LH PFS 5/28/25 Leadership update meeting pushed to 6/2 due to calendar conflicts 5/19/25 Leadership update meeting pushed to 5/27 to allow more time for solutioning 5/14/25 Meeting 5/12 with FXF LH to discuss Prioirty #1 requirements Tom McDowel will discuss potential solution with other architects Meeting scheduled for 5/19 for leadership update on progress 4/25/25 FXF LH IT has agreed to discuss the option of moving project from Bus w/ Tech to Local. Meetings next week to review what is being asked and what work would be involved. Meeting May 12th with leadership to discuss if we have enough details to make the Local decision. 4/7/25 #36 on Enterprise Demand Priority L2 List Waiting on prioritization and architect assignment 4/01/25 #32 on Enterprise Demand Priority L2 List Waiting on prioritization and architect assignment 3/25/25 #29 on Enterprise Demand Priority L2 List Waiting on prioritization and architect assignment 3/19/25 Surged to L2 3/13 #29 on Enterprise Demand Priority L2 List Waiting on architect assignment 3/11/25 Contacted by FEC EA to size project, but solution was building tool outside of ACCOPS to make projections. Informed EA that was not acceptable solution. 2/18/25 #18 (Top FXF) project on Enterprise Demand Priority List Demand status - Backlog 2/11/25 #19 (Top FXF) project on Enterprise Demand Priority List Waiting on BA assignment 2/4/25 #30 (Top FXF) project on Enterprise Demand Priority List Waiting on BA assignment 1/28/25 #25 (Top FXF) project on Enterprise Demand Priority List Waiting on BA assignment 1/20/25 Added to Enterprise Demand Priority List waiting for BA assignment #18 (top FXF) project on the list | E: L2 | On Hold | L2
Business Only Initiative: Trailer Cube Utilization Process | 35229 | 8120 | Business Only Initiative | FXF - LH | Freight | Sara Bailey, Tyler Sanders | On Track | 2.11.25 Approved for L5 2/6 Project moved to LH Pod Actuals entered $2.1M vs $1.1 forecast 2.4.25 Waiting on finance approval for L5 Moving project to LH pod 1.28.25 Finance data updated per request from Alex Waiting on his approval 1.20.25 Forecast updated to 18% mileage reduction Submitted to L5 1.13.25 Setting up new tables needed for LH view of TCU Migrating TCU to PowerBI from spotfire Working through logic of BNF reporting 1.7.25 Meeting to discuss size and prioritization of adding through trailers to LH View Need size and prioritization for BNF compliance report 1.3.25 Start logic for BNF compliance report 12.16.24 BNF being added to TCU this week to allow centers to start using and learning tool through holiday weeks Full rollout and compliance report expected early January 12.9.24 Creating video for BNF rollout DEN asked to test out BNF this week 12.2.24 Updates completed from DAY and LOU feedback Working on communication for BNF rollout 11.25.24 Bump and fill changes being made based on DAY and LOU testing LH View work to start mid december 11.18.24 Focus lanes will stay the same for Q3 from Q2 Company goal will be 10.1% extra trailer. -Changing baseline to Aug-Nov and adjusting goals to meet company 10.1% Change requests for TCU -Adding goal and extra trailers to meet goal to banner of report -Pulling contract feet for TLX and exclusive use to calculate cube Bump and Fill testing at DAY and LOU LH View work to begin this week 11.11.24 Actuals entered Testing bump and fill report Q3 Goal and Focus Lane meeting this week 11.4.24 Reforecast completed 11/1 Bump and fill report to be added in test this week Logic changes for capturing unload only trailers to be tested this week Continue support of field with questions on updated tool. | K: L5 | Completed | L5 | 2023-11-28 | 2024-09-06
Business Only Initiative: NE Mapping Solution |  | 108338 | Business Only Initiative | FXF - LH | Freight | Chris Wade | On Track | 12-10-25 QA Review for SL2 performed by Kelli Ostertag. Approved. Attended Triag meeting 4/14 and was authorized to proceed to L1. Leadership has determined the work to be cancelled in Planview until the Tech support side has been established. | E: L2 | Cancelled | L2 Feedback Requested
Business w/ Tech Initiative: Digital Hub Planner Model + App | 26135 | 8382 | Business w/ Tech Initiative | FXF - LH | Freight | Kevin Kotil, Allen Floyd | On Track | Cancellation Request Rationale - DHP is currently being used to inform NITRO and this initative has been modified to serve in it's current capacity. The current output will continue to be utilized by the field and the output will continue to feed NITRO. 3/20/2025: - Deploying latest updates to the schedule - Haritha working on the new estimated weight for dummy pros based on historical average. Predicts to be complete by next week to start testing. 3/17/2025: - Starting to pilot with centers for the OB forecast data. (DAY, DTR, GRR, TOL, WRN, NAS, FMY, VLD) 3/12/2025: - Had initial converstaions with Pilot locations to pilot OB forecating data, looking to start piloting by 3/17 - Deploying latest updates to production to resolve the issue where some jobs were failing - Updated model run times for all pilot locations and deployed to stage - Integrated improvements to the OB forecasting data into stage environment - Monitoring production for any issues/bugs - Updated QRG 2/25/2025: - We were able to resolve the issue we were expereiencing when trying to connect to stage PowerBi environment - We are near completion of the debugging of the projected/dummy pros within the tool. From the most recent output of NEA/NDA we found only a few minor discrepancies. 2/17/2025: - Having issues connecting to stage/testing PowerBi. Reached out to Raj from Dataworks to put us in contact with someone who can assist. - Completing the necessary changes to the stage enviornment. Which includes the removal of the duplication of the dummy pros and ensuring we take the difference between the forecasted shipment count to the actual on-hand confirmed shipment count. 2/07/2025: - We need to add a validation in the query to only pull in active service centers to prevent the optimization model from failing/erroing out. 2/04/2025: - We have the projecitons integrated into production, and have removed the dummy pros/projections from the report. We're working to limit the top opportunities to only display opportunities where we have at least 6,000 lbs or .33 of a trailer. - We will create a seperate report utilizing the prod data with the projections and test with operators possibly starting next thursday if we are able to integrate the new forecast and do some initial testing in stage prior to getting with operations. - Hueon is looking into possibly improving the NLI output. 1/30/2025: - Hueon is looking into the network level model for potential discrepancies - Bumping up maximum weight constraint for a shipment from 12,000 to 30,000 lbs. 1/23/2025: - Haritha has integrated a fix for duplicate pros, and removal of constraint limiting weight to 12,000 lbs. This has been integrated into stage environment. Working with dataworks team to push to prod. Estimated date to move to prod 1/31. 1/20/2025: - Haritha has begun work on the stage environment and should have an update on the progress of the test environment for the OB projections by EOD wednesday 1/22. 1/13/2025: - Haritha is going to begin working on getting the data in a test table starting Wednesday 1/06/2025: - Working to get the test environment set up for validating the projections data for OB shift. Encountering some delays due to the transition of work from Ali to Haritha. Haritha is working on a high priority P&C project and may not be able to complete setting up the table in test environment until next week. - Monitoring production workflows to ensure there are no errors/bugs. 12/20/2024: - Met with Jamie Outlaw and Haritha to discuss the ability to set up test environment to build a test power bi to get feedback from front line operations on the new OB forecast piece. Reached out to Ankit and Raymond to see if we'd be able to get Elena to assist in the development of test report because it'll take longer for haritha to gain access/build a copy of the report. - Waiting on response from Raymond/Vijoe on their thougts for the bullet point above. 12/19/2024: - Ali has comple | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-05-29 | 2025-11-28
Business Only Initiative: Weekend Bump & Fill |  | 155193 | Business Only Initiative | FXF - LH | Freight | Kelsey Grape, Kelli Ostertag | On Track | 9/19- Aiming for surge to L3 on 9/25. Milestone plan is added, need to create and get finance plan approved. 9/23- QA review performed by Kelli Ostertag for L3 - approved. Will be surging with leadership on 9/25. 10/14- Acquired TCU data, incorporating into scorecard. Planning to launch to all identified centers at once instead of gradual roll out. 10/28- Rolled out to all lanes. Working with finance to update our timeline and KPIs. 11/18- Timeline and KPIs are adjusted. Tracking all lanes in scorecard. 1/20- Initiative milestones all complete, just tracking results in steady state. Asked to cancel to reduce load. | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2025-07-02 | 2026-05-29
Business Only Initiative: Network Load Integrity improvements |  | 177220 | Business Only Initiative | FXF - LH | Freight | Allen Floyd, Stan Bradford | On Track | 12/16/25 Evan Earwood •Migrating from one data source to another. Sequel server to another place. Development environment is writing where it needs to go. For infosec have to promote to test and then production. Middle January as a target at this to a point we get this to production before we can start testing. •Procedurally correct is to have this to production before we can start testing in the UI •Currently duplicated pipeline. •We have the correct information in sequel server and they might be able to use this so we can test before then Mounica: •UI is almost done. A few things that still need to be wrapped up. Might still need to have a couple weeks after the information is in production to write everything out correctly. Really looking at end of January. Allen: •To actually roll this out to centers we will need to do some extensive testing once they have backend and UI complete. oTo me it seems like Mid-February might be the earliest this could be rolled out depending upon when we could start testing. oAlso need to get some more eyes on column headers and the tool in general to ensure operations feels it is usable. On Track | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: FXF - PD - Extended area | 26149 | 6676 | Business Only Initiative | FXF - P&D | Freight | Mark Williams, Jaclyn Natoli | On Track | 2026-01-19: Closing out the initiative. Future revisions to the approach will be based on direction from the new FDXF Sales and Marketing leadership. 2026-01-12: Continue monitoring compliance, feedback and pending change review direction from leadership. 2026-01-05: Continue monitoring compliance, feedback and pending change review direction from leadership. 2025-12-29: Continue monitoring compliance, feedback and pending change review direction from leadership. 2025-12-22: Continue monitoring compliance, feedback and pending change review direction from leadership. 2025-12-15: Continue monitoring compliance, feedback and pending change review direction from leadership. 2025-12-08: Continue monitoring compliance, feedback and pending change review direction from leadership. 2025-12-01: Monitoring compliance, feedback and change review direction fro leadership. 2025-11-24: Monitoring compliance, feedback and change review direction fro leadership. 2025-11-17: Monitoring compliance, feedback and change review direction fro leadership. 2025-11-10: Monitoring compliance, feedback and change review direction fro leadership. 2025-11-03: Monitoring compliance, feedback and change review direction fro leadership. 2025-10-27: Monitoring compliance, feedback and change review direction fro leadership. 2025-10-20: Monitoring compliance, feedback and change review direction fro leadership. 2025-10-13: Monitoring compliance, feedback and change review direction fro leadership. 2025-10-06: Monitoring compliance, feedback and change review direction fro leadership. 2025-09-29: Leadership review on FE/OPS change requests. 2025-09-22: Working with FE on change request questions. 2025-09-15: Working with FE on change request questions. 2025-09-08: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. Work through FE Zip Code Change request review. 2025-09-01: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-08-25: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-08-18: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-08-11: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-08-04: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. Enter July actuals. 2025-07-28: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-07-21: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-07-14: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Continue to provide Senior Leadership daily recap on OPS utilization. 2025-07-07: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Provide weekly compliance reporting. Report Monthly DRIVE actuals. 2025-06-30: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Provide weekly compliance reporting. 2025-06-23: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Provide weekly compliance reporting. 2025-06-16: Continue utilization / Compliance Reporting and monitoring OPS/Customer Feedback. Provide weekly compliance reporting. 2025-06-09: Continue utilization / Compliance Reporting and monitoring OPS/Cus | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2023-05-15 | 2025-08-29
Business Only Initiative: [Enabler] PD Bidding System | 26150 | 6677 | Business Only Initiative | FXF - P&D | Freight | Kelsey Grape, Christen Daniels | On Track | Tool is in production server. New education is deployed. | K: L5 | Completed | L5 | 2023-06-01 | 2024-03-29
Business Only Initiative: Pickup Efficiency | 26151 | 6678 | Business Only Initiative | FXF - P&D | Freight | Shane Turner, Edgar Correa | On Track | WE 9/27 - Reported weekly status. Added Trailer Floor Utilization report and Pickup Service report links. WE 9/20 - Reported weekly status. Added Gate in By Hour tab. WE 9/6 - Reported monthly status. WE 3/15 - Reported weekly status. Met with city dispatchers to get feedback on push report creation. Ongoing work on DUP stop logic improvement. WE 3/8 - First monthly report goes out. Working thru DUP stop logic improvement. Met with Field Engineering to discuss push reports further. WE 2/8 - First report went out network wide identifying all center baselines and performance. Report also identifies top performers. Continuing to drive overall report utilization. WE 2/1 - Updated rank logic. WE 1/18/25 - Performance report continuing to be developed. WE 12/30/24 - No change. Still rolling out and enhancing usability. WE 12/7/24 - Communication distributed via Leadership Headlines. Worked on enhanced ranking system. Worked on KPI report. Discussed enhancements to come. WE 11/16/24 - Dashboard enhancements officially went live and usable to all via the Reporting Hub. FE Mngr communication sent regarding status. WE 11/9/24 - Dahsboard enhancements final review performed. SWAP financial assessment reviewed and approved. WE 11/2/24 - Finalized video training 1. Dashboard gateway role creation in process by Image team. WE 8/31/24 - All current enhancements should be in production and scheduled by 10/18/24 due to new data processes. Discussed documentation needed to educate leadership for a smooth launch. Create PUEfficiency@fedex.com account to enable leadership to easily communicate with developers. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2023-07-28 | 2025-12-31
Business Only Initiative: [Enabler] Salary Staffing | 26239 | 6690 | Business Only Initiative | FXF - P&D | Freight | Nicole Brown, David Gedlinske | On Track | 9/30: No update. Preparing for L5 surge 9/23: No update. Preparing for L5 surge 9/16: All image roles approved. Completed L4 Surge 9/8: Salary Staffing tool has been deployed to Prod. Image roles have been submitted for FE and Management team. Prepping for 9/11 L4 surge. 9/2: Salary Staffing Scheduler complete/tested. Continuing to work towrds Sept 8th Prod deployment 8/26: * Completed UAT * Preparing for L4 surge * Targeting September 8th Prod Deployment (Vacation conflict) 8/19: * Aditya is working on creating credentials; will be completed by 8/27 at the latest. Already have server available * Confirming Drayage counts. Working with Kinn to get updated Rail data dump for excel file so we can compare the same data sets in both tool. Targeting Aug 22nd completion * Beginning work on Salary Staffing scheduling tab. 8/12: Extended the testing to Aug 13th to allow the users to confirm the following items. Will touchbase on Prod deployment tasks. **Open Items:** * Ready for Test- Confirm Drayage and Non-Domicile Driver count calculations (following up with Wayne L during Tuesday touchpoint) **Closed Items:** * Export functionality * Update default HUB and HUB dispatch shift times to 9 hours * Access issues 8/5:Test link has been set out to FEs and we are targeting August 8th for all feedback. Working with Aditya on Prod deployment tasks 7/29: Access issue has been fixed. Currently completing testing with the team. We will meet on Thursday 8/31 before sending link to FE testers. 7/22: Working with Aditya on web app test environment access issues (John and I are showing a blank screen byt Aditya/Barry can see the fields). Entry and Totals tab functionality is ready (except Drayage) 7/15: Discussion on Rail data query to be held 7/15. Continue back-end development; pending Aditya sending link to UI on 7/18 for internal testing (Pending rail data) 7/8: Continuing development of web app. Meeting wth Kinn/Karthik scheduled on 7/15 to discuss how to pull Rail data and demo current app development 7/2: We have been given the green light to continue the development of the MVP which will include the Instructions & Entry and Totals tabs 7/1: Initiative will be placed On Hold as Freight prioritizes resources needed for the separation 7/1: Demo on Instructions & Entry Tab and Totals functionality to be held 7/1. Tab will have 10 days of data; plan to have 20 days on data for further testing with the FE team (After July 7th) 6/24: Included additional FEs for test; image roles requests are complete. Development still in progress. 6/17: Development still in progress. Image roles request complete for test environment 6/10: Development still in progress. Demo on Instructions/entry tab targeted to begin June 10. Will work with Barry Wells to get test image roles:fxf_salary_staffing_basicuser_test_app3541436 6/3: Aditya is still working on the Instructions & Entry tab and should be able to demo the tab next week (June 10). It won't have the connections to the backend but at least we will be able to take a look. 5/27: Sys Dev is currently review the MVP queries (Jelena Dostic - back end dev) and Landing Page development has begun (Aditya - front end dev). Will confirm milestones/timeline on 5/27. Jelena will have some data ready on 6/2 5/20: MVP migration in progress; weekly Tuesday calls have been schedule with Sys Dev to discuss progress; Timeline/Tasks TBD 5/12: Meeting held with developer to begin MVP migration. Weekly calls held on Tuesdays 12 CST. 5/6: MVP migration to web app will begin on May 9th. 4/29: Sys Dev meeting scheuduled for May 9th with developer to begin MVP migration tasks 4/22: no update. Sys Dev meeting is rescheduled for April 29th. Bandwidth still may be pending. TBD Requirements: **** Export Functionality of the Instructions and/Entry Tab and Totals tab**** * Who entered info and date ****Save functionality**** * When user goes back to the form, they can search | K: L5 | Completed | L5 | 2024-02-01 | 2025-09-08
Business Only Initiative: OSD Optimization - Automate On Hand Form & Central | 26240 | 6691 | Business Only Initiative | FXF - P&D | Freight | Kelsey Grape, Christen Daniels | On Track | 8/28- Dashboard is live in the production environment (https://fxfonhandform.freight.fedex.com/all-forms). Development team is working on adding a few improvements, but the tool is fully functional. OSD team is using the tool and have given very positive feedback. 9/19- Development team is adding the requested improvements to the tool. 10/6- OSD team is working on a list of enhancements for a future iteration of the tool. Tool is live and in use every day with no reported issues. | K: L5 | Completed | L5 | 2024-08-26 | 2025-08-15
Business Only Initiative: Stops Per Driver | 82174 | 6802 | Business Only Initiative | FXF - P&D | Freight | Jose Chavez, Camden English | On Track | 4/1/2025: Adjusted future baseline values. Sent out Monthly recap. 3/31/2025: Previous week data has finally updated.Good Monday results. RE-baselined initiative. Based in YTD performance projected savings has decreased by 2 million. 3/24/2025: System update is causing metrics to publish incorrectly. Will continue to monitor and update once data is correct. 3/17/2025: System outage this weekend. Continued to update actuals throughout week. Settled at 103k in savings. 3/10/2025: Good bounce but under goal. 3/3/2025: Monday system outage. Affected overall day performance 2/24/2025: Rough month. Weather event and 2 network outages on seperate Saturdays prevented us from hiting goal for the month. We did finish the month strong. 2/17/2025: 2/13/2025: Monthly recap sent. Below goal perhaps caused by major system outage on Sat Feb 8 that caused a loss of freight visibility. 2/4/2025: sent out monthly recap. Submitted for L5 approval. 1/28/2025: Bounce back in savings from previous weeks. Declines are due to bad weather events. Expect to increase savings as weather improves and volume increases. Typical freight industry seasonality trends. 1/21/2025: There is a decline in savings. This is due to freight seasonality and negative impacts from several weather events around the country. Expect a bounce back in February and March. 1/13/2025: All on track. Begin to review L5 requirements to submit in the next surge sessions. 1/6/2025:On track. No update. 12/30/2024: On Track. This week will prepare December actuals and update accordingly. 12/16/2024: All on track. Savings show there is an increased focus on Monday stops performance. 12/9/2024: First Monday in December had the highest savings since the start of the initiative. 12/2/2024: On track, we have seen improvement, December may be challenging with the holidays and ADS decrease. Will continue to monitor. 11/26/2024: On Track results improved week over week. 11/21/2024: On track. results improved over previous Monday. Uploaded new SPD Drive Initiatives Results v2, which will serve as the most up to date results tracker. 11/14/ 2024: On track, with more push towards the tracking of financials. Tracking and performance recaps being sent weekly. Have been approved for L4 | K: L5 | Completed | L5 | 2024-08-19 | 2024-10-07
Business Only Initiative: Yard Time Reduction | 82172 | 7049 | Business Only Initiative | FXF - P&D | Freight | Camden English, Jose Chavez | On Track | Initiative rolled out as expected. After financial re-evaluation, we are ontrack to meet monthly goals. The wew goals implimented across the company is the driving force of the completion of the initiative. | K: L5 | Completed | L5 | 2024-07-23 | 2025-01-31
Business Only Initiative: Cartage Compliance & Cost Savings | 87607 | 7129 | Business Only Initiative | FXF - P&D | Freight | Jeff Jacobs, David Gedlinske | On Track | WE 7/3/2025 - Initiative will be placed "on hold" in preparation for separation of FXF from FEC. No timeline established for continuance of work at this time. Current state - business processes + related documentation officially updated. Tracking dashboard in progress (automated compilation of file used by Transportation for compliance to keyword/status coding in progress - Haritha Appojalla assigned), will be paused. Work will continue when personnel free up from separation planning and other initiative work. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-11-01 | 2025-07-31
Business Only Initiative: Target Accounts | 87172 | 7132 | Business Only Initiative | FXF - P&D | Freight | Travis Winston, David Gedlinske | On Track | WE 8/23/2024 - Initiative being changed to "On Hold" status. The effort is pivoting from DRIVE rigor to a collaborative push by Service Center Management and Sales reps in the field to give focused attention to top 25 markets within company, targeting growth of fields sales customer accounts instead of an all-up companywide initiative. (8/20/2024) - Also reached out to Sankeerth for financial information used in the target sales account dashboard. He advised he thought the imitative was cancelled. I have told him its not cancelled but on hold so we may need the financials. The measure of this initiative is ADS and revenue growth. James Wright and James Stith advised we should use June 2024 as the baseline figures and referred me to Sankeerth for financial information. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FXF PD Stop Sequencing | 72740 | 7520 | Business w/ Tech Initiative | FXF - P&D | Freight | Sara Bailey, David Gedlinske, Christen Daniels | Some Issues | 7.21.25 SCO PEL canceled to align with Platforms. Pausing initiative at end of L2 stage. When picked back up, will be ready for PEL greenlights and L3 surge. 7.15.25 Removed from Platforms PEL by IT leadership due to intiative being paused. Waiting on next steps from platform SCO PEL scheduled for 7/17. 7.8.25 PEL meetings moved to 7/17 SCO and 7/15 Platform Will pause after greenlight approval 6.30.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment, entanglement Waiting on Platform costing. Ready for PEL greenlight once that is received. SCO PEL Greenlight meeting moved to 7/10 Epic #1 Working on ARB reviews and finalizing solutions Epic #2 Recieved final approvals for MSA. Now will submit to legal for review Epic #3 Requested SA. In backlog waiting allocation 6.24.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment, entanglement Still waiting on Platform costing and greenligh to move project to L3 SCO PEL Greenlight meeting 7/3 Epic #1 Working on ARB reviews and finalizing solutions Epic #2 Recieved final approvals for MSA. Now will submit to legal for review Epic #3 Requested SA. In backlog waiting allocation 6.16.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment, entanglement Still waiting on Platform costing to move project to L3 Epic #1 Working on ARB review scheduling and finalizing solution Epic #2 Pending final 2 approvals for MSA to then submit to legal for approval Epic #3 Requested SA 6.10.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment, entanglement MSA request started. Going through approvals to get to Finance for final approval. RS cannot start work until MSA/SOW is complete Platform costing engaged. Waiting for final costing estimate. Epic #1 nearing completion of solution and app architecture. ARB review needed once completed. Epic #2 now all RS responsibility Epic #3 needs RS engagement. Working on getting SA assigned 6.4.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment, entanglement, no response from Platform, and SOW for RS Platform costing request sent week of 4/17. No response from Platform on multiple emails and messages sent since. MSA request submitted to Legal. Need SOW and funding for RS to begin any work on UI and Epic #2 Epic #1 Solution and app architecture continues 5.28.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment and entanglement Waiting on costing estimate from Platform Portfolio. David and Sara continue to reach out for progress. This is needed for greenlight in L2 to move to L3. Angela Curtis out of office 5/19-6/2 Epic #1 Solution and App architecture continues Waiting on Eric Grecco decision on resourcing, work assignments, contract, SOW, etc. Review of GUI requirements completed with RS. Ready to begin when funded. 5.19.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment and entanglement Waiting on costing estimate from Platform Portfolio. David and Sara continue to reach out for progress. This is needed for greenlight in L2 to move to L3. Epic #1 Solution and App architecture continues RS engagement - waiting on Eric Grecco decision on resourcing, work assignments, contract, etc. Larry at RS and Steven Payne working on this. Weekly meetings set up to start working through GUI requirements Epic #2 Potentially all RS work. Waiting on Grecco decisions 5.6.25 Status remains at some issues due to the need for an IT Manager/FTE Assignment and entanglement Waiting on costing estimate from Platform Portfolio. David and Sara continue to reach out for progress. This is needed for greenlight in L2 to move to L3. Completed data cleanup for Planview and Agility tooling changes Epic #1 Solution and App architecture continues Epic #2 Continuing solutions architecture 4.29.25 Status remains at some issues due to the need for an IT Manager/FT | E: L2 | On Hold | L2 | 2025-02-04 | 2027-07-01
Business Only Initiative: OT Reduction |  | 80138 | Business Only Initiative | FXF - P&D | Freight | Mark Madson, Noelle Dallas | On Track | Field engineers have all selected two centers to focus on and reduce overtime. Finance is completing their analysis and should be done this week or early next week. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-11-19 | 2025-05-07
Business Only Initiative: No Pro Stop Reduction |  | 80149 | Business Only Initiative | FXF - P&D | Freight | Karl Olsheski, David Gedlinske | On Track | 7/1/25 - Project set on hold due to freeing up system resources for spin off. Files saved to the project for future development. 3/13/25 - L3 surged, working through feedback requested to submit to SL3. 3/4/25 - Green light recieved from CCH review. Met with Laurie Oswalt to review submitting to L3. Set milestone plan and ramp up period for the project. 2/10/25 - Meeting with Micheal Anderson about ICS data that comes into ACCOPS from customers. With the spinoff approaching in 18months the ability to correct this issue from the front end won't be possible. Plan is to give operations data and best practices to manage the ICS screen to avoid Check No Freight reason codes. This will be handled by contacting customers and ability to find information about customer before send a driver for a pickup. Sent updates to Karen with status to move from CCH to L3 surge. Upated finaical data with narrowed project scope and project description. Will be working with Doug C. to gather a team to speed up the initative to get to all operators and get clear feedback to process being developed. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2025-03-17 | 2025-10-27
Business w/ Tech Initiative: RFID Automated Delivery |  | 84485 | Business w/ Tech Initiative | FXF - P&D | Freight | Patrick Duane, Jacob Maher | Some Issues | 2/25/25: Initiative placed on hold due to low prioritization. 2/7/25: Submitting new proposal in Supply Chain portfolio after it was determined that Dataworks will not be needed. 1/15/25: Proposal approved by IT owner, moving on to next steps. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: GAMDs and timezones |  | 87989 | Business Only Initiative | FXF - P&D | Freight | Christen Daniels, David Gedlinske | On Track | Initiative assessment revealed little value in updating GAMD eligibility on zips that are in a different time zone than delivering Service Center. Assessment revealed value in increasing the reach of Guaranteed product through complete zip code review and additional Guaranteed service product(s). Summary Presentation and Data have been uploaded to the initiative. Place initiative on hold until after FedEx Freight separation from FedEx Corporation. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Increase FXF Weight per Shipment |  | 113539 | Business Only Initiative | FXF - Revenue Quality | Freight | Brienne Parker, Vickie R. Odom | On Track | 6/25/2025: Iniative to be cancelled per Heather Rorie and Pod Lead Curtis Long. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Modernized FMCSA Imaging / Database | 26283 | 8161 | Business w/ Tech Initiative | FXF - Safety | Freight | Sharina McBee, Wayne Bailey | On Track | 6-10-25 QA Review for SL3 has been completed / approved by Kelli Ostertag. 4/17 Looking to get greenlit by the portfolios for L3 approval. Working with both EDM and RCC teams to move this forward. 2/5/25 Set to SURGE for L3. IT partners are requesting we move forward in DRIVE L gates. 7/29/24 Need architecture in IT for the platform build | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-11-07 | 2026-04-30
Business Only Initiative: [Enabler] Modernize Comms in Safety & Fleet Mtnc. | 35225 | 8162 | Business Only Initiative | FXF - Safety | Freight | Sharina McBee, Wayne Bailey | On Track | All targeted education development completed. | K: L5 | Completed | L5 | 2023-10-09 | 2024-12-31
Business w/ Tech Initiative: Safety Awards | 72093 | 8163 | Business w/ Tech Initiative | FXF - Safety | Freight | Sharina McBee, Wayne Bailey | Some Issues | 9/2 Exusia trying to access the storage container but having issues. Ops Research to create output files as a backup. 4/17 New code for Safety Awards is on track. Need change to ACCOPS screen prioritized by IT. Without this in place, the Safety awards code risks picking up incorrect data. Working with Jessie to get prioritization. 3/19 Awaiting prioritization within the RCC team for ACCOPS changes. From Freight team, should have first run of report on 3/21. 1/12/26 Cancelling UKG issue fixed. Any additional fixes will need to have a contract with vendor Exusia to make corrections. | E: L2 | Cancelled | L2 | 2024-04-29 | 2025-10-31
Business Only Initiative: Blindspotter Technology | 86108 | 8164 | Business Only Initiative | FXF - Safety | Freight | Sharina McBee, Wayne Bailey | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 10/17 3,140 installs complete 9/12 2,930 installs complete. FM stating that the installs will pick up. 9/5 2,918 installs completed 8/29 2,895 installs pushing FM to push the vendor. We fell short on installs this month. 8/1 2,847 installs completed. 7/11 2,730 installs completed. 5/23 2,384 installed 4/25 2,089 installed. 3/19 on track with installations 2/28 1,584 units installed. 1//31 1,407 units have been installed. 11/18 487 units have been installed. 11/19 535 units installed | I: L4 | Cancelled | TEMP L4 - Enter L4 | 2024-06-03 | 2025-11-18
Business w/ Tech Initiative: Riskonnect | 90203 | 8165 | Business w/ Tech Initiative | FXF - Safety | Freight | Sharina McBee, Wayne Bailey | On Track | 2/27 - requesting cancellation. project has completed all milestones, freight moving out of planview to wave 2/3 Riskonnect Intake completed full scale launch 9/5 Gallagher Bassett and Sedgick have accespted extracts. IT has begun standing up API. Final OSHA review changes submitted to Riskonnect. 9/2 IT has received user id and security information from Riskonnect. Can start smoke testing this week. 4/24 Team is working through data points that will be sent to FXF via API. 4/17 Contract executed. Intake form is complete, team is finalizing extract that is sent to Sedwick for Work Comp. Working through email routing for incidents. 3/19 redlined contract received back from Legal and sent to Riskonnect. 3/3/25 contract is still with Legal. This is causing some of the milestones to be late to start or late to end. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2024-12-16 | 2026-01-13
Business w/ Tech Initiative: WheelRight |  | 84493 | Business w/ Tech Initiative | FXF - Safety | Freight | Sharina McBee, Gann Brooks | On Track | 9/17 Per leadership, we will not be pursuing at this time - cancel. 9/2 still working through contract. DP made a call to Snider to assist in alignment. 7/28/25 Snider to return contrct to Legal this week. 6/5/25 QA Review for SL3 completed by Kelli Ostertag - approved. 6/3 went through PEL, received approval. 5/29 Need Greenlight from Platform Portfolio. PEL scheduled for 6/3 5/5/25 Contract moving through Encore. Need Greenlight from Portfolio to move forward. 4/17/25 working on entering contract into Encore. 3/2025 switched to an enabler via PDSM ticket 2/5 haven't received WheelRight back into queue since SURGE on 11/13. Working to get landlord approval for installation in ground. Meeting with Fiance on 11/8. Scheduled for L2 SURGE on 11/13. | G: L3 | Cancelled | L3 | 2025-02-07 | 2026-08-31
Business Only Initiative: Grill Guards |  | 84500 | Business Only Initiative | FXF - Safety | Freight | Sharina McBee | On Track | 1/19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 8/5 FM reporting installs complete. 7/9 116 of 165 installs completed in FSR. 4/17 Top locations have been identified. Gathering equipment count for MSP, GRB, BUF, SFL, GJN and also gathering equipment count for high hit lanes in DEN and NHS. 3/19 team to meet this week to determine where to install next. 3/3 tracking animal strikes guards vs no guard costing. Ops Research to have new heat map and top centers for animal strikes completed this coming week. | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-11-11 | 2028-08-15
Business Only Initiative: FXF Preventable Accident Reduction |  | 87635 | Business Only Initiative | FXF - Safety | Freight | Sharina McBee | On Track | 1.19/2026: INC033683598 - FedEx Freight is preparing to move away from Planview. We will do this in stages. First approach is to put the L4's and L5's where the work is completed - in cancellation status. I am the Freight Domain PM and have full support from Domain Lead. Please status the below initiatives to "CANCELLATION" - and the Domain Lead will approve in Planview. 5/22 Updated forecast to FY28 5/13 Met with Finance, confirme we were good to move to L4, possibly ask for L5 during the SURGE as we have tracked 5 months of actuals. 2.2% reduction overall. Met 5% in April. 4/17 Team following action plans to drive down preventable accidents. 3/19/25 Team continues to track and investigate top opportunities. 3/3/25 Team continues to track and investigate top opportunities. | K: L5 | Cancelled | TEMP L5 - Enter L5 | 2024-06-03 | 2025-05-30
Business Only Initiative: FXF Yard Incident Reduction |  | 87638 | Business Only Initiative | FXF - Safety | Freight | Sharina McBee | On Track | 7/9 Money Step evidence uploaded. 4/23 Extended money step until Dec 31, 2025. Initiative is not showing improvement as we would like. Asked Laurie if can reforecast to FY25 values starting Jun 1st got approval. 4/17 Field Safety pushing on yard incident reduction. 3/19/25 Team continues to track and investigate top opportunities. 3/3/25 Team continues to track and investigate top opportunities. | K: L5 | Completed | L5 | 2024-09-11 | 2025-12-31
Business Only Initiative: FXFC/FXCC Safety Metrics |  | 98723 | Business Only Initiative | FXF - Safety | Freight | Sharina McBee | On Track | 6/30 email from Trevor stating to put on hold. 6-20-25 QA Review performed for SL2, by Kelli Ostertag - approved. 6.20.25 able to gather tables for the FXFC metrics | E: L2 | On Hold | L2
Business Only Initiative: Vacation Bidding Tool |  | 104470 | Business Only Initiative | FXF - Safety | Freight | Kelsey Grape | On Track | 7/24- Matthew is close to finishing the tool. He has 1.5 more weeks with us until his internship ends. He is working with Haritha in OR to hand over the tool once he's done. On track to have a functioning tool by the end of his internship and full functionality for the network by December. 9/19- Vikas is working on updating the tool. He got in contact with HR to get access to roster data and has rebuilt the microsoft form for us to use. 10/14- Demo of the tool looks good. Working on adding vacation accrual and multi-round bidding. On track for 10/17 completion 10/17- Tool development is complete. We are testing in WBA on Monday. 10/28- Testing in WBA and FTW complete. Vikas will analyze the results tomorrow. Working on educational materials and adding accruals data to the tool. 11/3- Pilot launch in MEM, NWA, AUR, NEM, NAT, PIT, BHM, FRO through 11/14. Full launch to the network planned after these pilot centers are done. 11/6- Testing discovered need to add visibility for employees to make informed bid decisions. Tool not usable in current state. Meeting tomorrow to discuss options, with potential need to pivot for this bidding cycle. 12/19- New developers have been added on to create a web tool. The new web tool will include features deemed necessary but not possible with the microsoft form. 4/1/26- Canceling to recreate in WAVE | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2025-05-02 | 2026-03-10
Business Only Initiative: Single Trailer Dispatch Reduction | 81743 | 6981 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Daniel Vardon, Connor Soboslay | On Track | SANCOD Single Trailer Dispatch screen completed and shared with field linehaul engineers and transportation leadership. Communication completed for RVPs and working to finish combining reporting to encompass weekend initiative as well. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-11 | 2025-06-26
Business w/ Tech Initiative: Overflow / Reload Rules | 542 | 8104 | Business w/ Tech Initiative | FXG LHN - Dispatch Rules | Linehaul | Mark Johnson, Kyle Hahn | On Track | 12/09/2024: Updated November Actual Results 11/12/2024: Updated October Actual results 6/17/2024: Presented on the OB Load planning application during the monthly Routing and Dock (RAD) Priorities Call 6/12/2024: Completed all training classed on the OB Load Planning application with the engineering support staff. 6/4/2024: Set-up four training calls with the Field Engineers, DM's and Regional Engineers on 6/6, 6/7, 6/11 and 6/12 4/12/2024: Updated Milestones to move money step to 6/1/2024 to allow for adequate training of the field once the dashboard is complete. 11/05: Focusing on aligning with Dispatch Rules Initiative on rolling out cheat sheet guidance. 10/28: On track, documents have been updated to proceed to L3 pending final approval 10/21: On track, will review in SURGE meeting today for feedback. | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-01 | 2025-11-28
Business Only Initiative: LH Reconciliation | 69424 | 8116 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Kay Subosits, Adam Baker | On Track |  | K: L5 | Completed | L5 | 2024-01-15 | 2025-05-30
Business Only Initiative: Low Volume Directs | 534 | 8127 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Clint Damman, Kyle Hahn | On Track |  | K: L5 | Completed | L5 | 2022-08-23 | 2023-07-04
Business Only Initiative: DROP/RED: Hub Area | 535 | 8138 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Clint Damman, Kyle Hahn | On Track |  | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-01 | 2023-06-30
Business Only Initiative: Redcell Short Shuttle | 1033 | 8802 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Jon Warner, Clint Damman | On Track | Week of 8/19/2024 *Currently working to get everything ready for this initiative to move to L5 status. L5 presurge call is scheduled for Thursday 8/22/2024. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-06-29 | 2024-04-26
Business Only Initiative: DROP/RED: Mainline | 1762 | 8880 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Clint Damman, Kyle Hahn | On Track |  | K: L5 | Active | TEMP L5 - Enter L5 | 2022-11-01 | 2024-05-27
Business Only Initiative: Backhaul Rail Partial Reduction |  | 161554 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Daniel Vardon | On Track | Currently moving through the L Gates on time. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Transit Changes for Dispatch Rules |  | 161558 | Business Only Initiative | FXG LHN - Dispatch Rules | Linehaul | Daniel Vardon | On Track | On track. | E: L2 | Active | TEMP L2 - Enter Value Prop
Business Only Initiative: Rental Trailer Efficiency | 546 | 7483 | Business Only Initiative | FXG LHN - Equipment Balance | Linehaul | Denise hanchulak, Michael Zervanos | On Track | Update 7/3/2023: As of today, there are 26 rentals left to be located and returned. We have exceeded our return amount and the cost saving and have been tracking for more than 3 months; therefore, we feel that we can move to L5. Of the 26 rentals that remain, 8 have been dormant between 200-500 days and 18 have been dormant for more than 500 days. We will continue to search for these rental trailers as the total buy out cost is currently $741,500.00. Sending an email to Patrick Duffy asking for L5 approval. DH The status will be communicated by the number of returned trailers reported weekly, bi-weekly, or monthly. | K: L5 | Completed | L5 | 2022-10-07 | 2023-05-31
Business w/ Tech Initiative: Equipment Balance Data Analytics, Visibility, and | 531 | 7494 | Business w/ Tech Initiative | FXG LHN - Equipment Balance | Linehaul | Earl Woodyard, Rachel Vigna | On Track | 4/30/2025 FY26 Rebaseline And Reforecast Completed 2022-10-31 Initiative is on track. 2022-11-7 Initiative is on track. 11/17/2022 - Milestone #1468 expected to be delayed due to an extend vacation from one of the Dataworks Data Scientists, risk has been identified, since many of the milestones are occurring during the holiday season - Need to identify systems support and confirm Azure rates needed to support the dashboard for long term use 11/23/2022 - DW is working to finish Milestone #1468 to define trip logic and domicile - All other milestones are on track 12/12022 - DW is working to finish Milestone #1468 to define trip logic and domicile - First iteration of the dashboard is tentatively planned for week of 12/12 - All other milestones are on track 1/6/2023 Milestone Status #1573 – Tech milestone will finish when pilot is released #1575 – Tech milestone will finish when pilot is released #5684 – On hold #1576 – Tech milestone will finish when pilot is released #5544 – The Dashboard is not complete yet, so I cannot finish this milestone. #5685 – In Progress, I am creating a decision tree; however, we do not have a clear understanding of responsibility and accountability for each imbalance problem. 1/9/2023 Late Milestone Status: #1573, #1575, #1576 - These are technology milestones, which are still progressing. They will be completed, once the dashboard moves to pilot stage. #5684 - Compliance standards for data are still being explored. I have a meeting with Linehaul Engineering to discuss in late-January 1/13/2023 - Initiative is on track - Working with Dataworks on dashboard visualizations before pilot starts - Identifying next steps for the Dashboard development with the Dataworks team 1/20/2023 - Initiative is on track - Dataworks team to enhance the dashboard visuals - User engagement sessions are going well, feedback will be assessed and implemented into the dashboard 1/27/2023 - Initiative is on track - The dashboard survey has been finalized and will be released today along with the permanent image role - Dataworks team is working to enhance the dashboard based on user feedback - the Equipment Balance Playbook is entering round 3 of draft phase, will continue to review next week - Need to define escalation framework to include within the equipment balance playbook 2/2/2023 - Initiative is on track - Meeting with End Users and planning dashboard changes based on feedback - Escalation framework will be included into the playbook once the pilots have ended and the feedback has been assessed for all pod initiative 2/9/2023 - Looking into Purchased Transportation Rate ingestion problem with Dataworks and Ground, some fields are missing in the Dataworks data - Dataworks is working on enhancing meet point, customer spot, and date analysis within the the dashboard. - Enhancing the Equipment Balance Playbook based on feedback. 2/17/2023 - meet point and customer logic has been enhanced, working on improving user interface ahead of next dashboard update - meeting with FXG University to make the Equipment Balance Playbook look professional and discuss next steps for legal review 2/24/2023 - Dashboard interface was finalized for the update, pushing update to production process has started - Communications and a new set of engagement sessions will be set out once production has been completed 3/3/2023 - Update for dashboard was successful - Second round of user engagement session have been completed, exploring new dashboard interface updates - Equipment Balance Playbook has been submitted for Legal and University review 3/10/23 - Pilot phase has been completed - Equipment Balance Playbook has been reviewed by legal and university, working on finalization - next steps are to create slide decks for managers to educate their teams on Equipment balance and asset control 3/10/23 - Pilot phase has been completed - Equipment Balance Playbook has been reviewed by legal and university, working on fina | K: L5 | Completed | L5 | 2022-08-01 | 2024-07-22
Business w/ Tech Initiative: Purchase/ FXG Trailer Mismatch | 547 | 7505 | Business w/ Tech Initiative | FXG LHN - Equipment Balance | Linehaul | Chris Avitabile, Laurie Nicholson | On Track | Initiative is on track. | K: L5 | Completed | L5 | 2022-10-26 | 2024-09-27
Business Only Initiative: [ENABLER] Field LH Processes, Procedures & Complia | 548 | 7516 | Business Only Initiative | FXG LHN - Equipment Balance | Linehaul | Lynn Kossick, Glenn Pilon | On Track | Surging to L5 | K: L5 | Completed | L5 | 2022-07-01 | 2023-07-31
Business Only Initiative: [Enabler] Right Equipment, Right Lane | 27913 | 9253 | Business Only Initiative | FXG LHN - Equipment Balance | Linehaul | Amy Varner, Earl Woodyard | On Track | **ON HOLD** It was decided to put Right Equipment, Right Lane (RERL) on hold given the current span of focus on FedEx Surface equipment (developing Equipment Strategy within Transportation, analysis of a 53' network within the Dispatch Rules pod, and other efforts). RERL would not add enough independent value to continue the project as it stands today. Once the Equipment Strategy work gains consistent resources, RERL will be revisited to see what changes are necessary to support the overall strategy. **L2 Updates:** 10/7/24: L3 Surge follow-up items are being addressed: Define optimal 53’ utilization on Mainline; Confirm that current target is an incremental step and “no-regret” situation; Re-evaluate 3-months+ milestones; Identify KPIs for markets where business rules are implemented to monitor for negative impact. 9/30/24: Met with all milestone owners on 9/26. Meeting with Field and Transportation SMEs on 10/1 to gain feedback on drafted business rules. 9/23/24: Successful pre-surge meeting on 9/17. L3 surge meeting scheduled for 9/30. L3 date changed from 9/23 to 10/5 to allow time for meeting and any necessary response. 9/16/24: L3 pre-surge meeting scheduled for 9/17. All milestones have been entered into Wave; L3 date was changed from 9/21 (Saturday) to 9/23 (Monday). 9/9/24: Project and pilot milestones have been drafted for review with Pod lead and LHE stakeholders. 8/19/24: Responded to L2 points of feedback: * Safety connection was explored and disconnect events of 28' vessels was targeted for potential improvement * Money Step was modified to address ask for implementation and monitoring compliance * After exploration, it was determined that RERL should not be added as an enabler for Single Trailer Dispatch (#81743, 58949 to be combined) since the majority of savings (77%) tie to Hub Area (out of scope for RERL) and there is no clear enablement of Single Trailer Dispatch KPIs through Right Equip, Right Lane efforts. **L0/L1 Updates:** 7/29/24: Continuing to explore possibility of aligning efforts with #68604 - [ENABLER] CUBEs Improvement. 7/15/24: Determined during 6/28 meeting with Market Tune-up team (75057) that independent pilot market should be utilized. Adds additional step of identifying pilot markets, but work is still on track at this time. February 2024: No savings identified for FY24. Removing from current surge. Foundational work will need to be completed to achieve capital savings in the FY26 trailer purchase. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2024-09-16 | 2025-11-25
Business w/ Tech Initiative: Assessing FedEx system capacity for Vector deploy |  | 165741 | Business w/ Tech Initiative | FXG LHN - Equipment Balance | Linehaul | Thomas Quimby | On Track | #165741 - Assessing FedEx system capacity for Vector deploy will be put on hold. Kyle Q, Matt, and I agreed yesterday that the best course of action at this time is for Matt to explore other potential options to complete the assessment. The initiative will be on hold, rather than cancelled, in case it needs to be resurrected. If the assessment can be realized outside of DRIVE, then the initiative will be cancelled. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Accelerated Excess Property Disposition | 2890 | 8936 | Business Only Initiative | FXG LHN - Facility Infrastructure (Rent & Maint) | Linehaul | Michael Costanzo, Rachel Ryman | On Track | 5/13/24: Initiative is now in L5. Same update as last week. North Savannah, GA still in agreement in place for a 6/30 termination date. It will continue to be tracked as an active property until the agreement is signed. We are currently tracking 13 properties that have been deemed excess. 2 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 40 Properties have been marked as complete. 5/6/24: Met with Drive committee to discuss moving initiative to L5. Attachments were updated and memo was sent. Same update as last week. North Savannah, GA still in agreement in place for a 6/30 termination date. It will continue to be tracked as an active property until the agreement is signed. We are currently tracking 13 properties that have been deemed excess. 2 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 40 Properties have been marked as complete. 4/29/24: Same update as last week. North Savannah, GA has an early termination agreement in place for a 6/30 termination date. It will continue to be tracked as an active property until the agreement is signed. We are currently tracking 13 properties that have been deemed excess. 2 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 40 Properties have been marked as complete. 4/22/24: North Savannah, GA has an early termination agreement in place for a 6/30 termination date. It will continue to be tracked as an active property until the agreement is signed. We are currently tracking 13 properties that have been deemed excess. 2 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 40 Properties have been marked as complete. 4/15/24: Prescott, AZ has been signed and executed for an early termination, saving FedEx a lease obligation of $153,252.40 We are currently tracking 13 properties that have been deemed excess. 2 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 40 Properties have been marked as complete. 4/8/24: No new terminations the fist week of April We are currently tracking 14 properties that have been deemed excess. 3 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 39 Properties have been marked as complete. 4/1/24: 2 properties (Marion, IL and Jonesboro, AR) were successfully negotiated for an early termination. Prescott, AZ is expected to be early terminated in early April as well We are currently tracking 14 properties that have been deemed excess. 3 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 39 Properties have been marked as complete. 3/26/24: Marion, IL has been fully executed for early termination. Expected savings are $37,149.95 3/25/24: Weekly Update is as follows: No new signed Early Terminations. Still working on the early terminations for Prescott, AZ, Jonesboro, AR and Marion, IL. Marion, IL is expected to be fully executed early this week. Weekly Initiative numbers are as follows: We are currently tracking 16 properties that have been deemed excess. 5 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 37 Properties have been marked as complete. 3/18/24: Weekly Update is as follows: No new signed Early Terminations. Still working on the Prescott, AZ early termination, as well as the Jonesboro, AR and Marion, IL Early Terminations. New target terminations by 4/1. Weekly Initiative numbers are as follows: We are currently tracking 16 properties that have been deemed excess. 5 are currently targeted for an Early Termination negotiation. 11 are currently targeted for Sublease. 37 Properties have been marked as complete. 3/11/24: Weekly Update is as follows: No new signed Early Terminations. Still working on the Prescott, AZ early termination, as | K: L5 | Completed | L5 | 2022-11-01 | 2024-06-28
Business Only Initiative: Early Long Term Lease Renewals | 2892 | 8938 | Business Only Initiative | FXG LHN - Facility Infrastructure (Rent & Maint) | Linehaul | Tim Wadas, Rachel Ryman | On Track | Target Properties greater than 200,000 SF with lease expiration dates within 3-5 years for early long-term renewal to leverage a longer term into a lower monthly rent. Week 4/7/25 In L5. Some changes this week as follows: Executed Amendments - 35 Savings to Date: New Total Monthly Rent Savings is $168,135.79 per month over the previous budgeted rent and $175,000 in one-time savings. Total savings over the various terms is $15,286,934.98. Week of 1/6/25 Initiative approved for L5 on 11/12/24. Update will remain the same week over week unless anything changes. Continuing to review ongoing opportunities for early renewals on a case-by-case basis, bundle basis, and quarterly. Negotiations – 0 (Updated to show the current ones that are still active rather than the amount Real Estate started with) CLEARs Submitted - 32 CLEARs Routing - 0 CLEAR Approved - 32 RTPs Submitted - 32 Executed Amendments - 32 Locations removed from program where opportunities don't currently exist for savings - 19 Savings to Date New Total Monthly Rent Savings is $154,481.63 per month over the previous budgeted rent and $175,000 in one-time savings. Total savings over the various terms is $13,648,436.24. Week 11/25/24 Initiative approved for L5 on 11/12/24. Update will remain the same week over week unless anything changes. Continuing to review ongoing opportunities for early renewals on a case-by-case basis, bundle basis, and quarterly. Negotiations – 0 (Updated to show the current ones that are still active rather than the amount Real Estate started with) CLEARs Submitted - 27 CLEARs Routing - 0 CLEAR Approved - 27 RTPs Submitted - 27 Executed Amendments - 27 Locations removed from program where opportunities don't currently exist for savings - 19 Savings to Date New Total Monthly Rent Savings is $149,207.96 per month over the previous budgeted rent and $175,000 in one-time savings. Total savings over the various terms is $13,272,612.24. Week 11/11/24 Surge for L5 completed on 11/8/24. Continuing to review ongoing opportunities for early renewals on a case-by-case basis, bundle basis, and quarterly. Negotiations – 0 (Updated to show the current ones that are still active rather than the amount Real Estate started with) CLEARs Submitted - 27 CLEARs Routing - 0 CLEAR Approved - 27 RTPs Submitted - 27 Executed Amendments - 27 Locations removed from program where opportunities don't currently exist for savings - 19 Savings to Date New Total Monthly Rent Savings is $149,207.96 per month over the previous budgeted rent and $175,000 in one-time savings. Total savings over the various terms is $13,272,612.24. Week 11/4/24 Ready for L5. Pre-surge complete. Surge on 11/8/24. Continuing to review ongoing opportunities for early renewals on a case-by-case basis, bundle basis, and quarterly. Negotiations – 0 (Updated to show the current ones that are still active rather than the amount Real Estate started with) CLEARs Submitted - 27 CLEARs Routing - 0 CLEAR Approved - 27 RTPs Submitted - 27 Executed Amendments - 27 Locations removed from program where opportunities don't currently exist for savings - 19 Savings to Date New Total Monthly Rent Savings is $149,207.96 per month over the previous budgeted rent and $175,000 in one-time savings. Total savings over the various terms is $13,272,612.24. Week 10/28/24 Ready for L5. Negotiations – 0 (Updated to show the current ones that are still active rather than the amount Real Estate started with) CLEARs Submitted - 27 CLEARs Routing - 0 CLEAR Approved - 27 RTPs Submitted - 27 Executed Amendments - 27 Locations removed from program where opportunities don't currently exist for savings - 19 Savings to Date It was discovered that Florida tax was included in the rent value for Tampa, FL old rent (outside of this initiative) when it shouldn’t have been. This was caught in the savings calculations after reaching L4 and removed from the old rent value, reducing the perceived rent savings neg | K: L5 | Completed | L5 | 2022-11-02 | 2024-07-31
Business Only Initiative: Property tax appeals for new facilities | 2925 | 8940 | Business Only Initiative | FXG LHN - Facility Infrastructure (Rent & Maint) | Linehaul | Sharon Laszczynski, Niki Slavkin | On Track | Identify new properties in the network and challenge the first full year property tax assessment. - 5/5/2025 Real Estate recently completed their rebaseling for FY26-28 - 2/25/2025 Real Estate had to submit a help ticket to update the recurring benefits to one-time benefits and remove the forecasted saving ($700k) in FY26 and FY27 in Planview. Real Estate is currently waiting for this update before they have the L5 surge meeting. - 2/4/2025 Real Estate recently had their L5 pre-surge meeting and was approved to move forward for their L5 surge meeting. Real Estate is currently waiting for that meeting to be scheduled. - 1/28/2025 Real Estate has secured an successfull appeal savings in the amount of $650,000 for their Wayne, NJ location. - 1/7/2025 Real Estate is preparing for their L5 pre-surge meeting and looking to schedule that later next week. - 12/30/2024 Real Estate had to reschedule their meeting with their landlord, RMR until after the holidays. Planning to get that on the calendar sometime next week. - 12/20/2024 Real Estate will be reaching out to agreeabe landlords after the holidays to work on any potential appeals. - 12/16/2024 Real Estate is continuing to work towards their L5 date by working with agreeable landlords and the states that have not been historically pursued. - 12/9/2024 Real Estate is meeting with their landlord, RMR to discuss all appeal opportunties within their portfolio. - 12/3/2024 Real Estate is currently working with their landlord on an appeal at their Chino, CA location. - 11/25/2024 Real Estate is on track for L5 and just secured savings of $46,227 for their Norcross GA location. - 11/18/2024 Real Estate had their L4 surge meeting on 11/14 and has been fully approved. Real Estate will now be focused on securing 3 months of mature benefits for their L5 date. - 11/12/2024 Real Estate is working with their Landlord, RMR, on a appeal for Everett, WA in addition to preparing for their L4 surge meeting on 11/14. - 11/4/2024 Real Estate is preparing for their L4 pre-surge meeting on 11/6/2024. - 10/25/2024 Real Estate has defined their L4 deliverables and scheduled their L4 pre-surge meeting. - 10/21/2024 Real Estate is working on their deliverables for L4. - 10/7/2024 Real Estate is in the process of scheduling their pre-surge meeting for next week. - 9/30/2024 Real Estate moved the L4 date of 10/19 to 11/11 due to it being scheduled during the blackout period. - 9/23/2024 Real Estate has completed the final list of appeals and is currently working on L4 preparations. - 9/16/2024 Real Estate had to reschedule a few of the Landlord appeal meetings from last week to this week (9/16) due to scheduling conflicts. - 9/9/2024 Real Estate is meeting with the remaining Landlords from their final list this week which will complete the list of appeals. - 8/30/2024 Real Estate is following up with the landlords where there were appeal opportunities for our final list of 14 properties. - 8/26/2024 Real Estate is currently narrowing in on a few options for what we want our future state to look like. - 8/16/2024 Real Estate is working through the final list of properties, and we have 10 properties being reviewed by the landlord and 4 properties where we are waiting on responses. After this review, Real Estate will be done with the list. - 8/8/2024 Real Estate is meeting tomorrow, 8/9 with the landlord about two possible appeal opportunities for our Brookfield and Hattiesburg locations. - 8/5/2024 Real Estate received feedback from Landlords and were advised no appeal opportunity for four properties. - 7/29/2024 Real Estate is meeting with Setzer, the landlord this week to review two properties potential appeals. - 7/22/2024 Real Estate is reaching out to Landlords on final list to determine if there is an opportunity to appeal. - 7/15/2024 Real Estate has a meeting with CPI Grand Island, the landlord on 7/15 about an opportunity for appeal savings at our Grand Island, NE location. Also, Re | K: L5 | Completed | L5 | 2022-11-08 | 2024-11-11
Business Only Initiative: Expand usage of lower cost Modular Conveyor Equipm | 4707 | 9032 | Business Only Initiative | FXG LHN - Facility Infrastructure (Rent & Maint) | Linehaul | Mike Collins, Larry Schamus | On Track | Week of 11/7/22: - Provided impact and cost savings estimated to move initiative to L1 - Created narrative for business case to prepare for move to L2 - Attended Surge Meeting 11/11/22 - Moved initiative to L2 11/11/22 Week of 11/14/22: - Upper management L2 review and approval - L2 100% approved 11/17/22 afternoon - Discussion & review of milestones, KPIs, and risks with team members Week of 11/21/22: - Completed Milestones - Added to Change Management fields Week of 11/28/22: - Completed KPI's and updated impacts based on feedback - Attended surge meetings - Submitted for L3 approval Week of 12/5/22: - L3 approval received - Capitalization & depreciation review & modification in process - Addressed design questions regarding equipment maintenance and life expectancy comparing mod conveyors to welded Week of 12/12/22: - Capitalization & depreciation review complete - Next step is to update WAVE with finalized capitalization & depreciation numbers Week of 12/19/22: - Working through WAVE process to understand how to record capitalization & depreciation numbers. Waiting for guidance. Week of 12/26/22: - It was agreed to not capture depreciation numbers in the WAVE tool. No financial adjustments will be made at this time. Week of 1/2/23: - Milestones on schedule. Week of 1/9/23: - Completed and submitted KPI details regarding "Data Source(s)" and "Owner of Calculation". - Milestones on schedule. Week of 1/16/23: - Updated status of (2) flagged milestones. - All other milestones on schedule. Week of 1/23/23: - Changed money step from FY23 MH start-up to FY25 MH start-up to be inclusive of all modular conveyor projects across all 3 years. - All FY23 milestones now complete. - Monitoring (5) FY24 projects - received report that (2) FY24 projects were deferred / cancelled. Week of 1/30/23: - Modified FY24 milestone dates for material handling contract execute & material handling start install. These delays are due to incomplete conveyor integrator bids. These delays do not prevent the completion of FY24 projects in time for peak. Week of 2/6/23: - All milestones on schedule. - investigated initiative flag that weekly update had not been provided when in fact it had been provided for the previous week. This week's update provided on 2/9/23. Week of 2/13/23: - Closely tracking next milestone 10717 for FY24 Project Material Handling Contract Executed for 3/3/23, which is still on schedule. - All other milestones on schedule. Week of 2/20/23: - Closely tracking next milestone 10717 for FY24 Project Material Handling Contract Executed for 3/3/23, which is still on schedule. - All other milestones on schedule. Week of 2/27/23: - Modified FY24 milestone dates for material handling contract execute & material handling start install. These delays are due to incomplete conveyor integrator bids which led to delays in executing the material handling contract. Currently the contract is routing for signature and is expected to be complete by March 18. These delays do not prevent the completion of FY24 projects in time for peak. Week of 3/6/23: - The "start" material handling contract execution is now expected to be done this week. Next week's update will confirm completion. - Modified FY24 milestone dates for material handling start install, project certificate of occupancy, and project startup, to line up with modified dates being tracked in the regional tracking sheet owned by Project Engineering. Two FY24 projects, Bozeman & Manitowoc, are being tracked and both are expected to be complete before the November 11, 2023 milestone for FY24 Material Handling Start-up. Week of 3/13/23: - The material handling contract execution milestone has started for the (2) FY24 projects with the execution of the Bozeman MT contract. Once the Manitowoc WI contract has been executed this milestone will be complete. - Completed a review of all FY23, FY24, & FY25 modular conveyor projects that were included with initiative #4707. Recommenda | K: L5 | Completed | L5 | 2022-01-03 | 2023-08-11
Business Only Initiative: Launch new FXG repair facility RFP | 55127 | 9169 | Business Only Initiative | FXG LHN - Facility Infrastructure (Rent & Maint) | Linehaul | Rahul Bajaj, Kyle Mitchell | On Track | Initiative has been updated for FY25 rebaselining | K: L5 | Completed | L5 | 2023-11-21 | 2024-10-11
Business Only Initiative: Purchased Casings for Retread Tires | 25418 | 9536 | Business Only Initiative | FXG LHN - Facility Infrastructure (Rent & Maint) | Linehaul | Kelly Kull, Rachel Ryman | On Track | Figures from Goodyear for March 23 came in this week reporting the total savings for FY23 to be $796,373.12. Bridgestone services five FXG facilities. THey are not on the program at this time. Talks have gained momentum, having received the dealer quotes for purchasing casings meeting FXG standards. | K: L5 | Completed | L5 | 2022-07-12 | 2024-10-31
Business Only Initiative: Maximizing One Way Purchased Transportation Motor | 86220 | 7828 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Amy Zalud, Sharief McDougle | On Track | Week of 2/9 January actuals entered. Overall mileage ran across network down due to no longer dispatching partials. There has also been an increase in Rail utilization. Week of 12/9 November actuals entered. Overall mileage ran across network down due to no longer dispatching partials. Week of 11/18 L5 date will be 8/15/25. This was determined by the data showing the first full month of hitting the 11% PT target will be May 2025. 3 months of 11% data will all of May, June, and July. The July data should be available by August 15th. Week of 11/11 Actuals for October entered. L4 was approved. Update to empty miles due to different way of engineering to process report. Week of 10/28 Surge scheduled for 10/28 for L4 Submitted for L4 approval 10/28 Week of 10/21 Pre Surge scheduled for 10/24 for L4 Money step file attached for LHE PT recommended report. Completed Money Step milestone as well as the Evaluate PT Recommended Report milestone. Week of 10/14 Engineering produced recommended PT report Week of 10/7 Mike Yatsco is still working on tracking acceptable TSP empty miles. Pre Surge scheduled for 10/24. Surge scheduled for 10/28. Expected launch for engineered PT recommended lanes by 10/19 Week of 9/30 Mike Yatsco is still working on tracking acceptable TSP empty miles. I have joined in on ML and Engineering that have been meeting weekly to discuss recommended lanes and how to make it match the network. Adjusting Milestone/L4 Date/Money Step to 11/18 due to Wave blackout period/planview launch. ***Updated back to 10/29 based on Dom and Connor's guidance that we will still be able to complete the surge during the blackout period. Week of 9/23 OCM Milestone Completed 9/23. Money Step Milestone started 9/23. Mike Yatsco is still working on tracking acceptable TSP empty miles. Week of 9/16 Discussing with engineering 9/17 about a possible better way to track acceptable TSP empty miles. Milestone 89316 completed 9/17. Report has been launched. Week of 9/9 First engineering recommended PT lanes report to be sent out 9/9. Meeting with Mainline Planning 9/10 to discuss OCM. Meeting with Mainline Planning and Linehaul Engineering to discuss thoughts/issues on engineering recommended lanes. Milestones 89316, 89317, 89319 started 9/10. Milestone 89315 completed 9/10. Week of 9/2 Savings/Impacts data entered. Week of 8/26 L2 Submitted 8/21 and approved 8/23. L3 submitted 8/23 and approved 8/28. Impacts were updated to show the savings for FY26 of $24.7m. Week of 8/19 Surge meeting set for 8/21 for L2 and L3. More discussions held about not hitting $30m target. Trying to target where it was initially discussed to save $30m. No information finance sent over had the $30m of savings. Sent over all finance information showing original projections and current projections and the differences between both mostly highlighting the 1.3 vs 1.5. Week of 8/12 Pre Surge meeting 8/12 for L2 and L3. Entered L2 information. Some required L3 data locked until approved for L2, but most data is entered. Tracking for on time completion. Surge meeting is scheduled for 8/20. Week of 8/5 Engineering/Finance has sent over savings/projections/impacts. Targeting end of week to get through L1. Officially L1 status 8/7/24. Week of 7/29 Engineering/Finance agree on miles. Now looking through available data of PT miles/MT TSP miles to make sure all data sources match and report the same information accurately. Week of 7/22 Working with Engineering/Finance to discuss tracking savings through percentage or miles. Still discussing best way to show savings. Week of 7/15 Talking with Engineering/Finance to find right data and information to best represent the savings for this initiative accurately. Working through data to advance through L0. Week of 7/8 Initiative 550 will be cancelled and replaced by #86220: Maximizing One Way Purchased Transportation Motor due to 550's current method of only look at replacing TSPs...with 86220 we wi | K: L5 | Active | TEMP L5 - Enter L5 | 2024-06-17 | 2024-10-29
Business Only Initiative: Reducing cancellations for Purchased Transportatio | 76380 | 7829 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Sharief McDougle, Alex Ryan, Scott Shaffer | On Track | 8/28/25: Cancelling initiative is being cancelled -- TONU spend is a cost of doing business and is not directly correlated with cancellations, thus we do not have a reliable metric for measuring savings. June 2025 Rebaselining for FY26. May 2025 PowerBI Draft published for revisions. Presented TONU educational slides to transportation stakeholders. Apr 2025 Completed interviewing all LH planning personnel,identified necessary PowerBI revisions, and revised educational TONU slides. Reconciled cancellation codes as "controllable" vs "non-controllable." Conclusions surrounding FY25 data as we near year's end: Reduced cancellations do not correlate with reduced TONU costs. Mar 2025 Outlined changes needed to the current method of TONU/Cancellation data collection to align current reports. Conducted linehaul specialist and advisor interviews regarding current PT planning practices to identify the TONU generation workflow. The input provided during these meetings provided us a starting point for a new PowerBI to create a "one size fits all" solution for TONU reporting. Identified TONU spend on cancellations previously un-reported in the previoius DRIVE PowerBI. Drafted educational TONU slides for general distribution. Feb 2025 Information gathering surrounding TONU practices, current tools, invoicing, and identify impacted employees. We discovered a new TONU tool was made available to the LH Planning team allowing for easier access to historical TONU data. Comparing the data provided in this new PowerBI and the DRIVE PowerBI utilized for this initative showed a discrenpancy in reporting. Weekly TONU updates begin. Week of 1/31 ML transition complete. Week of 1/15 ML completed Dec data Week of 1/4 Transition to ML Planning started Week of 11/4 IO will transition over to ML Planning starting week of 11/11 Money step is being moved back based on review of ML planning process not complete and overall savings are not showing improvement week of 9/30 Changed the cancellation trends process to review high cancellation lanes every week instead of every 2 weeks. week of 9/23 Continuing to explore the opportunity to improve customer projections and holding customers accountable to more accurate projections. No other updates week of 9/16 No updates week of 9/9 No Updates week of 9/3 We had a kickoff meeting for sub team to look into customer projections to receive better projections throughout the year but especially during large customer events (way-day, prime day..etc). Team will be looking into what the big events are for the year and then assessing next steps. Week of 8/19/24 Reviewing the Mainline planning process to get a grasp on if there are areas of opportunity. Meeting with Routing systems to discuss their market tune-up initiative to see if it could be an enabler Week of 8/12/24 New sub team formed to address customer projections Week of 8/5/24 No Updates Week of 7/29/24 Initiative was moved into L3 and launched cancellation trends process (milestone 84656). Week of 7/15/24 - OCM plan uploaded, Retracted L3 request and pending email review to submit to L3 Week of 7/8/24 Submitted for L3 on 7/3 Working on OCM plan, should be completed by 7/12 Week of 7/1/24 * Need to make updates to KPI's and Impacts which should be done by EOD 7/3 to resubmit for L3 Week of 6/17/24 * Presenting to get approval to move to L2 on 6/18 at 8am * 4 Sub teams addressing proactive cancellation tool and how to build power only schedules and flowing out the PT planning process have started working on solutions. Reactive process looking at PT cancellation trends has met with a goal to launch a pilot of the process late June. * Finance has validated the monthly delivery profile of the impact * Pending L2 approval, team is looking to move to L3 on 6/20 Prior to 6/1/24 - Received cancellation survey responses from current PT Carriers. Team is digging into the data to see if cancellations impact on rates is so | E: L2 | Cancelled | L2 | 2024-03-18 | 2025-10-21
Business Only Initiative: Rail Containerization | 1275 | 8835 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Ed Steklachick, Kimberly Olivito | On Track | Week Ending 6/10 6/5 - Week ending date 6/3 - containerization was 99.3% / estimated $1mil savings. 6/8 - FY23 complete. Q1 66.9% Q2 69.8% Q3 72.1% Q4 99.1% 6/8 - Per the L5 surge, McIntyre asked that we adjust the impacts forecast from June onwards as we're consistently. exceeding the 90% container goal. Forecast has been updated to 99% containerization based on the original L1 FY22 baseline. Week Ending 6/3/23 5/30 - 6/2 - Business Travel 6/5 - Week ending date 5/27 - containerization was 99.6% / estimated $764k savings. 6/5 - Average chassis/container dwell for the network is 8 days with $93.04 of chassis spend per container. Week Ending 5/27/23 5/22 Milestone 17219 marked complete. Dashboard is fully functional. 5/25 - Week ending date 5/20 - containerization was 100% / estimated $917k savings. Week Ending 5/20/23 5/17 - Attending Wave dashboards training. 5/18 - Week ending date 5/13 - containerization was 99.8% / estimated $866k savings. Week Ending 5/13/23 5/8 - April KPI/Impacts updated Week Ending 5/6/23 5/3- Communications update (success message update) -In Legal review. 5/4- Milestone 17219 still in progress. Dashboard implementation in development. 5/4- Week ending date 4/29 - containerization was 99.8% / estimated $790k savings. Week Ending 4/29/23 4/26- Milestone 17219 still in progress. Dashboard implementation in development. 4/26- Week ending date 4/22 - containerization was 99.6% / estimated $406k savings. 4/26- Communications update (success message update) - expected to be approved by management today. Week Ending 4/22/23 4/18- Milestone 17219 still in progress. Initial data query extracted. Now need to incorporate that data into the weekly dashboard. 4/19 - Updated KPI's for March. Left out some key data in the formula on the initial input on 4/6. Week Ending 4/8/23 4/14- Week ending date 4/8 - containerization was 99.6% 4/14- Milestone 17219 still in progress. Week Ending 4/1/23 4/5 - Initiative was called out on investor DRIVE update. 4/6- Week ending date 4/1 - containerization was 99.5% 4/6 - March containerization was 98% with $2.46m savings. 4/6 - Milestone 7426: Marked complete. Week Ending 4/1/23 3/27 - Week ending date 3/11 - containerization was 99.47% 3/27 - Week ending date 3/17 - containerization was 98.91% 3/27 - Week ending date 3/25 - containerization was 99.44% 3/27 - L4 approved 3/28 - L2 & L4 Calculations file updated with dashboard screenshots presented on the finance call on 3/27. 3/28 - Milestone 17219: Logic for reporting was created and appears to be working. Waiting on LHE management to approve. Week Ending 3/18/23 3/14 - Updated KPI/Impacts. More accurate reporting came out for February. Containerization was 74.9%. 3/14 - Week ending 3/11 99.47% containerized. 3/14 - Milestone 14714: Marked complete. 3/14 - Milestone 14715: Marked complete. 3/14 - Milestone 14717: Marked complete. 3/14 - Milestone 14718: Marked complete. 3/16 - Trailer rate request form demonstrated to LH planning and agreed upon. Form is live. This form requires dual approval levels, reasons, estimates cost impact, and sets a firm end date and notification to remove the trailer rate from TMS. This is the checks and balance to maintain 90%+ containerization going forward. These forms are archived for historical purposes, and we expect to be able to add this data to the weekly update. 3/17 - Weekly report logic needs updated. As we've hit 99% containerization, the savings are incorrectly under reporting. (PLACE HOLDER - MEETING UPDATE NOTES) 3/17 - Milestone 17219 - confirmed logic requirements for the report. MO is starting to compile the data. 3/17 - KPI/Impacts updated to reflect savings by removing the 37% container baseline. 3/17 - Initiative approved for L4 Week Ending 3/11/23 3/8 - KPI LH domain meeting 3/9 - L2 & L4 Calculation file has been re-uploaded. The last file was missing the impacts tab that has the calculations for February actuals. 3/9 - Week ending date | K: L5 | Completed | L5 | 2022-10-31 | 2023-05-31
Business Only Initiative: CT Linehaul - Enterprise RFP | 2161 | 8900 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Gaurav Singh, Lee Willhite | On Track |  | K: L5 | Completed | L5 | 2022-12-01 | 2023-05-31
Business w/ Tech Initiative: Intermodal Effectiveness: Purchased Transportation | 544 | 9285 | Business w/ Tech Initiative | FXG LHN - Mode Optimization | Linehaul | Amber Parker, Brian Dineson | On Track | Update as of 3/31/2026 *Returning and repairing peak equipment. _________________________________ Update as of 3/6/2026 * Peak return period/Leased eq. returns prioritized * Reduced urgency from the field due to consecutive weather events and the high likelihood that the equipment will be needed to safely respond to weather-related conditions _________________________________ Update as of 2/6/2026 * The latest invoice includes charges from November through December, during which extensive DPU container plans were in place. * Peak return period/Leased eq. returns prioritized * Weather impacts _________________________________ Update as of 1/5/2026 * Peak equipment volume _________________________________ Update as of 12/9/2025 * Peak ramp up for equipment _________________________________ Update as of 11/5/2025 * October KPI goals were not met. * Early Peak Equipment ramp up * Nothing over 13 days _________________________________ Update as of 9/3/2025 * August KPI goals were not met. * Updated the field training plan for properly managing rental equipment using Blume. * Presented the plan to SoCal stakeholders during PGH Peak Planning meetings. * Planning additional field trainings for high-impact areas ahead of the peak season. _________________________________ Upate as of 8/1/2025 KPI goals missed for July. Reasons why we didn't make goal: Lathrop, CA: 29% baseline not being followed/street turns/miscommunication/change in leadership - action plan in place for better FIFO - should see reduction next month ININ: plan not fully executed due to ISS/dock (accounted for 6% of 8+ day demurrage charges $5,350) _________________________________ Week of 7/1/25 -Updated forecast with new updated goals, 20% better then average for KPI #7561 & KPI #6814 and 40% better then average for IMPACTS #861. _______________________ Week of 6/5/25-6/11/25 -FXF Blume deadline has been established and communicated. June 19, 2025 they FXF Power Bi tool will be retired. -Earl Woodyard added Rental Container Dwell to FY26 LH OKR's. This will add accountability to the field on Rental Container Dwell greater than 8 days of Dwell. This will have a positive effect on this initiative. -Field rollout has been completed -Engagement survey completed -Feedback has been tallied -IT replacement METL/Blume is completed and live _______________________ Week of 5/29/25-6/4/25 -Earl Woodyard added Rental Container Dwell to FY26 LH OKR's. This will add accountability to the field on Rental Container Dwell greater than 8 days of Dwell. This will have a positive effect on this initiative. -Field rollout has been completed -Engagement survey completed -Feedback has been tallied -IT replacement METL/Blume is completed and live _______________________ Week of 5/22/25-5/28/25 -Field rollout has been completed -Engagement survey completed -Feedback has been tallied -IT replacement METL/Blume is completed and live _______________________ Week of 5/15/25-5/21/25 -Field rollout has been completed -Engagement survey completed -Feedback has been tallied -IT replacement METL/Blume is completed and live -Previous Power BI was retired 5/14/2025 _______________________ Week of 5/8/25-5/14/25 -Field rollout has been completed -Engagement survey completed -Feedback has been tallied -IT replacement METL/Blume is completed and live -Previous Power BI will be taken down 5/14/2025 _______________________ Week of 4/24/25-4/30/25 -Field rollout has been completed -Engagement survey sent to all employees who attending training -Feedback has been requested for onsite training locations -IT replacement METL/Blume is completed and live _______________________ Week of 4/17/25-4/23/25 -Field Virtual training finishing this week, All Locations have been trained to date thi final week is for make -up calls -Engagement survey sent to all employees who attending training -Feedback has been requested for onsite training locations -Waiting on IT for replacement METL/Blume solution to | I: L4 | Active | TEMP L4 - Enter L4 | 2022-12-01 | 2025-07-02
Business Only Initiative: Maximizing Intermodal | 540 | 9296 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Ed Steklachick, Sharief McDougle | On Track | Week Ending 10/1: Rail Miles 13.3% Week Ending 9/3: Rail Miles 13% Week Ending 8/27: Rail Miles 12.7% Week Ending 8/20: Rail Miles 11.9% Week Ending 8/13: Rail miles 12.3% Week Ending 8/6: Rail Miles 13.3% Week Ending 7/29: Rail Miles 13.6% Week Ending 7/23: Rail Miles 13.3% Week Ending 7/16: Rail Miles 13.0% Week Ending 7/9: Rail Miles 13.6% Week Ending 7/2: Rail Miles 13.4% Week Ending 6/25: Rail Miles 13.1% Week Ending 6/18: Rail Miles 13.7% Week Ending 6/11: Rail Miles 13.9% Week Ending 6/4: Rail Miles 14.8% Week Ending 5/21: Rail Miles 13.6% Week Ending 4/30: Rail Miles 9.2% Week Ending 4/30: Rail Miles 12.5% Week Ending 4/23: Rail Miles 11.7% Week Ending 4/16: Rail Miles 11% Week Ending 4/9: Rail Miles 10.6% Week Ending 4/2: Rail Miles 9.7% Week Ending 3/26: Rail Miles 10.8% Week Ending 3/19: Rail Miles 10.9% Week Ending 3/12: Rail Miles 10.2% Week Ending 3/5: Rail Miles 9.2% Week Ending 2/27: Rail Miles 11.1% Week Ending 2/20: Rail Miles 10.0% Week Ending 2/13: Rail Miles 10.4% Week Ending 2/6: Rail Miles 10.8% Week Ending 1/30: Rail Miles 10.4% Week Ending 1/23: Pre-Surge Meeting held 1/5; Surge Meeting held 1/22/24. Approval to submit for L4 granted. Rail Miles 11.2% Week Ending 1/16: Rail Miles 11.6% Week Ending 1/9: Rail Miles 13.1% Week Ending 1/2: Rail Miles 13.5% Week Ending 12/19: Rail Miles 15.9% Week Ending 12/12: Rail Miles 16.9% Week Ending 12/5: Rail Miles 14.9% Week Ending 11/28: Rail Miles 13.7% Week Ending 11/21: Rail Miles 12.1% Week Ending 11/14: Rail Miles 11.5% Week Ending 11/7: Rail Miles 12% Week Ending 10/31: Rail Miles 11.8% Week Ending 10/24: Rail Miles 12.1% Week Ending 10/17: Rail Miles 11.7% Week Ending 10/10: Rail Miles 11.5% Week Ending 10/3: Rail Miles 11.7% Week Ending 9/26: Rail Miles 12.4% Week Ending 9/19: Rail Miles 11.7% Week Ending 9/12: Rail Miles 12.3% Week Ending 9/8: Rail Miles 10.7% Week Ending 8/26: Money Step may be impacted by delay in launch of Blume usage by PGH rail team. Field usage will not impact money step. Rail miles 12.5% Week Ending 8/19: Rail Miles 12.5% working with finance for reforecast. Week Ending 8/12: Rail Miles 13.2% Week Ending 8/5: Rail Miles Percent 13.7% Week Ending 7/29: Rail Miles Percent 13.9% Week Ending 7/22: Rail Miles Percent 12.2% Week Ending 7/15 Milestone 5072: Had working session with PGH linehaul planning in regards the dashboards. Reinforced the process we have been developing and documenting and answered all questions the team had. Rail Miles Percent: 12.1% Week Ending 7/8 Rail Miles Percent: 11.4% Week Ending 7/1 Milestone 5064: With rail % continuing to rise (12.7%), feedback loop is working effectively and will be documented. Week Ending 6/10 Milestone 4960: Rail Planning process has been integrated into linehaul planning educational playbook for planning volume, milestone has been marked complete. Milestone 5075: Marked complete, as we have seen over a month's worth of week over week improvement after having linehaul planning utilize the tools KPI/Impacts/Attachment 6 updated with May updates. Week Ending 6/3 Working with CMO in reviewing educational materials created for Network Planning Reviewing rail equipment balance resources and potential collaboration with FXF drayage Milestone 5071 - All requirements for adjusting the baseline plan based on KPIs have been met. Marking this milestone complete ahead of schedule Milestone 4960 - Working with mainline planning to integrate process into larger process initiative Week Ending 5/27 Milestone 5066 - Next steps for KPI containing dashboards have begun, this milestone is now marked complete Milestone 28663 - Measured compliance to documented rail plan; at beginning of newly launched plan in April, the plan attainment was in the low 50% range. As of this week, we have reached 91% attainment with the continuous refinement of the plan, using the Rail Baseline tool. This Milestone is marked complete. Milestone 50 | I: L4 | Active | TEMP L4 - Enter L4 | 2022-11-03 | 2024-05-31
Business Only Initiative: PT Motor Effectiveness: Purchased Transportation B | 545 | 9307 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Darren Beck, Sharief McDougle | On Track | -Moving forward update is - "Initiative in L5, on track" Week of 08/07-08/14/24: -Transitioning initiative to new IO, waiting on Wave Admins to Change IO to Darren Beck and reinstate his WAVE access. -@Jay, any update on progress of request? ______________________________ Week of 06/06-06/12/24: Entered in May financials - -$2.993M in Savings on goal of $3.010M -$2.292 Rate/Mile on goal of $2.290 -79.223% compliance on actual PT miles vs planned awarded PT miles on goal of 80% _________________________ Week of 05/23-05/29/24: 05/30/24: Updated forecast on impacts since last May was using FY22 vs FY23 baseline. Dropped it from $4.2M to $3M ________________________ Week of 05/16-05/22/24: -L5 on track -Per discussions with Patrick Duffy, Dave McIntyre, and Adam on how to move forward with the baseline information for the savings calculations, it was decided to keep the change in DAT due to Market impacts the same as last year for consistency. Updated the savings information from $555,676 to $2.98M in wave. Attached the email discussions in Wave Attachments as well for history of the decision. __________________________________ Week of 05/09/24-05/15/24: -PT Business team entered actuals for savings while Kristen was OOO -With the baseline still being compared to Fy22 the drop in DAT from Jan2022 and Jan2024 (new bid year) was down 27.34% -With the new bid year starting and the new DAT % drop, the savings for April utilizing the Jaggaer tools was $555,676 -Cost/Mile came in at $2.282 on a plan of $2.344 -PT Mileage compliance to plan was 86.8% (actual miles vs planned bid miles) ___________________________________ Week of 05/02/24-05/08/24: -PT business team to assist with actual reporting while Kristen is OOO this week - Pod Lead (Zak) has details on who is doing what. ______________________________ Week of 04/25-05/01/24: -Working with Finance this week to finalize new actuals tracker for the new bid year with April results. -No other updates, initiative now in L5 _______________________________________ 04/18/24-04/24/24: -Business working to finalize Year Round Bid -Working with Business to create new tracking/reporting file for the new bid year starting with April results. ____________________________________ Week of 04/11-04/17/24: -Received approval for L5 on Thursday, 04/11 -Also received confirmation from InfoSec that our Exemption we had for the delay in SSO integration has been closed as well since SSO has fully been integrated. ____________________________________ Week of 04/04/24-04/10/24: -Entered March results into Wave 04/08 (1) PT Bid Mileage compliance (Actual vs Planned) is 78.91% - slightly under goal of 80% (2) Savings of $2.826M on a forecasted goal of $2.511M (3) Cost/Mile of $2.351/mile on a forecasted goal of $2.385/mile -Business waiting a few more validations from users to ensure everyone can enter through SSO without issue, then we will close the last milestone and submit for L5 approval as planned during the L5 surge meeting. -04/10 - Business just confirmed that SSO integration is fully complete, all users have been validated and are able to enter Jaggaer through Purple ID. Closed milestone and will be sending out the L5 approval email request today. -04/11 Leadership approved summary email for Neil and Patrick, submitting for L5 approval today. ________________________________ Week of 03/27-04/03/24: -Jaggaer completed SSO integration Monday, April 1st -Business working through the validation with all users now to confirm everything is working as expected with ability to login successfully with SSO -Once validation is complete (expected this week), then SSO milestone can be completed and L5 approval emails will be distributed per the L5 Surge meeting conversation. _____________________________ Week of 03/21/24 - 03/27/24: -Jaggaer scheduled to complete SSO integration on Mon, 03/25 - Tue, 03/26 -Once complete and verified, Kristen will send out the L5 email su | K: L5 | Completed | L5 | 2022-10-25 | 2024-02-29
Business Only Initiative: FXE CT Linehaul FY25 Bid | 73558 | 9426 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Gaurav Singh, Lee Willhite | On Track | The new carries are performing well on the lanes and we did not have many replacement of the carriers on the lanes | K: L5 | Completed | L5 | 2024-03-04 | 2024-08-30
Business w/ Tech Initiative: Purchased Transportation Request Application |  | 90397 | Business w/ Tech Initiative | FXG LHN - Mode Optimization | Linehaul | Sharief McDougle, Mary Howell | On Track | On hold until new opportunity statement for larger scope is crafted. Will likely cancel and resubmit a new initiative. Adding IO | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: EMR CFT - CT Supply Chain Increase SUM |  | 131676 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Michael A. Andrejco | On Track | This initiative was created in support of Enterprise Margin Recovery and was considered a placeholder. | C: L1 | Cancelled | L1
Business Only Initiative: EMR CFT - CT Linehaul & Rail - US Increase SUM |  | 131679 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Michael A. Andrejco | On Track | This initiative was created in support of Enterprise Margin Recovery and was considered a placeholder. | C: L1 | Cancelled | L1
Business Only Initiative: Reduce PT Adhoc Spend |  | 132376 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Sharief McDougle | On Track | **11/12/25** Soft benefits initiative -- best managed outside of DRIVE L1 information populated, ready for SL2 | E: L2 | Cancelled | L2 | 2025-09-29 | 2026-02-06
Business Only Initiative: Reduce High MT Percentage Tractors run |  | 132379 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Sharief McDougle, Glenn Pilon | On Track | 10/22/25: Submitting for SL2 | E: L2 | Active | L2 | 2026-02-02 | 2026-05-29
Business Only Initiative: EMR - Drayage Mode Optimization |  | 132382 | Business Only Initiative | FXG LHN - Mode Optimization | Linehaul | Sharief McDougle, Keith Brawner | On Track | Submitting for SL2. | I: L4 | Active | L4 | 2025-02-03 | 2026-02-02
Business w/ Tech Initiative: Annual Linehaul Baseline Planning |  | 170760 | Business w/ Tech Initiative | FXG LHN - Mode Optimization | Linehaul | Joshua N. Tyler | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Monthly Linehaul Mode & Routing Decisions |  | 170763 | Business w/ Tech Initiative | FXG LHN - Mode Optimization | Linehaul | Joshua N. Tyler | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Market Tune-Ups | 75057 | 7613 | Business w/ Tech Initiative | FXG LHN - Network Optimization | Linehaul | Michael Harris, Dave Vining, Joshua N. Tyler, Mauricio Tobar | On Track | Biweekly statuses are shared via email with a number of MDs and the core team audience. These updates are focused on project planning and execution, but also review high-level DRIVE milestones and progress. I'm restricted to a select number of attachments in Wave, but these communications are posted in my Teams page as well. Please reach out if you'd like to receive these emails and/or be added to the Market Tune-Ups Teams page. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-03-19 | 2026-08-31
Business Only Initiative: Dual Hub Market Strategy | 529 | 7849 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Mark Johnson, Chris Giesey | On Track | 12/9/2024: Updated November Actual Results Initiative is not planned to start until the OTP Clouser initiative, working on the base framework for queries that will need to be performed at that time. The timeline of this initiative is being completely changed to have all markets actively work at the same time and share best practices through Bi-weekly discussions. The goal will be to identify the top opportunities for each region during each meeting (two weeks) and determine what changes can be implemented to reduce Hub area trips to the stations. | K: L5 | Completed | L5 | 2023-01-02 | 2024-01-12
Business Only Initiative: Consolidation of Underutilized GND and ECON Sorts/ | 527 | 7860 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Dave Vining, Mark Johnson | On Track |  | K: L5 | Completed | L5 | 2022-10-21 | 2023-05-19
Business Only Initiative: GND Comm on Weekend Preloads and in Rail Lanes | 528 | 7871 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Justin Lanning | On Track | W.E. 02.11.23- Milestones are on track W.E. 01.28.23- Determined there was no overlap in rail. All milestones are current and work is being prioritized accordingly no issues. W.E. 01.21.23- Have a check base with Kim this week to discuss overlap between rail portions. All milestones moving forward as entered in wave. W.E. 01.14.23- Continuing on based on milestone plan. Held meetings to develop and ensure KPI's are able to be measured properly. Setting up communication plan to move Rail portion through milestones at an accelerated pace | K: L5 | Completed | L5 | 2022-11-08 | 2024-04-19
Business Only Initiative: [Enabler] DW Network Capacity Bundle 1: Unload Di | 1031 | 8801 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Mitchell McGee, Chris Giesey | On Track | 12/8/23: L5 is being pushed back to post-peak, most likely January. UDR has been in a quiet period during peak, and we'll reexamine adoption and ties to DROP-RED performance in early CY24. _____________________________ 10/30/23: The UDR has successfully migrated to OIP and all milestones are marked as complete. Awaiting L4 submission. _____________________________ 10/13/23: This DRIVE initiative is past due for L4. Dataworks is responsible for the final milestone that hasn't been completed yet. All data sources have been ingested, so we're now in the midst of validating the accuracy of the new dashboard. I'm anticipating a 1 week delay and and L4 date of 10/20. _____________________________ 8/10/23: L4 date is being delayed roughly 2 months as the Data Engineering team at Dataworks continue progressing on 1031's final milestone: migrating the tool to the OIP environment. We have projected 4 weeks to the completion of data ingestion to Atlas, 2 additional weeks after ingestion to validate data, 2 weeks to complete the actual move and changing of notebooks, and 1 week to validate overall performance by comparing the tool in the current RACER environment to the tool in the new OIP environment. This timeline would project completion on October 13. _____________________________ 6/12/23: Two significant updates were deployed last week: 1) A change in logic to improve package count accuracy within a trailer and 2) a fix to improve accuracy within the Product Type filter. The latter enables our end-users to parse out FXSP volume from PLD views, giving them a true sense of hot volume. The team is continuing to work on LMO trailer integration. As a final note, we are beginning an RSF trial at LERS/378 this week to understand what unique needs the RSF facility type requires to benefit from the tool. _____________________________ 6/5/23: No major updates from a technical perspective; still working on two features: 1) FXE/LMO trailer integration and 2) Product Type accuracy. Our team identified an area of opportunity last week that will lead to improved package count accuracy, which will be deployed this week. _____________________________ 5/30/23: The team is on the verge of completing the requirements to display FXE/LMO trailers in the product. We are also developing the ability to sort volume by Product Type so users can parse out Economy volume when looking at PLD commit-date views. On the technical side, the Data Engineering team is continuing to upload and make connections to the manual sources required for OIP migration. On the business side, I am joining various regional engineering calls to provide UDR updates in order to positively impact adoption rates. _____________________________ 5/17/23: Dataworks is still developing the requirements needed for OIP migration. New milestone date will be set to mid-July. As discussed with Naman and others, all functionality required for DROP RED initiatives is COMPLETE. _____________________________ 4/10/23: The rollout to FXG Hubs has been completed, and the focus will now shift towards engagement and identifying opportunities for enhancement. User adoption continues to exceed expectations which is driving quite a bit of feedback. Since dashboard creation, there have been 5,082 total views (ranking 176th out of 39k Dataworks Power BI products) and 276 active end-users. A survey will be sent out this week to assess data accuracy and feature prioritization. _____________________________ 4/3/23: The third and final wave of trainings will take place this week, which will expand the total number of facilities to 49. Monitorization and control will be required for 1-2 weeks after Wave 3, and then this initiative will begin conclusion. Future UDR development is currently being examined. _____________________________ 3/27/23: Wave 2 training sessions have concluded in the East and Central regions, bringing the total number of facilities to 32. Our third and final Hub Wave will take pla | K: L5 | Completed | L5 | 2022-12-01 | 2024-04-26
Business Only Initiative: Weekend Rehandle Reduction | 87264 | 8865 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Justin Lanning, Heather Mullins | On Track | Working on Financial analysis / savings | I: L4 | Active | TEMP L4 - Enter L4 | 2025-05-19 | 2026-04-20
Business Only Initiative: Destination Station Connections Reduction | 59548 | 8873 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Victoria Likovich, Mark Johnson | On Track | The money step has been achieved. The evidence of achievement is linked in the "Attachments" tab. There are screenshots of DMT screens showing the origins no longer make the connections we had included in our elimination list and there is a file that we are using to track the results. The next 3 months will be spent collecting data and tracking the results, so in September L5 can be discussed. | K: L5 | Completed | L5 | 2023-12-01 | 2024-08-14
Business w/ Tech Initiative: Autodock |  | 105977 | Business w/ Tech Initiative | FXG LHN - Network Optimization | Linehaul | Junbo Wang, Clint Damman, John Robinson | On Track | 2/13/2026 - PDSM ticket has been submitted to get L1 Hard NRB updated. 2/11/2026 - Savings were approved by Domain Finance Lead via Email 1/27/2026 - Savings were reassessed to be $56M, recived approval confirmation from Business Owner 10/14/2025 - Additional saving opportunity identitfied in HUB area partial reduction due to potential development of Spot Forecast 5/13/2025 - saving determined by Kyle H and Clint D as ML Partial Reduction 4/24/2025 - high level Architecture Assessment on Autodock init to move from L1 to L2 4/15/2025 - autodock (this use case) to be an enabler for drop/red initiative 3/28/2025 - preparing L1 LBC 3/19/2025 - presented and approved in Triage | E: L2 | Active | L2 | 2025-06-09 | 2026-01-30
Business w/ Tech Initiative: Finish Line Dashboard |  | 144763 | Business w/ Tech Initiative | FXG LHN - Network Optimization | Linehaul | James Pittenger | On Track | 8/7 - working on completion of lean business case 10/2 - had L1 surge call, working on quantifying cost savings 10/21 - sent email requesting L2 approval with $0 cost savings for now 2/19/2026 - Cancelling due to inability to get prioritized with $0 cost savings. Cancellation approved by Dave McIntyre by email on 2/19/2026. | E: L2 | Cancelled | L2
Business w/ Tech Initiative: FICO Renewal for Flow Plan Optimization (FPO) |  | 164551 | Business w/ Tech Initiative | FXG LHN - Network Optimization | Linehaul | Michael Harris | On Track | The FICO license was renewed with legal. We were able to update the security key on our own. We no longer need Tech support. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Holiday Planning & Exceptions |  | 170835 | Business w/ Tech Initiative | FXG LHN - Network Optimization | Linehaul | Joshua N. Tyler | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Middle Mile / Linehaul – Vessel Integration |  | 170838 | Business w/ Tech Initiative | FXG LHN - Network Optimization | Linehaul | Joshua N. Tyler | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: ECON Flow Plan Handles Reduction |  | 171264 | Business Only Initiative | FXG LHN - Network Optimization | Linehaul | Michael Harris | On Track | On Track | E: L2 | Active | L2 Feedback Requested
Business Only Initiative: Engineered Rightsizing of LH Flat Rates | 91749 | 7029 | Business Only Initiative | FXG LHN - Power Play | Linehaul | Emily Zeigler | On Track | Projections have been updated through FY26. Savings will be realized in Q1 - Q3. At that point, there will be no more savings associated with this initiative. L4 was kicked off in Feb 2025. 3 months of achieved savings was met at the end of April 2025 therefore making it ready for L5. Email approval sent and Adam Baker as instructed the submission for L5 in Planview. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-11-11 | 2025-02-17
Business w/ Tech Initiative: [ENABLER] Purchased Motor Carrier Dashboard/KPIs | 85573 | 7030 | Business w/ Tech Initiative | FXG LHN - Power Play | Linehaul | Michael Yatsco, Craig Molinaro | On Track | 29 May 2025 ON HOLD Waiting for prioritization/no work currently being completed 14 April 2025 Waiting to be prioritized for the last several weeks Need architects. 24 January 2025 -Working with FXF DB team to get schema mapping of tables to see what is or is not currently in Atlas -Work continues on getting the administrative information and requirements to get to L3 17 January 2025 -DW working with Finance to get costing compiled oLooking to have completed end of next week (1/25) -Still working to get an Architect assigned 10 January 2024 -Followed up with IT Finance to get needed costing as part of move to L3 -Followed up with Enterprise Strategic Program Management about getting an architect assigned -Continuing to make progress with gathering data and getting into Atlas oFXF sources are mostly compiled oWorking with FXE to get needed data streams in place 20 December 2024 -Progress continues towards move to L3 oWorking with IT Finance to get costing oEntering EPICs into Planview -After meetings with legacy Express, it is now understood what data was missing in Atlas and steps are being taken to get the data entered 13 December 2024 -DW met with FXE and FXF to review data sources -Met with Enterprise Architecture Enablement to work on getting an architect assigned, making progress on the move toward L3 9 December 2024 -Working on getting items needed to move to L3 oArchitect needs assigned oEPICs added oProject and Portfolio Management number to be assigned to the Enabler -DW was granted access to TRIPS delay report oProvides DW the full picture of the current FXE process for tracking PT carrier performance 22 November 2024 -Received the raw Power BI file of legacy Grounds’ PT dashboard oAllows for deeper investigation to the data sources and calculations -Dataworks starting to build data map of the FXF and legacy Express data sources 15 November 2024 -Legacy Ground to provide Power BI file of their dashboard oWill allow Dataworks to review how the data is transformed and the needed calculations -Dataworks in the process of getting access to legacy Express and FXF data tables -Met with legacy Express to discuss their dashboard 12 November 2024 - Update from Friday (11/8) -Legacy Ground provided a demo of their dashboard to SMEs from FXF to gain insight to how a similar dashboard can be built for FXF -The team met with FXF to scope out development of a dashboard oThe goal is to recreate the Excel version from FXF in Power BI, where FXF can then use that information to provide automated weekly updates to their carriers -Meeting to be held with legacy Express to review their version of a dashboard oGoal is to also move their report to Power BI 25 October 2024 - Demo of dashboard was post-poned. The team will use the legacy Ground tool to help standardize the metrics from FXE and FXF. Met with FXF to discuss to learn more about their decision process of 3rd party procurement. 23 October 2024 - team has met with SMEs from the legacy OpCos and reviewed a dashboard that has been created by legacy Ground. Meeting provided a lot of insight into the the metrics and how Ground measures the performance of their 3rd party carriers. Info to be used to help get FXE and FXF standardized. Demo of a wireframe of the dashboard to be held tomorrow, 24 October 2024. - After update on 10/23, demo meeting ended up being cancelled. (edit- 10/25) IO continues to work with SME across legacy Op-Cos to talk through proposed metric data sources along with definition DataWorks continues to identify existing data sources and is working towards an initial demo of the dashboard on 10-24-24. 20 September 2024 - Dataworks continues to work on data source collection and work has begun on the first draft of the dashboard. Meeting to demo the dashboard has been scheduled. 13 September 2024 - Data sources have been identified and Dataworks is determining if the data tables an | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-08-26 | 2025-04-30
Business w/ Tech Initiative: Spots - Low Trailer Fullness | 532 | 8027 | Business w/ Tech Initiative | FXG LHN - Power Play | Linehaul | Michael Hinkle, Craig Molinaro | Some Issues | We are having to re-baseline our savings using the new process. we think we will need to push our L4 date back 6 weeks. | K: L5 | Completed | L5 | 2022-11-07 | 2025-08-29
Business w/ Tech Initiative: Inefficient P&D Spots - Bobtail to Bobtail | 1266 | 8833 | Business w/ Tech Initiative | FXG LHN - Power Play | Linehaul | Michael Hinkle, Craig Molinaro | On Track | Week of 4/8 * Met on 4/4 with Ben Komada, Dataworks director and obtained approval for Craig Molinaro's team to own and modify the Power BI report in DEV environment. Dataworks will promote PBI changes to PROD environment. * Awaiting completion of IMAGE provisioning to additional job codes. * Awaiting completion of IMAGE job code mapping for One FedEx IMAGE roles Refresh. Week of 4/1 * Refresher training session 3 of 3 takes place this week. * Awaiting completion of IMAGE provisioning to additional job codes. * Awaiting completion of IMAGE job code mapping for One FedEx IMAGE roles Refresh. * Provided draft of Playbook to Dataworks last week, as requested, to support formal transition from development to maintenance phase. Week of 3/25 * Announced refresher training in The Daily Ground and on Spot Analytics SharePoint * Submitted additional job codes to IMAGE roles; awaiting completion of provisioning. * Submitted job code mapping for One FedEx IMAGE roles Refresh. * Will present Spot Analytics on District Manager call this week. * Dataworks is adding a Network Efficiency trend line to PBI Report; scheduled to be done this week. Next Steps * Finish writing Playbook for knowledge transfer to interim Spots owner. Week of 3/18 * Followed up with facilities that are not using their assigned licenses. * Scheduled 3 refresher training sessions to drive improved compliance. Awaiting approval to publish announcement. Next Steps * Finish writing Playbook for knowledge transfer to interim Spots owner. Week of 3/11 * Contacted Jay Avery in McKinsey to restore the KPI Plan, Forecast, and Estimate rows from June 2023 forward to their correct order: % of Trips first, % of Settlement second. Wave Admins had reversed the "Measure and Unit" names in an effort to correct data errors that were caused by the re-baseline upload template not matching the order of KPIs in Wave. * Image role access issues appear to have been resolved by most recent re-provisioning. Awaiting confirmation from users known to have had issues. Then will announce fix to Field. Next Steps * Communicate access issues fix to the Field, after confirming successful solution. * Follow-up with facilities that have not requested licenses. * Finish writing Playbook for knowledge transfer to interim Spots owner. Week of 3/4 Cancelled milestone 6228 because ownership is not in our control and requires surface organization alignment under One FedEx. Extended milestone 23542 end date to 3/31 to allow tweaks to UI and PBI Report, and resolution of ongoing IMAGE roles access issues. PPM project number has not been assigned and will no longer be tracked in the weekly update. Next Steps: Continue updating Security Group for User Interface licenses. Continue developing Playbook for knowledge transfer to interim Spots owner. Week of 2/26 Awaiting re-provisioning of IMAGE access to resolve ongoing issues. Facilities continue slowly entering Spot Analytics user license requests, causing manual rework for IO. Awaiting PPM project number assignment from Project Managment Principal (ITFPC). Awaiting identification of 1) Spots owner and 2) department to receive knowledge transfer for the network implementation and post-L4 support. Next Steps: Continue updating Security Group for User Interface licenses. Continue developing Playbook for knowledge transfer to interim Spots owner. Week of 2/19 Identified errors in KPI forecast for certain months, due to Finance re-upload. Kay Subosits will work with McKinsey to correct. Awaiting re-provisioning of IMAGE access to resolve ongoing issues. Facilities continue slowly entering Spot Analytics user license requests, causing manual rework for IO. Awaiting PPM project number assignment from Project Managment Principal (ITFPC). Awaiting identification of 1) Spots owner and 2) department to receive knowledge transfer for the network implementation and post-L4 support. Next Steps: Continue updating Security Group for User Interface licenses. Co | K: L5 | Completed | L5 | 2022-11-01 | 2024-05-31
Business w/ Tech Initiative: Inefficient P&D Spots - Empty to Empty | 1716 | 8883 | Business w/ Tech Initiative | FXG LHN - Power Play | Linehaul | Michael Hinkle, Craig Molinaro | On Track | Week of 4/8 * Met on 4/4 with Ben Komada, Dataworks director and obtained approval for Craig Molinaro's team to own and modify the Power BI report in DEV environment. Dataworks will promote PBI changes to PROD environment. * Awaiting completion of IMAGE provisioning to additional job codes. * Awaiting completion of IMAGE job code mapping for One FedEx IMAGE roles Refresh. Week of 4/1 * Refresher training session 3 of 3 takes place this week. * Awaiting completion of IMAGE provisioning to additional job codes. * Awaiting completion of IMAGE job code mapping for One FedEx IMAGE roles Refresh. * Provided draft of Playbook to Dataworks last week, as requested, to support formal transition from development to maintenance phase. Week of 3/25 * Announced refresher training in The Daily Ground and on Spot Analytics SharePoint * Submitted additional job codes to IMAGE roles; awaiting completion of provisioning. * Submitted job code mapping for One FedEx IMAGE roles Refresh. * Will present Spot Analytics on District Manager call this week. * Dataworks is adding a Network Efficiency trend line to PBI Report; scheduled to be done this week. Next Steps * Finish writing Playbook for knowledge transfer to interim Spots owner. Week of 3/18 * Followed up with facilities that are not using their assigned licenses. * Scheduled 3 refresher training sessions to drive improved compliance. Awaiting approval to publish announcement. Week of 3/11 Image role access issues appear to have been resolved by most recent re-provisioning. Awaiting confirmation from users known to have had issues. Then will announce fix to Field. Next Steps * Communicate access issues fix to the Field, after confirming successful solution. * Follow-up with facilities that have not requested licenses. * Finish writing Playbook for knowledge transfer to interim Spots owner. Week of 3/4 Cancelled milestone 6256 because ownership is not in our control and requires surface organization alignment under One FedEx. Extended milestone 23543 end date to 3/31 to allow tweaks to UI and PBI Report, and resolution of ongoing IMAGE roles access issues. PPM project number has not been assigned and will no longer be tracked in the weekly update. Next Steps: Continue updating Security Group for User Interface licenses. Continue developing Playbook for knowledge transfer to interim Spots owner. Week of 2/26 Updated forecasted KPI and Impacts for February through May 2024, based on gradual recovery from Peak pause and slow network-wide adoption. Awaiting re-provisioning of IMAGE access to resolve ongoing issues. Facilities continue slowly entering Spot Analytics user license requests, causing manual rework for IO. Awaiting PPM project number assignment from Project Managment Principal (ITFPC). Awaiting identification of 1) Spots owner and 2) department to receive knowledge transfer for the network implementation and post-L4 support. Next Steps: Continue updating Security Group for User Interface licenses. Continue developing Playbook for knowledge transfer to interim Spots owner. Week of 2/19 Identified errors in KPI forecast for certain months, due to Finance re-upload. Kay Subosits will work with McKinsey to correct. Awaiting re-provisioning of IMAGE access to resolve ongoing issues. Facilities continue slowly entering Spot Analytics user license requests, causing manual rework for IO. Awaiting PPM project number assignment from Project Managment Principal (ITFPC). Awaiting identification of 1) Spots owner and 2) department to receive knowledge transfer for the network implementation and post-L4 support. Next Steps: Continue updating Security Group for User Interface licenses. Conclude hosting Office Hours this week. Continue developing Playbook for knowledge transfer to interim Spots owner. Week of 2/12 Presented initiative to Senior Officers. Received positive feedback. Provided VP Transportation with list of facilities that have not requested licenses, for follow-up with Reg | K: L5 | Completed | L5 | 2022-11-01 | 2024-05-31
Business Only Initiative: Autonomous Vehicle Linehaul Project - Phase 1 |  | 97537 | Business Only Initiative | FXG LHN - Power Play | Linehaul | Adenike Adeoye | On Track | Team is working on the financial business that focuses on near and middle term goals | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: FY26 Customer Spot Efficiency |  | 130994 | Business Only Initiative | FXG LHN - Power Play | Linehaul | Michael Hinkle | On Track | Sub Team formed and working on LBC for L2. | I: L4 | Active | TEMP L4 - Enter L4 | 2025-08-04 | 2025-11-14
Business Only Initiative: FY26 Engineered Right-sizing of Flat Rates |  | 141769 | Business Only Initiative | FXG LHN - Power Play | Linehaul | Emily Zeigler | On Track | Working on L2 submission | I: L4 | Active | L4 | 2025-11-24 | 2026-02-26
Business w/ Tech Initiative: Customer Spot Operation Modernization |  | 167497 | Business w/ Tech Initiative | FXG LHN - Power Play | Linehaul | Michael Hinkle, Craig Molinaro | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: FY25 Transit Strategy | 83121 | 6718 | Business Only Initiative | FXG LHN - Technology & Modernization | Linehaul | Brian Buchanan, Victoria Bonetto | On Track | 9/15 L5 has been approved. Transitioning to Brian Buchanan as primary IO. Financials will be tracked through May (initiative can retire in June after May actuals are inputted). 9/8 Entered 3 months of consistant actuals. Reviewed with Connor Soboslay, Jackie Makinen and Adam Baker. Submitting for L5 5/8 Initiative has been updated for FY25 rebaselining 5/5 Brian and I have been working with Adam Baker and his team to finalize the rebaselining. Pre-surge meeting for L4 scheduled for 3/17. Surge meeting with Dave McIntyre, Clay Roach and Adam Baker for 3/20. Money Step estimated for 3/31. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-07-23 | 2025-09-30
Business Only Initiative: FY25 Transit Strategy- Rail | 86432 | 6719 | Business Only Initiative | FXG LHN - Technology & Modernization | Linehaul | Brian Buchanan, Victoria Bonetto | On Track | 9/15 Transitioning to Brian Buchanan as primary IO. Financials will be tracked through March (initiative can retire in April after March actuals are inputted) 6/23 L5 Pre-Surge meeting conducted with Connor Soboslay and Jackie Makienen. L5 Surge scheduled for 7/1. 5/8 Initiative has been updated for FY25 rebaselining 5/5 Rebaslining sent to Adam Baker and team for review before uploading into Planview Pre-surge meeting for L4 scheduled for 3/17. Surge meeting with Dave McIntyre, Clay Roach and Adam Baker for 3/20. Money Step estimated for 3/31. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-09-24 | 2025-07-04
Business Only Initiative: Saturday Coverage Reduction | 61764 | 8134 | Business Only Initiative | FXG LHN - Technology & Modernization | Linehaul | Brian Buchanan, Victoria Bonetto | On Track | we 7/13: Reduction not supported by leadership or commercial domain. we 4/19: No movement in approval. Pushed timeline back 1 week to reflect delay, plus 2 weeks for scheduled PTO the next two weeks. we 4/12: We have passed the original start date to adhere to the stated timeline. Each week without approval will push savings back 1 week. we 3/22: New scenarios created for TO review below the lowest prior option. They size the impact needed to produce $15M, $20M, or $25M in annual savings. we 3/8: Commercial Clearinghouse declined to approve any presented reduction ranging from 65-92% US coverage. TO or XO will need to override decision for initiative to continue. we 3/1: F&LM assumptions changed to allow ISP resources to scale with available volume. New supporting materials attached, impacts updated, and L2 surge completed (+$29M) we 2/23: Materials loaded in preparation for L2 surge and impacts updated to include F&LM PLPD (+$5M) | E: L2 | On Hold | L2 & CCH
Business Only Initiative: Sunday 7-Day | 1757 | 8881 | Business Only Initiative | FXG LHN - Technology & Modernization | Linehaul | Brian Buchanan, Kyle Hahn | On Track | we 2/23 Update Feb-24 to May-26 forecast loaded into impacts tab based on current realization of savings. Increase from original NRB from $54M to $84M. we 7/21 F&LM 107 contracts behind original timeline, renegotiation had longer timeline than stated and savings delayed on missed contracts by 1 year. Estimated impact $4.4M in FY24. Other savings in line with expectations. we 3/24: Changes implemented 3/19 with first week recap showing savings above forecast. Broken down by money step, F&LM and Linehaul savings are above target, with Dock impact by weather. we 3/10: Still on track for 3/19 implementation. System updates have began to propagate we 1/27: Field review has been completely, station and zip level detail reviewed for 51.6% US population coverage. we 12/23: 50% has been chosen as the target by Brie and John, 3/19 target start date for all tasks that need completed first w/e 12/2: Still awaiting decision, next meeting Tuesday 12/6 for Commercial Drive. Continued delays in decision may put money step at risk of delay. w/e 11/25: Ground Sr Leadership still looking to reduce Sunday coverage for additional savings. Savings should be at minimum what is entered for 45% coverage, but could have an additional ~$70M at 0%. w/e 11/11: Commercial DRIVE meeting on 11/7 set target to 44.5% which reduces overall savings potential. Working on aligning original business case assumptions with DRIVE default assumptions. w/e 11/4: Refined plans of 30% coverage and options to go lower while covering capacity constraints. Preparing for review at Commercial DRIVE meeting scheduled for Monday 11/7. w/e 10/25: Target Sunday coverage set by Ground Commercial SteerCom at 30% on 10/26, which targets $90M savings. Moving forward with a more detailed plan of which 30% would remain on. | K: L5 | Completed | L5 | 2022-10-14 | 2024-07-01
Business w/ Tech Initiative: Enterprise Linehaul Route Optimization with Techno | 93402 | 8894 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Johanne Doucet, Greg Kaufman | On Track | Initiative is on track, still testing buy scenario (results prior to end of month). | E: L2 | Active | L2 | 2025-11-13 | 2028-01-03
Business w/ Tech Initiative: Automated Dispatch and Arrival for One FedEx | 94562 | 9060 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Greg Kaufman, Pamela Seitz-Wintermantel, Lisa Mangelsdorf | On Track | 11/26/2025 - Placing on hold per request from Jackie Makinen. 5/15 - Per guidance received I am re-working this request to focus on an enterprise level solution for the US, Canada, and the EU, and defining potential drive initiatives and value bundles. 4/8/2025 - Finalizing business case savings with the newer reduced scope. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Safety & Regulatory Integration with Mobile Trip A | 94583 | 9061 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Greg Kaufman, Lisa Mangelsdorf | On Track | 2/16/2026 Placing on hold per request from POD lead Jackie Makinen. With the adoption of ROCS in North America and the current initiatives being added in support of that transition, this will not likely be an initiative in the future, so placing on-hold. 11/04/24 Preparing to submit for SL2. 11/22/24 Preparing to submit for SL2. 12/12/24 Waiting on EA assignment. | E: L2 | On Hold | L2
Business w/ Tech Initiative: Linehaul Route Optimization | 541 | 9507 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Dominick Aveni, Greg Kaufman | On Track | n/a | K: L5 | Completed | L5 | 2022-10-28 | 2024-08-01
Business w/ Tech Initiative: Hazmat/Dangerous Goods Manifest for all LH Movemen |  | 92466 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Scott Morrison, Jackie Makinen, Ed Steklachick | On Track | Added Scott as primary IO. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-30 | 2027-11-09
Business w/ Tech Initiative: Enterprise Linehaul Two-Way Communication |  | 133022 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Greg Kaufman | On Track | Placing on hold per email request from Jackie Makinen. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Linehaul Gate Automation for Third Party Transport | 543 | 7272 | Business w/ Tech Initiative | FXG LHN - Technology & Modernization | Linehaul | Thomas Quimby, Lori Parks | On Track | 4/22 Current Status Overall implementation remains on track, with focused risks around security gate code integration and carrier automation readiness. Phase One carrier training and field readiness continue while contingency planning is underway for identified technical constraints. Work Completed in the Last 2 Weeks Carrier Training & Integration: •30% of small, medium, and ad hoc carriers attended at least one onboarding session. •Four additional onboarding sessions scheduled. •Phase One carrier launch email drafted with lanes, launch date, and key attachments. •Carrier concerns addressed and follow-ups initiated. Security & Facilities: •Facility security assessments progressed; unresponsive sites escalated. •Non-working equipment mitigated; overall low risk. Process, Change & Reporting: •Escalation ownership defined for field-facing and carrier-facing issues. •Vector dashboard limitations reviewed; training feedback collection initiated. Contracts: •Three remaining carrier agreements require follow-up; none expected to block launch. Work In Progress Carrier Integration: •Limited API integrations; some CSV connections pending. Security / Gate Code Capacity: •Lenel patch ready but untested; backup strategies under review. Process & IT: •File transfer testing between TMW and Vector planned. •Brokerage workflow and escalation procedures under refinement. Change Management & Reporting: •KPI reporting approach and ownership being finalized. Training & Deployment: Phase Two training logistics underway and field support structure finalized. Next Steps •Finalize gate code solution approach. •Continue carrier onboarding and integration updates. •Complete Phase Two training logistics. •Assign interim reporting owners and advance BI hiring. •Resume field communications post-security alignment. Risks / Awareness •Gate code API delay may impact automated access at launch. •Majority of carriers lack automation, increasing manual work. •Reporting limitations require manual solutions at launch. •Field communications delayed pending security resolution. Requests for Support from Leadership •Decision support on gate code mitigation strategy once presented options •IT prioritization to accelerate patch testing. 4/15 •Successful Training Sessions: oPhase One Market Champion training and Special Assignment Specialist onboarding in (PGH) were highly effective, with strong engagement and positive feedback. oScott and Chad were commended for their facilitation, with notable improvements already being made to future training materials. •Staffing Updates: oSpecial Assignment Managers: Three candidates identified; one accepted and starting tomorrow, two offers pending finalization. oAdditional positions: Business Intelligence Analyst and Line Hall Net Support Manager roles are posted, with interviews imminent. oTemporary assignments for carrier champs are ending; transition plans in place using existing staff, with additional hires posted for night/weekend operations. •Phase Two Preparation: orequesting Market Champion nominees by end of next week; training for Phase Two to follow. oOngoing coordination to align Special Assignment team with Market Champions and support deployment across regions, notably the Southwest. Sub-Team Updates Security •Facility Assessments: 18 of 47 sites assessed; escalation email sent to prompt completion. •Mitigation Plans: Contract security available if equipment not repaired by deployment; not currently considered a Phase 1 risk but will revisit next week. •Documentation: Ongoing work on driver disassociation and access control requests. Process/IT •PT Enhancements: Minor improvements underway before deployment. •IT Support: Diraj to coordinate with Vector IT on outstanding TMW connection and deployment support plans. •Brokerage Workflow: Collaboration with brokerage team; need to appoint a new sub-team manager. •File Issues: Incident from February discussed; plan in place | G: L3 | Active | TEMP L3 - Enter L3 | 2022-12-01 | 2026-08-31
Business Only Initiative: [Enabler] USGO Surface Hubs (load doors) | 88483 | 9242 | Business Only Initiative | Network 2.0 - Facilities | Network 2.0 | Amy Besserud, Deborah Lauro, Zachary McElwain | On Track | . | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2028-09-01
Business Only Initiative: [Enabler] Vehicle Maintenance Shops | 86728 | 9244 | Business Only Initiative | Network 2.0 - Facilities | Network 2.0 | Russell Meyer, Deborah Lauro, Kelly Kull, Zachary McElwain | On Track | 1/28/26 Input actuals for month of December 2025. Forecast for this month was $0 due to no anticipated completed projects or shop dismantles within this time period – ties to the November 2025 N2.0 Business Case forecast. 3/13/26 Input actuals for month of January 2026. Forecast for this month was $0 due to no anticipated completed projects or shop dismantles within this time period – ties to the November 2025 N2.0 Business Case forecast. 4/16/26 Input actuals for month of February 2026. Forecast for this month was $0 due to no anticipated completed projects or shop dismantles within this time period – ties to the November 2025 N2.0 Business Case forecast. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-05-31
Business w/ Tech Initiative: [Enabler] USGO Station Projects & Build to Suits | 92125 | 9246 | Business w/ Tech Initiative | Network 2.0 - Facilities | Network 2.0 | Dean Bonenberger, Deborah Lauro, Zachary McElwain | On Track | . | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-05-31
Business Only Initiative: [Enabler] USGO Air Hubs & Ramps | 88485 | 9247 | Business Only Initiative | Network 2.0 - Facilities | Network 2.0 | Jonathan Rader, Deborah Lauro, Zachary McElwain | On Track | . | G: L3 | Active | TEMP L3 - Enter L3 | 2025-02-03 | 2027-08-31
Business Only Initiative: [Enabler] Off-Site Parking for Legacy Express Faci | 88484 | 9250 | Business Only Initiative | Network 2.0 - Facilities | Network 2.0 | Michael Costanzo, Deborah Lauro, Tim Wadas, Zachary McElwain | On Track | . | G: L3 | Active | TEMP L3 - Enter L3 | 2027-05-31 | 2027-05-31
Business Only Initiative: [Enabler] Linehaul Connection Costs | 87772 | 9400 | Business Only Initiative | Network 2.0 - Middle Mile | Network 2.0 | Donna Apollonio, David Borchardt | On Track | 04/03/26: Forecast $ values entered as proxy for Mar 2026 actuals. Fall district launches to be evaluated with Feb/Mar 26 data as all waves of districts s/b evaluated at the same time, and data must exclude peak. 02/04/26: Forecast $ values entered as proxy for Jan/Feb 2026 actuals. 02/03/26: Uploaded file containing actuals through Aug 2025 and Refresh Biz Case forecast Sept 2025 to May 2028. a) Annualized exit rate increased from $109M to $115M, versus FY25 baseline primarily due to fewer station closures than previous July 2025 biz case. b) Sept/Oct 2025 actuals will need to wait for Jan/Feb post-peak data to be available since those districts had staggered station launches. Expect to enter forecast as proxy for Jan/Feb actuals until analysis of post peak data is completed. 01/13/26: Entered forecast in for actuals. Will enter actuals likely through Aug/Sept launches by beginning of Feb once Surface LH Eng approves values. Also expect to amend forecast to align with Refresh Plan at that time. 12/11/25: Clean actuals analysis requires a data set 9 weeks post launch and cannot include peak activity. Therefore, forecast will be input for actuals as a proxy until appropriate analysis is complete. Surface LH is currently analyzing network impacts for July through October launches. Until then forecast will be in place of actuals. 10/14/25: Financials and KPIs updated to reflect: a) Split between FXE Surface (vans) and FXE I&A (trucks) b) Forecast and actuals rebaselined to FY25. Exit rate total now $109M instead of $123M c) July-Sep actuals reflect rebaselined forecast until validated actuals are available July 2025 Model Update: Methodology and inputs updated to reflect additional learnings and network design changes (including NEEDLES and other project changes). Impact and KPIs updated to $123M. Updated cost forecast to align with recent model refinements. Total was $286M, now $276M. Impact and KPI Plan updated by month. Miles in thousands. | G: L3 | Active | TEMP L3 - Enter L3 | 2027-08-31 | 2027-08-31
Business Only Initiative: FY24.01 Jun - Logan, UT | 90518 | 7463 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Brian Carlson, Katherine Kerekes, Michael Kozy, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L5 because market is immaterial and launched in FY24. | K: L5 | Active | L5 | 2023-03-14 | 2023-06-29
Business Only Initiative: FY24.04 Sep - Macon, GA | 90526 | 7471 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Jeffrey Conti, Michael Patafio, John Fitzgerald, Michael Kozy, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because market launched in Sep. FY24. | I: L4 | Active | L4 Feedback Requested | 2023-06-06 | 2025-10-03
Business Only Initiative: FY24.04 Sep - Lufkin, TX | 90531 | 7478 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Logan Banasky, Sally Robbins, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because market launched in Sep. FY24. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-06-06 | 2023-10-11
Business Only Initiative: FY24.06 Nov - Gunnison, CO | 90534 | 7482 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Rudolf Ottersen, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Follow-up needs to occur with district ops leadership to improve results before moving to L5. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-08-10 | 2023-11-30
Business Only Initiative: FY24.06 Nov - Humboldt, TN | 90536 | 7485 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Ryan Busch, Scott A. Cuffman, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Market not currently hitting targets, as such follow-up required by District leadership. | I: L4 | Active | TEMP L4 - Enter L4 | 2023-08-09 | 2023-11-30
Business Only Initiative: FY25.03 Aug - Panama City, FL | 90541 | 7490 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Aaron Weatherby, Jeno Czabafy, Michael Kozy, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because market already launched. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-07 | 2024-10-29
Business Only Initiative: FY25.03 Aug - Punta Gorda, FL | 90542 | 7492 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Zachary McElwain, Jennifer Beatty, Jeffrey Urban, John A. Pizzola, Michael Kozy, Ben Forness, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because market already launched. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-17 | 2024-10-29
Business Only Initiative: FY25.04 Sep - Hickory, NC | 90543 | 7493 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Donald Davis, Mark Potts, Michael Kozy, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | 02/10/2026: Moving to L5 because market has hit three months of performance at or above target. | K: L5 | Active | L5 | 2024-06-12 | 2024-12-02
Business Only Initiative: FY25.04 Sep - South Augusta, GA | 90544 | 7495 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Jeffrey Conti, Michael Patafio, John Fitzgerald, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because market already launched. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-05 | 2024-12-02
Business Only Initiative: FY25.05 Oct - North Portland, OR | 90545 | 7496 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Jeffrey Lewis, Joshua Kubisch, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because market has already launched. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-06-04 | 2024-12-31
Business Only Initiative: Piedmont District - Wave 1 | 98432 | 7543 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Ben Forness, Davorah Bowen, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L4 because Wave 1 launched on 9/1/2025. 1/28/2026: Updating to reflect 'Refresh' business case 02/10/2026: Moving to L5 because since Sep'25 Piedmont Wave 1 has been hitting / exceeding target. | K: L5 | Active | L5 | 2025-08-29 | 2027-08-31
Business Only Initiative: Prairie District | 98543 | 7556 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Davorah Bowen, Jennifer Beatty, Ben Forness, Elizabeth Regan, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Preparing to move to L4 when Wave 2 of Praire launches on 9/29. 1/28/2026: Updating to reflect 'Refresh' business case | I: L4 | Active | TEMP L4 - Enter L4 | 2025-10-29 | 2025-10-29
Business Only Initiative: FY24.01 Jun - Clarksville, TN | 90516 | 7460 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Market already launching, just needing to move to L3 to track actuals. | K: L5 | Completed | L5 | 2023-03-08 | 2023-06-29
Business Only Initiative: FY24.01 Jun - Jonesboro, AR | 90517 | 7462 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 since market launched 12+ months ago. | K: L5 | Completed | L5 | 2023-03-08 | 2023-06-29
Business Only Initiative: FY24.01 Jun - Pittsburg, KS | 90519 | 7464 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 since market launched 12+ months ago and savings will be in the run-rate with rebaseline. | K: L5 | Completed | L5 | 2023-03-08 | 2023-06-29
Business Only Initiative: FY24.02 Jul - Cookeville, TN | 90520 | 7465 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because the market launched 12+ months ago and savings will be in the run-rate when we rebaseline. | K: L5 | Completed | L5 | 2023-04-07 | 2023-08-01
Business Only Initiative: FY24.02 Jul - Starkville, MS | 90522 | 7467 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 since market launched in July FY24. | K: L5 | Completed | L5 | 2023-04-12 | 2023-08-02
Business Only Initiative: FY24.04 Sep - Jackson, MS | 90525 | 7470 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market launched in Sep. FY24 and is performing at or above target. | K: L5 | Completed | L5 | 2023-06-06 | 2023-10-04
Business Only Initiative: FY24.04 Sep - Alexandria, LA | 90524 | 7469 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because the market launched in Sep FY24 and is performing at or above target. | K: L5 | Completed | L5 | 2023-06-02 | 2023-10-04
Business Only Initiative: FY24.03 Aug - Joplin, MO | 90523 | 7468 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market launched in Aug. FY24 and is performing at or above target. | K: L5 | Completed | L5 | 2023-03-08 | 2023-08-31
Business Only Initiative: FY24.02 Jul - Prescott, AZ | 90521 | 7466 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 since market launched 12+ months ago. | K: L5 | Completed | L5 | 2023-04-12 | 2023-08-02
Business Only Initiative: FY24.06 Nov - Marion, IL | 90538 | 7487 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market is at or near targets. | K: L5 | Completed | L5 | 2023-08-01 | 2023-11-30
Business Only Initiative: FY24.06 Nov - Kingman, AZ | 90537 | 7486 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market is at or near targets. | K: L5 | Completed | L5 | 2023-08-10 | 2023-11-30
Business Only Initiative: FY24.06 Nov - Hermitage, PA & Oil City, PA | 90535 | 7484 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because the market has show 12 months of mature benefits realized (via Confirmed Actuals). | K: L5 | Completed | L5 | 2023-08-08 | 2023-11-30
Business Only Initiative: FY24.05 Oct - Lafayette, IN | 90533 | 7480 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market launched and is performing at or near target. | K: L5 | Completed | L5 | 2023-07-11 | 2023-11-02
Business Only Initiative: FY24.04 Sep - Coos Bay, OR | 90530 | 7477 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L4 because market launched in Sep. FY24 as is performing at or near target. | K: L5 | Completed | L5 | 2023-06-14 | 2023-10-11
Business Only Initiative: FY24.04 Sep - The Dalles, OR | 90529 | 7476 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market launched in Sep. FY24 and is at or near target.. | K: L5 | Completed | L5 | 2023-06-06 | 2023-10-03
Business Only Initiative: FY24.04 Sep - Temple, TX | 90528 | 7474 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Victoria Bonetto, Jennifer Beatty, Maria Taylor, Sally Robbins, Michael Kozy, Ben Forness, Zachary McElwain, Candra Wiguna, Tavell Brown, Zachary Jarrett | On Track | Moving to L5 because market launched in Sep. FY24 is at or above target. | K: L5 | Active | TEMP L5 - Enter L5 | 2023-06-06 | 2023-10-03
Business Only Initiative: FY24.04 Sep - McComb, MS | 90527 | 7473 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market launched in Sep. FY24 and is at or above target. | K: L5 | Completed | L5 | 2023-06-06 | 2023-10-03
Business Only Initiative: FY24.05 Oct - Bowling Green, OH | 90532 | 7479 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market launched in Oct FY24 and is at or near targets. | K: L5 | Completed | L5 | 2023-07-13 | 2023-11-02
Business Only Initiative: CY22 AK 10 FXE Facilities | 1645 | 8879 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Dale Shaw, Brian Read | On Track | Corp Finance working through actual performance for Impact and KPIs. | K: L5 | Completed | L5 | 2022-09-01 | 2022-10-11
Business Only Initiative: Canada Transformation Plan | 87656 | 7724 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Donna Apollonio, Manlio Staropoli, Daniella M. Dias, Brianna Cormier, Jennifer Beatty | On Track | Ready to launch last phase on schedule April 1, 2025 Stations in all markets in Canada have been launched as of April 1, 2025 CTP being closed out in N2.0 at end of FY25 and moved to Canada Efficiency Pod in Americas Domain to track / manage FY26+ new initiatives. | K: L5 | Completed | L5 | 2022-11-01 | 2024-12-30
Business Only Initiative: FY24.09 Feb - Bozeman, MT | 90540 | 7489 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because the reason for the cost vs savings target is because service providers baseline cost per VDE is $621 and the FXE baseline cost per courier is $511. Overall the market has reduced resources and is meeting or exceeding the other KPI targets since November 2024. | K: L5 | Completed | L5 | 2023-09-27 | 2024-02-29
Business Only Initiative: FY24.06 Nov - Tupelo, MS | 90539 | 7488 | Business Only Initiative | Network 2.0 - District Planning | Network 2.0 | Jennifer Beatty, Lynn Kossick, Maria Taylor | On Track | Moving to L5 because market is at or near targets. | K: L5 | Completed | L5 | 2023-08-08 | 2023-11-30
Business Only Initiative: [Enabler] Transition "Insurance" Levers (STAR and | 88116 | 6953 | Business Only Initiative | Network 2.0 - P&D | Network 2.0 | Shaman Smith, Jennifer Beatty, Chris Allen, John R. Kozorra, Zachary McElwain | On Track | na | G: L3 | Active | TEMP L3 - Enter L3 | 2027-05-31 | 2027-05-31
Business Only Initiative: [Enabler] Canada Post Launch Support (DCA, Conting | 87128 | 7617 | Business Only Initiative | Network 2.0 - P&D | Network 2.0 | Jennifer Beatty, Manlio Staropoli, Brianna Cormier, Lakshmi Chaitanya Kakarla | On Track | Moving to L5 because post-launch support in Canada has ended and any incremental costs should be tracked in the overall Canada Transition Plan initiative. | K: L5 | Completed | L5 | 2025-05-30 | 2025-05-30
Business Only Initiative: [Enabler] Larger Vehicle Needs Associated with Net | 93469 | 7789 | Business Only Initiative | Network 2.0 - P&D | Network 2.0 | Amanda Sewell, Scott Love, Jennifer Beatty, Zachary McElwain | On Track | Placing on hold until vehicle forecast and process to track vehicle leases can both be finalized. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-12-01 | 2027-05-31
Business Only Initiative: [Enabler] P&D Contingency | 87989 | 8905 | Business Only Initiative | Network 2.0 - P&D | Network 2.0 | Matt Anderson, Tanner Sansonetti, Matthew Clark, Jennifer Beatty, Zachary McElwain | On Track | **13 April 2026:** Financials updated for Mar 2026 **12 March 2026:** Financials updated for Feb 2026 **11 Feb 2026:** Financials updated for Jan 2026 Financials updated for Dec 2025 | G: L3 | Active | TEMP L3 - Enter L3 | 2027-05-31 | 2027-05-31
Business Only Initiative: [Enabler] Service Providers Hiring Couriers Incent | 88108 | 8906 | Business Only Initiative | Network 2.0 - P&D | Network 2.0 | Matthew Noel, Courtney King, Brianna Cormier | On Track | N/a | G: L3 | Active | TEMP L3 - Enter L3 | 2024-09-23 | 2027-05-31
Business Only Initiative: Personal Liability and Property Damage (PLPD) Redu | 87993 | 8907 | Business Only Initiative | Network 2.0 - P&D | Network 2.0 | Joanna C. Bardos, Andrew Kuwik, David Scopa, Jennifer Beatty, Zachary McElwain | On Track | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-22 | 2027-05-31
Business w/ Tech Initiative: Global OnRoad Coordination Sys (Com. Disp ESSP) | 77048 | 7100 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Celly Surmacz, David Burgan | On Track | 3/11/2026 - Decomp to be completed by end of next week. 12/24/25 - Impact Assessment and scope finalized 8/27/25 - This initiative ID will be used for Phase 1 of Common Dispatch which will focus on enabling N2.0 ESSP stations. 06/18/25 - This initiative has been blocked due to higher priorities in SCO -- namely FRO and now GPDE. The foundational work is also dependent upon commercial initiatives that have not yet been prioritiized. We are working to identify the first piece of work we can move thru the op model / DRIVE process that will be led by SCO with minimal involvement/dependencies with commercial. 04/15/25 - Refining details to shape value bundles for initial work. | E: L2 | Active | L2 | 2023-04-18 | 2023-05-12
Business w/ Tech Initiative: Enabler - Foundation for LH Systems Modernization | 536 | 7205 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Allyson Burley | On Track | 12/10/25: Three months have passed since the move to production, with no issues. 5/14/25: In consideration of senior leadership decision/direction to utilize ROCS as the Enterprise LH Execution system, the decision was made to finish the dispatch validation foundation capability to align with revised scope. Revised milestone target: CY25 PI3 9/18/23: Decision was made this week for this goal of this initiative to remain focused on completing Dispatch and Arrival rules development for the TRX execution system (foundational work for Enterprise Surface Execution Eco-system). Additional future work for Enterprise Surface Execution Eco-System will be aligned under a new DRIVE initiative in WAVE. this initiative in WAVE. | K: L5 | Completed | L5 | 2022-05-23 | 2025-10-28
Business w/ Tech Initiative: Common Sort - Value Bundle 1 | 69924 | 7216 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Erin Wise, Adam Fettig, Stephen Murphy | Some Issues | On Track | G: L3 | Active | TEMP L3 - Enter L3 | 2024-10-07 | 2027-03-26
Business w/ Tech Initiative: Origin Market Surface First - N2.0 Tech Phase II / | 1913 | 7228 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Stephen Murphy, Jim Franklin, Donna Apollonio | On Track | 04.03.202506.11.2025 Cross-Network Flow Planning (Own the Border): Last capability: Production move complete | K: L5 | Completed | L5 | 2022-11-01 | 2027-10-05
Business w/ Tech Initiative: N2.0 Tech Phase 3 FY24 (Minus USGO Part 1 & LH Par | 8891 | 8041 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Hayden Kuhn, Victoria Bonetto | On Track | 4/23/2026 Submitted for L4 Updated start date to end of the month to gain business support and agreement on milestones and expected end dates. | H: SL4 | Active | SL4 Finance Domain Lead Approval | 2023-09-01 | 2029-02-23
Business w/ Tech Initiative: SSP Enablement for Surface LH Execution | 31862 | 9058 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Allyson Burley, Lisa Mangelsdorf | On Track | 3/25/26: Deployment to production complete, all validation successful. Closeout activities underway. 3/19/26: Deployment on track for week of 3/23 3/5/26: Final feature acceptance moved to 3/17. Deployment moved to week of 3/23 due to higher priority ROCS work. Delays due to: Ephemeral environment deployment,Code fixes.Infrastructure provisioning.Code and quality control review timeline,Header logic re-work 2/18/26: Resolving issue found in testing. Next step to complete testing and prepare for deployment. 2/5/26: Tech delivery date for milestone 75461 has moved back to week of March 6 to complete testing of code changes and testing to features E-484090 and E-512720. 12/3/25: Tech delivery date has moved to February 2026, to allow sufficient time to complete development and execute the multi-application deployment plan 11/15/24: Development and testing work for milestone 75461 continues as planned. IT forecasting completion in January 2026 due to work complexity and sequencing. 10/15/24: Development work for milestone 75461 continues as planned. IT forecasting completion in January 2026 due to work complexity and sequencing. 8/28/24: Using estimates developed as part of solutioning the Hydration of Trip Data to Core (75461) milestone, completion date was set to Jan 31,2026. This was reviewed and accepted by the IT and Business MD owners of the initiative - Jim Connolly and Mark Scott. 8/27/24: Visibility to Legacy Express Trips and Assets milestone (41498) was completed with launch of this capability in the Trip Execution (TRX) application.. 7/1/24: Leadership decision made to align the short term align and depart work to provide pre-peak visibility (31862) with other Linehaul Execution Initiatives to develop a longer term Surface Linehaul Solution: Initiative 536: Legacy ground departure and arrival capabilities will be completed in partnership with the existing work to develop dispatch and arrival business rule engines Initiative 45258: Legacy express work to identify depart and arrive business rules, and include them in the central business rule engine created by initiative 536. 4/18/24: Due to time needed to complete CLEAR documentation, review business case with Finance and obtain authorization, Leadership agreed to adjustment of target date for "Ability to arrive inbound trips from origin facility, either manually from a single source or via automation" milestone to H2 2025 3/25/24: IT and Business leadership determined additional funding is needed to support arrival (58637) and dispatch (58636) milestones, along with any functionality in single view of surface LH trips (75461) that wasn't included in the first request for CLEAR funding. 3/22/24: Leadership approved team recommendation to push out the "Ability to depart trips outbound from origin facility, either manually from a single source or via automation" milestone to H2 2025. Solutioning for this milestone will begin week of 3/25/24 to confirm approach and estimated IT effort. 3/21/24: Milestone created to track/monitor progress for adoption/hydration of core for LH Trip/asset/location/facility data. This work is a predecessor to enabling a single view of Surface LH trip data (combined FXE and FXG trips). The work was formally combined with milestone 41498 Visibility to FXE trips and assets, and is now separated out for tracking accuracy. 2/26/24: After further review of milestone 58882 "Add, update and manage FXE/FXG locations in the Facility Management System (FMT/OMT), decision was made to defer migrating location management from FXG TMS system to FMT/OMT, removing the transition from this initiative. While a decision was made to support FXG location management in FMT/OMT, this has not yet been determined for all of One FedEx. 12/18/23: Obtained TCH approval. IT MDs meeting on 12/18/23 to agree on architectural approach and associated timeline for delivering visibility to FXE moves. Outcome of this meeting will inform updated capability | I: L4 | Active | L4 | 2023-09-22 | 2026-03-27
Business w/ Tech Initiative: Manage Shipment Handling Unit Flow Plan | 78276 | 9325 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Stephen Murphy, Connor Bomba, Ashley Laird | On Track | . | K: L5 | Completed | L5 | 2024-03-14 | 2025-01-31
Business w/ Tech Initiative: FRO system legacy reduction to support N2.0 SSP |  | 91814 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Hayden Kuhn, Victoria Bonetto | On Track | Status is dependent on architecture and business timeline decisions, which are pending | E: L2 | Active | L2
Business w/ Tech Initiative: North American Shipment Flow Plan for Common Sort |  | 92265 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Stephen Murphy, Hunter McCormick | On Track | 25.10.20 Deliverables for 10/31 remain on track. 26.03.09 Work is on track to begin integration testing with Common Sort at the end of the month 26.04.06 PI Planning this week to identify remaining work and plan for completion | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-07 | 2026-06-30
Business w/ Tech Initiative: N2.0 One FedEx Reporting and Visibility - MVP1 (Pr | 51325 | 7200 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Traci Andrews, Ronald Thies | On Track | . | E: L2 | Active | L2 | 2024-01-31 | 2024-10-24
Business w/ Tech Initiative: [Enabler] Network 2.0 Financial Digital Tooling - | 72215 | 7456 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Jennifer Beatty, Jamie Heinzman | On Track | WE 11/13/2024: IMPORTANT: 202411 * Dataworks is reporting issues with deployment, impacting all of Finance Insights Platform (FIP) including Network 2.0 Financial Digital Tooling. * Alteryx Server installation at risk - tight timeline and impacted by deployment issue, also impacted by internal licensing hurdles WE 10/5/2024: IMPORTANT: 20241003 VP Meeting Attendees: •Finance: Megan Melichar, Sushil Sehrawat, Shravan Gunti, Jamie Heinzman, Scott Higgins •Dataworks: Tom Seipp, Srivanthi Peruru, Sourav Mohanty, Peter Murphy, Julie Smith, Vishwas Hannurkar Key Takeaways: Status Report – Alteryx Server in MS Azure o10/3/2024: Decision is Alteryx Server will be installed in MS Azure - aligned with Tony Kreager, Tom Seipp, Jeff Hurlbut, Scott Higgins oAlteryx Server remains the highest priority deliverable for the initiative oDW remains committed to providing solution oPrevious roadblock was installation of PAM (Infosec requirement) oOriginal Alteryx license is not usable. Can value be applied to future costs? Status Report – Migrating the Alteryx Modeling to MS Azure o10/3/2024: Direction is this is not a priority item and should be discontinued pending large scope work to define/align on work of Jeff Hurlbut and team. Certainly not to be prioritized above first item - Alteryx Server in Azure. oProject 72115 Network 2.0 Financial Digital Tooling: Plan for migration is in scope. Migration is NOT in scope. Next Steps: Jamie to update Feature in ADO to include decision & set to Ready for User Story Creation (done). Feature 370251: N2.0 ¦ Alteryx Modeling ¦ Enable Alteryx modeling through CY2025. Jamie to share Sourcing / Procurement POC for Alteryx. Joanna Barnas, Sourcing & Procurement Specialist-Senior (copied) Peter / Vishwas to update report with feedback from Scott & team Team to provide verbal update to Tom and Scott in 1 week (due 10/11/2024) Sravanthi and Megan agreed to a draft plan available to Tom and Scott in 2 weeks (due 10/18/2024). Include any risks / issues (e.g., Infosec requirements). Include Alteryx information re. typical installation. | E: L2 | Active | L2 | 2024-02-01 | 2025-09-15
Business w/ Tech Initiative: N2.0 Tech Phase 1 (18 month roadmap) | 1671 | 7816 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Megan C. Silva, David Fenster, Asma Jiwani | On Track | • Apr3,2023: Accelerated milestone dates were shared with N2.0 leadership based on using DRO solution for RLMO. • Mar 24, 2023: Communication re scope change for RLMO as a result of using DRO as interim solution •Mar 8, 2023: Hyperdrive 1 milestones were re-priortized and approved at SLT with focus on RLMO readiness with parallel efforts on closing fringe enablers for FXG SSP as capacity allows •Technical Approach for RLMO initial rollout has changed. RLMO Phase 1 epic is currently on pause as of 3/22 in favor of utilizing DRO for P&D planning to reduce complexity for short term. •EE SSP - Route Planning and Execution epic has been created to encompass the DRO solution that will be used for CY23 and CY24 EE SSP markets. Sep 13, 2023: Milestone # 6983. Full solution for FXE automated pickup cancellations. This milestone will be deferred to Phase 3 and cancelled in Phase 1 as workshops are taking place to rationalize pickup PFS with commercial. Sep 13, 2023: Milestone #6981 Fringe volume for Pharmacy. Added DG scope to be delivered by IT end of January for March SSP rollout. | K: L5 | Completed | L5 | 2022-11-01 | 2026-07-08
Business w/ Tech Initiative: Designated Workforce Phase 3 | 93802 | 8330 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Angiana Jones, Randy Kelley | On Track | 2/9/26: Work on Epic 1 (3+ Dispatches) is progressing as planned, with development scheduled to complete in June 2026, followed by testing and MTP in July 2026. Development for three of the four required applications is underway, and Pre‑Load Assist (Capability 1.4) is now targeted to begin toward the end of February. Although the development effort for PLA is larger than initially estimated and will not meet the original March 31 MTP date, Business and IT have aligned on a revised June 2026 completion timeline, which does not impact downstream work or alignment with broader N2.0 rollout schedules. No additional risks have been identified beyond the PLA schedule adjustment for Epic 1, and teams are actively advancing development, building out test plans and test cases, and coordinating identification of test resources to support timely delivery. Work is on track for the remaining capabilites—Multiple PSD Submits, Multiple FRO Submits, and Additional PSD Attributes— as development continues. Conceptual architecture for the remaining capabilities began on January 22, with solutioning expected to continue through late March to early April. 1/16/26: : The work for the remaining 3 epics/capabilities in DWF Phase 3 (Multiple PSD submits, Multiple FRO submits, Additional PSD attributes) continues with PRT/Core team calls on T-TH. The development timeline for Epic 1- Capability 1.4 (Pre-load Assist) has been updated to June 2026. Overall status is On Track with a revised timeline; development to be completed in June followed by testing and MTP in July 2026. 12/15/25: Exepedited Epic 1 recieved ARB and SCOPEL approvals prior to being handed off to the ARTs on 11/17, development at ART level continues. Remaining 3 capabilities/epics are being decomposed as a group, decomp expected to continue until late Jan 2026. 10/20/25: Epic 1- Dispatch Volume Assignment logical architecture complete. Solution architechure wrapping up final diagrams, ARB 2/3 on 10/27. Following ARB 2/3 approval, SCOPEL on 10/30 will be scheduled. 9/29/25: Met with CCH and revised the value prop and risk to customer. No impact to value prop 9/22/25: Recieved Gen0/1 VP approval on 9/25/25 for the following applications: Trip adapter, PSD-Planned Sort Date, FXGFEExecConvey-PlanConveyTrip, SAD-Service Area Design 9/16/25: Epic 1/Capability 1.0-Dispatch Volume Assignment identified to be exepedited by leadership, remaining 3 capabilities will not be exepeditied and will follow normal schedule Initial initiative (81132 - L3) was broken out into phases. Due to GPDE and Roadmap initiatives, additional capabilities have been added to DWF Phase 3 which require immediate solutioning and movement into L2. | E: L2 | Active | L2 Feedback Requested | 2024-07-22 | 2026-12-30
Business w/ Tech Initiative: [Enabler] Designated Courier Workforce Phase 4 | 96792 | 8331 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Angiana Jones, Randy Kelley | On Track | Initial initiative (81132 - L3) was broken off for phase 2. Additional initiatives have been created to represent the remaining phases. | C: L1 | Active | TEMP L1 - Create L1 LBC | 2024-12-31 | 2025-12-02
Business w/ Tech Initiative: Designated Courier Workforce Phase 5 | 96809 | 8332 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Andrew Kuwik, Angiana Jones, Randy Kelley | On Track | Initial initiative (81132 - L3) was broken off into just Phase 2. Additional initiatives have been created for the remaining phases of this project. | D: SL2 | Active | SL2 Finance Domain Lead Approval | 2025-01-01 | 2025-11-14
Business w/ Tech Initiative: [Enabler] Designated Courier Workforce Phases 1 & | 81132 | 9326 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Angiana Jones, Randy Kelley, Amanda Winter | On Track | 2/9/26: Premium Scoring is on track as teams work toward the February MTP and March 2026 readiness milestones. The updated Premium Scoring model is partially tested in L3, with remaining components planned by the end of February, followed by integrated E2E testing with DMUI fixes. DMUI is enabled from an IT standpoint at Myrtle Beach, with station access expected after February MTP updates, and both Myrtle Beach and Charleston pilots will remain paused until these fixes and model updates are validated. CLS rule issues at Myrtle Beach have been addressed through numeric based rules, with long term hierarchy changes required to prevent recurrence. In parallel, the Volume Assessment Team has defined the HU volume ramp approach, with a throttle Feature planned for creation by late February, development completing in April, and a five month scalability ramp toward 100% by September 2026. Key risks include two Cap 3.6 gaps (LIFE facilities without primary locations and US FXE stations not yet available in MOP service), system wide scalability concerns raised by SCO teams, and limitations in testing Contextual NOI due to missing Test Premium Shipper Accounts. Additionally, N2.0’s shift from market level to district level launches extends lead times to 8–9 months, positioning the earliest Premium Scoring district go live at September 2026. Despite these dependencies, teams remain aligned, risks are being managed, and pilot expansion opportunities remain for Spring 2026 once core updates are in place. 1/21/2026- Phase 2 is on track. The Myrtle Beach (MYBE) loaction is set to resume pilot. Updated Premium Scoring model is ready for testing and targeted to be completed by EO January, Dispatch Management User Interface (DMUI) changes required to support updated Premium Scoring are in progress and targeted to be completed in early February. The N2.0 launch team has advised that due to launch plans shifting from markets to entire districts the lead time required has increased from 6 months to 8-9 months, thus the earliest a station can go live with Premium Scoring is September 2026. 12/17/2025- Novemeber financial actuals updated. Phase 1 was successfully deployed in late July. Phase 2 (On Track) has been split into three key parts: •Part 1 – Designated Work Force Functionality – MTP complete. Launch date shifted to April 1 to accommodate station level preparedness. Will launch in Mobile market. •Part 2 – Premium Scoring Functionality – E2E Testing for Cap. 3.5 is unblocked. Utilizing alternative station for testing DG codes, testing scheduled pulled back to complete on April 11. * Part 2 -update 7/10/25- the DW determied premium score is not being applied to the HU in production becuase there are too many meessages for CSV (Coordinate Shipment View) to consume. DW is looking into alternatives to shrink the messages that CSV must comsume by not sending any scores for FXG pkgs and only sending when their is an update to the score. * Part 3 - Dispacth UI - new UI which is a front end for CLS which houses the rules for what pkgs get assigned to the DWF. Update 7/10/25- MTP is plnned for Early Ayg. Mote: this UI is not needed for Phase 3 and not neede for a launch of a few piot locations. However, it will be needed for a full scale launch, shichis current;y planned for early Cy2026. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-06-03 | 2028-02-04
Business w/ Tech Initiative: N2.0 - District Rollout Support (Zenith) |  | 107401 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Joshua N. Tyler, David Borchardt | Attention Needed | 01/2//2026 - cancellation approved by Stephanie Cohen during N2.0 Domain stand up meeting User Engagement • Facilitated cross-pod discussions and alignment ahead of NPET Program Increment (PI) planning to ensure shared understanding of N2.0 District Rollout Support (DRS) outcomes, learnings, and path forward. • Aligned with the NPET Product Manager on transitioning DRS learnings and completed work into broader Surface planning workstreams aligned to the PFS. Successes • Reached alignment to formally close N2.0 DRS as a standalone initiative and fold completed capabilities, documentation, and architectural artifacts into NPET Surface roadmap workstreams. • Established agreement to retire the DRS Planview ID and consolidate remaining scope, artifacts, and learnings under the existing Surface Planning Planview ID to reduce fragmentation and rework. • Preserved value from DRS feasibility work (User Interface, User Experience, data exploration, and modeling insights) to inform future Surface planning capabilities without further near-term delivery risk. In Progress / Next Steps • Ensure all DRS documentation, feasibility outputs, RITAs, and architectural learnings are captured and transitioned into the NPET Surface planning backlog. • Refine Surface planning approach to better align with PFS objectives, scalability expectations, and long-term Network and Linehaul planning needs prior to resuming development. • Support NPET PI planning discussions by clearly articulating what DRS validated, what remains unresolved, and where future investment will deliver scalable value. Risks / Callouts • Without consolidation, there is risk of losing institutional knowledge and repeating feasibility and alignment work across future Surface planning initiatives. • Delaying architectural alignment could reintroduce rework risk when Surface capabilities resume development. Leadership Ask • Acknowledge the closure of N2.0 DRS as a standalone initiative and support consolidation of all remaining scope, artifacts, and learnings into NPET Surface planning workstreams aligned to PFS. • Confirm expectations for when and how Surface planning capabilities will be re-prioritized for delivery following architectural and roadmap refinement. | G: L3 | Cancelled | TEMP L3 - Enter L3 | 2025-07-23 | 2026-05-29
Business w/ Tech Initiative: Standard Operating Procedure - Automated Planning |  | 109485 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Laura DeRose, Megan C. Silva, Laurie Nicholson, Chad Verbeek, Matthew Penix | On Track | Initiative development is already well underway in vendor environment, incorporating FedEx Cloud Platform standards and best practices. The goal is to port into FedEx environment in end-April and then test and deploy in May. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-07-31 | 2026-12-31
Business w/ Tech Initiative: Sort By Lookup Phase 2 |  | 114013 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Negar Solgi, Marina Gavranovic | On Track | **04/08/2026 -** * We had Commercial L2 Triage meeting. The commercial impact is the eTNMS service that will provide the range of barcode ids that we'll use to create a CONS HU. It already supports what we need, so their only involvement is on-boarding and testing. Commercial portfolio was added as the impacted portfolio and has to go through greenlight process. * Waiting for the Tech CLEAR which includes the cost documentation. Kyle and Melissa will be the managers working across the various ART leaders to pull that information together * Stakeholder review for detailed capability 2.3 analysis has been done last week and now the team are starting to work on solutioning for 2.3 and capability 2.5 detailed analysis. * Waiting for platform portfolio to give the approval. **03/30/2026** - * We met with N2.0 Domain Finance last week and it was decided to exclude hard benefits from Planview as it will be difficult to measure over the rollout timeframe and VB2 tech deployment starts after we stop tracking N2.0 benefits. •Sort Architecture has defined a percentage of what is needed. The Platform portfolio is now reviewing it to determine if it is enough to move forward to L3. **02/13/2026** - * Conceptual Architecture Process is over and the team is working on getting ARB approval and working on L2 planview checklist to move to L3 **07/31/ 2025** - * Team is working on solutions and ideas for obtaining business value for Common Sort VB2 to produce tangible values/savings needed for our lean business case. **04/17/2026** - * Platform team received the information they were looking for. Once they get them all, they will send the details to IT Operations for costing. * On Apr 22, 2026, Sanjay will present in the Platform ARB and then submit the costing to PEO so they can forward it to Finance and obtain Greenlight approval. * Commercial L2 Triage meeting was done. The commercial impact is the eTNMS service that will provide the range of barcode ids that we'll use to create a CONS HU. It already supports what we need, so their only involvement is on-boarding and testing. * L3 PRT sessions are happening on a weekly basis. 2.3 in solutioning and 2.5 in detailed capability analysis. | E: L2 | Active | L2 | 2025-09-23 | 2028-11-06
Business w/ Tech Initiative: North American Shipment Flow Planning |  | 170632 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Joshua N. Tyler | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: FRO Epic 3/4 Gap Closure |  | 163574 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Jon-Elliott Burke, Rip Rucker, Ramon Mosqueda, Darma Taimuty, Jessica Riley | On Track | N/A | E: L2 | Active | L2
Business w/ Tech Initiative: DTWR & ONTR Interoperability - Sort by Look Up |  | 177611 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Laura W. Tam, Erin Wise | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Consume Assets for Surface LH Execution |  | 183739 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Allyson Burley, Jordan Johnson | On Track | Submitted to L2 | E: L2 | Active | L2 | 2026-11-27 | 2026-11-27
Business w/ Tech Initiative: Global OnRoad Coordination Sys (Com. Disp CSSP) |  | 185158 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Celly Surmacz | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Unified Surface LH Operational Location Mgmt |  | 185713 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Johanne Doucet, Allyson Burley | On Track | 2026-04-16: PPM Approval; PRT Kickoff; Begin weekly Assessment and Decomp meetings 2026-04-02: Moved to L2; Submitted PPM form 2026-03-20: The majority of the assessment looks to be complete and the architects are taking some time now to finalize the agreement of the architectural ownership. 2026-02-18: Submitted UPR Request (1838669), Waiting for Architectural Review with EPM | E: L2 | Active | L2
Business w/ Tech Initiative: Consume Surface LH TSP and Employee Drivers |  | 187728 | Business w/ Tech Initiative | Network 2.0 - Technology | Network 2.0 | Allyson Burley, Pete Mitrou | On Track | 3.2.26 - On Track - Waiting for finance approval to advance to L2 3.5.26 - On Track - Waiting on EPM call invite. 3.12.26 - On track - Waiting on EPM call invite. L1 Architectural assessment complete. TPI estimate complete. 4.7.26 - On track - Entered L2, completed Value proposition / customer service risk 4.14.26 - On Track - PPM was submitted and has been approved. PPM Project 1842257 has been created. | E: L2 | Active | L2
Business Only Initiative: [Enabler] Security Threat Assessment for Legacy Gr | 87294 | 6954 | Business Only Initiative | Network 2.0 - Workforce & Communications | Network 2.0 | Ilazabeth Obi, Chris Allen, Jennifer Beatty, John R. Kozorra, Zachary McElwain | On Track | Network 2.0 is working to certify legecy FXG employees during rollout. This initiative is no longer needed at this stage. Announcement to pursue 100% STA regardless of N2.0 status has been made as of 1/12/2026. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-03-24 | 2027-05-31
Business Only Initiative: [Enabler] 401K Package Handler Benefit Alignment | 87567 | 7458 | Business Only Initiative | Network 2.0 - Workforce & Communications | Network 2.0 | Jennifer Beatty, Renee Miller, Zachary McElwain | On Track | 07/01/2025: Moving this initiative to L5 since the costs are already in the FY25 run-rate and Planview now needs to match the forecast / plan. Additionally, a separate / new initiative was entered in the Enterprise Processes and Tools Domain to track the savings associated with switching to voluntary enrollment. 05/29/2025: Variance is attributable to annual true-up of company matching contributions. Match before the true-up was $17,482,824 and with the addition of the match true-up of $4,792,358, the total match for May was $22,153,604. 05/16/2025: Status updated through April 2025. Trends consistent. 025: Confirmed FY25 Baseline complete 03/03/2025: Company matching contributions and participant recordkeeping fees are monitored and updated monthly. Costs are higher than estimated because participation rates among package handlers are higher than expected. With the exception of peak hiring, trends are consistent. 02/14/2025: January has five pay dates, therefore higher match cost. When comparing to November (which also has five pay dates), costs are slightly higher and most likely attributable to tail end of peak. 02/06/2025: Company matching contributions and participant recordkeeping fees are monitored and updated monthly. Costs are higher than estimated because participation rates among package handlers are higher than expected. With the exception of peak hiring, trends are consistent. Note that months with five pay dates (August 2024, November 2024 and January 2025) will show higher costs, but again, the trend here is consistent. November costs are higher because November includes five pay check dates instead of the typical four. | K: L5 | Completed | L5 | 2027-05-31 | 2027-05-31
Business Only Initiative: [Enabler] Dangerous Goods Training | 87580 | 9248 | Business Only Initiative | Network 2.0 - Workforce & Communications | Network 2.0 | Keith Holmes, Jennifer Beatty, Deborah Lauro, Zachary McElwain, John R. Kozorra | On Track | Moving to L3. | G: L3 | Active | TEMP L3 - Enter L3 | 2027-05-31 | 2027-05-31
Business w/ Tech Initiative: One FedEx Global Facility Identification Expansion |  | 108807 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Rodrika Thompson, Rip Rucker | On Track | 04/07 - Development is in progress. 02/18 - E2E testing is scheduled from April 1 to May 15, with our Money Step date being May 29th. 11/14 - Worked with Tom to get the Forecasted Cost updated for L3 Financials 11/03 - Final ARB and solution architecture is complete. 10/14 - Updated PPM number is 1227673. System will not allow us to update it. 4/22 - Working with Rip and John to get the GPDE initiative moved to L2. 06/11 - Still engaging in L2 conceptual architcture until the week of June 20th. The team is aiming to have the architecture peer review next week as well and our ARB is scheduled for June 26 with all of the MDs. After this discussion we are hoping to be set to move into solutioning for L3. 09/02 - We are scheduled to go through PEL on Wednesday, September 3. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-05-01 | 2026-07-03
Business w/ Tech Initiative: Vehicle Incident Reporting |  | 109780 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Adela Djajamartana, Andrea Simons | Some Issues | 6/4 - Will need to reach out to an Enterprise Architect for advise on how to move forward. Vehicle Incident Reporting encompasses many different areas, & it's not clear is this should all be addressed as 1 big initiative, or if it we need to have a couple child initiatives that represent each area that uses the reporting. 7/10 - 1) applied for new status reason codes. specific to Trailer Disruption events 2) identified proper Data Architecture team(s) to conduct project analysis to determine if the effort should be split into smaller segments( Meeting to be held next week) 8/6: A brand new status code with associated reason code will be implemented & loaded on 9/15 to provide additional visibility when a pkg has been involved in an incident. This will also enable better detailed reporting to provide metrics around the it. We are still looking for the best way to quantify value | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Spotlight ENM |  | 110818 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Carmen Rullo, Patrick Easley | On Track | 8/18/2025 > Launched 8/1/2025 > Switching data ingestion from directquery to import logic. Will increase stability and user experience > Launch still for mid-August 7/22/2025 > ENM has experienced some performance issues within the PBI embedded. Working with MSFT to try to figure out > Launch has been delayed until mid-August 7/9/2025 > ENM to be included in the expansive SPOTlight enhamcenets going in for July 28th. > Currently in dashboard development 6/27/2025 > Business team working with Datworks to validae DDS data. > Dashboarding expected to start early next week 6/17/2025 > Submitted initiative to L3 in Planview > DDS data is in CFR, however curation will seemingly take a little longer for DW to clean up due to the dataset needing flattened to access service number column > As of now, not too worried about timeline issues for mid July 6/12/2025 >Production data staging on-track to be finalized by this Friday >Will work through data curations starting next week >Working through some issues with the PPM# pushing through this iniative to L3 6/4/2025 > Working through ingestion of Enterprise Network Monitor (ENM) data and Delivery Itinerary data from Delivery Destination Service (DDS) into Atlas. Est completion 6/13 > Testing SQL warehouse setup > Starting curation code in anticipation of data ingestions | G: L3 | Active | TEMP L3 - Enter L3 | 2025-04-28 | 2025-07-11
Business Only Initiative: Improve payment structure and demand planning proc | 27409 | 6711 | Business Only Initiative | F&LM - Core Fleet | P&D | Brandon Woodward, Richard Lapradd | On Track |  | K: L5 | Completed | L5 | 2023-06-13 | 2024-05-24
Business w/ Tech Initiative: Align settlement model with daily op performance | 27413 | 6714 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Mattew Stevenson, Megan C. Silva, Victoria Bonetto, Chris Helkowski | On Track | **04/10/2026**: Enterprise Ranking - **64** **Supply Chain Organization (SCO):** * SCO L3 greenlight approval on 1/15/2026 * No update this week for SCO. **Platform:** * We have a call on the schedule for Friday March 13, 2026 with SCO Solutions Architects, Platform PRT Lead, Data and AI Product Manger Lead to discuss the solutioning of this data for FRO-A. * March 10, 2026 - Platform PRT Lead sent the TPI Estimates (for both Platform and Data and AI) to Finance for costing for FRO-A * Platform TPI estimates have been submitted to Finance. * Next Steps - * Recieve Finance Platform costing and upload to Planview. * Greenlight / EGC . **Data and AI (DAI):** * We recieved costing from DAI back on December 4, 2025; before the merger of Platform and DAI. * March 16, 2026 - Recieved Data & AI costing from Finance - Uploaded into Planview. * Next Steps - * Greenlight / EGC **RouteSmart**: * March 9, 2026 - We worked with RouteSmart and the leadership team to come up with a plan structure for Statements of Work, Payment, and Data delivery for the development of FRO-A. * **March 30** - met with leadershipand discussed breaking out the costing for RouteSmart * **March 31** - started working on statements of work. * Next Steps - * Send RouteSmart costing to Finance and once rteviewed and sent back - upload to Planview * Greenlight / EGC **04/02/2026**: Enterprise Ranking - **64** **Supply Chain Organization (SCO):** * SCO L3 greenlight approval on 1/15/2026 * No update this week for SCO. **Platform:** * We have a call on the schedule for Friday March 13, 2026 with SCO Solutions Architects, Platform PRT Lead, Data and AI Product Manger Lead to discuss the solutioning of this data for FRO-A. * March 10, 2026 - Platform PRT Lead sent the TPI Estimates (for both Platform and Data and AI) to Finance for costing for FRO-A * Platform TPI estimates have been submitted to Finance. * Next Steps - * Recieve Finance Platform costing and upload to Planview. * Greenlight / EGC . **Data and AI (DAI):** * We recieved costing from DAI back on December 4, 2025; before the merger of Platform and DAI. * March 16, 2026 - Recieved Data & AI costing from Finance - Uploaded into Planview. * Next Steps - * Greenlight / EGC **RouteSmart**: * March 9, 2026 - We worked with RouteSmart and the leadership team to come up with a plan structure for Statements of Work, Payment, and Data delivery for the development of FRO-A. * **March 30** - met with leadershipand discussed breaking out the costing for RouteSmart * **March 31** - started working on statements of work. * Next Steps - * Send RouteSmart costing to Finance and once rteviewed and sent back - upload to Planview * Greenlight / EGC **3/27/2026**: Enterprise Ranking - **49** **Supply Chain Organization (SCO):** * SCO L3 greenlight approval on 1/15/2026 * No update this week for SCO. **Platform:** * We have a call on the schedule for Friday March 13, 2026 with SCO Solutions Architects, Platform PRT Lead, Data and AI Product Manger Lead to discuss the solutioning of this data for FRO-A. * March 10, 2026 - Platform PRT Lead sent the TPI Estimates (for both Platform and Data and AI) to Finance for costing for FRO-A * Platform TPI estimates have been submitted to Finance. * Next Steps - * Recieve Finance Platform costing and upload to Planview. * Greenlight / EGC . **Data and AI (DAI):** * We recieved costing from DAI back on December 4, 2025; before the merger of Platform and DAI. * March 16, 2026 - Recieved Data & AI costing from Finance - Uploaded into Planview. * Next Steps - * Greenlight / EGC **RouteSmart**: * March 9, 2026 - We worked with RouteSmart and the leadership team to come up with a plan structure for Statements of Work, Payment, and Data delivery for the development of FRO-A. * Meeting scheduled for March 27 with leadership to work on RouteSmart Costing * Next Steps - * Send RouteSmart costing to Finance and once rteviewed and sent back - upload to Planview * Greenlight / | E: L2 | Active | L2 & CCH | 2023-08-01 | 2027-12-30
Business w/ Tech Initiative: NOP Delivery Forecast | 71066 | 6727 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Steven Nelson, Brian McElhinny, Patrick Easley | On Track | 2/13/2026 * Enterprise ranking 35 * Weekly working sessions started 10/13/2025 * Updated lead IO to Brian McElhinny * Updated milestones to align with new project plan 7/25/2025 * Entered L3 * Dashboard data discovery is in progress; meeting with Dataworks on Tuesday, 7/22 * Reviewing 1.4 requirements with Dataworks on Wednesday, 7/23 6/13/2025 * Submitted to L3; pending SVP Finance approval. * Initital testing is complete by IO. Final approval required by business area leads. * Forecast model ready to be deployed into production pending business area approval. * To ensure the initiative delivers its full capabilities, we’ll need greater support and ownership from the business team that owns it. 6/6/2025 * Cleaning up the initiative for L3 submission --- linking to the enabler is pending until I’m added as secondary IO to #6714. * We're currently testing and validating NOP 1.2, but need existing forecast and historical data to complete the comparison. * To ensure the initiative delivers its full capabilities, we’ll need greater support and ownership from the business team that owns it. | G: L3 | Active | TEMP L3 - Enter L3 | 2024-02-27 | 2026-12-24
Business w/ Tech Initiative: [ENABLER] SPOTlight Evolution - Customer Experienc | 65383 | 6827 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Stacey Sabo, Carmen Rullo | On Track | Updated Data and AI | K: L5 | Completed | L5 | 2023-12-05 | 2025-03-31
Business w/ Tech Initiative: Global P&D Ecosystem Enabler | 86931 | 7406 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Rip Rucker, Erin Greco, Hayden Kuhn, Cheryl A. Smith | On Track | N/A | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-29 | 2035-10-26
Business w/ Tech Initiative: [ENABLER] SPOTlight Evolution - NW 2.0 Service Exc | 81470 | 7876 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Carmen Rullo, Stacey Sabo | On Track |  | K: L5 | Completed | L5 | 2024-08-01 | 2024-10-18
Business w/ Tech Initiative: Suspend PPOD on Ground Economy Stops | 85769 | 8123 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | James Shields, Tyson Wolfe | On Track | Decision from 11/06 CCH | E: L2 | Cancelled | L2 & CCH | 2024-08-21 | 2024-08-29
Business Only Initiative: Recoup USPS overpayment | 83153 | 8323 | Business Only Initiative | F&LM - Core Fleet | P&D | James Kurtz | On Track | Actively working with legal and the USPS for next steps as this progresses. No timelines set, other than going through the process for submission escalation for higher level USPS / council review. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business Only Initiative: Optimize Peak settlement spend--Driver Years of Ex | 83156 | 8333 | Business Only Initiative | F&LM - Core Fleet | P&D | Jillian Litos | On Track |  | K: L5 | Completed | L5 | 2024-07-02 | 2024-11-22
Business w/ Tech Initiative: F&LME Settlement Model SAS Conversion | 83161 | 8383 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Tyson Wolfe | On Track | Initiative no longer needed for SAS migration | C: L1 | Cancelled | L2 - Enter Value Prop
Business Only Initiative: P&D Geographic Planning and Optimization | 322 | 8785 | Business Only Initiative | F&LM - Core Fleet | P&D | James Shields | On Track |  | K: L5 | Completed | L5 | 2022-11-08 | 2025-01-30
Business w/ Tech Initiative: SPOTlight- | 563 | 8896 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Carmen Rullo, Patrick Easley | On Track | SPOTlight application continues to be in steady-state since January. Waiting for contract stand-up for L4 time period. | K: L5 | Active | L5 Feedback Requested | 2022-09-30 | 2025-01-01
Business w/ Tech Initiative: MEDALS (G/S/B) | 562 | 9007 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Patrick Easley, Carmen Rullo | On Track | Submitted for L5 review following Steph Stahovic's guidance | K: L5 | Active | TEMP L5 - Enter L5 | 2022-03-01 | 2025-01-24
Business w/ Tech Initiative: N2.0 Settlement Automation | 51028 | 9035 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Matt Anderson, Prasham Jain | Some Issues | **4/16/2026:** Architecture review scheduled for 4/17. Current rank is 214. **4/8/2026:** Awaiting architecture review. Current rank is 220. **4/1/2026:** Awaiting architecture review. Current rank is now 232. **3/25/2026:** Awaiting architecture review. Current rank is now 224. **3/18/2026:** Awaiting architecture review. Current rank is 213. EPM has confirmed this initiative is no longer on pause and states that architecture works through priority rank order, but has provided no indication of how quickly that occurs for L1 which should be a light review. **3/11/2026:** Still awaiting architecture. Current rank is 213. Supposedly this initiative is still flagged somewhere as being "on pause"; trying to identify where that is notated and remove that identifier so architecture can be assigned accordingly. **3/9/2026**: Awaiting Architecture Review. The current rank in queue is 215. **3/5/2026**: Awaiting Architecture Review. The current rank in queue is 208. **2/26/2026**: Awaiting Architecture Review. The current rank in queue is 211. **2/19/2026**: Awaiting Architecture Review. The current rank in queue is 217. **2/13/2026**: Awaiting Architecture Review. The current rank in queue is 215. **2/6/2026**: Awaiting Architecture Review. The current rank in queue is 216. **1/30/2026**: Awaiting Architecture Review. The current rank in queue is 220. **1/21/2026**: Updated demand description and completed all L1 LBC prompts. Reached out to CCH lead (Karen McConnico) to schedule SL2 readiness meeting. **01/16/2026:** Held preliminary L1 QA check with Commercial Domain QA Expert/CCH lead (Karen McConnico) to update demand description. CCH guidance was also given and confirmed there is no Commercial value proposition impact with this initiative. *Next steps -* complete L1 LBC and then schedule SL2 readiness with Karen McConnico to assess and approve for SL2 approval **1/14/2026**: Updated Planview with more relevant information. Scheduled time to meet and review with CCH Lead (Karen McConnico). **1/8/2026**: Held meeting with department MD to discuss scope of iniative. **12/1/2026**: Updated Primary IO from Andrew Kuwik to Bryce Lindsley. Matt Anderson also added as IO. | D: SL2 | Active | SL2 Domain Lead Approval | 2024-07-22 | 2025-03-06
Business Only Initiative: Global P&D Ecosystem FORGE Enabler | 94240 | 9459 | Business Only Initiative | F&LM - Core Fleet | P&D | Ryan P. Baker, Rip Rucker, Ben Dabat | On Track | New IO assigned to this initiative. Currently working through and cleaning up initiative details. | K: L5 | Completed | L5 | 2024-10-01 | 2025-05-30
Business w/ Tech Initiative: CPC Broker Retention |  | 130904 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | David Burgan, Abhimanyu Sharma, Joseph King | On Track | Cancelling due to finding an alternative that did not require any coding or tech changes. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: FRO Routing Sequence - SPOTlight |  | 153749 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Samantha Nagle | On Track | 4/23/26 - Enterprise Raking 50 (L2) Wrapping up decomp, conceptual architecture should be starting next week. Reviewed capabilities with SPS and Service representatives. 4/16/26 - Enterprise Raking 49 (L2) Decomp ongoing 4/9/26 - Enterprise Raking 49 (L2) Decomp began 4/1 and we are having meetings twice a week. Currently working on defining capabilities 3/20/26 - Enterprise Ranking 58 (L2) Had team introduction meeting with architecture group. Provided overview of project and made plans for Decomp kickoff and cadence. First decomp meeting will be next week with a regular twice a week 2hr call cadence. 3/12/26 - Enterpirse Ranking 59 (L2) D&AI Architect assigned is Raja Kumar. Other architeture team members identifies. Sam Gaskin will set up a kickoff meeting. 3/5/26 - enterprise Ranking 57(L2) Determined data ingestion form will require assitance from an architect. Still waiting to be assigned 2/26/26 - Enterprise Ranking 57 (L2) Working on a data ingestion request to keep movement with IT. No updates relating to Architecture review. 2/18/26 - Enterprise Ranking 56 (L2). Still waiting on offical start for Architeture review or next steps. Was reached out to by Madu Kallemoochikkal Madhavan, he said he was assigned EA but was looking for information on when L2 analysis was starting. I informed him I was waiting on guidance. I also revieced instructions to complete an ingestion intake request for ATLAS, which I will begin this week. 1/22/26 - N2.0 roadmap boosted. Current Enterprise Ranking around 52. No word from D&AI or anyone else on architecture review or next steps. 12/6 - Added to N2.0 Roadmap and approved to move forward by ExCom 11/21 - EPC had the T-Size updated from medium to small in another effort to boost priority. D&AI portfolio remains as impacted. 11/14 - Follow up from Emilee: Your initiative, FRO Routing Sequence – SPOTlight #153749, was brought to the EPC (Enterprise Prioritization Council) for a recent booster request. An action item was taken to review the scope inclusive of business context for owning the dashboard and the ask of the portfolio being a data connection. EA did review this initiative and determined based on that understanding of scope, the only impacted portfolio is SCO. Due to this only impacting 1 portfolio and there being no soft or hard benefits in the business case, we recommend for you to cancel this initiative out at business with tech and resubmit as local enhancements for SCO. 11/7 - Notes from EPC: Booster re-reviewed for # 153749/ FRO Routing Sequence – SPOTlight in the P&D Domain Not approved as of now This initiative was brought to EPC on 10/23 and was prioritized at 216 on the L2 list. The primary type of value was changed to “Service – Modernization” and it was given a “high” primary type of value impact, which lead to a “natural boost” to enterprise priority 145. After discussions with the domains, it was determined that there were no other highly-prioritized initiatives that could have their scope bundled with this one. Next steps are for @Emilee James to circle back with the architecture teams to confirm impacted portfolios and sizing as well as whether or not this work requires SAD architecture for D&AI 10/22- Updating Primary Type of Value for prioritization. It appears that I cannot also update the Priamry Type of Value Impact so I will be entering a PDSM ticket for that. 10/15 - Gathering information for L2. Drafting rough milestones to be reviewed by appropriate owners. Setup a touch point between parties involved with this initiative and the internal reporting initiative (Improve Visibility to Plan vs. Actual FRO Seqeunce - 143646) 10/2- Submitting for SL2 08/27 - Updating LBC | E: L2 | Active | L2
Business Only Initiative: SPOTlight - CSCA |  | 160581 | Business Only Initiative | F&LM - Core Fleet | P&D | Jessica Riley | On Track | 08/26 - Working with SPOTlight team to include metric in dashboard. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: MEDALS - PPOD |  | 160584 | Business Only Initiative | F&LM - Core Fleet | P&D | Jessica Riley | On Track | 08/26 - MEDALS team has data - will work with team to pull metrics into MEDALS | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: GPDE Bundle 2 Postal Code Overlap |  | 163564 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Seth D'Mello | On Track | 10/15 Architecture Reviewed, added file and T-Shirt size. Impacting Supply Chain Ops and taken on by Enterprise Architecture. 10/14 Awaiting Architecture Review 9/15 Triage | E: L2 | Active | L2
Business w/ Tech Initiative: SPOTlight - CSCA |  | 163571 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Jessica Riley, Ashley Semple | Attention Needed | 2/26/2026 : Backlog Enterprise Ranking: 176 (L2) | E: L2 | Active | L2 Feedback Requested
Business w/ Tech Initiative: GCP & P&D Data Migration |  | 164522 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Jessica Riley, Eric Rowland | Attention Needed | 2/26/2026: Backlog Enterprise Ranking: 110 (L2) | E: L2 | Active | L2
Business w/ Tech Initiative: Last Mile Performance |  | 91513 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Prasham Jain, Sarah Mertz, McKenzie Worden, Bryce Lindsley, Matt Anderson, Carmen Rullo | On Track | 4/24/2026: * Enterprise Ranking - 54 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 4/17/2026: * Enterprise Ranking - 55 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 4/10/2026: * Enterprise Ranking - 54 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 4/3/2026: * Enterprise Ranking - 55 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 3/27/2026: * Enterprise Ranking - 58 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 3/20/2026: * Enterprise Ranking - 63 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 3/13/2026: * Enterprise Ranking - 63 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 3/6/2026: * Enterprise Ranking - 135 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 2/27/2026: * Enterprise Ranking - 137 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 2/20/2026: * Enterprise Ranking - 136 (L2) * Waiting on Architecture Decompostion * This will allow to move from L2 to L3 | E: L2 | Active | L2 | 2025-10-01 | 2025-11-28
Business w/ Tech Initiative: P&D Full GAS Metadata Adoption |  | 167323 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Leslie Velderman, Rip Rucker | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SPOTlight - Canadian TSP Access Expansion |  | 168066 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Jonathan Fako | On Track | 4/24/2026 * Enterprise Ranking: 270 (L1) * Awaiting prioritization of SPOTlight initiatives 4/17/2026 * Enterprise Ranking: 275 (L1) * Awaiting prioritization of SPOTlight initiatives 4/10/2026 * Enterprise Ranking: 292 (L1) * Awaiting prioritization of SPOTlight initiatives 4/3/2026 * Enterprise Ranking: 298 (L1) * Awaiting prioritization of SPOTlight initiatives 3/27/2026 * Enterprise Ranking: 298 (L1) * Awaiting prioritization of SPOTlight initiatives 3/20/2026 * Enterprise Ranking: 291 (L1) * Awaiting prioritization of SPOTlight initiatives 3/13/2026 * Enterprise Ranking: 284 (L1) * Awaiting prioritization of SPOTlight initiatives 3/6/2026 * Enterprise Ranking: 283 (L1) * Awaiting prioritization of SPOTlight initiatives 2/27/2026 * Enterprise Ranking: 283 (L1) * Awaiting prioritization of SPOTlight initiatives 2/20/2026 * Enterprise Ranking: 287 (L1) * Awaiting prioritization of SPOTlight initiatives | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Spotlight - Mobile UI and MFA Enhancement |  | 168071 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Patrick Easley | On Track | **4/27/2026** Enterprise Ranking: 274 (L1) Update: Awaiting prioritization. **4/17/2026** Enterprise Ranking: 280 (L1) Update: Awaiting prioritization. **4/10/2026** Enterprise Ranking: 291 (L1) Update: Awaiting prioritization. **4/3/2026** Enterprise Ranking: 302 (L1) Update: Awaiting prioritization. **3/27/2026** Enterprise Ranking: 296 (L1) Update: Awaiting prioritization. **3/20/2026** Enterprise Ranking: 295 (L1) Update: Awaiting prioritization. **3/13/2026** Enterprise Ranking: 287 (L1) Update: Awaiting prioritization. **3/6/2026** Enterprise Ranking: 282 (L1) Update: Awaiting prioritization. **2/27/2026** Enterprise Ranking: 289 (L1) Update: Awaiting prioritization. **2/20/2026** Enterprise Ranking: 290 (L1) Update: Awaiting prioritization. **2/13/2026** Enterprise Ranking: 286 (L1) Update: Awaiting prioritization. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Spotlight PFS - GenAI Chatbot |  | 168075 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Patrick Easley | On Track | **4/24/2026** Enterprise Ranking: 325 (L1) Update: Awaiting prioritization. **4/17/2026** Enterprise Ranking: 330 (L1) Update: Awaiting prioritization. **4/10/2026** Enterprise Ranking: 341 (L1) Update: Awaiting prioritization. **4/3/2026** Enterprise Ranking: 351 (L1) Update: Awaiting prioritization. **3/27/2026** Enterprise Ranking: 343 (L1) Update: Awaiting prioritization. **3/20/2026** Enterprise Ranking: 341 (L1) Update: Awaiting prioritization. **3/13/2026** Enterprise Ranking: 333 (L1) Update: Awaiting prioritization. **3/6/2026** Enterprise Ranking: 329 (L1) Update: Awaiting prioritization. **2/27/2026** Enterprise Ranking: 337 (L1) Update: Awaiting prioritization. **2/20/2026** Enterprise Ranking: 338 (L1) Update: Awaiting prioritization. **2/13/2026** Enterprise Ranking: 334 (L1) Update: Awaiting prioritization. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Spotlight PFS - Live Data and Mobile Notifications |  | 168078 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Carmen Rullo, Prasham Jain | On Track | **4/23/2026** * Enterprise Ranking: 278 (L1) * Update: Awaiting prioritization **4/16/2026** * Enterprise Ranking: 284 (L1) * Update: Awaiting prioritization **4/09/2026** * Enterprise Ranking: 295 (L1) * Update: Awaiting prioritization **4/02/2026** * Enterprise Ranking: 306 (L1) * Update: Awaiting prioritization **3/26/2026** * Enterprise Ranking: 300 (L1) * Update: Awaiting prioritization **3/19/2026** * Enterprise Ranking: 290 (L1) * Update: Awaiting prioritization **3/12/2026** * Enterprise Ranking: 289 (L1) * Update: Awaiting prioritization **3/5/2026** * Enterprise Ranking: 284 (L1) * Update: Awaiting prioritization **2/26/2026** * Enterprise Ranking: 290 (L1) * Update: Awaiting prioritization | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SPOTlight - Data Exporting/Mobile Device Reporting |  | 168331 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Jonathan Fako | On Track | 4/24/2026 * Enterprise Ranking: 272 (L1) * Awaiting prioritization of SPOTlight initiatives 4/17/2026 * Enterprise Ranking: 277 (L1) * Awaiting prioritization of SPOTlight initiatives 4/10/2026 * Enterprise Ranking: 293 (L1) * Awaiting prioritization of SPOTlight initiatives 4/3/2026 * Enterprise Ranking: 300 (L1) * Awaiting prioritization of SPOTlight initiatives 3/27/2026 * Enterprise Ranking: 300 (L1) * Awaiting prioritization of SPOTlight initiatives 3/20/2026 * Enterprise Ranking: 293 (L1) * Awaiting prioritization of SPOTlight initiatives 3/13/2026 * Enterprise Ranking: 286 (L1) * Awaiting prioritization of SPOTlight initiatives 3/6/2026 * Enterprise Ranking: 285 (L1) * Awaiting prioritization of SPOTlight initiatives 2/27/2026 * Enterprise Ranking: 285 (L1) * Awaiting prioritization of SPOTlight initiatives 2/20/2026 * Enterprise Ranking: 289 (L1) * Awaiting prioritization of SPOTlight initiatives | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: SPOTlight - Report Access Controls |  | 168430 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Jonathan Fako | On Track | 4/24/2026 * Enterprise Ranking: 276 (L1) * Awaiting prioritization of SPOTlight initiatives 4/17/2026 * Enterprise Ranking: 281 (L1) * Awaiting prioritization of SPOTlight initiatives 4/10/2026 * Enterprise Ranking: 297 (L1) * Awaiting prioritization of SPOTlight initiatives 4/3/2026 * Enterprise Ranking: 304 (L1) * Awaiting prioritization of SPOTlight initiatives 3/27/2026 * Enterprise Ranking: 304 (L1) * Awaiting prioritization of SPOTlight initiatives 3/20/2026 * Enterprise Ranking: 297 (L1) * Awaiting prioritization of SPOTlight initiatives 3/13/2026 * Enterprise Ranking: 289 (L1) * Awaiting prioritization of SPOTlight initiatives 3/6/2026 * Enterprise Ranking: 288 (L1) * Awaiting prioritization of SPOTlight initiatives 2/27/2026 * Enterprise Ranking: 289 (L1) * Awaiting prioritization of SPOTlight initiatives 2/20/2026 * Enterprise Ranking: 291 (L1) * Awaiting prioritization of SPOTlight initiatives | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: ALT VAN Scan in FORGE |  | 170574 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Laura Ashmore, Ryan P. Baker | On Track | 4/23/26 Enterprise Ranking 104 4/15/26 Enterprise Ranking 105 4/09/26 Enterprise Ranking 103 04/02/26 Enterprise Ranking 102 3/26/26 Enterprise Ranking 103 3/19/26 Enterprise Ranking 113 3/12/26 Enterprise Ranking 117 3/5/26 Enterprise Ranking 118 2/26/26 Enterprise Ranking 115 Arch Alignment meet on 2/20/26 was complete moved to L2 2/18/26 Enterprise Ranking 54 Gate: CL1 Satus: On Track Significant change to prioritization ranking due to change in ESI to Service instead of Customer Service. I also changed the primary value type to correct reflect Service Moderinatization. At the same time this change was being made, Mark Engstrom advised they were working toward approval this Friday, February 20. We should have an update soon as to outcome from Architectural Review. 2/13/26 Enterprise Ranking 251 Waiting for Architectural Alignment meeting submitted for ESI change to Customer Service 1/14/26 to the owner/delegates have made contact with Justin Troy about the request, however, have not receieved a response confirming if the request has been approved. I sent follow up request 2/6/26/ & 2/13/26 12/19/25 LBC waiting on Architectural Alignment meeting 12/17/25 Submitted for EPM Review SL2 11/28/25 Starting Lean Business Case | D: SL2 | Active | SL2 Domain Lead Approval
Business w/ Tech Initiative: SPOTlight - Safety/SRI Data |  | 177912 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Jonathan Fako | On Track | 4/24/2026 * Enterprise Ranking: 302 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are currently testing ingestions and curations in development environment before moving to production. 4/17/2026 * Enterprise Ranking: 307 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are currently testing ingestions and curations in development environment before moving to production. 4/10/2026 * Enterprise Ranking: 325 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are currently testing ingestions and curations in development environment before moving to production. 4/3/2026 * Enterprise Ranking: 331 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are currently testing ingestions and curations in development environment before moving to production. 3/27/2026 * Enterprise Ranking: 329 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are planning to complete their ingestion/curation work by end of March 2026. 3/20/2026 * Enterprise Ranking: 319 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are planning to complete their ingestion/curation work by end of March 2026. 3/13/2026 * Enterprise Ranking: 311 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are planning to complete their ingestion/curation work by end of March 2026. 3/6/2026 * Enterprise Ranking: 312 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are planning to complete their ingestion/curation work by end of March 2026. 2/27/2026 * Enterprise Ranking: 312 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their team's Azure/Databricks workspace as part of their team's migration from SAS. They are planning to complete their ingestion/curation work by end of March 2026. 2/20/2026 * Enterprise Ranking: 314 (L1) * Awaiting confirmation from Safey P&A that all relevant data sources have been made available in their teams's Azure/Databricks workspace as part of their team's migration from SAS. | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: GPDE Intl Expansion Capabilities Phase 1 |  | 180106 | Business w/ Tech Initiative | F&LM - Core Fleet | P&D | Chun Wai Lo, Gunter Loh | On Track | On Track | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Transparent Agreement Facilitation | 27411 | 6713 | Business Only Initiative | F&LM - Capacity Management | P&D | Jeremy Torrence, Richard Lapradd, Joe Sandhorst | On Track | 10/31/2024 - Conducted reforecasting | K: L5 | Active | TEMP L5 - Enter L5 | 2023-05-01 | 2025-02-28
Business Only Initiative: CDAS Termination Timely Entries | 38751 | 7095 | Business Only Initiative | F&LM - Capacity Management | P&D | Gene Fitlin, Phill Peterson | On Track |  | K: L5 | Completed | L5 | 2023-09-05 | 2024-05-07
Business w/ Tech Initiative: [ENABLER] CDAS Enhancements to Support MEDALS | 64473 | 7378 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Gene Fitlin, Matt Anderson | On Track | Launched on 1/19/2025 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-07-29 | 2025-01-31
Business w/ Tech Initiative: Contingency Process Overhaul - Front End | 2316 | 7560 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Matt Anderson, Tanner Sansonetti, Jared Hodge | On Track | **13 April 2026:** Financials updated for Mar 2026 **12 March 2026:** Financials updated for Feb 2026 **11 Feb 2026:** Financials updated for Jan 2026 Financials updated for Dec 2025 | K: L5 | Active | TEMP L5 - Enter L5 | 2022-12-06 | 2025-11-28
Business w/ Tech Initiative: Service Provider Contract Start-Up Period | 554 | 7671 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Tim Means, Jared Hodge, Joe Sandhorst | On Track | Good to go | K: L5 | Completed | L5 | 2022-11-04 | 2024-01-30
Business Only Initiative: Reduce time to Fill Open CSAs | 557 | 7782 | Business Only Initiative | F&LM - Capacity Management | P&D | Joe Sandhorst, Courtney King | On Track | Additional communication and engagement is planned over the next few weeks to ensure consistent usage of the Open CSA dashboard. | K: L5 | Completed | L5 | 2022-10-31 | 2023-04-20
Business Only Initiative: [Enabler] Contingency Spend Reduction | 551 | 8039 | Business Only Initiative | F&LM - Capacity Management | P&D | Matt Anderson, Tanner Sansonetti, Matthew Clark | On Track | On track | K: L5 | Completed | L5 | 2022-11-16 | 2024-02-23
Business Only Initiative: Capacity Agreement Spend Reduction | 1630 | 8040 | Business Only Initiative | F&LM - Capacity Management | P&D | Tanner Sansonetti, Matthew Clark | On Track | Most current guidance is additional headcount/backfills likely won't be approved until FY24, at the earliest. Adjusting timelines, as such. | K: L5 | Completed | L5 | 2022-11-16 | 2024-04-26
Business Only Initiative: [Enabler] Reduce # of Open CSAs | 556 | 8266 | Business Only Initiative | F&LM - Capacity Management | P&D | Joe Sandhorst, Courtney King | On Track | 3/3/2023 - Root cause analysis findings/ L4 approval reviewed with Domain leadership. The main finding of the analysis was a strong correlation between open CSAs and multiple CSA ownership. A new initiative has been entered at L0 to address entity scale. Recommendation to leave this initiative in L1 until additional data can be gathered around root cause for Open CSAs. Other identifiable root causes - negotiations impasse, viable CSA scale, and MEDALS - are all covered under other initiatives. This team will complete the exercise and determine what components are left to address and will size that opportunity accordingly. | K: L5 | Completed | L5 | 2022-11-04 | 2023-02-24
Business Only Initiative: Current Cartage Cost Reduction | 552 | 8344 | Business Only Initiative | F&LM - Capacity Management | P&D | Nadeana Cook | On Track |  | K: L5 | Completed | L5 | 2022-11-16 | 2023-10-17
Business Only Initiative: Unpaid Service Provider Invoices & Accident-Relate | 12611 | 8408 | Business Only Initiative | F&LM - Capacity Management | P&D | Michele A. Goetz, Heather Dornan | On Track | Update 09/18/24- No new update. I will update when the feature is completed. Update 9/11/24- Milestone 83676- (OVP IT fix) IT SnS started working on the analysis feature Update 8/28/24 - Milestone 12700-(Dispute) Dispute multiple times installed 08/24/24- closing milestone today Milestone 83676- (OVP IT fix) SET-200 –SET-200 was communicated on 8/22. The policy is active in policies and procedures. Overpayment fix is pending prioritization with IT. Update 8/21/24 - Milestone 12700-(Dispute) On target for 8/24 install Milestone 83676- (OVP IT fix) SET-200 is approved. Waiting on the communications to advise when the communication will be sent out regarding SET-200. TVS still has epic in back log for OVP fix. Update 8/14/24 - Milestone 12700-(Dispute) Install slated for 8/24 due to alignment with rebranders needed and approvals Milestone 83676- (OVP IT fix) SET-200 approved, Update 8/7/24 - Milestone 12700-(Dispute) No update Milestone 83676- (OVP IT fix) followed up with Hattie and Luca today since I red-lined SET-200 to remove all RAP teams recovery on Friday. Michele is waiting to hear back. TVS still has epic in back log for OVP fix. Update 7/31/24 - Milestone 12700-(Dispute) No update Milestone 83676- (OVP IT fix) SET-200 will go through the approval process again due to Luca’s redlines. Feature for agreement type analysis submitted to Jason on 7/17/24. Update 7/24/24 - Milestone 12700-(Dispute) install delayed due to freeze. IT team is hopeful for an August install now. Milestone 83676- (OVP IT fix) SET200 with Luca for review Update 7/17/24 - Milestone 12700-(Dispute) Testing completed, install planned this weekend Milestone 83676- (OVP IT fix) Legal changes to SET200 (Escalation Policy) made and re routed for approval. Update 7/10/24 - Milestone 12700-(Dispute) Terminated agreement install completed. BA testing continues, in SPL next week, still on track with install at end of July Milestone 83676- (OVP IT fix) Still waiting on legal approval for procedure/comms. Hattie asked if Luca can be added as an approver. EPIC review meeting with Joe King and IT scheduled on 7/17. Update 7/3/24 - Milestone 12700-(Dispute) Testing defects being cleaned up and testing continues. Termination feature to allow terminated agreement accident charges to be invoiced is being installed this weekend Milestone 83676- (OVP IT fix) Still waiting on legal approval for procedure/comms. Michele followed up with Hattie and she advised she would have today, has red line changes and will need to be re-routed for approval Update 6/26/24 - Milestone 12700-(Dispute) No update Milestone 83676- (OVP IT fix) No update Update 6/19/24 - Milestone 12700-(Dispute) Testing slated to be completed by 7/12 and install completed 7/20 Milestone 83676- (OVP IT fix) EPIC written Update 6/12/24 - General Initiative Update- emailed about moving to L4 in WAVE. Waiting on meeting to be scheduled with Clayton Milestone 12693- (Escalation) Milestone completed in WAVE, process is established Milestone 12700-(Dispute) testing still in progress. Planned July install to align with all the June installs for One FedEx Milestone 73410- (OVP adjust) Completed milestone in WAVE since overpayments are being added to charge statements. Milestone 83676- (OVP IT fix) Michele is working on creating Epic so can be prioritized Update 6/5/24 Milestone 12693- (Escalation) Working on getting procedure approved by Josh Croft, Beth R sent instructions. Communication planned to be drafted this week. Milestone 12700-(Dispute) testing still in progress. Planned July install to align with all the June installs for One FedEx Milestone 73410- (OVP adjust) Manual work around to change agreement type to deduct prior to weekly settlement run then change back to non-deduct after settlement run. IT is trying to identify the cause of the scanners load errors with deduct agreement type. Submitting EPIC for permanent solution. Update 5/29/24 Milestone 12693- (Esca | K: L5 | Completed | L5 | 2022-12-09 | 2025-01-31
Business w/ Tech Initiative: [Enabler] SPECS - Service Provider Engagement Comm | 27914 | 8418 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Lynn Teams, Joe Sandhorst | On Track | Sept & Oct 2025: PBI Dashboard launched, issues arose but were troubleshot. Seeking to move to L5 by November now that desired KPIs can be measured. 7/22/2025: After giving update to P&D Domain, changed status to Some Issues. Currently on track to publish a new PBI Dashboard with Row Level Security within the next 30 days, pending any unforeseeable issues. 5/20/2025: Pending gaining access to Workday Data to set up Row Level Security (RLS) for the PBI Dashboard, a 2-phase approach is planned to be implemented. Phase 1 involves Dataworks ingesting, transforming, and curating the SPECS data from CDAS. Phase 2 involves a solution to access the Workday data, which may come from Dataworks via Atlas or may come from HR via a pending PDSM Request, to then use the Workdata data to set up RLS. Phase 1 can start immediately while Phase 2's Work occurs simultaneously. February 2025: Needs Attention and escalated to Senior Leadership November 2024: working with Dataworks to resolve PBI Dashboard major issues | K: L5 | Active | TEMP L5 - Enter L5 | 2022-12-15 | 2024-09-13
Business Only Initiative: [Enabler] Reduce barriers to entry by understandin | 28274 | 8910 | Business Only Initiative | F&LM - Capacity Management | P&D | Debra OBrien, Joe Sandhorst |  | The initiative will be reevaluated, and a new initiative owner will be identified. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-06-09 | 2025-01-15
Business Only Initiative: [Enabler] Ensure Structured Bench | 27977 | 8913 | Business Only Initiative | F&LM - Capacity Management | P&D | Joe Sandhorst, Courtney King, Lisa Salamon | On Track | June 2025: On hold until SSPS Assignments are finalized and decisions about path forward are made. 2024: Decided to pause communicating the reports to a bigger audience until we finalize a location for them. We have received feedback from management and the field (team included Gene Fitlin, Crissy Sharp, Bryce Newton, Tom Pierce, Jeremy Torrence, Colleen Ferrari, Kelly Simpson). We decided to not duplicate efforts and have similar reports in two different places and BDS is currently working on Open Area Tracking Dashboards and thought that we could make a new tab there to highlight the prioritization reports. Once completed, we will then communicate to a larger audience how to utilize this report moving forward. The overall goal is to provide the field with viable external candidates to include in negotiations and identify areas where there is a structured bench. We will use this predictive tool to highlight high risk stations that may enter negotiations in the upcoming future. | I: L4 | On Hold | TEMP L4 - Enter L4 | 2023-06-08 | 2025-05-09
Business Only Initiative: Pursuit of Liquidated Damages for Service Failures | 2442 | 8914 | Business Only Initiative | F&LM - Capacity Management | P&D | Tim Means, Ray Legault, Joe Sandhorst | On Track | Good | K: L5 | Completed | L5 | 2022-10-28 | 2025-11-28
Business w/ Tech Initiative: Project Mercury – Next Generation BD and SPECS |  | 89838 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Gene Fitlin, Matt Anderson, Phill Peterson | On Track | PM being identified to lead initiative. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2024-10-01 | 2025-11-28
Business w/ Tech Initiative: SP Turnover Analytics |  | 93125 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Lynn Teams, Patrick Easley | On Track | On Track | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: Contingency Overhaul - Back End |  | 94471 | Business w/ Tech Initiative | F&LM - Capacity Management | P&D | Bradley Moore, Courtney D. Peterson, Joe Sandhorst | Some Issues | L2 Enterprise Ranking 4/17/2026: 257 L2 Enterprise Ranking 4/9/2026: 265 L2 Enterprise Ranking 3/12/2026: 280 L2 Enterprise Ranking 3/6/2026: 283 L2 Enterprise Ranking 2/26/2026: 283 L2 Enterprise Ranking 2/19/2026: 280 L2 Enterprise Ranking 2/12/2026: 288 Jan-Mar 2026: After not being approved for prioritization by the Boost Process and the EPC, the plan is to update appropriate fields in Planview with new financial and legal/risk assessments. An audit of the current manual process is being conducted starting at the end of January and ending up to 12 weeks later. The results of the audit and the Planview changes will be reviewed for a final attempt at escalation after the audit is completed. December 2025: New Legal Risks identified: the current manual process is technically breaching the ISPA in multiple ways, which cannot be mitigated/resolved by any manual process. Value type of this Initiative will change to, or add, Legal/Regulatory. These Risks were presented to the Enterprise Prioritization Council on 12/18/2025. An ePDSM Ticket to update L1 fields in this Initaitive was submitted on 12/22/2025. November 2025: Stuck in L2 queue; waiting for BA/EA/SA. Delayed by > 2 months by Planview system and/or admin. Legal and ICA and ESPM will be consulted to attempt prioritization after consulting the P&D Domain. April 2025: Just approved for L1, just assigned IO, will be reaching out to SMEs this week to determine next steps | E: L2 | Active | L2
Business Only Initiative: LMSC - Last Mile Strategic Capacity |  | 168318 | Business Only Initiative | F&LM - Capacity Management | P&D | Eric Pagano, Thomas Pierce | On Track | 12/23/2025- Bi-weekly update calls continue | E: L2 | Active | L2 Feedback Requested | 2026-04-30 | 2026-07-31
Business Only Initiative: Open CSA Triage |  | 189309 | Business Only Initiative | F&LM - Capacity Management | P&D | Joe Sandhorst, Kelly Prohaska | On Track | On Track | C: L1 | Active | L1
Business w/ Tech Initiative: Operational Hold to Match (HTM) | 46208 | 7151 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Chris Helkowski, Jamie Heinzman, Nathan Tonkinson | On Track | 4/17/2026: Enterprise Ranking: 43 (L3) Challenge: Planning for Mother's Day IT peak restriction period 5/2-5/10 •Development - "On Track" oAdded User Story 16 - Pipeline Purge; required for efficiency and to meet best-practice standards •Validation - "Complete" oTesting solution for Ground Economy barcode issue (FedEx vs. USPS barcode response in Preload Assist). Test environments down as of 4/17/2026. •Implementation - "On Track" oWave 1 - Complete! 1 district, 23 facilities oWave 2 - In progress, 4/12/2026 - 4/25/2026, 5 districts oWave 3 - In progress, 4/19/2026 - 5/2/2026, 8 districts oWave 4 - In preparation, 4/26/2026 - 5/9/2026, 9 districts oWave 5 - pending, 5/3/2026 - 5/9/2026, 7 districts oWave 6 - pending, 5/10/2026 - 5/23/2026, 7 districts oWave 7 - pending, 5/17/2026 - 5/30/2026, 8 districts 4/10/2026: Development - "Complete" Validation - "Complete" Implementation - "On Track" Wave 1 - Complete - 23 facilities live! Wave 2 - In progress, 4/12/2026 - 4/25/2026, 5 districts Wave 3 - In preparation Wave 4 - In preparation Wave 5 - pending Wave 6 - pending Wave 7 - pending 4/3/2026: Development - "Complete" Validation - "Complete" Implementation - "On Track" 12 facilities holding packages Wave 1 - In progress, 3/29/2026 - 4/11/2026 Wave 2 - In preparation, 4/12/2026 - 4/25/2026 3/27/2026: •Development - "Complete" •Validation - "Complete" •Implementation - "On Track" oManual Pilot - successful, 3/18 Preload oAutomated Pilot - successful, 3/23 Preload oWave 1 - In progress, 3/29/2026 - 4/11/2026 oWave 2 - In preparation, district training 3/20/2026: * Enterprise Ranking: 34 (L3) * Schedule - "On Track" * Roseville 3/17/2026 - Live! * Maple Grove - Technology Enablement scheduled for 3/22/2026 * Development - "Complete" * Additional user story for data purging - complete and in production! * Validation - "Complete" * Round 2 testing completed 3/13/2026. 19 of 19 "non-negotiable tests" pass. * UAT - Production check complete * Implementation - "On Track" * Manual Pilot - successful, 3/18 Preload * Automated Pilot - pending, 3/23 Preload * Wave 1 - Schedule for facilities complete * Wave 2 - Preparation Activities started 3/13/2026: * Enterprise Ranking: 34 (L3) * Schedule - "On Track" - Prepared for pilots - Roseville 3/17/2026 and Maple Grove 3/22/2026 * Development - "On Track" - Additional user story for data purging under way * Validation - "On Track" - Round 2 testing completed 3/13/2026. 19 of 19 "non-negotiable tests" pass. UAT - "On Track" - 95% pass in UAT, Production check pending * Implementation - "On Track" - Technology teams prepared for enablement. FLME Field Support team trained for additional district rollout support. 3/6/2026: * Enterprise Ranking: 37 (L3) * Schedule - "On Track" - On track for pilots - Roseville 3/15/2026 and Maple Grove 3/22/2026. * Development - Complete. HTM code will be pushed to Production environment ahead of pilots. * Validation - "Some Issues" - Confidence in completing validation by 3/13/2026 - Medium. * Round 1 testing complete - Execution Rate 89%, Pass Rate 100%, 8 days of 21-day schedule lost to TEST system instability. Round 2 testing will proceed on 3/9/2026; code freeze in place. Initiated UAT - 50%+ complete & pass. * Implementation - "On Track" - Finalizing technology enablement steps and roll-back plans. Training FLME Field Support team for additional district rollout support. 2/27/2026: * Enterprise Ranking: 37 (L3) * Reminder: There is NO slack in the project schedule. Any delay will result in go live delay. * Schedule - "Some Issues" - Currently 10-day delay. Implementation team can absorb a 5-day delay. This week, the team lost 3 additional days due to test system down-time. * Development - Complete. * Validation - "Some Issues" - Confidence in completing validation by 3/13/2026 - Medium. To date, lost 5 days of 15-day schedule for Round 1 testing; 5 days remain. Initiated UAT early to get a jump start. * Implementa | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-15 | 2026-06-30
Business w/ Tech Initiative: Hold to Match (HTM) - Actuals Tracking Only | 558 | 7894 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Chris Helkowski, Heath Baker, Samantha Nagle | On Track |  | K: L5 | Completed | L5 | 2023-12-29 | 2025-01-10
Business w/ Tech Initiative: Minimizing Mailroom Delivery Stop Splitting | 559 | 7905 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Sara Hahn, Lindsay Evanish | On Track | Based on PI2 planning prioritization decisions, the overall initiative timeline and milestones have been extended an additional 10 weeks - dev is now planned to be complete by the end of PI3 and a production rollout is planned during PI4. | K: L5 | Completed | L5 | 2023-01-25 | 2023-10-18
Business w/ Tech Initiative: Alternate Day Service (ADS) | 560 | 7927 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Samantha Nagle, Brian Carlson | On Track | 11/10/2025 - CCH small group meeting held on 11/06 to evalute path forward for ADS initiative. - Decision: proposal to cancel 7927 accepted by CCH based on favorable performance of 7625 - Action: Cancel 7927 ADS in Planview 03/07/2024 - Did not get Greenlight from CCH. Will re-evaluate in 6 months following sales initiative attempt to increase volume in identified zip codes. | C: L1 | Cancelled | L1 | 2024-07-22 | 2025-07-14
Business w/ Tech Initiative: Remove Commercial Signature - Ground | 83154 | 8309 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Chris Helkowski, Erin Wichtoski, Jennifer Stringfellow | On Track | It has been determined that this initiative is dependent on the successful launch and implementation of a number of other DRIVE initiatives. | E: L2 | On Hold | L2 & CCH | 2024-08-22 | 2025-11-28
Business Only Initiative: Collect Billing | 4579 | 9029 | Business Only Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | John Ropelewski, Lindsay Evanish | On Track | Detailed questions sent to the DIRE team regarding the scanner functionality and projected rollout schedule for this intitiative | K: L5 | Completed | L5 | 2022-08-22 | 2023-10-31
Business w/ Tech Initiative: Drop Box Sensor Technology Enhancement |  | 167511 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Glenn A. Hill, Tyler Howcroft, Mark Enfield | On Track | 03/04/2026t * Connecting DBX Chute Pull Data to Cancel Zero Package Notification (ZPN) Stops with CXPC Backend Systems * Request for Proposal/Quote ( FRP/RFQ) is with Sourcing with 13 Suppliers * Currrently Testing in a few Markets , Possible Network Launch in Late 2026 or Early 2027 03/18/26 * L1 Architecture Alignment step has been completed on 3/16/2026 04/22/26 * Please cross rreference PV # 192357 under Drop Box Sensor where both initiative have been approved to the level LBC stage. effective 4/14/26 * We will continue the process under the PV # 192357 * Bradley Boze,an is the orginal Sponsor under the initiative PV 167511 * | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: DropBox Sensors |  | 192357 | Business w/ Tech Initiative | FXG P&D - F&LM - Upstream Optimization | P&D | Tyler Howcroft, Glenn A. Hill, Mark Enfield | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: Enable "bring your own vehicles" for employees |  | 112948 | Business Only Initiative | FXG P&D - Roadmap | P&D | James Shields, Jamie Heinzman | On Track | Canceled as of 7/16/2025 Requirements merged into Initiative 130349 Roadmap Employee Model with BYOV | C: L1 | Cancelled | L1 | 2025-07-01 | 2025-08-29
Business w/ Tech Initiative: Ground Economy Postal Injection | 64470 | 7276 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Dan Koller, Juan Leoni, Jamie Heinzman | On Track | Given changes to USPS injection environment as well as Roadmap 3.3, this initiative is pending further review. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: [Pilot] Roadmap Techniques for Last Mile Delivery | 87006 | 8011 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Jamie Heinzman, James Shields, Sushil Sehrawat | On Track | 12/05/2025: Roadmap Chicago and Fort Worth Pilots are complete. Reports available in Teams / SharePoint. https://myfedex.sharepoint.com/teams/Roadmap3.3/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2FRoadmap3%2E3%2FShared%20Documents%2FGeneral%2FReporting&viewid=042ffa02%2D94e2%2D4288%2Db362%2D279b2de4cb2a 11/13/2025: Working on Closing documentation Pilots are complete - discontinued in July 2025. We will not roll out the SP labor model or the employee labor model at this time. | E: L2 | Cancelled | Portfolio Greenlight | 2024-08-21 | 2025-11-28
Business Only Initiative: Roadmap alternate vehicle driver qualifications |  | 130345 | Business Only Initiative | FXG P&D - Roadmap | P&D | Fausto Bizzarri, Jamie Heinzman | On Track | Canceled as of 7/16/2025 Requirements merged into Initiative 130349 Roadmap Employee Model with BYOV | C: L1 | Cancelled | L1 | 2025-07-14 | 2025-08-29
Business Only Initiative: Roadmap Employee Model with BYOV |  | 130349 | Business Only Initiative | FXG P&D - Roadmap | P&D | Lauren Stremple, Jamie Heinzman | On Track | 2/27/2026: Employee Driver functionality is included in Network 2.0. Current requirements outlined in report on Project SharePoint Updating project to include: * Residential Delivery Driver – Hours, Wage, Benefits, Work Assignment * Alternative Vehicle Requirements (previously 112948) * Alternative Vehicle Driver (previously 130345) | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2025-06-02 | 2025-07-31
Business Only Initiative: Roadmap SP Model Settlement Structure |  | 130352 | Business Only Initiative | FXG P&D - Roadmap | P&D | Tyson Wolfe, Jamie Heinzman | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC | 2025-07-01 | 2025-08-28
Business w/ Tech Initiative: Roadmap Vehicles - Vehicle Share |  | 130998 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Jamie Heinzman | On Track | Move to On Hold Vehicle Share is not currently prioritized for research / evaluation. | C: L1 | On Hold | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: P&D Plan Decision Engine |  | 131381 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Jamie Heinzman, James Shields, Andrew Kuwik, Angiana Jones, Rip Rucker | On Track | 2026/01/22 - Replaced by N2.0 P&D Planning project. POC: Andrew Kuwik 2026/01/15 - Considered part of "Refresh" - as such is "approved." N2.0 FLME has been work with P&D Technology on strategy and work breakdown. Bozeman has given the thumbs up to proceed through DRIVE to the L2 gate. | C: L1 | Cancelled | TEMP L1 - Create L1 LBC | 2025-06-02 | 2025-09-30
Business w/ Tech Initiative: Roadmap Drivers - Gig Worker Labor Model |  | 131386 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Jamie Heinzman | On Track | Move to On Hold Gig Worker Labor Model is not currently prioritized for research / evaluation. | C: L1 | On Hold | TEMP L1 - Create L1 LBC | 2025-07-15 | 2025-08-29
Business w/ Tech Initiative: Create Special Assignment Courier Role |  | 142398 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Jackie Kerscher | On Track |  | C: L1 | Active | TEMP L1 - Create L1 LBC
Business Only Initiative: [Pilot] IndiGO Technologies Collaboration |  | 163911 | Business Only Initiative | FXG P&D - Roadmap | P&D | Jamie Heinzman, Jillian Litos, James Shields | On Track | 11/20/2025: FedEx is discontinuing the efforts to stand up a pilot with IndiGO Technologies. IndiGO does NOT have rideshare platform. IndiGO does not have Motor Carrier Authority to deliver FedEx packages. IndiGO does not have a written legal opinion regarding the defensibility of the independent contractor labor model with gig drivers. 11/7/2025: Collaborating with Legal regarding rideshare model and motor carrier authority. * IndiGO intends to use 1099 Independent Contractors - challenges with definition of IC * IndiGO must pursue Motor Carrier Authority to move FedEx packages (interstate); this takes about ~23 days from submit | C: L1 | Cancelled | L1 Feedback Requested
Business w/ Tech Initiative: [Pilot] Temporary Hold at Location (HAL) |  | 167493 | Business w/ Tech Initiative | FXG P&D - Roadmap | P&D | Jamie Heinzman, James Shields | On Track | 2/27/2026: * Enterprise Priority 76 (L1) * Waiting 12/11/2025: * Next Up: Review with Manager and Director * Target L2: 1/9/2026 (extended timeframe due to holidays) | C: L1 | Active | L1 Feedback Requested | 2026-01-09 | 2026-11-12
Business w/ Tech Initiative: P&D Safety Analytics | 27225 | 6704 | Business w/ Tech Initiative | FXG S - Accountability & Claims | Safety | Jason Handerhan, Jay Sinnott | On Track | Returning to on hold after temporary activation to fill out azure subscription group. On hold Rationale: Due to legal concerns around some of the features critical to the model, this initiative has been put on hold. To move forward with these features, and thus the model, operating agreement langauge changes are needed. Instead, we will shift our focus to courier initiatives where there is opportunity for more immediate and substantial financial savings. | G: L3 | On Hold | TEMP L3 - Enter L3 | 2023-11-01 | 2025-09-01
Business w/ Tech Initiative: Ergonomics Program/482072 | 69025 | 7278 | Business w/ Tech Initiative | FXG S - Accountability & Claims | Safety | Dane Mitcheson, Alexis Malovich, Holly Vernon, Sean Keaton, Jordan Taylor | On Track | 5/8/2025- Updated my money step milestone from complete to inprogress and pushed date to align with technology completion date to ensure my initiative didn't show overdue to go to L4 due to the direction from the Planview team to go back from L4 to L3 if technology is still in development to avoid tech status being marked "complete" in agility. The money step for this initiative was complete in april 2025. 3/20/25- Project continues to be on track and is ready for L4. | I: L4 | Active | L4 | 2023-07-03 | 2026-08-19
Business w/ Tech Initiative: Liability Coverage Contribution and Safe Operating | 580 | 8304 | Business w/ Tech Initiative | FXG S - Accountability & Claims | Safety | Jay Sinnott, Sean Keaton, Fausto Bizzarri, Heather Dornan, Kelly Prohaska | On Track | Week Ending 7/29 Q2 CY23 LCC-SOI results ( classifications/incentives/contributions) have been published and communicated Expecting 60% plus of the SPs to be impacted by the program (Money Step) Next steps move initiative to L4 stage CDAS technology and oversight changes greenlit by TCH - added to list for target implementation date Disputes are current in preparation for new round of disputes | I: L4 | Active | TEMP L4 - Enter L4 | 2022-08-01 | 2025-07-15
Business Only Initiative: Temporary Return-to-Work Program | 584 | 8315 | Business Only Initiative | FXG S - Accountability & Claims | Safety | Barbara Jones, Michelle Ward, Kelly Prohaska, Sean Keaton | On Track | Initiative is on track. | K: L5 | Completed | L5 | 2022-10-31 | 2024-01-31
Business w/ Tech Initiative: FedEx Injury Reporting System Alignment | 87081 | 8859 | Business w/ Tech Initiative | FXG S - Accountability & Claims | Safety | Jeannie Idaughe, Heather Dornan, Sean Keaton, Bill Stanek | Some Issues | 04/17/2026 -Work Progress:​Development of Intake/Update (UI) in progress (Ravenclaw Team) Prototype for Design of Injury Intake Screen in progress (Jeannie & Doug)​ (Boats & Code): This team will work on the "When and Where" Backend Screen and UI in the upcoming PI. Dec 2028 constraint still in place. Ravenclaw team has Odyssey help and will start work on the intake/upate screens again next PI. 02/18/2026 The Enterprise Odyssey initiative takes precedence over all other IT projects.The new target date will be established after Odyssey is completed over the next two PIs (approximately 20 weeks). Critical Issue: The revised timeline must allow this project to reach MTP by December 29, 2028. Missing this deadline would prevent the company from meeting future regulatory reporting requirements. End of year deadlines akso mean all prior year reportiong for OSHA Annual Posting and OER plus BLS must be accurate and ontime. The Systems Architect has communicated this to the Manager of Safety Processes & Compliance, and it has also been relayed to Safety Management. In addition, the Systems Architect has informed all teams and leadership that there will be no capacity to remediate either system once the Odyssey transition layer is implemented, and there will be no way to identify employees by OPCO after the transition layer is decommissioned. | G: L3 | Active | TEMP L3 - Enter L3 | 2025-01-15 | 2028-12-29
Business Only Initiative: Drug and Alcohol Testing Alignment for Surface Ops |  | 88668 | Business Only Initiative | FXG S - Accountability & Claims | Safety | Renee Mccormick, Dawn Eberle, Mark Goslawski, Sean Keaton | Some Issues | 05.15.2025 On hold; currently looking at alignment before we consider aligning to one vendor 05.12.2025 On track- Working thru business case 7.31.25-Upon meeting with the EPM, we determined that the scope of this initiative has changed significantly. As a result, it was recommended to cancel the current initiative and resubmit a new one reflecting the updated scope. | C: L1 | Cancelled | L1
Business w/ Tech Initiative: Accident and Injury Dashboard | 26281 | 6700 | Business w/ Tech Initiative | FXG S - Accountability & Claims | Safety | Kor'an Sharif | On Track | 4/20: * New date 5/31/2026 (6/1 because it's a weekend) * 2 of the data jobs are running successfully. The remaining 5 jobs aren’t currently in Atlas, awaiting more details from DW. 3/25: •L4 Date: 03/31/2026 •Current Status: At Risk •Work completed in the last 2 weeks oSafety & Performance Analytics (S&PA) promoted 12 Databricks notebooks and 4 jobs oIngestion issue regarding Legacy Ground core injury table fixed and validated oIngestion issue regarding Legacy Express core safety tables fixed and validated •Work in Progress oS&PA working with Platform Engineering team to increase DB size and limits to prevent future ingestion failures in ATLAS (install this weekend) oS&PA working with Data and AI to diagnose data flow connection issues between Power BI and stage storage accounts This is prohibiting any development and validation in DEV and PRE-PROD workspaces Bridge calls on Tuesday evening and Wednesday morning oS&PA working with Data and AI to establish e-mail alerting for ingestion failures in both ATLAS and Labor Insights Platform (LIP) •Next Steps oS&PA to validate after Work in Progress issues above are fixed oFinish development and testing on remaining Databricks code and Power BI dashboards and then move to production (MTP oMonitor dashboards in production for stability while establishing user access via IMAGE based on existing Spotfire Safety Dashboard user base oFinalize communication, training strategy, and roll-out timeline •Risk/Awareness oIssues listed in Work in Progress need to be fixed and validated for S&PA to feel confident about rolling out these dashboards •Requests for Support from Leadership oConsideration for setting appropriate SLAs and processes for different risk levels and MTP types oCurrent and future moves to production for Safety Dashboard present minimal risk / operational impact but still require CAB approval 3/13: User testing and validation in progress – 4 out 5 bug fixes deployed on 2/19, 1 bug investigation on-going Data ingestion is unstable causing several failures Meeting with Safety and Dataworks MDs to identify escalation options for resolutions 2/25: User testing and validation in progress – 4 out 5 bug fixes deployed this week, 1 bug investigation on-going DescriptionIDNotes Ops Reporting Views526635Approved in CAB last week; deployed yesterday Ops Reporting TLH Monthly Actual Data Not Updating547461Approved in CAB last week; deployed yesterday Ops Reporting Daily Summary Table Not Updating547488Approved in CAB last week; deployed yesterday SCMPF100 (LG Injuries) Missing Data543310Under investigation AFDC (eForms) Tables Update Failure536813Seems to be fixed but will monitor throughout the week Quota Limit Increase Needed for Production Workspace548781Approved in CAB last week; deployed yesterday LIP Ingestion Job Failure E-Mail Alerts538362* Not a bug but important that we have visibility on when ingestions fail Goes through Core Frameworks – plan to discuss with Srikant 2/5: Lesko's team is finishing development and testing for both the Databricks code and Power BI dashboard. Srikant's team is assisting Lesko's team with some data-related bugs they found during validation. Plan is to launch Power BI Dashboard by 3/31 (money step) and retire the existing Spotfire data at the end of FY26. 1/22: * Post-peak, all the Data engineering work was completed in production * DW team now helping George's team with moving some data transformations in to production by close of business 1/23 * PowerBI dashboard creation in progress 11/25: L4 date updated to 3/31/2026 11/21: Priority #3 data status - delayed​ completion – data discovery and data connection access in progress. Data ingestions from EIW, completed. CDAS view creation is completed, testing completed by DW team. (new) Additonal six (6) data sets requested from Riskconnect, complete. Backend data MTP moved to post-peak L4 date will need to be adjusted 10/24: Priority # | E: L2 | Active | L2 Feedback Requested | 2023-09-13 | 2026-06-01
Business w/ Tech Initiative: FEC One Accident Reporting System |  | 109287 | Business w/ Tech Initiative | FXG S - Accountability & Claims | Safety | Chris Burg, Dawn Eberle | On Track | 10-3-2025: Initiative has been approved by Safety Council, and is moving forward with the Spend Control tower request. 11-24-2025 Business Continuity Review was not approved at this time. First Request has been started and is pending submission until the Encore Request is started. Procurement has begun the RFQ process. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Criminal Background Check Alignment |  | 114016 | Business Only Initiative | FXG S - Accountability & Claims | Safety | Jessica McArdle | On Track | 7/22/25 - Added June actuals & submitted to L4 6/3/25 - Working with EPSM & Finance to make adjustments before submitting to SL2 | J: SL5 | Active | SL5 Finance Domain Lead Approval | 2025-03-03 | 2028-06-30
Business Only Initiative: Drug and Alcohol Testing One FedEx Alignment |  | 160572 | Business Only Initiative | FXG S - Accountability & Claims | Safety | Renee Mccormick | On Track | Alignment efforts do not fit into the parameters of Planview. All parties have been consulted and agree that the work being done outside of Planview will continue. The team is still on track to go live with random drug testing starting January 1, 2026. | C: L1 | Cancelled | L1
Business Only Initiative: Service Provider Accountability FADV requests |  | 167072 | Business Only Initiative | FXG S - Accountability & Claims | Safety | Sean Keaton | On Track | On Track | F: SL3 | Active | SL3 Finance Domain Lead Approval | 2026-04-01 | 2026-07-31
Business Only Initiative: Safety AI Pilot |  | 187507 | Business Only Initiative | FXG S - Accountability & Claims | Safety | Jordan Taylor | On Track | On Track | E: L2 | Active | L2
Business w/ Tech Initiative: HOS (Hours of Service) Vendor | 58563 | 7249 | Business w/ Tech Initiative | FXG S - Technology & Certification | Safety | Mark Goslawski, Mitchell Giesey, Kelly Prohaska, Sean Keaton | On Track | L3 approval requested. | G: L3 | Active | TEMP L3 - Enter L3 | 2023-11-17 | 2027-12-31
Business Only Initiative: Yard Switcher VEDR Vendor Transition | 63744 | 7279 | Business Only Initiative | FXG S - Technology & Certification | Safety | Jordan Taylor, Heather Dornan, Holly Vernon, Kelly Prohaska, Sean Keaton | On Track | Renewed Velocitor MSA. Submit CLEAR request in EnCoRE. Decomissioned all SmartDrive VEDR devices. Installed Velocitor VEDR devices in all switchers. Developed VEDR KPI in alignment with CSP/Courier measurement. | K: L5 | Completed | L5 | 2024-02-29 | 2024-11-29
Business w/ Tech Initiative: Safety Certification (Qualification Certification) | 578 | 7938 | Business w/ Tech Initiative | FXG S - Technology & Certification | Safety | Kelley Taylor, Dawn Eberle | On Track | Week ending: 1/13/2023 4448: Met with FADV (Josh) and BDS (Michelle) regarding means for FADV to support ensuring training compliance at time of onboarding. FADV and BDS were to have additional discussions on some suggestions. 6083: Testing completed for Certified/Qualified Observer Conditions Page. 4419: 90.5% Compliance 4474: Waiting for release date date 4607: 26.5% Compliance Week ending: 1/27/2023 4419: 90.5% Agreements with training terms 4448: Collaborating with BDS on a resolution to a short-term solution. BDS continues to investigate options 4607: 30.53% Driver Compliance 4426: Drafting final Safety Council deck for next week. All agreements with drivers past due will require training by May. 31st or OTC to be issued. Communicate set to send out next week. 4465: Final draft of Data Sharing Agreement in the hands of vendors for review. 1 vendor accepted. 4461: Collaborated with FADV to answer additional questions/concerns FADV designers had. 4627: Started. Discussions with management to construct a team. Week ending: 2/3/2023 4419: 90.6% Agreements with training terms 4448: Team investigating if a Certificate should be uploaded to FADV 4474: Collaborated with CDAS IT re: Observed Hours requirements to assist with programming 4607: 32.39% Driver Compliance 4426: MGBA Notice drafted and being reviewed by stakeholders 4465: Vendors continue to review the terms of the Data Sharing Agreement. J.J. Keller is active asking questions 4627: 1st introduction meeting lead by Lonnie. Team page created. Weekly meeting to be scheduled Week ending: 2/17/2023 6082 Met with CDAS IT to answer any Observed Hour process questions 6083 Supply testing scripts for the Conditions tab to CDAS IT for their records 4419 498 of 4791 ISPA remaining to implement Qualification Certification 4448 Assigned a new milestone owner: Lonnie Mattison. Continued conversations with BDS on uploading Certification to FADV 4607 38.52% Driver Compliance 4614 In-person meeting with vendor J.J. Keller to discuss the recertification process for CTs and the expectations to adjust program based on performance review 4426 Accountability plan approved by Safety Council. Final details and draft communications in progress 4461 Met with FADV and reviewed their Road Test development screens. Need to review again with Legal why FXG previous Road Tests removed the 'worksheet' portion 4627 Assigned to new milestone owner: Lonnie Mattison. Conducted 2nd team meeting reviewing Charter and start brainstorming on idea. Plans to meet with other OpCo's to review their training program. Week ending: 2/24/2023 6082 TVS performed demo of 2nd of 3 screens for team, the Observed Hours page in CDAS 4419 91.7% Agreements with training terms 4448 Collaboration continues with BDS and FADV to develop plan 4474 Final demo of 1 of 3 new CDAS screens. Certified/Qualified Observer conditions page to be installed in CDAS on 2/25/2023 --> Project was reviewed on the TCH Architecture Assessment 4607 40.67% Driver Compliance 4426 Continue to fine-tune the MGBA Notice and communications. One letter for all ISPs with LATE drivers and one letter for all remaining agreements as reminders of requirements 4465 Due to loss of Safer Driver Team member, assigned another member to document the status of each agreement and discover next steps for signed agreements 4461 FedEx Ground will need to bring all stakeholders back together to discuss the requirements for road tests. Compliance and Liability needs. Meetings to be scheduled 4627 Team collected/reviewed training requirement of other transportation business; Reviewing current cost of 'Direct to Driver' from current process; updated timelines based on Accountability (#4426) Week ending: 3/3/23 6082 1st of 3 pages released into production (Trainer/Observer Condition). Reviewed Observed Hours page design and functionality 4419 394 of 5267 ISP remaining to implement Qualification Certifica | I: L4 | Active | TEMP L4 - Enter L4 | 2022-03-01 | 2026-09-01
Business Only Initiative: In Cab Alerts for Service Providers Using VEDR | 63729 | 7949 | Business Only Initiative | FXG S - Technology & Certification | Safety | Aaliyah Armstead, Glen Lyles, Kelly Prohaska, Sean Keaton | On Track | Launch began Oct. 1 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-01-09 | 2025-01-16
Business w/ Tech Initiative: P&D Technology (backing sensors and three camera b | 579 | 7960 | Business w/ Tech Initiative | FXG S - Technology & Certification | Safety | Glen Lyles, Heather Dornan, Kelly Prohaska | On Track | Week ending 1/6/2023 2826 -selection and formal notification is planned to be sent to vendors on 1/27/2023. No further updates to note until those replies are returned. 4295 - rentals timeline has been added to the attachment section. This work is estimated to be completed in May of 2023 and the end date has been updated. A soft stop should be completed as part of PE1 by 1/30/2020 2790 - Communication on the deadline is being routed and should be communicated to the field in January. Field Safety has been updated and will continue to engage stations for compliance. 2831 - Money Step - The process has started for a subset of vehicles that should have been installed prior to June 1, 2022. We will continue this process for all vehicles in the network after April 30th once the incentive program has expired. Week ending 1/13/2023 2790 - Communication has been published informing the field of the incentive deadline. Week ending 1/20/2023 2790 - 91% of network is installation. This is the entire network, not just those that are eligible for the incentive. Week Ending 1/27/2023 2790 - 91.52% of the network is installed. Communication has been routed for approval to inform those SPs that are part of the vehicle standard and are not installed. Those SPs will have 30 days to install or must be required to remove the vehicle from service. Week ending 2/3/2023 2790 - 92.33% complaint. Discussion will be held at the safety council (2/13) to ensure buy in to take vehicles out of service after the 4/30 deadline. 2826 - a meeting is scheduled for 2/15 to discuss the Checkbox platform used by Memphis. This may be an alternative to the 3rd party vendor. Week Ending 2/10/2023 2790 - 92.96% compliant Week ending 2/24/2023 2790 - 94.43% compliant Week ending 3/16/2023 2790 - 95% compliant Week ending 4/7/2023 2790 - 96.55% complaint Week ending 4/28/2023 2790 - 98% compliant Week ending 5/12/2023 2790 - 99% compliant | I: L4 | Active | TEMP L4 - Enter L4 | 2022-01-03 | 2027-10-25
Business Only Initiative: STAR V Motion Blocking Vendor Change | 15472 | 9234 | Business Only Initiative | FXG S - Technology & Certification | Safety | Joe Melichar, Matt Gurneal | On Track |  | K: L5 | Completed | L5 | 2022-11-04 | 2023-11-30
Business w/ Tech Initiative: Employee Driver Optimization |  | 104036 | Business w/ Tech Initiative | FXG S - Technology & Certification | Safety | Rebecca Kelch, Julie Dille, Dawn Eberle, Jay Sinnott, Kelley Taylor, Kor'an Sharif, Fausto Bizzarri, Bruna Kramer | On Track | First Advantage has begun migration work and on track to scope out subsequent phases with data cleansing and CDAS development 2/12/26 - still waiting a portfilo architectural | E: L2 | Active | L2 | 2024-07-22 | 2026-06-30
Business Only Initiative: Stations - Inbound (AM); Improve Inbound Smalls So | 73254 | 7298 | Business Only Initiative | Express Operations - Sortation | Surface Operations | JT Pickard, Dorothy Rizzo | On Track | This initiative has been rolled into the 7413 project which is targeting all IB sort tasks and operations | I: L4 | Cancelled | L4 | 2024-01-19 | 2024-08-02
Business Only Initiative: Station Outbound (PM): Reload Captain Criteria Re | 78447 | 7398 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Arthur Keating | On Track | Changed Primary to Richard Wooten | K: L5 | Completed | L5 | 2024-04-08 | 2024-09-02
Business Only Initiative: Station Outbound (PM): PM Splitter and Diverter Cr | 78450 | 7400 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Arthur Keating | On Track | VALET Steer is reviewing. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-08 | 2024-07-30
Business Only Initiative: Improve Inbound (AM) Sort | 73253 | 7413 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Timothy Orris | On Track | active | I: L4 | Active | TEMP L4 - Enter L4 | 2024-01-19 | 2026-03-31
Business Only Initiative: Stations - Inbound (AM); Increase Finesort Pk/Hr | 73255 | 7558 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Jill Wilson, Richard Wooten | On Track | collapsed into #7413 | I: L4 | Cancelled | L4 | 2024-01-19 | 2024-08-30
Business Only Initiative: Stations - Outbound (PM): Improve Planned PM TLH ( | 74114 | 8092 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Arthur Keating | On Track | On Track | I: L4 | Active | TEMP L4 - Enter L4 | 2024-03-26
Business Only Initiative: Station Outbound (PM): Bypass Volume Verification | 78453 | 8094 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Arthur Keating | On Track | Ensuring the accuracy of the planned parameters should be responsibility of VALETSTEER team. Updating the bypass volume in the plan will change the goal but may or may not change how the location operates. The recommendation is to change the pkg/PM hand hr calculation to use sort volume and not station volume to address the bypass issue. The Common Calculations initiative is in the process of addressing this. Focus of OB TLH improvement initiative is on improving performance against goal and establishing new strategies and ways of operating on Outbound as well as rethinking existing processes. | C: L1 | Cancelled | L1 Data Migration - TEMP | 2024-07-22 | 2024-09-25
Business Only Initiative: Station Outbound (PM): Mixed Document % -Enabler | 78211 | 8793 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Arthur Keating | On Track | VALET Steer needs to approve. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-23 | 2024-09-02
Business Only Initiative: Station Outbound (PM): Transporter Logic Criteria | 78444 | 8795 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Arthur Keating | On Track | VALET Steer needs to approve | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-23 | 2024-09-02
Business Only Initiative: Stations - Remove Guarantee Minimum Hours | 73252 | 8923 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Micah S. Peterson, John Lamia, Ana Whitten | On Track | **6/9/2025**- May spend (actuals) inputted, savings stable. **5/6/2025** April payroll (actuals) inputted, savings stable. **4/7/2025** March payroll (actuals) inputted, submitted to L5. **3/28/2025**- Ready for L5, submit in April after actuals (Mar payroll) reported based on money step completed May 2024. Savings realized over the remainder of FY2025. Financials through FY28 updated by 3/31. **2/13/2025**- January actuals reported in Feb. Process stable, savings realized over the remainder of FY2025. Move to L5 in April. Initiative on-track, COE data obtained and broken down in order to estimate annualized savings. Need to discuss and review with Finance before moving forward. ***1/29/2025*** - Micah Peterson added as IO. Money step completed May 2024. Savings being reported and realized over the remainder of FY2025. | K: L5 | Completed | L5 | 2024-04-01 | 2024-08-30
Business Only Initiative: Stations - HR Overtime Policy Change | 74685 | 8924 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Micah S. Peterson, John Lamia, Ana Whitten | On Track | **5/14/2025** Total hours and OT % increased to above baseline (840k v. 774k) for April 2025 payroll, no cost savings recorded. Financials and KPIs updated. *4/15/2025 Total hours and OT % increased to above baseline (810k v. 754k) for March 2025 payroll, no cost savings recorded. Financials and KPIs updated.* **3/28/2025** Moved to L5 based on the completion of the money step in May 2024 (implementation of IT changes). Initiative has been realizing savings throughout FY25. **2/13/2025**- January actuals reported in Feb. Process stable, savings realized over the remainder of FY2025. Move to L5 in April. ***1/29/2025*** - Micah Peterson added as IO. Money step completed May 2024. Savings being reported and realized over FY2025. | K: L5 | Completed | L5 | 2024-04-01 | 2024-08-30
Business Only Initiative: Stations - Outbound (PM); Reduce PST allocated hou | 74115 | 9270 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Richard Wooten, Art Goulard | On Track | Up to date | K: L5 | Completed | L5 | 2024-04-18 | 2024-10-01
Business Only Initiative: Automated Smalls Sorter (SOLO) for Ramps and Stati | 23520 | 9501 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Fico Arredondo, Leslie Van Horn | On Track | Initiative on hold, as the TCH has said they cannot support my project until Phase 3 of N2.0. Timeframe for N2.0 Phase 3 is CY24-CY27. I am not privy to exact dates as that is P&C information. | E: L2 | On Hold | L2 | 2023-02-01 | 2025-03-07
Business Only Initiative: Standardize temp agency worker pay rates and harmo | 24444 | 9526 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Anne Hemp, Patrick McEntire |  | 9526 is on hold, it should be changed to canceled as it is duplicative. We are capturing savings under another temp labor initiative focused on supplier reduction and rate optimization (8901 - Temp Staffing US RFP). In terms of standardizing the job roles (or job categories) enterprise wide, we will accomplish this via another initiative to implement a Global Vendor Management System (9442: Global Temp Labor VMS).Initiative #24444 “on hold” at the direction of Leslie and Justin. We’ve placed the initiative on hold until post=peak alignment with operations and HR. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2023-06-27 | 2024-11-04
Business Only Initiative: Express Dock (Inbound & Outbound) Certification |  | 87593 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Timothy Orris, Wes Harris | On Track | 11/21 - On Track | C: L1 | Active | L1 Feedback Requested
Business w/ Tech Initiative: Inbound Saturday Sort Stat41 Reduction |  | 87598 | Business w/ Tech Initiative | Express Operations - Sortation | Surface Operations | Kassandra M. Harden | On Track | Opportunity has been quantified and gone through triage review - 11/21 | C: L1 | Active | TEMP L1 - Create L1 LBC
Business w/ Tech Initiative: MOBIUS - SURFCO - Waves 1 - 8 Implementation |  | 104743 | Business w/ Tech Initiative | Express Operations - Sortation | Surface Operations | Kevin Lofgren | On Track | QA was complete by Kassandra Harden on 5/5/2025 prior to submission for EPM Review SL3 QA was complete by Kassandra Harden on 10/29/2025 | G: L3 | Active | TEMP L3 - Enter L3 | 2025-01-01 | 2027-12-17
Business Only Initiative: Business Only Initiative: Origin LMO Reduction | 96562 | 7580 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Mauricio Tobar, Mitchell McGee, Jeff Ledoux | On Track | Initiative is on track. Changes were executed during the week of October 14th. | K: L5 | Completed | L5 | 2024-09-09 | 2024-11-05
Business Only Initiative: EMR 15K Facility Design Footprint Reduction |  | 161187 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Jared Cirelli | On Track | **Initial estiamtes of savings will be provided when Real Estate and cost data is available for Perris, CA. Gary, IN was initially used but did not offer a fair and direct comparison of the reduction inititiave. For this initiative, stations with 15K thruput and 6 vanlines need to be compared. Gary was 15K thruput but only 4 vanlines.** Cost avoidance will be tracked when the Certificate of Occupancy date for Perris, CA begins in CY 28. It was recommended to remove/cancel this initiative from Planview and DRIVE. Cost avoidance and not DRIVE savings. Numbers will be tracked outside of Planview. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Hytrol Shoe Sorter 3D Printing |  | 164947 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Kevin Lofgren | On Track | 10/2/25 - L1 business case entered 11/24/25 - Cancelled as requested via PDSM ticket #INC033183097. | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Admin / Misc Productivity | 76757 | 6730 | Business Only Initiative | Express Operations - Sortation | Surface Operations | Kailash S. Maraj, Arthur Keating | On Track | Entered KPI and Revenue information into the Financials tab on 04/10/2026. The ETF has moved from the Assess to the Build phase on 04/06/2026. Some locations missed entering data for their daily Admin/Misc Hours and reason for missing plan. Locations notified to update the information. April's workbook added to TEAMS and all focus locations notified and updated on 04/02/26. ETF updated to In Progress on 03/09/26. As of today 03/04/26, all 5 focus locations have been notified and updated with a link to TEAMS for their updates on Admin-Misc Hours. Email sent to four focus locaitons, LKSA/MWLA/WASA/PNVA on 03/02/26 and 03/03/23 with TEAMS link for Admin/Misc hours and variance to update if missed BUD plan. Communication was sent on 02/25/26 to the focus locations. Locations will report weekly on their progress via the TEAMS site. A standardized form will be provided to record results for measurement and processes utilized for improvements. Vehicle Repositioning enabling initiative was delayed 1 month and is pushing back the money step milestone for the initiative. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-05-03 | 2026-08-24
Business w/ Tech Initiative: Missing Customer Facing Scans Express Packages |  | 188370 | Business w/ Tech Initiative | Express Operations - Sortation | Surface Operations | Eric Rowland | On Track | On Track | C: L1 | Active | L1
Business Only Initiative: SDR SO Offering Cost Savings | 74117 | 7149 | Business Only Initiative | Express Operations - Courier | Surface Operations | Kathleen C. Pruss, Timothy Orris, Nisha Sivan | On Track | SDR SO went live on 3/8/25 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-26 | 2024-08-30
Business w/ Tech Initiative: Remove Commercial Signature - Express | 89006 | 7390 | Business w/ Tech Initiative | Express Operations - Courier | Surface Operations | Chris Helkowski, Jennifer Stringfellow, Erin Wichtoski | On Track | It has been determined that this initiative is dependent on the successful launch and implementation of a number of other DRIVE initiatives. | E: L2 | On Hold | L2 & CCH | 2024-08-22 | 2024-08-29
Business Only Initiative: Stations- P&D, Analyze and Implement FRO | 74120 | 7419 | Business Only Initiative | Express Operations - Courier | Surface Operations | Randy Kelley, M. Reza Ziai | On Track | Rollout ends 3/31/25 | I: L4 | Active | TEMP L4 - Enter L4 | 2024-04-01 | 2026-06-01
Business Only Initiative: Ensure accurate break compliance | 74095 | 7576 | Business Only Initiative | Express Operations - Courier | Surface Operations | Spain Powell, Jeff Ledoux, Austin Clark | On Track | Break Reporting dashboard was launched and communicated to the field on calls held in June and early July; adoption and effectiveness in June actuals are not represented in the data and reporting at the monthly level. | I: L4 | Active | TEMP L4 - Enter L4 | 2024-03-20
Business Only Initiative: Courier Staffing Optimization using Courier Hiring | 77427 | 7591 | Business Only Initiative | Express Operations - Courier | Surface Operations | Jeff Ledoux, Richard Wooten | On Track | adoption and engagement is active and ongoing | I: L4 | Active | TEMP L4 - Enter L4 | 2022-01-03 | 2024-07-31
Business Only Initiative: Stop Per Hour Execution Excellence for Employee Co | 87653 | 7735 | Business Only Initiative | Express Operations - Courier | Surface Operations | Jeff Ledoux, Richard Wooten | On Track | Was approved for L2 prior to Planview migration; updating and resubmitting to L2 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-08-21 | 2025-04-23
Business w/ Tech Initiative: Product Commit Modeling | 1120 | 7787 | Business w/ Tech Initiative | Express Operations - Courier | Surface Operations | Kelly Morefield, Sandeep Dhaliwal, Scott Campbell, Scott E. Moulden | On Track | We are in the assess phase and building a consensus of needed inputs and outputs. Fourth base case is complete verification is underway to examine input and outputs from the base case to build a delta for future modeling. We are currently at the Tech Clearing House requesting additional resources to allow the project to move forward. | I: L4 | Active | TEMP L4 - Enter L4 | 2022-12-06 | 2024-07-22
Business Only Initiative: Increase Handler Usage Onroad | 74097 | 7869 | Business Only Initiative | Express Operations - Courier | Surface Operations | Spain Powell, Jeff Ledoux | On Track | Moving L4 date to 7/1/25 | G: L3 | Active | TEMP L3 - Enter L3 | 2024-03-25 | 2026-07-01
Business Only Initiative: Drop Box Time Changes | 326 | 8797 | Business Only Initiative | Express Operations - Courier | Surface Operations | Mark Enfield, Jenny Vogelsang 1 | On Track | Overview: Lower costs by adjusting Drop Box Pickup Times without losing competitive positioning aimed at reducing On Road hours and miles while improving freight availability. Approved at L4 YTD (FY24) Impact vs Bankable Plan: Over-Delivering by 8% or $280K due to: - Initiative is ahead of plan, changing more Drop Box times than originally forecasted, currently (through August) 15.8K Drop Box changes vs. 13K total forecasted changes. - Drop Box time changes have been accelerated (earlier than planned) in certain markets due to the DRIVE - Streamline the PM initiative. August Impact vs. Bankable Plan: Over-Delivering by 5% or $56K due to: - Continued benefit of updating more Drop Boxes than forecasted/planned | K: L5 | Completed | L5 | 2022-11-08 | 2023-07-14
Business Only Initiative: Delivering Future Day Volume (Stat 41s) Tuesday - | 1114 | 8807 | Business Only Initiative | Express Operations - Courier | Surface Operations | Jason Straub, Robert Nowlen | On Track | Exceeded planned impact by 23.37% for May. This is due to field over-performance versus expectation in reducing STAT41s Tuesday - Friday. | K: L5 | Completed | L5 | 2022-11-07 | 2023-03-31
Business w/ Tech Initiative: Bulk Pickup Streamlining | 1106 | 8819 | Business w/ Tech Initiative | Express Operations - Courier | Surface Operations | David Hankins, Nisha Sivan | Some Issues | Solution has started POC (October 22, 2024) with one customer account. Initial results were very favorable, with the majority of customer packages process as intended and limited service impacts. However, opportunities were identified with specific features of the code on subsequent POC testing has produced a list of minor changes that must be made before broader rollout can be successful. Demand Request entered for Commercial & Surface portfolios to deliver two features, one pre-peak (customer visibility) and second post-peak (internal SME visibility). The post-peak work is being bundled with a 1FDX initiative whose roadmap and initiative approval is unclear and the available time for Jan26 appears unattainable. | G: L3 | Active | TEMP L3 - Enter L3 | 2022-10-25 | 2026-07-31
Business Only Initiative: Drop Box - Rationalize PM Retail Drop Off Network | 1600 | 8830 | Business Only Initiative | Express Operations - Courier | Surface Operations | Mark Enfield, Jenny Vogelsang 1 | On Track | Retail Marketing working with CIA to map distance between, pickups times and ADV of Retail outlets. Placeholder of 5K Drop Boxes with low volume and close proximity to other Retail drop off outlet. Eliminating 5K drop boxes would save $18M in planned capital spend. Overview: Lower costs by reducing redundant drop off channels (Drop Boxes) while maintaining appropriate customer access as we right-size the Retail Network considering existing points of injection. After pausing Drop Box removals (Feb and March) as we assess customer impact in LAX and DTW markets, NO substantial customer complaints received. YTD (FY24) Impact vs Bankable Plan: Initiative is Over-Delivering by 115% or $635K. August Impact vs Bankable Plan: Initiative is Over-Delivering by 136% or $195K. Initiative is ahead of Bankable plan due to lower than forecasted Drop Box removal costs continuing through July~$354 per box when $700 was planned for business case. Current removal costs do not include "beyond-point" or extended area removals which will be realized later this calendar year. | K: L5 | Completed | L5 | 2022-11-01 | 2024-01-31
Business Only Initiative: Automated Regular Mass Enrollment | 1111 | 8841 | Business Only Initiative | Express Operations - Courier | Surface Operations | Mark Enfield, Jenny Vogelsang 1 | On Track | Leverage existing technology to mass enroll eligible Regular customers in Automated Regular Pickup Service. Focusing on 16K Regular Customers, eligible for Automated Regular Pickup Service that currently ship between 50-85% of days scheduled. Team has identified Regular Customers and AUT eligibility. Overview: Lower costs by leveraging existing Pickup technology that will reduce Nonproductive Regular stops while improving On Road efficiencies in the afternoon time cycles. Through October 19.3K customers enrolled up 11K from Sept. ‘22 baseline. YTD (FY24) Impact vs Bankable Plan: Over-Performing by 12% YTD or $152K variance to Bankable Plan (pending Finance approval) October Impact vs Bankable Plan: Over-Performing by 61% or $134K variance to Bankable Plan (pending Finance approval) Special Note - Effective 11/1 submitting to L5, L5 delayed as the Initiative has not hit/exceeded the forecast savings for 3 months. | K: L5 | Completed | L5 | 2022-11-07 | 2023-05-31
Business Only Initiative: Domestic One Wave 2023 | 339 | 8874 | Business Only Initiative | Express Operations - Courier | Surface Operations | Tom Maxwell, Neil Connolly | On Track | This initiative is progressing as planned. Milestones are complete, and initiative now shows being at L4. All impacts and KPI's have been updated through November. | K: L5 | Completed | L5 | 2022-11-01 | 2023-05-31
Business Only Initiative: Later AM Sort start on Monday | 74092 | 8885 | Business Only Initiative | Express Operations - Courier | Surface Operations | Zachary James, Spain Powell | On Track | 02/26 - Need one more month of actuals before submitting to L5. 04/2026 - Moved to L5. | K: L5 | Active | L5 | 2024-04-01 | 2024-09-30
Business Only Initiative: US Ops Retail Fuel Best Price | 340 | 8897 | Business Only Initiative | Express Operations - Courier | Surface Operations | Heath Ferry, Dan Doherty | On Track | Requesting L5 approval and for canceling this initiative due to lapping ourselves YoY and over lapping initiatives for fuel rebates along with sourcing fuel POD. | K: L5 | Completed | L5 | 2022-10-25 | 2023-02-17
Business w/ Tech Initiative: Settlement - Canada Amalgamation |  | 85902 | Business w/ Tech Initiative | Express Operations - Courier | Surface Operations | Michele A. Goetz | On Track | Green - The deadline for Canada Amalgamation is Dec 2026 per Legal. It was suggested that this is put on hold. | C: L1 | Active | L1 Feedback Requested
Business Only Initiative: Bulk PU Productivity - lowest performers |  | 87406 | Business Only Initiative | Express Operations - Courier | Surface Operations | Timothy Orris, Spain Powell | On Track | Completed LBC and looking to move to L2 10/16/25 - SL3 QA Review with Zach James | G: L3 | Active | TEMP L3 - Enter L3 | 2024-07-23 | 2026-05-29
Business Only Initiative: Couriers leveraging FXG fuel islands |  | 90687 | Business Only Initiative | Express Operations - Courier | Surface Operations | Jeff Ledoux | On Track | Conflict with other similar DRIVE initiatives under Sourcing | C: L1 | Cancelled | L1 Feedback Requested
Business Only Initiative: Redistribution of Excessive Courier OT |  | 104457 | Business Only Initiative | Express Operations - Courier | Surface Operations | Mark Centofanti, David Henderson | On Track | QA was complete by Kassandra Harden prior to submission for EPM Review. | I: L4 | Active | L5 | 2025-06-02 | 2026-04-24
Business Only Initiative: GPS Trailer Tracking: Carrier Optimization |  | 94375 | Business Only Initiative | Express Operations - Courier | Surface Operations | Brad Bannon, Joe Melichar | On Track | Implementation currently underway | K: L5 | Active | L5 Feedback Requested | 2024-08-01
Business Only Initiative: Improving Stops Per Courier to reduce routes |  | 171195 | Business Only Initiative | Express Operations - Courier | Surface Operations | Jeff Ledoux | On Track | This initiative will move to an enabler and KPI under newly submitted Courier Stop Per Hour initiative | C: L1 | Cancelled | TEMP L1 - Create L1 LBC
Business Only Initiative: Business Only Initiative: Stations - Admin/Misc; F | 74107 | 6731 | Business Only Initiative | Express Operations - Admin | Surface Operations | Richard Wooten, Michael Lewis, Chris Rooney | On Track | Due to N2.0 and need for extra resources for the new structure, this initiative should be cancelled. | G: L3 | Cancelled | L3 Data Migration - TEMP | 2024-03-15 | 2025-11-11
Business Only Initiative: Stations - Admin/Misc; Update Environmental hours | 73250 | 7174 | Business Only Initiative | Express Operations - Admin | Surface Operations | Debbie McLeod, Ronaldo Caparaz | On Track | To submit to L5 | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-19 | 2024-07-31
Business Only Initiative: Stations - Admin/Misc; Reduce Group Meeting Hours | 74110 | 7612 | Business Only Initiative | Express Operations - Admin | Surface Operations | Philippe Solet, Chris Hutson | On Track | Chris Hutson is no longer with the company. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-16 | 2024-05-31
Business Only Initiative: Business Only Initiative: Stations - Admin/Misc; O | 74108 | 7983 | Business Only Initiative | Express Operations - Admin | Surface Operations | Martin Marshall, Stephen McCarthy | On Track |  | K: L5 | Completed | L5 - Restarted Initiative | 2024-04-19 | 2024-05-31
Business Only Initiative: Business Only Initiative: Meetings / Travel / Ente | 74828 | 8270 | Business Only Initiative | Express Operations - Admin | Surface Operations | Jason Straub | On Track | This initiative #8270 Meetings/Travel/Entertainment Spend Rationalization was recently discussed with the Domain Managing Director, and we collectively agreed it’s not something we plan to move forward with. Based on that discussion, we’d like to formally cancel it in Planview. It appears you're listed as the primary Initiative Owner, so only you have the ability to cancel in the system. Would you be able to help with canceling it in Planview? Here is a job aid in case it's helpful. Setting Initiatives to On Hold-Cancel Please let me know if you have any questions and thank you in advance for your time! | E: L2 | Cancelled | L2
Business Only Initiative: Admin/Misc Rate Review - Queue/Case Research | 74294 | 8279 | Business Only Initiative | Express Operations - Admin | Surface Operations | Kailash S. Maraj, Arthur Keating | On Track | L4 pushed 1 week because of FAMIS re-alignment which delayed the BUD Plan snapshot for PAC West. 7/5/24 - L4 pushed 1 week again because of FAMIS re-alignment which continues to delay the BUD Plan snapshot for West Division. 7/5/24 - Change Management date pushed back as well. TheSource communication representative said that they should be able to publish the work rate change between 7/8 and 7/12/24. 7/17/24 - We have been trying to publish notice of the updated case research work rates in TheSource. I have worked through Richard Wooten and Kelly Lovato. We have been sending drafts of the information for publication and it is just taking longer than anticipated. This is the first time I've used this form of communication and so I will know that a longer lead time in the future will be required. | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-24 | 2024-07-31
Business Only Initiative: Business Only Initiative: Stations – Other Outside | 74826 | 8296 | Business Only Initiative | Express Operations - Admin | Surface Operations | Dan Doherty | On Track |  | E: L2 | Cancelled | L2
Business w/ Tech Initiative: Business w/ Tech Initiative: Lexis Nexis | 330 | 8786 | Business w/ Tech Initiative | Express Operations - Admin | Surface Operations | Carol Woodard, Jenny Vogelsang 1 | On Track | Received and entered May invoice -Submitted and approved at L4. LexisNexis enables a functionality at the front counter for address input. The functionality is scheduled to be terminated June 2023. Agents will manually enter the street name once this functionality is removed. $1.6M annual savings. | K: L5 | Completed | L5 | 2022-10-11 | 2023-07-07
Business Only Initiative: Stations - Admin/Misc; Optimize Vehicle Reposition | 74704 | 9091 | Business Only Initiative | Express Operations - Admin | Surface Operations | Spain Powell, Anisa Young | On Track | Initiative well documented. Annualized Impacts have been validated. Working through milestones and diving deeper into each piece of the initiative in order to identify forecasted dates and thus monthly savings. Budget A-Team meeting completed. VALET Steer call completed on Tuesday 4/23. GMSE discussion completed on 4/29. BP team review completed on 6/3. VALET enhancement request created on 5/6. Communication plan developed for Phase 1. Needs to be developed for Phase 2 and 3. Should highlight what change is occurring, the expectations with the change, and impact to engineering + express legacy station ops. VALET MTP + next budgeted month = money step. Phase 1 launched. Phase 2 launching in June for July planning. | K: L5 | Completed | L5 - Restarted Initiative | 2024-03-15 | 2024-11-29
Business Only Initiative: Stations - Admin/Misc; Remove Obsolete Task | 73246 | 9277 | Business Only Initiative | Express Operations - Admin | Surface Operations | Debbie McLeod, Arthur Keating | On Track | Name update | K: L5 | Active | TEMP L5 - Enter L5 | 2024-04-19 | 2024-06-28